## G1 - Investment
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2021
SECTION G: INVESTMENT MONITORING
Table G1: Summary - Investment
|  |  |  | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90
Line Ref | Description | Units | Field Type | Report Year Pre 2015 | Actual Report Year 2015-16 | Actual Report Year 2016-17 | Actual Report Year 2017-18 | Actual Report Year 2018-19 | Actual Report Year 2019-20 | Actual Report Year 2020-21 | Forecast Post 2021 | Forecast Total Financed in SR15-21
Capital Maintenance
G1.01 | Water Service Infrastructure | £m | I | 0 | 84.2454 | 116.0252 | 146.5405 | 95.5402 | 74.4717 | 75.475 | 97.5291 | 689.8271
G1.02 | Water Service Non-Infrastructure | £m | I | 0 | 71.4392 | 73.7395 | 76.4921 | 99.3587 | 95.7881 | 118.9687 | 0 | 535.7863
G1.03 | Wastewater Service Infrastructure | £m | I | 0 | 27.2715 | 37.469 | 37.6199 | 68.0166 | 50.8597 | 35.0635 | 0 | 256.3001
G1.04 | Wastewater Service Non-Infrastructure | £m | I | 0 | 49.72 | 58.9505 | 72.8746 | 67.3166 | 86.2356 | 67.0676 | 0 | 402.1649
G1.05 | Management and General | £m | I | 0 | 27.3818 | 52.4878 | 61.3964 | 53.2956 | 41.0293 | 45.6724 | 0 | 281.2632
G1.06 | Total Capital Maintenance | £m | C | 0 | 260.0579 | 338.672 | 394.9235 | 383.5276 | 348.3843 | 342.2472 | 97.5291 | 2165.3416
Growth
G1.07 | Growth in the Water Network | £m | I | 0 | 3.4002 | 7.1177 | 7.8441 | 9.1804 | 13.2788 | 14.8453 | 0 | 55.6664
G1.08 | Growth in the Wastewater Network | £m | I | 0 | 9.8958 | 10.2296 | 15.3006 | 36.4738 | 40.4087 | 40.6893 | 0 | 152.9978
G1.09 | Water Reasonable Cost Contributions | £m | I | 0 | 8.1987 | 7.2182 | 6.7422 | 10.4484 | 6.3965 | 10.2543 | 0 | 49.2583
G1.10 | Wastewater Reasonable Cost Contributions | £m | I | 0 | 8.6536 | 10.4298 | 9.8565 | 18.229 | 9.9867 | 13.055 | 0 | 70.2106
G1.11 | Service Relocations Water | £m | I | 0 | 15.0386 | 12.4052 | 9.3687 | 7.7985 | 6.1906 | 3.4885 | 0 | 54.2901
G1.12 | Service Relocations Wastewater | £m | I | 0 | 4.8054 | 4.9606 | 3.4735 | 1.8201 | 2.4883 | 1.0228 | 0 | 18.5708
G1.13 | Total Growth Expenditure | £m | C | 0 | 49.9923 | 52.3611 | 52.5857 | 83.9502 | 78.7497 | 83.3552 | 0 | 400.9941
Q&SIV Enhancement Expenditure
G1.14 | Improving drinking water quality compliance and reliability | £m | I | 9.2909 | 18.0605 | 46.4014 | 56.5863 | 66.1679 | 85.5889 | 61.6972 | 130.0308 | 473.8238
G1.15 | Improving drinking water availability and resilience of service | £m | I | 3.3164 | 10.9888 | 14.5593 | 17.997 | 30.8453 | 26.1705 | 10.7858 | 17.2887 | 131.9519
G1.16 | Protecting and enhancing the environment | £m | I | 8.9269 | 14.9754 | 24.8366 | 41.1725 | 31.2002 | 36.3358 | 36.4659 | 47.4465 | 241.3597
G1.17 | Reducing flooding and pollution from sewers | £m | I | 21.1556 | 24.1093 | 15.6515 | 15.2362 | 16.0317 | 28.6606 | 26.8997 | 45.555 | 193.2996
G1.18 | Improving the customer experience | £m | I | 0.9286 | 1.8248 | 6.1398 | 5.2653 | 4.9185 | 9.3087 | 9.8056 | 3.7709 | 41.9621
G1.19 | Climate Change | £m | I | 0.23491 | 0.15567 | 0.41575 | 0.34953 | 0.039188 | 0.31892 | 0.062397 | 0.0208 | 1.5972
G1.20 | Reducing long term cost of service | £m | I | 2.9412 | 4.7829 | 4.445 | 2.9189 | 1.6093 | 1.5669 | 1.8209 | 3.2065 | 23.2915
G1.21 | Total Q&SIV Enhancement Expenditure | £m | C | 46.7946 | 74.8973 | 112.4493 | 139.5257 | 150.8121 | 187.9503 | 147.5374 | 247.3191 | 1107.2857
Q&SIV Enhancement - IR18
G1.22 | Total remaining IR18 Unallocated Investment | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Q&SIIIa & Q&SIIIb Completion Expenditure
G1.23 | Total OMG180 Completion Expenditure | £m | I | 0 | 72.5889 | 96.2252 | 34.7904 | 29.6706 | 25.899 | 13.8297 | 30.0146 | 303.0183
G1.24 | Total Non OMG180 Completion Expenditure | £m | I | 0 | 4.1527 | 26.9688 | 24.4691 | 11.5241 | 5.4523 | -0.24068 | 0.041218 | 72.3675
G1.25 | Total Completion Expenditure | £m | C | 0 | 76.7416 | 123.194 | 59.2595 | 41.1947 | 31.3512 | 13.5891 | 30.0558 | 375.3859
Q&SV Early Start
G1.26 | Total Q&SV Early Start Enhancement Expenditure | £m | I | 0 | 0.025045 | 0.034179 | 0.36752 | 0.44851 | 18.1615 | 24.8987 | 0 | 43.9355
Total Additional Operating Expenditure
G1.27 | Additional Operating Expenditure from Capital Maintenance | £m | I | 0 | 0.97566 | 0.75877 | 0.41055 | 0.43433 | 0.7358 | 0.22439 | 0 | 3.5395
G1.28 | Additional Operating Expenditure from Water Growth | £m | I | 0 | 0 | 0.025756 | 0.0040854 | 0.0025373 | 0.050724 | 0 | 0 | 0.083102
G1.29 | Additional Operating Expenditure from Wastewater Growth | £m | I | 0 | 0 | 0 | 0 | 0 | 0.017705 | 0.050907 | 0 | 0.068612
G1.30 | Additional Operating Expenditure from Improving drinking water quality compliance and reliability | £m | I | 0 | 0 | 0 | 0.008662 | 0.07916 | 0.38221 | 0.098269 | 0.28741 | 0.85571
G1.31 | Additional Operating Expenditure from Improving drinking water availability and resilience of service | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0.018005 | 0.015239 | 0.033244
G1.32 | Additional Operating Expenditure from Protecting and enhancing the environment | £m | I | 0 | 0 | 0 | 0 | 0.207 | 0.50596 | 0.19624 | 0.22684 | 1.136
G1.33 | Additional Operating Expenditure from Reducing flooding and pollution from sewers | £m | I | 0 | 0.0054 | 0 | 0 | 0 | 0 | 0 | 0.2115 | 0.2169
G1.34 | Additional Operating Expenditure from Improving the customer experience | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42161 | 0.42161
G1.35 | Additional Operating Expenditure from Climate Change | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.36 | Additional Operating Expenditure from Reducing long term cost of service | £m | I | 0 | 0 | 0 | 0.11 | 0 | 0 | 0 | -1 | -0.89
G1.37 | Additional Operating Expenditure from IR18 | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.38 | Additional Operating Expenditure from Completion | £m | I | 0 | 0.20123 | 0.63448 | 0.23556 | 0.25855 | 0.20122 | 0.070354 | 0.30856 | 1.9099
G1.39 | Additional Operating Expenditure from Q&SV Early Start | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.40 | Total Additional Operating Expenditure | £m | C | 0 | 1.1823 | 1.419 | 0.76886 | 0.98157 | 1.8936 | 0.65817 | 0.47116 | 7.3747
Grants and Capital Contributions
G1.41 | Grants for infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.42 | Grants for non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.43 | Contributions to infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | -3.2872 | 0 | -3.2872
G1.44 | Contributions to non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.45 | Contributions to service relocations - Water | £m | I | 0 | -10.7902 | -6.5168 | -7.3147 | -4.6331 | -5.9057 | -2.1839 | 0 | -37.3445
G1.46 | Contributions to service relocations - Wastewater | £m | I | 0 | -5.5586 | -3.3571 | -3.7682 | -1.7827 | -3.0027 | -2.5883 | 0 | -20.0576
G1.47 | “Infrastructure charge" contributions for infrastructure assets | £m | I | 0 | -1.7095 | -14.871 | -7.0921 | -20.084 | -27.38 | -18.6866 | 0 | -89.8232
G1.48 | Total Capital Contributions | £m | C | 0 | -18.0583 | -24.745 | -18.1751 | -26.4998 | -36.2883 | -26.746 | 0 | -150.5125
Expenditure Totals
G1.49 | Capital Maintenance Expenditure | £m | C | 0 | 260.0579 | 338.672 | 394.9235 | 383.5276 | 348.3843 | 342.2472 | 97.5291 | 2165.3416
G1.50 | Growth Expenditure | £m | C | 0 | 49.9923 | 52.3611 | 52.5857 | 83.9502 | 78.7497 | 83.3552 | 0 | 400.9941
G1.51 | Q&SIV Enhancement Expenditure | £m | C | 46.7946 | 74.8973 | 112.4493 | 139.5257 | 150.8121 | 187.9503 | 147.5374 | 247.3191 | 1107.2857
G1.52 | Q&SIIIa & Q&SIIIb Completion Expenditure | £m | C | 0 | 76.7416 | 123.194 | 59.2595 | 41.1947 | 31.3512 | 13.5891 | 30.0558 | 375.3859
G1.53 | Q&SV Early Start Expenditure | £m | C | 0 | 0.025045 | 0.034179 | 0.36752 | 0.44851 | 18.1615 | 24.8987 | 0 | 43.9355
G1.54 | Gross Capital Investment | £m | C | 46.7946 | 461.7141 | 626.7105 | 646.6619 | 659.9331 | 664.5971 | 611.6275 | 374.9041 | 4092.9428
G1.55 | Total Capital Contributions | £m | C | 0 | -18.0583 | -24.745 | -18.1751 | -26.4998 | -36.2883 | -26.746 | 0 | -150.5125
G1.56 | Net Capital Investment | £m | C | 46.7946 | 443.6558 | 601.9656 | 628.4868 | 633.4333 | 628.3087 | 584.8815 | 374.9041 | 3942.4303
G1.57 | Total Additional Operating Expenditure | £m | C | 0 | 1.1823 | 1.419 | 0.76886 | 0.98157 | 1.8936 | 0.65817 | 0.47116 | 7.3747
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by:

## G2 - Q&SIV Outputs
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2021
SECTION G: INVESTMENT MONITORING
Table G2: Summary - Outputs
|  |  |  | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90
Line Ref | Description | Units | Field Type | Report Year Pre 2016 | Actual Report Year 2015-16 | Actual Report Year 2016-17 | Actual Report Year 2017-18 | Actual Report Year 2018-19 | Actual Report Year 2019-20 | Actual Report Year 2020-21 | Forecast Post 2021 | Forecast Total Financed in SR15-21
Growth
G2.1 | Strategic Capacity - Water Treatment [WG1] | Pe | I | 0 | 0 | 14677 | 0 | 0 | 0 | 388 | 0 | 15065
G2.2 | Strategic Capacity - Wastewater Treatment [SG1] | Pe | I | 0 | 1351 | 792 | 3188 | 671 | 6651 | 21268 | 0 | 33921
G2.3 | Strategic Water Network Capacity (Infrastructure Charge) [WG5 ] | Pe | I | 0 | 1920 | 12758 | 10705 | 2058 | 0 | 1934 | 0 | 29375
G2.4 | Strategic Wastewater Network Capacity (Infrastructure Charge) [SG5 ] | Pe | I | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
Q&SIV Enhancements - Drinking Water Quality
G2.5 | Number of water treatment works improved | No. | I | 0 | 0 | 1 | 3 | 6 | 4 | 1 | 17 | 15
G2.6 | Number of zones made compliant with iron & manganese standards | No. | I | 0 | 0 | 0 | 4 | 34 | 19 | 4 | 21 | 61
G2.7 | Number of enhancements to improve reliability of supply (catchments and treatment) | No. | I | 0 | 2 | 1 | 5 | 4 | 6 | 10 | 26 | 28
G2.8 | Number of enhancements to improve reliability of supply (networks and storage) | No. | I | 0 | 1 | 10 | 2 | 9 | 28 | 16 | 21 | 66
G2.9 | Distribution mains cleaned (km) | Km | I | 0 | 0 | 0 | 108.37 | 451.01 | 1575.17 | 1729.548 | 2694.038 | 3864.098
G2.10 | Water supply resilience strategy and improvements made | No. | I | 0 | 4 | 3 | 1 | 4 | 2 | 1 | 3 | 15
G2.11 | Number of zones with improved security of supply (SOSI) | No. | I | 0 | 1 | 0 | 0 | 3 | 2 | 0 | 4 | 6
G2.12 | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | I | 0 | 3 | 74 | 195 | 188 | 101 | 125 | 1 | 686
G2.13 | Number of water quality etc studies to inform future periods | No. | I | 0 | 12 | 74 | 134 | 43 | 24 | 70 | 3 | 357
G2.14 | 2010-15 outputs planned to complete in the 2015-21 period | No. | I | 0 | 2 | 4 | 2 | 5 | 4 | 1 | 4 | 18
Q&SIV Enhancements - Environment
G2.15 | Number of WWTWs improved to meet UWWTD | No. | I | 1 | 5 | 1 | 8 | 6 | 2 | 0 | 3 | 23
G2.16 | Number of waste water networks improved to meet UWWTD | No. | I | 0 | 4 | 13 | 5 | 7 | 9 | 6 | 14 | 44
G2.17 | Number of improvements required to meet UWWTD - Glasgow completion | No. | I | 0 | 24 | 12 | 15 | 10 | 8 | 2 | 14 | 71
G2.18 | Number of improvements required to meet the Water Framework Directive | No. | I | 0 | 1 | 0 | 0 | 1 | 1 | 2 | 26 | 5
G2.19 | Number of revised Bathing Waters Directive studies | No. | I | 0 | 0 | 0 | 8 | 0 | 2 | 1 | 3 | 11
G2.20 | Number of studies and catchments to meet the requirements of the Flood Risk Management Act | No. | I | 0 | 0 | 13 | 52 | 75 | 62 | 16 | 0 | 218
G2.21 | Number of environmental studies to inform future periods | No. | I | 0 | 0 | 5 | 28 | 33 | 46 | 16 | 2 | 128
G2.22 | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | I | 0 | 10 | 9 | 8 | 4 | 7 | 16 | 43 | 54
G2.23 | 2010-15 outputs planned to complete in the 2015-21 period | No. | I | 0 | 7 | 1 | 4 | 1 | 1 | 0 | 1 | 14
G2.24 | Number of improvements to dams to meet the requirements of the Flood Risk Management Act | No. | I | 0 | 6 | 4 | 7 | 19 | 9 | 9 | 0 | 54
Q&SIV Enhancements - Supporting Economic Development
G2.25 | Number of climate change vulnerability assessments | No. | I | 0 | 4 | 50 | 3 | 2 | 51 | 13 | 0 | 123
G2.26 | Improvements in renewable power and energy efficiency | Gwh | I | 0.52 | 0.423 | 7.051 | 2.6592 | 6.918 | 0 | 0 | 0 | 17.5712
Q&SIV Enhancements - Output Monitoring Group - Annual Measures
G2.27 | Number of lead communication pipes replaced | No. | I | 0 | 1343 | 1350 | 1169 | 1551 | 1458 | 1131 | 0 | 8002
G2.28 | Assessment of levels of pressure for all customers and number of improvements if low levels of service are found | No. | I | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
G2.29 | Improve response times to reduce average duration of short term interruptions to supply | No. | I | 0 | TBC | TBC | TBC | TBC | TBC | TBC | TBC | 0
G2.30 | Number of water efficiency advice and water saving packs provided (to 2% of customer base) | No. | I | 0 | 0 | 233 | 6684 | 18362 | 18295 | 13252 | 0 | 56826
G2.31 | Number of internal flooding improvements | No. | I | 0 | 47 | 39 | 54 | 101 | 62 | 34 | 0 | 337
G2.32 | Number of internal flooding improvements - completion programme | No. | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.33 | Number of external flooding investigations and improvements | No. | I | 0 | 29 | 22 | 49 | 45 | 28 | 361 | 0 | 534
G2.34 | % of customers covered by flood resilience assessments | No. | I | 0 | n/a | 66.4% | 66.4% | 66.4% | 78.55% | 89.21% | TBC | 89.21%
G2.35 | Number of surface water management investigations | No. | I | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
G2.36 | Number of connections for new households and businesses | No. | I | 0 | 19803 | 22844 | 23914 | 24459 | 25213 | 23943 | 0 | 140176
G2.37 | New water & waste water capacity for 73,290 people | No. | I | 0 | 1351 | 15469 | 3188 | 671 | 6651 | 21656 | 0 | 48986
G2.38 | Number of developer constructed assets (Part 2&3) adopted | No. | I | 0 | 25 | 416 | 838 | 834 | 1443 | 1412 | 0 | 4968
G2.39 | Number of first time non domestic meters installed | No. | I | 0 | 4069 | 3313 | 2586 | 2825 | 2405 | 1246 | 0 | 16444
G2.40 | Number of statutory requirements to relocate services for transport infrastructure projects | No. | I | 0 | 77 | 59 | 60 | 40 | 14 | 14 | 0 | 264
G2.41 | Improved contact management and proactive communication | No. | I | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
G2.42 | Number of wholesale meter accuracy improvements | No. | I | 0 | 7729 | 10441 | 13868 | 15562 | 17737 | 10198 | 0 | 75535
G2.43 | Number of Strategic Mains Diversions | No. | I | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 1 | 4
Q&SIIIa & Q&SIIIb Delivery projects
G2.44 | Q&SIIIa projects remaining | No. | I | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
G2.45 | Q&SIIIb projects remaining | No. | I | 36 | 14 | 8 | 3 | 2 | 1 | 1 | 0
G2.46 | Q&S3b Km of Mains Rehabilitated remaining | Km | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by:

## G3 -Serviceability
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2021 | [18 empty] | Remove hidden columns?
SECTION G: INVESTMENT MONITORING
Table G3: Monitoring Serviceability
|  |  |  | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 110 | 120 | 130 | 140 | 150 |  | 160 | 170
Line Ref | Description | Units | Field Type | Ministerial Target 2015-21 | Baseline Delivery Plan Target Mar 2015 | Actual March 2015 | Delivery Plan Target Mar 2016 | Actual March 2016 | Delivery Plan Target Mar 2017 | Actual March 2017 | Delivery Plan Target Mar 2018 | Actual March 2018 | Delivery Plan Target Mar 2019 | Actual March 2019 | Delivery Plan Target Mar 2020 | Actual March 2020 | Delivery Plan Target Mar 2021 | Actual March 2021 |  | Delivery Plan Target Post Mar 2021 | Forecast Post March 2021 | Variance Value | Variance %
Drinking Water Quality Indicators
G3.1 | Number of failing zones for iron | Nr | I | n/a | n/a | 16 | n/a | 21 | n/a | 18 | n/a | 25 | n/a | 29 | n/a | 21 | n/a | 16 |  |  |  | -5 | -23.8095
G3.2 | Number of failing zones for manganese | Nr | I | n/a | n/a | 14 | n/a | 11 | n/a | 7 | n/a | 9 | n/a | 15 | n/a | 10 | n/a | 13 |  |  |  | 3 | 30
G3.3 | Number of microbiological failures at WTWs | Nr | I | n/a | 38 | 40 | n/a | 16 | n/a | 33 | n/a | 22 | n/a | 24 | n/a | 32 | n/a | 18 |  |  |  | -14 | -43.75
G3.4 | Number of Customer Contacts relating to Taste | Nr | I | 5000 | n/a | 2671 | 5000 | 2691 | 5000 | 2526 | 5000 | 2503 | 5000 | 2224 | 5000 | 2027 | 5000 | 1553 |  |  |  | -474 | -23.3843
G3.5 | Number of Customer Contacts relating to Discolouration | Nr | I | 10000 | n/a | 9211 | 10000 | 6325 | 10000 | 5973 | 10000 | 4744 | 10000 | 6101 | 10000 | 7111 | 10000 | 9495 |  |  |  | 2384 | 33.5255
Environment Serviceability Indicators
G3.6 | Number of failing WWTW | Nr | I | 5 | 18 | 3 | 5 | 6 | 5 | 4 | 5 | 0 | 5 | 2 | 5 | 3 | 5 | 2 |  |  |  | -1 | -33.3333
G3.7 | Number of sludge treatment facilities improved to comply with safe sludge matrix | Nr | I | n/a | 2 | 2 | n/a | 8 | n/a | 8 | 8 | 9 | 8 | 11 | 8 | 11 | 8 | 11 |  |  |  | 0 | 0
G3.8 | Maximum number of UIDs | Nr | I | n/a | n/a | 791 | n/a | 761 | n/a | 738 | n/a | 720 | n/a | 704 | n/a | 686 | n/a | 656 |  |  |  | -30 | -4.3732
G3.9 | Number of pollution incidents | Nr | I | 330 | 548 | 249 | 330 | 260 | 330 | 239 | 330 | 193 | 330 | 227 | 330 | 229 | 330 | 203 |  |  |  | -26 | -11.3537
G3.10 | Total number of Pollution incidents (sewerage) | Nr | I | n/a | n/a | 249 | 329 | 257 | 329 | 238 | 329 | 191 | 329 | 219 | 329 | 223 | 329 | 193 |  |  |  | -30 | -13.4529
G3.11 | Serious pollution incidents (sewerage) Cat 1 & 2 | Nr | I | n/a | n/a | 8 | 13 | 10 | 13 | 12 | 13 | 5 | 13 | 9 | 13 | 5 | 13 | 5 |  |  |  | 0 | 0
G3.12 | Serious pollution incidents (water) Cat 1 | Nr | I | n/a | n/a | 1 | 1 | 3 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 |  |  |  | 1 | #DIV/0!
G3.13 | Discharge permit compliance | % | I | n/a | n/a | 99.49% | n/a | 98.98% | n/a | 99.32% | n/a | 100% | n/a | 99.67% | n/a | 99.5% | n/a | 99.66% |  |  |  | 0.0016 | 0.1608
G3.14 | Satisfactory sludge disposal | % | I | 100% | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  | 0 | 0
G3.15a | Greenhouse gas (GHG) emissions (ktCO2e) | ktCO2e | I | n/a | n/a | 379* | n/a | 404* | n/a | 352 | n/a | 315 | n/a | 272 | n/a | 254 | n/a | 249 |  |  |  | -5 | -1.9685
G3.15b | Scope 1: All direct emissions (process,onsite combustion of fossil fuels and vehicles owned or leased) | tC02e | I | [12 empty] | 29 |  | 39 |  |  |  | 10 | 34.4828
G3.15c | Scope 2: emissions associated with the production of the grid electricity used (Renewable export netted) | tC02e | I | [12 empty] | 109 |  | 102 |  |  |  | -7 | -6.422
G3.15d | Scope 3: indirect emissions, including business travel, outsourced activities (e.g. PFI) | tC02e | I | [12 empty] | 115 |  | 108 |  |  |  | -7 | -6.087
G3.15e | Carbon intensity ratios for water services (tonnes per Ml) | tC02e/ML | I | [12 empty] | 0.1 |  | 0.08 |  |  |  | -0.02 | -20
G3.15f | Carbon intensity ratios for wastewater services (tonnes per Ml) | tCO2e/ML | I | [12 empty] | 0.19 |  | 0.19 |  |  |  | 0 | 0
G3.15g | Renewable electricity generated | GWh | I | [12 empty] | 39.62 |  | 40.03 |  |  |  | 0.41 | 1.0348
G3.15h | Renewable electricity exported | GWh | I | [12 empty] | 22.3 |  | 21.58 |  |  |  | -0.72 | -3.2287
G3.15i | Renewable electricity used | GWh | I | [12 empty] | 16.4 |  | 17.63 |  |  |  | 1.23 | 7.5
G3.15j | Reduction in energy use from efficiency projects | GWh | I | [12 empty] | 6.3 |  | 1.02 |  |  |  | -5.28 | -83.8095
G3.15k | Annual electricity usage (regulatory operational usage) | GWh | I | [12 empty] | 441.3 |  | 448.02 |  |  |  | 6.72 | 1.5228
Customer Service Serviceability Indicators
G3.16 | Properties on the low pressure register | Nr | I | 100 | 240 | 46 | 100 | 47 | 100 | 45 | 100 | 45 | 100 | 51 | 100 | 37 | 100 | 34 |  |  |  | -3 | -8.1081
G3.17 | Properties with unplanned interruptions to supply > 12 hrs | Nr | I | <1,000 | 684 | 563 | <1,000 | 716 | <1,000 | 648 | <1,000 | 552 | <1,000 | 357 | <1,000 | 302 | <1,000 | 596 |  |  |  | 294 | 97.351
G3.17a | Properties with unplanned interruptions to supply > 6 hrs | Nr | I | 13000 | n/a | n/a | 13000 | 6434 | 13000 | 6027 | 13000 | 6393 | 13000 | 4989 | 13000 | 5604 | 13000 | 5381 |  |  |  | -223 | -3.9793
G3.18 | Number of hours lost due to water supply interruptions for three hours or longer | Hrs/prop | I | n/a | n/a | 0.2763 | n/a | 0.26106 | n/a | 0.2607 | n/a | 0.386 | n/a | 0.391 | n/a | 0.3 | n/a | 0.21883 |  |  |  | -0.081169 | -27.0565
G3.19 | Bursts per 1,000km of mains | Nr | I | n/a | 188 | 160 | n/a | 140.2219 | n/a | 137.3576 | n/a | 157 | n/a | 172 | n/a | 150 | n/a | 176 |  |  |  | 26 | 17.3333
G3.20 | Properties at risk of internal sewer flooding | Nr | I | 370 | 341 | 302 | 370 | 334 | 370 | 315/381 | >370 | 373 | 370 | 307 | 370 | 281 | 370 | 314 |  |  |  | 33 | 11.7438
G3.21 | Properties internally flooded due to other causes | Nr | I | n/a | 1270 | 367 | n/a | 389 | n/a | 328 | n/a | 346 | n/a | 369 | n/a | 341 | n/a | 267 |  |  |  | -74 | -21.7009
G3.22 | Properties internally flooded due to overloaded sewers | Nr | I | n/a | n/a | 54 | n/a | 95 | n/a | 121 | n/a | 63 | n/a | 129 | n/a | 131 | n/a | 332 |  |  |  | 201 | 153.4351
G3.23 | Incidents of internal sewer flooding for properties that have flooded within the last ten years | Nr | I | n/a | n/a | 156 | n/a | 243 | n/a | 241 | n/a | 202 | n/a | 125 | n/a | 339 | n/a | 270 |  |  |  | -69 | -20.354
G3.24 | Properties at risk of external sewer flooding | Nr | I | <5,000 | n/a | 3708 | <5,000 | 3693 | <5,000 | 3699 | <5,000 | 3701 | <5,000 | 3698 | <5,000 | 3703 | <5,000 | 3407 |  |  |  | -296 | -7.9935
G3.25 | Incidents of external sewer flooding due to other causes | Nr | I | 13000 | n/a | 10768 | 13000 | 9981 | 13000 | 8565 | 13000 | 7498 | 13000 | 8169 | 13000 | 8921 | 13000 | 8166 |  |  |  | -755 | -8.4632
G3.26 | Incidents of external sewer flooding due to overloaded sewers | Nr | I | 400 | n/a | 227 | 400 | 349 | 400 | 159 | 400 | 120 | 400 | 116 | 400 | 407 | 400 | 314 |  |  |  | -93 | -22.8501
G3.27 | The Overall Satisfaction level (from the customer service questionnaire) | % | I | n/a | >78% | 92% | n/a | 89.51% | n/a | 90.7% | n/a | 91.5% | n/a | 92.32% | n/a | 93.29% | n/a | 94.08% |  |  |  | 0.0079 | 0.84682
G3.28 | The maximum number of 'second tier' complaints referred to Scottish Public Services Ombudsman | Nr | I | n/a | <121 | 4 | n/a | 1 | n/a | 2 | n/a | 3 | n/a | 0 | n/a | 1 | n/a | 0 |  |  |  | -1 | -100
G3.29 | The number of telephone contacts relating to drinking water quality | Nr | I | n/a | <24,168 | 14150 | n/a | 11667 | n/a | 10563 | n/a | 9309 | n/a | 10193 | n/a | 10658 | n/a | 12925 |  |  |  | 2267 | 21.2704
G3.30 | The Overall Performance Assessment (OPA) Score (In Year Value) | Nr | I | 380-385 | 380 | 400 | 380 | 393 | 381 | 398.38 | 382 | 406 | 383 | 403 | 384 | 402 | 385 | 404 |  |  |  | 2 | 0.49751
G3.31 | The Overall Performance Assessment (OPA) Score (Period Average) | Nr | I | 382.5 | n/a | 370 | 382.5 | 393 | 382.5 | 396.16 | 382.5 | 399 | 382.5 | 400 | 382.5 | 400 | 382.5 | 401 |  |  |  | 1 | 0.25
G3.32 | The average annual level of leakage | Ml/d | I | 575 | 600 | 543.993 | 575 | 499.63 | 575 | 494.7575 | 575 | 491.979 | 575 | 492 | 575 | 464.4 | 575 | 462.664 |  |  |  | -1.736 | -0.37382
G3.33 | Household Customer Experience Measure (HCEM) | Nr | I | >82.60 | n/a | 82.6 | >82.60 | 84.32 | >82.60 | 85.88 | >82.60 | 86.36 | >82.60 | 87.54 | >82.60 | 88.02 | >82.60 | 88.45 |  |  |  | 0.43 | 0.48853
G3.34 | Non-Household Customer Experience Measure (nHHCEM) | Nr | I | n/a | n/a | n/a | n/a | n/a | n/a | 83.92 | n/a | 77.5 | n/a | 81.74 | n/a | 85.19 | n/a | 88.36 |  |  |  | 3.17 | 3.7211
G3.35 | High Esteem Test | % | I | n/a | n/a | n/a | n/a | 78.6% | n/a | 76.4% | n/a | 76.4% | n/a | 78.1% | n/a | 77.6% | n/a | 78.6% |  |  |  | 0.01 | 1.2887
G3.36 | Wholesale Key Performance Indicator (KPI's) | % | I | 95% | 95% | 92% | 95% | 90.96% | 95% | 91.92% | 95% | 97.6% | 95% | 98.4% | 95% | 98.1% | 95% | 98.8% |  |  |  | 0.007 | 0.71356
Resilience of supply
G3.37 | Water Available for Supply Index: % of Population covered by 1:40 level of Service | % | I | n/a | n/a | 88.9% | n/a | 87.3% | n/a | 86.8% | n/a | 86.74% | n/a | 86.71% | n/a | 86.6% | n/a | 79.8% |  |  |  | -0.068 | -7.8522
G3.38 | Water Available for Supply Index: % of Population covered by 1:100 level of Service | % | I | n/a | n/a | 71.5% | n/a | 77.3% | n/a | 82.2% | n/a | 70.1% | n/a | 71.35% | n/a | 75.85% | n/a | 61.4% |  |  |  | -0.1445 | -19.0508
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by:

## G4 - OMD Inputs
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2021
SECTION G: INVESTMENT MONITORING
Table G4: OMD Inputs including Q&SIIIa&b Project Sign-Offs
Q&SIV Enhancements - Drinking Water Quality - OMD Outputs
Line Ref. | Output | Drivers | Total No Outputs | OMG Programme Group | OMD Weighting % | Milestone Stage | Units | Field Type | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | 2020/21 |  |  |  | 2015-21
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
G4.1 | Number of water treatment works improved | DW2, DW3B, DW3C, DW23, DW25, DW25P, DW25T | 32 | 1 | 13 | 1 | No. | I | 15 | 18 | 20 | 25 | 26 | 27 | 27 | 27 | 27 | 29 | 29 | 30 | 30 | 30 | 30 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
[6 empty] | 2 | Zones | I | 1 | 1 | 2 | 10 | 10 | 14 | 14 | 16 | 17 | 17 | 18 | 22 | 22 | 22 | 23 | 26 | 26 | 28 | 28 | 31 | 31 | 31 | 31 | 31 | 31
[6 empty] | 3 | Zones | I | 0 | 0 | 1 | 8 | 8 | 13 | 13 | 16 | 16 | 17 | 18 | 22 | 22 | 22 | 22 | 24 | 26 | 27 | 28 | 31 | 31 | 31 | 31 | 31 | 31
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 5 | 5 | 8 | 12 | 13 | 16 | 16 | 16 | 16 | 17 | 18 | 18 | 18 | 18 | 19 | 20 | 20
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 5 | 6 | 10 | 10 | 12 | 13 | 14 | 14 | 14 | 14 | 15 | 15
G4.2 | Number of zones made compliant with iron & manganese standards | DW5 | 82 | 2 | 6.8 | 1 | No. | I | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 65 | 65 | 65 | 72 | 72 | 72 | 72 | 72 | 72 | 81 | 82 | 82 | 82 | 82 | 82 | 82
[6 empty] | 2 | Zones | I | 0 | 0 | 0 | 23 | 28 | 39 | 39 | 51 | 51 | 56 | 56 | 57 | 62 | 64 | 64 | 67 | 70 | 70 | 80 | 80 | 80 | 80 | 81 | 82 | 82
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 1 | 20 | 27 | 36 | 50 | 51 | 56 | 56 | 57 | 62 | 64 | 64 | 67 | 70 | 70 | 79 | 79 | 79 | 80 | 80 | 81 | 81
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 12 | 14 | 20 | 30 | 42 | 45 | 49 | 55 | 58 | 60 | 60 | 64 | 64 | 64 | 68 | 76 | 76
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 10 | 10 | 17 | 38 | 41 | 47 | 47 | 57 | 58 | 58 | 58 | 61 | 61
G4.3 | Number of enhancements to improve reliability of supply (catchments and treatment) | WR1, DW25P | 54 | 3 | 5.9 | 1 | No. | I | 4 | 5 | 6 | 17 | 21 | 23 | 28 | 36 | 38 | 40 | 41 | 47 | 49 | 49 | 51 | 51 | 52 | 53 | 53 | 53 | 54 | 54 | 54 | 54 | 54
[6 empty] | 2 | Zones | I | 1 | 1 | 1 | 7 | 8 | 9 | 10 | 15 | 16 | 16 | 20 | 28 | 28 | 30 | 34 | 35 | 39 | 39 | 41 | 45 | 48 | 50 | 51 | 51 | 51
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 6 | 8 | 9 | 9 | 15 | 16 | 16 | 17 | 24 | 25 | 29 | 30 | 33 | 38 | 39 | 40 | 44 | 45 | 48 | 50 | 51 | 51
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 3 | 3 | 3 | 4 | 5 | 7 | 9 | 9 | 13 | 13 | 13 | 16 | 16 | 17 | 19 | 21 | 24 | 24 | 26 | 29 | 33 | 33
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 4 | 6 | 8 | 8 | 8 | 9 | 12 | 13 | 14 | 14 | 18 | 19 | 20 | 20 | 28 | 28
G4.4 | Number of enhancements to improve reliability of supply (networks and storage) | DW25D, DW25P, DW25T | 87 | 4 | 2.1 | 1 | No. | I | 1 | 4 | 14 | 28 | 29 | 41 | 42 | 61 | 61 | 61 | 61 | 85 | 85 | 86 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87
[6 empty] | 2 | Zones | I | 0 | 0 | 2 | 9 | 10 | 19 | 19 | 28 | 28 | 29 | 39 | 63 | 63 | 64 | 66 | 81 | 83 | 83 | 84 | 85 | 85 | 85 | 86 | 86 | 86
[6 empty] | 3 |  | I | 0 | 0 | 1 | 8 | 10 | 18 | 18 | 21 | 27 | 27 | 28 | 48 | 62 | 64 | 65 | 66 | 80 | 83 | 83 | 84 | 84 | 84 | 85 | 86 | 86
[6 empty] | 4 |  | I | 0 | 0 | 1 | 3 | 4 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 23 | 34 | 36 | 37 | 42 | 47 | 47 | 54 | 57 | 59 | 66 | 74 | 74
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 1 | 3 | 10 | 10 | 11 | 11 | 12 | 13 | 13 | 14 | 14 | 22 | 22 | 29 | 41 | 42 | 50 | 52 | 54 | 55 | 66 | 66
G4.5 | Distribution mains cleaned (km) | DW25D, DW25FS | 6558 | 5 | 5.8 | 1 | Km | I | 115.03 | 509.95 | 1513.88 | 2225.55 | 2435.91 | 3280.99 | 3575.94 | 3575.94 | 3575.94 | 3575.94 | 3575.94 | 3575.94 | 4394.528 | 4523.51 | 5818.606 | 5874.126 | 5874.126 | 6390.336 | 6390.336 | 6558.136 | 6558.136 | 6558.136 | 6558.136 | 6558.136 | 6558.136
[6 empty] | 2 | Zones | I | 0 | 0 | 0 | 384.75 | 384.75 | 493.76 | 493.76 | 723.42 | 750.39 | 992.71 | 1685.57 | 2004.97 | 2683.13 | 3575.94 | 3825.44 | 3825.44 | 4523.51 | 4728.608 | 5874.126 | 6390.336 | 6390.336 | 6390.336 | 6474.236 | 6558.136 | 6558.136
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 108.15 | 295.88 | 318.74 | 345.51 | 667.3 | 729.48 | 846.8 | 1068.45 | 1685.57 | 2039.64 | 2341.16 | 3406.19 | 3825.44 | 3825.44 | 4951.194 | 4951.194 | 6390.336 | 6390.336 | 6390.336 | 6390.336 | 6558.136 | 6558.136
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110.66 | 144.92 | 277.32 | 286.2 | 504.96 | 543.1 | 603.45 | 643.2 | 1386.51 | 2205.43 | 2623.21 | 3326.308 | 3793.108 | 3793.108 | 3869.4 | 3869.4 | 5062.495 | 5062.495
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.94 | 108.37 | 363.14 | 363.14 | 445.93 | 559.38 | 746.3 | 1064.32 | 1190.89 | 2134.55 | 2535.53 | 3121.95 | 3560.7 | 3864.098 | 3864.098
G4.6 | Water supply resilience strategy and improvements made | CS16WR | 18 | 6 | 7.2 | 1 | No. | I | 2 | 4 | 6 | 11 | 11 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
[6 empty] | 2 | Zones | I | 1 | 1 | 3 | 8 | 8 | 9 | 9 | 10 | 13 | 13 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18
[6 empty] | 3 | Zones | I | 1 | 1 | 1 | 8 | 8 | 9 | 9 | 9 | 13 | 13 | 14 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18
[6 empty] | 4 | Zones | I | 1 | 1 | 1 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 13 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 4 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 12 | 12 | 13 | 13 | 14 | 14 | 15 | 15 | 15 | 15
G4.7 | Number of zones with improved security of supply (SOSI) | WG4 | 10 | 7 | 2.7 | 1 | No. | I | 2 | 2 | 3 | 5 | 5 | 5 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
[6 empty] | 2 | Zones | I | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
[6 empty] | 3 | Zones | I | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 5 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
[6 empty] | 4 | Zones | I | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
[6 empty] | 5 | Zones | I | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G4.8 | Number of security measures and improvements to the infrastructure of critical reservoirs | DW9A, DW9D, DW9F, DW9H | 687 | 8 | 4.5 | 1 | No. | I | 633 | 683 | 683 | 683 | 683 | 684 | 684 | 685 | 686 | 686 | 686 | 686 | 686 | 687 | 687 | 687 | 687 | 687 | 687 | 687 | 687 | 687 | 687 | 687 | 687
[6 empty] | 2 | Zones | I | 30 | 80 | 80 | 286 | 286 | 286 | 286 | 317 | 318 | 441 | 441 | 569 | 569 | 570 | 686 | 686 | 686 | 687 | 687 | 687 | 687 | 687 | 687 | 687 | 687
[6 empty] | 3 | Zones | I | 30 | 80 | 80 | 286 | 286 | 286 | 286 | 315 | 317 | 318 | 441 | 569 | 569 | 570 | 685 | 686 | 686 | 687 | 687 | 687 | 687 | 687 | 687 | 687 | 687
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 3 | 3 | 5 | 41 | 139 | 139 | 156 | 240 | 345 | 351 | 368 | 451 | 542 | 559 | 564 | 639 | 663 | 664 | 668 | 680 | 686 | 686
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 3 | 3 | 5 | 41 | 77 | 139 | 145 | 176 | 272 | 279 | 339 | 355 | 460 | 469 | 557 | 557 | 561 | 660 | 662 | 678 | 686 | 686
G4.9 | Number of water quality etc studies to inform future periods | CS16S, DW2_S, DW25PS, DW25TS, DW3C_S, | 360 | 18 | 1.7 | 1 | No. | I | 232 | 339 | 340 | 340 | 340 | 340 | 340 | 340 | 351 | 351 | 351 | 356 | 359 | 359 | 359 | 359 | 359 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360
[6 empty] | 2 | Zones | I | 27 | 49 | 189 | 339 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 350 | 354 | 354 | 356 | 357 | 358 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360
[6 empty] | 3 | Zones | I | 27 | 49 | 188 | 339 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 350 | 350 | 354 | 355 | 356 | 358 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 12 | 12 | 40 | 59 | 113 | 117 | 154 | 185 | 252 | 252 | 302 | 302 | 307 | 307 | 320 | 320 | 349 | 352 | 353 | 353 | 358 | 358
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 12 | 12 | 18 | 36 | 86 | 106 | 138 | 138 | 220 | 220 | 220 | 220 | 263 | 263 | 278 | 278 | 287 | 315 | 352 | 353 | 357 | 357
G4.10 | 2010-15 outputs planned to complete in the 2015-21 period | DW5, DW13, DW23, DW25 | 22 | 19 | 3.5 | 1 | No | I | 18 | 20 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
[6 empty] | 2 | Zones | I | 13 | 14 | 16 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
[6 empty] | 3 |  | I | 13 | 14 | 14 | 17 | 17 | 17 | 17 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
[6 empty] | 4 |  | I | 1 | 3 | 3 | 4 | 4 | 4 | 6 | 8 | 8 | 8 | 9 | 11 | 11 | 13 | 13 | 15 | 16 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18
[6 empty] | 5 | Zones | I | 0 | 0 | 1 | 2 | 2 | 3 | 3 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 13 | 13 | 15 | 16 | 17 | 17 | 17 | 17 | 18 | 18
Q&SIV Enhancements - Environment - OMD Outputs
Line Ref. | Output | Drivers | Total No Outputs | OMG Programme Group | OMD Weighting % | Milestone Stage | Units | Field Type | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | 2020/21 |  |  |  | 2015-21
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
G4.11 | Number of WWTWs improved to meet UWWTD | EC01A, EC10A | 26 | 9 | 6.7 | 1 | No. | I | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 24 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
[6 empty] | 2 | Zones | I | 6 | 6 | 7 | 18 | 18 | 18 | 18 | 18 | 18 | 21 | 21 | 23 | 23 | 23 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
[6 empty] | 3 | Zones | I | 6 | 6 | 6 | 14 | 18 | 18 | 18 | 18 | 18 | 19 | 21 | 23 | 23 | 23 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
[6 empty] | 4 | Zones | I | 4 | 5 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 10 | 15 | 18 | 18 | 19 | 21 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
[6 empty] | 5 | Zones | I | 4 | 5 | 5 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 15 | 15 | 17 | 19 | 21 | 21 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G4.12 | Number of waste water networks improved to meet UWWTD | CS11, EC01B,EC01C, EC01F, EC10B | 58 | 10 | 6.8 | 1 | No. | I | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 49 | 49 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58
[6 empty] | 2 | Zones | I | 1 | 8 | 14 | 28 | 28 | 28 | 30 | 31 | 32 | 34 | 35 | 35 | 40 | 40 | 44 | 45 | 45 | 45 | 46 | 55 | 55 | 55 | 55 | 55 | 55
[6 empty] | 3 | Zones | I | 1 | 6 | 10 | 19 | 28 | 28 | 28 | 31 | 31 | 33 | 34 | 35 | 35 | 40 | 42 | 44 | 44 | 44 | 44 | 54 | 54 | 54 | 55 | 55 | 55
[6 empty] | 4 | Zones | I | 0 | 2 | 4 | 7 | 7 | 13 | 17 | 17 | 18 | 20 | 21 | 23 | 23 | 25 | 25 | 29 | 29 | 38 | 38 | 38 | 38 | 42 | 42 | 44 | 44
[6 empty] | 5 | Zones | I | 0 | 0 | 4 | 4 | 7 | 7 | 7 | 17 | 17 | 17 | 19 | 22 | 23 | 23 | 25 | 29 | 29 | 29 | 36 | 38 | 38 | 38 | 38 | 44 | 44
G4.13 | Number of improvements required to meet UWWTD - Glasgow completion | EC01B, EC04B, EC10B | 85 | 20 | 15.5 | 1 | No. | I | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85
[6 empty] | 2 | Zones | I | 38 | 38 | 38 | 56 | 56 | 60 | 63 | 63 | 64 | 65 | 67 | 69 | 70 | 71 | 72 | 78 | 78 | 80 | 81 | 85 | 85 | 85 | 85 | 85 | 85
[6 empty] | 3 | Zones | I | 31 | 37 | 37 | 47 | 51 | 53 | 58 | 62 | 62 | 64 | 66 | 68 | 70 | 70 | 70 | 73 | 74 | 76 | 77 | 84 | 84 | 85 | 85 | 85 | 85
[6 empty] | 4 | Zones | I | 3 | 8 | 23 | 27 | 27 | 29 | 32 | 37 | 43 | 46 | 52 | 53 | 56 | 57 | 58 | 64 | 65 | 66 | 67 | 71 | 71 | 71 | 72 | 74 | 74
[6 empty] | 5 | Zones | I | 0 | 6 | 7 | 24 | 25 | 25 | 29 | 36 | 36 | 41 | 43 | 51 | 51 | 52 | 56 | 61 | 62 | 65 | 65 | 69 | 69 | 69 | 69 | 71 | 71
G4.14 | Number of improvements required to meet the Water Framework Directive | EC10A, WR1, WR2A | 31 | 11 | 1.8 | 1 | No. | I | 12 | 12 | 12 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 23 | 23 | 23 | 26 | 27 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 31 | 31
[6 empty] | 2 | Zones | I | 1 | 1 | 1 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 15 | 15 | 21 | 21 | 21 | 21 | 26 | 26 | 26 | 27 | 27 | 27
[6 empty] | 3 | Zones | I | 1 | 1 | 1 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 21 | 21 | 21 | 21 | 22 | 24 | 25 | 25 | 26 | 26
[6 empty] | 4 | Zones | I | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 5
G4.15 | Number of revised Bathing Waters Directive studies | EC16, EC16A, EC16B | 14 | 12 | 2.1 | 1 | No. | I | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
[6 empty] | 2 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 13 | 14 | 14 | 14 | 14
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 9 | 9 | 9 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 14 | 14 | 14 | 14
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 10 | 11 | 11 | 11 | 11 | 11
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 10 | 10 | 10 | 11 | 11 | 11
G4.16 | Number of studies and catchments to meet the requirements of the Flood Risk Management Act | CS16D | 218 | 13 | 1.2 | 1 | No. | I | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218
[6 empty] | 2 | Zones | I | 0 | 5 | 17 | 55 | 177 | 187 | 201 | 216 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218
[6 empty] | 3 | Zones | I | 0 | 0 | 6 | 47 | 166 | 187 | 193 | 210 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 23 | 29 | 44 | 55 | 71 | 83 | 103 | 115 | 147 | 167 | 178 | 188 | 208 | 213 | 216 | 217 | 218 | 218
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13 | 16 | 38 | 51 | 65 | 73 | 91 | 101 | 140 | 151 | 162 | 179 | 202 | 211 | 214 | 215 | 218 | 218
G4.17 | Number of environmental studies to inform future periods | EC01D, EC01G, EC06C, EC08C, EC10D, EC10E, EC10H, EC21, LA01_S, WR1A, WR2B | 130 | 14 | 2.8 | 1 | No. | I | 98 | 123 | 123 | 123 | 123 | 123 | 123 | 126 | 126 | 126 | 126 | 127 | 127 | 129 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
[6 empty] | 2 | Zones | I | 9 | 10 | 11 | 31 | 56 | 93 | 109 | 122 | 125 | 125 | 126 | 126 | 126 | 126 | 126 | 128 | 129 | 129 | 129 | 130 | 130 | 130 | 130 | 130 | 130
[6 empty] | 3 | Zones | I | 9 | 9 | 10 | 21 | 37 | 78 | 98 | 116 | 125 | 125 | 126 | 126 | 126 | 126 | 126 | 128 | 128 | 129 | 129 | 130 | 130 | 130 | 130 | 130 | 130
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 7 | 10 | 23 | 36 | 42 | 51 | 68 | 87 | 93 | 101 | 105 | 121 | 123 | 125 | 127 | 129 | 129
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 6 | 16 | 33 | 35 | 35 | 42 | 66 | 78 | 93 | 106 | 112 | 121 | 122 | 123 | 128 | 128
G4.18 | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | EC08A, EC23A, LA01, WQ01D, WQ01E | 97 | 15 | 2.5 | 1 | No. | I | 15 | 18 | 38 | 38 | 39 | 39 | 40 | 40 | 42 | 43 | 43 | 96 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97
[6 empty] | 2 | Zones | I | 9 | 10 | 11 | 12 | 21 | 26 | 27 | 29 | 29 | 36 | 36 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 95 | 96 | 96 | 96 | 96 | 96 | 96
[6 empty] | 3 | Zones | I | 9 | 10 | 11 | 12 | 21 | 25 | 26 | 28 | 29 | 36 | 36 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 41 | 94 | 94 | 94 | 94 | 95 | 95
[6 empty] | 4 | Zones | I | 6 | 7 | 10 | 11 | 11 | 11 | 11 | 20 | 21 | 22 | 27 | 28 | 29 | 29 | 31 | 31 | 35 | 35 | 35 | 38 | 38 | 38 | 45 | 65 | 65
[6 empty] | 5 | Zones | I | 4 | 5 | 6 | 10 | 10 | 10 | 10 | 19 | 19 | 20 | 22 | 27 | 28 | 28 | 29 | 31 | 31 | 31 | 31 | 38 | 38 | 38 | 38 | 54 | 54
G4.19 | 2010-15 outputs planned to complete in the 2015-21 period | EC16, WG4, WR1 | 15 | 21 | 2.8 | 1 | No. | I | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
[6 empty] | 2 | Zones | I | 8 | 9 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
[6 empty] | 3 | Zones | I | 5 | 7 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
[6 empty] | 4 | Zones | I | 0 | 0 | 1 | 7 | 7 | 8 | 8 | 10 | 10 | 10 | 10 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 7 | 7 | 7 | 8 | 8 | 10 | 10 | 10 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14
G4.20 | Number of improvements to dams to meet the requirements of the Flood Risk Management Act | WR6 | 54 | 26 | 0.6 | 1 | No. | I | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 2 | Zones | I | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 3 | Zones | I | 0 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 6 | 6 | 7 | 8 | 11 | 11 | 16 | 16 | 25 | 27 | 32 | 35 | 40 | 47 | 48 | 48 | 48 | 51 | 51 | 53 | 54 | 54
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 6 | 6 | 7 | 8 | 10 | 10 | 10 | 13 | 17 | 18 | 22 | 24 | 36 | 36 | 43 | 44 | 45 | 46 | 48 | 51 | 54 | 54
Q&SIV Enhancements -Supporting Economic Development - OMD Outputs
Line Ref. | Output | Drivers | Total No Outputs | OMG Programme Group | OMD Weighting % | Milestone Stage | Units | Field Type | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | 2020/21 |  |  |  | 2015-21
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
G4.21 | Number of climate change vulnerability assessments | CC3S, CC4S, CC4W, CC5S, CC7S | 123 | 17 | 1.5 | 1 | No. | I | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123
[6 empty] | 2 | Zones | I | 3 | 55 | 55 | 55 | 55 | 55 | 57 | 57 | 57 | 111 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123
[6 empty] | 3 | Zones | I | 3 | 55 | 55 | 55 | 55 | 55 | 57 | 57 | 57 | 109 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 4 | 6 | 31 | 54 | 54 | 55 | 55 | 56 | 59 | 59 | 59 | 59 | 81 | 98 | 98 | 110 | 110 | 121 | 121 | 121 | 123 | 123
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 4 | 6 | 31 | 54 | 54 | 54 | 55 | 55 | 57 | 57 | 57 | 57 | 59 | 79 | 91 | 91 | 110 | 121 | 121 | 121 | 123 | 123
G4.22 | Improvements in renewable power and energy efficiency | I2S_WNI, I2S_WWNI | 17.5 | 16 | 2.5 | 1 | Gwh | I | 2.273 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712
[6 empty] | 2 | Zones | I | 1.85 | 1.85 | 2.273 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712
[6 empty] | 3 | Zones | I | 0.52 | 1.11 | 1.11 | 12.6042 | 12.6042 | 12.6042 | 12.6042 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 13.3442 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712
[6 empty] | 4 | Zones | I | 0.52 | 0.52 | 0.52 | 6.824 | 6.864 | 6.914 | 7.684 | 8.298 | 9.829 | 9.949 | 10.9747 | 11.8682 | 13.1612 | 13.3332 | 13.3332 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712
[6 empty] | 5 | Zones | I | 0.52 | 0.52 | 0.52 | 0.943 | 0.943 | 0.943 | 0.943 | 7.994 | 9.829 | 9.829 | 10.4997 | 10.6532 | 12.6862 | 13.3332 | 13.3332 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712 | 17.5712
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by:

## G5 - Growth
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2021
SECTION G: INVESTMENT MONITORING
Table G5: Growth
|  |  |  | 10 | 20 | 30 | 40 | 50 | 60 | 70
Line Ref | Line Title | Units | Field Type | Report Year 2015-16 | Report Year 2016-17 | Report Year 2017-18 | Report Year 2018-19 | Report Year 2019-20 | Report Year 2020-21 | Forecast Post 2021
Growth expenditure (gross)
G5.1 | Expenditure for reasonable cost contributions - household - water | £m | I | 8.2148 | 7.2236 | 6.6699 | 10.4821 | 6.4053 | 10.0653 | 0
G5.2 | Expenditure for reasonable cost contributions - non-household - water | £m | I | -0.016061 | -0.0053652 | 0.072344 | -0.03366 | -0.0088256 | 0.18896 | 0
G5.3 | Total expenditure on reasonable cost contributions - water | £m | C | 8.1987 | 7.2182 | 6.7422 | 10.4484 | 6.3965 | 10.2543 | 0
G5.4 | Expenditure for reasonable cost contributions - household - wastewater | £m | I | 8.6536 | 10.3839 | 9.8368 | 18.2287 | 9.988 | 13.0534 | 0
G5.5 | Expenditure for reasonable cost contributions - non-household - wastewater | £m | I | 0 | 0.045892 | 0.019743 | 0.00035978 | -0.001211 | 0.0015925 | 0
G5.6 | Total expenditure on reasonable cost contributions - wastewater | £m | C | 8.6536 | 10.4298 | 9.8565 | 18.229 | 9.9867 | 13.055 | 0
G5.7 | Total expenditure on reasonable cost Contributions - water and wastewater | £m | C | 16.8523 | 17.648 | 16.5987 | 28.6775 | 16.3832 | 23.3093 | 0
G5.8 | Expenditure on Part 3 strategic capacity - water | £m | I | 1.0214 | 1.9914 | 4.8385 | 5.604 | 9.7415 | 13.7129 | 0
G5.9 | Expenditure on Part 3 strategic capacity - wastewater | £m | I | 2.5455 | 4.131 | 6.4918 | 13.8471 | 11.5936 | 7.3036 | 0
G5.10 | Total expenditure on Part 3 strategic capacity - water and wastewater | £m | C | 3.5668 | 6.1224 | 11.3304 | 19.4511 | 21.3351 | 21.0165 | 0
G5.11 | Expenditure on Part 4 assets - water | £m | I | 2.3788 | 5.1263 | 3.0056 | 3.5764 | 3.5373 | 1.1323 | 0
G5.12 | Expenditure on Part 4 assets - wastewater | £m | I | 7.3503 | 6.0985 | 8.8088 | 22.6267 | 28.8151 | 33.3857 | 0
G5.13 | Total expenditure on Part 4 assets - water and wastewater | £m | C | 9.7291 | 11.2248 | 11.8143 | 26.2031 | 32.3524 | 34.518 | 0
G5.14 | Total gross expenditure on growth - (RCC + Part 3 strategic capacity + Part 4) | £m | C | 30.1483 | 34.9952 | 39.7434 | 74.3317 | 70.0707 | 78.8438 | 0
Service Relocations
G5.15 | Service Relocations Water | £m | I | 15.0386 | 12.4052 | 9.3687 | 7.7985 | 6.1906 | 3.4885 | 0
G5.16 | Service Relocations Wastewater | £m | I | 4.8054 | 4.9606 | 3.4735 | 1.8201 | 2.4883 | 1.0228 | 0
G5.17 | Service Relocations Water Contributions | £m | I | -10.7902 | -6.5168 | -7.3147 | -4.6331 | -5.9057 | -2.1839 | 0
G5.18 | Service Relocations Wastewater Contributions | £m | I | -5.5586 | -3.3571 | -3.7682 | -1.7827 | -3.0027 | -2.5883 | 0
G5.19 | Net Service Relocations | £m | C | 3.4952 | 7.4919 | 1.7593 | 3.2028 | -0.2294 | -0.26085 | 0
Growth income (Infrastructure charge)
G5.20 | Water household infrastructure charge income | £m | I | 6.5083 | 7.5061 | 8.0983 | 8.4815 | 8.8808 | 8.6213 | 0
G5.21 | Water non-household infrastructure charge income | £m | I | 0.18903 | 0.21293 | 0.053823 | 0.106 | 0.18323 | 0.11468 | 0
G5.22 | Wastewater household infrastructure charge income | £m | I | 5.0938 | 6.4276 | 7.3153 | 7.8088 | 8.4648 | 8.052 | 0
G5.23 | Wastewater non-household infrastructure charge income | £m | I | 0.077305 | 0.057785 | 0.027592 | 0.017794 | 0.039702 | 0.022047 | 0
G5.24 | Total infrastructure charge income | £m | C | 11.8684 | 14.2044 | 15.495 | 16.4142 | 17.5685 | 16.8101 | 0
Growth expenditure (net of income)
G5.25 | Total net growth expenditure | £m | C | 21.7751 | 28.2827 | 26.0077 | 61.1203 | 52.2728 | 61.7729 | 0
Growth - properties and populations
G5.26 | Number of new household properties connected to the water network | Nr | I | 19244 | 22214 | 23756 | 24157.029 | 24703 | 23627 | 0
G5.27 | Number of new non-household properties connected to the water network | Nr | I | 559 | 630 | 158 | 301.8949 | 510 | 316 | 0
G5.28 | Total number of new properties connected to the water network | Nr | C | 19803 | 22844 | 23914 | 24458.9239 | 25213 | 23943 | 0
G5.29 | Number of new household properties connected to the wastewater network | Nr | I | 15061 | 19022 | 21459 | 22241.0463 | 23546 | 22067 | 0
G5.30 | Number of new non-household properties connected to the wastewater network | Nr | I | 229 | 171 | 81 | 50.6804 | 110 | 61 | 0
G5.31 | Total number of new properties connected to the wastewater network | Nr | C | 15290 | 19193 | 21540 | 22291.7268 | 23656 | 22128 | 0
G5.32 | Number of new household properties receiving reasonable cost contributions - water | Nr | I | 14393 | 15914 | 13807 | 14948.7873 | 11564 | 26148 | 0
G5.33 | Number of new non-household properties receiving reasonable cost contributions - water | Nr | I | 0 | 0 | 150 | -78.3154 | 0 | 491 | 0
G5.34 | Total number of properties receiving reasonable cost contributions - water part 2 & 3 | Nr | C | 14393 | 15914 | 13957 | 14870.4719 | 11564 | 26639 | 0
G5.35 | Number of new household properties receiving reasonable cost contributions - wastewater | Nr | I | 11211 | 12961 | 7469 | 12159.3207 | 10832 | 14218 | 0
G5.36 | Number of new non-household properties receiving reasonable cost contributions - wastewater | Nr | I | 0 | 57 | 15 | 15.1585 | 0 | 2 | 0
G5.37 | Total number of properties receiving reasonable cost contributions - wastewater part 2 & 3 | Nr | C | 11211 | 13018 | 7484 | 12174.4791 | 10832 | 14220 | 0
G5.38 | Number of household property infrastructure charge payments - water | Nr | I | 19244 | 22214 | 23756 | 24157.029 | 24703 | 23627 | 0
G5.39 | Number of non-household property infrastructure charge payments - water | Nr | I | 559 | 630 | 158 | 301.8949 | 510 | 316 | 0
G5.40 | Total number of infrastructure charge payments - water | Nr | C | 19803 | 22844 | 23914 | 24458.9239 | 25213 | 23943 | 0
G5.41 | Number of household property infrastructure charge payments - wastewater | Nr | I | 15061 | 19022 | 21459 | 22241.0463 | 23546 | 22067 | 0
G5.42 | Number of non-household property infrastructure charge payments - wastewater | Nr | I | 229 | 171 | 81 | 50.6804 | 110 | 61 | 0
G5.43 | Total number of property infrastructure charge - wastewater | Nr | C | 15290 | 19193 | 21540 | 22291.7268 | 23656 | 22128 | 0
G5.44 | Additional population equivalent served from new part 4 investment - water | Pe | I | 0 | 14677 | 0 | 0 | 0 | 388 | 0
G5.45 | Additional population equivalent served from new part 4 investment - wastewater | Pe | I | 1351 | 792 | 3188 | 671 | 6651 | 21268 | 0
Prepared by: …………………………………….……………………………….. |  |  | Date: ……………………
Checked by: …………………………….………………………………………….. |  |  | Date: ……………………
Authorised by:

## G6 - Project Analysis
SCOTTISH WATER
[12 empty] | Prepared by: …………………………………….……………………………….. |  |  |  | Date: ……………………
ANNUAL RETURN INFORMATION REQUIREMENTS 2021
[12 empty] | Checked by: …………………………….………………………………………….. |  |  |  | Date: ……………………
SECTION G : INVESTMENT PLAN | [11 empty] | Authorised by:
Table G6: Project Analysis - Actuals & Forecast - Water & Wastewater
Include all projects with expenditure in the price control period
Regulatory Outputs
[63 empty] | OMG-01 | OMG-02 | OMG-03 | OMG-04 | OMG-05 | OMG-06 | OMG-07 | OMG-08 | OMG-09 | OMG-10 | OMG-11 | OMG-12 | OMG-13 | OMG-14 | OMG-15 | OMG-16 | OMG-17 | OMG-18 | OMG-19 | OMG-20 | OMG-21 | OMG-22 | OMG-23 | OMG-24 | OMG-25 | OMG-26 | OMG-27 | OMG-28 | OMG-29 | OMG-30 | OMG-31 | OMG-32 | OMG-33 | OMG-34 | OMG-35 | OMG-36 | OMG-37 | OMG-38 | OMG-39 | OMG-40 | OMG-41 | OMG-42 | OMG-43 | OMG-44 | OMG-45 | OMG-46 | OMG-47 | OMG-48 | OMG-49 | OMG-50
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 19a | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 27a | 27b | 28 | 28a | 28b | 28c | 28d | 28e | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105
Project Autocode | Project Title | Q&S Period (3b,4, IR18,5) | Programme Grouping (1) | Programme Grouping (2) | Programme Grouping (3) | Programme Grouping (4) | Water or wastewater project (primary purpose) | Technical Expression - Sign-off Owner | Accountability | Programme Grouping | Current Project Status Code | Forecast MS1 Date | Forecast MS2 Date | Forecast MS3 Date | Forecast MS4 Date | Forecast MS5 Date | Project location - Local Authority | Expenditure Pre 2015-16 | Programme Expenditure Pre 2015-16 | Actual Expenditure 2015-16 | Actual Expenditure 2016-17 | Actual Expenditure 2017-18 | Actual Expenditure 2018-19 | Forecast Expenditure 2019-20 | Forecast Expenditure 2020-21 | Total Q&SIV period expenditure to 2020-21 | Post 2020-21 expenditure | Programme Post 2020-21 Expenditure | Programme Post 2020-21 Expenditure Inc Risk | Project Grand Total expenditure | Additional Risk SR15 Completion | IR18 Additional Risk | CL Additional Risk | Total Additional Risk | Grand Total Expenditure Including Risk | Table K Budget allocation | Grants for infrastructure assets | Grants for non-infrastructure assets | Contributions to infrastructure assets | Contributions to non-infrastructure assets | Impact of project on OPEX - additional operating expediture | Regulatory sign off required | Driver 1 | Driver 1 % allocation | Driver 2 | Driver 2 % allocation | Driver 3 | Driver 3 % allocation | Driver 4 | Driver 4 % allocation | Driver 5 | Driver 5 % allocation | Driver 6 | Driver 6 % allocation | Driver 7 | Driver 7 % allocation | Driver 8 | Driver 8 % allocation | Driver 9 | Driver 9 % allocation | Driver 10 | Driver 10 % allocation | Number of water treatment works made compliant with water quality standards | Number of water supply zones made compliant with iron and manganese standards | Water quality completion programme | Number of raw water catchments where reliability is improved | Number of enhancements to networks and treated water storage to improve reliability of supply | Length of distribution mains refurbished | Water supply resilience strategy and the number of improvements made. | Improvements to Drought Resilience | DWSP | Number of improvements required to meet SEMD requirements | Number of improvements to dams to meet the obligations of the FRMA | Number of lead communication pipes replaced | Number of improvements in the infrastructure of critical – reservoirs | Number of properties where low pressure issues are addressed’ | Average duration of short term interruptions in supply | Number of water efficiency advice and water saving packs provided (to 2% of customer base) | Number of improvements delivered to meet UWWTD: above ground works | Number of improvements delivered to meet UWWTD: below ground networks | Number of improvements delivered to meet UWWTD: Glasgow scheme | Number of improvements to meet the WFD | Number of improvements to meet the rBWD | Number of catchments improved to meet the Flood Risk Management Act (FRMA) | Number of studies to prepare for future investment periods | Number of Sludge Management sites investigated and / or improved | Develop a national strategy on the Priority Substances Directive | Number of improvements to meet the Habitats Directive | Number of improvements required under the Compliance Assessment Scheme | Number of improvements required by Scot. Gov’t to protect the water environment | Number of improvements required by SEPA and LAs to reduce odour nuisance | Number of properties removed from the internal flooding register | Number of internal flooding improvements - completion programme | Number of external flooding investigations and improvements | % of customers covered by flood resilience assessments | Number of surface water management investigations | Number of reasonable cost contributions made to connect new households and businesses - water | Number of RCC made to connect new households and businesses - waste water | Delivery of new waste water capacity for 58,000 people | Number of developer constructed assets (Part 2&3) adopted | Number of first time non domestic meters installed | Number of projects completed under statutory requirements to relocate services for transport infrastructure projects | Improved contact management and proactive communication | Number of wholesale meters | Renewable power generation | Reduction in energy usage | Number of vulnerability assessments and monitoring improvements to support Climate Change mitigation and reduction | Number of Research & Innovation projects completed | Number of water quality studies to prepare for future investment periods | OMG-48 (not used) | Strategic Mains Diversions | OMG-50 (not used)
507985 | N-WW-I-310720-Clachnaharry_Road_Inverness_DOA_Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-07-31 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559.79 | 1559.79 | 0 | 0 | 0 | 1559.79 | 0 | 0 | 0 | 0 | 1559.79 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507754 | N-WW-NI-170720-Balmaqueen_STW_Access_Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-21 |  | 2021-02-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 400 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508232 | N-WW-NI-170820-Tobermory_STW_FE_Chamber_Cover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-18 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2336.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506721 | N-WW-NI-200520-Oban_Corran_Parks_SPS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-05-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346.57 | 6346.57 | 0 | 0 | 0 | 6346.57 | 0 | 0 | 0 | 0 | 6346.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507857 | N-WW-NI-240720-Alness&Invergordon_STW_Aeration_Blower_A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-09-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3541.94 | 3541.94 | 0 | 0 | 0 | 3541.94 | 0 | 0 | 0 | 0 | 3541.94 | 90601.29 | [5 empty] | N | WWNI | 100%
500707 | (Longforgan) Station Road WWPS 1995 NO316293 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2015-06-12 | 2017-12-20 | 2018-03-29 | 2021-06-16 |  | Perth and Kinross | 0 | 0 | 21000 | 32778 | 223222 | 470506 | 126307.08 | 274908.92 | 1148722 | 875 | 0 | 0 | 1149597 | 0 | 0 | 50403 | 50403 | 1200000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503268 | 1 Waverley Road Dalkeith - Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-06-21 | 2028-01-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266999.98 | 0 | 0 | 266999.98 | 0 | 0 | 0 | 0 | 266999.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512221 | 12 Jean Armour Drive - Trap_MH Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-08-02 | 2021-10-22 | 2022-06-06 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39999.96 | 0 | 0 | 39999.96 | 0 | 0 | 0 | 0 | 39999.96 | 209381.79 | [5 empty] | N | WWI | 100%
501813 | 13 Carleton Cresent Glenrothes - Replace Pipe Bridge pipework | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2017-04-28 | 2018-03-14 | 2018-03-26 | 2018-06-29 |  | Fife | 0 | 0 | 0 | 6606.12 | 25859.88 | 52613.32 | 0.68 | 589.02 | 85669.02 | 0 | 0 | 0 | 85669.02 | 0 | 0 | 0 | 0 | 85669.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500058 | 152 to 158 Busby Road Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-11-30 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | East Renfrewshire | 192.99 | 192.99 | 34807.01 | 3000 | 4000 | 164.1 | 0 | 0 | 41971.11 | 0 | 0 | 0 | 42164.1 | 0 | 0 | 0 | 0 | 42164.1 | 106252.93 | [5 empty] | N | FL_DD | 100%
510624 | 19 Hamilton Road - emergency tankering | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2021-01-19 | 2021-03-18 | 2021-07-19 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90533.75 | 90533.75 | 9466.25 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510288 | 19 Hamilton Road Rutherglen - Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-12-22 | 2021-03-17 | 2021-07-02 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109829.12 | 109829.12 | 40547.65 | 0 | 0 | 150376.77 | 0 | 0 | 0 | 0 | 150376.77 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503367 | 1989-1 - Plumtree Place Galashiels | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-09-01 | 2022-01-10 | 2022-03-14 | 2023-01-27 | 2023-05-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 46000 | 51045.73 | 126560.27 | 223606 | 89446.18 | 0 | 0 | 313052.18 | 0 | 0 | 0 | 0 | 313052.18 | 175086.76 | [5 empty] | N | FL_DD | 100%
503392 | 1990-1 - Rinkvale Cottages Hawick | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-08-30 | 2023-01-09 | 2023-03-13 | 2024-01-26 | 2024-04-29 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 46000 | 45675.72 | 73217.1 | 164892.82 | 135310.95 | 0 | 0 | 300203.77 | 0 | 0 | 0 | 0 | 300203.77 | 175086.76 | [5 empty] | N | FL_DD | 100%
401087 | 2010- 2015 Asset Disposals (Finance) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 |  | 2020-08-17 |  | 2020-08-17 |  | Scottish Water Wide | 13710.93 | 0 | -1703.83 | 0 | 83.18 | 1949.4 | 49.17 | 1570.05 | 1947.96 | -1423.52 | 0 | 0 | 14235.37 | 0 | 0 | 0 | 0 | 14235.37 | 613322.63 | [5 empty] | N | OHDS1 | 50% | OHDW1 | 50%
503523 | 2019 Generator Replacement (Energy Programme) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-05-07 | 2019-05-07 | 2020-02-25 | 2021-04-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 131720 | 168280 | 300000 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503524 | 2019 Small Value Capital Maintenance Works (Energy Programme) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-04-04 | 2019-04-04 | 2020-10-12 | 2021-04-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 50364 | 53587 | 103951 | 4010 | 0 | 0 | 107961 | 0 | 0 | 0 | 0 | 107961 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503770 | 218-2- Mossbeath Crescent Uddingston | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-06-10 | 2022-10-17 | 2022-12-19 | 2023-11-03 | 2023-12-27 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 55805.39 | 66532.91 | 122338.3 | 177661.71 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 175086.76 | [5 empty] | N | FL_DD | 100%
500928 | 248 Sauchie Road Crieff | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2016-07-15 | 2021-02-01 | 2020-11-12 | 2028-04-01 | Perth and Kinross | 0 | 0 | 8367.68 | 58778.32 | 52031.1 | 111037.1 | 74785.79 | 18150.97 | 323150.97 | -1465.18 | 0 | 0 | 321685.79 | 0 | 0 | 0 | 0 | 321685.79 | 281339.69 | [5 empty] | N | FL_DD | 100%
503467 | 35 Montrose Street Clydebank | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2019-04-02 | 2019-04-02 | 2019-06-03 | 2019-09-04 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 361861.15 | 216.85 | 362078 | 0 | 0 | 0 | 362078 | 0 | 0 | 0 | 0 | 362078 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509544 | 4 Tollcross Road Glasgow - sewer repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-11-16 | 2021-03-01 | 2021-10-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27273 | 27273 | 47727.26 | 0 | 0 | 75000.26 | 0 | 0 | 0 | 0 | 75000.26 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508423 | 48 London Road - Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-09-11 | 2021-02-15 | 2021-12-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11187.89 | 11187.89 | 38857.14 | 0 | 0 | 50045.03 | 0 | 0 | 0 | 0 | 50045.03 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501582 | 49 Ardrossan Road Saltcoats Connection Realignment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-05-04 | 2017-09-29 | 2018-01-22 | 2018-03-26 |  | North Ayrshire | 0 | 0 | 0 | 74411 | 185822 | 14767 | 0 | -3055.01 | 271944.99 | 0 | 0 | 0 | 271944.99 | 0 | 0 | 0 | 0 | 271944.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501435 | 500100 - Balmore WTW - Network Risk | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-04-01 | 2016-07-25 | 2016-07-26 | 2016-09-30 | 2016-09-30 | East Dunbartonshire | 0 | 0 | 0 | 776.72 | 0 | 0 | 0 | 0 | 776.72 | 0 | 0 | 0 | 776.72 | 0 | 0 | 0 | 0 | 776.72 | 822776.29 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
501440 | 500109 - Corrie WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-30 | 2017-03-01 | 2017-03-02 | 2017-03-31 | 2017-03-31 | North Ayrshire | 0 | 0 | 0 | 930.57 | 268.83 | 0 | 0 | 0 | 1199.4 | 0 | 0 | 0 | 1199.4 | 0 | 0 | 0 | 0 | 1199.4 | 438946.64 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
501418 | 500122 - Ness WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2017-04-28 | 2018-12-10 | 2018-12-18 | 2021-12-03 | 2022-02-24 | Na H-Eileanan an Iar | 0 | 0 | 0 | 96266.67 | 469886.82 | 573399.93 | 2873739.62 | 1352625.96 | 5365919 | 1489279.76 | 1489279.76 | 2374851.7494 | 6855198.76 | 885571.9894 | 0 | 0 | 885571.9894 | 7740770.7494 | 1530909.4 |  |  |  |  | 12500.0004 | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
501436 | 500788 - Alexandria WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS3 | 2016-07-06 | 2016-07-25 | 2016-07-25 | 2021-04-28 | 2021-04-29 | Scottish Water Wide | 0 | 0 | 0 | 20408.28 | 1704.25 | 7688.77 | 320.28 | 0 | 30121.58 | 0 | 0 | 2024.1698 | 30121.58 | 2024.1698 | 0 | 385.5512 | 2409.721 | 32531.301 | 620807.32 | [5 empty] | Y | CM_WSNI | 16.11% | DW25P | 83.89% | [19 empty] | 1 | [45 empty] | 0
501421 | 500793 - Carrick Castle WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS3 | 2018-03-08 | 2019-06-26 | 2019-06-26 | 2021-04-01 | 2021-06-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 514.26 | 140.03 | 2192.4 | 757.38 | 3604.06 | 0 | 288.3248 | 576.6496 | 3604.06 | 288.3248 | 0 | 0 | 288.3248 | 3892.3848 | 141622.2 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
501419 | 500799 - Sewer flooding Customer Risk Assessment | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater | SW | SWD | Flood Assessments | MS3 | 2017-03-03 | 2019-07-31 | 2019-09-16 | 2021-04-01 | 2021-04-07 | Scottish Water Wide | 0 | 0 | 0 | 135738.62 | 266210.21 | 235051.17 | 307238.27 | 198948.73 | 1143187 | 0 | 0 | 0 | 1143187 | 0 | 0 | 0 | 0 | 1143187 | 980565.38 | [5 empty] | N | CS15E | 100%
501439 | 500902 - Improving resilience of supplies - Newmore | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | SWD | Supply Resilience | MS7 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2017-01-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 2197.89 | 0 | 0 | 0 | 0 | 2197.89 | 0 | 0 | 0 | 2197.89 | 0 | 0 | 0 | 0 | 2197.89 | 1989709.51 | [5 empty] | Y | CS16WR | 100% | [24 empty] | 1 | [42 empty] | 0
501791 | 501121 - Service Relocations Water | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | GW2 | 2021-06-15 |  |  | 2021-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275178.14 | 0 | 0 | 275178.14 | 0 | 0 | 0 | 0 | 275178.14 | 0 |  |  | 37344454.017 |  |  | N | CS23W | 100%
501796 | 501122 - Service Relocations Wastewater | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | GW2 | 2021-06-15 |  |  | 2021-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175129.7 | 0 | 0 | 175129.7 | 0 | 0 | 0 | 0 | 175129.7 | 2566127.23 |  |  | 20057589.31 |  |  | N | CS23S | 100%
502046 | 50531 UID Lyle Road PS EO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | SWMD | UWWTD - UID | MS7 | 2013-02-02 | 2017-01-26 | 2017-03-21 | 2017-09-30 | 2018-01-31 | North Lanarkshire | 0 | 0 | 65.42 | 9690.21 | 31906.51 | 0.01 | 0 | 0 | 41662.14 | 0 | 0 | 0 | 41662.14 | 0 | 0 | 0 | 0 | 41662.14 | 42442.63 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
511687 | 5116870000 Tiree WOA - Coalas SR (OMG05) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-03-31 | 2021-03-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
503584 | 59052 - Event and Duration Monitoring Phase 1 - East | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2019-08-29 | 2021-07-23 | 2021-11-22 | 2022-09-09 | 2022-12-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 50890 | 72354.77 | 123244.77 | 603834.81 | 0 | 0 | 727079.58 | 0 | 166553.2456 | 0 | 166553.2456 | 893632.8256 | 284605.17 | [5 empty] | N | CS29 | 100%
503583 | 59052 - Event and Duration Monitoring Phase 1 - North | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2019-08-27 | 2020-12-17 | 2021-03-08 | 2022-01-21 | 2022-03-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7863.39 | 67588.92 | 75452.31 | 244594.12 | 0 | 0 | 320046.43 | 0 | 67465.3791 | 0 | 67465.3791 | 387511.8091 | 284605.17 | [5 empty] | N | CS29 | 100%
503585 | 59052 - Event and Duration Monitoring Phase 1 - South | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2019-08-27 | 2022-01-10 | 2022-04-28 | 2022-11-01 | 2023-01-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 11387.42 | 10060.58 | 21448 | 129552.5 | 0 | 0 | 151000.5 | 0 | 35733.9276 | 0 | 35733.9276 | 186734.4276 | 284605.17 | [5 empty] | N | CS29 | 100%
503339 | 671-2 - Bridgend Stewarton | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-04-01 | 2022-03-02 | 2022-05-17 | 2022-12-16 | 2023-03-20 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 20000 | 59637.65 | 38628.06 | 118265.71 | 181734.29 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 175086.76 | [5 empty] | N | FL_DD | 100%
503428 | 719-1 Queen Street Dumfries | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-08-09 | 2021-12-13 | 2022-02-14 | 2022-10-07 | 2023-01-09 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 45000 | 90000 | 67696.83 | 202696.83 | 997303.17 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 175086.76 | [5 empty] | N | FL_DD | 100%
503398 | 719-2 Noblehill Place Dumfries | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-05-12 | 2021-09-20 | 2021-11-22 | 2022-07-15 | 2022-10-17 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 49000 | 59354.72 | 16635.28 | 124990 | 775010.19 | 0 | 0 | 900000.19 | 0 | 0 | 0 | 0 | 900000.19 | 175086.76 | [5 empty] | N | FL_DD | 100%
503604 | 719-3 Bellevue Street Dumfries | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS2 | 2021-02-22 | 2021-02-26 | 2021-07-05 | 2021-09-24 | 2021-08-27 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 42683.47 | -3671.47 | 39012 | 35987.59 | 0 | 0 | 74999.59 | 0 | 0 | 0 | 0 | 74999.59 | 175086.76 | [5 empty] | N | FL_DD | 100%
502809 | 722131 Leny Street Glasgow g20 7sh Developer payment | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2017-07-10 | 2017-07-10 | 2017-11-21 | 2017-12-04 | 2017-12-04 | Glasgow City | 0 | 0 | 0 | 0 | 239291.31 | 0 | 0 | 0 | 239291.31 | 0 | 0 | 0 | 239291.31 | 0 | 0 | 0 | 0 | 239291.31 | 444766.03 | [5 empty] | N | WG5 | 100%
503335 | A76 New Cumnock Wall Replacement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-08-20 | 2018-10-25 | 2018-10-25 | 2019-01-22 | 2019-01-22 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 105333 | 37935.02 | 0 | 143268.02 | 0 | 0 | 0 | 143268.02 | 0 | 0 | 0 | 0 | 143268.02 | 38730.22 | [5 empty] | N | CS23W | 100%
403650 | A96 Corridor - Foul Drainage | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2014-02-03 | 2014-03-24 | 2014-03-24 | 2019-02-20 | 2019-02-20 | Highland | 1400000 | 0 | 0 | -426630.55 | 1251663.32 | 5737181.62 | 0 | 0 | 6562214.39 | 0 | 0 | 0 | 7962214.39 | 0 | 0 | 0 | 0 | 7962214.39 | 0 |  |  |  |  | 17705 | N | SG5 | 100%
402736 | Aberargie WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-06-11 | 2013-05-16 | 2013-10-28 | 2014-02-26 | 2014-02-26 | Perth and Kinross | 205340.87 | 0 | 3635 | 181.62 | 41.37 | 0 | 0 | 0 | 3857.99 | 0 | 0 | 0 | 209198.86 | 0 | 0 | 0 | 0 | 209198.86 | 0 | [5 empty] | N | SG1 | 100%
401379 | Aberchirder South Street - Sewer Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2010-09-24 | 2012-10-29 | 2015-01-19 | 2015-03-13 | 2015-03-13 | Aberdeenshire | 50142 | 50142 | -46590.69 | 0 | 0 | 0 | 0 | 0 | -46590.69 | 0 | 0 | 0 | 3551.31 | 0 | 0 | 0 | 0 | 3551.31 | 175086.76 | [5 empty] | N | FL_DD | 100%
403781 | Aberchirder WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2017-01-10 | 2019-06-28 | 2019-09-30 | 2021-07-08 |  | Aberdeenshire | 11188 | 0 | 26952.58 | 6246.1 | 5733.84 | 144320.68 | 253261.87 | 876936.71 | 1313451.77 | 45725.48 | 0 | 0 | 1370365.25 | 0 | 0 | 86634.75 | 86634.75 | 1457000 | 0 | [5 empty] | N | SG1 | 100%
503203 | Aberdeen- Aberdeenshire WW Growth Strategic Study | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2023-10-12 | 2025-01-15 | 2025-05-14 | 2025-12-30 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 322752.25 | 162386.94 | 187026.68 | 672165.87 | 77834.13 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 750000 | 122419.09 | [5 empty] | N | SG1 | 100%
511153 | Aberdeen Airport Critical Sewers Investigation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWMD | SR21 Early Start | MS0 | 2021-03-01 | 2021-04-26 | 2021-05-24 | 2021-11-19 | 2022-02-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264.15 | 2264.15 | 28000 | 0 | 0 | 30264.15 | 0 | 0 | 0 | 0 | 30264.15 | 0 | [5 empty] | N | SR21_WW | 100%
403478 | Aberdeen Area Water Network Model | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2013-07-02 | 2013-10-21 | 2013-10-21 | 2014-12-18 | 2015-01-21 | Aberdeenshire | 428744 | 0 | -10603.49 | 0 | 0 | 0 | 0 | 0 | -10603.49 | 0 | 0 | 0 | 418140.51 | 0 | 0 | 0 | 0 | 418140.51 | 0 | [5 empty] | N | WG5 | 100%
403788 | Aberdeen Greenwell Road (International Base) Sewer Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-10-21 | 2014-11-21 | 2015-01-14 | 2015-07-21 |  | Aberdeen City | 105136 | 0 | 4169 | 1430.86 | -1974.49 | 0 | 0 | 0 | 3625.37 | 0 | 0 | 0 | 108761.37 | 0 | 0 | 0 | 0 | 108761.37 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402477 | Aberdeen Integrated Catchment Study (Nigg and Persley Sewer Catchment Areas) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-02-20 | 2013-02-20 | 2015-03-26 | 2015-03-30 | Scottish Water Wide | 1447201 | 0 | 121043 | -25526.68 | 15675.73 | 0 | 0 | 0 | 111192.05 | 0 | 0 | 0 | 1558393.05 | 0 | 0 | 0 | 0 | 1558393.05 | 0 | [5 empty] | N | CS16S | 100%
46262 | Aberdeen Mannofield No1 TWP Refurb - TWP000443 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-12-03 | 2010-09-27 | 2013-01-21 | 2013-07-31 |  | Aberdeen City | 742687.29 | 0 | -30786.58 | 0 | 0 | 0 | 0 | 0 | -30786.58 | 4450.04 | 0 | 0 | 716350.75 | 0 | 0 | 0 | 0 | 716350.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509552 | Aberdeen Redcraigs TWS Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-04-12 | 2021-07-01 | 2022-02-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3286 | 3286 | 96714.32 | 0 | 0 | 100000.32 | 0 | 0 | 0 | 0 | 100000.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501094 | Aberdeen Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-07-20 | 2016-07-25 | 2019-03-31 | 2019-12-31 | Aberdeen City | 0 | 0 | 4738 | 79992.21 | 13869.79 | 21400 | 1348.29 | 1254.66 | 122602.95 | 0 | 0 | 0 | 122602.95 | 0 | 0 | 0 | 0 | 122602.95 | 0 | [5 empty] | Y | EC10D | 100% | [40 empty] | 1 | [26 empty] | 0
500814 | Aberdeenshire and Aberdeen City Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-13 | 2015-12-11 | 2015-12-11 | 2018-02-01 | 2018-02-01 | Aberdeenshire | 0 | 0 | 49031.93 | 1973.87 | -7925.99 | 0 | 0 | 0 | 43079.82 | 0 | 0 | 0 | 43079.82 | 0 | 0 | 0 | 0 | 43079.82 | 106252.93 | [5 empty] | N | FL_DD | 100%
501095 | Aberdeenshire Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-09-26 | 2016-09-28 | 2019-03-31 | 2019-12-31 | Aberdeenshire | 0 | 0 | 3730 | 45232.36 | 20237.64 | 24800 | 10083.46 | 0 | 104083.46 | 0 | 0 | 0 | 104083.46 | 0 | 0 | 0 | 0 | 104083.46 | 0 | [5 empty] | Y | EC10D | 100% | [40 empty] | 1 | [26 empty] | 0
402969 | Aberfoyle Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-26 | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | Stirling | 37520 | 0 | 363.29 | 0 | 0 | 0 | 0 | 0 | 363.29 | 0 | 0 | 0 | 37883.29 | 0 | 0 | 0 | 0 | 37883.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503078 | Aberfoyle SPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2019-02-14 | 2019-02-14 | 2019-02-14 | 2019-01-15 |  | Stirling | 0 | 0 | 0 | 0 | 8884.13 | 6769.84 | 0 | 0 | 15653.97 | 0 | 0 | 0 | 15653.97 | 0 | 0 | 0 | 0 | 15653.97 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500916 | Aberfoyle Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-09-28 | 2018-03-22 | 2018-03-27 | 2020-03-31 |  | Stirling | 0 | 0 | 10485 | 67740.26 | 145567.74 | 714755.29 | 291960.36 | -25915.31 | 1204593.34 | 5000 | 0 | 0 | 1209593.34 | 0 | 0 | 0 | 0 | 1209593.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500112 | Aberlour DOA (DOA000499) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2019-02-26 | 2019-05-17 | Moray | 0 | 0 | 8751 | 15597 | 27193 | 22659 | 8434 | 0 | 82634 | 0 | 0 | 0 | 82634 | 0 | 0 | 0 | 0 | 82634 | 11218.6 | [5 empty] | N | EC01G | 22.69% | CS16D | 37.97% | EC01D | 39.33%
400946 | Aberlour High Street - Internal Flooding Programme | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-05-31 | 2013-09-12 | 2013-09-30 | 2014-08-08 | 2014-03-31 | Moray | 1811330 | 0 | 1376.14 | -12031.84 | 7328.87 | 0 | 0 | 0 | -3326.83 | 0 | 0 | 0 | 1808003.17 | 0 | 0 | 0 | 0 | 1808003.17 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
505294 | Aberlour WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-04-25 | 2025-02-14 | 2025-07-17 | 2026-06-19 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57039.97 | 57039.97 | 1943912.8 | 0 | 0 | 2000952.77 | 0 | 0 | 0 | 0 | 2000952.77 | 122419.09 | [5 empty] | N | SG1 | 100%
45537 | Abington STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-03-23 | 2011-10-12 | 2012-08-30 | 2012-11-26 | South Lanarkshire | 764146.75 | 0 | 38434.37 | 0 | 0 | 0 | 0 | 0 | 38434.37 | 0 | 0 | 0 | 802581.12 | 0 | 0 | 0 | 0 | 802581.12 | 28761.13 | [5 empty] | N | WQ01 | 100%
400092 | Aboyne (Tanarside) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-11-04 | 2011-03-29 | 2011-07-18 | 2012-06-25 | 2012-09-25 | Aberdeenshire | 1620884.6 | 0 | -1887.58 | 0 | 0 | -3702.6 | 0 | 0 | -5590.18 | 3096.61 | 3096.61 | 4298.6219 | 1618391.03 | 1202.0119 | 0 | 0 | 1202.0119 | 1619593.0419 | 28761.13 | [5 empty] | N | DW23 | 100%
502958 | Aboyne WwTW - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2017-11-29 | 2021-07-09 | 2021-10-04 | 2022-10-13 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 28353.13 | 26629.88 | 112841.94 | 35784.89 | 203609.82 | 1066165.7 | 0 | 0 | 1269775.52 | 0 | 0 | 0 | 0 | 1269775.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500722 | Aboyne WWTW CM | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-24 | 2018-08-24 | 2018-08-23 | 2018-08-23 | 2018-08-23 | Aberdeenshire | 0 | 0 | 36204 | 34571.42 | 16338.91 | 860.16 | 0 | 0 | 87974.5 | 0 | 0 | 0 | 87974.5 | 0 | 0 | 0 | 0 | 87974.5 | 122419.09 | [5 empty] | N | SG1 | 100%
503100 | ABV Incentivisation Actual | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2018-07-09 | 2018-07-09 | 2020-03-24 | 2021-05-01 | 2022-11-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 95356.2 | -756228.17 | -365425.6 | -1026297.57 | 7026297.57 | 3091232.455 | 4291156.9166 | 6000000 | 1199924.4616 | 0 | 0 | 1199924.4616 | 7199924.4616 | 754428.1 | [5 empty] | N | SR15_RSK_EHR | 8.846e-11% | SR15_CMA_MAG | 0.03317% | SR15_CMA_WSNI | 0.2647% | SR15_ENV_ENVS | 0.3109% | SR15_SED_INFC | 0.4526% | SR21_SS | 0.529% | SR15_ENV_WFD | 0.9771% | SR15_ENV_RBWD | 1.428% | SR15_ENV_UWWD | 1.507% | SR15_SED_SCAP | 1.628%
502227 | AC Water Mains Study | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-12 | 2016-09-15 | 2016-10-21 | 2017-12-06 |  | Scottish Water Wide | 0 | 0 | 0 | 33697.12 | 9185.86 | -829.11 | 0 | 0 | 42053.87 | 0 | 0 | 0 | 42053.87 | 0 | 0 | 0 | 0 | 42053.87 | 311236.79 | [5 empty] | N | CM_M&G | 100%
500673 | Access to SW Systems | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-03 | 2017-03-16 | 2017-03-16 | 2017-01-16 |  | Scottish Water Wide | 0 | 0 | 60205.5 | 83.72 | 0 | 0 | 0 | 0 | 60289.22 | 0 | 0 | 0 | 60289.22 | 0 | 0 | 0 | 0 | 60289.22 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501059 | Acharacle WTW GAC Units | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-10-08 | 2015-11-25 | 2015-11-25 | 2015-11-25 |  | Highland | 0 | 0 | 1689.39 | 0 | 0 | 0 | 0 | 0 | 1689.39 | 0 | 0 | 0 | 1689.39 | 0 | 0 | 0 | 0 | 1689.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502845 | Achiltibuie WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-04 | 2019-04-04 | Highland | 0 | 0 | 0 | 0 | 20930.23 | 956.55 | -21463.56 | 0 | 423.22 | 0 | 0 | 0 | 423.22 | 0 | 0 | 0 | 0 | 423.22 | 122419.09 | [5 empty] | N | WG1 | 100%
45300 | Achmore WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-03-01 | 2011-08-15 | 2012-07-03 | 2012-09-24 | Highland | 1496054.78 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 1496124.78 | 0 | 0 | 0 | 0 | 1496124.78 | 28761.13 | [5 empty] | N | DW23 | 100%
511240 | Achmore WwTW - Settlement Pond Removal | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-04-01 | 2022-06-23 | 2023-02-03 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.42 | 65.42 | 29999.98 | 0 | 0 | 30065.4 | 0 | 0 | 0 | 0 | 30065.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510325 | Achnasheen WTW - PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2021-03-30 | 2022-10-06 | 2023-01-04 | 2023-12-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20510.24 | 20510.24 | 379489.76 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510477 | Acreknowe Reservoir - Dam Embankment Reinforcement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-01-20 | 2021-07-02 | 2022-02-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17931.08 | 17931.08 | 222133.38 | 0 | 0 | 240064.46 | 0 | 0 | 0 | 0 | 240064.46 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509947 | Acreknowe Reservoir MIOS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2020-12-22 | 2020-12-22 | 2021-02-01 | 2021-02-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1394.23 | 1394.23 | 0 | 0 | 0 | 1394.23 | 0 | 0 | 0 | 0 | 1394.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403590 | Addition of Dunbar East BW Culverted Watercourse Investigation | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-27 | 2014-05-23 | 2014-06-02 | 2014-12-19 | 2015-03-27 | East Lothian | 55258 | 0 | -18430.19 | 0 | 0 | 0 | 0 | 0 | -18430.19 | 0 | 0 | 0 | 36827.81 | 0 | 0 | 0 | 0 | 36827.81 | 0 | [5 empty] | N | EC16 | 100%
403592 | Addition of Fisherrow Sands Bathing Water Study | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2013-09-27 | 2014-09-30 | 2014-09-30 | 2016-09-30 | 2016-10-31 | City of Edinburgh | 231036 | 0 | 159888 | 62253.21 | 6233.45 | -6233.45 | 0 | 0 | 222141.21 | 0 | 0 | 0 | 453177.21 | 0 | 0 | 0 | 0 | 453177.21 | 356071 | [5 empty] | Y | EC16 | 100% | [65 empty] | 1 |  | 0
402688 | Additional Security requirements at 3 regraded water assets | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-11-19 | 2016-02-02 | 2015-04-14 | 2015-04-14 | 2015-04-14 | Scottish Water Wide | 149291.88 | 0 | -11135.82 | 0 | 0 | 0 | 0 | 0 | -11135.82 | 0 | 0 | 0 | 138156.06 | 0 | 0 | 0 | 0 | 138156.06 | 0 | [5 empty] | N | DW9A | 100%
500791 | Additional Water Quality Sampling | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-10-30 | 2015-10-30 | 2016-05-06 | 2018-04-11 |  | Scottish Water Wide | 0 | 0 | 8028 | 0 | 0 | -7992.86 | 0 | 0 | 35.14 | 0 | 0 | 0 | 35.14 | 0 | 0 | 0 | 0 | 35.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403916 | Address Update | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2014-09-03 | 2015-02-16 | 2015-02-18 | 2015-10-15 | 2015-10-15 | Scottish Water Wide | 335925 | 0 | 139459.14 | 7022.5 | 0 | 0 | 0 | 0 | 146481.64 | 0 | 0 | 0 | 482406.64 | 0 | 0 | 0 | 0 | 482406.64 | 0 | [5 empty] | N | CS20 | 100%
402506 | Adpro Security Equipment Replacement - Bradan Dam Comms. link replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-06 | 2012-09-24 | 2013-11-25 | 2016-12-01 |  | Scottish Water Wide | 29728.86 | 0 | 4683.4 | -15513.26 | 0 | 0 | 0 | 0 | -10829.86 | 0 | 0 | 0 | 18899 | 0 | 0 | 0 | 0 | 18899 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404110 | ADPRO Security Video Handling System Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-04-24 | 2015-06-10 | 2015-09-07 | 2017-01-20 |  | Scottish Water Wide | 0 | 0 | 233134 | 12140 | 0 | -709.46 | 0 | 0 | 244564.54 | 0 | 0 | 0 | 244564.54 | 0 | 0 | 0 | 0 | 244564.54 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402462 | Advanced Scheduler Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-12-20 | 2013-01-22 | 2013-01-22 | 2016-02-17 |  | Scottish Water Wide | 1652053 | 0 | 57744.73 | 0 | 0 | 0 | 0 | 0 | 57744.73 | 0 | 0 | 0 | 1709797.73 | 0 | 0 | 0 | 0 | 1709797.73 | 306661.32 | [5 empty] | N | CM_M&G | 100%
403657 | Afaria Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-01-10 | 2014-01-10 | 2014-01-10 | 2015-02-09 |  | Scottish Water Wide | 256705 | 0 | 6426.06 | 0 | 0 | 0 | 0 | 0 | 6426.06 | 0 | 0 | 0 | 263131.06 | 0 | 0 | 0 | 0 | 263131.06 | 613322.63 | [5 empty] | N | CM_M&G | 100%
34813 | Afton Bradan Penwhapple WRZ-WFD Compliance | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-15 | 2012-09-25 | 2012-11-01 | 2013-03-18 | 2013-03-18 | Scottish Water Wide | 484317 | 0 | 4453.16 | 361.52 | 0 | 0 | 0 | 0 | 4814.68 | 0 | 0 | 0 | 489131.68 | 0 | 0 | 0 | 0 | 489131.68 | 28761.13 | [5 empty] | N | WR1 | 100%
501273 | Afton Lorg Windfarm | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | GW2 | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-05-02 | East Ayrshire | 0 | 0 | 0 | 12014.76 | 7849.5 | 17327.94 | -27706.37 | 9559.11 | 19044.94 | -19043.94 | -19043.938 | -26436.2281 | 1 | -7392.2901 | 0 | 0 | -7392.2901 | -7391.2901 | 0 | [5 empty] | N | I2S_WI | 100%
506372 | Afton Old CWT - Leaking Scour Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2020-12-07 | 2021-04-08 | 2021-07-15 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
46242 | Afton Reservoir - Repairs to Bridge and Valvetower | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-01-08 | 2010-11-22 | 2011-03-31 | 2014-03-28 | 2014-03-28 | East Ayrshire | 1191831.77 | 0 | -555.3 | 0 | 0 | 0 | 0 | 0 | -555.3 | 0 | 0 | 0 | 1191276.47 | 0 | 0 | 0 | 0 | 1191276.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506429 | Afton Reservoir Pitching Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-05-26 | 2021-09-15 | 2021-12-22 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31831 | 31831 | 18169.2 | 0 | 0 | 50000.2 | 0 | 0 | 0 | 0 | 50000.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501274 | Afton Scottish Power OHL | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS4 | 2019-12-11 | 2019-12-11 | 2019-12-17 | 2019-12-17 | 2021-02-15 | East Ayrshire | 0 | 0 | 0 | 19382.03 | 20968.07 | 9569.12 | 43.06 | -49962.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | I2S_WI | 100%
501278 | Afton Windfarm | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS7 | 2020-05-14 | 2020-05-14 | 2020-12-14 | 2020-05-22 | 2021-01-07 | East Ayrshire | 0 | 0 | 0 | 120635.21 | 68964.99 | -104358.88 | -32566.06 | -52675.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | I2S_WI | 100%
507240 | Afton WTW - Chemical Spill Tank Ingress Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-11-25 | 2021-07-20 | 2022-03-02 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5042.72 | 5042.72 | 0 | 0 | 0 | 5042.72 | 0 | 0 | 0 | 0 | 5042.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402951 | Afton WTW - SCADA - PLC Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-09-28 | 2013-10-22 | 2013-11-18 | 2014-10-27 |  | East Ayrshire | 263017 | 0 | 24 | 251.96 | 0 | 0 | 0 | 0 | 275.96 | 0 | 0 | 0 | 263292.96 | 0 | 0 | 0 | 0 | 263292.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502651 | Afton WTW_Ayrshire_THM Research and Investigation | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2018-02-21 | 2019-12-10 | 2020-03-18 | 2022-07-19 | 2022-10-19 | South Ayrshire | 0 | 0 | 0 | 0 | 8155.11 | 73764.1 | 316404.8 | 55202 | 453526 | 1008479 | 1123396 | 1123396 | 1462005 | 0 | 114917 | 0 | 114917 | 1576922 | 279835.22 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
500650 | Agile Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-08-19 | 2016-08-29 | 2016-08-29 | 2018-06-14 |  | Scottish Water Wide | 0 | 0 | 283087 | 660952.64 | 621341.6 | -18146.91 | 0 | 0 | 1547234.33 | 0 | 0 | 0 | 1547234.33 | 0 | 0 | 0 | 0 | 1547234.33 | 613322.63 | [5 empty] | N | CM_M&G | 100%
402658 | Agile Working | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-05-31 | 2014-05-19 | 2014-05-19 | 2014-03-20 |  | Scottish Water Wide | 1712711.83 | 0 | 506.26 | 0 | 0 | 0 | 0 | 0 | 506.26 | 0 | 0 | 0 | 1713218.09 | 0 | 0 | 0 | 0 | 1713218.09 | 306661.32 | [5 empty] | N | CM_M&G | 100%
502710 | Aiginis Knock Lewis Overland Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 2607.67 | 0 | 0 | 0 | 2607.67 | 0 | 0 | 0 | 2607.67 | 0 | 0 | 0 | 0 | 2607.67 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503733 | Aird aMhachair - Benbecula DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-10-03 | 2021-02-23 | 2021-03-05 | 2022-05-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 22869.98 | 421548.13 | 444418.11 | 1529961.97 | 0 | 0 | 1974380.08 | 0 | 0 | 197344.92 | 197344.92 | 2171725 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45810 | Aird Tong SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-03-21 | 2014-02-03 | 2014-03-31 | 2014-03-31 | Na H-Eileanan an Iar | 1262685.36 | 0 | -18435.15 | 0 | 0 | 0 | 0 | 0 | -18435.15 | 0 | 0 | 0 | 1244250.21 | 0 | 0 | 0 | 0 | 1244250.21 | 28761.13 | [5 empty] | N | WQ01C | 100%
509525 | Airlie DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-01-07 | 2023-07-18 | 2023-10-16 | 2024-09-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249999.96 | 0 | 0 | 249999.96 | 0 | 0 | 0 | 0 | 249999.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502378 | Airth DSR Mainout | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-12-23 | 2020-10-08 | 2020-12-10 | 2020-12-10 |  | Falkirk | 0 | 0 | 0 | 3082.93 | 8720.43 | 8319.69 | 4381.04 | -4280.89 | 20223.2 | 0 | 0 | 0 | 20223.2 | 0 | 0 | 0 | 0 | 20223.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
30009 | Airth STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-08 | 2012-01-09 | 2012-03-20 | 2013-07-15 | 2013-10-09 | Falkirk | 2021289.87 | 0 | 1874.96 | 0 | 0 | 0 | 0 | 0 | 1874.96 | 0 | 0 | 0 | 2023164.83 | 0 | 0 | 0 | 0 | 2023164.83 | 241781.51 | [5 empty] | N | CM_WWNI | 5% | SG1 | 15% | EC01A | 80%
502874 | Albany Terrace Perth | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2017-12-20 | 2018-10-25 | 2018-12-12 | 2019-01-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 13775.94 | 68915.06 | 2843.18 | 680.04 | 86214.21 | 0 | 0 | 0 | 86214.21 | 0 | 0 | 0 | 0 | 86214.21 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500204 | Albert Rd WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-05-01 | 2017-04-28 | 2017-05-02 | 2018-03-06 |  | City of Edinburgh | 0 | 0 | 205000 | 331514 | 1494098 | -5095.88 | -18705.8 | -240.68 | 2006569.64 | 0 | 0 | 0 | 2006569.64 | 0 | 0 | 0 | 0 | 2006569.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503433 | Alemoor Drawdown Improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 | 2019-10-04 | 2021-03-19 | 2021-04-29 | 2021-10-27 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 18058.54 | 26153.76 | 44212.3 | 365380.86 | 0 | 0 | 409593.16 | 0 | 0 | 0 | 0 | 409593.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501208 | Alexandria WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2016-07-06 | 2016-07-25 | 2016-07-25 | 2018-04-30 | 2018-06-30 | West Dunbartonshire | 0 | 0 | 0 | 445.09 | 9044.16 | -9489.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | DW25D | 100% | [22 empty] | 1 | [44 empty] | 0
500723 | Alford WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2017-08-28 | 2020-03-31 | 2020-09-21 | 2022-01-14 |  | Aberdeenshire | 0 | 0 | 34493.38 | 59294.5 | 26842.33 | 10146.94 | 179416.32 | 1043285.48 | 1353478.95 | 396654.37 | 0 | 0 | 1750133.32 | 0 | 0 | 174866.68 | 174866.68 | 1925000 | 122419.09 | [5 empty] | N | SG1 | 100%
401936 | Allander Park Bearsden - Infrastructure Growth | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2011-09-12 | 2015-09-11 | 2015-09-14 | 2015-10-23 |  | East Dunbartonshire | 101213 | 0 | -2732.23 | 0 | 0 | 0 | 0 | 0 | -2732.23 | 0 | 0 | 0 | 98480.77 | 0 | 0 | 0 | 0 | 98480.77 | 0 | [5 empty] | N | SG5 | 100%
502690 | Allanfearn PFI - Odour Improvement Plan | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater | SEPA | SWD | Odour | MS7 | 2015-08-01 | 2016-03-01 | 2016-03-01 | 2016-03-31 | 2017-07-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | CS2 | 100% | [46 empty] | 1 | [20 empty] | 0
503319 | Allanfearn WwTW - PFI SR 21 - Post Concession Expiry Investment Review | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-01-30 | 2024-12-24 | 2025-03-24 | 2026-08-27 | 2026-11-27 | Highland | 0 | 0 | 0 | 0 | 0 | 70513.86 | 38109.38 | 88193.76 | 196817 | 11803182.86 | 0 | 0 | 11999999.86 | 0 | 0 | 0 | 0 | 11999999.86 | 0 | [5 empty] | N | SR21_WW | 100%
506172 | Allangillfoot White Esk River Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-05-05 | 2021-02-23 | 2021-06-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112228 | 112228 | 135771.64 | 0 | 0 | 247999.64 | 0 | 0 | 0 | 0 | 247999.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
30011 | Allers (East Kilbride) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-23 | 2012-02-21 | 2012-02-21 | 2014-06-11 | 2014-07-02 | South Lanarkshire | 4577775.74 | 0 | 32363.33 | -6590.11 | 0 | 0 | 0 | 0 | 25773.22 | 0 | 0 | 0 | 4603548.96 | 0 | 0 | 0 | 0 | 4603548.96 | 176884.68 | [5 empty] | N | EC10A | 10.34% | EC01A | 25.02% | EC04A | 25.02% | CM_WWNI | 39.63%
402221 | Allers Sludge Storage and Phase 2 M-E refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2011-09-27 | 2011-09-27 | 2011-10-10 | 2019-09-19 |  | South Lanarkshire | 732771.85 | 0 | 296.49 | 112.5 | 667.84 | 0 | 0 | 0 | 1076.83 | 0 | 0 | 0 | 733848.68 | 0 | 0 | 0 | 0 | 733848.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403883 | Alliance Mobilisation - Consultancy Support | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2014-07-24 | 2014-10-02 | 2014-10-02 | 2018-09-03 |  | Scottish Water Wide | 449856 | 224928 | 136096 | -41186.42 | 139635.92 | -139635.92 | 0 | 0 | 94909.58 | 0 | 0 | 0 | 544765.58 | 0 | 0 | 0 | 0 | 544765.58 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503711 | Alliance Partners- Post-Project Land Liabilities | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2019-09-30 | 2019-09-30 | 2020-01-28 | 2021-06-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 104690.11 | -42952.77 | 61737.34 | 468428.57 | 0 | 0 | 530165.91 | 0 | 0 | 0 | 0 | 530165.91 | 1244947.14 | [5 empty] | N | CM_WSI | 100%
45302 | Alligin WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-17 | 2011-07-22 | 2013-03-22 | 2013-04-10 | Highland | 232842.88 | 0 | -137.68 | 0 | 0 | 0 | 0 | 0 | -137.68 | 0 | 0 | 0 | 232705.2 | 0 | 0 | 0 | 0 | 232705.2 | 28761.13 | [5 empty] | N | DW13 | 100%
502739 | All-mains model build and maintenance Water Yr 3 to 6 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2017-05-31 | 2018-03-23 | 2018-05-11 | 2021-02-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 459488.53 | 690864.93 | 683298.65 | 111329.37 | 1944981.48 | 15358.26 | 0 | 0 | 1960339.74 | 0 | 0 | 0 | 0 | 1960339.74 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500111 | Alloa DOA (DOA000269) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-17 | 2017-03-17 | 2017-05-08 | 2018-06-18 | 2018-07-20 | Clackmannanshire | 0 | 0 | 10830 | 51324 | 55724.67 | 5685.03 | 0 | 0 | 123563.7 | 0 | 0 | 0 | 123563.7 | 0 | 0 | 0 | 0 | 123563.7 | 277404.61 | [5 empty] | N | CS16D | 100%
402874 | Alloa Drainage Network EPI Resolution Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-12-21 | 2016-02-15 | 2016-02-01 | 2016-02-19 |  | Clackmannanshire | 67374 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 68034 | 0 | 0 | 0 | 0 | 68034 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501159 | Alloa STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-07-07 | 2018-12-31 | 2019-06-14 | 2022-08-01 |  | Clackmannanshire | 0 | 0 | 0 | 54819.57 | 236259.02 | 680414.51 | 1241717.9 | 321476 | 2534687 | 2429837.71 | 0 | 0 | 4964524.71 | 0 | 0 | 1035475.29 | 1035475.29 | 6000000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500195 | Allt Sanna Pearl Mussels Habitats Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWD | Environmental Studies | MS7 | 2015-03-20 | 2016-03-14 | 2016-03-21 | 2016-11-30 | 2017-02-28 | Angus | 0 | 0 | 11755 | 29014.14 | 8298.07 | 442.47 | 0 | 0 | 49509.68 | 0 | 0 | 0 | 49509.68 | 0 | 0 | 0 | 0 | 49509.68 | 14757 | [5 empty] | Y | EC08C | 100% | [40 empty] | 1 | [26 empty] | 0
503234 | Allt Sanna WFPM | IR18 | Protecting and enhancing the environment | Habitats Directive |  |  | Wastewater | SEPA | SWMD | Habitats Directive | MS2 | 2018-06-29 | 2019-12-18 | 2021-06-21 | 2021-12-20 | 2022-03-22 | Highland | 0 | 0 | 0 | 0 | 0 | 88200.69 | 63021.59 | 5836.41 | 157058.69 | 628096.32 | 627755.308 | 627755.308 | 785155.01 | 0 | -341.012 | 0.002 | -341.01 | 784814 | 479915.76 | [5 empty] | Y | EC08D | 100% | [43 empty] | 1 | [23 empty] | 0
400723 | Almondbank WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2013-03-18 | 2013-05-21 | 2013-11-15 | 2013-11-15 | Perth and Kinross | 251977 | 0 | -6059.86 | 0 | 0 | 0 | 0 | 0 | -6059.86 | 0 | 0 | 0 | 245917.14 | 0 | 0 | 0 | 0 | 245917.14 | 0 | [5 empty] | N | SG1 | 100%
504758 | Alness and Invergordon STC - Lime Plant Modifcations | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-10 | 2022-08-15 | 2023-03-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 817.76 | 31053.36 | 31871.12 | 183128.88 | 0 | 0 | 215000 | 0 | 0 | 0 | 0 | 215000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500189 | Alness and Invergordon WWTW Odour Upgrade | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater | SEPA | SWD | Odour | MS7 | 2015-03-16 | 2015-10-02 | 2015-10-02 | 2015-03-31 | 2015-10-31 | Highland | 0 | 0 | 0.07 | 0 | -318.33 | 0 | 0 | 0 | -318.26 | 0 | 0 | 0 | -318.26 | 0 | 0 | 0 | 0 | -318.26 | 2490.44 | [5 empty] | Y | CS2 | 100% | [46 empty] | 1 | [20 empty] | 0
500854 | Alnwickhill B RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-03-31 | 2018-03-23 | 2018-06-14 | 2019-03-31 | 2019-09-30 | City of Edinburgh | 0 | 0 | 22932.61 | 23674.39 | 51034.96 | 209635.39 | 85340.02 | -22228.23 | 370389.14 | 0 | 0 | 0 | 370389.14 | 0 | 0 | 0 | 0 | 370389.14 | 830064.37 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 47.69 | [43 empty] | 0
501387 | Alnwickhill PRV | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWMD | Energy efficiency | MS7 | 2016-09-26 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | City of Edinburgh | 0 | 0 | 0 | 309793 | 59612 | -24636.57 | 0 | 0 | 344768.43 | 0 | 0 | 0 | 344768.43 | 0 | 0 | 0 | 0 | 344768.43 | 311236.79 | [5 empty] | N | I2S_WI | 18.62% | CM_WSI | 81.38%
403410 | Alnwickhill PRV Hydro | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-03-01 | 2015-02-18 | 2015-02-23 | 2015-02-24 | 2015-02-24 | City of Edinburgh | 1763.37 | 0 | 0 | 0 | 275.63 | 0 | 0 | 0 | 275.63 | 0 | 0 | 0 | 2039 | 0 | 0 | 0 | 0 | 2039 | 0 | [5 empty] | N | CC1W | 100%
502401 | Alnwickhill Revcovery Project | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-12-13 | 2016-12-13 | 2017-02-15 | 2018-07-20 |  | City of Edinburgh | 0 | 0 | 0 | 556674 | 2046423.88 | 136945.93 | 16540.12 | 468.07 | 2757052 | 3398.48 | 0 | 0 | 2760450.48 | 0 | 0 | 0 | 0 | 2760450.48 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506636 | Alva WWTW - Inlet Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-07-29 | 2021-05-03 | 2021-12-13 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 100000 | 0 | 0 | 115000 | 0 | 0 | 0 | 0 | 115000 | 90601.29 | [5 empty] | N | WWNI | 100%
501222 | Alves WWPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2015-11-18 | 2021-04-19 | 2021-07-19 | 2022-04-11 |  | Moray | 0 | 0 | 5969.18 | 23718.82 | 2768.29 | 0 | 2955.71 | 292568.26 | 327980.26 | 1336207.15 | 0 | 0 | 1664187.41 | 0 | 0 | 0 | 0 | 1664187.41 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402202 | Alyth WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-07-01 | 2013-07-24 | 2013-09-30 | 2015-03-27 | 2015-03-27 | Angus | 2016856 | 0 | 483832 | -79.17 | 1887.66 | 0 | 0 | 0 | 485640.49 | 0 | 0 | 0 | 2502496.49 | 0 | 0 | 0 | 0 | 2502496.49 | 0 | [5 empty] | N | SG1 | 100%
403864 | AM - BIP - IDP Development Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-31 | 2015-02-26 | 2015-02-26 | 2017-09-01 |  | Scottish Water Wide | 898925 | 449462.5 | 1069828 | 246951 | -117775.09 | 0 | 0 | 0 | 1199003.91 | 0 | 0 | 0 | 2097928.91 | 0 | 0 | 0 | 0 | 2097928.91 | 613322.63 | [5 empty] | N | CM_M&G | 100%
505548 | Amey Bypasses East Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-03-09 | 2020-07-29 | 2021-01-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 11560.71 | 199088.27 | 210648.98 | 0 | 0 | 0 | 210648.98 | 0 | 0 | 0 | 0 | 210648.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511345 | Amey Bypasses East Phase 4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-05-10 | 2021-06-14 | 2021-10-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682.96 | 682.96 | 250000 | 0 | 0 | 250682.96 | 0 | 0 | 0 | 0 | 250682.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511348 | Amey Bypasses East Phase 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-24 | 2021-06-14 | 2021-11-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000.02 | 0 | 0 | 250000.02 | 0 | 0 | 0 | 0 | 250000.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510835 | Amey Bypasses North Ph 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-29 | 2021-06-14 | 2022-05-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13214.95 | 13214.95 | 191283.05 | 0 | 0 | 204498 | 0 | 0 | 0 | 0 | 204498 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510836 | Amey Bypasses North Ph 4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-29 | 2021-07-14 | 2022-05-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10336.45 | 10336.45 | 147745.55 | 0 | 0 | 158082 | 0 | 0 | 0 | 0 | 158082 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505549 | Amey Bypasses North Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-03-09 | 2020-08-24 | 2021-03-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 10743.39 | 284738.61 | 295482 | 14517.96 | 0 | 0 | 309999.96 | 0 | 0 | 0 | 0 | 309999.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505551 | Amey Bypasses Phase 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-03-09 | 2020-10-12 | 2021-05-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7130.84 | 168119.16 | 175250 | 34750.11 | 0 | 0 | 210000.11 | 0 | 0 | 0 | 0 | 210000.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502258 | Amlaird - Gorbals TWPS and Drumboy Hill DSR | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WWINF | Exceptional Capital Maintenance | MS5 | 2016-06-17 | 2016-06-17 | 2016-07-01 | 2018-09-28 | 2018-09-28 | East Renfrewshire | 0 | 0 | 0 | 20899687 | 2303097 | 1491496 | 379335 | 341692 | 25415307 | 1847 | 1847 | 2563.9504 | 25417154 | 716.9504 | 0 | 0 | 716.9504 | 25417870.9504 | 0 | [5 empty] | N | SR15_EXC_EXC | 100%
503194 | Amlaird RSZ - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS3 | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-04-01 | 2021-09-13 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 821924 | 2735201.37 | 1160285.63 | 4717411 | 31999.99 | 31999.99 | 511239.4899 | 4749410.99 | 479239.4999 | 0 | 0 | 479239.4999 | 5228650.4899 | 0 | [5 empty] | N | DW5FS | 5.91% | DW5MR | 94.09%
502607 | Amlaird RSZ Cleaning - Mains Conditioning | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS5 | 2018-06-28 | 2018-12-20 | 2019-03-28 | 2019-12-31 | 2021-03-31 | East Ayrshire | 0 | 0 | 0 | 46347 | 250250.91 | 135664.1 | 78253.18 | -73738.18 | 436777 | 0 | 0 | 0 | 436777 | 0 | 0 | 0 | 0 | 436777 | 528018.37 | [5 empty] | Y | DW5MC | 100% | [23 empty] | 36.366 | [43 empty] | 0
503069 | Amlaird WR1 Mitigation Loch Goin | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS3 | 2018-02-12 | 2018-02-12 | 2018-06-13 | 2021-05-21 | 2021-07-21 | North Ayrshire | 0 | 0 | 0 | 0 | 21602.31 | 93852.26 | 204450.84 | 199486.65 | 519392.06 | 34610.24 | 34610.24 | 48044.9054 | 554002.3 | 13434.6654 | 0 | 0 | 13434.6654 | 567436.9654 | 9015175.25 | [5 empty] | N | DW25P | 100%
402614 | Amlaird WTW Essential Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-04-02 | 2019-06-07 |  | East Ayrshire | 841384 | 0 | 31616 | 62477.35 | 66188.06 | 0 | 0 | 0 | 160281.41 | 0 | 0 | 0 | 1001665.41 | 0 | 0 | 0 | 0 | 1001665.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403572 | AMR Project Phase 7 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 2015-07-31 |  | Scottish Water Wide | 568891.54 | 0 | 8644.95 | 0 | 0 | 0 | 0 | 0 | 8644.95 | 0 | 0 | 0 | 577536.49 | 0 | 0 | 0 | 0 | 577536.49 | 306661.32 | [5 empty] | N | CM_M&G | 100%
504100 | Ancrum WWTW Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-04-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 25461.71 | 374.05 | 25835.76 | 0 | 0 | 0 | 25835.76 | 0 | 0 | 0 | 0 | 25835.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500919 | Angus Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2016-06-30 | 2016-07-01 | 2017-09-11 | 2017-09-11 | Angus | 0 | 0 | 8951.12 | 62105.02 | -51525 | 0 | 0 | 0 | 19531.14 | 0 | 0 | 0 | 19531.14 | 0 | 0 | 0 | 0 | 19531.14 | 106252.93 | [5 empty] | N | FL_DD | 100%
503385 | Anguston ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-02-26 | 2019-02-26 | 2019-02-26 | 2019-02-26 | 2019-02-26 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 64479.98 | 0 | 0 | 64479.98 | 0 | 0 | 0 | 64479.98 | 0 | 0 | 0 | 0 | 64479.98 | 122419.09 | [5 empty] | N | SG1 | 100%
500114 | Annan DOA (DOA000111) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-17 | 2016-02-26 | 2016-08-11 | 2019-03-21 | 2019-08-28 | Dumfries and Galloway | 0 | 0 | 30381 | 102008.99 | 55979.53 | 9737 | 9347.33 | 0 | 207453.85 | 0 | 0 | 0 | 207453.85 | 0 | 0 | 0 | 0 | 207453.85 | 47383.58 | [5 empty] | N | EC01G | 7.97% | EC01D | 39.2% | CS16D | 52.83%
500113 | Anstruther Billowness DOA (DOA000254) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-17 | 2016-02-26 | 2016-03-21 | 2018-12-11 | 2019-03-22 | Fife | 0 | 0 | 21739 | 31819.52 | 51739.48 | 15842 | -10831.74 | 0 | 110308.27 | 0 | 0 | 0 | 110308.27 | 0 | 0 | 0 | 0 | 110308.27 | 4768.64 | [5 empty] | N | CS16D | 50% | EC01D | 50%
503576 | Anthony Road Largs Rail Sewer Crossing | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-06-08 | 2023-01-09 | 2023-04-07 | 2024-06-13 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 43918.96 | 190887.04 | 234806 | 1135663.95 | 0 | 0 | 1370469.95 | 0 | 0 | 0 | 0 | 1370469.95 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509219 | APNRV Standards and Specs Update | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2020-12-15 | 2021-01-20 | 2021-05-07 | 2021-06-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8322 | 8322 | 11177.59 | 0 | 0 | 19499.59 | 0 | 0 | 0 | 0 | 19499.59 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502626 | Applecross WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 20930.23 | 415.9 | 1196.3 | -19769.44 | 0 | 2772.99 | 0 | 0 | 0 | 2772.99 | 0 | 0 | 0 | 0 | 2772.99 | 122419.09 | [5 empty] | N | WG1 | 100%
501922 | Application Integration and Service Architecture Refresh 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2019-01-15 | 2019-01-15 | 2019-01-15 | 2020-05-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 459619.24 | 1078763.73 | -2490.08 | 1535892.89 | 0 | 0 | 0 | 1535892.89 | 0 | 0 | 0 | 0 | 1535892.89 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500587 | Application Platforms Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-01-18 | 2016-08-22 | 2016-08-22 | 2017-10-12 |  | Scottish Water Wide | 0 | 0 | 196259 | 17838.39 | 27739.32 | 0 | 0 | 0 | 241836.71 | 0 | 0 | 0 | 241836.71 | 0 | 0 | 0 | 0 | 241836.71 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403797 | Applications Remediation and Packaging Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-06-11 | 2014-06-11 | 2014-06-26 | 2015-03-12 |  | Scottish Water Wide | 2012615 | 0 | -15928.57 | 0 | 0 | 0 | 0 | 0 | -15928.57 | 0 | 0 | 0 | 1996686.43 | 0 | 0 | 0 | 0 | 1996686.43 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500435 | Arbroath Dangerpoint WWPS NO644406 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-04-30 | 2017-10-18 | 2018-03-06 | 2019-09-23 |  | Angus | 0 | 0 | 36000 | 35530 | 336259 | 246268 | 47546.45 | -0.45 | 701603 | 2399.55 | 0 | 0 | 704002.55 | 0 | 0 | 0 | 0 | 704002.55 | 299983.07 | [5 empty] | N | CM_WWNI | 30% | CM_WWI | 70%
510822 | ARC Archiestown DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-12-06 | 2022-03-07 | 2022-07-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 893.82 | 893.82 | 71667.5 | 0 | 0 | 72561.32 | 0 | 0 | 0 | 0 | 72561.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510526 | ARC Aultbea DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-08-24 | 2021-11-24 | 2022-04-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 571 | 138909.01 | 0 | 0 | 139480.01 | 0 | 0 | 0 | 0 | 139480.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510527 | ARC Balcraig DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-10-04 | 2022-01-04 | 2022-05-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 444 | 444 | 85633.39 | 0 | 0 | 86077.39 | 0 | 0 | 0 | 0 | 86077.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510528 | ARC Brockloch DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-08-23 | 2021-11-23 | 2022-04-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 571 | 124698.49 | 0 | 0 | 125269.49 | 0 | 0 | 0 | 0 | 125269.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509764 | ARC Broomhills DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-04-12 | 2021-07-01 | 2022-02-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3055 | 3055 | 120586.06 | 0 | 0 | 123641.06 | 0 | 0 | 0 | 0 | 123641.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510825 | ARC Carnbee DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-02-03 | 2022-09-01 | 2022-12-02 | 2023-04-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647348.6 | 0 | 0 | 647348.6 | 0 | 0 | 0 | 0 | 647348.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509767 | ARC Clatt Tillyangus DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-06-21 | 2021-07-30 | 2022-03-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778 | 1778 | 140327.6 | 0 | 0 | 142105.6 | 0 | 0 | 0 | 0 | 142105.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510821 | ARC Craigmill DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-12-06 | 2022-03-07 | 2022-07-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 833 | 115023.24 | 0 | 0 | 115856.24 | 0 | 0 | 0 | 0 | 115856.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510828 | ARC Crombie DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-11-22 | 2022-02-15 | 2022-06-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 833 | 125975.22 | 0 | 0 | 126808.22 | 0 | 0 | 0 | 0 | 126808.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510829 | ARC Drumbow DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-12-06 | 2022-03-01 | 2022-07-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271.75 | 271.75 | 131112.05 | 0 | 0 | 131383.8 | 0 | 0 | 0 | 0 | 131383.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509766 | ARC Durisdeer DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-04-12 | 2021-05-20 | 2021-07-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 10500 | 196774.65 | 0 | 0 | 207274.65 | 0 | 0 | 0 | 0 | 207274.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510831 | ARC Ellenbeich DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-12-06 | 2022-02-23 | 2022-07-06 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815 | 815 | 71686.06 | 0 | 0 | 72501.06 | 0 | 0 | 0 | 0 | 72501.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510128 | ARC Fala DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-06-07 | 2021-09-02 | 2022-01-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 98654.73 | 0 | 0 | 99654.73 | 0 | 0 | 0 | 0 | 99654.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510023 | ARC Fetterangus DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-06-21 | 2021-08-02 | 2022-03-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5333 | 5333 | 111428.29 | 0 | 0 | 116761.29 | 0 | 0 | 0 | 0 | 116761.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509268 | ARC Fisherford DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-06-21 | 2021-06-21 | 2022-07-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278 | 1278 | 39453.14 | 0 | 0 | 40731.14 | 0 | 0 | 0 | 0 | 40731.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510832 | ARC Furnace (Goatfield) DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2022-02-28 | 2022-05-27 | 2022-10-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788 | 788 | 96966.09 | 0 | 0 | 97754.09 | 0 | 0 | 0 | 0 | 97754.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510531 | ARC Gallowhill DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-09-08 | 2021-12-08 | 2022-04-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292.27 | 292.27 | 115947.11 | 0 | 0 | 116239.38 | 0 | 0 | 0 | 0 | 116239.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510837 | ARC Gateside DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-12-06 | 2022-02-28 | 2022-07-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815 | 815 | 207455.53 | 0 | 0 | 208270.53 | 0 | 0 | 0 | 0 | 208270.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510109 | ARC Hazelbank DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-05-24 | 2021-08-30 | 2022-01-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1556 | 1556 | 85336.82 | 0 | 0 | 86892.82 | 0 | 0 | 0 | 0 | 86892.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509269 | ARC Hazeldene DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-04-12 | 2021-07-01 | 2022-02-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8856 | 8856 | 61743.68 | 0 | 0 | 70599.68 | 0 | 0 | 0 | 0 | 70599.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510532 | ARC Helensburgh Low CWT Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-07-19 | 2021-10-19 | 2022-03-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667 | 667 | 162256.66 | 0 | 0 | 162923.66 | 0 | 0 | 0 | 0 | 162923.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510534 | ARC Insch Inschfield DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-08-09 | 2021-11-09 | 2022-03-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499.82 | 499.82 | 200095.75 | 0 | 0 | 200595.57 | 0 | 0 | 0 | 0 | 200595.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509847 | ARC Lamberton DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-04-12 | 2021-07-01 | 2022-02-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3786 | 3786 | 217156.32 | 0 | 0 | 220942.32 | 0 | 0 | 0 | 0 | 220942.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510535 | ARC Menzieshill DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-06-21 | 2021-09-20 | 2023-02-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1333 | 1333 | 138147.06 | 0 | 0 | 139480.06 | 0 | 0 | 0 | 0 | 139480.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510895 | ARC Muirhead Upper DSR Bypass SVCD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2022-01-17 | 2022-04-12 | 2022-08-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 225572.91 | 0 | 0 | 226372.91 | 0 | 0 | 0 | 0 | 226372.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510125 | ARC Octomore DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-09-13 | 2021-12-20 | 2022-05-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859.92 | 859.92 | 164122.5 | 0 | 0 | 164982.42 | 0 | 0 | 0 | 0 | 164982.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510921 | ARC Peterhead Meethill DSR Bypass SVCD1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-12-06 | 2022-02-28 | 2022-07-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815 | 815 | 232799.12 | 0 | 0 | 233614.12 | 0 | 0 | 0 | 0 | 233614.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510839 | ARC Rashfield DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-12-20 | 2022-03-18 | 2022-08-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815 | 815 | 202024.77 | 0 | 0 | 202839.77 | 0 | 0 | 0 | 0 | 202839.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510785 | ARC Saddell CWT Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-11-08 | 2022-02-04 | 2022-06-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850.57 | 850.57 | 83344.07 | 0 | 0 | 84194.64 | 0 | 0 | 0 | 0 | 84194.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510793 | ARC Scabbed Hill DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-11-08 | 2022-02-10 | 2022-06-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121.5 | 1121.5 | 85244.49 | 0 | 0 | 86365.99 | 0 | 0 | 0 | 0 | 86365.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510786 | ARC Strathdon DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2022-03-14 | 2022-06-10 | 2022-10-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 694.56 | 694.56 | 85289.96 | 0 | 0 | 85984.52 | 0 | 0 | 0 | 0 | 85984.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509979 | ARC Turlundie DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-06-21 | 2021-08-02 | 2022-03-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 93231.73 | 0 | 0 | 113231.73 | 0 | 0 | 0 | 0 | 113231.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510845 | ARC Voe & Vidilin DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-12-20 | 2022-03-18 | 2022-08-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815 | 815 | 198404.21 | 0 | 0 | 199219.21 | 0 | 0 | 0 | 0 | 199219.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510846 | ARC Whalsay Upper DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-12-20 | 2022-03-25 | 2022-08-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992.54 | 992.54 | 168534.93 | 0 | 0 | 169527.47 | 0 | 0 | 0 | 0 | 169527.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510847 | ARC Whitehills Ruthven DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-11-22 | 2022-02-15 | 2022-06-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 833 | 85244.49 | 0 | 0 | 86077.49 | 0 | 0 | 0 | 0 | 86077.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500989 | ARCS | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-09-25 | 2016-05-12 | 2016-05-12 | 2016-05-12 |  | Scottish Water Wide | 0 | 0 | 62742.86 | 0 | 0 | 0 | 0 | 0 | 62742.86 | 0 | 0 | 0 | 62742.86 | 0 | 0 | 0 | 0 | 62742.86 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503760 | Ardeonaig Intake Structure | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2019-10-04 | 2019-10-04 | 2020-01-15 | 2020-07-03 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 342475.77 | -8841.68 | 333634.09 | -1081.95 | 0 | 0 | 332552.14 | 0 | 0 | 0 | 0 | 332552.14 | 119022.58 | [5 empty] | N | CM_WSI | 100%
500115 | Ardersier DOA (DOA000501) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater | SEPA | SWMD | Flood Assessments | MS7 | 2015-03-17 | 2015-11-30 | 2016-01-12 | 2017-02-28 | 2017-07-31 | Highland | 0 | 0 | 49955 | 86901.95 | -3667.97 | 0 | 0 | 0 | 133188.98 | 0 | 0 | 0 | 133188.98 | 0 | 0 | 0 | 0 | 133188.98 | 558366.35 | [5 empty] | Y | CS15 | 33.33% | CS16D | 33.33% | CS11 | 33.33% | [35 empty] | 1 | [27 empty] | 0
501290 | Ardersier WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2015-12-24 | 2018-05-31 | 2018-06-26 | 2022-01-13 |  | Highland | 0 | 0 | 33462 | 284751.32 | 487405.34 | 5031420.48 | 4188617.86 | 2061903.44 | 12087560.44 | 262439.56 | 0 | 0 | 12350000 | 0 | 0 | 1650000 | 1650000 | 14000000 | 122419.09 | [5 empty] | N | SG1 | 100%
500649 | Ardersier WWTW - Outfall Extension | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS6 | 2015-06-30 | 2018-11-07 | 2018-12-10 | 2019-06-30 | 2020-03-31 | Highland | 0 | 0 | 61832 | 345821.35 | 613713.65 | 2668752 | 606481 | 0 | 4296600 | 400 | 400 | 555.2681 | 4297000 | 155.2681 | 0 | 0 | 155.2681 | 4297155.2681 | 0 | [5 empty] | Y | EC01A | 100% | [65 empty] | 1 |  | 0
500012 | Ardersier WwTW - UV | Q&S4 | Protecting and enhancing the environment | Habitats Directive |  |  | Wastewater | SEPA | NONINF | Habitats Directive | MS7 | 2015-06-17 | 2016-11-30 | 2016-12-07 | 2017-11-30 | 2018-01-31 | Highland | 0 | 0 | 88006 | 841003.84 | 1509147.92 | -1647243.3 | -105322.46 | -43266.53 | 642325.47 | 0 | 0 | 0 | 642325.47 | 0 | 0 | 0 | 0 | 642325.47 | 266250.97 | [5 empty] | Y | EC08A | 100% | [43 empty] | 1 | [23 empty] | 0
45305 | Ardfern (New) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-31 | 2011-05-16 | 2011-10-24 | 2011-12-07 | Argyll and Bute-North Argyll | 41157.73 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 41169.73 | 0 | 0 | 0 | 0 | 41169.73 | 28761.13 | [5 empty] | N | DW13 | 100%
507798 | Ardfern WTW - PLC Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-10-05 | 2023-08-22 | 2024-01-30 | 2025-08-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8200 | 8200 | 491800.58 | 0 | 0 | 500000.58 | 0 | 0 | 0 | 0 | 500000.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502316 | Ardfern WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-03 | 2020-04-03 | 2021-04-01 | 2020-04-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 26143.02 | 3238.09 | 1237.31 | 20063.5 | -6853.01 | 43828.91 | 0 | 0 | 0 | 43828.91 | 0 | 0 | 0 | 0 | 43828.91 | 122419.09 | [5 empty] | N | WG1 | 100%
501183 | Ardgay Street Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-23 | 2019-03-12 | 2018-02-01 | 2019-01-28 | 2019-01-28 | Glasgow City | 0 | 0 | 0 | 52000 | 35130.28 | -87129.28 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 180449.74 | [5 empty] | N | FL_DD | 100%
402632 | Ardgour - Growth Project | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater | SEPA | SWMD | Infra Charge | MS7 | 2012-06-11 | 2014-01-21 | 2014-02-03 | 2015-03-31 | 2015-05-31 | Highland | 840340 | 0 | 69475 | -5975.51 | -1387.53 | 0 | 0 | 0 | 62111.96 | 0 | 0 | 0 | 902451.96 | 0 | 0 | 0 | 0 | 902451.96 | 0 | [5 empty] | Y | SG5 | 100% | [34 empty] | 3 | [32 empty] | 0
501330 | Ardgowan WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2016-05-11 | 2017-07-27 | 2017-10-30 | 2018-03-30 |  | Inverclyde | 0 | 0 | 0 | 49217 | 830835 | 43922 | 0 | -1556.07 | 922417.93 | 0 | 0 | 0 | 922417.93 | 0 | 0 | 0 | 0 | 922417.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512031 | Ardoch DOA - Steven Street Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-03-29 | 2022-05-23 | 2023-01-03 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74999.97 | 0 | 0 | 74999.97 | 0 | 0 | 0 | 0 | 74999.97 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500121 | Ardoch DOA (DOA000707) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-17 | 2016-06-27 | 2016-08-24 | 2020-01-27 | 2020-03-23 | West Dunbartonshire | 0 | 0 | 17396 | 68936 | 218548.35 | 150000 | 36306.51 | 20715.64 | 511902.5 | 0 | 0 | 0 | 511902.5 | 0 | 0 | 0 | 0 | 511902.5 | 179237.65 | [5 empty] | N | EC01G | 10.86% | EC01D | 40.15% | CS16D | 48.99%
501158 | Ardoch STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-12-14 | 2018-10-15 | 2018-10-22 | 2021-06-03 |  | West Dunbartonshire | 0 | 0 | 20690 | 258206.33 | 175176.19 | 506094.22 | 1323648.2 | 216389.06 | 2500204 | 256645 | 0 | 0 | 2756849 | 0 | 0 | 258510 | 258510 | 3015359 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503416 | Ardross WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-01-13 | 2021-10-28 | 2022-04-12 | 2023-01-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 60503.3 | 32206.69 | 41742.36 | 134452.36 | 272894.44 | 0 | 0 | 407346.8 | 0 | 0 | 0 | 0 | 407346.8 | 122419.09 | [5 empty] | N | SG1 | 100%
511847 | Ardrossan WWPS - Capital Maintenance project | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2024-03-04 | 2025-09-10 | 2025-12-09 | 2026-11-16 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000.04 | 0 | 0 | 5000000.04 | 0 | 0 | 0 | 0 | 5000000.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501187 | Ardvourlie WTW - Intake | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-12 | 2016-06-28 | 2016-08-08 | 2018-02-09 |  | Na H-Eileanan an Iar | 0 | 0 | 3276 | 19316.83 | 60691.04 | -781.14 | 0 | 0 | 82502.73 | 0 | 0 | 0 | 82502.73 | 0 | 0 | 0 | 0 | 82502.73 | 119022.58 | [5 empty] | N | CM_WSI | 100%
508962 | Ardvourlie WTW - PLC | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-01-03 | 2023-07-24 | 2023-10-23 | 2024-07-31 | 2025-07-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3229 | 3229 | 246770.48 | 0 | 0 | 249999.48 | 0 | 0 | 0 | 0 | 249999.48 | 0 | [5 empty] | N | SR21_WA | 100%
503721 | Ardvourlie WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-24 | 2024-02-08 | 2024-07-18 | 2026-01-29 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7459 | 7459 | 992541.15 | 0 | 0 | 1000000.15 | 0 | 0 | 0 | 0 | 1000000.15 | 122419.09 | [5 empty] | N | SG1 | 100%
403552 | Argyle Street Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS6 | 2013-09-25 | 2018-11-29 | 2018-11-30 | 2019-05-27 | 2019-05-27 | Glasgow City | 65107.01 | 65107.01 | 39892.99 | 27387 | 33994.12 | 128616.36 | 1592.3 | 0.22 | 231482.99 | 0 | 0 | 0 | 296590 | 0 | 0 | 0 | 0 | 296590 | 965523.52 | [5 empty] | N | FL_DD | 5.715% | FL_NAMED | 94.28%
509932 | Argyll Mainland Reservoir vegetation clearance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-11-24 | 2021-05-21 | 2022-01-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.31 | 981.31 | 14088.83 | 0 | 0 | 15070.14 | 0 | 0 | 0 | 0 | 15070.14 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509931 | Argyll Mull Reservoir vegetation clearance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-11-24 | 2021-05-21 | 2022-01-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.1 | 327.1 | 4696.32 | 0 | 0 | 5023.42 | 0 | 0 | 0 | 0 | 5023.42 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503587 | Argyll SCADA - Ardrishaig | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2019-09-30 | 2020-03-26 | 2020-03-27 | 2021-10-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 338316 | 472966.54 | 811282.54 | 263403 | 0 | 0 | 1074685.54 | 0 | 0 | -47034.54 | -47034.54 | 1027651 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503586 | Argyll SCADA - Tarbert | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2019-09-30 | 2020-03-26 | 2020-03-27 | 2021-06-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 351605 | 510709.48 | 862314.48 | 67424 | 0 | 0 | 929738.48 | 0 | 0 | 0 | 0 | 929738.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500793 | Argyll SCADA Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS2 | 2016-06-28 | 2021-03-31 | 2021-06-18 | 2024-01-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 13644.19 | 225569.48 | 65768.43 | 61791.93 | 206494.56 | 573268.59 | 2814755.47 | 0 | 0 | 3388024.06 | 0 | 0 | 0 | 0 | 3388024.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500906 | Argyll-Bute and West Dumbartonshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2016-10-14 | 2016-10-14 | 2016-10-14 | 2016-10-14 | Argyll and Bute-Cowal & Bute | 0 | 0 | 4940.33 | 679.91 | 0 | 0 | 0 | 0 | 5620.24 | 0 | 0 | 0 | 5620.24 | 0 | 0 | 0 | 0 | 5620.24 | 106252.93 | [5 empty] | N | FL_DD | 100%
500224 | Arinagour Coll - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-03-30 | 2016-06-28 | 2017-12-31 | 2018-06-30 | Argyll and Bute-North Argyll | 0 | 0 | 561.48 | 28073.18 | 17720.18 | 1653.3 | 545.39 | 0 | 48553.53 | 0 | 0 | 0 | 48553.53 | 0 | 0 | 0 | 0 | 48553.53 | 221514.54 | [5 empty] | Y | DW5FS | 100% | [19 empty] | 1 | [47 empty] | 0
505075 | Arinagour SEP - replacement outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-03-24 | 2022-08-10 | 2022-11-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2093.02 | 1649.98 | 3743 | 26257.4 | 0 | 0 | 30000.4 | 0 | 0 | 0 | 0 | 30000.4 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508961 | Arinagour WTW - PLC & SCADA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-01-03 | 2023-08-07 | 2023-11-06 | 2024-10-14 | 2025-10-13 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12498 | 12498 | 487502.61 | 0 | 0 | 500000.61 | 0 | 0 | 0 | 0 | 500000.61 | 0 | [5 empty] | N | SR21_WA | 100%
502315 | Arinagour WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-07-30 | 2019-07-30 | 2019-07-30 | 2019-06-28 | 2019-06-28 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 25265.2 | 43741.87 | 4014.31 | -19843.5 | 0 | 53177.88 | 0 | 0 | 0 | 53177.88 | 0 | 0 | 0 | 0 | 53177.88 | 122419.09 | [5 empty] | N | WG1 | 100%
500821 | Arkleston Road Paisley | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-24 | 2015-09-22 | 2015-09-23 | 2018-03-07 | 2018-03-07 | Renfrewshire | 0 | 0 | 44095.56 | 8998.91 | -3488.7 | 0 | 0 | 0 | 49605.77 | 0 | 0 | 0 | 49605.77 | 0 | 0 | 0 | 0 | 49605.77 | 106252.93 | [5 empty] | N | FL_DD | 100%
501548 | Arklet Hydro Scheme | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2015-12-24 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | Falkirk | 0 | 0 | 5923 | 61503.07 | 0 | 0 | 0 | 0 | 67426.07 | 0 | 0 | 0 | 67426.07 | 0 | 0 | 0 | 0 | 67426.07 | 1525750.06 | [5 empty] | N | I2S_WI | 100%
500670 | Armadale (Phase 2) Sewer Infrastructure Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2019-12-03 | 2019-12-03 | East Lothian | 0 | 0 | 409914 | -208778.24 | 0 | 273.23 | 37.41 | 0 | 201446.39 | 0 | 0 | 0 | 201446.39 | 0 | 0 | 0 | 0 | 201446.39 | 1470767.03 | [5 empty] | N | SG5 | 100%
501713 | Armadale and Blackridge WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-07-19 | 2020-05-07 | 2020-10-26 | 2021-05-24 |  | West Lothian | 0 | 0 | 0 | 15078 | 9922 | 0 | 11561 | 146773.01 | 183334.01 | 17004.08 | 0 | 0 | 200338.08 | 0 | 0 | 0 | 0 | 200338.08 | 209381.79 | [5 empty] | N | CM_WWI | 100%
30028 | Armadale STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-16 | 2010-09-20 | 2011-03-17 | 2013-03-18 | 2013-03-18 | West Lothian | 1579435.98 | 0 | 508.04 | 0 | 0 | 0 | 0 | 0 | 508.04 | 0 | 0 | 0 | 1579944.02 | 0 | 0 | 0 | 0 | 1579944.02 | 119362.42 | [5 empty] | N | CM_WWNI | 50% | EC01A | 50%
403997 | Arnisdale WTW - Water Quality Upgrade - Cartridge & UV Option | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-12-23 | 2016-01-29 | 2016-05-03 | 2017-02-13 | 2017-03-22 | Highland | 24239 | 0 | 95460 | 368953.18 | 2495.22 | 894.07 | 0 | 0 | 467802.47 | 0 | 0 | 0 | 492041.47 | 0 | 0 | 0 | 0 | 492041.47 | 0 | [5 empty] | N | DW23 | 100%
502370 | Arnisdale WTW Crypto Risk Mitigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-07-30 | 2019-07-30 | 2019-07-30 | 2019-06-28 |  | Highland | 0 | 0 | 0 | 5006.46 | 28996.65 | 2038.63 | 19038.06 | 0 | 55079.8 | 0 | 0 | 0 | 55079.8 | 0 | 0 | 0 | 0 | 55079.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
46849 | Arnisdale WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2016-04-01 | 2014-09-17 | 2014-11-04 | 2014-11-04 | Highland | 238767.23 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 238765.23 | 0 | 0 | 0 | 0 | 238765.23 | 28761.13 | [5 empty] | N | DW23 | 100%
503470 | Arnold Clark - Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2019-04-03 | 2019-04-03 | 2019-05-08 | 2019-09-04 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 628037.83 | 0.17 | 628038 | 0 | 0 | 0 | 628038 | 0 | 0 | 0 | 0 | 628038 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510248 | Arnot Reservoir H&S Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-12-22 | 2021-06-21 | 2022-02-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10739.63 | 10739.63 | 260.37 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 11000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501721 | ARROCHAR RWP NN299038 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2027-07-07 | 2028-04-21 | 2028-08-25 | 2029-01-04 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12073.02 | 0 | 0 | 12073.02 | 0 | 0 | 0 | 0 | 12073.02 | 4989107.96 | [5 empty] | N | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 28.57% | CM_WSI | 47.62%
401323 | Asbestos Inspections | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-09-13 | 2011-02-04 | 2011-04-01 | 2017-01-31 |  | Scottish Water Wide | 1029421 | 0 | 50407 | 6006.06 | 0 | 0 | 0 | 0 | 56413.06 | 0 | 0 | 0 | 1085834.06 | 0 | 0 | 0 | 0 | 1085834.06 | 119022.58 | [5 empty] | N | CM_M&G | 100%
503835 | Ashfield Land - Topgolf Cambuslang - Glasgow Sludge M | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | GW0 |  | 2022-04-07 | 2022-04-22 | 2022-12-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1308.41 | 344.15 | 1652.56 | 0 | 0 | 0 | 1652.56 | 0 | 0 | 0 | 0 | 1652.56 | 2566127.23 | [5 empty] | N | CS23S | 100%
30030 | Ashgill STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2010-06-28 | 2010-09-06 | 2011-12-22 | 2012-01-10 | South Lanarkshire | 1787178.82 | 0 | 189.37 | 0 | 0 | 0 | 0 | 0 | 189.37 | 0 | 0 | 0 | 1787368.19 | 0 | 0 | 0 | 0 | 1787368.19 | 119362.42 | [5 empty] | N | CM_WWNI | 19.63% | EC04A | 80.37%
503405 | Ashgillhead Road Ashgill | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2018-10-12 | 2019-08-27 | 2020-01-13 | 2020-03-25 | 2020-08-04 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 40178 | 334063.56 | -8971.29 | 365270.27 | 0 | 0 | 0 | 365270.27 | 0 | 0 | 0 | 0 | 365270.27 | 180449.74 | [5 empty] | N | FL_DD | 100%
403435 | Ashgillhead Road Graham Place Ashgill | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2013-04-16 | 2019-03-06 | 2019-03-06 | 2019-01-14 | 2019-01-14 | South Lanarkshire | 120677.02 | 120677.02 | 7647.98 | 24700 | 33318.87 | 24566.06 | 3084.84 | 0 | 93317.75 | 0 | 0 | 0 | 213994.77 | 0 | 0 | 0 | 0 | 213994.77 | 209381.79 | [5 empty] | N | CM_WWI | 28% | FL_NAMED | 72%
501620 | Assess Risk Of Low Pressure To All Customers | Q&S4 | Improving drinking water availability and resilience of service | Pressure |  |  | Water | DWQR | SWD | Pressure | MS7 | 2016-02-12 | 2016-07-14 | 2016-08-15 | 2018-02-23 | 2018-04-16 | Scottish Water Wide | 0 | 0 | 319.15 | 30478.26 | 104552.28 | -1250.6 | 0 | 0 | 134099.09 | 0 | 0 | 0 | 134099.09 | 0 | 0 | 0 | 0 | 134099.09 | 233555.83 | [5 empty] | N | CS1B | 100%
403915 | Asset Capacity View | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2014-12-10 | 2015-03-09 | 2015-03-10 | 2015-05-15 | 2015-08-06 | Scottish Water Wide | 124054 | 0 | -6078.08 | 0 | 0 | 0 | 0 | 0 | -6078.08 | 0 | 0 | 0 | 117975.92 | 0 | 0 | 0 | 0 | 117975.92 | 0 | [5 empty] | N | CS18W | 100%
511041 | Asset Inspection Guidance Consultant Support | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2021-02-08 | 2021-05-24 | 2021-09-22 | 2022-03-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4039.3 | 4039.3 | 296488.79 | 0 | 0 | 300528.09 | 0 | 0 | 0 | 0 | 300528.09 | 311236.79 | [5 empty] | N | WSI | 100%
400661 | Asset Lifecycle Planning | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-02 | 2012-05-23 | 2012-05-23 | 2014-04-11 |  | Scottish Water Wide | 7108827.57 | 0 | 0 | 0 | 145.57 | 0 | 0 | 0 | 145.57 | 0 | 0 | 0 | 7108973.14 | 0 | 0 | 0 | 0 | 7108973.14 | 613322.63 | [5 empty] | N | CM_M&G | 100%
512070 | Asset Management Transformation Routemap (AMTR) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2021-05-01 |  | 2027-03-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 797.38 | 797.38 | 9047502.62 | 0 | 0 | 9048300 | 0 | 0 | 0 | 0 | 9048300 | 311236.79 | [5 empty] | N | CM_M&G | 100%
508495 | Asset Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS0 | 2020-11-04 | 2021-04-26 | 2021-08-25 | 2023-04-05 | 2023-04-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670650 | 670650 | 655657.32 | 0 | 0 | 1326307.32 | 0 | 0 | 0 | 0 | 1326307.32 | 0 | [5 empty] | N | SR21_SS | 100%
500053 | Asset Renewal - Stodswell DMA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-13 | 2016-07-13 | 2016-07-14 | 2016-07-28 |  | Dundee City | 0 | 0 | 2012.48 | 471.18 | 0 | 0 | 0 | 0 | 2483.66 | 0 | 0 | 0 | 2483.66 | 0 | 0 | 0 | 0 | 2483.66 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507608 | Assynt Back-up scada repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-07-15 | 2021-01-18 | 2021-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5872 | 5872 | 5047.35 | 0 | 0 | 10919.35 | 0 | 0 | 0 | 0 | 10919.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505244 | Assynt CWT Scour telemetry and building condition investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-02-19 | 2020-12-04 | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 766.91 | 3576.45 | 4343.36 | 744.8 | 0 | 0 | 5088.16 | 0 | 0 | 0 | 0 | 5088.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503089 | Assynt WOA - Cromarty SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2020-09-22 | 2022-04-15 | 2022-08-12 | 2023-08-03 |  | Highland | 0 | 0 | 0 | 0 | 21827.48 | 25729.12 | 940 | 5048.39 | 53544.98 | 792158.9 | 0 | 0 | 845703.88 | 0 | 0 | 0 | 0 | 845703.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403558 | Assynt WOA - Dingwall North Link Main | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2013-08-27 | 2014-08-20 | 2014-08-27 | 2015-12-21 | 2015-12-21 | Highland | 155920 | 0 | 280688 | 6104.95 | -3553.68 | 0 | 0 | 0 | 283239.27 | 0 | 0 | 0 | 439159.27 | 0 | 0 | 0 | 0 | 439159.27 | 0 | [5 empty] | N | WG5 | 100%
503659 | Assynt WOA - Easter Bennetsfield mains rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2019-09-02 | 2019-09-02 | 2019-12-09 | 2021-03-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 145499.25 | 180738.75 | 326238 | 0 | 0 | 0 | 326238 | 0 | 0 | 0 | 0 | 326238 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503063 | Assynt WOA - Maryburgh Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-10-07 | 2023-04-26 | 2023-07-18 | 2025-10-24 |  | Highland | 0 | 0 | 0 | 0 | 21627.78 | 139841.99 | -136537.85 | 35152.29 | 60084.21 | 4739915.79 | 0 | 0 | 4800000 | 0 | 0 | 0 | 0 | 4800000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403171 | Assynt WOA - Removal of Small Diameter AC Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-11 | 2013-03-11 | 2013-07-15 | 2016-03-25 |  | Highland | 734085 | 0 | 169803 | 14576.17 | 463.98 | 0 | 0 | 0 | 184843.15 | 0 | 0 | 0 | 918928.15 | 0 | 0 | 0 | 0 | 918928.15 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500753 | Assynt WOA -Mulbuie SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-08-27 | 2027-09-29 | 2027-11-23 | 2028-01-03 |  | Highland | 0 | 0 | 95506 | 39579.88 | 589.87 | 446.09 | 3650.51 | -2551.08 | 137221.27 | 1317778.73 | 0 | 0 | 1455000 | 0 | 0 | 0 | 0 | 1455000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502833 | Assynt WOA- Newmore Primary School Iron Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2018-07-17 | 2018-07-17 | 2018-07-17 | 2018-07-17 |  | Highland | 0 | 0 | 0 | 0 | 20520.17 | 2247.8 | 0 | 0 | 22767.96 | 0 | 0 | 0 | 22767.96 | 0 | 0 | 0 | 0 | 22767.96 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503402 | Assynt WOA Rosemarkie SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-01 | 2028-07-12 | 2028-11-02 | 2029-06-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 24279.1 | 4641.94 | -728.92 | 28192.12 | 693806.9 | 0 | 0 | 721999.02 | 0 | 0 | 0 | 0 | 721999.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500789 | Assynt WTW - CWT Additional Storage | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | NONINF | Supply Resilience | MS5 | 2015-09-17 | 2017-12-22 | 2017-12-22 | 2020-03-12 | 2020-08-31 | Highland | 0 | 0 | 126145 | 212052.45 | 1043502.58 | 3865138.5 | 1386085.43 | -75512.96 | 6557411 | 137604.44 | 137604.44 | 191018.3893 | 6695015.44 | 53413.9493 | 0 | 0 | 53413.9493 | 6748429.3893 | 1989709.51 | [5 empty] | Y | CS16WR | 100% | [24 empty] | 1 | [42 empty] | 0
507546 | Assynt WTW - SCADA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-10-05 | 2023-08-22 | 2024-01-30 | 2025-08-12 | 2025-11-12 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29708.65 | 29708.65 | 470411.81 | 0 | 0 | 500120.46 | 0 | 0 | 0 | 0 | 500120.46 | 0 | [5 empty] | N | SR21_WA | 100%
32111 | Assynt WTW - Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2005-09-20 | 2008-03-28 | 2008-08-18 | 2010-04-30 | 2011-03-31 | Highland | 19237618.42 | 0 | 0.58 | 29 | 0 | 0 | 0 | 0 | 29.58 | 0 | 0 | 0 | 19237648 | 0 | 0 | 0 | 0 | 19237648 | 119022.58 | [5 empty] | N | DW13 | 13.25% | DW3B | 13.25% | DW3J | 13.25% | DW4A | 13.25% | WSNI | 20% | WG1 | 27%
503258 | Athelstaneford WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-04-01 | 2028-09-13 | 2029-01-15 | 2030-01-09 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 80855.55 | 8356.93 | 475.26 | 89687.74 | 0 | 0 | 0 | 89687.74 | 0 | 0 | 0 | 0 | 89687.74 | 122419.09 | [5 empty] | N | SG1 | 100%
501551 | ATOM Holding Line - SWD | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2021-03-23 |  | 2021-03-29 |  | Scottish Water Wide | 0 | 0 | 91261.68 | -90741.92 | -519.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWI | 100%
503622 | Auchenback Treated Water Pump Station (TWP) | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-08-26 | 2020-02-26 | 2020-02-26 | 2021-10-12 | 2021-12-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 22391.3 | 51586.7 | 73978 | 746021.79 | 0 | 0 | 819999.79 | 0 | 205772.0893 | 0 | 205772.0893 | 1025771.8793 | 158124.78 | [5 empty] | N | DW25P | 100%
503662 | Auchenback WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-07-27 | 2023-03-06 | 2023-07-07 | 2025-01-30 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 33585.28 | 89786.61 | 123371.89 | 776628.11 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508147 | Auchengaich and Helensburgh Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-27 | 2021-09-02 | 2022-03-25 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6215.11 | 6215.11 | 79024.19 | 0 | 0 | 85239.3 | 0 | 0 | 0 | 0 | 85239.3 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402178 | Auchengaich Reservoir Valve Tower Access Bridge Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-03-27 | 2012-06-18 | 2014-12-08 | 2014-12-08 | Argyll and Bute-North Argyll | 350229.84 | 0 | -2299.18 | 0 | 0 | 0 | 0 | 0 | -2299.18 | 0 | 0 | 0 | 347930.66 | 0 | 0 | 0 | 0 | 347930.66 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501224 | Auchengate Dundonald Camp Replacement of Sewage Pumping Station and Rising Main | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS6 | 2016-02-22 | 2016-11-21 | 2016-11-29 | 2018-03-27 | 2018-03-27 | North Ayrshire | 0 | 0 | 74252 | 100211.8 | 293385 | 177 | 43687.45 | 85.44 | 511798.69 | 6.88 | 0 | 0 | 511805.57 | 0 | 0 | 0 | 0 | 511805.57 | 0 | [5 empty] | N | SG6 | 100%
503221 | Auchleven North ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-05-05 | 2022-08-26 | 2022-12-23 | 2023-12-20 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 80312.1 | 28838.9 | 10899 | 120050 | 541665.68 | 0 | 0 | 661715.68 | 0 | 0 | 0 | 0 | 661715.68 | 122419.09 | [5 empty] | N | SG1 | 100%
505138 | Auchnacloich mains rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-02-12 |  | 2021-08-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 9008.86 | 68627.85 | 77636.71 | 42381.57 | 0 | 0 | 120018.28 | 0 | 0 | 0 | 0 | 120018.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503162 | Auchneel WTW - Lime to Caustic | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2018-08-27 | 2018-08-27 | 2021-10-05 | 2022-08-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 37074.77 | 75374.99 | 32332.46 | 144782.22 | 1955264.82 | 0 | 0 | 2100047.04 | 0 | 0 | 399952.96 | 399952.96 | 2500000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404090 | Auchterarder Water Mains Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS4 | 2015-07-17 | 2015-07-17 | 2015-07-17 | 2021-02-19 |  | Perth and Kinross | 0 | 0 | 96394 | 4000 | 922630.13 | 0 | 0 | 561.57 | 1023585.7 | 0 | 0 | 0 | 1023585.7 | 0 | 0 | 0 | 0 | 1023585.7 | 0 | [5 empty] | N | WG5 | 100%
503282 | Auldgirth WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-01-15 | 2029-05-18 | 2030-05-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 74149.38 | 5976.45 | 0.17 | 80126 | 0 | 0 | 0 | 80126 | 0 | 0 | 0 | 0 | 80126 | 122419.09 | [5 empty] | N | SG1 | 100%
502846 | Aultbea WTW Growth - SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 0 | 20930.23 | 2496.43 | -18754.4 | 0 | 4672.26 | 0 | 0 | 0 | 4672.26 | 0 | 0 | 0 | 0 | 4672.26 | 122419.09 | [5 empty] | N | WG1 | 100%
509882 | Aviemore AC inlet main rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-25 | 2021-10-11 | 2022-05-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9229 | 9229 | 110771.23 | 0 | 0 | 120000.23 | 0 | 0 | 0 | 0 | 120000.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506758 | Aviemore final water sample tap replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-05-27 | 2020-09-07 | 2020-12-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35086.15 | 35086.15 | 0 | 0 | 0 | 35086.15 | 0 | 0 | 0 | 0 | 35086.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501188 | Aviemore WTW - Chloramination | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-12 | 2016-07-29 | 2016-11-28 | 2017-08-29 |  | Highland | 0 | 0 | 8324 | 731271.07 | 189546.62 | 17719.66 | 0 | 0 | 946861.35 | 0 | 0 | 0 | 946861.35 | 0 | 0 | 0 | 0 | 946861.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507550 | Aviemore WTW - SCADA | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-10-24 | 2024-09-09 | 2025-02-17 | 2026-08-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6160 | 6160 | 493840.6 | 0 | 0 | 500000.6 | 0 | 0 | 0 | 0 | 500000.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502562 | Aviemore WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS2 | 2021-01-19 | 2021-02-22 | 2021-04-08 | 2021-04-22 |  | Highland | 0 | 0 | 0 | 0 | 11848.31 | 1899.58 | 53889.19 | 840.01 | 68477.09 | 0 | 0 | 0 | 68477.09 | 0 | 0 | 0 | 0 | 68477.09 | 122419.09 | [5 empty] | N | WG1 | 100%
404069 | Aviemore WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS4 | 2015-03-09 | 2018-01-31 | 2018-10-31 | 2021-03-24 |  | Highland | 2936.05 | 0 | 146656.95 | 365789.82 | 451304.76 | 1134971.62 | 1187468.81 | 477185.99 | 3763377.95 | 13985 | 0 | 0 | 3780299 | 0 | 0 | 322978 | 322978 | 4103277 | 0 | [5 empty] | N | SG1 | 100%
505031 | Aviemore WwTW 2005 - Inlet Screen Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-14 | 2022-08-29 | 2022-12-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 4148.74 | 4345 | 42654.63 | 0 | 0 | 46999.63 | 0 | 0 | 0 | 0 | 46999.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506255 | Avoch DSR mains power connection and telemetry review | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-04-22 | 2022-01-10 | 2022-06-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8618 | 8618 | 41382.06 | 0 | 0 | 50000.06 | 0 | 0 | 0 | 0 | 50000.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402228 | Avondale VC and Trunk Main Diversion | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-29 | 2012-02-14 | 2012-04-10 | 2020-04-24 |  | Falkirk | 870005 | 0 | -290488 | 19584.27 | 53384.96 | 149760.77 | 14267.2 | -17174.2 | -70665 | 0 | 0 | 0 | 799340 | 0 | 0 | 0 | 0 | 799340 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501799 | AVSE PFI Edinburgh WwTW Grade 5 HC Sewer Ph2 Central & East | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-04-28 | 2019-01-29 | 2019-03-11 | 2019-09-30 |  | City of Edinburgh | 0 | 0 | 0 | 4742.5 | 13656.5 | 52483 | 29118 | 0 | 100000 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
401207 | Ayr Cluster 1 Delivery Maybole Road | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2011-07-06 | 2011-08-29 | 2013-03-28 |  | South Ayrshire | 1661943.78 | 0 | 35525.22 | 0.26 | 120084.49 | 0 | -130317.11 | 0 | 25292.86 | 0 | 0 | 0 | 1687236.64 | 0 | 0 | 0 | 0 | 1687236.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503507 | Ayr Cluster 1 Delivery Maybole Road - Additional Costs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2019-04-04 | 2019-04-04 | 2019-04-24 | 2019-04-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 138856.4 | 0 | 138856.4 | 0 | 0 | 0 | 138856.4 | 0 | 0 | 0 | 0 | 138856.4 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400288 | Ayr Cluster 3 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-17 | 2011-11-21 | 2012-02-06 | 2013-02-07 |  | Inverclyde | 629609 | 0 | 0 | -34550.53 | 27.28 | 0 | 0 | 0 | -34523.25 | 0 | 0 | 0 | 595085.75 | 0 | 0 | 0 | 0 | 595085.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506125 | Ayr First Time Provision - Cluster 1 | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWMD | Revised Bathing Waters Directive | MS0 | 2020-08-18 | 2022-11-04 | 2023-04-14 | 2024-10-25 | 2025-01-27 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21161 | 21161 | 121924 | 0 | 0 | 143085 | 0 | 33629.7901 | 0 | 33629.7901 | 176714.7901 | 1035209.71 | [5 empty] | N | EC16B | 100%
506150 | Ayr First Time Provision - Cluster 2 | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWMD | Revised Bathing Waters Directive | MS0 | 2020-08-20 | 2022-11-04 | 2023-04-14 | 2024-10-25 | 2025-01-27 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18410 | 18410 | 98674 | 0 | 0 | 117084 | 0 | 27216.8393 | 0 | 27216.8393 | 144300.8393 | 1035209.71 | [5 empty] | N | EC16B | 100%
506152 | Ayr First Time Provision - Cluster 3 | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWMD | Revised Bathing Waters Directive | MS0 | 2020-08-18 | 2022-11-04 | 2023-04-14 | 2024-10-25 | 2025-01-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15145 | 15145 | 70374 | 0 | 0 | 85519 | 0 | 19410.9679 | 0 | 19410.9679 | 104929.9679 | 1035209.71 | [5 empty] | N | EC16B | 100%
506162 | Ayr First Time Provision - Cluster 4 | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWMD | Revised Bathing Waters Directive | MS0 | 2020-08-18 | 2022-11-04 | 2023-04-14 | 2024-10-25 | 2025-01-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20011 | 20011 | 133774 | 0 | 0 | 153785 | 0 | 36898.3264 | 0 | 36898.3264 | 190683.3264 | 1035209.71 | [5 empty] | N | EC16B | 100%
401500 | Ayr Leakage Region New and Replacement Leakage Assets | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-15 | 2012-03-26 | 2012-04-30 | 2015-03-26 |  | All West Unitary Authorities | 396128 | 0 | 3750 | -1395.66 | 0 | 0 | 0 | 0 | 2354.34 | 0 | 0 | 0 | 398482.34 | 0 | 0 | 0 | 0 | 398482.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503393 | Ayr Shore Road SPS - Emergency Repairs to Transfer Pumps and Wet Well Guide Rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2018-10-02 | 2018-10-02 | 2018-10-15 | 2021-07-08 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 1244866.77 | 295564.52 | 489803.71 | 2030235 | 33574.32 | 0 | 0 | 2063809.32 | 0 | 0 | 187999.68 | 187999.68 | 2251809 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
33957 | Ayr SPS - Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2007-03-27 | 2008-02-12 | 2008-04-14 | 2010-03-31 |  | South Ayrshire | 8357062.73 | 0 | 48495.27 | 102708.9 | 0 | 0 | 0 | 0 | 151204.17 | 0 | 0 | 0 | 8508266.9 | 0 | 0 | 0 | 0 | 8508266.9 | 299983.07 | [5 empty] | N | WWI | 3.82% | WWNI | 96.18%
500704 | Ayre Road WWPS 1997 HY448112 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-06-12 | 2020-10-06 | 2020-10-27 | 2020-10-06 |  | Orkney Islands | 0 | 0 | 56471 | 29804 | 31758.11 | 5554.53 | -154.14 | 0 | 123433.5 | 0 | 0 | 0 | 123433.5 | 0 | 0 | 0 | 0 | 123433.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502834 | Ayrshire Bathing Water Solution Development (IR18) | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWMD | Revised Bathing Waters Directive | MS3 | 2020-05-06 | 2020-06-09 | 2019-12-09 | 2023-12-13 | 2024-03-14 | East Ayrshire | 0 | 0 | 0 | 0 | 148647.66 | 278937.35 | 194052.43 | 170828.57 | 792466 | 154942.38 | 0 | 0 | 947408.38 | 0 | 42737.1126 | 0 | 42737.1126 | 990145.4926 | 1035209.71 | [5 empty] | N | EC16B | 100%
509928 | Ayrshire Reservoir vegetation clearance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-11-24 | 2021-05-21 | 2022-01-03 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2943.93 | 2943.93 | 42056.07 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 45000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500523 | Ayrshire Strategic Resilience | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water | DWQR | WINF | Exceptional Capital Maintenance | MS3 | 2016-11-02 | 2021-03-29 | 2021-03-29 | 2023-09-20 | 2023-12-20 | South Ayrshire | 0 | 0 | 331276.92 | 292053.08 | 753269 | 750440.04 | 3902464.03 | 11732907.24 | 17762410.31 | 72577765.69 | 72577765.688 | 94986804.9705 | 90340176 | 22409039.2825 | 0 | 0 | 22409039.2825 | 112749215.2825 | 0 | [5 empty] | Y | SR15_EXC_EXC | 100% | [24 empty] | 1 | [42 empty] | 0
502278 | Ayrshire Strategic Resilience- Highlees DSR | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water | DWQR | WINF | Exceptional Capital Maintenance | MS5 | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-27 | 2019-03-29 | East Ayrshire | 0 | 0 | 0 | 1776359 | 41280859 | 14894029.84 | 2280402.37 | 1344374.9 | 61576025.11 | -231692.37 | -231692.3717 | -321628.4565 | 61344332.74 | -89936.0848 | 0 | 0 | -89936.0848 | 61254396.6552 | 0 | [5 empty] | N | SR15_EXC_EXC | 100%
403887 | Ayrshire Water Mains Refurbishment - Afton | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2014-07-10 | 2015-01-23 | 2015-01-26 | 2016-08-12 |  | East Ayrshire | 1500715 | 0 | 2698535 | 666534 | -26022 | -157670.29 | -13685.22 | 36.94 | 3167728.43 | 0 | 0 | 0 | 4668443.43 | 0 | 0 | 0 | 0 | 4668443.43 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403889 | Ayrshire Water Mains Refurbishment - Bradan A | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2014-07-10 | 2015-05-25 | 2015-06-25 | 2018-08-20 |  | South Ayrshire | 114943.4 | 0 | 3927523.6 | 3535670 | 2542941.82 | 244235.1 | 159095.51 | -177981.34 | 10231484.69 | 0 | 0 | 0 | 10346428.09 | 0 | 0 | 0 | 0 | 10346428.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403888 | Ayrshire Water Mains Refurbishment - Bradan B | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2014-07-10 | 2015-12-03 | 2015-12-07 | 2018-07-30 |  | South Ayrshire | 298158.19 | 0 | 1864758.81 | 5341320 | 4501579.63 | 135118.22 | 436.9 | -23715.05 | 11819498.51 | 0 | 0 | 0 | 12117656.7 | 0 | 0 | 0 | 0 | 12117656.7 | 311236.79 |  |  |  |  | 90027.8051 | N | CM_WSI | 100%
403890 | Ayrshire Water Mains Refurbishment - Dougliehill | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2014-07-10 | 2015-03-30 | 2015-04-16 | 2017-05-10 |  | Inverclyde | 146251 | 0 | 718528 | 79562.03 | -21334.5 | -267080.25 | 23967.74 | -39064.92 | 494578.11 | 0 | 0 | 0 | 640829.11 | 0 | 0 | 0 | 0 | 640829.11 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403891 | Ayrshire Water Mains Refurbishment - Kaim Lochwinnoch | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2014-07-10 | 2015-03-30 | 2015-03-30 | 2017-05-18 |  | Renfrewshire | 615298 | 0 | 1495271 | 199767.38 | -39500.79 | -160426.72 | 21963.22 | -62462.54 | 1454611.56 | 0 | 0 | 0 | 2069909.56 | 0 | 0 | 0 | 0 | 2069909.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403863 | Ayrshire Water Quality Sampling - Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-11 | 2014-06-11 | 2014-06-11 | 2017-03-09 |  | South Ayrshire | 9350 | 0 | 40650 | -43941.21 | -1071.73 | 0 | 0 | 0 | -4362.94 | 0 | 0 | 0 | 4987.06 | 0 | 0 | 0 | 0 | 4987.06 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403568 | Baberton Square Juniper Green Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2013-08-30 | 2015-01-20 | 2015-01-26 | 2015-03-30 | 2015-03-30 | City of Edinburgh | 143194 | 143194 | 16786.07 | -0.01 | 783.45 | 0 | 0 | 0 | 17569.51 | 0 | 0 | 0 | 160763.51 | 0 | 0 | 0 | 0 | 160763.51 | 372507.62 | [5 empty] | N | FL_NAMED | 100%
502600 | Back Tolsta- Main out form North Lochs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS3 | 2016-05-18 | 2019-09-30 | 2019-09-30 | 2022-01-10 | 2022-04-11 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 232046 | 573417.96 | 3072300.04 | 2678747.76 | 6556511.76 | 2774541.33 | 2774541.33 | 3566186.4114 | 9331053.09 | 791645.0814 | 0 | 0.0025 | 791645.0839 | 10122698.1739 | 4534056.88 | [5 empty] | Y | DW25P | 10% | DW3B | 90% | [16 empty] | 1 | [48 empty] | 0
500795 | Backies RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-09-25 | 2019-02-15 | Highland | 0 | 0 | 89774 | 110985.97 | 186230.4 | 80328.35 | 29586.34 | 552.4 | 497457.47 | 0 | 0 | 0 | 497457.47 | 0 | 0 | 0 | 0 | 497457.47 | 810447.22 | [5 empty] | N | DW5FS | 100%
403721 | Backies WOA - Bridge of Horn SR Outlet Rehab - Pitfure and Knockarthur WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-12 | 2014-05-27 | 2014-06-30 | 2015-01-05 |  | Highland | 309486.23 | 0 | 811.81 | 342.64 | 0 | 0 | 0 | 0 | 1154.45 | 0 | 0 | 0 | 310640.68 | 0 | 0 | 0 | 0 | 310640.68 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403383 | Backies WOA - Golspie Secondary Link Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-07 | 2013-05-13 | 2013-09-18 | 2014-05-12 |  | Highland | 332839 | 0 | 0 | -159.47 | 0 | 0 | 0 | 0 | -159.47 | 0 | 0 | 0 | 332679.53 | 0 | 0 | 0 | 0 | 332679.53 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403199 | Backies WOA - Navidale Helmsdale Rehab-Network Improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-12-17 | 2014-02-21 | 2014-06-30 | 2017-09-26 |  | Highland | 322176 | 0 | 23702 | 35688.92 | 20303.5 | -49.17 | 0 | 0 | 79645.25 | 0 | 0 | 0 | 401821.25 | 0 | 0 | 0 | 0 | 401821.25 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504389 | Backies WOA - Park Terrace Brora - Quality & UITS Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-01-22 | 2021-03-02 | 2021-06-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 104819 | 105119 | 0 | 0 | 0 | 105119 | 0 | 0 | 0 | 0 | 105119 | 311236.79 | [5 empty] | N | WSI | 100%
501259 | Backies WOA Brora Dalchalm & Victoria Road Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2016-02-19 | 2018-10-24 | 2018-10-29 | 2021-06-15 |  | Highland | 0 | 0 | 1308.41 | 2087 | 69137.59 | 833023.6 | 278974.21 | 6848.47 | 1191379.28 | 85789.9 | 0 | 0 | 1277169.18 | 0 | 0 | 22830.82 | 22830.82 | 1300000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501198 | Backies WTW Dosing & Chemical Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-04-25 | 2027-05-25 | 2027-08-04 | 2028-04-24 |  | Highland | 0 | 0 | 0 | 86866.37 | 0 | 0 | 101.4 | 0 | 86967.77 | 749032.2 | 0 | 0 | 835999.97 | 0 | 0 | 0 | 0 | 835999.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402905 | Backies WTW Loch Lunndaidh RWM Rehab and Abstraction Chamber Replace | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-11 | 2013-07-17 | 2013-10-28 | 2015-02-09 |  | Highland | 782545.41 | 0 | 7794.59 | -3471.12 | 0 | 0 | 0 | 0 | 4323.47 | 0 | 0 | 0 | 786868.88 | 0 | 0 | 0 | 0 | 786868.88 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402276 | Backies WTW Replacement Lime Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-08-11 | 2013-11-25 | 2014-03-31 | 2015-01-16 |  | Highland | 540209.07 | 0 | 337.5 | 277.23 | 0 | 0 | 0 | 0 | 614.73 | 0 | 0 | 0 | 540823.8 | 0 | 0 | 0 | 0 | 540823.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403266 | Backlog of missing M&E plant | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-01 | 2013-07-03 | 2013-07-03 | 2016-08-01 |  | All East Unitary Authorities | 438898 | 0 | -26250.02 | 60 | 0 | 0 | 0 | 0 | -26190.02 | 0 | 0 | 0 | 412707.98 | 0 | 0 | 0 | 0 | 412707.98 | 90601.29 | [5 empty] | N | CM_WWI | 100%
500956 | Backup Restore and Archive | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-05 | 2016-09-29 | 2016-09-29 | 2017-11-15 |  | Scottish Water Wide | 0 | 0 | 165092 | 1079630.52 | 152559.98 | 0 | 0 | 0 | 1397282.5 | 0 | 0 | 0 | 1397282.5 | 0 | 0 | 0 | 0 | 1397282.5 | 306661.32 | [5 empty] | N | CM_M&G | 100%
510004 | Backwater Reservoir - Drainange Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-30 | 2021-05-21 | 2022-01-03 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5353.3 | 5353.3 | 74797.46 | 0 | 0 | 80150.76 | 0 | 0 | 0 | 0 | 80150.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509469 | Backwater Reservoir - Valve Tower and Spillway Channel Drone Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-11-04 | 2021-05-21 | 2022-01-03 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969 | 969 | 3031.39 | 0 | 0 | 4000.39 | 0 | 0 | 0 | 0 | 4000.39 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401361 | Backwater Reservoir Spillway Joint Sealant Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-10 | 2015-06-25 | 2015-06-03 | 2017-03-01 |  | Angus | 296794 | 0 | 724855 | 68348.69 | 1190.99 | -1006.02 | 0 | 0 | 793388.66 | 0 | 0 | 0 | 1090182.66 | 0 | 0 | 0 | 0 | 1090182.66 | 119022.58 | [5 empty] | N | CM_WSI | 100%
507119 | Backwater Spillway Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-06-16 |  | 2021-11-26 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644.32 | 644.32 | 29412.13 | 0 | 0 | 30056.45 | 0 | 0 | 0 | 0 | 30056.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502844 | Badachro WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2020-05-22 |  | Highland | 0 | 0 | 0 | 0 | 21033.13 | 687.48 | 0 | -20361.16 | 1359.45 | 0 | 0 | 0 | 1359.45 | 0 | 0 | 0 | 0 | 1359.45 | 122419.09 | [5 empty] | N | WG1 | 100%
501197 | Badachro WTW Intake Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-12 | 2016-11-30 | 2016-12-08 | 2018-09-07 |  | Highland | 0 | 0 | 9849 | 60703.23 | 162325.13 | 37101.64 | -6572.92 | 57.46 | 263463.54 | 0 | 0 | 0 | 263463.54 | 0 | 0 | 0 | 0 | 263463.54 | 119022.58 | [5 empty] | N | CM_WSI | 100%
45307 | Badachro WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-11 | 2011-07-22 | 2012-01-19 | 2012-03-14 | Highland | 176835.3 | 0 | -135.35 | 0 | 0 | 0 | 0 | 0 | -135.35 | 0 | 0 | 0 | 176699.95 | 0 | 0 | 0 | 0 | 176699.95 | 28761.13 | [5 empty] | N | DW13 | 100%
502843 | Badcaul WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 0 | 20930.23 | 902.22 | -20280.63 | 0 | 1551.82 | 0 | 0 | 0 | 1551.82 | 0 | 0 | 0 | 0 | 1551.82 | 122419.09 | [5 empty] | N | WG1 | 100%
500226 | Badentinan - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS6 | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-09-30 | 2021-03-31 | Moray | 0 | 0 | 1449 | 0 | 43421 | 63943.12 | 434248.89 | 4062.97 | 547124.98 | 0 | 0 | 0 | 547124.98 | 0 | 0 | 0 | 0 | 547124.98 | 835826.18 | [5 empty] | Y | DW5FS | 10.4% | DW5 | 89.6% | [17 empty] | 1 | [47 empty] | 0
511450 | Badentinan Reservoir - Drainage Investigations | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 |  | 2021-05-24 | 2021-08-13 | 2022-03-28 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.3 | 13.3 | 10000 | 0 | 0 | 10013.3 | 0 | 0 | 0 | 0 | 10013.3 | 0 | [5 empty] | N | SR21_WA | 100%
500844 | Badentinan RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-07-27 | 2018-06-28 | 2018-12-04 | 2019-12-23 | 2020-10-28 | Moray | 0 | 0 | 19062.39 | 9488.15 | 41920.38 | 219638.01 | 145889.56 | 59063.44 | 495061.93 | -5615.42 | -5615.42 | -7795.159 | 489446.51 | -2179.739 | 0 | 0 | -2179.739 | 487266.771 | 1051546.41 | [5 empty] | N | DW5FS | 100%
403197 | Badentinan Wellfield Control Panel Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-16 | 2013-08-19 | 2013-11-01 | 2015-02-20 |  | Moray | 936364 | 0 | 44163.16 | 812.76 | 0 | 0 | 0 | 0 | 44975.92 | 0 | 0 | 0 | 981339.92 | 0 | 0 | 0 | 0 | 981339.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503419 | Badentinan WTW - Interim THM and Cryptosporidium measures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2018-10-31 | 2020-07-29 | 2020-09-28 | 2021-03-19 |  | Moray | 0 | 0 | 0 | 0 | 0 | 34589.25 | -8727.56 | 122613.31 | 148475 | 15330.7 | 0 | 0 | 163805.7 | 0 | 0 | 0 | 0 | 163805.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501218 | Badentinan WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS3 | 2018-03-28 | 2020-09-28 | 2020-12-07 | 2021-08-27 | 2021-11-19 | Aberdeenshire | 0 | 0 | 4604.65 | 1324.77 | 6865.27 | 872.11 | 10495.62 | 32642.59 | 56805 | 50378.99 | 50378.99 | 74962.3015 | 107183.99 | 24583.3115 | 0 | 0 | 24583.3115 | 131767.3015 | 319550.12 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
509530 | Badgemaker Replacement project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS2 | 2020-11-16 | 2020-11-30 | 2021-05-05 | 2021-06-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237794 | 237794 | 75745.1 | 0 | 0 | 313539.1 | 0 | 0 | 0 | 0 | 313539.1 | 613322.63 | [5 empty] | N | CM_M&G | 100%
46256 | Badinsgill Reservoir - Various repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-11-13 | 2010-06-28 | 2010-11-02 | 2012-02-14 |  | Scottish Borders | 280871.42 | 0 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 280871.55 | 0 | 0 | 0 | 0 | 280871.55 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501526 | Bairdsknowe SR Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-12-22 | 2028-07-07 | 2028-08-07 | 2029-03-30 |  | East Renfrewshire | 0 | 0 | 0 | 2612.08 | 52.07 | -27.84 | 3387.63 | -3430.5 | 2593.44 | 342471.64 | 0 | 0 | 345065.08 | 0 | 0 | 0 | 0 | 345065.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402853 | Balaclava Quay - Shore Street Fraserburgh | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2014-08-26 | 2014-08-26 | 2014-08-29 | 2014-09-01 | Aberdeenshire | 22777.22 | 0 | -571.18 | 0 | 0 | 0 | 0 | 0 | -571.18 | 0 | 0 | 0 | 22206.04 | 0 | 0 | 0 | 0 | 22206.04 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
502760 | Balado ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-05-31 | 2018-05-31 | 2018-05-31 | 2018-05-31 | 2018-05-31 | Perth and Kinross | 0 | 0 | 0 | 0 | 34831.63 | 14.27 | 0 | 0 | 34845.9 | 0 | 0 | 0 | 34845.9 | 0 | 0 | 0 | 0 | 34845.9 | 122419.09 | [5 empty] | N | SG1 | 100%
507830 | Balallan East ST - Access Improvements | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-09-08 | 2024-04-02 | 2024-06-27 | 2025-05-07 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37332 | 37332 | 362667.76 | 0 | 0 | 399999.76 | 0 | 0 | 0 | 0 | 399999.76 | 90601.29 | [5 empty] | N | WWNI | 100%
507831 | Balallan Mid ST - Access Improvements | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-09-08 | 2024-04-02 | 2024-06-27 | 2025-05-07 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36691.76 | 36691.76 | 363354.98 | 0 | 0 | 400046.74 | 0 | 0 | 0 | 0 | 400046.74 | 90601.29 | [5 empty] | N | WWNI | 100%
45547 | Balbeggie STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-03-24 | 2011-07-25 | 2012-03-22 | 2012-03-27 | Perth and Kinross | 491171.2 | 0 | 30.72 | 0 | 0 | 0 | 0 | 0 | 30.72 | 0 | 0 | 0 | 491201.92 | 0 | 0 | 0 | 0 | 491201.92 | 28761.13 | [5 empty] | N | WQ01 | 100%
503320 | Balbeggie WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-06-13 | 2025-04-04 | 2025-07-04 | 2026-08-07 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 79559.16 | 5106.35 | 18086.49 | 102752 | 1897247.39 | 0 | 0 | 1999999.39 | 0 | 0 | 0 | 0 | 1999999.39 | 122419.09 | [5 empty] | N | SG1 | 100%
400056 | Balfron STW Refurb STW002010 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2011-02-28 | 2011-02-28 | 2011-02-28 | 2011-02-28 | Stirling | 30347.9 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0 | 30349 | 0 | 0 | 0 | 0 | 30349 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508045 | Balgillie Reservoir MIOS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-08-31 | 2020-11-23 | 2021-11-29 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50326 | 50326 | 99674.26 | 0 | 0 | 150000.26 | 0 | 0 | 0 | 0 | 150000.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505794 | Balgillie Reservoir Perimeter Fence Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-31 | 2021-04-19 | 2021-06-25 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4938 | 4938 | 862.07 | 0 | 0 | 5800.07 | 0 | 0 | 0 | 0 | 5800.07 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507117 | Balgillie Reservoir Tower Bridge - H&S works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-06-16 |  | 2021-07-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17896.92 | 17896.92 | 3096.39 | 0 | 0 | 20993.31 | 0 | 0 | 0 | 0 | 20993.31 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401585 | Balgray Reservoir - Seepage QH | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-08 | 2011-05-03 | 2011-06-13 | 2014-01-17 | 2014-01-17 | East Renfrewshire | 443245 | 0 | -532.49 | 0 | 0 | 0 | 0 | 0 | -532.49 | 0 | 0 | 0 | 442712.51 | 0 | 0 | 0 | 0 | 442712.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503601 | Balivanich WwTW - Replacement Dewaterer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2020-07-27 | 2020-09-18 | 2020-10-06 | 2021-01-27 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 733.74 | 355450.26 | 356184 | 0 | 0 | 0 | 356184 | 0 | 0 | 0 | 0 | 356184 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503401 | Balkiellie TWS - QUALITY (Reduction of risk identified in Drinking Water Safety Plan - Transmission) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS7 | 2019-02-07 | 2020-03-10 | 2020-03-31 | 2020-03-10 | 2020-03-31 | Angus | 0 | 0 | 0 | 0 | 0 | 37986.64 | -29284.19 | 0 | 8702.45 | 0 | 0 | 0 | 8702.45 | 0 | 0 | 0 | 0 | 8702.45 | 466277.79 | [5 empty] | N | DW25T | 100%
500845 | Ballachulish RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-11-04 | 2016-03-25 | 2017-01-02 | 2018-03-31 | 2018-06-30 | Highland | 0 | 0 | 3166.17 | 9897.5 | 37880.89 | 0 | 0 | -4609.07 | 46335.49 | 0 | 0 | 0 | 46335.49 | 0 | 0 | 0 | 0 | 46335.49 | 15535.81 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 39.24 | [43 empty] | 0
501064 | Ballater WTW - Source | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-07-02 | 2028-12-07 | 2029-04-04 | 2030-03-25 |  | Aberdeenshire | 0 | 0 | 16952.66 | 1001.08 | 272.7 | 631.84 | 0 | 0 | 18858.28 | 981124.28 | 0 | 0 | 999982.56 | 0 | 0 | 0 | 0 | 999982.56 | 119022.58 | [5 empty] | N | CM_WSI | 100%
503270 | Ballater WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-03-08 | 2025-01-13 | 2025-04-17 | 2026-07-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 79664.11 | 5416.78 | 19897.11 | 104978 | 2895021.81 | 0 | 0 | 2999999.81 | 0 | 0 | 0 | 0 | 2999999.81 | 122419.09 | [5 empty] | N | SG1 | 100%
403586 | Ballo Reservoir - Emergency Valve Tower Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-09-25 | 2014-02-12 | 2014-02-12 | 2016-09-26 | 2014-08-05 | Scottish Water Wide | 836876 | 0 | 16443 | 5128.34 | 48.04 | 0 | 0 | 0 | 21619.38 | 0 | 0 | 0 | 858495.38 | 0 | 0 | 0 | 0 | 858495.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508807 | Ballygrant WTW - PLC & SCADA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-03-30 | 2023-11-01 | 2024-01-31 | 2025-01-08 | 2026-01-07 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5588.29 | 5588.29 | 494411.72 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WA | 100%
502870 | Ballygrant WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-26 | 2020-04-08 | 2020-04-08 | 2020-05-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 21238 | 1850.55 | -19376.24 | 36.94 | 3749.25 | 0 | 0 | 0 | 3749.25 | 0 | 0 | 0 | 0 | 3749.25 | 122419.09 | [5 empty] | N | WG1 | 100%
402008 | Balmaha | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-05-27 | 2014-07-31 | 2014-09-08 | 2015-03-11 | 2015-03-23 | Stirling | 744278.86 | 0 | -1397.43 | 36.75 | 0 | 0 | 0 | 0 | -1360.68 | 0 | 0 | 0 | 742918.18 | 0 | 0 | 0 | 0 | 742918.18 | 0 | [5 empty] | N | WQ01 | 100%
503108 | Balmaha WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-04-01 | 2023-01-23 | 2023-04-21 | 2024-05-22 |  | Stirling | 0 | 0 | 0 | 0 | 30976.74 | 52621.46 | 53165.33 | 107402.21 | 244165.74 | 2089766.26 | 0 | 0 | 2333932 | 0 | 0 | 0 | 0 | 2333932 | 122419.09 | [5 empty] | N | SG1 | 100%
505276 | Balmedie Eventide SPS - Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-03-17 | 2020-10-26 | 2020-12-11 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 188.79 | 40772.62 | 40961.41 | 0 | 0 | 0 | 40961.41 | 0 | 0 | 0 | 0 | 40961.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502813 | Balmedie WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-04-01 | 2023-07-21 | 2023-10-12 | 2025-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 67136.2 | 15448.8 | 33214.61 | 191378.38 | 307178 | 4230137.37 | 0 | 0 | 4537315.37 | 0 | 0 | 0 | 0 | 4537315.37 | 122419.09 | [5 empty] | N | SG1 | 100%
507222 | Balmichael BH No. 5 - CCTV Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-25 | 2021-04-01 | 2021-11-12 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1914.09 | 1914.09 | 38085.91 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500002 | Balmichael RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2015-11-23 | 2017-12-21 | 2018-03-20 | 2020-01-17 | 2020-11-30 | North Ayrshire | 0 | 0 | 44466 | 14100 | 71361 | 130509.27 | 53423.75 | -17525.02 | 296335 | 2500 | 2500 | 3470.4256 | 298835 | 970.4256 | 0 | 0 | 970.4256 | 299805.4256 | 1048999.43 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 73.41 | [43 empty] | 0
502094 | Balmichael WTW | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2019-05-22 | 2019-05-22 | 2019-09-26 | 2019-09-27 |  | North Ayrshire | 0 | 0 | 16326 | 1157.27 | 0 | 833.51 | -9538.49 | 0 | 8778.29 | 0 | 0 | 0 | 8778.29 | 0 | 0 | 0 | 0 | 8778.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502564 | Balmichael WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-06-29 | 2020-06-29 | 2021-01-11 | 2021-01-29 |  | North Ayrshire | 0 | 0 | 0 | 20930.23 | 1679.04 | 6320.73 | 14086.16 | -1700.11 | 41316.05 | 0 | 0 | 0 | 41316.05 | 0 | 0 | 0 | 0 | 41316.05 | 122419.09 | [5 empty] | N | WG1 | 100%
46837 | Balmichael WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-09-14 | 2011-10-17 | 2015-08-20 | 2016-12-20 | North Ayrshire | 3449705.96 | 0 | 79678.71 | 16329.86 | -2539.08 | 0 | 0 | 0 | 93469.49 | 0 | 0 | 0 | 3543175.45 | 0 | 0 | 0 | 0 | 3543175.45 | 28761.13 |  |  |  |  | 50776.882 | N | DW23 | 100%
501196 | Balmoor (Forehill WTW) RWP - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-09-23 | 2018-02-26 | 2018-02-26 | 2018-03-06 |  | Aberdeenshire | 0 | 0 | 6087.85 | 17675.82 | -1294.42 | 0 | 0 | 0 | 22469.25 | 0 | 0 | 0 | 22469.25 | 0 | 0 | 0 | 0 | 22469.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500846 | Balmore A RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-09-20 | 2017-12-20 | 2017-12-20 | 2019-09-24 | 2020-05-21 | North Lanarkshire | 0 | 0 | 12698.42 | 12928.34 | 14062.57 | 144909.81 | 15867.19 | -32630.33 | 167836 | 0 | 0 | 0 | 167836 | 0 | 0 | 0 | 0 | 167836 | 701949.75 | [5 empty] | N | DW5FS | 100%
500847 | Balmore C5 South RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-07-27 | 2018-09-28 | 2018-10-01 | 2019-01-31 | 2019-08-31 | Glasgow City | 0 | 0 | 27600 | 11361.76 | 124769.24 | 351996.39 | -137051.88 | 16956.23 | 395631.74 | 0 | 0 | 0 | 395631.74 | 0 | 0 | 0 | 0 | 395631.74 | 1140801.77 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 5.71 | [43 empty] | 0
500227 | Balmore E - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS6 | 2015-03-27 | 2016-03-30 | 2016-04-20 | 2017-02-07 | 2020-01-31 | West Lothian | 0 | 0 | 6098 | 30706.71 | 31617.25 | 18440.5 | 184572.96 | -7089.14 | 264346.28 | 0 | 0 | 0 | 264346.28 | 0 | 0 | 0 | 0 | 264346.28 | 1096553.94 | [5 empty] | N | DW5FS | 29.49% | DW5MR | 70.51%
500228 | Balmore F - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS6 | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2019-12-23 | 2020-03-31 | West Lothian | 0 | 0 | 104446 | 1064630 | 1792108 | 946308.69 | 241491.05 | -47325.31 | 4101658.43 | 0 | 0 | 0 | 4101658.43 | 0 | 0 | 0 | 0 | 4101658.43 | 2734927.74 | [5 empty] | N | DW5 | 100%
500848 | Balmore F RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-03-31 | 2017-12-19 | 2018-03-20 | 2019-03-01 | 2019-05-14 | West Lothian | 0 | 0 | 5413.63 | 8820.37 | 760.73 | 113256.16 | 4034.81 | -33530.94 | 98754.76 | 0 | 0 | 0 | 98754.76 | 0 | 0 | 0 | 0 | 98754.76 | 217432.61 | [5 empty] | N | DW5FS | 100%
400109 | Balmore Gowanbank Pumps Crawhill Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-23 | 2010-02-22 | 2010-11-15 | 2012-09-26 |  | Falkirk | 2225356 | 0 | 197289 | 1219597.9 | 1633871.74 | 799552.75 | 3232.59 | -86.38 | 3853457.59 | 0 | 0 | 0 | 6078813.59 | 0 | 0 | 0 | 0 | 6078813.59 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502430 | Balmore Pipe Bridges | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2018-01-22 | 2022-08-22 | 2022-10-04 | 2023-06-30 |  | East Dunbartonshire | 0 | 0 | 0 | 23738.26 | 20517.34 | 84319.04 | 216095.09 | 97741.64 | 442411.37 | 7557588.64 | 0 | 0 | 8000000 | 0 | 0 | 0 | 0 | 8000000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502783 | Balmore Pipebridge Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-09-06 | 2018-12-20 | 2019-01-15 | 2022-06-23 |  | Glasgow City | 0 | 0 | 0 | 0 | 85000 | 397484.24 | 953166.18 | 83543.43 | 1519193.85 | 394236.85 | 0 | 0 | 1913430.7 | 0 | 0 | 292321.3 | 292321.3 | 2205752 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501082 | Balmore South Region Tweed WOA Dechmont WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-04-28 | 2017-02-15 | 2017-02-15 | 2017-02-15 |  | West Lothian | 0 | 0 | 14760 | -11329.46 | 1973.72 | 0 | 0 | 0 | 5404.26 | 0 | 0 | 0 | 5404.26 | 0 | 0 | 0 | 0 | 5404.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501081 | Balmore South Region Tweed WOA East Craigs WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-06 | 2028-07-17 | 2028-08-28 | 2029-03-28 |  | West Lothian | 0 | 0 | 59472 | -12687 | 0 | -2719 | 2931.93 | 0 | 46997.93 | 273468.19 | 0 | 0 | 320466.12 | 0 | 0 | 0 | 0 | 320466.12 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506259 | Balmore TWP - Bankell Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-04-24 | 2020-09-10 | 2021-03-08 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40943.38 | 40943.38 | 556.62 | 0 | 0 | 41500 | 0 | 0 | 0 | 0 | 41500 | 119022.58 | [5 empty] | N | Wa6 | 100%
500035 | Balmore WTW - Filter Refurbishment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS6 | 2016-04-01 | 2017-03-22 | 2017-03-22 | 2019-12-31 | 2020-03-31 | East Dunbartonshire | 0 | 0 | 500406 | 654504.78 | 1503828.33 | 1530676.44 | 102612.45 | -21462 | 4270566 | 18299.65 | 16738.6899 | 23236.1512 | 4288865.65 | 6497.4613 | 0 | 0 | 6497.4613 | 4295363.1113 | 1048868.51 | [5 empty] | Y | CM_WSNI | 8.53% | DW25P | 91.47% | [19 empty] | 1 | [45 empty] | 0
502550 | Balmore WTW - Garbethill & Drumbow SRs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2018-04-30 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | North Lanarkshire | 0 | 0 | 0 | 0 | 17909.57 | 455.88 | 0 | 0 | 18365.44 | 0 | 0 | 0 | 18365.44 | 0 | 0 | 0 | 0 | 18365.44 | 929845.93 | [5 empty] | N | DW25P | 100%
507285 | Balmore WTW - Replacement Lime dosing lines | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-07-03 | 2021-03-10 | 2021-08-27 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34730 | 34730 | 36119.93 | 0 | 0 | 70849.93 | 0 | 0 | 0 | 0 | 70849.93 | 119022.58 | [5 empty] | N | WSNI | 100%
507988 | Balmore WTW Building & Site Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2020-08-04 | 2021-05-10 | 2021-07-12 | 2022-03-07 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24824.83 | 24824.83 | 335228.34 | 0 | 0 | 360053.17 | 0 | 0 | 0 | 0 | 360053.17 | 119022.58 | [5 empty] | N | Wa6 | 100%
401053 | Balmore WTW Filter Refurb Media Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | [5 empty] | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 206.4 | 0 | 0 | 206.4 | 0 | 0 | 0 | 206.4 | 0 | 0 | 0 | 0 | 206.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502210 | Balquhidder WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-05-11 | 2016-09-13 | 2016-09-13 | 2017-05-05 | 2017-10-11 | Stirling | 0 | 0 | 0 | 44.15 | 0 | 0 | 0 | 0 | 44.15 | 0 | 0 | 0 | 44.15 | 0 | 0 | 0 | 0 | 44.15 | 270378.76 | [5 empty] | N | DW25P | 100%
506698 | Banchory Arbeadie DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-24 | 2021-08-06 | 2022-03-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000.03 | 0 | 0 | 150000.03 | 0 | 0 | 0 | 0 | 150000.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402600 | Banchory Raemoir Rd WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-27 | 2012-12-13 | 2013-01-21 | 2013-10-01 |  | All East Unitary Authorities | 87764 | 0 | -395.66 | 0 | 0 | 0 | 0 | 0 | -395.66 | 0 | 0 | 0 | 87368.34 | 0 | 0 | 0 | 0 | 87368.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501021 | Banchory WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2018-01-09 | 2020-05-01 | 2020-05-01 | 2022-03-31 |  | Aberdeenshire | 0 | 0 | 43768.74 | 76143.85 | 51038.96 | 397233.62 | 510192.87 | 2215084.96 | 3293463 | 2599026 | 0 | 0 | 5892489 | 0 | 0 | 1012944 | 1012944 | 6905433 | 213020.38 | [5 empty] | N | CM_WWNI | 4% | SG1 | 96%
402856 | Bank Street Cupar | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2014-08-28 | 2014-10-27 | 2015-01-28 | 2015-02-02 | Fife | 140163 | 0 | 17498.16 | 0 | 0 | 0 | 0 | 0 | 17498.16 | 0 | 0 | 0 | 157661.16 | 0 | 0 | 0 | 0 | 157661.16 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
503930 | Bannockburn SST Replacement Storm Return Screw Pump | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2019-11-29 |  | 2020-08-14 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 7042.06 | 3249.94 | 10292 | 89707.84 | 0 | 0 | 99999.84 | 0 | 0 | 0 | 0 | 99999.84 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501160 | Barassie SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-12-10 | 2017-03-28 | 2017-06-30 | 2019-07-22 |  | South Ayrshire | 0 | 0 | 9030.91 | 262407.05 | 871421.04 | 793882 | 39030 | 53.4 | 1975824.4 | 2400 | 0 | 0 | 1978224.4 | 0 | 0 | 0 | 0 | 1978224.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502896 | Barcraigs Drawdown Capacity Enhancement (MIoS) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-09-18 | 2020-11-25 | 2021-02-15 | 2021-10-07 |  | Renfrewshire | 0 | 0 | 0 | 0 | 21315.78 | 7847.15 | 92259.55 | 448169.52 | 569592 | 1054927.2 | 0 | 0 | 1624519.2 | 0 | 0 | 239240.8 | 239240.8 | 1863760 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402358 | Barcraigs Impounding Resevoir - Resmix System | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-09-20 | 2012-03-28 | 2012-04-27 | 2013-06-26 |  | Renfrewshire | 418100 | 0 | 867.57 | 0 | 0 | 0 | 0 | 0 | 867.57 | 0 | 0 | 0 | 418967.57 | 0 | 0 | 0 | 0 | 418967.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46244 | Barcraigs Longpark embankment - Valve Chamber | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-12-11 | 2010-09-29 | 2010-10-28 | 2011-01-19 |  | Renfrewshire | 30696.12 | 0 | 5455.88 | 0 | 0 | 0 | 0 | 0 | 5455.88 | 0 | 0 | 0 | 36152 | 0 | 0 | 0 | 0 | 36152 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500655 | Barmore Road Tarbert | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-04-27 | 2020-02-04 | 2020-09-01 | 2021-10-18 | 2021-10-18 | Argyll and Bute-North Argyll | 0 | 0 | 72873 | 95043 | 51084 | 300327 | 849749.62 | 825800.1 | 2194876.72 | 652961 | 699240.28 | 699240.28 | 2847837.72 | 0 | 0 | 46279.28 | 46279.28 | 2894117 | 180449.74 | [5 empty] | N | FL_DD | 100%
403274 | Barnton Grove - Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-01-23 | 2014-11-27 | 2015-01-09 | 2015-03-20 | 2015-03-20 | City of Edinburgh | 474654 | 474654 | -20869 | -0.02 | -1638.26 | 0 | 0 | 0 | -22507.28 | 0 | 0 | 0 | 452146.72 | 0 | 0 | 0 | 0 | 452146.72 | 180449.74 | [5 empty] | N | FL_DD | 100%
505303 | Barra DSR - Filters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-04-25 | 2023-12-18 | 2024-03-18 | 2025-05-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 3934 | 3974 | 996025.59 | 0 | 0 | 999999.59 | 0 | 0 | 0 | 0 | 999999.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402635 | Barrasie Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-04-16 | 2013-01-03 | 2013-03-11 | 2014-12-05 |  | South Ayrshire | 1640969 | 0 | 21228 | -31370.16 | 0 | 0 | 0 | 0 | -10142.16 | 0 | 0 | 0 | 1630826.84 | 0 | 0 | 0 | 0 | 1630826.84 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403303 | Barrcraigs Reservoir Pipe through dam failure risk | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-27 | 2014-08-25 | 2014-10-20 | 2017-11-10 |  | Renfrewshire | 685659.82 | 0 | 478168.51 | 541097.8 | 132308.8 | -24695.52 | 35327.08 | -34433.58 | 1127773.08 | 0 | 0 | 0 | 1813432.9 | 0 | 0 | 0 | 0 | 1813432.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502392 | Barrhead South SDO | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2017-05-16 | 2017-05-16 | 2017-08-07 | 2021-05-26 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 196261.68 | 0 | 0 | 1853316.32 | 2049578 | -39578 | 0 | 0 | 2010000 | 0 | 0 | 160800 | 160800 | 2170800 | 444766.03 | [5 empty] | N | WG5 | 100%
508977 | Bath Street Glasgow | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2022-02-22 | 2023-09-12 | 2023-12-19 | 2025-01-28 | 2025-01-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29470.62 | 29470.62 | 1087497.94 | 0 | 0 | 1116968.56 | 0 | 0 | 0 | 0 | 1116968.56 | 0 | [5 empty] | N | SR21_WW | 100%
500116 | Bathgate DOA (DOA000537) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS7 | 2015-03-26 | 2016-09-29 | 2016-09-30 | 2019-03-27 | 2020-01-08 | West Lothian | 0 | 0 | 18657 | 155319 | 122816 | 33504 | 28831 | -8760.22 | 350366.78 | 0 | 0 | 0 | 350366.78 | 0 | 0 | 0 | 0 | 350366.78 | 277404.61 | [5 empty] | N | CS16D | 100%
503330 | Bathgate Flood Minimisation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2027-04-01 | 2028-06-14 | 2028-06-22 | 2028-08-02 | 2028-11-02 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79465.94 | 79465.94 | 420530 | 0 | 0 | 499995.94 | 0 | 0 | 0 | 0 | 499995.94 | 0 | [5 empty] | N | SR21_WA | 100%
30087 | Bathgate STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-16 | 2010-12-17 | 2011-03-28 | 2012-09-24 | 2012-10-05 | West Lothian | 1993686.17 | 0 | 3399.44 | 0 | 0 | 0 | 0 | 0 | 3399.44 | 0 | 0 | 0 | 1997085.61 | 0 | 0 | 0 | 0 | 1997085.61 | 119362.42 | [5 empty] | N | CM_WWNI | 20% | EC04A | 80%
502183 | Bathgate Trunk Main - Alternative Mains Feed | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-11-01 | 2022-06-09 | 2022-09-15 | 2024-11-29 |  | West Lothian | 0 | 0 | 20930.23 | 86269.77 | 488747.23 | 162411.49 | 3400.5 | 4883.78 | 766643 | 8460675.95 | 0 | 0 | 9227318.95 | 0 | 0 | 0 | 0 | 9227318.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502242 | Bathgate Trunk Main - Emergency Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-06-01 | 2016-08-31 | 2016-08-31 | 2017-03-28 |  | West Lothian | 0 | 0 | 0 | 721017.38 | -20051 | -6188.84 | 77.96 | 0 | 694855.5 | 0 | 0 | 0 | 694855.5 | 0 | 0 | 0 | 0 | 694855.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502184 | Bathgate Trunk Main Burst Contral | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-22 | 2020-07-29 | 2020-07-29 | 2020-05-26 |  | West Lothian | 0 | 0 | 1308.41 | 32669.13 | 355.8 | 64894.76 | 10511.43 | -109739.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-30 | Scottish Water Wide | 475.02 | 475.02 | 4034.98 | 57396 | 33031.95 | -11809.66 | 0 | 0 | 82653.27 | 0 | 0 | 0 | 83128.29 | 0 | 0 | 0 | 0 | 83128.29 | 0 | [5 empty] | N | EC16 | 100%
502778 | Battery Park Coarse Screens CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-06-16 | 2019-07-31 | 2019-11-07 | 2021-04-30 |  | Inverclyde | 0 | 0 | 0 | 0 | 3394.85 | 91391.33 | 753631.83 | 253853 | 1102271 | 277 | 0 | 0 | 1102548 | 0 | 0 | 0 | 0 | 1102548 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501352 | Battery Park WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-08-31 | 2018-09-05 | 2018-10-10 | 2021-09-09 |  | Inverclyde | 0 | 0 | 0 | 27067 | 271229 | 1618405 | 3308728 | 265966.72 | 5491395.72 | 146758 | 0 | 0 | 5638153.72 | 0 | 0 | 10741.28 | 10741.28 | 5648895 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503723 | Battock Terrace - Torphins DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-10-03 | 2020-11-03 | 2020-11-09 | 2021-06-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 24605.31 | 251520.69 | 276126 | 500 | 0 | 0 | 276626 | 0 | 0 | 0 | 0 | 276626 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500849 | Bayhead Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-06-01 | 2018-06-27 | 2019-02-04 | 2019-06-30 | 2020-01-31 | Na H-Eileanan an Iar | 0 | 0 | 4021.83 | 1480.39 | 30733.78 | 88301.99 | 40972.98 | 202.59 | 165713.56 | 0 | 0 | 0 | 165713.56 | 0 | 0 | 0 | 0 | 165713.56 | 178298.2 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 71.59 | [43 empty] | 0
503673 | Beasdale SR10 Completion | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS5 | 2015-08-26 | 2015-12-23 | 2016-01-22 | 2019-12-31 | 2019-12-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2211 | 2211 | 2789.22 | 2789.22 | 3871.9122 | 5000.22 | 1082.6922 | 0 | 0 | 1082.6922 | 6082.9122 | 184123.25 | [5 empty] | Y | DW23 | 100% | [20 empty] | 1 | [46 empty] | 0
500690 | Beasdale WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2015-08-26 | 2015-12-23 | 2016-01-22 | 2016-06-23 | 2016-06-24 | Highland | 0 | 0 | 336686 | -336686 | 4962.01 | 3000.98 | 0 | 0 | 7962.99 | 0 | 0 | 0 | 7962.99 | 0 | 0 | 0 | 0 | 7962.99 | 184123.25 | [5 empty] | N | DW23 | 100%
45309 | Beasdale WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-31 | 2013-04-01 | 2013-04-02 | 2016-04-01 | Highland | 47621.11 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0 | 0 | 47643.61 | 0 | 0 | 0 | 0 | 47643.61 | 28761.13 | [5 empty] | N | DW13 | 100%
502369 | Beasdale WTW UV Alterations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water | DWQR | SWMD | Water Non infrastructure | MS3 | 2015-08-26 | 2015-12-23 | 2016-01-22 |  |  | Highland | 0 | 0 | 0 | 0 | 2029.38 | 1977.41 | 10649.88 | 28355.34 | 43012 | 548276.81 | 0 | 0 | 591288.81 | 0 | 0 | 0 | 0 | 591288.81 | 119022.58 | [5 empty] | Y | CM_WSNI | 100% | [67 empty] | 0
402857 | Beeches Ladybank Cupar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-08-15 | 2012-12-04 | 2013-01-18 | 2015-08-13 | 2015-08-13 | Fife | 42581.6 | 42581.6 | -42580.6 | 662.24 | 0 | 0 | -0.01 | 0 | -41918.37 | 0 | 0 | 0 | 663.23 | 0 | 0 | 0 | 0 | 663.23 | 180449.74 | [5 empty] | N | FL_DD | 100%
502709 | Beeslack House Pipe Bridge Penicuik | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 |  | Midlothian | 0 | 0 | 0 | 0 | 2609.3 | 0 | 0 | 0 | 2609.3 | 0 | 0 | 0 | 2609.3 | 0 | 0 | 0 | 0 | 2609.3 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500118 | Beeswing DOA (DOA000135) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-09-27 | 2017-03-08 | 2017-04-04 | 2017-04-04 | Dumfries and Galloway | 0 | 0 | 19644 | -2009 | -2696.49 | 41.28 | 0 | 0 | 14979.79 | 0 | 0 | 0 | 14979.79 | 0 | 0 | 0 | 0 | 14979.79 | 72047.27 | [5 empty] | N | CS11 | 100%
402992 | Bell Street Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2013-03-15 | 2013-06-03 | 2013-10-25 | 2013-10-25 | Glasgow City | 103140 | 0 | -7519.29 | 0 | 0 | 0 | 0 | 0 | -7519.29 | 0 | 0 | 0 | 95620.71 | 0 | 0 | 0 | 0 | 95620.71 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
503546 | Belleisle Golf Course CSO Bathing Water Improvement | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater | SEPA | WWINF | Revised Bathing Waters Directive | MS3 | 2019-07-09 | 2020-07-29 | 2020-09-07 | 2021-07-01 | 2021-10-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 275965 | 2405622.27 | 2681587.27 | 156934 | 170805.7315 | 170805.7315 | 2838521.27 | 0 | 13871.7315 | -0.0015 | 13871.73 | 2852393 | 1035209.71 | [5 empty] | Y | EC16B | 100% | [38 empty] | 1 | [28 empty] | 0
501527 | Bellsbank High SR Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-05-28 | 2028-01-25 | 2028-05-30 | 2028-10-09 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145956.97 | 0 | 0 | 145956.97 | 0 | 0 | 0 | 0 | 145956.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503141 | Belmore Tank WSZ - Faslane Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2020-09-22 | 2020-09-22 | 2020-09-22 | 2021-01-25 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 7836.28 | 2332.72 | 2314.25 | -2258.84 | 10224.41 | 0 | 0 | 0 | 10224.41 | 0 | 0 | 0 | 0 | 10224.41 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508487 | Belmore WOA ITS - Shandon & Garelochead short term solution | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-10-09 | 2020-11-12 | 2021-10-08 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22974 | 22974 | 40823.37 | 0 | 0 | 63797.37 | 0 | 0 | 0 | 0 | 63797.37 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501209 | Belmore WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS6 | 2017-12-22 | 2018-11-28 | 2019-03-18 | 2020-01-24 | 2021-09-03 | Argyll and Bute-Cowal & Bute | 0 | 0 | 12558.14 | 7317.87 | 59031.48 | 201345.51 | 609311 | 12487 | 902051 | 25741 | 25741 | 35732.8903 | 927792 | 9991.8903 | 0 | 0 | 9991.8903 | 937783.8903 | 834383.36 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
508848 | Belmore WTW - DAF scraper drive system and blades replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2020-11-17 | 2021-09-21 | 2022-02-01 | 2023-01-06 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 4839 | 473160.97 | 0 | 0 | 477999.97 | 0 | 0 | 0 | 0 | 477999.97 | 119022.58 | [5 empty] | N | WSNI | 100%
508568 | Belmore WTW - lime dosing flushing-dust exposure improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-05-10 | 2021-05-10 | 2021-12-20 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7208 | 7208 | 12791.6 | 0 | 0 | 19999.6 | 0 | 0 | 0 | 0 | 19999.6 | 119022.58 | [5 empty] | N | WSNI | 100%
500855 | Benbecula RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-07-25 | 2018-06-27 | 2019-02-18 | 2019-06-30 | 2019-12-31 | Na H-Eileanan an Iar | 0 | 0 | 4692.29 | 1846.8 | 14611.16 | 90096.62 | 33077.43 | 2975.97 | 147300.27 | -2975.97 | -2975.97 | -4131.153 | 144324.3 | -1155.183 | 0 | 0 | -1155.183 | 143169.117 | 270193.45 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 82.39 | [43 empty] | 0
403045 | Benbecula Zone - Ardmore Iron Specials Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-13 | 2013-01-14 | 2013-09-04 |  | Na H-Eileanan an Iar | 183184.99 | 0 | 1634 | 0 | 0 | 0 | 0 | 0 | 1634 | 0 | 0 | 0 | 184818.99 | 0 | 0 | 0 | 0 | 184818.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506762 | Bennan Reservoir Responsive | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-05-26 |  | 2021-08-17 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15582.31 | 15582.31 | 29509.41 | 0 | 0 | 45091.72 | 0 | 0 | 0 | 0 | 45091.72 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503539 | Bertha Park - Growth - Plan Stage | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 48304.07 | 167582.16 | -211909.81 | 3976.42 | -3976.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG5 | 100%
503303 | Bertha Park - Perth | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2018-08-14 | 2018-08-14 | 2019-07-10 | 2021-03-05 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 3742.77 | 3656.65 | -7399.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG5 | 100%
508949 | Bertha Park - WI Growth | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW2 | 2021-06-25 | 2023-03-28 | 2023-04-24 | 2025-05-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458959.66 | 458959.66 | 11284921.78 | 0 | 0 | 11743881.44 | 0 | 0 | 0 | 0 | 11743881.44 | 444766.03 | [5 empty] | N | WG5 | 100%
502766 | Bertha Park Perth - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-06-25 | 2023-03-28 | 2023-04-24 | 2025-05-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 83645 | 46696.24 | 194835.09 | 121796.2 | 446972.53 | 29553420.6 | 0 | 0 | 30000393.13 | 0 | 0 | 0 | 0 | 30000393.13 | 122419.09 | [5 empty] | N | SG1 | 100%
500951 | Bespoke Application Development Platform Refresh | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2015-09-30 | 2016-05-16 | 2016-05-16 | 2018-11-22 |  | Scottish Water Wide | 0 | 0 | 119842 | 485188.83 | 759734.71 | -165162.03 | 0 | 0 | 1199603.51 | 0 | 0 | 0 | 1199603.51 | 0 | 0 | 0 | 0 | 1199603.51 | 617898.1 | [5 empty] | N | CM_M&G | 50% | CM_WSI | 50%
403796 | Beyond Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-10-15 | 2014-10-15 | 2014-11-06 | 2015-03-12 |  | Scottish Water Wide | 1007215 | 0 | -17927.06 | 0 | 0 | 0 | 0 | 0 | -17927.06 | 0 | 0 | 0 | 989287.94 | 0 | 0 | 0 | 0 | 989287.94 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500051 | Biggar WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS6 | 2016-09-30 | 2018-09-06 | 2018-09-24 | 2019-05-29 | 2019-05-29 | South Lanarkshire | 0 | 0 | 46503.28 | 24619.39 | 251268.59 | 856184.64 | 51108.1 | -30394.76 | 1199289.24 | 18564.76 | 0 | 0 | 1217854 | 0 | 0 | 0 | 0 | 1217854 | 122419.09 | [5 empty] | N | SG1 | 100%
501654 | BIGGAR WWTW 2002 NT049369 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 |  | Scottish Borders | 0 | 0 | 0 | 0 | 26344.16 | 1774.5 | 0 | 0 | 28118.66 | 0 | 0 | 0 | 28118.66 | 0 | 0 | 0 | 0 | 28118.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508569 | Bioresource modelling and STC capability | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS2 | 2020-10-20 | 2021-01-23 | 2021-06-30 | 2021-12-29 | 2022-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395917 | 395917 | 104083 | 0 | 0 | 500000 | 0 | 28708.7812 | 0 | 28708.7812 | 528708.7812 | 108174.77 | [5 empty] | N | EC10A_ID | 100%
402498 | Birgham WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-04-18 | 2014-01-29 | 2014-03-13 | 2014-09-15 | 2014-09-15 | Scottish Borders | 519000 | 0 | 432.06 | 0 | 0 | 0 | 0 | -224.51 | 207.55 | 0 | 0 | 0 | 519207.55 | 0 | 0 | 0 | 0 | 519207.55 | 0 | [5 empty] | N | SG1 | 100%
506746 | Bishopton WWPS - Replacement Isolation valve and metering equipment. | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-07-22 | 2020-09-10 | 2021-06-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35415 | 35415 | 14585.4 | 0 | 0 | 50000.4 | 0 | 0 | 0 | 0 | 50000.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505935 | Black Cart Water Aesthetic Study - SR21 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWMD | SR21 Early Start | MS3 | 2020-04-29 | 2020-07-07 | 2020-08-17 | 2021-06-28 | 2021-09-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 457.14 | 40110.86 | 40568 | 19432.14 | 0 | 0 | 60000.14 | 0 | 0 | 0 | 0 | 60000.14 | 0 | [5 empty] | N | SR21_WW | 100%
500239 | Black Esk - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-08-27 | 2019-08-01 | Dumfries and Galloway | 0 | 0 | 4000 | 12763.62 | 144074.67 | 21594.73 | 30170.56 | -5147.25 | 207456.33 | 0 | 0 | 0 | 207456.33 | 0 | 0 | 0 | 0 | 207456.33 | 1905549.22 | [5 empty] | N | DW5FS | 100%
503426 | Black Esk & Kettleton WRZ - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2020-12-11 | 2022-09-20 | 2022-12-14 | 2023-11-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG1 | 100%
502358 | Black Esk & Winterhope WOA - Gretna Water Supply | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | NONINF | Strategic Capacity | MS0 | 2018-11-21 | 2021-04-26 | 2021-08-09 | 2022-12-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 69147.69 | 24322.57 | 100348.34 | 348767.8 | 415891.6 | 958478 | 5754488 | 0 | 0 | 6712966 | 0 | 0 | 0 | 0 | 6712966 | 444766.03 | [5 empty] | N | WG5 | 44.3% | WG1 | 55.7%
500797 | Black Esk RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS5 | 2015-09-30 | 2018-06-28 | 2018-09-28 | 2019-12-23 | 2020-12-16 | Dumfries and Galloway | 0 | 0 | 133210 | 8719.89 | 218976.11 | 136142.64 | 257139.91 | 110271.45 | 864460 | 17614.56 | 17614.56 | 24452.0081 | 882074.56 | 6837.4481 | 0 | 0 | 6837.4481 | 888912.0081 | 1267638.63 | [5 empty] | N | DW5FS | 100%
500799 | Black Esk Winterhope RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2015-09-30 | 2017-09-29 | 2017-10-11 | 2019-06-30 | 2020-01-31 | Dumfries and Galloway | 0 | 0 | 20929 | -1919 | 124172.58 | 163697.38 | 33083.53 | -16152.22 | 323811.27 | 0 | 0 | 0 | 323811.27 | 0 | 0 | 0 | 0 | 323811.27 | 291348.7 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 110.73 | [43 empty] | 0
501140 | Black Esk WOA Birsca WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2016-05-27 | 2022-10-25 | 2022-11-22 | 2024-11-14 |  | Dumfries and Galloway | 0 | 0 | 76680 | 41139.01 | 283992 | 188963.21 | 2705.73 | 4058.37 | 597538.32 | 0 | 0 | 0 | 597538.32 | 0 | 0 | 0 | 0 | 597538.32 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501136 | Black Esk WOA Birset Dalton WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501134 | Black Esk WOA Birset WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501135 | Black Esk WOA Burnswark WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501131 | Black Esk WOA Canonbie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501142 | Black Esk WOA Castlemilk WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501130 | Black Esk WOA Clunie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501143 | Black Esk WOA Douglashall WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501132 | Black Esk WOA Eskdale WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 49.5 | 0 | 0 | 0 | 49.5 | 0 | 0 | 0 | 49.5 | 0 | 0 | 0 | 0 | 49.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501133 | Black Esk WOA Jockstown WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501141 | Black Esk WOA Kerrbush WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 |  | Dumfries and Galloway | 0 | 0 | 81 | -81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501129 | Black Esk WOA Langholm WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501137 | Black Esk WOA Leakaims WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 |  | Dumfries and Galloway | 0 | 0 | 81 | -81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501138 | Black Esk WOA Shieldhill WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2016-04-04 | 2023-12-06 | 2024-01-01 | 2024-10-14 |  | Dumfries and Galloway | 0 | 0 | 97776 | -10683 | 104803 | 100550.44 | -27033.69 | -5479.73 | 259933.02 | 0 | 0 | 0 | 259933.02 | 0 | 0 | 0 | 0 | 259933.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507107 | Black Esk WTW - Clarified Turbidity Alarms | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-06-11 | 2020-11-17 | 2021-07-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23116 | 23116 | 12884.09 | 0 | 0 | 36000.09 | 0 | 0 | 0 | 0 | 36000.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503049 | Black Esk WTW - RGF valves and MEICA | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water | DWQR | SWMD | Water Non infrastructure | MS4 | 2014-03-31 | 2016-03-23 | 2016-03-28 | 2017-11-30 | 2021-10-08 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 17631.55 | 248528.11 | -457.68 | 166895.02 | 432597 | 66261.39 | 0 | 0 | 498858.39 | 0 | 0 | 0 | 0 | 498858.39 | 119022.58 | [5 empty] | Y | CM_WSNI | 100% | [18 empty] | 1 | [48 empty] | 0
46196 | Black Isle Service Reservoir Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-08-12 | 2011-03-22 | 2011-05-02 | 2011-08-29 |  | Highland | 402081.62 | 0 | -0.69 | 0 | 0 | 0 | 0 | 0 | -0.69 | 0 | 0 | 0 | 402080.93 | 0 | 0 | 0 | 0 | 402080.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508185 | Black Isle trunk main strategic valve replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-08-19 | 2021-03-31 | 2022-04-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29882 | 29882 | 60117.76 | 0 | 0 | 89999.76 | 0 | 0 | 0 | 0 | 89999.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507420 | Black Isle trunk mains cathodic protection repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-07-07 | 2020-11-23 | 2022-05-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48296 | 48296 | 114156.89 | 0 | 0 | 162452.89 | 0 | 0 | 0 | 0 | 162452.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508145 | Black Linn and Greenlands Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-19 | 2022-01-14 | 2022-08-29 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4206 | 4206 | 27822.24 | 0 | 0 | 32028.24 | 0 | 0 | 0 | 0 | 32028.24 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508797 | Black Sands Anstruther Seawater Infiltration Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-01 | 2021-12-06 | 2022-04-06 | 2022-10-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.72 | 42.72 | 0 | 0 | 0 | 42.72 | 0 | 0 | 0 | 0 | 42.72 | 209381.79 | [5 empty] | N | CM_WWI | 100%
401008 | Blackford WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2014-02-27 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | Perth and Kinross | 141079 | 0 | 257403 | 212180.64 | -9871.74 | 72.86 | -13440.37 | 0 | 446344.39 | 0 | 0 | 0 | 587423.39 | 0 | 0 | 0 | 0 | 587423.39 | 0 | [5 empty] | N | SG1 | 100%
30097 | Blackridge STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-20 | 2010-06-28 | 2010-10-04 | 2012-03-16 | 2012-03-23 | West Lothian | 5265641.6 | 0 | 1720.87 | 0 | 0 | 0 | 0 | 0 | 1720.87 | 0 | 0 | 0 | 5267362.47 | 0 | 0 | 0 | 0 | 5267362.47 | 148123.55 | [5 empty] | N | CM_WWNI | 8.955% | EC10A | 30.35% | EC04A | 60.7%
501709 | Blackridge WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-06-29 | 2016-06-29 | 2016-06-29 | 2016-06-02 |  | West Lothian | 0 | 0 | 0 | 1674.42 | 138.65 | 61.22 | 0 | 0 | 1874.29 | 0 | 0 | 0 | 1874.29 | 0 | 0 | 0 | 0 | 1874.29 | 209381.79 | [5 empty] | N | CM_WWI | 100%
401345 | Blackstand WSZ Low Pressure Enhancement WSZ000184 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-12-13 | 2013-02-25 | 2014-09-04 | 2013-09-30 | Highland | 80825 | 0 | -1758.88 | 98.34 | 0 | 0 | 0 | 0 | -1660.54 | 0 | 0 | 0 | 79164.46 | 0 | 0 | 0 | 0 | 79164.46 | 0 | [5 empty] | N | CS1 | 100%
500120 | Blackwood DOA (DOA000598) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-12 | 2017-04-30 | 2017-07-31 | South Lanarkshire | 0 | 0 | 51658 | 53991 | 6357.43 | 123.84 | 0 | 0 | 112130.27 | 0 | 0 | 0 | 112130.27 | 0 | 0 | 0 | 0 | 112130.27 | 72047.27 | [5 empty] | Y | CS11 | 44.65% | CS16D | 55.35% | [37 empty] | 1 | [27 empty] | 0
502815 | Blackwood WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS4 | 2020-09-15 | 2020-09-15 | 2020-09-16 | 2021-03-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 80034.79 | 17145.69 | 31731.78 | 24113.19 | 153025.44 | 0 | 0 | 0 | 153025.44 | 0 | 0 | 0 | 0 | 153025.44 | 122419.09 | [5 empty] | N | SG1 | 100%
503502 | Blairdardie (Rotherwood) Tunnel - Structural Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-23 | 2022-02-28 | 2022-05-06 | 2022-09-20 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2215.34 | 2215.34 | 689872.83 | 0 | 0 | 692088.17 | 0 | 0 | 0 | 0 | 692088.17 | 311236.79 | [5 empty] | N | CM_M&G | 100%
503231 | Blairgowrie WwTW - Inlet Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2019-01-28 | 2019-01-28 | 2019-05-31 | 2021-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 184249.6 | 209658.22 | 184016.7 | 577924.52 | 12622.3 | 0 | 0 | 590546.82 | 0 | 0 | 0 | 0 | 590546.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502818 | Blairgowrie WwTW - Investigation and Scope Definition for Potential | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2020-08-10 | 2022-07-18 | 2023-01-11 | 2022-06-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 64892.94 | 24485.8 | 21353.59 | 49718.1 | 160450.43 | 1800634.62 | 0 | 0 | 1961085.05 | 0 | 0 | 0 | 0 | 1961085.05 | 122419.09 | [5 empty] | N | SG1 | 100%
502931 | Blairgowrie WwTW - Sludge Thickener | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2017-10-31 | 2018-08-23 | 2019-03-11 | 2021-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 6800 | 286583.53 | 181582.1 | 89224.37 | 564190 | 12005.8 | 0 | 0 | 576195.8 | 0 | 0 | 0 | 0 | 576195.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400062 | Blairingone WwTW Upgrade WQ01 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-08-31 | 2012-02-21 | 2012-08-07 | 2013-02-14 | 2013-03-21 | Clackmannanshire | 933359.83 | 0 | -755.31 | 0 | 0 | 0 | 0 | 0 | -755.31 | 0 | 0 | 0 | 932604.52 | 0 | 0 | 0 | 0 | 932604.52 | 119362.42 | [5 empty] | N | CM_WWNI | 10% | WQ01 | 90%
501565 | Blairlinnans Main Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-02-10 | 2016-08-31 | 2016-09-26 | 2019-03-18 |  | West Dunbartonshire | 0 | 0 | 5514 | 563128.15 | 634631 | 1018492 | 2874.26 | 0 | 2224639.41 | 0 | 0 | 0 | 2224639.41 | 0 | 0 | 0 | 0 | 2224639.41 | 311236.79 | [5 empty] | N | CM_M&G | 100%
503600 | Blairlinnans Milton Pipeline Emergency Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water | SW | WINF | Water infrastructure | MS4 | 2019-10-03 | 2020-03-19 | 2020-01-06 | 2021-03-26 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 3800000 | 1354429.8 | 5154429.8 | -285410.21 | 0 | 0 | 4869019.59 | 0 | 0 | 0 | 0 | 4869019.59 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503408 | Blairlinnans PSC TM Monitoring | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2020-02-20 | 2021-10-11 | 2021-11-18 | 2022-05-27 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 32148.84 | 55370.33 | -35548.17 | 51971 | 3114028.75 | 0 | 0 | 3165999.75 | 0 | 0 | 0 | 0 | 3165999.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508156 | Blairlinnans T W Res 2 Proactive Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-09-02 | 2021-08-05 | 2022-02-15 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3739 | 3739 | 11261.43 | 0 | 0 | 15000.43 | 0 | 0 | 0 | 0 | 15000.43 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501215 | Blairlinnans WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-21 | 2016-09-08 | 2016-09-09 | 2016-09-30 | 2016-09-30 | Inverclyde | 0 | 0 | 3341.78 | 2231.83 | 0 | 341.04 | 0 | 0 | 5914.65 | 0 | 0 | 0 | 5914.65 | 0 | 0 | 0 | 0 | 5914.65 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
505145 | Blairlinnans WTW - final sample tap access improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-28 |  | 2020-08-26 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 1685 | 18.47 | 1703.47 | 0 | 0 | 0 | 1703.47 | 0 | 0 | 0 | 0 | 1703.47 | 119022.58 | [5 empty] | N | WSNI | 100%
511805 | Blairlinnans WTW - replacement of domestic service water tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-24 | 2021-12-17 | 2022-08-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287.92 | 287.92 | 50000 | 0 | 0 | 50287.92 | 0 | 0 | 0 | 0 | 50287.92 | 119022.58 | [5 empty] | N | WSNI | 100%
503575 | Blairlinnans WTW - SCADA replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-09-09 | 2019-09-09 | 2019-09-23 | 2021-08-27 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 436706.5 | 103233.5 | 539940 | 132280.23 | 0 | 0 | 672220.23 | 0 | 0 | 0 | 0 | 672220.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502565 | Blairnamarrow WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS4 | 2021-01-05 | 2021-01-05 | 2021-01-18 | 2021-01-18 |  | Moray | 0 | 0 | 0 | 20930.23 | 2988.95 | 89869.85 | 87210.97 | -5092.19 | 195907.81 | 0 | 0 | 0 | 195907.81 | 0 | 0 | 0 | 0 | 195907.81 | 122419.09 | [5 empty] | N | WG1 | 100%
403139 | Blairnamarrow WTW to Tomintoul - Replacement Water Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-12 | 2013-06-28 | 2013-09-02 | 2014-11-15 |  | Moray | 447551 | 0 | -7274 | 3744.23 | 0 | 0 | 0 | 0 | -3529.77 | 0 | 0 | 0 | 444021.23 | 0 | 0 | 0 | 0 | 444021.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403934 | Blairythan Terrace (Foveran) ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS3 | 2017-06-20 | 2020-12-18 | 2021-03-15 | 2022-03-10 |  | Aberdeenshire | 2745 | 0 | 38205.19 | 21927.45 | 28903.36 | 254723.97 | 130785.86 | 782087.86 | 1256633.69 | 1408931.81 | 0 | 0 | 2668310.5 | 0 | 0 | 100882.5 | 100882.5 | 2769193 | 0 | [5 empty] | N | SG1 | 100%
500770 | Blantyre Farm Road Uddingston Replace Overland Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-24 | 2017-12-21 | 2018-02-26 | 2018-12-20 |  | South Lanarkshire | 0 | 0 | 26795 | 98510 | 420695 | 505938 | 6303.76 | -4777.44 | 1053464.32 | 0 | 0 | 0 | 1053464.32 | 0 | 0 | 0 | 0 | 1053464.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500694 | Bo ness WWTW NT022813 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-08-25 | 2018-11-30 | 2018-12-18 | 2021-11-22 |  | Falkirk | 0 | 0 | 38324 | 261068.37 | 130952.12 | 517779.64 | 1136329.52 | 542921.35 | 2627375 | 211656 | 0 | 0 | 2839031 | 0 | 0 | 254622 | 254622 | 3093653 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500864 | Boardhouse WTW - Auto Coagulation Control | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS6 | 2015-08-10 | 2017-05-31 | 2017-08-02 | 2018-03-31 | 2021-03-31 | Orkney Islands | 0 | 0 | 1337.86 | 24414.31 | 227533.02 | 46839.46 | 2535.1 | -1600.54 | 301059.2 | 1600.54 | 1600.5435 | 2221.8269 | 302659.74 | 621.2834 | 0 | 0 | 621.2834 | 303281.0234 | 456504.91 | [5 empty] | Y | DW25P | 5% | DW3C | 95% | [16 empty] | 1 | [48 empty] | 0
300016 | Boardhouse WTW - Kirbister WTW Provision of Chloramination | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-05-23 | 2011-09-20 | 2011-10-31 | 2012-08-15 | 2013-07-25 | Orkney Islands | 3535272.03 | 0 | -430 | 0 | 0 | 0 | 0 | 0 | -430 | 0 | 0 | 0 | 3534842.03 | 0 | 0 | 0 | 0 | 3534842.03 | 28761.13 | [5 empty] | N | DW3 | 100%
502235 | Boardhouse WTW - Network Dead Ends | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2016-11-18 | 2017-10-31 | 2017-10-31 | 2019-02-28 | 2019-02-28 | Orkney Islands | 0 | 0 | 0 | 38463.2 | 52908.8 | 196782.38 | 327.09 | 96.82 | 288578.29 | 0 | 0 | 0 | 288578.29 | 0 | 0 | 0 | 0 | 288578.29 | 0 | [5 empty] | N | DW25D | 100%
501570 | Boardhouse WTW - Quality (Reduction of risks identified in Drinking Water Safety Plan) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS6 | 2016-03-25 | 2017-09-28 | 2017-10-23 | 2018-01-31 | 2019-09-30 | Orkney Islands | 0 | 0 | 4696.28 | 5496.43 | 52309.95 | 11395.94 | 15.39 | -2991.14 | 70922.85 | 0 | 0 | 0 | 70922.85 | 0 | 0 | 0 | 0 | 70922.85 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
502186 | Boardhouse WTW - SR Dead Zones | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-21 | 2016-09-30 | 2016-11-07 | 2019-09-30 | 2019-09-30 | Orkney Islands | 0 | 0 | 2093 | 82392.9 | 5583.41 | 2339.54 | 29288.78 | -10891.84 | 110805.79 | 0 | 0 | 0 | 110805.79 | 0 | 0 | 0 | 0 | 110805.79 | 466277.79 | [5 empty] | N | DW25T | 100%
502388 | Boardhouse WTW- Filter Remedial Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-15 | 2021-06-21 | 2021-08-19 | 2022-02-28 |  | Orkney Islands | 0 | 0 | 0 | 10046.51 | 3142.96 | 5111.2 | 12578.31 | 25250.48 | 56129.46 | 715554.54 | 0 | 0 | 771684 | 0 | 0 | 0 | 0 | 771684 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400258 | Boardhouse WTW Wastewater Treatment Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-01-25 | 2010-03-11 | 2011-10-10 | 2017-09-29 |  | Orkney Islands | 283940 | 0 | 571 | 512.74 | 0 | 0 | 0 | 0 | 1083.74 | 0 | 0 | 0 | 285023.74 | 0 | 0 | 0 | 0 | 285023.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509500 | Boat of Garten WwTW - Chemical Dosing & Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-11-11 | 2021-09-13 | 2022-04-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35072 | 35072 | 100927.59 | 0 | 0 | 135999.59 | 0 | 0 | 0 | 0 | 135999.59 | 90601.29 | [5 empty] | N | WWNI | 100%
400815 | Boat of Garten WwTW - Growth | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-05-03 | 2013-11-18 | 2013-11-25 | 2015-06-10 | 2015-06-10 | Highland | 4883648.21 | 0 | 440694.64 | 12963.31 | -1080.77 | 0 | 0 | 0 | 452577.18 | 0 | 0 | 0 | 5336225.39 | 0 | 0 | 0 | 0 | 5336225.39 | 209381.79 | [5 empty] | N | CS11A | 1.982% | CM_WWI | 2.972% | SG1 | 95.05%
403284 | Bogend Farm - Mains rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-08 | 2013-03-19 | 2013-03-19 | 2013-09-13 |  | West Lothian | 176014 | 0 | -17.57 | 0 | 0 | 0 | 0 | 0 | -17.57 | 0 | 0 | 0 | 175996.43 | 0 | 0 | 0 | 0 | 175996.43 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506701 | Boglashin DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-06-23 | 2023-08-11 | 2023-11-14 | 2025-02-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 645554.52 | 0 | 0 | 654554.52 | 0 | 0 | 0 | 0 | 654554.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501528 | Bomains TWS Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-07-22 | 2028-07-03 | 2028-11-06 | 2029-06-21 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617604.01 | 0 | 0 | 1617604.01 | 0 | 0 | 0 | 0 | 1617604.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510779 | Bonawe WwTW & Clachan WwTW - Provision of Toilet Facilities | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-06-23 | 2022-12-23 | 2023-08-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308.41 | 1308.41 | 48691.59 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502427 | Bonchester Bridge WwTW Outfall | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS7 | 2017-06-19 | 2017-09-18 | 2017-10-02 | 2017-12-31 | 2018-01-31 | Scottish Borders | 0 | 0 | 0 | 4280.32 | 26271.92 | 16632.76 | -2185 | -707.19 | 44292.81 | 0 | 0 | 0 | 44292.81 | 0 | 0 | 0 | 0 | 44292.81 | 41330.23 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
45405 | Bonchester WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-28 | 2012-09-10 | 2013-05-29 | 2013-08-22 | Scottish Borders | 1002209.01 | 0 | -18746.08 | 0 | 0 | 0 | 0 | 0 | -18746.08 | 0 | 0 | 0 | 983462.93 | 0 | 0 | 0 | 0 | 983462.93 | 28761.13 | [5 empty] | N | DW23 | 100%
500798 | Bonkle Bridge Newmains Replace Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-24 | 2017-09-12 | 2018-03-26 | 2018-11-29 |  | South Lanarkshire | 0 | 0 | 62345 | 94301 | 204917.34 | 215947.66 | 36085 | -10574.82 | 603021.18 | 0 | 0 | 0 | 603021.18 | 0 | 0 | 0 | 0 | 603021.18 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500800 | Bonnycraig RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-01-12 | 2017-03-09 | 2017-03-30 | 2019-05-14 | 2019-12-19 | Scottish Borders | 0 | 0 | 15247.21 | 31202.93 | 40058.29 | 121580.63 | 20588.24 | -4969.03 | 223708.27 | 0 | 0 | 0 | 223708.27 | 0 | 0 | 0 | 0 | 223708.27 | 203777.52 | [5 empty] | N | DW5FS | 100%
500244 | Bonnycraig WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS5 | 2016-02-26 | 2018-03-27 | 2018-03-27 | 2021-02-28 | 2021-03-31 | Scottish Borders | 0 | 0 | 30177.5 | 322708.87 | 901046.7 | 300533.11 | 1636784.82 | 205879.36 | 3397130.36 | 109343.64 | 54671.82 | 257176.2681 | 3506474 | 202504.4481 | 0 | 195160.5 | 397664.9481 | 3904138.9481 | 614012.43 |  |  |  |  | 36252 | Y | CM_WSNI | 50% | DW25P | 50% | [19 empty] | 1 | [45 empty] | 0
502714 | Bonnycraig WTW - UV Treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-05-12 | 2017-05-12 | 2017-10-01 | 2021-06-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 452474.31 | 8736.03 | 2097.03 | 170.88 | 463478.24 | 0 | 0 | 0 | 463478.24 | 0 | 0 | 0 | 0 | 463478.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502570 | Bonnycraig WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWMD | Strategic Capacity | MS7 | 2020-06-25 | 2020-06-26 | 2020-07-08 | 2020-08-10 |  | Scottish Borders | 0 | 0 | 0 | 20930.23 | 80868.29 | 185035.64 | 953208.08 | -957523.37 | 282518.87 | 0 | 0 | 0 | 282518.87 | 0 | 0 | 0 | 0 | 282518.87 | 122419.09 | [5 empty] | N | WG1 | 100%
508944 | Borders Area - Pipebridges Refurb_Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-10-16 | 2021-06-11 | 2022-01-24 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7228.44 | 7228.44 | 17857.2 | 0 | 0 | 25085.64 | 0 | 0 | 0 | 0 | 25085.64 | 311236.79 | [5 empty] | N | WSI | 100%
46268 | Borehole Remedial Actions Programme | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-12-17 | 2010-12-17 | 2011-01-26 | 2013-12-23 |  | Scottish Water Wide | 1507464.71 | 0 | 3356.88 | 0 | 0 | 0 | 0 | 0 | 3356.88 | 0 | 0 | 0 | 1510821.59 | 0 | 0 | 0 | 0 | 1510821.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501394 | Boreholes - Phase 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-06-29 | 2017-06-29 | 2017-10-16 | 2019-08-01 |  | Scottish Water Wide | 0 | 0 | 0 | 42885.71 | 974265.44 | 509895.68 | 18840.74 | 1237.43 | 1547125 | 1307.6 | 0 | 0 | 1548432.6 | 0 | 0 | 0 | 0 | 1548432.6 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500939 | Bothwell Road Hamilton Overland Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-09-02 | 2018-04-30 | 2018-09-28 | 2019-03-19 |  | South Lanarkshire | 0 | 0 | 44364 | 34062 | 214724 | 927963 | -49407 | -39609.11 | 1132096.89 | 42109.11 | 0 | 0 | 1174206 | 0 | 0 | 0 | 0 | 1174206 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503415 | Bothwell Sewer - Replacement of approximatly 130m of 600mm | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-02-28 | 2019-02-28 | 2019-03-18 | 2022-04-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 32834.84 | 613525.42 | 637812.98 | 1284173.24 | 2265548.2 | 0 | 0 | 3549721.44 | 0 | 0 | 950278.56 | 950278.56 | 4500000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
30107 | Bothwellbank STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-23 | 2010-09-20 | 2010-11-29 | 2014-10-21 | 2015-01-05 | South Lanarkshire | 1948423.25 | 0 | 1623.02 | -1742.01 | 0 | 0 | 0 | 0 | -118.99 | 0 | 0 | 0 | 1948304.26 | 0 | 0 | 0 | 0 | 1948304.26 | 119362.42 | [5 empty] | N | CM_WWNI | 20% | EC01A | 80%
502307 | Bothwellbank WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-12-21 | 2023-01-11 | 2023-05-04 | 2023-11-16 |  | South Lanarkshire | 0 | 0 | 0 | 35014.7 | 690.59 | 5572.45 | 23109.49 | 36328.78 | 100716 | 233132.27 | 0 | 0 | 333848.27 | 0 | 0 | 0 | 0 | 333848.27 | 122419.09 | [5 empty] | N | SG1 | 100%
403750 | Bothwellbank WwTW Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-04-03 | 2014-04-03 | 2014-07-30 | 2017-02-22 |  | South Lanarkshire | 352139 | 0 | 115361 | -38421.14 | 0 | 0 | 0 | 0 | 76939.86 | 0 | 0 | 0 | 429078.86 | 0 | 0 | 0 | 0 | 429078.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500729 | Boughden Braes Lesmahagow Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2015-08-21 | 2021-08-10 | 2021-10-11 | 2022-06-17 |  | Scottish Water Wide | 0 | 0 | 5306 | 95727 | 120208 | -23350 | -3037.91 | 241.57 | 195094.67 | 843472.32 | 0 | 0 | 1038566.98 | 0 | 0 | 0 | 0 | 1038566.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403404 | Boughden Braes Sewer Collapse - Undertake Sewer Diversion Works | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-05 | 2013-10-24 | 2013-11-18 | 2013-12-09 | 2014-03-21 | South Lanarkshire | 89207 | 0 | -618.32 | 0 | 0 | 0 | 0 | 0 | -618.32 | 0 | 0 | 0 | 88588.68 | 0 | 0 | 0 | 0 | 88588.68 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501513 | BOWHOUSE WWPS NS934805 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-06-29 | 2017-12-20 | 2018-03-26 | 2021-04-01 |  | Falkirk | 0 | 0 | 0 | 85352 | 205270 | 814546.02 | 88777.74 | 3701.24 | 1197647 | 0 | 0 | 0 | 1197647 | 0 | 0 | 0 | 0 | 1197647 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501814 | Bowhouse WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-08-31 | 2016-09-29 | Fife | 0 | 0 | 10640.68 | 6602.48 | 0 | 0 | 0 | 0 | 17243.16 | 0 | 0 | 0 | 17243.16 | 0 | 0 | 0 | 0 | 17243.16 | 122419.09 | [5 empty] | N | SG1 | 100%
500898 | Bowling Reservoir Breach FRMA | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water | DWQR | SWMD | Flood Risk Management Act | MS7 | 2015-06-30 | 2015-06-30 | 2015-07-31 | 2017-08-31 | 2017-10-31 | West Dunbartonshire | 0 | 0 | 7000 | 330140.57 | 81493.7 | 0 | -170.26 | 0 | 418464.01 | 0 | 0 | 0 | 418464.01 | 0 | 0 | 0 | 0 | 418464.01 | 980126.37 | [5 empty] | Y | WR6 | 100% | [28 empty] | 1 | [38 empty] | 0
508846 | Bowmore WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-04-03 | 2025-02-13 | 2025-05-15 | 2026-10-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59942 | 59942 | 1940058.21 | 0 | 0 | 2000000.21 | 0 | 0 | 0 | 0 | 2000000.21 | 122419.09 | [5 empty] | N | SG1 | 100%
503379 | Bowmore WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-03-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 66783.08 | 7075.32 | -60144.89 | 13713.51 | 0 | 0 | 0 | 13713.51 | 0 | 0 | 0 | 0 | 13713.51 | 122419.09 | [5 empty] | N | SG1 | 100%
401333 | Bradan A - Iron & Manganese Distribution WQ Improvements - Guiltreehill Cluster | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2013-02-13 | 2013-12-19 | South Ayrshire | 6347735.04 | 0 | 8822.96 | 745.43 | 0 | 0 | 0 | 0 | 9568.39 | 0 | 0 | 0 | 6357303.43 | 0 | 0 | 0 | 0 | 6357303.43 | 311236.79 | [5 empty] | N | DW5 | 46.23% | CM_WSI | 53.77%
401334 | Bradan A - Iron & Manganese Distribution WQ Improvements - Knockjarder Cluster | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWMD | Non OMG180 | MS5 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2018-03-31 | 2019-03-31 | South Ayrshire | 7858175 | 0 | -565446.03 | 26323.18 | 91419.67 | 548242.66 | 674239.68 | -965219.16 | -190440 | 4653.8 | 3824.4768 | 5309.0249 | 7672388.8 | 1484.5481 | 0 | 0 | 1484.5481 | 7673873.3481 | 375538.26 | [5 empty] | Y | CM_WSI | 17.82% | DW5 | 82.18% | [18 empty] | 1 | [46 empty] | 0
401335 | Bradan B - Iron - Manganese Distribution WQ Improvements - Irvine Cluster | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water | DWQR | SWMD | Water infrastructure | MS5 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2018-08-31 | 2019-03-31 | South Ayrshire | 9254841 | 0 | -292999.35 | 19123.95 | 76176.06 | 24037.1 | -8330060.49 | 1090074.55 | -7413648.18 | 0 | 0 | 0 | 1841192.82 | 0 | 0 | 0 | 0 | 1841192.82 | 76679 | [5 empty] | Y | CM_WSI | 100% | [20 empty] | 1 | [46 empty] | 0
401336 | Bradan B - Iron - Manganese Distribution WQ Improvements - Kilmarnock Cluster | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2012-04-30 | 2013-06-25 | South Ayrshire | 2784173 | 0 | 27722 | -146080.1 | 0 | 0 | 0 | 0 | -118358.1 | 0 | 0 | 0 | 2665814.9 | 0 | 0 | 0 | 0 | 2665814.9 | 311236.79 | [5 empty] | N | DW5 | 41.48% | CM_WSI | 58.52%
500005 | Bradan Incident - Pipe Bridge Testing & Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-04-24 | 2019-02-12 | 2019-02-25 | 2019-04-30 |  | South Ayrshire | 0 | 0 | 89898 | 203683.62 | 272171.38 | 207426 | -1098.16 | 0 | 772080.85 | 0 | 0 | 0 | 772080.85 | 0 | 0 | 0 | 0 | 772080.85 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403942 | Bradan Interim Resilience | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-09-25 | 2016-03-29 | 2016-04-04 | 2017-03-16 |  | South Ayrshire | 335975.53 | 0 | 464830.47 | 82986.42 | 66897.06 | 0 | 0 | 0 | 614713.95 | 0 | 0 | 0 | 950689.48 | 0 | 0 | 0 | 0 | 950689.48 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500040 | Bradan RSZ Cleaning Programme | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2015-04-13 | 2016-09-23 | 2016-09-26 | 2021-04-26 | 2021-08-05 | South Ayrshire | 0 | 0 | 312710 | 139433 | 627304 | 357720.08 | 212753.3 | 175467.62 | 1825388 | 329330.44 | 329330.44 | 418850.2502 | 2154718.44 | 89519.8102 | 0 | 0 | 89519.8102 | 2244238.2502 | 2266445.18 | [5 empty] | N | DW5FS | 100%
403309 | Bradan trunk main Cathodic protection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-06-06 | 2020-03-27 | 2020-05-05 | 2020-05-06 |  | South Ayrshire | 24000 | 0 | 37122.47 | 8892.53 | 142104 | 113520 | -8138.23 | -5177.34 | 288323.43 | 0 | 0 | 0 | 312323.43 | 0 | 0 | 0 | 0 | 312323.43 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500685 | Bradan Trunk Mains Permanent Bypasses | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-07-09 | 2028-02-14 | 2028-03-14 | 2028-06-05 |  | South Ayrshire | 0 | 0 | 416098 | 92035 | -10000 | 27820 | 12424.28 | -78934.16 | 459443.12 | 897032.86 | 0 | 0 | 1356475.98 | 0 | 0 | 0 | 0 | 1356475.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501178 | Bradan WOA Amlaird WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-25 | 2028-02-02 | 2028-04-03 | 2028-10-13 |  | East Ayrshire | 0 | 0 | 0 | 20152.97 | 0 | 14304.76 | -804.9 | 0 | 33652.83 | 737408.04 | 0 | 0 | 771060.87 | 0 | 0 | 0 | 0 | 771060.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS3 | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2022-01-27 | 2022-03-22 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 816462.8 | 779493.2 | 1595956 | 2268746.97 | 2268746.97 | 684430.9045 | 3864702.97 | -1584316.0655 | 0 | 0 | -1584316.0655 | 2280386.9045 | 3607589.06 | [5 empty] | N | DW5MR | 100%
503632 | Bradan WQ Improvement Pennyburn Road DMA Mains Rehabilitation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS3 | 2020-03-04 | 2021-03-31 | 2020-11-09 | 2022-07-04 | 2022-08-24 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 45151.98 | 221307.81 | 266459.79 | 1496281.61 | 1496281.613 | 2039285.5116 | 1762741.4 | 543003.8986 | 0 | 0.0014 | 543003.9 | 2305745.3 | 0 | [5 empty] | Y | DW5MR | 100% | [19 empty] | 1 | [47 empty] | 0
512086 | Bradan WTW - 2RGF no 1 Puddle Joint | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-10-11 | 2021-12-31 | 2022-08-15 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509089 | Bradan WTW - Coag Lime Building Dust Seal | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-11-27 | 2022-04-08 | 2022-11-21 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4568 | 4568 | 16831.66 | 0 | 0 | 21399.66 | 0 | 0 | 0 | 0 | 21399.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509086 | Bradan WTW - Flow Meter Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-11-27 | 2021-07-01 | 2022-02-11 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253.72 | 253.72 | 144999.99 | 0 | 0 | 145253.71 | 0 | 0 | 0 | 0 | 145253.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507454 | Bradan WTW - Ortho Bund Refurb Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-10-08 | 2021-03-10 | 2022-01-13 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675.15 | 1675.15 | 0 | 0 | 0 | 1675.15 | 0 | 0 | 0 | 0 | 1675.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505699 | Bradan WTW - Redundant Final Sample Tap Removal Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-03 | 2020-08-14 | 2021-06-17 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332.68 | 332.68 | 5350 | 0 | 0 | 5682.68 | 0 | 0 | 0 | 0 | 5682.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504434 | Bradan WTW - Top and Bottom Generator Install | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-03-25 | 2021-01-25 | 2021-01-12 | 2021-11-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 47067.18 | 669287.82 | 716355 | 484876.6 | 0 | 0 | 1201231.6 | 0 | 0 | 180185.4 | 180185.4 | 1381417 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500709 | Bradan WTW CM | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2015-07-16 | 2017-03-30 | 2017-03-30 | 2021-10-11 | 2022-01-06 | South Ayrshire | 0 | 0 | 35821 | -6582.56 | 57931.55 | 165906.79 | 786390.22 | 339449 | 1378916 | 952071.95 | 704620.0718 | 924354.5026 | 2330987.95 | 219734.4308 | 0 | 43927.7191 | 263662.1499 | 2594650.0999 | 1698906.14 | [5 empty] | Y | CM_WSNI | 25.99% | DW25P | 74.01% | [19 empty] | 1 | [45 empty] | 0
403316 | Bradan WTW Essential Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-03-25 | 2013-03-25 | 2013-04-02 | 2018-12-10 |  | South Ayrshire | 980000 | 0 | 116583 | 47995.52 | 34000 | -14902.4 | -1605.18 | 0 | 182070.94 | 0 | 0 | 0 | 1162070.94 | 0 | 0 | 0 | 0 | 1162070.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502960 | Bradan WTW Filter Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS4 | 2017-11-07 | 2018-07-13 | 2018-07-13 | 2019-12-24 |  | South Ayrshire | 0 | 0 | 0 | 0 | 222976.29 | 4227444.63 | 2620332.56 | 83325.52 | 7154079 | 54775 | 0 | 0 | 7208854 | 0 | 0 | 0 | 0 | 7208854 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505395 | BRADAN WTW NX436993-WNI-Bradan WTW - Coag Lime Service Water Line Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-02-28 | 2020-09-10 | 2021-08-20 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17769 | 17769 | 3990.8 | 0 | 0 | 21759.8 | 0 | 0 | 0 | 0 | 21759.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
46266 | Bradan WTW Refurb - WTW000028 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-11-20 | 2010-11-26 | 2011-02-28 | 2014-09-16 |  | South Ayrshire | 1007295.56 | 0 | 1382.64 | -362 | 0 | 0 | 0 | 0 | 1020.64 | 0 | 0 | 0 | 1008316.2 | 0 | 0 | 0 | 0 | 1008316.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502412 | Bradan WTW Water Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2015-07-16 | 2017-03-13 | 2017-03-27 | 2021-06-25 | 2021-07-09 | South Ayrshire | 0 | 0 | 0 | 1151164.05 | 11277843.69 | 2270210.3 | 140076.56 | 47826.4 | 14887121 | 82609.12 | 82609.12 | 1571468.7055 | 14969730.12 | 1488859.5855 | 0 | 0 | 1488859.5855 | 16458589.7055 | 6258896.35 |  |  |  |  | 48000 | N | DW25PS | 33.33% | DW25P | 33.33% | DW2_S | 33.33%
403407 | Braeface Difgen | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water | SW | SWMD | Renewable power | MS6 | 2013-03-01 | 2013-03-01 | 2017-03-27 | 2018-03-31 | 2018-04-30 | Stirling | 758220.29 | 758220.29 | 54797.71 | -4385 | 824054.75 | 325972.81 | 90578.8 | 9251.65 | 1300270.71 | 169.35 | 169.35 | 235.0866 | 2058660.35 | 65.7366 | 0 | 0 | 65.7366 | 2058726.0866 | 0 | [5 empty] | Y | CC1W | 100% | [60 empty] | 0.74 | [6 empty] | 0
501185 | Braehead Larkhall SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2016-05-31 | 2017-09-15 | 2018-02-09 | 2018-11-30 |  | South Lanarkshire | 0 | 0 | 0 | 106074 | 719318 | 905838 | 9806 | -14052.45 | 1726983.55 | 0 | 0 | 0 | 1726983.55 | 0 | 0 | 0 | 0 | 1726983.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502557 | Braemar WTW - Interruptions to Supply | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-05-17 | 2029-02-27 | 2029-05-23 | 2029-12-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 57911.7 | 12332.11 | 2810.24 | 0 | 73054.04 | 666945.96 | 0 | 0 | 740000 | 0 | 0 | 0 | 0 | 740000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501210 | Braemar WTW QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS6 | 2017-03-20 | 2018-03-13 | 2018-07-27 | 2018-11-30 | 2019-03-31 | Aberdeenshire | 0 | 0 | 1440 | 25259.9 | 12692.1 | 157760.52 | 2059.87 | 745.61 | 199958 | 924.84 | 924.84 | 1283.8354 | 200882.84 | 358.9954 | 0 | 0 | 358.9954 | 201241.8354 | 44350.8 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
45312 | Braemar WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-23 | 2011-07-22 | 2012-01-19 | 2012-03-14 | Aberdeenshire | 202516.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202516.79 | 0 | 0 | 0 | 0 | 202516.79 | 0 | [6 empty] | DW13 | 100%
503322 | Braemar WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-05-01 | 2019-05-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 64479.32 | 0 | 0 | 64479.32 | 0 | 0 | 0 | 64479.32 | 0 | 0 | 0 | 0 | 64479.32 | 122419.09 | [5 empty] | N | SG1 | 100%
506772 | Braemorlich DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-26 | 2021-06-25 | 2022-02-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500875 | Braes Skye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-08-18 | 2017-07-25 | 2018-02-28 | 2018-05-31 | 2019-12-31 | Highland | 0 | 0 | 969 | 1179.65 | 3727.09 | 9278.21 | -344.83 | 0 | 14809.12 | 0 | 0 | 0 | 14809.12 | 0 | 0 | 0 | 0 | 14809.12 | 20559.44 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 3.05 | [43 empty] | 0
500934 | Brechin - Montrose Street Sewer - Emergency Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2015-10-07 | 2016-07-21 | 2016-08-26 | 2019-05-07 |  | Angus | 0 | 0 | 515113 | 781423.75 | 1282268.43 | 768277.25 | 138099.23 | 716.34 | 3485898 | 1230.8 | 0 | 0 | 3487128.8 | 0 | 0 | 0 | 0 | 3487128.8 | 418763.58 | [5 empty] | N | CM_WWI | 100%
500123 | Brechin DOA (DOA000645) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-11-24 | 2016-11-25 | 2018-11-29 | 2019-03-29 | Angus | 0 | 0 | 14782 | 19950 | 5490 | 7156 | -3181.16 | 0 | 44196.84 | 0 | 0 | 0 | 44196.84 | 0 | 0 | 0 | 0 | 44196.84 | 4617.88 | [5 empty] | N | EC01G | 39.74% | CS16D | 60.26%
500969 | Brechin Sewers Cluster | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2015-10-13 | 2021-08-20 | 2021-10-18 | 2022-05-24 |  | Angus | 0 | 0 | 3478.79 | 146.15 | 45.7 | 9.11 | 44216.25 | -47432.12 | 463.88 | 0 | 0 | 0 | 463.88 | 0 | 0 | 0 | 0 | 463.88 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45673 | Brechin STC Refurb - STC000075 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2010-12-21 | 2011-05-09 | 2013-03-28 |  | Angus | 451850.43 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 451856.43 | 0 | 0 | 0 | 0 | 451856.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
30115 | Brechin STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-11-12 | 2010-12-23 | 2011-03-07 | 2013-11-29 | 2013-12-12 | Angus | 2585102.49 | 0 | 234536.1 | 0 | 0 | 0 | 0 | 0 | 234536.1 | 0 | 0 | 0 | 2819638.59 | 0 | 0 | 0 | 0 | 2819638.59 | 119362.42 | [5 empty] | N | EC01A | 40% | CM_WWNI | 60%
502885 | Brechin WwTP SR15 CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-08-31 | 2023-05-31 | 2023-08-31 | 2024-06-11 |  | Angus | 0 | 0 | 0 | 0 | 47918.17 | 5647.33 | 12139.9 | 27294.6 | 93000 | 657000.08 | 0 | 0 | 750000.08 | 0 | 0 | 0 | 0 | 750000.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503564 | Brechin WwTW - Bio Filter Media Filter | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2019-10-02 | 2019-10-02 | 2020-08-24 | 2022-02-03 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 135851.49 | 1393144.47 | 1528995.96 | 916481.22 | 0 | 0 | 2445477.18 | 0 | 0 | 154522.82 | 154522.82 | 2600000 | 122419.09 | [5 empty] | N | SG1 | 100%
502333 | Brechin WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-06-06 | 2024-05-09 | 2024-08-12 | 2026-03-17 |  | Angus | 0 | 0 | 0 | 45288.41 | 16165.98 | 45692.12 | 12670.79 | 107459.69 | 227277 | 3100784.48 | 0 | 0 | 3328061.48 | 0 | 0 | 0 | 0 | 3328061.48 | 122419.09 | [5 empty] | N | SG1 | 100%
500856 | Bressay Shetland RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-06-01 | 2017-05-31 | 2017-08-07 | 2019-01-31 | 2019-08-31 | Shetland Islands | 0 | 0 | 1178.51 | 926.64 | 8874.98 | 18247.5 | 10334.04 | -439.16 | 39122.52 | 0 | 0 | 0 | 39122.52 | 0 | 0 | 0 | 0 | 39122.52 | 50429.66 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 7.66 | [43 empty] | 0
502775 | Bridge of Orchy - First Time Provision | IR18 | Supporting economic development | First Time Provision |  |  | Water |  | WINF | First Time Provision | MS0 | 2020-02-21 | 2022-07-25 | 2022-08-10 | 2023-11-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 12118.64 | 117033.87 | 66296.73 | 239155.78 | 434605.01 | 3315394.78 | 0 | 0 | 3749999.79 | 0 | 914471.5608 | 0 | 914471.5608 | 4664471.3508 | 1084027.07 | [5 empty] | N | WG3 | 100%
403068 | Bridge Street Cadell Place Bathgate Fauldhouse | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-11-21 | 2014-07-15 | 2014-07-16 | 2015-03-30 | 2015-03-30 | West Lothian | 511864 | 511864 | 16096 | -0.47 | -12652.83 | 0 | 0 | 0 | 3442.7 | 0 | 0 | 0 | 515306.7 | 0 | 0 | 0 | 0 | 515306.7 | 180449.74 | [5 empty] | N | FL_DD | 100%
402691 | Bridgend Water Supply - WQ Fe Failures | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-31 | 2013-09-24 | 2013-11-12 | 2014-11-04 |  | Aberdeenshire | 308442 | 0 | 8312 | -1648.43 | 0 | 0 | 0 | 0 | 6663.57 | 0 | 0 | 0 | 315105.57 | 0 | 0 | 0 | 0 | 315105.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511198 | Broadford WTW - PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-06-01 | 2023-12-08 | 2024-03-07 | 2025-02-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000.04 | 0 | 0 | 500000.04 | 0 | 0 | 0 | 0 | 500000.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503295 | Broadford WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2020-05-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 20233.02 | -19648.22 | 0 | 584.8 | 0 | 0 | 0 | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 122419.09 | [5 empty] | N | WG1 | 100%
30119 | Broadford WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-31 | 2011-10-17 | 2013-08-08 | 2015-03-06 | Highland | 232609.57 | 0 | 1846.82 | 0 | 0 | 0 | 0 | 0 | 1846.82 | 0 | 0 | 0 | 234456.39 | 0 | 0 | 0 | 0 | 234456.39 | 28761.13 | [5 empty] | N | DW13 | 100%
501834 | Broadside - Glenhead Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2027-07-15 | 2028-03-22 | 2028-06-19 | 2029-01-17 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439829.7 | 0 | 0 | 439829.7 | 0 | 0 | 0 | 0 | 439829.7 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402822 | Broadside to Braeface mains replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-11 | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | Falkirk | 52290 | 0 | -1735.32 | 0 | 0 | 0 | 0 | 0 | -1735.32 | 0 | 0 | 0 | 50554.68 | 0 | 0 | 0 | 0 | 50554.68 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401973 | Brockloch - Bradan WOA 250 mm HPPE Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-05-12 | 2016-03-31 | 2016-10-10 | 2017-10-06 |  | South Ayrshire | 34191 | 0 | 41708 | 83421 | -19430.88 | 0 | 0 | 0 | 105698.12 | 0 | 0 | 0 | 139889.12 | 0 | 0 | 0 | 0 | 139889.12 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503382 | Brodick WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-05-28 | 2020-05-28 | 2020-08-28 | 2020-08-28 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 64237.59 | 9628.18 | -8112.91 | 65752.86 | 0 | 0 | 0 | 65752.86 | 0 | 0 | 0 | 0 | 65752.86 | 122419.09 | [5 empty] | N | SG1 | 100%
403430 | Broomhill Avenue Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-04-18 | 2014-11-04 | 2014-11-04 | 2015-03-27 | 2015-03-27 | Aberdeenshire | 600114 | 600114 | 120977 | 0.48 | -1155.86 | 0 | 0 | 0 | 119821.62 | 0 | 0 | 0 | 719935.62 | 0 | 0 | 0 | 0 | 719935.62 | 180449.74 | [5 empty] | N | FL_DD | 100%
500117 | Brora DOA (DOA000456) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-03-30 | 2016-08-31 | 2019-07-31 | 2019-12-31 | Highland | 0 | 0 | 23507 | 3106 | 44279 | 40324 | 47725.88 | 962.49 | 159904.37 | 0 | 0 | 0 | 159904.37 | 0 | 0 | 0 | 0 | 159904.37 | 88730.58 | [5 empty] | Y | EC01G | 14.83% | EC01D | 85.17% | [38 empty] | 1 | [26 empty] | 0
509513 | Brora WwTW - FE Outfall Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-01 | 2022-04-01 | 2022-11-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.42 | 65.42 | 934.58 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 90601.29 | [5 empty] | N | WWNI | 100%
503722 | Brownhill Farm - Drongan DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-10-03 | 2020-08-31 | 2020-09-07 | 2021-04-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 17843.91 | 486659.09 | 504503 | 149608.76 | 0 | 0 | 654111.76 | 0 | 0 | 0 | 0 | 654111.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
300021 | Brownscroft Cottage Drainage | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-03-30 | 2011-08-30 | 2011-10-10 | 2012-02-20 |  | Aberdeenshire | 36835.17 | 0 | -642.63 | 0 | 0 | 0 | 0 | 0 | -642.63 | 0 | 0 | 0 | 36192.54 | 0 | 0 | 0 | 0 | 36192.54 | 209381.79 | [5 empty] | N | WWI | 100%
503511 | Bruce Embankment SPS Storm Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2019-12-03 | 2020-02-04 | 2020-03-09 | 2021-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 538526.6 | 464935.4 | 1003462 | 26903.14 | 0 | 0 | 1030365.14 | 0 | 0 | 0 | 0 | 1030365.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402990 | Brunswick Street Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2013-03-15 | 2013-11-18 | 2014-01-23 | 2014-01-23 | Glasgow City | 20060 | 0 | -316.06 | 0 | 0 | 0 | 0 | 0 | -316.06 | 0 | 0 | 0 | 19743.94 | 0 | 0 | 0 | 0 | 19743.94 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
402644 | Buchanan St SPS - Noise Issue | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-06-18 | 2012-06-18 | 2012-07-30 | 2017-01-02 |  | North Ayrshire | 649024.58 | 0 | 94390.42 | 7115.59 | 0 | 0 | 0 | 0 | 101506.01 | 0 | 0 | 0 | 750530.59 | 0 | 0 | 0 | 0 | 750530.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504375 | Buchanan Street WWPS - SPSO Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-01-07 |  | 2020-07-10 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 26376.7 | 70712.33 | 97089.03 | -7170.18 | 0 | 0 | 89918.85 | 0 | 0 | 0 | 0 | 89918.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502864 | Buchanan Street WwPS - SPSO Structural Surveys | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-08-28 | 2018-02-23 | 2018-02-26 | 2020-05-28 |  | North Ayrshire | 0 | 0 | 0 | 0 | 143775.04 | 19624.97 | 19600 | -2851.61 | 180148.4 | 0 | 0 | 0 | 180148.4 | 0 | 0 | 0 | 0 | 180148.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509983 | Building Condition Surveys W and WW West | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2020-12-14 | 2021-01-07 | 2021-05-17 | 2021-09-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34287 | 34287 | 165713.4 | 0 | 0 | 200000.4 | 0 | 0 | 0 | 0 | 200000.4 | 311236.79 | [5 empty] | N | CM_M&G | 100%
46245 | Buittle Reservoir - Freeboard | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-12-11 | 2010-10-04 | 2010-09-27 | 2011-02-01 | 2011-02-01 | Dumfries and Galloway | 129350.3 | 0 | 1.68 | 0 | 0 | 0 | 0 | 0 | 1.68 | 0 | 0 | 0 | 129351.98 | 0 | 0 | 0 | 0 | 129351.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500027 | Bunessan WOA - Iona Subsea Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-11-22 | 2017-06-21 | 2017-06-21 | 2017-06-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 502.5 | 911.25 | 0 | 0 | 0 | 0 | 1413.75 | 0 | 0 | 0 | 1413.75 | 0 | 0 | 0 | 0 | 1413.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506436 | Bunessan WOA - Iona Undersea Crossing II | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2020-07-16 | 2020-07-16 | 2020-08-20 | 2020-08-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
500642 | Bunessan WOA Iona Subsea Crossing (Clamshell Option) | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | SWMD | Supply Resilience | MS7 | 2015-06-23 | 2015-10-23 | 2016-03-14 | 2016-02-29 | 2016-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 709154 | 480481.06 | 4453.63 | 675.33 | 0 | 0 | 1194764.02 | 0 | 0 | 0 | 1194764.02 | 0 | 0 | 0 | 0 | 1194764.02 | 2300946.3 | [5 empty] | Y | CS16WR | 1.674% | CM_WSI | 98.33% | [22 empty] | 1 | [42 empty] | 0
500911 | Bunessan WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-11-24 | 2016-03-25 | 2016-03-25 | 2016-03-31 | 2016-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
507557 | Bunessan WTW - SCADA & PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2020-12-10 | 2023-02-15 | 2023-07-26 | 2025-02-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14407 | 14407 | 948599.28 | 0 | 0 | 963006.28 | 0 | 0 | 0 | 0 | 963006.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508976 | Burnbrae Gardens Clydebank | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2021-09-28 | 2023-03-28 | 2023-06-27 | 2024-04-16 | 2024-04-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20157.84 | 20157.84 | 313427.16 | 0 | 0 | 333585 | 0 | 0 | 0 | 0 | 333585 | 0 | [5 empty] | N | SR21_WW | 100%
500786 | Burncrooks Reservoir - Improve Stability of Retaining Wall | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-08-14 | 2016-03-07 | 2016-04-25 | 2016-05-03 |  | Stirling | 0 | 0 | 238924.93 | 272.45 | 0 | 0 | 0 | 0 | 239197.38 | 0 | 0 | 0 | 239197.38 | 0 | 0 | 0 | 0 | 239197.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508219 | Burncrooks Reservoir MIOS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-07-26 | 2023-06-12 | 2023-11-20 | 2025-06-02 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15773 | 15773 | 384226.63 | 0 | 0 | 399999.63 | 0 | 0 | 0 | 0 | 399999.63 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502556 | Burncrooks Round CWT capital maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-11-21 | 2019-06-27 | 2019-08-12 | 2021-08-12 |  | Stirling | 0 | 0 | 0 | 14408.37 | 23098.84 | 14095.14 | 37844.49 | 55196.16 | 144643 | 1000 | 0 | 0 | 145643 | 0 | 0 | 0 | 0 | 145643 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500697 | Burncrooks Supply Zone - Ortho Non Compliance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-07-15 | 2016-06-28 | 2016-07-22 | 2016-08-30 |  | Stirling | 0 | 0 | 2490 | 284341.33 | -831.33 | -102.16 | 0 | 0 | 285897.84 | 0 | 0 | 0 | 285897.84 | 0 | 0 | 0 | 0 | 285897.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503548 | Burncrooks WTW - Installation & Commissioning of Poly Activated Carbon Dosing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-04-29 | 2020-04-29 | 2020-10-14 | 2021-07-08 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 796.61 | 18827.1 | 19623.71 | 0 | 0 | 0 | 19623.71 | 0 | 0 | 0 | 0 | 19623.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502132 | Burncrooks WTW Quality THM Compliance | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | SEPA | WINF | DWQ Compliance | MS3 | 2016-03-17 | 2019-03-29 | 2019-03-29 | 2023-01-20 | 2023-04-17 | Stirling | 0 | 0 | 19141.6 | 189820.4 | 758551.95 | 5045526.27 | 15036021.52 | 6460245.11 | 27509306.85 | 9790365.15 | 5554074.1463 | 6981087.0698 | 37299671.99 | 1427012.9235 | 0 | 519381.9299 | 1946394.8534 | 39246066.8434 | 8497651.09 |  |  |  |  | 137222.3733 | N | WR1 | 2.01% | DW25P | 5.05% | CM_WSNI | 43.27% | DW2 | 49.67%
403900 | Burncrooks WTW Quality THM Compliance and Capital | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS7 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-06-01 | 2016-07-01 | Stirling | 576.81 | 393.9614 | 48350.75 | -48927.56 | 0 | 0 | 0 | 0 | -576.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WR1 | 100%
402998 | Burnmouth to Lamberton Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-22 | 2013-09-24 | 2014-02-07 | 2014-07-04 |  | Scottish Borders | 393397.08 | 0 | 3518.12 | 0 | 0 | 0 | 0 | 0 | 3518.12 | 0 | 0 | 0 | 396915.2 | 0 | 0 | 0 | 0 | 396915.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510506 | Burns Road - PLC Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-29 | 2021-08-18 | 2022-03-31 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.43 | 124.43 | 5350 | 0 | 0 | 5474.43 | 0 | 0 | 0 | 0 | 5474.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402848 | Burnside Cottage Long Road Avoch | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-08-15 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-23 | Highland | 204996 | 204996 | -32318 | -172677 | 0 | 0 | 0 | 0 | -204995 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 180449.74 | [5 empty] | N | FL_DD | 100%
503122 | Burnside Gate Hamilton | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2019-02-08 | 2020-07-29 | 2020-08-24 | 2021-03-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 266.18 | 188327.82 | 123108.35 | 470411.99 | 782114.34 | 0 | 0 | 0 | 782114.34 | 0 | 0 | 0 | 0 | 782114.34 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502579 | Burnside Place Coalburn Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 2017-03-15 |  | South Lanarkshire | 0 | 0 | 0 | 2209.57 | 228.35 | 212.9 | 0 | 0 | 2650.82 | 0 | 0 | 0 | 2650.82 | 0 | 0 | 0 | 0 | 2650.82 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45789 | Burnside Road SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-12-12 | 2012-02-13 | 2013-03-28 | 2013-03-29 | Dundee City | 730464.48 | 0 | -3196.05 | 0 | 0 | 0 | 0 | 0 | -3196.05 | 0 | 0 | 0 | 727268.43 | 0 | 0 | 0 | 0 | 727268.43 | 148123.55 | [5 empty] | N | WQ01B | 5% | CM_WWNI | 25% | WQ01C | 70%
500233 | Burrelton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS3 | 2018-09-04 | 2020-05-28 | 2021-01-27 | 2021-11-08 |  | Perth and Kinross | 0 | 0 | 51135.77 | 46906.81 | 27162.89 | 57031.53 | 251504.47 | 845320.25 | 1279061.72 | 671450.32 | 0 | 0 | 1950512.04 | 0 | 0 | 49695.96 | 49695.96 | 2000208 | 122419.09 | [5 empty] | N | SG1 | 100%
500049 | Busby WWPS | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2012-12-31 | 2016-12-20 | 2017-02-06 | 2017-12-31 | 2018-01-31 | East Renfrewshire | 0 | 0 | 61000 | 239240 | 194480 | 0 | -11086.49 | 0 | 483633.51 | 0 | 0 | 0 | 483633.51 | 0 | 0 | 0 | 0 | 483633.51 | 110618.07 | [5 empty] | Y | EC01F | 20.58% | CM_WWNI | 79.42% | [33 empty] | 1 | [31 empty] | 0
500674 | Business Insights | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS4 | 2015-06-05 | 2018-02-28 | 2018-02-28 | 2020-09-23 |  | Scottish Water Wide | 0 | 0 | 216302 | 531415 | 1123073.78 | 1238451.23 | 1281607.6 | 594042.39 | 4984892 | 0 | 0 | 0 | 4984892 | 0 | 0 | 0 | 0 | 4984892 | 613322.63 | [5 empty] | N | CM_M&G | 100%
506422 | Business Management System | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS0 | 2020-06-23 | 2021-08-30 | 2021-10-01 | 2022-02-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266524.73 | 266524.73 | 746835.27 | 0 | 0 | 1013360 | 0 | 0 | 0 | 0 | 1013360 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500588 | Business Systems 2015 Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-09-25 | 2018-01-31 | 2018-01-31 | 2021-01-19 |  | Scottish Water Wide | 0 | 0 | 297862 | 493380.36 | 394478.48 | 9868.61 | 118371.2 | -15469.61 | 1298491.04 | 0 | 0 | 0 | 1298491.04 | 0 | 0 | 0 | 0 | 1298491.04 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502587 | Buskhead Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-27 | 2027-11-24 | 2028-02-10 | 2028-06-26 |  | Angus | 0 | 0 | 0 | 5320 | 7880.79 | 1220.12 | 1359.6 | 0 | 15780.51 | 720852.49 | 0 | 0 | 736633 | 0 | 0 | 0 | 0 | 736633 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503608 | BW Sewer Misconnection Remediation | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS4 | 2019-09-30 | 2019-09-30 | 2019-11-18 | 2021-03-19 | 2021-07-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 197230 | 392230 | 770.4 | 770.4 | 1069.4464 | 393000.4 | 299.0464 | 0 | 0 | 299.0464 | 393299.4464 | 0 | [5 empty] | N | EC16 | 100%
504882 | Bypass Interventions West B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-02-03 | 2020-03-02 | 2021-06-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 15444.73 | 423490.64 | 438935.36 | 60189.98 | 0 | 0 | 499125.34 | 0 | 0 | 0 | 0 | 499125.34 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508789 | Bypass Interventions West C | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-09-24 | 2020-10-12 | 2021-05-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129891 | 129891 | 135810.22 | 0 | 0 | 265701.22 | 0 | 0 | 0 | 0 | 265701.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505661 | C19 Digital Preparations | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2020-07-29 | 2020-08-19 | 2020-08-19 | 2021-05-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 228131.54 | 147057.46 | 375189 | 0 | 0 | 0 | 375189 | 0 | 0 | 0 | 0 | 375189 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503529 | Caaf MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2019-06-12 | 2019-06-12 | 2019-07-15 | 2021-01-21 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 762424.2 | 40767.8 | 803192 | 2493.33 | 0 | 0 | 805685.33 | 0 | 0 | 0 | 0 | 805685.33 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403893 | Caaf Reservoir Breach (transfer from 402179) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-07-10 | 2015-01-29 | 2015-04-06 | 2018-10-22 |  | North Ayrshire | 108014.75 | 0 | 543674.25 | 34079 | 255500.42 | 13282.46 | 0 | 0 | 846536.13 | 0 | 0 | 0 | 954550.88 | 0 | 0 | 0 | 0 | 954550.88 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402179 | Caaf Reservoir Freeboard Improvement Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-14 | 2015-04-17 | 2014-08-14 | 2014-08-14 | 2014-08-14 | North Ayrshire | 735726 | 0 | 51.8 | 0 | 0 | 0 | 0 | 0 | 51.8 | 0 | 0 | 0 | 735777.8 | 0 | 0 | 0 | 0 | 735777.8 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508661 | Caaf Reservoir Spillway and Scour Control | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-09-14 | 2020-12-14 | 2020-12-17 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159206.09 | 159206.09 | 0 | 0 | 0 | 159206.09 | 0 | 0 | 0 | 0 | 159206.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401376 | Caddonfoot (Clovenfords) WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-11-08 | 2012-05-02 | 2012-08-27 | 2013-12-19 | 2013-12-19 | Scottish Borders | 1719185.32 | 0 | 1833.26 | 0 | 0 | 0 | 0 | 0 | 1833.26 | 0 | 0 | 0 | 1721018.58 | 0 | 0 | 0 | 0 | 1721018.58 | 0 | [5 empty] | N | SG1 | 100%
506702 | Cairnborrow Huntly DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-08-22 | 2023-10-09 | 2024-01-18 | 2024-12-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5393 | 5393 | 604606.57 | 0 | 0 | 609999.57 | 0 | 0 | 0 | 0 | 609999.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403910 | Cairnfield WSZ Main Out | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2014-10-24 | 2015-09-21 | 2015-11-30 | 2018-09-26 | 2018-09-26 | Aberdeen City | 13417 | 0 | 33649 | 9509.63 | 3052 | 147064.9 | 12963.62 | -5392.85 | 200846.3 | 0 | 0 | 0 | 214263.3 | 0 | 0 | 0 | 0 | 214263.3 | 0 | [5 empty] | N | WG5 | 100%
501567 | Cairnton RWI Pump - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-03-29 | 2021-12-20 | 2022-04-07 | 2023-07-05 |  | Aberdeen City | 0 | 0 | 5023.26 | 35993.26 | 59273.57 | 22834.85 | 77673.13 | 158158.17 | 358956.24 | 1421161.09 | 0 | 0 | 1780117.33 | 0 | 0 | 0 | 0 | 1780117.33 | 119022.58 | [5 empty] | N | CM_WSI | 100%
404096 | Calderwood Infrastructure Charge Funding | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2015-03-18 | 2015-03-18 | 2015-03-18 | 2016-10-13 | 2017-03-02 | West Lothian | 351960.59 | 0 | 5921.41 | 64118.12 | 0 | 0 | 0 | 0 | 70039.53 | 0 | 0 | 0 | 422000.12 | 0 | 0 | 0 | 0 | 422000.12 | 0 | [5 empty] | N | WG5 | 100%
402876 | California Drainage Network EPI Resolution | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-12-21 | 2017-06-30 | 2017-08-21 | 2018-05-30 |  | Falkirk | 26923 | 0 | 28893.64 | 114175.36 | 322796 | 42200.92 | 25.08 | -12027.9 | 496063.1 | 0 | 0 | 0 | 522986.1 | 0 | 0 | 0 | 0 | 522986.1 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402875 | Callander Drainage Network EPI Resolution Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-11 | 2016-02-29 | 2016-02-18 | 2016-02-19 |  | Stirling | 88246 | 0 | 8283.31 | 0 | 0 | 0 | 0 | 0 | 8283.31 | 0 | 0 | 0 | 96529.31 | 0 | 0 | 0 | 0 | 96529.31 | 628145.36 | [5 empty] | N | CM_M&G | 24% | CM_WWI | 76%
503307 | Callander WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-21 | 2029-06-21 | 2030-06-19 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 28915.3 | 6540.98 | -0.28 | 35456 | 0 | 0 | 0 | 35456 | 0 | 0 | 0 | 0 | 35456 | 122419.09 | [5 empty] | N | SG1 | 100%
500232 | Callanish WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2015-09-08 | 2015-09-08 | 2015-09-08 | 2015-08-19 | 2015-09-08 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG1 | 100%
501720 | Cambuslang SPS 2 RM - Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2019-03-13 | 2020-03-18 | 2020-07-27 | 2021-06-17 |  | Glasgow City | 0 | 0 | 0 | 6731.42 | 0 | 11432.22 | 252781.95 | 1226356.41 | 1497302 | 26584.96 | 0 | 0 | 1523886.96 | 0 | 0 | 9402.04 | 9402.04 | 1533289 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501161 | Cambuslang SPS No.1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2016-02-11 | 2017-06-05 | 2017-11-09 | 2018-10-31 |  | Glasgow City | 0 | 0 | 1126 | 114705 | 508928 | 144232 | 2500 | -23963.24 | 747527.76 | 23962.95 | 0 | 0 | 771490.71 | 0 | 0 | 0 | 0 | 771490.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501162 | Cambuslang SPS No.2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-02-17 | 2017-06-05 | 2017-11-09 | 2019-02-27 |  | Glasgow City | 0 | 0 | 858.64 | 92229.36 | 517442 | 188650 | 24067 | -26791.33 | 796455.67 | 28399.33 | 0 | 0 | 824855 | 0 | 0 | 0 | 0 | 824855 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510572 | Camieston DSR - Replacement Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-22 | 2021-07-16 | 2022-02-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3835.53 | 3835.53 | 24266.62 | 0 | 0 | 28102.15 | 0 | 0 | 0 | 0 | 28102.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509332 | Camisky CWT outlet sum modification | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-29 | 2021-06-08 | 2021-09-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3329.36 | 3329.36 | 16691.55 | 0 | 0 | 20020.91 | 0 | 0 | 0 | 0 | 20020.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507578 | Camisky WTW - SCADA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-01-28 | 2023-12-15 | 2024-05-24 | 2025-12-05 | 2026-03-09 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23992.9 | 23992.9 | 476034.78 | 0 | 0 | 500027.68 | 0 | 0 | 0 | 0 | 500027.68 | 0 | [5 empty] | N | SR21_WA | 100%
508845 | Camisky WTW Borehole 3 cleaning | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-09-24 | 2021-05-04 | 2021-09-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4466.66 | 4466.66 | 41818.57 | 0 | 0 | 46285.22 | 0 | 0 | 0 | 0 | 46285.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507003 | Camisky WTW Borehole power supply | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-06-11 | 2021-07-06 | 2021-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24138.36 | 24138.36 | 60882.99 | 0 | 0 | 85021.35 | 0 | 0 | 0 | 0 | 85021.35 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508300 | Camisky WTW high lift pump replacement and inspection | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-08-28 | 2022-01-17 | 2022-09-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3938.36 | 3938.36 | 36083.13 | 0 | 0 | 40021.49 | 0 | 0 | 0 | 0 | 40021.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506258 | Camisky WTW NRV refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-22 | 2020-07-24 | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187926.72 | 187926.72 | 38772.29 | 0 | 0 | 226699.01 | 0 | 0 | 0 | 0 | 226699.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506214 | Camisky WTW PLC and Scada modifications | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-17 | 2020-10-08 | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4772 | 4772 | 23792.15 | 0 | 0 | 28564.15 | 0 | 0 | 0 | 0 | 28564.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510711 | Camisky WTW telemtery alarm repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-20 | 2021-05-11 | 2021-07-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3636 | 3636 | 21364.48 | 0 | 0 | 25000.48 | 0 | 0 | 0 | 0 | 25000.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501112 | Campbeltown WOA Auchencorvie SDN | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-08-25 | 2020-04-24 | 2020-04-24 | 2019-06-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 18000 | 55006.2 | 553 | 0 | -4536.68 | -1280.84 | 67741.68 | 0 | 0 | 0 | 67741.68 | 0 | 0 | 0 | 0 | 67741.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403331 | Campbeltown WOA Southend Rehab - 6inch AC | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-19 | 2013-02-19 | 2013-03-01 | 2013-08-09 |  | Argyll and Bute-North Argyll | 631330.27 | 0 | 5661.45 | 0 | 0 | 0 | 0 | 0 | 5661.45 | 0 | 0 | 0 | 636991.72 | 0 | 0 | 0 | 0 | 636991.72 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505698 | Campbeltown WTW - pH Correction | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-08-02 | 2024-03-26 | 2024-06-25 | 2025-08-14 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8293.2 | 8293.2 | 991808.95 | 0 | 0 | 1000102.15 | 0 | 0 | 0 | 0 | 1000102.15 | 119022.58 | [5 empty] | N | WSNI | 100%
511811 | Campbeltown WwTW - Replace SHT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000.03 | 0 | 0 | 150000.03 | 0 | 0 | 0 | 0 | 150000.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502978 | Campbeltown WwTW - Replacement Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-12-14 | 2024-11-26 | 2025-03-25 | 2026-10-08 |  | Highland | 0 | 0 | 0 | 0 | 31695.59 | 1005.99 | 14461.37 | 151028.05 | 198191 | 2601808.71 | 0 | 0 | 2799999.71 | 0 | 0 | 0 | 0 | 2799999.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46246 | Camphill Reservoir - Drawdown facilities | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-01-05 | 2011-06-23 | 2011-07-22 | 2012-01-25 | 2012-01-25 | North Ayrshire | 284478.74 | 0 | 3.55 | 0 | 0 | 0 | 0 | 0 | 3.55 | 0 | 0 | 0 | 284482.29 | 0 | 0 | 0 | 0 | 284482.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506829 | Camphill Reservoir American Signal Crayfish Mitigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-07-05 | 2021-07-05 | 2022-02-14 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5518.89 | 5518.89 | 44481.11 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508135 | Camphill Reservoir Drain Repair | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-31 | 2021-09-09 | 2022-04-22 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6709 | 6709 | 38291.51 | 0 | 0 | 45000.51 | 0 | 0 | 0 | 0 | 45000.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509580 | Camphill Reservoir MIOS Ground investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-11-09 | 2021-02-08 | 2021-05-21 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18529 | 18529 | 1124.97 | 0 | 0 | 19653.97 | 0 | 0 | 0 | 0 | 19653.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511454 | Camphill Reservoir Spillway Bridge Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-03-03 | 2021-06-23 | 2022-02-03 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16028.04 | 16028.04 | 228971.96 | 0 | 0 | 245000 | 0 | 0 | 0 | 0 | 245000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503061 | Camphill Spillway Improvements and Drawdown Capacity Enhancement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-11-30 | 2021-09-20 | 2022-01-21 | 2024-03-14 |  | North Ayrshire | 0 | 0 | 0 | 0 | 6402.7 | 0 | 18380.26 | 55062.04 | 79845 | 741548.11 | 0 | 0 | 821393.11 | 0 | 0 | 0 | 0 | 821393.11 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503736 | Camphill to Bradan 21 Inch Main - Survey and Remedial Works | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | GW2 | 2021-04-01 | 2021-08-30 | 2021-11-08 | 2022-06-06 | 2022-07-28 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 694085.1228 | 500000 | 194085.1228 | 0 | 0 | 194085.1228 | 694085.1228 | 6258896.35 | [5 empty] | N | DW2_S | 50% | DW25P | 50%
502136 | Camphill WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-30 | 2017-11-10 | 2017-11-30 | 2017-07-31 | 2019-03-31 | North Ayrshire | 0 | 0 | 0 | 802.96 | 1239.68 | 85.17 | 0 | 0 | 2127.8 | 0 | 0 | 0 | 2127.8 | 0 | 0 | 0 | 0 | 2127.8 | 37826.8 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
402204 | Camphill WTW - Roof Collapse Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-07-19 | 2011-09-21 | 2011-10-17 | 2012-02-21 |  | North Ayrshire | 141431.12 | 0 | 374.85 | 0 | 0 | 0 | 0 | 0 | 374.85 | 0 | 0 | 0 | 141805.97 | 0 | 0 | 0 | 0 | 141805.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506983 | Camphill WTW- Filter Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-05-31 | 2024-04-16 | 2024-09-24 | 2026-04-07 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10648.61 | 10648.61 | 789351.39 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 800000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502785 | Camps Bridge - recycled project | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-02-28 | 2021-12-06 | 2022-06-02 | 2022-09-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 10670.11 | 19896.12 | 92541.6 | 49970.17 | 173078 | 634922.41 | 0 | 0 | 808000.41 | 0 | 0 | 0 | 0 | 808000.41 | 119022.58 | [5 empty] | N | CM_WSI | 100%
500016 | Camps DIR - Access Bridge | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2015-05-08 | 2019-07-31 | 2019-07-31 | 2019-07-31 |  | South Lanarkshire | 0 | 0 | 35428 | 52345.52 | -84612.51 | 76069.91 | -77451.87 | 0 | 1779.05 | -1779.04 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 306661.32 | [5 empty] | N | CM_M&G | 100%
511033 | Camps Reservoir additional Scour Valve Install | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS2 |  | 2021-02-25 | 2021-08-13 | 2022-03-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 14000 | 156000 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 170000 | 0 | [5 empty] | N | SR21_WA | 100%
508802 | Camps Reservoir Spillway Upgrade - TWL management | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 |  | 2020-09-22 | 2020-11-02 | 2021-12-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941 | 2941 | 7058.88 | 0 | 0 | 9999.88 | 0 | 0 | 0 | 0 | 9999.88 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511035 | Camps Reservoir Spring 2021 TWL control | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS2 |  | 2021-02-25 | 2021-08-13 | 2022-03-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 174999.95 | 0 | 0 | 189999.95 | 0 | 0 | 0 | 0 | 189999.95 | 0 | [5 empty] | N | SR21_WA | 100%
502735 | Camps Road Carnock | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-10-20 | 2019-02-21 | 2019-04-23 | 2021-08-17 |  | Fife | 0 | 0 | 0 | 0 | 22566 | 100133 | 237342 | 104433 | 464474 | 0 | 0 | 0 | 464474 | 0 | 0 | 0 | 0 | 464474 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501275 | Camps Windfarm | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MSU | 2019-12-05 | 2020-01-09 | 2019-12-05 | 2019-12-11 | 2019-12-11 | Scottish Water Wide | 0 | 0 | 0 | 41062.04 | -11907.62 | -19022.56 | -10131.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | I2S_WI | 100%
500038 | Camps WTW - Part refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2015-05-08 | 2020-11-02 | 2027-08-03 | 2027-09-13 |  | South Lanarkshire | 0 | 0 | 61609 | 148634.01 | 7216.62 | 0 | 0 | -28289.73 | 189169.91 | 0 | 0 | 0 | 189169.91 | 0 | 0 | 0 | 0 | 189169.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505057 | Camusterrach DOA - Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-03-10 |  | 2021-07-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2289.72 | 35872.13 | 38161.85 | 0 | 0 | 0 | 38161.85 | 0 | 0 | 0 | 0 | 38161.85 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504891 | Canal Road Inverurie DOA - Sewer Rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-02-17 | 2021-03-08 | 2021-09-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 9053.83 | 32955.53 | 42009.35 | 114990.65 | 0 | 0 | 157000 | 0 | 0 | 0 | 0 | 157000 | 209381.79 | [5 empty] | N | WWI | 100%
402123 | Cannich ST Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-05-27 | 2013-09-17 | 2013-10-21 | 2014-03-26 | 2014-03-26 | Highland | 490340 | 0 | 1445.71 | 0 | 0 | 0 | 0 | 0 | 1445.71 | 0 | 0 | 0 | 491785.71 | 0 | 0 | 0 | 0 | 491785.71 | 0 | [5 empty] | N | SG1 | 100%
510695 | Canonbie DSR 2 Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-08-19 | 2023-10-09 | 2024-01-17 | 2024-12-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 837.21 | 837.21 | 414892.43 | 0 | 0 | 415729.64 | 0 | 0 | 0 | 0 | 415729.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403465 | Canonbie ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-04-15 | 2015-04-23 | 2015-02-12 | 2015-02-12 | 2015-02-12 | Dumfries and Galloway | 660977.3 | 0 | 365.46 | 0 | 0 | 0 | 0 | 0 | 365.46 | 0 | 0 | 0 | 661342.76 | 0 | 0 | 0 | 0 | 661342.76 | 0 | [5 empty] | N | SG1 | 100%
403943 | Canonbie WwTW - Upgrade Growth (Transfer from 403465) | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2014-12-19 | 2019-08-26 | 2019-09-30 | 2021-08-23 |  | Dumfries and Galloway | 79731 | 0 | 254057 | 309429 | 502245 | 296718 | 1890846.27 | 2199310.04 | 5452605.3 | 1218548.65 | 0 | 0 | 6750884.95 | 0 | 0 | 249115.05 | 249115.05 | 7000000 | 0 | [5 empty] | N | SG1 | 100%
500597 | Cap Inv Alliance Management SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 1774532.76 | 1929016.3 | 1814460.46 | 1506491.79 | 1436329.2 | 1314644.24 | 9775474.75 | 0 | 0 | 0 | 9775474.75 | 0 | 0 | 0 | 0 | 9775474.75 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500598 | Cap Inv Asset Management Director SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 274139.35 | 499417.02 | 550632.43 | 1273989.17 | 748788.58 | 667349.13 | 4014315.68 | 0 | 0 | 0 | 4014315.68 | 0 | 0 | 0 | 0 | 4014315.68 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500599 | Cap Inv Capital Projects Completion SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 203924.34 | 201080.54 | -263805.04 | 0 | 0 | 0 | 141199.84 | 0 | 0 | 0 | 141199.84 | 0 | 0 | 0 | 0 | 141199.84 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500600 | Cap Inv Commercial SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 1049362.04 | 1633223.89 | 2100086.67 | 2488812.12 | 1766393.17 | 1935380.91 | 10973258.79 | 0 | 0 | 0 | 10973258.79 | 0 | 0 | 0 | 0 | 10973258.79 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500601 | Cap Inv Controller of Cap Inv SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 185856.56 | 9600.99 | 34494.69 | 31329.22 | -58016.19 | 36860.79 | 240126.05 | 0 | 0 | 0 | 240126.05 | 0 | 0 | 0 | 0 | 240126.05 | 306661.32 |  |  |  |  | 7362 | N | CM_OVH | 100%
500602 | Cap Inv Managed Delivery SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 1215211.18 | 1348764.06 | 940614.85 | 837785.73 | 801273.05 | 561982.84 | 5705631.71 | 0 | 0 | 0 | 5705631.71 | 0 | 0 | 0 | 0 | 5705631.71 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500603 | Cap Inv Portfolio Management SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 3480760.2 | 4556197.16 | 4912233.18 | 4815935.25 | 4444058.73 | 4333584.16 | 26542768.69 | 0 | 0 | 0 | 26542768.69 | 0 | 0 | 0 | 0 | 26542768.69 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500604 | Cap Inv Procurement & Supply Chain SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 1194333.15 | 1340614.23 | 1597066.93 | 1747431.29 | 1482306.32 | 1267467.06 | 8629218.98 | 0 | 0 | 0 | 8629218.98 | 0 | 0 | 0 | 0 | 8629218.98 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500605 | Cap Inv Specialist Services Commercial SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 297039.97 | 1038702.22 | 1634463.49 | 1345474.6 | 1396267.64 | 1702244.89 | 7414192.81 | 0 | 0 | 0 | 7414192.81 | 0 | 0 | 0 | 0 | 7414192.81 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500596 | Cap Inv Specialist Services Non-Comm SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 328648.62 | 274894.56 | 208045.43 | 245244.82 | 212520.32 | 190448.19 | 1459801.94 | 0 | 0 | 0 | 1459801.94 | 0 | 0 | 0 | 0 | 1459801.94 | 306661.32 | [5 empty] | N | CM_OVH | 100%
400736 | CAP MAINT SR10 PRV REPLACEMENT EAST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-04-21 | 2011-04-01 | 2015-07-02 |  | Scottish Water Wide | 667304.77 | 0 | 50190.75 | 827.2 | 0 | 0 | 0 | 0 | 51017.95 | 0 | 0 | 0 | 718322.72 | 0 | 0 | 0 | 0 | 718322.72 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400735 | CAP MAINT SR10 PRV REPLACEMENT WEST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-04-21 | 2010-04-21 | 2016-10-06 |  | Scottish Water Wide | 440186 | 0 | 12505.69 | 0 | 0 | 0 | 0 | 0 | 12505.69 | 0 | 0 | 0 | 452691.69 | 0 | 0 | 0 | 0 | 452691.69 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400397 | Cap Maint Water Infra Invercannie Aqueduct | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2001-02-25 | 2005-01-21 | 2005-02-21 | 2018-10-08 |  | Aberdeen City | -0.2 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311236.79 | [5 empty] | N | WSI | 100%
506467 | Capability Studies/ Assessments - I Jones - 85K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-05-06 |  | 2021-02-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23482.54 | 23482.54 | 61517.46 | 0 | 0 | 85000 | 0 | 0 | 0 | 0 | 85000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400753 | Capital Maintenance SR10 Service Reservoir Control East Leakage Delivery Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2011-04-29 | 2015-06-15 |  | Scottish Water Wide | 524000 | 0 | -15665.75 | 0 | 0 | 0 | 0 | 0 | -15665.75 | 0 | 0 | 0 | 508334.25 | 0 | 0 | 0 | 0 | 508334.25 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400754 | Capital Maintenance SR10 Service Reservoir Control West Leakage Delivery Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-06-21 | 2015-06-15 |  | Scottish Water Wide | 176973 | 0 | -671.15 | 0 | 0 | 0 | 0 | 0 | -671.15 | 0 | 0 | 0 | 176301.85 | 0 | 0 | 0 | 0 | 176301.85 | 311236.79 | [5 empty] | N | CM_WSI | 100%
30532 | Carbarns (Wishaw) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-02-19 | 2010-06-28 | 2010-10-04 | 2012-03-22 | 2012-03-26 | North Lanarkshire | 8631398.41 | 0 | 14242.54 | -14364.54 | 0 | 0 | 0 | 0 | -122 | 0 | 0 | 0 | 8631276.41 | 0 | 0 | 0 | 0 | 8631276.41 | 299303.77 | [5 empty] | N | SG1 | 4.005% | EC10A | 6.014% | EC04A | 18.65% | EC01A | 23.4% | CM_WWNI | 47.93%
500806 | Carbarns WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2016-07-19 | 2017-08-28 | 2017-06-12 | 2017-06-12 | 2017-06-12 | North Lanarkshire | 0 | 0 | 10836.78 | 91986.07 | 21321.91 | 0 | 0 | 0 | 124144.76 | 0 | 0 | 0 | 124144.76 | 0 | 0 | 0 | 0 | 124144.76 | 122419.09 | [5 empty] | N | SG1 | 100%
502584 | Carbarns WwTW - Inlet Screen Replacement | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS4 | 2017-03-07 | 2018-10-03 | 2018-10-15 | 2021-03-24 |  | North Lanarkshire | 0 | 0 | 0 | 4285.05 | 146534.61 | 696721.61 | 842614.59 | 546588.66 | 2236744.53 | 8338.18 | 0 | 0 | 2245082.71 | 0 | 0 | -82.71 | -82.71 | 2245000 | 122419.09 |  |  |  |  | 18113 | N | SG1 | 100%
506756 | Carbost (New) WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2023-02-28 | 2025-04-01 | 2025-07-01 | 2027-04-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12816 | 12816 | 4987184.35 | 0 | 0 | 5000000.35 | 0 | 0 | 0 | 0 | 5000000.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500857 | Carbost Skye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-08-17 | 2017-06-25 | 2018-02-02 | 2018-04-30 | 2018-12-31 | Highland | 0 | 0 | 978.55 | 911.7 | 8342.19 | 14327.03 | -1821.45 | 0 | 22738.02 | 0 | 0 | 0 | 22738.02 | 0 | 0 | 0 | 0 | 22738.02 | 4035.65 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 13.25 | [43 empty] | 0
502627 | Carbost WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 20930.23 | 291.13 | 2187.97 | -17356.48 | 0 | 6052.85 | 0 | 0 | 0 | 6052.85 | 0 | 0 | 0 | 0 | 6052.85 | 122419.09 | [5 empty] | N | WG1 | 100%
403528 | Cardowan Drive Stepps Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2013-07-12 | 2014-09-30 | 2014-11-10 | 2015-03-27 | 2015-03-27 | Glasgow City | 298317 | 298317 | -36304.44 | 74.61 | 0.01 | 66026.5 | 0 | 0 | 29796.68 | 0 | 0 | 0 | 328113.68 | 0 | 0 | 0 | 0 | 328113.68 | 180449.74 | [5 empty] | N | FL_DD | 100%
45562 | Cardrona STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-02-07 | 2011-05-09 | 2011-11-10 | 2011-11-17 | Scottish Borders | 519365.92 | 0 | 78.34 | 0 | 0 | 0 | 0 | 0 | 78.34 | 0 | 0 | 0 | 519444.26 | 0 | 0 | 0 | 0 | 519444.26 | 119362.42 | [5 empty] | N | WQ01 | 19.75% | CM_WWNI | 80.25%
502824 | Cardrona WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-06-02 | 2028-09-19 | 2029-01-10 | 2029-12-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 74056.35 | 14864.16 | 17434.57 | 17128.93 | 123484 | 0 | 0 | 0 | 123484 | 0 | 0 | 0 | 0 | 123484 | 122419.09 | [5 empty] | N | SG1 | 100%
502222 | Carfin Improvement Plan - Rollout of Network Access System | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-08-15 | 2016-08-15 | 2016-11-16 | 2017-07-20 |  | Scottish Water Wide | 0 | 0 | 0 | 566760 | -58287.71 | 0 | 0 | 0 | 508472.29 | 0 | 0 | 0 | 508472.29 | 0 | 0 | 0 | 0 | 508472.29 | 311236.79 | [5 empty] | N | CM_M&G | 100%
501554 | Carfin Incident - MD interventions | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-12-23 | 2015-12-23 | 2016-04-27 | 2022-08-10 |  | Scottish Water Wide | 0 | 0 | 400509 | 338338 | 7093756.8 | 1278126.75 | 23839.55 | 54228.9 | 9188799 | 29722.69 | 0 | 0 | 9218521.69 | 0 | 0 | 781478.31 | 781478.31 | 10000000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501555 | Carfin Incident - SWD interventions | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-12-23 | 2015-12-23 | 2016-02-01 | 2020-04-01 |  | Scottish Water Wide | 0 | 0 | 81 | 758928.19 | 173329.75 | 30761.06 | -131899.62 | 0 | 831200.38 | 0 | 0 | 0 | 831200.38 | 0 | 0 | 0 | 0 | 831200.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502398 | Carfin Incident Plan - Consultancy Support | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2020-08-19 | 2020-08-24 | 2020-08-27 | 2020-08-27 |  | Scottish Water Wide | 0 | 0 | 0 | 99300 | 1834927.88 | 336393.97 | 120165.21 | -17573.26 | 2373213.8 | 0 | 0 | 0 | 2373213.8 | 0 | 0 | 0 | 0 | 2373213.8 | 311236.79 | [5 empty] | N | CM_M&G | 100%
506210 | Cargen BH - Relocation of Ortho Plant | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-05 | 2020-10-30 | 2021-06-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41886 | 41886 | 12208.34 | 0 | 0 | 54094.34 | 0 | 0 | 0 | 0 | 54094.34 | 119022.58 | [5 empty] | N | WSNI | 100%
501212 | Cargen Borehole WTW - Improving WQ in Network (OMG5) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-01-28 | 2016-03-04 | 2016-03-07 | 2016-03-31 | 2016-06-30 | Dumfries and Galloway | 0 | 0 | 2527 | -2092.11 | 0 | 0 | 0 | 0 | 434.89 | 0 | 0 | 0 | 434.89 | 0 | 0 | 0 | 0 | 434.89 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
508283 | Cargen WTW - Inadequate Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-09-14 | 2021-03-23 | 2021-04-23 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095 | 1095 | 3905.32 | 0 | 0 | 5000.32 | 0 | 0 | 0 | 0 | 5000.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511766 | Cargen WTW - Welfare Facilities Provision | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-23 | 2021-09-15 | 2022-04-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168.25 | 168.25 | 109831.75 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 110000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501151 | Cargenbridge SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-06-14 | 2018-04-30 | 2018-10-18 | 2021-04-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 35966 | 306274 | 928796 | 484476.89 | 140829.17 | 1896342.06 | -13544.06 | 0 | 0 | 1882798 | 0 | 0 | 117202 | 117202 | 2000000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402933 | Carloway WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-10-23 | 2013-12-23 | 2015-05-18 | 2018-04-01 | 2018-04-01 | Na H-Eileanan an Iar | 38035 | 0 | 3315 | 90811.13 | 204932.6 | -169.48 | -107.56 | 0 | 298781.69 | 0 | 0 | 0 | 336816.69 | 0 | 0 | 0 | 0 | 336816.69 | 0 | [5 empty] | N | SG1 | 100%
403342 | Carluke (Mauldslie) - Overland sewer pipelines and pipebridges | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-04 | 2013-08-20 | 2013-08-20 | 2015-10-15 |  | South Lanarkshire | 1975828 | 0 | 36754 | 5977.45 | -26818.82 | 30.96 | 0 | 0 | 15943.59 | 0 | 0 | 0 | 1991771.59 | 0 | 0 | 0 | 0 | 1991771.59 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508264 | Carman Reservoir Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-31 | 2021-11-04 | 2022-04-22 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13465.63 | 13465.63 | 186778.31 | 0 | 0 | 200243.94 | 0 | 0 | 0 | 0 | 200243.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501163 | Carmyle SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-12-02 | 2017-06-05 | 2017-11-09 | 2019-02-27 |  | Glasgow City | 0 | 0 | 1438 | 74837 | 515613 | 163895 | 5204.45 | -18615.12 | 742372.33 | 18698.67 | 0 | 0 | 761071 | 0 | 0 | 0 | 0 | 761071 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502240 | Carmyle SPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-09-29 |  | Glasgow City | 0 | 0 | 0 | 9332.07 | 1681.32 | 0 | 2382.69 | -8011.73 | 5384.35 | 0 | 0 | 0 | 5384.35 | 0 | 0 | 0 | 0 | 5384.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
404089 | Carnac SPS - Main MCC Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-01-20 | 2015-03-27 | 2015-09-07 | 2016-06-16 |  | Highland | 12787.39 | 0 | 283932.61 | -35613.94 | 0 | 0 | 0 | 0 | 248318.67 | 0 | 0 | 0 | 261106.06 | 0 | 0 | 0 | 0 | 261106.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503079 | Carnethie Street Rosewell | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2020-04-28 | 2022-05-16 | 2022-08-26 | 2023-04-13 |  | Midlothian | 0 | 0 | 0 | 0 | 9700.06 | 7036.58 | 23541.25 | 38295.1 | 78573 | 740875.32 | 0 | 0 | 819448.32 | 0 | 0 | 0 | 0 | 819448.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503828 | Carnoustie Ravensby Rd SW Flap Valve (SVCD-MD) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2019-12-04 |  | 2020-03-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 17651.03 | 3503.49 | 21154.52 | 0 | 0 | 0 | 21154.52 | 0 | 0 | 0 | 0 | 21154.52 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502367 | Carradale TWP Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-04-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 17507.18 | 13935.17 | 687.06 | 0 | 0 | 32129.41 | 0 | 0 | 0 | 32129.41 | 0 | 0 | 0 | 0 | 32129.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503240 | Carradale WTW Treatment Issues | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2021-02-08 | 2021-02-22 | 2021-04-01 | 2021-04-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 4790.28 | 37148.26 | -35176.16 | 6762.38 | 0 | 0 | 0 | 6762.38 | 0 | 0 | 0 | 0 | 6762.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
45315 | Carradale WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2013-03-22 | 2013-09-06 | Argyll and Bute-North Argyll | 267842.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267842.49 | 0 | 0 | 0 | 0 | 267842.49 | 0 | [6 empty] | DW13 | 100%
505028 | Carrbridge WwTW - RAS/SAS Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-01 | 2022-10-17 | 2023-05-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 261.68 | 5707.32 | 5969 | 91030.44 | 0 | 0 | 96999.44 | 0 | 0 | 0 | 0 | 96999.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506516 | Carriston Lower DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-03-31 | 2023-05-18 | 2023-08-24 | 2024-07-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1533.03 | 1533.03 | 568466.97 | 0 | 0 | 570000 | 0 | 0 | 0 | 0 | 570000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502598 | Carron Valley CWTs Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2017-06-30 | 2018-06-28 | 2018-07-16 | 2019-05-30 |  | Falkirk | 0 | 0 | 0 | 1709.09 | 178429.55 | 1015727.85 | 10204.51 | -38508.61 | 1167562.39 | 0 | 0 | 0 | 1167562.39 | 0 | 0 | 0 | 0 | 1167562.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502276 | Carron Valley IOS Works | IR18 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water | DWQR | SWMD | Reservoirs | MS6 | 2017-04-04 | 2018-07-30 | 2018-08-06 | 2020-03-12 | 2020-04-30 | Stirling | 0 | 0 | 0 | 8222.26 | 17414.74 | 836163.79 | 85533.83 | 5719.24 | 953053.86 | 1382.64 | 0 | 0 | 954436.5 | 0 | 381.3678 | 0 | 381.3678 | 954817.8678 | 620599.9 | [5 empty] | Y | WR6 | 100% | [30 empty] | 1 | [36 empty] | 0
507706 | Carron Valley Reservoir Drawdown Improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-05-26 | 2024-01-19 | 2024-04-18 | 2025-06-09 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7447 | 7447 | 992553.03 | 0 | 0 | 1000000.03 | 0 | 0 | 0 | 0 | 1000000.03 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503250 | Carron Valley RSZ Cleaning Flushing | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS3 | 2018-06-28 | 2019-06-21 | 2019-09-11 | 2021-07-30 | 2022-07-28 | Stirling | 0 | 0 | 0 | 0 | 0 | 541245 | 725018.24 | 345676.76 | 1611940 | 220688.87 | 312320 | 312320 | 1832628.87 | 0 | 91631.13 | 0 | 91631.13 | 1924260 | 1464613.17 | [5 empty] | N | DW5FS | 100%
502605 | Carron Valley RSZ Cleaning - Mains Conditioning | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS3 | 2018-06-28 | 2019-06-11 | 2019-08-02 | 2021-09-30 | 2022-04-29 | Stirling | 0 | 0 | 0 | 46297 | 189763.03 | 154348.98 | 259526.19 | 349199.81 | 999135 | 147939.56 | 205293 | 205293 | 1147074.56 | 0 | 57353.44 | 0 | 57353.44 | 1204428 | 3353220.77 | [5 empty] | N | DW5MC | 100%
501089 | Carron Valley WOA Banton WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-04-13 | 2018-09-06 | 2018-09-17 | 2019-02-11 |  | Falkirk | 0 | 0 | 6048 | 5410.17 | 70355.83 | 335435.14 | 5550.61 | -2297.66 | 420502.09 | 0 | 0 | 0 | 420502.09 | 0 | 0 | 0 | 0 | 420502.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500013 | Carron Valley WOA Beltmoss WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-19 | 2028-03-16 | 2028-05-19 | 2029-01-22 |  | Falkirk | 716 | 0 | 24477 | 2326 | 0 | 13742 | -6050.12 | 734.41 | 35229.29 | 319421.71 | 0 | 0 | 355367 | 0 | 0 | 0 | 0 | 355367 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501088 | Carron Valley WOA Drumtrocher WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-13 | 2028-03-09 | 2028-05-12 | 2029-01-15 |  | Falkirk | 0 | 0 | 0 | 10138.89 | 3861.11 | 5778 | -4607.75 | 0 | 15170.25 | 723754.04 | 0 | 0 | 738924.29 | 0 | 0 | 0 | 0 | 738924.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501087 | Carron Valley WOA Little Denny WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
500105 | Carron Valley WOA Parkhead WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-04-13 | 2017-01-25 | 2017-01-25 | 2018-02-21 |  | Falkirk | 0 | 0 | 40069 | 644286 | 351224 | 327051.01 | -54909.93 | 0 | 1307720.08 | 0 | 0 | 0 | 1307720.08 | 0 | 0 | 0 | 0 | 1307720.08 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500061 | Carron Valley WTW - Broadside Landfill | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-05-08 | 2027-06-10 | 2027-08-05 | 2028-11-27 |  | Falkirk | 0 | 0 | 45283 | 55525.4 | -5579.15 | -1545.93 | -1619.83 | 1929.99 | 93993.49 | 1469010.16 | 0 | 0 | 1563003.65 | 0 | 0 | 0 | 0 | 1563003.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508072 | Carronside SW WWPS - Wet well clean & pump replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-08-20 | 2021-07-08 | 2021-11-26 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29106 | 29106 | 45894.09 | 0 | 0 | 75000.09 | 0 | 0 | 0 | 0 | 75000.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505553 | Carsphairn Auto Shutdown Low Chlorine | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS4 | 2020-03-19 | 2020-03-23 | 2020-03-23 | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 215.3 | 663.35 | 878.65 | 0 | 0 | 0 | 878.65 | 0 | 0 | 0 | 0 | 878.65 | 214171.41 | [5 empty] | Y | DW25P | 100% | [67 empty] | 0
500478 | Carsphairn WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS5 | 2016-12-13 | 2018-03-30 | 2018-08-13 |  | 2021-03-31 | Dumfries and Galloway | 0 | 0 | 11106.06 | 19425.05 | 18815.94 | 61230.85 | 199821.05 | 49125.27 | 359524.22 | 125183.28 | 125183.28 | 173775.7046 | 484707.5 | 48592.4246 | 0 | 0 | 48592.4246 | 533299.9246 | 214171.41 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
511932 | Carsphairn WTW - Welfare Facilities Provision | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.42 | 65.42 | 67434.58 | 0 | 0 | 67500 | 0 | 0 | 0 | 0 | 67500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508278 | Carsphairn WTW - Inadequate Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-09-09 | 2021-03-08 | 2021-04-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2132 | 2132 | 2868.45 | 0 | 0 | 5000.45 | 0 | 0 | 0 | 0 | 5000.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
30136 | Carstairs Village STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-15 | 2010-12-30 | 2011-02-14 | 2011-12-21 | 2012-03-02 | North Lanarkshire | 1317525.88 | 0 | 1380.88 | 0 | 0 | 0 | 0 | 0 | 1380.88 | 0 | 0 | 0 | 1318906.76 | 0 | 0 | 0 | 0 | 1318906.76 | 28761.13 | [5 empty] | N | EC04A | 100%
500052 | Carstairs Village WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-07-07 | 2019-08-30 | 2020-01-13 | 2022-05-10 |  | South Lanarkshire | 0 | 0 | 54006.59 | 101633.03 | 403261 | 378898.83 | 803459.82 | 1431082.73 | 3172342 | 3733119.01 | 0 | 0 | 6905461.01 | 0 | 0 | 1094538.99 | 1094538.99 | 8000000 | 122419.09 | [5 empty] | N | SG1 | 100%
400067 | Cartland ST Zero Carbon Pilot Plant | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-09-24 | 2012-01-24 | 2012-02-06 | 2013-03-01 | 2013-03-27 | South Lanarkshire | 1669686.31 | 0 | 89751.58 | -29024.87 | 0 | 0 | 0 | 0 | 60726.71 | 0 | 0 | 0 | 1730413.02 | 0 | 0 | 0 | 0 | 1730413.02 | 86283.39 |  |  |  |  | 16632 | N | EC10A | 33.33% | SG3 | 33.33% | EC04A | 33.33%
502169 | Cartmoor Burn Scone | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-05-06 | 2017-02-03 | 2017-03-17 | 2017-06-30 |  | Perth and Kinross | 0 | 0 | 0 | 79196 | 65961 | 8549.36 | -2236.47 | 0 | 151469.89 | 0 | 0 | 0 | 151469.89 | 0 | 0 | 0 | 0 | 151469.89 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500119 | Castle Douglas DOA (DOA000097) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-01-19 | 2016-03-21 | 2017-07-25 | 2017-08-30 | Dumfries and Galloway | 0 | 0 | 24256 | 106458.72 | 7380.49 | -2383.68 | 0 | 0 | 135711.53 | 0 | 0 | 0 | 135711.53 | 0 | 0 | 0 | 0 | 135711.53 | 52680.68 | [5 empty] | N | CS16D | 50% | EC01D | 50%
503314 | Castle Douglas WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-04-25 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 29390.39 | 0 | 0 | 29390.39 | 0 | 0 | 0 | 29390.39 | 0 | 0 | 0 | 0 | 29390.39 | 122419.09 | [5 empty] | N | SG1 | 100%
512003 | Castle Golf Course Sewer St Andrews | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2022-03-28 | 2023-10-04 | 2024-01-02 | 2024-12-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18669.77 | 18669.77 | 731330.23 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 750000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
404117 | Castle House Meeting Rms Refurbishment | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-07-10 |  | Fife | 80000 | 0 | 5617.98 | 0 | 0 | 0 | 0 | 0 | 5617.98 | 0 | 0 | 0 | 85617.98 | 0 | 0 | 0 | 0 | 85617.98 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501657 | Castle St-Mount Pleasant Rothesay - Relay sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2016-06-29 | 2017-05-25 | 2017-05-29 | 2018-03-14 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 9173.02 | 139370.48 | -36968.98 | -7266.58 | 0 | 104307.94 | 0 | 0 | 0 | 104307.94 | 0 | 0 | 0 | 0 | 104307.94 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500991 | Castle Street Dingwall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-10-21 | 2017-05-09 | 2017-06-30 | 2018-04-30 |  | Highland | 0 | 0 | 10755 | 94268 | 153803 | 15554.63 | 0 | -24185.55 | 250195.08 | 0 | 0 | 0 | 250195.08 | 0 | 0 | 0 | 0 | 250195.08 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400058 | Castlegreen SPS Refurb SPS000108 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2012-01-24 | 2012-04-23 | 2013-01-16 |  | West Dunbartonshire | 876403.11 | 0 | -52.2 | 0 | 0 | 0 | 0 | 0 | -52.2 | 0 | 0 | 0 | 876350.91 | 0 | 0 | 0 | 0 | 876350.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510008 | Castlehill Reservoir - Pressure Relief Pipe Cleaning | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-04-12 | 2021-07-02 | 2022-02-14 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369.35 | 369.35 | 39642.82 | 0 | 0 | 40012.17 | 0 | 0 | 0 | 0 | 40012.17 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501529 | Castlemilk High SR Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS7 | 2016-12-23 | 2018-03-09 | 2018-04-04 | 2019-01-31 |  | Glasgow City | 0 | 0 | 0 | 3385.88 | 160839.22 | 774041.83 | -79573.73 | -29641.69 | 829051.51 | 0 | 0 | 0 | 829051.51 | 0 | 0 | 0 | 0 | 829051.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402775 | Cat 2 Access improvements at 8nr package SPS - North | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-07-16 | 2013-06-19 | 2013-10-16 | 2016-03-21 |  | Highland | 657779 | 0 | 87436 | -22476.02 | 0 | 0 | 0 | 0 | 64959.98 | 0 | 0 | 0 | 722738.98 | 0 | 0 | 0 | 0 | 722738.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500031 | Catchment Assessment Study for Drinking Water Quality Protection | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-02-27 | 2015-07-17 | 2015-07-27 | 2017-07-01 | 2017-07-14 | Scottish Water Wide | 153.33 | 153.33 | 126569.65 | 38277.02 | 8613.7 | -10136.01 | 0 | 0 | 163324.36 | 0 | 0 | 0 | 163477.69 | 0 | 0 | 0 | 0 | 163477.69 | 300888.64 | [5 empty] | N | DW25PS | 100%
502967 | Catherinefield Road SPS RM | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 12576.16 | 13056.58 | 0 | 0 | 25632.74 | 0 | 0 | 0 | 25632.74 | 0 | 0 | 0 | 0 | 25632.74 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501588 | Cathodic Protection Dunblane to North Third | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-08 | 2027-11-10 | 2027-12-30 | 2028-07-26 |  | Falkirk | 0 | 0 | 0 | 3865.55 | 0 | 2000.09 | 295.34 | -2295.43 | 3865.55 | 285349.44 | 0 | 0 | 289214.99 | 0 | 0 | 0 | 0 | 289214.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501812 | Cathodic Protection Quarter to Millhall Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-08 | 2027-11-10 | 2027-12-30 | 2028-07-26 |  | Falkirk | 0 | 0 | 0 | 13522.28 | -8206.31 | 2000.31 | 365.85 | -2366.16 | 5315.97 | 354337.03 | 0 | 0 | 359653 | 0 | 0 | 0 | 0 | 359653 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507933 | Catrineholm WwTW- Emergency Project to Maintain CAR Licence Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2020-08-03 | 2021-07-05 | 2021-11-03 | 2022-05-04 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41562.69 | 41562.69 | 858437.31 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
30138 | Catrineholm (Catrine) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2011-07-01 | 2011-07-25 | 2016-09-29 | 2016-03-29 | East Ayrshire | 1939092.84 | 0 | 2222069.07 | 828721 | -391.78 | -5747.28 | 0 | 0 | 3044651.01 | 0 | 0 | 0 | 4983743.85 | 0 | 0 | 0 | 0 | 4983743.85 | 119362.42 | [5 empty] | N | CM_WWNI | 25% | EC04A | 75%
401912 | Causewayend Private Water Supply Improvements | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-03-22 | 2011-09-05 | 2011-09-05 | 2012-07-31 | 2015-06-22 | West Lothian | 112498 | 0 | 23216 | 17662.7 | -1450.13 | 0 | 0 | 0 | 39428.57 | 0 | 0 | 0 | 151926.57 | 0 | 0 | 0 | 0 | 151926.57 | 0 | [5 empty] | N | DW10 | 100%
500303 | CC Dom Wastewater Aberdeen City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Aberdeen City | 0 | 0 | 254224.19 | 544716.15 | 692967.54 | 1268171.26 | 886475.95 | 405289.16 | 4051844.25 | 0 | 0 | 0 | 4051844.25 | 0 | 0 | 0 | 0 | 4051844.25 | 1011948.65 | [5 empty] | N | SG2 | 100%
500304 | CC Dom Wastewater Aberdeenshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-04-30 |  | Aberdeenshire | 0 | 0 | 2020013.3 | 1091246.23 | 310401.06 | 1678995.2 | 698595.31 | 367100.42 | 6166351.52 | 0 | 0 | 0 | 6166351.52 | 0 | 0 | 0 | 0 | 6166351.52 | 1011948.65 | [5 empty] | N | SG2 | 100%
500305 | CC Dom Wastewater Angus (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Angus | 0 | 0 | 21522.26 | 16661.26 | 479084.16 | 162543.39 | 2874.93 | 37637.45 | 720323.44 | 0 | 0 | 0 | 720323.44 | 0 | 0 | 0 | 0 | 720323.44 | 1011948.65 | [5 empty] | N | SG2 | 100%
500306 | CC Dom Wastewater Argyll and Bute (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 98082.67 | 76627.67 | 128.21 | 29777.78 | 63280.98 | 267897.31 | 0 | 0 | 0 | 267897.31 | 0 | 0 | 0 | 0 | 267897.31 | 1011948.65 | [5 empty] | N | SG2 | 100%
500307 | CC Dom Wastewater Borders (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Scottish Borders | 0 | 0 | 9514.16 | 26792.35 | 30109.49 | 358603.49 | 171153.48 | 19245.09 | 615418.06 | 0 | 0 | 0 | 615418.06 | 0 | 0 | 0 | 0 | 615418.06 | 1011948.65 | [5 empty] | N | SG2 | 100%
500308 | CC Dom Wastewater Clackmannan (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Clackmannanshire | 0 | 0 | 54538.61 | 30267.08 | 222971.46 | 37093.97 | 610.64 | 163165.18 | 508646.94 | 0 | 0 | 0 | 508646.94 | 0 | 0 | 0 | 0 | 508646.94 | 1011948.65 | [5 empty] | N | SG2 | 100%
500309 | CC Dom Wastewater Dumfries and Galloway (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Dumfries and Galloway | 0 | 0 | 28905.21 | 150914.7 | 47019.63 | 17885.22 | 64091.33 | 589.36 | 309405.45 | 0 | 0 | 0 | 309405.45 | 0 | 0 | 0 | 0 | 309405.45 | 1011948.65 | [5 empty] | N | SG2 | 100%
500310 | CC Dom Wastewater Dundee City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Dundee City | 0 | 0 | 66288.53 | 94544.33 | 58972.54 | 302518.83 | 67275.67 | 117463.83 | 707063.73 | 0 | 0 | 0 | 707063.73 | 0 | 0 | 0 | 0 | 707063.73 | 1011948.65 | [5 empty] | N | SG2 | 100%
500311 | CC Dom Wastewater East Ayrshire(2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | East Ayrshire | 0 | 0 | 280489.15 | 321981.45 | 92805.26 | 91502.54 | 151961.81 | 88292.18 | 1027032.39 | 0 | 0 | 0 | 1027032.39 | 0 | 0 | 0 | 0 | 1027032.39 | 1011948.65 | [5 empty] | N | SG2 | 100%
500312 | CC Dom Wastewater East Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | East Dunbartonshire | 0 | 0 | 56046.76 | 1040136.62 | 124499.1 | 885950.63 | 421320.98 | 338948.1 | 2866902.19 | 0 | 0 | 0 | 2866902.19 | 0 | 0 | 0 | 0 | 2866902.19 | 1011948.65 | [5 empty] | N | SG2 | 100%
500314 | CC Dom Wastewater East Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | East Renfrewshire | 0 | 0 | 75241.12 | 218545.95 | 158046.77 | 2332741.98 | 31012.91 | 226452.55 | 3042041.28 | 0 | 0 | 0 | 3042041.28 | 0 | 0 | 0 | 0 | 3042041.28 | 1011948.65 | [5 empty] | N | SG2 | 100%
500315 | CC Dom Wastewater Edinburgh City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | City of Edinburgh | 0 | 0 | 242058.68 | 859110.26 | 622915.13 | 1412193.36 | 518165.34 | 1507930.18 | 5162372.95 | 0 | 0 | 0 | 5162372.95 | 0 | 0 | 0 | 0 | 5162372.95 | 1011948.65 | [5 empty] | N | SG2 | 100%
500316 | CC Dom Wastewater Falkirk (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Falkirk | 0 | 0 | 685598.42 | 283684.21 | 183599.29 | 1658746.26 | 190739.44 | 563137.82 | 3565505.45 | 0 | 0 | 0 | 3565505.45 | 0 | 0 | 0 | 0 | 3565505.45 | 1011948.65 | [5 empty] | N | SG2 | 100%
500317 | CC Dom Wastewater Fife (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Fife | 0 | 0 | 150300.27 | 340500.72 | 358938.91 | 800041.95 | 523761 | 468906.12 | 2642448.97 | 0 | 0 | 0 | 2642448.97 | 0 | 0 | 0 | 0 | 2642448.97 | 1011948.65 | [5 empty] | N | SG2 | 100%
500318 | CC Dom Wastewater Glasgow City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Glasgow City | 0 | 0 | 682112.31 | 892085.69 | 991262.39 | 904494.88 | 1038583.18 | 1120538.25 | 5629076.7 | 0 | 0 | 0 | 5629076.7 | 0 | 0 | 0 | 0 | 5629076.7 | 1011948.65 | [5 empty] | N | SG2 | 100%
500319 | CC Dom Wastewater Highland (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Highland | 0 | 0 | 1030869.59 | 689020.41 | -29432.39 | 543262.7 | 1095294.01 | 193663.17 | 3522677.49 | 0 | 0 | 0 | 3522677.49 | 0 | 0 | 0 | 0 | 3522677.49 | 1011948.65 | [5 empty] | N | SG2 | 100%
500320 | CC Dom Wastewater Inverclyde (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Inverclyde | 0 | 0 | 257553.29 | 240311.07 | 16405.55 | 74627.52 | 110268.56 | 160572.75 | 859738.73 | 0 | 0 | 0 | 859738.73 | 0 | 0 | 0 | 0 | 859738.73 | 1011948.65 | [5 empty] | N | SG2 | 100%
500321 | CC Dom Wastewater Midlothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Midlothian | 0 | 0 | 384664.79 | 871358.43 | 588529.28 | 569016.61 | 940721.52 | 418476.31 | 3772766.94 | 0 | 0 | 0 | 3772766.94 | 0 | 0 | 0 | 0 | 3772766.94 | 1011948.65 | [5 empty] | N | SG2 | 100%
500322 | CC Dom Wastewater Moray (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Moray | 0 | 0 | 807072.06 | 33976.31 | -14445.99 | 134255.05 | 35619.66 | 56671.33 | 1053148.42 | 0 | 0 | 0 | 1053148.42 | 0 | 0 | 0 | 0 | 1053148.42 | 1011948.65 | [5 empty] | N | SG2 | 100%
500323 | CC Dom Wastewater Na H-Eileanan an Iar (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 185611.68 | 19525.26 | 0 | -0.27 | 0 | 205136.67 | 0 | 0 | 0 | 205136.67 | 0 | 0 | 0 | 0 | 205136.67 | 1011948.65 | [5 empty] | N | SG2 | 100%
500324 | CC Dom Wastewater North Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | North Ayrshire | 0 | 0 | 268608.65 | 43792.6 | 223003.54 | 67380.08 | 0 | 429659.09 | 1032443.96 | 0 | 0 | 0 | 1032443.96 | 0 | 0 | 0 | 0 | 1032443.96 | 1011948.65 | [5 empty] | N | SG2 | 100%
500325 | CC Dom Wastewater North Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | North Lanarkshire | 0 | 0 | 592093.94 | 582885.44 | 422669.22 | 1138659.03 | 713779.03 | 1153414.59 | 4603501.26 | 0 | 0 | 0 | 4603501.26 | 0 | 0 | 0 | 0 | 4603501.26 | 1011948.65 | [5 empty] | N | SG2 | 100%
500326 | CC Dom Wastewater Orkney Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Orkney Islands | 0 | 0 | 20133.36 | 199627.9 | 23049.18 | 24305.76 | 67768.77 | 37432.87 | 372317.84 | 0 | 0 | 0 | 372317.84 | 0 | 0 | 0 | 0 | 372317.84 | 1011948.65 | [5 empty] | N | SG2 | 100%
500327 | CC Dom Wastewater Perth and Kinross (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Perth and Kinross | 0 | 0 | 72711.5 | 521075.4 | 177505 | 101391.53 | 257313.02 | 536279.05 | 1666275.49 | 0 | 0 | 0 | 1666275.49 | 0 | 0 | 0 | 0 | 1666275.49 | 1011948.65 | [5 empty] | N | SG2 | 100%
500328 | CC Dom Wastewater Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Renfrewshire | 0 | 0 | 131987.72 | 317456.35 | 73537.99 | 258213.93 | 661714.99 | 869114.49 | 2312025.47 | 0 | 0 | 0 | 2312025.47 | 0 | 0 | 0 | 0 | 2312025.47 | 1011948.65 | [5 empty] | N | SG2 | 100%
500329 | CC Dom Wastewater Shetland Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Shetland Islands | 0 | 0 | 50395.99 | 59317.6 | 0 | 9283.71 | 15224.69 | 0 | 134221.99 | 0 | 0 | 0 | 134221.99 | 0 | 0 | 0 | 0 | 134221.99 | 1011948.65 | [5 empty] | N | SG2 | 100%
500330 | CC Dom Wastewater South Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | South Ayrshire | 0 | 0 | 53428.95 | 72710.97 | 28707.71 | 245389.72 | 0.29 | 70189.16 | 470426.8 | 0 | 0 | 0 | 470426.8 | 0 | 0 | 0 | 0 | 470426.8 | 1011948.65 | [5 empty] | N | SG2 | 100%
500331 | CC Dom Wastewater South Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | South Lanarkshire | 0 | 0 | -103318.83 | 677623.79 | 538167.65 | 1036275.47 | 735061.42 | 1228378.43 | 4112187.93 | 0 | 0 | 0 | 4112187.93 | 0 | 0 | 0 | 0 | 4112187.93 | 1011948.65 | [5 empty] | N | SG2 | 100%
500332 | CC Dom Wastewater Stirling (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Stirling | 0 | 0 | 46253.97 | 285817.68 | 571397.51 | -91748.37 | 37336.79 | 335308.4 | 1184365.97 | 0 | 0 | 0 | 1184365.97 | 0 | 0 | 0 | 0 | 1184365.97 | 1011948.65 | [5 empty] | N | SG2 | 100%
500333 | CC Dom Wastewater West Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | West Dunbartonshire | 0 | 0 | 123410.3 | 58898.69 | 182041.61 | 106368.85 | 31282.88 | 79079.96 | 581082.29 | 0 | 0 | 0 | 581082.29 | 0 | 0 | 0 | 0 | 581082.29 | 1011948.65 | [5 empty] | N | SG2 | 100%
500334 | CC Dom Wastewater West Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | West Lothian | 0 | 0 | 124195.87 | 1002145.24 | 782055.56 | 853864.72 | 37878.59 | 950254.09 | 3750394.07 | 0 | 0 | 0 | 3750394.07 | 0 | 0 | 0 | 0 | 3750394.07 | 1011948.65 | [5 empty] | N | SG2 | 100%
500367 | CC Dom Water Aberdeen City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-02 |  | Aberdeen City | 0 | 0 | 375481.16 | 547820.36 | 195990.97 | 340791.95 | 385113.72 | 441995.71 | 2287193.87 | 0 | 0 | 0 | 2287193.87 | 0 | 0 | 0 | 0 | 2287193.87 | 276932.45 | [5 empty] | N | WG2 | 100%
500368 | CC Dom Water Aberdeenshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Aberdeenshire | 0 | 0 | 760768.23 | 700523.79 | 458756.96 | 723835.15 | 1408647.09 | 125534.98 | 4178066.2 | 0 | 0 | 0 | 4178066.2 | 0 | 0 | 0 | 0 | 4178066.2 | 276932.45 | [5 empty] | N | WG2 | 100%
500369 | CC Dom Water Angus (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Angus | 0 | 0 | 59694.27 | 158331 | 57680.31 | 129778.42 | 15514.22 | 70287.15 | 491285.37 | 0 | 0 | 0 | 491285.37 | 0 | 0 | 0 | 0 | 491285.37 | 276932.45 | [5 empty] | N | WG2 | 100%
500370 | CC Dom Water Argyll and Bute (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 74804.16 | 232.19 | 59517.92 | 7935.02 | 61804.66 | 204293.95 | 0 | 0 | 0 | 204293.95 | 0 | 0 | 0 | 0 | 204293.95 | 276932.45 | [5 empty] | N | WG2 | 100%
500371 | CC Dom Water Borders (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Scottish Borders | 0 | 0 | 73618.17 | 178059.23 | 21456.88 | 148962.38 | 71862.14 | 48993.99 | 542952.8 | 0 | 0 | 0 | 542952.8 | 0 | 0 | 0 | 0 | 542952.8 | 276932.45 | [5 empty] | N | WG2 | 100%
500372 | CC Dom Water Clackmannan (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Clackmannanshire | 0 | 0 | 10173.05 | 100112.37 | 70834.04 | 32170.29 | 46757.57 | 78782.23 | 338829.55 | 0 | 0 | 0 | 338829.55 | 0 | 0 | 0 | 0 | 338829.55 | 276932.45 | [5 empty] | N | WG2 | 100%
500373 | CC Dom Water Dumfries and Galloway (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Dumfries and Galloway | 0 | 0 | 35570.14 | 105679.16 | 12935.6 | 65029.22 | 25205.59 | -38410.01 | 206009.71 | 0 | 0 | 0 | 206009.71 | 0 | 0 | 0 | 0 | 206009.71 | 276932.45 | [5 empty] | N | WG2 | 100%
500374 | CC Dom Water Dundee City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Dundee City | 0 | 0 | 103943.99 | 277335.46 | -684.57 | 107572.73 | 141570.93 | 24344.88 | 654083.42 | 0 | 0 | 0 | 654083.42 | 0 | 0 | 0 | 0 | 654083.42 | 276932.45 | [5 empty] | N | WG2 | 100%
500375 | CC Dom Water East Ayrshire(2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | East Ayrshire | 0 | 0 | 164251.4 | 191074.94 | 54880.3 | 114398.04 | 65109.83 | 162654.29 | 752368.8 | 0 | 0 | 0 | 752368.8 | 0 | 0 | 0 | 0 | 752368.8 | 276932.45 | [5 empty] | N | WG2 | 100%
500376 | CC Dom Water East Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-02 |  | East Dunbartonshire | 0 | 0 | 74255.24 | 59107.84 | 170608.06 | 130369.06 | 148313.47 | 89564.67 | 672218.34 | 0 | 0 | 0 | 672218.34 | 0 | 0 | 0 | 0 | 672218.34 | 276932.45 | [5 empty] | N | WG2 | 100%
500313 | CC Dom Water East Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | East Lothian | 0 | 0 | 481890.8 | 615184.71 | 384161.33 | 564471.02 | 222885.21 | 1048748.72 | 3317341.79 | 0 | 0 | 0 | 3317341.79 | 0 | 0 | 0 | 0 | 3317341.79 | 1011948.65 | [5 empty] | N | SG2 | 100%
500377 | CC Dom Water East Lothian (2015-18) - 5003770000 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | East Lothian | 0 | 0 | 166882.23 | 914100.22 | 84550.17 | 353801.48 | 180009.09 | 309486.62 | 2008829.82 | 0 | 0 | 0 | 2008829.82 | 0 | 0 | 0 | 0 | 2008829.82 | 276932.45 | [5 empty] | N | WG2 | 100%
500378 | CC Dom Water East Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | East Renfrewshire | 0 | 0 | 87873.85 | 190420.97 | -18786.08 | 97657.74 | 57466.02 | 143207.59 | 557840.09 | 0 | 0 | 0 | 557840.09 | 0 | 0 | 0 | 0 | 557840.09 | 276932.45 | [5 empty] | N | WG2 | 100%
500379 | CC Dom Water Edinburgh City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | City of Edinburgh | 0 | 0 | 366936.26 | 949991.89 | 420888.69 | 793237.75 | 487619.08 | 769351.71 | 3788025.37 | 0 | 0 | 0 | 3788025.37 | 0 | 0 | 0 | 0 | 3788025.37 | 276932.45 | [5 empty] | N | WG2 | 100%
500380 | CC Dom Water Falkirk (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Falkirk | 0 | 0 | 560808.56 | 131548.21 | 161399.41 | 1143452.34 | 76031.89 | 176353.88 | 2249594.29 | 0 | 0 | 0 | 2249594.29 | 0 | 0 | 0 | 0 | 2249594.29 | 276932.45 | [5 empty] | N | WG2 | 100%
500381 | CC Dom Water Fife (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-02 |  | Fife | 0 | 0 | 272632.63 | 512547.8 | 364422.41 | 370969.47 | 254236.53 | 854691.83 | 2629500.67 | 0 | 0 | 0 | 2629500.67 | 0 | 0 | 0 | 0 | 2629500.67 | 276932.45 | [5 empty] | N | WG2 | 100%
500382 | CC Dom Water Glasgow City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Glasgow City | 0 | 0 | 372677.09 | 613249.84 | 191630.13 | 643297.68 | 286988.95 | 583801.78 | 2691645.46 | 0 | 0 | 0 | 2691645.46 | 0 | 0 | 0 | 0 | 2691645.46 | 276932.45 | [5 empty] | N | WG2 | 100%
500383 | CC Dom Water Highland (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Highland | 0 | 0 | 246372.47 | 312008.04 | 220747.74 | 547777.28 | 609151.53 | 520460.44 | 2456517.5 | 0 | 0 | 0 | 2456517.5 | 0 | 0 | 0 | 0 | 2456517.5 | 276932.45 | [5 empty] | N | WG2 | 100%
500384 | CC Dom Water Inverclyde (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Inverclyde | 0 | 0 | 17540.78 | 72535.9 | -8796.47 | 36096.22 | 19105.23 | 34464.03 | 170945.69 | 0 | 0 | 0 | 170945.69 | 0 | 0 | 0 | 0 | 170945.69 | 276932.45 | [5 empty] | N | WG2 | 100%
500385 | CC Dom Water Midlothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 |  | Midlothian | 0 | 0 | 238339.11 | 510078.81 | 232535 | 521933.89 | 90288.63 | 464590.76 | 2057766.21 | 0 | 0 | 0 | 2057766.21 | 0 | 0 | 0 | 0 | 2057766.21 | 276932.45 | [5 empty] | N | WG2 | 100%
500386 | CC Dom Water Moray (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-03-31 | 2015-03-31 | 2021-03-02 |  | Moray | 0 | 0 | 442268.06 | 166783.43 | 51252.99 | 235777.03 | 51359.62 | 245728.18 | 1193169.32 | 0 | 0 | 0 | 1193169.32 | 0 | 0 | 0 | 0 | 1193169.32 | 276932.45 | [5 empty] | N | WG2 | 100%
500387 | CC Dom Water Na H-Eileanan an Iar (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 21859.87 | 3171.82 | 1132.69 | 0 | 0 | 26164.38 | 0 | 0 | 0 | 26164.38 | 0 | 0 | 0 | 0 | 26164.38 | 276932.45 | [5 empty] | N | WG2 | 100%
500388 | CC Dom Water North Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | North Ayrshire | 0 | 0 | 62489.6 | 117012.01 | 33780.97 | 96012.94 | 85435.63 | 91409.03 | 486140.18 | 0 | 0 | 0 | 486140.18 | 0 | 0 | 0 | 0 | 486140.18 | 276932.45 | [5 empty] | N | WG2 | 100%
500389 | CC Dom Water North Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | North Lanarkshire | 0 | 0 | 150190.61 | 640013.63 | 313693.63 | 805911.21 | 84463.47 | 685333.24 | 2679605.8 | 0 | 0 | 0 | 2679605.8 | 0 | 0 | 0 | 0 | 2679605.8 | 276932.45 | [5 empty] | N | WG2 | 100%
500390 | CC Dom Water Orkney Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Orkney Islands | 0 | 0 | 11093.41 | 44233.26 | -2628.72 | 48179.5 | -23252.78 | 41830.14 | 119454.81 | 0 | 0 | 0 | 119454.81 | 0 | 0 | 0 | 0 | 119454.81 | 276932.45 | [5 empty] | N | WG2 | 100%
500391 | CC Dom Water Perth and Kinross (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Perth and Kinross | 0 | 0 | 127705.48 | 287620.14 | 177599.35 | 240068.85 | 360236.98 | 336743.9 | 1529974.7 | 0 | 0 | 0 | 1529974.7 | 0 | 0 | 0 | 0 | 1529974.7 | 276932.45 | [5 empty] | N | WG2 | 100%
500392 | CC Dom Water Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Renfrewshire | 0 | 0 | 137377.62 | 270137.4 | 202499.3 | 749409.84 | 580831.7 | 750418.65 | 2690674.51 | 0 | 0 | 0 | 2690674.51 | 0 | 0 | 0 | 0 | 2690674.51 | 276932.45 | [5 empty] | N | WG2 | 100%
500393 | CC Dom Water Shetland Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Shetland Islands | 0 | 0 | 43760.67 | 43568.91 | -27414.04 | 5070.97 | -0.15 | 0 | 64986.35 | 0 | 0 | 0 | 64986.35 | 0 | 0 | 0 | 0 | 64986.35 | 276932.45 | [5 empty] | N | WG2 | 100%
500394 | CC Dom Water South Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | South Ayrshire | 0 | 0 | 98713.77 | 163263.59 | -36603.53 | 114910.17 | -38437.18 | 25600.41 | 327447.23 | 0 | 0 | 0 | 327447.23 | 0 | 0 | 0 | 0 | 327447.23 | 276932.45 | [5 empty] | N | WG2 | 100%
500395 | CC Dom Water South Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | South Lanarkshire | 0 | 0 | 151888.6 | 537900.98 | 594934.31 | 714887.57 | 666422.22 | 608991.64 | 3275025.32 | 0 | 0 | 0 | 3275025.32 | 0 | 0 | 0 | 0 | 3275025.32 | 276932.45 | [5 empty] | N | WG2 | 100%
500396 | CC Dom Water Stirling (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Stirling | 0 | 0 | 101982.96 | 143246.93 | 151660.38 | 143210.32 | 13999.93 | 97111.23 | 651211.75 | 0 | 0 | 0 | 651211.75 | 0 | 0 | 0 | 0 | 651211.75 | 276932.45 | [5 empty] | N | WG2 | 100%
500397 | CC Dom Water West Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | West Dunbartonshire | 0 | 0 | 105166.84 | 45809.65 | 43540.57 | 52103.31 | 23449.35 | 57696.41 | 327766.13 | 0 | 0 | 0 | 327766.13 | 0 | 0 | 0 | 0 | 327766.13 | 276932.45 | [5 empty] | N | WG2 | 100%
500398 | CC Dom Water West Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | West Lothian | 0 | 0 | 336950.81 | 526884.38 | 807970.26 | 222566.64 | 123822.47 | 583504.45 | 2601699.01 | 0 | 0 | 0 | 2601699.01 | 0 | 0 | 0 | 0 | 2601699.01 | 276932.45 | [5 empty] | N | WG2 | 100%
500335 | CC Non-Dom Wastewater Aberdeen City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Aberdeen City | 0 | 0 | 0 | -102.67 | 102.67 | -23389.85 | 0 | 0 | -23389.85 | 0 | 0 | 0 | -23389.85 | 0 | 0 | 0 | 0 | -23389.85 | 1011948.65 | [5 empty] | N | SG2 | 100%
500336 | CC Non-Dom Wastewater Aberdeenshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Aberdeenshire | 0 | 0 | 0 | 24558.86 | -12183.44 | -12323.23 | -52.19 | 1488.61 | 1488.61 | 0 | 0 | 0 | 1488.61 | 0 | 0 | 0 | 0 | 1488.61 | 1011948.65 | [5 empty] | N | SG2 | 100%
500337 | CC Non-Dom Wastewater Angus (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Angus | 0 | 0 | 0 | 8362.42 | -4094.23 | -4181.21 | -86.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500338 | CC Non-Dom Wastewater Argyll and Bute (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500339 | CC Non-Dom Wastewater Borders (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Scottish Borders | 0 | 0 | 0 | -10.82 | 10.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500403 | CC Non-Dom Wastewater Borders (2015-18) - 5004030000 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Scottish Borders | 0 | 0 | 0 | 15.95 | 82.29 | 316.36 | -414.6 | -12314.63 | -12314.63 | 0 | 0 | 0 | -12314.63 | 0 | 0 | 0 | 0 | -12314.63 | 276932.45 | [5 empty] | N | WG2 | 100%
500340 | CC Non-Dom Wastewater Clackmannan (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500341 | CC Non-Dom Wastewater Dumfries and Galloway (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 9546.06 | -4778.54 | -4767.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500342 | CC Non-Dom Wastewater Dundee City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Dundee City | 0 | 0 | 0 | 0 | 36.32 | 0 | -36.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500343 | CC Non-Dom Wastewater East Ayrshire(2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500347 | CC Non-Dom Wastewater Edinburgh City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | City of Edinburgh | 0 | 0 | 0 | -77.31 | 321.54 | 0 | -241.94 | 0 | 2.29 | 0 | 0 | 0 | 2.29 | 0 | 0 | 0 | 0 | 2.29 | 1011948.65 | [5 empty] | N | SG2 | 100%
500348 | CC Non-Dom Wastewater Falkirk (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Falkirk | 0 | 0 | 0 | 50.1 | -50.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500349 | CC Non-Dom Wastewater Fife (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500350 | CC Non-Dom Wastewater Glasgow City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Glasgow City | 0 | 0 | 0 | 3575.22 | -1721.61 | -1787.61 | -66 | 103.94 | 103.94 | 0 | 0 | 0 | 103.94 | 0 | 0 | 0 | 0 | 103.94 | 1011948.65 | [5 empty] | N | SG2 | 100%
500351 | CC Non-Dom Wastewater Highland (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500352 | CC Non-Dom Wastewater Inverclyde (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500353 | CC Non-Dom Wastewater Midlothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Midlothian | 0 | 0 | 0 | 0 | 75 | 0 | -75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500354 | CC Non-Dom Wastewater Moray (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Moray | 0 | 0 | 0 | 0 | 180 | 0 | -180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500355 | CC Non-Dom Wastewater Na H-Eileanan an Iar (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | -39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500356 | CC Non-Dom Wastewater North Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | North Ayrshire | 0 | 0 | 0 | -111.94 | 439.69 | 0 | -327.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500357 | CC Non-Dom Wastewater North Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500358 | CC Non-Dom Wastewater Orkney Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500359 | CC Non-Dom Wastewater Perth and Kinross (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500360 | CC Non-Dom Wastewater Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500361 | CC Non-Dom Wastewater Shetland Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500362 | CC Non-Dom Wastewater South Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500363 | CC Non-Dom Wastewater South Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 6053.6 | 0 | 0 | 6053.6 | 0 | 0 | 0 | 6053.6 | 0 | 0 | 0 | 0 | 6053.6 | 1011948.65 | [5 empty] | N | SG2 | 100%
500364 | CC Non-Dom Wastewater Stirling (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Stirling | 0 | 0 | 0 | -25.33 | 170.12 | 0 | -144.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500365 | CC Non-Dom Wastewater West Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500366 | CC Non-Dom Wastewater West Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
500399 | CC Non-Dom Water Aberdeen City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Aberdeen City | 0 | 0 | 0 | 22026.88 | 2729.99 | -19118.95 | 0 | 2006.12 | 7644.04 | 0 | 0 | 0 | 7644.04 | 0 | 0 | 0 | 0 | 7644.04 | 276932.45 | [5 empty] | N | WG2 | 100%
500400 | CC Non-Dom Water Aberdeenshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Aberdeenshire | 0 | 0 | 0 | -2166.62 | 25940.47 | -9661.61 | 0 | 36932.04 | 51044.28 | 0 | 0 | 0 | 51044.28 | 0 | 0 | 0 | 0 | 51044.28 | 276932.45 | [5 empty] | N | WG2 | 100%
500401 | CC Non-Dom Water Angus (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Angus | 0 | 0 | 0 | 0 | 0 | 1854.03 | 0 | 17751.41 | 19605.44 | 0 | 0 | 0 | 19605.44 | 0 | 0 | 0 | 0 | 19605.44 | 276932.45 | [5 empty] | N | WG2 | 100%
500402 | CC Non-Dom Water Argyll and Bute (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | -142.68 | 1934.9 | -862.53 | -929.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500404 | CC Non-Dom Water Clackmannan (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 68.05 | 0 | -68.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500405 | CC Non-Dom Water Dumfries and Galloway (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 4.2 | 942.78 | 1412.56 | 0 | -608.98 | 1750.56 | 0 | 0 | 0 | 1750.56 | 0 | 0 | 0 | 0 | 1750.56 | 276932.45 | [5 empty] | N | WG2 | 100%
500406 | CC Non-Dom Water Dundee City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Dundee City | 0 | 0 | 0 | -115.55 | 2906.02 | -1977.02 | -813.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500407 | CC Non-Dom Water East Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | East Ayrshire | 0 | 0 | 0 | 0 | 740.59 | 499.77 | 0 | 10048.87 | 11289.23 | 0 | 0 | 0 | 11289.23 | 0 | 0 | 0 | 0 | 11289.23 | 276932.45 | [5 empty] | N | WG2 | 100%
500408 | CC Non-Dom Water East Dumbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | East Dunbartonshire | 0 | 0 | 0 | -85.65 | 159.32 | 0 | -73.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500409 | CC Non-Dom Water East Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | East Lothian | 0 | 0 | 0 | -142.59 | 627.25 | 58 | -542.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500410 | CC Non-Dom Water East Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | East Renfrewshire | 0 | 0 | 0 | 62.66 | -62.66 | 386.8 | -773.6 | 2541.84 | 2155.04 | 0 | 0 | 0 | 2155.04 | 0 | 0 | 0 | 0 | 2155.04 | 276932.45 | [5 empty] | N | WG2 | 100%
500411 | CC Non-Dom Water Edinburgh City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | City of Edinburgh | 0 | 0 | 0 | -451.54 | 1053.09 | 1846.32 | 0 | 75523.31 | 77971.18 | 0 | 0 | 0 | 77971.18 | 0 | 0 | 0 | 0 | 77971.18 | 276932.45 | [5 empty] | N | WG2 | 100%
500412 | CC Non-Dom Water Falkirk (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Falkirk | 0 | 0 | 0 | 125.32 | -125.32 | 74.27 | -74.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500413 | CC Non-Dom Water Fife (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Fife | 0 | 0 | 0 | -225.54 | 1415.71 | 427.9 | 0 | 0 | 1618.07 | 0 | 0 | 0 | 1618.07 | 0 | 0 | 0 | 0 | 1618.07 | 276932.45 | [5 empty] | N | WG2 | 100%
500414 | CC Non-Dom Water Glasgow City (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Glasgow City | 0 | 0 | 0 | -295.63 | 5478.32 | 2132.81 | 0 | 9260.92 | 16576.42 | 0 | 0 | 0 | 16576.42 | 0 | 0 | 0 | 0 | 16576.42 | 276932.45 | [5 empty] | N | WG2 | 100%
500415 | CC Non-Dom Water Highland (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Highland | 0 | 0 | 490 | -198.54 | 591.19 | 1412.89 | 0 | 0 | 2295.54 | 0 | 0 | 0 | 2295.54 | 0 | 0 | 0 | 0 | 2295.54 | 276932.45 | [5 empty] | N | WG2 | 100%
500416 | CC Non-Dom Water Inverclyde (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Inverclyde | 0 | 0 | 317.76 | -49.63 | 113.07 | 456.67 | -837.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500417 | CC Non-Dom Water Midlothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Midlothian | 0 | 0 | 0 | -197.14 | 197.14 | 350.22 | -350.22 | 4807.98 | 4807.98 | 0 | 0 | 0 | 4807.98 | 0 | 0 | 0 | 0 | 4807.98 | 276932.45 | [5 empty] | N | WG2 | 100%
500418 | CC Non-Dom Water Moray (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Moray | 0 | 0 | 0 | 109.55 | 3993.17 | -2661.49 | 0 | 3899.64 | 5340.87 | 0 | 0 | 0 | 5340.87 | 0 | 0 | 0 | 0 | 5340.87 | 276932.45 | [5 empty] | N | WG2 | 100%
500419 | CC Non-Dom Water Na H-Eileanan an Iar (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | -105.46 | 445.08 | 265.51 | -605.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500420 | CC Non-Dom Water North Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | North Ayrshire | 0 | 0 | 0 | -103.35 | 729.13 | 114.4 | -740.18 | 9836.41 | 9836.41 | 0 | 0 | 0 | 9836.41 | 0 | 0 | 0 | 0 | 9836.41 | 276932.45 | [5 empty] | N | WG2 | 100%
500421 | CC Non-Dom Water North Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | North Lanarkshire | 0 | 0 | 0 | 62.66 | 67.29 | 1123.14 | 0 | 4264.85 | 5517.94 | 0 | 0 | 0 | 5517.94 | 0 | 0 | 0 | 0 | 5517.94 | 276932.45 | [5 empty] | N | WG2 | 100%
500422 | CC Non-Dom Water Orkney Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 45.7 | -45.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500423 | CC Non-Dom Water Perth and Kinross (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Perth and Kinross | 0 | 0 | 0 | -314.7 | 3295.43 | -2681.98 | -298.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500424 | CC Non-Dom Water Renfrewshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 1877.47 | 0 | -3528.42 | -1650.95 | 0 | 0 | 0 | -1650.95 | 0 | 0 | 0 | 0 | -1650.95 | 276932.45 | [5 empty] | N | WG2 | 100%
500425 | CC Non-Dom Water Shetland Islands (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 77.55 | -77.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
500426 | CC Non-Dom Water South Ayrshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | South Ayrshire | 0 | 0 | 0 | 0 | 173.06 | 477.66 | -650.72 | 1421.62 | 1421.62 | 0 | 0 | 0 | 1421.62 | 0 | 0 | 0 | 0 | 1421.62 | 276932.45 | [5 empty] | N | WG2 | 100%
500427 | CC Non-Dom Water South Lanarkshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | South Lanarkshire | 0 | 0 | 0 | -359.7 | 439.51 | 1006.1 | 0 | 11501.97 | 12587.88 | 0 | 0 | 0 | 12587.88 | 0 | 0 | 0 | 0 | 12587.88 | 276932.45 | [5 empty] | N | WG2 | 100%
500428 | CC Non-Dom Water Stirling (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Stirling | 0 | 0 | 0 | -212.17 | 997.72 | 180.16 | -965.71 | 7879.08 | 7879.08 | 0 | 0 | 0 | 7879.08 | 0 | 0 | 0 | 0 | 7879.08 | 276932.45 | [5 empty] | N | WG2 | 100%
500429 | CC Non-Dom Water West Dunbartonshire (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 758.29 | 250.59 | 0 | 5193.14 | 6202.02 | 0 | 0 | 0 | 6202.02 | 0 | 0 | 0 | 0 | 6202.02 | 276932.45 | [5 empty] | N | WG2 | 100%
500430 | CC Non-Dom Water West Lothian (2015-18) | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | West Lothian | 0 | 0 | 0 | 12.7 | 395.43 | 155.66 | -563.79 | 2541.84 | 2541.84 | 0 | 0 | 0 | 2541.84 | 0 | 0 | 0 | 0 | 2541.84 | 276932.45 | [5 empty] | N | WG2 | 100%
400226 | CC Non-Domestic WasteWater Aberdeen City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeen City | 0 | 0 | 0 | 0 | 41001.33 | 40875.6 | 0 | 0 | 81876.93 | 0 | 0 | 0 | 81876.93 | 0 | 0 | 0 | 0 | 81876.93 | 0 | [5 empty] | N | SG2 | 100%
400229 | CC Non-Domestic WasteWater Argyll and Bute | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | [5 empty] | N | SG2 | 100%
400233 | CC Non-Domestic WasteWater Dundee City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dundee City | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | [5 empty] | N | SG2 | 100%
400234 | CC Non-Domestic WasteWater East Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Ayrshire | 0 | 0 | 0 | 0 | 120 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
400238 | CC Non-Domestic WasteWater Edinburgh City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | City of Edinburgh | 0 | 0 | 0 | -73.96 | 73.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
400240 | CC Non-Domestic WasteWater Fife | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Fife | 0 | 0 | 0 | 0.74 | 0 | 0 | 0 | 0 | 0.74 | 0 | 0 | 0 | 0.74 | 0 | 0 | 0 | 0 | 0.74 | 0 | [5 empty] | N | SG2 | 100%
400241 | CC Non-Domestic WasteWater Glasgow City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
400248 | CC Non-Domestic WasteWater North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG2 | 100%
400162 | CC Non-Domestic Water Aberdeen City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeen City | 15805.15 | 0 | -15805.15 | 51.93 | -13400.17 | 0 | 0 | 0 | -29153.39 | 0 | 0 | 0 | -13348.24 | 0 | 0 | 0 | 0 | -13348.24 | 0 | [5 empty] | N | WG2 | 100%
400163 | CC Non-Domestic Water Aberdeenshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeenshire | 55.15 | 0 | -55.15 | -12323.23 | 15079.31 | -5512.16 | 0 | 0 | -2811.23 | 0 | 0 | 0 | -2756.08 | 0 | 0 | 0 | 0 | -2756.08 | 0 | [5 empty] | N | WG2 | 100%
400164 | CC Non-Domestic Water Angus | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Angus | 0 | 0 | 0 | -4181.21 | 4181.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400168 | CC Non-Domestic Water Dumfries and Galloway | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dumfries and Galloway | 1008.78 | 0 | -1008.78 | -4713.89 | 4713.89 | 0 | 0 | 0 | -1008.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400169 | CC Non-Domestic Water Dundee City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dundee City | 0 | 0 | 0 | -51.09 | 4044.39 | -7986.6 | 0 | 0 | -3993.3 | 0 | 0 | 0 | -3993.3 | 0 | 0 | 0 | 0 | -3993.3 | 0 | [5 empty] | N | WG2 | 100%
400170 | CC Non-Domestic Water East Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400172 | CC Non-Domestic Water East Lothian | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Lothian | 0 | 0 | 0 | 51.93 | -51.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400173 | CC Non-Domestic Water East Renfrewshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400174 | CC Non-Domestic Water Edinburgh City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | City of Edinburgh | 0 | 0 | 0 | 53.62 | -53.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400177 | CC Non-Domestic Water Glasgow City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Glasgow City | 0 | 0 | 0 | -1787.61 | 1787.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400178 | CC Non-Domestic Water Highland | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Highland | 0 | 0 | 0 | 104.26 | 195.04 | 0 | 0 | 0 | 299.3 | 0 | 0 | 0 | 299.3 | 0 | 0 | 0 | 0 | 299.3 | 0 | [5 empty] | N | WG2 | 100%
400182 | CC Non-Domestic Water Na H-Eileanan an Iar | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Na H-Eileanan an Iar | 61.34 | 0 | 0 | 62.66 | -124 | 0 | 0 | 0 | -61.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400184 | CC Non-Domestic Water North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | North Lanarkshire | 0 | 0 | 0 | -11.65 | 11.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400186 | CC Non-Domestic Water Perth and Kinross | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Perth and Kinross | 0 | 0 | 0 | 62.66 | -62.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400190 | CC Non-Domestic Water South Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | South Lanarkshire | 0 | 0 | 0 | 62.96 | -62.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400192 | CC Non-Domestic Water West Dunbartonshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400193 | CC Non-Domestic Water West Lothian | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
400194 | CC WasteWater Aberdeen City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeen City | 645202.78 | 0 | -120 | -198754.89 | 49424.59 | 149450.3 | 0 | -3017.82 | -3017.82 | 0 | 0 | 0 | 642184.96 | 0 | 0 | 0 | 0 | 642184.96 | 0 | [5 empty] | N | SG2 | 100%
400195 | CC WasteWater Aberdeenshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeenshire | 4439801.95 | 0 | -135 | -308500.05 | 270842.55 | 37417.5 | 0 | -9295.71 | -9670.71 | 0 | 0 | 0 | 4430131.24 | 0 | 0 | 0 | 0 | 4430131.24 | 0 | [5 empty] | N | SG2 | 100%
400196 | CC WasteWater Angus | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Angus | 811134.81 | 0 | -121.16 | -4219.1 | -142979.72 | 147319.98 | 0 | 0 | 0 | 0 | 0 | 0 | 811134.81 | 0 | 0 | 0 | 0 | 811134.81 | 0 | [5 empty] | N | SG2 | 100%
400197 | CC WasteWater Argyll and Bute | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Argyll and Bute-North Argyll | 385341.75 | 0 | 0 | 75.96 | 0 | -128.21 | 0 | 0 | -52.25 | 0 | 0 | 0 | 385289.5 | 0 | 0 | 0 | 0 | 385289.5 | 0 | [5 empty] | N | SG2 | 100%
400198 | CC WasteWater Borders | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Scottish Borders | 904594.34 | 0 | -240 | 0 | 195 | -213.56 | 0 | 0 | -258.56 | 0 | 0 | 0 | 904335.78 | 0 | 0 | 0 | 0 | 904335.78 | 0 | [5 empty] | N | SG2 | 100%
400199 | CC WasteWater Clackmannan | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Clackmannanshire | 123262.65 | 0 | -47.95 | 0 | -75821.97 | 75869.92 | 0 | 0 | 0 | 0 | 0 | 0 | 123262.65 | 0 | 0 | 0 | 0 | 123262.65 | 0 | [5 empty] | N | SG2 | 100%
400200 | CC WasteWater Dumfries and Galloway | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dumfries and Galloway | 1160392.46 | 0 | -120 | 0 | 0 | -18.02 | 0 | 0 | -138.02 | 0 | 0 | 0 | 1160254.44 | 0 | 0 | 0 | 0 | 1160254.44 | 0 | [5 empty] | N | SG2 | 100%
400201 | CC WasteWater Dundee City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dundee City | 537363.9 | 0 | 0 | 23174.69 | -23174.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537363.9 | 0 | 0 | 0 | 0 | 537363.9 | 0 | [5 empty] | N | SG2 | 100%
400202 | CC WasteWater East Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Ayrshire | 1320355.31 | 0 | 0 | -22374.34 | 22618.17 | -363.83 | 0 | 0 | -120 | 0 | 0 | 0 | 1320235.31 | 0 | 0 | 0 | 0 | 1320235.31 | 0 | [5 empty] | N | SG2 | 100%
400203 | CC WasteWater East Dunbartonshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Dunbartonshire | 294546.85 | 0 | 0 | -58430.09 | 58430.09 | 0 | 245058.8 | 9734.3 | 254793.1 | 0 | 0 | 0 | 549339.95 | 0 | 0 | 0 | 0 | 549339.95 | 0 | [5 empty] | N | SG2 | 100%
400204 | CC WasteWater East Lothian | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Lothian | 524744.49 | 0 | 0 | -55300.94 | 29371.14 | 25929.8 | 0 | -24304.13 | -24304.13 | 0 | 0 | 0 | 500440.36 | 0 | 0 | 0 | 0 | 500440.36 | 0 | [5 empty] | N | SG2 | 100%
400205 | CC WasteWater East Renfrewshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Renfrewshire | 556219.32 | 0 | 0 | -11874.36 | 12242.36 | -368 | 0 | 0 | 0 | 0 | 0 | 0 | 556219.32 | 0 | 0 | 0 | 0 | 556219.32 | 0 | [5 empty] | N | SG2 | 100%
400206 | CC WasteWater Edinburgh City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | City of Edinburgh | 1833388.1 | 0 | 0 | -301097.78 | 350903.21 | -50128.47 | 0 | 0 | -323.04 | 0 | 0 | 0 | 1833065.06 | 0 | 0 | 0 | 0 | 1833065.06 | 0 | [5 empty] | N | SG2 | 100%
400207 | CC WasteWater Falkirk | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Falkirk | 1665249.56 | 0 | 0 | -103404.58 | 103404.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665249.56 | 0 | 0 | 0 | 0 | 1665249.56 | 0 | [5 empty] | N | SG2 | 100%
400208 | CC WasteWater Fife | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Fife | 2628158.85 | 0 | 0 | -36249.94 | 36384.94 | -255 | 0 | 29699.98 | 29579.98 | 0 | 0 | 0 | 2657738.83 | 0 | 0 | 0 | 0 | 2657738.83 | 0 | [5 empty] | N | SG2 | 100%
400209 | CC WasteWater Glasgow City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Glasgow City | 1708218.33 | 0 | -900 | -39275.1 | -138558.92 | 178469.57 | 0 | -9701.9 | -9966.35 | 0 | 0 | 0 | 1698251.98 | 0 | 0 | 0 | 0 | 1698251.98 | 0 | [5 empty] | N | SG2 | 100%
400210 | CC WasteWater Highland | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Highland | 2526715.38 | 0 | 0 | -149013.25 | 121138.75 | 27874.5 | -25145.14 | -48698.99 | -73844.13 | 0 | 0 | 0 | 2452871.25 | 0 | 0 | 0 | 0 | 2452871.25 | 0 | [5 empty] | N | SG2 | 100%
400211 | CC WasteWater Inverclyde | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Inverclyde | 480370.59 | 0 | 0 | -16910.01 | 16910.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480370.59 | 0 | 0 | 0 | 0 | 480370.59 | 0 | [5 empty] | N | SG2 | 100%
400212 | CC WasteWater Midlothian | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Midlothian | 1866126.33 | 0 | 0 | -84908.97 | 103443.41 | -18534.44 | 0 | 0 | 0 | 0 | 0 | 0 | 1866126.33 | 0 | 0 | 0 | 0 | 1866126.33 | 0 | [5 empty] | N | SG2 | 100%
400213 | CC WasteWater Moray | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Moray | 820705.08 | 0 | -8 | 120 | 0 | -112 | 0 | 0 | 0 | 0 | 0 | 0 | 820705.08 | 0 | 0 | 0 | 0 | 820705.08 | 0 | [5 empty] | N | SG2 | 100%
400214 | CC WasteWater Na H-Eileanan an Iar | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Na H-Eileanan an Iar | 91019.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0.04 | 0 | 0 | 0 | 91020 | 0 | 0 | 0 | 0 | 91020 | 0 | [6 empty] | SG2 | 100%
400215 | CC WasteWater North Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Ayrshire | 1188743.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0 | 0 | 0 | 1188744 | 0 | 0 | 0 | 0 | 1188744 | 0 | [6 empty] | SG2 | 100%
400216 | CC WasteWater North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | North Lanarkshire | 4389311.79 | 0 | -453.34 | -116379.9 | 88297.39 | 28535.85 | -116410.86 | -48617.07 | -165027.93 | 0 | 0 | 0 | 4224283.86 | 0 | 0 | 0 | 0 | 4224283.86 | 0 | [5 empty] | N | SG2 | 100%
400217 | CC WasteWater Orkney Islands | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Orkney Islands | 191435.15 | 0 | 0 | -3274.15 | 3274.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191435.15 | 0 | 0 | 0 | 0 | 191435.15 | 0 | [5 empty] | N | SG2 | 100%
400218 | CC WasteWater Perth and Kinross | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Perth and Kinross | 1119987.02 | 0 | -120 | -49460.52 | 46312.91 | 3267.61 | 0 | 0 | 0 | 0 | 0 | 0 | 1119987.02 | 0 | 0 | 0 | 0 | 1119987.02 | 0 | [5 empty] | N | SG2 | 100%
400219 | CC WasteWater Renfrewshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Renfrewshire | 916586.78 | 0 | 0 | -68843.18 | 69201.88 | -367.54 | 0 | 0 | -8.84 | 0 | 0 | 0 | 916577.94 | 0 | 0 | 0 | 0 | 916577.94 | 0 | [5 empty] | N | SG2 | 100%
400220 | CC WasteWater Shetland Islands | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Shetland Islands | 105388.02 | 0 | 48593.2 | -48593.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105388.02 | 0 | 0 | 0 | 0 | 105388.02 | 0 | [5 empty] | N | SG2 | 100%
400221 | CC WasteWater South Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | South Ayrshire | 522741.26 | 0 | 60 | 3719.43 | -3599.43 | -188 | 0 | 0 | -8 | 0 | 0 | 0 | 522733.26 | 0 | 0 | 0 | 0 | 522733.26 | 0 | [5 empty] | N | SG2 | 100%
400222 | CC WasteWater South Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | South Lanarkshire | 5203100.88 | 0 | -48593.2 | -190209.94 | 109802.15 | 128930.27 | 123423.3 | 102363.9 | 225716.48 | 0 | 0 | 0 | 5428817.36 | 0 | 0 | 0 | 0 | 5428817.36 | 0 | [5 empty] | N | SG2 | 100%
400223 | CC WasteWater Stirling | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Stirling | 876227.43 | 0 | 0 | 0 | -81607.23 | 81607.23 | 0 | 0 | 0 | 0 | 0 | 0 | 876227.43 | 0 | 0 | 0 | 0 | 876227.43 | 0 | [5 empty] | N | SG2 | 100%
400224 | CC WasteWater West Dunbartonshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | West Dunbartonshire | 629488.04 | 0 | 970.48 | -15973.4 | 9647.77 | 5355.15 | 2533.02 | 0 | 2533.02 | 0 | 0 | 0 | 632021.06 | 0 | 0 | 0 | 0 | 632021.06 | 0 | [5 empty] | N | SG2 | 100%
400225 | CC WasteWater West Lothian | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | West Lothian | 1781393.84 | 0 | 0 | -241683.55 | 378765.97 | -137322.42 | 0 | 0 | -240 | 0 | 0 | 0 | 1781153.84 | 0 | 0 | 0 | 0 | 1781153.84 | 0 | [5 empty] | N | SG2 | 100%
400130 | CC Water Aberdeen City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeen City | 602219.62 | 0 | 109098 | -177069.04 | 58754.47 | 9348.96 | 0 | 0 | 132.39 | 0 | 0 | 0 | 602352.01 | 0 | 0 | 0 | 0 | 602352.01 | 0 | [5 empty] | N | WG2 | 100%
400131 | CC Water Aberdeenshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Aberdeenshire | 2579408.49 | 0 | 141116.83 | -254073.28 | 109137.58 | 3091.82 | 0 | 0 | -727.05 | 0 | 0 | 0 | 2578681.44 | 0 | 0 | 0 | 0 | 2578681.44 | 0 | [5 empty] | N | WG2 | 100%
400132 | CC Water Angus | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Angus | 420625.65 | 0 | 39054 | -65339.95 | 31652.7 | -3581.08 | 0 | 0 | 1785.67 | 0 | 0 | 0 | 422411.32 | 0 | 0 | 0 | 0 | 422411.32 | 0 | [5 empty] | N | WG2 | 100%
400134 | CC Water Borders | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Scottish Borders | 468068.58 | 0 | 32618.54 | -84900.07 | 53337.35 | -1439.89 | 0 | 0 | -384.07 | 0 | 0 | 0 | 467684.51 | 0 | 0 | 0 | 0 | 467684.51 | 0 | [5 empty] | N | WG2 | 100%
400135 | CC Water Clackmannan | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Clackmannanshire | 137638.4 | 0 | 9863 | -19797.51 | -4878.09 | 14812.6 | 0 | 0 | 0 | 0 | 0 | 0 | 137638.4 | 0 | 0 | 0 | 0 | 137638.4 | 0 | [5 empty] | N | WG2 | 100%
400136 | CC Water Dumfries and Galloway | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dumfries and Galloway | 386310.47 | 0 | 37398.03 | -64344.43 | 25836.49 | 698.6 | 0 | 0 | -411.31 | 0 | 0 | 0 | 385899.16 | 0 | 0 | 0 | 0 | 385899.16 | 0 | [5 empty] | N | WG2 | 100%
400133 | CC Water Dundee City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Argyll and Bute-North Argyll | 101248.09 | 0 | 9357.56 | -14729.49 | 5919.83 | -547.9 | 509.62 | -509.62 | 0 | 0 | 0 | 0 | 101248.09 | 0 | 0 | 0 | 0 | 101248.09 | 0 | [5 empty] | N | WG2 | 100%
400137 | CC Water Dundee City - 4001370000 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Dundee City | 138755.3 | 0 | 17014 | -79227.05 | 65140.08 | -2927.03 | 0 | 0 | 0 | 0 | 0 | 0 | 138755.3 | 0 | 0 | 0 | 0 | 138755.3 | 0 | [5 empty] | N | WG2 | 100%
400138 | CC Water East Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Ayrshire | 386826.37 | 0 | 31578 | -88779.22 | 57201.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386826.37 | 0 | 0 | 0 | 0 | 386826.37 | 0 | [5 empty] | N | WG2 | 100%
400139 | CC Water East Dunbartonshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Dunbartonshire | 795837.97 | 0 | 58903.97 | -26300.03 | -51945.57 | 17552.57 | 0 | 0 | -1789.06 | 0 | 0 | 0 | 794048.91 | 0 | 0 | 0 | 0 | 794048.91 | 0 | [5 empty] | N | WG2 | 100%
400140 | CC Water East Lothian | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Lothian | 398452.4 | 0 | 44080 | -338418.85 | 294833.47 | -1450.88 | 0 | 0 | -956.26 | 0 | 0 | 0 | 397496.14 | 0 | 0 | 0 | 0 | 397496.14 | 0 | [5 empty] | N | WG2 | 100%
400141 | CC Water East Renfrewshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | East Renfrewshire | 270590.47 | 0 | 25292 | -97209.86 | 61894.97 | 9959.71 | 0 | 0 | -63.18 | 0 | 0 | 0 | 270527.29 | 0 | 0 | 0 | 0 | 270527.29 | 0 | [5 empty] | N | WG2 | 100%
400142 | CC Water Edinburgh City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | City of Edinburgh | 1157931.44 | 0 | 128814 | -333612.93 | 181144.03 | 25698.17 | 0 | 77409.18 | 79452.45 | 0 | 0 | 0 | 1237383.89 | 0 | 0 | 0 | 0 | 1237383.89 | 0 | [5 empty] | N | WG2 | 100%
400143 | CC Water Falkirk | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Falkirk | 941192.69 | 0 | 57398 | -2447.5 | -58773.24 | 3614.76 | 0 | -77517.71 | -77725.69 | 0 | 0 | 0 | 863467 | 0 | 0 | 0 | 0 | 863467 | 0 | [5 empty] | N | WG2 | 100%
400144 | CC Water Fife | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Fife | 1005678.27 | 0 | 81652.08 | -125041.41 | 44964.39 | -3609.67 | 0 | 13827.5 | 11792.89 | 0 | 0 | 0 | 1017471.16 | 0 | 0 | 0 | 0 | 1017471.16 | 0 | [5 empty] | N | WG2 | 100%
400145 | CC Water Glasgow City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Glasgow City | 1554091.97 | 0 | 127372 | -244326.86 | 116677.62 | 145.5 | 0 | -10324.3 | -10456.04 | 0 | 0 | 0 | 1543635.93 | 0 | 0 | 0 | 0 | 1543635.93 | 0 | [5 empty] | N | WG2 | 100%
400147 | CC Water Inverclyde | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Inverclyde | 170845.8 | 0 | 10052 | -44621.8 | 34569.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170845.8 | 0 | 0 | 0 | 0 | 170845.8 | 0 | [5 empty] | N | WG2 | 100%
400146 | CC Water Midlothian | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Highland | 1641396.02 | 0 | 91700.49 | -109838.86 | -3486.95 | 20930.56 | 0 | -16276.67 | -16971.43 | 0 | 0 | 0 | 1624424.59 | 0 | 0 | 0 | 0 | 1624424.59 | 0 | [5 empty] | N | WG2 | 100%
400148 | CC Water Midlothian - 4001480000 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Midlothian | 6064127.31 | 0 | 85130 | -161879.55 | 95364.14 | -19119.9 | 0 | 15782.12 | 15276.81 | 0 | 0 | 0 | 6079404.12 | 0 | 0 | 0 | 0 | 6079404.12 | 0 | [5 empty] | N | WG2 | 100%
400150 | CC Water Na H-Eileanan an Iar | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Na H-Eileanan an Iar | 48969.15 | 0 | 1577.57 | -1440 | -104 | -33.57 | 0 | 0 | 0 | 0 | 0 | 0 | 48969.15 | 0 | 0 | 0 | 0 | 48969.15 | 0 | [5 empty] | N | WG2 | 100%
400149 | CC Water North Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Moray | 808713.57 | 0 | 32897.99 | -61268.74 | 36311.03 | -7288.66 | 0 | -6369.86 | -5718.24 | 0 | 0 | 0 | 802995.33 | 0 | 0 | 0 | 0 | 802995.33 | 0 | [5 empty] | N | WG2 | 100%
400151 | CC Water North Ayrshire - 4001510000 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | North Ayrshire | 509894.72 | 0 | 25990 | -43203.66 | 16590.28 | 524.4 | 0 | 0 | -98.98 | 0 | 0 | 0 | 509795.74 | 0 | 0 | 0 | 0 | 509795.74 | 0 | [5 empty] | N | WG2 | 100%
400152 | CC Water North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | North Lanarkshire | 1108414.75 | 0 | 97132 | -168925.96 | 71422.19 | 114.98 | 0 | 0 | -256.79 | 0 | 0 | 0 | 1108157.96 | 0 | 0 | 0 | 0 | 1108157.96 | 0 | [5 empty] | N | WG2 | 100%
400153 | CC Water Orkney Islands | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Orkney Islands | 88474.77 | 0 | 11156.85 | -16465.21 | 5961.51 | -741.6 | 0 | 0 | -88.45 | 0 | 0 | 0 | 88386.32 | 0 | 0 | 0 | 0 | 88386.32 | 0 | [5 empty] | N | WG2 | 100%
400154 | CC Water Perth and Kinross | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Perth and Kinross | 354294.87 | 0 | 29642.4 | -97366.67 | 67742.51 | -509.86 | -1114 | 9250.57 | 7644.95 | 0 | 0 | 0 | 361939.82 | 0 | 0 | 0 | 0 | 361939.82 | 0 | [5 empty] | N | WG2 | 100%
400155 | CC Water Renfrewshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Renfrewshire | 462500.09 | 0 | 59129.46 | -83199.14 | 22319.73 | 1688.33 | 0 | 0 | -61.62 | 0 | 0 | 0 | 462438.47 | 0 | 0 | 0 | 0 | 462438.47 | 0 | [5 empty] | N | WG2 | 100%
400156 | CC Water Shetland Islands | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Shetland Islands | 83911.64 | 0 | 6369.59 | -25988.92 | 19933.4 | -314.07 | 0 | 0 | 0 | 0 | 0 | 0 | 83911.64 | 0 | 0 | 0 | 0 | 83911.64 | 0 | [5 empty] | N | WG2 | 100%
400157 | CC Water South Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | South Ayrshire | 208279.15 | 0 | 18900 | -71314.56 | 53122.83 | -1319.15 | 0 | 0 | -610.88 | 0 | 0 | 0 | 207668.27 | 0 | 0 | 0 | 0 | 207668.27 | 0 | [5 empty] | N | WG2 | 100%
400158 | CC Water South Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | South Lanarkshire | 1139178.19 | 0 | 57800.51 | -106378.26 | 3159.79 | 45328.47 | -253490.26 | -10272.34 | -263852.09 | 0 | 0 | 0 | 875326.1 | 0 | 0 | 0 | 0 | 875326.1 | 0 | [5 empty] | N | WG2 | 100%
400159 | CC Water Stirling | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | Clackmannanshire | 216448.68 | 0 | 20149.14 | -51784.25 | 22568.32 | 8876.15 | 0 | 7216.06 | 7025.42 | 0 | 0 | 0 | 223474.1 | 0 | 0 | 0 | 0 | 223474.1 | 0 | [5 empty] | N | WG2 | 100%
400160 | CC Water West Dunbartonshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | West Dunbartonshire | 290437.66 | 0 | 22886 | -17529.43 | -38839.6 | 33483.03 | 0 | 0 | 0 | 0 | 0 | 0 | 290437.66 | 0 | 0 | 0 | 0 | 290437.66 | 0 | [5 empty] | N | WG2 | 100%
400161 | CC Water West Lothian | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-11 | 2019-04-11 | West Lothian | 951240.54 | 0 | 93318 | -165404.13 | 80364.69 | -8157.91 | 0 | -887.12 | -766.47 | 0 | 0 | 0 | 950474.07 | 0 | 0 | 0 | 0 | 950474.07 | 0 | [5 empty] | N | WG2 | 100%
502191 | CCTV Phase 2A Ayrshire Inverclyde and Renfrewshire | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-09-20 | 2018-01-17 | 2018-02-26 | 2020-01-28 |  | Scottish Water Wide | 0 | 0 | 0 | 3427.06 | 191062.89 | 416163.05 | -2494 | 0 | 608159 | 0 | 0 | 0 | 608159 | 0 | 0 | 0 | 0 | 608159 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502404 | CCTV Phase 2B Dalmarnock North & South Lanarkshire | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-04-28 | 2018-06-21 | 2018-08-31 | 2020-06-11 |  | South Lanarkshire | 0 | 0 | 0 | 1807.55 | 12425.55 | 732232.9 | -4976 | 4082 | 745572 | 428 | 0 | 0 | 746000 | 0 | 0 | 0 | 0 | 746000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502405 | CCTV Phase 2C West Highland Aberdeenshire & Moray | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-04-28 | 2018-03-27 | 2018-05-31 | 2020-01-30 |  | Aberdeenshire | 0 | 0 | 0 | 1674.42 | 88929.58 | 565647 | -251 | 0 | 656000 | 0 | 0 | 0 | 656000 | 0 | 0 | 0 | 0 | 656000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502641 | CCTV Phase 3A Falkirk & West Lothian | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-01-30 | 2018-12-05 | 2019-05-13 | 2021-05-21 |  | West Lothian | 0 | 0 | 0 | 6630.7 | 10429.17 | 139380.13 | 365823 | 88098.36 | 610361.36 | 2500 | 0 | 0 | 612861.36 | 0 | 0 | 0 | 0 | 612861.36 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502642 | CCTV Phase 3B West Highland & Argyle & Bute | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-01-30 | 2018-10-26 | 2019-01-31 | 2021-05-21 |  | Highland | 0 | 0 | 0 | 4420.47 | 11454.23 | 159542.3 | 262272 | 58422 | 496111 | 31607 | 0 | 0 | 527718 | 0 | 0 | 0 | 0 | 527718 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502643 | CCTV Phase 3C North Highland | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-03-29 | 2019-03-05 | 2019-07-08 | 2021-05-21 |  | Highland | 0 | 0 | 0 | 4420.47 | 6005.08 | 63639.2 | 277747.26 | 59759 | 411571 | 2123 | 0 | 0 | 413694 | 0 | 0 | 0 | 0 | 413694 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503046 | CCTV Phase 4A Stirlingshire and Clackmannanshire | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-10-26 | 2019-08-19 | 2020-01-13 | 2021-07-09 |  | Stirling | 0 | 0 | 0 | 0 | 5261.77 | 4207.2 | 207164.41 | 161841.62 | 378475 | 48597 | 0 | 0 | 427072 | 0 | 0 | 0 | 0 | 427072 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503201 | CCTV Phase 4B (Dumfries Borders East & Mid Lothian) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-07-27 | 2019-07-22 | 2019-10-14 | 2021-06-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 48847.9 | 218521.1 | 144403 | 411772 | 12216 | 0 | 0 | 423988 | 0 | 0 | 0 | 0 | 423988 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503411 | CCTV Phase 4C Fife Perth & Kinross Dundee and Angus | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2020-04-13 | 2021-02-26 | 2021-03-22 | 2022-02-11 |  | Fife | 0 | 0 | 0 | 0 | 0 | 15023.15 | 13733.91 | 183486.94 | 212244 | 1047098.47 | 0 | 0 | 1259342.47 | 0 | 0 | 0 | 0 | 1259342.47 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403614 | CCTV Sewer Surveys | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-12-19 | 2014-04-30 | 2014-06-09 | 2016-03-30 |  | Scottish Water Wide | 682168 | 0 | 359296.72 | 25137.03 | 0 | 0 | 0 | 0 | 384433.75 | 0 | 0 | 0 | 1066601.75 | 0 | 0 | 0 | 0 | 1066601.75 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402858 | Central Bar Market Street St. Andrews | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2013-09-18 | 2013-12-19 | 2014-06-13 | 2014-06-13 | Fife | 2279102 | 0 | -7665 | -882.94 | 0 | 0 | 0 | 0 | -8547.94 | 0 | 0 | 0 | 2270554.06 | 0 | 0 | 0 | 0 | 2270554.06 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
403344 | Central Borders Trunk Main Capacity | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-25 | 2014-09-10 | 2014-10-06 | 2015-07-17 |  | Scottish Borders | 65921 | 0 | 2170.65 | 0 | 0 | 0 | 0 | 0 | 2170.65 | 0 | 0 | 0 | 68091.65 | 0 | 0 | 0 | 0 | 68091.65 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502585 | Ceres Burn Crossing Ceres | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 |  | Fife | 0 | 0 | 0 | 2930.23 | 1575.13 | 0 | 0 | 0 | 4505.36 | 0 | 0 | 0 | 4505.36 | 0 | 0 | 0 | 0 | 4505.36 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502394 | Chapleton Development Infrastructure Funding | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2017-02-21 | 2017-02-21 | 2017-03-01 | 2021-06-18 |  | Aberdeenshire | 0 | 0 | 0 | 911064 | 0 | -425507.3 | 0.01 | 0 | 485556.71 | 0 | 0 | 0 | 485556.71 | 0 | 0 | 0 | 0 | 485556.71 | 0 | [5 empty] | N | SG5 | 100%
402076 | Charging At Vacant Properties | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-06-16 | 2011-06-16 | 2011-07-05 | 2015-03-31 |  | Scottish Water Wide | 11231.71 | 0 | -457.76 | 0 | 0 | 0 | 0 | 0 | -457.76 | 0 | 0 | 0 | 10773.95 | 0 | 0 | 0 | 0 | 10773.95 | 0 | [5 empty] | N | CS20 | 100%
401562 | Charleston Low Pressure Enhancement WSZ000362 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-11-02 | 2011-12-15 | 2012-03-12 | 2014-03-17 | 2013-09-30 | Fife | 74079.7 | 0 | 238.67 | 217.89 | 0 | 0 | 0 | 0 | 456.56 | 0 | 0 | 0 | 74536.26 | 0 | 0 | 0 | 0 | 74536.26 | 0 | [5 empty] | N | CS1 | 100%
502084 | Charlotte St SPS rising main - Relay Rising Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2020-06-29 | 2020-06-29 | 2020-09-30 | 2020-09-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 28.57% | CM_WSI | 47.62%
507466 | Charlotte St SPS Rising Main Investigation | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS0 | 2020-09-29 | 2021-11-08 | 2022-03-09 | 2022-09-07 | 2022-12-08 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642 | 1642 | 58358.37 | 0 | 0 | 60000.37 | 0 | 0 | 0 | 0 | 60000.37 | 0 | [5 empty] | N | SR21_WW | 100%
509336 | Chem Dosing H&S CSD interventions | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-22 | 2021-09-15 | 2022-04-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16028.04 | 16028.04 | 228971.96 | 0 | 0 | 245000 | 0 | 0 | 0 | 0 | 245000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509771 | Chemical Dosing - Balmore WTW Alum Tank Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-05-18 | 2022-09-23 | 2022-12-22 | 2023-11-15 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23233 | 23233 | 476767.49 | 0 | 0 | 500000.49 | 0 | 0 | 0 | 0 | 500000.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512138 | Chemical Dosing H&S East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3999999.96 | 0 | 0 | 3999999.96 | 0 | 0 | 0 | 0 | 3999999.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512131 | Chemical Dosing H&S North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3999999.96 | 0 | 0 | 3999999.96 | 0 | 0 | 0 | 0 | 3999999.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512132 | Chemical Dosing H&S South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3999999.96 | 0 | 0 | 3999999.96 | 0 | 0 | 0 | 0 | 3999999.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512141 | Chemical Dosing H&S West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3999999.96 | 0 | 0 | 3999999.96 | 0 | 0 | 0 | 0 | 3999999.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502847 | Chemical Dosing Programme - Phase 1 - Braemar WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2018-08-24 | 2020-05-21 | 2020-06-19 | 2020-06-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 6451.26 | 6899.21 | -971.29 | 12379.18 | 0 | 0 | 0 | 12379.18 | 0 | 0 | 0 | 0 | 12379.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502848 | Chemical Dosing Programme - Phase 1 - Castle Moffat WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-21 | 2021-05-10 | 2021-08-16 | 2021-11-19 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 5548 | 761.49 | 30811.51 | 37121 | 262878.99 | 0 | 0 | 299999.99 | 0 | 0 | 0 | 0 | 299999.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502849 | Chemical Dosing Programme - Phase 1 - Daer WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-13 | 2021-06-21 | 2021-08-23 | 2022-02-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 6980.42 | -2806.03 | 21848.79 | 26023.18 | 171033.16 | 0 | 0 | 197056.34 | 0 | 0 | 0 | 0 | 197056.34 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502850 | Chemical Dosing Programme - Phase 1 - East sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2018-08-28 | 2021-03-19 | 2021-05-03 | 2022-09-09 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 13698 | 12183.85 | 187827.15 | 213709 | 652032.74 | 0 | 0 | 865741.74 | 0 | 0 | 0 | 0 | 865741.74 | 328404.37 | [5 empty] | N | CM_M&G | 33.98% | CM_WSNI | 66.02%
502851 | Chemical Dosing Programme - Phase 1 - Forehill WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2021-11-08 | 2022-01-24 | 2022-06-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 5902 | 15839.97 | 15623.26 | 14309.77 | 51675 | 70404.37 | 0 | 0 | 122079.37 | 0 | 0 | 0 | 0 | 122079.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502852 | Chemical Dosing Programme - Phase 1 - Glenconvinth WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2021-06-07 | 2021-09-20 | 2022-06-29 |  | Highland | 0 | 0 | 0 | 0 | 5994.49 | 9735.19 | 2178.01 | 52786.31 | 70694 | 642659.69 | 0 | 0 | 713353.69 | 0 | 0 | 0 | 0 | 713353.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502853 | Chemical Dosing Programme - Phase 1 - Glendevon WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2021-10-11 | 2021-10-22 | 2022-07-22 |  | Fife | 0 | 0 | 0 | 0 | 13267.6 | 107717.07 | 256409.83 | 509046.5 | 886441 | 481179.5 | 0 | 0 | 1367620.5 | 0 | 0 | 0 | 0 | 1367620.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502854 | Chemical Dosing Programme - Phase 1 - Glenfarg WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-08-24 | 2020-12-21 | 2021-03-31 | 2021-12-13 |  | Fife | 0 | 0 | 0 | 0 | 0 | 6591.66 | 8640.56 | 31006.78 | 46239 | 79179.27 | 0 | 0 | 125418.27 | 0 | 0 | 0 | 0 | 125418.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502855 | Chemical Dosing Programme - Phase 1 - Milnathort WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS1 | 2018-08-20 | 2021-10-25 | 2021-12-06 | 2022-05-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 6952.29 | 7189.8 | 16723.91 | 30866 | 111448.67 | 0 | 0 | 142314.67 | 0 | 0 | 0 | 0 | 142314.67 | 209381.79 | [5 empty] | N | CM_M&G | 100%
502858 | Chemical Dosing Programme - Phase 1 - North sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2017-11-23 | 2020-04-30 | 2020-07-08 | 2022-05-19 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 13308.69 | 5197.11 | 3975.51 | 143104.69 | 165586 | 747989.28 | 0 | 0 | 913575.28 | 0 | 0 | 0 | 0 | 913575.28 | 328404.37 |  |  |  |  | 20119 | N | CM_M&G | 21.7% | CM_WSNI | 78.3%
502861 | Chemical Dosing Programme - Phase 1 - Rawburn WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-20 | 2021-10-25 | 2022-01-31 | 2022-11-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 6005.89 | -1505.29 | 55464.4 | 59965 | 540035.13 | 0 | 0 | 600000.13 | 0 | 0 | 0 | 0 | 600000.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502860 | Chemical Dosing Programme - Phase 1 - Shotts STW | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS1 | 2018-11-20 | 2021-10-11 | 2022-01-28 | 2022-12-23 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 8243.17 | 23343.34 | -8272.51 | 23314 | 176686.06 | 0 | 0 | 200000.06 | 0 | 0 | 0 | 0 | 200000.06 | 209381.79 | [5 empty] | N | CM_M&G | 100%
502859 | Chemical Dosing Programme - Phase 1 - South sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-13 | 2022-05-06 | 2022-09-07 | 2023-03-14 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 5369.59 | -3353.15 | 13717.42 | 15733.87 | 133766.13 | 0 | 0 | 149500 | 0 | 0 | 0 | 0 | 149500 | 328404.37 |  |  |  |  | 100456 | N | CM_M&G | 8.629% | CM_WSNI | 91.37%
502857 | Chemical Dosing Programme - Phase 1 - Turriff WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2021-10-25 | 2022-04-01 | 2023-01-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 9408.24 | 52011.24 | 3855.79 | 74227.73 | 139503 | 600319.19 | 0 | 0 | 739822.19 | 0 | 0 | 0 | 0 | 739822.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502856 | Chemical Dosing Programme - Phase 1 - West sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2017-11-15 | 2020-03-31 | 2020-07-13 | 2022-04-13 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 80449.88 | -9315.36 | 79816.05 | 71688.77 | 222639.34 | 463289.34 | 0 | 0 | 685928.68 | 0 | 0 | 0 | 0 | 685928.68 | 328404.37 | [5 empty] | N | CM_M&G | 25% | CM_WSNI | 75%
402671 | Chemical Dosing System HS Review | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-05-16 | 2013-07-31 | 2013-07-31 | 2014-09-25 |  | Scottish Water Wide | 1896620 | 0 | 4181.91 | -534.6 | 0 | 0 | 0 | 0 | 3647.31 | 0 | 0 | 0 | 1900267.31 | 0 | 0 | 0 | 0 | 1900267.31 | 119022.58 | [5 empty] | N | CM_M&G | 100%
512136 | Chemical Investigation Programme 3 Scotland | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MSU | 2022-04-01 | 2022-11-10 | 2023-03-14 | 2023-09-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.98 | 0 | 0 | 999999.98 | 0 | 0 | 0 | 0 | 999999.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503242 | Chemical Storage tanks Investigations- Pan Scotland | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-09-13 | 2020-02-28 | 2020-07-13 | 2021-11-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 351102.33 | 549316.7 | 747193.39 | 1647612.42 | 324637.82 | 0 | 0 | 1972250.24 | 0 | 0 | 0 | 0 | 1972250.24 | 119022.58 | [5 empty] | N | CM_M&G | 100%
510842 | Chemical Storage tanks Investigations Phase 2 - Pan Scotland | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2021-03-30 | 2021-12-06 | 2022-04-06 | 2022-10-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.42 | 65.42 | 999999.98 | 0 | 0 | 1000065.4 | 0 | 0 | 0 | 0 | 1000065.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504448 | Chemical Tank Remedials | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-01 | 2021-05-28 | 2021-09-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 16514.31 | -16514.31 | 0 | 249000 | 0 | 0 | 249000 | 0 | 0 | 0 | 0 | 249000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503227 | Chirnside WwTW - SR21 Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-08-02 | 2023-05-22 | 2023-08-21 | 2024-08-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 85886 | 32213.47 | 17080.53 | 135180 | 1134038.12 | 0 | 0 | 1269218.12 | 0 | 0 | 0 | 0 | 1269218.12 | 122419.09 | [5 empty] | N | SG1 | 100%
402849 | Church Street Lossiemouth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-04 | 2014-11-28 | 2014-12-01 | 2015-03-27 | 2015-03-27 | Moray | 875097 | 875097 | 12381.68 | 178.02 | 0 | 0 | 0 | 0 | 12559.7 | 0 | 0 | 0 | 887656.7 | 0 | 0 | 0 | 0 | 887656.7 | 180449.74 | [5 empty] | N | FL_DD | 100%
400088 | CID Overheads for SR10-15 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2009-12-18 | 2009-12-18 | 2011-10-06 | 2018-10-08 |  | Scottish Water Wide | -2985513.38 | 0 | -117957.33 | 0 | 60.28 | 0 | 32.58 | 0 | -117864.47 | 0 | 0 | 0 | -3103377.85 | 0 | 0 | 0 | 0 | -3103377.85 | 613322.63 | [5 empty] | N | OHDS1 | 50% | OHDW1 | 50%
401028 | CID QS IIIA Land Cost run-offs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS7 | 2010-04-21 | 2012-02-28 | 2012-03-01 | 2015-11-03 |  | Scottish Water Wide | 865439 | 0 | 2184.12 | 0 | 262.72 | 0 | 0 | 0 | 2446.84 | 0 | 0 | 0 | 867885.84 | 0 | 0 | 0 | 0 | 867885.84 | 730242.44 | [5 empty] | N | WSI | 25% | WSNI | 25% | WWI | 25% | WWNI | 25%
502299 | CIP - Funding Provision for Byelaws Compliance Officers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-09-09 | 2016-09-09 | 2016-11-02 | 2017-09-19 |  | Scottish Water Wide | 0 | 0 | 0 | 164559.45 | 117899.73 | 0 | 0 | 0 | 282459.18 | 0 | 0 | 0 | 282459.18 | 0 | 0 | 0 | 0 | 282459.18 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502773 | CIP - ICC Network Access Resources | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-09-20 | 2017-09-20 | 2017-09-29 | 2021-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 78446 | 222045.67 | 159489.46 | 177999.87 | 637981 | 62018.8 | 0 | 0 | 699999.8 | 0 | 0 | 0 | 0 | 699999.8 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502223 | CIP - Valve Inspection & Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-07-21 | 2016-07-21 | 2016-11-02 | 2021-08-24 |  | Scottish Water Wide | 0 | 0 | 0 | 789224.56 | 1173962.45 | 1215484.74 | 729541.99 | 817359.02 | 4725572.76 | -50572.76 | 0 | 0 | 4675000 | 0 | 0 | 0 | 0 | 4675000 | 622473.57 | [5 empty] | N | CM_WSI | 33.33% | CM_M&G | 66.67%
400806 | CITY RAIN NET - IMPROVED RAINFALL MONITORING IN URBAN AREAS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-05-05 | 2010-05-05 | 2010-05-05 | 2020-02-13 |  | Scottish Water Wide | 166238 | 0 | 786.98 | 0 | 0 | 0 | 0 | 0 | 786.98 | 0 | 0 | 0 | 167024.98 | 0 | 0 | 0 | 0 | 167024.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502417 | Clachan Pipe Bridges | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-06-29 | 2018-10-25 | 2019-07-03 | 2020-02-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 4202.33 | 12934.93 | 38586.49 | 65674.21 | 63.79 | 121461.75 | 0 | 0 | 0 | 121461.75 | 0 | 0 | 0 | 0 | 121461.75 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508816 | Clachan WwTW - Replacement Washwater Set | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-10 | 2022-06-23 | 2023-02-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8258.91 | 8258.91 | 46742.09 | 0 | 0 | 55001 | 0 | 0 | 0 | 0 | 55001 | 90601.29 | [5 empty] | N | WWNI | 100%
500925 | Clackmannanshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | Clackmannanshire | 0 | 0 | 6000 | 793.41 | 0 | 0 | 0 | 0 | 6793.41 | 0 | 0 | 0 | 6793.41 | 0 | 0 | 0 | 0 | 6793.41 | 106252.93 | [5 empty] | N | FL_DD | 100%
502932 | Cladich WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-05-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 21179.77 | 1106.24 | -19575.67 | 0 | 2710.34 | 0 | 0 | 0 | 2710.34 | 0 | 0 | 0 | 0 | 2710.34 | 122419.09 | [5 empty] | N | WG1 | 100%
402863 | Claire Street Newmains Wishaw | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2012-08-15 | 2014-09-30 | 2014-11-03 | 2016-08-12 | 2016-08-12 | North Lanarkshire | 324755 | 324755 | -12655 | 5000 | 0 | 40102.86 | 0 | 0 | 32447.86 | 0 | 0 | 0 | 357202.86 | 0 | 0 | 0 | 0 | 357202.86 | 180449.74 | [5 empty] | N | FL_DD | 100%
402854 | Claredon Place Dunblane | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2012-08-15 | 2020-03-05 | 2020-08-05 | 2020-08-05 | 2021-04-01 | Stirling | 39648.83 | 39648.83 | 2030.17 | 43927.91 | 30393.09 | 49747.29 | 16672.78 | 1110.59 | 143881.83 | 0 | 0 | 0 | 183530.66 | 0 | 0 | 0 | 0 | 183530.66 | 384468.55 | [5 empty] | N | CM_WWI | 40% | FL_DD | 60%
502357 | Clatto & Lintrathen Hydro Generator Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-11-27 | 2016-11-27 | 2017-08-01 | 2018-06-26 |  | Dundee City | 0 | 0 | 0 | 129000 | 226612.19 | -49650 | 0 | 0 | 305962.19 | 0 | 0 | 0 | 305962.19 | 0 | 0 | 0 | 0 | 305962.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501616 | Clatto 40inch & 48inch Raw Water Mains - Air & Scour Valves | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2027-12-09 | 2028-09-05 | 2028-12-01 | 2029-04-16 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142050.03 | 0 | 0 | 142050.03 | 0 | 0 | 0 | 0 | 142050.03 | 4989107.96 | [5 empty] | N | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 28.57% | CM_WSI | 47.62%
501711 | Clatto 40inch & 48inch Raw Water Mains - Pipe Bridges | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-05-03 | 2027-11-29 | 2028-03-29 | 2028-08-11 |  | East Lothian | 0 | 0 | 0 | 10169.61 | 24820.81 | 14989.58 | 0 | 0 | 49980 | 1845794.03 | 0 | 0 | 1895774.03 | 0 | 0 | 0 | 0 | 1895774.03 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510112 | Clatto Dundee Drainage CCTV | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-12-17 | 2021-06-21 | 2022-02-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1057 | 1057 | 6943.26 | 0 | 0 | 8000.26 | 0 | 0 | 0 | 0 | 8000.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500062 | Clatto East - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS7 | 2015-03-19 | 2016-05-26 | 2016-05-30 | 2017-09-14 | 2018-12-19 | Dundee City | 0 | 0 | 405493 | 1254291 | 114503 | 13965.24 | 47560.31 | 0 | 1835812.55 | 0 | 0 | 0 | 1835812.55 | 0 | 0 | 0 | 0 | 1835812.55 | 365786.94 | [5 empty] | N | DW5 | 100%
500802 | Clatto East RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2015-11-23 | 2016-09-30 | 2017-01-11 | 2019-01-31 | 2019-06-30 | Dundee City | 0 | 0 | 29821 | 176000.51 | 140878.08 | 204431.31 | 7764.94 | 0 | 558895.84 | 0 | 0 | 0 | 558895.84 | 0 | 0 | 0 | 0 | 558895.84 | 541547.32 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 109.01 | [43 empty] | 0
506773 | Clatto Fife DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW0 |  | 2023-08-28 | 2023-11-13 | 2024-10-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 243999.87 | 0 | 0 | 244130.71 | 0 | 0 | 0 | 0 | 244130.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508046 | Clatto Old No1 MIOS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-08-31 | 2021-02-05 | 2021-09-20 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28098 | 28098 | 71902.38 | 0 | 0 | 100000.38 | 0 | 0 | 0 | 0 | 100000.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS7 | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2019-03-28 | 2019-09-02 | Dundee City | 332.03 | 283.879 | 306152.97 | 831400 | 2530470 | 1721070.28 | 45985.96 | 2850.62 | 5437929.83 | 0 | 0 | 0 | 5438261.86 | 0 | 0 | 0 | 0 | 5438261.86 | 3253306.99 | [5 empty] | N | CM_WSI | 16.77% | DW5 | 83.23%
500803 | Clatto West RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2015-11-23 | 2017-12-20 | 2018-03-26 | 2019-03-31 | 2020-02-29 | Dundee City | 0 | 0 | 55736 | 80652.12 | 178133.13 | 223430.24 | 50360.09 | -4227.16 | 584084.41 | 0 | 0 | 0 | 584084.41 | 0 | 0 | 0 | 0 | 584084.41 | 771983.06 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 120.49 | [43 empty] | 0
500067 | Clatto WOA Balbeuchley WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2015-03-11 | 2017-05-24 | 2017-08-10 | 2021-01-25 |  | Perth and Kinross | 0 | 0 | 73000 | 65144 | 878108 | 585257.9 | 572954.89 | 322048.49 | 2496513.28 | -4632.95 | 0 | 0 | 2491880.33 | 0 | 0 | 0 | 0 | 2491880.33 | 622473.57 | [5 empty] | N | CM_WSI | 100%
501202 | Clatto WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2016-02-11 | 2027-07-07 | 2027-07-08 | 2028-06-30 |  | Dundee City | 0 | 0 | 14109 | 159419.88 | -1838.88 | -4586.03 | 0 | 0.03 | 167104 | 0 | 0 | 0 | 167104 | 0 | 0 | 0 | 0 | 167104 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505627 | Clatto WTW - MCC Relocate | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-09-24 | 2023-03-17 | 2023-06-30 | 2024-11-15 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46719 | 46719 | 1453281.59 | 0 | 0 | 1500000.59 | 0 | 0 | 0 | 0 | 1500000.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507253 | Clatto WTW - Standby Generator installation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-07-01 | 2022-11-24 | 2023-02-23 | 2024-06-25 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55595 | 55595 | 975405.28 | 0 | 0 | 1031000.28 | 0 | 0 | 0 | 0 | 1031000.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502270 | Clatto WTW CM - Water champ and RGF 6 & 10 refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-06-15 | 2028-09-04 | 2028-12-29 | 2029-08-10 |  | Dundee City | 0 | 0 | 0 | 10190.5 | 454.79 | 5575.53 | 0 | 0 | 16220.82 | 234455.2 | 0 | 0 | 250676.02 | 0 | 0 | 0 | 0 | 250676.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
45620 | Clatto WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-04-01 | 2013-05-01 | 2013-12-30 | Dundee City | 604974.56 | 0 | -609.16 | 0 | 0 | 0 | 0 | 0 | -609.16 | 0 | 0 | 0 | 604365.4 | 0 | 0 | 0 | 0 | 604365.4 | 28761.13 | [5 empty] | N | DW1A | 100%
404070 | Clay Crescent EPI | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2014-12-09 | 2014-12-09 | 2014-12-09 | 2017-07-03 |  | North Lanarkshire | 579203.01 | 0 | 25945.99 | 0 | -25945.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579203.01 | 0 | 0 | 0 | 0 | 579203.01 | 0 | [5 empty] | N | CM_WWI | 100%
503961 | Clay Crescent sewer cleaning | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2019-12-04 |  | 2021-02-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 44102.56 | 110604.94 | 154707.5 | 292.5 | 0 | 0 | 155000 | 0 | 0 | 0 | 0 | 155000 | 209381.79 | [5 empty] | N | WWI | 100%
400721 | Cleghorn ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2014-05-22 | 2014-06-02 | 2015-03-19 | 2015-03-19 | South Lanarkshire | 338093.74 | 0 | 31002.26 | 2676.95 | 5077.65 | 0 | 0 | 0 | 38756.86 | 0 | 0 | 0 | 376850.6 | 0 | 0 | 0 | 0 | 376850.6 | 0 | [5 empty] | N | SG1 | 100%
502928 | Clerkland Bridge - Pipe replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2017-11-13 | 2018-09-05 | 2019-06-24 | 2020-02-25 |  | East Ayrshire | 0 | 0 | 0 | 0 | 6921.17 | 49583.09 | 536088.55 | 2831.51 | 595424.32 | 190.68 | 0 | 0 | 595615 | 0 | 0 | 0 | 0 | 595615 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508963 | Cliasmol WTW - PLC | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-01-03 | 2023-11-20 | 2024-04-29 | 2025-11-10 | 2026-02-10 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3229 | 3229 | 246770.41 | 0 | 0 | 249999.41 | 0 | 0 | 0 | 0 | 249999.41 | 0 | [5 empty] | N | SR21_WA | 100%
502871 | Cliasmol WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-26 | 2020-03-31 | 2020-03-31 | 2020-05-22 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 21238 | 1111.63 | -19082.67 | 0 | 3266.96 | 0 | 0 | 0 | 3266.96 | 0 | 0 | 0 | 0 | 3266.96 | 122419.09 | [5 empty] | N | WG1 | 100%
500097 | Climate Change Impacts - Wastewater System Vulnerability | Q&S4 | Climate Change | Climate Change |  |  | Wastewater | SEPA | SWMD | Climate Change | MS7 | 2015-03-31 | 2016-11-29 | 2016-11-30 | 2017-12-31 | 2018-02-28 | Scottish Water Wide | 0 | 0 | 6176 | 37820.8 | 113010.85 | -133871.42 | 133467.7 | 0 | 156603.93 | 0 | 0 | 0 | 156603.93 | 0 | 0 | 0 | 0 | 156603.93 | 229645.78 | [5 empty] | Y | CC4S | 100% | [62 empty] | 1 |  |  |  |  | 0
500099 | Climate Change Impacts - Water Treatment Vulnerability | Q&S4 | Climate Change | Climate Change |  |  | Water | SEPA | SWMD | Climate Change | MS7 | 2015-03-31 | 2016-11-29 | 2016-11-30 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 1498 | 27962.87 | 30084.31 | 1345.99 | 0 | 0 | 60891.17 | 0 | 0 | 0 | 60891.17 | 0 | 0 | 0 | 0 | 60891.17 | 54751.77 | [5 empty] | Y | CC4W | 100% | [62 empty] | 1 |  |  |  |  | 0
500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change |  |  | Water | SEPA | SWD | Climate Change | MS4 | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2021-02-17 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 1798 | 150 | 28984.72 | 13160.62 | 164437.37 | 51469.29 | 260000 | 0 | 0 | 20800 | 260000 | 20800 | 0 | 0 | 20800 | 280800 | 482736.04 | [5 empty] | N | CC4W | 100%
500098 | Climate Change Risk Assessments | Q&S4 | Climate Change | Climate Change |  |  | General | SEPA | SWD | Climate Change | MS7 | 2015-03-31 | 2015-09-25 | 2015-09-25 | 2016-06-14 | 2016-03-30 | Scottish Water Wide | 0 | 0 | 20843.73 | 10622.38 | 0 | 0 | 0 | 0 | 31466.11 | 0 | 0 | 0 | 31466.11 | 0 | 0 | 0 | 0 | 31466.11 | 68045.58 | [5 empty] | N | CC4S | 50% | CC4W | 50%
500093 | Climate Change Trend Data Storage System | Q&S4 | Climate Change | Climate Change |  |  | General |  | SWD | Climate Change | MS7 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | Scottish Water Wide | 0 | 0 | 4186.05 | 71.18 | 0 | 0 | 0 | 0 | 4257.23 | 0 | 0 | 0 | 4257.23 | 0 | 0 | 0 | 0 | 4257.23 | 81600.61 | [5 empty] | N | CC4S | 50% | CC4W | 50%
500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change |  |  | Wastewater | SEPA | SWD | Climate Change | MS7 | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-28 | 2019-08-29 | Scottish Water Wide | 0 | 0 | 10465.12 | 871.87 | 30086.3 | 97914.71 | 36594.86 | 0 | 175932.86 | 0 | 0 | 0 | 175932.86 | 0 | 0 | 0 | 0 | 175932.86 | 931439.43 | [5 empty] | N | CC4S | 100%
500091 | Climate Change Trends Monitoring B Corrosion and Sulphide | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWD | Climate Change | MS7 | 2015-09-30 | 2015-12-21 | 2015-12-21 | 2018-11-30 | 2019-05-14 | Scottish Water Wide | 0 | 0 | 17558.09 | 11550 | 667.91 | 4724 | -11441.73 | 0 | 23058.28 | 0 | 0 | 0 | 23058.28 | 0 | 0 | 0 | 0 | 23058.28 | 166180.02 | [5 empty] | N | CC4S | 100%
500094 | Climate Change Trends Monitoring C Groundwater | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWD | Climate Change | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-24 | 2016-05-20 | Scottish Water Wide | 0 | 0 | 418.6 | 0 | 0 | 0 | 0 | 0 | 418.6 | 0 | 0 | 0 | 418.6 | 0 | 0 | 0 | 0 | 418.6 | 0 | [5 empty] | N | CC4W | 100%
500719 | Clinterty WWTW 1960-1970 NJ832110 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-06-30 | 2017-04-06 | 2017-05-02 | 2018-07-11 |  | Aberdeen City | 0 | 0 | 69870 | 182475.89 | 665982.11 | 16672 | 0 | -15511.7 | 919488.3 | 0 | 0 | 0 | 919488.3 | 0 | 0 | 0 | 0 | 919488.3 | 299983.07 | [5 empty] | N | CM_WWI | 5.5% | CM_WWNI | 94.5%
402631 | Clochandighter to Stranog TM Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-04-16 | 2012-08-01 | 2012-09-03 | 2013-08-07 |  | Aberdeen City | 396613 | 0 | -1837.82 | 0 | 0 | 0 | 0 | 0 | -1837.82 | 0 | 0 | 0 | 394775.18 | 0 | 0 | 0 | 0 | 394775.18 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501304 | Cloud Capacity | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-10 | 2016-06-02 | 2016-06-02 | 2017-11-15 |  | Scottish Water Wide | 0 | 0 | 69734 | 208440.13 | 104835.58 | 0 | 0 | 0 | 383009.71 | 0 | 0 | 0 | 383009.71 | 0 | 0 | 0 | 0 | 383009.71 | 306661.32 | [5 empty] | N | CM_M&G | 100%
401383 | Clovenfords Smithy Row - Sewer Flooding | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-24 | 2012-07-16 | 2012-10-29 | 2013-06-24 | 2013-06-24 | Highland | 232257 | 0 | -2072.3 | 0 | 0 | 0 | 0 | 0 | -2072.3 | 0 | 0 | 0 | 230184.7 | 0 | 0 | 0 | 0 | 230184.7 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
509396 | Clubbiedean Ground Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 |  | 2020-11-04 | 2020-11-23 | 2021-07-12 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4103 | 4103 | 3897.25 | 0 | 0 | 8000.25 | 0 | 0 | 0 | 0 | 8000.25 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500885 | Clunas RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-10-06 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 0 | 2518.66 | 181.34 | 11378 | -11073.87 | 0 | 0 | 3004.14 | 0 | 0 | 0 | 3004.14 | 0 | 0 | 0 | 0 | 3004.14 | 205473.42 | [5 empty] | N | DW5FS | 100%
45791 | Cluny SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-06-28 | 2011-11-14 | 2012-09-06 | 2012-11-26 | Fife | 495961.95 | 0 | 312.49 | 0 | 0 | 0 | 0 | 0 | 312.49 | 0 | 0 | 0 | 496274.44 | 0 | 0 | 0 | 0 | 496274.44 | 57522.26 | [5 empty] | N | WQ01B | 14.53% | WQ01C | 85.47%
400122 | Clyde Cluster 1 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-26 | 2012-10-29 | 2015-03-25 |  | Glasgow City | 4403337 | 0 | -48209 | -73606.87 | 121.32 | 0 | 0 | 0 | -121694.55 | 0 | 0 | 0 | 4281642.45 | 0 | 0 | 0 | 0 | 4281642.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400123 | Clyde Cluster 2 Capital maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-26 | 2012-10-29 | 2014-03-24 |  | Glasgow City | 1171462.37 | 0 | 710.63 | -1472.26 | 0 | 0 | 0 | 0 | -761.63 | 0 | 0 | 0 | 1170700.74 | 0 | 0 | 0 | 0 | 1170700.74 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501717 | Clydeside Expressway - Sewer Investigations | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-27 | 2017-01-27 | 2017-01-27 | 2016-12-06 |  | Glasgow City | 0 | 0 | 0 | 1674.42 | 0 | 0 | 0 | 0 | 1674.42 | 0 | 0 | 0 | 1674.42 | 0 | 0 | 0 | 0 | 1674.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500718 | CM Asbestos Management Yrs 1 & 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-06-01 |  | Scottish Water Wide | 0 | 0 | 149946.61 | 215079.39 | 265717.1 | 410769.93 | 495552.14 | 177977.32 | 1715042.49 | -29322.58 | 0 | 0 | 1685719.91 | 0 | 0 | 0 | 0 | 1685719.91 | 613322.63 | [5 empty] | N | CM_M&G | 100%
401390 | CM DI Meter Verification Programme SR10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-09-20 | 2010-10-07 | 2011-05-02 | 2015-09-04 |  | Scottish Water Wide | 301994.4 | 0 | 32301.34 | 0 | 0 | 0 | 0 | 0 | 32301.34 | 0 | 0 | 0 | 334295.74 | 0 | 0 | 0 | 0 | 334295.74 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505349 | CM North Loch Glass Spillway Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-03-11 | 2020-11-02 | 2021-03-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1635.51 | 20306.74 | 21942.25 | 0 | 0 | 0 | 21942.25 | 0 | 0 | 0 | 0 | 21942.25 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506939 | CM of 4in CI main Dykescroft Moscow | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-06-17 | 2020-10-12 | 2021-01-29 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40971 | 40971 | 0 | 0 | 0 | 40971 | 0 | 0 | 0 | 0 | 40971 | 311236.79 | [5 empty] | N | WSI | 100%
502443 | CM Raw Water Intake Surveys | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-10 | 2017-02-10 | 2017-02-10 | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 10509.26 | 9004.01 | 29654.7 | 20916.78 | -10691.56 | 59393.19 | 0 | 0 | 0 | 59393.19 | 0 | 0 | 0 | 0 | 59393.19 | 119022.58 | [5 empty] | N | CM_WSI | 100%
402705 | CM Start Early Wastewater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-05-16 | 2015-05-07 | 2015-05-07 | 2015-04-09 |  | Scottish Water Wide | 190000 | 0 | 705.72 | 0 | 0 | 0 | 0 | 0 | 705.72 | 0 | 0 | 0 | 190705.72 | 0 | 0 | 0 | 0 | 190705.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402703 | CM Start Early Water | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-05-16 | 2013-10-11 | 2013-10-14 | 2017-03-17 |  | Scottish Water Wide | 1650000 | 0 | 50000 | -10890.65 | 0 | 0 | 0 | 0 | 39109.35 | 0 | 0 | 0 | 1689109.35 | 0 | 0 | 0 | 0 | 1689109.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503985 | CM Woodhill Rd DMA - St Mungos Street Bishopbriggs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2019-12-09 |  | 2021-03-23 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 98614.05 | 162385.3 | 260999.35 | 0 | 0 | 0 | 260999.35 | 0 | 0 | 0 | 0 | 260999.35 | 119022.58 | [5 empty] | N | WSNI | 100%
501632 | CMA Market Releases | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2021-05-07 |  | Scottish Water Wide | 0 | 0 | 0 | 201299.1 | 177872 | 560710 | -110858.63 | 116542.53 | 945565 | 0 | 0 | 0 | 945565 | 0 | 0 | 75645.2 | 75645.2 | 1021210.2 | 306661.32 | [5 empty] | N | CM_M&G | 100%
402071 | CMA System changes - March Release | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-03-29 | 2011-03-29 | 2011-04-01 | 2016-08-08 |  | Scottish Water Wide | 983867 | 0 | 13080.11 | 0 | 0 | 0 | 0 | 0 | 13080.11 | 0 | 0 | 0 | 996947.11 | 0 | 0 | 0 | 0 | 996947.11 | 0 | [5 empty] | N | CS20 | 100%
403350 | CMAP Customer Service Delivery Identified Sewer Rehabilitation Phase 4 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-04-29 | 2013-04-29 | 2013-05-22 | 2014-11-14 |  | Scottish Water Wide | 822926.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822926.35 | 0 | 0 | 0 | 0 | 822926.35 | 0 | [6 empty] | CM_WWI | 100%
403351 | CMAP Customer Service Delivery Identified Sewer Rehabilitation Phase 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-03-18 | 2013-03-18 | 2013-07-01 | 2015-06-25 |  | Scottish Water Wide | 1630000 | 0 | -31971.24 | 0 | 0 | 0 | 0 | 0 | -31971.24 | 0 | 0 | 0 | 1598028.76 | 0 | 0 | 0 | 0 | 1598028.76 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403904 | CMC Aviemore WwTW Package Centrifuge Dewatering Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-09-15 | 2015-01-19 | 2016-09-19 | 2017-05-29 |  | Highland | 69877 | 0 | 348919 | 160228 | 24653.64 | 15056.15 | 0 | 0 | 548856.79 | 0 | 0 | 0 | 618733.79 | 0 | 0 | 0 | 0 | 618733.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403748 | CMC DI Metering Pilot | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-24 | 2014-02-24 | 2014-04-09 | 2016-03-10 |  | Scottish Water Wide | 327673.97 | 0 | 34007.2 | 0 | 0 | 0 | 0 | 0 | 34007.2 | 0 | 0 | 0 | 361681.17 | 0 | 0 | 0 | 0 | 361681.17 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403615 | CMC Energy Improvement Prog Accelerated Energy Consumption Reduction Prog (W & WW) | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWMD | Non OMG180 | MS7 | 2013-12-18 | 2013-12-18 | 2014-02-03 | 2016-12-14 |  | Scottish Water Wide | 3424237 | 0 | -31727.02 | -44475 | 302.29 | 0 | 0 | 0 | -75899.73 | 0 | 0 | 0 | 3348337.27 | 0 | 0 | 0 | 0 | 3348337.27 | 0 | [5 empty] | N | ESP | 100%
402441 | CMC Health and Safety - Lifting Chain Compliance Programme | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-11-10 | 2012-10-31 | 2012-11-19 | 2017-05-29 |  | Scottish Water Wide | 1238293 | 0 | 13139.3 | 104.91 | 44.59 | 0 | 0 | 0 | 13288.8 | 0 | 0 | 0 | 1251581.8 | 0 | 0 | 0 | 0 | 1251581.8 | 209381.79 | [5 empty] | N | CM_M&G | 100%
403375 | CMC HL Non Complex Projects 2013-15 South Wastewater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-28 | 2019-02-14 |  | All South Unitary Authorities | 3653315 | 0 | 431465 | -30591.53 | 27723.83 | 11685.39 | -943.79 | 0 | 439338.9 | 0 | 0 | 0 | 4092653.9 | 0 | 0 | 0 | 0 | 4092653.9 | 90601.29 | [5 empty] | N | CM_WWI | 100%
403378 | CMC HL Non Complex Projects 2013-15 West Wastewater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-22 | 2017-03-06 |  | All West Unitary Authorities | 2988090 | 0 | 737457 | -56711.58 | -3822.02 | 63.87 | 0 | 0 | 676987.27 | 0 | 0 | 0 | 3665077.27 | 0 | 0 | 0 | 0 | 3665077.27 | 90601.29 | [5 empty] | N | CM_WWI | 100%
403371 | CMC HL Non Complex Projects 2014-15 North Wastewater | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2014-05-15 | 2014-05-16 |  | All North Unitary Authorities | 9820.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9820.49 | 0 | 0 | 0 | 0 | 9820.49 | 0 | [6 empty] | CM_WWI | 100%
404021 | CMC Ness Area Metering | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-11-26 | 2014-11-26 | 2015-01-12 | 2015-07-30 |  | All North Unitary Authorities | 99599 | 0 | 197893.81 | 0 | 0 | 0 | 0 | 0 | 197893.81 | 0 | 0 | 0 | 297492.81 | 0 | 0 | 0 | 0 | 297492.81 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403627 | CMC Programme Line for RCC | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-11-13 | 2013-11-13 | 2014-05-06 | 2019-05-08 |  | Scottish Water Wide | 142968 | 0 | 3874 | 3026.98 | 4472.98 | 902.08 | 1969.74 | 0 | 14245.78 | 0 | 0 | 0 | 157213.78 | 0 | 0 | 0 | 0 | 157213.78 | 311236.79 | [5 empty] | N | CM_WSI | 100%
30148 | Coalburn STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2010-06-28 | 2010-09-20 | 2012-02-01 | 2012-03-12 | South Lanarkshire | 3371144.21 | 0 | 1198.09 | 0 | 0 | 0 | 0 | 0 | 1198.09 | 0 | 0 | 0 | 3372342.3 | 0 | 0 | 0 | 0 | 3372342.3 | 148123.55 | [5 empty] | N | CM_WWNI | 26.6% | EC04A | 33.84% | EC10A | 39.56%
400073 | Cobden Street WwPS Refurb SPS001318 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-06 | 2011-03-30 | 2011-09-19 | 2012-09-05 |  | Angus | 678633.81 | 0 | 75.52 | 0 | 0 | 0 | 0 | 0 | 75.52 | 0 | 0 | 0 | 678709.33 | 0 | 0 | 0 | 0 | 678709.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506535 | Cochno DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-08-24 | 2022-10-21 | 2023-01-23 | 2023-12-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570.8 | 1570.8 | 287429.2 | 0 | 0 | 289000 | 0 | 0 | 0 | 0 | 289000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503133 | Cochno SR - New Tanks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2027-04-01 | 2028-05-31 | 2028-10-03 | 2029-05-15 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 11932.82 | 33284.81 | 4720.21 | 49937.84 | 235586.51 | 0 | 0 | 285524.35 | 0 | 0 | 0 | 0 | 285524.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403221 | Cochno SR - Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-16 | 2014-10-01 | 2014-10-01 | 2014-10-01 |  | Glasgow City | 138508.25 | 0 | 550.84 | 0 | 0 | 0 | 0 | 0 | 550.84 | 1864.03 | 0 | 0 | 140923.12 | 0 | 0 | 0 | 0 | 140923.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506517 | Cockmuir DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-07-20 | 2022-09-05 | 2022-12-12 | 2023-11-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2344.54 | 2344.54 | 449905.46 | 0 | 0 | 452250 | 0 | 0 | 0 | 0 | 452250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403065 | Cockmuir SR and TWP - Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-11-22 | 2014-10-01 | 2014-10-01 | 2014-10-21 |  | Glasgow City | 157857.02 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 157873.02 | 0 | 0 | 0 | 0 | 157873.02 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
511466 | Cocksburn - Lossburn Reservoir Maintenance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 |  | 2021-05-24 | 2021-08-13 | 2022-03-28 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148000 | 0 | 0 | 148000 | 0 | 0 | 0 | 0 | 148000 | 0 | [5 empty] | N | SR21_WA | 100%
403565 | Colinsburgh WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-08-27 | 2016-12-15 | 2016-12-15 | 2016-12-16 | 2016-12-16 | Fife | 41656 | 0 | 46642.9 | 46237.73 | 0 | 0 | 0 | 0 | 92880.63 | 0 | 0 | 0 | 134536.63 | 0 | 0 | 0 | 0 | 134536.63 | 0 | [5 empty] | N | SG1 | 100%
503831 | Colintraive BPT - inlet main relocation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-01-22 |  | 2020-11-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 539.85 | -539.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WSI | 100%
509367 | Colintraive BPT - inlet main relocation & pressure management | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-11-20 | 2021-03-18 | 2021-08-06 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16021 | 16021 | 33978.97 | 0 | 0 | 49999.97 | 0 | 0 | 0 | 0 | 49999.97 | 311236.79 | [5 empty] | N | WSI | 100%
502313 | Coll RWM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-06-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 5133.26 | 923.31 | 42.58 | -4248.62 | 0 | 1850.53 | 0 | 0 | 0 | 1850.53 | 0 | 0 | 0 | 0 | 1850.53 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402934 | Coll-Garyguirm ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-10-23 | 2013-12-18 | 2017-02-02 | 2017-02-07 | 2017-02-07 | Na H-Eileanan an Iar | 39672 | 0 | 33359 | -21609.79 | 0 | 0 | 0 | 0 | 11749.21 | 0 | 0 | 0 | 51421.21 | 0 | 0 | 0 | 0 | 51421.21 | 0 | [5 empty] | N | SG1 | 100%
507585 | Colonsay WTW - PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-10-05 | 2023-08-22 | 2024-01-30 | 2025-08-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8898 | 8898 | 491102.77 | 0 | 0 | 500000.77 | 0 | 0 | 0 | 0 | 500000.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506052 | Colpy DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-07-20 | 2022-09-06 | 2022-12-08 | 2023-11-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35460 | 35460 | 732133.32 | 0 | 0 | 767593.32 | 0 | 0 | 0 | 0 | 767593.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403170 | Comely Bank Edinburgh | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-11-26 | 2013-05-20 | 2013-06-25 | 2013-10-23 | 2013-10-23 | City of Edinburgh | 40917 | 0 | -3265.08 | 0 | 0 | 0 | 0 | 0 | -3265.08 | 0 | 0 | 0 | 37651.92 | 0 | 0 | 0 | 0 | 37651.92 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
300025 | Commerce Road Stranraer - Surface Water Management Plan | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-09-05 | 2011-09-05 | 2011-10-19 | 2012-03-16 | 2011-03-14 | Dumfries and Galloway | 35891.52 | 0 | -2843.7 | 0 | 0 | 0 | 0 | 0 | -2843.7 | 0 | 0 | 0 | 33047.82 | 0 | 0 | 0 | 0 | 33047.82 | 28761.13 | [5 empty] | N | EC01D | 100%
505498 | Commissioners Rd PRV A & B Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-03-05 |  | 2020-08-15 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 1308.41 | 42671.59 | 43980 | 1305.15 | 0 | 0 | 45285.15 | 0 | 0 | 0 | 0 | 45285.15 | 119022.58 | [5 empty] | N | WSNI | 100%
504991 | Complex Bypass Pilot | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2020-02-12 | 2020-03-03 | 2021-01-05 | 2022-09-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683808 | 683808 | 777029.12 | 0 | 0 | 1460837.12 | 0 | 0 | 0 | 0 | 1460837.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509465 | Complex Repair at Bogbain DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-12-09 | 2023-02-06 | 2023-05-12 | 2024-04-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1525.77 | 1525.77 | 275069.23 | 0 | 0 | 276595 | 0 | 0 | 0 | 0 | 276595 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506673 | Complex Repair at Dervaig DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-10-03 | 2023-11-20 | 2024-02-28 | 2025-06-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1613.44 | 1613.44 | 599123.28 | 0 | 0 | 600736.72 | 0 | 0 | 0 | 0 | 600736.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401202 | Compliance with Lead Regulations Comms Pipes - East Cluster | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-07-19 | 2010-12-17 | 2011-01-24 | 2014-06-20 | 2014-07-31 | All East Unitary Authorities | 1318698 | 0 | 646 | -818.25 | 0 | 0 | 0 | 0 | -172.25 | 0 | 0 | 0 | 1318525.75 | 0 | 0 | 0 | 0 | 1318525.75 | 0 | [5 empty] | N | DW1A | 100%
401204 | Compliance with Lead Regulations Comms Pipes - North Cluster 2 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-07-19 | 2010-12-17 | 2011-01-24 | 2014-03-28 | 2014-03-31 | All North Unitary Authorities | 496352 | 0 | 240 | -753.63 | 0 | 0 | 0 | 0 | -513.63 | 0 | 0 | 0 | 495838.37 | 0 | 0 | 0 | 0 | 495838.37 | 0 | [5 empty] | N | DW1A | 100%
400069 | Compliance with SEPA Matrix for WwTW Flow Monitoring WQ01A | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-10-06 | 2011-09-21 | 2011-09-23 | 2015-03-30 | 2015-03-30 | Scottish Water Wide | 3463779.75 | 0 | 4733.51 | 0 | 323.47 | 0 | 0 | 0 | 5056.98 | 0 | 0 | 0 | 3468836.73 | 0 | 0 | 0 | 0 | 3468836.73 | 28761.13 | [5 empty] | N | WQ01A | 100%
500589 | Compute and Storage Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-01 | 2016-11-09 | 2016-11-09 | 2017-06-30 |  | Scottish Water Wide | 0 | 0 | 386941.66 | 270481.57 | 38834.74 | -2789.45 | 0 | 0 | 693468.52 | 0 | 0 | 0 | 693468.52 | 0 | 0 | 0 | 0 | 693468.52 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403413 | Condition Monitoring Feasibility-Scoping Study | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2013-05-24 | 2021-04-01 | 2021-04-01 | 2021-04-22 |  | Scottish Water Wide | 50000 | 0 | 0 | 0 | 0 | -48780.49 | 8504.63 | 31136.86 | -9139 | 9138.59 | 0 | 0 | 49999.59 | 0 | 0 | 0 | 0 | 49999.59 | 730242.44 | [5 empty] | N | WSI | 0.25% | WSNI | 0.25% | WWNI | 0.25% | WWI | 99.25%
502631 | Condition Surveys Forrest Rd TM Cumbernauld | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-06-15 | 2018-02-28 | 2018-05-18 | 2018-11-12 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 227319 | 78536.08 | 51.97 | 0 | 305907.05 | 0 | 0 | 0 | 305907.05 | 0 | 0 | 0 | 0 | 305907.05 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503325 | Condition Surveys -Mains Park loop Erskine Dechmont TM & Megget E RWM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2018-07-31 | 2019-03-19 | 2019-04-24 | 2020-03-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 34513.01 | 110744.86 | 0 | 145257.87 | 0 | 0 | 0 | 145257.87 | 0 | 0 | 0 | 0 | 145257.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506055 | Conisby DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-06-21 | 2022-07-13 | 2022-10-13 | 2023-09-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4397.81 | 4397.81 | 455602.19 | 0 | 0 | 460000 | 0 | 0 | 0 | 0 | 460000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502377 | Connel ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-11-02 | 2018-11-02 | 2018-11-02 | 2018-11-02 | 2018-11-02 | Highland | 0 | 0 | 0 | 46062.91 | 16468.81 | 340.06 | 0 | 0 | 62871.78 | 0 | 0 | 0 | 62871.78 | 0 | 0 | 0 | 0 | 62871.78 | 122419.09 | [5 empty] | N | SG1 | 100%
502794 | Conon Bridge WwTW - Compliance Risk Reduction | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-07-08 | 2024-04-16 | 2024-07-15 | 2025-05-26 |  | Highland | 0 | 0 | 0 | 0 | 20817.18 | 537.73 | 7349.91 | 3677.31 | 32382.13 | 967617.88 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502923 | Consultants Onsite Plans | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW1 | 2021-07-30 | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2021-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 227947.58 | 9243.4 | 243538.67 | -208048.41 | 272681.24 | 227318.76 | 227318.76 | 315557.1389 | 500000 | 88238.3789 | 0 | 0 | 88238.3789 | 588238.3789 | 0 | [5 empty] | N | WR6 | 100%
511000 | Control System Replacement - Bonnybridge STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509711 | Control System Replacement - Livingston WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2022-03-21 | 2024-02-05 | 2024-07-15 | 2026-01-26 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28151.57 | 28151.57 | 1272065.27 | 0 | 0 | 1300216.84 | 0 | 0 | 0 | 0 | 1300216.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506126 | Coordination of Drainage Partnerships | IR18 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWD | Flood Risk Management Act | MS2 | 2020-04-14 | 2020-05-11 | 2023-07-13 | 2023-07-14 | 2023-09-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75477.32 | 75477.32 | 181522.68 | 0 | 0 | 257000 | 0 | 50068.6463 | 0 | 50068.6463 | 307068.6463 | 1106452.62 | [5 empty] | N | CS16D_ID | 100%
402850 | Corbiehall Boness | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2012-08-20 | 2014-09-30 | 2015-01-13 | 2015-03-24 | 2015-03-24 | West Lothian | 295629 | 295629 | 40885.66 | 204.5 | -1631.25 | 0 | 0 | 0 | 39458.92 | 0 | 0 | 0 | 335087.92 | 0 | 0 | 0 | 0 | 335087.92 | 180449.74 | [5 empty] | N | FL_DD | 100%
500957 | Core Infrastructure and Capabilities | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-11-24 | 2017-03-01 | 2017-03-01 | 2018-03-28 |  | Scottish Water Wide | 0 | 0 | 416746 | 2445157.22 | 1950165.12 | -31285.66 | 0 | 0 | 4780782.68 | 0 | 0 | 0 | 4780782.68 | 0 | 0 | 0 | 0 | 4780782.68 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503321 | Cornceres WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-05-13 | 2028-10-25 | 2029-02-28 | 2030-02-26 |  | Fife | 0 | 0 | 0 | 0 | 0 | 78524.5 | 3454.5 | 0 | 81979 | 0 | 0 | 0 | 81979 | 0 | 0 | 0 | 0 | 81979 | 122419.09 | [5 empty] | N | SG1 | 100%
504502 | Corpach Beach pumping station - rising main repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 11322.16 | 64.59 | 11386.75 | 0 | 0 | 0 | 11386.75 | 0 | 0 | 0 | 0 | 11386.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500122 | Corpach DOA (DOA000325) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-09-27 | 2020-01-07 | Highland | 0 | 0 | 10844 | 16121 | 7511 | 62607 | 33072.13 | 0 | 130155.13 | 0 | 0 | 0 | 130155.13 | 0 | 0 | 0 | 0 | 130155.13 | 22032.23 | [5 empty] | N | EC01G | 23.78% | EC01D | 32.91% | CS16D | 43.31%
46334 | Corpach WWTW - STW001632 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-13 | 2015-04-30 | 2015-02-12 | 2015-02-12 |  | Highland | 513456.45 | 0 | 33.08 | 0 | 0 | 0 | 0 | 0 | 33.08 | 0 | 0 | 0 | 513489.53 | 0 | 0 | 0 | 0 | 513489.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503326 | Corpach WwTW - WwTW DOA rationalisation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2022-03-09 | 2024-01-11 | 2024-03-25 | 2025-05-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 21764.56 | 6185.94 | 16707.5 | 44658 | 1955342.23 | 0 | 0 | 2000000.23 | 0 | 0 | 0 | 0 | 2000000.23 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403918 | Corpach WwTW (transfer from 046334) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2014-10-10 | 2017-11-22 | 2018-01-29 | 2019-06-10 |  | Highland | 2005.85 | 0 | 184042.15 | 77833 | 792790 | 617312 | 22285.3 | 44055.7 | 1738318.15 | 0 | 0 | 0 | 1740324 | 0 | 0 | 0 | 0 | 1740324 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500621 | Corporate Comms SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 927543.35 | 1113164.28 | 1235000.8 | 1253028.3 | 1341151.18 | 1430684 | 7300571.91 | 0 | 0 | 0 | 7300571.91 | 0 | 0 | 0 | 0 | 7300571.91 | 306661.32 | [5 empty] | N | CM_OVH | 100%
403272 | Corporate Risk Reduction - Assessment of pipelines crossing gas and oil pipes | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-28 | 2014-04-29 | 2014-04-29 | 2014-05-06 |  | Scottish Water Wide | 15537.85 | 0 | 0 | 47.45 | 0 | 0 | 0 | 0 | 47.45 | 0 | 0 | 0 | 15585.3 | 0 | 0 | 0 | 0 | 15585.3 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501029 | Corporate Web Site Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-23 | 2016-05-16 | 2016-05-16 | 2020-02-12 |  | Scottish Water Wide | 0 | 0 | 10154 | 456629.5 | 339687.6 | 218106.4 | 147010.6 | 0 | 1171588.1 | 0 | 0 | 0 | 1171588.1 | 0 | 0 | 0 | 0 | 1171588.1 | 306661.32 | [5 empty] | N | CM_M&G | 100%
504478 | Corran Sep replacement outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-02-05 | 2020-08-13 | 2020-11-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 38682.06 | 39682.06 | 0 | 0 | 0 | 39682.06 | 0 | 0 | 0 | 0 | 39682.06 | 209381.79 | [5 empty] | N | CM_WWI | 100%
50042 | Correction to Previous Year - CM | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -6170000 | 6170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_M&G | 100%
50041 | Correction to Previous Year - SR21 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 6170000 | -6170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SR21_SS | 100%
400719 | Corrie Terrace ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2011-11-10 | 2012-09-28 | 2013-02-19 | 2013-02-19 | North Ayrshire | 279753 | 0 | 25360 | -8232.95 | 0 | 0 | 0 | 0 | 17127.05 | 0 | 0 | 0 | 296880.05 | 0 | 0 | 0 | 0 | 296880.05 | 122419.09 | [5 empty] | N | SG1 | 100%
30154 | Corsehouse WTW - Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2005-11-03 | 2007-04-11 | 2007-04-11 | 2011-03-31 | 2013-12-23 | East Ayrshire | 10950532.62 | 0 | 13484.3 | 0 | 0 | 0 | 0 | 0 | 13484.3 | 0 | 0 | 0 | 10964016.92 | 0 | 0 | 0 | 0 | 10964016.92 | 119022.58 | [5 empty] | N | WSNI | 6% | DW13 | 18.8% | DW2 | 18.8% | DW3C | 18.8% | DW3G | 18.8% | DW4A | 18.8%
502708 | Corserig Crescent Kirkconnel | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-10-23 | 2019-07-31 | 2019-10-14 | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 30066.08 | 194303.92 | 989580 | 88664 | 1302614 | 0 | 0 | 0 | 1302614 | 0 | 0 | 0 | 0 | 1302614 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501047 | Cost and Investment Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-11-18 | 2016-04-11 | 2016-04-11 | 2018-01-24 |  | Scottish Water Wide | 0 | 0 | 104225 | 271529.32 | 0 | 0 | 0 | 0 | 375754.32 | 0 | 0 | 0 | 375754.32 | 0 | 0 | 0 | 0 | 375754.32 | 306661.32 | [5 empty] | N | CM_M&G | 100%
501898 | Cost Investment Intelligence Project - EES & SWISS Strategic Refresh Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-03-01 | 2019-09-30 | 2019-09-30 | 2021-09-29 |  | Scottish Water Wide | 0 | 0 | 0 | 294324.8 | 1279591.97 | -419395.69 | 2029341.28 | 1964543.61 | 5148405.97 | 565858.1 | 0 | 0 | 5714264.07 | 0 | 0 | 457141.1256 | 457141.1256 | 6171405.1956 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502306 | Cotlandhill SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-09-21 | 2020-12-08 | 2021-02-05 | 2021-09-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 37591.29 | 4800.23 | 18870.7 | 35542.75 | 154867.03 | 251672 | 444369.19 | 0 | 0 | 696041.19 | 0 | 0 | 0 | 0 | 696041.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507017 | Cotlandhill SR roof replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2020-09-22 | 2022-05-06 | 2022-08-05 | 2023-12-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123954 | 123954 | 1071743.67 | 0 | 0 | 1195697.67 | 0 | 0 | 0 | 0 | 1195697.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508370 | Coulter Draw-off Tower Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-09-08 | 2021-04-09 | 2021-07-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57166.3 | 57166.3 | 150109.14 | 0 | 0 | 207275.44 | 0 | 0 | 0 | 0 | 207275.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403357 | Coulter Reservoir - IoS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-04 | 2015-09-22 | 2015-11-09 | 2016-03-23 |  | South Lanarkshire | 9239 | 0 | 255761 | 23865.75 | -2386.58 | 0 | 0 | 0 | 277240.17 | 0 | 0 | 0 | 286479.17 | 0 | 0 | 0 | 0 | 286479.17 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500805 | Coulter RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2015-10-28 | 2017-07-21 | 2017-08-14 | 2018-03-31 | 2018-06-30 | South Lanarkshire | 0 | 0 | 31000 | 369.43 | 188786.38 | 21571.48 | -510.17 | 0 | 241217.13 | 0 | 0 | 0 | 241217.13 | 0 | 0 | 0 | 0 | 241217.13 | 529906.83 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 84.43 | [43 empty] | 0
506335 | Coulter Scour Valve Repair | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-06-29 | 2021-04-12 | 2021-08-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3096 | 3096 | 7903.83 | 0 | 0 | 10999.83 | 0 | 0 | 0 | 0 | 10999.83 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503056 | Coulter WOA -Water Crossing and Bank Protection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2020-09-21 | 2021-12-20 | 2022-01-24 | 2022-08-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 23260.53 | 13691.1 | 1855.28 | 135424.16 | 174231.08 | 891804.92 | 0 | 0 | 1066036 | 0 | 0 | 0 | 0 | 1066036 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402855 | Coupar Angus Road Dundee | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2014-07-07 | 2014-07-21 | 2014-09-23 | 2014-09-23 | Dundee City | 68615 | 0 | 150 | -249.92 | 0 | 0 | 0 | 0 | -99.92 | 0 | 0 | 0 | 68515.08 | 0 | 0 | 0 | 0 | 68515.08 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
503232 | Coupar Angus WwTW - Inlet Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2019-01-28 | 2019-01-28 | 2019-05-31 | 2020-03-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 140375.9 | 270645.09 | 20782.01 | 431803 | 385.2 | 0 | 0 | 432188.2 | 0 | 0 | 0 | 0 | 432188.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
30157 | Coursington (Motherwell) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-16 | 2011-12-20 | 2012-02-29 | 2015-01-26 | 2015-03-30 | North Lanarkshire | 2189671.29 | 0 | -260.38 | 1653.56 | 0 | 0 | 0 | 0 | 1393.18 | 0 | 0 | 0 | 2191064.47 | 0 | 0 | 0 | 0 | 2191064.47 | 119362.42 | [5 empty] | N | CM_WWNI | 25% | EC04A | 75%
503542 | Coursington WWTW Chemical Dosing | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWD | UWWTD - Works | MS5 | 2018-01-31 | 2018-01-31 | 2018-02-26 | 2019-03-31 | 2019-03-31 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 27672.9 | 353082.67 | 4767.43 | 385523 | 0 | 0 | 0 | 385523 | 0 | 0 | 0 | 0 | 385523 | 604657.61 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
502754 | Cove Spine Waste Water Infrastructure | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Wastewater |  | SWD | DWQ Reliability | MS3 | 2017-07-12 | 2017-07-12 | 2017-10-17 | 2022-04-01 | 2022-04-01 | Aberdeen City | 0 | 0 | 0 | 0 | 109508.13 | 0 | -1415.53 | 0 | 108092.6 | 0 | 0 | 0 | 108092.6 | 0 | 0 | 0 | 0 | 108092.6 | 2956221.11 | [5 empty] | N | DW25P | 22.92% | SG5 | 77.08%
502755 | Cove Spine Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2022-01-28 |  | Aberdeen City | 0 | 0 | 0 | 0 | 5011.28 | 58814.2 | -615.83 | 13.33 | 63222.98 | 0 | 0 | 0 | 63222.98 | 0 | 0 | 0 | 0 | 63222.98 | 444766.03 | [5 empty] | N | WG5 | 100%
501947 | Cove WwTW Long Sea Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-03-29 | 2024-07-09 | 2024-09-03 | 2025-01-08 |  | Scottish Borders | 0 | 0 | 785 | 10943 | -4000.44 | 0 | 0 | 7727.44 | 15455 | 685076.88 | 0 | 0 | 700531.88 | 0 | 0 | 0 | 0 | 700531.88 | 209381.79 | [5 empty] | N | CM_WWI | 100%
46175 | Cowdenbeath Storm Tank SPS Refurb - SPS001511 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2010-12-23 | 2011-03-18 | 2012-10-03 |  | Fife | 3032171.08 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 3032361.08 | 0 | 0 | 0 | 0 | 3032361.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402177 | Cowgill Lower Spillway Pitching Repair and CCTV of Outlet Pipe | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-11 | 2012-09-05 | 2012-11-16 | 2014-03-26 | 2014-03-26 | South Lanarkshire | 336527.8 | 0 | 984.52 | 0 | 0 | 0 | 0 | 0 | 984.52 | 0 | 0 | 0 | 337512.32 | 0 | 0 | 0 | 0 | 337512.32 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507148 | Cowie WwTW - Interim Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-29 | 2024-01-22 | 2024-04-22 | 2025-05-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101059 | 101059 | 1898940.58 | 0 | 0 | 1999999.58 | 0 | 0 | 0 | 0 | 1999999.58 | 0 | [5 empty] | N | SG1 | 100%
510937 | Cowie WwTW Outfall Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2021-10-20 | 2023-05-12 | 2023-08-15 | 2024-09-18 | 2024-09-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52863.94 | 52863.94 | 997136.06 | 0 | 0 | 1050000 | 0 | 0 | 0 | 0 | 1050000 | 0 | [5 empty] | N | SR21_WW | 100%
500721 | Cowlairs Infrastructure Improvement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-12-14 | 2016-03-29 | 2016-04-02 | 2020-03-13 |  | Glasgow City | 0 | 0 | 403500 | 325728.74 | 1055.77 | 9842.74 | 122663.71 | 0 | 862790.96 | 0 | 0 | 0 | 862790.96 | 0 | 0 | 0 | 0 | 862790.96 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500892 | Cowsrieve Service Reservoir | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | WINF | Infra Charge | MS2 | 2019-02-28 | 2021-03-31 | 2021-06-02 | 2022-06-27 |  | Aberdeenshire | 0 | 0 | 23824.63 | 13707.34 | 80228.18 | 9017.79 | 258429.1 | 994972 | 1380179.04 | 3165025.06 | 0 | 0 | 4545204.1 | 0 | 0 | 363616.328 | 363616.328 | 4908820.428 | 444766.03 | [5 empty] | N | WG5 | 100%
30397 | Coylton (Joppa) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-15 | 2015-03-12 | 2015-03-12 | 2015-03-12 | 2015-03-12 | South Ayrshire | 803468.51 | 0 | 12 | -5643.07 | 0 | 0 | 0 | 0 | -5631.07 | 0 | 0 | 0 | 797837.44 | 0 | 0 | 0 | 0 | 797837.44 | 28761.13 | [5 empty] | N | EC04A | 100%
511707 | COYLTON STW REPLACEMENT OF 2 No. PST & 2 No. FST RADIAL SCRAPER BRIDGES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2024-03-04 | 2025-09-10 | 2025-12-09 | 2026-11-16 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20930.23 | 20930.23 | 379069.77 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000 | 90601.29 | [5 empty] | N | WWNI | 100%
503279 | Coylton WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-08-26 | 2019-08-26 | 2019-08-26 | 2019-08-26 | 2019-08-26 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 77202.87 | 0 | 0 | 77202.87 | 0 | 0 | 0 | 77202.87 | 0 | 0 | 0 | 0 | 77202.87 | 122419.09 | [5 empty] | N | SG1 | 100%
403936 | Coylton WwTW (Transfer from 030397) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS6 | 2009-05-15 | 2016-09-28 | 2017-01-23 | 2017-10-30 | 2017-10-30 | East Ayrshire | 47684 | 0 | 152230 | 1132068.88 | 2838971.48 | 201095.15 | -8377.67 | -200810.78 | 4115177.06 | 98955.37 | 49477.674 | 68683.4348 | 4261816.43 | 19205.7608 | 0 | 0 | 19205.7608 | 4281022.1908 | 90601.29 |  |  |  |  | 11000 | N | EC04A | 50% | CM_WWNI | 50%
507153 | CP602 Efficient Energy Operation of Rising Mains project | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-06-11 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 4800 | 11250 | 0 | 0 | 16050 | 0 | 0 | 0 | 0 | 16050 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507155 | CP603 Preventing Invert Corrosion in Rising Mains | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-06-11 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9250 | 9250 | 17500 | 0 | 0 | 26750 | 0 | 0 | 0 | 0 | 26750 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502957 | Craigend Outfall Perth | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-05-13 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 6440.28 | 25472.16 | 2667.6 | 0 | 34580.03 | 0 | 0 | 0 | 34580.03 | 0 | 0 | 0 | 0 | 34580.03 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502877 | Craigend Overland Sewer Scotlandwell | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-03-31 | 2022-10-19 | 2023-01-24 | 2024-02-27 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 16501.61 | 13539.97 | 2555.68 | 28150 | 60747.25 | 949179.75 | 0 | 0 | 1009927 | 0 | 0 | 0 | 0 | 1009927 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403323 | Craigendunton Reservoir - Spillway & other remedial works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-05-07 | 2014-12-17 | 2014-12-17 | 2015-08-25 |  | East Ayrshire | 203413 | 0 | 203087 | 0 | -693.62 | 0 | 0 | 0 | 202393.38 | 0 | 0 | 0 | 405806.38 | 0 | 0 | 0 | 0 | 405806.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500774 | Craigengillan Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-27 | 2017-12-21 | 2018-02-26 | 2018-07-18 |  | East Ayrshire | 0 | 0 | 4000 | 75402.21 | 296040.79 | 250151.03 | 37127.97 | -78595.97 | 584126.03 | 0 | 0 | 0 | 584126.03 | 0 | 0 | 0 | 0 | 584126.03 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502159 | Craighead Raw Water Springs - Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-06-20 | 2016-06-20 | 2016-06-20 | 2016-05-26 |  | Aberdeenshire | 0 | 0 | 0 | 20930.23 | 0 | 0 | 0 | 0 | 20930.23 | 0 | 0 | 0 | 20930.23 | 0 | 0 | 0 | 0 | 20930.23 | 119022.58 | [5 empty] | N | CM_WSI | 100%
505791 | Craighead Reservoir Access Track improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-03-31 | 2020-07-27 | 2020-08-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9651.88 | 9651.88 | 0 | 0 | 0 | 9651.88 | 0 | 0 | 0 | 0 | 9651.88 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500896 | Craighead WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-10-27 | 2020-11-30 | 2020-11-30 | 2022-11-07 |  | Aberdeenshire | 0 | 0 | 64413.05 | 378292.91 | 92578.51 | 112542.02 | 1161705.59 | 3743900.74 | 5553432.82 | 11258820 | 0 | 0 | 16812252.82 | 0 | 0 | 1187747.18 | 1187747.18 | 18000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509016 | Craighouse Square Kilbirnie Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2021-10-11 | 2023-03-27 | 2023-06-26 | 2024-04-15 | 2024-04-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28415.49 | 28415.49 | 221584.51 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | [5 empty] | N | SR21_WW | 100%
507583 | Craighouse WTW - PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-10-05 | 2023-08-22 | 2024-01-30 | 2025-08-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 495000.21 | 0 | 0 | 500000.21 | 0 | 0 | 0 | 0 | 500000.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502645 | Craighouse WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-06 | 2020-04-03 | 2020-04-03 | 2020-04-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 21594.1 | 1821.56 | -19140.72 | 0 | 4274.94 | 0 | 0 | 0 | 4274.94 | 0 | 0 | 0 | 0 | 4274.94 | 122419.09 | [5 empty] | N | WG1 | 100%
404008 | Craiglockhart Drive South Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2014-12-04 | 2015-08-31 | 2015-10-19 | 2016-09-07 | 2016-10-03 | City of Edinburgh | 71964 | 71964 | 858071.55 | 87464.45 | 0 | -6875.79 | 0 | 0 | 938660.21 | 0 | 0 | 0 | 1010624.21 | 0 | 0 | 0 | 0 | 1010624.21 | 180449.74 | [5 empty] | N | FL_DD | 100%
511549 | Craigluscar E&W - IoS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000.04 | 0 | 0 | 350000.04 | 0 | 0 | 0 | 0 | 350000.04 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500893 | Craigmaddie and Milngavie VT Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2019-10-04 | 2021-12-20 | 2022-03-18 | 2023-06-22 |  | East Dunbartonshire | 0 | 0 | 11086.02 | 42349.12 | 692.25 | 2891.45 | 11038.72 | 16192.09 | 84249.65 | 1020500.66 | 0 | 0 | 1104750.31 | 0 | 0 | 0 | 0 | 1104750.31 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507903 | Craignafeich Reservoir Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-19 | 2021-05-06 | 2021-11-03 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5129.36 | 5129.36 | 54831.16 | 0 | 0 | 59960.52 | 0 | 0 | 0 | 0 | 59960.52 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500231 | Craignure Mull - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-03-23 | 2016-04-25 | 2016-10-03 | 2017-02-28 | 2017-10-31 | Argyll and Bute-North Argyll | 0 | 0 | 604.07 | 9907.51 | 1531.96 | 1138.46 | -808.96 | 0 | 12373.04 | 0 | 0 | 0 | 12373.04 | 0 | 0 | 0 | 0 | 12373.04 | 11989.73 | [5 empty] | Y | DW5FS | 100% | [19 empty] | 1 | [47 empty] | 0
500858 | Craignure Mull RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS7 | 2016-03-31 | 2017-06-25 | 2017-06-30 | 2018-03-29 | 2018-12-11 | Argyll and Bute-North Argyll | 0 | 0 | 2040.25 | 1994.75 | 10024.31 | 6946.55 | -3343.87 | 0 | 17662 | 0 | 0 | 0 | 17662 | 0 | 0 | 0 | 0 | 17662 | 11393.23 | [5 empty] | N | DW5FS | 100%
500633 | Craignure TTU Provision | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2015-06-09 | 2015-07-20 | 2015-08-03 | 2015-11-02 | 2015-12-17 | Argyll and Bute-North Argyll | 0 | 0 | 1835327.61 | 13397.06 | 2462.45 | 0 | 108.15 | 208.05 | 1851503.32 | 0 | 0 | 0 | 1851503.32 | 0 | 0 | 0 | 0 | 1851503.32 | 638845.62 | [5 empty] | N | CS16WR | 100%
45029 | Craignure WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2012-11-07 | 2013-11-20 | 2015-10-27 | 2015-10-27 | Argyll and Bute-North Argyll | 7472159.47 | 0 | 151595.78 | 2195.38 | -51425.15 | 0 | 0 | 0 | 102366.01 | 0 | 0 | 0 | 7574525.48 | 0 | 0 | 0 | 0 | 7574525.48 | 28761.13 | [5 empty] | N | WG1 | 25% | DW23 | 75%
503376 | Crail Kilminning WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-06-10 | 2028-04-18 | 2028-08-21 | 2029-02-09 |  | Fife | 0 | 0 | 0 | 0 | 0 | 77571.46 | 5044.68 | -0.14 | 82616 | 0 | 0 | 0 | 82616 | 0 | 0 | 0 | 0 | 82616 | 122419.09 | [5 empty] | N | SG1 | 100%
500992 | Crail Kilminning WWTW - screen replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2015-10-07 | 2017-01-31 | 2017-03-21 | 2017-12-11 |  | Fife | 0 | 0 | 919 | 52148.14 | 184096.85 | -1058.67 | 238.39 | -338.4 | 236005.31 | 0 | 0 | 0 | 236005.31 | 0 | 0 | 0 | 0 | 236005.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501251 | Crathie WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-11-10 | 2028-01-19 | 2028-05-23 | 2029-08-17 |  | Aberdeenshire | 0 | 0 | 18868.52 | 92874.81 | 0 | 0 | -4660.92 | -60.33 | 107022.08 | 2392481.92 | 0 | 0 | 2499504 | 0 | 0 | 0 | 0 | 2499504 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
45319 | Crathie WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-08-27 | 2011-03-16 | 2005-02-21 | 2011-07-12 | 2011-03-14 | Aberdeenshire | 50042.19 | 0 | 4.37 | 0 | 0 | 0 | 0 | 0 | 4.37 | 0 | 0 | 0 | 50046.56 | 0 | 0 | 0 | 0 | 50046.56 | 28761.13 | [5 empty] | N | DW13 | 100%
400093 | Creetown Catchment UID Improvements | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-04 | 2012-03-14 | 2012-04-16 | 2015-09-11 | 2014-10-01 | Dumfries and Galloway | 3699596 | 0 | -214980 | 2874.91 | -6871.24 | 0 | 0 | 0 | -218976.33 | 0 | 0 | 0 | 3480619.67 | 0 | 0 | 0 | 0 | 3480619.67 | 238142.92 | [5 empty] | N | CM_WWI | 3% | CS11A | 7% | EC01B | 90%
503337 | Crianlarich Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2020-09-22 | 2020-09-22 | 2028-06-05 | 2021-01-20 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 7233.49 | 408.48 | -408.48 | 7233.49 | 0 | 0 | 0 | 7233.49 | 0 | 0 | 0 | 0 | 7233.49 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502977 | Crieff Road Aberfeldy | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2018-03-29 | 2018-11-08 | 2019-04-08 | 2019-08-26 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 8520.81 | 46727.19 | 78454 | 2026.04 | 135728.04 | 0 | 0 | 0 | 135728.04 | 0 | 0 | 0 | 0 | 135728.04 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509224 | Crieff WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-05-05 | 2025-02-26 | 2025-05-26 | 2026-06-29 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84114 | 84114 | 1915885.8 | 0 | 0 | 1999999.8 | 0 | 0 | 0 | 0 | 1999999.8 | 122419.09 | [5 empty] | N | SG1 | 100%
401340 | Crimond Crimongorth WSZ Low Pressure Enhancement WSZ000442 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-03-21 | 2012-08-27 | 2015-03-27 | 2014-03-31 | Aberdeenshire | 187812 | 0 | 8626.93 | 668.23 | 0 | 0 | 0 | 0 | 9295.16 | 0 | 0 | 0 | 197107.16 | 0 | 0 | 0 | 0 | 197107.16 | 0 | [5 empty] | N | CS1 | 100%
507655 | Critical Alarm Testing DWQR - Pilot | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS2 |  | 2020-07-30 | 2021-05-24 | 2021-09-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36577.82 | 36577.82 | 13422.19 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 306661.32 | [5 empty] | N | CM_WWNI | 100%
503093 | Critical Reservoir Assets (works to prevent MIOS) Years 4 - 6 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-04-01 | 2021-04-01 | 2021-05-10 | 2021-05-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water | DWQR | SWMD | Reservoirs | MS4 | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2021-03-18 | 2022-05-10 | Scottish Water Wide | 0 | 0 | 865651.6 | 2635142.06 | 1113436.65 | 790634.3 | 1438510.37 | 37418.77 | 6880793.75 | 0 | 0 | 119206.2492 | 6880793.75 | 119206.2492 | 0 | 0.0008 | 119206.25 | 7000000 | 2601944.88 | [5 empty] | N | CS22 | 100%
510463 | Critical Sewers Rehabilitation Phase 2 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-01-05 | 2023-07-07 | 2023-10-05 | 2024-10-03 | 2024-10-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16263.17 | 16263.17 | 683895.02 | 0 | 0 | 700158.19 | 0 | 0 | 0 | 0 | 700158.19 | 0 | [5 empty] | N | SR21_WW | 100%
502786 | CRM Integration | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2019-03-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 416407.83 | 718410.49 | 0 | 0 | 1134818.32 | 0 | 0 | 0 | 1134818.32 | 0 | 0 | 0 | 0 | 1134818.32 | 306661.32 | [5 empty] | N | CM_M&G | 100%
402474 | Crocketford WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-12-19 | 2014-02-24 | 2014-02-27 | 2016-04-27 | 2016-05-20 | Dumfries and Galloway | 2083096.6 | 0 | 531766.4 | 212679 | -1142.83 | 0 | 0 | 0 | 743302.57 | 0 | 0 | 0 | 2826399.17 | 0 | 0 | 0 | 0 | 2826399.17 | 90601.29 | [5 empty] | N | CM_WWNI | 8.919% | SG1 | 91.08%
508517 | Croft James DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-09-29 | 2023-11-16 | 2024-02-26 | 2025-01-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 933.33 | 933.33 | 345481.44 | 0 | 0 | 346414.77 | 0 | 0 | 0 | 0 | 346414.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503042 | Cromarty Sutors WwTW - Replacement Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-12-14 | 2024-10-16 | 2025-01-14 | 2026-03-26 |  | Highland | 0 | 0 | 0 | 0 | 31203.1 | 664.69 | 14727.79 | 134683.42 | 181279 | 2444720.64 | 0 | 0 | 2625999.64 | 0 | 0 | 0 | 0 | 2625999.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500493 | Crossapol Tiree Septic Tank | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2015-06-16 | 2015-11-16 | 2015-11-17 | 2017-02-13 | 2017-02-13 | Highland | 0 | 0 | 94.75 | 0 | 0 | 0 | 0 | 0 | 94.75 | 0 | 0 | 0 | 94.75 | 0 | 0 | 0 | 0 | 94.75 | 1104204.13 | [5 empty] | N | EC01A | 100%
45807 | Crossford Nethan Foot SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-07-28 | 2011-09-05 | 2012-06-20 | 2012-06-29 | South Lanarkshire | 865891.06 | 0 | 22.22 | 0 | 0 | 0 | 0 | 0 | 22.22 | 0 | 0 | 0 | 865913.28 | 0 | 0 | 0 | 0 | 865913.28 | 28761.13 | [5 empty] | N | WQ01C | 100%
502403 | Crossford WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-10-02 | 2022-08-25 | 2022-11-23 | 2023-11-13 |  | South Lanarkshire | 0 | 0 | 0 | 31033.94 | 34245.79 | 30578.15 | 56024.67 | 86739.46 | 238622 | 1135408.73 | 0 | 0 | 1374030.73 | 0 | 0 | 0 | 0 | 1374030.73 | 122419.09 | [5 empty] | N | SG1 | 100%
503088 | Crossgates WSZ - Forteviot Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2020-10-01 | 2020-10-01 | 2028-07-06 | 2021-01-21 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 18614.12 | 2769.88 | 6496.06 | -6601.66 | 21278.4 | 0 | 0 | 0 | 21278.4 | 0 | 0 | 0 | 0 | 21278.4 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501400 | Crosswood WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-01 | 2028-04-12 | 2028-08-16 | 2029-04-02 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249999.97 | 0 | 0 | 249999.97 | 0 | 0 | 0 | 0 | 249999.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403907 | Crowlista WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2015-03-30 | 2017-02-17 | 2017-02-17 | 2017-02-20 | 2017-02-20 | Na H-Eileanan an Iar | 365.85 | 0 | 12550.15 | 32787.12 | 486.4 | 0 | 0 | 0 | 45823.67 | 0 | 0 | 0 | 46189.52 | 0 | 0 | 0 | 0 | 46189.52 | 0 | [5 empty] | N | SG1 | 100%
507808 | Croy WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2021-03-30 | 2023-03-06 | 2023-06-05 | 2024-07-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42807 | 42807 | 1125563.38 | 0 | 0 | 1168370.38 | 0 | 0 | 0 | 0 | 1168370.38 | 122419.09 | [5 empty] | N | SG1 | 100%
502817 | Croy WwTW - Investigation and Scope Definition for Potential Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 |  | Highland | 0 | 0 | 0 | 0 | 39079.11 | 2454.6 | 17298.79 | 23277.95 | 82110.45 | 0 | 0 | 0 | 82110.45 | 0 | 0 | 0 | 0 | 82110.45 | 122419.09 | [5 empty] | N | SG1 | 100%
505029 | Croy WwTW - Replace Washwater System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-03-03 | 2021-05-10 | 2021-10-11 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 6329.49 | 41132.51 | 47462 | 47538.43 | 0 | 0 | 95000.43 | 0 | 0 | 0 | 0 | 95000.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501726 | Crumhaugh Trunk Mains System Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-07-23 | 2028-06-01 | 2028-08-29 | 2029-03-29 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965939.99 | 0 | 0 | 965939.99 | 0 | 0 | 0 | 0 | 965939.99 | 4989107.96 | [5 empty] | N | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 28.57% | CM_WSI | 47.62%
500620 | CSD Customer Service SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 40337 | 53069.86 | 50922.05 | 51657.75 | 615604.93 | 2347539.93 | 3159131.52 | 0 | 0 | 0 | 3159131.52 | 0 | 0 | 0 | 0 | 3159131.52 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500632 | CSD Health & Safety SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 345715.43 | 400937.3 | 453239.93 | 800824.86 | 1582460.2 | 2064867.18 | 5648044.89 | 0 | 0 | 0 | 5648044.89 | 0 | 0 | 0 | 0 | 5648044.89 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500472 | CSO treatment - Wetlands study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-31 | 2016-02-05 | 2016-03-28 | 2020-01-29 | 2020-03-31 | South Lanarkshire | 0 | 0 | 46326 | 40332 | 39378.09 | 43963.91 | 53000 | -2994.13 | 220005.87 | 0 | 0 | 0 | 220005.87 | 0 | 0 | 0 | 0 | 220005.87 | 196736.15 | [5 empty] | Y | EC10E | 100% | [40 empty] | 1 | [26 empty] | 0
509953 | Culburnie DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2023-03-28 | 2024-05-20 | 2024-08-20 | 2025-07-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082.19 | 1082.19 | 967818.16 | 0 | 0 | 968900.35 | 0 | 0 | 0 | 0 | 968900.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510265 | Culburnie SR Sample tap replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2022-06-23 | 2022-09-15 | 2023-04-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3333 | 3333 | 6666.66 | 0 | 0 | 9999.66 | 0 | 0 | 0 | 0 | 9999.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512103 | Culloden DOA - Westhill Tower Brae North Bonnie View - Install APNRV | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32499.99 | 0 | 0 | 32499.99 | 0 | 0 | 0 | 0 | 32499.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46265 | Cults Pitfodels TWP Refurb - TWP000440 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-12-03 | 2010-09-27 | 2011-09-26 | 2012-09-21 |  | Aberdeen City | 738943.5 | 0 | 3901.84 | -3901.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738943.5 | 0 | 0 | 0 | 0 | 738943.5 | 0 | [5 empty] | N | CM_WSNI | 100%
403069 | Culzean Drive Newarthill Motherwell Internal Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-11-21 | 2014-06-20 | 2014-07-21 | 2015-03-31 | 2015-03-31 | North Lanarkshire | 1143423 | 1143423 | 56391 | 576.37 | 0 | 0 | 0 | 0 | 56967.37 | 0 | 0 | 0 | 1200390.37 | 0 | 0 | 0 | 0 | 1200390.37 | 180449.74 | [5 empty] | N | FL_DD | 100%
501564 | Cumnock - Glenmuir Water Road Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2016-04-25 | 2018-09-28 | 2018-10-29 | 2019-05-31 |  | North Ayrshire | 0 | 0 | 0 | 12366.29 | 35867.71 | 536689.45 | 47930.28 | 200.27 | 633054 | 0 | 0 | 0 | 633054 | 0 | 0 | 0 | 0 | 633054 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400808 | Cumnock (Underwood) STC Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-05-31 | 2012-09-26 | 2012-11-13 | 2014-06-27 |  | East Ayrshire | 1054658.77 | 0 | -23446.33 | -19.68 | 0 | 0 | 0 | 0 | -23466.01 | 0 | 0 | 0 | 1031192.76 | 0 | 0 | 0 | 0 | 1031192.76 | 90601.29 |  |  |  |  | 17000 | N | CM_WWNI | 100%
402220 | Cumnock STC - Upgrade of existing caustic dosing system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-07-19 | 2013-02-25 | 2013-05-13 | 2014-06-27 |  | East Ayrshire | 511013.57 | 0 | 346.95 | 0 | 0 | 0 | 0 | 0 | 346.95 | 0 | 0 | 0 | 511360.52 | 0 | 0 | 0 | 0 | 511360.52 | 90601.29 |  |  |  |  | 16219 | N | CM_WWNI | 100%
403380 | Cumnock STC Sludge Cake Storage Area | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-15 | 2014-03-04 | 2014-08-06 | 2015-01-28 |  | East Ayrshire | 254257 | 0 | -3080.9 | 0 | 0 | 0 | 0 | 0 | -3080.9 | 0 | 0 | 0 | 251176.1 | 0 | 0 | 0 | 0 | 251176.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502599 | Cumnock STC Sludge Digestors Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-21 | 2017-02-21 | 2017-07-25 | 2017-11-28 |  | East Ayrshire | 0 | 0 | 0 | 17284.98 | 420615.02 | 86 | 914 | -685.36 | 438214.64 | 0 | 0 | 0 | 438214.64 | 0 | 0 | 0 | 0 | 438214.64 | 90601.29 | [5 empty] | N | CM_WWI | 100%
402966 | Cuninghill Avenue Inverurie | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-10-01 | 2014-09-22 | 2014-10-06 | 2015-02-27 | 2015-02-27 | Aberdeenshire | 403795 | 403795 | 11273.18 | 163.19 | 0 | 0 | 0 | 0 | 11436.37 | 0 | 0 | 0 | 415231.37 | 0 | 0 | 0 | 0 | 415231.37 | 180449.74 | [5 empty] | N | FL_DD | 100%
501816 | Cupar WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | Fife | 0 | 0 | 0 | 16572.1 | 25925.36 | 0 | 0 | 0 | 42497.46 | 0 | 0 | 0 | 42497.46 | 0 | 0 | 0 | 0 | 42497.46 | 122419.09 | [5 empty] | N | SG1 | 100%
500915 | Cushnie TWP - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-10-29 | 2027-04-26 | 2027-04-26 | 2027-04-26 |  | Aberdeenshire | 0 | 0 | 3493.49 | 55289.57 | -19213.4 | 15660.3 | 586.15 | 2464.96 | 58281.07 | -4301.98 | 0 | 0 | 53979.09 | 0 | 0 | 0 | 0 | 53979.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500645 | Customer 2015 Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-01 | 2015-12-16 | 2015-12-16 | 2019-03-04 |  | Scottish Water Wide | 0 | 0 | 732572.3 | 229609.75 | 272363.53 | 1121444.11 | 0 | 0 | 2355989.69 | 0 | 0 | 0 | 2355989.69 | 0 | 0 | 0 | 0 | 2355989.69 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500647 | Customer Connections SR15 Programme | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-06-01 |  | Scottish Water Wide | 0 | 0 | 843078.31 | 857302.45 | 187208.99 | 548113.99 | 354117.41 | 1617678.79 | 4407499.94 | -1060521.94 | 0 | 0 | 3346978 | 0 | 0 | 0 | 0 | 3346978 | 276932.45 | [5 empty] | N | WG2 | 100%
402935 | Customer Experience Improvements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-08-05 | 2013-08-05 | 2013-07-24 | 2014-06-11 |  | Scottish Water Wide | 589597.82 | 0 | 0 | 0 | 3023.37 | 0 | 0 | 0 | 3023.37 | 0 | 0 | 0 | 592621.19 | 0 | 0 | 0 | 0 | 592621.19 | 306661.32 | [5 empty] | N | CM_M&G | 100%
403482 | Customer Experience Improvements Strand 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-10-17 | 2015-06-24 | 2015-06-24 | 2015-06-15 |  | Scottish Water Wide | 392.77 | 0 | -154.77 | 0 | 0 | 0 | 0 | 0 | -154.77 | 0 | 0 | 0 | 238 | 0 | 0 | 0 | 0 | 238 | 306661.32 | [5 empty] | N | CM_M&G | 100%
401920 | Customer Requested Lead Pipe removal | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2011-07-29 | 2012-01-24 | 2012-02-06 | 2016-05-18 | 2016-06-22 | Scottish Water Wide | 2607539.13 | 0 | 339301.87 | -307532.11 | 0 | 0 | 0 | 0 | 31769.76 | 0 | 0 | 0 | 2639308.89 | 0 | 0 | 0 | 0 | 2639308.89 | 0 | [5 empty] | N | DW1C | 100%
402588 | Customer Satisfaction Focused Delivery CID WWI | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-21 | 2012-03-21 | 2012-04-04 | 2016-12-19 |  | All East Unitary Authorities | 434110 | 0 | 0 | -2641.95 | 97.55 | 0 | 0 | 0 | -2544.4 | 0 | 0 | 0 | 431565.6 | 0 | 0 | 0 | 0 | 431565.6 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503342 | CVT - FOP Field Response Vehicles | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2019-03-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 165740.98 | 0 | 0 | 165740.98 | 0 | 0 | 0 | 165740.98 | 0 | 0 | 0 | 0 | 165740.98 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502354 | CVT - FOP Scientific Vans | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-11-03 | 2016-11-03 | 2017-01-04 | 2017-03-23 |  | Scottish Water Wide | 0 | 0 | 0 | 193364 | 4500.4 | 0 | 0 | 0 | 197864.4 | 0 | 0 | 0 | 197864.4 | 0 | 0 | 0 | 0 | 197864.4 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503341 | CVT - FOP Scientific Vehicles | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2019-04-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 12170.73 | 553902.49 | 0 | 566073.22 | 0 | 0 | 0 | 566073.22 | 0 | 0 | 0 | 0 | 566073.22 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502215 | CVT - Heavy Goods Vehicle Asset Replacement 2016-17 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2017-09-27 |  | Scottish Water Wide | 0 | 0 | 0 | 3748560 | -49337 | 0 | 0 | 0 | 3699223 | 0 | 0 | 0 | 3699223 | 0 | 0 | 0 | 0 | 3699223 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502686 | CVT - Heavy Goods Vehicle Asset Replacement 2017-18 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-05-29 | 2017-05-29 | 2017-07-03 | 2018-10-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 3496926.74 | 2384801.83 | 8238.34 | 0 | 5889966.91 | 0 | 0 | 0 | 5889966.91 | 0 | 0 | 0 | 0 | 5889966.91 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503142 | CVT - Heavy Goods Vehicle Asset Replacement 2018-19 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-03-27 | 2018-03-27 | 2018-04-02 | 2019-05-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2111015.02 | -830413.78 | 0 | 1280601.24 | 0 | 0 | 0 | 1280601.24 | 0 | 0 | 0 | 0 | 1280601.24 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503633 | CVT - Heavy Goods Vehicle Asset Replacement 2019-20 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2019-08-19 | 2019-08-19 | 2019-08-19 | 2020-06-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1253572.53 | -877.51 | 1252695.02 | 0 | 0 | 0 | 1252695.02 | 0 | 0 | 0 | 0 | 1252695.02 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503762 | CVT - Heavy Goods Vehicle Asset Replacement 2020-21 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2021-08-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 20780.49 | 1231791.51 | 1252572 | 0 | 0 | 0 | 1252572 | 0 | 0 | 0 | 0 | 1252572 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502198 | CVT - Light Commercial Vehicle Asset Replacement 2016-17 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2017-09-27 |  | Scottish Water Wide | 0 | 0 | 0 | 6077169 | 187783.02 | -14965.85 | 0 | 0 | 6249986.17 | 0 | 0 | 0 | 6249986.17 | 0 | 0 | 0 | 0 | 6249986.17 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502687 | CVT - Light Commercial Vehicle Asset Replacement 2017-18 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-05-29 | 2017-05-29 | 2017-07-03 | 2018-11-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 6126142.57 | 2963663.34 | -565137.46 | 0 | 8524668.45 | 0 | 0 | 0 | 8524668.45 | 0 | 0 | 0 | 0 | 8524668.45 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503143 | CVT - Light Commercial Vehicle Asset Replacement 2018-19 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-03-27 | 2018-03-27 | 2018-04-02 | 2019-05-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 5344998 | 78218.07 | 0 | 5423216.07 | 0 | 0 | 0 | 5423216.07 | 0 | 0 | 0 | 0 | 5423216.07 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503568 | CVT - Light Commercial Vehicle Asset Replacement 2019-20 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2020-10-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3769011.8 | -1084.82 | 3767926.98 | 0 | 0 | 0 | 3767926.98 | 0 | 0 | 0 | 0 | 3767926.98 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503763 | CVT - Light Commercial Vehicle Asset Replacement 2020-21 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2021-08-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 70851.59 | 4017747.41 | 4088599 | 0 | 0 | 0 | 4088599 | 0 | 0 | 0 | 0 | 4088599 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502214 | CVT - Plant Equipment Asset Replacement 2016-17 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2017-09-27 |  | Scottish Water Wide | 0 | 0 | 0 | 318679 | -24827.13 | 1484.13 | -1224 | 1224 | 295336 | 0 | 0 | 0 | 295336 | 0 | 0 | 0 | 0 | 295336 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502688 | CVT - Plant Equipment Asset Replacement 2017-18 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-05-22 | 2017-05-22 | 2017-06-01 | 2018-06-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 399843.99 | 48147.78 | 0 | 0 | 447991.77 | 0 | 0 | 0 | 447991.77 | 0 | 0 | 0 | 0 | 447991.77 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503144 | CVT - Plant Equipment Asset Replacement 2018-19 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-03-26 | 2018-03-26 | 2018-04-02 | 2019-04-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1014947.06 | -202561.38 | 0 | 812385.68 | 0 | 0 | 0 | 812385.68 | 0 | 0 | 0 | 0 | 812385.68 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503569 | CVT - Plant Equipment Asset Replacement 2019-20 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2020-06-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 762133.33 | 3991.8 | 766125.13 | 0 | 0 | 0 | 766125.13 | 0 | 0 | 0 | 0 | 766125.13 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503764 | CVT - Plant Equipment Asset Replacement 2020-21 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2021-08-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7707.32 | 439475.68 | 447183 | 0 | 0 | 0 | 447183 | 0 | 0 | 0 | 0 | 447183 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502287 | CVT - Wastewater Tankers | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2017-01-19 |  | Scottish Water Wide | 0 | 0 | 0 | 819534 | 0 | 0 | 0 | 0 | 819534 | 0 | 0 | 0 | 819534 | 0 | 0 | 0 | 0 | 819534 | 306661.32 | [5 empty] | N | CM_M&G | 100%
502753 | CVT -Telematics Project 2017-18 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-05-22 | 2017-05-22 | 2017-06-01 | 2018-12-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 276867.74 | 47802.5 | 0 | 0 | 324670.24 | 0 | 0 | 0 | 324670.24 | 0 | 0 | 0 | 0 | 324670.24 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503101 | CWA Incentivisation Actual | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWD | Exceptional Capital Maintenance | MS2 | 2018-07-09 | 2018-07-09 | 2020-03-24 | 2021-05-01 | 2022-11-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2310165.4 | 2511179.05 | 357621.4 | 5178965.85 | 4350357.95 | 2754754.4999 | 3842221.8798 | 9529323.8 | 1087467.3799 | 0 | 0 | 1087467.3799 | 10616791.1799 | 1065664.89 | [5 empty] | N | SR15_CMA_WWNI | 0.04535% | SR15_CMP_LATE | 0.07787% | FL_NAMED | 0.2123% | SR15_CMA_MAG | 0.2864% | SR15_UID_UWWD | 0.3154% | WG3 | 0.5829% | SR21_SS | 0.6031% | SR15_CMA_WWI | 0.9055% | SR15_SED_INFC | 1.17% | FL_DD | 1.526%
511541 | CWA Integrated Wedge Holding Line Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU |  | 2021-05-01 |  | 2027-03-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72 | 0 | 0 | 0.72 | 0 | 0 | 0 | 0 | 0.72 | 306661.32 | [5 empty] | N | CM_M&G | 100%
511540 | CWA Transformation Factory Conveyor Holding Line Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU |  | 2021-05-01 |  | 2027-03-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440080.5 | 440080.5 | -440079.5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 306661.32 | [5 empty] | N | CM_M&G | 100%
402350 | CWG External Flooding Lethamhill Road Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2012-03-27 | 2012-10-29 | 2013-11-08 | 2013-11-08 | Glasgow City | 985456 | 0 | -7545.57 | 0 | 0 | 0 | 0 | 0 | -7545.57 | 0 | 0 | 0 | 977910.43 | 0 | 0 | 0 | 0 | 977910.43 | 0 | [5 empty] | N | CS15 | 100%
402349 | CWG Internal and External Flooding at Fullarton Avenue Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2012-03-27 | 2013-03-28 | 2014-01-22 | 2014-01-22 | Glasgow City | 1146942 | 0 | 0 | 0 | 0 | -4653.36 | 0 | 0 | -4653.36 | 0 | 0 | 0 | 1142288.64 | 0 | 0 | 0 | 0 | 1142288.64 | 0 | [5 empty] | N | CS11A | 50% | CS15 | 50%
508132 | C-W-NI-100820 Fort William Stores Roof Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS2 |  | 2020-08-27 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77948.79 | 77948.79 | 119706.51 | 0 | 0 | 197655.3 | 0 | 0 | 0 | 0 | 197655.3 | 306661.32 | [5 empty] | N | CM_M&G | 100%
510247 | C-W-NI-101220-TWS Pre-Post Samples-Multi Site | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-11 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904.1 | 1904.1 | 12780.12 | 0 | 0 | 14684.22 | 0 | 0 | 0 | 0 | 14684.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509238 | C-W-NI-131020 - Priority HV Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-13 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16674.76 | 16674.76 | 61135.24 | 0 | 0 | 77810 | 0 | 0 | 0 | 0 | 77810 | 119022.58 | [5 empty] | N | CM_WWNI | 100%
507244 | C-W-NI-170620 Parkside DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-22 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 4151.4 | 0 | 0 | 4400 | 0 | 0 | 0 | 0 | 4400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508995 | C-W-NI-290920 Balgeddie DSR PRV | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.31 | 981.31 | 15633.69 | 0 | 0 | 16615 | 0 | 0 | 0 | 0 | 16615 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509006 | C-W-NI-Bench Instrumentation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-29 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158087.18 | 158087.18 | 4277.97 | 0 | 0 | 162365.15 | 0 | 0 | 0 | 0 | 162365.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510284 | C-W-NI-Crieff Knock DSR PRV Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654.21 | 654.21 | 10245.81 | 0 | 0 | 10900.02 | 0 | 0 | 0 | 0 | 10900.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511486 | C-WW-NI - Scotland-wide - Management of Wastewater Temporary Process Units investigatory work | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-24 | 2021-08-13 | 2022-03-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125666.72 | 0 | 0 | 125666.72 | 0 | 0 | 0 | 0 | 125666.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511608 | C-WW-NI - Scotland-wide - Wastewater Temporary Process Units MA021 Investigatory Work | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS1 | 2021-03-22 | 2021-12-06 | 2022-04-06 | 2022-10-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000.04 | 0 | 0 | 100000.04 | 0 | 0 | 0 | 0 | 100000.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511616 | C-WW-NI-SR21 MCC Replacement - Stevenston Point STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2799999.97 | 0 | 0 | 2799999.97 | 0 | 0 | 0 | 0 | 2799999.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510964 | Cyber and Security Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2028-04-28 | 2029-03-30 | 2029-08-01 | 2031-03-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260727.91 | 0 | 0 | 260727.91 | 0 | 0 | 0 | 0 | 260727.91 | 613322.63 | [5 empty] | N | CM_M&G | 100%
509226 | D&G Radio Links Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-23 | 2022-04-04 | 2022-11-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26077 | 26077 | 923.12 | 0 | 0 | 27000.12 | 0 | 0 | 0 | 0 | 27000.12 | 119022.58 | [5 empty] | N | WSNI | 100%
34562 | D/S - Non Domestic Water - Edinburgh City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG2 | 100%
34574 | D/S - Non Domestic Water - South Ayrshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | South Ayrshire | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0 | 0 | 0 | 0 | 6.96 | 0 | [6 empty] | WG2 | 100%
506201 | Daaf Reservoir Spillway Repair | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-04-15 |  | 2021-06-06 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685.28 | 685.28 | 43323.06 | 0 | 0 | 44008.34 | 0 | 0 | 0 | 0 | 44008.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503238 | Daer Clarifier Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-07-21 | 2022-07-01 | 2022-10-21 | 2023-10-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 62472.15 | 34530.59 | 80636.06 | 177638.79 | 1824671.14 | 0 | 0 | 2002309.93 | 0 | 0 | 0 | 0 | 2002309.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500807 | Daer Coulter RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2015-09-30 | 2017-03-23 | 2017-03-28 | 2018-03-31 | 2018-06-30 | South Lanarkshire | 0 | 0 | 20200 | 28708.15 | 112380.59 | 49259.1 | 0 | -2723.21 | 207824.63 | 0 | 0 | 0 | 207824.63 | 0 | 0 | 0 | 0 | 207824.63 | 220398.43 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 36.7 | [43 empty] | 0
501179 | DAER CWT NS975097 | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS1 | 2015-10-30 | 2027-06-23 | 2027-06-24 | 2027-11-10 | 2028-02-10 | South Lanarkshire | 0 | 0 | 19618 | 139667.88 | 67484 | -71469.17 | 0 | -6102.83 | 149197.88 | 2354.41 | 0 | 0 | 151552.29 | 0 | 649.4063 | 0 | 649.4063 | 152201.6963 | 645915.7 | [5 empty] | N | DW25T | 100%
403741 | Daer IoS Drainage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-03-19 | 2014-11-17 | 2015-02-03 | 2016-05-10 |  | Scottish Water Wide | 88085 | 0 | 180591 | -36656 | -460.02 | 0 | 0 | 0 | 143474.98 | 0 | 0 | 0 | 231559.98 | 0 | 0 | 0 | 0 | 231559.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501276 | Daer Windfarm | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | GW2 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | South Lanarkshire | 0 | 0 | 0 | 500.62 | 5050.75 | 284.22 | 39134.17 | 72615.22 | 117584.98 | -117583.98 | -117583.98 | -163226.5824 | 1 | -45642.6024 | 0 | 0 | -45642.6024 | -45641.6024 | 0 | [5 empty] | N | I2S_WI | 100%
501670 | DAER WOA - Stablewood Pipe Bridge - H&S upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2017-10-27 | 2021-09-27 | 2021-11-15 | 2022-10-24 |  | South Lanarkshire | 0 | 0 | 0 | 7135.19 | 21492.19 | 93983.11 | 35918.9 | 56139.61 | 214669 | 756433.74 | 0 | 0 | 971102.74 | 0 | 0 | 0 | 0 | 971102.74 | 430259.37 | [5 empty] | N | CM_M&G | 50% | CM_WSI | 50%
501239 | Daer WOA Camps WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2016-06-29 | 2018-08-31 | 2018-05-29 | 2021-01-05 |  | South Lanarkshire | 0 | 0 | 322649 | -230766 | 261499.24 | 2563825.06 | 739367.1 | 7650.22 | 3664224.62 | -26711.96 | 0 | 0 | 3637512.66 | 0 | 0 | 0 | 0 | 3637512.66 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501124 | Daer WOA Crawford WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501121 | Daer WOA Daer WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-04-11 | 2018-02-05 | 2018-02-06 | 2018-11-29 |  | South Lanarkshire | 0 | 0 | 55800 | 1291 | 496512 | 1365663.23 | 145065.38 | -45253.97 | 2019077.64 | 0 | 0 | 0 | 2019077.64 | 0 | 0 | 0 | 0 | 2019077.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501240 | Daer WOA Douglas Moor WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501238 | Daer WOA East Rogerton WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501123 | Daer WOA Hirst WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501122 | Daer WOA Muirkirk WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501241 | Daer WOA Udston WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
502772 | Daer WRZ SR Residual Chorine Monitors | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS4 | 2018-02-26 | 2019-03-07 | 2019-07-29 | 2021-03-31 | 2021-06-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 28483.23 | 54576.58 | 70957.49 | 244245.52 | 398262.82 | 36812.34 | 61737.18 | 61737.18 | 435075.16 | 0 | 24924.84 | 5.8208e-11 | 24924.84 | 460000 | 442547.58 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
501219 | Daer WTW - Improving WQ in Network (OMG5) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWMD | DWQ Compliance | MS3 | 2016-03-30 | 2018-10-31 | 2018-12-10 | 2021-07-01 | 2021-07-02 | South Lanarkshire | 0 | 0 | 24826.32 | 78122.11 | 61176.98 | 206443.93 | 490110.18 | 358648.48 | 1219328 | 117208.09 | 117208.09 | 296416.3108 | 1336536.09 | 179208.2208 | 0 | 0 | 179208.2208 | 1515744.3108 | 0 | [5 empty] | Y | DW25D | 100% | [22 empty] | 1 | [44 empty] | 0
503374 | Dairsie WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-02-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 78298.42 | 65318.01 | -63770.19 | 79846.25 | 0 | 0 | 0 | 79846.25 | 0 | 0 | 0 | 0 | 79846.25 | 122419.09 | [5 empty] | N | SG1 | 100%
501107 | Dalbeattie Catchment Study (DAS) | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-12-19 | 2016-12-19 | 2017-01-24 | 2017-01-24 | Dumfries and Galloway | 0 | 0 | 600 | 14811.19 | -434 | 0 | 0 | 0 | 14977.19 | 0 | 0 | 0 | 14977.19 | 0 | 0 | 0 | 0 | 14977.19 | 9525.18 | [5 empty] | N | EC01D | 100%
46326 | Dalbeattie STW - STW000217 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-09 | 2012-01-17 | 2012-01-25 | 2016-03-10 |  | Dumfries and Galloway | 7453224.62 | 0 | 236247.16 | -34829.52 | -22895.13 | 0 | 0 | 0 | 178522.51 | 0 | 0 | 0 | 7631747.13 | 0 | 0 | 0 | 0 | 7631747.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46851 | Dalchreichart WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-06-05 | 2012-08-13 | 2013-06-14 | 2016-04-01 | Highland | 1475368.72 | 0 | -22610.64 | 0 | 0 | 0 | 0 | 0 | -22610.64 | 0 | 0 | 0 | 1452758.08 | 0 | 0 | 0 | 0 | 1452758.08 | 28761.13 | [5 empty] | N | DW23 | 100%
504329 | Dalderse WWTW - FST 2 Scraper Bridge refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2019-12-13 |  | 2020-07-09 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 6325.24 | 262855.76 | 269181 | 22169.42 | 0 | 0 | 291350.42 | 0 | 0 | 0 | 0 | 291350.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503306 | Dalderse WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-06-01 | 2025-03-25 | 2025-06-24 | 2026-07-28 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 28174.04 | 6730.84 | 45956.44 | 80861.32 | 1919138.68 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 122419.09 | [5 empty] | N | SG1 | 100%
501579 | DALDERSE WWTW 1966 NS903822 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-09-05 | 2019-09-23 | 2019-11-25 | 2022-07-20 |  | Falkirk | 0 | 0 | 0 | 134375.2 | 345738.22 | 195180.5 | 2259205.32 | 1723337.76 | 4657837 | 3595021.17 | 0 | 0 | 8252858.17 | 0 | 0 | 1247141.83 | 1247141.83 | 9500000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502654 | DALDOWIE - Cluster 1 - AIRDRIE 130M S-O SPORTS CENTRE CSO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS2 | 2019-12-17 | 2021-02-18 | 2021-10-21 | 2021-12-01 | 2021-12-02 | North Lanarkshire | 0 | 0 | 0 | 0 | 202623.77 | 133376.23 | 21784.21 | 29715.84 | 387500.05 | 3275.95 | 0 | 0 | 390776 | 0 | 903.5917 | 0 | 903.5917 | 391679.5917 | 177138.89 | [5 empty] | N | EC01F_ID | 100%
502661 | DALDOWIE - Cluster 10 - 7 Bell St-east O Hattonrig Rd | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS7 | 2020-01-30 | 2020-01-30 | 2020-01-30 | 2020-01-30 | 2020-06-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 79632.03 | 80367.97 | -40076.76 | 0 | 119923.24 | 0 | 0 | 0 | 119923.24 | 0 | 0 | 0 | 0 | 119923.24 | 177138.89 | [5 empty] | N | EC10B_ID | 100%
502663 | DALDOWIE - Cluster 11 - Spindlehowe Rd-New Edinburgh Uddingston | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | WWINF | Environmental Studies | MS0 | 2019-12-17 | 2027-06-21 | 2027-08-30 | 2028-07-25 | 2028-10-25 | North Lanarkshire | 0 | 0 | 0 | 0 | 132239.88 | 72760.12 | 113989 | 180470 | 499459 | 0 | 0 | 0 | 499459 | 0 | 0 | 0 | 0 | 499459 | 354277.77 | [5 empty] | N | EC01F_ID | 48.39% | EC10B_ID | 51.61%
502662 | DALDOWIE - Cluster 12 - Uddingston E-O Pond-n-o Glasgow Zoo CSO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS2 | 2019-12-17 | 2021-02-18 | 2021-07-15 | 2021-09-08 | 2021-09-09 | North Lanarkshire | 0 | 0 | 0 | 0 | 105016.39 | 76983.61 | 3000 | 751.2 | 185751.2 | 150248.8 | 0 | 0 | 336000 | 0 | 41442.502 | 0 | 41442.502 | 377442.502 | 177138.89 | [5 empty] | N | EC01F_ID | 100%
502363 | DALDOWIE - Cluster 13 - 3 HERMISTON PL DUAL MANHOLE | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS7 | 2028-04-03 | 2028-04-03 | 2019-09-23 | 2019-09-23 | 2019-09-23 | North Lanarkshire | 0 | 0 | 0 | 59085.93 | 35914.07 | 350.56 | 2442.64 | 0 | 97793.2 | 0 | 0 | 0 | 97793.2 | 0 | 0 | 0 | 0 | 97793.2 | 177138.89 | [5 empty] | N | EC01F_ID | 100%
502664 | DALDOWIE - Cluster 14 - Hattonrigg Rd - Cronin Place Dual Manhole | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | WWINF | Environmental Studies | MS0 | 2019-07-31 | 2027-03-29 | 2027-06-07 | 2028-02-28 | 2028-05-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 102613.92 | 52887.08 | 92371 | 158647 | 406519 | 0 | 0 | 0 | 406519 | 0 | 0 | 0 | 0 | 406519 | 354277.77 | [5 empty] | N | EC01F_ID | 48.78% | EC10B_ID | 51.22%
502665 | DALDOWIE - Cluster 15 - Coatbridge Sykeside Sps CSO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-08-02 | 2021-02-18 | 2021-07-15 | 2021-04-07 | 2021-12-09 | North Lanarkshire | 0 | 0 | 0 | 0 | 52101.75 | 28898.25 | 24000 | -4865.97 | 100134.03 | 0 | 0 | 0 | 100134.03 | 0 | 0 | 0 | 0 | 100134.03 | 354277.77 | [5 empty] | N | EC01F_ID | 28.57% | EC01B_ID | 71.43%
502666 | DALDOWIE - Cluster 16 - Coatbridge Shawhead Sps CSO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-07-31 | 2021-02-18 | 2027-09-23 | 2021-04-07 | 2028-05-11 | North Lanarkshire | 0 | 0 | 0 | 0 | 51897.82 | 35053.18 | 71469 | 27319.24 | 185739.24 | 23458.76 | 0 | 0 | 209198 | 0 | 6470.5323 | 0 | 6470.5323 | 215668.5323 | 354277.77 | [5 empty] | N | EC01F_ID | 47.44% | EC01B_ID | 52.56%
502667 | DALDOWIE - Cluster 17 - Coatbridge Hagmill Road Sps CSO -EO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-08-09 | 2021-02-18 | 2021-09-09 | 2021-04-07 | 2021-11-29 | North Lanarkshire | 0 | 0 | 0 | 0 | 58533.13 | 23466.87 | 13336.58 | 844.2 | 96180.78 | 0 | 0 | 0 | 96180.78 | 0 | 0 | 0 | 0 | 96180.78 | 354277.77 | [5 empty] | N | EC01F_ID | 24.73% | EC01B_ID | 75.27%
502668 | DALDOWIE - Cluster 18 - Airdrie Park 40m Sw 97 Alexander St | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-08-02 | 2021-02-18 | 2021-10-21 | 2021-04-07 | 2022-01-27 | North Lanarkshire | 0 | 0 | 0 | 0 | 136000 | 83000 | 11000 | -1972.79 | 228027.21 | 0 | 0 | 0 | 228027.21 | 0 | 0 | 0 | 0 | 228027.21 | 177138.89 | [5 empty] | N | EC01F_ID | 100%
502655 | DALDOWIE - Cluster 2 - Chapelhall Burniebrae Storm Tk CSO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-07-31 | 2021-02-18 | 2021-09-23 | 2021-04-07 | 2021-12-13 | North Lanarkshire | 0 | 0 | 0 | 0 | 87081 | 96919 | 21000 | -1721.6 | 203278.4 | 148721.6 | 0 | 0 | 352000 | 0 | 41021.2607 | 0 | 41021.2607 | 393021.2607 | 354277.77 | [5 empty] | N | EC01F_ID | 3.125% | EC10B_ID | 96.88%
502656 | DALDOWIE - Cluster 3 - Airdrie Nw Of Monkland Bridge CSO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS2 | 2019-07-30 | 2021-03-02 | 2028-05-11 | 2029-10-09 | 2030-01-09 | North Lanarkshire | 0 | 0 | 0 | 0 | 93000 | 41000 | 15103.4 | 4076.3 | 153179.7 | 34003.32 | 0 | 0 | 187183.02 | 0 | 9378.9944 | 0 | 9378.9944 | 196562.0144 | 354277.77 | [5 empty] | N | EC01F_ID | 25.68% | EC10B_ID | 74.32%
502364 | DALDOWIE - Cluster 4 - CALDERBANK FORGE ROW WWPS 2003 NS772630 Calderbank 56 Woodhall Ave CSO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-08-19 | 2021-02-18 | 2021-09-14 | 2021-04-07 | 2021-12-07 | North Lanarkshire | 0 | 0 | 0 | 50737.41 | 27262.59 | 67000 | 18000 | -4298.85 | 158701.15 | 150298.84 | 0 | 0 | 308999.99 | 0 | 41456.3043 | 0 | 41456.3043 | 350456.2943 | 177138.89 | [5 empty] | N | EC01B_ID | 100%
502657 | DALDOWIE - Cluster 5 - Tannochside 110m SE Rosebank CSO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2020-04-28 | 2028-01-05 | 2028-03-28 | 2029-12-07 | 2030-03-11 | North Lanarkshire | 0 | 0 | 0 | 0 | 237098.77 | 149065.24 | 24342.51 | -3839.29 | 406667.22 | 150401.83 | 0 | 0 | 557069.05 | 0 | 41484.7116 | 0 | 41484.7116 | 598553.7616 | 354277.77 | [5 empty] | N | EC01F_ID | 38.57% | EC10B_ID | 61.43%
502658 | DALDOWIE - Cluster 6 - Uddingston Daldowie Crematorium No1 CSO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2021-06-28 | 2028-01-05 | 2028-03-28 | 2029-12-07 | 2030-03-11 | North Lanarkshire | 0 | 0 | 0 | 0 | 75726.18 | 43273.83 | 20384.97 | 17115.03 | 156500 | 198500.01 | 0 | 0 | 355000.01 | 0 | 54751.4326 | 0 | 54751.4326 | 409751.4426 | 354277.77 | [5 empty] | N | EC01F_ID | 6.25% | EC10B_ID | 93.75%
502659 | DALDOWIE - Cluster 8 - Uddingston 4 Lady Jane Gate CSO | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-10-03 | 2021-02-18 | 2021-07-01 | 2021-04-07 | 2021-09-23 | North Lanarkshire | 0 | 0 | 0 | 0 | 85996.95 | 87003.05 | -8444.7 | -1378.48 | 163176.82 | 150823.22 | 0 | 0 | 314000.04 | 0 | 41600.9418 | 0 | 41600.9418 | 355600.9818 | 177138.89 | [5 empty] | N | EC01F_ID | 100%
502660 | DALDOWIE - Cluster 9 - Bellshill 11 Holytown Rd-leander Cres | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | WWINF | Environmental Studies | MS0 | 2019-10-03 | 2027-06-21 | 2027-08-30 | 2028-07-18 | 2028-10-18 | South Lanarkshire | 0 | 0 | 0 | 0 | 192169.01 | 141830.99 | 53347 | 107987 | 495334 | 4666 | 0 | 0 | 500000 | 0 | 1287.0034 | 0 | 1287.0034 | 501287.0034 | 354277.77 | [5 empty] | N | EC01F_ID | 10.98% | EC10B_ID | 89.02%
506059 | Daldowie and Upper Clyde Aesthetic Surveys | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2020-05-13 | 2020-08-28 | 2020-09-25 | 2021-10-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63715 | 63715 | 116285.1 | 0 | 0 | 180000.1 | 0 | 0 | 0 | 0 | 180000.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500816 | Daldowie Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-27 | 2016-06-03 | 2016-06-06 | 2018-06-20 | 2018-06-20 | Glasgow City | 0 | 0 | 127000 | 82027.42 | -123027.42 | 4179.42 | 0 | 0 | 90179.42 | 0 | 0 | 0 | 90179.42 | 0 | 0 | 0 | 0 | 90179.42 | 106252.93 | [5 empty] | N | FL_DD | 100%
500495 | Daldowie WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-09-17 | 2018-08-30 | 2018-08-30 | 2018-08-30 |  | South Lanarkshire | 0 | 0 | 3426.08 | 42006.07 | 31030.87 | -76212.7 | 86.12 | 0 | 336.44 | 0 | 0 | 0 | 336.44 | 0 | 0 | 0 | 0 | 336.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501829 | Daldowie WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2020-01-16 | 2020-12-08 | 2021-03-01 | 2021-10-06 |  | South Lanarkshire | 0 | 0 | 0 | 6398.15 | 0 | 0 | 15314.85 | 656175.71 | 677888.71 | 383298.84 | 0 | 0 | 1061187.55 | 0 | 0 | 37915.45 | 37915.45 | 1099103 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402926 | Dalgety bay Sewer -Release Ph 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-13 | 2013-02-08 | 2013-04-12 | 2016-12-14 |  | Fife | 831253 | 0 | 19333 | -34509.55 | 385.13 | 0 | 0 | 0 | -14791.43 | 0 | 0 | 0 | 816461.58 | 0 | 0 | 0 | 0 | 816461.58 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400070 | Dalgety Bay SPS Refurb SPS002983 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-06 | 2011-10-17 | 2012-02-13 | 2012-10-03 |  | Fife | 452125.42 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 475 | 0 | 0 | 0 | 452600.42 | 0 | 0 | 0 | 0 | 452600.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46330 | Dalgrain Grangemouth SPS - SPS001527 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-29 | 2011-08-29 | 2011-08-26 | 2013-09-23 |  | Falkirk | 1217196.16 | 0 | -406.44 | 0 | 0 | 0 | 0 | 0 | -406.44 | 0 | 0 | 0 | 1216789.72 | 0 | 0 | 0 | 0 | 1216789.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400514 | Dalkeith Jarnac Court - Internal Flooding | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-03-31 | 2012-03-20 | 2012-04-30 | 2013-03-25 | 2013-03-25 | Midlothian | 96979 | 0 | -126.02 | 0 | 0 | 0 | 0 | 0 | -126.02 | 0 | 0 | 0 | 96852.98 | 0 | 0 | 0 | 0 | 96852.98 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
503982 | Dall Terrace Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2019-11-26 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2854.93 | 44361.82 | 47216.75 | 0 | 0 | 0 | 47216.75 | 0 | 0 | 0 | 0 | 47216.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501402 | DALMACOULTER DSR NS767679 | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS4 | 2018-03-30 | 2019-03-12 | 2019-03-29 | 2021-03-31 | 2021-09-07 | North Lanarkshire | 0 | 0 | 0 | 0 | 7684.05 | 288020.67 | 1392156.53 | 1059443.75 | 2747305 | 59961 | 510598 | 510598 | 2807266 | 0 | 450637 | 0 | 450637 | 3257903 | 1882113.51 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
503412 | Dalmacoulter WSZ Trunk Main Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS3 | 2020-03-31 | 2020-10-29 | 2021-03-23 | 2021-09-30 | 2022-09-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 97009.29 | 263239.21 | 444998.76 | 805247.26 | 732363.74 | 732363.74 | 907621.5882 | 1537611 | 175257.8482 | 0 | -0.001 | 175257.8472 | 1712868.8472 | 539345.26 | [5 empty] | Y | DW5 | 100% | [23 empty] | 83.9 | [43 empty] | 0
45321 | Dalmally (New) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2012-10-24 | 2012-12-11 | Argyll and Bute-North Argyll | 185708.62 | 0 | 170.38 | 0 | 0 | 0 | 0 | 0 | 170.38 | 0 | 0 | 0 | 185879 | 0 | 0 | 0 | 0 | 185879 | 28761.13 | [5 empty] | N | DW13 | 100%
502322 | Dalmally WOA - Stronmilchan Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-09-13 | 2017-04-24 | 2017-05-02 | 2017-05-08 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 15221.97 | 1453.01 | 0 | 0 | 0 | 16674.98 | 0 | 0 | 0 | 16674.98 | 0 | 0 | 0 | 0 | 16674.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510925 | Dalmally WTW - PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-11-03 | 2023-05-12 | 2023-08-10 | 2024-07-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000.04 | 0 | 0 | 500000.04 | 0 | 0 | 0 | 0 | 500000.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500817 | Dalmarnock Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-24 | 2015-12-08 | 2015-12-09 | 2017-09-11 | 2017-09-11 | Glasgow City | 0 | 0 | 23668.9 | 30784.26 | 1367.05 | 118.75 | 0 | 0 | 55938.96 | 0 | 0 | 0 | 55938.96 | 0 | 0 | 0 | 0 | 55938.96 | 106252.93 | [5 empty] | N | FL_DD | 100%
504916 | Dalmarnock Sludge WWPS - Relocation of Hydraulic Power Packs H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | MPT | Wastewater non infrastructure | MS0 | 2020-02-28 | 2021-12-20 | 2022-02-08 | 2022-11-29 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 344.48 | 30892.52 | 31237 | 918763.01 | 0 | 0 | 950000.01 | 0 | 0 | 0 | 0 | 950000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
30186 | Dalmarnock STW Refurb - STW000222 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-15 | 2011-09-23 | 2011-09-23 | 2012-03-20 |  | Glasgow City | 731914.11 | 0 | 63.12 | 0 | 0 | 0 | 0 | 0 | 63.12 | 0 | 0 | 0 | 731977.23 | 0 | 0 | 0 | 0 | 731977.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510951 | Dalmarnock WWTW - Brick Perimeter Wall Safety | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-02-05 | 2021-07-15 | 2022-02-25 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2715.7 | 2715.7 | 22500 | 0 | 0 | 25215.7 | 0 | 0 | 0 | 0 | 25215.7 | 209381.79 | [5 empty] | N | CM_M&G | 100%
503269 | Dalmarnock WWTW Improvements | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | MPT | UWWTD - Works | MS3 | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2022-04-30 | 2022-07-13 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 9452152 | 3104190.6 | 7822841.38 | 20379183.98 | 12718263.02 | 12718263.0244 | 15329232.9627 | 33097447 | 2610969.9383 | 0 | -3.7253e-09 | 2610969.9383 | 35708416.9383 | 15547843.63 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
503701 | Dalmarnock WwTW STW000222 - Asset Cleaning Project & Control of Odours | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | MPT | Wastewater infrastructure | MS3 | 2019-10-03 | 2019-11-29 | 2020-01-07 | 2021-05-14 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 611075.58 | 710924.42 | 1322000 | 3000 | 0 | 0 | 1325000 | 0 | 0 | 0 | 0 | 1325000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502826 | Dalmeny WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-01 | 2018-08-01 | 2018-07-31 | 2018-07-31 | 2018-07-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 74702.5 | -48454.2 | 0 | 0 | 26248.3 | 0 | 0 | 0 | 26248.3 | 0 | 0 | 0 | 0 | 26248.3 | 122419.09 | [5 empty] | N | SG1 | 100%
402643 | Dalmoak SPS pumps and screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-07-13 | 2013-01-07 | 2013-03-15 | 2017-12-14 |  | West Dunbartonshire | 510258 | 0 | 85000 | 70001 | 310707.78 | 1033.23 | -319.66 | 0 | 466422.34 | 0 | 0 | 0 | 976680.34 | 0 | 0 | 0 | 0 | 976680.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500804 | Dalmuir Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater | SW | SWD | Flooding Demand Driven | MS7 | 2015-08-27 | 2019-03-29 | 2019-04-15 | 2019-04-15 | 2019-04-15 | Glasgow City | 0 | 0 | 75100 | 155575.08 | 97355.2 | 74943.1 | 7627.01 | 0 | 410600.39 | 0 | 0 | 0 | 410600.39 | 0 | 0 | 0 | 0 | 410600.39 | 106252.93 | [5 empty] | N | FL_DD | 100%
402620 | Dalmuir PFI | Q&S3B | Completion | PFI |  |  | Wastewater |  | SWD | PFI | MS3 | 2012-03-27 | 2013-10-23 | 2013-11-25 | 2021-06-18 |  | West Dunbartonshire | 17774429.59 | 0 | 3562731.52 | 1045417.97 | 1711010.83 | 65363.63 | 889403.4 | 129457.37 | 7403384.72 | 0 | 0 | 0 | 25177814.31 | 0 | 0 | 0 | 0 | 25177814.31 | 4181829.69 | [5 empty] | N | PFI | 100%
402841 | Dalmuir Sludge Pumping Station - Health and Safety Project | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-08-24 | 2013-08-09 | 2013-10-08 | 2015-02-24 |  | West Dunbartonshire | 390289.36 | 0 | 1339.4 | -619.9 | 100.88 | 0 | 0 | 0 | 820.38 | 0 | 0 | 0 | 391109.74 | 0 | 0 | 0 | 0 | 391109.74 | 209381.79 | [5 empty] | N | CM_M&G | 100%
503473 | Dalmuir to Erskine Sludge Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2019-02-13 | 2019-02-13 | 2019-03-06 | 2020-04-23 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 934807.88 | 2426399.59 | 380864.51 | 3742071.98 | -1262.96 | 0 | 0 | 3740809.02 | 0 | 0 | 0 | 0 | 3740809.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503530 | Dalmuir to Erskine WWTW Sludge Main Replacement - Historic Reactive Costs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2019-05-21 | 2019-05-21 | 2020-07-29 | 2020-03-17 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 52710 | -19999.72 | 32710.28 | 0 | 0 | 0 | 32710.28 | 0 | 0 | 0 | 0 | 32710.28 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503531 | Dalmuir to Erskine WWTW Sludge Main Replacement - Reactive Costs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2019-05-21 | 2019-05-21 | 2020-03-17 | 2020-03-17 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 150848.01 | -20000 | 130848.01 | 0 | 0 | 0 | 130848.01 | 0 | 0 | 0 | 0 | 130848.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503229 | Dalmuir Wastewater Strategy Review | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater | SEPA | SWMD | Wastewater infrastructure | MS3 | 2018-02-28 | 2019-03-25 | 2019-03-25 | 2021-12-10 | 2022-04-11 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 105966.42 | 283780.61 | 326819.89 | 716566.92 | 189811 | 0 | 0 | 906377.92 | 0 | 0 | 43622.08 | 43622.08 | 950000 | 209381.79 | [5 empty] | Y | CM_WWI | 100% | [40 empty] | 1 | [26 empty] | 0
505938 | Dalmuir WWTW Ammonia Modelling | Q&S3B | Completion | PFI |  |  | Wastewater |  | SWMD | PFI | MS7 | 2020-04-29 | 2020-07-07 | 2020-08-17 | 2021-01-05 | 2020-12-15 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60547.01 | 60547.01 | -24428.46 | -24428.458 | -33910.8585 | 36118.55 | -9482.4005 | 0 | 0 | -9482.4005 | 26636.1495 | 0 | [5 empty] | N | SR15_CMP_PFI | 100%
501776 | Dalmuir WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2020-01-16 | 2021-03-22 | 2021-04-19 | 2021-11-25 |  | West Dunbartonshire | 0 | 0 | 0 | 12538.58 | 17.8 | 0 | 75143.62 | 77357 | 165057 | 635805.19 | 0 | 0 | 800862.19 | 0 | 0 | 0 | 0 | 800862.19 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507679 | Dalry - 300mm Sewer repair. | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-07-20 | 2020-12-03 | 2021-07-22 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30803 | 30803 | 500 | 0 | 0 | 31303 | 0 | 0 | 0 | 0 | 31303 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501603 | DALRYMPLE WWTW NS353141 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2016-07-19 | 2022-04-07 | 2022-08-05 | 2023-10-23 |  | South Ayrshire | 0 | 0 | 0 | 39427.59 | 139582.28 | -24523.99 | 251999.12 | 70192 | 476677 | 2223315 | 0 | 0 | 2699992 | 0 | 0 | 0 | 0 | 2699992 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501289 | Dalscone WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-10-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 59031.7 | 114.37 | 36.43 | 0 | 0 | 59182.5 | 0 | 0 | 0 | 59182.5 | 0 | 0 | 0 | 0 | 59182.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500124 | Dalscone DOA (DOA000101) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2019-01-31 | 2019-06-18 | Dumfries and Galloway | 0 | 0 | 11549 | 32755.28 | 49515.73 | 35034 | -1008.62 | 0 | 127845.39 | 0 | 0 | 0 | 127845.39 | 0 | 0 | 0 | 0 | 127845.39 | 55692.34 | [5 empty] | N | EC01G | 7.61% | CS16D | 33.61% | EC01D | 58.78%
503058 | Dalscone WwTW - Replace Percolating Filters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2022-04-08 | 2024-02-16 | 2024-05-14 | 2025-08-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 27469.33 | 60096.74 | 56754.06 | 52219.87 | 196540 | 3007715.35 | 0 | 0 | 3204255.35 | 0 | 0 | 0 | 0 | 3204255.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
404135 | Dalwhinnie WTW - TTU | Q&S3B | Completion | OMG180 |  |  | Water | DWQR | SWMD | OMG180 | MS3 | 2016-03-31 | 2019-03-28 | 2019-03-29 | 2023-01-27 | 2023-04-20 | Highland | 0 | 0 | 0 | 0 | 113265.2 | 680912.36 | 796319.77 | 2290685.38 | 3881182.71 | 1849934.6 | 1849934.6 | 2611414.034 | 5731117.31 | 761479.434 | 0 | -0.005 | 761479.429 | 6492596.739 | 5541471 |  |  |  |  | 50.25 | Y | DW25 | 100% | [20 empty] | 1 | [46 empty] | 0
404102 | Dalwhinnie WTW Q&S IIIb Additional Requirements | Q&S3B | Completion | OMG180 |  |  | Water |  | SWD | OMG180 | MS7 | 2016-03-31 | 2018-01-24 | 2017-12-12 | 2017-12-12 | 2017-12-20 | Highland | 0 | 0 | 25960.89 | 102140.32 | 5148.73 | 0 | 110.82 | 312.36 | 133673.12 | 0 | 0 | 0 | 133673.12 | 0 | 0 | 0 | 0 | 133673.12 | 0 | [5 empty] | N | DW25 | 100%
507486 | Dalwhinnie WTW tanker discharge point | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-07 | 2021-09-13 | 2022-02-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4359 | 4359 | 5641.14 | 0 | 0 | 10000.14 | 0 | 0 | 0 | 0 | 10000.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509601 | Dams and Reservoirs West - Mole Control | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-11-09 | 2021-04-02 | 2021-10-11 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10112 | 10112 | 21887.67 | 0 | 0 | 31999.67 | 0 | 0 | 0 | 0 | 31999.67 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402605 | Danger Point WWPS - Arbroath | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2016-02-26 | 2016-03-01 | 2015-08-04 |  | All East Unitary Authorities | 99973 | 0 | -39088.42 | 0 | 26.8 | 0 | 0 | 0 | -39061.62 | 0 | 0 | 0 | 60911.38 | 0 | 0 | 0 | 0 | 60911.38 | 209381.79 | [5 empty] | N | CM_M&G | 100%
503738 | Darnhay Farm - Mauchline DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 | 2019-10-04 | 2019-10-04 | 2019-11-11 | 2022-04-14 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 244864.72 | 20081.28 | 264946 | 0 | 0 | 0 | 264946 | 0 | 0 | 0 | 0 | 264946 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403658 | Darnley Mains Development - Trunk Mains Diversion | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2014-01-29 | 2014-09-30 | 2014-09-30 | 2022-04-28 |  | East Renfrewshire | 2061305 | 0 | -21500 | -62816.62 | -228033.83 | 105288.86 | 144119.34 | 82592.02 | 19649.77 | 2657674 | 0 | 0 | 4738628.77 | 0 | 0 | 261371.23 | 261371.23 | 5000000 | 0 | [5 empty] | N | CM_WSI | 100%
501078 | Data and Application Integration | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-29 | 2016-03-29 | 2016-03-29 | 2017-10-12 |  | Scottish Water Wide | 0 | 0 | 1634947 | -590672.14 | 389651.61 | 0 | 0 | 0 | 1433926.47 | 0 | 0 | 0 | 1433926.47 | 0 | 0 | 0 | 0 | 1433926.47 | 306661.32 | [5 empty] | N | CM_M&G | 100%
510962 | Data Regulation Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2028-04-28 | 2029-03-30 | 2029-08-01 | 2031-03-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425701.65 | 0 | 0 | 425701.65 | 0 | 0 | 0 | 0 | 425701.65 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502788 | Davidston Dam Raw Water Improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-11-23 | 2028-07-26 | 2028-10-19 | 2029-03-21 |  | Moray | 0 | 0 | 0 | 0 | 5739.53 | 3860.47 | 0 | 0 | 9600 | 190399.98 | 0 | 0 | 199999.98 | 0 | 0 | 0 | 0 | 199999.98 | 622473.57 | [5 empty] | N | CM_WSI | 100%
500976 | DC LAN Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-02-15 | 2017-01-31 | 2017-01-31 | 2018-03-28 |  | Scottish Water Wide | 0 | 0 | 164128 | 1079965.71 | 82591.67 | 9532.08 | 0 | 0 | 1336217.46 | 0 | 0 | 0 | 1336217.46 | 0 | 0 | 0 | 0 | 1336217.46 | 306661.32 | [5 empty] | N | CM_M&G | 100%
501822 | Dean Street Stewarton - Pipe Bridge replace pipework | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2017-05-30 | 2021-06-22 | 2021-09-29 | 2021-12-28 |  | East Ayrshire | 0 | 0 | 0 | 6296.59 | 1860.82 | 125.79 | 1186.49 | 692.31 | 10162 | 29303.09 | 0 | 0 | 39465.09 | 0 | 0 | 0 | 0 | 39465.09 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504962 | Deanston WWTW - Major Mechanical refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2021-08-11 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23200 | 23200 | 89300.17 | 0 | 0 | 112500.17 | 0 | 0 | 0 | 0 | 112500.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502629 | Dechmont WSZ - A89 trunk main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-08-17 | 2022-06-22 | 2022-09-05 | 2023-04-06 |  | East Lothian | 0 | 0 | 0 | 18070.09 | 7703.23 | 12626.68 | 0 | -11178.96 | 27221.04 | 772778.91 | 0 | 0 | 799999.95 | 0 | 0 | 0 | 0 | 799999.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502225 | Denholm WWTW Access Road | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2016-06-13 | 2016-08-30 | 2016-09-12 | 2017-01-10 |  | Scottish Borders | 0 | 0 | 0 | 942638.79 | 48186 | 0 | -628.12 | 0 | 990196.67 | 0 | 0 | 0 | 990196.67 | 0 | 0 | 0 | 0 | 990196.67 | 306661.32 | [5 empty] | N | CM_M&G | 100%
403406 | Denny Difgen | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-03-01 | 2013-03-01 | 2013-03-01 | 2013-03-28 | 2013-03-28 | Stirling | 1007399.77 | 0 | 32228.23 | 52411 | 14528.79 | 0 | 0 | 0 | 99168.02 | 0 | 0 | 0 | 1106567.79 | 0 | 0 | 0 | 0 | 1106567.79 | 0 | [5 empty] | N | CC1W | 100%
30196 | Denny STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-02-09 | 2010-11-15 | 2010-11-16 | 2011-07-27 | 2011-09-13 | Falkirk | 503650.63 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 0 | 0 | 503658.13 | 0 | 0 | 0 | 0 | 503658.13 | 119362.42 | [5 empty] | N | EC01A | 26.53% | CM_WWNI | 73.47%
500699 | Dervaig WOA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-11 | 2015-08-13 | 2015-08-25 | 2016-04-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 432864 | 578.74 | -892.54 | 0 | 0 | 0 | 432550.2 | 0 | 0 | 0 | 432550.2 | 0 | 0 | 0 | 0 | 432550.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507567 | Dervaig WTW - SCADA & PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-03-09 | 2024-01-24 | 2024-07-03 | 2026-01-14 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 494999.96 | 0 | 0 | 499999.96 | 0 | 0 | 0 | 0 | 499999.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510408 | Dervaig WwTW - Replace Pipework & Manholes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-12-22 | 2021-05-10 | 2021-10-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11321.76 | 11321.76 | 13753.02 | 0 | 0 | 25074.78 | 0 | 0 | 0 | 0 | 25074.78 | 90601.29 | [5 empty] | N | WWNI | 100%
36801 | Designated Site W-Bridge Bridge Scoping Works | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-01-30 | 2010-01-26 | 2010-02-05 | 2010-07-21 | 2010-07-21 | Falkirk | 717171.38 | 0 | 288.8 | 0 | 0 | 0 | 0 | 0 | 288.8 | 0 | 0 | 0 | 717460.18 | 0 | 0 | 0 | 0 | 717460.18 | 28761.13 | [5 empty] | N | DW9 | 100%
403070 | Desktop Refresh Project IT Enablement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-11-07 | 2014-06-11 | 2014-06-11 | 2016-12-15 |  | Scottish Water Wide | 8318677 | 0 | 192753 | 176015.03 | -5005.04 | 0 | 0 | 0 | 363762.99 | 0 | 0 | 0 | 8682439.99 | 0 | 0 | 0 | 0 | 8682439.99 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501549 | Develop and Retrofit Attenuation Roof Drainage Study | Q&S4 | Reducing flooding and pollution from sewers | Surface Water |  |  | Wastewater | SW | SWD | Surface Water | MS7 | 2015-12-23 | 2015-12-23 | 2015-12-31 | 2017-02-08 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 14746 | 18147.06 | -2427.56 | 0 | 0 | 0 | 30465.5 | 0 | 0 | 0 | 30465.5 | 0 | 0 | 0 | 0 | 30465.5 | 44865.02 | [5 empty] | N | CS15C | 100%
402381 | Developer Connections Improvement Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-12-06 | 2012-03-13 | 2012-03-13 | 2014-12-03 |  | Scottish Water Wide | 7392794 | 0 | -2824.02 | 0 | 0 | 0 | 0 | 0 | -2824.02 | 0 | 0 | 0 | 7389969.98 | 0 | 0 | 0 | 0 | 7389969.98 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503071 | Developer Services | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS4 | 2018-07-12 | 2019-01-21 | 2019-01-07 | 2020-12-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 52065.37 | 4676726.47 | 4516432.2 | 556373.96 | 9801598 | 0 | 0 | 0 | 9801598 | 0 | 0 | 0 | 0 | 9801598 | 613322.63 | [5 empty] | N | CM_M&G | 100%
34299 | Developer Services - Wastewater - Aberdeen City | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Aberdeen City | 1449470.45 | 0 | -8222.3 | 0 | 0 | 0 | 0 | 0 | -8222.3 | 0 | 0 | 0 | 1441248.15 | 0 | 0 | 0 | 0 | 1441248.15 | 0 | [5 empty] | N | SG2 | 100%
34283 | Developer Services - Wastewater - Dumfries & Galloway | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Dumfries and Galloway | 1483009.38 | 0 | 0 | 0 | 50 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 1483009.38 | 0 | 0 | 0 | 0 | 1483009.38 | 0 | [5 empty] | N | SG2 | 100%
34310 | Developer Services - Wastewater - Fife | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Fife | 5101908.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5101908.73 | 0 | 0 | 0 | 0 | 5101908.73 | 0 | [6 empty] | SG2 | 100%
34302 | Developer Services - Wastewater - Highland | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Highland | 3062146.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3062146.64 | 0 | 0 | 0 | 0 | 3062146.64 | 0 | [6 empty] | SG2 | 100%
34295 | Developer Services - Wastewater - North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | North Lanarkshire | 5552571.17 | 0 | 0 | 15245.45 | -15245.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5552571.17 | 0 | 0 | 0 | 0 | 5552571.17 | 0 | [5 empty] | N | SG2 | 100%
34298 | Developer Services - Wastewater - South Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | South Lanarkshire | 4101443.71 | 0 | 0 | 0 | 0 | 53.23 | -53.23 | 0 | 0 | 0 | 0 | 0 | 4101443.71 | 0 | 0 | 0 | 0 | 4101443.71 | 0 | [5 empty] | N | SG2 | 100%
34261 | Developer Services - Water - Aberdeenshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Aberdeenshire | 2362342.39 | 0 | 0 | 0 | 15 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 2362342.39 | 0 | 0 | 0 | 0 | 2362342.39 | 0 | [5 empty] | N | WG2 | 100%
33782 | Developer Services - Water - Argyll & Bute | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Argyll and Bute | 77914.14 | 0 | 0 | 723 | 0 | -723 | 0 | 0 | 0 | 0 | 0 | 0 | 77914.14 | 0 | 0 | 0 | 0 | 77914.14 | 0 | [5 empty] | N | WG2 | 100%
33776 | Developer Services - Water - Borders | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Scottish Borders | 535758.6 | 0 | 50.87 | -50.87 | -0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 535758.6 | 0 | 0 | 0 | 0 | 535758.6 | 0 | [5 empty] | N | WG2 | 100%
33777 | Developer Services - Water - Dumfries & Galloway | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Dumfries and Galloway | 532969.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 532969.39 | 0 | 0 | 0 | 0 | 532969.39 | 0 | [6 empty] | WG2 | 100%
34270 | Developer Services - Water - Falkirk | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Falkirk | 942078.55 | 0 | 52.84 | -52.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 942078.55 | 0 | 0 | 0 | 0 | 942078.55 | 0 | [5 empty] | N | WG2 | 100%
34271 | Developer Services - Water - Fife | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Fife | 1937816.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937816.48 | 0 | 0 | 0 | 0 | 1937816.48 | 0 | [6 empty] | WG2 | 100%
33786 | Developer Services - Water - Glasgow City | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Glasgow City | 1679396.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679396.48 | 0 | 0 | 0 | 0 | 1679396.48 | 0 | [6 empty] | WG2 | 100%
34263 | Developer Services - Water - Highland | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Highland | 1431260.07 | 0 | -233.26 | 0 | 0 | 0 | 0 | 0 | -233.26 | 0 | 0 | 0 | 1431026.81 | 0 | 0 | 0 | 0 | 1431026.81 | 0 | [5 empty] | N | WG2 | 100%
33789 | Developer Services - Water - North Lanarkshire | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | North Lanarkshire | 1247591.02 | 0 | 0 | 0 | 0.39 | -0.39 | 0 | 0 | 0 | 0 | 0 | 0 | 1247591.02 | 0 | 0 | 0 | 0 | 1247591.02 | 0 | [5 empty] | N | WG2 | 100%
402094 | Developing the QSIV Investment Plan | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-03-31 | 2011-08-29 | 2011-09-06 | 2016-01-30 |  | Scottish Water Wide | 3436890.58 | 3436890.58 | 519210.42 | -7982.66 | 0 | 0 | 0 | 0 | 511227.76 | 0 | 0 | 0 | 3948118.34 | 0 | 0 | 0 | 0 | 3948118.34 | 613322.63 | [5 empty] | N | QS4EQS | 50% | QS4EQW | 50%
500508 | Development of a National Substance Strategy (PSD) | Q&S4 | Protecting and enhancing the environment | Priority Substances Directive |  |  | Wastewater | SEPA | SWMD | Priority Substances Directive | MS5 | 2015-06-02 | 2015-09-18 | 2015-09-18 | 2020-01-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 458869 | 681131 | 485000 | 222501.64 | 125908.46 | 30700.4 | 2004110.5 | 54222.84 | 54222.8416 | 75270.5353 | 2058333.34 | 21047.6937 | 0 | 0 | 21047.6937 | 2079381.0337 | 2958548.45 | [5 empty] | Y | EC23A | 100% | [42 empty] | 1 | [24 empty] | 0
500706 | Development of Renewable Energy Projects | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water | SW | SWD | Renewable power | MS5 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 366968.14 | 176715.18 | 170867.12 | 226449.56 | 63367.47 | 73812.25 | 1078179.72 | 121863.28 | 121863.28 | 169166.9793 | 1200043 | 47303.6993 | 0 | 0 | 47303.6993 | 1247346.6993 | 1525750.06 | [5 empty] | Y | I2S_WI | 100% | [60 empty] | 4.227 | [6 empty] | 0
507029 | Devon Village WWPS - Gravity sewer repair / ground stabilisation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-06-22 | 2020-06-24 | 2020-11-23 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28380 | 28380 | 0 | 0 | 0 | 28380 | 0 | 0 | 0 | 0 | 28380 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506685 | Devonside (Tillicoultry) Combined Sewer Stabilisation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-08-25 | 2021-06-10 | 2022-03-15 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2917.71 | 2917.71 | 47082.22 | 0 | 0 | 49999.93 | 0 | 0 | 0 | 0 | 49999.93 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500666 | DG2401 High St Gatehouse of Fleet | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-06-24 | 2019-06-24 | 2019-06-24 | 2019-05-09 | 2019-05-09 | Dumfries and Galloway | 0 | 0 | 79001 | 6405.19 | 30848.92 | -116254.11 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 180449.74 | [5 empty] | N | FL_DD | 100%
506893 | Dhu Loch VT Bridge Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2020-06-04 | 2020-06-30 | 2020-08-24 | 2021-02-25 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642614.81 | 642614.81 | -1297.9 | 0 | 0 | 641316.91 | 0 | 0 | 0 | 0 | 641316.91 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501569 | Dhu Loch WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-30 | 2016-08-26 | 2016-08-29 | 2019-02-28 | 2019-12-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 65.42 | 1268.97 | 40.43 | 1383.85 | 559.78 | 0 | 3318.45 | 0 | 0 | 0 | 3318.45 | 0 | 0 | 0 | 0 | 3318.45 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
505059 | Dhu Loch WTW - inlet flash mixer No1 replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 120.7 | 18.47 | 139.17 | 1705.83 | 0 | 0 | 1845 | 0 | 0 | 0 | 0 | 1845 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509366 | Dhu Loch WTW - Replacement & upgrading to SW Specification of SCADA PLC & HMI | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-07-15 | 2023-01-23 | 2023-04-21 | 2024-03-28 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2738.48 | 2738.48 | -2738.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WSNI | 100%
511408 | Dhu Loch WTW H&S - sludge press skip removal facility improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-03 | 2021-08-13 | 2022-04-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708.14 | 1708.14 | 18291.86 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 119022.58 | [5 empty] | N | WSNI | 100%
502649 | Dhu Loch_Argyll and Bute_THM Research and Investigation | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2018-02-27 | 2020-01-31 | 2020-03-23 | 2022-11-15 | 2023-02-21 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 38519.49 | 300045.5 | 1454006.01 | 1036870 | 2829441 | 3888792 | 5170559 | 5170559 | 6718233 | 0 | 1281767 | 0 | 1281767 | 8000000 | 2549769.68 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
500070 | DI - Meter Verification | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-02-27 | 2015-04-01 | 2015-04-01 | 2017-06-19 |  | Scottish Water Wide | 0 | 0 | 69516 | 102084.13 | -4846.61 | 0 | 0 | 0 | 166753.52 | 0 | 0 | 0 | 166753.52 | 0 | 0 | 0 | 0 | 166753.52 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500069 | DI - Replacement Meters Verification Chambers Bypasses and Redundant DI Site Tidy Up | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-03-18 | 2015-04-20 | 2015-06-19 | 2021-07-05 |  | Scottish Water Wide | 0 | 0 | 457723 | 416289.3 | 531464.32 | 1726519.73 | 925966.88 | 213773.77 | 4271737 | 368262.64 | 0 | 0 | 4639999.64 | 0 | 0 | 0 | 0 | 4639999.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500071 | DI - Reporting & Zone Hosting | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-27 | 2015-03-24 | 2015-03-24 | 2021-06-30 |  | Scottish Water Wide | 0 | 0 | 133771 | 131429 | 112618.74 | 119900.18 | 122571.48 | 139864.6 | 760155 | 5964.4 | 0 | 0 | 766119.4 | 0 | 0 | 0 | 0 | 766119.4 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400799 | DI Meter Verification Chambers SR10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-04-30 | 2010-08-02 | 2015-09-30 |  | Scottish Water Wide | 1949140 | 0 | 12539.98 | 0 | 0 | 0 | 0 | 0 | 12539.98 | 0 | 0 | 0 | 1961679.98 | 0 | 0 | 0 | 0 | 1961679.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502399 | DI Meter Verification Program | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-11-29 | 2016-11-29 | 2017-03-15 | 2021-05-12 |  | Scottish Water Wide | 0 | 0 | 0 | 15983.03 | 94168.97 | 135798.91 | 137648.1 | 114841.11 | 498440.11 | 37658.9 | 0 | 0 | 536099 | 0 | 0 | 0 | 0 | 536099 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511684 | DI Meter Verification Programme RP | Q&S4 | Improving drinking water availability and resilience of service | Leakage |  |  | Water |  | SWD | Leakage | MS2 | 2021-03-19 | 2021-03-29 | 2021-04-01 | 2022-07-01 | 2022-07-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9158.88 | 9158.88 | 130841.12 | 130841.12 | 181629.7497 | 140000 | 50788.6297 | 0 | 0 | 50788.6297 | 190788.6297 | 0 | [5 empty] | N | SR15_DWA_LEAK | 100%
503671 | DI Replacement Meters Verification Chambers Bypasses and Redundant DI Site Tidy Up (Phase 2) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-09-18 | 2020-03-06 | 2020-02-25 | 2022-02-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 60714.87 | 280433.13 | 341148 | 538851.78 | 0 | 0 | 879999.78 | 0 | 0 | 0 | 0 | 879999.78 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508695 | DI Replacement Meters Verification Chambers bypasses and redundant site tidy up | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 | 2021-03-18 | 2021-03-31 | 2021-04-01 | 2022-07-01 | 2022-10-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67736.36 | 67736.36 | 962263.64 | 0 | 0 | 1030000 | 0 | 0 | 0 | 0 | 1030000 | 0 | [5 empty] | N | SR21_SS | 100%
511570 | DI Reporting & Zone Hosting | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS2 | 2021-03-16 | 2021-03-23 | 2021-04-01 | 2022-07-01 | 2022-07-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9158.88 | 9158.88 | 130841.12 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 140000 | 0 | [5 empty] | N | SR21_WA | 100%
400763 | DI SYSTEMS REPORTING - ZONE HOSTING SR10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2011-04-29 | 2015-06-08 |  | Scottish Water Wide | 671126.59 | 0 | -1226 | 0 | 0 | 0 | 0 | 0 | -1226 | 0 | 0 | 0 | 669900.59 | 0 | 0 | 0 | 0 | 669900.59 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502836 | Diabeg WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-25 | 2020-03-26 | 2020-03-26 | 2020-05-07 |  | Highland | 0 | 0 | 0 | 0 | 21346.13 | 0 | -20630.78 | 0 | 715.35 | 0 | 0 | 0 | 715.35 | 0 | 0 | 0 | 0 | 715.35 | 122419.09 | [5 empty] | N | WG1 | 100%
46833 | Diabeg WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-10 | 2011-06-21 | 2011-10-24 | 2011-12-07 | Highland | 40031.2 | 0 | 30.72 | 0 | 0 | 0 | 0 | 0 | 30.72 | 0 | 0 | 0 | 40061.92 | 0 | 0 | 0 | 0 | 40061.92 | 28761.13 | [5 empty] | N | DW13 | 100%
510600 | Digital Ad Hoc Repairs & Specials | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS0 | 2021-03-08 | 2021-04-26 | 2021-08-25 | 2027-01-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910200 | 0 | 0 | 910200 | 0 | 0 | 0 | 0 | 910200 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403556 | Digital Platform - Asset Tagging & Data Cleanse Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-10-11 | 2014-01-14 | 2014-01-14 | 2015-12-01 |  | Scottish Water Wide | 1439810 | 0 | -82934.47 | 0 | 0 | 0 | 0 | 0 | -82934.47 | 0 | 0 | 0 | 1356875.53 | 0 | 0 | 0 | 0 | 1356875.53 | 613322.63 | [5 empty] | N | CM_M&G | 100%
510602 | Digital Portfolio New Demand | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS0 | 2021-03-08 | 2021-04-26 | 2021-08-25 | 2027-01-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1189000 | 0 | 0 | 1189000 | 0 | 0 | 0 | 0 | 1189000 | 613322.63 | [5 empty] | N | CM_M&G | 100%
510601 | Digital Portfolio Risk | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | GW0 | 2028-04-28 | 2029-03-30 | 2029-08-01 | 2031-03-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000.08 | 0 | 0 | 2200000.08 | 0 | 0 | 0 | 0 | 2200000.08 | 613322.63 | [5 empty] | N | CM_M&G | 100%
508491 | Digital Workplace Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW0 | 2021-05-03 | 2022-02-14 | 2022-06-15 | 2024-02-07 | 2024-04-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11313 | 11313 | 82129.32 | 0 | 0 | 93442.32 | 0 | 0 | 0 | 0 | 93442.32 | 0 | [5 empty] | N | SR21_SS | 100%
509394 | Dindinnie Lower - Vegetation Clearance and management | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-11-04 | 2021-02-15 | 2021-06-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39894.08 | 39894.08 | 40170.48 | 0 | 0 | 80064.56 | 0 | 0 | 0 | 0 | 80064.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509034 | Dingwall DOA - Ferry Road - Railway Crossing Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2021-02-23 | 2022-11-14 | 2023-02-14 | 2024-01-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27357.74 | 27357.74 | 447642.26 | 0 | 0 | 475000 | 0 | 0 | 0 | 0 | 475000 | 209381.79 | [5 empty] | N | WWI | 100%
512122 | Dingwall DOA - Mill Street - Reduce risk of choke or collapse under railway | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249999.96 | 0 | 0 | 249999.96 | 0 | 0 | 0 | 0 | 249999.96 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505064 | Dingwall WwTW - Decant pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-10-26 | 2021-02-15 | 2021-04-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 52521.36 | 72521.36 | 0 | 0 | 0 | 72521.36 | 0 | 0 | 0 | 0 | 72521.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506298 | DIR North CM Loch AChoire Leith Penstock Emergency Repair | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-04-22 |  | 2020-05-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24730.29 | 24730.29 | 0 | 0 | 0 | 24730.29 | 0 | 0 | 0 | 0 | 24730.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505789 | DIR North CM Loch an Duin Spillway and Scour | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-24 | 2021-05-03 | 2021-09-03 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 2633.29 | 3267.71 | 5901 | 38098.59 | 0 | 0 | 43999.59 | 0 | 0 | 0 | 0 | 43999.59 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506204 | DIR North CM Loch Orasay Bridge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2022-04-14 | 2022-09-14 | 2022-12-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5643.67 | 5643.67 | 85057.17 | 0 | 0 | 90700.84 | 0 | 0 | 0 | 0 | 90700.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505928 | DIR North CM Skye Maintenance 2020 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-04-01 | 2020-12-16 | 2021-08-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29332 | 29332 | 7319.83 | 0 | 0 | 36651.83 | 0 | 0 | 0 | 0 | 36651.83 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509644 | DIR North Loch Calder Pro-active Works 2021 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS2 |  | 2020-11-18 | 2021-07-12 | 2021-11-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14292.74 | 14292.74 | 167157.85 | 167157.85 | 232043.5537 | 181450.59 | 64885.7037 | 0 | 0 | 64885.7037 | 246336.2937 | 2601944.88 | [5 empty] | N | CS22 | 100%
508004 | DIR North Loch Poll an Droighinn Emergency Repairs to Access Track | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-08-12 |  | 2020-10-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30756.79 | 30756.79 | 0 | 0 | 0 | 30756.79 | 0 | 0 | 0 | 0 | 30756.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507945 | DIR North Loch Ussie Access Track | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-08-12 |  | 2020-09-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
509631 | DIR North SWD Loch Lannsaidh Topgraphic Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-11-09 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184.18 | 184.18 | 1615.82 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509155 | DIR North SWD Loch Ussie Access Track | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6521.78 | 6521.78 | 94168.32 | 0 | 0 | 100690.1 | 0 | 0 | 0 | 0 | 100690.1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505414 | Discontinuance of Loch Craisg | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-04 | 2021-07-12 | 2021-09-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 394.67 | 10292.94 | 10687.61 | 42001.26 | 0 | 0 | 52688.87 | 0 | 0 | 0 | 0 | 52688.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505415 | Discontinuance of Loch Crocach | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-04 | 2021-07-12 | 2021-09-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 11448.6 | 6550.31 | 17998.91 | 42482.11 | 0 | 0 | 60481.02 | 0 | 0 | 0 | 0 | 60481.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505412 | Discontinuance of Loch Mor | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-04 | 2021-07-12 | 2021-09-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12148.91 | 12148.91 | 13339.31 | 0 | 0 | 25488.22 | 0 | 0 | 0 | 0 | 25488.22 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503621 | Disinfection Improvements - Delivery of High Priority Significant Improvements Ph 1 | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2019-08-29 | 2022-02-14 | 2022-05-09 | 2023-10-20 | 2023-12-13 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 32930.68 | 213.6 | 33144.28 | 14570413.67 | 0 | 0 | 14603557.95 | 0 | 4018896.6365 | 0 | 4018896.6365 | 18622454.5865 | 158124.78 | [5 empty] | N | DW25P | 100%
503423 | Disinfection Improvements - Development of High Priority Significant Improvements Group 1 | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-02-07 | 2019-04-30 | 2019-05-15 | 2021-10-25 | 2021-10-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 43733.65 | 142771.08 | 22066.57 | 208571.3 | 423926.95 | 0 | 0 | 632498.25 | 0 | 116930.0087 | 0 | 116930.0087 | 749428.2587 | 788701.34 | [5 empty] | N | DW25P_ID | 100%
503623 | Disinfection Improvements - Development of High Priority Significant Improvements Group 3 | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-08-26 | 2020-02-26 | 2020-02-26 | 2021-09-01 | 2021-09-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 69016.67 | -66059.52 | 2957.15 | 817042.93 | 0 | 0 | 820000.08 | 0 | 225361.5551 | 0 | 225361.5551 | 1045361.6351 | 250727.71 | [5 empty] | N | DW25P | 100%
8488 | Disposals | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS4 |  |  |  | 2004-03-31 |  | Scottish Water Wide | -7365.25 | 0 | 0 | 0 | 0 | 983.96 | -251 | 2760.44 | 3493.4 | 0 | 0 | 0 | -3871.85 | 0 | 0 | 0 | 0 | -3871.85 | 306661.32 | [5 empty] | N | CM_M&G | 100%
45127 | Distribution Water Quality Rehab - Afton RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWMD | Non OMG180 | MS6 | 2009-03-24 | 2010-09-14 | 2010-10-18 | 2016-11-30 | 2017-03-31 | All West Unitary Authorities | 6251083.65 | 0 | 104516.65 | 189117.24 | 68991.88 | 40264.33 | 181269.14 | 11550.97 | 595710.21 | 0 | 0 | 0 | 6846793.86 | 0 | 0 | 0 | 0 | 6846793.86 | 339997.92 | [5 empty] | Y | CM_WSI | 38.37% | DW5 | 61.63% | [18 empty] | 1 | [46 empty] | 0
45132 | Distribution Water Quality Rehab - Ashgrove RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-30 | 2012-09-24 | 2014-10-27 | 2014-12-19 | North Ayrshire | 2638525 | 0 | 0 | 583.11 | 0 | 0 | 0 | 0 | 583.11 | 0 | 0 | 0 | 2639108.11 | 0 | 0 | 0 | 0 | 2639108.11 | 339997.92 | [5 empty] | N | CM_WSI | 5.24% | DW5 | 94.76%
45145 | Distribution Water Quality Rehab - Blairlinnans North RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-08-16 | 2011-05-19 | 2011-09-08 | 2012-06-27 | West Dunbartonshire | 224125.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224125.02 | 0 | 0 | 0 | 0 | 224125.02 | 0 | [6 empty] | DW5 | 100%
45151 | Distribution Water Quality Rehab - Burncrooks RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-12-24 | 2011-03-31 | 2015-12-10 | 2015-12-10 | West Dunbartonshire | 2664465.4 | 0 | -269374.4 | -1252.74 | -14592.1 | 15588.26 | 195.78 | 0 | -269435.2 | 0 | 0 | 0 | 2395030.2 | 0 | 0 | 0 | 0 | 2395030.2 | 339997.92 | [5 empty] | N | CM_WSI | 30% | DW5 | 70%
404130 | Distribution Water Quality Rehab - Burncrooks RSZ - Transfer Project | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | WINF | Non OMG180 | MS7 | 2015-08-26 | 2016-12-20 | 2017-02-06 | 2018-03-31 | 2019-03-31 | West Dunbartonshire | 0 | 0 | 5209 | 117704 | 449809 | -52608.34 | 3445.83 | -15780.14 | 507779.35 | 0 | 0 | 0 | 507779.35 | 0 | 0 | 0 | 0 | 507779.35 | 311236.79 | [5 empty] | Y | CM_WSI | 1.347% | DW5 | 98.65% | [18 empty] | 1 | [46 empty] | 0
45155 | Distribution Water Quality Rehab - Carron Valley A RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-10-15 | 2015-08-31 | 2016-08-31 | Falkirk | 3804649 | 0 | 176790 | 17935.94 | -1399.27 | 0 | 0 | 0 | 193326.67 | 0 | 0 | 0 | 3997975.67 | 0 | 0 | 0 | 0 | 3997975.67 | 339997.92 | [5 empty] | Y | CM_WSI | 15.35% | DW5 | 84.65% | [18 empty] | 1 | [46 empty] | 0
45160 | Distribution Water Quality Rehab - Corsehouse RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-31 | 2013-05-13 | 2014-07-24 | 2015-06-23 | North Ayrshire | 1533921.62 | 0 | 4112.84 | 35.5 | 0 | 0 | 0 | 0 | 4148.34 | 0 | 0 | 0 | 1538069.96 | 0 | 0 | 0 | 0 | 1538069.96 | 339997.92 | [5 empty] | N | CM_WSI | 44.61% | DW5 | 55.39%
45163 | Distribution Water Quality Rehab - Daer A RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-09-17 | 2016-03-31 | 2017-04-30 | South Lanarkshire | 4236875 | 0 | 611992 | 56682.7 | 23881 | -2673.9 | 0 | 0 | 689881.8 | 0 | 0 | 0 | 4926756.8 | 0 | 0 | 0 | 0 | 4926756.8 | 339997.92 | [5 empty] | Y | CM_WSI | 32.12% | DW5 | 67.88% | [18 empty] | 1 | [46 empty] | 0
45165 | Distribution Water Quality Rehab - Daer Camps RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-08-20 | 2015-03-31 | 2015-03-31 | South Lanarkshire | 1346759.31 | 0 | 24793.57 | -39.53 | 0 | 0 | 0 | 0 | 24754.04 | 0 | 0 | 0 | 1371513.35 | 0 | 0 | 0 | 0 | 1371513.35 | 339997.92 | [5 empty] | N | CM_WSI | 41.77% | DW5 | 58.23%
46921 | Distribution Water Quality Rehab - Dougliehill RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-09-22 | 2010-10-25 | 2011-07-27 | 2013-02-28 | Inverclyde | 1470427 | 0 | -4096 | -208733.04 | 0 | 0 | 0 | 0 | -212829.04 | 0 | 0 | 0 | 1257597.96 | 0 | 0 | 0 | 0 | 1257597.96 | 339997.92 | [5 empty] | N | CM_WSI | 20.26% | DW5 | 79.74%
45173 | Distribution Water Quality Rehab - Fairmilehead A RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-09-09 | 2010-09-20 | 2012-05-15 | 2015-03-30 | City of Edinburgh | 770298 | 0 | -1421 | 0 | 0 | 0 | 0 | 0 | -1421 | 0 | 0 | 0 | 768877 | 0 | 0 | 0 | 0 | 768877 | 339997.92 | [5 empty] | N | CM_WSI | 16.96% | DW5 | 83.04%
45179 | Distribution Water Quality Rehab - Gartcarron RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-10-15 | 2016-12-31 | 2018-03-31 | Stirling | 2271787.36 | 0 | 1222345.64 | 847483.74 | 545021.88 | 85549.44 | 44469.07 | 9.24 | 2744879 | 0 | 0 | 0 | 5016666.36 | 0 | 0 | 0 | 0 | 5016666.36 | 339997.92 | [5 empty] | Y | DW5 | 45.59% | CM_WSI | 54.41% | [18 empty] | 1 | [46 empty] | 0
46935 | Distribution Water Quality Rehab - Glassford RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2012-05-21 | 2012-08-06 | 2014-09-17 | 2015-02-17 | South Lanarkshire | 151575 | 0 | -550.59 | 0 | 0 | 0 | 0 | 0 | -550.59 | 0 | 0 | 0 | 151024.41 | 0 | 0 | 0 | 0 | 151024.41 | 339997.92 | [5 empty] | N | DW5 | 43% | CM_WSI | 57%
45186 | Distribution Water Quality Rehab - Greenock RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-30 | 2012-08-20 | 2014-12-01 | 2016-11-30 | Inverclyde | 3419495 | 0 | 0 | -32448.31 | 0 | 0 | 0 | 0 | -32448.31 | 0 | 0 | 0 | 3387046.69 | 0 | 0 | 0 | 0 | 3387046.69 | 651234.7 | [5 empty] | N | DW5 | 5.929% | CM_WSI | 94.07%
46937 | Distribution Water Quality Rehab - Kaim Lochwinnoch RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-10-11 | 2011-04-22 | 2017-01-31 | 2017-03-31 | Renfrewshire | 1561928 | 0 | 0 | 0.37 | -53466.09 | 0 | 0 | 0 | -53465.72 | 0 | 0 | 0 | 1508462.28 | 0 | 0 | 0 | 0 | 1508462.28 | 339997.92 | [5 empty] | Y | DW5 | 43.36% | CM_WSI | 56.64% | [18 empty] | 1 | [46 empty] | 0
46172 | Distribution Water Quality Rehab - Kirbister Orkney RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWD | Non OMG180 | MS3 | 2009-03-24 | 2012-10-31 | 2013-05-06 | 2021-06-22 | 2021-11-01 | Orkney Islands | 3792639 | 0 | 986828 | 127646.49 | 213229.99 | 10270.64 | 241385.88 | 90629 | 1669990 | 16750.04 | 7123.9634 | 194924.3463 | 5479379.04 | 187800.3829 | 0 | 251506.887 | 439307.2699 | 5918686.3099 | 679995.83 | [5 empty] | Y | DW5 | 42.53% | CM_WSI | 57.47% | [18 empty] | 1 | [46 empty] | 0
45197 | Distribution Water Quality Rehab - Lintrathen RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-09-14 | 2011-04-14 | 2015-03-31 | 2015-12-31 | Shetland Islands | 997307 | 0 | 18158 | -57.62 | 0 | 0 | 0 | 0 | 18100.38 | 0 | 0 | 0 | 1015407.38 | 0 | 0 | 0 | 0 | 1015407.38 | 339997.92 | [5 empty] | Y | CM_WSI | 42% | DW5 | 58% | [18 empty] | 1 | [46 empty] | 0
45200 | Distribution Water Quality Rehab - Mannofield South RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-10-31 | 2013-02-18 | 2015-08-31 | 2016-02-29 | Aberdeen City | 5033316 | 0 | -7124 | -0.16 | -3901.49 | 0 | 0 | 0 | -11025.65 | 0 | 0 | 0 | 5022290.35 | 0 | 0 | 0 | 0 | 5022290.35 | 339997.92 | [5 empty] | Y | CM_WSI | 26% | DW5 | 74% | [18 empty] | 1 | [46 empty] | 0
45201 | Distribution Water Quality Rehab - Marchbank A RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-08-16 | 2011-08-15 | 2013-12-11 | 2014-03-28 | West Lothian | 1698138 | 0 | -283.69 | -79.06 | 0 | 0 | 0 | 0 | -362.75 | 0 | 0 | 0 | 1697775.25 | 0 | 0 | 0 | 0 | 1697775.25 | 339997.92 | [5 empty] | N | CM_WSI | 38% | DW5 | 62%
45211 | Distribution Water Quality Rehab - Muirdykes RSZ - Phase 1 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2011-09-30 | 2011-09-30 | 2013-03-29 | 2014-02-17 | Renfrewshire | 3709218.83 | 0 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0 | 0 | 0 | 3709219.38 | 0 | 0 | 0 | 0 | 3709219.38 | 311236.79 | [5 empty] | N | CM_WSI | 31.93% | DW5 | 68.07%
45217 | Distribution Water Quality Rehab - Penwhirn RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-03-24 | 2010-08-16 | 2010-09-06 | 2012-02-23 | 2014-02-17 | Dumfries and Galloway | 3349210.88 | 0 | 0 | -96098.51 | 0 | 0 | 0 | 0 | -96098.51 | 0 | 0 | 0 | 3253112.37 | 0 | 0 | 0 | 0 | 3253112.37 | 339997.92 | [5 empty] | N | DW5 | 39% | CM_WSI | 61%
46923 | Distribution Water Quality Rehab - Rawburn RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-08-16 | 2010-09-27 | 2015-03-24 | 2016-03-31 | Scottish Borders | 4779276 | 0 | 45890 | -189436.84 | 5229.5 | 0 | 0 | 0 | -138317.34 | 0 | 0 | 0 | 4640958.66 | 0 | 0 | 0 | 0 | 4640958.66 | 339997.92 | [5 empty] | N | DW5 | 48.81% | CM_WSI | 51.19%
45223 | Distribution Water Quality Rehab - Roberton RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-08-16 | 2011-02-22 | 2013-01-08 | 2014-05-15 | Scottish Borders | 2202529.46 | 0 | 0 | 0 | 0 | 34496.31 | -51744.46 | 0 | -17248.15 | 0 | 0 | 0 | 2185281.31 | 0 | 0 | 0 | 0 | 2185281.31 | 339997.92 | [5 empty] | N | CM_WSI | 45.67% | DW5 | 54.33%
45228 | Distribution Water Quality Rehab - Spynie RSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-10-11 | 2011-01-10 | 2012-12-19 | 2013-03-27 | Moray | 4737473 | 0 | -723.66 | 0 | 0 | 0 | 0 | 0 | -723.66 | 0 | 0 | 0 | 4736749.34 | 0 | 0 | 0 | 0 | 4736749.34 | 339997.92 | [5 empty] | N | CM_WSI | 23.62% | DW5 | 76.38%
507096 | Diversion of 9in AC Main Townhead Kilmaurs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-06-25 | 2020-11-09 | 2021-05-03 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68056 | 68056 | 0 | 0 | 0 | 68056 | 0 | 0 | 0 | 0 | 68056 | 311236.79 | [5 empty] | N | WSI | 100%
500077 | DMA FLA - DMA Leak Detection Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-09 | 2015-03-25 | 2015-03-25 | 2021-06-04 |  | Scottish Water Wide | 0 | 0 | 280000 | 245000 | 208138 | 241224 | 204582 | 71297 | 1250241 | 0 | 0 | 0 | 1250241 | 0 | 0 | 0 | 0 | 1250241 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500076 | DMA FLA - DMA Meter Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-06-28 |  | Scottish Water Wide | 0 | 0 | 420000 | 417476.54 | 389816.46 | 430256.81 | 488165.19 | 239553.92 | 2385268.92 | -44278.92 | 0 | 0 | 2340990 | 0 | 0 | 0 | 0 | 2340990 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500072 | DMA FLA - DMA Metering | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-11-25 |  | Scottish Water Wide | 0 | 0 | 664230.74 | 835769.26 | 535148 | 912187.63 | 685355.37 | 571489 | 4204180 | 0 | 0 | 0 | 4204180 | 0 | 0 | 0 | 0 | 4204180 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500073 | DMA FLA - DMA-FLA Loggers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-07-30 |  | Scottish Water Wide | 0 | 0 | 540000 | 610000 | 445035 | 436250 | 401593 | 359246.26 | 2792124.26 | -45010.26 | 0 | 0 | 2747114 | 0 | 0 | 0 | 0 | 2747114 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500078 | DMA Optimisation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-26 | 2015-03-26 | 2015-03-26 | 2021-07-28 |  | Scottish Water Wide | 0 | 0 | 245000 | 10000 | 46823 | 14527 | 26293 | 51213 | 393856 | 0 | 0 | 0 | 393856 | 0 | 0 | 0 | 0 | 393856 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503689 | Dodside Pumping Station Air conditioning | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWMD | Interruptions to Supply | MS3 | 2020-02-24 | 2020-02-21 | 2020-10-13 | 2021-09-09 | 2021-11-02 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 4901.77 | 27043.23 | 31945 | 48664.7 | 48664.7 | 67554.8886 | 80609.7 | 18890.1886 | 0 | 0 | 18890.1886 | 99499.8886 | 941431.82 | [5 empty] | N | CS12 | 100%
501530 | Dodside SR Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-09-07 | 2030-01-11 | 2030-08-28 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633253.07 | 0 | 0 | 633253.07 | 0 | 0 | 0 | 0 | 633253.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
46410 | Dodside SR Refurb - TWS000252 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-19 | 2011-12-29 | 2011-12-19 |  | Glasgow City | 58082.24 | 0 | -517.53 | 0 | 0 | 0 | 0 | 0 | -517.53 | 0 | 0 | 0 | 57564.71 | 0 | 0 | 0 | 0 | 57564.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502929 | Doms Documentation Refresh | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2018-05-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 93355.75 | 36953.35 | 0 | 0 | 130309.1 | 0 | 0 | 0 | 130309.1 | 0 | 0 | 0 | 0 | 130309.1 | 119022.58 | [5 empty] | N | CM_M&G | 100%
401215 | Don Cluster 1 - Scalloway to Tingwall | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2013-02-28 | 2013-03-20 | 2013-12-03 |  | Shetland Islands | 544688 | 0 | -496.83 | 0 | 0 | 0 | 0 | 0 | -496.83 | 0 | 0 | 0 | 544191.17 | 0 | 0 | 0 | 0 | 544191.17 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501049 | Don Large Middle Ground Scheme | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2015-10-05 | 2016-09-22 | 2017-03-20 | 2018-03-26 |  | Aberdeen City | 0 | 0 | 22441 | 75432.21 | 205354.85 | 12275.11 | 572.47 | -1072.48 | 315003.16 | 0 | 0 | 0 | 315003.16 | 0 | 0 | 0 | 0 | 315003.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506163 | Doonbank Park ST Intervention Development | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWMD | Revised Bathing Waters Directive | MS0 | 2020-08-18 | 2022-11-04 | 2023-04-14 | 2024-10-25 | 2025-01-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22690 | 22690 | 157524 | 0 | 0 | 180214 | 0 | 43449.1901 | 0 | 43449.1901 | 223663.1901 | 1035209.71 | [5 empty] | N | EC16B | 100%
510931 | Dores DMA - Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-07-30 | 2023-02-07 | 2023-05-08 | 2024-04-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18918.77 | 18918.77 | 781081.23 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 800000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400095 | Dornoch UID Improvements | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-04 | 2012-12-07 | 2013-01-17 | 2013-06-03 | 2013-09-18 | Highland | 295059 | 0 | -1471.84 | 0 | 0 | 0 | 0 | 0 | -1471.84 | 0 | 0 | 0 | 293587.16 | 0 | 0 | 0 | 0 | 293587.16 | 28761.13 | [5 empty] | N | EC03B | 100%
502273 | Dougliehill and Greenock WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | SEPA | SWMD | SOSI | MS5 | 2018-09-17 | 2020-03-27 | 2020-08-11 | 2020-12-31 | 2021-03-31 | Inverclyde | 0 | 0 | 0 | 8916.28 | 0 | 12155.73 | 42774.8 | 222582.68 | 286429.49 | 999.9 | 999.9 | 1388.0314 | 287429.39 | 388.1314 | 0 | 0 | 388.1314 | 287817.5214 | 0 | [5 empty] | Y | WR1 | 100% | [37 empty] | 1 | [29 empty] | 0
510232 | Dougliehill DSR demolition | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-11-09 | 2023-05-18 | 2023-08-16 | 2024-07-23 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8808.65 | 8808.65 | 591191.35 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501573 | Dougliehill WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS5 | 2017-01-20 | 2017-03-20 | 2017-03-20 | 2021-03-31 | 2021-03-31 | Inverclyde | 0 | 0 | 3348.84 | 522.86 | -55.04 | 833.51 | 0 | -2177 | 2473.17 | 2180.52 | 2180.52 | 3138.6243 | 4653.69 | 958.1043 | 0 | -0.0043 | 958.1 | 5611.79 | 182982.34 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
45559 | Doune STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2012-06-11 | 2012-08-08 | 2013-03-22 | 2013-03-22 | Stirling | 626942.67 | 0 | -9.29 | 0 | 0 | 0 | 0 | 0 | -9.29 | 0 | 0 | 0 | 626933.38 | 0 | 0 | 0 | 0 | 626933.38 | 119362.42 | [5 empty] | N | CM_WWNI | 10% | WQ01 | 90%
500250 | Doune to Callander Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2015-04-20 | 2022-10-20 | 2022-11-04 | 2023-09-25 |  | Stirling | 0 | 0 | 67869 | 102191 | -72633 | 117343.48 | 0 | -0.48 | 214770 | 2835499.79 | 0 | 0 | 3050269.79 | 0 | 0 | 0 | 0 | 3050269.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502822 | Doune WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Falkirk | 0 | 0 | 0 | 0 | 81094.05 | 931.2 | 0 | 0 | 82025.25 | 0 | 0 | 0 | 82025.25 | 0 | 0 | 0 | 0 | 82025.25 | 122419.09 | [5 empty] | N | SG1 | 100%
500726 | Dovecot Park Aberdour Relay SW Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-09-07 | 2016-03-25 | 2016-06-20 | 2016-09-28 |  | Fife | 0 | 0 | 12476.17 | 91182.83 | 0 | 956.11 | 0 | 0 | 104615.11 | 0 | 0 | 0 | 104615.11 | 0 | 0 | 0 | 0 | 104615.11 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403945 | DR & Business Continuity | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-10-03 | 2015-06-30 | 2015-06-30 | 2015-06-30 |  | Scottish Water Wide | 246316 | 0 | 11479.29 | 0 | 0 | 0 | 0 | 0 | 11479.29 | 0 | 0 | 0 | 257795.29 | 0 | 0 | 0 | 0 | 257795.29 | 613322.63 | [5 empty] | N | CM_M&G | 100%
45324 | Drimnin WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2013-03-18 | 2013-09-06 | Highland | 299550.24 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 299549.24 | 0 | 0 | 0 | 0 | 299549.24 | 0 | [5 empty] | N | DW13 | 100%
511611 | DRONGAN STW REPLACEMENT OF 2 No. PST TRAVELLING SCRAPER BRIDGES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-12-02 | 2024-06-11 | 2024-09-09 | 2025-08-15 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4186.05 | 4186.05 | 245813.95 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401315 | Drongan STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-30 | 2012-02-21 | 2012-06-18 | 2015-01-27 | 2015-02-10 | South Ayrshire | 2911721.34 | 0 | 5831.36 | 2633.52 | 5 | 0 | 0 | 0 | 8469.88 | 0 | 0 | 0 | 2920191.22 | 0 | 0 | 0 | 0 | 2920191.22 | 90601.29 | [5 empty] | N | CM_WWNI | 19.99% | EC04A | 80.01%
503543 | Drongan WwTW Bathing Water Improvement | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater | SEPA | WWINF | Revised Bathing Waters Directive | MS3 | 2019-07-09 | 2020-06-29 | 2020-09-07 | 2021-07-16 | 2021-10-20 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 312131.84 | 1171365.16 | 1483497 | 334064 | 361430 | 361430 | 1817561 | 0 | 27366 | 0 | 27366 | 1844927 | 1035209.71 |  |  |  |  | 30939.9996 | Y | EC16B | 100% | [38 empty] | 1 | [28 empty] | 0
512139 | Drought Measures - Badentinan RWI | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312999.96 | 0 | 0 | 312999.96 | 0 | 0 | 0 | 0 | 312999.96 | 119022.58 | [5 empty] | N | CM_WSI | 100%
507118 | Drought Measures - Badentinan Boreholes Temporary Pumping | IR18 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS4 | 2021-03-10 | 2021-03-10 | 2021-04-12 | 2021-03-11 | 2021-04-12 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418.6 | 418.6 | 0 | 0 | 0 | 418.6 | 0 | 0 | 0 | 0 | 418.6 | 45578.23 | [5 empty] | N | CS16WRID | 100%
507348 | Drought Measures - Semi Permanent Installation to support possible future additional RW extraction | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-09-30 | 2020-11-03 | 2021-04-16 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140315 | 140315 | 738.2 | 0 | 0 | 141053.2 | 0 | 0 | 0 | 0 | 141053.2 | 119022.58 | [5 empty] | N | CM_WSI | 100%
506637 | Drought Mitigation - Marchfield - Heathhall Mains Augmentation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-05-22 | 2020-07-03 | 2021-07-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100951 | 100951 | 3483.98 | 0 | 0 | 104434.98 | 0 | 0 | 0 | 0 | 104434.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503627 | Drought Operations - North Area 2019 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2019-08-13 | 2019-08-13 | 2019-09-10 | 2020-03-25 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 188074.31 | 384.58 | 188458.89 | 0 | 0 | 0 | 188458.89 | 0 | 0 | 0 | 0 | 188458.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | SWD | Supply Resilience | MS5 | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2021-01-06 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 83503.85 | 60196.32 | 58417.52 | 82781.6 | 111629.18 | -6528.47 | 390000 | 0 | 0 | 0 | 390000 | 0 | 0 | 0 | 0 | 390000 | 640245.27 | [5 empty] | N | WR7 | 100%
500056 | Drought Resilience - Improved Hydrological Information | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS3 | 2016-01-12 | 2016-05-18 | 2016-05-20 | 2021-12-14 | 2022-03-16 | Scottish Water Wide | 0 | 0 | 55970 | 146030 | 101000 | 104400 | 121386.43 | 41293.34 | 570079.77 | 120000 | 120000 | 166580.4295 | 690079.77 | 46580.4295 | 0 | 0 | 46580.4295 | 736660.1995 | 530117.3 | [5 empty] | N | WG4A | 100%
500669 | Drought Resilience Improved Hydrological Information Bathymetry Surveys | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2015-07-15 | 2015-08-31 | 2015-10-05 | 2017-12-06 | 2017-12-06 | Scottish Water Wide | 0 | 0 | 117700 | 253028.76 | 479202.4 | 0 | 0 | 0 | 849931.16 | 0 | 0 | 0 | 849931.16 | 0 | 0 | 0 | 0 | 849931.16 | 530117.3 | [5 empty] | N | WG4A | 100%
500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | SWD | SOSI | MS3 | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2021-03-18 | 2021-03-22 | Scottish Water Wide | 0 | 0 | 29053.58 | 9978.47 | 37004.15 | 9049.99 | 63086.82 | -28173 | 120000 | 0 | 0 | 9600 | 120000 | 9600 | 0 | 0 | 9600 | 129600 | 530117.3 | [5 empty] | N | WG4A | 100%
502968 | Drum Sewer Infiltration | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2020-08-20 | 2021-09-07 | 2022-01-10 | 2022-05-27 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 8263.62 | 4696.21 | 34798.12 | 23292.82 | 71050.77 | 740158.23 | 0 | 0 | 811209 | 0 | 0 | 0 | 0 | 811209 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502259 | Drum WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-19 | 2016-09-29 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG1 | 100%
511532 | Drumain Reservoir - Additional Spillway Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29999.97 | 0 | 0 | 29999.97 | 0 | 0 | 0 | 0 | 29999.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502842 | Drumbeg WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2020-04-27 |  | Highland | 0 | 0 | 0 | 0 | 20930.23 | 2492.6 | -17415.56 | 0 | 6007.27 | 0 | 0 | 0 | 6007.27 | 0 | 0 | 0 | 0 | 6007.27 | 122419.09 | [5 empty] | N | WG1 | 100%
46848 | Drumfearn WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-02-28 | 2011-06-06 | 2013-03-22 | 2013-11-21 | Highland | 768115.59 | 0 | 669.83 | 0 | 0 | 0 | 0 | 0 | 669.83 | 0 | 0 | 0 | 768785.42 | 0 | 0 | 0 | 0 | 768785.42 | 28761.13 | [5 empty] | N | DW23 | 100%
502759 | Drumlithie WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-08-02 | 2019-08-02 | 2019-08-02 | 2019-05-23 | 2019-05-23 | Aberdeenshire | 0 | 0 | 0 | 0 | 53034.17 | 56265.15 | -21862.51 | 0 | 87436.8 | 0 | 0 | 0 | 87436.8 | 0 | 0 | 0 | 0 | 87436.8 | 122419.09 | [5 empty] | N | SG1 | 100%
502332 | Drumnadrochit WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2019-12-18 | 2021-08-16 | 2021-09-07 | 2022-07-25 |  | Highland | 0 | 0 | 0 | 21363.18 | 6387.56 | 25217.76 | 45696.1 | 217369.4 | 316034 | 907966 | 0 | 0 | 1224000 | 0 | 0 | 0 | 0 | 1224000 | 122419.09 | [5 empty] | N | SG1 | 100%
400738 | Drumoak WwTP Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-09-21 | 2012-01-23 | 2012-05-04 | 2013-02-20 | 2013-02-20 | Aberdeenshire | 502604 | 0 | -5891.95 | 0 | 0 | 0 | 0 | 0 | -5891.95 | 0 | 0 | 0 | 496712.05 | 0 | 0 | 0 | 0 | 496712.05 | 90601.29 | [5 empty] | N | CM_WWNI | 14.6% | SG1 | 85.4%
403911 | Drumoak-Banchory Strategic Water Mains Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2014-10-15 | 2014-10-15 | 2014-10-15 | 2016-09-08 | 2016-09-08 | Aberdeenshire | 1165662.55 | 0 | 0 | 1601.53 | 0 | 0 | 0 | 0 | 1601.53 | 0 | 0 | 0 | 1167264.08 | 0 | 0 | 0 | 0 | 1167264.08 | 0 | [5 empty] | N | WG5 | 100%
500679 | Drumore Road Killearn | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-05-08 | 2019-05-08 | 2019-05-08 | 2019-01-21 | 2019-01-21 | Stirling | 0 | 0 | 121951 | -28962.9 | 26026.61 | -119013.71 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 45708.96 | [5 empty] | N | FL_NAMED | 100%
505096 | Drumossie Meter chamber investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-02-12 | 2020-08-13 | 2021-09-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 890.02 | 5738.98 | 6629 | 35479.38 | 0 | 0 | 42108.38 | 0 | 0 | 0 | 0 | 42108.38 | 311236.79 | [5 empty] | N | WSI | 100%
503526 | Drymen WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-01-03 | 2020-01-03 | 2027-04-08 | 2020-01-13 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 59441.86 | 26515.88 | 430.76 | 86388.5 | 0 | 0 | 0 | 86388.5 | 0 | 0 | 0 | 0 | 86388.5 | 122419.09 | [5 empty] | N | SG1 | 100%
505388 | DSEAR Amlaird WTW PAC Unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-28 |  | 2020-06-17 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 44.12 | 26037.53 | 26081.65 | 0 | 0 | 0 | 26081.65 | 0 | 0 | 0 | 0 | 26081.65 | 119022.58 | [5 empty] | N | WSNI | 100%
503592 | DSEAR Compliance (Desktop) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2019-06-28 | 2019-06-28 | 2020-03-16 | 2024-04-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1026699.76 | 2447191.02 | 3473890.78 | 526109.22 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 328404.37 | [5 empty] | N | CM_M&G | 100%
503278 | Dufftown WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-02-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 78150.66 | 9577.52 | -3888.09 | 83840.09 | 0 | 0 | 0 | 83840.09 | 0 | 0 | 0 | 0 | 83840.09 | 122419.09 | [5 empty] | N | SG1 | 100%
501355 | Dufftown WWTW Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-02-22 | 2016-10-13 | 2016-10-10 | 2016-09-28 |  | Moray | 0 | 0 | 378.72 | 3835.28 | -115.21 | 0 | 0.38 | 0 | 4099.17 | 0 | 0 | 0 | 4099.17 | 0 | 0 | 0 | 0 | 4099.17 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501716 | Dumbarton Road Glasgow - Clean out sewers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2017-03-29 | 2018-08-28 | 2018-09-24 | 2019-09-30 |  | Glasgow City | 0 | 0 | 0 | 4171 | 16019 | 147347 | 55682 | 25813 | 249032 | 0 | 0 | 0 | 249032 | 0 | 0 | 0 | 0 | 249032 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502901 | Dumfries and Galloway - Area Strategy Study | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS3 | 2018-08-23 | 2018-02-27 | 2019-06-24 | 2021-04-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 17156.64 | 90581.25 | 87663.67 | 14395.5 | 209797.07 | 0 | 0 | 0 | 209797.07 | 0 | 0 | 0 | 0 | 209797.07 | 122419.09 | [5 empty] | N | SG1 | 100%
500924 | Dumfries and Galloway Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2017-08-11 | 2017-08-11 | 2017-07-18 | 2017-07-18 | Dumfries and Galloway | 0 | 0 | 7000 | 1000 | -897 | 0 | 0 | 0 | 7103 | 0 | 0 | 0 | 7103 | 0 | 0 | 0 | 0 | 7103 | 106252.93 | [5 empty] | N | FL_DD | 100%
502218 | Dumfries Garroch Loaning Wastewater Pump Station | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2016-09-29 | 2016-09-29 | 2017-03-07 | 2021-06-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 23282.36 | 29.76 | 0 | 232635.29 | 70853.59 | 326801 | 27199.16 | 0 | 0 | 354000.16 | 0 | 0 | 0 | 0 | 354000.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502962 | Dumfries Loganbarns - Storm Pumps-MCC Construction Design Package | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2018-04-20 | 2018-04-20 | 2018-08-23 | 2020-01-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 179111.53 | 235794.91 | 5490.56 | 420397 | 416.75 | 0 | 0 | 420813.75 | 0 | 0 | 0 | 0 | 420813.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402035 | Dunbar New TWS | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2011-05-26 | 2012-12-19 | 2013-01-21 | 2014-04-30 | 2014-04-30 | East Lothian | 1655701.16 | 0 | 2080.84 | -426.2 | 0 | 0 | 0 | 0 | 1654.64 | 0 | 0 | 0 | 1657355.8 | 0 | 0 | 0 | 0 | 1657355.8 | 119022.58 | [5 empty] | N | CM_WSNI | 50% | WG5 | 50%
502331 | Dunbar WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-04-22 | 2024-04-03 | 2024-08-01 | 2026-01-27 |  | East Lothian | 0 | 0 | 0 | 31014.87 | 6183.27 | 3814.71 | 97634.1 | 81002.06 | 219649 | 6051438.68 | 0 | 0 | 6271087.68 | 0 | 0 | 0 | 0 | 6271087.68 | 122419.09 | [5 empty] | N | SG1 | 100%
504528 | Dunbar WWTW Incident | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2020-01-10 | 2020-06-26 | 2020-06-23 | 2020-10-26 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 294117.67 | 1044117.67 | 0 | 0 | 0 | 1044117.67 | 0 | 0 | 0 | 0 | 1044117.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503171 | Dunbar WwTW PLC-SCADA | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2018-07-31 | 2018-07-31 | 2018-08-20 | 2018-09-28 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 302841.12 | 0 | -0.12 | 302841 | 0 | 0 | 0 | 302841 | 0 | 0 | 0 | 0 | 302841 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502379 | Dunblane Glen Road DSR Mainout | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-12-22 | 2018-03-26 | 2018-05-07 | 2022-04-06 |  | Stirling | 0 | 0 | 0 | 6537.58 | 19236.2 | 85288.76 | 13069.54 | 1058.43 | 125190.51 | 37699.67 | 0 | 0 | 162890.18 | 0 | 0 | 0 | 0 | 162890.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500237 | Dunblane WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-09-27 | 2016-09-27 | 2016-09-27 | 2016-09-05 | 2016-09-05 | Stirling | 0 | 0 | 41093.15 | 80.7 | 0 | 0 | 0 | 0 | 41173.85 | 0 | 0 | 0 | 41173.85 | 0 | 0 | 0 | 0 | 41173.85 | 122419.09 | [5 empty] | N | SG1 | 100%
502344 | Dundee - Baldovie Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-10-31 | 2018-11-21 | 2018-11-23 | 2018-11-26 |  | Dundee City | 0 | 0 | 0 | 13271.03 | 42513.89 | 6501.53 | 0 | 0 | 62286.45 | 0 | 0 | 0 | 62286.45 | 0 | 0 | 0 | 0 | 62286.45 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403257 | Dundee Flow Control Valves Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-18 | 2017-01-10 | 2017-01-16 | 2017-01-17 |  | Dundee City | 29690 | 0 | 12840 | 3638.04 | 0 | 0 | 0 | 0 | 16478.04 | 0 | 0 | 0 | 46168.04 | 0 | 0 | 0 | 0 | 46168.04 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402478 | Dundee Integrated Catchment Study (Tay PFI Sewer Catchment Areas) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-01-11 | 2013-01-11 | 2015-07-17 | 2015-08-31 | Scottish Water Wide | 1219702 | 0 | 22503 | 35819.6 | 0 | -1645.26 | 0 | 0 | 56677.34 | 0 | 0 | 0 | 1276379.34 | 0 | 0 | 0 | 0 | 1276379.34 | 0 | [5 empty] | N | CS16S | 100%
503403 | Dundee Sewer Gates Surveys Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2020-09-29 | 2021-05-24 | 2021-06-10 | 2022-01-12 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 10562.95 | 1186.8 | 16429.25 | 28179 | 125986.17 | 0 | 0 | 154165.17 | 0 | 0 | 0 | 0 | 154165.17 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502429 | Dundee Tesco SPS Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 2017-05-12 |  | Dundee City | 0 | 0 | 0 | 4019 | 2880.01 | 35.22 | 0 | 0 | 6934.23 | 0 | 0 | 0 | 6934.23 | 0 | 0 | 0 | 0 | 6934.23 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510363 | Dundee Waterfront Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-01-13 | 2023-06-22 | 2023-09-20 | 2024-11-13 | 2024-11-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44278.92 | 44278.92 | 1040322.08 | 0 | 0 | 1084601 | 0 | 0 | 0 | 0 | 1084601 | 0 | [5 empty] | N | SR21_WW | 100%
30238 | Dunecht STW Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-09 | 2010-12-21 | 2011-09-19 | 2012-05-10 | 2012-05-31 | Aberdeenshire | 542444.18 | 0 | 1780.2 | 0 | 0 | 0 | 0 | 0 | 1780.2 | 0 | 0 | 0 | 544224.38 | 0 | 0 | 0 | 0 | 544224.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46384 | Dunfermline Eastern Expansion (DEX) | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2009-08-14 | 2011-03-02 | 2011-03-11 | 2012-10-15 | 2012-12-10 | Fife | 3199346 | 0 | -7318.43 | 0 | 0 | 0 | 0 | 0 | -7318.43 | 0 | 0 | 0 | 3192027.57 | 0 | 0 | 0 | 0 | 3192027.57 | 444766.03 | [5 empty] | N | WG5 | 100%
502372 | Dunfermline STC - Belt Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2016-11-25 | 2017-01-31 | 2017-02-27 | 2017-11-24 |  | Fife | 0 | 0 | 0 | 995828.08 | 1962781.37 | 153489.46 | 5746.39 | 13738.7 | 3131584 | 1002.9 | 0 | 0 | 3132586.9 | 0 | 0 | 0 | 0 | 3132586.9 | 90601.29 |  |  |  |  | 57960 | N | CM_WWNI | 100%
504415 | Dunfermline STC - Replace Sludge Holding Tank No1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2020-10-12 | 2021-01-15 | 2021-09-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWNI | 100%
46746 | Dunfermline STW - Enhancement of Sludge Treatment Facilities | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-01 | 2011-10-18 | 2011-10-18 | 2012-03-23 | 2012-03-31 | Fife | 759944.01 | 0 | 620.39 | 0 | 0 | 0 | 0 | 0 | 620.39 | 0 | 0 | 0 | 760564.4 | 0 | 0 | 0 | 0 | 760564.4 | 28761.13 | [5 empty] | N | EC06 | 100%
502949 | Dunfermline Wellwood Waste Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater | SW | SWD | Infra Charge | MS3 | 2018-01-10 | 2018-01-10 | 2018-05-31 | 2021-04-02 |  | Fife | 0 | 0 | 0 | 0 | 73140.19 | 420008.81 | 27.55 | 371.93 | 493548.47 | 624451.5 | 0 | 0 | 1117999.97 | 0 | 0 | 89439.9976 | 89439.9976 | 1207439.9676 | 0 | [5 empty] | N | SG5 | 100%
500965 | Dunfermline WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS6 | 2015-10-05 | 2018-08-31 | 2018-08-31 | 2020-09-29 |  | Fife | 0 | 0 | 53894.37 | 177451.74 | 173730.92 | 550048.92 | 1926823.21 | 164993.84 | 3046943 | 44628 | 0 | 0 | 3091571 | 0 | 0 | 0 | 0 | 3091571 | 90601.29 |  |  |  |  | 35000 | N | CM_WWNI | 100%
503213 | Dunfermline WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-24 | 2024-01-01 | 2024-04-05 | 2026-07-15 |  | Fife | 0 | 0 | 0 | 0 | 0 | 15513.66 | 16052.84 | 67918.5 | 99485 | 2800515.35 | 0 | 0 | 2900000.35 | 0 | 0 | 0 | 0 | 2900000.35 | 122419.09 | [5 empty] | N | SG1 | 100%
45546 | Dunkeld STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-03-24 | 2011-06-27 | 2012-03-23 | 2012-03-27 | Perth and Kinross | 505350.33 | 0 | 30.72 | 0 | 0 | 0 | 0 | 0 | 30.72 | 0 | 0 | 0 | 505381.05 | 0 | 0 | 0 | 0 | 505381.05 | 119362.42 | [5 empty] | N | CM_WWNI | 21.67% | WQ01 | 78.33%
502910 | Dunlop Road Stewarton Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2017-11-14 | 2017-11-14 | 2017-12-01 | 2021-12-20 |  | East Ayrshire | 0 | 0 | 0 | 0 | 19364.49 | 0 | 0 | 2671.92 | 22036.41 | 313963.5 | 0 | 0 | 335999.91 | 0 | 0 | 0 | 0 | 335999.91 | 444766.03 | [5 empty] | N | WG5 | 100%
404000 | Dunnet WWTW Outfall and PAA Dosing de-commissioning | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-03-03 | 2019-07-02 | 2019-09-23 | 2020-05-26 |  | Highland | 509.68 | 0 | 131402.32 | 44109 | 3327 | 134638 | 3345876 | 78091.25 | 3737443.57 | 11010 | 0 | 0 | 3748963.25 | 0 | 0 | 0 | 0 | 3748963.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500812 | Dunning and Aberuthven DMA Station Road Mains Rhab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2027-09-16 | 2029-05-09 | 2029-09-11 | 2031-04-07 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79661.9 | 0 | 0 | 79661.9 | 0 | 0 | 0 | 0 | 79661.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503375 | Dunning WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-06-10 | 2028-04-18 | 2028-08-21 | 2029-02-09 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 77822.42 | 5025.04 | -0.46 | 82847 | 0 | 0 | 0 | 82847 | 0 | 0 | 0 | 0 | 82847 | 122419.09 | [5 empty] | N | SG1 | 100%
501271 | Dunnswood DOA (DOA000557) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS7 | 2015-03-31 | 2016-07-29 | 2016-08-18 | 2019-03-27 | 2020-01-08 | North Lanarkshire | 0 | 0 | 20938 | 185376 | 132088 | 74776 | 32361.07 | 0 | 445539.07 | 0 | 0 | 0 | 445539.07 | 0 | 0 | 0 | 0 | 445539.07 | 282022.48 | [5 empty] | N | EC01G | 0.4899% | CS16D | 99.51%
30241 | Dunnswood STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2011-06-28 | 2011-08-23 | 2013-12-09 | 2014-01-14 | North Lanarkshire | 11639043.34 | 0 | -13327.86 | 555.62 | 0 | 0 | 0 | 0 | -12772.24 | 0 | 0 | 0 | 11626271.1 | 0 | 0 | 0 | 0 | 11626271.1 | 299303.77 | [5 empty] | N | CM_WWNI | 2.952% | SG1 | 6.868% | EC10A | 23.96% | EC01A | 32.93% | EC04A | 33.29%
500128 | Dunoon DOA (DOA002568) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-09-27 | 2015-11-02 | 2017-07-03 | 2017-07-21 | Argyll and Bute-Cowal & Bute | 0 | 0 | 96713 | 138490.05 | 34186.35 | 123.84 | 0 | 0 | 269513.24 | 0 | 0 | 0 | 269513.24 | 0 | 0 | 0 | 0 | 269513.24 | 72047.27 | [5 empty] | N | CS11 | 42.57% | CS16D | 57.43%
503558 | Dunoon WwTW Rock Stabilisation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2019-10-03 | 2019-10-03 | 2019-12-09 | 2020-04-23 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 460727.05 | 1559.47 | 462286.52 | 0 | 0 | 0 | 462286.52 | 0 | 0 | 0 | 0 | 462286.52 | 209381.79 | [5 empty] | N | CM_M&G | 100%
500130 | Dunragit DOA (DOA000090) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-09-27 | 2017-03-01 | 2017-04-28 | 2017-04-28 | Dumfries and Galloway | 0 | 0 | 15635 | -2752.89 | -2772.35 | 0 | 0 | 0 | 10109.76 | 0 | 0 | 0 | 10109.76 | 0 | 0 | 0 | 0 | 10109.76 | 72047.27 | [5 empty] | N | CS11 | 100%
502628 | Dunvegan Osedale WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 20930.23 | 457.49 | 2229.43 | -18617.25 | 0 | 4999.9 | 0 | 0 | 0 | 4999.9 | 0 | 0 | 0 | 0 | 4999.9 | 122419.09 | [5 empty] | N | WG1 | 100%
506788 | Dunwan Reservoir Responsive Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-05-26 |  | 2021-08-18 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8410.43 | 8410.43 | 1589.57 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500745 | Durley Dene Crescent Bridge of Earn Kintillo - NR | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-05-08 | 2019-05-08 | 2019-05-08 | 2019-04-11 | 2019-04-11 | Perth and Kinross | 0 | 0 | 23000 | 26411.54 | 20558.25 | 312.26 | -73760.42 | 0 | -3478.37 | 3479.37 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 180449.74 | [5 empty] | N | FL_DD | 100%
500730 | Durris WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-06-01 | 2024-03-20 | 2024-06-18 | 2025-02-26 |  | Aberdeenshire | 0 | 0 | 22957.9 | 45941.32 | 44775.98 | 6238.5 | 13309.39 | 18090.91 | 151314 | 8685.85 | 0 | 0 | 159999.85 | 0 | 0 | 0 | 0 | 159999.85 | 122419.09 | [5 empty] | N | SG1 | 100%
500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-19 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 702341 | 483956.81 | 514143.51 | 217874.03 | 31822.17 | -241996.3 | 1708141.22 | 0 | 0 | 0 | 1708141.22 | 0 | 0 | 0 | 0 | 1708141.22 | 244943.71 | [5 empty] | N | DW5A | 100%
404122 | Dyce Drive water Infra Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-09-08 | 2017-01-18 | Aberdeen City | 0 | 0 | 386989.63 | 114122.16 | 0 | 0 | 0 | 0 | 501111.79 | 0 | 0 | 0 | 501111.79 | 0 | 0 | 0 | 0 | 501111.79 | 0 | [5 empty] | N | WG5 | 100%
500474 | Dynamic Wastewater Treatment Control Prototype | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWD | Climate Change | MS5 | 2015-04-30 | 2015-07-22 | 2015-07-27 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 56700 | 73300 | 0 | -5639.04 | 0 | 6993.04 | 131354 | 0 | 0 | 0 | 131354 | 0 | 0 | 0 | 0 | 131354 | 34072.29 | [5 empty] | N | CC3S | 100%
504087 | E TWS & WTW sample tap investigations & resolution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-02-07 | 2020-11-30 | 2021-01-21 | 2022-05-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3451.96 | 165340.18 | 168792.14 | 1213664.9 | 0 | 0 | 1382457.04 | 0 | 0 | 0 | 0 | 1382457.04 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
512205 | E&M Fixed Wire Testing RP | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5349999.97 | 0 | 0 | 5349999.97 | 0 | 0 | 0 | 0 | 5349999.97 | 328404.37 | [5 empty] | N | CM_M&G | 100%
404100 | E&M Planned Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS7 | 2015-01-27 | 2015-02-26 | 2015-02-26 | 2016-11-03 |  | Scottish Water Wide | 769247 | 0 | 301073 | 1409.55 | 0 | 0 | 0 | 0 | 302482.55 | 0 | 0 | 0 | 1071729.55 | 0 | 0 | 0 | 0 | 1071729.55 | 209623.87 | [5 empty] | N | WSNI | 50% | WWNI | 50%
512206 | E&M Planned Maintenance (ATOM) RP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWD | Wastewater non infrastructure | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5885000.03 | 0 | 0 | 5885000.03 | 0 | 0 | 0 | 0 | 5885000.03 | 209623.87 | [5 empty] | N | CM_WSNI | 50% | CM_WWNI | 50%
512203 | E&M Statutory Maintenance RP | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1783333.02 | 0 | 0 | 1783333.02 | 0 | 0 | 0 | 0 | 1783333.02 | 328404.37 | [5 empty] | N | CM_M&G | 100%
509616 | E_WW-I_041120-Cartmore Lochgelly - CCTV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-11-17 | 2021-02-19 | 2021-12-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51987 | 51987 | 61833.55 | 0 | 0 | 113820.55 | 0 | 0 | 0 | 0 | 113820.55 | 209381.79 | [5 empty] | N | WWI | 100%
403745 | E034 - Ajd. No15. Invergarry Quadrant PS EO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2014-03-17 | 2016-02-17 | 2016-03-07 | 2016-03-31 | 2016-04-30 | East Renfrewshire | 2769.81 | 2769.81 | 9020.77 | 8476.42 | -55.2 | -1158.86 | 0 | 0 | 16283.13 | 0 | 0 | 0 | 19052.94 | 0 | 0 | 0 | 0 | 19052.94 | 385248.68 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
500659 | E1009 - Orchard Brae Gardens Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW1 | 2021-09-24 | 2022-02-23 | 2022-04-20 | 2023-02-22 | 2023-05-23 | City of Edinburgh | 0 | 0 | 27200 | 30185.26 | 44114.74 | 51500 | 137832.4 | 8324.33 | 299156.73 | 50804.89 | 50804.89 | 70525.8366 | 349961.62 | 19720.9466 | 0 | 0 | 19720.9466 | 369682.5666 | 841699.91 | [5 empty] | N | FL_NAMED | 100%
500661 | E1010 - Craigleith Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS1 | 2020-02-10 | 2021-04-01 | 2021-04-26 | 2022-05-11 | 2022-08-11 | City of Edinburgh | 0 | 0 | 30125 | 36128.94 | 23746.06 | 133538.67 | 219214.33 | 593728 | 1036481 | 2908796.73 | 2908796.73 | 4354251.4132 | 3945277.73 | 1445454.6832 | 0 | 0 | 1445454.6832 | 5390732.4132 | 841699.91 | [5 empty] | N | FL_NAMED | 100%
500634 | E1014 - Haymarket Terrace | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2015-06-29 | 2017-09-27 | 2017-10-08 | 2018-08-30 | 2018-08-30 | Scottish Water Wide | 0 | 0 | 339906.11 | 13031.89 | 2677684 | 287101 | 14004 | -126131.36 | 3205595.64 | 72068.36 | 0 | 0 | 3277664 | 0 | 0 | 0 | 0 | 3277664 | 180449.74 | [5 empty] | N | FL_DD | 100%
501114 | E1047 -Meadowbank Ave | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-17 | 2019-04-24 | 2019-06-12 | 2019-04-26 | 2019-04-26 | City of Edinburgh | 0 | 0 | 227849 | 40991.89 | -146750.84 | 707.42 | -9523.41 | 0 | 113274.06 | 0 | 0 | 0 | 113274.06 | 0 | 0 | 0 | 0 | 113274.06 | 180449.74 | [5 empty] | N | FL_DD | 100%
503609 | E1049 - Comiston Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-08-13 | 2022-07-13 | 2022-09-23 | 2023-04-20 | 2023-07-19 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 53853.4 | 44965.32 | 98818.72 | 201159.94 | 0 | 0 | 299978.66 | 0 | 0 | 0 | 0 | 299978.66 | 180449.74 | [5 empty] | N | FL_DD | 100%
503594 | E1050 Marchmont Road - Warrender Park Road Edinburgh (Recycled) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WINF | Flooding Demand Driven | MS0 | 2020-10-27 | 2021-10-04 | 2022-01-05 | 2023-04-19 | 2023-04-20 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 141218.66 | 429748.34 | 570967 | 6059205.44 | 0 | 0 | 6630172.44 | 0 | 0 | 0 | 0 | 6630172.44 | 355536.5 | [5 empty] | N | FL_DD | 100%
500299 | E117 - Brown Street Armadale | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2019-04-30 | 2020-06-30 | 2020-10-26 | 2021-07-16 | 2021-07-16 | West Lothian | 0 | 0 | 51910 | 50307 | 29816.15 | 39466.85 | 202792 | 891034.81 | 1265326.81 | 512826 | 553477.192 | 553477.192 | 1778152.81 | 0 | 0 | 40651.19 | 40651.19 | 1818804 | 286702.67 | [5 empty] | N | FL_DD | 100%
500667 | E1272 - Mayfield Nicolton Road Rumford Falkirk | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2018-01-17 | 2019-03-28 | 2019-03-28 | 2019-01-16 | 2019-01-16 | Falkirk | 0 | 0 | 70514 | 55002.86 | 33324.11 | -157983.87 | -230.16 | 0 | 626.94 | 0 | 0 | 0 | 626.94 | 0 | 0 | 0 | 0 | 626.94 | 977447.99 | [5 empty] | N | FL_NAMED | 100%
500995 | E1280 - Station Road Brightons Falkirk | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-20 | 2018-03-27 | 2018-03-27 | 2018-02-13 | 2018-02-13 | Falkirk | 0 | 0 | 22430 | 41053.04 | 14661.87 | 293.39 | 434.36 | 0 | 78872.65 | 0 | 0 | 0 | 78872.65 | 0 | 0 | 0 | 0 | 78872.65 | 180449.74 | [5 empty] | N | FL_DD | 100%
500665 | E1282 - Carronflats Road Grangemouth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS3 | 2018-06-13 | 2020-01-09 | 2020-03-31 | 2021-11-22 | 2021-11-22 | Falkirk | 0 | 0 | 42857 | 31078.83 | 18077.17 | 204675 | 505718 | 1262309 | 2064715 | 310812 | 310812 | 378962.708 | 2375527 | 68150.708 | 0 | 0 | 68150.708 | 2443677.708 | 464547.5 | [5 empty] | N | FL_NAMED | 100%
503571 | E1287 - Claredon Place Dunblane | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2019-07-08 | 2021-03-31 | 2021-06-10 | 2022-03-31 | 2022-03-31 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 265224 | 386937.11 | 652161.11 | 1911518.36 | 2116612.7181 | 2116612.7181 | 2563679.47 | 0 | 0 | 205094.3576 | 205094.3576 | 2768773.8276 | 355536.5 | [5 empty] | N | FL_DD | 100%
500680 | E1336 Seabegs Road Bonnybridge | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW1 | 2021-08-24 | 2022-01-03 | 2022-03-07 | 2023-02-03 | 2023-05-04 | Falkirk | 0 | 0 | 107555 | -6059.86 | 15504.86 | 26000 | 102280 | 76657.19 | 321937.19 | 294113.27 | 294113.27 | 408279.2903 | 616050.46 | 114166.0203 | 0 | 0 | 114166.0203 | 730216.4803 | 355339.9 | [5 empty] | N | FL_NAMED | 100%
501118 | E1340 - Corbiehall Boness Phase 2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-04-08 | 2019-04-08 | 2019-04-08 | 2018-02-27 | 2018-02-27 | Falkirk | 0 | 0 | 35985 | 33299.51 | 22502.49 | -91786.01 | 2200.93 | 0 | 2201.92 | 0 | 0 | 0 | 2201.92 | 0 | 0 | 0 | 0 | 2201.92 | 180449.74 | [5 empty] | N | FL_DD | 100%
501541 | E1359 - Avonbridge Inn Falkirk Road Avonbridge Falkirk | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-03-28 | 2019-03-28 | Falkirk | 0 | 0 | 21930 | 4421.24 | 1506.36 | -27856.6 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 175086.76 | [5 empty] | N | FL_DD | 100%
503327 | E1383 - Seaview Row Pittenweem | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-10-07 | 2022-02-10 | 2022-04-07 | 2022-10-28 | 2022-12-09 | Fife | 0 | 0 | 0 | 0 | 0 | 123324.23 | 34838.37 | 22548.4 | 180711 | 394289.49 | 0 | 0 | 575000.49 | 0 | 0 | 0 | 0 | 575000.49 | 175086.76 | [5 empty] | N | FL_DD | 100%
500996 | E1401 - Kinnessburn Road St Andrews Fife | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-09-22 | 2018-02-22 | 2018-02-23 | 2018-02-22 | 2018-02-22 | Fife | 0 | 0 | 24530 | 29007.06 | 5463.44 | -58904.42 | 8944.08 | 0 | 9040.16 | 0 | 0 | 0 | 9040.16 | 0 | 0 | 0 | 0 | 9040.16 | 180449.74 | [5 empty] | N | FL_DD | 100%
500059 | E1420 - Burnside Auchtermuchty Fife | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2015-10-07 | 2018-03-27 | 2018-03-27 | 2018-03-28 | 2018-03-28 | Fife | 0 | 0 | 83434 | 58219.13 | 70933.87 | 89904.46 | -1.01 | 0 | 302490.45 | 0 | 0 | 0 | 302490.45 | 0 | 0 | 0 | 0 | 302490.45 | 707465.16 | [5 empty] | N | FL_NAMED | 100%
501117 | E1425 Nos. 3 & 5 Beeches Ladybank Cupar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-09-26 | 2020-04-29 | 2020-04-29 | 2020-04-29 | 2021-04-01 | Angus | 0 | 0 | 99657 | 35295.04 | 19667.17 | -154452.66 | 1723.5 | 218.1 | 2108.15 | 0 | 0 | 0 | 2108.15 | 0 | 0 | 0 | 0 | 2108.15 | 180449.74 | [5 empty] | N | FL_DD | 100%
502362 | E1429 2& 8 Drummochy Road Lower Largo | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-12-24 | 2022-11-24 | 2023-02-13 | 2023-09-15 | 2023-12-14 | Fife | 0 | 0 | 0 | 0 | 0 | 44000 | 9186.51 | 4661.49 | 57848 | 542151.42 | 0 | 0 | 599999.42 | 0 | 0 | 0 | 0 | 599999.42 | 175086.76 | [5 empty] | N | FL_DD | 100%
501190 | E1441 - High Street Kirkcaldy Fife | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-05-29 | 2019-03-19 | 2019-03-19 | 2019-01-21 | 2019-01-21 | Fife | 0 | 0 | 22430 | 24592.69 | 17977.31 | 1495.95 | 0 | 0 | 66495.95 | 0 | 0 | 0 | 66495.95 | 0 | 0 | 0 | 0 | 66495.95 | 180449.74 | [5 empty] | N | FL_DD | 100%
502349 | E1448 Park Road Roysth Dunfermline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-07-06 | 2022-11-09 | 2023-01-11 | 2023-11-07 | 2024-02-07 | Fife | 0 | 0 | 0 | 0 | 0 | 44000 | 22238.99 | 18312.01 | 84551 | 816517.34 | 0 | 0 | 901068.34 | 0 | 0 | 0 | 0 | 901068.34 | 175086.76 | [5 empty] | N | FL_DD | 100%
501019 | E1460 - Yetholm Park Dunfermline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS4 | 2018-10-26 | 2020-03-31 | 2020-07-20 | 2021-03-12 | 2021-04-01 | Fife | 0 | 0 | 21930 | 61223.86 | 29097.89 | 140478.14 | 198143.42 | 638972.7 | 1089846 | 3000 | 60154 | 60154 | 1092846 | 0 | 0 | 57154 | 57154 | 1150000 | 180449.74 | [5 empty] | N | FL_DD | 100%
500696 | E1539 - Featherhall Crescent Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-17 | 2018-04-10 | 2018-02-06 | 2018-02-06 | 2018-02-06 | City of Edinburgh | 0 | 0 | 37390 | 29380.72 | -66770.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | FL_DD | 100%
500300 | E1549 - Drumbrae South Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-17 | 2018-12-17 | 2018-12-17 | 2018-07-05 | 2018-07-05 | City of Edinburgh | 0 | 0 | 30000 | 66063.67 | 24936.33 | -120999 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 180449.74 | [5 empty] | N | FL_DD | 100%
503333 | E1614 - Margaret Walk Dumfries | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-07-22 | 2021-11-29 | 2022-01-31 | 2022-12-16 | 2023-03-20 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 49000 | 95634.8 | 128722.28 | 273357.08 | 5380963.14 | 0 | 0 | 5654320.22 | 0 | 0 | 0 | 0 | 5654320.22 | 175086.76 | [5 empty] | N | FL_DD | 100%
500997 | E1646 - Falkirk Road Avonbridge Falkirk | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-02-26 | 2019-02-26 | Falkirk | 0 | 0 | 21930 | 26959.06 | 58110.94 | 26468.7 | -133173.85 | 0 | 294.85 | 0 | 0 | 0 | 294.85 | 0 | 0 | 0 | 0 | 294.85 | 175086.76 | [5 empty] | N | FL_DD | 100%
500792 | E1700 SR15 Aberchirder Flooding Project | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2015-10-01 | 2016-07-20 | 2016-10-24 | 2017-03-30 | 2017-03-30 | Aberdeenshire | 0 | 0 | 95302.39 | 474632.61 | 61373 | 11346.37 | 0 | 0 | 642654.37 | 0 | 0 | 0 | 642654.37 | 0 | 0 | 0 | 0 | 642654.37 | 180449.74 | [5 empty] | N | FL_DD | 100%
500658 | E2 - 144 Comiston Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2020-03-13 | 2020-03-13 | 2019-09-25 | 2019-09-25 | 2019-09-25 | City of Edinburgh | 0 | 0 | 36500 | 29973.22 | 22526.78 | -83089.49 | -3244.29 | 0 | 2666.22 | 0 | 0 | 0 | 2666.22 | 0 | 0 | 0 | 0 | 2666.22 | 440892.73 | [5 empty] | N | FL_NAMED | 100%
500657 | E4 - Mountcastle Drive Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2017-03-31 | 2017-07-21 | 2017-07-24 | 2017-11-15 | 2017-11-15 | City of Edinburgh | 0 | 0 | 33500 | 43336.73 | 101790.47 | 0 | 0 | -1692.54 | 176934.67 | 0 | 0 | 0 | 176934.67 | 0 | 0 | 0 | 0 | 176934.67 | 688771.38 | [5 empty] | N | FL_NAMED | 100%
500131 | Eaglesfield DOA (DOA000112) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-09-28 | 2015-11-02 | 2016-12-31 | 2017-07-31 | Dumfries and Galloway | 0 | 0 | 48451 | 48679.75 | 243.66 | 61.92 | 0 | 0 | 97436.33 | 0 | 0 | 0 | 97436.33 | 0 | 0 | 0 | 0 | 97436.33 | 72047.27 | [5 empty] | Y | CS11 | 46.39% | CS16D | 53.61% | [37 empty] | 1 | [27 empty] | 0
509748 | Eaglesfield SPS Pumping Main | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2021-12-22 | 2023-06-30 | 2023-09-28 | 2024-08-14 | 2024-08-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14573.06 | 14573.06 | 386543.49 | 0 | 0 | 401116.55 | 0 | 0 | 0 | 0 | 401116.55 | 0 | [5 empty] | N | SR21_WW | 100%
30247 | Eaglesham STW Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-06-09 | 2010-11-16 | 2011-03-31 | 2015-06-02 |  | East Renfrewshire | 2191314.21 | 0 | 151832 | -27667.31 | 1973.27 | 0 | 0 | 0 | 126137.96 | 0 | 0 | 0 | 2317452.17 | 0 | 0 | 0 | 0 | 2317452.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500859 | Earlish Skye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-08-19 | 2017-07-25 | 2018-03-26 | 2018-06-30 | 2018-12-31 | Highland | 0 | 0 | 830.84 | 889.12 | 10545.98 | 31627.31 | -12919.23 | 0 | 30974.02 | 0 | 0 | 0 | 30974.02 | 0 | 0 | 0 | 0 | 30974.02 | 33902.12 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 12.6 | [43 empty] | 0
46834 | Earlish Uig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-05-23 | 2011-10-24 | 2011-12-07 | Highland | 36466.91 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 | 0 | 36468.16 | 0 | 0 | 0 | 0 | 36468.16 | 28761.13 | [5 empty] | N | DW13 | 100%
502620 | Earlish WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 20930.23 | 291.13 | 2591.75 | 30467.47 | -41839.42 | 12441.16 | 0 | 0 | 0 | 12441.16 | 0 | 0 | 0 | 0 | 12441.16 | 122419.09 | [5 empty] | N | WG1 | 100%
402503 | Earlsburn No1 and No 2 Reservoirs - Interests of safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-02 | 2012-10-30 | 2012-11-19 | 2013-12-10 | 2013-12-10 | Stirling | 506565 | 0 | -5027.11 | 0 | 0 | 0 | 0 | 0 | -5027.11 | 0 | 0 | 0 | 501537.89 | 0 | 0 | 0 | 0 | 501537.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508301 | Earlsburn Reservoir No2 MIOS works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-31 | 2021-08-06 | 2022-03-21 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15276.03 | 15276.03 | 214769.84 | 0 | 0 | 230045.87 | 0 | 0 | 0 | 0 | 230045.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402959 | Earlsburn Road Lenzie Kirkintilloch Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-28 | 2015-02-10 | 2015-02-16 | 2015-05-22 | 2015-05-22 | East Dunbartonshire | 255590 | 255590 | 105419.3 | 4987.11 | -4252.11 | 0 | 0 | 0 | 106154.3 | 0 | 0 | 0 | 361744.3 | 0 | 0 | 0 | 0 | 361744.3 | 180449.74 | [5 empty] | N | FL_DD | 100%
506774 | Earlsfield DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-10 | 2021-08-06 | 2022-03-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501500 | Earlston WwTW | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS4 | 2016-04-18 | 2018-09-26 | 2018-11-26 | 2021-03-31 |  | Scottish Borders | 0 | 0 | 0 | 175824.43 | 128158.76 | 244937.45 | 525010.55 | 77739.81 | 1151671 | 184650.61 | 0 | 0 | 1336321.61 | 0 | 0 | 133632.39 | 133632.39 | 1469954 | 122419.09 | [5 empty] | N | SG1 | 100%
501592 | EARLSTON WWTW 1959 NT573382 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-06-09 | 2018-09-27 | 2018-11-26 | 2021-04-01 |  | Scottish Borders | 0 | 0 | 0 | 75107.07 | 346589.02 | 538459.69 | 1630877.54 | 562089.17 | 3153122.49 | 181480.28 | 0 | 0 | 3334602.77 | 0 | 0 | 333460.23 | 333460.23 | 3668063 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502426 | Earlston WwTW Outfall | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS7 | 2017-06-19 | 2017-09-18 | 2017-09-21 | 2018-03-31 | 2018-03-31 | Scottish Borders | 0 | 0 | 0 | 3869.46 | 32462.3 | 23138.15 | 832.09 | -3225.92 | 57076.08 | 0 | 0 | 0 | 57076.08 | 0 | 0 | 0 | 0 | 57076.08 | 41330.23 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
502640 | Early scoping for Wastewater- Water Growth - post 2021 delivery | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2021-03-11 |  | Scottish Water Wide | 0 | 0 | 0 | 42118.71 | 120870.69 | -72368.28 | -36978.08 | 2584.44 | 56227.48 | 0 | 0 | 0 | 56227.48 | 0 | 0 | 0 | 0 | 56227.48 | 122419.09 | [5 empty] | N | SG1 | 100%
502930 | Easdale - Seaview Cottage ST (Option 1A Part 1) | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS2 | 2012-09-17 | 2019-07-22 | 2021-08-16 | 2022-02-08 | 2022-05-13 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 11714.07 | 100753.94 | 208320.36 | 29771.64 | 350560 | 226251 | 226251 | 270950.8106 | 576811 | 44699.8106 | 0 | 0 | 44699.8106 | 621510.8106 | 455015.39 |  |  |  |  | 2480.0003 | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
501316 | East SPS MCC Replacement Ph 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-05-31 | 2018-07-20 | 2018-10-15 | 2021-04-29 |  | Scottish Water Wide | 0 | 0 | 0 | 55664 | 107649 | 1636959 | 178707 | 105140 | 2084119 | 2000 | 0 | 0 | 2086119 | 0 | 0 | 0 | 0 | 2086119 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500923 | East Ayrshire and South Ayrshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-02-15 | 2017-02-15 | 2017-02-07 | 2017-02-15 | East Ayrshire | 0 | 0 | 5000 | 1687.39 | 35.36 | 0 | 0 | 0 | 6722.75 | 0 | 0 | 0 | 6722.75 | 0 | 0 | 0 | 0 | 6722.75 | 106252.93 | [5 empty] | N | FL_DD | 100%
507786 | East Building Condition Interventions | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 |  | 2020-07-22 | 2021-02-26 | 2021-10-04 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15410 | 15410 | 166417.14 | 0 | 0 | 181827.14 | 0 | 0 | 0 | 0 | 181827.14 | 306661.32 | [5 empty] | N | CM_M&G | 100%
501586 | East Burn Sewer Kirkcaldy - Repair sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2016-07-19 | 2021-10-18 | 2022-01-10 | 2022-04-12 |  | Fife | 0 | 0 | 0 | 11799 | -8628.34 | 0 | 0 | -861.64 | 2309.02 | 104630.34 | 0 | 0 | 106939.36 | 0 | 0 | 0 | 0 | 106939.36 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500132 | East Calder DOA (DOA000529) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-12-22 | 2016-03-22 | 2018-05-31 | 2018-07-31 | West Lothian | 0 | 0 | 68167 | 328852.05 | 97035.32 | -1248 | 2716.06 | 0 | 495522.43 | 0 | 0 | 0 | 495522.43 | 0 | 0 | 0 | 0 | 495522.43 | 72047.27 | [5 empty] | Y | CS11 | 10.86% | CS16D | 89.14% | [37 empty] | 1 | [27 empty] | 0
505360 | East CM Glenlatterach IOS Phase 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-02-26 |  | 2020-12-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
507923 | East CM Glenlatterach IOS Phase 2 PPD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2020-09-22 | 2020-10-29 | 2021-01-11 | 2021-11-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269500 | 269500 | 275953.61 | 0 | 0 | 545453.61 | 0 | 0 | 0 | 0 | 545453.61 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400076 | East Kilbride Dual Manhole System Upgrades | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-10-06 | 2011-07-28 | 2011-08-22 | 2013-02-20 | 2013-09-30 | South Lanarkshire | 1714911 | 0 | -3246.93 | 0 | 0 | 0 | 0 | 0 | -3246.93 | 0 | 0 | 0 | 1711664.07 | 0 | 0 | 0 | 0 | 1711664.07 | 28761.13 | [5 empty] | N | EC04D | 100%
402988 | East King Street Helensburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-10-23 | 2014-07-01 | 2014-07-18 | 2015-03-18 | 2015-03-18 | Argyll and Bute-Cowal & Bute | 1347271 | 1347271 | 80471 | -24999.66 | -46643.91 | 0 | 0 | 0 | 8827.43 | 0 | 0 | 0 | 1356098.43 | 0 | 0 | 0 | 0 | 1356098.43 | 180449.74 | [5 empty] | N | FL_DD | 100%
400762 | East Leak Detection Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | City of Edinburgh | 465000 | 0 | -41243.42 | 0 | 0 | 0 | 0 | 0 | -41243.42 | 0 | 0 | 0 | 423756.58 | 0 | 0 | 0 | 0 | 423756.58 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500229 | East Linton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS2 | 2018-08-03 | 2020-04-03 | 2021-07-16 | 2023-06-21 |  | East Lothian | 0 | 0 | 39725.61 | 15077.35 | 42278.79 | 102800.01 | 603635.68 | 254776.56 | 1058294 | 3789503 | 0 | 0 | 4847797 | 0 | 0 | 1652203 | 1652203 | 6500000 | 213020.38 | [5 empty] | N | CM_WWNI | 4% | SG1 | 96%
500921 | East Lothian Midlothian and West Lothian Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-01-31 | 2017-01-31 | 2016-12-16 | 2017-01-31 | East Lothian | 0 | 0 | 6000 | -529.59 | 35.36 | 0 | 0 | 0 | 5505.77 | 0 | 0 | 0 | 5505.77 | 0 | 0 | 0 | 0 | 5505.77 | 106252.93 | [5 empty] | N | FL_DD | 100%
402976 | East PH 2 - WW Lumphinnans Hydrobrake | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-26 | 2013-05-27 | 2013-07-17 | 2013-12-20 |  | Fife | 123879 | 0 | -1242.71 | 0 | 0 | 0 | 0 | 0 | -1242.71 | 0 | 0 | 0 | 122636.29 | 0 | 0 | 0 | 0 | 122636.29 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403036 | East Ph 2 East Bylaw Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-05-17 | 2015-05-25 | 2015-06-22 | 2015-12-22 |  | Shetland Islands | 17398 | 0 | 111316 | 0.39 | -276.29 | 0 | 0 | 0 | 111040.1 | 0 | 0 | 0 | 128438.1 | 0 | 0 | 0 | 0 | 128438.1 | 90601.29 | [5 empty] | N | CM_WWI | 100%
403031 | East Ph 2 North Queensferry Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-06 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 722 | 0 | 0 | -355.98 | 0 | 0 | 0 | 0 | -355.98 | 0 | 0 | 0 | 366.02 | 0 | 0 | 0 | 0 | 366.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403035 | East Ph 2 Saline Intrusion in pumping stations in Orkney-Shetland | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-11-22 | 2016-06-24 | 2016-06-24 | 2016-06-28 |  | Orkney Islands | 4544 | 0 | 8939.14 | 442.86 | 0 | 0 | 0 | 0 | 9382 | 0 | 0 | 0 | 13926 | 0 | 0 | 0 | 0 | 13926 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402974 | East Ph2 - River Ore Pollution Trunk sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-15 | 2016-12-11 | 2016-04-01 | 2016-12-13 |  | Fife | 26237 | 0 | 108541 | 60232.09 | 0 | 0 | 0 | 0 | 168773.09 | 0 | 0 | 0 | 195010.09 | 0 | 0 | 0 | 0 | 195010.09 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403003 | East Ph2 -Torphins network infiltration | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-30 | 2016-12-11 | 2016-12-12 | 2016-12-12 |  | Aberdeenshire | 14556 | 0 | 2933 | -2851.37 | 0 | 0 | 0 | 0 | 81.63 | 0 | 0 | 0 | 14637.63 | 0 | 0 | 0 | 0 | 14637.63 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402973 | East phase 2- Dysart SPS Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-26 | 2016-03-14 | 2016-03-17 | 2016-09-16 |  | Fife | 1000 | 0 | 4785.9 | 0 | 0 | 0 | 0 | 0 | 4785.9 | 0 | 0 | 0 | 5785.9 | 0 | 0 | 0 | 0 | 5785.9 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400629 | East Pollution Hotspots Phase 1A | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2012-03-02 | 2012-05-25 | 2013-03-18 |  | All East Unitary Authorities | 213408 | 0 | 7727.53 | 0 | 0 | 0 | 0 | 0 | 7727.53 | 0 | 0 | 0 | 221135.53 | 0 | 0 | 0 | 0 | 221135.53 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400628 | East Pollution Hotspots Phase 1B | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2012-03-28 | 2012-09-11 | 2013-03-18 |  | All East Unitary Authorities | 300970 | 0 | 4744.13 | 0 | 0 | 0 | 0 | 0 | 4744.13 | 0 | 0 | 0 | 305714.13 | 0 | 0 | 0 | 0 | 305714.13 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511481 | East Repair-Refurb-Replace DMA Meters and Loggers RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-24 | 2021-04-01 | 2022-07-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34018.69 | 34018.69 | 485981.31 | 0 | 0 | 520000 | 0 | 0 | 0 | 0 | 520000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500015 | East Rogerton TWS - Tower Roofs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS7 | 2015-05-08 | 2017-11-24 | 2018-01-30 | 2019-03-06 |  | South Lanarkshire | 0 | 0 | 64060 | 144225.01 | 225743.59 | 766388.24 | 17360.93 | -79643.69 | 1138134.08 | 5582.98 | 0 | 0 | 1143717.06 | 0 | 0 | 0 | 0 | 1143717.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512005 | East Shore Pittenweem Sewers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2022-03-28 | 2023-10-04 | 2024-01-02 | 2024-12-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14190.7 | 14190.7 | 285809.3 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503373 | East Wemyss WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-01-16 | 2019-01-16 | Fife | 0 | 0 | 0 | 0 | 0 | 74030.64 | 0 | 0 | 74030.64 | 0 | 0 | 0 | 74030.64 | 0 | 0 | 0 | 0 | 74030.64 | 122419.09 | [5 empty] | N | SG1 | 100%
402978 | East WWI Ph 2 - Arbroath John Street West | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-07-20 | 2016-07-20 | 2016-07-20 |  | Angus | 3142 | 0 | 44.69 | 40.93 | 0 | 0 | 0 | 0 | 85.62 | 0 | 0 | 0 | 3227.62 | 0 | 0 | 0 | 0 | 3227.62 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402982 | East WWI Ph 2 - Haugh Road Burntisland Storm Pump Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-02-19 | 2016-04-27 | 2016-07-07 |  | Fife | 224.88 | 0 | 45069.01 | 93018.52 | 313.66 | -1455.43 | 0 | 0 | 136945.76 | 0 | 0 | 0 | 137170.64 | 0 | 0 | 0 | 0 | 137170.64 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402984 | East WWI Ph 2 - Methil Day Care Centre | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-02-19 | 2016-04-27 | 2016-07-31 |  | Fife | 5349.96 | 0 | 32642.04 | 77500 | 0 | 3913.64 | 0 | 0 | 114055.68 | 0 | 0 | 0 | 119405.64 | 0 | 0 | 0 | 0 | 119405.64 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402975 | East WWI ph 2 - River Ore Trunk sewer Jamphalars Cardenden | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-09 | 2013-08-26 | 2013-10-14 | 2014-04-08 |  | Fife | 35597 | 0 | 418.72 | -385.56 | 0 | 0 | 0 | 0 | 33.16 | 0 | 0 | 0 | 35630.16 | 0 | 0 | 0 | 0 | 35630.16 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402983 | East WWI Ph 2 St Andrews DOA PIF | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 1000 | 0 | 0 | -411.71 | 0 | 0 | 0 | 0 | -411.71 | 0 | 0 | 0 | 588.29 | 0 | 0 | 0 | 0 | 588.29 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402985 | East WWI Ph 2 Woodhaven Pier | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 732 | 0 | 1000 | -620.48 | 0 | 0 | 0 | 0 | 379.52 | 0 | 0 | 0 | 1111.52 | 0 | 0 | 0 | 0 | 1111.52 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402979 | East WWI Ph2 - Balmerino ST | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 894 | 0 | 0 | -502.29 | 0 | 0 | 0 | 0 | -502.29 | 0 | 0 | 0 | 391.71 | 0 | 0 | 0 | 0 | 391.71 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402980 | East WWI Ph2 - Glovers Wynd Earlesferrry | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-08-12 | 2016-08-12 | 2016-08-12 |  | Fife | 6960 | 0 | 1054.97 | 0 | 0 | 0 | 0 | 0 | 1054.97 | 0 | 0 | 0 | 8014.97 | 0 | 0 | 0 | 0 | 8014.97 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402972 | East WWI Ph2 Lower Largo | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 2514 | 0 | 0 | -491.7 | 0 | 0 | 0 | 0 | -491.7 | 0 | 0 | 0 | 2022.3 | 0 | 0 | 0 | 0 | 2022.3 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402971 | East WWI Ph2 WWI - 295 Cowdenbeath High Street | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-06-06 | 2016-07-15 | 2016-11-02 |  | Fife | 224.88 | 0 | 37453.12 | 133708 | -0.28 | -4015.14 | 0 | 0 | 167145.7 | 0 | 0 | 0 | 167370.58 | 0 | 0 | 0 | 0 | 167370.58 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402604 | East WWPSs HS Access Issues | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2015-01-08 | 2015-05-29 | 2016-09-26 |  | All East Unitary Authorities | 280394 | 0 | 687878 | 136053.91 | 0 | -2386.22 | 0 | 0 | 821545.69 | 0 | 0 | 0 | 1101939.69 | 0 | 0 | 0 | 0 | 1101939.69 | 209381.79 | [5 empty] | N | CM_M&G | 100%
501318 | East WWTW MCC Replacement Ph 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS6 | 2016-07-07 | 2018-07-31 | 2018-09-25 | 2020-02-13 |  | All East Unitary Authorities | 0 | 0 | 0 | 22116.32 | 265307.96 | 695088.78 | 117338.52 | 274.42 | 1100126 | 9524 | 0 | 0 | 1109650 | 0 | 0 | 0 | 0 | 1109650 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502762 | Eastern Stirling Villages - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-12-06 | 2024-06-19 | 2024-09-18 | 2027-04-14 |  | Stirling | 0 | 0 | 0 | 0 | 199470.48 | 71241.53 | 316451.83 | 120380.84 | 707544.68 | 44292455.32 | 0 | 0 | 45000000 | 0 | 0 | 0 | 0 | 45000000 | 122419.09 | [5 empty] | N | SG1 | 100%
501249 | Eastriggs - Rigg Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2015-12-07 | 2020-12-03 | 2027-05-20 | 2021-03-23 |  | Dumfries and Galloway | 0 | 0 | 21096 | 17517.2 | 1390.57 | 0 | 17061.63 | -24380.84 | 32684.56 | 0 | 0 | 0 | 32684.56 | 0 | 0 | 0 | 0 | 32684.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500125 | Eastriggs DOA (DOA000853) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-04-27 | 2016-08-25 | 2018-11-30 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 9973 | 27292.27 | 71585.73 | 15154.66 | -6859.44 | 0 | 117146.22 | 0 | 0 | 0 | 117146.22 | 0 | 0 | 0 | 0 | 117146.22 | 67317.2 | [5 empty] | Y | EC01G | 9.54% | EC01D | 90.46% | [38 empty] | 1 | [26 empty] | 0
506489 | East-WWI-060520-Levenmouth DOA-Marmion Drive Glenrothes resolve defect and rehabilitate sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-05-07 | 2020-07-22 | 2020-09-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10571.49 | 10571.49 | 0 | 0 | 0 | 10571.49 | 0 | 0 | 0 | 0 | 10571.49 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501101 | EC01G Aesthetic Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-08-31 | 2016-10-03 | 2018-07-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 1129 | 24269.31 | 29965.47 | 4513.28 | 0 | 0 | 59877.06 | 0 | 0 | 0 | 59877.06 | 0 | 0 | 0 | 0 | 59877.06 | 4617.88 | [5 empty] | Y | EC01G | 100% | [40 empty] | 6 | [26 empty] | 0
503281 | Ecclefechan WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-01-15 | 2029-05-18 | 2030-05-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 79101.97 | 5658 | 0.03 | 84760 | 0 | 0 | 0 | 84760 | 0 | 0 | 0 | 0 | 84760 | 122419.09 | [5 empty] | N | SG1 | 100%
505271 | Echt STW - Septic Tank Overflow & Recirculation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-03-19 | 2021-05-10 | 2021-10-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 155.48 | 47844.52 | 48000 | 6999.98 | 0 | 0 | 54999.98 | 0 | 0 | 0 | 0 | 54999.98 | 90601.29 | [5 empty] | N | WWNI | 100%
402230 | Echt WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-06-28 | 2013-10-24 | 2014-01-09 | 2015-03-04 | 2015-03-04 | Aberdeenshire | 1706967 | 0 | 17055 | 9149.9 | 48827.06 | 0 | 0 | 0 | 75031.96 | 0 | 0 | 0 | 1781998.96 | 0 | 0 | 0 | 0 | 1781998.96 | 0 | [5 empty] | N | SG1 | 100%
503313 | Eddleston WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2021-03-31 | 2023-01-30 | 2023-05-08 | 2024-06-19 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 91433.53 | 85071.06 | 176504.59 | 2312453.41 | 0 | 0 | 2488958 | 0 | 0 | 0 | 0 | 2488958 | 122419.09 | [5 empty] | N | SG1 | 100%
502612 | Edgar Road SPS Rising Main Elgin | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-09-30 |  | Moray | 0 | 0 | 0 | 9623.72 | 812.95 | 598.05 | 3638.48 | -8958.83 | 5714.37 | 0 | 0 | 0 | 5714.37 | 0 | 0 | 0 | 0 | 5714.37 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501104 | Edinburgh DAS Aesthetic and Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2017-02-27 | 2017-03-27 | 2018-12-01 | 2019-01-23 | City of Edinburgh | 0 | 0 | 591 | 12353.81 | 28250.19 | 18872.46 | 0 | 0 | 60067.46 | 0 | 0 | 0 | 60067.46 | 0 | 0 | 0 | 0 | 60067.46 | 45641.25 | [5 empty] | N | EC01D | 15.25% | EC01G | 31.12% | EC10E | 53.63%
400948 | Edinburgh Haymarket Terrace - Internal Flooding Programme | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2010-05-31 | 2013-10-18 | 2015-10-19 | 2015-10-19 | 2015-10-19 | City of Edinburgh | 126235.14 | 126235.14 | -126234.15 | -7832.14 | 1897.01 | 0 | 0 | 0 | -132169.28 | 0 | 0 | 0 | -5934.14 | 0 | 0 | 0 | 0 | -5934.14 | 0 | [5 empty] | N | FL_NAMED | 100%
501311 | Edinburgh High Consequence Sewer Rehab Ph1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-02-17 | 2017-01-31 | 2017-02-06 | 2019-05-31 |  | City of Edinburgh | 0 | 0 | 9734 | 390061 | 525183 | 800846 | 462.82 | 20713.18 | 1747000 | 0 | 0 | 0 | 1747000 | 0 | 0 | 0 | 0 | 1747000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500819 | Edinburgh Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2017-03-28 | 2017-03-28 | 2016-12-02 | 2017-03-28 | City of Edinburgh | 0 | 0 | 5092.83 | 1913.91 | 532 | 0 | 0 | 0 | 7538.74 | 0 | 0 | 0 | 7538.74 | 0 | 0 | 0 | 0 | 7538.74 | 106252.93 | [5 empty] | N | FL_DD | 100%
402479 | Edinburgh Integrated Catchment Study (AVSE PFI - Edinburgh Sewer Catchment Area) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-04-30 | 2013-04-30 | 2016-08-30 | 2016-11-07 | Scottish Water Wide | 1241862 | 0 | 92738.46 | 69372.54 | 29997 | 26793.75 | 0 | 0 | 218901.75 | 0 | 0 | 0 | 1460763.75 | 0 | 0 | 0 | 0 | 1460763.75 | 0 | [5 empty] | N | CS16S | 100%
502961 | Edinburgh Rising Mains project | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS1 | 2021-03-23 | 2021-07-02 | 2021-07-12 | 2021-09-06 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 20048.62 | 80188.07 | 60780.87 | 58 | 161075.56 | 20977.1 | 0 | 0 | 182052.66 | 0 | 0 | 0 | 0 | 182052.66 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503772 | Edinburgh Strategic Growth Investigation | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS0 | 2019-10-02 | 2021-11-29 | 2022-03-31 | 2022-10-26 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 208684.13 | 100676.16 | 309360.29 | 550639.71 | 0 | 0 | 860000 | 0 | 0 | 0 | 0 | 860000 | 122419.09 | [5 empty] | N | SG1 | 100%
501096 | Edinburgh Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-09-26 | 2016-09-28 | 2018-10-31 | 2019-07-31 | City of Edinburgh | 0 | 0 | 3837 | 34236.82 | 39826.18 | 15100 | -5018.55 | 0 | 87981.45 | 0 | 0 | 0 | 87981.45 | 0 | 0 | 0 | 0 | 87981.45 | 0 | [5 empty] | Y | EC10D | 100% | [40 empty] | 1 | [26 empty] | 0
503034 | Edzell Rural DMA - North Water Bridge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2019-12-11 | 2019-12-12 | 2020-10-27 | 2020-11-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 12453.61 | 16346.39 | 77255.84 | 109.45 | 106165.3 | 0 | 0 | 0 | 106165.3 | 0 | 0 | 0 | 0 | 106165.3 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502819 | Edzell WwTW - Investigation and Scope Definition for Potential Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-12-18 | 2019-12-18 | 2027-04-01 | 2019-09-12 | 2019-09-12 | Angus | 0 | 0 | 0 | 0 | 63338.94 | 12729.93 | -42340.54 | 0 | 33728.33 | 0 | 0 | 0 | 33728.33 | 0 | 0 | 0 | 0 | 33728.33 | 122419.09 | [5 empty] | N | SG1 | 100%
500223 | Eela Water - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-20 | 2020-01-31 | Shetland Islands | 0 | 0 | 604.56 | 31705.62 | 47595.16 | 6062.66 | 23726.07 | 0 | 109694.07 | 0 | 0 | 0 | 109694.07 | 0 | 0 | 0 | 0 | 109694.07 | 608770.69 | [5 empty] | N | DW5FS | 100%
505114 | Eela Water - Raw water main replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-03-18 | 2020-09-28 | 2021-05-28 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 10166.69 | 119266.71 | 129433.4 | 21169.3 | 0 | 0 | 150602.7 | 0 | 0 | 0 | 0 | 150602.7 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500860 | Eela Water Shetland RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-06-03 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Shetland Islands | 0 | 0 | 16989.46 | 10147.45 | 7415.4 | 0 | 0 | 0 | 34552.31 | 0 | 0 | 0 | 34552.31 | 0 | 0 | 0 | 0 | 34552.31 | 870817.86 | [5 empty] | N | DW5FS | 100%
501256 | Eela Water WTW - CM | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS7 | 2020-09-22 | 2020-09-22 | 2028-07-10 | 2020-09-30 | 2029-02-07 | Shetland Islands | 0 | 0 | 1684.21 | 18090.52 | 11568.76 | 800.88 | 23159.71 | 0 | 55304.07 | 0 | 0 | 0 | 55304.07 | 0 | 0 | 0 | 0 | 55304.07 | 0 | [5 empty] | N | SR21_WA | 100%
501091 | Eela Water WTW QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2016-11-02 | 2018-02-28 | 2018-03-28 | 2021-10-26 | 2022-01-31 | Shetland Islands | 0 | 0 | 3448.91 | 58429.83 | 402540.72 | 1229484.01 | 365545.31 | 360263.74 | 2419712.52 | 922840 | 922840 | 1401909.5939 | 3342552.52 | 479069.5939 | 0 | 4.6566e-10 | 479069.5939 | 3821622.1139 | 53220.96 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
500030 | Eela WTW to Sullom Voe | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | WINF | Supply Resilience | MS4 | 2016-08-01 | 2018-06-29 | 2018-09-28 | 2021-03-31 | 2021-06-30 | Shetland Islands | 0 | 0 | 160186.88 | 55510.12 | 61639 | 2011383.72 | 3274515.61 | 1697065.67 | 7260301 | 112348.22 | 112348.22 | 254790.4949 | 7372649.22 | 142442.2749 | 0 | 9.3132e-10 | 142442.2749 | 7515091.4949 | 1989709.51 | [5 empty] | Y | CS16WR | 100% | [24 empty] | 1 | [42 empty] | 0
507211 | E-E-NI-150620-Badentinan WTW - Assessment of Generator (6646) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2637.92 | 2637.92 | 0 | 0 | 0 | 2637.92 | 0 | 0 | 0 | 0 | 2637.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503578 | EFOS - Ford Avenue Dreghorn Irvine | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-11-22 | 2022-03-28 | 2022-05-30 | 2023-12-22 | 2024-02-14 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 47707.35 | 87887.35 | 135594.7 | 64405.29 | 0 | 0 | 199999.99 | 0 | 0 | 0 | 0 | 199999.99 | 106252.93 | [5 empty] | N | FL_DD | 100%
503693 | EFOS - High Road Saltcoats | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-11-16 | 2023-06-26 | 2023-10-27 | 2025-05-22 | 2025-07-15 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 32243.83 | 113566.73 | 145810.55 | 54189.45 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 106252.93 | [5 empty] | N | FL_DD | 100%
503626 | EFOS - Meadowpark and Belmont Road Ayr | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-01-25 | 2022-09-02 | 2023-01-05 | 2022-09-02 | 2024-09-23 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 34989.67 | 183514.33 | 218504 | 50648.32 | 0 | 0 | 269152.32 | 0 | 0 | 0 | 0 | 269152.32 | 106252.93 | [5 empty] | N | FL_DD | 100%
502912 | EFOS - Meadowpark Ayr | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2021-04-20 | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2019-09-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 6000 | 19314.69 | -25313.68 | 1.01 | 0.24 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0 | 1.25 | 106252.93 | [5 empty] | N | FL_DD | 100%
503615 | EFOS - Middlepart Crescent Saltcoats | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-11-16 | 2023-06-26 | 2023-10-27 | 2025-05-22 | 2025-07-15 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 46024.69 | 107279.75 | 153304.44 | 146695.57 | 0 | 0 | 300000.01 | 0 | 0 | 0 | 0 | 300000.01 | 106252.93 | [5 empty] | N | FL_DD | 100%
503692 | EFOS - Russell Street Hamilton | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-09-13 | 2022-01-17 | 2022-03-21 | 2023-10-13 | 2023-12-06 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 35590 | 78596.27 | 114186.27 | 85813.73 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 106252.93 | [5 empty] | N | FL_DD | 100%
503506 | EFOS - STAMPERLAND GARDENS CLARKSTON | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-08-19 | 2022-01-03 | 2022-03-07 | 2023-01-20 | 2023-04-24 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 41860.47 | 24008.1 | 65262.43 | 131131 | 2380411.04 | 0 | 0 | 2511542.04 | 0 | 0 | 0 | 0 | 2511542.04 | 106252.93 | [5 empty] | N | FL_DD | 100%
503391 | EFOS - 1968-2 Lawers Square Penicuik | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-10-05 | 2022-02-14 | 2022-04-18 | 2023-03-03 | 2023-06-05 | Midlothian | 0 | 0 | 0 | 0 | 0 | 29000 | 48282.06 | 42266.94 | 119549 | 530451.11 | 0 | 0 | 650000.11 | 0 | 0 | 0 | 0 | 650000.11 | 106252.93 | [5 empty] | N | FL_DD | 100%
502955 | EFOS - A8 East Hamilton Street Greenock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-08-23 | 2022-01-13 | 2022-03-21 | 2023-02-22 | 2023-05-25 | Inverclyde | 0 | 0 | 0 | 0 | 6000 | 21000 | 87380.72 | 178208.57 | 292589.28 | 1543010.72 | 0 | 0 | 1835600 | 0 | 0 | 0 | 0 | 1835600 | 106252.93 | [5 empty] | N | FL_DD | 100%
502700 | EFOS - Aulton Way Montrose | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-09-13 | 2022-01-17 | 2022-03-21 | 2023-02-03 | 2023-05-08 | Angus | 0 | 0 | 0 | 0 | 57000 | 16000 | 10688.81 | 89108.19 | 172797 | 1827203.16 | 0 | 0 | 2000000.16 | 0 | 0 | 0 | 0 | 2000000.16 | 106252.93 | [5 empty] | N | FL_DD | 100%
503625 | EFOS - Barron Terrace and Waggon Road Leven Fife | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-10-29 | 2022-03-07 | 2022-05-09 | 2023-12-01 | 2024-01-24 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 25555.4 | 94847.37 | 120402.77 | 3259618.58 | 0 | 0 | 3380021.35 | 0 | 0 | 0 | 0 | 3380021.35 | 106252.93 | [5 empty] | N | FL_DD | 100%
503368 | EFOS - Bayview Court Cullen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-07-09 | 2021-04-01 | Moray | 0 | 0 | 0 | 0 | 0 | 11000 | 24235.14 | -5147.57 | 30087.57 | 0 | 0 | 0 | 30087.57 | 0 | 0 | 0 | 0 | 30087.57 | 106252.93 | [5 empty] | N | FL_DD | 100%
502699 | EFOS - Cheapside Street Eaglesham | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-09-06 | 2018-09-06 | 2018-09-06 | 2018-08-16 | 2018-08-16 | Renfrewshire | 0 | 0 | 0 | 0 | 34931.28 | 15511.35 | 846.75 | 0 | 51289.38 | 0 | 0 | 0 | 51289.38 | 0 | 0 | 0 | 0 | 51289.38 | 106252.93 | [5 empty] | N | FL_DD | 100%
506749 | EFOS - Cheapside Street Eaglesham 2020 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2023-01-23 | 2023-05-30 | 2023-07-31 | 2025-02-10 | 2025-05-13 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28571 | 28571 | 171429.03 | 0 | 0 | 200000.03 | 0 | 0 | 0 | 0 | 200000.03 | 106252.93 | [5 empty] | N | FL_DD | 100%
503552 | EFOS - Colston Rd_Meadowside Gdns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-10-01 | 2022-01-07 | 2022-03-11 | 2022-09-08 | 2022-12-09 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 39289.03 | 82151.97 | 121441 | 78558.78 | 0 | 0 | 199999.78 | 0 | 0 | 0 | 0 | 199999.78 | 106252.93 | [5 empty] | N | FL_DD | 100%
503860 | EFOS - Crow Wood Terrace Chryston - W1000 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS3 | 2020-02-28 | 2021-03-24 | 2021-03-31 | 2022-04-28 | 2022-07-22 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 190443 | 649677 | 840120 | 2803997.82 | 2803997.82 | 3454069.0009 | 3644117.82 | 650071.1809 | 0 | 4.6566e-10 | 650071.1809 | 4294189.0009 | 0 |  |  |  |  | 34719.9996 | N | FL_NAMED | 100%
502913 | EFOS - Cumbrae Road Saltcoats | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-09-20 | 2022-05-06 | 2022-07-27 | 2022-12-09 | 2023-03-06 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 7000 | 53842.3 | 79701.03 | 140543.33 | 134456.69 | 0 | 0 | 275000.02 | 0 | 0 | 0 | 0 | 275000.02 | 106252.93 | [5 empty] | N | FL_DD | 100%
503694 | EFOS - Deepdene Road Bearsden (Dalmuir) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-08-06 | 2023-03-16 | 2023-07-19 | 2025-02-11 | 2025-04-04 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 29445.26 | 97287.17 | 126732.43 | 73267.57 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 106252.93 | [5 empty] | N | FL_DD | 100%
503696 | EFOS - Dunbeath and Windsor Avenues Newton Mearns (Shieldhall) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-10-01 | 2022-02-07 | 2022-04-11 | 2023-11-03 | 2023-12-27 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 26530 | 98533 | 125063 | 74937 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 106252.93 | [5 empty] | N | FL_DD | 100%
502693 | EFOS - Glovers Wynd Earlsferry | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-05-18 | 2018-05-18 | 2018-04-25 | 2018-05-18 | 2018-05-18 | Fife | 0 | 0 | 0 | 0 | 8000 | -5087.05 | 0 | 0 | 2912.95 | 0 | 0 | 0 | 2912.95 | 0 | 0 | 0 | 0 | 2912.95 | 106252.93 | [5 empty] | N | FL_DD | 100%
506594 | EFOS - Harley Terrace Portlethen Village - FC761 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2023-02-22 | 2023-06-29 | 2023-08-30 | 2024-07-17 | 2024-07-18 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10840.18 | 10840.18 | 89159.82 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 106252.93 | [5 empty] | N | FL_DD | 100%
503210 | EFOS - Holm Road Stewarton | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-09-16 | 2022-01-20 | 2022-03-24 | 2023-02-08 | 2023-05-11 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 11000 | 47157.35 | 40722.13 | 98879.48 | 1120.52 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 106252.93 | [5 empty] | N | FL_DD | 100%
510669 | EFOS - Inchgreen Dry Dock Greenock - 385-1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-03-28 | 2022-08-02 | 2022-10-03 | 2023-04-03 | 2023-04-04 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4929 | 4929 | 95071.39 | 0 | 0 | 100000.39 | 0 | 0 | 0 | 0 | 100000.39 | 106252.93 | [5 empty] | N | FL_DD | 100%
502920 | EFOS - Inveroran Drive Bearsden | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2022-07-05 | 2023-03-06 | 2023-05-25 | 2023-10-09 | 2024-01-02 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 63829.35 | 83829.35 | 116170.65 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 106252.93 | [5 empty] | N | FL_DD | 100%
503598 | EFOS - Kirkview and Laightoun Court Cumbernauld (Dalmuir) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2020-10-27 | 2021-03-23 | 2022-05-05 | 2022-11-21 | 2023-02-20 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 69543.31 | 95632.02 | 165175.33 | 14824.62 | 0 | 0 | 179999.95 | 0 | 0 | 0 | 0 | 179999.95 | 106252.93 | [5 empty] | N | FL_DD | 100%
507136 | EFOS - Lady Street Brydekirk - SE485 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-10-24 | 2023-02-28 | 2023-05-01 | 2024-03-18 | 2024-03-19 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27354.78 | 27354.78 | 72783.17 | 0 | 0 | 100137.95 | 0 | 0 | 0 | 0 | 100137.95 | 106252.93 | [5 empty] | N | FL_DD | 100%
502761 | EFOS - Leven Road Coatbridge | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-05-31 | 2022-05-02 | 2022-08-05 | 2023-06-23 | 2023-11-02 | North Lanarkshire | 0 | 0 | 0 | 0 | 84150.78 | 46849.22 | 48770.38 | 1701.98 | 181472.36 | 2198527.49 | 0 | 0 | 2379999.85 | 0 | 0 | 0 | 0 | 2379999.85 | 106252.93 | [5 empty] | N | FL_DD | 100%
507094 | EFOS - Mackenzie Crescent Peterhead - 1569/1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2023-03-01 | 2023-07-06 | 2023-09-06 | 2025-03-19 | 2025-06-19 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3397 | 3397 | 96603 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 106252.93 | [5 empty] | N | FL_DD | 100%
502697 | EFOS - Montrose Avenue Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-14 | 2018-08-14 | Glasgow City | 0 | 0 | 0 | 0 | 90079.44 | 10276.26 | 0 | 0 | 100355.69 | 0 | 0 | 0 | 100355.69 | 0 | 0 | 0 | 0 | 100355.69 | 106252.93 | [5 empty] | N | FL_DD | 100%
506606 | EFOS - New Elgin Road Elgin - FC73 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2023-03-01 | 2023-07-06 | 2023-09-06 | 2024-07-24 | 2024-07-25 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34736.2 | 34736.2 | 65263.8 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 106252.93 | [5 empty] | N | FL_DD | 100%
503612 | EFOS - Poplar Avenue Newton Mearns (Shieldhall) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2020-10-26 | 2022-11-09 | 2023-03-14 | 2024-10-07 | 2024-11-28 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 42382.18 | 134063.82 | 176446 | 23489.93 | 0 | 0 | 199935.93 | 0 | 0 | 0 | 0 | 199935.93 | 106252.93 | [5 empty] | N | FL_DD | 100%
503338 | EFOS - Prestwick Strategic Study | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-07-22 | 2022-04-29 | 2022-07-08 | 2022-11-22 | 2023-02-22 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 45000 | 346469.33 | 237783.67 | 629253 | 120746.76 | 0 | 0 | 749999.76 | 0 | 0 | 0 | 0 | 749999.76 | 106252.93 | [5 empty] | N | FL_DD | 100%
503597 | EFOS - Ranfurly Road Bridge of Weir (Erskine) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2020-10-27 | 2022-11-09 | 2023-03-14 | 2024-10-07 | 2024-11-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 43872.73 | 101083.26 | 144955.99 | 35043.96 | 0 | 0 | 179999.95 | 0 | 0 | 0 | 0 | 179999.95 | 106252.93 | [5 empty] | N | FL_DD | 100%
502916 | EFOS - Riverside Road Galston | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-09-20 | 2022-05-09 | 2022-07-27 | 2022-12-12 | 2023-03-07 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 8000 | 52258.8 | 68168.13 | 128426.93 | 4985568.18 | 0 | 0 | 5113995.11 | 0 | 0 | 0 | 0 | 5113995.11 | 106252.93 | [5 empty] | N | FL_DD | 100%
505053 | EFOS - Sauchie Road Crieff - 0248 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-05-10 | 2021-08-30 | 2021-11-08 | 2022-11-07 | 2022-11-08 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24340.01 | 24340.01 | 2827659.99 | 0 | 0 | 2852000 | 0 | 0 | 0 | 0 | 2852000 | 106252.93 | [5 empty] | N | FL_DD | 100%
503192 | EFOS - Station Road and Churchill Place Kilbarchan | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-02-09 | 2022-07-04 | 2022-09-05 | 2023-07-21 | 2023-10-23 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 20000 | 40851.23 | 70.77 | 60922 | 39078.36 | 0 | 0 | 100000.36 | 0 | 0 | 0 | 0 | 100000.36 | 106252.93 | [5 empty] | N | FL_DD | 100%
503438 | EFOS - W688 Rhindmuir Road Baillieston | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-12-22 | 2022-03-29 | 2022-06-01 | 2022-11-29 | 2023-03-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 42435.12 | 27564.88 | 83546.82 | 153546.82 | 46733.24 | 0 | 0 | 200280.06 | 0 | 0 | 0 | 0 | 200280.06 | 106252.93 | [5 empty] | N | FL_DD | 100%
502694 | EFOS - Waggon Road Leven | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-05-18 | 2018-05-18 | 2018-04-25 | 2018-05-18 | 2018-05-18 | Fife | 0 | 0 | 0 | 0 | 6000 | -5243.45 | 0 | 0 | 756.55 | 0 | 0 | 0 | 756.55 | 0 | 0 | 0 | 0 | 756.55 | 106252.93 | [5 empty] | N | FL_DD | 100%
502922 | EFOS - Waverley Drive Airdrie | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-05-26 | 2021-10-04 | 2021-12-06 | 2022-12-01 | 2023-04-25 | North Lanarkshire | 0 | 0 | 0 | 0 | 84000 | 53000 | 38550 | -30535 | 145015 | 3592984.86 | 0 | 0 | 3737999.86 | 0 | 0 | 0 | 0 | 3737999.86 | 106252.93 | [5 empty] | N | FL_DD | 100%
503766 | EFOS - Wrangholm Drive Motherwell | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-03-30 | 2022-08-08 | 2022-10-10 | 2023-08-25 | 2023-10-18 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 28899.76 | 113170.13 | 142069.89 | 37929.99 | 0 | 0 | 179999.88 | 0 | 0 | 0 | 0 | 179999.88 | 106252.93 | [5 empty] | N | FL_DD | 100%
503695 | EFOS 281-1 - Main Street Bridge of Weir (Erskine) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2020-10-27 | 2021-04-07 | 2023-03-14 | 2024-10-07 | 2024-11-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 39550 | 90065.66 | 129615.66 | 40350.99 | 0 | 0 | 169966.65 | 0 | 0 | 0 | 0 | 169966.65 | 106252.93 | [5 empty] | N | FL_DD | 100%
300022 | Electronic - Physical Security improvements at water Assets | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-08-22 | 2015-08-05 | 2015-01-16 | 2015-04-14 | 2014-12-01 | Scottish Water Wide | 104313.6 | 0 | -3953.47 | 0 | 0 | 0 | 0 | 0 | -3953.47 | 0 | 0 | 0 | 100360.13 | 0 | 0 | 0 | 0 | 100360.13 | 28761.13 | [5 empty] | N | DW9 | 100%
507365 | Elgin DOA East Back Street Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-07-10 | 2020-08-24 | 2021-05-27 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132532 | 132532 | 414.24 | 0 | 0 | 132946.24 | 0 | 0 | 0 | 0 | 132946.24 | 209381.79 | [5 empty] | N | CM_WWI | 100%
46844 | Elgol WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-05-25 | 2012-06-28 | 2012-08-02 | 2012-09-05 | Highland | 200866.84 | 0 | 13656.76 | -6822.72 | 0 | 0 | 0 | 0 | 6834.04 | 0 | 0 | 0 | 207700.88 | 0 | 0 | 0 | 0 | 207700.88 | 28761.13 | [5 empty] | N | DW23 | 100%
503214 | Elie ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-08-23 | 2025-08-12 | 2025-11-18 | 2027-07-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 84764.25 | 8244.81 | 55741.94 | 148751 | 6806248.97 | 0 | 0 | 6954999.97 | 0 | 0 | 0 | 0 | 6954999.97 | 122419.09 | [5 empty] | N | SG1 | 100%
404098 | ELL - Factors Affecting ALC Performance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-01-28 | 2015-02-05 | 2015-02-05 | 2015-04-24 |  | Scottish Water Wide | 19822.04 | 0 | 2882.23 | 0 | 0 | 0 | 0 | 0 | 2882.23 | 0 | 0 | 0 | 22704.27 | 0 | 0 | 0 | 0 | 22704.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402489 | ELL Comparisons with other parts of the UK | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-12-16 | 2013-11-27 | 2013-12-06 | 2013-12-03 |  | Scottish Water Wide | 15808.39 | 0 | 0 | 0 | 0 | -0.05 | 0 | 0 | -0.05 | 0 | 0 | 0 | 15808.34 | 0 | 0 | 0 | 0 | 15808.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502250 | Ellipse Enhancements for Loggers | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-07-08 | 2016-07-08 | 2017-03-02 | 2018-06-22 |  | Scottish Water Wide | 0 | 0 | 0 | 16773 | 17840 | 6711.42 | 0 | 0 | 41324.42 | 0 | 0 | 0 | 41324.42 | 0 | 0 | 0 | 0 | 41324.42 | 613322.63 | [5 empty] | N | CM_WSNI | 50% | CM_WWNI | 50%
505021 | Ellon Corridor Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-10-15 | 2022-02-14 | 2022-03-11 | 2023-01-06 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117750 | 117750 | 7882250.06 | 0 | 0 | 8000000.06 | 0 | 0 | 0 | 0 | 8000000.06 | 0 | [5 empty] | N | WG1 | 100%
403902 | Ellon WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2014-10-20 | 2019-06-27 | 2019-06-28 | 2021-11-22 |  | Aberdeenshire | 34032 | 0 | 142378 | 431194.61 | 454746.84 | 725974.47 | 2885775.52 | 3972365.56 | 8612435 | 2089004.07 | 0 | 0 | 10735471.07 | 0 | 0 | 1264528.93 | 1264528.93 | 12000000 | 0 | [5 empty] | N | SG1 | 100%
45031 | Elphin At Knockan WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-06-22 | 2011-07-11 | 2012-12-11 | 2013-01-21 | Highland | 1705909 | 0 | 105.53 | 30.25 | 0 | 0 | 0 | 0 | 135.78 | 0 | 0 | 0 | 1706044.78 | 0 | 0 | 0 | 0 | 1706044.78 | 28761.13 | [5 empty] | N | DW23 | 100%
503731 | Elsrickle DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-09-30 | 2021-03-31 | 2021-03-31 | 2022-08-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 40053.63 | 96001.04 | 136054.67 | 1100661.33 | 0 | 0 | 1236716 | 0 | 0 | 113284 | 113284 | 1350000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503354 | Emergency Drought Operations - Picketlaw WTW | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2018-08-13 | 2018-08-28 | 2018-08-30 | 2019-07-09 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 580000 | -37363.55 | 355.4 | 542991.85 | 0 | 0 | 0 | 542991.85 | 0 | 0 | 0 | 0 | 542991.85 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502635 | Energy Efficiency - Power Reduction at WTW due to reduction in Leakage. | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS7 | 2018-11-23 | 2018-11-23 | 2018-12-13 | 2018-12-14 | 2018-12-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 36.43 | -36.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | I2S_WNI | 100%
500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water | SW | SWD | Energy efficiency | MS3 | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2021-04-01 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 49919 | 43692.27 | 163137.85 | 43555.73 | 65153.1 | 93542.05 | 459000 | 0 | 0 | 0 | 459000 | 0 | 0 | 0 | 0 | 459000 | 94753.86 | [5 empty] | N | I2S_WNI | 100%
500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater | SW | SWD | Energy efficiency | MS3 | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2021-07-30 | 2021-07-30 | Scottish Water Wide | 0 | 0 | 139847.22 | 1892905.78 | 855491.91 | 618236.55 | 778312.24 | 632811.31 | 4917605 | 47594.9 | 47594.9 | 66069.824 | 4965199.9 | 18474.924 | 0 | 0 | 18474.924 | 4983674.824 | 1280912.62 |  |  |  |  | -999999.9996 | N | I2S_WWNI | 100%
403296 | Energy Improvement Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-02-04 | 2013-11-18 | 2013-11-19 | 2015-10-30 |  | Scottish Water Wide | 2179530 | 0 | -90527.29 | 0 | 0 | 0 | 0 | 0 | -90527.29 | 0 | 0 | 0 | 2089002.71 | 0 | 0 | 0 | 0 | 2089002.71 | 306661.32 | [5 empty] | N | CM_M&G | 100%
505338 | ENF Peterhead Kirkton WWPS Storm penstock no1 service-repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-08-28 |  | 2021-07-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 22500 | 14000 | 0 | 0 | 36500 | 0 | 0 | 0 | 0 | 36500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500001 | Enhanced Contact Management System | Q&S4 | Improving the customer experience | Contact Management |  |  | Wastewater | SW | SWD | Contact Management | MS7 | 2015-09-07 | 2016-11-01 | 2016-11-01 | 2019-03-04 | 2019-03-04 | Scottish Water Wide | 532206 | 532206 | 1492056 | 4070208.94 | 3324387.47 | 163296.15 | 29280.4 | 0 | 9079228.96 | 0 | 0 | 0 | 9611434.96 | 0 | 0 | 0 | 0 | 9611434.96 | 5985921.07 | [5 empty] | N | CM_M&G | 33.33% | CS21W | 33.33% | CS21S | 33.33%
503517 | Enhanced Odour Mitigations - Boat of Garten WwTW | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWMD | Odour | MS3 | 2019-02-18 | 2019-02-18 | 2019-02-22 | 2021-05-11 | 2021-08-11 | Highland | 0 | 0 | 0 | 0 | 0 | 65833.73 | 937010.31 | 65270.96 | 1068115 | 3131.19 | 3131.19 | 4346.6248 | 1071246.19 | 1215.4348 | 0 | 0 | 1215.4348 | 1072461.6248 | 25746.48 |  |  |  |  | 196244 | N | CS2 | 100%
45046 | Enhancement of Borehole Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-27 | 2010-11-25 | 2011-03-14 | 2014-12-15 | 2015-02-17 | Scottish Water Wide | 2247100.9 | 0 | -1260.15 | 1282.33 | 0 | 0 | 0 | 0 | 22.18 | 0 | 0 | 0 | 2247123.08 | 0 | 0 | 0 | 0 | 2247123.08 | 28761.13 | [5 empty] | N | DW9B | 100%
46874 | Enhancement of Physical Security at GRP housed alarm panels | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-02-25 | 2012-08-29 | 2012-11-26 | 2015-01-20 | 2015-01-22 | Scottish Water Wide | 3245931.28 | 0 | 11260.46 | -1901.75 | 0 | 0 | 0 | 0 | 9358.71 | 0 | 0 | 0 | 3255289.99 | 0 | 0 | 0 | 0 | 3255289.99 | 28761.13 | [5 empty] | N | DW9E | 100%
500225 | Enhancement of Physical Security Vulnerable Point | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWMD | SEMD | MS6 | 2015-03-27 | 2017-06-29 | 2017-07-24 | 2018-06-30 | 2018-10-31 | Scottish Water Wide | 167.15 | 167.15 | 752.34 | 11455.51 | 428699.92 | 110928.61 | 1009.38 | 190.09 | 553035.85 | 0 | 0 | 0 | 553203 | 0 | 0 | 0 | 0 | 553203 | 273508.41 | [5 empty] | Y | DW9D | 100% | [27 empty] | 1 | [39 empty] | 0
500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWMD | SEMD | MS7 | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-03-27 | 2017-06-30 | Scottish Water Wide | 504.83 | 504.83 | 70671.17 | 335813.36 | 46072.45 | -11444.17 | 448.66 | -544.04 | 441017.43 | 0 | 0 | 0 | 441522.26 | 0 | 0 | 0 | 0 | 441522.26 | 19987.52 | [5 empty] | N | DW9F | 100%
502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWD | SEMD | MS7 | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-03 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 4814.14 | 1962.24 | 0 | 0 | 0 | 6776.38 | 0 | 0 | 0 | 6776.38 | 0 | 0 | 0 | 0 | 6776.38 | 78123.85 | [5 empty] | N | DW9F | 100%
501641 | Enhancement of security at vulnerable points - Phase 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWMD | SEMD | MS6 | 2015-03-31 | 2018-10-31 | 2019-03-06 | 2020-01-19 | 2020-07-31 | Scottish Water Wide | 0 | 0 | 0 | 13397.32 | 150802.68 | 432865.14 | 1174507.11 | 65315.75 | 1836888 | 3816.66 | 3816.66 | 5298.1738 | 1840704.66 | 1481.5138 | 0 | 0 | 1481.5138 | 1842186.1738 | 273508.41 | [5 empty] | Y | DW9D | 100% | [27 empty] | 1 | [39 empty] | 0
500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWMD | SEMD | MS7 | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-16 | 2017-06-30 | Scottish Water Wide | 393.93 | 393.93 | 89765.07 | 343522.2 | 45628.04 | -18227.96 | 486.3 | -264.66 | 460908.99 | 0 | 0 | 0 | 461302.92 | 0 | 0 | 0 | 0 | 461302.92 | 58136.33 | [5 empty] | N | DW9F | 100%
502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWMD | SEMD | MS6 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-06-12 | 2019-09-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 3978892.39 | 6524810.52 | 153591.86 | 9231.23 | 10666526 | 0 | 0 | 0 | 10666526 | 0 | 0 | 0 | 0 | 10666526 | 392530.99 | [5 empty] | N | CM_WSNI | 50% | DW9D | 50%
45045 | Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2014-10-15 | 2014-11-03 | 2016-03-30 | 2016-03-30 | Scottish Water Wide | 2067970.45 | 0 | -7525.44 | -21729.24 | 0 | 0 | 0 | 0 | -29254.68 | 0 | 0 | 0 | 2038715.77 | 0 | 0 | 0 | 0 | 2038715.77 | 28761.13 | [5 empty] | N | DW9A | 100%
402490 | Enhancement of WTW Security Phase 1 Sites | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-02-09 | 2012-03-13 | 2012-03-13 | 2013-06-10 | 2013-10-30 | Scottish Water Wide | 380616.69 | 0 | -38224.37 | 0 | 0 | 0 | 0 | 0 | -38224.37 | 0 | 0 | 0 | 342392.32 | 0 | 0 | 0 | 0 | 342392.32 | 0 | [5 empty] | N | DW9A | 100%
500066 | Enhancement of WWTW Security | Q&S4 | Protecting and enhancing the environment | Scottish Government Requirements |  |  | Wastewater |  | SWD | Scottish Government Requirements | MS7 | 2016-06-08 | 2016-06-08 | 2015-12-21 | 2016-06-08 | 2016-06-08 | Scottish Water Wide | 0 | 0 | 21139.53 | 0 | 0 | 0 | 0 | 0 | 21139.53 | 0 | 0 | 0 | 21139.53 | 0 | 0 | 0 | 0 | 21139.53 | 0 | [5 empty] | N | EC21A | 100%
503824 | E-NI-14112019-Glassiebarns TWS-New Inlet Valve controller (5246) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-03-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2727.56 | 1252.84 | 3980.4 | 0 | 0 | 0 | 3980.4 | 0 | 0 | 0 | 0 | 3980.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503820 | E-NI-W-13112019-Lomondhills WTW-Spare ortho Pump (5245) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2356.7 | 0 | 2356.7 | 0.51 | 0 | 0 | 2357.21 | 0 | 0 | 0 | 0 | 2357.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503832 | E-NI-W-14112019-Gamekeepers Road TWP-Renew roof (5251) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-02-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 2833.36 | 0 | 2833.36 | 0 | 0 | 0 | 2833.36 | 0 | 0 | 0 | 0 | 2833.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503864 | E-NI-WW-15112019-PETERHEAD BUCHANHAVEN WWPS-ROTORK REPAIR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-01-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1217.23 | 0 | 1217.23 | 0 | 0 | 0 | 1217.23 | 0 | 0 | 0 | 0 | 1217.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503819 | E-NI-WW-31102019-KEITH WWTW-NETWORK INFILTRATION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-10 |  | 2020-03-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 95567.26 | 0 | 95567.26 | 0 | 0 | 0 | 95567.26 | 0 | 0 | 0 | 0 | 95567.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503846 | E-NI-WW-4112019-GARDENSTOWN WWTW-SHT REFURB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-10 |  | 2020-01-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 27626.51 | 0 | 27626.51 | 0 | 0 | 0 | 27626.51 | 0 | 0 | 0 | 0 | 27626.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500953 | Enterprise Management Tool Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-11-10 | 2016-11-01 | 2016-11-01 | 2017-06-23 |  | Scottish Water Wide | 0 | 0 | 33727 | 627257.6 | 11967.07 | 0 | 0 | 0 | 672951.67 | 0 | 0 | 0 | 672951.67 | 0 | 0 | 0 | 0 | 672951.67 | 306661.32 | [5 empty] | N | CM_M&G | 100%
501303 | Environment Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-02 | 2017-04-14 | 2017-01-27 | 2017-01-27 |  | Scottish Water Wide | 0 | 0 | 87463 | 32450.58 | 0 | 0 | 0 | 0 | 119913.58 | 0 | 0 | 0 | 119913.58 | 0 | 0 | 0 | 0 | 119913.58 | 306661.32 | [5 empty] | N | CM_M&G | 100%
502336 | Environmental Studies - Development Costs | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2021-04-01 | 2021-03-01 | 2021-03-09 | 2021-03-09 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 82563.99 | 13120.33 | 0 | 14387.24 | 39928.44 | 150000 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000 | 4617.88 | [5 empty] | N | EC01G | 100%
505056 | Eoropie DOA - Sewer rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-04-09 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37971 | 37971 | 1881.72 | 0 | 0 | 39852.72 | 0 | 0 | 0 | 0 | 39852.72 | 209381.79 | [5 empty] | N | WWI | 100%
402923 | EP Volunteer Database | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-08-24 | 2012-08-24 | 2012-09-03 | 2013-06-07 |  | Scottish Water Wide | 11021.46 | 0 | 0 | 0 | 356.48 | 0 | 0 | 0 | 356.48 | 0 | 0 | 0 | 11377.94 | 0 | 0 | 0 | 0 | 11377.94 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502206 | ePay | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-08-29 |  | Scottish Water Wide | 0 | 0 | 0 | 30553.57 | 0 | 0 | 0 | 0 | 30553.57 | 0 | 0 | 0 | 30553.57 | 0 | 0 | 0 | 0 | 30553.57 | 306661.32 | [5 empty] | N | CM_M&G | 100%
402440 | Eredine Water Supply and Network - Upgrading -Adoption of Private Supply | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-02-21 | 2013-08-30 | 2013-11-25 | 2015-02-25 | 2015-03-26 | Argyll and Bute-North Argyll | 837864 | 0 | 170136 | -631.01 | 801.41 | 0 | 0 | 0 | 170306.4 | 0 | 0 | 0 | 1008170.4 | 0 | 0 | 0 | 0 | 1008170.4 | 0 |  |  |  |  | 9524.8 | N | DW10 | 100%
502881 | Eredine WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-05-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 21104.91 | 934.24 | -20131.81 | 0 | 1907.34 | 0 | 0 | 0 | 1907.34 | 0 | 0 | 0 | 0 | 1907.34 | 122419.09 | [5 empty] | N | WG1 | 100%
502909 | Erradale Street Glasgow Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-11-29 | 2018-11-29 | 2018-12-11 | 2020-01-07 |  | Glasgow City | 0 | 0 | 0 | 0 | 765890 | 1036515.77 | 890921.1 | 2613.88 | 2695940.75 | 0 | 0 | 0 | 2695940.75 | 0 | 0 | 0 | 0 | 2695940.75 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502820 | Errol WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-08-07 | 2020-08-07 | 2020-08-07 | 2020-10-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 62548.68 | 8775.8 | 168610.82 | -166673.01 | 73262.29 | 0 | 0 | 0 | 73262.29 | 0 | 0 | 0 | 0 | 73262.29 | 122419.09 | [5 empty] | N | SG1 | 100%
508446 | Erskine Bridge Trunk Mains Inspection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 | 2021-03-12 | 2021-03-16 | 2022-04-06 | 2022-10-05 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2533 | 2533 | 147466.58 | 0 | 0 | 149999.58 | 0 | 0 | 0 | 0 | 149999.58 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510186 | Erskine Bridge Weld Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 | 2021-02-22 | 2021-02-23 | 2021-04-15 | 2022-04-25 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105590.4 | 105590.4 | 1489226.4 | 0 | 0 | 1594816.8 | 0 | 0 | 0 | 0 | 1594816.8 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511364 | Erskine DOA - Gryffe Valley Trunk Sewer River Crossings Crossing No. 3 inspection and repairs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-03-22 | 2022-03-02 | 2022-10-13 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1962.62 | 1962.62 | 18037.38 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510069 | Erskine DOA - Mill of Gryffe Road Bridge of Weir - Complex sewer repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-12-02 | 2021-03-08 | 2021-05-21 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19545 | 19545 | 80454.54 | 0 | 0 | 99999.54 | 0 | 0 | 0 | 0 | 99999.54 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508519 | Erskine DOA - Sewer replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-09-22 | 2021-05-31 | 2022-01-11 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9973 | 9973 | 20026.7 | 0 | 0 | 29999.7 | 0 | 0 | 0 | 0 | 29999.7 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500126 | Erskine DOA (DOA002466) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS5 | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2020-09-25 | 2021-03-18 | Renfrewshire | 0 | 0 | 24529 | 88292.38 | 235047.62 | 153697 | 94051.97 | 58502.03 | 654120 | 14251.9 | 14251.9 | 19784.0635 | 668371.9 | 5532.1635 | 0 | 0 | 5532.1635 | 673904.0635 | 527520.69 | [5 empty] | N | EC01G | 0.8999% | EC10E | 4.03% | EC01D | 19.66% | CS11 | 21.86% | CS16D | 53.55%
503255 | Erskine Road SPS Rising Main Diversion | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-06-21 | 2028-01-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 375000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400066 | Erskine STW Refurb STW000281 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-09-04 | 2011-10-18 | 2011-11-28 | 2015-07-15 |  | Renfrewshire | 4225236.58 | 0 | 60049.65 | -571.88 | 541.42 | 0 | 0 | 0 | 60019.19 | 0 | 0 | 0 | 4285255.77 | 0 | 0 | 0 | 0 | 4285255.77 | 90601.29 |  |  |  |  | 32057 | N | CM_WWNI | 100%
501684 | Erskine trunk mains ITS Phase 1 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-09-01 | 2028-05-04 | 2028-08-01 | 2028-12-14 |  | Renfrewshire | 0 | 0 | 0 | 15537.96 | 6213.07 | 1437.52 | 16739.15 | -6968.7 | 32959 | 1503741.25 | 0 | 0 | 1536700.25 | 0 | 0 | 0 | 0 | 1536700.25 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503271 | Erskine WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-12-23 | 2024-12-04 | 2025-03-10 | 2026-10-09 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 77147.74 | 61024.32 | 97137.87 | 235309.93 | 9744374.07 | 0 | 0 | 9979684 | 0 | 0 | 0 | 0 | 9979684 | 122419.09 | [5 empty] | N | SG1 | 100%
502780 | Erskine WwTW Coarse Screens Replacement CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-06-16 | 2019-08-30 | 2019-09-12 | 2021-06-11 |  | Renfrewshire | 0 | 0 | 0 | 0 | 2911.39 | 82254.07 | 814371.74 | 165948.81 | 1065486 | 63484.84 | 0 | 0 | 1128970.84 | 0 | 0 | 83000.16 | 83000.16 | 1211971 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503102 | ESD Incentivisation Actual | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS2 | 2018-07-09 | 2018-07-09 | 2020-02-07 | 2023-12-29 | 2022-09-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 327102.8 | 0 | -565457.19 | -238354.39 | -9594369.84 | -3661399.0756 | -5082645.2543 | -9832724.23 | -1421246.1787 | 0 | 0 | -1421246.1787 | -11253970.4087 | 856283.1 | [5 empty] | N | SR15_RSK_EHR | 9.34e-11% | SR15_ENV_HABD | 0.0857% | SR15_ENV_ODO | 0.09105% | SR15_CMA_MAG | 0.5202% | SR15_DWA_SOSI | 0.5367% | SR15_CMA_WSI | 0.5558% | SR15_SED_INFC | 0.8528% | SR15_DWA_SRE | 1.106% | SR15_CMP_PLAN | 1.783% | SR21_SS | 2.308%
511544 | ESD Integrated Wedge Holding Line Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU |  | 2021-05-01 |  | 2027-03-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72 | 0 | 0 | 0.72 | 0 | 0 | 0 | 0 | 0.72 | 306661.32 | [5 empty] | N | CM_M&G | 100%
511543 | ESD Transformation Factory Conveyor Belt Holding Line Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU |  | 2021-05-01 |  | 2027-03-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250172.5 | 250172.5 | -250171.5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 306661.32 | [5 empty] | N | CM_M&G | 100%
510226 | Eskdalemuir WwTW Septic Tank and Outfall Replacement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-12-08 | 2024-08-27 | 2024-11-22 | 2025-07-17 | 2025-07-18 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8167 | 8167 | 391833.38 | 0 | 0 | 400000.38 | 0 | 0 | 0 | 0 | 400000.38 | 0 | [5 empty] | N | SR21_WW | 100%
502277 | Establishing Business Alarms within Situational Awareness | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-12-18 | 2018-12-18 | 2019-01-03 | 2019-07-29 |  | Scottish Water Wide | 0 | 0 | 0 | 126533.47 | 15374.53 | 25967 | -151.71 | 0 | 167723.29 | 0 | 0 | 0 | 167723.29 | 0 | 0 | 0 | 0 | 167723.29 | 613322.63 | [5 empty] | N | CM_WSNI | 50% | CM_WWNI | 50%
502950 | European Games 2018 South Calder | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2018-05-15 | 2018-05-15 | 2018-05-17 | 2019-02-27 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 473670.51 | 1520.69 | 8424.8 | 483616 | 659.68 | 0 | 0 | 484275.68 | 0 | 0 | 0 | 0 | 484275.68 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508527 | E-W-01092020-CAIRNHIGH VALVE METER HOUSE (7071) -REPLACEMENT OF MH COVERS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2020-10-09 |  | 2021-02-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3894.8 | 3894.8 | 0 | 0 | 0 | 3894.8 | 0 | 0 | 0 | 0 | 3894.8 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507063 | E-W-050620-Glenfarg WTW-PAC Dosing Plant-128 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-06-17 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2155.97 | 2155.97 | 0 | 0 | 0 | 2155.97 | 0 | 0 | 0 | 0 | 2155.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512246 | E-W-070421-Glenfarg WTW - Replace RGF Upwash actuator (6503) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995.02 | 0 | 0 | 2995.02 | 0 | 0 | 0 | 0 | 2995.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511748 | E-W-110321- GLENLATTERACH WTW 1950 NJ201547 - Investigation only for installation of clarifier cones | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-11 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490.65 | 490.65 | 6428.58 | 0 | 0 | 6919.23 | 0 | 0 | 0 | 0 | 6919.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508718 | E-W-140920-Kirbister WTW - sludge press service and installation of additional plates (6246) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354.45 | 1354.45 | 19349.34 | 0 | 0 | 20703.79 | 0 | 0 | 0 | 0 | 20703.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507893 | E-W-270220-Whitehillocks RGF 6 Replacement Turbidity Monitor (6854) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-08-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5313.5 | 5313.5 | 0 | 0 | 0 | 5313.5 | 0 | 0 | 0 | 0 | 5313.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508459 | E-W-300820-Killiecrankie WTW - Chlorinator Obsolescence - (6878) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7486.85 | 7486.85 | 0 | 0 | 0 | 7486.85 | 0 | 0 | 0 | 0 | 7486.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504261 | E-WE-NI-09122019-Perth RWI - Backwash Pump Replacement(5264) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-02-14 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 2086.6 | 0 | 2086.6 | 0 | 0 | 0 | 2086.6 | 0 | 0 | 0 | 0 | 2086.6 | 119022.58 | [5 empty] | N | CM_WSI | 100%
506932 | E-W-I-010620-Crathie WSZ - AC Mains Replacement (7040) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-06-15 | 2021-06-18 | 2021-11-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12055 | 12055 | 46802.09 | 0 | 0 | 58857.09 | 0 | 0 | 0 | 0 | 58857.09 | 311236.79 | [5 empty] | N | WSI | 100%
510119 | E-W-I-031220-Clatto Raw Water Leak | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-04-12 | 2021-04-12 | 2021-05-04 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512191 | E-W-I-060421-Marykirk DMA - Slip Lining 4 in AC Main - (6936) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-06 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10677.52 | 0 | 0 | 10677.52 | 0 | 0 | 0 | 0 | 10677.52 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507589 | E-W-I-080720-Banff DMA-mains diversion Institution Terrace | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-07-20 | 2020-10-26 | 2020-12-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79933.56 | 79933.56 | 0 | 0 | 0 | 79933.56 | 0 | 0 | 0 | 0 | 79933.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509193 | E-W-I-091020-Ballinluig and Dowally DMA - Dalnabo Bridge Main Replacement - (6894) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1986.6 | 1986.6 | 28380 | 0 | 0 | 30366.6 | 0 | 0 | 0 | 0 | 30366.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507142 | E-W-I-110620-Clatto WTW-Cathodic Protection-129 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2164.7 | 2164.7 | 6181.3 | 0 | 0 | 8346 | 0 | 0 | 0 | 0 | 8346 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509209 | E-W-I-121020-Blackfaulds Farm Main Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-06-07 | 2021-09-13 | 2022-04-26 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6012.35 | 6012.35 | 12537.3 | 0 | 0 | 18549.65 | 0 | 0 | 0 | 0 | 18549.65 | 311236.79 | [5 empty] | N | WSI | 100%
505206 | E-W-I-140220-Slainspark DSR-Catterline Pipe renewal(5281) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-19 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 7107.76 | 0 | 7107.76 | 0 | 0 | 0 | 7107.76 | 0 | 0 | 0 | 0 | 7107.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508725 | E-W-I-140920-Alford Meikle Ley DMA - Valve Installation (7038) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-09-18 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305.91 | 305.91 | 4370.18 | 0 | 0 | 4676.09 | 0 | 0 | 0 | 0 | 4676.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505781 | E-W-I-170320-Mosstodloch - Replacement Fire Hydrant (5607) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 6000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506276 | E-W-I-200420-Clatto Simprin Farm RW Leak (6840) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-05-04 | 2020-05-11 | 2020-07-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25406.9 | 25406.9 | 0 | 0 | 0 | 25406.9 | 0 | 0 | 0 | 0 | 25406.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503906 | E-W-I-21112019-Spynie to Forres Trunk Main-Chlorination (5571) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-01-08 |  | 2020-03-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5972.94 | -3983 | 1989.94 | 0 | 0 | 0 | 1989.94 | 0 | 0 | 0 | 0 | 1989.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
512078 | E-W-I-290321-Scone RWI Air-Duct Pipe Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000.04 | 0 | 0 | 500000.04 | 0 | 0 | 0 | 0 | 500000.04 | 119022.58 | [5 empty] | N | CM_WSI | 100%
506412 | E-W-I-300420-Leakage customer complaints-50 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-05-01 |  | 2020-06-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6438.8 | 6438.8 | 0 | 0 | 0 | 6438.8 | 0 | 0 | 0 | 0 | 6438.8 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506409 | E-W-I-300420-Mannofield WOA-maintaining supplies-45 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338.33 | 338.33 | 4833.33 | 0 | 0 | 5171.66 | 0 | 0 | 0 | 0 | 5171.66 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506417 | E-W-I-300420-UITS-51-Tarvit WSZ-UITS-51 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2021-05-01 |  | 2020-06-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6189.35 | 6189.35 | 423.25 | 0 | 0 | 6612.6 | 0 | 0 | 0 | 0 | 6612.6 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510993 | E-WI-NI-010221-Monikie TWS - Engineer Report - (6924) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 7691.05 | 0 | 0 | 8041.05 | 0 | 0 | 0 | 0 | 8041.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506340 | E-W-I-South Esk Overland Hose (6481) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-06-05 | 2020-06-29 | 2020-12-14 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58565.42 | 58565.42 | -1307.35 | 0 | 0 | 57258.07 | 0 | 0 | 0 | 0 | 57258.07 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505528 | E-W-N-040320-Glendevon WTW - Scada Additonal UPS (5290) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-10-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2377.41 | 2377.41 | 0 | 0 | 0 | 2377.41 | 0 | 0 | 0 | 0 | 2377.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504281 | E-W-N-29122019-INVERCANNIE WTW - Refurbishment of Generator Key Components identified as an Issue (6237) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-23 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 9471.93 | -8453.29 | 1018.64 | 14552 | 0 | 0 | 15570.64 | 0 | 0 | 0 | 0 | 15570.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511692 | E-W-NI- 090321- BOARDHOUSE WTW 1989 HY269254 - REPLACE FILTERED WATER ALUM MONITOR (6266) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-09 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883.18 | 883.18 | 12616.82 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 13500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510990 | E-W-NI-00221-KINGSWELLS DSR 1988 - Replace inlet hydrant cover - (7129) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-04-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7489.99 | 7489.99 | 0 | 0 | 0 | 7489.99 | 0 | 0 | 0 | 0 | 7489.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509675 | E-W-NI0-091120-Finmont DSR - Replace Fence (6475) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2020-01-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1583.6 | 1583.6 | 0 | 0 | 0 | 1583.6 | 0 | 0 | 0 | 0 | 1583.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511002 | E-W-NI-010221-Forehill Low RWP - Investigation into pump 3 faults - (7127) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438.54 | 438.54 | 5997.7 | 0 | 0 | 6436.24 | 0 | 0 | 0 | 0 | 6436.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510996 | E-W-NI-010221-Perth WTW - Replacement Hypo Pump - (6923) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4290 | 4290 | 1753.36 | 0 | 0 | 6043.36 | 0 | 0 | 0 | 0 | 6043.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511004 | E-W-NI-010221-Shapinsay WTW (old) - roof replacement (6265) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419.08 | 419.08 | 5719.75 | 0 | 0 | 6138.83 | 0 | 0 | 0 | 0 | 6138.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510997 | E-W-NI-010221-TURRIFF LOW LEVEL DSR - repair Boundary Wall - (7128) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488.2 | 3488.2 | 0 | 0 | 0 | 3488.2 | 0 | 0 | 0 | 0 | 3488.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512159 | E-W-NI-010421-Clatto WTW - Lime Mixing Tank Motor and Gearbox Refurb - (6934) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-01 |  | 2021-07-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2835.28 | 0 | 0 | 2835.28 | 0 | 0 | 0 | 0 | 2835.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512150 | E-W-NI-010421-Inchgarth RWI-Investigations and Repair works-(7143) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-01 |  | 2021-07-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79670.99 | 0 | 0 | 79670.99 | 0 | 0 | 0 | 0 | 79670.99 | 119022.58 | [5 empty] | N | CM_WSI | 100%
512169 | E-W-NI-010421-Mannofield WTW - Modifications to AIR BLOWERS DIFF PRESSURE MONITOR - (7142) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-01 |  | 2021-07-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1645.21 | 0 | 0 | 1645.21 | 0 | 0 | 0 | 0 | 1645.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512178 | E-W-NI-010421-Turriff WTW - Essential CM Additional Scope (7139) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-02 |  | 2021-07-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34849.99 | 0 | 0 | 34849.99 | 0 | 0 | 0 | 0 | 34849.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512152 | E-W-NI-010421-Whitehillocks WTW - Sludge Poly Pump Replacement - (6935) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-01 |  | 2021-07-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3644.97 | 0 | 0 | 3644.97 | 0 | 0 | 0 | 0 | 3644.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506973 | E-W-NI-010620-Perth Hand-held Turbidity Monitors (6844) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-06-29 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2707.34 | 2707.34 | 0 | 0 | 0 | 2707.34 | 0 | 0 | 0 | 0 | 2707.34 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506936 | E-W-NI010620-Rousay School WTW - differential pressure gauge installation (6237) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257.78 | 257.78 | 2967.8 | 0 | 0 | 3225.58 | 0 | 0 | 0 | 0 | 3225.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508528 | E-W-NI-010920- Lintrathen Rotork Valve Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-09-17 | 2021-03-29 | 2021-11-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12096.44 | 12096.44 | 23989.28 | 0 | 0 | 36085.72 | 0 | 0 | 0 | 0 | 36085.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508525 | E-W-NI-010920-Whitehillocks-Sludge Thickener Tank 2 Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-11-10 | 2020-12-01 | 2021-01-18 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40169.4 | 40169.4 | 0 | 0 | 0 | 40169.4 | 0 | 0 | 0 | 0 | 40169.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509053 | E-W-NI-011020-GLENFARG WTW 1984 - OFF SITE ACCESS ROAD (6466) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-05 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19512.41 | 19512.41 | 0 | 0 | 0 | 19512.41 | 0 | 0 | 0 | 0 | 19512.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509066 | E-W-NI-011020-Whitehillocks WTW - RGF 3 Outlet Valve Replacement- (6889) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297.71 | 297.71 | 4253 | 0 | 0 | 4550.71 | 0 | 0 | 0 | 0 | 4550.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505732 | E-W-NI0-160320-Whitehillocks Inlet Screens Investigation (5300) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5350 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505485 | E-W-NI-020320-Mannofield WTW - RGF 6 Repair (5914) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-10 |  | 2020-09-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 306.6 | 4417.41 | 4724.01 | 0 | 0 | 0 | 4724.01 | 0 | 0 | 0 | 0 | 4724.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512173 | E-W-NI-020421-Herricks WTW - PLCs Telemetry Watchdogs (6696) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-02 |  | 2021-07-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6860.91 | 0 | 0 | 6860.91 | 0 | 0 | 0 | 0 | 6860.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512176 | E-W-NI-020421-Mannofield WTW - GENERATOR 2 install a new intelligent charger with new GEL battery installation - (7141) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-02 |  | 2021-07-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20134.03 | 0 | 0 | 20134.03 | 0 | 0 | 0 | 0 | 20134.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506970 | E-W-NI-020620-Badentinan wtw-Borehole Control Valves-115 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-08-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3755.2 | 3755.2 | 242.86 | 0 | 0 | 3998.06 | 0 | 0 | 0 | 0 | 3998.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506956 | E-W-NI-020620-KINGSEAT TWP NT125903-Pump Replacement-111 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-06-08 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3178.1 | 3178.1 | 0 | 0 | 0 | 3178.1 | 0 | 0 | 0 | 0 | 3178.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506975 | E-W-NI-020620-Mannofield WTW - Repair Potholes on Site Access Road (5924) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-29 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4882.26 | 4882.26 | 0 | 0 | 0 | 4882.26 | 0 | 0 | 0 | 0 | 4882.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506960 | E-W-NI-020620-Skerries WTW-Chemical Waste Tank Pump-112 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-10 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268.4 | 1268.4 | 0 | 0 | 0 | 1268.4 | 0 | 0 | 0 | 0 | 1268.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506955 | E-W-NI-020620-spey GWS-Mechanical Assistance Flow-110 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270.91 | 270.91 | 3727.15 | 0 | 0 | 3998.06 | 0 | 0 | 0 | 0 | 3998.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506961 | E-W-NI-020620-Turriff WTW-Repair Flow Meter-113 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-07-20 |  | 2021-02-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6211.17 | 6211.17 | 361.84 | 0 | 0 | 6573.01 | 0 | 0 | 0 | 0 | 6573.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506964 | E-W-NI-020620-turriff wtw-Repair Service Water Pipe Repair-114 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-07-20 |  | 2021-02-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2525.76 | 2525.76 | 0 | 0 | 0 | 2525.76 | 0 | 0 | 0 | 0 | 2525.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506947 | E-W-NI020620-Whalsay Water Treatment Works-remoneralsiation Vessel Modification-109 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-06 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3980.12 | 3980.12 | 0 | 0 | 0 | 3980.12 | 0 | 0 | 0 | 0 | 3980.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511118 | E-W-NI-020821-Craighead WTW - WQ Monitors (5570) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3179.44 | 3179.44 | 45420.55 | 0 | 0 | 48599.99 | 0 | 0 | 0 | 0 | 48599.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508544 | E-W-NI-02092020-TURRIFF WTW-THICKENED SLUDGE PUMP 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2544.89 | 2544.89 | 0 | 0 | 0 | 2544.89 | 0 | 0 | 0 | 0 | 2544.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508550 | E-W-NI-02092020-WALLS DSR-REPLACE ROTTEN DOOR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2862.4 | 2862.4 | 295.99 | 0 | 0 | 3158.39 | 0 | 0 | 0 | 0 | 3158.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509090 | E-W-NI-021020-Herricks WTW - FW Turbidity Meter (6662) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4264.51 | 4264.51 | 0 | 0 | 0 | 4264.51 | 0 | 0 | 0 | 0 | 4264.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509088 | E-W-NI-021020-LOCHANDIGHTER DSR 1962 - Clochandighter chamber cover Valve chamber cover requires replacement (7089) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-04 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4464.96 | 4464.96 | 0 | 0 | 0 | 4464.96 | 0 | 0 | 0 | 0 | 4464.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509574 | E-W-NI-0211202-TURRIFF MUIRESK RWP 1971 - Radio comms replacement - (7099) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-03-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372.06 | 372.06 | 5315.08 | 0 | 0 | 5687.14 | 0 | 0 | 0 | 0 | 5687.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509576 | E-W-NI-021120-Glenlatterach WTW - Safe Access to Chemical Dosing Chambers (6671) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5291.14 | 5291.14 | 0 | 0 | 0 | 5291.14 | 0 | 0 | 0 | 0 | 5291.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509569 | E-W-NI-021120-River Earn RWP - Arc Flash Study (6473) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 420 | 6000 | 0 | 0 | 6420 | 0 | 0 | 0 | 0 | 6420 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509572 | E-W-NI-021120-Sanday WTW-critical PLC spares (6254) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2020-09-12 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6809.75 | 6809.75 | 0 | 0 | 0 | 6809.75 | 0 | 0 | 0 | 0 | 6809.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504101 | E-W-NI-02122019 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-01-08 |  | 2020-11-10 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 27778.95 | 4985 | 32763.95 | -680 | 0 | 0 | 32083.95 | 0 | 0 | 0 | 0 | 32083.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504099 | E-W-NI02122019-CONICAVEL DSR 1994 NH992526-Replace Dupline Analog Transmitter(5580) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1248.78 | -1114.48 | 134.3 | 1918.53 | 0 | 0 | 2052.83 | 0 | 0 | 0 | 0 | 2052.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504090 | E-W-NI-02122019-HERRICKS WTW 1970 NJ458494-005000214085 DAF TANK B Replacement Rotork(5579) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2236.18 | 1439.81 | 3675.99 | 0 | 0 | 0 | 3675.99 | 0 | 0 | 0 | 0 | 3675.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504107 | E-W-NI-02122019-HERRICKS WTW-Replace Pac Dosing Pump A(5581) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1082.26 | -965.87 | 116.39 | 1662.7 | 0 | 0 | 1779.09 | 0 | 0 | 0 | 0 | 1779.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504088 | E-W-NI-02122019-KIRBISTER RWI 1962 HY369073-land purchase(5034) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-01-08 |  | 2020-09-03 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 16115.06 | 16 | 16131.05 | -29.9 | 0 | 0 | 16101.15 | 0 | 0 | 0 | 0 | 16101.15 | 119022.58 | [5 empty] | N | CM_WSI | 100%
504114 | E-W-NI-03022019-TOMNAVOULIN WTW-Raised Platform for ULTRA MEMBRANE(5583) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-01-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1712 | 0 | 1712 | 0 | 0 | 0 | 1712 | 0 | 0 | 0 | 0 | 1712 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504983 | E-W-NI-030220-Boardhouse WTW-Alum Auger replacement (5051) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-05-18 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 8159.17 | 3017.78 | 11176.95 | 0 | 0 | 0 | 11176.95 | 0 | 0 | 0 | 0 | 11176.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504990 | E-W-NI-030220-Glenlatterach WTW - Treated / Filter HMI (5605) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5630.88 | 0 | 5630.88 | 0 | 0 | 0 | 5630.88 | 0 | 0 | 0 | 0 | 5630.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504988 | E-W-NI-030220-Skerries WTW - Code changes for auto shutdown improvement (5048) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1132.21 | -1030.74 | 101.47 | 1449.5 | 0 | 0 | 1550.97 | 0 | 0 | 0 | 0 | 1550.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504984 | E-W-NI-030220-Westray WTW - Storm Damage - Intake flood light replacement (5050) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-05 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1477.49 | 0 | 1477.49 | 0 | 0 | 0 | 1477.49 | 0 | 0 | 0 | 0 | 1477.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511048 | E-W-NI-030221-Mannofield WTW-Automate Existing Poly Batching System | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-16 | 2021-05-21 | 2022-01-03 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5119.16 | 5119.16 | 75130.84 | 0 | 0 | 80250 | 0 | 0 | 0 | 0 | 80250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511038 | E-W-NI-030221-Whitehillocks WTW - Road Repairs - (6925) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 7000 | 490 | 0 | 0 | 7490 | 0 | 0 | 0 | 0 | 7490 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505508 | E-W-NI-030320-Glendevon WTW- Wash Water outlet actuator boxed spare (5287) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-19 |  | 2020-05-19 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4356.24 | 4356.24 | 0 | 0 | 0 | 4356.24 | 0 | 0 | 0 | 0 | 4356.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505510 | E-W-NI-030320-GLENDEVON WTW-RGF spare Rotork actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-05-05 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3271.2 | 3271.2 | 229.84 | 0 | 0 | 3501.04 | 0 | 0 | 0 | 0 | 3501.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506083 | E-W-NI-030420-Spey Wellfield-Borehole Pump Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-04-22 | 2020-10-12 | 2020-12-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212989.75 | 212989.75 | 0 | 0 | 0 | 212989.75 | 0 | 0 | 0 | 0 | 212989.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507005 | E-W-NI-030620-Castlehill pumping station-measuring weir-118 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6366.5 | 6366.5 | 0 | 0 | 0 | 6366.5 | 0 | 0 | 0 | 0 | 6366.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507021 | E-W-NI-030620-GLENDEVON WTW-BACKWASH WATER INLET VALVE NO5-119 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 842.73 | 842.73 | 12039.01 | 0 | 0 | 12881.74 | 0 | 0 | 0 | 0 | 12881.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507025 | E-W-NI-030620-Glendevon wtw-sulphuric acid dosing pump A-120 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-08 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3435.03 | 3435.03 | 0 | 0 | 0 | 3435.03 | 0 | 0 | 0 | 0 | 3435.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507001 | E-W-NI-030620-Mid Dods Farm Forfar DD8 2RX-Termanal Hydrant-116 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 597.82 | 597.82 | 1542.18 | 0 | 0 | 2140 | 0 | 0 | 0 | 0 | 2140 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507000 | E-W-NI-030620-Recraigs DSR-REDCRAIGS DSR 1905 NT074926-117 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-20 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5002.15 | 5002.15 | 0 | 0 | 0 | 5002.15 | 0 | 0 | 0 | 0 | 5002.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508008 | E-W-NI-030820-Forehill WTW - Install Autosampler (5902) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-03-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10396.91 | 10396.91 | 0 | 0 | 0 | 10396.91 | 0 | 0 | 0 | 0 | 10396.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508006 | E-W-NI-030820-Forehill WTW - SITE SERVICE WATER PUMP (DUTY) (7063) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-21 |  | 2020-09-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4453.93 | 4453.93 | 0 | 0 | 0 | 4453.93 | 0 | 0 | 0 | 0 | 4453.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508001 | E-W-NI-030820-Glenfarg WTW - S/n turbidity monitor replacement (6447) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662.72 | 662.72 | 8895.59 | 0 | 0 | 9558.31 | 0 | 0 | 0 | 0 | 9558.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507998 | E-W-NI-030820-Killiecrankie Dirty Washwater Tank Mixer Replacement (6865) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-21 |  | 2020-09-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3348.36 | 3348.36 | 0 | 0 | 0 | 3348.36 | 0 | 0 | 0 | 0 | 3348.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507995 | E-W-NI-030820-Perth Muirhall Damage to Sewer by Water Main (6861) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-10-09 |  | 2020-08-18 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272 | 1272 | 0 | 0 | 0 | 1272 | 0 | 0 | 0 | 0 | 1272 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507997 | E-W-NI-030820-Perth Sulphuric Acid Sump Pump Replacement (6866) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-09-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354 | 1354 | 0 | 0 | 0 | 1354 | 0 | 0 | 0 | 0 | 1354 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508003 | E-W-NI-030820-Pourie DSR Ladder Replacement with Stairs (6858) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6540 | 6540 | 457.8 | 0 | 0 | 6997.8 | 0 | 0 | 0 | 0 | 6997.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508564 | E-W-NI-03092020-LINTRATHEN WTW-REPLACE RGF OUTLET VALVE | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.5 | 87.5 | 1250 | 0 | 0 | 1337.5 | 0 | 0 | 0 | 0 | 1337.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508570 | E-W-NI-03092020-PANMURE DSR-REPAIR DAMAGE TO SR BUILDING | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4392.07 | 4392.07 | -112.07 | 0 | 0 | 4280 | 0 | 0 | 0 | 0 | 4280 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508566 | E-W-NI-03092020-PERTH WTW-REPLACE 6 TURBIDITY MONITORS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2021-02-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38325.35 | 38325.35 | 194.65 | 0 | 0 | 38520 | 0 | 0 | 0 | 0 | 38520 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509593 | E-W-NI-031120-Badentinan WTW - Safe Access to Generator (6669) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2090.78 | 2090.78 | 0 | 0 | 0 | 2090.78 | 0 | 0 | 0 | 0 | 2090.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509596 | E-W-NI-031120-Braemar WTW - Site MCC replacement parts (7072) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2020-11-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1994.67 | 1994.67 | 2443.34 | 0 | 0 | 4438.01 | 0 | 0 | 0 | 0 | 4438.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509591 | E-W-NI-031120-Craighead WTW - Repairs to Floor (6670) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.2 | 120.2 | 1431.3 | 0 | 0 | 1551.5 | 0 | 0 | 0 | 0 | 1551.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509595 | E-W-NI-031120-Glendevon WTW - Castehill raw water turbidity monitor (6470) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2020-10-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5607.85 | 5607.85 | -55.62 | 0 | 0 | 5552.23 | 0 | 0 | 0 | 0 | 5552.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509598 | E-W-NI-031120-ROCHOMIE DSR 1978 NJ441632 Telemetry - Install level instrument cable via existing ducts & traywork (7069) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-03 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3890.25 | 3890.25 | 0 | 0 | 0 | 3890.25 | 0 | 0 | 0 | 0 | 3890.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509607 | E-W-NI-031120-Spey Wellfield - Flow Checks (5606) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-03 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354.31 | 354.31 | 5061.6 | 0 | 0 | 5415.91 | 0 | 0 | 0 | 0 | 5415.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504120 | E-W-NI-03122019-BADENTINAN WTW-replacement valve for cell D(5585) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2049.04 | -1828.68 | 220.36 | 3148 | 0 | 0 | 3368.36 | 0 | 0 | 0 | 0 | 3368.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504128 | E-W-NI-03122019-GLENLATTERACH WTW-installation of extraction fan in room(5586) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-07-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 744.33 | 479.25 | 1223.58 | 0 | 0 | 0 | 1223.58 | 0 | 0 | 0 | 0 | 1223.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504131 | E-W-NI-03122019-LINTRATHEN WTW-Refurb Sludge Press(5259) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-04-29 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 7101.87 | 0 | 7101.87 | 0 | 0 | 0 | 7101.87 | 0 | 0 | 0 | 0 | 7101.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504116 | E-W-NI-03122019-SPYNIE DSR 1976-Replace Corroded Covers(5584) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-02-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3696.85 | 0 | 3696.85 | 0 | 0 | 0 | 3696.85 | 0 | 0 | 0 | 0 | 3696.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505004 | E-W-NI-040220-Glenfarg WTW-DAFT Tank 2 Scraper Replace Gearbox(5275) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 4159.51 | 0 | 4159.51 | 0 | 0 | 0 | 4159.51 | 0 | 0 | 0 | 0 | 4159.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505012 | E-W-NI-040220-WESTHILLS SERVICE RES-Replace Chloinator Pumps(5276) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1391.5 | 0 | 1391.5 | 0 | 0 | 0 | 1391.5 | 0 | 0 | 0 | 0 | 1391.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505522 | E-W-NI-040320-Glenlatterach WTW - Aluminium Sulphate Dosing Meter B (5609) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-05-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1707.5 | 1707.5 | 0 | 0 | 0 | 1707.5 | 0 | 0 | 0 | 0 | 1707.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505525 | E-W-NI-040320-Lomondhills WTW - Scada additonal UPS (5289) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-10-19 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2377.41 | 2377.41 | 0 | 0 | 0 | 2377.41 | 0 | 0 | 0 | 0 | 2377.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505530 | E-W-NI-040320-Mannofield WTW - Upgrade Faulty Central Heating Panel (5916) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.41 | 37.41 | 9530.53 | 0 | 0 | 9567.94 | 0 | 0 | 0 | 0 | 9567.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506450 | E-W-NI-040520-Clatto WTW-Modify Sump Pump-54 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-06-18 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278.77 | 1278.77 | 0 | 0 | 0 | 1278.77 | 0 | 0 | 0 | 0 | 1278.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506442 | E-W-NI-040520-Herricks WTW-Replace Slide Valve-53 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-06-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2645.04 | 2645.04 | 0 | 0 | 0 | 2645.04 | 0 | 0 | 0 | 0 | 2645.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506455 | E-W-NI-040520-Hill of Tarvit TWS-Repairs to tank-55 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-06-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8132 | 8132 | 0 | 0 | 0 | 8132 | 0 | 0 | 0 | 0 | 8132 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507027 | E-W-NI-040620-Forehill WTW-Lime Canvas-122 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377.96 | 377.96 | 4827.59 | 0 | 0 | 5205.55 | 0 | 0 | 0 | 0 | 5205.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507007 | E-W-NI-040620-Gowersfield DSR-Fife Drought 2020 (covid 123) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-06-05 | 2020-06-10 | 2020-12-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187200.07 | 187200.07 | 0 | 0 | 0 | 187200.07 | 0 | 0 | 0 | 0 | 187200.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504140 | E-W-NI-04122019-Boardhouse WTW Alum pump flow switch enhancement (5035) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-01-25 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1222.91 | 0 | 1222.91 | 0 | 0 | 0 | 1222.91 | 0 | 0 | 0 | 0 | 1222.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504143 | E-W-NI-04122019-GLENDEVON WTW-GLENDEVON MODIFICATION TO 3-STREAM AZTEC(5260) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-05 |  | 2020-06-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2486.44 | 1600.96 | 4087.4 | 0 | 0 | 0 | 4087.4 | 0 | 0 | 0 | 0 | 4087.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504152 | E-W-NI-04122019-GLENLATTERACH WTW-replacement power screw feeders(5587) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-02-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2471.7 | 0 | 2471.7 | 0 | 0 | 0 | 2471.7 | 0 | 0 | 0 | 0 | 2471.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504148 | E-W-NI-04122019-KEMBACK TWP-Replace Pump(5261) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2019-12-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2961.55 | 0 | 2961.55 | 0 | 0 | 0 | 2961.55 | 0 | 0 | 0 | 0 | 2961.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504160 | E-W-NI-04122019-Whitehillocks WTW-replacement alum aztec monitor required(5588) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-07-08 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 13812.54 | 5012.62 | 18825.16 | 0 | 0 | 0 | 18825.16 | 0 | 0 | 0 | 0 | 18825.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510520 | E-W-NI-050121-Glendevon WTW - Standby pH monitor (6486) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1316.1 | 1316.1 | 0 | 0 | 0 | 1316.1 | 0 | 0 | 0 | 0 | 1316.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510524 | E-W-NI-050121-Glenfarg WTW - Spare ortho pump (6482) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-03-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1607.36 | 1607.36 | 0.88 | 0 | 0 | 1608.24 | 0 | 0 | 0 | 0 | 1608.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511070 | E-W-NI-050221-Clatto Media Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4186.05 | 4186.05 | 2995813.95 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505541 | E-W-NI-050320-Ballater WTW - Replace Soda Ash Pump Gearbox (5915) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-05-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1299.98 | 1299.98 | 0 | 0 | 0 | 1299.98 | 0 | 0 | 0 | 0 | 1299.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505554 | E-W-NI-050320-Boardhouse WTW - Generator repair (5054) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26527.4 | 0 | 0 | 26527.4 | 0 | 0 | 0 | 0 | 26527.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505559 | E-W-NI-050320-GLENFARG WTW - Emergency Lighting (5291) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-13 |  | 2020-06-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 349.65 | 4995 | 5344.65 | 0 | 0 | 0 | 5344.65 | 0 | 0 | 0 | 0 | 5344.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506487 | E-W-NI-050520-Forehill WTW Replace Lime Dosing Pumps (7039) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21464.25 | 21464.25 | 0 | 0 | 0 | 21464.25 | 0 | 0 | 0 | 0 | 21464.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506488 | E-W-NI-050520-GLENDEVON WTW-Replacement Pump-57 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-05-20 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4982.33 | 4982.33 | 0 | 0 | 0 | 4982.33 | 0 | 0 | 0 | 0 | 4982.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509101 | E-W-NI-051020-CAIRNBALLOCH DSR outlet main hydrant reinstatment (7076) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344.89 | 344.89 | 4927.01 | 0 | 0 | 5271.9 | 0 | 0 | 0 | 0 | 5271.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509113 | E-W-NI-051020-Gamrie & Pennan DMA - Replace 3 Scour Branch & Hydrant (5913) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525.04 | 525.04 | 7500.53 | 0 | 0 | 8025.57 | 0 | 0 | 0 | 0 | 8025.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509096 | E-W-NI-051020-INVERCANNIE WTW - ICA DOUBLE PANEL WITH HMI Replace HMI and configure (7085) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3953.86 | 3953.86 | 3468.3 | 0 | 0 | 7422.16 | 0 | 0 | 0 | 0 | 7422.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509094 | E-W-NI-051020-INVERCANNIE WTW 1866 - NEUTRALISATION REIRC PH&REDOX MONITOR Installation of fixed access platforms (7088) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-09 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7245.97 | 7245.97 | 0 | 0 | 0 | 7245.97 | 0 | 0 | 0 | 0 | 7245.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509103 | E-W-NI-051020-Turriff WTW - Emergency Generator 1 Maintenance (7058) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328.65 | 328.65 | 4695 | 0 | 0 | 5023.65 | 0 | 0 | 0 | 0 | 5023.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509102 | E-W-NI-051020-Turriff WTW - Emergency Generator 2 Maintenance (7059) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312.03 | 312.03 | 4457.5 | 0 | 0 | 4769.53 | 0 | 0 | 0 | 0 | 4769.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509099 | E-W-NI-051020-Turriff WTW Service water System replacement of existing pump set (7078) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12151.54 | 12151.54 | 165.66 | 0 | 0 | 12317.2 | 0 | 0 | 0 | 0 | 12317.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509649 | E-W-NI-051120-Lintrathen WTW - RGF 4 Butterfly Valve Replacement - (6902) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2020-11-27 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10862.4 | 10862.4 | 0 | 0 | 0 | 10862.4 | 0 | 0 | 0 | 0 | 10862.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504174 | E-W-NI-05122019 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-01-08 |  | 2020-03-04 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 2208.94 | 0 | 2208.94 | 80 | 0 | 0 | 2288.94 | 0 | 0 | 0 | 0 | 2288.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504181 | E-W-NI-05122019-Denfind TWP-Monikie TWS level control system(5262) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 2797.41 | 0 | 2797.41 | -39.75 | 0 | 0 | 2757.66 | 0 | 0 | 0 | 0 | 2757.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504180 | E-W-NI-05122019-KEMBACK TWP-Replace Pump(5261) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1801.57 | -1607.82 | 193.75 | 2767.8 | 0 | 0 | 2961.55 | 0 | 0 | 0 | 0 | 2961.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505589 | E-W-NI-060320-Glenlatterach WTW - Polymer Dosing Pumps (5611) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-10 |  | 2020-09-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 600.68 | 8581.2 | 9181.88 | 0 | 0 | 0 | 9181.88 | 0 | 0 | 0 | 0 | 9181.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505583 | E-W-NI-060320-Papa Stour WTW-GAC vessel replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2021-02-16 | 2021-03-19 | 2021-08-03 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 2239.53 | 40453.47 | 42693 | 86989.81 | 0 | 0 | 129682.81 | 0 | 0 | 0 | 0 | 129682.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505575 | E-W-NI-060320-Skerries WTW-Provision of CO2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-12-18 | 2021-01-14 | 2021-07-16 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 2239.53 | 107295.83 | 109535.36 | 66162.34 | 0 | 0 | 175697.7 | 0 | 0 | 0 | 0 | 175697.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506089 | E-W-NI-060420-Whitehillocks WTW-Inlet Screen Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-04-14 | 2020-06-01 | 2020-07-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174035.22 | 174035.22 | 0 | 0 | 0 | 174035.22 | 0 | 0 | 0 | 0 | 174035.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512223 | E-W-NI-060421-Dykeneuk DSR - Contribution to access repairs. (6508) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-06 |  | 2021-07-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1799.98 | 0 | 0 | 1799.98 | 0 | 0 | 0 | 0 | 1799.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512226 | E-W-NI-060421-Glendevon WTW - Repair sludge Building (6505) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-06 |  | 2021-07-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3650.01 | 0 | 0 | 3650.01 | 0 | 0 | 0 | 0 | 3650.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512197 | E-W-NI-060421-Kirkmichael WTW - Replacement CIP tank thermometer - (6931) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-06 |  | 2021-07-06 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3492.23 | 0 | 0 | 3492.23 | 0 | 0 | 0 | 0 | 3492.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512210 | E-W-NI-060421-Muiresk RWP - Replacement part for Radio Link - (7138) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-06 |  | 2021-07-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4329.99 | 0 | 0 | 4329.99 | 0 | 0 | 0 | 0 | 4329.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512194 | E-W-NI-060421-Nether Strathkinness DSR _ Faulty Inlet FCV (21200) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-06 |  | 2021-07-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5553.03 | 0 | 0 | 5553.03 | 0 | 0 | 0 | 0 | 5553.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506532 | E-W-NI-060520-Badentinan WTW - Neutralisation Pump (6643) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-29 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1792.04 | 1792.04 | 0 | 0 | 0 | 1792.04 | 0 | 0 | 0 | 0 | 1792.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506518 | E-W-NI-060520-Glenfarg WTW-Dual Water Carrier Pipes-58 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-05-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1867.31 | 1867.31 | 0 | 0 | 0 | 1867.31 | 0 | 0 | 0 | 0 | 1867.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506531 | E-W-NI-060520-Invercannie WTW - Sludge Press Control Software (7035) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7115.5 | 7115.5 | 0 | 0 | 0 | 7115.5 | 0 | 0 | 0 | 0 | 7115.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506530 | E-W-NI-060520-Sandy Loch WTW - Ammonia Transfer Pump replacement (6235) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-21 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1457.09 | 1457.09 | 0 | 0 | 0 | 1457.09 | 0 | 0 | 0 | 0 | 1457.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506528 | E-W-NI-060520-Skerries WTW - chemical waste tank pump replacement (6236) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.98 | 82.98 | 1185.45 | 0 | 0 | 1268.43 | 0 | 0 | 0 | 0 | 1268.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507542 | E-W-NI-060720-Lintrathen Alum Pipework Leak (6850) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-19 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573.26 | 1573.26 | 0 | 0 | 0 | 1573.26 | 0 | 0 | 0 | 0 | 1573.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507532 | E-W-NI-060720-Perth Building Cladding Repairs (6849) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-13 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117546.27 | 117546.27 | 35297.52 | 0 | 0 | 152843.79 | 0 | 0 | 0 | 0 | 152843.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507538 | E-W-NI-060720-Perth Burghmuir Pump 5 Non-Return Valve (6851) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-13 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 105 | 1500 | 0 | 0 | 1605 | 0 | 0 | 0 | 0 | 1605 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507540 | E-W-NI-060720-Whitehillocks Settled Turbidity Monitor - A (6848) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-27 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2339.81 | 2339.81 | 14.19 | 0 | 0 | 2354 | 0 | 0 | 0 | 0 | 2354 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
509668 | E-W-NI-061120-Boardhouse DMA - Stones of Stenness 2 main replacement (6256) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-18 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12072.09 | 12072.09 | 1500 | 0 | 0 | 13572.09 | 0 | 0 | 0 | 0 | 13572.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509669 | E-W-NI-061120-Lintrathen WTW - Coag Monitors Replacement - (6904) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2021-02-17 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2338.18 | 2338.18 | -37.42 | 0 | 0 | 2300.76 | 0 | 0 | 0 | 0 | 2300.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509671 | E-W-NI-061120-Whitehillocks WTW - Actuator Critical Spare - (6905) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-03-05 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3879.11 | 3879.11 | 671.38 | 0 | 0 | 4550.49 | 0 | 0 | 0 | 0 | 4550.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504223 | E-W-NI-06122019-NEWTYLE DSR-Renew inlet meter(5263) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1637.02 | -1417.64 | 219.38 | 2471.67 | 0 | 0 | 2691.05 | 0 | 0 | 0 | 0 | 2691.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512258 | E-W-NI-070421-Burn of Davidston RWI - Screening Improvements (6680) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2730 | 0 | 0 | 2730 | 0 | 0 | 0 | 0 | 2730 | 119022.58 | [5 empty] | N | CM_WSI | 100%
512238 | E-W-NI-070421-Craighead WTW - Restoration of Emergency Generator (6688) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13655.11 | 0 | 0 | 13655.11 | 0 | 0 | 0 | 0 | 13655.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512240 | E-W-NI-070421-Craigluscar Valve House - Building repairs (6501) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100 | 0 | 0 | 9100 | 0 | 0 | 0 | 0 | 9100 | 306661.32 | [5 empty] | N | CM_M&G | 100%
512251 | E-W-NI-070421-Mannofield WTW - Install intake adjustable weir gate to CLARIFIER 1 - (7136) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3237.5 | 0 | 0 | 3237.5 | 0 | 0 | 0 | 0 | 3237.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507552 | E-W-NI-070720-Boardhouse TWP - High lift pump 1 VSD replacement (6241) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-10-17 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5149.51 | 5149.51 | 0 | 0 | 0 | 5149.51 | 0 | 0 | 0 | 0 | 5149.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507556 | E-W-NI-070720-Crathie WTW - Replace Obsolete Solenoid Valves (7055) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-11-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3682.95 | 3682.95 | 0 | 0 | 0 | 3682.95 | 0 | 0 | 0 | 0 | 3682.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507586 | E-W-NI-070720-Forehill WTW - Replacement Generator Breaker (5904) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-07-13 |  | 2021-03-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7957.79 | 7957.79 | 0 | 0 | 0 | 7957.79 | 0 | 0 | 0 | 0 | 7957.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507549 | E-W-NI-070720-H&S Access Issues - Various Sites (6853) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2526.87 | 2526.87 | 0 | 0 | 0 | 2526.87 | 0 | 0 | 0 | 0 | 2526.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507559 | E-W-NI-070720-Mannofield WTW - Install Interlock on Gas Boiler (7056) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900.15 | 1900.15 | 0 | 0 | 0 | 1900.15 | 0 | 0 | 0 | 0 | 1900.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507560 | E-W-NI-070720-West Burrafirth CWT - Building maintenance (5068) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441.82 | 441.82 | 6311.66 | 0 | 0 | 6753.48 | 0 | 0 | 0 | 0 | 6753.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508620 | E-W-NI-070920-Forehill WTW - Install LIME DOSING HOPPER AIR CONVEYOR BLOWER (7070) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280.38 | 5280.38 | 0 | 0 | 0 | 5280.38 | 0 | 0 | 0 | 0 | 5280.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508603 | E-W-NI-070920-Kinloch Rannoch WTW- Soakaway Drain Replacement (6881) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-11 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5983.44 | 5983.44 | 0 | 0 | 0 | 5983.44 | 0 | 0 | 0 | 0 | 5983.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508606 | E-W-NI-070920-TURRIFF TWP pump sump replace (7077) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037.36 | 2037.36 | 2165.47 | 0 | 0 | 4202.83 | 0 | 0 | 0 | 0 | 4202.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509151 | E-W-NI-071020-FOREHILL WTW 1965 - PRIMARY ELECTROCHLORINATION PLANT - (7090) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16495.12 | 16495.12 | 0 | 0 | 0 | 16495.12 | 0 | 0 | 0 | 0 | 16495.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509150 | E-W-NI-071020-Gowerfield DSR - Installation of Hydrant to allow extension in to Forth Valley - (6468) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-07 |  | 2021-02-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1954.45 | 1954.45 | 361.03 | 0 | 0 | 2315.48 | 0 | 0 | 0 | 0 | 2315.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510182 | E-W-NI-071220-Ballinluig TWS - Ball Valve Replacement - (6913) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-18 |  | 2021-02-26 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2803.4 | 2803.4 | 0 | 0 | 0 | 2803.4 | 0 | 0 | 0 | 0 | 2803.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510190 | E-W-NI-071220-Glendevon - New press curtains (6480) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252.7 | 252.7 | 3610.02 | 0 | 0 | 3862.72 | 0 | 0 | 0 | 0 | 3862.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510191 | E-W-NI-071220-GLENLATTERACH WTW - FILTERED LIME TANK leak - (6676) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2829.03 | 2829.03 | 0 | 0 | 0 | 2829.03 | 0 | 0 | 0 | 0 | 2829.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510176 | E-W-NI-071220-Kirbister WTW - control room window replacement (6263) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1598.41 | 1598.41 | 0 | 0 | 0 | 1598.41 | 0 | 0 | 0 | 0 | 1598.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510189 | E-W-NI-071220-Lomondhills WTW - Sulphuric Acid Pipework (6479) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-18 |  | 2021-03-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4009.36 | 4009.36 | 18.09 | 0 | 0 | 4027.45 | 0 | 0 | 0 | 0 | 4027.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510174 | E-W-NI-071220-Pipelands DSR - Scour outlet drain repair (6841) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12341.75 | 12341.75 | 9058.23 | 0 | 0 | 21399.98 | 0 | 0 | 0 | 0 | 21399.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510193 | E-W-NI-071220-Sanday WTW - Alum Dosing pump 1 replacement (6259) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-18 |  | 2021-02-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1432.81 | 1432.81 | 284.25 | 0 | 0 | 1717.06 | 0 | 0 | 0 | 0 | 1717.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510221 | E-W-NI-071220-Sanday WTW - Supernatant chlorine and pH monitor replacement (6260) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-18 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4815.44 | 4815.44 | 2226.33 | 0 | 0 | 7041.77 | 0 | 0 | 0 | 0 | 7041.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510192 | E-W-NI-071220-Stromness DSR - perimeter fence repair (6258) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5360.11 | 5360.11 | 4406.14 | 0 | 0 | 9766.25 | 0 | 0 | 0 | 0 | 9766.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504573 | E-W-NI-08012020-FOREHILL WTW - Replacement UPS Batteries (6238) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-13 |  | 2020-01-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5414.41 | 0 | 5414.41 | 0 | 0 | 0 | 5414.41 | 0 | 0 | 0 | 0 | 5414.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504568 | E-W-NI-08012020-MANNOFIELD TWP 2 1986 NJ916041-Replace 005000203807 MOTOR CONTROL CENTRE (6238) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 30182.97 | 33096.33 | 63279.3 | 1082.42 | 0 | 0 | 64361.72 | 0 | 0 | 0 | 0 | 64361.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510638 | E-W-NI-08012021-Craighead WTW - DAF Tank Scraper Guards (6681) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168.82 | 168.82 | 2125.8 | 0 | 0 | 2294.62 | 0 | 0 | 0 | 0 | 2294.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510587 | E-W-NI-080120-Glenfarg WTW - Spare main poly pump (6488) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5721.87 | 5721.87 | -398.87 | 0 | 0 | 5323 | 0 | 0 | 0 | 0 | 5323 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510584 | E-W-NI-080120-TURRIFF WTW 1970 - Aluminium Sulphate Tanks install of Automated outlet valves - (7117) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4956 | 4956 | -339.44 | 0 | 0 | 4616.56 | 0 | 0 | 0 | 0 | 4616.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511114 | E-W-NI-080221- Loch Lee DIR - Handrail and Safety Cover - (6927) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-03-16 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3280 | 3280 | 229.6 | 0 | 0 | 3509.6 | 0 | 0 | 0 | 0 | 3509.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511091 | E-W-NI-080221-Glenlatterach WTW - Clarified Water Turbidity Monitor (6685) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4408.53 | 4408.53 | 3867.13 | 0 | 0 | 8275.66 | 0 | 0 | 0 | 0 | 8275.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511084 | E-W-NI-080221-MANNOFIELD TWP 2 1986 - PITFODELS PUMP ABB heater install - (7130) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555.24 | 555.24 | 7932 | 0 | 0 | 8487.24 | 0 | 0 | 0 | 0 | 8487.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511088 | E-W-NI-080221-Perth RWI - Security Fencing - (6922) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-08 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498.04 | 498.04 | 7114.8 | 0 | 0 | 7612.84 | 0 | 0 | 0 | 0 | 7612.84 | 119022.58 | [5 empty] | N | CM_WSI | 100%
508643 | E-W-NI-080920-Newport DSR - Replace sample tap (6456) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357.77 | 357.77 | 5111 | 0 | 0 | 5468.77 | 0 | 0 | 0 | 0 | 5468.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508635 | E-W-NI-080920-Tayport DSR - Replace sample tap (6455) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-23 |  | 2021-03-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7632.96 | 7632.96 | 0 | 0 | 0 | 7632.96 | 0 | 0 | 0 | 0 | 7632.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508641 | E-W-NI-080920-Turriff WTW UV - Provision of Critical Spares (7078) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-23 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18085.25 | 18085.25 | 0 | 0 | 0 | 18085.25 | 0 | 0 | 0 | 0 | 18085.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509161 | E-W-NI-081020-Muirhead TWS - Building Repairs - (6872) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10931.02 | 10931.02 | 21168.98 | 0 | 0 | 32100 | 0 | 0 | 0 | 0 | 32100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504586 | E-W-NI-09012020-GLENDEVON WTW-Glendevon source inlet valve actuator (6242) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-13 |  | 2020-04-02 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 4034.7 | 0 | 4034.7 | 0 | 0 | 0 | 4034.7 | 0 | 0 | 0 | 0 | 4034.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504583 | E-W-NI-09012020-INVERCANNIE WTW-GLENFARG WTW-ALUM DOSING PUMP A (6241) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-13 |  | 2020-02-07 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 3053.71 | 0 | 3053.71 | 0 | 0 | 0 | 3053.71 | 0 | 0 | 0 | 0 | 3053.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504579 | E-W-NI-09012020-INVERCANNIE WTW-Investigation Hermetically sealed Transformers refurbishment (6240) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-13 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2802.94 | 1851.56 | 4654.5 | 0 | 0 | 0 | 4654.5 | 0 | 0 | 0 | 0 | 4654.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505609 | E-W-NI-090320-Invercannie WTW - Replace Sludge Press Cloths (5926)- | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-05-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10862.45 | 10862.45 | 0 | 0 | 0 | 10862.45 | 0 | 0 | 0 | 0 | 10862.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511688 | E-W-NI-090321- BADENTINAN WTW 1994 NJ282568 - REPLACE LID TO LIME ACCESS CHAMBER | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-09 |  | 2021-06-09 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1800 | 0 | 0 | 1937.38 | 0 | 0 | 0 | 0 | 1937.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511694 | E-W-NI-090321- KIRBISTER WTW 1963 HY368071 - final water alum monitor replacement (6268) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-09 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883.18 | 883.18 | 12616.82 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 13500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511691 | E-W-NI-090321- KIRBISTER WTW 1963 HY368071 - inlet pump 2 replacement (6267) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-09 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 444.86 | 444.86 | 5828.58 | 0 | 0 | 6273.44 | 0 | 0 | 0 | 0 | 6273.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507100 | E-W-NI-090620-Sandness DSR-Control Building Door-125 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2021-02-10 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2726.58 | 2726.58 | 979.09 | 0 | 0 | 3705.67 | 0 | 0 | 0 | 0 | 3705.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508686 | E-W-NI-090920-Mannofield WTW - Replace TWP 4 VSD (7079) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-09-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7608.77 | 7608.77 | 0 | 0 | 0 | 7608.77 | 0 | 0 | 0 | 0 | 7608.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509197 | E-W-NI-091020-ARNAGE SCHOOL TWP NJ974357 -New Pump set - (7092) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9413.66 | 9413.66 | 142.54 | 0 | 0 | 9556.2 | 0 | 0 | 0 | 0 | 9556.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509194 | E-W-NI-091020-Glenlatterach WTW - Lime Compressor (6663)) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5018.3 | 5018.3 | 0 | 0 | 0 | 5018.3 | 0 | 0 | 0 | 0 | 5018.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509195 | E-W-NI-091020-Sanday WTW - dirty washwater tank desludge pumps replacement (6252) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228.97 | 228.97 | 3271 | 0 | 0 | 3499.97 | 0 | 0 | 0 | 0 | 3499.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509198 | E-W-NI-091020-South Hoy WTW - chlorine and pH monitor replacement (6250) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168.14 | 168.14 | 2401.98 | 0 | 0 | 2570.12 | 0 | 0 | 0 | 0 | 2570.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509199 | E-W-NI-091020-South Hoy WTW - Recycle pump critical spare (6251) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-10-23 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1362.67 | 1362.67 | 0 | 0 | 0 | 1362.67 | 0 | 0 | 0 | 0 | 1362.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509182 | E-W-NI-091020-Turriff WTW-Install Clarifier Monitoring for Turbidity and Flow (SPG15) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW0 |  | 2021-10-11 | 2021-11-19 | 2022-07-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 1050 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 1050 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509678 | E-W-NI-091120-Clatto WTW - Outdoor Light Repair - (6896) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 168 | 2400 | 0 | 0 | 2568 | 0 | 0 | 0 | 0 | 2568 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509677 | E-W-NI-091120-Craighead WTW - Alum Dosing Shutdown Facility (6666) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-03-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1363.18 | 1363.18 | 0 | 0 | 0 | 1363.18 | 0 | 0 | 0 | 0 | 1363.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509676 | E-W-NI-091120-Eela Water WTW - motor and gearbox replacement for sludge thickener B (6255) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246.51 | 246.51 | 3521.62 | 0 | 0 | 3768.13 | 0 | 0 | 0 | 0 | 3768.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504244 | E-W-NI-09122019-Glenlatterach WTW-Relocation of Settled Water Sample Point (5590) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 821.44 | -733.1 | 88.34 | 1262 | 0 | 0 | 1350.34 | 0 | 0 | 0 | 0 | 1350.34 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504240 | E-W-NI-09122019-Tomnavoulin WTW-Roof Repairs (4022) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-06-23 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 2754.41 | 1441.81 | 4196.22 | 0 | 0 | 0 | 4196.22 | 0 | 0 | 0 | 0 | 4196.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504603 | E-W-NI-10012020-Boardhouse WTW - interstage pump motor replacement (5039) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-02-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1006.69 | 0 | 1006.69 | 214.92 | 0 | 0 | 1221.61 | 0 | 0 | 0 | 0 | 1221.61 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504600 | E-W-NI-10012020-FOREHILL WTW-005000333071 INITIAL LIME DOSE PUMP (6244) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6330.12 | 0 | 0 | 6330.12 | 0 | 0 | 0 | 0 | 6330.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504594 | E-W-NI-10012020-FOREHILL WTW-Replace 005000333076 FINAL LIME DOSE PUMP (6243) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-13 |  | 2020-02-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 8855.8 | 0 | 8855.8 | 0 | 0 | 0 | 8855.8 | 0 | 0 | 0 | 0 | 8855.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505124 | E-W-NI-100220-Glenlatterach WTW - Coagulation pH Trial (SPG012) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-02-18 |  | 2020-01-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 4779.79 | 1767.87 | 6547.66 | 0 | 0 | 0 | 6547.66 | 0 | 0 | 0 | 0 | 6547.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505108 | E-W-NI-100220-Invercannie WTW - Replace Coag pH Monitors (SPG003) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 31426.78 | 9611.9 | 41038.68 | 2011.7 | 0 | 0 | 43050.38 | 0 | 0 | 0 | 0 | 43050.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505119 | E-W-NI-100220-Turriff WTW - Install Acid Flush to Improve Coag pH Dosing (SPG007) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 4692.53 | -2340.02 | 2352.51 | 6970.4 | 0 | 0 | 9322.91 | 0 | 0 | 0 | 0 | 9322.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505117 | E-W-NI-100220-Turriff WTW - Install Alum Pump Pulsation Dampers (SPG006) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5350.54 | 1956.3 | 7306.84 | 22.66 | 0 | 0 | 7329.5 | 0 | 0 | 0 | 0 | 7329.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505112 | E-W-NI-100220-Turriff WTW - Install Secondary pH Monitor (SPG004) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 11950.83 | -3471.12 | 8479.71 | 7891.29 | 0 | 0 | 16371 | 0 | 0 | 0 | 0 | 16371 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505115 | E-W-NI-100220-Turriff WTW - Press Repairs (SPG005) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-08-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 14915.89 | 5108.83 | 20024.72 | 0 | 0 | 0 | 20024.72 | 0 | 0 | 0 | 0 | 20024.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505123 | E-W-NI-100220-Turriff WTW - Replace 3Nr. Sludge Air Compressors (SPG008) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 14059.8 | -12799.8 | 1260 | 18000 | 0 | 0 | 19260 | 0 | 0 | 0 | 0 | 19260 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511160 | E-W-NI-100221-Lomondhills WTW - Inlet Valve Actuator (6496) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210.28 | 210.28 | 3004 | 0 | 0 | 3214.28 | 0 | 0 | 0 | 0 | 3214.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511720 | E-W-NI-100321- BLAIRNAMARROW WTW 1964 NJ211154 - REPLACE TRANSMITTER | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-10 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464.49 | 464.49 | 6085.74 | 0 | 0 | 6550.23 | 0 | 0 | 0 | 0 | 6550.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509104 | E-W-NI-100520-Lintrathen SO2 regulator replacement (6835) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17133.5 | 17133.5 | -13.5 | 0 | 0 | 17120 | 0 | 0 | 0 | 0 | 17120 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507618 | E-W-NI-100720-Glenlatterach DIR - R Lossie abstraction - drought prevention (NCSD 132) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-12-18 | 2021-10-01 | 2022-05-16 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9030 | 9030 | 12370.36 | 0 | 0 | 21400.36 | 0 | 0 | 0 | 0 | 21400.36 | 311236.79 | [5 empty] | N | CM_M&G | 100%
508688 | E-W-NI-100920-Aberfeldy DSR - Hypo Pump Replacement - (6882) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082.4 | 1082.4 | 0 | 0 | 0 | 1082.4 | 0 | 0 | 0 | 0 | 1082.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510243 | E-W-NI-101120-Cauldhame DSR - Telemetry Outstation replacement (6261) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-18 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252.7 | 252.7 | 3610.02 | 0 | 0 | 3862.72 | 0 | 0 | 0 | 0 | 3862.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509713 | E-W-NI-101120-Glenfarg WTW - Replacement Polymer dosing (6476) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-03-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6505.77 | 6505.77 | 0.9 | 0 | 0 | 6506.67 | 0 | 0 | 0 | 0 | 6506.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509706 | E-W-NI-101120-Mannofield WTW - Poly Batching Outlet Valve Automation (5843) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2020-11-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3381.67 | 3381.67 | 0 | 0 | 0 | 3381.67 | 0 | 0 | 0 | 0 | 3381.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504285 | E-W-NI-10122019-MONIKIE TWP-Renew PUMP 2(5265) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-23 |  | 2020-02-12 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 13333.83 | 50.87 | 13384.7 | 0 | 0 | 0 | 13384.7 | 0 | 0 | 0 | 0 | 13384.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505105 | E-W-NI-102020-Inchgarth RWP - Automatic Shutdown of RWI on Various Pollution Monitoring Parameters (SPG002) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-11-11 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5872.31 | 2171.95 | 8044.26 | 0 | 0 | 0 | 8044.26 | 0 | 0 | 0 | 0 | 8044.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510658 | E-W-NI-110121-CRAIGHEAD WTW 1974 - Site Roads and Paving improvements - (6682) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.41 | 37.41 | 6723.96 | 0 | 0 | 6761.37 | 0 | 0 | 0 | 0 | 6761.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510629 | E-W-NI-110121-Edintore DIR - Telemetry Integration (6683) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2923.44 | 2923.44 | -4.63 | 0 | 0 | 2918.81 | 0 | 0 | 0 | 0 | 2918.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510725 | E-W-NI-110121-INVERCANNIE WTW 1866 - SLUDGE CONSOL FEED PUMP 1 NRV. - (7116) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483.16 | 483.16 | 6704 | 0 | 0 | 7187.16 | 0 | 0 | 0 | 0 | 7187.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510636 | E-W-NI-110121-Knowehead Borehole - Trial of new turbidity meter (6489) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1171.61 | 1171.61 | -37.41 | 0 | 0 | 1134.2 | 0 | 0 | 0 | 0 | 1134.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506562 | E-W-NI-110520-GLENFARG WTW- Filtration-63 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2716.07 | 2716.07 | 0 | 0 | 0 | 2716.07 | 0 | 0 | 0 | 0 | 2716.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506572 | E-W-NI-110520-Spey Wellfield - Replacement of Borehole Pumps Nos 4 8 and 32 (6635) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-21 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27780.95 | 27780.95 | 0 | 0 | 0 | 27780.95 | 0 | 0 | 0 | 0 | 27780.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507140 | E-W-NI-110620-Unst WTW-Chlorine Probe-130 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-08-20 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2069.81 | 2069.81 | 144.89 | 0 | 0 | 2214.7 | 0 | 0 | 0 | 0 | 2214.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508716 | E-W-NI-110920-Herricks WTW - Lime Dosing Control (6670) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6738.63 | 6738.63 | 0 | 0 | 0 | 6738.63 | 0 | 0 | 0 | 0 | 6738.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510295 | E-W-NI-111220-Blairnamarrow WTW - Ammonium Sulphate Pump (6678) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-18 |  | 2021-03-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422.99 | 1422.99 | 0 | 0 | 0 | 1422.99 | 0 | 0 | 0 | 0 | 1422.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510290 | E-W-NI-111220-ELLON LOW LEVEL TWS NEW 1960 - Installation of staircase with handrails - (7115) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-18 |  | 2021-02-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3855.48 | 3855.48 | 0 | 0 | 0 | 3855.48 | 0 | 0 | 0 | 0 | 3855.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510661 | E-W-NI-120120-TURRIFF WTW 1970 - Ortho pumps replacement and software update - (7118) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4924.85 | 4924.85 | 2093.92 | 0 | 0 | 7018.77 | 0 | 0 | 0 | 0 | 7018.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509204 | E-W-NI-120120-Turriff WTW 1970 -H&S Improvements to improve access - (7094) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-23 |  | 2021-04-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10282.7 | 10282.7 | 0 | 0 | 0 | 10282.7 | 0 | 0 | 0 | 0 | 10282.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510667 | E-W-NI-120121-BEREFOLD DMA - Arnage to Berefold cross connection. - (7111) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1432.03 | 1432.03 | 19923.2 | 0 | 0 | 21355.23 | 0 | 0 | 0 | 0 | 21355.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505153 | E-W-NI-120220-Balbeuchley TWS- Pump 2 replacement(5279) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1670.81 | 0 | 1670.81 | 0 | 0 | 0 | 1670.81 | 0 | 0 | 0 | 0 | 1670.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505156 | E-W-NI-120220-Eela Water WTW - Survey for Clarifier flow control upgrade (5055) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-05-14 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1002.66 | 390.65 | 1393.31 | 0 | 0 | 0 | 1393.31 | 0 | 0 | 0 | 0 | 1393.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511215 | E-W-NI-120221-Forehill WTW - Replace Walkway Roof (7133) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6933.6 | 0 | 0 | 6933.6 | 0 | 0 | 0 | 0 | 6933.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511213 | E-W-NI-120221-Gannochy TSW - PRV Replacement - (6928) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-12 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.7 | 119.7 | 1710 | 0 | 0 | 1829.7 | 0 | 0 | 0 | 0 | 1829.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511220 | E-W-NI-120221-Herricks WTW - Addition of LOH Meters to SCADA (6686) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289.13 | 289.13 | 4130.35 | 0 | 0 | 4419.48 | 0 | 0 | 0 | 0 | 4419.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511842 | E-W-NI-120321- Fetlar WTW - Final water chlorine monitor replacement (6271) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-16 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261.68 | 261.68 | 3428.58 | 0 | 0 | 3690.26 | 0 | 0 | 0 | 0 | 3690.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511840 | E-W-NI-120321- GLENFARG WTW 1984 NO116104 - REPLACE INLET FLASH TANK pH PROBE | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-16 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556.07 | 556.07 | 7285.74 | 0 | 0 | 7841.81 | 0 | 0 | 0 | 0 | 7841.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511844 | E-W-NI-120321- GLENLATTERACH WTW 1950 NJ201547 - INVESTIGATE LIME BATCHING CONTROL REMOVAL | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-16 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2518.6 | 2518.6 | 81.4 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511858 | E-W-NI-120321- TOWNHILL DSR 1984 NT111896 - REPAIR ACCESS ROAD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314.02 | 314.02 | 4114.26 | 0 | 0 | 4428.28 | 0 | 0 | 0 | 0 | 4428.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506579 | E-W-NI-120520-LADYBANK TOWER TWP 1908 NO304103-Replace PUMP NO3-62 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5168.07 | 5168.07 | 0 | 0 | 0 | 5168.07 | 0 | 0 | 0 | 0 | 5168.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506581 | E-W-NI-120520-North Mavine DSR-Installation of bypass valve-65 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1396.94 | 1396.94 | 15921.01 | 0 | 0 | 17317.95 | 0 | 0 | 0 | 0 | 17317.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509230 | E-W-NI-121020-Badentinan WTW - Membrane Control Valves (6650) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10226.02 | 10226.02 | 0 | 0 | 0 | 10226.02 | 0 | 0 | 0 | 0 | 10226.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509227 | E-W-NI-121020-Mannofield WTW - Install Cover on Poly Dosing Pipework (7053) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-10-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1127.51 | 1127.51 | 0 | 0 | 0 | 1127.51 | 0 | 0 | 0 | 0 | 1127.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509754 | E-W-NI-121120-Frandy Burn Intake - fit handrails etc. (6445) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-03-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4132.5 | 4132.5 | 950 | 0 | 0 | 5082.5 | 0 | 0 | 0 | 0 | 5082.5 | 119022.58 | [5 empty] | N | CM_WSI | 100%
509756 | E-W-NI-121120-Frandy Private WTW - Access steps (6446) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-03-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4006.79 | 4006.79 | 875.08 | 0 | 0 | 4881.87 | 0 | 0 | 0 | 0 | 4881.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509757 | E-W-NI-121120-Slateford Burn RWI - H&S needs (6448) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2021-02-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7019.2 | 7019.2 | 0 | 0 | 0 | 7019.2 | 0 | 0 | 0 | 0 | 7019.2 | 119022.58 | [5 empty] | N | CM_WSI | 100%
504336 | E-W-NI-12122019-Boardhouse WTW - Guttering repair and clean (5038) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-23 |  | 2021-02-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 4194.35 | 1281.16 | 5475.51 | 241.53 | 0 | 0 | 5717.04 | 0 | 0 | 0 | 0 | 5717.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504634 | E-W-NI-13012020-Herricks WTW - DAF Feed Pump (5592) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2242.29 | 0 | 0 | 2242.29 | 0 | 0 | 0 | 0 | 2242.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504626 | E-W-NI-13012020-Herricks WTW - Installation of DOC Panels and Debubblers (5527) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 7914.27 | 0 | 7914.27 | 0 | 0 | 0 | 7914.27 | 0 | 0 | 0 | 0 | 7914.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510680 | E-W-NI-130121-MANNOFIELD WTW 1986 - Replace Chemical Dosing MCC UPS - (7121) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11133.63 | 11133.63 | 0 | 0 | 0 | 11133.63 | 0 | 0 | 0 | 0 | 11133.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505713 | E-W-NI-130320-Clatto WTW - RGF 3 & 8 Investigation (4128) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-11-03 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3950 | 3950 | 0 | 0 | 0 | 3950 | 0 | 0 | 0 | 0 | 3950 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505723 | E-W-NI-130320-Kirbister WTW - replace inlet pump 1 (5064) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-25 |  | 2020-11-04 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6110 | 6110 | 716.6 | 0 | 0 | 6826.6 | 0 | 0 | 0 | 0 | 6826.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506602 | E-W-NI-130520-Turriff Muiresk RWP- Pump 1 Replace Mechanical Seal (CV19 32) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-05-21 | 2020-06-15 | 2020-12-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14882.79 | 14882.79 | 0 | 0 | 0 | 14882.79 | 0 | 0 | 0 | 0 | 14882.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507636 | E-W-NI-130720-Badentinan WTW - FW Free Chlorine Probe (6649) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1822.64 | 1822.64 | 0 | 0 | 0 | 1822.64 | 0 | 0 | 0 | 0 | 1822.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507663 | E-W-NI-130720-Mannofield TWP 2 - Repair Pump 3 Motor (7051) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-10-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11850.04 | 11850.04 | 0 | 0 | 0 | 11850.04 | 0 | 0 | 0 | 0 | 11850.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507651 | E-W-NI-130720-Turriff WTW - Install New Poly Dosing Screen (7050) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1942.01 | 1942.01 | 0 | 0 | 0 | 1942.01 | 0 | 0 | 0 | 0 | 1942.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507640 | E-W-NI-130720-Turriff WTW - Remove H&S Risks (7052) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2370.05 | 2370.05 | 0 | 0 | 0 | 2370.05 | 0 | 0 | 0 | 0 | 2370.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508193 | E-W-NI-130820-Slateford Burn RWI - H&S needs (6448) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7019.2 | 0 | 0 | 7019.2 | 0 | 0 | 0 | 0 | 7019.2 | 119022.58 | [5 empty] | N | CM_WSI | 100%
506608 | E-W-NI-140520-Craighead WTW - Upgrade Mn removal - Covid 19 - 66 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW0 |  | 2021-11-08 | 2022-02-04 | 2022-09-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1862 | 1862 | 95137.9 | 0 | 0 | 96999.9 | 0 | 0 | 0 | 0 | 96999.9 | 119022.58 | [5 empty] | N | CM_WSI | 100%
507683 | E-W-NI-140720-Glenfarg WTW - Sludge presses refurbishment (6440) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-16 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7019.2 | 7019.2 | 0 | 0 | 0 | 7019.2 | 0 | 0 | 0 | 0 | 7019.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508735 | E-W-NI-140920-Chapel TWP - Replace level control system (6457) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-09-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4443.71 | 4443.71 | 0 | 0 | 0 | 4443.71 | 0 | 0 | 0 | 0 | 4443.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508746 | E-W-NI-140920-Lintrathen WTW- Supernatent Pump C Replacement(6885) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-10-13 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3980.4 | 3980.4 | 0 | 0 | 0 | 3980.4 | 0 | 0 | 0 | 0 | 3980.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508729 | E-W-NI-140920-Townhill DSR - Replace level control system (6457) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1871.02 | 1871.02 | 0 | 0 | 0 | 1871.02 | 0 | 0 | 0 | 0 | 1871.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510315 | E-W-NI-141220-Boardhouse WTW - Flocculator replacement (6262) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2277.3 | 2277.3 | 420.17 | 0 | 0 | 2697.47 | 0 | 0 | 0 | 0 | 2697.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510306 | E-W-NI-141220-CAIRNTON RWI 1926 - Installation of handrails - (7113) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-18 |  | 2021-04-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2002.06 | 2002.06 | -37.41 | 0 | 0 | 1964.65 | 0 | 0 | 0 | 0 | 1964.65 | 119022.58 | [5 empty] | N | CM_WSI | 100%
510305 | E-W-NI-141220-CAIRNTON RWI 1959 - Installation of handrails - (7114) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1065.93 | 1065.93 | 0 | 0 | 0 | 1065.93 | 0 | 0 | 0 | 0 | 1065.93 | 119022.58 | [5 empty] | N | CM_WSI | 100%
510313 | E-W-NI-141220-Clatto WTW- Raw Colour Monitor Replacement - (6914) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-17 |  | 2021-03-27 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274.52 | 2274.52 | -18.69 | 0 | 0 | 2255.83 | 0 | 0 | 0 | 0 | 2255.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510308 | E-W-NI-141220-MID BELTIE TWP 1980 - Replacement of Telemetry remote terminal unit - (7112) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-18 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8150.78 | 8150.78 | 492.82 | 0 | 0 | 8643.6 | 0 | 0 | 0 | 0 | 8643.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510721 | E-W-NI-150121-Lomondhills WTW - Repair Access Road (6490) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-04-05 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15640.7 | 15640.7 | 0 | 0 | 0 | 15640.7 | 0 | 0 | 0 | 0 | 15640.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511222 | E-W-NI-150221-Glendevon WTW -Sludge building electrical re-fit (6497) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 1050 | 15000 | 0 | 0 | 16050 | 0 | 0 | 0 | 0 | 16050 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511234 | E-W-NI-150221-River Earn RWP - replace battery charging unit (6499) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6559.94 | 6559.94 | -649.94 | 0 | 0 | 5910 | 0 | 0 | 0 | 0 | 5910 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511787 | E-W-NI-150321- BOARDHOUSE WTW 1989 HY269254 - SPMA MA033 - FILTER MEDIA CHEMICAL CLEAN (6269) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-15 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7810.7 | 7810.7 | 89189.31 | 0 | 0 | 97000 | 0 | 0 | 0 | 0 | 97000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506633 | E-W-NI-150520-Clatto WTW-chlorine analyser-70 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248.62 | 1248.62 | 1105.38 | 0 | 0 | 2354 | 0 | 0 | 0 | 0 | 2354 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506646 | E-W-NI-150520-forehill wtw-Actuator Replacement-79 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-10-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3505.53 | 3505.53 | 0 | 0 | 0 | 3505.53 | 0 | 0 | 0 | 0 | 3505.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506643 | E-W-NI-150520-Pitfodels TWP-Actuator Inspection-76 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2272.7 | 2272.7 | 0 | 0 | 0 | 2272.7 | 0 | 0 | 0 | 0 | 2272.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507179 | E-W-NI-150620-Ballater WTW - Replace PACL Dosing Pump A (7049) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2660.07 | 2660.07 | 0 | 0 | 0 | 2660.07 | 0 | 0 | 0 | 0 | 2660.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507182 | E-W-NI-150620-Balmoor RWI - Prevent Unauthorised Access (7041) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-31 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4064.7 | 4064.7 | 0 | 0 | 0 | 4064.7 | 0 | 0 | 0 | 0 | 4064.7 | 119022.58 | [5 empty] | N | CM_WSI | 100%
507204 | E-W-NI-150620-Clatto Main Cathodic Protection (6842) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520.26 | 520.26 | 7146.3 | 0 | 0 | 7666.56 | 0 | 0 | 0 | 0 | 7666.56 | 119022.58 | [5 empty] | N | CM_WSI | 100%
507184 | E-W-NI-150620-Eday WTW - RadioLink Station replacement (6240) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-23 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5884.82 | 5884.82 | 0 | 0 | 0 | 5884.82 | 0 | 0 | 0 | 0 | 5884.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507193 | E-W-NI-150620-Glenlatterach WTW - Polyelectrolyte Unit (5608) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101650 | 0 | 0 | 101650 | 0 | 0 | 0 | 0 | 101650 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507178 | E-W-NI-150620-Invercannie WTW - Adjust PLC to Abort CEB (7048) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3042.22 | 3042.22 | 0 | 0 | 0 | 3042.22 | 0 | 0 | 0 | 0 | 3042.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507188 | E-W-NI-150620-Invercannie WTW - Replace Filtrate Pump VSD Membrane Cells 3 & 4 (7043) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4297.04 | 4297.04 | 0 | 0 | 0 | 4297.04 | 0 | 0 | 0 | 0 | 4297.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507191 | E-W-NI-150620-Invercannie WTW - Replace Sludge Feed Pump 2 VSD (7042) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1690.01 | 1690.01 | 0 | 0 | 0 | 1690.01 | 0 | 0 | 0 | 0 | 1690.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507180 | E-W-NI-150620-Mannofield TWP 1 - Refurb or Replace Corroded Floor Plates (7047) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5643.7 | 5643.7 | 0 | 0 | 0 | 5643.7 | 0 | 0 | 0 | 0 | 5643.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507709 | E-W-NI-150720-Glendevon WTW - Front End dosing POA Trial (6441) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-11-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15384.33 | 15384.33 | 0 | 0 | 0 | 15384.33 | 0 | 0 | 0 | 0 | 15384.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508768 | E-W-NI-150920-Glenfarg WTW - New heaters for sludge building (6459) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2513.43 | 2513.43 | 0 | 0 | 0 | 2513.43 | 0 | 0 | 0 | 0 | 2513.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504351 | E-W-NI-15122019-Glenfarg WTW - PLC1 modifications (5266) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-23 |  | 2020-02-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 4237.2 | 0 | 4237.2 | 0 | 0 | 0 | 4237.2 | 0 | 0 | 0 | 0 | 4237.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504349 | E-W-NI-15122019-Kirbister WTW- uttering repair and clean (5037) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-08-31 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 289.68 | 4428 | 4717.68 | 0 | 0 | 0 | 4717.68 | 0 | 0 | 0 | 0 | 4717.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504350 | E-W-Ni-15122019-Turriff WTW - Contact Steps Repair (5898) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-23 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 6305.62 | -1843.34 | 4462.28 | 5149 | 0 | 0 | 9611.28 | 0 | 0 | 0 | 0 | 9611.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504689 | E-W-NI-16012020-BALCARRES TWP - RADIO OUTSTATION RENEWAL (5250) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 3794.5 | 0 | 3794.5 | -232.93 | 0 | 0 | 3561.57 | 0 | 0 | 0 | 0 | 3561.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504681 | E-W-NI-16012020-Peterhead Newfield TWP Replacement Power Module (5900) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-11 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 7718.87 | 0 | 7718.87 | 0 | 0 | 0 | 7718.87 | 0 | 0 | 0 | 0 | 7718.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511270 | E-W-NI-160221-Inchgarth RWI-Develop Emergency Pumping Plans (7131) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-29 | 2021-08-13 | 2022-03-28 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26125.74 | 26125.74 | 173874.27 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 119022.58 | [5 empty] | N | CM_WSI | 100%
505751 | E-W-NI-160320-Brackans DSR - Tapping to Install Final Monitoring Equipment (5921) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-29 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3022.81 | 3022.81 | 171.57 | 0 | 0 | 3194.38 | 0 | 0 | 0 | 0 | 3194.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505864 | E-W-NI-160320-Craighead WTW-Backwash Pump (5612) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-25 |  | 2020-05-11 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2368.52 | 2368.52 | 105.75 | 0 | 0 | 2474.27 | 0 | 0 | 0 | 0 | 2474.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505748 | E-W-NI-160320-Glendevon WTW - RGF Condition assment (5292) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750 | 4750 | -4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
505758 | E-W-NI-160320-Mannofield WTW - Repair gasket on RGF 5 & 6 Backwash Pipe (5923) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2020-08-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3063.3 | 3063.3 | 214.43 | 0 | 0 | 3277.73 | 0 | 0 | 0 | 0 | 3277.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505757 | E-W-NI-160320-Newmachar Kinmundy TWP - Replace Expansion Joints (5919) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-06-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3350 | 3350 | 0 | 0 | 0 | 3350 | 0 | 0 | 0 | 0 | 3350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505734 | E-W-NI-160320-Whitehillocks drain repairs (5299) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-06-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490 | 2490 | 0 | 0 | 0 | 2490 | 0 | 0 | 0 | 0 | 2490 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505736 | E-W-NI-160320-Whitehillocks sludge press replacement cloths (5302) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-10-22 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2483.41 | 2483.41 | 0 | 0 | 0 | 2483.41 | 0 | 0 | 0 | 0 | 2483.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507207 | E-W-NI-160620-Whitehillocks sludge thickener tank access (6839) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704.7 | 704.7 | 13627.63 | 0 | 0 | 14332.33 | 0 | 0 | 0 | 0 | 14332.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509806 | E-W-NI-161120-Badentinan WTW- Membrane CIP Neutralisation System upgrade (SPG010) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-05-10 | 2021-07-30 | 2022-03-14 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4467 | 4467 | 120533.38 | 0 | 0 | 125000.38 | 0 | 0 | 0 | 0 | 125000.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509810 | E-W-NI-161120-Glenlatterach WTW - Final Lime pH Analyser (6672) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7478.1 | 7478.1 | 0 | 0 | 0 | 7478.1 | 0 | 0 | 0 | 0 | 7478.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509805 | E-W-NI-161120-Lintrathen WTW - Filter Hose Replacement - (6907) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2020-11-27 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1327.16 | 1327.16 | 0 | 0 | 0 | 1327.16 | 0 | 0 | 0 | 0 | 1327.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505761 | E-W-NI-170320-Newmachar Craigie TWP - Roof Replacement (5918) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-25 |  | 2020-05-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13575 | 13575 | -11268.08 | 0 | 0 | 2306.92 | 0 | 0 | 0 | 0 | 2306.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505775 | E-W-NI-170320-Towerhill DSR - re-dash gable wall (5061) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2306.92 | 0 | 0 | 2306.92 | 0 | 0 | 0 | 0 | 2306.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505759 | E-W-NI-170320-Turriff Muiresk RWP - Replace Contactors on MCC No1 (5920) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-25 |  | 2020-04-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 4448.38 | 0 | 4448.38 | 311.39 | 0 | 0 | 4759.77 | 0 | 0 | 0 | 0 | 4759.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508235 | E-W-NI-170820-Frandy Private WTW - Access steps (6446) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4881.88 | 0 | 0 | 4881.88 | 0 | 0 | 0 | 0 | 4881.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508215 | E-W-NI-170820-Glenfarg WTW - Replace obsolete alum monitors (2 No.) (6452) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-21 |  | 2021-03-05 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27594.93 | 27594.93 | 261.45 | 0 | 0 | 27856.38 | 0 | 0 | 0 | 0 | 27856.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508211 | E-W-NI-170820-Invercannie WTW - Replacement of Membrane backwash Chlorine dosing pipework (7065) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-21 |  | 2020-10-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340.74 | 1340.74 | 0 | 0 | 0 | 1340.74 | 0 | 0 | 0 | 0 | 1340.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508225 | E-W-NI-170820-Kemback TWP - Replace pump No. 1 (6451) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-21 |  | 2020-08-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2961.56 | 2961.56 | 0 | 0 | 0 | 2961.56 | 0 | 0 | 0 | 0 | 2961.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508213 | E-W-NI-170820-Locherlour Access Road Maintenance (6867) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3350.98 | 3350.98 | -67.14 | 0 | 0 | 3283.84 | 0 | 0 | 0 | 0 | 3283.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508207 | E-W-NI-170820-Turriff WTW - replacement Rotor & stator for Lime dosing pump No2 (7066) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-21 |  | 2020-09-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700.38 | 3700.38 | 0 | 0 | 0 | 3700.38 | 0 | 0 | 0 | 0 | 3700.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509843 | E-W-NI-171120-Badentinan WTW - Temporary Fuel Storage (6673) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383.91 | 383.91 | -383.92 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | -0.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509841 | E-W-NI-171120-Braemar WTW - SODIUM HYPOCHLORITE PUMP 1 - (7103) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-16 |  | 2021-02-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6602.93 | 6602.93 | -37.42 | 0 | 0 | 6565.51 | 0 | 0 | 0 | 0 | 6565.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510755 | E-W-NI-180121-Boardhouse WTW - replace washwater pump (6264) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4388.8 | 4388.8 | 187.59 | 0 | 0 | 4576.39 | 0 | 0 | 0 | 0 | 4576.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510754 | E-W-NI-180121-ELLON HIGH LEVEL DSR 1977 - H&S Access Improvements - (7123) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700.29 | 3700.29 | 0 | 0 | 0 | 3700.29 | 0 | 0 | 0 | 0 | 3700.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510753 | E-W-NI-180121-Glendevon WTW - Glendevon WTW - Sulphuric Acid Flow switches (6491) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2556.87 | 2556.87 | 0.4 | 0 | 0 | 2557.27 | 0 | 0 | 0 | 0 | 2557.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510733 | E-W-NI-180121-Glendevon WTW - Sulphuric Acid pipework (6493) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-04-04 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1871.53 | 1871.53 | 0.96 | 0 | 0 | 1872.49 | 0 | 0 | 0 | 0 | 1872.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510756 | E-W-NI-180121-Glenfarg WTW - Express water tank extension (6487) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3507.14 | 3507.14 | -37.13 | 0 | 0 | 3470.01 | 0 | 0 | 0 | 0 | 3470.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505259 | E-W-NI-180220-Craighead WTW - Soda Ash Vacuum Unit (5560) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-19 |  | 2020-06-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1498.27 | 554.15 | 2052.42 | 0 | 0 | 0 | 2052.42 | 0 | 0 | 0 | 0 | 2052.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505265 | E-W-NI-180220-Forehill WTW - Replace Access Steps to Poly Dosing Unit (5911) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-19 |  | 2020-07-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1025.69 | 437 | 1462.69 | 0 | 0 | 0 | 1462.69 | 0 | 0 | 0 | 0 | 1462.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505272 | E-W-NI-180220-Invercannie WTW - Install Auto-Desludge Sequence to Thickeners (5908) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-19 |  | 2020-05-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2599.01 | 961.28 | 3560.29 | 0 | 0 | 0 | 3560.29 | 0 | 0 | 0 | 0 | 3560.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505251 | E-W-NI-180220-INVERCANNIE WTW-Kirbister WTW - replace both Sludge Poly dosing pumps (5058) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-30 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 2278.54 | 0 | 2278.54 | 0 | 0 | 0 | 2278.54 | 0 | 0 | 0 | 0 | 2278.54 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505252 | E-W-NI-180220-Pourie TWS - Door Repair (5280) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 1991.81 | -1813.31 | 178.5 | 2550 | 0 | 0 | 2728.5 | 0 | 0 | 0 | 0 | 2728.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505796 | E-W-NI-180320-Invercannie WTW - Replace VSD Sludge Pump 2 (5922) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2432 | 0 | 2432 | 170.24 | 0 | 0 | 2602.24 | 0 | 0 | 0 | 0 | 2602.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505792 | E-W-NI-180320-Perth filter Turbidity Monitors Replacement (5284) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-08-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35954.99 | 35954.99 | 2356.73 | 0 | 0 | 38311.72 | 0 | 0 | 0 | 0 | 38311.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505799 | E-W-NI-180320-Whitehillocks Ceiling Replacement (5286) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-25 |  | 2020-11-19 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3007.8 | 3007.8 | 759.46 | 0 | 0 | 3767.26 | 0 | 0 | 0 | 0 | 3767.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506659 | E-W-NI-180520-Glenlatterach WTW - lime batching system improvement (CV19- 73) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW0 |  | 2021-10-25 | 2022-01-21 | 2022-09-02 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4444 | 4444 | 42620.31 | 0 | 0 | 47064.31 | 0 | 0 | 0 | 0 | 47064.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506666 | E-W-NI-180520-Newfield to Ellon Trunk Main-Pressure Loggers-64 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-09 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4761.5 | 4761.5 | 0 | 0 | 0 | 4761.5 | 0 | 0 | 0 | 0 | 4761.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508247 | E-W-NI-180820-Glenlomond TWP - replacement pump set and controls (6453) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2128.51 | 2128.51 | 16502.52 | 0 | 0 | 18631.03 | 0 | 0 | 0 | 0 | 18631.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508242 | E-W-NI-180820-Turriff WTW - Replacement of ORTHOPHOSPHORIC ACID DOSING PUMP B (7064) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-19 |  | 2020-09-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2367.58 | 2367.58 | 0 | 0 | 0 | 2367.58 | 0 | 0 | 0 | 0 | 2367.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508827 | E-W-NI-180920-Edintore DIR - Restoration of Comms Link (6658) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-09 |  | 2021-02-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3114.63 | 3114.63 | 0 | 0 | 0 | 3114.63 | 0 | 0 | 0 | 0 | 3114.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508829 | E-W-NI-180920-Forehill WTW - Fire Alarm Fault (7074) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.55 | 116.55 | 1665 | 0 | 0 | 1781.55 | 0 | 0 | 0 | 0 | 1781.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508828 | E-W-NI-180920-INVERCANNIE WTW 1866 - Sludge Press No 1 (7083) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-10-13 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2253.77 | 2253.77 | 63.94 | 0 | 0 | 2317.71 | 0 | 0 | 0 | 0 | 2317.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508824 | E-W-NI-180920-Killicrankie RWI - Wooden Walkway Replacement - (6888) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-29 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7276 | 7276 | 0 | 0 | 0 | 7276 | 0 | 0 | 0 | 0 | 7276 | 119022.58 | [5 empty] | N | CM_WSI | 100%
508825 | E-W-NI-180920-TURRIFF WTW-Replacement access ladders (7082) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-09 |  | 2021-02-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7527.45 | 7527.45 | 0 | 0 | 0 | 7527.45 | 0 | 0 | 0 | 0 | 7527.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508822 | E-W-NI-180920-Whitehillocks WTW - Replacement Windows - (6890) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2330.6 | 2330.6 | 0 | 0 | 0 | 2330.6 | 0 | 0 | 0 | 0 | 2330.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503856 | E-W-NI-18112019-Lomondhills WTW-Critical Spare actuator (5253) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 4579.88 | 0 | 4579.88 | -252.85 | 0 | 0 | 4327.03 | 0 | 0 | 0 | 0 | 4327.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509860 | E-W-NI-181120-TURRIFF WTW 1970 - Lime batching chute access hatches - (7102) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407.5 | 2407.5 | 0 | 0 | 0 | 2407.5 | 0 | 0 | 0 | 0 | 2407.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510425 | E-W-NI-181220-Glenfarg WTW - spares for sludge pump (6483) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2424.17 | 2424.17 | 170.58 | 0 | 0 | 2594.75 | 0 | 0 | 0 | 0 | 2594.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510770 | E-W-NI-190121-ARNAGE SCHOOL TWP NJ974357 - Don pressure loggers Customer Issue (7087) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5333.91 | 5333.91 | 0 | 0 | 0 | 5333.91 | 0 | 0 | 0 | 0 | 5333.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510764 | E-W-NI-19-01-21-Glenlatterach WTW - Access to Inlet Flowmeter (6667) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-04-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2439.6 | 2439.6 | 0 | 0 | 0 | 2439.6 | 0 | 0 | 0 | 0 | 2439.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505825 | E-W-NI-190320-Knapp TWP Floor Refurbishment (5297) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-25 |  | 2020-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2195 | 2195 | 153.65 | 0 | 0 | 2348.65 | 0 | 0 | 0 | 0 | 2348.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506689 | E-W-NI-190520-Glenfarg wtw-Repair Leaking Roof-82 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-24 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15941.77 | 15941.77 | 0 | 0 | 0 | 15941.77 | 0 | 0 | 0 | 0 | 15941.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506687 | E-W-NI-190520-Turriff WTW-Replace Final Lime Pump No2-81 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-20 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4612.77 | 4612.77 | 0 | 0 | 0 | 4612.77 | 0 | 0 | 0 | 0 | 4612.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509315 | E-W-NI-191020-Loan DSR - Access Road Improvements. (6469) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-21 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7062 | 7062 | 0 | 0 | 0 | 7062 | 0 | 0 | 0 | 0 | 7062 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509314 | E-W-NI-191020-Westary WTW - final chlorine monitor replacement (6253) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-03-12 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4677.95 | 4677.95 | 0 | 0 | 0 | 4677.95 | 0 | 0 | 0 | 0 | 4677.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505335 | E-W-NI-200220-Boardhouse WTW - roof repair (5049) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-26 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 19715.85 | -17153.29 | 2562.56 | 38931.99 | 0 | 0 | 41494.55 | 0 | 0 | 0 | 0 | 41494.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507758 | E-W-NI-2002720-Herricks WTW - RGF Pressure Gauges (6652) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-10-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2181.2 | 2181.2 | 0 | 0 | 0 | 2181.2 | 0 | 0 | 0 | 0 | 2181.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505860 | E-W-NI-200320-River Earn RWP 5 - Rewind Motor (5309) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-02 |  | 2020-10-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21202.5 | 21202.5 | 0 | 0 | 0 | 21202.5 | 0 | 0 | 0 | 0 | 21202.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506727 | E-W-NI-200520-180mm Main Hillend Rd Inverkeithing-PRV Installation-85 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-20 |  | 2020-06-29 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15755.5 | 15755.5 | 0 | 0 | 0 | 15755.5 | 0 | 0 | 0 | 0 | 15755.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506766 | E-W-NI-200520-Badentinan WTW - Replace 2 Obsolete WQ Monitors (SPG031) - SPG031 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-10-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46345.36 | 46345.36 | 0 | 0 | 0 | 46345.36 | 0 | 0 | 0 | 0 | 46345.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506759 | E-W-NI-200520-Ballater WTW - Replace 3 Obsolete WQ Monitors (SPG025) - SPG025 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61416.39 | 61416.39 | 15623.61 | 0 | 0 | 77040 | 0 | 0 | 0 | 0 | 77040 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506757 | E-W-NI-200520-Braemar WTW - Replace 3 Obsolete WQ Monitors (SPG024) - SPG024 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45797.45 | 45797.45 | 10912.55 | 0 | 0 | 56710 | 0 | 0 | 0 | 0 | 56710 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506761 | E-W-NI-200520-Crathie WTW - Replace 1 Obsolete WQ Monitors (SPG027) - SPG027 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11038.06 | 11038.06 | 1801.94 | 0 | 0 | 12840 | 0 | 0 | 0 | 0 | 12840 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506764 | E-W-NI-200520-Forehill WTW - Replace 4 Obsolete WQ Monitors (SPG029) - SPG029 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66564.1 | 66564.1 | 15825.91 | 0 | 0 | 82390.01 | 0 | 0 | 0 | 0 | 82390.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506722 | E-W-NI-200520-Glendevon WTW-Crit Spare Rotork-84 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-21 |  | 2020-08-11 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3849.63 | 3849.63 | 0 | 0 | 0 | 3849.63 | 0 | 0 | 0 | 0 | 3849.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506780 | E-W-NI-200520-Glenlatterach WTW - Replace 5 Obsolete WQ Monitors (SPG032) - SPG032 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83503.63 | 83503.63 | 19356.15 | 0 | 0 | 102859.78 | 0 | 0 | 0 | 0 | 102859.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506765 | E-W-NI-200520-Herricks WTW - Replace 3 Obsolete WQ Monitors (SPG030) - SPG030 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35137.5 | 35137.5 | 6592.5 | 0 | 0 | 41730 | 0 | 0 | 0 | 0 | 41730 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506716 | E-W-NI-200520-Herricks WTW-Replace Rotork Motor-83 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1841.67 | 1841.67 | 0 | 0 | 0 | 1841.67 | 0 | 0 | 0 | 0 | 1841.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506744 | E-W-NI-200520-Invercannie WTW - Replace 6 Obsolete WQ Monitors (SPG022) - SPG022 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46539.41 | 46539.41 | 99575.51 | 0 | 0 | 146114.92 | 0 | 0 | 0 | 0 | 146114.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506760 | E-W-NI-200520-Lumsden WTW - Replace 4 Obsolete WQ Monitors (SPG026) - SPG026 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75207.58 | 75207.58 | 17882.42 | 0 | 0 | 93090 | 0 | 0 | 0 | 0 | 93090 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506755 | E-W-NI-200520-Mannofield WTW - Replace 8 Failed/ Obsolete WQ Monitors (SPG023) - SPG023 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75942.04 | 75942.04 | 84893.26 | 0 | 0 | 160835.3 | 0 | 0 | 0 | 0 | 160835.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506763 | E-W-NI-200520-Tomnavoulin WTW - Replace 2 Obsolete WQ Monitors (SPG028) - SPG028 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33755.96 | 33755.96 | 7974.04 | 0 | 0 | 41730 | 0 | 0 | 0 | 0 | 41730 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507765 | E-W-NI-200720-Forehill WTW - Remove Fall From Height Risk at Lime Tank (5933) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-10-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4975.6 | 4975.6 | 0 | 0 | 0 | 4975.6 | 0 | 0 | 0 | 0 | 4975.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507761 | E-W-NI-200720-Herricks WTW - Filter No 1 Air Scour Valve (6651) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2137.75 | 2137.75 | 0 | 0 | 0 | 2137.75 | 0 | 0 | 0 | 0 | 2137.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508304 | E-W-NI-200820-Glenlomond TWP - Renovate building drainage and fencing (6454) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810.7 | 1810.7 | 25581.3 | 0 | 0 | 27392 | 0 | 0 | 0 | 0 | 27392 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508297 | E-W-NI-200820-Kenmore Replacement MSP Dosing Pump (6870) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-21 |  | 2020-09-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2174.07 | 2174.07 | 0 | 0 | 0 | 2174.07 | 0 | 0 | 0 | 0 | 2174.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509345 | E-W-NI-201020-Carnbee WSZ - New Flushing Point (6472). | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-21 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 210 | 3000 | 0 | 0 | 3210 | 0 | 0 | 0 | 0 | 3210 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509505 | E-W-NI201020-INCHGARTH RWI 1985 NJ903026 - Inspection of intakes - (7098) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16050 | 0 | 0 | 16050 | 0 | 0 | 0 | 0 | 16050 | 119022.58 | [5 empty] | N | CM_WSI | 100%
509357 | E-W-NI-201020-Stanley TWS - Flushing Point Installation - (6897) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-21 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185.56 | 185.56 | 2650.79 | 0 | 0 | 2836.35 | 0 | 0 | 0 | 0 | 2836.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509916 | E-W-NI-201120-Kirbister & Boardhouse WOA - network modelling for Boardhouse filter media replacement (6257) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2398.73 | 2398.73 | 8301.26 | 0 | 0 | 10699.99 | 0 | 0 | 0 | 0 | 10699.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510442 | E-W-NI-201220-Glendevon WTW - Spare sulphuric pump (6485) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-03-29 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1999.58 | 1999.58 | 0.24 | 0 | 0 | 1999.82 | 0 | 0 | 0 | 0 | 1999.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510443 | E-W-NI-201220-Herricks WTW - Raw Water Reservoir Outlet Valves (6679) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180.6 | 180.6 | 2580 | 0 | 0 | 2760.6 | 0 | 0 | 0 | 0 | 2760.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505332 | E-W-NI-202020-Turriff WTW - Modify Hypo Dosing Control (5903) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-26 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2522.31 | -2194.47 | 327.84 | 4683.38 | 0 | 0 | 5011.22 | 0 | 0 | 0 | 0 | 5011.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504746 | E-W-NI-210120-Kirbister WTW - fire door replacement (5040) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-10-28 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427 | 3427 | 239.89 | 0 | 0 | 3666.89 | 0 | 0 | 0 | 0 | 3666.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508850 | E-W-NI210920-Auchtermuchty DSR - Remove slip trip fall hazards (6462) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5778 | 5778 | 0 | 0 | 0 | 5778 | 0 | 0 | 0 | 0 | 5778 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503915 | E-W-NI-21112019-Badentinan WTW-Temporary Fuel Storage (5575) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1710.72 | -1547.4 | 163.32 | 2333.18 | 0 | 0 | 2496.5 | 0 | 0 | 0 | 0 | 2496.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503910 | E-W-NI-21112019-Craighead WTW-Air Saturator Flow Meter (5574) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-01-09 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 702.52 | 0 | 702.52 | 0 | 0 | 0 | 702.52 | 0 | 0 | 0 | 0 | 702.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503922 | E-W-NI-21112019-Muiresk RWI-Pump No1 bearing replacement (5883) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-04-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 11520.8 | 0 | 11520.8 | 0 | 0 | 0 | 11520.8 | 0 | 0 | 0 | 0 | 11520.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503920 | E-W-NI-21112019-Ordiequish RWP-Pump Connections (5576) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-02-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2545.65 | 0 | 2545.65 | 0 | 0 | 0 | 2545.65 | 0 | 0 | 0 | 0 | 2545.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510441 | E-W-NI-2-12-20-Glenfarg WTW - Spare hypo pump (6484) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-27 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2497.38 | 2497.38 | 0 | 0 | 0 | 2497.38 | 0 | 0 | 0 | 0 | 2497.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511385 | E-W-NI-220221-Braemar GWS - Investigate Swabbing of Raw Water Main (7104) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS2 |  | 2021-03-09 | 2021-05-21 | 2022-01-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266.26 | 266.26 | 50000 | 0 | 0 | 50266.26 | 0 | 0 | 0 | 0 | 50266.26 | 0 | [5 empty] | N | SR21_WA | 100%
511376 | E-W-NI-220221-INCHGARTH RWP 1986 - LOW LIFT PUMP 4 - (7097) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-24 | 2021-08-13 | 2022-03-28 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511948 | E-W-NI-220321-Eela Water WTW - OSEC plant replacement (6270) (MA046) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW0 |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654.21 | 654.21 | 120000.05 | 0 | 0 | 120654.26 | 0 | 0 | 0 | 0 | 120654.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506314 | E-W-NI-220420-Dickmontlaw TWS Chlorination unit-30 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-23 |  | 2020-06-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9469.5 | 9469.5 | 0 | 0 | 0 | 9469.5 | 0 | 0 | 0 | 0 | 9469.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506323 | E-W-NI-220420-forehill lime batching-33 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-23 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207.9 | 207.9 | 2970 | 0 | 0 | 3177.9 | 0 | 0 | 0 | 0 | 3177.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506324 | E-W-NI-220420-Inchgarth Raw Water Pumping Station-LOW LIFT PUMP 4-34 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-23 |  | 2020-10-20 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36817.66 | 36817.66 | 0 | 0 | 0 | 36817.66 | 0 | 0 | 0 | 0 | 36817.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506326 | E-W-NI-220420-Invercannie WTW-Membrane call number 4-36 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-23 |  | 2021-05-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.95 | 75.95 | 1085 | 0 | 0 | 1160.95 | 0 | 0 | 0 | 0 | 1160.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506325 | E-W-NI-220420-Pitfodels TWP-Fernhill Pump 1-35 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-04-23 |  | 2021-03-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8142.7 | 8142.7 | 0 | 0 | 0 | 8142.7 | 0 | 0 | 0 | 0 | 8142.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506316 | E-W-NI-220420-turriff-muiresk RWP-32 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-23 |  | 2020-04-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
508865 | E-W-NI-220920-Glendevon WTW - Replace Poly pump (6463) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-16 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6505.77 | 6505.77 | 0 | 0 | 0 | 6505.77 | 0 | 0 | 0 | 0 | 6505.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503934 | E-W-NI-22112019-Cairnton RWI-River Intake Actuator replacement (5889) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-05-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 11663.25 | 5357.24 | 17020.49 | 0 | 0 | 0 | 17020.49 | 0 | 0 | 0 | 0 | 17020.49 | 119022.58 | [5 empty] | N | CM_WSI | 100%
503938 | E-W-NI-22112019-Forehill WTW-GAC interstage pump VSD replacement (5890) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2019-12-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3220.7 | 0 | 3220.7 | 0 | 0 | 0 | 3220.7 | 0 | 0 | 0 | 0 | 3220.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503928 | E-W-NI-22112019-Turriff WTW-Lime pump spares (5888) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2019-12-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3930.7 | 0 | 3930.7 | 0 | 0 | 0 | 3930.7 | 0 | 0 | 0 | 0 | 3930.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505888 | E-W-NI-230220-Mannofield WTW - Install Mixer Shaft Guards (5928) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-25 |  | 2020-07-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992.93 | 1992.93 | 114.97 | 0 | 0 | 2107.9 | 0 | 0 | 0 | 0 | 2107.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505890 | E-W-NI-230320-Castlehill RWP - remote switchgear | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-09-12 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9326.54 | 9326.54 | 1132.71 | 0 | 0 | 10459.25 | 0 | 0 | 0 | 0 | 10459.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505883 | E-W-NI-230320-Lomondhills WTW - Refurbish Showers (5306) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-25 |  | 2020-09-08 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 2520 | 176.4 | 0 | 0 | 2696.4 | 0 | 0 | 0 | 0 | 2696.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505887 | E-W-NI-230320-Mannofield WTW - Upsize Poly Dosing Pipework (5930) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-25 |  | 2020-07-25 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5006.52 | 5006.52 | 350.46 | 0 | 0 | 5356.98 | 0 | 0 | 0 | 0 | 5356.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505886 | E-W-NI-230320-Pipelands DSR - Control Building security (5307) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575.49 | 0 | 0 | 2575.49 | 0 | 0 | 0 | 0 | 2575.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505879 | E-W-NI-230320-Whitehillocks WTW - RGF 4 Actuator replacement (5308) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-25 |  | 2020-04-04 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1819 | 1819 | 127.33 | 0 | 0 | 1946.33 | 0 | 0 | 0 | 0 | 1946.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507315 | E-W-NI230620-Loch Lee Overhead Crane (6846) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.6 | 117.6 | 1680 | 0 | 0 | 1797.6 | 0 | 0 | 0 | 0 | 1797.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507849 | E-W-NI-230720-Dickmontlaw Replacement Chlorine Pump (6855) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-27 |  | 2020-09-04 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5164.68 | 5164.68 | 0 | 0 | 0 | 5164.68 | 0 | 0 | 0 | 0 | 5164.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508921 | E-W-NI-230920-Croftgary - Replace TWP (6460) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-08-16 | 2022-07-08 | 2023-02-20 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017.33 | 2017.33 | -2017.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
508903 | E-W-NI-230920-Meikle Tullo Replacement Telemetry Equipment (6871) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8648.28 | 8648.28 | 0 | 0 | 0 | 8648.28 | 0 | 0 | 0 | 0 | 8648.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509442 | E-W-NI-231020-Inchgarth RWI- Inspection of intakes - (7098) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-10-30 | 2020-12-01 | 2021-03-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14542.06 | 14542.06 | 0 | 0 | 0 | 14542.06 | 0 | 0 | 0 | 0 | 14542.06 | 119022.58 | [5 empty] | N | CM_WSI | 100%
509955 | E-W-NI-231120-Clatto WTW - Handrail Installation - (6912) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1057.98 | 1057.98 | 1171.2 | 0 | 0 | 2229.18 | 0 | 0 | 0 | 0 | 2229.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509933 | E-W-NI-231120-FOREHILL WTW 1965 - H&S Handrail for Lime - (7106) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 429.11 | 429.11 | 5558.34 | 0 | 0 | 5987.45 | 0 | 0 | 0 | 0 | 5987.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509944 | E-W-NI-231120-Glenlatterach WTW - Dust Extraction (6675) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9622.99 | 9622.99 | 0 | 0 | 0 | 9622.99 | 0 | 0 | 0 | 0 | 9622.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509951 | E-W-NI-231120-Herricks WTW - Final Water Aluminium Monitor (6674) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24034.19 | 24034.19 | 0 | 0 | 0 | 24034.19 | 0 | 0 | 0 | 0 | 24034.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509924 | E-W-NI-231120-Lintrathen Media Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-03-17 | 2023-08-17 | 2023-11-30 | 2024-11-14 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1255.81 | 1255.81 | -1255.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
509930 | E-W-NI-231120-MANNOFIELD WTW 1986 - RGF 6 Range High performance differential - (7107) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-03-29 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436.23 | 1436.23 | -37.42 | 0 | 0 | 1398.81 | 0 | 0 | 0 | 0 | 1398.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509927 | E-W-NI-231120-TURRIFF MUIRESK RWP 1971 - Install Ammonia Monitor - (7108) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5147.87 | 5147.87 | 12065.32 | 0 | 0 | 17213.19 | 0 | 0 | 0 | 0 | 17213.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505923 | E-W-NI-240320-Badentinan WTW - Power Supply to Chlorine Analyser (5615) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-11-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1695.95 | 1695.95 | -9.97 | 0 | 0 | 1685.98 | 0 | 0 | 0 | 0 | 1685.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505919 | E-W-NI-240320-Charleston TWP Flow Monitor Installation (5298) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4280 | 0 | 0 | 4280 | 0 | 0 | 0 | 0 | 4280 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505909 | E-W-NI-240320-Forehill WTW - Ferric & Lime MCC (5932) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-25 |  | 2020-04-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700.54 | 2700.54 | 149.01 | 0 | 0 | 2849.55 | 0 | 0 | 0 | 0 | 2849.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505916 | E-W-NI-240320-Invercannie WTW - Sludge Feed Pump 3 (5927) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1770.09 | 74.82 | 1844.91 | 2239.24 | 0 | 0 | 4084.15 | 0 | 0 | 0 | 0 | 4084.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505903 | E-W-NI-240320-Lawton DSR - Tree Maintenance (5282) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-25 |  | 2020-05-27 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6837.41 | 6837.41 | -1480.43 | 0 | 0 | 5356.98 | 0 | 0 | 0 | 0 | 5356.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505913 | E-W-NI-240320-Lettar of Ballied Bladder Replacement (5293) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 3660 | 0 | 3660 | 256.2 | 0 | 0 | 3916.2 | 0 | 0 | 0 | 0 | 3916.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505908 | E-W-NI-240320-Mannofield WTW - Coag Dosing Software SCADA Changeover (5929) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-02-25 |  | 2020-05-29 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3101.19 | 3101.19 | 56.97 | 0 | 0 | 3158.16 | 0 | 0 | 0 | 0 | 3158.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508336 | E-W-NI-240820-BRACKANS SR GARDENSTOWN TM OUTLET METER - Install new PRV Bypass (7067) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739.74 | 739.74 | 10567.67 | 0 | 0 | 11307.41 | 0 | 0 | 0 | 0 | 11307.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508339 | E-W-NI-240820-Craighead DIR - Aeration Plant Controller (6657) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.25 | 171.25 | 2446.47 | 0 | 0 | 2617.72 | 0 | 0 | 0 | 0 | 2617.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508331 | E-W-NI-240820-Perth WTW- Additional Hypo Pump-(6869) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5884.55 | 5884.55 | 0 | 0 | 0 | 5884.55 | 0 | 0 | 0 | 0 | 5884.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508952 | E-W-NI-240920-EN Tracker - Greentoft DSR - 2< Outlet Flow Meter replacement (6248) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115.15 | 1115.15 | 0 | 0 | 0 | 1115.15 | 0 | 0 | 0 | 0 | 1115.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508940 | E-W-NI-240920-Glenlatterach WTW - Coagulation Controller (5522) (SPG11) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-10-11 | 2021-12-31 | 2022-08-15 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 98471.92 | 0 | 0 | 99471.92 | 0 | 0 | 0 | 0 | 99471.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508956 | E-W-NI-240920-Staney Hill TWP - pump 4 replacement (6247) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-22 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8104.52 | 8104.52 | 0 | 0 | 0 | 8104.52 | 0 | 0 | 0 | 0 | 8104.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508950 | E-W-NI-240920-Westray WTW - Hypo dosing pump critical spare (6249) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-22 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230.34 | 1230.34 | 0 | 0 | 0 | 1230.34 | 0 | 0 | 0 | 0 | 1230.34 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509975 | E-W-NI-241120-Alyth TWS - Road Repairs -(6909) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385 | 385 | 5500 | 0 | 0 | 5885 | 0 | 0 | 0 | 0 | 5885 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509994 | E-W-NI-241120-CRAIGIE NEWMACHAR DSR 1970 - Inlet Valve chamber - (7101) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981.5 | 5981.5 | 179.04 | 0 | 0 | 6160.54 | 0 | 0 | 0 | 0 | 6160.54 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509974 | E-W-NI-241120-Gannochy TWS - Road Repairs - (6910) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5992 | 5992 | 0 | 0 | 0 | 5992 | 0 | 0 | 0 | 0 | 5992 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509963 | E-W-NI-241120-Knoxhill TWS - Road Repairs - (6911) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6206 | 6206 | 0 | 0 | 0 | 6206 | 0 | 0 | 0 | 0 | 6206 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510862 | E-W-NI-250121-Cheynehill TWS - Replacement Flow Meter - (6919) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3425.28 | 3425.28 | 239.77 | 0 | 0 | 3665.05 | 0 | 0 | 0 | 0 | 3665.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510871 | E-W-NI-250121-Glenfarg WTW - Clean Lime Slurry Tanks(6494) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32303.65 | 32303.65 | -1656.65 | 0 | 0 | 30647 | 0 | 0 | 0 | 0 | 30647 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510866 | E-W-NI-250121-INCHGARTH RWP - HV SWITCHGEAR removal of redundant asset - (7124) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545.3 | 545.3 | 7790 | 0 | 0 | 8335.3 | 0 | 0 | 0 | 0 | 8335.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510856 | E-W-NI-250121-INCHGARTH RWP - Replace Low Lift Pump 3- (7125) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228.1 | 1228.1 | 18571.08 | 0 | 0 | 19799.18 | 0 | 0 | 0 | 0 | 19799.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510855 | E-W-NI-250121-Kinloch Rannoch WTW - Electrics Repair - (6921) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3252 | 3252 | 600 | 0 | 0 | 3852 | 0 | 0 | 0 | 0 | 3852 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505401 | E-W-NI-250220-Eela water WTW - FRA action (5060) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-26 |  | 2020-09-10 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1275.47 | 471.75 | 1747.22 | 0 | 0 | 0 | 1747.22 | 0 | 0 | 0 | 0 | 1747.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505403 | E-W-NI-250220-Turriff WTW - Replace Filter Press Cloths (5912) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-26 |  | 2020-08-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 7525.66 | 2783.47 | 10309.13 | 0 | 0 | 0 | 10309.13 | 0 | 0 | 0 | 0 | 10309.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505929 | E-W-NI-250320-Dunicher TWS - Reliable power source (5301) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-22 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7241.06 | 7241.06 | 0 | 0 | 0 | 7241.06 | 0 | 0 | 0 | 0 | 7241.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503957 | E-W-NI-25112019-LINTRATHEN WTW-Replace SUPERNATENT RETURN PUMP (5254) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-03-05 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 4378.53 | 0 | 4378.53 | 0 | 0 | 0 | 4378.53 | 0 | 0 | 0 | 0 | 4378.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503967 | E-W-NI-25112019-Mannofield TWP-Refurbish Pump 3 (6235) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-03-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 27666.22 | 0 | 27666.22 | 0 | 0 | 0 | 27666.22 | 0 | 0 | 0 | 0 | 27666.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509993 | E-W-NI-251120-St Fillans TWS - Road Repairs and Maintenance-(6908) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322 | 322 | 4600 | 0 | 0 | 4922 | 0 | 0 | 0 | 0 | 4922 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511505 | E-W-NI-260221-CRAIGIE NEWMACHAR DSR 1970 - Installation of reservoir signal wiring - (7134) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-01 |  | 2021-05-26 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546.07 | 546.07 | 8347.1 | 0 | 0 | 8893.17 | 0 | 0 | 0 | 0 | 8893.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511504 | E-W-NI260221-CUSHNIE TWP 1975 - Whole site electrical refurbishment - (7135) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-01 |  | 2021-05-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1311.54 | 1311.54 | 18736.23 | 0 | 0 | 20047.77 | 0 | 0 | 0 | 0 | 20047.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509451 | E-W-NI-261020- FOREHILL WTW 1965 - Repair LIME FEED HOPPER - (7093) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877.99 | 877.99 | 12542.76 | 0 | 0 | 13420.75 | 0 | 0 | 0 | 0 | 13420.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509450 | E-W-NI-261020-Gowriehill TWP - Pump Refurbishment - (6898) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.08 | 959.08 | 13701.08 | 0 | 0 | 14660.16 | 0 | 0 | 0 | 0 | 14660.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509449 | E-W-NI261020-INCHGARTH RWP 1986 - LOW LIFT PUMP 4 - (7097) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41982.27 | 41982.27 | 817.73 | 0 | 0 | 42800 | 0 | 0 | 0 | 0 | 42800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509470 | E-W-NI-261020-Killiecrankie WTW - Monitors Replacement - (6901) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274.13 | 2274.13 | 31915.78 | 0 | 0 | 34189.91 | 0 | 0 | 0 | 0 | 34189.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503994 | E-W-NI-26112019-MANNOFIELD WTW-Change Fixed Speed Poly Mixers to Variable (5892) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-05-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 8115.57 | 3727.69 | 11843.26 | 0 | 0 | 0 | 11843.26 | 0 | 0 | 0 | 0 | 11843.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503987 | E-W-NI-26112019-TURRIFF TWP-Highlift Pump Repair Motor (5891) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-01-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 13685.3 | 0 | 13685.3 | 0 | 0 | 0 | 13685.3 | 0 | 0 | 0 | 0 | 13685.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510013 | E-W-NI-261120-St Andrews HL WSZ - New scour valve (6478) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139.21 | 139.21 | 1988.76 | 0 | 0 | 2127.97 | 0 | 0 | 0 | 0 | 2127.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507879 | E-W-NI-270220-Badentinan WTW - Lime Dosing MCC (6654) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-09-02 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6738.11 | 6738.11 | 0 | 0 | 0 | 6738.11 | 0 | 0 | 0 | 0 | 6738.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507886 | E-W-NI-270220-INVERCANNIE WTW - Replacement of SLUDGE CONSOL PUMP 3 VSD (7061) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-09-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1601.82 | 1601.82 | 0 | 0 | 0 | 1601.82 | 0 | 0 | 0 | 0 | 1601.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507902 | E-W-NI-270220-Lomondhills WTW - Sulphuric Acid Pipework (6442) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-09 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2869.92 | 2869.92 | 0 | 0 | 0 | 2869.92 | 0 | 0 | 0 | 0 | 2869.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507906 | E-W-NI-270720-Aberdeen Bluehill DSR - Replacement of Concrete sleepers (7060) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-09-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7123.41 | 7123.41 | 0 | 0 | 0 | 7123.41 | 0 | 0 | 0 | 0 | 7123.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507896 | E-W-NI-270720-Lomondhills WTW - Guard Valve Spare actuator (6443) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-09-13 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3434.36 | 3434.36 | 0 | 0 | 0 | 3434.36 | 0 | 0 | 0 | 0 | 3434.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507881 | E-W-NI-270720-Mannofield WTW - Inlet Flow meter replacement (7057) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-09 |  | 2021-03-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13438.07 | 13438.07 | 860.61 | 0 | 0 | 14298.68 | 0 | 0 | 0 | 0 | 14298.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507878 | E-W-NI-270720-Papa Stour WTW-control system software restoration/upgrade (6243) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW0 |  | 2021-04-22 | 2021-05-20 | 2021-11-25 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2205.59 | 2205.59 | 10432.24 | 0 | 0 | 12637.83 | 0 | 0 | 0 | 0 | 12637.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507890 | E-W-NI-270720-Westray WTW - Filter inlet valve and actuator replacement (6244) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-06 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3109.47 | 3109.47 | 0 | 0 | 0 | 3109.47 | 0 | 0 | 0 | 0 | 3109.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509497 | E-W-NI-271020-Whitehillocks WTW - RGF PLC Modifications - (6895) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2021-02-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679.63 | 1679.63 | 0 | 0 | 0 | 1679.63 | 0 | 0 | 0 | 0 | 1679.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504016 | E-W-NI-27112019-DALACHY TWP-Replace BOOSTER PUMP NO1 (5255) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2789.88 | -1458.86 | 1331.02 | 3196.87 | 0 | 0 | 4527.89 | 0 | 0 | 0 | 0 | 4527.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504886 | E-W-NI-28012020-GLENDEVON WTW- SODIUM HYPOCHLORITE STORAGE TANK A (5270) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-01-31 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 33060.49 | 0 | 33060.49 | 0 | 0 | 0 | 33060.49 | 0 | 0 | 0 | 0 | 33060.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510945 | E-W-NI-280121-Forehill WTW - Emergency Generator access - (7122) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169.6 | 169.6 | 2422.88 | 0 | 0 | 2592.48 | 0 | 0 | 0 | 0 | 2592.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510947 | E-W-NI-280121-Whitehillocks CWT valve Replacement (5296) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376.95 | 376.95 | 5385 | 0 | 0 | 5761.95 | 0 | 0 | 0 | 0 | 5761.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505461 | E-W-NI-280220-Auchtermuchty DSR - Contribution to access track upgrade (5283) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-10 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 11407.78 | 0 | 11407.78 | 173.01 | 0 | 0 | 11580.79 | 0 | 0 | 0 | 0 | 11580.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506899 | E-W-NI-280520-Balgeddie TWP-BALGEDDIE TWP NO257032-99 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.98 | 177.98 | 2399.58 | 0 | 0 | 2577.56 | 0 | 0 | 0 | 0 | 2577.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506902 | E-W-NI-280520-glenlatterach wtw-scada/ pacl & poly dosing plc.-103 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3669.1 | 3669.1 | 0 | 0 | 0 | 3669.1 | 0 | 0 | 0 | 0 | 3669.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506900 | E-W-NI-280520-herricks wtw-PACL dosing PLC-102 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4648.68 | 4648.68 | 0 | 0 | 0 | 4648.68 | 0 | 0 | 0 | 0 | 4648.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506892 | E-W-NI-280520-KILLIECRANKIE WTW-PH PROBES-97 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220.49 | 220.49 | 3149.84 | 0 | 0 | 3370.33 | 0 | 0 | 0 | 0 | 3370.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506890 | E-W-NI-280520-Kinnloch Rannoch WTW-Silicate and Ortho Transfer Pumps-96 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-28 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656.84 | 1656.84 | 0 | 0 | 0 | 1656.84 | 0 | 0 | 0 | 0 | 1656.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506880 | E-W-NI-280520-Lintrathen WTW-Sludge Transfer Pump-94 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-07-20 |  | 2020-07-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197.16 | 1197.16 | 2440.85 | 0 | 0 | 3638.01 | 0 | 0 | 0 | 0 | 3638.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506888 | E-W-NI-280520-PERTH WTW GOWANS TERRACE-SULPHURIC ACID-95 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.81 | 183.81 | 2625.84 | 0 | 0 | 2809.65 | 0 | 0 | 0 | 0 | 2809.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506894 | E-W-NI-280520-Redcraigs DSR-Redcraigs DSR-98 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-06-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5392 | 5392 | 0 | 0 | 0 | 5392 | 0 | 0 | 0 | 0 | 5392 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506879 | E-W-NI-280520-Waters of May Intake feeds Glenfarg reservoir-intake valve-86 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-06-05 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3372.86 | 3372.86 | 0 | 0 | 0 | 3372.86 | 0 | 0 | 0 | 0 | 3372.86 | 119022.58 | [5 empty] | N | CM_WSI | 100%
507953 | E-W-NI-280720-Invercannie WTW - New Access Platform at Acid Neut Tank (7054) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4664.13 | 4664.13 | 0 | 0 | 0 | 4664.13 | 0 | 0 | 0 | 0 | 4664.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508453 | E-W-NI-280820-Perth WTW- RGF 1 Outlet Valve Replacement - (6880) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-18 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2930.64 | 2930.64 | 0 | 0 | 0 | 2930.64 | 0 | 0 | 0 | 0 | 2930.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508444 | E-W-NI-280820-Slateford Burn RWI & Frandy RWI - WTW - combined H&S project (644564466448) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-09 | 2020-12-09 | 2020-12-18 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4192.86 | 4192.86 | -2361.19 | 0 | 0 | 1831.67 | 0 | 0 | 0 | 0 | 1831.67 | 119022.58 | [5 empty] | N | CM_M&G | 100%
508458 | E-W-NI-280820-Whitehillocks WTW- Window Replacement - (6879) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-13 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2330.6 | 2330.6 | 0 | 0 | 0 | 2330.6 | 0 | 0 | 0 | 0 | 2330.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509518 | E-W-NI-281020-Glenlatterach CWT - Level Probe (6656) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-11-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5178.06 | 5178.06 | 0 | 0 | 0 | 5178.06 | 0 | 0 | 0 | 0 | 5178.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509503 | E-W-NI-281020-Perth WTW - Monitors Replacement - (6899) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8669.81 | 8669.81 | 20319.9 | 0 | 0 | 28989.71 | 0 | 0 | 0 | 0 | 28989.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509522 | E-W-NI-281020-STRACHAN GLENDYE DSR 1969 Leak investigation and repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-11-06 | 2020-12-07 | 2021-05-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 91000 | 0 | 0 | 0 | 91000 | 0 | 0 | 0 | 0 | 91000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504038 | E-W-NI-28112019-INVERCANNIE WTW-Add Missing Telem Signals (5893) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-01-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2648 | 0 | 2648 | 0 | 0 | 0 | 2648 | 0 | 0 | 0 | 0 | 2648 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504062 | E-W-NI-28112019-INVERCANNIE WTW-SLUDGE PRESSING LATE PRESS REfURB(5894) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-03-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5092.83 | 0 | 5092.83 | 0 | 0 | 0 | 5092.83 | 0 | 0 | 0 | 0 | 5092.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504054 | E-W-NI-28112019-KIRRIEMUIR HIGH DSR NO393547-Replace Telem Kiosk(5257) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-01-02 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 5216.25 | 18.71 | 5234.96 | 0 | 0 | 0 | 5234.96 | 0 | 0 | 0 | 0 | 5234.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504913 | E-W-NI-290120-Badentinan CWT - Replacement UPS (5601) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1165.43 | 0 | 1165.43 | 0 | 0 | 0 | 1165.43 | 0 | 0 | 0 | 0 | 1165.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504910 | E-W-NI-290120-Clatto WTW - Raw water main Inspection (5268) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-27 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 2464.12 | 0 | 2464.12 | 0 | 0 | 0 | 2464.12 | 0 | 0 | 0 | 0 | 2464.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504909 | E-W-NI-290120-Herricks WTW-DAF Outlet Valves (5603) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-02-18 |  | 2021-03-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5347.35 | 260.06 | 5607.41 | 760 | 0 | 0 | 6367.41 | 0 | 0 | 0 | 0 | 6367.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504918 | E-W-NI-290120-Loch of Boardhouse RWI - Inlet screen winch replacement (5042) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-10-07 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 6897 | 1315.67 | 8212.67 | 0 | 0 | 0 | 8212.67 | 0 | 0 | 0 | 0 | 8212.67 | 119022.58 | [5 empty] | N | CM_WSI | 100%
504926 | E-W-NI-290120-Sandy Loch WTW - Inlet Valve replacement (5045) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-06-19 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 4846.64 | -2022.09 | 2824.55 | 0 | 0 | 0 | 2824.55 | 0 | 0 | 0 | 0 | 2824.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512076 | E-W-NI-290321- Whitehillocks Access Road Resurfacing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000.03 | 0 | 0 | 150000.03 | 0 | 0 | 0 | 0 | 150000.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506906 | E-W-NI-290520-Eela water WTW & Skerries WTW-Shetalnd Control Project (6238&6239) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | GW0 |  | 2021-04-12 | 2021-04-16 | 2021-11-10 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4621 | 4621 | 7879.36 | 0 | 0 | 12500.36 | 0 | 0 | 0 | 0 | 12500.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504043 | E-W-NI-29112019-Caddam BM Kiosk-Replace Kiosk (5894) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-01-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 4875 | 0 | 4875 | 341.25 | 0 | 0 | 5216.25 | 0 | 0 | 0 | 0 | 5216.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504071 | E-W-NI-29112019-CULTS PITFODELS TWP-Refurb Pump as Critical Spare(5896) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2019-12-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 8824.29 | 0 | 8824.29 | 0 | 0 | 0 | 8824.29 | 0 | 0 | 0 | 0 | 8824.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504080 | E-W-NI-29112019-GLENLATTERACH WTW-Replace Lime Dosing Pump 1(5578) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-01-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3249.83 | 0 | 3249.83 | 0 | 0 | 0 | 3249.83 | 0 | 0 | 0 | 0 | 3249.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504076 | E-W-NI-29112019-TURRIFF WTW-Generator control unit (5895) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-08 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1865.35 | -1667.3 | 198.05 | 2829.35 | 0 | 0 | 3027.4 | 0 | 0 | 0 | 0 | 3027.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505990 | E-W-NI-300320-Boardhouse WTW - RGF 1 Inlet valve actuator replacement (5066) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-23 |  | 2020-10-19 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3467.53 | 3467.53 | 0 | 0 | 0 | 3467.53 | 0 | 0 | 0 | 0 | 3467.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505991 | E-W-NI-300320-Flotta DSR - Valve chamber cover replacement (5067) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-31 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5634.23 | 5634.23 | 0 | 0 | 0 | 5634.23 | 0 | 0 | 0 | 0 | 5634.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505977 | E-W-NI-300320-Lintrathen WTW - Replace de-stratification compressor motor (5311) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-23 |  | 2020-04-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576.85 | 1576.85 | 0 | 0 | 0 | 1576.85 | 0 | 0 | 0 | 0 | 1576.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507438 | E-W-NI-300620-Clatto WTW-Replacement Hypo UPS-131 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-06 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2334.93 | 2334.93 | 0 | 0 | 0 | 2334.93 | 0 | 0 | 0 | 0 | 2334.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507444 | E-W-NI-300620-Glendevon WTW - Spare Backwash Inlet Valve Actuator (6438) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-07 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2921.1 | 2921.1 | 0 | 0 | 0 | 2921.1 | 0 | 0 | 0 | 0 | 2921.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507446 | E-W-NI-300620-Harperlease Reservoir - Public Footpath bridge repairs (6439) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-31 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1321.41 | 1321.41 | 0 | 0 | 0 | 1321.41 | 0 | 0 | 0 | 0 | 1321.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508460 | E-W-NI-300820-Cheynehill DSR - Valve Access - (6877) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-10-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4151.56 | 4151.56 | 0 | 0 | 0 | 4151.56 | 0 | 0 | 0 | 0 | 4151.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509019 | E-W-NI-300920-Burghill DSR - Flow Totaliser Replacement - (6891) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2973.38 | 2973.38 | 0 | 0 | 0 | 2973.38 | 0 | 0 | 0 | 0 | 2973.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509010 | E-W-NI-300920-Glendevon WTW - Replace acid dosing pw (6464) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-09 |  | 2021-02-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3122.07 | 3122.07 | 0 | 0 | 0 | 3122.07 | 0 | 0 | 0 | 0 | 3122.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509018 | E-W-NI-300920-INVERCANNIE WTW 1866 - SLUDGE CONSOLIDATION FEED PUMP 1 new slower speed gearboxes (7084) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10972.21 | 10972.21 | 0 | 0 | 0 | 10972.21 | 0 | 0 | 0 | 0 | 10972.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509022 | E-W-NI-300920-Killiecrankie WTW- Turbidity Filter Monitor Replacements - (6884) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40430.32 | 40430.32 | 0 | 0 | 0 | 40430.32 | 0 | 0 | 0 | 0 | 40430.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509035 | E-W-NI-300920-PIPELANDS DSR - Surface water drainage repairs (6465) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3905.5 | 3905.5 | 0 | 0 | 0 | 3905.5 | 0 | 0 | 0 | 0 | 3905.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509013 | E-W-NI-300920-TURRIFF WTW -Washwater system Replacement of WWR decant valves (7086) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677.19 | 677.19 | 9674.1 | 0 | 0 | 10351.29 | 0 | 0 | 0 | 0 | 10351.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510050 | E-W-NI-301120-MANNOFIELD WTW 1986 - RGF 6 Turbidity Monitor - (7109) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5589.11 | 5589.11 | -37.42 | 0 | 0 | 5551.69 | 0 | 0 | 0 | 0 | 5551.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505980 | E-W-NI-303020-Rousay School WTW - HMI replacement (5065) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-23 |  | 2020-04-23 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1461.78 | 1461.78 | 0 | 0 | 0 | 1461.78 | 0 | 0 | 0 | 0 | 1461.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505995 | E-W-NI-303020-Turriff Muiresk RWP - Refurb RWP 4 (5934) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-22 |  | 2021-05-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1404.37 | 1404.37 | 19490.59 | 0 | 0 | 20894.96 | 0 | 0 | 0 | 0 | 20894.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505211 | E-W-NI-31012019-Loch Lee-Wash Day with silt trap (5272) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-09-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1432.59 | 1413.61 | 2846.2 | 0 | 0 | 0 | 2846.2 | 0 | 0 | 0 | 0 | 2846.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504969 | E-W-NI-31012020-PANMURE TWP-Replace Flow Meter(5273) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1494.72 | 0 | 1494.72 | 0 | 0 | 0 | 1494.72 | 0 | 0 | 0 | 0 | 1494.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506004 | E-W-NI-310320-Glendevon WTW - Replacement s/n pump (5312) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-07 |  | 2020-05-07 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1728.86 | 1728.86 | 0 | 0 | 0 | 1728.86 | 0 | 0 | 0 | 0 | 1728.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504958 | E-W-NI-Badentinan WTW - Sodium Hypochlorite Dosing Control (5602) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-07-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 7905.72 | 1508.09 | 9413.81 | 0 | 0 | 0 | 9413.81 | 0 | 0 | 0 | 0 | 9413.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503851 | E-W-NI-Balreavie TWS - 18112019 - Balreavie TWS - Replace Telemetry kiosk (5252) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2019-11-25 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 6088.3 | 0 | 6088.3 | 0 | 0 | 0 | 6088.3 | 0 | 0 | 0 | 0 | 6088.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504889 | E-W-NI-BANKFOOT DSR-280120-Contribution for Access Track Repairs(5271) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 426.46 | -358.88 | 67.58 | 467.42 | 0 | 0 | 535 | 0 | 0 | 0 | 0 | 535 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507713 | E-W-NI-Boardhouse WTW - Big Breck sludge storage capacity extension (6242) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-03 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9204.14 | 9204.14 | 0 | 0 | 0 | 9204.14 | 0 | 0 | 0 | 0 | 9204.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505185 | E-W-NI-Cullen TWP - RTU Replacement (5907) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-05-13 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 4733.87 | 1885.71 | 6619.58 | 0 | 0 | 0 | 6619.58 | 0 | 0 | 0 | 0 | 6619.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505179 | E-W-NI-Forehill WTW - Replace Poly Dosing Pump 2 (5905) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-04-29 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1476.67 | 546.17 | 2022.84 | 0 | 0 | 0 | 2022.84 | 0 | 0 | 0 | 0 | 2022.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504734 | E-W-NI-GLENDEVON WTW-Backwash pump No4 inverter replacement(6247) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-01-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 4813.81 | 0 | 4813.81 | 0 | 0 | 0 | 4813.81 | 0 | 0 | 0 | 0 | 4813.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509069 | E-W-NI-GLENFARG WTW 1984 - TELEMETRY OUTSTATION addition of raw water signals (6467) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-09 |  | 2021-02-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679.6 | 1679.6 | 760 | 0 | 0 | 2439.6 | 0 | 0 | 0 | 0 | 2439.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505022 | E-W-NI-GLENFARG WTW-PRESS CLOTH WASH PUMP Refurbishment(5277) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 6948.38 | 0 | 6948.38 | 0 | 0 | 0 | 6948.38 | 0 | 0 | 0 | 0 | 6948.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510179 | E-W-NI-GLENLATTERACH WTW - Chlorine Gas changeover replacement - (6677) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-02-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4866.93 | 4866.93 | 0 | 0 | 0 | 4866.93 | 0 | 0 | 0 | 0 | 4866.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508925 | E-W-NI-Harelaw TWP Replacement (6435) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-06-21 | 2021-11-15 | 2022-06-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1786.29 | 1786.29 | -1786.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
504771 | E-W-NI-Herricks WTW - Control System Modifications (5599) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-04-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1862.01 | 0 | 1862.01 | 0 | 0 | 0 | 1862.01 | 0 | 0 | 0 | 0 | 1862.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505178 | E-W-NI-Herricks WTW - Radon Mitigation (5560) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-10-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5091.21 | 3883.05 | 8974.26 | 0 | 0 | 0 | 8974.26 | 0 | 0 | 0 | 0 | 8974.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505172 | E-W-NI-Inchgarth RWP - Repair Cavity Wall Ties (5909) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-08-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3983.61 | 1473.39 | 5457 | 0 | 0 | 0 | 5457 | 0 | 0 | 0 | 0 | 5457 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504730 | E-W-NI-INCHGARTH RWP-LOW LIFT PUMP 3 Refurbishment (6245) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 9911.03 | 6547.01 | 16458.04 | 0 | 0 | 0 | 16458.04 | 0 | 0 | 0 | 0 | 16458.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505739 | E-W-NI-Invercannie WTW - Add Additional Rinse to Membrane Wash Programme v2 (5925) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-05-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8958.13 | 8958.13 | 0 | 0 | 0 | 8958.13 | 0 | 0 | 0 | 0 | 8958.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503924 | E-W-NI-Invercannie WTW-CIP pump refurbishment to become a spare (5885) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-10-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5741.52 | 2637.23 | 8378.75 | 0 | 0 | 0 | 8378.75 | 0 | 0 | 0 | 0 | 8378.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509137 | E-W-NI-KILLIECRANKIE RWI 1980 - Concrete Repair works - (6893) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8346 | 8346 | 0 | 0 | 0 | 8346 | 0 | 0 | 0 | 0 | 8346 | 119022.58 | [5 empty] | N | CM_WSI | 100%
511073 | E-W-NI-Killiecrankie WTW- Broadband Installation - (6916) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-05 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.83 | 150.83 | 2154.7 | 0 | 0 | 2305.53 | 0 | 0 | 0 | 0 | 2305.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504802 | E-W-NI-Killiecrankie WTW Turbidity monitors(5269) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-08-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 9989.02 | 6598.53 | 16587.55 | 0 | 0 | 0 | 16587.55 | 0 | 0 | 0 | 0 | 16587.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506374 | E-W-NI-Killiecrankie WTW-Replace RGF 1 Outlet valve Module Card-47 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-20 |  | 2020-05-20 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1965.91 | 1965.91 | 0 | 0 | 0 | 1965.91 | 0 | 0 | 0 | 0 | 1965.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504738 | E-W-NI-Lagahorie SR - Safety Improvement (5593) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 9653.01 | 0 | 9653.01 | 0 | 0 | 0 | 9653.01 | 0 | 0 | 0 | 0 | 9653.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510738 | E-W-NI-Limekilns DSR - Replacment of power generator (6492) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-16 |  | 2021-04-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2765.92 | 2765.92 | 2180.12 | 0 | 0 | 4946.04 | 0 | 0 | 0 | 0 | 4946.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506974 | E-W-NI-Lintrathen Sludge Press Replacement Cloths (6838) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 175 | 2500 | 0 | 0 | 2675 | 0 | 0 | 0 | 0 | 2675 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511209 | E-W-NI-Lomondhills WTW-Replacement Ortho dosing pumps (6498) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6701.83 | 6701.83 | 112.21 | 0 | 0 | 6814.04 | 0 | 0 | 0 | 0 | 6814.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508234 | E-W-NI-Mannofield TWP-Replacement of TWP building cooling lagging (7062) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326.87 | 326.87 | 4669.5 | 0 | 0 | 4996.37 | 0 | 0 | 0 | 0 | 4996.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504692 | E-W-NI-Mannofield WTW - Laboratory Coagulation Analyser (5866) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 13461.07 | 0 | 13461.07 | 0 | 0 | 0 | 13461.07 | 0 | 0 | 0 | 0 | 13461.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505183 | E-W-NI-Mannofield WTW Final Water Instrumentation (4269) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-06-04 | 2020-11-02 | 2021-09-22 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 65.42 | 75431.58 | 75497 | 91947.41 | 0 | 0 | 167444.41 | 0 | 0 | 0 | 0 | 167444.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511027 | E-W-NI-Mannofield WTW-Automate Existing Poly Batching System | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-24 | 2021-08-13 | 2022-03-28 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 75000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504731 | E-W-NI-Ordiequish RWP-TRANSFER PUMP A Refurbish(6246) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-02-05 |  | 2022-06-11 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 6336.73 | 4185.91 | 10522.64 | 0 | 0 | 0 | 10522.64 | 0 | 0 | 0 | 0 | 10522.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505018 | E-W-NI-PERTH WTW TWP-BURGHMUIR PUMP 3 Strip and Repair(5277) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-05 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 9279.8 | 0 | 9279.8 | 0 | 0 | 0 | 9279.8 | 0 | 0 | 0 | 0 | 9279.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504765 | E-W-NI-Spey Wellfield - Replacement Borehole Pump (5595) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-05-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 6637.83 | 4384.8 | 11022.63 | 0 | 0 | 0 | 11022.63 | 0 | 0 | 0 | 0 | 11022.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504642 | E-W-NI-Staney Hill TWP - Pump 2 replacement (5043) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-05 |  | 2020-03-04 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 8104.5 | 0 | 8104.5 | 0 | 0 | 0 | 8104.5 | 0 | 0 | 0 | 0 | 8104.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504684 | E-W-NI-Stromness DSR - perimeter fence repair (5044) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-05 |  | 2020-09-17 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1326.8 | 876.45 | 2203.25 | 0 | 0 | 0 | 2203.25 | 0 | 0 | 0 | 0 | 2203.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505176 | E-W-NI-Turriff WTW - Replace RGF 6 Actuator (5901) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2122.25 | 822.35 | 2944.6 | -37.41 | 0 | 0 | 2907.19 | 0 | 0 | 0 | 0 | 2907.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508195 | E-Ws-NI-130820-Pipelands DSR - Non return Valve (6449) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.22 | 1116.22 | 15946 | 0 | 0 | 17062.22 | 0 | 0 | 0 | 0 | 17062.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505550 | E-WW-04032020-DUNKELD WEST BIRNAM WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-06 |  | 2020-05-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 131.76 | 1938.4 | 2070.16 | 0 | 0 | 0 | 2070.16 | 0 | 0 | 0 | 0 | 2070.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508689 | E-WW-10092020-CRIEFF WWTW-INSTALLATION OF CHEMICAL DOSING UNIT (QP20) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-13 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9163.47 | 9163.47 | 128413.17 | 0 | 0 | 137576.64 | 0 | 0 | 0 | 0 | 137576.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504963 | E-WW-31012020-DRUM WWTW-SUPPLY 12 VALVES (CRITICAL SPARES FOR NETWORK VACCUM SYSTEM) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-29 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 16048.02 | 0 | 16048.02 | 0 | 0 | 0 | 16048.02 | 0 | 0 | 0 | 0 | 16048.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512233 | E-WW-I-01042021-KENMORE WWPS-FLOOD PREVENTION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10890.46 | 0 | 0 | 10890.46 | 0 | 0 | 0 | 0 | 10890.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511815 | E-WW-I-02032021-34 SEATOWNLOSSIEMOUTH- 20M REPLACEMENT OF LATERAL SEWER | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 635.68 | 635.68 | 8328.66 | 0 | 0 | 8964.34 | 0 | 0 | 0 | 0 | 8964.34 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511812 | E-WW-I-02032021-MOSSTODLOCH MOSSMIL PARK-INFILTRATION REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1856.75 | 1856.75 | 26525 | 0 | 0 | 28381.75 | 0 | 0 | 0 | 0 | 28381.75 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512185 | E-WW-I-02042021-BURNTISLAND LINWELL COURT SPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2514.47 | 0 | 0 | 2514.47 | 0 | 0 | 0 | 0 | 2514.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512180 | E-WW-I-02042021-CROSSFORD KEAVIL FARM WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2247 | 0 | 0 | 2247 | 0 | 0 | 0 | 0 | 2247 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512182 | E-WW-I-02042021-DUNFERMLINE LIGGARS PLACE WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2075.78 | 0 | 0 | 2075.78 | 0 | 0 | 0 | 0 | 2075.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512244 | E-WW-I-02042021-GOWKHALL SPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-07 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3284.89 | 0 | 0 | 3284.89 | 0 | 0 | 0 | 0 | 3284.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512184 | E-WW-I-02042021-GREENLAW PLACE WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1703.94 | 0 | 0 | 1703.94 | 0 | 0 | 0 | 0 | 1703.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512247 | E-WW-I-02042021-KELTY ST PCSO-INLET SCREEN REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-07 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25279.8 | 0 | 0 | 25279.8 | 0 | 0 | 0 | 0 | 25279.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512239 | E-WW-I-02042021-KINGHORN HARBOUR WWPS-REPLACE SCREEN COMPONENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-07 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5849.13 | 0 | 0 | 5849.13 | 0 | 0 | 0 | 0 | 5849.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512181 | E-WW-I-02042021-SOUTH KNOWE WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2075.78 | 0 | 0 | 2075.78 | 0 | 0 | 0 | 0 | 2075.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509701 | E-WW-I-02112020-COWDENBEATH SELKIRK AVE SST-NEW ACCESS ROAD | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-11-25 |  | 2021-03-26 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4788.25 | 4788.25 | 0 | 0 | 0 | 4788.25 | 0 | 0 | 0 | 0 | 4788.25 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504279 | E-WW-I-031219-7 ST GILES TCEDUNDEE-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 1331.27 | -1191.27 | 140 | 2000 | 0 | 0 | 2140 | 0 | 0 | 0 | 0 | 2140 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504365 | E-WW-I-041219-6 TRAQUIAR GARDENSPERTH-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 31030 | -10843.58 | 20186.42 | 10843.58 | 0 | 0 | 31030 | 0 | 0 | 0 | 0 | 31030 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511845 | E-WW-I-05032021-STRAIT PATHGARDENSTOWN-SEWER RELINING | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2565.37 | 2565.37 | 36648.19 | 0 | 0 | 39213.56 | 0 | 0 | 0 | 0 | 39213.56 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509720 | E-WW-I-05112020-DUNFERMLINE REX PARK SST-REPLACE STORM RETURN PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19462.94 | 19462.94 | -37.41 | 0 | 0 | 19425.53 | 0 | 0 | 0 | 0 | 19425.53 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504719 | E-WW-I-06012020-ASHBYGARVOCK RDLAURENCEKIRK-SEWER REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2449.61 | -2157.19 | 292.42 | 4177.41 | 0 | 0 | 4469.83 | 0 | 0 | 0 | 0 | 4469.83 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505159 | E-WW-I-06022020-213 BROAD STCOWDENBEATH-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-14 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 4280 | -4000 | 280 | 4000 | 0 | 0 | 4280 | 0 | 0 | 0 | 0 | 4280 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505168 | E-WW-I-06022020-51 SHAFTSBURY RDDUNDEE-SEWER RELAY 3M. | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-13 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 1819 | -1700 | 119 | 1700 | 0 | 0 | 1819 | 0 | 0 | 0 | 0 | 1819 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509747 | E-WW-I-06112020-GARMOUTH CORRIE COTTAGE-INSTALL APNRV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603.85 | 603.85 | 8626.36 | 0 | 0 | 9230.21 | 0 | 0 | 0 | 0 | 9230.21 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509760 | E-WW-I-06112020-LOSSIEMOUTH MARINER VILLA SST-INSTALL-REPLACEMENT APNRV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-11-25 |  | 2021-02-10 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7405.3 | 7405.3 | 0 | 0 | 0 | 7405.3 | 0 | 0 | 0 | 0 | 7405.3 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505164 | E-WW-I-07022020-10 ABERDEEN AVEKINGHORN-INSTALL MANHOLE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-13 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 3210 | -3000 | 210 | 3000 | 0 | 0 | 3210 | 0 | 0 | 0 | 0 | 3210 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512261 | E-WW-I-07042021-WHINNYKNOWE SPS-REPLACE NO1 FOUL PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168.23 | 0 | 0 | 1168.23 | 0 | 0 | 0 | 0 | 1168.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511856 | E-WW-I-08032021-10 ROSEMOUNT CRESCENTGLENROTHES-MANHOLE REBUILD | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1427.25 | 1427.25 | 20389.32 | 0 | 0 | 21816.57 | 0 | 0 | 0 | 0 | 21816.57 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507590 | E-WW-I-08072020-27-33 HOLYROOD STCARNOUSTIE-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-07-08 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16605.84 | 16605.84 | 4794.16 | 0 | 0 | 21400 | 0 | 0 | 0 | 0 | 21400 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504823 | E-WW-I-09012020-36 GRANGE PLACEARBROATH-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-24 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 6588.54 | 0 | 6588.54 | -2206.75 | 0 | 0 | 4381.79 | 0 | 0 | 0 | 0 | 4381.79 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508130 | E-WW-I-100820-111 Seafield Road Broughty Ferry-Drain Modification | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-08-10 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29700.6 | 29700.6 | 8819.4 | 0 | 0 | 38520 | 0 | 0 | 0 | 0 | 38520 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505297 | E-WW-I-11022020-1 DENBURN PLACEKIRKCALDY-SEWER REHAB 5M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 5004.83 | 0 | 5004.83 | 0 | 0 | 0 | 5004.83 | 0 | 0 | 0 | 0 | 5004.83 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505290 | E-WW-I-11022020-19 LANGHOUSE GREENCRAIL-SEWER REHAB 3M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2758.43 | 0 | 2758.43 | 0 | 0 | 0 | 2758.43 | 0 | 0 | 0 | 0 | 2758.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505231 | E-WW-I-11-02-2020-DUNCHOPPIN-NEW BYTH-TURRIFF-SEWER REHAB 7M- | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1945.44 | 0 | 1945.44 | 0 | 0 | 0 | 1945.44 | 0 | 0 | 0 | 0 | 1945.44 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504055 | E-WW-I-111119-25 ROSEANGLEDUNDEE-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-05 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 8145.76 | 0 | 8145.76 | -270.01 | 0 | 0 | 7875.75 | 0 | 0 | 0 | 0 | 7875.75 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504102 | E-WW-I-111119-BULLION COTTAGESINVERGOWRIE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-03 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1810.62 | 0 | 1810.62 | 864.38 | 0 | 0 | 2675 | 0 | 0 | 0 | 0 | 2675 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505304 | E-WW-I-12022020-108 THE HAZELSDUNDEE-SEWER REHAB 7M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 6903.57 | -1403.41 | 5500.16 | 1403.41 | 0 | 0 | 6903.57 | 0 | 0 | 0 | 0 | 6903.57 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505213 | E-WW-I-12022020-62 FRITHSIDE STFRASERBURGH-RECURRING CHOKES | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-17 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 9991.63 | 0 | 9991.63 | 0 | 0 | 0 | 9991.63 | 0 | 0 | 0 | 0 | 9991.63 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505201 | E-WW-I-12022020-72 MAIN STLEUCHARS-INSTALL MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-14 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1804.77 | 0 | 1804.77 | 0 | 0 | 0 | 1804.77 | 0 | 0 | 0 | 0 | 1804.77 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505197 | E-WW-I-12022020-78 LUMPHINANS RDLOCHGELLY-REPLACE MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-17 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1408.12 | 0 | 1408.12 | 0 | 0 | 0 | 1408.12 | 0 | 0 | 0 | 0 | 1408.12 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509770 | E-WW-I-121120-DOUGLAS TCE SEWER REPAIR | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-11-24 | 2021-02-12 | 2021-03-04 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28675 | 28675 | 0 | 0 | 0 | 28675 | 0 | 0 | 0 | 0 | 28675 | 209381.79 | [5 empty] | N | WWI | 100%
504453 | E-WW-I-121219-2 EAST GLEBE STONEHAVEN-REBUILD MANHOLE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2263.79 | -2053.79 | 210 | 3000 | 0 | 0 | 3210 | 0 | 0 | 0 | 0 | 3210 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504643 | E-WW-I-13012020-WOODSIDE COTTAGELUTHERMUIR-SEWER REHAB-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1294.03 | -1139.56 | 154.47 | 2206.75 | 0 | 0 | 2361.22 | 0 | 0 | 0 | 0 | 2361.22 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508190 | E-WW-I-130820-Lochty Sewer Damaged | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-08-17 | 2020-09-21 | 2020-10-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14341.07 | 14341.07 | 0 | 0 | 0 | 14341.07 | 0 | 0 | 0 | 0 | 14341.07 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504829 | E-WW-I-14012020-50 ANNAND RDELLON-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 4028.48 | 0 | 4028.48 | 0 | 0 | 0 | 4028.48 | 0 | 0 | 0 | 0 | 4028.48 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510405 | E-WW-I-14122020-CLIFF PLACEST CYRUSMONTROSE-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 821.96 | 821.96 | 11170.45 | 0 | 0 | 11992.41 | 0 | 0 | 0 | 0 | 11992.41 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511913 | E-WW-I-15032021-3-4 GLEBE PARKINCHTURE-SEWER REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 874.44 | 874.44 | 12491.99 | 0 | 0 | 13366.43 | 0 | 0 | 0 | 0 | 13366.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507183 | E-WW-I-150620-Kelty Siphon-Clean | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-06-23 | 2021-01-18 | 2021-08-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 100211.92 | 0 | 0 | 150211.92 | 0 | 0 | 0 | 0 | 150211.92 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507694 | E-WW-I-150720-BAIRD AVENUE DUNDEE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-07-17 | 2021-04-09 | 2021-11-22 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6501 | 6501 | 43498.64 | 0 | 0 | 49999.64 | 0 | 0 | 0 | 0 | 49999.64 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509287 | E-WW-I-151020-River Ore Trunk Sewer NDT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-11-06 | 2021-04-02 | 2021-04-07 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.14 | 1918.14 | 0 | 0 | 0 | 1918.14 | 0 | 0 | 0 | 0 | 1918.14 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504837 | E-WW-I-16012020-4 ELRICK CIRCLEBRIDGE OF DON-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 5663.7 | 0 | 5663.7 | 1675.27 | 0 | 0 | 7338.97 | 0 | 0 | 0 | 0 | 7338.97 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504834 | E-WW-I-16012020-75 LYNINGHILLSFOFAR-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 5567.5 | 0 | 5567.5 | 1387.5 | 0 | 0 | 6955 | 0 | 0 | 0 | 0 | 6955 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510479 | E-WW-I-16122020-STRATHALLAN DRIVEKIRKCALDY-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5248.06 | 5248.06 | 74972.37 | 0 | 0 | 80220.43 | 0 | 0 | 0 | 0 | 80220.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505306 | E-WW-I-17022020- 1 LICKLEY STREETPERTH-SEWER REHAB 3M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1719.24 | 0 | 1719.24 | 0 | 0 | 0 | 1719.24 | 0 | 0 | 0 | 0 | 1719.24 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504501 | E-WW-I-171219-56 JUSTICE MILL LANEABERDEEN-SEWER REHAB 3.5M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2021-05-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 3772.98 | -3404.51 | 368.47 | 4981.53 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510914 | E-WW-I-18012021-MILLFIELD PLACEFREUCHIE-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1593.75 | 1593.75 | 22767.8 | 0 | 0 | 24361.55 | 0 | 0 | 0 | 0 | 24361.55 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511917 | E-WWI-180321-River Ore Sewer - Thornton Bank Erosion | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-03-22 | 2021-09-15 | 2022-03-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.04 | 28.04 | 60000.01 | 0 | 0 | 60028.05 | 0 | 0 | 0 | 0 | 60028.05 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504503 | E-WW-I-191219-47 HAUGH ROADELGIN-SEWER REHAB 5.5M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 9647.84 | -1252.86 | 8394.98 | 5285.43 | 0 | 0 | 13680.41 | 0 | 0 | 0 | 0 | 13680.41 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504463 | E-WW-I-191219-ROSELEA COTTAGEGUILDTOWN-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 860.68 | -780.84 | 79.84 | 1140.59 | 0 | 0 | 1220.43 | 0 | 0 | 0 | 0 | 1220.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504956 | E-WW-I-22012020-49 DUNNICHEN RDKINGSMUIR-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 8297.58 | -597.5 | 7700.08 | 597.5 | 0 | 0 | 8297.58 | 0 | 0 | 0 | 0 | 8297.58 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511374 | E-WW-I-220221-Portlethen Burn of Finden - SW Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-03-04 | 2021-09-15 | 2022-04-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.15 | 104.15 | 25000 | 0 | 0 | 25104.15 | 0 | 0 | 0 | 0 | 25104.15 | 209381.79 | [5 empty] | N | WWI | 100%
511369 | E-WW-I-220221-Strathmiglo-River Bank Erosion | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-03-04 | 2021-09-15 | 2022-04-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.02 | 14.02 | 45000 | 0 | 0 | 45014.02 | 0 | 0 | 0 | 0 | 45014.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508133 | E-WW-I-224 St Fillans Road Dundee-Relay Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-08-13 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20985.01 | 20985.01 | 4694.99 | 0 | 0 | 25680 | 0 | 0 | 0 | 0 | 25680 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507414 | E-WW-I-23062020-INCHMACOBLE PARK SST-REPLACE FENCE & COVERS/FRAMES | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-08 |  | 2020-09-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9737 | 9737 | 0 | 0 | 0 | 9737 | 0 | 0 | 0 | 0 | 9737 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508984 | E-WW-I-23092020-1 WOODSIDE CRESCENTPERTH-REPLACEMENT HEADWALL | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6671.35 | 6671.35 | 3278.63 | 0 | 0 | 9949.98 | 0 | 0 | 0 | 0 | 9949.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504861 | E-WW-I-24012020-27 JAMES MITCHELL PLACEMINTLAW-MANHOLE REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2421.5 | 0 | 2421.5 | 0 | 0 | 0 | 2421.5 | 0 | 0 | 0 | 0 | 2421.5 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512140 | E-WW-I-25032021-KELTY SST-REPLACE PERIMETER FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-04-01 |  | 2021-06-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16585 | 0 | 0 | 16585 | 0 | 0 | 0 | 0 | 16585 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506837 | E-WW-I-260520-Fettercairn STW FE Outfall Pipe Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-05-28 | 2020-07-20 | 2021-05-14 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 95999.99 | 0 | 0 | 245999.99 | 0 | 0 | 0 | 0 | 245999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505035 | E-WW-I-27012020-11 DORWOOD PLACEMONTROSE-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 4280 | -43.26 | 4236.74 | 43.26 | 0 | 0 | 4280 | 0 | 0 | 0 | 0 | 4280 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504185 | E-WW-I-271119-15 METHVEN ROADKIRKCALDY-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 5511.52 | 0 | 5511.52 | -0.01 | 0 | 0 | 5511.51 | 0 | 0 | 0 | 0 | 5511.51 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505019 | E-WW-I-28012020-CLAYPOPTTS FC-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 18190 | -5057.15 | 13132.85 | 5057.15 | 0 | 0 | 18190 | 0 | 0 | 0 | 0 | 18190 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505556 | E-WW-I-28022020-PITMEDDEN OUTFALL-CONSTRUCT NEW ACCESS STEPS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-06 |  | 2020-08-26 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 308.84 | 4412 | 4720.84 | 0 | 0 | 0 | 4720.84 | 0 | 0 | 0 | 0 | 4720.84 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509551 | E-WW-I-29102020-GARTHDEE SYPHON HOUSE (SOUTH)-REPLACE HANDRAILS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-26 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2509.15 | 2509.15 | 0 | 0 | 0 | 2509.15 | 0 | 0 | 0 | 0 | 2509.15 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504273 | E-WW-I291119-COLLEGE MILL RDALMONDBANK-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-07 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 4269.93 | 0 | 4269.93 | 10.07 | 0 | 0 | 4280 | 0 | 0 | 0 | 0 | 4280 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512211 | E-WW-I-30032021-INCHTURE CROSSGATES SPS-REPLACEMENT FENCING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4039.28 | 0 | 0 | 4039.28 | 0 | 0 | 0 | 0 | 4039.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512204 | E-WW-I-30032021-KIRKCALDY WWPS-REPLACEMENT MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5272.47 | 0 | 0 | 5272.47 | 0 | 0 | 0 | 0 | 5272.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503908 | E-WW-I-301019-HAUGHS OF COSSANS FORFAR-REPAIR MANHOLE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 2544.41 | 0 | 2544.41 | 1093.59 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 3638 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509563 | E-WW-I-301020-DUNFERMLINE BANNERMAN ST | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-11-02 | 2020-11-05 | 2021-05-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46527 | 46527 | 3472.84 | 0 | 0 | 49999.84 | 0 | 0 | 0 | 0 | 49999.84 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506016 | E-WW-I-31032020-37 HOLYROOD ST CARNOUSTIE-SEWER REHAB 35M | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-04-01 |  | 2020-05-12 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17068.19 | 17068.19 | 0 | 0 | 0 | 17068.19 | 0 | 0 | 0 | 0 | 17068.19 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512231 | E-WW-I-31032021-KINTORE TRANSFER WWPS-MANHOLE REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-06 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6239.03 | 0 | 0 | 6239.03 | 0 | 0 | 0 | 0 | 6239.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503882 | E-WW-I-41119-3 ASHGROVE ROAD-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2021-05-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 13652.75 | 0 | 13652.75 | -9372.75 | 0 | 0 | 4280 | 0 | 0 | 0 | 0 | 4280 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503887 | E-WW-I-51119-197 WESTBURN RD-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2021-05-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 4955.3 | 4796.58 | 9751.88 | -2261.88 | 0 | 0 | 7490 | 0 | 0 | 0 | 0 | 7490 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503901 | E-WW-I-51119-75 MAIN STNEWMILLS-SEWER REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-06 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 16281.69 | -14671.69 | 1610 | 23000 | 0 | 0 | 24610 | 0 | 0 | 0 | 0 | 24610 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511634 | E-WWI-St Andrews Renew Sewer & Carry Out Other Required Repair Work | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2021-03-10 | 2021-12-06 | 2022-03-04 | 2022-09-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 117000 | 0 | 0 | 517000 | 0 | 0 | 0 | 0 | 517000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511007 | E-WW-NI-01022021-CAIRNEYHILL WWPS-REPLACE ROTORK ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.3 | 114.3 | 1632.9 | 0 | 0 | 1747.2 | 0 | 0 | 0 | 0 | 1747.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511104 | E-WW-NI-01022021-KINGSKETTLE SHORE RD WWPS-REFURB MCC BUILDING FLOORING & INSTALL SOAKAWAY ON ACCESS ROAD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-09 |  | 2021-05-08 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 238 | 3400 | 0 | 0 | 3638 | 0 | 0 | 0 | 0 | 3638 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511096 | E-WW-NI-01022021-PERTH SOUTH INCH PFPS P&K SPS-REPLACE ROTORK ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-09 |  | 2021-05-08 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495.53 | 495.53 | 7079 | 0 | 0 | 7574.53 | 0 | 0 | 0 | 0 | 7574.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511561 | E-WW-NI-01032021-INVERURIE WWTW-REPLACE RETURN LIQOUR PUMPS FLOW METER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.07 | 91.07 | 1193.22 | 0 | 0 | 1284.29 | 0 | 0 | 0 | 0 | 1284.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511550 | E-WW-NI-010321-New Aberdour WWTW Access bridge condition assessment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-29 | 2021-09-24 | 2022-05-09 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806.41 | 806.41 | 11999.97 | 0 | 0 | 12806.38 | 0 | 0 | 0 | 0 | 12806.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506144 | E-WW-NI-01042020-DALGETY BAY SOUTHERN WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-06-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7585.66 | 7585.66 | 0 | 0 | 0 | 7585.66 | 0 | 0 | 0 | 0 | 7585.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506041 | E-WW-NI-01042020-DRUMLITHIE WWTW-REPLACE ROTORK VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-07-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1761.76 | 1761.76 | 0 | 0 | 0 | 1761.76 | 0 | 0 | 0 | 0 | 1761.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506131 | E-WW-NI-01042020-ELGIN EDGAR RD SPS-REFURB PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-07-06 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8925.9 | 8925.9 | 0 | 0 | 0 | 8925.9 | 0 | 0 | 0 | 0 | 8925.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506458 | E-WW-NI-01052020-ARCHIESTOWN WWTW-INSTALL SUBMERSIBLE PUMP & TRANSFORMER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142.2 | 1142.2 | 0 | 0 | 0 | 1142.2 | 0 | 0 | 0 | 0 | 1142.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506520 | E-WW-NI-01052020-BANCHORY WWTW-REPAIRS TO PISTA GRIT CONVEYOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-07 |  | 2020-08-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9095 | 9095 | 0 | 0 | 0 | 9095 | 0 | 0 | 0 | 0 | 9095 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506475 | E-WW-NI-01052020-CUMINESTOWN WWTW-INSTALL SUBMERSIBLE PUMP & TRANSFORMER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-06 |  | 2020-07-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170.26 | 1170.26 | 0 | 0 | 0 | 1170.26 | 0 | 0 | 0 | 0 | 1170.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506460 | E-WW-NI-01052020-FORDYCE WWTW-INSTALL SUBMERSIBLE PUMP & TRANSFORMER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170.26 | 1170.26 | 0 | 0 | 0 | 1170.26 | 0 | 0 | 0 | 0 | 1170.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506504 | E-WW-NI-01052020-HUNTLY DEVERON RD WWPS-REPLACE PUMP 1&2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-29 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5456.42 | 5456.42 | 0 | 0 | 0 | 5456.42 | 0 | 0 | 0 | 0 | 5456.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506456 | E-WW-NI-01052020-KENNETHMONT WWTW-INSTALL SUBMERSIBLE PUMP & TRANSFORMER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142.2 | 1142.2 | 0 | 0 | 0 | 1142.2 | 0 | 0 | 0 | 0 | 1142.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506453 | E-WW-NI-01052020-LONGSIDE WWTW-INSTALL SUBMERSIBLE PUMP & TRANSFORMER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123.5 | 1123.5 | 0 | 0 | 0 | 1123.5 | 0 | 0 | 0 | 0 | 1123.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506466 | E-WW-NI01052020-NEW ABERDOUR WWTW-INSTALL SUBMERSIBLE PUMP & TRANSFORMER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-06 |  | 2020-07-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170.26 | 1170.26 | 0 | 0 | 0 | 1170.26 | 0 | 0 | 0 | 0 | 1170.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506481 | E-WW-NI-01052020-WILLOWBANK WWTW-INSTALL SUBMERSIBLE PUMP & TRANSFORMER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-06 |  | 2020-07-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170.26 | 1170.26 | 0 | 0 | 0 | 1170.26 | 0 | 0 | 0 | 0 | 1170.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506959 | E-WW-NI-01062020-FOWLIS WESTER WWTW-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-04 |  | 2020-06-17 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491.59 | 1491.59 | 0 | 0 | 0 | 1491.59 | 0 | 0 | 0 | 0 | 1491.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507079 | E-WW-NI-01062020-SCONE MURRAYSHALL WWPS-SUPPLY/ERECT POSTS & FENCING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-08 |  | 2020-06-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8097.2 | 8097.2 | 0 | 0 | 0 | 8097.2 | 0 | 0 | 0 | 0 | 8097.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507490 | E-WW-NI-01072020-KEITH WWTW-REPLACE COLLAPSED SECTION OF PIPE IN PUMP HOUSE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-08-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1512.98 | 1512.98 | 0 | 0 | 0 | 1512.98 | 0 | 0 | 0 | 0 | 1512.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508536 | E-WW-NI-01092020-FORFAR WWTW-REFURB COMPACTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-03 |  | 2020-09-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1923 | 1923 | 0 | 0 | 0 | 1923 | 0 | 0 | 0 | 0 | 1923 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509126 | E-WW-NI-01102020-ABERDOUR SHORE RD WWPS-RENEW KIOSK DOORS & WET WELL COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-12 |  | 2020-11-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4868.5 | 4868.5 | 0 | 0 | 0 | 4868.5 | 0 | 0 | 0 | 0 | 4868.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509114 | E-WW-NI-01102020-BRECHIN WWTW-REPLACE RETURN PUMPS PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-12 |  | 2020-11-17 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3582.57 | 3582.57 | 0 | 0 | 0 | 3582.57 | 0 | 0 | 0 | 0 | 3582.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509127 | E-WW-NI-01102020-CARDENDEN SST-WELFARE UPGRADE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-10-12 |  | 2020-11-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4146.25 | 4146.25 | 0 | 0 | 0 | 4146.25 | 0 | 0 | 0 | 0 | 4146.25 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509068 | E-WW-NI-01102020-CUPAR WWTW-REPLACE PRESSURE VESSEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-13 |  | 2020-10-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1446.11 | 1446.11 | 0 | 0 | 0 | 1446.11 | 0 | 0 | 0 | 0 | 1446.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509132 | E-WW-NI-01102020-MONTROSE WWTW-REPLACE FINAL EFFLUENT PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-09 |  | 2021-04-05 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23886.49 | 23886.49 | 0 | 0 | 0 | 23886.49 | 0 | 0 | 0 | 0 | 23886.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510227 | E-WW-NI-01122020-FRASERBURGH KESSOCK RD WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-10 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194.39 | 194.39 | 2777 | 0 | 0 | 2971.39 | 0 | 0 | 0 | 0 | 2971.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510208 | E-WW-NI-01122020-MAUD WWTW-WASHWATER PUMP REPLACEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-10 |  | 2021-03-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750.5 | 2750.5 | 0 | 0 | 0 | 2750.5 | 0 | 0 | 0 | 0 | 2750.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511112 | E-WW-NI-02022021-DURRIS WWTW-CONSTRUCT HUMUS TANK WALL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-09 |  | 2021-05-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389.14 | 4389.14 | 0 | 0 | 0 | 4389.14 | 0 | 0 | 0 | 0 | 4389.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511022 | E-WW-NI-02022021-ESSLEMONT CIRCLE WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-02 |  | 2021-05-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1745.58 | 1745.58 | 0 | 0 | 0 | 1745.58 | 0 | 0 | 0 | 0 | 1745.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511056 | E-WW-NI-02022021-HATTON OF CRUDEN WWTW-CIVIL GROUND REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-05 |  | 2021-04-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4066 | 4066 | 0 | 0 | 0 | 4066 | 0 | 0 | 0 | 0 | 4066 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511107 | E-WW-NI-02022021-KEMNAY WWTW-REFURBISH AERATOR NO1 ROTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-09 |  | 2021-03-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17976 | 17976 | 0 | 0 | 0 | 17976 | 0 | 0 | 0 | 0 | 17976 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505491 | E-WW-NI-02032020-BURNTISLAND STW-REPLACE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-03 |  | 2020-03-19 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1952.87 | 0 | 1952.87 | 0 | 0 | 0 | 1952.87 | 0 | 0 | 0 | 0 | 1952.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505647 | E-WW-NI-02032020-CHARLOTTE ST WWPS-SUPPLY 20FT STORAGE CONTAINER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-09-16 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 185.5 | 2650 | 2835.5 | 0 | 0 | 0 | 2835.5 | 0 | 0 | 0 | 0 | 2835.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511580 | E-WW-NI-02032021-CUPAR WWTW-REPLACE SUPERNATANT PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-04 |  | 2021-06-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127.28 | 127.28 | 1667.64 | 0 | 0 | 1794.92 | 0 | 0 | 0 | 0 | 1794.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506165 | E-WW-NI-02042020-ABERDOUR SHORE RD WWPS-FIT NEW PUMPS & PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-27 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2069.03 | 2069.03 | 29557.63 | 0 | 0 | 31626.66 | 0 | 0 | 0 | 0 | 31626.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506146 | E-WW-NI-02042020-ALFORD WWTW-REPLACE HST 1 DESLUDGE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-10-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4840.36 | 4840.36 | 0 | 0 | 0 | 4840.36 | 0 | 0 | 0 | 0 | 4840.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512187 | E-WW-NI-02042021-CUMINESTOWN WWTW-REPLACE HUMUS DESLUDGE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2153.06 | 0 | 0 | 2153.06 | 0 | 0 | 0 | 0 | 2153.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512241 | E-WW-NI-02042021-FOCHABERS WWTW-BUILDING & WELFARE REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-07 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17922.52 | 0 | 0 | 17922.52 | 0 | 0 | 0 | 0 | 17922.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512186 | E-WW-NI-02042021-WILLOWBANK WWTW-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108.52 | 0 | 0 | 1108.52 | 0 | 0 | 0 | 0 | 1108.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507019 | E-WW-NI-02062020-CROSSGATES HUMBUG PARK SPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-05 |  | 2020-06-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492.6 | 1492.6 | 0 | 0 | 0 | 1492.6 | 0 | 0 | 0 | 0 | 1492.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507084 | E-WW-NI-02062020-MILNATHORT WWTW-SUPPLY GRIT SCREW CLASSIFER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-10 |  | 2020-10-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17765.45 | 17765.45 | 0 | 0 | 0 | 17765.45 | 0 | 0 | 0 | 0 | 17765.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507022 | E-WW-NI-02062020-MONTROSE COBDEN ST CSO-REPLACE CSO SCREEN NO1 MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-06-05 |  | 2020-07-28 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346.2 | 1346.2 | 0 | 0 | 0 | 1346.2 | 0 | 0 | 0 | 0 | 1346.2 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506994 | E-WW-NI-02062020-NEWTYLE WWTW-REPLACE DO PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-04 |  | 2020-08-03 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2370.92 | 2370.92 | 0 | 0 | 0 | 2370.92 | 0 | 0 | 0 | 0 | 2370.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507129 | E-WW-NI-02062020-TAYPORT SPINNAKER POINT WWPS-INSTALL NEW PUMPS & PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-11 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922.78 | 922.78 | 15565.59 | 0 | 0 | 16488.37 | 0 | 0 | 0 | 0 | 16488.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507533 | E-WW-NI-02072020-FRASERBURGH LACKIEHEAD WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-09-11 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7794.61 | 7794.61 | 0 | 0 | 0 | 7794.61 | 0 | 0 | 0 | 0 | 7794.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507535 | E-WW-NI-02072020-MILNATHORT WWTW-REPLACEMENT DOORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-08-24 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7222.5 | 7222.5 | 0 | 0 | 0 | 7222.5 | 0 | 0 | 0 | 0 | 7222.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507537 | E-WW-NI-02072020-PITMEDDEN WWTW-INSTALL MLSS PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-08-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4391.92 | 4391.92 | 0 | 0 | 0 | 4391.92 | 0 | 0 | 0 | 0 | 4391.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508621 | E-WW-NI-02092020-CRAIL KIRK WYND WWPS-REPLACEMENT PUMPS & PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-15 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2396.47 | 2396.47 | 42077.48 | 0 | 0 | 44473.95 | 0 | 0 | 0 | 0 | 44473.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508542 | E-WW-NI-020920-Pitscottie SPS-Reinforce river banking to protect SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-09-04 | 2021-09-06 | 2022-03-07 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8652 | 8652 | 51348 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 60000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509081 | E-WW-NI-02102020-FORFAR WWTW-REPLACE PRV &PRC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-13 |  | 2020-11-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1471.07 | 1471.07 | 0 | 0 | 0 | 1471.07 | 0 | 0 | 0 | 0 | 1471.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509142 | E-WW-NI-02102020-KIRRIEMUIR WWTW-REPAIRS TO INLET SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7699.37 | 7699.37 | 0 | 0 | 0 | 7699.37 | 0 | 0 | 0 | 0 | 7699.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509136 | E-WW-NI-02102020-LOSSIEMOUTH INCHBROOM WWPS-REPLACEMENT RTU | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7218.29 | 7218.29 | 0 | 0 | 0 | 7218.29 | 0 | 0 | 0 | 0 | 7218.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509135 | E-WW-NI-02102020-MONTROSE WWTW-REPLACEMENT STORM MIXER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-12 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3254.38 | 3254.38 | 0 | 0 | 0 | 3254.38 | 0 | 0 | 0 | 0 | 3254.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509695 | E-WW-NI-02112020-CUPAR WWTW-REPLACE SLUDGE MIXER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1046.41 | 1046.41 | 14948.77 | 0 | 0 | 15995.18 | 0 | 0 | 0 | 0 | 15995.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509692 | E-WW-NI-02112020-GUARDBRIDGE WWTW-REPLACE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-25 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3010.85 | 3010.85 | 0 | 0 | 0 | 3010.85 | 0 | 0 | 0 | 0 | 3010.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509585 | E-WW-NI-02112020-NEWMACHAR WWTW-REPLACE INTERMEDIATE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-26 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547.76 | 1547.76 | 0 | 0 | 0 | 1547.76 | 0 | 0 | 0 | 0 | 1547.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510229 | E-WW-NI-02122020-DURRIS WWTW-DO PROBE INSTALLATION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-10 |  | 2021-04-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13386.88 | 13386.88 | 0 | 0 | 0 | 13386.88 | 0 | 0 | 0 | 0 | 13386.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510239 | E-WW-NI-02122020-FRIOCKHEIM WWTW-REPLACEMENT PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-10 |  | 2021-02-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3087.25 | 3087.25 | 0 | 0 | 0 | 3087.25 | 0 | 0 | 0 | 0 | 3087.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511127 | E-WW-NI-03022021-NEWMACHAR WWTW-INSTALL TURBIDITY MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-09 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524.04 | 524.04 | 7486.3 | 0 | 0 | 8010.34 | 0 | 0 | 0 | 0 | 8010.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511039 | E-WW-NI-03022021-TARVES BRAIKLAY PARK WWPS-INSTALL TELEMETRY HARDWARE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565.41 | 1565.41 | 0 | 0 | 0 | 1565.41 | 0 | 0 | 0 | 0 | 1565.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505659 | E-WW-NI-03032020-MONTROSE COBDEN ST WWPS-REPLACE GUIDERAILS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-04-02 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 3225.66 | 0 | 3225.66 | 0 | 0 | 0 | 3225.66 | 0 | 0 | 0 | 0 | 3225.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511820 | E-WW-NI-03032021-DUNFERMLINE WWTW-REPLACEMENT SENSOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4163.38 | 4163.38 | -216.15 | 0 | 0 | 3947.23 | 0 | 0 | 0 | 0 | 3947.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511836 | E-WW-NI-03032021-FORFAR WWTW-REPLACE MONITORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15919.63 | 15919.63 | 37311.66 | 0 | 0 | 53231.29 | 0 | 0 | 0 | 0 | 53231.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511592 | E-WW-NI-03032021-INVERURIE WWTW-REPLACE WASHWATER PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-04 |  | 2021-06-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.15 | 117.15 | 1534.92 | 0 | 0 | 1652.07 | 0 | 0 | 0 | 0 | 1652.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511833 | E-WW-NI-03032021-KINROSS WWTW-INSTALL PLATFORM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850.15 | 850.15 | 12145 | 0 | 0 | 12995.15 | 0 | 0 | 0 | 0 | 12995.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511604 | E-WW-NI-03032021-LAURENCEKIRK WWTW-REPLACE LIQUOR RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-04 |  | 2021-06-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.42 | 76.42 | 1001.28 | 0 | 0 | 1077.7 | 0 | 0 | 0 | 0 | 1077.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511824 | E-WW-NI-03032021-NEWMACHAR WWTW-INSTALL pH & TURBIDITY MONITORING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905.6 | 2905.6 | 6810 | 0 | 0 | 9715.6 | 0 | 0 | 0 | 0 | 9715.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506169 | E-WW-NI-03042020-DUNFERMLINE STC-REPLACE SOLIDS PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-27 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419.56 | 419.56 | 5993.68 | 0 | 0 | 6413.24 | 0 | 0 | 0 | 0 | 6413.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506119 | E-WW-NI-03042020-KINTORE TRANSFER SPS-INSTALL NEW ACCESS DOORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-04-27 |  | 2021-04-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5082.5 | 5082.5 | 0 | 0 | 0 | 5082.5 | 0 | 0 | 0 | 0 | 5082.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507036 | E-WW-NI-03062020-COMRIE WWTW-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-05 |  | 2020-07-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2488.14 | 2488.14 | 0 | 0 | 0 | 2488.14 | 0 | 0 | 0 | 0 | 2488.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507095 | E-WW-NI-03062020-FRIOCKHEIM WWTW-INSTALL 2XJET VAC SUBMERSIBLE AERATORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-10 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1876.71 | 1876.71 | 26810.1 | 0 | 0 | 28686.81 | 0 | 0 | 0 | 0 | 28686.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507090 | E-WW-NI-03062020-KIRKCALDY STC-REPLACE NO2 SLUDGE CAKE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-10 |  | 2020-10-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19478.8 | 19478.8 | 0 | 0 | 0 | 19478.8 | 0 | 0 | 0 | 0 | 19478.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507102 | E-WW-NI-03062020-WATERYBUTTS WWPS-REPLACEMENT PIPE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-10 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4564.96 | 4564.96 | -18.7 | 0 | 0 | 4546.26 | 0 | 0 | 0 | 0 | 4546.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507564 | E-WW-NI-03072020-DUNFERMLINE WWTW-COARSE SCREEN FLOORING REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-08 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266.49 | 266.49 | 3807 | 0 | 0 | 4073.49 | 0 | 0 | 0 | 0 | 4073.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507573 | E-WW-NI-03072020-FORFAR WWTW-REPLACE PRESSURE & RELIEF VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-07-28 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3621.37 | 3621.37 | 0 | 0 | 0 | 3621.37 | 0 | 0 | 0 | 0 | 3621.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507520 | E-WW-NI-03072020-GOURDON SILLYFLAT WWPS-REPLACE COVER & FRAME | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-11-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1733.4 | 1733.4 | 0 | 0 | 0 | 1733.4 | 0 | 0 | 0 | 0 | 1733.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507551 | E-WW-NI-03072020-IRONMILL BAY WWTW- H&S PLATFORM IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-08 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571.01 | 571.01 | 4628.12 | 0 | 0 | 5199.13 | 0 | 0 | 0 | 0 | 5199.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507561 | E-WW-NI-03072020-KINROSS WWTW-H&S HANDRAILING IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-08 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1105.37 | 1105.37 | 15791 | 0 | 0 | 16896.37 | 0 | 0 | 0 | 0 | 16896.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507514 | E-WW-NI-03072020-NEW ABERDOUR ST-REPLACE WHOLE PERIMETER FENCE & INSTALL NEW GATE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-06 |  | 2020-10-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1839.43 | 1839.43 | 0 | 0 | 0 | 1839.43 | 0 | 0 | 0 | 0 | 1839.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507581 | E-WW-NI-03072020-PERTH CITY WWTW-INSTALL 2XSOLITAX HIGHLINE DENSITY PROBES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-07-21 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7116.48 | 7116.48 | 0 | 0 | 0 | 7116.48 | 0 | 0 | 0 | 0 | 7116.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507541 | E-WW-NI-03072020-SANDEND WWPS-REPLACE FOUL PUMP 1-3 & LCP REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39451.24 | 39451.24 | -0.01 | 0 | 0 | 39451.23 | 0 | 0 | 0 | 0 | 39451.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508333 | E-WW-NI-03082020-PERTH CITY WWTW-REPLACE COVER & BARRIER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-25 |  | 2020-10-29 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3531 | 3531 | 0 | 0 | 0 | 3531 | 0 | 0 | 0 | 0 | 3531 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508578 | E-WW-NI-03092020-BANCHORY WWTW-REPLACE GEARBOX ON INLET SCREEN NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-04 |  | 2020-10-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100.97 | 2100.97 | 0 | 0 | 0 | 2100.97 | 0 | 0 | 0 | 0 | 2100.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508624 | E-WW-NI-03092020-BLAIRGOWRIE WWTW-INLET SCREEN REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-15 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7554.03 | 7554.03 | 462.59 | 0 | 0 | 8016.62 | 0 | 0 | 0 | 0 | 8016.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508637 | E-WW-NI-03092020-CRIEFF TURRET PARK WWPS-CONVERSION TO CONCERTOR PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-15 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308.72 | 1308.72 | 18696 | 0 | 0 | 20004.72 | 0 | 0 | 0 | 0 | 20004.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508644 | E-WW-NI-03092020-CUPAR WWTW-CENTRIFUGE REFURB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20777.26 | 20777.26 | 0 | 0 | 0 | 20777.26 | 0 | 0 | 0 | 0 | 20777.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508586 | E-WW-NI-03092020-CUPAR WWTW-REPLACE GEARBOX ON FST TANK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-15 |  | 2020-10-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1926 | 1926 | 0 | 0 | 0 | 1926 | 0 | 0 | 0 | 0 | 1926 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508581 | E-WW-NI-03092020-EDZELL WWTW-REPLACE MOTOR & ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-15 |  | 2020-11-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1678.46 | 1678.46 | 0 | 0 | 0 | 1678.46 | 0 | 0 | 0 | 0 | 1678.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508633 | E-WW-NI-03092020-ELGIN WARDS RD WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-15 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3290.25 | 3290.25 | 0 | 0 | 0 | 3290.25 | 0 | 0 | 0 | 0 | 3290.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508642 | E-WW-NI-03092020-KINTORE HALLFOREST AV WWPS-REPLACE PUMP NO1 & REFURB ON PUMP 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-27 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3905.56 | 3905.56 | 0 | 0 | 0 | 3905.56 | 0 | 0 | 0 | 0 | 3905.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508588 | E-WW-NI-03092020-LAURENCEKIRK WWTW-REPLACE BOOSTER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-15 |  | 2020-10-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188.42 | 1188.42 | 0 | 0 | 0 | 1188.42 | 0 | 0 | 0 | 0 | 1188.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508629 | E-WW-NI-03092020-MILNATHORT WWTW-REPLACE INLET SAMPLER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10941.9 | 10941.9 | 466.9 | 0 | 0 | 11408.8 | 0 | 0 | 0 | 0 | 11408.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508640 | E-WW-NI-03092020-STRICHEN MARKET TCE WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-15 |  | 2021-02-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4487.02 | 4487.02 | -18.7 | 0 | 0 | 4468.32 | 0 | 0 | 0 | 0 | 4468.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509599 | E-WW-NI-03112020-BALMEDIE WWTW-ACCESS ROAD REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2140 | 2140 | 0 | 0 | 0 | 2140 | 0 | 0 | 0 | 0 | 2140 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509708 | E-WW-NI-03112020-DRUMOAK WWTW-REFURB INLET SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-25 |  | 2021-03-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9948.62 | 9948.62 | 0 | 0 | 0 | 9948.62 | 0 | 0 | 0 | 0 | 9948.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510234 | E-WW-NI-03122020-FINDOCHTY EAST BEACH WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-10 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190.82 | 190.82 | 2726 | 0 | 0 | 2916.82 | 0 | 0 | 0 | 0 | 2916.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510135 | E-WW-NI-03122020-FORRES WWTW-REPLACE CRITICAL SPARE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-04 |  | 2021-02-13 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656.98 | 1656.98 | 0 | 0 | 0 | 1656.98 | 0 | 0 | 0 | 0 | 1656.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510124 | E-WW-NI-03122020-GLENFARG WWTW-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88.41 | 88.41 | 1262.99 | 0 | 0 | 1351.4 | 0 | 0 | 0 | 0 | 1351.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510246 | E-WW-NI-03122020-NEWTYLE WWTW-INLET ROTORK REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-10 |  | 2021-03-25 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1915.51 | 1915.51 | 1189.96 | 0 | 0 | 3105.47 | 0 | 0 | 0 | 0 | 3105.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510241 | E-WW-NI-03122020-ROSSIE ISLAND WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-10 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13910 | 13910 | 0 | 0 | 0 | 13910 | 0 | 0 | 0 | 0 | 13910 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505030 | E-WW-NI-04022020-BRECHIN WWTW-REPLACE NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-28 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1534.79 | 0 | 1534.79 | 0 | 0 | 0 | 1534.79 | 0 | 0 | 0 | 0 | 1534.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505134 | E-WW-NI-04022020-NEWPORT & TAYPORT WWTW-REPLACE SLUDGE MIXER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-12 |  | 2020-04-20 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 6672.97 | 2468.09 | 9141.06 | 0 | 0 | 0 | 9141.06 | 0 | 0 | 0 | 0 | 9141.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511060 | E-WW-NI-04022021-BALLATER WWTW-REPLACEMENT ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123.38 | 123.38 | 1762.55 | 0 | 0 | 1885.93 | 0 | 0 | 0 | 0 | 1885.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511050 | E-WW-NI-04022021-BURNSIDE DUNTRUNE ST-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-04 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94.5 | 94.5 | 1350 | 0 | 0 | 1444.5 | 0 | 0 | 0 | 0 | 1444.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511067 | E-WW-NI-04022021-DALGETY BAY SEALSTRAND WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-04 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.5 | 154.5 | 1940 | 0 | 0 | 2094.5 | 0 | 0 | 0 | 0 | 2094.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511064 | E-WW-NI-04022021-DUNNING WWTW-REFURBISH CENTRE COLUMN (FILTER NO1) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.79 | 173.79 | 2482.7 | 0 | 0 | 2656.49 | 0 | 0 | 0 | 0 | 2656.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511134 | E-WW-NI-04022021-INVERURIE WWTW-SUPPLY SPARE AUTOSAMPLER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-09 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428.09 | 428.09 | 6115.5 | 0 | 0 | 6543.59 | 0 | 0 | 0 | 0 | 6543.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511131 | E-WW-NI-04022021-LETHAM WWTW-DOOR REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-11 |  | 2021-04-02 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3370.5 | 3370.5 | 0 | 0 | 0 | 3370.5 | 0 | 0 | 0 | 0 | 3370.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505672 | E-WW-NI-04032020-FORGANDENNY WWTW-REPLACE BLOWER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-04-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 3699.93 | 0 | 3699.93 | 0 | 0 | 0 | 3699.93 | 0 | 0 | 0 | 0 | 3699.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505552 | E-WW-NI-04032020-LAURENCEKIRK WWTW-REPLACE PS DESLUDGE PUMP A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-06 |  | 2020-05-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 89.48 | 1278.34 | 1367.82 | 0 | 0 | 0 | 1367.82 | 0 | 0 | 0 | 0 | 1367.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505663 | E-WW-NI-04032020-MILNATHORT WWTW-INSTALL WALKWAY | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-15 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 800.38 | 11434 | 12234.38 | 0 | 0 | 0 | 12234.38 | 0 | 0 | 0 | 0 | 12234.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505667 | E-WW-NI-04032020-NEWBIGGING WWTW-FILTER BED DECOMMISIONING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-06-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 462 | 6600 | 7062 | 0 | 0 | 0 | 7062 | 0 | 0 | 0 | 0 | 7062 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511621 | E-WW-NI-04032021-ELIE ST-REPLACEMENT TOP BEARING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-04 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161.49 | 161.49 | 2115.84 | 0 | 0 | 2277.33 | 0 | 0 | 0 | 0 | 2277.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511610 | E-WW-NI-04032021-PERTH ISLAND VIEW WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-04 |  | 2021-06-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2445.25 | 2445.25 | 0 | 0 | 0 | 2445.25 | 0 | 0 | 0 | 0 | 2445.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506485 | E-WW-NI-04052020-BURNTISLAND FAMILARS SPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-06 |  | 2020-07-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2263.22 | 2263.22 | 0 | 0 | 0 | 2263.22 | 0 | 0 | 0 | 0 | 2263.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506513 | E-WW-NI-04052020-COMRIE WWTW-CONVERSION TO CONCERTOR PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-07 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 902.44 | 902.44 | 15826.98 | 0 | 0 | 16729.42 | 0 | 0 | 0 | 0 | 16729.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506486 | E-WW-NI-04052020-COMRIE WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-06 |  | 2020-05-16 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1334.04 | 1334.04 | 0 | 0 | 0 | 1334.04 | 0 | 0 | 0 | 0 | 1334.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507065 | E-WW-NI-04062020-DYCE AVENUE WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-08 |  | 2020-08-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2662.82 | 2662.82 | 0 | 0 | 0 | 2662.82 | 0 | 0 | 0 | 0 | 2662.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507106 | E-WW-NI-04062020-ERROL LAGOONS WWTW-ACCESS ROAD REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-10 |  | 2020-06-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWNI | 100%
507105 | E-WW-NI-04062020-KIRKTON OF SKENE CSO-INSTALL NEW SECURITY FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-06-10 |  | 2020-09-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4664.64 | 4664.64 | 0 | 0 | 0 | 4664.64 | 0 | 0 | 0 | 0 | 4664.64 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507045 | E-WW-NI-04062020-PERTH FRIARTON WWPS-REPLACEMENT MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-08 |  | 2020-06-17 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2606.31 | 2606.31 | 0 | 0 | 0 | 2606.31 | 0 | 0 | 0 | 0 | 2606.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508047 | E-WW-NI-040820-Blackford WWTW SPS-Replace pumps with Xylem Concertor pump system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-07 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12840.59 | 12840.59 | -229.64 | 0 | 0 | 12610.95 | 0 | 0 | 0 | 0 | 12610.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508119 | E-WW-NI-040820-Burnside Road WWPS-Construct Platform for H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-10 |  | 2021-03-05 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2790 | 2790 | -18.7 | 0 | 0 | 2771.3 | 0 | 0 | 0 | 0 | 2771.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508041 | E-WW-NI-040820-Burntisland Haugh Road WWPS-Various Building Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-21 |  | 2020-10-07 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7896.6 | 7896.6 | 0 | 0 | 0 | 7896.6 | 0 | 0 | 0 | 0 | 7896.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508042 | E-WW-NI-040820-Dunfermline WWTW-Replace 2 SC200 dual-channel controllers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.54 | 317.54 | 3964.43 | 0 | 0 | 4281.97 | 0 | 0 | 0 | 0 | 4281.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508044 | E-WW-NI-040820-Kincardine WWTW-Replace pumps with Xylem Concertor pump system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1181.68 | 1181.68 | 16881.2 | 0 | 0 | 18062.88 | 0 | 0 | 0 | 0 | 18062.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508048 | E-WW-NI-040820-Pitlochry WWTW-Remove old bellmouths and replace with like for like Ham Baker stainless steel units | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-06 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1874.11 | 1874.11 | 26772.67 | 0 | 0 | 28646.78 | 0 | 0 | 0 | 0 | 28646.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508669 | E-WW-NI-04092020-KELTY SST-BUILD RETAINING WALL | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-11-27 |  | 2020-07-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14537.38 | 14537.38 | 0 | 0 | 0 | 14537.38 | 0 | 0 | 0 | 0 | 14537.38 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508676 | E-WW-NI-04092020-MONTROSE WWTW-CASS BASIN REFURB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350186.62 | 350186.62 | 0 | 0 | 0 | 350186.62 | 0 | 0 | 0 | 0 | 350186.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508687 | E-WW-NI-04092020-TOCHIENEAL ST-REPLACE ST OUTFALL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-30 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6113.37 | 6113.37 | 0 | 0 | 0 | 6113.37 | 0 | 0 | 0 | 0 | 6113.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509716 | E-WW-NI-04112020-EDZELL WWTW-REFURB STORM SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687.96 | 687.96 | 9828 | 0 | 0 | 10515.96 | 0 | 0 | 0 | 0 | 10515.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509710 | E-WW-NI-04112020-JOHNSHAVEN BEACH RD SPS-REPLACE IMPELLORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-25 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8093.09 | 8093.09 | 0 | 0 | 0 | 8093.09 | 0 | 0 | 0 | 0 | 8093.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509715 | E-WW-NI-04112020-MONTROSE WWTW-REPLACEMENT VALVES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305.28 | 305.28 | 4361.2 | 0 | 0 | 4666.48 | 0 | 0 | 0 | 0 | 4666.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504313 | E-WW-NI-041219-ST FILLANS HOTEL SPS-INSTALL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-07-27 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 16344.08 | 6831.47 | 23175.55 | 0 | 0 | 0 | 23175.55 | 0 | 0 | 0 | 0 | 23175.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510148 | E-WW-NI-04122020-ABERCHIRDER WWTW-REPLACE STORM RETURN FLOW METER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-07 |  | 2021-03-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1361.43 | 1361.43 | 0 | 0 | 0 | 1361.43 | 0 | 0 | 0 | 0 | 1361.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510257 | E-WW-NI-04122020-CAIRNEYHILL DRUMMORMIE RD STORM WELL 1 WWPS-REPLACEMENT PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-11 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2836.6 | 2836.6 | 40522.85 | 0 | 0 | 43359.45 | 0 | 0 | 0 | 0 | 43359.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510256 | E-WW-NI-04122020-CAIRNEYHILL DRUMMORMIE RD STORM WELL 2 WWPS-REPLACEMENT PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-11 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3407 | 3407 | 48671.41 | 0 | 0 | 52078.41 | 0 | 0 | 0 | 0 | 52078.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510249 | E-WW-NI-04122020-DUNDURCAS ST-ACCESS REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-10 |  | 2021-03-14 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4194.4 | 4194.4 | 0 | 0 | 0 | 4194.4 | 0 | 0 | 0 | 0 | 4194.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510525 | E-WW-NI-05012021-BLAIRGOWRIE WWTW-REPLACE DO & MLSS PROBES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-05 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5849.72 | 5849.72 | 409.48 | 0 | 0 | 6259.2 | 0 | 0 | 0 | 0 | 6259.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510616 | E-WW-NI-05012021-INVERGOWRIE VILLAGE WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-12 |  | 2021-03-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3705.37 | 3705.37 | 0 | 0 | 0 | 3705.37 | 0 | 0 | 0 | 0 | 3705.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510522 | E-WW-NI-05012021-NORTH QUEENSFERRY CARLINGNOSE SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-05 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4656.64 | 0 | 0 | 4656.64 | 0 | 0 | 0 | 0 | 4656.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505136 | E-WW-NI-05022020-PETER HOWLING SPS-INSTALL FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-12 |  | 2020-07-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2491.71 | 921.59 | 3413.3 | 0 | 0 | 0 | 3413.3 | 0 | 0 | 0 | 0 | 3413.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511140 | E-WW-NI-05022021-DUNFERMLINE STC-REFURB SLUDGE CAKE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-11 |  | 2021-04-04 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5288.44 | 5288.44 | 0 | 0 | 0 | 5288.44 | 0 | 0 | 0 | 0 | 5288.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511141 | E-WW-NI-05022021-FOCHABERS WWTW-ROTORK REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-09 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.13 | 317.13 | 4530.45 | 0 | 0 | 4847.58 | 0 | 0 | 0 | 0 | 4847.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511079 | E-WW-NI-05022021-MAUD WWTW-REPLACE FLOW METER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-08 |  | 2021-03-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1622.12 | 1622.12 | 0 | 0 | 0 | 1622.12 | 0 | 0 | 0 | 0 | 1622.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511076 | E-WW-NI-05022021-MAUD WWTW-REPLACE INLET FINE SCREEN LEVEL SENSOR & MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-08 |  | 2021-05-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1328.1 | 1328.1 | -18.71 | 0 | 0 | 1309.39 | 0 | 0 | 0 | 0 | 1309.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505568 | E-WW-NI-05032020-PITLOCHRY FERRY CRESCENT WWPS-LOGGER INSTALLATION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 144.14 | 0 | 144.14 | 2059.15 | 0 | 0 | 2203.29 | 0 | 0 | 0 | 0 | 2203.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505676 | E-WW-NI-05032020-ST FILLANS MAIN SPS-REPLACE MACERATOR PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-05-15 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 201.04 | 2909.45 | 3110.49 | 0 | 0 | 0 | 3110.49 | 0 | 0 | 0 | 0 | 3110.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511633 | E-WW-NI-05032021-CARNOUSTIE BARRY WWPS-REPLACEMENT PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-05 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.73 | 143.73 | 1883.16 | 0 | 0 | 2026.89 | 0 | 0 | 0 | 0 | 2026.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511639 | E-WW-NI-05032021-CRIEFF WWTW-REPLACE POWER CABLE & CABLE REEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-08 |  | 2021-08-03 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 168 | 2201.16 | 0 | 0 | 2369.16 | 0 | 0 | 0 | 0 | 2369.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511841 | E-WW-NI-05032021-CUPAR ENGINEERING WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.8 | 198.8 | 2604.66 | 0 | 0 | 2803.46 | 0 | 0 | 0 | 0 | 2803.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511843 | E-WW-NI-05032021-INVERKEITHING PRESTON CRES WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.17 | 255.17 | 3343.2 | 0 | 0 | 3598.37 | 0 | 0 | 0 | 0 | 3598.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507108 | E-WW-NI-05062020-ALMONDBANK WWTW-INSTALL PST STAIRWAY & FLOOR PANELS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-10 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857.72 | 857.72 | 11967.3 | 0 | 0 | 12825.02 | 0 | 0 | 0 | 0 | 12825.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507077 | E-WW-NI-05062020-CRAIL WEST BRAES WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-08 |  | 2020-07-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2045.82 | 2045.82 | 0 | 0 | 0 | 2045.82 | 0 | 0 | 0 | 0 | 2045.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507121 | E-WW-NI-05062020-FORGANDENNY WWTW-REPLACE SAF UNIT AIR BLOWER NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-10-15 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180.56 | 3180.56 | 0 | 0 | 0 | 3180.56 | 0 | 0 | 0 | 0 | 3180.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507110 | E-WW-NI-05062020-OLDMELDRUM WWTW-REPLACE GEARBOX & MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-10 |  | 2020-06-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3989.68 | 3989.68 | 0 | 0 | 0 | 3989.68 | 0 | 0 | 0 | 0 | 3989.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508340 | E-WW-NI-05082020-NEWTYLE WWTW-REPLACEMENT INLET SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-25 |  | 2020-11-03 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11537.39 | 11537.39 | 0 | 0 | 0 | 11537.39 | 0 | 0 | 0 | 0 | 11537.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509652 | E-WW-NI-05112020-ARDLER WWTW-REPLACEMENT MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-25 |  | 2021-02-20 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.53 | 1368.53 | 0 | 0 | 0 | 1368.53 | 0 | 0 | 0 | 0 | 1368.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509648 | E-WW-NI-05112020-AUCHTERARDER WWTW-REFURB PST DESLUGE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-03-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2480.78 | 2480.78 | 0 | 0 | 0 | 2480.78 | 0 | 0 | 0 | 0 | 2480.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509719 | E-WW-NI-05112020-BLAIRGOWRIE WWTW-CRITICAL SPARES FOR INLET SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-25 |  | 2021-02-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4893.75 | 4893.75 | 0 | 0 | 0 | 4893.75 | 0 | 0 | 0 | 0 | 4893.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509728 | E-WW-NI-05112020-ELGIN CEMETERY WWPS-COVER REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470.96 | 470.96 | 6728 | 0 | 0 | 7198.96 | 0 | 0 | 0 | 0 | 7198.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509726 | E-WW-NI-05112020-LOSSIEMOUTH INCHBROOM WWPS-COVER REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 453.74 | 453.74 | 6482 | 0 | 0 | 6935.74 | 0 | 0 | 0 | 0 | 6935.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509697 | E-WW-NI-05112020-NEWMILL KEITH WWPS-LAY TYPE 1 ON ACCESS TRACK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-25 |  | 2021-04-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2985.3 | 2985.3 | 0 | 0 | 0 | 2985.3 | 0 | 0 | 0 | 0 | 2985.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504321 | E-WW-NI-051219-AUCHLEVEN WWTW-REPLACE MISSING HANDRAILS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-02-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5423 | 0 | 5423 | 0 | 0 | 0 | 5423 | 0 | 0 | 0 | 0 | 5423 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504324 | E-WW-NI-051219-FOCHABERS WWTW-REPLACE HUMUS SLUDGE PUMP NO 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-01-15 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 2712.45 | 0 | 2712.45 | 0 | 0 | 0 | 2712.45 | 0 | 0 | 0 | 0 | 2712.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504231 | E-WW-NI-051219-UDNY GREEN WWTW-H&S CONCERNS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 832.05 | -744.55 | 87.5 | 1250 | 0 | 0 | 1337.5 | 0 | 0 | 0 | 0 | 1337.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504316 | E-WW-NI-051219-VALLEYFIELD WWTW-INSTALL NEW FLORRING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-02-21 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 4104.52 | 0 | 4104.52 | 0 | 0 | 0 | 4104.52 | 0 | 0 | 0 | 0 | 4104.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504201 | E-WW-NI-0512-2019-NEWMACHAR WWTW-H&S ISSUES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1397.83 | 249.17 | 1647 | 600 | 0 | 0 | 2247 | 0 | 0 | 0 | 0 | 2247 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504209 | E-WW-NI-05122019-TARVES WWTW-H&S ISSUES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-02-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1337.5 | 0 | 1337.5 | 0 | 0 | 0 | 1337.5 | 0 | 0 | 0 | 0 | 1337.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504534 | E-WW-NI-06012020-BOWHOUSE STW-REPLACE MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1468.82 | 0 | 1468.82 | 135.71 | 0 | 0 | 1604.53 | 0 | 0 | 0 | 0 | 1604.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504691 | E-WW-NI-06012020-BRUCE EMBANKMENT WWPS-REPLACE FORWARDING PUMP (CRITICAL SPARE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-04-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 7839.78 | 0 | 7839.78 | 0 | 0 | 0 | 7839.78 | 0 | 0 | 0 | 0 | 7839.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504711 | E-WW-NI-06012020-IRONMILL BAY WWTW-HANDRAILING IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-06 |  | 2020-10-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 12161.26 | 11279.47 | 23440.73 | 87.5 | 0 | 0 | 23528.23 | 0 | 0 | 0 | 0 | 23528.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504529 | E-WW-NI-06012020-TAYPORT WWTW-REPLACE ROTORK (CRITICAL SPARE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1095.68 | 0 | 1095.68 | 0 | 0 | 0 | 1095.68 | 0 | 0 | 0 | 0 | 1095.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510547 | E-WW-NI-06012021-BLAIRHALL WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-12 |  | 2021-03-20 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1526.76 | 1526.76 | 0 | 0 | 0 | 1526.76 | 0 | 0 | 0 | 0 | 1526.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510637 | E-WW-NI-06012021-CUPAR HAUGH PARK WWPS-REPLACEMENT STORM PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2175.49 | 2175.49 | 29934.64 | 0 | 0 | 32110.13 | 0 | 0 | 0 | 0 | 32110.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510647 | E-WW-NI-06012021-DAVIOT WWTW-MCC BUILDING REFURB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6059.38 | 6059.38 | -13.88 | 0 | 0 | 6045.5 | 0 | 0 | 0 | 0 | 6045.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510630 | E-WW-NI-06012021-DUNFERMLINE STC-REPLACE SLUDGE CAKE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700.26 | 1700.26 | 23717.6 | 0 | 0 | 25417.86 | 0 | 0 | 0 | 0 | 25417.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510628 | E-WW-NI-06012021-KEMNAY WWTW-INSTALL BIO-CAGES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5795.51 | 5795.51 | -37.42 | 0 | 0 | 5758.09 | 0 | 0 | 0 | 0 | 5758.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510634 | E-WW-NI-06012021-KIRKCALDY SOUTHERTON GDNS WWPS-REPLACEMENT PANEL & PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2271.96 | 2271.96 | 31884.72 | 0 | 0 | 34156.68 | 0 | 0 | 0 | 0 | 34156.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510544 | E-WW-NI-06012021-LOWER LARGO DRUMMOCHY RD WWPS- REPLACE WET WELL COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135.8 | 135.8 | 1940 | 0 | 0 | 2075.8 | 0 | 0 | 0 | 0 | 2075.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510619 | E-WW-NI-06012021-NORTH QUEENSFERRY BATTERY HOUSE WWPS-REPLACEMENT KIOSK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-12 |  | 2021-03-05 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5879.61 | 5879.61 | -37.4 | 0 | 0 | 5842.21 | 0 | 0 | 0 | 0 | 5842.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510625 | E-WW-NI-06012021-OLDMELDRUM WWTW-INSTALL BIO-CAGES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5758.1 | 5758.1 | -0.01 | 0 | 0 | 5758.09 | 0 | 0 | 0 | 0 | 5758.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510652 | E-WW-NI-06012021-PORT ELPHINSTONE WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-12 |  | 2021-03-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3729.76 | 3729.76 | -18.72 | 0 | 0 | 3711.04 | 0 | 0 | 0 | 0 | 3711.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510550 | E-WW-NI-06012021-SCOTLANDWELL WWPS-REPLACE ACTUATED VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155.28 | 1155.28 | 0 | 0 | 0 | 1155.28 | 0 | 0 | 0 | 0 | 1155.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505137 | E-WW-NI-06022020-COWDENBEATH GRAY PARK SPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-12 |  | 2020-04-09 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1169.39 | 432.52 | 1601.91 | 0 | 0 | 0 | 1601.91 | 0 | 0 | 0 | 0 | 1601.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505141 | E-WW-NI-06022020-KIRRIEMUIR WWTW-REFURB AERATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-12 |  | 2020-04-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 5187.58 | 1956.11 | 7143.69 | 0 | 0 | 0 | 7143.69 | 0 | 0 | 0 | 0 | 7143.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505679 | E-WW-NI-06032020=MODLEY PARK ELLON WWPS-REFURBISH SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-03-17 |  | 2021-03-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 220.2 | 3936.93 | 4157.13 | 55.39 | 0 | 0 | 4212.52 | 0 | 0 | 0 | 0 | 4212.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505587 | E-WW-NI-06032020-ABERDEEN YORK PL WWPS-REFURB FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-04-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 159.6 | 2280.02 | 2439.62 | 0 | 0 | 0 | 2439.62 | 0 | 0 | 0 | 0 | 2439.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505696 | E-WW-NI-06032020-KIRKCALDY WWTW-INSTALL NEW MAIN INLET CHANNEL ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-16 |  | 2020-06-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 416.57 | 5195 | 5611.57 | 0 | 0 | 0 | 5611.57 | 0 | 0 | 0 | 0 | 5611.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505690 | E-WW-NI-06032020-KITTYBREWSTER WWPS-PUMP REPLACEMENT & INSTALL CONCERTOR CONTROL SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-16 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1103.41 | 15763.05 | 16866.46 | 0 | 0 | 0 | 16866.46 | 0 | 0 | 0 | 0 | 16866.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505590 | E-WW-NI-06032020-MEIGLE STW-CSO OUTFALL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-03-25 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 2653.6 | 0 | 2653.6 | 0 | 0 | 0 | 2653.6 | 0 | 0 | 0 | 0 | 2653.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505684 | E-WW-NI-06032020-WESTHILL WWPS-REPLACE ISOLATION VALVES/PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-08-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 880.13 | 12573.35 | 13453.48 | 0 | 0 | 0 | 13453.48 | 0 | 0 | 0 | 0 | 13453.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506115 | E-WW-NI-06042020-KEMNAY WWTW-REPLACE RETURN LIQOUR PUMP 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-28 |  | 2020-05-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3913.41 | 3913.41 | 0 | 0 | 0 | 3913.41 | 0 | 0 | 0 | 0 | 3913.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512252 | E-WW-NI-06042021-IDOCH COTTAGES ST-FENCE REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.03 | 0 | 0 | 1199.03 | 0 | 0 | 0 | 0 | 1199.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512254 | E-WW-NI-06042021-PORTSOY COWHYTHIE ST-FENCE REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1630.65 | 0 | 0 | 1630.65 | 0 | 0 | 0 | 0 | 1630.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512256 | E-WW-NI-06042021-SILVERHILLOCKS ST-FENCE & HANDRAIL REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138.9 | 0 | 0 | 1138.9 | 0 | 0 | 0 | 0 | 1138.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506580 | E-WW-NI-06052020-EAST WEMYSS WWTW-INSTALL LOUVRE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-13 |  | 2020-05-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3344.05 | 3344.05 | 0 | 0 | 0 | 3344.05 | 0 | 0 | 0 | 0 | 3344.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506552 | E-WW-NI-06052020-FORFAR WWTW-INSTALL NEW SEEPEX POLY DOSING PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-10-27 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16723.03 | 16723.03 | 0 | 0 | 0 | 16723.03 | 0 | 0 | 0 | 0 | 16723.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506570 | E-WW-NI-06052020-GRANGE WWPS-REPLACE FOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-13 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 724.75 | 724.75 | 10353.58 | 0 | 0 | 11078.33 | 0 | 0 | 0 | 0 | 11078.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506574 | E-WW-NI-06052020-RAVENSCRAIG SPS-REPLACEMENT PUMP SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-13 |  | 2020-10-15 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11808.27 | 11808.27 | 0 | 0 | 0 | 11808.27 | 0 | 0 | 0 | 0 | 11808.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507553 | E-WW-NI-06072020-BANCHORY WWTW-REPLACE GEARBOX ON ST 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-08-09 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2002.18 | 2002.18 | 0 | 0 | 0 | 2002.18 | 0 | 0 | 0 | 0 | 2002.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507558 | E-WW-NI-06072020-BANCHORY WWTW-REPLACEMENT STATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-07-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2145.35 | 2145.35 | 0 | 0 | 0 | 2145.35 | 0 | 0 | 0 | 0 | 2145.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509138 | E-WW-NI-06102020-GARDENSTOWN NEWBANK SPS-REPLACE FLOW METER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308.97 | 1308.97 | 0 | 0 | 0 | 1308.97 | 0 | 0 | 0 | 0 | 1308.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509120 | E-WW-NI-06102020-PETERHEAD RIVERVIEW SPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-12 |  | 2020-11-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2305.55 | 2305.55 | 0 | 0 | 0 | 2305.55 | 0 | 0 | 0 | 0 | 2305.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509145 | E-WW-NI-06102020-SCOONIEHILL SPS-REPLACE KIOSK DOORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-09 |  | 2021-03-13 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.5 | 1658.5 | 0 | 0 | 0 | 1658.5 | 0 | 0 | 0 | 0 | 1658.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509734 | E-WW-NI-06112020-BRECHIN STC-REPAIRS TO SLUDGE PRESS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 867.51 | 867.51 | 12393 | 0 | 0 | 13260.51 | 0 | 0 | 0 | 0 | 13260.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509683 | E-WW-NI-06112020-FORFAR BEULAH HOWE WWPS-REPLACE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-25 |  | 2021-02-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2592.38 | 2592.38 | -37.41 | 0 | 0 | 2554.97 | 0 | 0 | 0 | 0 | 2554.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509663 | E-WW-NI-06112020-MONTROSE WWTW-REPLACE FAULTY DO PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-25 |  | 2020-03-12 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1107.19 | 1107.19 | 0 | 0 | 0 | 1107.19 | 0 | 0 | 0 | 0 | 1107.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504337 | E-WW-NI-061219-ABERLOUR WWTW-ROOF REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 2474.59 | 1034.32 | 3508.91 | 0 | 0 | 0 | 3508.91 | 0 | 0 | 0 | 0 | 3508.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504330 | E-WW-NI-061219-CELLARDYKE THE HAVEN SPS-REPLACE PUMP NO 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-05-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 13162.61 | 5501.68 | 18664.29 | 0 | 0 | 0 | 18664.29 | 0 | 0 | 0 | 0 | 18664.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504259 | E-WW-NI-061219-ECHT WWTW-REPLACE INLET PUMP B | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-10 |  | 2020-05-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1552.41 | 943.07 | 2495.48 | 0 | 0 | 0 | 2495.48 | 0 | 0 | 0 | 0 | 2495.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504257 | E-WW-NI-061219-ELLON WWTW-REPLACE PST PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-10 |  | 2020-02-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1853.77 | 0 | 1853.77 | 0 | 0 | 0 | 1853.77 | 0 | 0 | 0 | 0 | 1853.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504220 | E-WW-NI-061219-HUNTLY MEADOWS WWPS-REPLACE PUMP 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-10 |  | 2019-12-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2043.91 | 0 | 2043.91 | 0 | 0 | 0 | 2043.91 | 0 | 0 | 0 | 0 | 2043.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504363 | E-WW-NI-061219-MINTLAW WWTW-REPLACE WASHWATER PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-02-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3676.09 | 0 | 3676.09 | 0 | 0 | 0 | 3676.09 | 0 | 0 | 0 | 0 | 3676.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504262 | E-WW-NI-061219-TARVES WWTW-REPLACE WASHWATER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-10 |  | 2020-02-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1669.2 | 0 | 1669.2 | 0 | 0 | 0 | 1669.2 | 0 | 0 | 0 | 0 | 1669.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504570 | E-WW-NI-07012020-BLACKFORD WWTW-REPLACE HUMUS FEED PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-03-05 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1288.24 | 0 | 1288.24 | 0 | 0 | 0 | 1288.24 | 0 | 0 | 0 | 0 | 1288.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504566 | E-WW-NI-07012020-COMRIE PORTERFIELD WWPS-REPLACE FOUL PUMP NO 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-03-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2201.2 | 0 | 2201.2 | 0 | 0 | 0 | 2201.2 | 0 | 0 | 0 | 0 | 2201.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504563 | E-WW-NI-07012020-MONTROSE WWTW-REPLACE FAULTY PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-01-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1288.74 | 0 | 1288.74 | 0 | 0 | 0 | 1288.74 | 0 | 0 | 0 | 0 | 1288.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510562 | E-WW-NI-07012021-BALLATER BRIG SQ WWPS-REPLACE STATION OUTSTATION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485.12 | 1485.12 | -37.4 | 0 | 0 | 1447.72 | 0 | 0 | 0 | 0 | 1447.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510564 | E-WW-NI-07012021-ELIE ST-REPLACE BOTTOM BEARING INTERNALS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-12 |  | 2021-03-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2608.66 | 2608.66 | 0 | 0 | 0 | 2608.66 | 0 | 0 | 0 | 0 | 2608.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510654 | E-WW-NI-07012021-FORDYCE WWTW-SIPHON REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466.16 | 466.16 | 6125 | 0 | 0 | 6591.16 | 0 | 0 | 0 | 0 | 6591.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510656 | E-WW-NI-07012021-INVERURIE CONGLASS FARM WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-12 |  | 2021-04-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4595.95 | 4595.95 | -13.88 | 0 | 0 | 4582.07 | 0 | 0 | 0 | 0 | 4582.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510657 | E-WW-NI-07012021-OLDMELDRUM WWTW-REPLACE FLOW & DO MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-12 |  | 2021-03-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3111.41 | 3111.41 | 0 | 0 | 0 | 3111.41 | 0 | 0 | 0 | 0 | 3111.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505147 | E-WW-NI-07022020-AUCHTERARDER WWTW-REPLACE HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-12 |  | 2020-05-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 2797.12 | 1034.55 | 3831.67 | 0 | 0 | 0 | 3831.67 | 0 | 0 | 0 | 0 | 3831.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506124 | E-WW-NI-07042020-CUMINESTOWN WWTW-INSTALL NEW SIPHON | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-08-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6660.75 | 6660.75 | 0 | 0 | 0 | 6660.75 | 0 | 0 | 0 | 0 | 6660.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506123 | E-WW-NI-07042020-LHANBRYDE BURNSIDE RD SPS-REFURB PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-05-13 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3204.7 | 3204.7 | 0 | 0 | 0 | 3204.7 | 0 | 0 | 0 | 0 | 3204.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512260 | E-WW-NI-07042021-FRIOCKHEIM WWTW-REPLACE CONTROL ROOM DOOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1337.49 | 0 | 0 | 1337.49 | 0 | 0 | 0 | 0 | 1337.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506584 | E-WW-NI-07052020-ST ANDREWS HARBOUR SPS-REPLACE VSD SOFTSTART PANELS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-13 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1144.16 | 1144.16 | 16059.16 | 0 | 0 | 17203.32 | 0 | 0 | 0 | 0 | 17203.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507638 | E-WW-NI-07072020-FORFAR WWTW-REPLACE ODOUR UNIT FANS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-13 |  | 2020-09-21 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5917.1 | 5917.1 | 0 | 0 | 0 | 5917.1 | 0 | 0 | 0 | 0 | 5917.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508684 | E-WW-NI-07092020-BRECHIN STC-REPLACE CRITICAL SPARES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-09-16 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1742.24 | 1742.24 | 0 | 0 | 0 | 1742.24 | 0 | 0 | 0 | 0 | 1742.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508732 | E-WW-NI-07092020-BRECHIN STC-REPLACEMENT SLUDGE FEED PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-09 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6552.37 | 6552.37 | 0 | 0 | 0 | 6552.37 | 0 | 0 | 0 | 0 | 6552.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508682 | E-WW-NI-07092020-DUNFERMLINE DORNOCH PLACE WWPS-REPLACEMENT PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2611.09 | 2611.09 | 0 | 0 | 0 | 2611.09 | 0 | 0 | 0 | 0 | 2611.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508731 | E-WW-NI-07092020-DUNKELD WWTW-INSTALL NEW HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-01 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280.75 | 280.75 | 3782.04 | 0 | 0 | 4062.79 | 0 | 0 | 0 | 0 | 4062.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508600 | E-WW-NI-070920-Inverurie STW GBT Panels | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-09-29 | 2021-02-08 | 2021-02-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5526.08 | 5526.08 | 0 | 0 | 0 | 5526.08 | 0 | 0 | 0 | 0 | 5526.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510210 | E-WW-NI-07122020-CRAIGELLACHIE WWTW-INSTALL ACCESS PATH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-10 |  | 2021-02-10 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388.86 | 1388.86 | 0 | 0 | 0 | 1388.86 | 0 | 0 | 0 | 0 | 1388.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510351 | E-WW-NI-07122020-INVERGOWRIE BURNSIDE RD WWPS-REPLACE FOUL PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1504.51 | 1504.51 | 21492.97 | 0 | 0 | 22997.48 | 0 | 0 | 0 | 0 | 22997.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510349 | E-WW-NI-07122020-NEW ABERDOUR WWTW-REPLACE DESLUDGE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-17 |  | 2021-03-13 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4134.91 | 4134.91 | 0 | 0 | 0 | 4134.91 | 0 | 0 | 0 | 0 | 4134.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510668 | E-WW-NI-08012021-FETTERANGUS WWTW-REPLACE INLET PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-13 |  | 2021-02-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4502.01 | 4502.01 | 0 | 0 | 0 | 4502.01 | 0 | 0 | 0 | 0 | 4502.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510639 | E-WW-NI-08012021-KIRKCALDY WWTW-REPLACE IMMERSION HEATER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.23 | 203.23 | 2705 | 0 | 0 | 2908.23 | 0 | 0 | 0 | 0 | 2908.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510678 | E-WW-NI-08012021-MAUD WWTW-REPLACE DESLUDGE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-14 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017.57 | 1017.57 | 14338.44 | 0 | 0 | 15356.01 | 0 | 0 | 0 | 0 | 15356.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510663 | E-WW-NI-08012021-MINTLAW WWTW-REPLACE STORM RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883.5 | 883.5 | 12423.2 | 0 | 0 | 13306.7 | 0 | 0 | 0 | 0 | 13306.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510683 | E-WW-NI-08012021-MONTROSE WWTW- REPLACE ODOUR CONTROL UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-14 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895.26 | 895.26 | 12255 | 0 | 0 | 13150.26 | 0 | 0 | 0 | 0 | 13150.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510676 | E-WW-NI-08012021-ROTHES WWTW-INLET SCREEN BASKET (CRITICAL SPARES REPLACEMENT) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-14 |  | 2021-03-28 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9713.96 | 9713.96 | 0 | 0 | 0 | 9713.96 | 0 | 0 | 0 | 0 | 9713.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511117 | E-WW-NI-08022021-CUPAR WWTW-REPLACE MOTOR & GEARBOX ON NO1 FST SCRAPER BRIDGE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-09 |  | 2021-05-08 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139.02 | 139.02 | 1985.95 | 0 | 0 | 2124.97 | 0 | 0 | 0 | 0 | 2124.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511776 | E-WW-NI-08032021-FRIOCKHEIM WWTW-RELOCATE PROBES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.77 | 92.77 | 1215.42 | 0 | 0 | 1308.19 | 0 | 0 | 0 | 0 | 1308.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511859 | E-WW-NI-08032021-INVERGOWRIE BURNSIDE RD WWPS-LIGHTING REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349.65 | 349.65 | 4581.12 | 0 | 0 | 4930.77 | 0 | 0 | 0 | 0 | 4930.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511861 | E-WW-NI-08032021-MONTROSE WWTW-MANHOLE REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378 | 378 | 4952.58 | 0 | 0 | 5330.58 | 0 | 0 | 0 | 0 | 5330.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506173 | E-WW-NI-08042020-LETHAM WWTW-REPLACE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-06-03 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2260.84 | 2260.84 | 0 | 0 | 0 | 2260.84 | 0 | 0 | 0 | 0 | 2260.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506145 | E-WW-NI-080420-MONIFIETH BURGH YARD STORM PUMP REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-04-10 | 2021-08-09 | 2021-11-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16607.56 | 16607.56 | 176392.45 | 0 | 0 | 193000 | 0 | 0 | 0 | 0 | 193000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507124 | E-WW-NI-08062020-DUNDEE CENTRAL TESCO WWPS-INSTALL NEW SITE BOLLARDS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-08-26 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1473.9 | 1473.9 | 0 | 0 | 0 | 1473.9 | 0 | 0 | 0 | 0 | 1473.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507584 | E-WW-NI-08072020-ELGIN NORTH ST CSO-KIOSK REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-08 |  | 2020-07-22 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3144.35 | 3144.35 | 0 | 0 | 0 | 3144.35 | 0 | 0 | 0 | 0 | 3144.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508736 | E-WW-NI-08092020-GLENFARG WWTW-REPLACEMENT KIOSK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2021-02-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33844.2 | 33844.2 | -37.41 | 0 | 0 | 33806.79 | 0 | 0 | 0 | 0 | 33806.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508744 | E-WW-NI-08092020-PERTH CITY WWTW-INSTALL 6 NEW UPS UNITS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7406.55 | 7406.55 | 0 | 0 | 0 | 7406.55 | 0 | 0 | 0 | 0 | 7406.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508740 | E-WW-NI-08092020-PERTH DOWER PLACE WWPS-REPLACEMENT KIOSK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-03 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5794.01 | 5794.01 | 0 | 0 | 0 | 5794.01 | 0 | 0 | 0 | 0 | 5794.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508649 | E-WW-NI-080920-Oldmeldrum STW Inlet Screw No.1 Lower Bearing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-09-29 | 2020-12-02 | 2021-07-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68889 | 68889 | 1111.13 | 0 | 0 | 70000.13 | 0 | 0 | 0 | 0 | 70000.13 | 90601.29 | [5 empty] | N | CM_WWI | 100%
510355 | E-WW-NI-08122020-ARCHIESTOWN WWTW-ACCESS ROAD REFURB & INSTALL PATH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3675.8 | 3675.8 | 0 | 0 | 0 | 3675.8 | 0 | 0 | 0 | 0 | 3675.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510224 | E-WW-NI-08122020-BANCHORY WWTW-REPLACE WORM GEAR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-10 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125.01 | 125.01 | 1785.84 | 0 | 0 | 1910.85 | 0 | 0 | 0 | 0 | 1910.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510218 | E-WW-NI-08122020-GUARDBRIDGE WWTW-SOFT START REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-10 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545.79 | 1545.79 | 0 | 0 | 0 | 1545.79 | 0 | 0 | 0 | 0 | 1545.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510216 | E-WW-NI-08122020-ST ANDREWS STC-REPLACEMENT COMPONENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-10 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1583.82 | 1583.82 | 0 | 0 | 0 | 1583.82 | 0 | 0 | 0 | 0 | 1583.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504662 | E-WW-NI-09012020-ABERFELDY WWTW-REFURB SLUDGE FEED PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-02-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2974.96 | 0 | 2974.96 | 0 | 0 | 0 | 2974.96 | 0 | 0 | 0 | 0 | 2974.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504683 | E-WW-NI-09012020-CULROSS BLACKADDRER HAVEN WWPS-REFURB WET WELL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-04-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 5641.9 | 4652.91 | 10294.81 | 0 | 0 | 0 | 10294.81 | 0 | 0 | 0 | 0 | 10294.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504676 | E-WW-NI-09012020-DUNFERMLINE STC-REFURB SLUDGE CAKE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-03-13 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 3656.74 | 0 | 3656.74 | 0 | 0 | 0 | 3656.74 | 0 | 0 | 0 | 0 | 3656.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504656 | E-WW-NI-09012020-IRONMILL BAY STW-REFURB SLUDGE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-01-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 3030.44 | 73.88 | 3104.32 | 0 | 0 | 0 | 3104.32 | 0 | 0 | 0 | 0 | 3104.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511229 | E-WW-NI-09022021-KINTORE ARNISTON WWPS-REPLACE WET WELL COVER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195.86 | 195.86 | 2798 | 0 | 0 | 2993.86 | 0 | 0 | 0 | 0 | 2993.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511225 | E-WW-NI-09022021-KINTORE LOCHBURN WWPS-REPLACE WET WELL COVER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271.25 | 271.25 | 3875 | 0 | 0 | 4146.25 | 0 | 0 | 0 | 0 | 4146.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511221 | E-WW-NI-09022021-TORPHINS INGLEBY SPS PNRV- APNRV REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-16 |  | 2021-04-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4154.57 | 4154.57 | 0 | 0 | 0 | 4154.57 | 0 | 0 | 0 | 0 | 4154.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505635 | E-WW-NI-09032020-NEWMACHAR WWTW-FIT NEW DOORS ON MCC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-10 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 129.5 | 1513.62 | 1643.12 | 336.38 | 0 | 0 | 1979.5 | 0 | 0 | 0 | 0 | 1979.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511777 | E-WW-NI-09032021-MAUD WWTW-SUPPLY NEW MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.8 | 92.8 | 1215.9 | 0 | 0 | 1308.7 | 0 | 0 | 0 | 0 | 1308.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505598 | E-WW-NI-090320-BLACKFORD WWTW-OUTFALL PROTECTION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-03-17 | 2020-03-17 | 2020-11-24 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 71442.98 | 75442.98 | 0 | 0 | 0 | 75442.98 | 0 | 0 | 0 | 0 | 75442.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506184 | E-WW-NI-09042020-MAUD WWTW-WINDOW REPLACEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-09-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1189.84 | 1189.84 | 0 | 0 | 0 | 1189.84 | 0 | 0 | 0 | 0 | 1189.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507185 | E-WW-NI-09062020-GLENCARSE STW-REPLACE LIQUOR RETURN PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-15 |  | 2020-09-17 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5249.42 | 5249.42 | 0 | 0 | 0 | 5249.42 | 0 | 0 | 0 | 0 | 5249.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507644 | E-WW-NI-09072020-ALEHOUSEWELL WWPS-REPLACE PUMPS 1 &2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-13 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12375.26 | 12375.26 | 0 | 0 | 0 | 12375.26 | 0 | 0 | 0 | 0 | 12375.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507609 | E-WW-NI-09072020-BRECHIN WWTW-REPLACEMENT ROTORK VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-10 |  | 2021-02-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675.41 | 1675.41 | 0 | 0 | 0 | 1675.41 | 0 | 0 | 0 | 0 | 1675.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507653 | E-WW-NI-09072020-KILCONQUHAR WWPS-UPGRADE FOUL PUMPS 1&2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-14 |  | 2021-03-04 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12988.84 | 12988.84 | -37.41 | 0 | 0 | 12951.43 | 0 | 0 | 0 | 0 | 12951.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507598 | E-WW-NI-09072020-MINTLAW WWTW-WINDOWS & DOOR REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-10 |  | 2020-09-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8084.92 | 8084.92 | 0 | 0 | 0 | 8084.92 | 0 | 0 | 0 | 0 | 8084.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507602 | E-WWNI-09072020-MONTROSE WWTW-GRIT SYSTEM INVESTIGATION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-10 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8377.2 | 8377.2 | 25862.8 | 0 | 0 | 34240 | 0 | 0 | 0 | 0 | 34240 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508754 | E-WW-NI-09092020-LONGFORGAN STATION RD WWPS-OVERPUMPING COST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-23 |  | 2020-11-11 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16665.44 | 16665.44 | 942.48 | 0 | 0 | 17607.92 | 0 | 0 | 0 | 0 | 17607.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509187 | E-WW-NI-09102020-FORRES WWTW-CONCRETE REPAIRS ON TANKS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-12 |  | 2020-11-02 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935.52 | 1935.52 | 0 | 0 | 0 | 1935.52 | 0 | 0 | 0 | 0 | 1935.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509689 | E-WW-NI-09112020-HUNTLY LENNOX TCE CSO-REPLACE ACCESS STEPS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165.2 | 165.2 | 2360 | 0 | 0 | 2525.2 | 0 | 0 | 0 | 0 | 2525.2 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509804 | E-WW-NI-09112020-LONGSIDE MARKETHILL SPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252.91 | 252.91 | 3613 | 0 | 0 | 3865.91 | 0 | 0 | 0 | 0 | 3865.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509802 | E-WW-NI-09112020-LOSSIEMOUTH SHORE ST WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647.25 | 647.25 | 4013.67 | 0 | 0 | 4660.92 | 0 | 0 | 0 | 0 | 4660.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504423 | E-WW-NI-091219-SCONE MURRAYSHALL WWPS-INSTALL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-04-09 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 11067.37 | 0 | 11067.37 | 0 | 0 | 0 | 11067.37 | 0 | 0 | 0 | 0 | 11067.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510357 | E-WW-NI-09122020-INVERURIE WWTW-SUPPLY MOBILE PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424.59 | 424.59 | 6065.58 | 0 | 0 | 6490.17 | 0 | 0 | 0 | 0 | 6490.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510236 | E-WW-NI-09122020-KINGSBARNS WWTW-REPLACE INLET PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-10 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108.91 | 1108.91 | 0 | 0 | 0 | 1108.91 | 0 | 0 | 0 | 0 | 1108.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504754 | E-WW-NI-10012020-ABERFELDY WWTW-OPTIONEERING EXERCISE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 5863.96 | -5163.96 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504652 | E-WW-NI-10012020-BODDAM HARBOUR ST WWPS-REPAIR CONCRETE PLINTH & PAVING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-08-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1246.09 | 1027.66 | 2273.75 | 0 | 0 | 0 | 2273.75 | 0 | 0 | 0 | 0 | 2273.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504640 | E-WW-NI-10012020-COWDENBEATH SPS-REPLACE WASHWATER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-05-15 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 713.67 | 588.57 | 1302.24 | 0 | 0 | 0 | 1302.24 | 0 | 0 | 0 | 0 | 1302.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504735 | E-WW-NI-10012020-KEITH WWTW-REPLACE STORM RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-03-23 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 5404.2 | 0 | 5404.2 | 0 | 0 | 0 | 5404.2 | 0 | 0 | 0 | 0 | 5404.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504638 | E-WW-NI-10012020-PITLOCHRY WWTW-REPLACE FE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-02-15 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1231.98 | 0 | 1231.98 | 86.24 | 0 | 0 | 1318.22 | 0 | 0 | 0 | 0 | 1318.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511232 | E-WW-NI-10022021-ALFORD WWTW-REPLACE FILTER COLUMN SEAL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688.06 | 688.06 | 9829.45 | 0 | 0 | 10517.51 | 0 | 0 | 0 | 0 | 10517.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511156 | E-WW-NI-10022021-BROUGHTY 54 CAMPHILL RD APNRV-PNRV REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-10 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680.03 | 1680.03 | 0 | 0 | 0 | 1680.03 | 0 | 0 | 0 | 0 | 1680.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511148 | E-WW-NI-10022021-BROUGHTY 60 CAMPHILL RD APNRV-PNRV REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-10 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680.03 | 1680.03 | 0 | 0 | 0 | 1680.03 | 0 | 0 | 0 | 0 | 1680.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511151 | E-WW-NI-10022021-FORFAR ORCHARD LOAN SPS-PNRV REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228.98 | 228.98 | 3271.1 | 0 | 0 | 3500.08 | 0 | 0 | 0 | 0 | 3500.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511145 | E-WW-NI-10022021-INVERURIE CANAL RD PNRV SPS-APNRV REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2440.76 | 2440.76 | 0 | 0 | 0 | 2440.76 | 0 | 0 | 0 | 0 | 2440.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511242 | E-WW-NI-10022021-MONTROSE WWTW-REPLACE FINAL EFFLUENT PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1834.94 | 1834.94 | 26213.4 | 0 | 0 | 28048.34 | 0 | 0 | 0 | 0 | 28048.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511236 | E-WW-NI-10022021-ST FILLANS MAIN SPS- H&S UPGRADE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966.35 | 966.35 | 13805 | 0 | 0 | 14771.35 | 0 | 0 | 0 | 0 | 14771.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505737 | E-WW-NI-10032020-BURGHEAD STATION RD SPS-INSTALL NEW FLAP VALVE/PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-10-09 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 305.45 | 6496.23 | 6801.68 | 0 | 0 | 0 | 6801.68 | 0 | 0 | 0 | 0 | 6801.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505750 | E-WW-NI-10032020-NEW ABERDOUR WWTW-REFURB RBC1&2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 516.15 | 9515.33 | 10031.48 | 0 | 0 | 0 | 10031.48 | 0 | 0 | 0 | 0 | 10031.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505746 | E-WW-NI-10032020-STAR OF MARKINCH SPS-BUILDING REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-05-05 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 315.7 | 4547.41 | 4863.11 | 0 | 0 | 0 | 4863.11 | 0 | 0 | 0 | 0 | 4863.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511721 | E-WW-NI-100321-METHVEN WWTW-REED BED REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 | 2021-03-25 | 2021-03-25 | 2021-06-29 | 2022-06-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370000.01 | 0 | 0 | 370000.01 | 0 | 0 | 0 | 0 | 370000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506265 | E-WW-NI-10042020-NEWMACHAR STATION RD SPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-10-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175.01 | 3175.01 | 0 | 0 | 0 | 3175.01 | 0 | 0 | 0 | 0 | 3175.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506266 | E-WW-NI-10042020-NEWMACHAR WWTW-EXTEND DECANT PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-09-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25873.93 | 25873.93 | 0 | 0 | 0 | 25873.93 | 0 | 0 | 0 | 0 | 25873.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506267 | E-WW-NI-10042020-NEWMACHAR WWTW-INSTALL 2X DEWATERING PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-24 |  | 2020-10-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24773.21 | 24773.21 | 0 | 0 | 0 | 24773.21 | 0 | 0 | 0 | 0 | 24773.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507187 | E-WW-NI-10062020-KIRKCALDY STW-REPLACE WASHWATER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-17 |  | 2020-08-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4838.01 | 4838.01 | 0 | 0 | 0 | 4838.01 | 0 | 0 | 0 | 0 | 4838.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507660 | E-WW-NI-10072020-ELGIN BRAELOSSIE WWPS-REPLACEMENT PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-14 |  | 2021-04-03 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7375.59 | 7375.59 | 152.13 | 0 | 0 | 7527.72 | 0 | 0 | 0 | 0 | 7527.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507657 | E-WW-NI-10072020-KEMNAY WWTW-INSTALL MLSS PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-14 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4391.92 | 4391.92 | 0 | 0 | 0 | 4391.92 | 0 | 0 | 0 | 0 | 4391.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508693 | E-WW-NI-10092020-ALFORD WWTW-INSTALLATION OF CHEMICAL DOSING UNIT (QP888) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-13 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9081.83 | 9081.83 | 128413.17 | 0 | 0 | 137495 | 0 | 0 | 0 | 0 | 137495 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508706 | E-WW-NI-10092020-COWDENBEATH WWPS-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-01 |  | 2020-11-25 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2006.26 | 2006.26 | 0 | 0 | 0 | 2006.26 | 0 | 0 | 0 | 0 | 2006.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508701 | E-WW-NI-10092020-DAVIOT WWTW-INSTALLATION OF CHEMICAL DOSING UNIT (CAUSTIC) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-13 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9352.16 | 9352.16 | 128387.77 | 0 | 0 | 137739.93 | 0 | 0 | 0 | 0 | 137739.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508704 | E-WW-NI-10092020-DAVIOT WWTW-INSTALLATION OF CHEMICAL DOSING UNIT (QP888) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-13 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9469.54 | 9469.54 | 128406.47 | 0 | 0 | 137876.01 | 0 | 0 | 0 | 0 | 137876.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508697 | E-WW-NI-10092020-DRUMOAK WWTW-INSTALLATION OF CHEMICAL DOSING UNIT (QP888) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-13 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9163.77 | 9163.77 | 128331.23 | 0 | 0 | 137495 | 0 | 0 | 0 | 0 | 137495 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508700 | E-WW-NI-10092020-DUNFERMLINE WWTW-INSTALLATION OF CHEMICAL DOSING UNIT (QP20) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-13 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9154.42 | 9154.42 | 128340.59 | 0 | 0 | 137495.01 | 0 | 0 | 0 | 0 | 137495.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508774 | E-WW-NI-10092020-FALKLAND WWPS-REPLACEMENT KIOSK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9242.1 | 9242.1 | 0 | 0 | 0 | 9242.1 | 0 | 0 | 0 | 0 | 9242.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508776 | E-WW-NI-10092020-INVERGOWRIE BURNSIDE RD SPS-REPLACE CRITICAL SPARE FOUL PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-09-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11339.3 | 11339.3 | 0 | 0 | 0 | 11339.3 | 0 | 0 | 0 | 0 | 11339.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508755 | E-WW-NI-10092020-NEWTON OF FALKLAND WWPS-KIOSK REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-11 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4568.9 | 4568.9 | 0 | 0 | 0 | 4568.9 | 0 | 0 | 0 | 0 | 4568.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509338 | E-WW-NI-101020-Forfar WWTW Rotork Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-27 |  | 2021-03-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551.9 | 2551.9 | 0 | 0 | 0 | 2551.9 | 0 | 0 | 0 | 0 | 2551.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504284 | E-WW-NI-101219-DALGETY BAY MAIN WWPS-REPLACE ACTUATED VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-02-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2192.43 | 0 | 2192.43 | 0 | 0 | 0 | 2192.43 | 0 | 0 | 0 | 0 | 2192.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504308 | E-WW-NI-101219-KILRENNY MILL WWPS-REPLACE PUMP NO 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-01-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2429.43 | 0 | 2429.43 | 0 | 0 | 0 | 2429.43 | 0 | 0 | 0 | 0 | 2429.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504426 | E-WW-NI-101219-MONTROSE WWTW-REFURB WETWELL CHAMBER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-08-21 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 9385.9 | 3923.07 | 13308.97 | 0 | 0 | 0 | 13308.97 | 0 | 0 | 0 | 0 | 13308.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510258 | E-WW-NI-10122020-DUNFERMLINE STC-REPLACE ROTORK ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-11 |  | 2021-03-04 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230.5 | 1230.5 | 0 | 0 | 0 | 1230.5 | 0 | 0 | 0 | 0 | 1230.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510366 | E-WW-NI-10122020-DUNNING WWTW-INLET SEWER FENCE REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199.5 | 199.5 | 2850 | 0 | 0 | 3049.5 | 0 | 0 | 0 | 0 | 3049.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510362 | E-WW-NI-10122020-KINCARDINE WWTW-INSTALL HANDRAILING & TOEBOARDS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295.05 | 295.05 | 4215 | 0 | 0 | 4510.05 | 0 | 0 | 0 | 0 | 4510.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510254 | E-WW-NI-10122020-LIMEKILNS ST-REPLACE OUTFALL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-11 |  | 2021-03-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2034.37 | 2034.37 | 0 | 0 | 0 | 2034.37 | 0 | 0 | 0 | 0 | 2034.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510255 | E-WW-NI-10122020-SALINE WWTW-REPLACE HUMUS SLUDGE RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-11 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1132.6 | 1132.6 | 0 | 0 | 0 | 1132.6 | 0 | 0 | 0 | 0 | 1132.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510745 | E-WW-NI-11012021-FORGANDENNY WWTW-INLET SCREEN BIN TIPPER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-19 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3314.83 | 3314.83 | -13.88 | 0 | 0 | 3300.95 | 0 | 0 | 0 | 0 | 3300.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510739 | E-WW-NI-11012021-LETHAM FIFE WWTW-FENCE REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-18 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575.5 | 1575.5 | 22240 | 0 | 0 | 23815.5 | 0 | 0 | 0 | 0 | 23815.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510741 | E-WW-NI-11012021-SCONE WWTW-REPLACEMENT PRIMARY LIFT PUMP NO3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-18 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278.77 | 278.77 | 3982.48 | 0 | 0 | 4261.25 | 0 | 0 | 0 | 0 | 4261.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505237 | E-WW-NI-11022020-DUNDEE CENTRAL TESCO WWPS-REPLACE STORM PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-05-01 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 2613.93 | 966.8 | 3580.73 | 0 | 0 | 0 | 3580.73 | 0 | 0 | 0 | 0 | 3580.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511249 | E-WW-NI-11022021-DURRIS FE WWPS-REPLACE FIINAL EFFLUENT PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287.17 | 287.17 | 4102.45 | 0 | 0 | 4389.62 | 0 | 0 | 0 | 0 | 4389.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511247 | E-WW-NI-11022021-KINGSKETTLE THE PADDOCK WWPS-REPLACE ACCES GATE & FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284.2 | 284.2 | 4060 | 0 | 0 | 4344.2 | 0 | 0 | 0 | 0 | 4344.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511251 | E-WW-NI-11022021-MONIFIETH BURGH YARD SPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-16 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3777.51 | 3777.51 | 0 | 0 | 0 | 3777.51 | 0 | 0 | 0 | 0 | 3777.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511181 | E-WW-NI-110221-Forres WWTW-Screw pump replacements | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2023-08-02 | 2025-02-07 | 2025-05-08 | 2026-04-15 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249999.96 | 0 | 0 | 249999.96 | 0 | 0 | 0 | 0 | 249999.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505762 | E-WW-NI-11032020-AUCHTERARDER CASTLETON RD SPS-REPLACE FOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-18 |  | 2020-04-09 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 324.63 | 4712.46 | 5037.09 | 0 | 0 | 0 | 5037.09 | 0 | 0 | 0 | 0 | 5037.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505755 | E-WW-NI-11032020-PERTH CITY WWTW-TOILET FACILITIES UPGRADE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-10-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 605.5 | 8687.41 | 9292.91 | 0 | 0 | 0 | 9292.91 | 0 | 0 | 0 | 0 | 9292.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511873 | E-WW-NI-11032021-COMRIE WWTW-SUPPLY NEW GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-17 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184.52 | 184.52 | 2417.64 | 0 | 0 | 2602.16 | 0 | 0 | 0 | 0 | 2602.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511868 | E-WW-NI-11032021-DUNFERMLINE WWTW-IINSTALL NEW POWER SUPPLY CABLE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454.81 | 454.81 | 5958.9 | 0 | 0 | 6413.71 | 0 | 0 | 0 | 0 | 6413.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511784 | E-WW-NI-11032021-KIRRIEMUIR WWTW-REPLACE WASHWATER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422.3 | 1422.3 | 0 | 0 | 0 | 1422.3 | 0 | 0 | 0 | 0 | 1422.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511881 | E-WW-NI-11032021-METHLICK WOOD WWPS-REPLACEMENT PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-17 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211.46 | 211.46 | 2770.5 | 0 | 0 | 2981.96 | 0 | 0 | 0 | 0 | 2981.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511796 | E-WW-NI-11032021-PERTH CITY WWTW-REPLACE GEARBOX & WHEEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.45 | 114.45 | 1499.52 | 0 | 0 | 1613.97 | 0 | 0 | 0 | 0 | 1613.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511865 | E-WW-NI-11032021-TARVES WWTW-PURCHASE & INSTALL SAF UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2233 | 2233 | 31900 | 0 | 0 | 34133 | 0 | 0 | 0 | 0 | 34133 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511751 | E-WW-NI-110321-NEW PITSLIGO WWTW 1992 NJ887568 - REPLACE MLSS PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-11 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2597.15 | 2597.15 | -163.55 | 0 | 0 | 2433.6 | 0 | 0 | 0 | 0 | 2433.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508344 | E-WW-NI-11082020-BRACO STW INLET WWPS-REPLACE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898.64 | 1898.64 | 26694.5 | 0 | 0 | 28593.14 | 0 | 0 | 0 | 0 | 28593.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508243 | E-WW-NI-11082020-PITLOCHRY WWTW-REPLACE HUMUS RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-19 |  | 2020-08-24 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4266.11 | 4266.11 | 0 | 0 | 0 | 4266.11 | 0 | 0 | 0 | 0 | 4266.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508154 | E-WW-NI-110820-Turriff WWTW-Scraper Bridge Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-13 |  | 2021-02-14 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23674.47 | 23674.47 | 6973.68 | 0 | 0 | 30648.15 | 0 | 0 | 0 | 0 | 30648.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508778 | E-WW-NI-11092020-KINGHORN HARBOUR WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8192.11 | 8192.11 | 0 | 0 | 0 | 8192.11 | 0 | 0 | 0 | 0 | 8192.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508711 | E-WW-NI-11092020-KINTORE TRANSFER WWPS-REPLACE UPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-01 |  | 2020-10-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1525.6 | 1525.6 | 0 | 0 | 0 | 1525.6 | 0 | 0 | 0 | 0 | 1525.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508779 | E-WW-NI-11092020-SOUTH ESPLANADE WWPS-INSTALL NEW ACCESS LADDER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-23 |  | 2021-03-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4108.8 | 4108.8 | 0 | 0 | 0 | 4108.8 | 0 | 0 | 0 | 0 | 4108.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509738 | E-WW-NI-11112020-CRIEFF WWTW-REPLACE POWER CABLE & CABLE REEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-25 |  | 2021-02-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2568 | 2568 | 0 | 0 | 0 | 2568 | 0 | 0 | 0 | 0 | 2568 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509811 | E-WW-NI-11112020-DUNFERMLINE WWTW-REPLACE STORM OUTFALL GRATINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242.5 | 1242.5 | 17750 | 0 | 0 | 18992.5 | 0 | 0 | 0 | 0 | 18992.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509735 | E-WW-NI-11112020-KINROSS WWTW-REPLACEMENT CSO SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8693.54 | 8693.54 | 46028.4 | 0 | 0 | 54721.94 | 0 | 0 | 0 | 0 | 54721.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509814 | E-WW-NI-11112020-ST MONANS WWTW-ACCESS ROAD REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-24 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24417.4 | 24417.4 | 0 | 0 | 0 | 24417.4 | 0 | 0 | 0 | 0 | 24417.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509929 | E-WW-NI-11112020-WELLBANK SPS-BUILDING REFURB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-03-06 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19378.77 | 19378.77 | 0 | 0 | 0 | 19378.77 | 0 | 0 | 0 | 0 | 19378.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510387 | E-WW-NI-11122020-BLACKFORD WWTW-DIVERT SLUDGE LIQUOR PUMP PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8067.35 | 8067.35 | 0 | 0 | 0 | 8067.35 | 0 | 0 | 0 | 0 | 8067.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510261 | E-WW-NI-11122020-BOWHOUSE WWTW-REPLACE SUPERNATANT RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-11 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369.99 | 1369.99 | 0 | 0 | 0 | 1369.99 | 0 | 0 | 0 | 0 | 1369.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510395 | E-WW-NI-11122020-BRODICK GARDENS WWPS-CONVERSION TO CONCERTOR PUMP SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1187.23 | 1187.23 | 16960.41 | 0 | 0 | 18147.64 | 0 | 0 | 0 | 0 | 18147.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510377 | E-WW-NI-11122020-CULLEN FINDLATER DR SPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.54 | 244.54 | 2921.59 | 0 | 0 | 3166.13 | 0 | 0 | 0 | 0 | 3166.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510370 | E-WW-NI-11122020-ROSEHEARTY WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211.61 | 211.61 | 3023 | 0 | 0 | 3234.61 | 0 | 0 | 0 | 0 | 3234.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510367 | E-WW-NI-11122020-STRATHMIGLO WWTW-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-17 |  | 2021-02-27 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4101.75 | 4101.75 | 0 | 0 | 0 | 4101.75 | 0 | 0 | 0 | 0 | 4101.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510687 | E-WW-NI-12012021-ELLON WWTW-REPLACE SLUDGE THICKENING PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-14 |  | 2021-02-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2097.59 | 2097.59 | 0 | 0 | 0 | 2097.59 | 0 | 0 | 0 | 0 | 2097.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505173 | E-WW-NI-12022020-MEIGLE WWTW-REPLACE FILTER COLUMN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-13 |  | 2020-07-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1000.52 | 370.06 | 1370.58 | 0 | 0 | 0 | 1370.58 | 0 | 0 | 0 | 0 | 1370.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511254 | E-WW-NI-12022021-STRICHEN APNRV WWPS-APNRV REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-16 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2756.84 | 2756.84 | 0 | 0 | 0 | 2756.84 | 0 | 0 | 0 | 0 | 2756.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511907 | E-WW-NI-12032021-DON SOUTH-PURCHASE 6 AUTOSAMPLERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1372.25 | 1372.25 | 19603.6 | 0 | 0 | 20975.85 | 0 | 0 | 0 | 0 | 20975.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506661 | E-WW-NI-12052020-CELLARDYKE THE HAVEN WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-19 |  | 2020-11-09 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18683 | 18683 | 0 | 0 | 0 | 18683 | 0 | 0 | 0 | 0 | 18683 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506665 | E-WW-NI-12052020-PERTH CITY WWTW-INLET SCREEN REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-19 |  | 2020-07-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20856.38 | 20856.38 | 0 | 0 | 0 | 20856.38 | 0 | 0 | 0 | 0 | 20856.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507195 | E-WW-NI-12062020-ABERCHIRDER IND ESTATE WWPS-REPLACE WET WELL COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-17 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294.35 | 294.35 | 4205 | 0 | 0 | 4499.35 | 0 | 0 | 0 | 0 | 4499.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507232 | E-WW-NI-12062020-BUCKIE RATHVEN SPS-REPLACE WET WELL COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-17 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251.49 | 251.49 | 2772.3 | 0 | 0 | 3023.79 | 0 | 0 | 0 | 0 | 3023.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507212 | E-WW-NI-12062020-ELGIN BRAELOSSIE WWPS-REPLACE WET WELL COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-17 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2887.38 | 2887.38 | -18.71 | 0 | 0 | 2868.67 | 0 | 0 | 0 | 0 | 2868.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507181 | E-WW-NI-12062020-FOCHABERS MILNECROFT SPS-REPLACE WET WELL COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1396.7 | 1396.7 | 77.76 | 0 | 0 | 1474.46 | 0 | 0 | 0 | 0 | 1474.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507219 | E-WW-NI-12062020-MACDUFF BARNHILL WWPS-REPLACE WET WELL COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-17 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247.46 | 247.46 | 3249.3 | 0 | 0 | 3496.76 | 0 | 0 | 0 | 0 | 3496.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507217 | E-WW-NI-12062020-NEW ABERDOUR WWPS-REPLACE WET WELL COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-17 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3016.84 | 3016.84 | -18.7 | 0 | 0 | 2998.14 | 0 | 0 | 0 | 0 | 2998.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503951 | E-WW-NI-121119-PITLESSIE CONCERTO SPS-REPLACE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-08-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 17530.52 | 0 | 17530.52 | 0 | 0 | 0 | 17530.52 | 0 | 0 | 0 | 0 | 17530.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503939 | E-WW-NI-121119-ST ANDREWS WWTW-REFURB PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2019-12-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 4463.69 | 0 | 4463.69 | 0 | 0 | 0 | 4463.69 | 0 | 0 | 0 | 0 | 4463.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509834 | E-WW-NI-12112020-KINROSS WWTW-REPLACEMENT INLET SCREENS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87491.76 | 0 | 0 | 87491.76 | 0 | 0 | 0 | 0 | 87491.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509824 | E-WW-NI-12112020-SALINE WWTW-INSTALL NEW HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-02-26 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3179.44 | 3179.44 | 0 | 0 | 0 | 3179.44 | 0 | 0 | 0 | 0 | 3179.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504339 | E-WW-NI-121219-KITTYBREWSTER WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-02-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1332.58 | 0 | 1332.58 | 0 | 0 | 0 | 1332.58 | 0 | 0 | 0 | 0 | 1332.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504338 | E-WW-NI-121219-NEWMACHAR WWTW-REPLACE WASHWATER PUMP B | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-03-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1662.35 | 0 | 1662.35 | 0 | 0 | 0 | 1662.35 | 0 | 0 | 0 | 0 | 1662.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510693 | E-WW-NI-13012021-ANSTRUTHER CORNCERES WWTW-REPLACE DETECTION SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-14 |  | 2021-02-26 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1670.77 | 1670.77 | -0.04 | 0 | 0 | 1670.73 | 0 | 0 | 0 | 0 | 1670.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510699 | E-WW-NI-13012021-COMRIE WWTW-REPLACEMENT MLSS PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-14 |  | 2021-03-07 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2479.06 | 2479.06 | 0 | 0 | 0 | 2479.06 | 0 | 0 | 0 | 0 | 2479.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510760 | E-WW-NI-13012021-DUNFERMLINE STC-REPLACEMENT BELTS & ROLLERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-19 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11670.78 | 11670.78 | 6310.5 | 0 | 0 | 17981.28 | 0 | 0 | 0 | 0 | 17981.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510747 | E-WW-NI-13012021-IRONMILL BAY WWTW-REPLACEMENT LIGHTING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-19 |  | 2021-03-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3753.53 | 3753.53 | 0 | 0 | 0 | 3753.53 | 0 | 0 | 0 | 0 | 3753.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510751 | E-WW-NI-13012021-MILNATHORT WWTW-INSTALL FLOWMETER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-19 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8329.24 | 8329.24 | -191.63 | 0 | 0 | 8137.61 | 0 | 0 | 0 | 0 | 8137.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510757 | E-WW-NI-13012021-ST MONANS WWTW-REPLACE DETECTION SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-19 |  | 2021-02-26 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3211.57 | 3211.57 | 0 | 0 | 0 | 3211.57 | 0 | 0 | 0 | 0 | 3211.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505245 | E-WW-NI-13022020-BRECHIN WWTW-REPLACE PRIMARY PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-05-06 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 2310.63 | 892.03 | 3202.66 | 0 | 0 | 0 | 3202.66 | 0 | 0 | 0 | 0 | 3202.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505241 | E-WW-NI-13022020-ELGIN TRINITY RD WWPS-INSTALL EMERGENCY LIGHTING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 2967.32 | -2701.4 | 265.92 | 3798.9 | 0 | 0 | 4064.82 | 0 | 0 | 0 | 0 | 4064.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505180 | E-WW-NI-13022020-KENNETHMONT WWTW-INSTALL GATES/HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-14 |  | 2020-03-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 75.67 | 0 | 75.67 | 0 | 0 | 0 | 75.67 | 0 | 0 | 0 | 0 | 75.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505187 | E-WW-NI-13022020-NEW BYTH WWTW-INSTALL LADDER/HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-14 |  | 2020-06-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1070.11 | 395.79 | 1465.9 | 0 | 0 | 0 | 1465.9 | 0 | 0 | 0 | 0 | 1465.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505193 | E-WW-NI-13022020-NEWBIGGING WWTW-REPLACE GRATINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-17 |  | 2020-06-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1814.5 | 671.11 | 2485.61 | 0 | 0 | 0 | 2485.61 | 0 | 0 | 0 | 0 | 2485.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505184 | E-WW-NI-13022020-STUARTFIELD WWTW-INSTALL HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-13 |  | 2021-03-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1077.92 | 398.68 | 1476.6 | 0 | 0 | 0 | 1476.6 | 0 | 0 | 0 | 0 | 1476.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505254 | E-WW-NI-13022020-TARVES STW-REPLACE INLET PENSTOCK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-04-09 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2490.61 | 921.19 | 3411.8 | 0 | 0 | 0 | 3411.8 | 0 | 0 | 0 | 0 | 3411.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505722 | E-WW-NI-13032020-BANCHORY WWTW-REPLACE FILTER 1 FEED PUMP A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-16 |  | 2020-05-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 139.68 | 1995.4 | 2135.08 | 0 | 0 | 0 | 2135.08 | 0 | 0 | 0 | 0 | 2135.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505776 | E-WW-NI-13032020-KINGSWELLS WWPS-FIT NEW PERIMETER FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-18 |  | 2020-04-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 179.2 | 2560 | 2739.2 | 0 | 0 | 0 | 2739.2 | 0 | 0 | 0 | 0 | 2739.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505714 | E-WW-NI-13032020-UDNY STATION WWTW-REPLACE INLET PUMP 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-16 |  | 2020-05-29 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 93.85 | 1340.73 | 1434.58 | 0 | 0 | 0 | 1434.58 | 0 | 0 | 0 | 0 | 1434.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511789 | E-WW-NI-13032021-BANCHORY WWTW-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94.55 | 94.55 | 1238.82 | 0 | 0 | 1333.37 | 0 | 0 | 0 | 0 | 1333.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511790 | E-WW-NI-13032021-FORFAR WWTW-REPLACE SOLENOID VALVE. | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110.78 | 110.78 | 1451.4 | 0 | 0 | 1562.18 | 0 | 0 | 0 | 0 | 1562.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511795 | E-WW-NI-13032021-MONTROSE BRAOCH RD WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.31 | 91.31 | 1196.4 | 0 | 0 | 1287.71 | 0 | 0 | 0 | 0 | 1287.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511911 | E-WW-NI-13032021-NEWMACHAR WWTW-REPLACE BLOWER B | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269.36 | 269.36 | 3529.14 | 0 | 0 | 3798.5 | 0 | 0 | 0 | 0 | 3798.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506668 | E-WW-NI-13052020-CHAPELHILL ST-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-19 |  | 2020-07-20 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3584.5 | 3584.5 | 0 | 0 | 0 | 3584.5 | 0 | 0 | 0 | 0 | 3584.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509358 | E-WW-NI-13102020-BOWHOUSE WWTW-ROOF REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-27 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4547.5 | 4547.5 | 0 | 0 | 0 | 4547.5 | 0 | 0 | 0 | 0 | 4547.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509247 | E-WW-NI-131020-Balmedie WWTW-Replace Grit Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-13 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1592.09 | 1592.09 | -29.89 | 0 | 0 | 1562.2 | 0 | 0 | 0 | 0 | 1562.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509244 | E-WW-NI-131020-Ceres WWTW-Replace Macerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-13 |  | 2020-10-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4090.61 | 4090.61 | 0 | 0 | 0 | 4090.61 | 0 | 0 | 0 | 0 | 4090.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509242 | E-WW-NI-131020-Daviot-WWTW SAF Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-13 |  | 2021-02-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2862.62 | 2862.62 | 0 | 0 | 0 | 2862.62 | 0 | 0 | 0 | 0 | 2862.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509249 | E-WW-NI-131020-Garthdee Syphon House (North)-Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-10-26 | 2021-01-05 | 2021-01-12 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21175.27 | 21175.27 | 0 | 0 | 0 | 21175.27 | 0 | 0 | 0 | 0 | 21175.27 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509243 | E-WW-NI-131020-Kemnay WWTW-Replace Auto sampler | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-13 |  | 2021-02-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8443.91 | 8443.91 | 0 | 0 | 0 | 8443.91 | 0 | 0 | 0 | 0 | 8443.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509783 | E-WW-NI-13112020-BALBEGGIE WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-25 |  | 2021-02-14 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231.22 | 1231.22 | 0 | 0 | 0 | 1231.22 | 0 | 0 | 0 | 0 | 1231.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509839 | E-WW-NI-13112020-BODDAM CLAYMORE DR WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383.63 | 383.63 | 4908.59 | 0 | 0 | 5292.22 | 0 | 0 | 0 | 0 | 5292.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509846 | E-WW-NI-13112020-CRUDEN BAY LOW BRAEHEADS WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.6 | 229.6 | 3280 | 0 | 0 | 3509.6 | 0 | 0 | 0 | 0 | 3509.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509857 | E-WW-NI-13112020-HUNTLY WWTW-UPGRADE WELFARE FACILITIES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20154.52 | 20154.52 | 0 | 0 | 0 | 20154.52 | 0 | 0 | 0 | 0 | 20154.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510771 | E-WW-NI-14012021-NEWBURGH WWTW-REPLACE 2XFE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-20 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8739.2 | 8739.2 | -18.7 | 0 | 0 | 8720.5 | 0 | 0 | 0 | 0 | 8720.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505203 | E-WW-NI-14022020-DUNSHALT WWPS-REPLACE ACTUATED VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-14 |  | 2020-03-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1124.57 | 0 | 1124.57 | 0 | 0 | 0 | 1124.57 | 0 | 0 | 0 | 0 | 1124.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505209 | E-WW-NI-14022020-NEWMACHAR STW-REPLACE FLOW METER/TRANSMITTERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-17 |  | 2020-05-16 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1598.48 | 591.22 | 2189.7 | 0 | 0 | 0 | 2189.7 | 0 | 0 | 0 | 0 | 2189.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505258 | E-WW-NI-14022020-PENNAN ST-REPLACE ST COVER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3510.26 | 1298.32 | 4808.58 | 0 | 0 | 0 | 4808.58 | 0 | 0 | 0 | 0 | 4808.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505260 | E-WW-NI-14022020-PETERHEAD KIRKTOWN WWPS-INVESTIGATE STORM PENSTOCK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 369.05 | 0 | 369.05 | -369.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWNI | 100%
506683 | E-WW-NI-14052020-ABOYNE WWTW-INSTALL FILTER ARM DIFFUSERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-21 |  | 2020-07-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7238.46 | 7238.46 | 0 | 0 | 0 | 7238.46 | 0 | 0 | 0 | 0 | 7238.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506674 | E-WW-NI-14052020-MAUD WWTW-REPLACE ISOLATION VALVES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-21 |  | 2020-07-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3894.8 | 3894.8 | 0 | 0 | 0 | 3894.8 | 0 | 0 | 0 | 0 | 3894.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506671 | E-WW-NI-14052020-TORPHINS WWTW-ACCESS GATE ALTERATIONS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-21 |  | 2020-08-13 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11958.86 | 11958.86 | 0 | 0 | 0 | 11958.86 | 0 | 0 | 0 | 0 | 11958.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506676 | E-WW-NI-14052020-TORPHINS WWTW-INSTALL FILTER ARMS DIFFUSERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-19 |  | 2020-07-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7238.46 | 7238.46 | 0 | 0 | 0 | 7238.46 | 0 | 0 | 0 | 0 | 7238.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508346 | E-WW-NI-14082020-BLACKFORD WWTW-REPLACEMENT STORM TANK MIXER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207.56 | 207.56 | 2965.08 | 0 | 0 | 3172.64 | 0 | 0 | 0 | 0 | 3172.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508350 | E-WW-NI-14082020-FORRES MACKENZIE DRIVE WWPS-REPLACE RTU | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-25 |  | 2020-02-12 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6513.61 | 6513.61 | 0 | 0 | 0 | 6513.61 | 0 | 0 | 0 | 0 | 6513.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508246 | E-WW-NI-14082020-METHVEN WWTW-REPLACE GRIT SYSTEM COMPRESSOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-19 |  | 2020-10-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257.62 | 2257.62 | 0 | 0 | 0 | 2257.62 | 0 | 0 | 0 | 0 | 2257.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509260 | E-WW-NI-141020-Forfar WWTW Sludge Pump Crit Spare Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-15 |  | 2020-11-20 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536.93 | 1536.93 | 0 | 0 | 0 | 1536.93 | 0 | 0 | 0 | 0 | 1536.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509264 | E-WW-NI-141020-Letham WWTW Replace RAS Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-15 |  | 2020-11-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4347.4 | 4347.4 | 0 | 0 | 0 | 4347.4 | 0 | 0 | 0 | 0 | 4347.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503933 | E-WW-NI-141119-CUPAR WWTW-REPLACE AERATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-01-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 8345.79 | 0 | 8345.79 | 0 | 0 | 0 | 8345.79 | 0 | 0 | 0 | 0 | 8345.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504764 | E-WW-NI-15012020-BRECHIN WWTW-REPLACE DOSING PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-06-03 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 3908.3 | 3223.19 | 7131.49 | 0 | 0 | 0 | 7131.49 | 0 | 0 | 0 | 0 | 7131.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504664 | E-WW-NI-15012020-COWDENBEATH SPS-REPLACE SCREEN & MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-02-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1362.01 | 0 | 1362.01 | 0 | 0 | 0 | 1362.01 | 0 | 0 | 0 | 0 | 1362.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510718 | E-WW-NI-15012021-BLAIRGOWRIE WWTW-REPLACE ROTORK ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-18 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1497.18 | 1497.18 | -37.41 | 0 | 0 | 1459.77 | 0 | 0 | 0 | 0 | 1459.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510778 | E-WW-NI-15012021-BURNTISLAND ROSS POINT WWPS-REPLACEMENT KIOSK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-20 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10015.2 | 10015.2 | 0 | 0 | 0 | 10015.2 | 0 | 0 | 0 | 0 | 10015.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510795 | E-WW-NI-15012021-FRASERBURGH LACKIEHEAD SPS-WET WELL CLEANING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17988.53 | 17988.53 | 0 | 0 | 0 | 17988.53 | 0 | 0 | 0 | 0 | 17988.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510791 | E-WW-NI-15012021-HOPEMAN HARBOUR WWPS-RTU REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-20 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3818.32 | 3818.32 | 3296.88 | 0 | 0 | 7115.2 | 0 | 0 | 0 | 0 | 7115.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510775 | E-WW-NI-15012021-KINCARDINE WWTW-REPLACEMENT INLET SCREEN NO1 BASKET | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-20 |  | 2021-03-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3401.4 | 3401.4 | 0 | 0 | 0 | 3401.4 | 0 | 0 | 0 | 0 | 3401.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510798 | E-WW-NI-15012021-KINGHORN HARBOUR WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491.07 | 8491.07 | -37.41 | 0 | 0 | 8453.66 | 0 | 0 | 0 | 0 | 8453.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510723 | E-WW-NI-15012021-NEWMILLS FOOTBALL PARK WWPS-REPLACEMENT WET WELL COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-18 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.06 | 177.06 | 1995 | 0 | 0 | 2172.06 | 0 | 0 | 0 | 0 | 2172.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511373 | E-WW-NI-15022021-BLAIRGOWRIE WWTW-REPLACE SCUM PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619.59 | 619.59 | 8851.3 | 0 | 0 | 9470.89 | 0 | 0 | 0 | 0 | 9470.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511370 | E-WW-NI-15022021-KINROSS WWTW-INSTALL 2XTOP WATER RETURN PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2315.66 | 2315.66 | 33080.8 | 0 | 0 | 35396.46 | 0 | 0 | 0 | 0 | 35396.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511381 | E-WW-NI-15022021-WINDSOR STREET WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-22 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392.12 | 392.12 | 5601.7 | 0 | 0 | 5993.82 | 0 | 0 | 0 | 0 | 5993.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511899 | E-WW-NI-15032021-ABERDOUR HOME PARK WWPS-SUPPLY & INSTALL RTU | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977.7 | 977.7 | 5274.66 | 0 | 0 | 6252.36 | 0 | 0 | 0 | 0 | 6252.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511808 | E-WW-NI-15032021-ABERLOUR WWTW-SITE LIGHTING REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.65 | 104.65 | 1371.12 | 0 | 0 | 1475.77 | 0 | 0 | 0 | 0 | 1475.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511848 | E-WW-NI-15032021-CUPAR HAUGH PARK WWPS-REPLACE FOUL PUMP NO3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.77 | 229.77 | 3010.5 | 0 | 0 | 3240.27 | 0 | 0 | 0 | 0 | 3240.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511798 | E-WW-NI-15032021-DUNFERMLINE WWTW-WALLHEAD REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 544.9 | 544.9 | 7139.28 | 0 | 0 | 7684.18 | 0 | 0 | 0 | 0 | 7684.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511892 | E-WW-NI-15032021-GUARDBRIDGE WWTW-REPLACE MLSS MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.16 | 229.16 | 3273.7 | 0 | 0 | 3502.86 | 0 | 0 | 0 | 0 | 3502.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511885 | E-WW-NI-15032021-KINGSKETTLE SHORE RD WWPS-FOUL WELL REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2624.32 | 2624.32 | 7420.2 | 0 | 0 | 10044.52 | 0 | 0 | 0 | 0 | 10044.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511852 | E-WW-NI-15032021-KIRKCALDY WWTW-REPLACE SULZER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574.41 | 574.41 | 7525.86 | 0 | 0 | 8100.27 | 0 | 0 | 0 | 0 | 8100.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511895 | E-WW-NI-15032021-LOWER LARGO THE TEMPLE WWPS-REPLACE 2XFOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508.34 | 508.34 | 6660.3 | 0 | 0 | 7168.64 | 0 | 0 | 0 | 0 | 7168.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511799 | E-WW-NI-15032021-MARYKIRK WWTW-REPLACE INLET ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.63 | 121.63 | 1593.6 | 0 | 0 | 1715.23 | 0 | 0 | 0 | 0 | 1715.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511803 | E-WW-NI-15032021-WHINNYKNOWE SPS-CONSTRUCT FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.15 | 136.15 | 1783.86 | 0 | 0 | 1920.01 | 0 | 0 | 0 | 0 | 1920.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506226 | E-WW-NI-15042020-BLACKFORD WWTW-REFURB HUMUS PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-05-07 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2006.88 | 2006.88 | 0 | 0 | 0 | 2006.88 | 0 | 0 | 0 | 0 | 2006.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506431 | E-WW-NI-15042020-MILNATHORT WWTW-REINTRODUCTION OXIDATION DITCH NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-06-08 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32685.41 | 32685.41 | 0 | 0 | 0 | 32685.41 | 0 | 0 | 0 | 0 | 32685.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506361 | E-WW-NI-15042020-NEW PITSLIGO STW-REPLACEMENT MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-08-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3268.85 | 3268.85 | 0 | 0 | 0 | 3268.85 | 0 | 0 | 0 | 0 | 3268.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506645 | E-WW-NI-15052020- NORTH QUEENSFERRY BATTERY RD SPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-18 |  | 2020-07-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1410.65 | 1410.65 | 0 | 0 | 0 | 1410.65 | 0 | 0 | 0 | 0 | 1410.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506647 | E-WW-NI-15052020-BERRYHILLOCK ST-MANHOLE REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-18 |  | 2020-05-26 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401.7 | 1401.7 | 0 | 0 | 0 | 1401.7 | 0 | 0 | 0 | 0 | 1401.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506635 | E-WW-NI-15052020-KINGSKETTLE SHORE RD WWPS-REPLACE ACTUATED VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-15 |  | 2020-07-25 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1408.58 | 1408.58 | 0 | 0 | 0 | 1408.58 | 0 | 0 | 0 | 0 | 1408.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506693 | E-WW-NI-15052020-ROTHES WWTW-INSTALL WATER & DRAINAGE CONNECTION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-04-12 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4023.2 | 4023.2 | 0 | 0 | 0 | 4023.2 | 0 | 0 | 0 | 0 | 4023.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507208 | E-WW-NI-15062020-IRONMILL BAY WWTW-REPLACE MOTOR ON AIR BLOWER NO3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-17 |  | 2020-07-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2094.16 | 2094.16 | 0 | 0 | 0 | 2094.16 | 0 | 0 | 0 | 0 | 2094.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507202 | E-WW-NI-15062020-THE PADDOCK WWPS-REPLACE TELEMETRY UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-17 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1690.52 | 1690.52 | -74.82 | 0 | 0 | 1615.7 | 0 | 0 | 0 | 0 | 1615.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507731 | E-WW-NI-15072020-CAIRNEYHILL DRUMMORMIE RD SPS-REPLACE STORM PUMP NO3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-17 |  | 2020-07-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2380.97 | 2380.97 | 0 | 0 | 0 | 2380.97 | 0 | 0 | 0 | 0 | 2380.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507722 | E-WW-NI-15072020-CRAIL HARBOUR WWPS-REPLACE COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-16 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884.81 | 884.81 | 1062.59 | 0 | 0 | 1947.4 | 0 | 0 | 0 | 0 | 1947.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507734 | E-WW-NI-15072020-CRIEFF HOLLYBUSH WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-17 |  | 2020-09-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028.42 | 2028.42 | 0 | 0 | 0 | 2028.42 | 0 | 0 | 0 | 0 | 2028.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507726 | E-WW-NI-15072020-CULROSS WESTEND WWPS-REPLACEMENT FOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-16 |  | 2020-07-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2621.16 | 2621.16 | 0 | 0 | 0 | 2621.16 | 0 | 0 | 0 | 0 | 2621.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507770 | E-WW-NI-15072020-DUNFERMLINE STC-FULLY REFURB SLUDGE CAKE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-21 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4055.7 | 4055.7 | -74.82 | 0 | 0 | 3980.88 | 0 | 0 | 0 | 0 | 3980.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507763 | E-WW-NI-15072020-MILESMARK WWPS-REPLACE 2X FOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-21 |  | 2020-09-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4226.03 | 4226.03 | 0 | 0 | 0 | 4226.03 | 0 | 0 | 0 | 0 | 4226.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507768 | E-WW-NI-15072020-MILNATHORT WWTW-UPGRADE WELFARE FACILITIES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-21 |  | 2020-08-13 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3862.66 | 3862.66 | 0 | 0 | 0 | 3862.66 | 0 | 0 | 0 | 0 | 3862.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508780 | E-WW-NI-15092020-MAUD WWTW-SLUDGE TRANSFER PUMP REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2319.16 | 2319.16 | -18.7 | 0 | 0 | 2300.46 | 0 | 0 | 0 | 0 | 2300.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508752 | E-WW-NI-150920-PERTH CITY WWTW-IFAS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2020-09-22 | 2021-05-24 | 2021-10-29 | 2023-05-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661142.56 | 661142.56 | 2871211.44 | 0 | 0 | 3532354 | 0 | 0 | 0 | 0 | 3532354 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503937 | E-WW-NI-151119-CUPAR WWTW-REPLACE ROTOR & STATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2019-12-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 3302.05 | 0 | 3302.05 | 0 | 0 | 0 | 3302.05 | 0 | 0 | 0 | 0 | 3302.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503964 | E-WW-NI-151119-FETTERCAIRN STW-REPLACE ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-01-29 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 2957.39 | 0 | 2957.39 | 0 | 0 | 0 | 2957.39 | 0 | 0 | 0 | 0 | 2957.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503926 | E-WW-NI-151119-KEITH WWTW-REPLACE GATE VALVES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2019-12-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2975.74 | 0 | 2975.74 | 0 | 0 | 0 | 2975.74 | 0 | 0 | 0 | 0 | 2975.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503954 | E-WW-NI-151119-KIRRIEMUIR STW-REPLACE GRATINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-03-05 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 5798.33 | 0 | 5798.33 | 0 | 0 | 0 | 5798.33 | 0 | 0 | 0 | 0 | 5798.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503971 | E-WW-NI-151119-LETHAM WWTW-REPLACE ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-01-28 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 3610.65 | 0 | 3610.65 | 0 | 0 | 0 | 3610.65 | 0 | 0 | 0 | 0 | 3610.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504001 | E-WW-NI-151119-MEIGLE WWTW-REPLACE FEED PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-02-25 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 21150.97 | 0 | 21150.97 | 0 | 0 | 0 | 21150.97 | 0 | 0 | 0 | 0 | 21150.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503959 | E-WW-NI-151119-PITSCOTTIE WWTW-REPLACE DISC AIR DIFFUSERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2019-12-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 3656.19 | 0 | 3656.19 | 0 | 0 | 0 | 3656.19 | 0 | 0 | 0 | 0 | 3656.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503872 | E-WW-NI-15112019-ELLON WWTW-BLOWER NO1 REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2019-12-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2353.57 | 0 | 2353.57 | 0 | 0 | 0 | 2353.57 | 0 | 0 | 0 | 0 | 2353.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510381 | E-WW-NI-15122020-FRASERBURGH BLACKCRAIG SPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223.68 | 223.68 | 2623.59 | 0 | 0 | 2847.27 | 0 | 0 | 0 | 0 | 2847.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510398 | E-WW-NI-15122020-KINNEFF WWTW-INSTALL FLEXIBLE DOSING SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-17 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13623.17 | 13623.17 | 0 | 0 | 0 | 13623.17 | 0 | 0 | 0 | 0 | 13623.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504784 | E-WW-NI-16012020-CUPAR WWTW-INSTALL MACERATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-02-26 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 11294.19 | 0 | 11294.19 | 0 | 0 | 0 | 11294.19 | 0 | 0 | 0 | 0 | 11294.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504789 | E-WW-NI-16012020-CUPAR WWTW-NEW SKIP BUILDING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 21186 | 0 | 21186 | 0 | 0 | 0 | 21186 | 0 | 0 | 0 | 0 | 21186 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504787 | E-WW-NI-16012020-CUPAR WWTW-PERSPEX BUILDING REMOVAL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-11 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 5992 | 0 | 5992 | 0 | 0 | 0 | 5992 | 0 | 0 | 0 | 0 | 5992 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504687 | E-WW-NI-16012020-STRICHEN WWTW-INSTALL HANDRAILING & GRATING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-06 |  | 2021-02-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 616.89 | 508.75 | 1125.64 | 0 | 0 | 0 | 1125.64 | 0 | 0 | 0 | 0 | 1125.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511393 | E-WW-NI-16022021-DUNFERMLINE STW INLET WWPS-INSTALL VARIABLE SPEED DRIVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.08 | 1116.08 | 15944 | 0 | 0 | 17060.08 | 0 | 0 | 0 | 0 | 17060.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511954 | E-WW-NI-16032021-CUPARMUIR SST-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646.8 | 646.8 | 8474.4 | 0 | 0 | 9121.2 | 0 | 0 | 0 | 0 | 9121.2 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511951 | E-WW-NI-16032021-EAST WEMYSS MAIN ST WWPS-REPLACE PUMPS & PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342.15 | 1342.15 | 19173.56 | 0 | 0 | 20515.71 | 0 | 0 | 0 | 0 | 20515.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511953 | E-WW-NI-16032021-NEW BYTH WWTW-H&S IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732.9 | 732.9 | 9602.46 | 0 | 0 | 10335.36 | 0 | 0 | 0 | 0 | 10335.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506366 | E-WW-NI-16042020-DUNFERLINE WWTW-REPAIR LEAK ON PST NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-27 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 525 | 7500 | 0 | 0 | 8025 | 0 | 0 | 0 | 0 | 8025 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506369 | E-WW-NI-16042020-WAULKMILL MERRYHILL WWPS- REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-11-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5450.57 | 5450.57 | 0 | 0 | 0 | 5450.57 | 0 | 0 | 0 | 0 | 5450.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507205 | E-WW-NI-160620-Anstruther Cornceres STW - Replace Inlet Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-08-03 | 2021-08-09 | 2022-03-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34369 | 34369 | 135630.72 | 0 | 0 | 169999.72 | 0 | 0 | 0 | 0 | 169999.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507746 | E-WW-NI-16072020-DALGETY BAY THE WYND SPS-REPLACE FOUL PUMP NO2 (CRITICAL SPARE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-17 |  | 2020-08-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1511.31 | 1511.31 | 0 | 0 | 0 | 1511.31 | 0 | 0 | 0 | 0 | 1511.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507789 | E-WW-NI-16072020-FORRES ADAM DRIVE WWPS-REPLACEMENT RTU | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-22 |  | 2020-10-21 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6656.44 | 6656.44 | 0 | 0 | 0 | 6656.44 | 0 | 0 | 0 | 0 | 6656.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507773 | E-WW-NI-16072020-KIRKCALDY WWTW-SUPPLY 2 WAY CONTROL VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-21 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4818.13 | 4818.13 | -74.82 | 0 | 0 | 4743.31 | 0 | 0 | 0 | 0 | 4743.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507777 | E-WW-NI-16072020-PERTH CITY WWTW-REPLACE SAS TRANSFER & TANK EMPTYING PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-22 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2967.62 | 2967.62 | 40678.99 | 0 | 0 | 43646.61 | 0 | 0 | 0 | 0 | 43646.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508199 | E-WW-NI-160820-Brechin WWTW-Refurb washwater pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-17 |  | 2020-10-13 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1915.09 | 1915.09 | 0 | 0 | 0 | 1915.09 | 0 | 0 | 0 | 0 | 1915.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508201 | E-WW-NI-160820-Dyke WWTW-Replace flow meter (E&M to install) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-17 |  | 2020-09-30 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510.36 | 1510.36 | 0 | 0 | 0 | 1510.36 | 0 | 0 | 0 | 0 | 1510.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508202 | E-WW-NI-160820-Dyke WWTW-Replace flow meter E&M to install | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-17 |  | 2020-11-13 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1529.06 | 1529.06 | 0 | 0 | 0 | 1529.06 | 0 | 0 | 0 | 0 | 1529.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508203 | E-WW-NI-160820-Forfar WWTW-Purchase and hold onsite critical spares | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-17 |  | 2020-10-24 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2082.46 | 2082.46 | 0 | 0 | 0 | 2082.46 | 0 | 0 | 0 | 0 | 2082.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508200 | E-WW-NI-160820-New Pitsligo WWTW-Replace parallel shaft helical gearmotor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-17 |  | 2020-09-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2491.2 | 2491.2 | 0 | 0 | 0 | 2491.2 | 0 | 0 | 0 | 0 | 2491.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508784 | E-WW-NI-160920-Kirkwall(Head of Work) STW-OSS water sludge trial | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-04-12 | 2021-07-02 | 2022-02-14 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31000 | 31000 | 0 | 0 | 0 | 31000 | 0 | 0 | 0 | 0 | 31000 | 311236.79 | [5 empty] | N | CM_M&G | 100%
509363 | E-WW-NI-16102020-VICTORIA BRIDGE WWPS-REPLACE MULTISMART CONTROLLER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-17 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4544.88 | 4544.88 | 0 | 0 | 0 | 4544.88 | 0 | 0 | 0 | 0 | 4544.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509936 | E-WW-NI-16112020-CARNOUSTIE HARRIS RD SPS-CONCERTOR UPGRADE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1137.76 | 1137.76 | 16253.76 | 0 | 0 | 17391.52 | 0 | 0 | 0 | 0 | 17391.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509820 | E-WW-NI-16112020-DUNFERMLINE STC-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-24 |  | 2020-08-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2891.42 | 2891.42 | 0 | 0 | 0 | 2891.42 | 0 | 0 | 0 | 0 | 2891.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509853 | E-WW-NI-16112020-GUARDBRIDGE MAIN ST WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-02-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342.29 | 1342.29 | 0 | 0 | 0 | 1342.29 | 0 | 0 | 0 | 0 | 1342.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509817 | E-WW-NI-16112020-NORTH QUEENSFERRY WWTW-REPLACE LOWER BEARING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-24 |  | 2020-08-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.28 | 2114.28 | 0 | 0 | 0 | 2114.28 | 0 | 0 | 0 | 0 | 2114.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509800 | E-WW-NI-161120-Newmill WWTW-Redundant asset demolition | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-02-12 | 2022-09-15 | 2023-04-28 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 44675.36 | 0 | 0 | 48675.36 | 0 | 0 | 0 | 0 | 48675.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504368 | E-WW-NI-161219-DAIRSIE WWTW-REPLACE FLOW MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-04-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1686.52 | 704.93 | 2391.45 | 0 | 0 | 0 | 2391.45 | 0 | 0 | 0 | 0 | 2391.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504373 | E-WW-NI-161219-KIRKCALDY CHARLOTTE ST WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-03-27 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 26141.22 | 0 | 26141.22 | 0 | 0 | 0 | 26141.22 | 0 | 0 | 0 | 0 | 26141.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504480 | E-WW-NI-161219-KIRKCALDY STW-REPLACE MOTOR FAN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-07 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2086.46 | -1892.91 | 193.55 | 2765 | 0 | 0 | 2958.55 | 0 | 0 | 0 | 0 | 2958.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504379 | E-WW-NI-161219-STRATHKINNESS SST-REPLACE WASHWATER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-01-29 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1280.79 | 0 | 1280.79 | 0 | 0 | 0 | 1280.79 | 0 | 0 | 0 | 0 | 1280.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504816 | E-WW-NI-17012020-BALMEDIE WWTW-REFURB INLET SCREEN 1&2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-08-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 11508.85 | 3331.26 | 14840.11 | 0 | 0 | 0 | 14840.11 | 0 | 0 | 0 | 0 | 14840.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504812 | E-WW-NI-17012020-BRIDGE OF EARN DURLEY DENE SPS-INSTALL CONCERTOR PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-05-21 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 9198.95 | 2662.66 | 11861.61 | 0 | 0 | 0 | 11861.61 | 0 | 0 | 0 | 0 | 11861.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504748 | E-WW-NI-17012020-DUNFERMLINE WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-04-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 4977.68 | 4105.12 | 9082.8 | 0 | 0 | 0 | 9082.8 | 0 | 0 | 0 | 0 | 9082.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504752 | E-WW-NI-17012020-DUNFERMLINE WWTW-REPLACE SAS ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-04-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2887.2 | 0 | 2887.2 | 0 | 0 | 0 | 2887.2 | 0 | 0 | 0 | 0 | 2887.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504815 | E-WW-NI-17012020-ELGIN EDGAR ROAD SPS-REFURB ACCESS PATH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-03-17 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 4961.6 | 0 | 4961.6 | 0 | 0 | 0 | 4961.6 | 0 | 0 | 0 | 0 | 4961.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504805 | E-WW-NI-17012020-ESSLEMONT CIRCLE WWPS-ROOF REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3166.54 | 2611.46 | 5778 | 0 | 0 | 0 | 5778 | 0 | 0 | 0 | 0 | 5778 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504713 | E-WW-NI-17012020-IRONMILL BAY WWTW-REPLACE POLYMER FEED PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-05-29 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1717.35 | 0 | 1717.35 | 0 | 0 | 0 | 1717.35 | 0 | 0 | 0 | 0 | 1717.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504828 | E-WW-NI-17012020-KIRRIEMUIR WWTW-REPLACE PROBES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-03-04 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 10737.21 | 0 | 10737.21 | 0 | 0 | 0 | 10737.21 | 0 | 0 | 0 | 0 | 10737.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504810 | E-WW-NI-17012020-MEIKLEMILL ELLON WWPS-ROOF REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 5966.33 | 1726.97 | 7693.3 | 0 | 0 | 0 | 7693.3 | 0 | 0 | 0 | 0 | 7693.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504808 | E-WW-NI-17012020-PETERHEAD KIRKTOWN WWPS-REMOVE REDUNDANT ASSETS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-05 |  | 2021-02-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 6606.95 | 1912.39 | 8519.34 | 0 | 0 | 0 | 8519.34 | 0 | 0 | 0 | 0 | 8519.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504715 | E-WW-NI-17012020-TOMNAVOULIN ST-INSTALL NEW FENCE & GATE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-02-25 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 2612.38 | 0 | 2612.38 | 0 | 0 | 0 | 2612.38 | 0 | 0 | 0 | 0 | 2612.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505281 | E-WW-NI-17022020-BALMEDIE ELGIE RD WWPS-REPLACE FAULTY FLOW METER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-03-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1285.18 | 0 | 1285.18 | 0 | 0 | 0 | 1285.18 | 0 | 0 | 0 | 0 | 1285.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505397 | E-WW-NI-17022020-CULROSS CENTRAL WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-25 |  | 2020-03-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 3755.06 | 112.23 | 3867.29 | 0 | 0 | 0 | 3867.29 | 0 | 0 | 0 | 0 | 3867.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505278 | E-WW-NI-17022020-DUNDEE BRIDGEFOOT WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-03-09 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 2053.63 | 149.64 | 2203.27 | 0 | 0 | 0 | 2203.27 | 0 | 0 | 0 | 0 | 2203.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505350 | E-WW-NI-17022020-FOWLIS SMIDDY BRAE WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-21 |  | 2020-04-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1702.95 | 629.86 | 2332.81 | 0 | 0 | 0 | 2332.81 | 0 | 0 | 0 | 0 | 2332.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505269 | E-WW-NI-17022020-INVERURIE WWTW-SUPPLY MOTOOR (CRITICAL SPARE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-03-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1044.92 | 0 | 1044.92 | 0 | 0 | 0 | 1044.92 | 0 | 0 | 0 | 0 | 1044.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505273 | E-WW-NI-17022020-MUTHILL WWTW-REPLACE SLUDGE TANK INLET VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-03-03 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1979.5 | 0 | 1979.5 | 0 | 0 | 0 | 1979.5 | 0 | 0 | 0 | 0 | 1979.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505398 | E-WW-NI-17022020-OAKLEY SST-FENCE REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-25 |  | 2020-08-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 4518.66 | 1727.41 | 6246.07 | 1645.18 | 0 | 0 | 7891.25 | 0 | 0 | 0 | 0 | 7891.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505899 | E-WW-NI-17032020-KIRKCALDY WWTW-REFURB LAMELLA DESLUDGE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-25 |  | 2020-04-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 3501.75 | 0 | 3501.75 | 0 | 0 | 0 | 3501.75 | 0 | 0 | 0 | 0 | 3501.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511854 | E-WW-NI-17032021-LOSSIE INCHBROOM WWPS-REPLACE LEG B PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288.46 | 288.46 | 3779.4 | 0 | 0 | 4067.86 | 0 | 0 | 0 | 0 | 4067.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511957 | E-WW-NI-17032021-MILNATHORT WWPS-INSTALL ELECTRIC CHAIN HOIST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314.65 | 314.65 | 4122.54 | 0 | 0 | 4437.19 | 0 | 0 | 0 | 0 | 4437.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511904 | E-WW-NI-17032021-THORNTON MAIN WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153.69 | 153.69 | 2013.72 | 0 | 0 | 2167.41 | 0 | 0 | 0 | 0 | 2167.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506370 | E-WW-NI-17042020-MEIGLE WWTW-REPLACE DRIVE SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-28 |  | 2020-05-19 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19998.06 | 19998.06 | 0 | 0 | 0 | 19998.06 | 0 | 0 | 0 | 0 | 19998.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507242 | E-WW-NI-17062020-GARDENSTOWN WWTW-REPLACE SHT LEVEL MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-17 |  | 2020-08-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213.04 | 1213.04 | 0 | 0 | 0 | 1213.04 | 0 | 0 | 0 | 0 | 1213.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507255 | E-WW-NI-17062020-KINCARDINE ONEIL WWTW-REPLACE FILTER GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-19 |  | 2020-08-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750.6 | 1750.6 | 0 | 0 | 0 | 1750.6 | 0 | 0 | 0 | 0 | 1750.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507252 | E-WW-NI-17062020-NEWMACHAR WWTW-ROAD IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-19 |  | 2020-09-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730.7 | 1730.7 | 0 | 0 | 0 | 1730.7 | 0 | 0 | 0 | 0 | 1730.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507806 | E-WW-NI-17072020-PERTH SOUTH INCH PFPS P&K SPS-REPLACE 4XCRAIGIE BURN STORM PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-22 |  | 2020-09-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180362.85 | 180362.85 | 991.16 | 0 | 0 | 181354.01 | 0 | 0 | 0 | 0 | 181354.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507809 | E-WW-NI-17072020-PERTH SOUTH INCH PFPS P&K SPS-REPLACE 4XSOUTH INCH STORM PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-22 |  | 2021-02-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWNI | 100%
508236 | E-WW-NI-17082020-BARRY WWPS-REPLACE WET WELL COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-18 |  | 2020-11-17 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1538.1 | 1538.1 | 0 | 0 | 0 | 1538.1 | 0 | 0 | 0 | 0 | 1538.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508238 | E-WW-NI-17082020-BRECHIN WWTW-REPLACE SLUDGE LOGGER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-19 |  | 2020-09-08 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2563.11 | 2563.11 | 0 | 0 | 0 | 2563.11 | 0 | 0 | 0 | 0 | 2563.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508359 | E-WW-NI-17082020-BURNTISLAND LAMMERLAWS WWPS-REPLACE KIOSK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-10-13 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5646.9 | 5646.9 | 0 | 0 | 0 | 5646.9 | 0 | 0 | 0 | 0 | 5646.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508354 | E-WW-NI-17082020-COWDENBEATH WETLAND WWTW- REPLACE TRANSFER STORM PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-10-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6015.42 | 6015.42 | 0 | 0 | 0 | 6015.42 | 0 | 0 | 0 | 0 | 6015.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508240 | E-WW-NI-17082020-TAYPORT NELSON ST WWPS-REPLACE COVERS & FRAMES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-18 |  | 2020-09-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.5 | 2086.5 | 0 | 0 | 0 | 2086.5 | 0 | 0 | 0 | 0 | 2086.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508204 | E-WW-NI-170820-East Wemyss STW-Replace both inlet screw pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-08-19 | 2021-03-15 | 2021-06-21 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107174 | 107174 | 90711.93 | 0 | 0 | 197885.93 | 0 | 0 | 0 | 0 | 197885.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508786 | E-WW-NI-17092020-ABERDOUR ST FILLANS WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-05 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1410.65 | 1410.65 | 0 | 0 | 0 | 1410.65 | 0 | 0 | 0 | 0 | 1410.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508799 | E-WW-NI-17092020-ARDLER WWTW-REPLACE INVERTER DRIVE & MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-09-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349.27 | 1349.27 | 0 | 0 | 0 | 1349.27 | 0 | 0 | 0 | 0 | 1349.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508788 | E-WW-NI-17092020-AUCHTERTOOL WWTW-SUPPLY & FIT NEW UPVC FACIAS & GUTTERINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-03-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765.5 | 1765.5 | 0 | 0 | 0 | 1765.5 | 0 | 0 | 0 | 0 | 1765.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508858 | E-WW-NI-17092020-KINGLASSIE SST-REPLACE EXISTING STORM RETURN PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263.28 | 1263.28 | 18046.83 | 0 | 0 | 19310.11 | 0 | 0 | 0 | 0 | 19310.11 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508844 | E-WW-NI-17092020-MOSSTODLOCH GLEBE RD SPS-WIDEN ACCESS ROAD & INSTALL NEW GATES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-22 |  | 2021-04-02 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6687.5 | 6687.5 | 0 | 0 | 0 | 6687.5 | 0 | 0 | 0 | 0 | 6687.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508803 | E-WW-NI-17092020-NEW PITSLIGO WWTW-REPLACE SLUGE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2604.7 | 2604.7 | 0 | 0 | 0 | 2604.7 | 0 | 0 | 0 | 0 | 2604.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508809 | E-WW-NI-17092020-RAEMOIR ROAD WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-22 |  | 2020-10-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2355.69 | 2355.69 | 0 | 0 | 0 | 2355.69 | 0 | 0 | 0 | 0 | 2355.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508840 | E-WW-NI-17092020-ROTHES WWTW-WELFARE FACILITIES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-22 |  | 2020-09-12 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11561.34 | 11561.34 | 168 | 0 | 0 | 11729.34 | 0 | 0 | 0 | 0 | 11729.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509980 | E-WW-NI-17112020-BANCHORY WWTW-INSTALL NEW GRATINGS & REFURB HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192.5 | 192.5 | 2750 | 0 | 0 | 2942.5 | 0 | 0 | 0 | 0 | 2942.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509977 | E-WW-NI-17112020-BLACKBURN WWPS-REPLACE GEARBOX & MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.31 | 317.31 | 4533 | 0 | 0 | 4850.31 | 0 | 0 | 0 | 0 | 4850.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509938 | E-WW-NI-17112020-CRUDEN BAY GOLF WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.51 | 370.51 | 5293 | 0 | 0 | 5663.51 | 0 | 0 | 0 | 0 | 5663.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509942 | E-WW-NI-17112020-LOSSIEMOUTH GREGORY PL WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279.79 | 279.79 | 3997 | 0 | 0 | 4276.79 | 0 | 0 | 0 | 0 | 4276.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504483 | E-WW-NI-171219-CULROSS CENTRAL WWPS-REPLACE FOUMP PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-01-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 3139.81 | 0 | 3139.81 | 0 | 0 | 0 | 3139.81 | 0 | 0 | 0 | 0 | 3139.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504445 | E-WW-NI-171219-ECHT WWTW-REPLACE MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-04-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1856.79 | 776.08 | 2632.87 | 0 | 0 | 0 | 2632.87 | 0 | 0 | 0 | 0 | 2632.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504432 | E-WW-NI-171219-LIMEKILNS RED ROW WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-01-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1290.96 | 0 | 1290.96 | 0 | 0 | 0 | 1290.96 | 0 | 0 | 0 | 0 | 1290.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510400 | E-WW-NI-17122020-BRUCE EMBANKMENT WWPS-REPLACEMENT ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-17 |  | 2021-03-27 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1607.62 | 1607.62 | 0 | 0 | 0 | 1607.62 | 0 | 0 | 0 | 0 | 1607.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510409 | E-WW-NI-17122020-BURNTISLAND FAMILARS WWPS-REPLACE NO2 FOUL PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-21 |  | 2021-02-22 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329.29 | 1329.29 | 0 | 0 | 0 | 1329.29 | 0 | 0 | 0 | 0 | 1329.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510457 | E-WW-NI-17122020-FORFAR WWTW-REPLACE ROTOR & STATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-27 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2859.86 | 2859.86 | 0 | 0 | 0 | 2859.86 | 0 | 0 | 0 | 0 | 2859.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510454 | E-WW-NI-17122020-MAUD WWTW-REPLACEMENT SLIP RINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3406.12 | 3406.12 | 0 | 0 | 0 | 3406.12 | 0 | 0 | 0 | 0 | 3406.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510416 | E-WW-NI-17122020-RAEMOIR ROAD WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-21 |  | 2021-03-13 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1586.25 | 1586.25 | 0 | 0 | 0 | 1586.25 | 0 | 0 | 0 | 0 | 1586.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505399 | E-WW-NI-18022020-BLAIR ATHOLL MEMORIAL PARK WWPS-INSTALL CONCERTOR PUMP SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-25 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 12863.53 | 11490.08 | 24353.61 | 352.19 | 0 | 0 | 24705.8 | 0 | 0 | 0 | 0 | 24705.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505400 | E-WW-NI-18022020-PERTH CITY WWTW-REPLACE ROTORK ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-25 |  | 2020-06-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 3128.31 | 1157.04 | 4285.35 | 0 | 0 | 0 | 4285.35 | 0 | 0 | 0 | 0 | 4285.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511398 | E-WW-NI-18022021-DUNFERMLINE ROSETHORN WWPS-REPLACEMENT PERIMETER WALL & BOLLARDS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-25 |  | 2021-04-05 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755.25 | 2755.25 | 0 | 0 | 0 | 2755.25 | 0 | 0 | 0 | 0 | 2755.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511404 | E-WW-NI-18022021-DUNFERMLINE WWTW-REFURB PRIMARY SLUDGE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4196.73 | 4196.73 | 0 | 0 | 0 | 4196.73 | 0 | 0 | 0 | 0 | 4196.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505906 | E-WW-NI-18032020-ABERDOUR SHORE RD WWPS-REPLACE FOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-25 |  | 2020-06-19 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 274.43 | 4032.63 | 4307.06 | 0 | 0 | 0 | 4307.06 | 0 | 0 | 0 | 0 | 4307.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505813 | E-WW-NI-18032020-LOSSIE INCHBROOM SPS-REPLACE MILLTRONICS HEAD/JUNCTION BOX & CABLE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-03-28 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 1352.9 | 0 | 1352.9 | 0 | 0 | 0 | 1352.9 | 0 | 0 | 0 | 0 | 1352.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505911 | E-WW-NI-18032020-PITLESSIE WWPS-REPLACE PUMP STOOLS & GUIDERAILS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-25 |  | 2020-04-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 270.13 | 3896.47 | 4166.6 | 0 | 0 | 0 | 4166.6 | 0 | 0 | 0 | 0 | 4166.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511969 | E-WW-NI-18032021-FORGANDENNY WWTW-REPLACE SAF AIR BLOWER NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206.85 | 206.85 | 2710.14 | 0 | 0 | 2916.99 | 0 | 0 | 0 | 0 | 2916.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511972 | E-WW-NI-18032021-INVERURIE WWTW-REPLACE UPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.8 | 198.8 | 2604.66 | 0 | 0 | 2803.46 | 0 | 0 | 0 | 0 | 2803.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511966 | E-WW-NI-18032021-OLDMELDRUM WWTW-REPLACEMENT BLOWERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494.28 | 494.28 | 6476.1 | 0 | 0 | 6970.38 | 0 | 0 | 0 | 0 | 6970.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511976 | E-WW-NI-18032021-PERTH SOUTH INCH WWPS-SUPPLY GEARBOX & MOTOR (CRITICAL SPARES) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613.57 | 613.57 | 8039.1 | 0 | 0 | 8652.67 | 0 | 0 | 0 | 0 | 8652.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511971 | E-WW-NI-18032021-ST ANDREWS WWTW-REPLACEMENT UV COMPRESSORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715.05 | 715.05 | 9368.64 | 0 | 0 | 10083.69 | 0 | 0 | 0 | 0 | 10083.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506816 | E-WW-NI-18052020-DALGETY BAY DOWNING POINT SPS-REPLACE 2X FOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-26 |  | 2020-07-15 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4030.07 | 4030.07 | 0 | 0 | 0 | 4030.07 | 0 | 0 | 0 | 0 | 4030.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506655 | E-WW-NI-180520-Methilhill CSO-Construct 2 Access Staircases to Allow Ops Acces to Maintain CSO | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-05-21 | 2021-06-14 | 2022-02-21 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5023 | 5023 | 38976.73 | 0 | 0 | 43999.73 | 0 | 0 | 0 | 0 | 43999.73 | 209381.79 | [5 empty] | N | CM_M&G | 100%
507267 | E-WW-NI-18062020-FORRES WWTW-PURCHASE MOTOR & GEARBOX (CRITICAL SPARES) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-19 |  | 2020-07-08 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2422.66 | 2422.66 | 0 | 0 | 0 | 2422.66 | 0 | 0 | 0 | 0 | 2422.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507290 | E-WW-NI-18062020-HUNTLY SCOTT COURT WWPS-REPLACE 3 SHAFT DRIVE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24561.74 | 24561.74 | -18.7 | 0 | 0 | 24543.04 | 0 | 0 | 0 | 0 | 24543.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507287 | E-WW-NI-18062020-LOWER LARGO THE TEMPLE WWPS-RENEWAL VALVE CHAMBER PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9493.42 | 9493.42 | 0 | 0 | 0 | 9493.42 | 0 | 0 | 0 | 0 | 9493.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507289 | E-WW-NI-18062020-RHYNIE WWTW-CONCRETE REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-09-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4954.47 | 4954.47 | 0 | 0 | 0 | 4954.47 | 0 | 0 | 0 | 0 | 4954.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508260 | E-WW-NI-18082020-ELIE SOUTH ST WWPS-REPLACE RISING MAINS & GUIDERAILS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-19 |  | 2020-09-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1182.94 | 1182.94 | 0 | 0 | 0 | 1182.94 | 0 | 0 | 0 | 0 | 1182.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508361 | E-WW-NI-18082020-KIRKCALDY WWPS-SUPPLY ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-01-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3205.35 | 3205.35 | 0 | 0 | 0 | 3205.35 | 0 | 0 | 0 | 0 | 3205.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508257 | E-WW-NI-18082020-SPRINGFIELD WWTW-REPLACE STORM TANK MIXER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-19 |  | 2020-09-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2339.24 | 2339.24 | 0 | 0 | 0 | 2339.24 | 0 | 0 | 0 | 0 | 2339.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508813 | E-WW-NI-18092020-LEUCHARS STATION RD WWPS-REPLACEMENT WINDOWS & DOORS (CONTROL BUILDING) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-22 |  | 2021-02-20 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2675 | 2675 | 0 | 0 | 0 | 2675 | 0 | 0 | 0 | 0 | 2675 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508870 | E-WW-NI-18092020-LONGSIDE WWTW-INSTALL CONCERTOR PUMP SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1099.12 | 1099.12 | 15701.67 | 0 | 0 | 16800.79 | 0 | 0 | 0 | 0 | 16800.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508869 | E-WW-NI-18092020-NEW GILSTON WWTW-REPLACE FILTER BED CENTRAL COLUMN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412.32 | 412.32 | 5890.31 | 0 | 0 | 6302.63 | 0 | 0 | 0 | 0 | 6302.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504073 | E-WW-NI-181119-BLAIR ATHOLL WWTW-INSTALL TOP WATER RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-03-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 40508.06 | 201.9 | 40709.96 | 0 | 0 | 0 | 40709.96 | 0 | 0 | 0 | 0 | 40709.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504069 | E-WW-NI-181119-BRACO WWTW-INSTALL TOP WATER RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2019-12-05 |  | 2020-09-11 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 16055.73 | 8653.26 | 24708.99 | 1021.86 | 0 | 0 | 25730.85 | 0 | 0 | 0 | 0 | 25730.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504078 | E-WW-NI-181119-PERTH CITY WWTW-CONSTRUCT FOOTPATH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-04-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 2991.15 | 1802.45 | 4793.6 | 0 | 0 | 0 | 4793.6 | 0 | 0 | 0 | 0 | 4793.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509970 | E-WW-NI-18112020-BANKFOOT WWTW-HANDRAILING IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307.79 | 307.79 | 4397 | 0 | 0 | 4704.79 | 0 | 0 | 0 | 0 | 4704.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509968 | E-WW-NI-18112020-DUNFERMLINE WWTW-REPLACE BOOSTER PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-24 |  | 2020-09-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762.66 | 3762.66 | 0 | 0 | 0 | 3762.66 | 0 | 0 | 0 | 0 | 3762.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509964 | E-WW-NI-18112020-KINLOCH RANNOCH (DUNALASTAIR) ST-INSTALL FLOW MEASUREMENT SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3437.86 | 3437.86 | 0 | 0 | 0 | 3437.86 | 0 | 0 | 0 | 0 | 3437.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504487 | E-WW-NI-181219-PETERHEAD BUCHANHAVEN WWPS-REPLACE 6 ROTORKS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-03-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 15030.48 | 0 | 15030.48 | 0 | 0 | 0 | 15030.48 | 0 | 0 | 0 | 0 | 15030.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510419 | E-WW-NI-18122020-BUCKIE STRATHLENE CARAVAN SPS-SUPPLY CRITICAL SPARE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-21 |  | 2021-03-15 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1991.23 | 1991.23 | 0 | 0 | 0 | 1991.23 | 0 | 0 | 0 | 0 | 1991.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510462 | E-WW-NI-18122020-FRIOCKHEIM WWTW-INLET SCREEN REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8815.9 | 8815.9 | 0 | 0 | 0 | 8815.9 | 0 | 0 | 0 | 0 | 8815.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510458 | E-WW-NI-18122020-NEW BYTH WWTW-SIPHON REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428.75 | 428.75 | 6125 | 0 | 0 | 6553.75 | 0 | 0 | 0 | 0 | 6553.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510433 | E-WW-NI-18122020-UDNY GREEN WWTW-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-21 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1869.66 | 1869.66 | 0 | 0 | 0 | 1869.66 | 0 | 0 | 0 | 0 | 1869.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510783 | E-WW-NI-19012021-CRIEFF WWTW-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-20 |  | 2021-03-05 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1653.15 | 1653.15 | 0 | 0 | 0 | 1653.15 | 0 | 0 | 0 | 0 | 1653.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510869 | E-WW-NI-19012021-CUPAR WWTW-REPLACE SLUDGE TRANSFER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535.76 | 535.76 | 7429.64 | 0 | 0 | 7965.4 | 0 | 0 | 0 | 0 | 7965.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510873 | E-WW-NI-19012021-SAUCHEN WWTW-REPLACE FAULTY DIFFUSER GRID | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6232.18 | 6232.18 | 0 | 0 | 0 | 6232.18 | 0 | 0 | 0 | 0 | 6232.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505327 | E-WW-NI-19022020-AUCHLEVEN NORTH STW-REPAIR OUTLET PIPE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-20 |  | 2020-08-18 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1196.24 | 442.77 | 1639.01 | 0 | 0 | 0 | 1639.01 | 0 | 0 | 0 | 0 | 1639.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505417 | E-WW-NI-19022020-DUNFERMLINE STW-REFURB PRIMARY SLUDGE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-26 |  | 2020-03-09 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 6396.2 | 0 | 6396.2 | 0 | 0 | 0 | 6396.2 | 0 | 0 | 0 | 0 | 6396.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505410 | E-WW-NI-19022020-DUNSHALT WWPS-ACCESS ROAD REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-26 |  | 2020-04-21 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 6561.24 | 2426.76 | 8988 | 0 | 0 | 0 | 8988 | 0 | 0 | 0 | 0 | 8988 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505420 | E-WW-NI-19022020-KINROSS WWTW-REPLACE SCREW PUMP GEARBOXES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-26 |  | 2020-08-27 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 7054.27 | 2609.11 | 9663.38 | 0 | 0 | 0 | 9663.38 | 0 | 0 | 0 | 0 | 9663.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505316 | E-WW-NI-19022020-NEWMACHAR WWTW-INSTALL NEW DUCT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-20 |  | 2020-08-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1923.74 | 711.52 | 2635.26 | 0 | 0 | 0 | 2635.26 | 0 | 0 | 0 | 0 | 2635.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511423 | E-WW-NI-19022021-HOPEMAN HARBOUR WWPS-WET WELL SEAL REPAIR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3258.69 | 3258.69 | 0 | 0 | 0 | 3258.69 | 0 | 0 | 0 | 0 | 3258.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504266 | E-WW-NI-1903-19-VALLEYFIELD WWTW-SCOPING & INVESTIGATION WORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-10 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 6656.36 | -5956.36 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505829 | E-WW-NI-19032020-KIRKCALDY CHAPEL NTH WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-20 |  | 2020-06-08 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 171.8 | 2454.28 | 2626.08 | 0 | 0 | 0 | 2626.08 | 0 | 0 | 0 | 0 | 2626.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505922 | E-WW-NI-19032020-LIMEKILNS RED ROW WWPS-CONVERT STATION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-25 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1091.73 | 74.82 | 1166.55 | 15521.26 | 0 | 0 | 16687.81 | 0 | 0 | 0 | 0 | 16687.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511996 | E-WW-NI-19032021-CUMINESTOWN WWTW-REFURB ACCESS ROAD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1445.5 | 1445.5 | 20650 | 0 | 0 | 22095.5 | 0 | 0 | 0 | 0 | 22095.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511993 | E-WW-NI-19032021-DUFFTOWN-WINDOWS REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-24 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670.6 | 670.6 | 8786.22 | 0 | 0 | 9456.82 | 0 | 0 | 0 | 0 | 9456.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511935 | E-WW-NI-19032021-KINROSS WWTW-REPLACE ROTORK ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-22 |  | 2021-06-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.45 | 136.45 | 1787.7 | 0 | 0 | 1924.15 | 0 | 0 | 0 | 0 | 1924.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512000 | E-WW-NI-19032021-MEADOW ROAD WWPS-REPLACE FOUL TRANSFER PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286.57 | 286.57 | 3754.62 | 0 | 0 | 4041.19 | 0 | 0 | 0 | 0 | 4041.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512001 | E-WW-NI-19032021-ST ANDREWS HARBOUR WWPS-REPLACE PUMP DRIVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194.25 | 194.25 | 2545.08 | 0 | 0 | 2739.33 | 0 | 0 | 0 | 0 | 2739.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506820 | E-WW-NI-19052020-ALYTH WWTW-REPLACE PUMP GUIDERAILS/STOOL & BRACKETS/ | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-27 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333.17 | 333.17 | 4759.52 | 0 | 0 | 5092.69 | 0 | 0 | 0 | 0 | 5092.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507294 | E-WW-NI-19062020-HUNTLY WWTW-REPLACE GRIT REMOVAL PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7984.86 | 7984.86 | 0 | 0 | 0 | 7984.86 | 0 | 0 | 0 | 0 | 7984.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509459 | E-WW-NI-191020200-MONTROSE COBDEN ST WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-27 |  | 2021-03-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18796.29 | 18796.29 | 0 | 0 | 0 | 18796.29 | 0 | 0 | 0 | 0 | 18796.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509455 | E-WW-NI-19102020-FRIOCKHEIM WWTW-REFURB INLET SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-27 |  | 2021-03-11 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10996.98 | 10996.98 | 0 | 0 | 0 | 10996.98 | 0 | 0 | 0 | 0 | 10996.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509461 | E-WWNI-19102020-MONIFIETH GRANGE RD WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-26 |  | 2021-03-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15689.4 | 15689.4 | 0 | 0 | 0 | 15689.4 | 0 | 0 | 0 | 0 | 15689.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509324 | E-WW-NI-191020-Marywell WWPS Replace Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-05 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1927.37 | 1927.37 | 0 | 0 | 0 | 1927.37 | 0 | 0 | 0 | 0 | 1927.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509323 | E-WW-NI-191020-St Andrews WWTW Sludge Pump Replacement. | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4594.51 | 4594.51 | 0 | 0 | 0 | 4594.51 | 0 | 0 | 0 | 0 | 4594.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503877 | E-WW-NI-191119-CERES WWTW-REPLACE DRY WELL PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-01-25 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2182.37 | 0 | 2182.37 | 0 | 0 | 0 | 2182.37 | 0 | 0 | 0 | 0 | 2182.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509888 | E-WW-NI-19112020-NEWMACHAR WWTW-INSTALL CONCRETE PLINTH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-24 |  | 2020-11-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765.5 | 1765.5 | 0 | 0 | 0 | 1765.5 | 0 | 0 | 0 | 0 | 1765.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504485 | E-WW-NI-191219-NEWMACHAR WWTW-INSTALL NEW POWER CABLE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-02-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 4429.15 | 0 | 4429.15 | 0 | 0 | 0 | 4429.15 | 0 | 0 | 0 | 0 | 4429.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510884 | E-WW-NI-20012021-PERTH CITY WWTW-REPLACE 2X ACTUATORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7249.21 | 7249.21 | 1597.02 | 0 | 0 | 8846.23 | 0 | 0 | 0 | 0 | 8846.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510877 | E-WW-NI-20012021-PERTH SOUTH INCH PFPS P&K SPS-SUPPLY GENERATOR CONTROL PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5617.5 | 5617.5 | 496.48 | 0 | 0 | 6113.98 | 0 | 0 | 0 | 0 | 6113.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505422 | E-WW-NI-20022020-BLACKFORD WWTW-HANDRAILING IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-26 |  | 2020-11-26 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 15322.84 | 5667.35 | 20990.19 | 0 | 0 | 0 | 20990.19 | 0 | 0 | 0 | 0 | 20990.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505333 | E-WW-NI-20022020-CRIMOND LOGIE AVE WWPS - REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-21 |  | 2020-05-11 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1295.76 | 479.25 | 1775.01 | 0 | 0 | 0 | 1775.01 | 0 | 0 | 0 | 0 | 1775.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505425 | E-WW-NI-20022020-KINROSS WWTW-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-26 |  | 2020-05-13 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 12690.53 | 4693.76 | 17384.29 | 0 | 0 | 0 | 17384.29 | 0 | 0 | 0 | 0 | 17384.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505926 | E-WW-NI-20032020-BLACKBURN WWPS-INSTALL NEW MANHOLE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-25 |  | 2020-08-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 545.81 | 7853.4 | 8399.21 | 0 | 0 | 0 | 8399.21 | 0 | 0 | 0 | 0 | 8399.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505930 | E-WW-NI-20032020-LONGSIDE WWTW- REPLACE FILTER FEED PUMP & CONTROL PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-25 |  | 2020-10-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1137.23 | 122224.01 | 123361.24 | -15199.86 | 0 | 0 | 108161.38 | 0 | 0 | 0 | 0 | 108161.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505834 | E-WW-NI-20032020-NEWMACHAR WWTW-REPLACE MIXER MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-20 |  | 2020-04-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 106.47 | 1520.95 | 1627.42 | 0 | 0 | 0 | 1627.42 | 0 | 0 | 0 | 0 | 1627.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506371 | E-WW-NI-20042020-MILNATHORT WWTW-REPLACE CHANNEL COVER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-28 |  | 2020-06-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1986.99 | 1986.99 | 0 | 0 | 0 | 1986.99 | 0 | 0 | 0 | 0 | 1986.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506828 | E-WW-NI-20052020-KIRRIEMUIR WWTW-PURCHASE OREGE THICKENING UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-07-08 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187250 | 187250 | 0 | 0 | 0 | 187250 | 0 | 0 | 0 | 0 | 187250 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506833 | E-WW-NI-20052020-NEWMILLS FOOTBALL PARK WWPS-REPLACE 2X FOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-09-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20927.65 | 20927.65 | 0 | 0 | 0 | 20927.65 | 0 | 0 | 0 | 0 | 20927.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507794 | E-WW-NI-20072020-CUPAR WWTW-REPLACEMENT RAS VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-22 |  | 2020-01-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3334.6 | 3334.6 | 0 | 0 | 0 | 3334.6 | 0 | 0 | 0 | 0 | 3334.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507802 | E-WW-NI-20072020-ST ANDREWS THE GLEBE WWPS-REPLACE NO2 STORM RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-22 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.87 | 163.87 | 2341 | 0 | 0 | 2504.87 | 0 | 0 | 0 | 0 | 2504.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507767 | E-WW-NI-200720-DUNFERMLINE STC-REPLACE SLUDGE HOLDING TANK NO1 (INSTALLATION) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-07-22 | 2020-10-23 | 2020-12-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216570.61 | 216570.61 | 0 | 0 | 0 | 216570.61 | 0 | 0 | 0 | 0 | 216570.61 | 90601.29 | [5 empty] | N | WWNI | 100%
504268 | E-WW-NI-200819-GLENFARG WWTW-REPLACE KIOSKS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-10 |  | 2020-06-16 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 8833.06 | 3289.43 | 12122.49 | 0 | 0 | 0 | 12122.49 | 0 | 0 | 0 | 0 | 12122.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508379 | E-WW-NI-20082020-BALMEDIE EVENTIDE WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-09-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2851.55 | 2851.55 | 0 | 0 | 0 | 2851.55 | 0 | 0 | 0 | 0 | 2851.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508362 | E-WW-NI-20082020-DALGETY BAY THE WYND SPS-REPLACE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977.62 | 977.62 | 13966.03 | 0 | 0 | 14943.65 | 0 | 0 | 0 | 0 | 14943.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508323 | E-WW-NI-20082020-INSCH WWTW-REFURB HUMUS SLUDGE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-24 |  | 2020-09-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2229.63 | 2229.63 | 0 | 0 | 0 | 2229.63 | 0 | 0 | 0 | 0 | 2229.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508366 | E-WW-NI-20082020-TARLAND WWTW-INLET PS CONCERTOR UPGRADE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15560.85 | 15560.85 | 0 | 0 | 0 | 15560.85 | 0 | 0 | 0 | 0 | 15560.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509487 | E-WW-NI-20102020-ABERDOUR SHORE ROAD WWPS-REPLACE RTU | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-26 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6085.94 | 6085.94 | 1847.08 | 0 | 0 | 7933.02 | 0 | 0 | 0 | 0 | 7933.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509378 | E-WW-NI-20102020-FALKLAND WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-07-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1769.01 | 1769.01 | 0 | 0 | 0 | 1769.01 | 0 | 0 | 0 | 0 | 1769.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509467 | E-WW-NI-20102020-INVERBERVIE WWPS-REPLACE IMPELLORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-26 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8004.72 | 8004.72 | 0 | 0 | 0 | 8004.72 | 0 | 0 | 0 | 0 | 8004.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509376 | E-WW-NI-20102020-KENMORE WWPS-OUTFALL REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-27 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 126 | 1800 | 0 | 0 | 1926 | 0 | 0 | 0 | 0 | 1926 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509489 | E-WW-NI-20102020-PETTYCUR BAY WWPS-PURCHASE INLET MACERATOR PUMP (CRITICAL SPARE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-10-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3135.1 | 3135.1 | 0 | 0 | 0 | 3135.1 | 0 | 0 | 0 | 0 | 3135.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509484 | E-WW-NI-20102020-PITLOCHRY FONAB CRESCENT SPS-KIOSK REPLACEMENT & GROUND UPGRADE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-03-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7195.75 | 7195.75 | 0 | 0 | 0 | 7195.75 | 0 | 0 | 0 | 0 | 7195.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509471 | E-WW-NI-20102020-SALINE WWTW-UPGRADE WELFARE FACILITIES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-11-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6246.11 | 6246.11 | 0 | 0 | 0 | 6246.11 | 0 | 0 | 0 | 0 | 6246.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503894 | E-WW-NI-201119-PITMEDDEN WWTW-REPLACE SAS PUMP 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-02-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1612.06 | 0 | 1612.06 | 0 | 0 | 0 | 1612.06 | 0 | 0 | 0 | 0 | 1612.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509973 | E-WW-NI-20112020-DRUMOIG WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-24 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3114.28 | 3114.28 | 0 | 0 | 0 | 3114.28 | 0 | 0 | 0 | 0 | 3114.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509946 | E-WW-NI-20112020-FORRES WWTW-EXTERNAL LIGHTING REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514.66 | 514.66 | 6780.46 | 0 | 0 | 7295.12 | 0 | 0 | 0 | 0 | 7295.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509948 | E-WW-NI-20112020-FRASERBURGH WESTSHORE WWPS-REPLACE STORM PUMP NO3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-03-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770.77 | 2770.77 | 0 | 0 | 0 | 2770.77 | 0 | 0 | 0 | 0 | 2770.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509910 | E-WW-NI-20112020-IRONMILL BAY WWTW-REPLACE BRUSH GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-02-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1631.75 | 1631.75 | 0 | 0 | 0 | 1631.75 | 0 | 0 | 0 | 0 | 1631.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509959 | E-WW-NI-20112020-NEW PITSLIGO WWTW-SCREW PUMP REPLACEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5761.61 | 5761.61 | 82308.78 | 0 | 0 | 88070.39 | 0 | 0 | 0 | 0 | 88070.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509945 | E-WW-NI-20112020-SANDEND WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290.78 | 290.78 | 4154 | 0 | 0 | 4444.78 | 0 | 0 | 0 | 0 | 4444.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510886 | E-WW-NI-2012021-ST FILLANS WWTW-INSTALL TOP WATER RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19676.17 | 19676.17 | 10902.38 | 0 | 0 | 30578.55 | 0 | 0 | 0 | 0 | 30578.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504493 | E-WW-NI-201219-BURRELTON WWTW-REPLACE FAULTY COMPONENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-02-11 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 8562.25 | 0 | 8562.25 | 0 | 0 | 0 | 8562.25 | 0 | 0 | 0 | 0 | 8562.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504477 | E-WW-NI-201219-COWDENBEATH SELKIRK AV SST-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-02-26 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1335.15 | 0 | 1335.15 | 0 | 0 | 0 | 1335.15 | 0 | 0 | 0 | 0 | 1335.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504457 | E-WW-NI-201219-DRUMLITHIE WWTW-REPLACE MLSS PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-01-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2548.33 | 0 | 2548.33 | 0 | 0 | 0 | 2548.33 | 0 | 0 | 0 | 0 | 2548.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504486 | E-WW-NI-201219-FORRES WWTW-REFURB INLET BAND SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-04-22 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 26590.06 | 2597 | 29187.06 | 0 | 0 | 0 | 29187.06 | 0 | 0 | 0 | 0 | 29187.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504489 | E-WW-NI-201219-NETHER KNOX WWTW-REPLACE GRIT PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-01-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 4469.91 | 0 | 4469.91 | 0 | 0 | 0 | 4469.91 | 0 | 0 | 0 | 0 | 4469.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504887 | E-WW-NI-21012020-IRONMILL BAY WWTW-REFURB SLUDGE FEED PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-01-31 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 3030.44 | 0 | 3030.44 | 0 | 0 | 0 | 3030.44 | 0 | 0 | 0 | 0 | 3030.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510814 | E-WW-NI-21012021-DUNFERMLINE STW INLET SPS-INSTALL NEW ISOLATOR SWITCH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880.15 | 2880.15 | -504.76 | 0 | 0 | 2375.39 | 0 | 0 | 0 | 0 | 2375.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510824 | E-WW-NI-210121-PERTH SOUTH INCH SPS CSO-SCREEN REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-01-22 | 2022-04-15 | 2022-11-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.57 | 31.57 | 165000 | 0 | 0 | 165031.57 | 0 | 0 | 0 | 0 | 165031.57 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505428 | E-WW-NI-21022020-ABOYNE WWTW-INSTALL CHEMICAL DOSING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-03-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 17848 | 0 | 17848 | 0 | 0 | 0 | 17848 | 0 | 0 | 0 | 0 | 17848 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505431 | E-WW-NI-21022020-BALMEDIE WWTW-INSTALL CHEMICAL DOSING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-03-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 16728 | 0 | 16728 | 0 | 0 | 0 | 16728 | 0 | 0 | 0 | 0 | 16728 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505436 | E-WW-NI-21022020-CRIEFF WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-04-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1396.95 | 0 | 1396.95 | 0 | 0 | 0 | 1396.95 | 0 | 0 | 0 | 0 | 1396.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505426 | E-WW-NI-21022020-KEITH WWTW-SUPPLY NEW ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-26 |  | 2020-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 2196.07 | 812.24 | 3008.31 | 0 | 0 | 0 | 3008.31 | 0 | 0 | 0 | 0 | 3008.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505353 | E-WW-NI-21022020-MONFIETH A92 SERVICES WWPS-REFURB ACCESS ROAD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-21 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1926 | 0 | 1926 | 0 | 0 | 0 | 1926 | 0 | 0 | 0 | 0 | 1926 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505430 | E-WW-NI-21022020-PITMEDDEN WWTW -INSTALL CHEMICAL DOSING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 15938 | 37.41 | 15975.41 | 1923.55 | 0 | 0 | 17898.96 | 0 | 0 | 0 | 0 | 17898.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505355 | E-WW-NI-210220-DUNFERMLINE STC-REPLACE SLUDGE HOLDING TANK NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-02-27 | 2020-10-19 | 2020-12-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 145457.53 | 147457.53 | 0 | 0 | 0 | 147457.53 | 0 | 0 | 0 | 0 | 147457.53 | 90601.29 | [5 empty] | N | WWNI | 100%
506375 | E-WW-NI-21042020-SCOTLANDWELL WWPS-REPLACE NO2 FOUL PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-29 |  | 2020-08-21 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11172.19 | 11172.19 | 0 | 0 | 0 | 11172.19 | 0 | 0 | 0 | 0 | 11172.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506373 | E-WW-NI-21042020-ST ANDREWS WWTW-REPLACE NO2 RAS PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-28 |  | 2020-06-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4623.39 | 4623.39 | 0 | 0 | 0 | 4623.39 | 0 | 0 | 0 | 0 | 4623.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507787 | E-WW-NI-210720-Durris FE PS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-09-01 | 2021-03-10 | 2021-04-27 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20256.42 | 20256.42 | 4743.58 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 90601.29 | [5 empty] | N | WWNI | 100%
508413 | E-WW-NI-21082020-BALMEDIE WWTW-REFURB INLET SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14477.07 | 14477.07 | -37.41 | 0 | 0 | 14439.66 | 0 | 0 | 0 | 0 | 14439.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508395 | E-WW-NI-21082020-BURNTISLAND LINKS CAR PARK SPS-REPLACE IMPELLORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-10-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3822.15 | 3822.15 | 0 | 0 | 0 | 3822.15 | 0 | 0 | 0 | 0 | 3822.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508384 | E-WW-NI-21082020-INSCH WWTW-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-10-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3476.9 | 3476.9 | 0 | 0 | 0 | 3476.9 | 0 | 0 | 0 | 0 | 3476.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508418 | E-WW-NI-21082020-KIRKCALDY WWTW-ALTERATIONS TO FIRE PROTECTION SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-11-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4840.38 | 4840.38 | 0 | 0 | 0 | 4840.38 | 0 | 0 | 0 | 0 | 4840.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508400 | E-WW-NI-21082020-KIRRIEMUIR WWTW-DAB DISMANTLE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-10-05 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13144.91 | 13144.91 | 0 | 0 | 0 | 13144.91 | 0 | 0 | 0 | 0 | 13144.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508386 | E-WW-NI-21082020-NO 2 CASH FEUS PNRV SPS-REPLACE KESSEL UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-10-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9799.41 | 9799.41 | 0 | 0 | 0 | 9799.41 | 0 | 0 | 0 | 0 | 9799.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508388 | E-WW-NI-21082020-NO 6 CASH FEUS PNRV SPS-REPLACE APNRV UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-10-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13980.35 | 13980.35 | 0 | 0 | 0 | 13980.35 | 0 | 0 | 0 | 0 | 13980.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508325 | E-WW-NI-21082020-PITMEDDEN WWTW-REPLACE INLET FLOW MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-24 |  | 2020-10-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520.42 | 2520.42 | 0 | 0 | 0 | 2520.42 | 0 | 0 | 0 | 0 | 2520.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508393 | E-WW-NI-21082020-RIVERSIDE ROAD WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-11-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3635.25 | 3635.25 | 0 | 0 | 0 | 3635.25 | 0 | 0 | 0 | 0 | 3635.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508397 | E-WW-NI-21082020-STRACHAN SPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-27 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3395.33 | 3395.33 | 0 | 0 | 0 | 3395.33 | 0 | 0 | 0 | 0 | 3395.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508838 | E-WW-NI-21092020-URQUHART WWPS-ELECTRICAL UPGRADE & TELEMETRY INSTALLATION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28972.05 | 28972.05 | 163.44 | 0 | 0 | 29135.49 | 0 | 0 | 0 | 0 | 29135.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509398 | E-WW-NI-21102020-AUCHTERARDER WWTW-REPLACE WASHWATER PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-18 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2199.17 | 2199.17 | 0 | 0 | 0 | 2199.17 | 0 | 0 | 0 | 0 | 2199.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509382 | E-WW-NI-21102020-BURRELTON WWTW-REFURB RECIRC PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1335.82 | 1335.82 | 0 | 0 | 0 | 1335.82 | 0 | 0 | 0 | 0 | 1335.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509492 | E-WW-NI-21102020-DUNFERMLINE STC-REPLACEMENT CAKE SKIPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-11-20 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17976 | 17976 | 0 | 0 | 0 | 17976 | 0 | 0 | 0 | 0 | 17976 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509388 | E-WW-NI-21102020-PERTH FRIARTON WWPS-PURCHASE CRITICAL SPARE MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2552.21 | 2552.21 | 0 | 0 | 0 | 2552.21 | 0 | 0 | 0 | 0 | 2552.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503918 | E-WW-NI-211119-KINCARDINE ONEIL WWTW-REPLACE FILTER GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-01-29 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1731.9 | 0 | 1731.9 | 0 | 0 | 0 | 1731.9 | 0 | 0 | 0 | 0 | 1731.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504081 | E-WW-NI-211119-KINROSS WWTW-REPLACE AERATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-03 |  | 2020-03-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 20130.98 | 0 | 20130.98 | 0 | 0 | 0 | 20130.98 | 0 | 0 | 0 | 0 | 20130.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510452 | E-WW-NI-21122020-FOCHABERS WWTW-REPLACE DRIVE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133.84 | 133.84 | 1340.23 | 0 | 0 | 1474.07 | 0 | 0 | 0 | 0 | 1474.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510466 | E-WW-NI-21122020-INVERKEITHING HARBOUR PLACE WWPS-INSTALL NEW PERIMETER FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122.15 | 122.15 | 1745 | 0 | 0 | 1867.15 | 0 | 0 | 0 | 0 | 1867.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510450 | E-WW-NI-21122020-KEITH WWTW-REPLACE WASHWATER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-21 |  | 2021-02-26 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.59 | 1199.59 | 0 | 0 | 0 | 1199.59 | 0 | 0 | 0 | 0 | 1199.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504126 | E-WW-NI-21219-FORFAR WWTW-REPLACE FE FILER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-01-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1884.54 | 0 | 1884.54 | 0 | 0 | 0 | 1884.54 | 0 | 0 | 0 | 0 | 1884.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504912 | E-WW-NI-22012020-DUNFERMLINE WWTW-REPLACE PRIMARY SLUDGE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-03-20 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 7060.87 | 0 | 7060.87 | 0 | 0 | 0 | 7060.87 | 0 | 0 | 0 | 0 | 7060.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504935 | E-WW-NI-22012020-MONIFIETH GRANGE RD WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 3008.2 | 0 | 3008.2 | 0 | 0 | 0 | 3008.2 | 0 | 0 | 0 | 0 | 3008.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510838 | E-WW-NI-22012021-FORFAR WWTW-REPLACE SLUDGE THICKENING PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1096.4 | 1096.4 | 14594 | 0 | 0 | 15690.4 | 0 | 0 | 0 | 0 | 15690.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510841 | E-WW-NI-22012021-FORFAR WWTW-REPLACEMENT HEATERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 497.76 | 497.76 | 7110.8 | 0 | 0 | 7608.56 | 0 | 0 | 0 | 0 | 7608.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510898 | E-WW-NI-22012021-FORFAR WWTW-REPLACEMENT pH MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530.74 | 530.74 | 7582 | 0 | 0 | 8112.74 | 0 | 0 | 0 | 0 | 8112.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510852 | E-WW-NI-22012021-ROTHES WWTW-INSTALL HANDRAILSSELF CLOSING GATES & FLOOR PANELS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.35 | 200.35 | 2327.64 | 0 | 0 | 2527.99 | 0 | 0 | 0 | 0 | 2527.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511384 | E-WW-NI-22022021-MONIFIETH BURGH YARD SPS-RISING MAIN REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-22 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42120.01 | 42120.01 | 1189.46 | 0 | 0 | 43309.47 | 0 | 0 | 0 | 0 | 43309.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511536 | E-WW-NI-22022021-NEWMACHAR WWTW-REPLACE 2XINTERSTAGE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.15 | 255.15 | 3342.96 | 0 | 0 | 3598.11 | 0 | 0 | 0 | 0 | 3598.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512098 | E-WW-NI-22032021-COLINSBURGH WWTW-REPLACE PERIMETER FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166.78 | 2166.78 | 30954 | 0 | 0 | 33120.78 | 0 | 0 | 0 | 0 | 33120.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512095 | E-WW-NI-22032021-CRIEFF WWTW-REPLACEMENT INLET SCREEN GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175.98 | 175.98 | 2305.68 | 0 | 0 | 2481.66 | 0 | 0 | 0 | 0 | 2481.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511960 | E-WW-NI-22032021-PORTSOY WWTW-REPLACE WASHWATER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-22 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.47 | 103.47 | 1355.7 | 0 | 0 | 1459.17 | 0 | 0 | 0 | 0 | 1459.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506839 | E-WW-NI-22052020-BELTS OF COLLONACH SPS-REPLACE TRANSFER PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-08-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3990.84 | 3990.84 | 0 | 0 | 0 | 3990.84 | 0 | 0 | 0 | 0 | 3990.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507480 | E-WW-NI-22052020-BUCKIE HIGH ST CSO-KIOSK REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-06 |  | 2020-07-22 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3144.35 | 3144.35 | 0 | 0 | 0 | 3144.35 | 0 | 0 | 0 | 0 | 3144.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506920 | E-WW-NI-22052020-CUPAR WWTW-REFURB SLUDGE FEED PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-02 |  | 2020-06-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3094.8 | 3094.8 | 0 | 0 | 0 | 3094.8 | 0 | 0 | 0 | 0 | 3094.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506845 | E-WW-NI-22052020-ELGIN LOSSIE WYND SPS-REPLACE FLOORING ON GRATING PLATFORM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-27 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025.16 | 1025.16 | 14359.3 | 0 | 0 | 15384.46 | 0 | 0 | 0 | 0 | 15384.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506851 | E-WW-NI-22052020-HUNTLY WWTW-REPLACE STORM RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-08-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8640.75 | 8640.75 | 0 | 0 | 0 | 8640.75 | 0 | 0 | 0 | 0 | 8640.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506840 | E-WW-NI-22052020-NEWBIGGING WWTW-REPAIRS TO REEDBED INLET CHAMBER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-27 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5231.14 | 5231.14 | -41.64 | 0 | 0 | 5189.5 | 0 | 0 | 0 | 0 | 5189.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506838 | E-WW-NI-22052020-NEWPORT & TAYPORT WWTW- REPLACE WASHWATER PUMP B | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-06-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3359.59 | 3359.59 | 0 | 0 | 0 | 3359.59 | 0 | 0 | 0 | 0 | 3359.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506775 | E-WW-NI-22052020-TARVES WWTW-REPLACE FEED PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-26 |  | 2020-07-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1921.38 | 1921.38 | 0 | 0 | 0 | 1921.38 | 0 | 0 | 0 | 0 | 1921.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507405 | E-WW-NI-22062020-KINROSS WWTW-REPLACE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-09 |  | 2020-07-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3449.32 | 3449.32 | 0 | 0 | 0 | 3449.32 | 0 | 0 | 0 | 0 | 3449.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507306 | E-WW-NI-22062020-LAURENCEKIRK WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-12 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1473.92 | 1473.92 | 0 | 0 | 0 | 1473.92 | 0 | 0 | 0 | 0 | 1473.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507297 | E-WW-NI-22062020-LAURENCEKIRK WWTW-REPLACE PST DESLUDGE PUMP A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-28 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2147.7 | 2147.7 | 0 | 0 | 0 | 2147.7 | 0 | 0 | 0 | 0 | 2147.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507295 | E-WW-NI-22062020-MILNATHORT WWTW-INSTALL TEMP FERRIC DOSING SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-09 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14536.46 | 14536.46 | 0 | 0 | 0 | 14536.46 | 0 | 0 | 0 | 0 | 14536.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507308 | E-WW-NI-22062020-MINTLAW WWTW-REPLACE INLET SCREEN LEVEL MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1539.46 | 1539.46 | 0 | 0 | 0 | 1539.46 | 0 | 0 | 0 | 0 | 1539.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507818 | E-WW-NI-22072020-DUFFTOWN WWTW-REPLACE SIEMENS HYDRORANGER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-22 |  | 2020-08-12 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1125.19 | 1125.19 | 0 | 0 | 0 | 1125.19 | 0 | 0 | 0 | 0 | 1125.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507825 | E-WW-NI-220720-DUNFERMLINE STC-REPLACE SLUDGE HOLDING TANK OCU | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-07-27 | 2021-03-08 | 2021-10-19 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 169999.97 | 0 | 0 | 219999.97 | 0 | 0 | 0 | 0 | 219999.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507827 | E-WW-NI-220720-PITLOCHRY WWTW-RBC NO3 REPLACEMENT INTERNALS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-07-27 | 2021-06-14 | 2022-01-25 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55500 | 55500 | 110500.06 | 0 | 0 | 166000.06 | 0 | 0 | 0 | 0 | 166000.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508878 | E-WW-NI-22092020-ABERUTHVEN ENTERPRISE PARK WWPS-REPLACE 2XFOUL PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-22 |  | 2020-11-16 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.08 | 2504.08 | 0 | 0 | 0 | 2504.08 | 0 | 0 | 0 | 0 | 2504.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508983 | E-WW-NI-22092020-DEN BURN EAST BURN PH2 PCSO-REPLACEMENT PANELS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966 | 966 | 13800 | 0 | 0 | 14766 | 0 | 0 | 0 | 0 | 14766 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508981 | E-WW-NI-22092020-DUNFERMLINE WWTW-REPLACE GEARBOX ON SCRAPER BRIDGE PST NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-30 |  | 2021-02-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3585.73 | 3585.73 | 0 | 0 | 0 | 3585.73 | 0 | 0 | 0 | 0 | 3585.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509399 | E-WW-NI-22102020-MILNATHORT WWTW-REPLACE SAS PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-09 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1424.64 | 1424.64 | 0 | 0 | 0 | 1424.64 | 0 | 0 | 0 | 0 | 1424.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509508 | E-WW-NI-22102020-NEWPORT & TAYPORT STW-REPLACE LAUNDER TROUGH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5595.43 | 5595.43 | 0 | 0 | 0 | 5595.43 | 0 | 0 | 0 | 0 | 5595.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504019 | E-WW-NI-221119-BUCKIE RATHVEN SPS-REPLACE PUMP 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-01-25 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 1313.09 | 0 | 1313.09 | 0 | 0 | 0 | 1313.09 | 0 | 0 | 0 | 0 | 1313.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504007 | E-WW-NI-221119-HATTON OF CRUDEN WWTW-REPLACE AIR END OF COMPRESSOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2019-12-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1478.74 | 0 | 1478.74 | 0 | 0 | 0 | 1478.74 | 0 | 0 | 0 | 0 | 1478.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504153 | E-WW-NI-221119-LHANBRYDE PARKVIEW SPS-REPLACE LEVEL CONROLLER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-01-09 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 1431.25 | 0 | 1431.25 | 0 | 0 | 0 | 1431.25 | 0 | 0 | 0 | 0 | 1431.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504263 | E-WW-NI-221119-PITSCOTTIE SPS CSO-FIT ANPRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-10 |  | 2020-01-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 12214.8 | 0 | 12214.8 | 0 | 0 | 0 | 12214.8 | 0 | 0 | 0 | 0 | 12214.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504083 | E-WW-NI-221119-TURRIFF WWTW-REPAIR LIQUOR RETURN PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-03 |  | 2020-02-14 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 5354.28 | 0 | 5354.28 | 0 | 0 | 0 | 5354.28 | 0 | 0 | 0 | 0 | 5354.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510492 | E-WW-NI-22122020-ST FERGUS SCOTSTON SPS-REPLACE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.13 | 183.13 | 2616.09 | 0 | 0 | 2799.22 | 0 | 0 | 0 | 0 | 2799.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511542 | E-WW-NI-23022021-ALMONDBANK RN STORES WWPS-REPLACEMENT COMPRESSOR. | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195.09 | 195.09 | 2556.06 | 0 | 0 | 2751.15 | 0 | 0 | 0 | 0 | 2751.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511538 | E-WW-NI-23022021-BUCHANAN COURT WWPS-REPLACE 2XTRANSFER PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527.31 | 527.31 | 6908.82 | 0 | 0 | 7436.13 | 0 | 0 | 0 | 0 | 7436.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511439 | E-WW-NI-23022021-CAIRNEYHILL THE SHEILINGS WWPS-REPLACE WET WELL & VALVE CHAMBER COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135.8 | 135.8 | 1940 | 0 | 0 | 2075.8 | 0 | 0 | 0 | 0 | 2075.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511409 | E-WW-NI-23022021-COUPAR ANGUS WWTW-REPLACE ROTORK ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.57 | 80.57 | 1151 | 0 | 0 | 1231.57 | 0 | 0 | 0 | 0 | 1231.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511425 | E-WW-NI-23022021-NEWPORT & TAYPORT WWTW-REPLACE MLSS MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2460.35 | 2460.35 | 0 | 0 | 0 | 2460.35 | 0 | 0 | 0 | 0 | 2460.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506005 | E-WW-NI-23032020-PERTH CITY WWTW-MODIFY CONTROL PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-03-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9398.31 | 9398.31 | 0 | 0 | 0 | 9398.31 | 0 | 0 | 0 | 0 | 9398.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511983 | E-WW-NI-23032021-BURRELTON WWTW-REPLACE RECIRC PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105.18 | 105.18 | 1378.08 | 0 | 0 | 1483.26 | 0 | 0 | 0 | 0 | 1483.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512105 | E-WW-NI-23032021-FRIOCKHEIM WWTW-REPLACE BRUSH ARM ASSEMBLY | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235.67 | 235.67 | 3087.78 | 0 | 0 | 3323.45 | 0 | 0 | 0 | 0 | 3323.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511986 | E-WW-NI-23032021-GUARDBRIDGE WWTW-REPLACE ACTUATED VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.9 | 95.9 | 1256.46 | 0 | 0 | 1352.36 | 0 | 0 | 0 | 0 | 1352.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512101 | E-WW-NI-23032021-KEITH WWTW-REPLACE INLET PUMP NO3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643.44 | 643.44 | 8430.36 | 0 | 0 | 9073.8 | 0 | 0 | 0 | 0 | 9073.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512102 | E-WW-NI-23032021-NEWPORT & TAYPORT WWTW-REPLACE SCREW ASSEMBLY | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240.56 | 240.56 | 3151.8 | 0 | 0 | 3392.36 | 0 | 0 | 0 | 0 | 3392.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506377 | E-WW-NI-23042020-FORDOUN MAIN WWPS-REPLACE PUMP & IMPELLOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-28 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5044.14 | 5044.14 | 0.01 | 0 | 0 | 5044.15 | 0 | 0 | 0 | 0 | 5044.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506379 | E-WW-NI-23042020-GILMERTON WWPS-CONVERSION TO CONCERTOR PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-29 |  | 2020-11-24 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21674.3 | 21674.3 | 0 | 0 | 0 | 21674.3 | 0 | 0 | 0 | 0 | 21674.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506380 | E-WW-NI-23042020-ST ANDREWS HARBOUR WWPS-REPLACE DRIVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-28 |  | 2020-05-20 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4398.8 | 4398.8 | 0 | 0 | 0 | 4398.8 | 0 | 0 | 0 | 0 | 4398.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507312 | E-WW-NI-23062020-BRECHIN WWTW-REPLACE INLET PLUG VALVES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-11 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2115.9 | 2115.9 | 0 | 0 | 0 | 2115.9 | 0 | 0 | 0 | 0 | 2115.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507423 | E-WW-NI-23062020-FORFAR QUEENSWELL RD WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-08-28 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4932.41 | 4932.41 | 0 | 0 | 0 | 4932.41 | 0 | 0 | 0 | 0 | 4932.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507314 | E-WW-NI-23062020-PERTH CITY WWTW-REPLACE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-15 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1468.87 | 1468.87 | 0 | 0 | 0 | 1468.87 | 0 | 0 | 0 | 0 | 1468.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507410 | E-WW-NI-23062020-PERTH FRIARTON WWPS-PURCHASE ECO LOWER BEARING INTERNALS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-08-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12840 | 12840 | 0 | 0 | 0 | 12840 | 0 | 0 | 0 | 0 | 12840 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507409 | E-WW-NI-23062020-PERTH SOUTH INCH WWPS-PURCHASE ECO LOWER BEARING INTERNALS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-08-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9362.5 | 9362.5 | 0 | 0 | 0 | 9362.5 | 0 | 0 | 0 | 0 | 9362.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507310 | E-WW-NI-230620-Torphins STW Filter Media Change | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-06-26 | 2020-07-20 | 2020-09-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253926.45 | 253926.45 | 0 | 0 | 0 | 253926.45 | 0 | 0 | 0 | 0 | 253926.45 | 90601.29 | [5 empty] | N | WWNI | 100%
507854 | E-WW-NI-230720-MUTHILL WWTW-FILTER REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-07-27 | 2021-04-09 | 2021-11-22 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27192 | 27192 | 222808.19 | 0 | 0 | 250000.19 | 0 | 0 | 0 | 0 | 250000.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504138 | E-WW-NI-230919-AUCHTERARDER WWTW-INSTALL NEW FLOORING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-02-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 14910.45 | 0 | 14910.45 | 0 | 0 | 0 | 14910.45 | 0 | 0 | 0 | 0 | 14910.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504142 | E-WW-NI-230919-BANKFOOT WWTW-INSTALL NEW FLOORING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-06-09 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 3147.79 | 1912.24 | 5060.03 | 0 | 0 | 0 | 5060.03 | 0 | 0 | 0 | 0 | 5060.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504495 | E-WW-NI-230919-STANLEY WWTW-H&S HANDRAILING IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-06-05 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 3646.21 | 1524.03 | 5170.24 | 0 | 0 | 0 | 5170.24 | 0 | 0 | 0 | 0 | 5170.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509444 | E-WW-NI23102020-CRIMOND KEYHEAD WWPS-INSTALL NEW MS COVERS & SAFETY GRILLS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-27 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.55 | 144.55 | 2065 | 0 | 0 | 2209.55 | 0 | 0 | 0 | 0 | 2209.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509440 | E-WW-NI-23102020-CRIMOND LOGIE AVE WWPS-INSTALL MS COVERS & SAFETY GRILLS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-27 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145.6 | 145.6 | 2080 | 0 | 0 | 2225.6 | 0 | 0 | 0 | 0 | 2225.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509510 | E-WW-NI-23102020-FOCHABERS WWTW-CONSTRUCTION OF ACCESS PATH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-26 |  | 2021-02-13 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5994.18 | 5994.18 | 0 | 0 | 0 | 5994.18 | 0 | 0 | 0 | 0 | 5994.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509516 | E-WW-NI-23102020-HUNTLY WWTW-REPLACE ACCESS PATHS & WALL REFURB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-26 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852.96 | 852.96 | 12185.15 | 0 | 0 | 13038.11 | 0 | 0 | 0 | 0 | 13038.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505016 | E-WW-NI-24012020-HATTON WWPS-REPLACE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-05-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 28149.68 | 37.41 | 28187.09 | 0 | 0 | 0 | 28187.09 | 0 | 0 | 0 | 0 | 28187.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504925 | E-WW-NI-24012020-KINLOSS GLEBE RD WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-20 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 3196.95 | 0 | 3196.95 | 0 | 0 | 0 | 3196.95 | 0 | 0 | 0 | 0 | 3196.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504937 | E-WW-NI-24012020-KINROSS WWTW-INSTALL WALKWAY | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-06-25 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 14319.81 | 0 | 14319.81 | 0 | 0 | 0 | 14319.81 | 0 | 0 | 0 | 0 | 14319.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505529 | E-WW-NI-24022020-AUCHTERMUCHTY SPS-SUPPLY NEW KIOSK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-05 |  | 2020-03-25 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 5628.2 | 37.41 | 5665.61 | 0 | 0 | 0 | 5665.61 | 0 | 0 | 0 | 0 | 5665.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505441 | E-WW-NI-24022020-FORFAR WWTW-SUPPLY MOTOR (CRITICAL SPARE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-04-30 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1303.25 | 1303.25 | 0 | 0 | 0 | 1303.25 | 0 | 0 | 0 | 0 | 1303.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505444 | E-WW-NI-24022020-GUARDBRIDGE WWTW-REPLACE ROTOR & STATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-28 |  | 2020-04-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1041.69 | 0 | 1041.69 | 0 | 0 | 0 | 1041.69 | 0 | 0 | 0 | 0 | 1041.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505526 | E-WW-NI-24022020-LOWER LARGO THE TEMPLE WWPS-REPLACE SOFTSTART PANELS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-03-04 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1125.45 | 16115.27 | 17240.72 | -37.41 | 0 | 0 | 17203.31 | 0 | 0 | 0 | 0 | 17203.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505456 | E-WW-NI-24022020-MARYWELL WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-28 |  | 2020-04-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1948.28 | 1948.28 | 0 | 0 | 0 | 1948.28 | 0 | 0 | 0 | 0 | 1948.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511459 | E-WW-NI-24022021-BRACO STW INLET WWPS-REPLACEMENT COMPRESSOR NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-25 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2 | 172.2 | 2460 | 0 | 0 | 2632.2 | 0 | 0 | 0 | 0 | 2632.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511444 | E-WW-NI-24022021-BRECHIN STC-DSEAR STC health check remedial works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-24 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511448 | E-WW-NI-24022021-DUNFERMLINE STC-DSEAR STC health check remedial works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511552 | E-WW-NI-24022021-ECHT WWTW-REPLACE 2X FE PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253.82 | 253.82 | 3325.56 | 0 | 0 | 3579.38 | 0 | 0 | 0 | 0 | 3579.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511449 | E-WW-NI-24022021-HUNTLY STC-DSEAR STC health check remedial works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511452 | E-WW-NI-24022021-KIRKCALDY STC-DSEAR STC health check remedial works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511453 | E-WW-NI-24022021-PERTH CITY STC-DSEAR STC health check remedial works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511455 | E-WW-NI24022021-ST ANDREWS STC-DSEAR STC health check remedial works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512117 | E-WW-NI-24032021-KEMNAY WWTW-INSTALL TEMP CHEMICAL DOSING SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949.76 | 949.76 | 13568 | 0 | 0 | 14517.76 | 0 | 0 | 0 | 0 | 14517.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512023 | E-WW-NI-24032021-MONTROSE WWTW-REPLACE FLOW MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-25 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.99 | 80.99 | 1061.16 | 0 | 0 | 1142.15 | 0 | 0 | 0 | 0 | 1142.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506348 | E-WW-NI-240420-Auchtertool WWTW-Replace Disk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-08-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21380.19 | 21380.19 | 0 | 0 | 0 | 21380.19 | 0 | 0 | 0 | 0 | 21380.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506347 | E-WW-NI-240420-Forfar WWTW-Porta Cabin | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-07-12 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42168.8 | 42168.8 | 0 | 0 | 0 | 42168.8 | 0 | 0 | 0 | 0 | 42168.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507431 | E-WW-NI-24062020-LOSSIEMOUTH SHORE ST CSO-REFURBISHMENT OF STORM SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-08 |  | 2020-10-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11487.61 | 11487.61 | 0 | 0 | 0 | 11487.61 | 0 | 0 | 0 | 0 | 11487.61 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507372 | E-WW-NI-24062020-MONTROSE WWTW-REPLACE MLSS PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-07-17 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2338.82 | 2338.82 | 0 | 0 | 0 | 2338.82 | 0 | 0 | 0 | 0 | 2338.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507895 | E-WW-NI-24072020-CAIRNIE WWTW-STRUCTURAL REHAB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-09-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21167.72 | 21167.72 | 0 | 0 | 0 | 21167.72 | 0 | 0 | 0 | 0 | 21167.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507889 | E-WW-NI-24072020-DAIRSIE WWTW-PURCHASE 2 MEDIA PACKS (CRITICAL SPARES) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-09-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7851.02 | 7851.02 | 0 | 0 | 0 | 7851.02 | 0 | 0 | 0 | 0 | 7851.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507871 | E-WW-NI-24072020-HOLEMILL WWTW-SEPA LICENCE RENEWAL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-08-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373.9 | 2373.9 | 0 | 0 | 0 | 2373.9 | 0 | 0 | 0 | 0 | 2373.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507867 | E-WW-NI-24072020-VALLEYFIELD WWTW-REPLACEMENT ROLLER DOOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-27 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.33 | 164.33 | 2347.6 | 0 | 0 | 2511.93 | 0 | 0 | 0 | 0 | 2511.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507863 | E-WW-NI-240720-KINCARDINE WWTW-MCC2 KIOSK REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-07-27 | 2021-01-21 | 2021-09-03 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14839 | 14839 | 35160.9 | 0 | 0 | 49999.9 | 0 | 0 | 0 | 0 | 49999.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508475 | E-WW-NI-24082020-EAST WEMYSS WWTW-REFURB ON DETECTION SYSTEMS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-01 |  | 2020-10-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175.4 | 3175.4 | 0 | 0 | 0 | 3175.4 | 0 | 0 | 0 | 0 | 3175.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508947 | E-WW-NI-24092020-CAIRNEYHILL DRUMMORMIE RD SPS-PURCHASE CRITICAL SPARE STORM PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-30 |  | 2020-10-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2306.15 | 2306.15 | 0 | 0 | 0 | 2306.15 | 0 | 0 | 0 | 0 | 2306.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508953 | E-WW-NI-24092020-IRONMILL BAY WWTW-REPLACE SLUDGE TANK ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-30 |  | 2020-01-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2578.49 | 2578.49 | 0 | 0 | 0 | 2578.49 | 0 | 0 | 0 | 0 | 2578.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510045 | E-WW-NI-24112020-BRECHIN STC-REPLACE SLUDGE LINK TANK MIXER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2021-05-01 |  | 2021-02-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5599.74 | 5599.74 | 0 | 0 | 0 | 5599.74 | 0 | 0 | 0 | 0 | 5599.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510043 | E-WW-NI-24112020-DUNDEE BURNSIDE RD SPS CSO-REPLACE ROTORKS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1446.15 | 1446.15 | 20659.23 | 0 | 0 | 22105.38 | 0 | 0 | 0 | 0 | 22105.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510041 | E-WW-NI-24112020-FORRES ADAM DRIVE WWPS-REPLACEMENT COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247.1 | 247.1 | 3530 | 0 | 0 | 3777.1 | 0 | 0 | 0 | 0 | 3777.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509987 | E-WW-NI-24112020-PITLOCHRY WWTW-INSTALL NEW PLATFORM & STAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133.77 | 133.77 | 1911 | 0 | 0 | 2044.77 | 0 | 0 | 0 | 0 | 2044.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510892 | E-WW-NI-25012021-COUPAR ANGUS WWTW-REPLACE CRITICAL SPARE DISK FILTER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1867.58 | 1867.58 | 0 | 0 | 0 | 1867.58 | 0 | 0 | 0 | 0 | 1867.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510908 | E-WW-NI-25012021-DRUMLITHIE WWTW-REPLACE MOTOR & GEARBOX (CRITICAL SPARES) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-28 |  | 2021-03-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2305.85 | 2305.85 | 0 | 0 | 0 | 2305.85 | 0 | 0 | 0 | 0 | 2305.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510867 | E-WW-NI-25012021-DRUMLITHIE WWTW-REPLACEMENT MLSS PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2465.66 | 2465.66 | 0 | 0 | 0 | 2465.66 | 0 | 0 | 0 | 0 | 2465.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510860 | E-WW-NI-25012021-MARYKIRK WWTW-REPLACEMENT MCC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-04-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1337.5 | 1337.5 | 0 | 0 | 0 | 1337.5 | 0 | 0 | 0 | 0 | 1337.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510857 | E-WW-NI-25012021-NEWTYLE WWTW-REPLACEMENT DO PROBES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-27 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2573.65 | 2573.65 | 0 | 0 | 0 | 2573.65 | 0 | 0 | 0 | 0 | 2573.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505532 | E-WW-NI-25022020-PADANARAM WWPS-REPLACE SHAFT DRIVEN PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1287.8 | 0 | 1287.8 | 18397.15 | 0 | 0 | 19684.95 | 0 | 0 | 0 | 0 | 19684.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511557 | E-WW-NI-25022021-ELLON WWTW-REPLACE FLOW & DO MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2943.89 | 2943.89 | 0 | 0 | 0 | 2943.89 | 0 | 0 | 0 | 0 | 2943.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511464 | E-WW-NI-25022021-MEIGLE WWTW-DOOR REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-25 |  | 2021-04-03 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1471.25 | 1471.25 | 0 | 0 | 0 | 1471.25 | 0 | 0 | 0 | 0 | 1471.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511473 | E-WW-NI-25022021-PITMEDDEN WWTW-REPLACE SCREW PUMP MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-26 |  | 2021-05-25 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1607.55 | 1607.55 | 0 | 0 | 0 | 1607.55 | 0 | 0 | 0 | 0 | 1607.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505946 | E-WW-NI-25032020-BLAIRGOWRIE WWTW-REPLACE ANOXIC ZONE MIXER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-26 |  | 2020-04-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 133.24 | 1996.89 | 2130.13 | 0 | 0 | 0 | 2130.13 | 0 | 0 | 0 | 0 | 2130.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512129 | E-WW-NI-25032021-ABERLOUR WWTW-CAUSTIC DOSING UNIT (UNLIMITED USE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884.52 | 884.52 | 12636 | 0 | 0 | 13520.52 | 0 | 0 | 0 | 0 | 13520.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512127 | E-WW-NI-25032021-BALMEDIE WWTW-INSTALL CHEMICAL DOSING UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949.76 | 949.76 | 13568 | 0 | 0 | 14517.76 | 0 | 0 | 0 | 0 | 14517.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512118 | E-WW-NI-25032021-COWDENBEATH WWPS-REPLACEMENT FENCING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1277.5 | 1277.5 | 18250 | 0 | 0 | 19527.5 | 0 | 0 | 0 | 0 | 19527.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512119 | E-WW-NI-25032021-LADYBANK WWPS-H&S IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2360.4 | 2360.4 | 33720 | 0 | 0 | 36080.4 | 0 | 0 | 0 | 0 | 36080.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512125 | E-WW-NI-25032021-PERTH FRIARTON WWPS-INSTALL VENTILATION SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.65 | 244.65 | 3205.44 | 0 | 0 | 3450.09 | 0 | 0 | 0 | 0 | 3450.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512146 | E-WW-NI-25032021-ST ANDREWS WWTW-REPLACE LOWER SCRAPER ASSEMBLY & BLADES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-07-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5140.1 | 0 | 0 | 5140.1 | 0 | 0 | 0 | 0 | 5140.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507376 | E-WW-NI-25062020-CARSIE WWTW-REPLACE PERIMETER FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-08-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765.5 | 1765.5 | 0 | 0 | 0 | 1765.5 | 0 | 0 | 0 | 0 | 1765.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507434 | E-WW-NI-25062020-KINROSSIE WWTW-INSTALL NEW GRATINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-11-26 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2790.56 | 2790.56 | 0 | 0 | 0 | 2790.56 | 0 | 0 | 0 | 0 | 2790.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507411 | E-WW-NI-25062020-PERTH FRIARTON WWPS-PURCHASE CRITICAL SPARE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-08-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14043.35 | 14043.35 | 0 | 0 | 0 | 14043.35 | 0 | 0 | 0 | 0 | 14043.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508478 | E-WW-NI-25082020-ABDERDEEN GRANDHOLM VILLAGE SPS-REPLACE PUMPS NO1 & NO2. | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-01 |  | 2020-10-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5501.19 | 5501.19 | 0 | 0 | 0 | 5501.19 | 0 | 0 | 0 | 0 | 5501.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508477 | E-WW-NI-25082020-MUGIEMOSS RD WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-01 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5053.72 | 5053.72 | 0 | 0 | 0 | 5053.72 | 0 | 0 | 0 | 0 | 5053.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508986 | E-WW-NI-25092020-BLAIRINGONE WWTW-INSTALL NEW FRAME & GRATINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237.16 | 237.16 | 3388 | 0 | 0 | 3625.16 | 0 | 0 | 0 | 0 | 3625.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508985 | E-WW-NI-25092020-ELGIN REIKET LANE WWPS-INSTALL NEW COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265.79 | 265.79 | 3797 | 0 | 0 | 4062.79 | 0 | 0 | 0 | 0 | 4062.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508988 | E-WW-NI-25092020-KEITH BROAD LANE CSO-INSTALL NEW COVERS & GRILLS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.6 | 425.6 | 6080 | 0 | 0 | 6505.6 | 0 | 0 | 0 | 0 | 6505.6 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508992 | E-WW-NI-25092020-KEITH NELSON TERRACE WWPS-INSTALL NEW COVERS & GRILLS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216.58 | 216.58 | 3094 | 0 | 0 | 3310.58 | 0 | 0 | 0 | 0 | 3310.58 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508975 | E-WW-NI-25092020-MINTLAW WWTW-REFURBISH BLOWER MOTOR NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-30 |  | 2021-04-05 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4659.78 | 4659.78 | 187.32 | 0 | 0 | 4847.1 | 0 | 0 | 0 | 0 | 4847.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504122 | E-WW-NI-251119-FRIOCKHEIM STW-CRITICAL SPARES (SURFACE AERATOR) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-03 |  | 2020-02-07 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 2418.12 | 0 | 2418.12 | 0 | 0 | 0 | 2418.12 | 0 | 0 | 0 | 0 | 2418.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504130 | E-WW-NI-251119-PERTH CITY WWTW-REFURB WASHPRESS UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-03-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 14425.19 | 0 | 14425.19 | 0 | 0 | 0 | 14425.19 | 0 | 0 | 0 | 0 | 14425.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504112 | E-WW-NI-251119-ST MONANS EASTSHORE SPS-REPLACE PUMP 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-03 |  | 2020-01-25 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2934.31 | 0 | 2934.31 | 0 | 0 | 0 | 2934.31 | 0 | 0 | 0 | 0 | 2934.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510047 | E-WW-NI-25112020-LETHAM WWTW-REPLACEMENT MCC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355.23 | 355.23 | 4502.91 | 0 | 0 | 4858.14 | 0 | 0 | 0 | 0 | 4858.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510060 | E-WW-NI-25112020-NEWMACHAR WWTW-REPLACEMENT PROBES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-01 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8805.88 | 8805.88 | 0 | 0 | 0 | 8805.88 | 0 | 0 | 0 | 0 | 8805.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510001 | E-WW-NI-25112020-PITLOCHRY WWTW-REPLACEMENT DRIVE ASSEMBLY (RBC NO2) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-25 |  | 2021-02-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23519.67 | 23519.67 | 0 | 0 | 0 | 23519.67 | 0 | 0 | 0 | 0 | 23519.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510057 | E-WW-NI-25112020-SAUCHEN WWTW-REPLACE INLET ROTORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-01 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261.56 | 261.56 | 3736.59 | 0 | 0 | 3998.15 | 0 | 0 | 0 | 0 | 3998.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511573 | E-WW-NI-26022021-CRIMOND NEW HADDO WWPS-REPLACE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3386.55 | 3386.55 | 0 | 0 | 0 | 3386.55 | 0 | 0 | 0 | 0 | 3386.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511567 | E-WW-NI-26022021-DUFFTOWN WWTW-INLET SCREEN BASKET REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-02 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270.27 | 270.27 | 3541.08 | 0 | 0 | 3811.35 | 0 | 0 | 0 | 0 | 3811.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511563 | E-WW-NI-26022021-HATTON OF CRUDEN WWTW-REPLACE SAND FILTER & UV FEED PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401.7 | 401.7 | 5565.78 | 0 | 0 | 5967.48 | 0 | 0 | 0 | 0 | 5967.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511571 | E-WW-NI-26022021-KELTY SST-ROAD REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13541.92 | 13541.92 | 0 | 0 | 0 | 13541.92 | 0 | 0 | 0 | 0 | 13541.92 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506009 | E-WW-NI-26032020-BURNTISLAND HAUGH RD WWPS-REPLACE NO3 STORM PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-01 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260.05 | 1260.05 | 16857.03 | 0 | 0 | 18117.08 | 0 | 0 | 0 | 0 | 18117.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506935 | E-WW-NI-26052020-AUCHTERARDER WWTW-REPLACEMENT INLET SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-02 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38835.05 | 38835.05 | 195.13 | 0 | 0 | 39030.18 | 0 | 0 | 0 | 0 | 39030.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506856 | E-WW-NI-26052020-CROSSGATES HUMBUG PARK WWPS-REPLACE FOUL PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-06-11 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1473.9 | 1473.9 | 0 | 0 | 0 | 1473.9 | 0 | 0 | 0 | 0 | 1473.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506972 | E-WW-NI-26052020-NEWPORT & TAYPORT WWTW-REPLACE DUPLEX FILTER SCREENS & BASKETS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-06-15 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.32 | 3146.32 | 0 | 0 | 0 | 3146.32 | 0 | 0 | 0 | 0 | 3146.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506938 | E-WW-NI-26052020-SAUCHEN WWTW-REPLACE STORM RETURN PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-02 |  | 2020-10-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3192.31 | 3192.31 | 0 | 0 | 0 | 3192.31 | 0 | 0 | 0 | 0 | 3192.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507460 | E-WW-NI-26062020-BALBEGGIE WWTW-INSTALL TEMP QP33 DOSING SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-07-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14517.76 | 14517.76 | 0 | 0 | 0 | 14517.76 | 0 | 0 | 0 | 0 | 14517.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507441 | E-WW-NI-26062020-COVE STONEYHILL TCE WWPS-REFURBISH WET WELL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-08 |  | 2020-09-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10180 | 10180 | 0 | 0 | 0 | 10180 | 0 | 0 | 0 | 0 | 10180 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507453 | E-WW-NI-26062020-CROSSGATES HUMBUG PARK WWPS-REPLACE DAMAGED CONCRETE PLINTH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-01-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4387 | 4387 | 0 | 0 | 0 | 4387 | 0 | 0 | 0 | 0 | 4387 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507463 | E-WW-NI-26062020-GLAMIS WWTW-REPLACE EXISTING CENTRE COLUMN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-09-24 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4232.92 | 4232.92 | 0 | 0 | 0 | 4232.92 | 0 | 0 | 0 | 0 | 4232.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507467 | E-WW-NI-26062020-LOSSIEMOUTH GREGORY PLACE WWPS- REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-09-15 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7777.03 | 7777.03 | 0 | 0 | 0 | 7777.03 | 0 | 0 | 0 | 0 | 7777.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507449 | E-WW-NI-26062020-NEWMACHAR WWTW-REPLACE PUMPS & INSTALL CONCERTOR CONTROL PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-06 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20466.31 | 20466.31 | 0.01 | 0 | 0 | 20466.32 | 0 | 0 | 0 | 0 | 20466.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503995 | E-WW-NI-261119-ELLON WWTW-REPLACE POLYMER PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-01-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2126.09 | 0 | 2126.09 | 0 | 0 | 0 | 2126.09 | 0 | 0 | 0 | 0 | 2126.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504994 | E-WW-NI-27012020-KIRKCALDY WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 4116.29 | 0 | 4116.29 | 0 | 0 | 0 | 4116.29 | 0 | 0 | 0 | 0 | 4116.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504939 | E-WW-NI-27012020-NORTH QUEENSFERRY BATTERY RD SPS-REPLACE WET WELL & VALVE CHAMBER COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-03-05 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 2487.75 | 0 | 2487.75 | 0 | 0 | 0 | 2487.75 | 0 | 0 | 0 | 0 | 2487.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510998 | E-WW-NI-27012021-MARYCULTER WWTW-BIO DISC OVERHAUL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688.04 | 688.04 | 9829.2 | 0 | 0 | 10517.24 | 0 | 0 | 0 | 0 | 10517.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510999 | E-WW-NI-27012021-ST ANDREWS WWTW-REPLACE 5XACTUATED VALVES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711.46 | 711.46 | 9896.5 | 0 | 0 | 10607.96 | 0 | 0 | 0 | 0 | 10607.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505457 | E-WW-NI-27022020-ABERDOUR SILVER SANDS WWTW-REPLACE TOP WATER RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-02 |  | 2020-04-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1153.59 | 426.67 | 1580.26 | 0 | 0 | 0 | 1580.26 | 0 | 0 | 0 | 0 | 1580.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505538 | E-WW-NI-27022020-ABERFELDY WWTW-WELFARE FACILITIES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 339.5 | 12450 | 12789.5 | 532 | 0 | 0 | 13321.5 | 0 | 0 | 0 | 0 | 13321.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505536 | E-WW-NI-27022020-BLACKFORD WWTW-WELFARE FACILITIES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0 | 616 | 8800 | 0 | 0 | 9416 | 0 | 0 | 0 | 0 | 9416 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505533 | E-WW-NI-27022020-DUNSHALT WWPS-REPLACE STORM PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-05 |  | 2020-05-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 175.65 | 2509.3 | 2684.95 | 0 | 0 | 0 | 2684.95 | 0 | 0 | 0 | 0 | 2684.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505459 | E-WW-NI-27022020-LADYBANK WWPS-INSTALL HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-02 |  | 2020-05-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1468.47 | 543.13 | 2011.6 | 0 | 0 | 0 | 2011.6 | 0 | 0 | 0 | 0 | 2011.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506014 | E-WW-NI-27032020-HATTON OF CRUDEN WWTW-INSTALL NEW SIPHON | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-08-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6218.87 | 6218.87 | 0 | 0 | 0 | 6218.87 | 0 | 0 | 0 | 0 | 6218.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506011 | E-WW-NI-27032020-MINTLAW WWTW-REPLACE MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-10-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5938.46 | 5938.46 | 0 | 0 | 0 | 5938.46 | 0 | 0 | 0 | 0 | 5938.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506495 | E-WW-NI-27042020-KINCARDINE WWTW-REPLACE PIPEWORK IN PST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-09 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11657.87 | 11657.87 | 0 | 0 | 0 | 11657.87 | 0 | 0 | 0 | 0 | 11657.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506951 | E-WW-NI-27052020-ABOYNE WWTW-INSTALL PERIMETER FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-02 |  | 2020-07-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9659.4 | 9659.4 | 0 | 0 | 0 | 9659.4 | 0 | 0 | 0 | 0 | 9659.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506946 | E-WW-NI-27052020-ANSTRUTHER ESPLANADE WWPS-REPLACEMENT PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-02 |  | 2020-09-11 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7824.32 | 7824.32 | 0 | 0 | 0 | 7824.32 | 0 | 0 | 0 | 0 | 7824.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506957 | E-WW-NI-27052020-IRONMILL BAY WWTW-REPLACE HOIST INLET & RAS PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-05 |  | 2020-07-02 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13953.6 | 13953.6 | 0 | 0 | 0 | 13953.6 | 0 | 0 | 0 | 0 | 13953.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506948 | E-WW-NI-27052020-SCOONIEHILL WWPS-REPLACEMENT PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-02 |  | 2020-11-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18123.25 | 18123.25 | 0 | 0 | 0 | 18123.25 | 0 | 0 | 0 | 0 | 18123.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507909 | E-WW-NI-27072020-CRIEFF TURRET PARK WWPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-28 |  | 2020-08-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768.15 | 1768.15 | 0 | 0 | 0 | 1768.15 | 0 | 0 | 0 | 0 | 1768.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507897 | E-WW-NI-270720-METHVEN WWTW-REED BED REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-07-28 | 2021-01-25 | 2021-09-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6394 | 6394 | 243605.3 | 0 | 0 | 249999.3 | 0 | 0 | 0 | 0 | 249999.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508489 | E-WW-NI-27082020-HUNTLY WWTW-REPLACE 6XPST DESLUDGING VALVES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-01 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6755.98 | 6755.98 | 0 | 0 | 0 | 6755.98 | 0 | 0 | 0 | 0 | 6755.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509570 | E-WW-NI-27102020-CROSSFORD LYNE GROVE WWPS-REPAIRS TO BRICK WALL & RELAYING OF MONO BLOCKS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-11-16 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979.91 | 2979.91 | 0 | 0 | 0 | 2979.91 | 0 | 0 | 0 | 0 | 2979.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509573 | E-WW-NI-27102020-MILNATHORT WWTW-REFURB RAS P[UMP NO3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-11-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6399.96 | 6399.96 | 0 | 0 | 0 | 6399.96 | 0 | 0 | 0 | 0 | 6399.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509531 | E-WW-NI-27102020-PITMEDDEN WWTW-REPLACEMENT MOTORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-11-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2102.98 | 2102.98 | 0 | 0 | 0 | 2102.98 | 0 | 0 | 0 | 0 | 2102.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509519 | E-WW-NI-27102020-TORRYBURN WWPS-REPLACE FOUL PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-11-19 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037.54 | 2037.54 | 0 | 0 | 0 | 2037.54 | 0 | 0 | 0 | 0 | 2037.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504037 | E-WW-NI-271119-NEWMACHAR STW-REPLACE INLET SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-01-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 48920.4 | 0 | 48920.4 | 0 | 0 | 0 | 48920.4 | 0 | 0 | 0 | 0 | 48920.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510063 | E-WW-NI-27112020-ABERFELDY WWTW-REPLACE SLUDGE THICKENER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-02 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125725 | 125725 | 0 | 0 | 0 | 125725 | 0 | 0 | 0 | 0 | 125725 | 181202.57 | [5 empty] | N | CM_WWNI | 100%
510071 | E-WW-NI-27112020-ABERFELDY WWTW-REPLACE SLUDGE THICKENER (2ND CODE) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-02 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 8225 | 117500 | 0 | 0 | 125725 | 0 | 0 | 0 | 0 | 125725 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510031 | E-WW-NI-27112020-ALYTH WWTW-REPLACE RAS PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2021-02-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1984.08 | 1984.08 | 0 | 0 | 0 | 1984.08 | 0 | 0 | 0 | 0 | 1984.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510081 | E-WW-NI-27112020-CHARLOTTE ST WWPS-REPLACEMENT DRIVES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-02 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28049.37 | 28049.37 | 0 | 0 | 0 | 28049.37 | 0 | 0 | 0 | 0 | 28049.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510068 | E-WW-NI-27112020-CUPAR WWTW-REPLACE DAMAGED & FAULTY LIGHTING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-02 |  | 2021-03-11 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6424.94 | 6424.94 | 0 | 0 | 0 | 6424.94 | 0 | 0 | 0 | 0 | 6424.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510035 | E-WW-NI-27112020-FINDOCHTY EAST BEACH SPS-REPLACE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-30 |  | 2021-02-20 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2323.38 | 2323.38 | 0 | 0 | 0 | 2323.38 | 0 | 0 | 0 | 0 | 2323.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510084 | E-WW-NI-27112020-KEITH WWTW-BOILERHOUSE REFURBISHMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-02 |  | 2021-05-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663.91 | 663.91 | 8912.59 | 0 | 0 | 9576.5 | 0 | 0 | 0 | 0 | 9576.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510061 | E-WW-NI-27112020-ST NICHOLAS WWPS-REPLACE NO1 FORWARDING PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-01 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3197.54 | 3197.54 | 45679.11 | 0 | 0 | 48876.65 | 0 | 0 | 0 | 0 | 48876.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510033 | E-WW-NI-27112020-STRATHMIGLO WWTW-REPLACE VSDS ON WASHWATER PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3249.46 | 3249.46 | 49.14 | 0 | 0 | 3298.6 | 0 | 0 | 0 | 0 | 3298.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510087 | E-WW-NI-27112020-WELLBANK WWPS-REPLACEMENT IMPELLORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-02 |  | 2021-03-11 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3021.64 | 3021.64 | 0 | 0 | 0 | 3021.64 | 0 | 0 | 0 | 0 | 3021.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510029 | E-WW-NI-271120-Garthdee Syphon CSO Screen & Syphon Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-12-02 | 2021-01-18 | 2021-04-19 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236000 | 236000 | 0 | 0 | 0 | 236000 | 0 | 0 | 0 | 0 | 236000 | 90601.29 | [5 empty] | N | WWNI | 100%
505006 | E-WW-NI-28012020-BRECHIN WWTW-REPLACE PRIMARY PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-23 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 2873.59 | 56.12 | 2929.71 | 0 | 0 | 0 | 2929.71 | 0 | 0 | 0 | 0 | 2929.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504950 | E-WW-NI-28012020-DUNDEE CITY QUAY WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-03-27 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 1476.47 | 0 | 1476.47 | 0 | 0 | 0 | 1476.47 | 0 | 0 | 0 | 0 | 1476.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505125 | E-WW-NI-28012020-MEIGLE WWTW-PIPE MODIFICATIONS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-12 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 54677 | -44694.92 | 9982.08 | 64917.92 | 0 | 0 | 74900 | 0 | 0 | 0 | 0 | 74900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504942 | E-WW-NI-28012020-SPRINGFIELD WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-28 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1510.41 | 0 | 1510.41 | 0 | 0 | 0 | 1510.41 | 0 | 0 | 0 | 0 | 1510.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504997 | E-WW-NI-28012020-STRATHMIGLO WWTW-REPLACE RAS PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-20 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 8481.89 | 55.41 | 8537.3 | 0 | 0 | 0 | 8537.3 | 0 | 0 | 0 | 0 | 8537.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511001 | E-WW-NI-28012021-MUTHILL WWTW-SUPPLY INSTALL 32 50MM BLAST FURNACE SLAG | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200.5 | 4200.5 | 59740 | 0 | 0 | 63940.5 | 0 | 0 | 0 | 0 | 63940.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505501 | E-WW-NI-28022020-AUCHTERARDER WWTW-REPLACE GRIT PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-03 |  | 2020-05-15 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 144.13 | 2059 | 2203.13 | 0 | 0 | 0 | 2203.13 | 0 | 0 | 0 | 0 | 2203.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505509 | E-WW-NI-28022020-COMRIE WWTW-REPLACE BOTTOM BEARING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-04 |  | 2020-04-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 1562.2 | 0 | 1562.2 | 0 | 0 | 0 | 1562.2 | 0 | 0 | 0 | 0 | 1562.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505496 | E-WW-NI-28022020-DRUMOAK WWTW-REFURB ACTUATING PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-03 |  | 2020-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 113.47 | 1621.02 | 1734.49 | 0 | 0 | 0 | 1734.49 | 0 | 0 | 0 | 0 | 1734.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505488 | E-WW-NI-28022020-MIDMAR HOUSING ST-FIT PERIMETER FENCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-03 |  | 2020-11-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 109.2 | 1560 | 1669.2 | 0 | 0 | 0 | 1669.2 | 0 | 0 | 0 | 0 | 1669.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505494 | E-WW-NI-28022020-MONTROSE GREY HARLINGS WWPS-REPLACE GUIDERAILS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2021-05-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1339.96 | 0 | 1339.96 | 0 | 0 | 0 | 1339.96 | 0 | 0 | 0 | 0 | 1339.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505545 | E-WW-NI-28022020-TURRIFF WWTW-REPAIR LIQUOR RETURN PUMPING MAIN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-03-06 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 205.38 | 2934.09 | 3139.47 | 0.01 | 0 | 0 | 3139.48 | 0 | 0 | 0 | 0 | 3139.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505546 | E-WW-NI-28022020-UDNY GREEN WWPS-INSTALL CONTROL KIOSK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 510.18 | 26.59 | 536.77 | 10115.45 | 0 | 0 | 10652.22 | 0 | 0 | 0 | 0 | 10652.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506393 | E-WW-NI-28042020-KIRRIEMUIR WWTW-AERATOR REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-29 |  | 2020-07-20 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39575.26 | 39575.26 | 0 | 0 | 0 | 39575.26 | 0 | 0 | 0 | 0 | 39575.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506391 | E-WW-NI-28042020-PERTH CITY STC-REPLACE FLOW MONITOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-29 |  | 2020-05-13 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070.47 | 2070.47 | 0 | 0 | 0 | 2070.47 | 0 | 0 | 0 | 0 | 2070.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507926 | E-WW-NI-28072020-MUTHILL WWTW-SUPPLY & INSTALL 600L SB DOSING TANK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-29 |  | 2020-10-09 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.46 | 2399.46 | 0 | 0 | 0 | 2399.46 | 0 | 0 | 0 | 0 | 2399.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508467 | E-WW-NI-28082020-ABERUTHVEN WWTW-REPLACEMENT HMI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-01 |  | 2020-10-13 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1818.92 | 1818.92 | 0 | 0 | 0 | 1818.92 | 0 | 0 | 0 | 0 | 1818.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508505 | E-WW-NI-28082020-CORNHILL WWTW-LAY NEW CONCRETE PATH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-01 |  | 2020-11-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3322.31 | 3322.31 | 0 | 0 | 0 | 3322.31 | 0 | 0 | 0 | 0 | 3322.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508508 | E-WW-NI-28082020-DUNFERMLINE WWTW-REPLACE GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-01 |  | 2021-02-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9537.98 | 9537.98 | 0 | 0 | 0 | 9537.98 | 0 | 0 | 0 | 0 | 9537.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508456 | E-WW-NI-28082020-DUNFERMLINE WWTW-REPLACEMENT DOORS (ADMIN BUILDING) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-10-24 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2134.65 | 2134.65 | 0 | 0 | 0 | 2134.65 | 0 | 0 | 0 | 0 | 2134.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508496 | E-WW-NI-28082020-KENNETHMONT WWTW-FILTER BED STRUCTURE REPAIR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-01 |  | 2020-09-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5044.83 | 5044.83 | 0 | 0 | 0 | 5044.83 | 0 | 0 | 0 | 0 | 5044.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508674 | E-WW-NI-28082020-MONTROSE WWTW-DAB UNIT REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-27 |  | 2020-11-06 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214037.41 | 214037.41 | 0 | 0 | 0 | 214037.41 | 0 | 0 | 0 | 0 | 214037.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508514 | E-WW-NI-28082020-VALLEYFIELD WWTW-REPLACE VSD ON OUTLET PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-01 |  | 2020-09-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2904.22 | 2904.22 | 0 | 0 | 0 | 2904.22 | 0 | 0 | 0 | 0 | 2904.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509575 | E-WW-NI-28102020-INVERKEITHING PRESTON CRES WWPS-UPGRADE WELFARE FACILITIES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2021-02-10 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6393.21 | 6393.21 | 0 | 0 | 0 | 6393.21 | 0 | 0 | 0 | 0 | 6393.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509577 | E-WW-NI-28102020-INVERURIE WWTW-ACCESS RD STONE DISTRIBUTION | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-08-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3295.6 | 3295.6 | 0 | 0 | 0 | 3295.6 | 0 | 0 | 0 | 0 | 3295.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509533 | E-WW-NI-28102020-NEWMACHAR WWTW-SITE SURVEY | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1861.36 | 1861.36 | 0 | 0 | 0 | 1861.36 | 0 | 0 | 0 | 0 | 1861.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504063 | E-WW-NI-281119-BANKTON PARK WWPS-CONTROL PANEL REPAIR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-02-09 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1870.33 | 0 | 1870.33 | 0 | 0 | 0 | 1870.33 | 0 | 0 | 0 | 0 | 1870.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510976 | E-WW-NI-29012021-BELHELVIE WWPS-INSTALL FALL ARREST GRATINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 147 | 2100 | 0 | 0 | 2247 | 0 | 0 | 0 | 0 | 2247 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510977 | E-WW-NI-29012021-DALMUINZIE ROAD WWPS-INSTALL FALL ARREST GRATINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.5 | 171.5 | 2450 | 0 | 0 | 2621.5 | 0 | 0 | 0 | 0 | 2621.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511005 | E-WW-NI-29012021-DUNFERMLINE WWTW-REFURB PRIMARY SLUDGE PUMP NO1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4919.07 | 4919.07 | 0 | 0 | 0 | 4919.07 | 0 | 0 | 0 | 0 | 4919.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510987 | E-WW-NI-29012021-GARDENSTOWN WWTW-HMI REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-01 |  | 2021-03-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2141.58 | 2141.58 | 0 | 0 | 0 | 2141.58 | 0 | 0 | 0 | 0 | 2141.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511016 | E-WW-NI-29012021-KEMNAY WWTW-INSTALL GALVANISED CHECKER PLATE RUNNERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 676.7 | 676.7 | 9400 | 0 | 0 | 10076.7 | 0 | 0 | 0 | 0 | 10076.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511015 | E-WW-NI-29012021-KEMNAY WWTW-INSTALL TURBIDITY MONITORING SYSTEM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3474.04 | 3474.04 | 8098.4 | 0 | 0 | 11572.44 | 0 | 0 | 0 | 0 | 11572.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510982 | E-WW-NI-29012021-POTTERTON DENHEAD WWPS-INSTALL FALL ARREST GRATINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.5 | 171.5 | 2450 | 0 | 0 | 2621.5 | 0 | 0 | 0 | 0 | 2621.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510989 | E-WWNI-29012021-SPRINGFIELD WWTW-CONSTRUCT SOAKAWAY | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-01 |  | 2021-03-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2426.2 | 2426.2 | 0 | 0 | 0 | 2426.2 | 0 | 0 | 0 | 0 | 2426.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511013 | E-WW-NI-29012021-ST FERGUS KIRKTOWN WWPS-KIOSK REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5564 | 5564 | 0 | 0 | 0 | 5564 | 0 | 0 | 0 | 0 | 5564 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510971 | E-WW-NI-29012021-TARLAND WWTW-REPLACE FILTER FEED PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.9 | 144.9 | 1802.72 | 0 | 0 | 1947.62 | 0 | 0 | 0 | 0 | 1947.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510994 | E-WW-NI-29012021-TURRIFF WWTW-SUPPLY 8XSAF KIOSK ACOUSTIC COUPLINGS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2597.4 | 2597.4 | -18.7 | 0 | 0 | 2578.7 | 0 | 0 | 0 | 0 | 2578.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506501 | E-WW-NI-29042020-AUCHTERMUCHTY SPS-REPLACE FORWARDING PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-06-23 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5763.89 | 5763.89 | 0 | 0 | 0 | 5763.89 | 0 | 0 | 0 | 0 | 5763.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506503 | E-WW-NI-29042020-OLDMELDRUM WWTW-CRITICAL SPARE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-05-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3970.98 | 3970.98 | 0 | 0 | 0 | 3970.98 | 0 | 0 | 0 | 0 | 3970.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506385 | E-WW-NI-290420-Aboyne STW Biofilter No.2 Media Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-05-13 | 2020-06-19 | 2020-08-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192118.42 | 192118.42 | 0 | 0 | 0 | 192118.42 | 0 | 0 | 0 | 0 | 192118.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506919 | E-WW-NI-29052020-DUFFUS WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-02 |  | 2020-07-07 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2174.41 | 2174.41 | 0 | 0 | 0 | 2174.41 | 0 | 0 | 0 | 0 | 2174.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506965 | E-WW-NI-29052020-PETERHEAD KEITH INCH SPS-REPLACE WWPS COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-03 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619.24 | 619.24 | 8560.3 | 0 | 0 | 9179.54 | 0 | 0 | 0 | 0 | 9179.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506971 | E-WW-NI-29052020-SANDHAVEN WWPS-REPLACE WWPS COVERS & RELAY TYPE 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-11-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8980.3 | 8980.3 | 0 | 0 | 0 | 8980.3 | 0 | 0 | 0 | 0 | 8980.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506913 | E-WW-NI-29052020-STRICHEN WWTW-ROOF REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-05 |  | 2021-03-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2123.91 | 2123.91 | -37.41 | 0 | 0 | 2086.5 | 0 | 0 | 0 | 0 | 2086.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506909 | E-WW-NI-29052020-TARVES WWTW-REPLACE FEED PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-05 |  | 2020-07-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1921.38 | 1921.38 | 0 | 0 | 0 | 1921.38 | 0 | 0 | 0 | 0 | 1921.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507426 | E-WW-NI-29062020-KEITH WWTW-REPLACE WINDOWS & DOORS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-09-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9839.72 | 9839.72 | 0 | 0 | 0 | 9839.72 | 0 | 0 | 0 | 0 | 9839.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507470 | E-WW-NI-29062020-PERTH CITY WWTW-REPLACE ROTORK ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-09-13 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1839.5 | 1839.5 | 0 | 0 | 0 | 1839.5 | 0 | 0 | 0 | 0 | 1839.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507968 | E-WW-NI-29072020-ABDERDEEN YORK PL WWPS-REPLACE ROTORK ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2020-10-11 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050.05 | 2050.05 | 0 | 0 | 0 | 2050.05 | 0 | 0 | 0 | 0 | 2050.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507961 | E-WW-NI-29072020-DUNDEE NINEWELLS WWPS-REPLACE STORM PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2020-08-27 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2436.6 | 2436.6 | 0 | 0 | 0 | 2436.6 | 0 | 0 | 0 | 0 | 2436.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508998 | E-WW-NI-29092020-ABOYNE WWTW-CREATE ACCESS ROAD PASSING PLACES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-29 |  | 2020-11-09 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623.7 | 1623.7 | 0 | 0 | 0 | 1623.7 | 0 | 0 | 0 | 0 | 1623.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509107 | E-WW-NI-29092020-SAUCHEN WWTW-REPLACE DIFFUSER MEMBRANES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-13 |  | 2020-10-21 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4678.25 | 4678.25 | 0 | 0 | 0 | 4678.25 | 0 | 0 | 0 | 0 | 4678.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509105 | E-WW-NI-29092020-TARLAND WWTW-UPGRADE ACCESS ROAD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-13 |  | 2020-11-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7597 | 7597 | 0 | 0 | 0 | 7597 | 0 | 0 | 0 | 0 | 7597 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509000 | E-WW-NI-290920-Aboyne STW Inlet Screw No.1 Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-11-16 | 2021-03-15 | 2021-12-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31030 | 31030 | 43970.07 | 0 | 0 | 75000.07 | 0 | 0 | 0 | 0 | 75000.07 | 90601.29 | [5 empty] | N | WWNI | 100%
509543 | E-WW-NI-29102020-MONTROSE COBDEN ST CSO-REPLACE DRIVE SHAFT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2021-02-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163.36 | 1163.36 | 0 | 0 | 0 | 1163.36 | 0 | 0 | 0 | 0 | 1163.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509545 | E-WW-NI-29102020-PITMEDDEN WWTW-REPLACE RAS SAS MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-11-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6294.96 | 6294.96 | 0 | 0 | 0 | 6294.96 | 0 | 0 | 0 | 0 | 6294.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504159 | E-WW-NI-291119-DRUMLITHIE WWTW-REPLACE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-01-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 6136.45 | 0 | 6136.45 | 0 | 0 | 0 | 6136.45 | 0 | 0 | 0 | 0 | 6136.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504094 | E-WW-NI-291119-GOURDIEBURN WWPS-REPLACE PUMP 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-03 |  | 2020-01-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2204.41 | 0 | 2204.41 | 0 | 0 | 0 | 2204.41 | 0 | 0 | 0 | 0 | 2204.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504173 | E-WW-NI-291119-KEMNAY PRELIM STW INLET SPS-REPLACE PENSTOCK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-02-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3443.26 | 0 | 3443.26 | 0 | 0 | 0 | 3443.26 | 0 | 0 | 0 | 0 | 3443.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504169 | E-WW-NI-291119-KENNETHMONT WWTW-REPLACE SCREEEN BASKET | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-08-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3585.41 | 2178.09 | 5763.5 | 0 | 0 | 0 | 5763.5 | 0 | 0 | 0 | 0 | 5763.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506118 | E-WW-NI-30032020-ABOYNE CHARLTON RD SPS-REPLACE 2XPUMPS & INSTALL CONCERTOR PUMP CONTROL PANEL; | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-28 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12414.1 | 12414.1 | 0 | 0 | 0 | 12414.1 | 0 | 0 | 0 | 0 | 12414.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506110 | E-WW-NI-30032020-COMRIE WWTW-INSTALL TOP WATER RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-11-17 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30063.45 | 30063.45 | 0 | 0 | 0 | 30063.45 | 0 | 0 | 0 | 0 | 30063.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506138 | E-WW-NI-30032020-OLDMELDRUM WWTW-PURCHASE 2XCOPA SAF UNITS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-09-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198852.23 | 198852.23 | 0 | 0 | 0 | 198852.23 | 0 | 0 | 0 | 0 | 198852.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512123 | E-WW-NI-30032021-ABERLOUR WWTW-REPLACE ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110.97 | 110.97 | 1453.98 | 0 | 0 | 1564.95 | 0 | 0 | 0 | 0 | 1564.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512199 | E-WW-NI-30032021-GUARDBRIDGE WWTW-INSTALL TURBIDITY PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4580.66 | 0 | 0 | 4580.66 | 0 | 0 | 0 | 0 | 4580.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512124 | E-WW-NI-30032021-INVERURIE WWTW-INSTALL SHOWER UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153.26 | 153.26 | 2008.02 | 0 | 0 | 2161.28 | 0 | 0 | 0 | 0 | 2161.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512196 | E-WW-NI-30032021-INVERURIE WWTW-INSTALL TURBIDITY & MLSS PROBES | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13741.98 | 0 | 0 | 13741.98 | 0 | 0 | 0 | 0 | 13741.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512218 | E-WW-NI-30032021-MONTROSE WWTW-REPLACE SLUDGE INLET VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-06 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2725.03 | 0 | 0 | 2725.03 | 0 | 0 | 0 | 0 | 2725.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512202 | E-WW-NI-30032021-STRATHMIGLO WWTW-INSTALL TURBIDITY PROBE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4580.66 | 0 | 0 | 4580.66 | 0 | 0 | 0 | 0 | 4580.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506506 | E-WW-NI-30042020-BLAIRGOWRIE WWTW-REPLACE MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-07 |  | 2020-06-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7377.65 | 7377.65 | 0 | 0 | 0 | 7377.65 | 0 | 0 | 0 | 0 | 7377.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507529 | E-WW-NI-30062020-CHARLESTOWN WWTW-REPLACE CORRODED COVERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-10-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4547.5 | 4547.5 | 0 | 0 | 0 | 4547.5 | 0 | 0 | 0 | 0 | 4547.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509111 | E-WW-NI-30092020-KINCARDINE WWTW-REPLACE INLET FLOW VALVE ACTUATOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-12 |  | 2020-10-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3173.62 | 3173.62 | 0 | 0 | 0 | 3173.62 | 0 | 0 | 0 | 0 | 3173.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509110 | E-WW-NI-30092020-LUMSDEN WWTW-REPLACE TELEMETRY UNIT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-12 |  | 2021-02-10 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6960.63 | 6960.63 | 0 | 0 | 0 | 6960.63 | 0 | 0 | 0 | 0 | 6960.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509014 | E-WW-NI-30092020-MONIFIETH GRANGE RD WWPS-REPLACE STORM PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-30 |  | 2020-09-12 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2573.86 | 2573.86 | 0 | 0 | 0 | 2573.86 | 0 | 0 | 0 | 0 | 2573.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509581 | E-WW-NI-30102020-INVERURIE WWTW-SUPPLY SECOND HAND STORAGE CONTAINER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2020-11-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3086.91 | 3086.91 | 0 | 0 | 0 | 3086.91 | 0 | 0 | 0 | 0 | 3086.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510042 | E-WW-NI-30112020-ABERLOUR WWTW-REFURB MOTOR & GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-30 |  | 2021-03-05 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4280 | 4280 | 0 | 0 | 0 | 4280 | 0 | 0 | 0 | 0 | 4280 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510049 | E-WW-NI-30112020-LOSSIEMOUTH SHORE ST WWPS-REPLACE PUMP NO3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2021-03-23 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1590.45 | 1590.45 | 0 | 0 | 0 | 1590.45 | 0 | 0 | 0 | 0 | 1590.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505132 | E-WW-NI-31012020-FRASERBURGH LACKIEHEAD SPS-REPLACE ULTRASONIC LEVEL METER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-12 |  | 2020-03-04 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1373.51 | 37.41 | 1410.92 | 0 | 0 | 0 | 1410.92 | 0 | 0 | 0 | 0 | 1410.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504986 | E-WW-NI-31012020-GRAHAM PLACE WWPS=REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-03-27 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 1386.08 | 0 | 1386.08 | 0 | 0 | 0 | 1386.08 | 0 | 0 | 0 | 0 | 1386.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505009 | E-WW-NI-31012020-HUNTLY WWTW-SHT REPAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 4630.64 | 0 | 4630.64 | 0 | 0 | 0 | 4630.64 | 0 | 0 | 0 | 0 | 4630.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504957 | E-WW-NI-31012020-TOMINTOUL WWTW-REPLACE ACCESS STAIRS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-23 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 1722.7 | 0 | 1722.7 | 0 | 0 | 0 | 1722.7 | 0 | 0 | 0 | 0 | 1722.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506020 | E-WW-NI-31032020-ABERFELDY WWTW-ABORTIVE AERATOR REFURB COSTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-06-03 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9225.94 | 9225.94 | 0 | 0 | 0 | 9225.94 | 0 | 0 | 0 | 0 | 9225.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506142 | E-WW-NI-31032020-NEWTYLE WWTW-REPLACE COVER ON FE CHAMBER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-06-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5285.9 | 5285.9 | 0 | 0 | 0 | 5285.9 | 0 | 0 | 0 | 0 | 5285.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512227 | E-WW-NI-31032021-BLAIR ATHOLL WWTW-SUPPLY NEW SCREEN BASKET | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3673.39 | 0 | 0 | 3673.39 | 0 | 0 | 0 | 0 | 3673.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512148 | E-WW-NI-31032021-DRUMOAK WWTW-REPLACEMENT GEARBOX | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-07-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1705.76 | 0 | 0 | 1705.76 | 0 | 0 | 0 | 0 | 1705.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512224 | E-WW-NI-31032021-KIRKCALDY WWTW-REPLACE ACTUATOR VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3722.39 | 0 | 0 | 3722.39 | 0 | 0 | 0 | 0 | 3722.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512229 | E-WW-NI-31032021-SALINE WWTW-PST DRY WELL PUMP ACCESS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-06 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4451.23 | 0 | 0 | 4451.23 | 0 | 0 | 0 | 0 | 4451.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508618 | E-WW-NI-31082020-ABERDOUR SHORE RD WWPS-REPLACE FOUL PUMPS & PANEL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-15 |  | 2021-05-01 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18031.13 | 18031.13 | 1386.05 | 0 | 0 | 19417.18 | 0 | 0 | 0 | 0 | 19417.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508613 | E-WW-NI-31082020-KIRKCALDY CREMATORIUM WWPS-REPLACEMENT PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-15 |  | 2020-11-08 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2776.61 | 2776.61 | 0 | 0 | 0 | 2776.61 | 0 | 0 | 0 | 0 | 2776.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509647 | E-WW-NI-4112020-MONIKIE ELM GROVE WWPS-REPLACE PUMP NO2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2021-02-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085.69 | 1085.69 | 0 | 0 | 0 | 1085.69 | 0 | 0 | 0 | 0 | 1085.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503797 | E-WW-NI-51119-MONTROSEWWTW-LAGOON REFURB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-10 |  | 2020-05-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 1802.7 | 633.29 | 2435.99 | 0 | 0 | 0 | 2435.99 | 0 | 0 | 0 | 0 | 2435.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504179 | E-WW-NI-51219-EAST WEMYSS MACDUFF SPS-REPLACE PUMP 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-01-25 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1288.79 | 0 | 1288.79 | 0 | 0 | 0 | 1288.79 | 0 | 0 | 0 | 0 | 1288.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504246 | E-WW-NI-61219-CRIMOND NEW HADDO WWPS-REPLACE SCREEN MOTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-09 |  | 2020-02-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 1612.69 | 0 | 1612.69 | 0 | 0 | 0 | 1612.69 | 0 | 0 | 0 | 0 | 1612.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505454 | E-WW-NI-MONTROSE TAYOCK WWPS-REPLACE 3M PIPEWORK | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-28 |  | 2020-06-17 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1826.86 | 1826.86 | 0 | 0 | 0 | 1826.86 | 0 | 0 | 0 | 0 | 1826.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505154 | E-WW-NI-SCONE MURRAYSHALL WWPS-HANDRAILING IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-14 |  | 2020-04-08 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 2788.53 | 1031.37 | 3819.9 | 0 | 0 | 0 | 3819.9 | 0 | 0 | 0 | 0 | 3819.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403175 | Existing Flooding Register Solution Development Study | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-02-05 | 2015-02-25 | 2015-04-20 | 2015-08-28 | 2014-12-11 | Scottish Water Wide | 239428.98 | 239428.98 | 19915.61 | -253489.92 | -5854.67 | 0 | 0 | 0 | -239428.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180449.74 | [5 empty] | N | FL_DD | 100%
402426 | External Flooding Carntyne Road Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2012-08-31 | 2012-08-31 | 2012-08-31 | 2012-08-31 | Glasgow City | 5859.09 | 0 | 563.01 | 0 | 0 | 0 | 0 | 0 | 563.01 | 0 | 0 | 0 | 6422.1 | 0 | 0 | 0 | 0 | 6422.1 | 0 | [5 empty] | N | CS15 | 100%
502272 | External Flooding Mitigations Policy Pilot Trials | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-11-21 | 2016-11-21 | 2017-02-27 | 2018-01-25 |  | Scottish Water Wide | 0 | 0 | 0 | 11602.65 | 17155.41 | 0 | 0 | 0 | 28758.06 | 0 | 0 | 0 | 28758.06 | 0 | 0 | 0 | 0 | 28758.06 | 209381.79 | [5 empty] | N | CM_WWI | 100%
401674 | External Flooding Register - PHASE 1 of 2 - Build and Investigations | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS7 | 2011-01-28 | 2011-12-07 | 2011-12-07 | 2015-10-30 |  | Scottish Water Wide | 1255309 | 0 | 6121 | -34.28 | 0 | 0 | 0 | 0 | 6086.72 | 0 | 0 | 0 | 1261395.72 | 0 | 0 | 0 | 0 | 1261395.72 | 306661.32 | [5 empty] | N | CM_M&G | 100%
502610 | Eyemouth (North Burn Surface Water) Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2017-03-13 | 2017-08-31 | 2017-09-15 | 2018-02-28 | 2018-03-31 | Scottish Borders | 0 | 0 | 0 | 314.02 | 27710.98 | -5003.31 | 0 | 0 | 23021.69 | 0 | 0 | 0 | 23021.69 | 0 | 0 | 0 | 0 | 23021.69 | 0 | [5 empty] | Y | EC16 | 100% | [38 empty] | 1 | [28 empty] | 0
500135 | Eyemouth DOA (DOA000070) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-05-26 | 2016-06-20 | 2019-02-20 | 2019-03-18 | Scottish Borders | 0 | 0 | 12083 | 41790 | 91336 | 58664.11 | 4760.81 | 0 | 208633.92 | 0 | 0 | 0 | 208633.92 | 0 | 0 | 0 | 0 | 208633.92 | 4617.88 | [5 empty] | N | CS16D | 28.51% | EC01G | 71.49%
46214 | Eyemouth STW Refurb - STW002274 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-15 | 2010-09-20 | 2010-10-04 | 2011-05-31 |  | Scottish Borders | 621165.62 | 0 | -1.27 | 0 | 0 | 0 | 0 | 0 | -1.27 | 0 | 0 | 0 | 621164.35 | 0 | 0 | 0 | 0 | 621164.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400617 | Facilities HS Minor Works | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-31 | 2010-03-31 | 2010-06-21 | 2016-01-01 |  | Scottish Water Wide | 793438 | 0 | -878.94 | 0 | 0 | 0 | 0 | 0 | -878.94 | 0 | 0 | 0 | 792559.06 | 0 | 0 | 0 | 0 | 792559.06 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500521 | Facilities- North Office Inverness | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-05-18 | 2016-10-21 | 2016-10-21 | 2017-08-30 |  | Highland | 0 | 0 | 76292 | 712181.39 | 354242.84 | 0 | 0 | 0 | 1142716.23 | 0 | 0 | 0 | 1142716.23 | 0 | 0 | 0 | 0 | 1142716.23 | 613322.63 | [5 empty] | N | CM_M&G | 100%
400623 | Facilities Security Measures | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-29 | 2010-03-29 | 2010-06-21 | 2015-08-21 |  | Scottish Water Wide | 397039.06 | 0 | 32225.34 | 0 | 0 | 0 | 0 | 0 | 32225.34 | 0 | 0 | 0 | 429264.4 | 0 | 0 | 0 | 0 | 429264.4 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502941 | Failing SRs Prioritisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-10-21 | 2020-10-21 | 2019-09-04 | 2019-09-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 93362.48 | 21585.48 | 511.85 | 682.75 | 116142.56 | 0 | 0 | 0 | 116142.56 | 0 | 0 | 0 | 0 | 116142.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502940 | Fair Isle WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWMD | DWQ Compliance | MS3 | 2014-01-13 | 2019-03-28 | 2019-05-27 | 2021-10-04 | 2022-12-28 | Shetland Islands | 0 | 0 | 0 | 0 | 119542.36 | 661527.35 | 1568123.65 | 2347966.73 | 4697160.08 | 622073.76 | 622073.76 | 1386401.7512 | 5319233.84 | 764327.9912 | 0 | 0 | 764327.9912 | 6083561.8312 | 4123672.09 |  |  |  |  | 23070 | Y | DW23 | 50% | DW25P | 50% | [16 empty] | 1 | [48 empty] | 0
511922 | Fairlie WWTW - Capital maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2024-03-04 | 2025-09-10 | 2025-12-09 | 2026-11-16 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | 209381.79 | [5 empty] | N | Ww3 | 100%
503377 | Fairlie WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-30 | 2028-08-08 | 2028-12-11 | 2029-06-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 74385.29 | 11181.68 | 0.03 | 85567 | 0 | 0 | 0 | 85567 | 0 | 0 | 0 | 0 | 85567 | 122419.09 | [5 empty] | N | SG1 | 100%
500240 | Fairmilehead B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | City of Edinburgh | 0 | 0 | 36243 | 37713 | 84227.13 | 0 | 0 | 0 | 158183.13 | 0 | 0 | 0 | 158183.13 | 0 | 0 | 0 | 0 | 158183.13 | 1037568.14 | [5 empty] | N | DW5 | 100%
500823 | Fairmilehead B RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2015-10-28 | 2017-12-21 | 2017-12-22 | 2019-03-01 | 2019-07-03 | City of Edinburgh | 0 | 0 | 39048 | -14111.63 | 130646.3 | 60561.4 | 21390.58 | 595 | 238129.65 | 0 | 0 | 0 | 238129.65 | 0 | 0 | 0 | 0 | 238129.65 | 1411518.74 | [5 empty] | N | DW5FS | 100%
503165 | Fairmilehead B RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-31 | 2020-03-25 | 2020-03-25 | 2020-06-10 | 2021-04-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 14465.46 | 1999.79 | -1999.79 | 14465.46 | 0 | 0 | 0 | 14465.46 | 0 | 0 | 0 | 0 | 14465.46 | 1037568.14 | [5 empty] | N | DW5FS | 100%
500241 | Fairmilehead C - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS4 | 2015-03-27 | 2018-09-28 | 2018-09-28 | 2021-01-15 | 2021-06-14 | City of Edinburgh | 0 | 0 | 38636.29 | 67025.71 | 79606 | 782355.59 | 908719.35 | 80530.13 | 1956873.07 | -25092.27 | -25092.2701 | 14756.3392 | 1931780.8 | 39848.6093 | 0 | 0 | 39848.6093 | 1971629.4093 | 2128406.55 | [5 empty] | N | DW5FS | 1.349% | DW5MR | 98.65%
500824 | Fairmilehead C RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-08-03 | 2018-03-23 | 2018-06-14 | 2019-03-01 | 2019-08-30 | City of Edinburgh | 0 | 0 | 8629.94 | 2508.99 | 70995.16 | 169784.48 | 12716.62 | -13377.61 | 251257.58 | 0 | 0 | 0 | 251257.58 | 0 | 0 | 0 | 0 | 251257.58 | 349675.99 | [5 empty] | N | DW5FS | 100%
503166 | Fairmilehead C RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-31 | 2020-03-27 | 2020-04-20 | 2020-06-10 | 2021-04-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 12610.96 | 2000 | -2000 | 12610.96 | 0 | 0 | 0 | 12610.96 | 0 | 0 | 0 | 0 | 12610.96 | 1064203.28 | [5 empty] | N | DW5FS | 100%
500818 | Falkirk Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-11-03 | 2017-03-13 | 2017-03-13 | 2016-09-12 | 2017-03-13 | Falkirk | 0 | 0 | 7066.63 | 7825.43 | 258.8 | 0 | 0 | 0 | 15150.86 | 0 | 0 | 0 | 15150.86 | 0 | 0 | 0 | 0 | 15150.86 | 106252.93 | [5 empty] | N | FL_DD | 100%
401378 | Fauldhouse STW Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-03-03 | 2012-09-26 | 2013-02-07 | 2014-03-14 |  | West Lothian | 1289380.3 | 0 | 5624.5 | 90 | 0 | 0 | 0 | 0 | 5714.5 | 0 | 0 | 0 | 1295094.8 | 0 | 0 | 0 | 0 | 1295094.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503284 | Fauldhouse WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-05-04 | 2025-02-25 | 2025-05-27 | 2026-06-30 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 81021.2 | 96.89 | 11764.92 | 92883 | 1907117.03 | 0 | 0 | 2000000.03 | 0 | 0 | 0 | 0 | 2000000.03 | 122419.09 | [5 empty] | N | SG1 | 100%
504546 | Featurenet Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS4 | 2020-03-24 | 2020-04-22 | 2020-04-07 | 2021-04-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 465043.75 | 528508.25 | 993552 | 0 | 0 | 0 | 993552 | 0 | 0 | 0 | 0 | 993552 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503225 | Ferniegair WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-03-25 | 2024-03-26 | 2024-06-20 | 2025-12-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 115199.52 | 81800.88 | 23964.6 | 220965 | 4774075.48 | 0 | 0 | 4995040.48 | 0 | 0 | 0 | 0 | 4995040.48 | 122419.09 | [5 empty] | N | SG1 | 100%
508647 | Ferniegair WwTW - Purchase of Interim SAF | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-05-12 | 2023-03-29 | 2023-09-06 | 2025-03-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400.9 | 400.9 | 0 | 0 | 0 | 400.9 | 0 | 0 | 0 | 0 | 400.9 | 122419.09 | [5 empty] | N | SG1 | 100%
500801 | Ferry Road Renfrew Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-08-13 | 2015-12-01 | 2015-12-01 | 2016-11-25 |  | Renfrewshire | 0 | 0 | 96757 | 823743.13 | 750 | 1891.91 | -5511.44 | 0 | 917630.6 | 0 | 0 | 0 | 917630.6 | 0 | 0 | 0 | 0 | 917630.6 | 209381.79 | [5 empty] | N | CM_WWI | 100%
401349 | Ferryhills WSZ Low Pressure Enhancement WSZ000609 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-09-20 | 2012-12-07 | 2014-11-21 | 2014-03-31 | Fife | 362720.13 | 0 | 1396.51 | 914.68 | 0 | 0 | 0 | 0 | 2311.19 | 0 | 0 | 0 | 365031.32 | 0 | 0 | 0 | 0 | 365031.32 | 0 | [5 empty] | N | CS1 | 100%
501083 | Fetlar WOA Fetlar WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-05-26 | 2028-02-14 | 2028-04-13 | 2029-06-22 |  | Shetland Islands | 0 | 0 | 13227.91 | 9695.09 | 0 | -274 | 430.33 | 0 | 23079.33 | 241.36 | 0 | 0 | 23320.69 | 0 | 0 | 0 | 0 | 23320.69 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46859 | Fetlar WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-07-31 | 2013-03-11 | 2015-07-06 | 2016-03-30 | Shetland Islands | 2851122.27 | 0 | 4707.48 | -3233.87 | 0 | 0 | 0 | 0 | 1473.61 | 0 | 0 | 0 | 2852595.88 | 0 | 0 | 0 | 0 | 2852595.88 | 28761.13 | [5 empty] | N | DW23 | 100%
503323 | Fetterangus WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2021-01-14 | 2021-01-14 | 2021-01-14 | 2021-02-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 39582.14 | 11886.18 | -6278.2 | 45190.12 | 0 | 0 | 0 | 45190.12 | 0 | 0 | 0 | 0 | 45190.12 | 122419.09 | [5 empty] | N | SG1 | 100%
45548 | Fettercairn STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-12-14 | 2012-02-27 | 2013-02-28 | 2013-03-29 | Aberdeenshire | 905991.77 | 0 | -66.49 | 0 | 0 | 0 | 0 | 0 | -66.49 | 0 | 0 | 0 | 905925.28 | 0 | 0 | 0 | 0 | 905925.28 | 119362.42 | [5 empty] | N | CM_WWNI | 20% | WQ01 | 80%
511344 | Field Service Transformation Project | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 | 2021-03-11 | 2021-03-31 | 2022-08-24 | 2024-04-17 | 2024-07-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2427234.79 | 2427234.79 | 15372765.21 | 0 | 0 | 17800000 | 0 | 0 | 1424000 | 1424000 | 19224000 | 613322.63 | [5 empty] | N | CM_M&G | 45% | SR21_SS | 55%
511055 | Field Services Transformation Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-03-26 | 2022-03-28 | 2022-07-27 | 2024-03-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17800000 | 0 | 0 | 17800000 | 0 | 0 | 0 | 0 | 17800000 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500922 | Fife Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2017-04-27 | 2017-04-27 | 2017-04-12 | 2017-04-27 | Fife | 0 | 0 | 5000 | 11724.57 | 161.72 | 0 | 0 | 0 | 16886.29 | 0 | 0 | 0 | 16886.29 | 0 | 0 | 0 | 0 | 16886.29 | 106252.93 | [5 empty] | N | FL_DD | 100%
510090 | Fife Reservoirs - Vegetation Clearance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-12-17 | 2021-06-21 | 2022-02-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13490.42 | 13490.42 | 4908.4 | 0 | 0 | 18398.82 | 0 | 0 | 0 | 0 | 18398.82 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511640 | Fife Reservoirs Mole Control | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS2 |  | 2021-03-18 | 2021-06-23 | 2022-02-03 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523.36 | 523.36 | 8000.01 | 0 | 0 | 8523.37 | 0 | 0 | 0 | 0 | 8523.37 | 0 | [5 empty] | N | SR21_WA | 100%
501097 | Fife Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-08-31 | 2016-08-31 | 2018-10-31 | 2019-03-31 | Fife | 0 | 0 | 4329 | 24171.43 | 6214.46 | 4784.92 | -2444.62 | 0 | 37055.19 | 0 | 0 | 0 | 37055.19 | 0 | 0 | 0 | 0 | 37055.19 | 0 | [5 empty] | Y | EC10D | 100% | [40 empty] | 1 | [26 empty] | 0
508408 | Final Sample Tap Replacement (All Regions) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-07 |  | 2020-10-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15774.25 | 15774.25 | 9225.75 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504498 | Final Turbidity Meter Tobermory WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 334.65 | 0 | 334.65 | 4780.74 | 0 | 0 | 5115.39 | 0 | 0 | 0 | 0 | 5115.39 | 119022.58 | [5 empty] | N | WSNI | 100%
500074 | Final Water Sampling Programme Extension | Q&S4 | Climate Change | Climate Change |  |  | Water | SEPA | SWD | Climate Change | MS7 | 2015-03-09 | 2015-06-30 | 2015-06-30 | 2016-09-01 | 2016-06-20 | Scottish Water Wide | 671 | 671 | 19409 | 89284.35 | 0 | 0 | 0 | 0 | 108693.35 | 0 | 0 | 0 | 109364.35 | 0 | 0 | 0 | 0 | 109364.35 | 243025.97 | [5 empty] | N | CC4W | 100%
500955 | Finance Systems Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-09-14 | 2017-03-30 | 2017-03-30 | 2018-09-14 |  | Scottish Water Wide | 0 | 0 | 304983 | 2895477.97 | 3969557.82 | 352790.78 | -2728.23 | 0 | 7520081.34 | 0 | 0 | 0 | 7520081.34 | 0 | 0 | 0 | 0 | 7520081.34 | 306661.32 | [5 empty] | N | CM_M&G | 100%
500631 | Financial Control SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 273864.48 | 462835.17 | 534409.54 | 538377.44 | 571844.29 | 586756.58 | 2968087.5 | 0 | 0 | 0 | 2968087.5 | 0 | 0 | 0 | 0 | 2968087.5 | 306661.32 | [5 empty] | N | CM_OVH | 100%
505144 | Finlay Rise - repair of burst rising main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-02-12 |  | 2020-07-09 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 42043.06 | 49006.73 | 91049.79 | 0 | 0 | 0 | 91049.79 | 0 | 0 | 0 | 0 | 91049.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500688 | Finnieston Tunnel | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-06-11 | 2015-11-04 | 2015-11-27 | 2016-09-01 |  | Glasgow City | 0 | 0 | 135984 | 136053 | 155 | 32430.47 | 350.93 | 0 | 304973.4 | 0 | 0 | 0 | 304973.4 | 0 | 0 | 0 | 0 | 304973.4 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502926 | Finnieston Tunnel - Structural Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-06-29 | 2018-08-07 | 2018-08-10 | 2022-03-15 |  | Glasgow City | 0 | 0 | 0 | 0 | 6027.91 | 311004.43 | 115255.28 | 30473.28 | 462760.9 | 39113.96 | 0 | 0 | 501874.86 | 0 | 0 | 0 | 0 | 501874.86 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503929 | Finnieston Tunnel sewer relining DALMUIR DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-11-29 |  | 2021-05-22 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 1808.41 | -165.86 | 1642.55 | 98357.45 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503574 | FIRE SAFETY FOLLOW ON WORK | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2019-09-10 | 2019-09-10 | 2019-09-10 | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 79464.59 | 220535.41 | 300000 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 209381.79 | [5 empty] | N | CM_M&G | 100%
36019 | Fire Safety Remedial Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWMD | Wastewater non infrastructure | MS7 | 2007-06-13 | 2007-06-13 | 2009-05-25 | 2017-03-28 |  | Scottish Water Wide | 962430 | 0 | -121.11 | 0 | 0 | 0 | 0 | 0 | -121.11 | 0 | 0 | 0 | 962308.89 | 0 | 0 | 0 | 0 | 962308.89 | 209623.87 | [5 empty] | N | WSNI | 50% | WWNI | 50%
50028 | First Time Provision | IR18 | Supporting economic development | First Time Provision |  |  | General |  | SWD | First Time Provision | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084027.07 | [5 empty] | N | WG3 | 100%
503670 | First Time Provision - Ayr Bathing Waters improvement study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2019-08-23 | 2020-05-06 | 2019-11-21 | 2020-03-24 | 2020-09-10 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 109386.27 | 10622.89 | 120009.16 | 0 | 0 | 0 | 120009.16 | 0 | 0 | 0 | 0 | 120009.16 | 0 | [5 empty] | N | EC16 | 100%
503669 | First Time Provision - Dhoon Bay Bathing Water improvement study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2019-08-23 | 2020-05-06 | 2019-11-21 | 2020-03-24 | 2020-08-11 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 36918 | 3480.98 | 40398.98 | 0 | 0 | 0 | 40398.98 | 0 | 0 | 0 | 0 | 40398.98 | 0 | [5 empty] | N | EC16 | 100%
402956 | Fisher Avenue Kilsyth Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-28 | 2015-08-25 | 2015-08-31 | 2015-09-14 | 2015-09-14 | East Dunbartonshire | 183243.64 | 183243.64 | -183243.64 | -782.71 | 80.86 | 0 | 0.34 | 0 | -183945.15 | 0 | 0 | 0 | -701.51 | 0 | 0 | 0 | 0 | -701.51 | 180449.74 | [5 empty] | N | FL_DD | 50% | FL_NAMED | 50%
400764 | Fixed Life Asset - System Meters DI Meter Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2011-04-29 | 2015-10-02 |  | Scottish Water Wide | 1980000 | 0 | 5564.1 | 0 | 0 | 0 | 0 | 0 | 5564.1 | 0 | 0 | 0 | 1985564.1 | 0 | 0 | 0 | 0 | 1985564.1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402214 | Fixed Life Asset - System Meters TM and SR Meter Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-08-02 | 2011-08-02 | 2011-08-01 | 2015-07-02 |  | Scottish Water Wide | 914154 | 0 | -880.78 | 3720.12 | 0 | 0 | 0 | 0 | 2839.34 | 0 | 0 | 0 | 916993.34 | 0 | 0 | 0 | 0 | 916993.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500959 | Fixed Wire Testing - Pilot Scheme | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS7 | 2015-09-17 | 2016-03-15 | 2016-03-15 | 2017-04-03 |  | Scottish Water Wide | 0 | 0 | 521826.19 | 1971873.09 | -290.21 | 0 | 0 | 0 | 2493409.07 | 0 | 0 | 0 | 2493409.07 | 0 | 0 | 0 | 0 | 2493409.07 | 328404.37 | [5 empty] | N | CM_M&G | 100%
502440 | Fixed Wire Testing - Wastewater East | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 447850.38 | 1432334.56 | 1294290.06 | 1491543.97 | 1024200.03 | 5690219 | 0 | 0 | 0 | 5690219 | 0 | 0 | 0 | 0 | 5690219 | 209381.79 | [5 empty] | N | CM_M&G | 100%
502442 | Fixed Wire Testing - Wastewater North | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 278955.53 | 660222.47 | 1458950 | 932267.94 | 370067.06 | 3700463 | 0 | 0 | 0 | 3700463 | 0 | 0 | 0 | 0 | 3700463 | 209381.79 | [5 empty] | N | CM_M&G | 100%
502436 | Fixed Wire Testing - Wastewater South | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 390610.3 | 1246277.51 | 611041.19 | 975142 | 960478 | 4183549 | 0 | 0 | 0 | 4183549 | 0 | 0 | 0 | 0 | 4183549 | 209381.79 | [5 empty] | N | CM_M&G | 100%
502438 | Fixed Wire Testing - Wastewater West | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 465388.44 | 481743.4 | 693211.16 | 740158 | 546332 | 2926833 | 0 | 0 | 0 | 2926833 | 0 | 0 | 0 | 0 | 2926833 | 209381.79 | [5 empty] | N | CM_M&G | 100%
502441 | Fixed Wire Testing - Water East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 354165.6 | 583928.4 | 540293 | 1636702.87 | 1068782.13 | 4183872 | 0 | 0 | 0 | 4183872 | 0 | 0 | 0 | 0 | 4183872 | 119022.58 | [5 empty] | N | CM_M&G | 100%
502435 | Fixed Wire Testing - Water North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 300991.69 | 1313771.87 | 674439.44 | 1025879 | 922745 | 4237827 | 0 | 0 | 0 | 4237827 | 0 | 0 | 0 | 0 | 4237827 | 119022.58 | [5 empty] | N | CM_M&G | 100%
502437 | Fixed Wire Testing - Water South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 390780.16 | 207725.84 | 326381 | 581253 | 468872 | 1975012 | 0 | 0 | 0 | 1975012 | 0 | 0 | 0 | 0 | 1975012 | 119022.58 | [5 empty] | N | CM_M&G | 100%
502439 | Fixed Wire Testing - Water West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 |  | All North Unitary Authorities | 0 | 0 | 0 | 468265.76 | 531870.24 | 472456.61 | 786171.12 | 655529.27 | 2914293 | 0 | 0 | 0 | 2914293 | 0 | 0 | 0 | 0 | 2914293 | 119022.58 | [5 empty] | N | CM_M&G | 100%
501552 | Fixed Wire Testing Holding Line - SWD | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2021-04-15 | 2021-05-01 |  | 2021-03-29 |  | Scottish Water Wide | 0 | 0 | 130841.12 | -130841.05 | 0 | 0 | 0 | 0 | 0.07 | 0 | 0 | 0 | 0.07 | 0 | 0 | 0 | 0 | 0.07 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502934 | Flemington Road Glenrothes Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2019-01-21 | 2020-06-29 | 2021-01-18 | 2021-09-01 |  | Fife | 0 | 0 | 0 | 0 | 16215.4 | 18762.43 | 185558.01 | 620401.16 | 840937 | 289955.67 | 0 | 0 | 1130892.67 | 0 | 0 | 24673.33 | 24673.33 | 1155566 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500432 | Flood Management Action Plan - FMAP | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-11 | 2016-09-19 | 2016-09-19 | Scottish Water Wide | 0 | 0 | 1021661 | 95378.34 | 2105.92 | 0 | 0 | 0 | 1119145.26 | 0 | 0 | 0 | 1119145.26 | 0 | 0 | 0 | 0 | 1119145.26 | 1470767.03 | [5 empty] | N | SG5 | 100%
503481 | Flood Risk Alleviation - Larchwood Road - Galashiels Selkirk Supply DMA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-12-15 | 2022-08-23 | 2022-10-31 | 2023-03-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 549.3 | 696.71 | 1246.01 | 201685.7 | 0 | 0 | 202931.71 | 0 | 0 | 0 | 0 | 202931.71 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS7 | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-07-22 | 2020-09-22 | Scottish Water Wide | 0 | 0 | 314167 | 270363.44 | 649727.46 | 1157101.2 | 931022.51 | 25141.29 | 3347522.9 | 0 | 0 | 0 | 3347522.9 | 0 | 0 | 0 | 0 | 3347522.9 | 7517904.3 | [5 empty] | N | CS16D | 100%
402021 | Flood Risk Mitigation at Balmoor RWI - PS Forehill WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-03-18 | 2012-07-06 | 2012-08-27 | 2013-03-28 | 2013-03-29 | Aberdeenshire | 33020 | 0 | -991.96 | 0 | 0 | 0 | 0 | 0 | -991.96 | 0 | 0 | 0 | 32028.04 | 0 | 0 | 0 | 0 | 32028.04 | 0 | [5 empty] | N | CS16W | 100%
46907 | Flood risk mitigation at Innerleithen WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MSU |  | 2014-06-27 | 2014-10-23 | 2015-04-25 | 2015-07-24 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20681 | N | CS16W | 100%
401684 | Flood risk mitigation at Kirbister WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-02-01 | 2014-07-24 | 2014-08-18 | 2015-03-19 | 2015-03-27 | Orkney Islands | 1243064 | 0 | 458533.6 | 10005.11 | -4595.23 | 0 | 0 | 0 | 463943.48 | 0 | 0 | 0 | 1707007.48 | 0 | 0 | 0 | 0 | 1707007.48 | 0 | [5 empty] | N | CS16W | 100%
401683 | Flood Risk Mitigation at River Tay Raw Water PS Perth | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-02-03 | 2013-10-17 | 2013-11-11 | 2014-03-07 | 2014-03-24 | Perth and Kinross | 368016 | 0 | -589.55 | -2645.27 | 0 | 0 | 0 | 0 | -3234.82 | 0 | 0 | 0 | 364781.18 | 0 | 0 | 0 | 0 | 364781.18 | 0 | [5 empty] | N | CS16W | 100%
402020 | Flood Risk Mitigation at Ross Priory RWPS | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-03-16 | 2012-12-19 | 2013-02-04 | 2014-03-13 | 2014-03-31 | West Dunbartonshire | 756766.86 | 0 | 12358.9 | 5811.77 | 0 | 0 | 0 | 0 | 18170.67 | 0 | 0 | 0 | 774937.53 | 0 | 0 | 0 | 0 | 774937.53 | 0 | [5 empty] | N | CS16W | 100%
502647 | Flooding Programme Support | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-05-31 | 2022-04-29 | 2022-07-20 | 2023-02-20 | 2023-05-23 | Scottish Water Wide | 0 | 0 | 0 | 10171.6 | 634301.92 | 190526.48 | 25239.48 | 74983.17 | 935222.64 | 264777.36 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 175086.76 | [5 empty] | N | FL_DD | 100%
501003 | Flow Return and Top End Compliance Utility | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-09-25 | 2016-02-29 | 2016-02-29 | 2019-05-13 |  | Scottish Water Wide | 0 | 0 | 32769.87 | 55709.13 | 12690 | 37597 | -2865.12 | 0 | 135900.88 | 0 | 0 | 0 | 135900.88 | 0 | 0 | 0 | 0 | 135900.88 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
500773 | Flures Avenue (Garnieland) Erskine Partial Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-24 | 2017-06-27 | 2017-07-31 | 2017-12-19 |  | Glasgow City | 0 | 0 | 27000 | 35014.12 | 464774.93 | 1482.07 | -1354.45 | -15992.31 | 510924.35 | 0 | 0 | 0 | 510924.35 | 0 | 0 | 0 | 0 | 510924.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502320 | FMAP - Flooding Management Action Plan - Year 2 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2016-08-23 | 2016-08-23 | 2016-10-26 | 2017-09-25 | 2017-09-25 | Scottish Water Wide | 0 | 0 | 0 | 1020877.33 | 195948.15 | -74690.4 | 0 | 0 | 1142135.08 | 0 | 0 | 0 | 1142135.08 | 0 | 0 | 0 | 0 | 1142135.08 | 1470767.03 | [5 empty] | N | SG5 | 100%
502716 | FMAP - Flooding Management Action Plan - Year 3 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2017-05-04 | 2017-05-04 | 2017-06-01 | 2018-10-01 | 2018-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 831214.95 | 424000 | -28841.11 | 0 | 1226373.84 | 0 | 0 | 0 | 1226373.84 | 0 | 0 | 0 | 0 | 1226373.84 | 1470767.03 | [5 empty] | N | SG5 | 100%
503559 | FMAP - Flooding Management Action Plan - Year 5 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS4 | 2019-03-26 | 2019-03-26 | 2019-06-03 | 2021-03-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 128017.64 | 1028017.64 | 0 | 0 | 0 | 1028017.64 | 0 | 0 | 0 | 0 | 1028017.64 | 1470767.03 | [5 empty] | N | SG5 | 100%
505610 | FMAP - Flooding Management Action Plan - Year 6 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2020-03-23 | 2020-03-31 | 2020-08-03 | 2021-09-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 821479 | 821479 | 178520.92 | 0 | 0 | 999999.92 | 0 | 0 | 0 | 0 | 999999.92 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503131 | FMAP - Flooding Management Action Plan - Yr 4 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2018-08-31 | 2018-08-31 | 2018-09-17 | 2019-07-15 | 2019-07-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 657266.95 | -11050.78 | -1867.16 | 644349.01 | 0 | 0 | 0 | 644349.01 | 0 | 0 | 0 | 0 | 644349.01 | 1470767.03 | [5 empty] | N | SG5 | 100%
501295 | FMAP Holding Line - SR15 Yr2-6 -Wastewater | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2021-04-15 | 2021-05-01 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 80.87 | 0 | 0 | -80.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG5 | 100%
500127 | Fochabers DOA (DOA000198) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-03-28 | 2018-03-29 | Moray | 0 | 0 | 8629 | 13732.56 | 37136.07 | 5231.94 | 0 | 0 | 64729.57 | 0 | 0 | 0 | 64729.57 | 0 | 0 | 0 | 0 | 64729.57 | 39668.02 | [5 empty] | N | EC01G | 3.399% | EC01D | 38.39% | CS16D | 58.21%
500938 | Fochabers Main SPS Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-09-02 | 2018-01-31 | 2018-03-12 | 2019-03-22 |  | Moray | 0 | 0 | 8755 | 97090 | 274388 | 913105 | 24536 | 0 | 1317874 | 0 | 0 | 0 | 1317874 | 0 | 0 | 0 | 0 | 1317874 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503216 | Fochabers WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2020-12-18 | 2023-01-03 | 2023-03-29 | 2024-05-24 |  | Moray | 0 | 0 | 0 | 0 | 0 | 65856.09 | 26606.5 | 71981.41 | 164444 | 2131297.93 | 0 | 0 | 2295741.93 | 0 | 0 | 0 | 0 | 2295741.93 | 122419.09 | [5 empty] | N | SG1 | 100%
500968 | FOCHABERS WWTW 1966 NJ341599 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS6 | 2015-10-05 | 2018-01-31 | 2018-02-26 | 2020-02-13 |  | Moray | 0 | 0 | 31252 | 205759.18 | 462381.3 | 1276842.4 | 437820.12 | -60049.56 | 2354005.44 | -15447.44 | 0 | 0 | 2338558 | 0 | 0 | 0 | 0 | 2338558 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500909 | Fochabers WwTW Discharge Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WINF | Wastewater non infrastructure | MS0 | 2015-09-02 | 2021-11-01 | 2022-01-10 | 2022-06-02 |  | Moray | 0 | 0 | 10688 | 109660 | 9722 | 0 | -6468.88 | 0.01 | 123601.13 | 93127.87 | 0 | 0 | 216729 | 0 | 0 | 0 | 0 | 216729 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502758 | Foodieash ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-02-02 | 2024-10-25 | 2025-01-20 | 2025-10-21 |  | Fife | 0 | 0 | 0 | 0 | 31143.1 | 1716.52 | 2461.71 | 29906.33 | 65227.66 | 535869.08 | 0 | 0 | 601096.74 | 0 | 0 | 0 | 0 | 601096.74 | 122419.09 | [5 empty] | N | SG1 | 100%
403486 | Foodieash ST - Growth - 4034860000 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-06-17 | 2016-12-14 | 2016-12-14 | 2016-12-15 | 2016-12-15 | Fife | 46190 | 0 | 8043 | -1340.27 | 121.29 | 0 | 0 | 0 | 6824.02 | 0 | 0 | 0 | 53014.02 | 0 | 0 | 0 | 0 | 53014.02 | 0 | [5 empty] | N | SG1 | 100%
503488 | FOP Funded Pressure Transient Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-03-05 | 2019-03-05 | 2020-03-23 | 2021-06-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 217451.72 | 146687.37 | 146234.91 | 510374 | 51625.75 | 0 | 0 | 561999.75 | 0 | 0 | 0 | 0 | 561999.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504527 | Fordyce WWTW Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-01-30 |  | 2021-09-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 36000 | 38000 | 24323 | 0 | 0 | 62323 | 0 | 0 | 0 | 0 | 62323 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501268 | Fordyce WwTW Final Effluent Discharge Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WINF | Wastewater non infrastructure | MS0 | 2016-02-12 | 2021-11-08 | 2022-01-17 | 2022-05-11 |  | Aberdeenshire | 0 | 0 | 541.27 | 36618.73 | -8056.16 | 17000 | -4049.4 | 0 | 42054.44 | 32945.56 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 75000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511468 | Forehill Raw Water Reservoir Vegetation Clearance | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS2 |  | 2021-03-04 | 2021-06-23 | 2022-02-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.31 | 981.31 | 15000.03 | 0 | 0 | 15981.34 | 0 | 0 | 0 | 0 | 15981.34 | 0 | [5 empty] | N | SR21_WA | 100%
504465 | Forehill WTW - Ferric Storage and delivery area | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-12-18 | 2022-08-12 | 2022-11-11 | 2024-01-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66647 | 66647 | 585184.83 | 0 | 0 | 651831.83 | 0 | 0 | 0 | 0 | 651831.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502360 | Forehill WTW CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-05-14 | 2028-12-28 | 2029-05-02 | 2030-07-23 |  | Aberdeenshire | 0 | 0 | 0 | 44037.75 | 8138.56 | 6234.58 | 4422.83 | 0 | 62833.71 | 33166.29 | 0 | 0 | 96000 | 0 | 0 | 0 | 0 | 96000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500728 | Forest Road WWPS 1994 NJ786165 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-07-07 | 2016-02-19 | 2016-05-31 | 2017-02-07 |  | Aberdeenshire | 0 | 0 | 38679.43 | 103300.57 | 12987 | -7239.14 | 0 | 0 | 147727.86 | 0 | 0 | 0 | 147727.86 | 0 | 0 | 0 | 0 | 147727.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403969 | Forestmill ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS7 | 2016-08-19 | 2019-12-23 | 2020-10-05 | 2020-11-25 |  | Clackmannanshire | 967.25 | 0 | 26789.19 | 16366.37 | 40698.19 | 96175 | 2392.02 | -6992.67 | 175428.1 | 0 | 0 | 0 | 176395.35 | 0 | 0 | 0 | 0 | 176395.35 | 0 | [5 empty] | N | SG1 | 100%
30282 | Forfar New STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2012-03-27 | 2012-10-15 | 2013-09-30 | 2013-10-16 | Angus | 1817236.61 | 0 | -1399.68 | 0 | 0 | 0 | 0 | 0 | -1399.68 | 0 | 0 | 0 | 1815836.93 | 0 | 0 | 0 | 0 | 1815836.93 | 119362.42 | [5 empty] | N | CM_WWNI | 45% | EC04A | 55%
506622 | Forfar WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-07-10 | 2025-05-01 | 2025-07-31 | 2026-09-03 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98217 | 98217 | 1901782.68 | 0 | 0 | 1999999.68 | 0 | 0 | 0 | 0 | 1999999.68 | 122419.09 | [5 empty] | N | SG1 | 100%
404115 | Former Ballerup High School East Kilbride Off Site Storage Solution | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-06-01 | 2020-02-28 | 2020-02-28 | 2019-09-19 |  | South Lanarkshire | 0 | 0 | 64458.99 | 0 | 0 | 0 | 61.99 | 0 | 64520.98 | 0 | 0 | 0 | 64520.98 | 0 | 0 | 0 | 0 | 64520.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500129 | Forres DOA (DOA000188) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2019-09-30 | 2020-01-07 | Moray | 0 | 0 | 24530.29 | 37738.71 | 25403 | 101905 | 77873 | 10062.31 | 277512.31 | 0 | 0 | 0 | 277512.31 | 0 | 0 | 0 | 0 | 277512.31 | 325378.39 | [5 empty] | N | EC01G | 3.18% | EC01D | 20.41% | CS16D | 76.41%
502811 | Forres WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-04-16 | 2028-07-27 | 2028-11-17 | 2029-11-07 |  | Moray | 0 | 0 | 0 | 0 | 64690.06 | 7241.07 | 2141.44 | 2378.82 | 76451.39 | -1451.39 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 75000 | 122419.09 | [5 empty] | N | SG1 | 100%
500580 | Forres WWTW 1973 NJ038595 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-06-02 | 2019-10-03 | 2019-11-05 | 2022-04-01 |  | Moray | 0 | 0 | 554787 | -170134.47 | 202978.36 | 574817.42 | 841409.69 | 1318021.2 | 3321879.2 | 2902117.8 | 0 | 0 | 6223997 | 0 | 0 | 1776003 | 1776003 | 8000000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502251 | Forres WwTW Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2018-05-30 | 2020-05-27 | 2020-06-22 | 2021-03-23 |  | Moray | 0 | 0 | 0 | 8334.97 | 3419.24 | 890.38 | 8548.97 | 33696.49 | 54890.05 | 284.02 | 0 | 0 | 55174.07 | 0 | 0 | 0 | 0 | 55174.07 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45577 | Fort Augustus New WTW Upgrade Disinfection Control DW13 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-07-25 | 2012-03-26 | 2012-04-16 | Highland | 54368.07 | 0 | 156.3 | 0 | 0 | 0 | 0 | 0 | 156.3 | 0 | 0 | 0 | 54524.37 | 0 | 0 | 0 | 0 | 54524.37 | 28761.13 | [5 empty] | N | DW13 | 100%
500825 | Fort Augustus RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-03-31 | 2017-11-30 | Highland | 0 | 0 | 7753 | 16822.39 | 6578.93 | 2798.68 | -1588.1 | 0 | 32364.9 | 0 | 0 | 0 | 32364.9 | 0 | 0 | 0 | 0 | 32364.9 | 35596.83 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 10.72 | [43 empty] | 0
502878 | Fort Augustus WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-26 | 2019-04-26 | Highland | 0 | 0 | 0 | 0 | 21360.69 | 1536.1 | -20947.96 | 0 | 1948.83 | 0 | 0 | 0 | 1948.83 | 0 | 0 | 0 | 0 | 1948.83 | 122419.09 | [5 empty] | N | WG1 | 100%
505106 | Fort Augustus WwTW - Inlet Screen Access | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-09-17 | 2021-10-29 | 2022-03-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17911 | 17911 | 19588.96 | 0 | 0 | 37499.96 | 0 | 0 | 0 | 0 | 37499.96 | 209381.79 | [5 empty] | N | CM_M&G | 100%
505116 | Fort Augustus WwTW - Scum Removal System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-06-09 | 2022-11-04 | 2023-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6988 | 6988 | 128012 | 0 | 0 | 135000 | 0 | 0 | 0 | 0 | 135000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
45796 | Fort Hill SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-03-21 | 2011-08-23 | 2012-03-22 | 2012-03-29 | Scottish Borders | 416246.08 | 0 | 266.75 | 0 | 0 | 0 | 0 | 0 | 266.75 | 0 | 0 | 0 | 416512.83 | 0 | 0 | 0 | 0 | 416512.83 | 119362.42 | [5 empty] | N | CM_WWNI | 10.06% | WQ01C | 89.94%
503388 | Forteviot ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-06-10 | 2028-10-27 | 2029-03-01 | 2030-04-08 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 70898.48 | 5567.17 | 0.35 | 76466 | 5534.35 | 0 | 0 | 82000.35 | 0 | 0 | 0 | 0 | 82000.35 | 122419.09 | [5 empty] | N | SG1 | 100%
508594 | Forth Area Reservoirs - Fencing Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 |  | 2020-09-14 | 2020-11-02 | 2021-04-19 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36871.62 | 36871.62 | 3128.38 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500004 | Forth Area Submarine PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-05-06 | 2017-05-31 | 2017-09-07 | 2018-08-27 |  | Scottish Water Wide | 0 | 0 | 129500 | 265188 | 1266094 | 639603 | 9563.55 | -38690.25 | 2271258.3 | 0 | 0 | 0 | 2271258.3 | 0 | 0 | 0 | 0 | 2271258.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400120 | Forth Cluster 1 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-24 | 2012-10-22 | 2014-06-16 |  | Clackmannanshire | 646814 | 0 | 427 | -132.04 | 0 | 0 | 0 | 0 | 294.96 | 0 | 0 | 0 | 647108.96 | 0 | 0 | 0 | 0 | 647108.96 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400121 | Forth Cluster 2 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-28 | 2012-10-22 | 2014-06-25 |  | East Dunbartonshire | 808054 | 0 | 1465.32 | 0 | 311.93 | 0 | 0 | 0 | 1777.25 | 0 | 0 | 0 | 809831.25 | 0 | 0 | 0 | 0 | 809831.25 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501282 | Forth Estuary Sewage Related Debris Study | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-12-01 | 2017-03-28 | 2017-05-22 | 2018-06-20 | 2018-06-20 | All East Unitary Authorities | 0 | 0 | 3722.95 | 142768.05 | 419241.86 | 53653.2 | 86.12 | 0 | 619472.18 | 0 | 0 | 0 | 619472.18 | 0 | 0 | 0 | 0 | 619472.18 | 4617.88 | [5 empty] | N | EC01G | 100%
401501 | Forth Leakage Region New and Replacement Leakage Assets | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-20 | 2011-12-20 | 2012-01-30 | 2015-03-10 |  | All West Unitary Authorities | 2336312 | 0 | 161930 | 37790.51 | 10986.62 | 0 | 0 | 0 | 210707.13 | 0 | 0 | 0 | 2547019.13 | 0 | 0 | 0 | 0 | 2547019.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403571 | Forth WwTW - Capital Maintenance Interventions CMC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-08-05 | 2013-08-05 | 2013-08-05 | 2017-02-16 |  | North Lanarkshire | 694483 | 0 | 227890 | 9808.41 | 1351.53 | 0 | 0 | 0 | 239049.94 | 0 | 0 | 0 | 933532.94 | 0 | 0 | 0 | 0 | 933532.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500139 | Fortrose DOA (DOA000907) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-12-19 | 2017-01-11 | 2019-02-28 | 2019-06-30 | Highland | 0 | 0 | 11621 | 15843 | 14703 | 43795 | -4338.45 | 0 | 81623.55 | 0 | 0 | 0 | 81623.55 | 0 | 0 | 0 | 0 | 81623.55 | 4617.88 | [5 empty] | Y | EC01G | 100% | [40 empty] | 1 | [26 empty] | 0
300029 | Fortrose WwTW - Completion Project (CID) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-11-16 | 2012-03-20 | 2012-06-06 | 2013-11-27 | 2013-09-30 | Highland | 2894000 | 0 | -2876.39 | 0 | 0 | 0 | 0 | 0 | -2876.39 | 0 | 0 | 0 | 2891123.61 | 0 | 0 | 0 | 0 | 2891123.61 | 28761.13 | [5 empty] | N | EC01 | 100%
504462 | Fortrose WwTW - Sea Outfall Protection | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2020-08-12 | 2021-11-08 | 2022-03-09 | 2022-09-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18662 | 18662 | 33838.14 | 0 | 0 | 52500.14 | 0 | 0 | 0 | 0 | 52500.14 | 209381.79 | [5 empty] | N | WWI | 100%
507265 | Forveran ST | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38852.57 | 38852.57 | -2385.68 | 0 | 0 | 36466.89 | 0 | 0 | 0 | 0 | 36466.89 | 122419.09 | [5 empty] | N | SG1 | 100%
501740 | Fossil Grove Kirkintilloch - Repair sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2020-07-03 | 2021-11-08 | 2022-01-10 | 2022-05-24 |  | East Dunbartonshire | 0 | 0 | 0 | 3348.84 | 9389.18 | 1967.45 | 9.24 | 25624.3 | 40339 | 383845.52 | 0 | 0 | 424184.52 | 0 | 0 | 0 | 0 | 424184.52 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501229 | Foula WTW (Reduction of risks identified in Drinking Water Safety Plan - Distribution) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-11-17 | 2015-11-17 | 2015-12-16 | 2015-12-31 | 2016-03-31 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | DW25D | 100% | [22 empty] | 1 | [44 empty] | 0
46857 | Foula WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-07-31 | 2013-06-28 | 2015-11-24 | 2015-12-22 | Shetland Islands | 3757923.44 | 0 | 20964.08 | -11369.61 | -782 | 0 | 0 | 0 | 8812.47 | 0 | 0 | 0 | 3766735.91 | 0 | 0 | 0 | 0 | 3766735.91 | 339997.92 | [5 empty] | N | CM_WSI | 30.28% | DW23 | 69.72%
403687 | Frandy Cottages PWS Improvements | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2014-03-18 | 2014-11-20 | 2014-11-20 | 2015-04-07 | 2015-05-28 | Perth and Kinross | 99049.85 | 0 | 787.97 | 0 | 0 | 0 | 0 | 0 | 787.97 | 0 | 0 | 0 | 99837.82 | 0 | 0 | 0 | 0 | 99837.82 | 0 | [5 empty] | N | DW10 | 100%
500978 | Fraser Street Inverness Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-06-24 | 2017-03-30 | 2017-09-18 | 2017-11-24 |  | Highland | 0 | 0 | 0 | 25442.08 | 117519.5 | 1282.86 | 1348.77 | 345.24 | 145938.45 | 0 | 0 | 0 | 145938.45 | 0 | 0 | 0 | 0 | 145938.45 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500141 | Fraserburgh Phingask DOA (DOA000360) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-20 | 2016-03-23 | 2018-03-28 | 2019-02-05 | Aberdeenshire | 0 | 0 | 82416 | 129492 | 80151 | 23194.48 | 0 | 0 | 315253.48 | 0 | 0 | 0 | 315253.48 | 0 | 0 | 0 | 0 | 315253.48 | 4617.88 | [5 empty] | N | EC01G | 19.97% | CS16D | 80.03%
403253 | Freuchie WwTW Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-11 | 2014-01-07 | 2014-05-19 | 2014-11-07 |  | Fife | 216779 | 0 | 0 | -242.01 | 0 | 0 | 0 | 0 | -242.01 | 0 | 0 | 0 | 216536.99 | 0 | 0 | 0 | 0 | 216536.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500788 | Friockheim Old & New WwTWs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-08-31 | 2027-07-07 | 2027-08-19 | 2028-06-30 |  | Angus | 0 | 0 | 40099 | 152180.95 | 12029.5 | -5772.9 | 0 | -8025.61 | 190510.94 | 1558005.54 | 0 | 0 | 1748516.48 | 0 | 0 | 0 | 0 | 1748516.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502615 | Friockheim Overland Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-04 |  | Angus | 0 | 0 | 0 | 2359.94 | 5926.05 | 0 | 0 | 0 | 8285.99 | 0 | 0 | 0 | 8285.99 | 0 | 0 | 0 | 0 | 8285.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501280 | Friockheim WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-07-27 | 2016-07-27 | Angus | 0 | 0 | 9054.59 | 747.63 | 0 | 0 | 0 | 0 | 9802.22 | 0 | 0 | 0 | 9802.22 | 0 | 0 | 0 | 0 | 9802.22 | 122419.09 | [5 empty] | N | SG1 | 100%
500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water | DWQR | SWMD | Flood Risk Management Act | MS4 | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2021-04-01 | 2021-10-21 | Scottish Water Wide | 0 | 0 | 195637 | 533343.97 | 670435.94 | 747653.69 | 242584.97 | 139573.43 | 2529229 | 40000.1 | 40000.1 | 126144.1275 | 2569229.1 | 86144.0275 | 0 | 0 | 86144.0275 | 2655373.1275 | 980126.37 | [5 empty] | N | WR6 | 100%
501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-23 | 2018-09-03 | Scottish Water Wide | 0 | 0 | 73764 | 126964.27 | 22205.77 | -15707.88 | 0 | 0 | 207226.16 | 0 | 0 | 0 | 207226.16 | 0 | 0 | 0 | 0 | 207226.16 | 0 | [5 empty] | N | CS16D | 100%
502534 | FRMA Section 33-34 -Optioneering - Aberdeen catchment | IR18 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-28 | 2017-02-28 | 2017-04-21 | 2018-02-26 | 2018-02-26 | Aberdeen City | 0 | 0 | 0 | 144000 | 123789.84 | 85023.16 | 11092.02 | 0 | 363905.02 | 0 | 0 | 0 | 363905.02 | 0 | 0 | 0 | 0 | 363905.02 | 4339404.28 | [5 empty] | N | FL_DD | 45.04% | EC10B | 54.96%
502535 | FRMA Section 33-34 -Optioneering - Ayrshire catchment | IR18 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-21 | 2017-09-15 | 2017-09-15 | North Ayrshire | 0 | 0 | 0 | 7365.72 | 29472.3 | 579.37 | 0 | 0 | 37417.39 | 0 | 0 | 0 | 37417.39 | 0 | 0 | 0 | 0 | 37417.39 | 4339404.28 | [5 empty] | N | FL_DD | 46.55% | EC10B | 53.45%
502536 | FRMA Section 33-34 -Optioneering - Edinburgh catchment | IR18 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-20 | 2017-09-15 | 2017-09-15 | City of Edinburgh | 0 | 0 | 0 | 10521.03 | 24906.82 | 0 | 0 | 0 | 35427.85 | 0 | 0 | 0 | 35427.85 | 0 | 0 | 0 | 0 | 35427.85 | 4339404.28 | [5 empty] | N | FL_DD | 28.23% | EC10B | 71.77%
502537 | FRMA Section 33-34 -Optioneering - Falkirk catchment | IR18 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-20 | 2017-09-15 | 2017-09-15 | Falkirk | 0 | 0 | 0 | 7365.72 | 15240.13 | 0 | 0 | 0 | 22605.85 | 0 | 0 | 0 | 22605.85 | 0 | 0 | 0 | 0 | 22605.85 | 4339404.28 | [5 empty] | N | EC10B | 46.55% | FL_DD | 53.45%
502538 | FRMA Section 33-34 -Optioneering - Tayside catchment | IR18 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-09-15 | 2017-09-15 | Dundee City | 0 | 0 | 0 | 7365.72 | 10423.78 | 0 | 0 | 0 | 17789.5 | 0 | 0 | 0 | 17789.5 | 0 | 0 | 0 | 0 | 17789.5 | 4339404.28 | [5 empty] | N | FL_DD | 43.79% | EC10B | 56.21%
403642 | Frontier BM Org Implementation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-12-18 | 2013-12-18 | 2013-12-30 | 2015-09-24 |  | Scottish Water Wide | 266683 | 0 | -25510.2 | 0 | 0 | 0 | 0 | 0 | -25510.2 | 0 | 0 | 0 | 241172.8 | 0 | 0 | 0 | 0 | 241172.8 | 306661.32 | [5 empty] | N | CM_M&G | 100%
402680 | Frontier Futures | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2012-05-18 | 2016-05-12 | 2015-11-05 | 2015-11-06 |  | Scottish Water Wide | 1414685.71 | 0 | -464.72 | 0 | 0 | 0 | 0 | 0 | -464.72 | 0 | 0 | 0 | 1414220.99 | 0 | 0 | 0 | 0 | 1414220.99 | 730242.44 | [5 empty] | N | WSI | 25% | WSNI | 25% | WWI | 25% | WWNI | 25%
403644 | Frontier Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-05-20 | 2014-05-20 | 2014-05-20 | 2015-07-28 |  | Scottish Water Wide | 496725 | 0 | -7024.38 | 0 | 0 | 0 | 0 | 0 | -7024.38 | 0 | 0 | 0 | 489700.62 | 0 | 0 | 0 | 0 | 489700.62 | 306661.32 | [5 empty] | N | CM_M&G | 100%
403287 | Frontier North Reservoir CM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-06 | 2013-07-12 | 2013-08-05 | 2014-12-17 |  | Scottish Water Wide | 538174.78 | 0 | -476.62 | 0 | 0 | 0 | 0 | 0 | -476.62 | 0 | 0 | 0 | 537698.16 | 0 | 0 | 0 | 0 | 537698.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403288 | Frontier South Reservoir CM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-06 | 2014-03-19 | 2014-03-03 | 2014-03-03 |  | Scottish Water Wide | 91330.89 | 0 | 1105 | 0 | 0 | 0 | 0 | 0 | 1105 | 0 | 0 | 0 | 92435.89 | 0 | 0 | 0 | 0 | 92435.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403286 | Frontier West Reservoir CM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-06 | 2014-03-19 | 2014-03-03 | 2014-03-03 |  | Scottish Water Wide | 281927.69 | 0 | 299 | 0 | 0 | 0 | 0 | 0 | 299 | 0 | 0 | 0 | 282226.69 | 0 | 0 | 0 | 0 | 282226.69 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510104 | Fruid Reservoir Scour Valve Repair | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS2 |  | 2021-01-28 | 2021-04-09 | 2022-02-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44786.75 | 44786.75 | 185213.25 | 0 | 0 | 230000 | 0 | 0 | 0 | 0 | 230000 | 0 | [5 empty] | N | SR21_WA | 100%
508286 | Fruid Spillway Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-09-08 | 2021-08-16 | 2022-03-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12712.08 | 12712.08 | 47351.76 | 0 | 0 | 60063.84 | 0 | 0 | 0 | 0 | 60063.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503541 | Fudstone WwPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2020-02-05 | 2020-12-22 | 2021-05-05 | 2021-10-29 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 18083.72 | 37253.28 | 281393 | 336730 | 290042.79 | 0 | 0 | 626772.79 | 0 | 0 | 0 | 0 | 626772.79 | 209381.79 | [5 empty] | N | CM_WWI | 100%
46360 | Fyvie WWTP Refurb - STW001483 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-28 | 2010-09-29 | 2011-02-21 | 2012-02-16 |  | Aberdeenshire | 1367791.79 | 0 | 622.5 | 0 | 0 | 0 | 0 | 0 | 622.5 | 0 | 0 | 0 | 1368414.29 | 0 | 0 | 0 | 0 | 1368414.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401921 | G SR10 Capital Maintenance Guillotine from SR6 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2011-01-27 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 16437820.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16437820.51 | 0 | 0 | 0 | 0 | 16437820.51 | 0 | [6 empty] | CM_WWNI | 100%
401923 | G SR10 Growth Guillotine (waste) from SR6 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2011-01-27 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 17229131.57 | 0 | 0.43 | 0 | 0 | 0 | 0 | 0 | 0.43 | 0 | 0 | 0 | 17229132 | 0 | 0 | 0 | 0 | 17229132 | 0 | [5 empty] | N | SG1 | 100%
401922 | G SR10 Growth Guillotine (water) from SR6 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2011-01-27 | 2019-03-27 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 4508509.77 | 0 | 0.23 | 0 | 0 | 0 | 0 | 0 | 0.23 | 0 | 0 | 0 | 4508510 | 0 | 0 | 0 | 0 | 4508510 | 0 | [5 empty] | N | WG1 | 100%
300017 | G SR6 Capital Maintenance Guillotine to SR10 | Q&S3A | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2011-01-26 | 2019-03-27 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | -16437820.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16437820.51 | 0 | 0 | 0 | 0 | -16437820.51 | 0 | [6 empty] | CM_WWNI | 100%
300019 | G SR6 Growth Guillotine (waste) to SR10 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2011-01-27 | 2019-03-27 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | -17229131.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17229131.57 | 0 | 0 | 0 | 0 | -17229131.57 | 0 | [6 empty] | SG1 | 100%
300018 | G SR6 Growth Guillotine (water) to SR10 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2011-01-26 | 2019-03-27 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | -4508509.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4508509.77 | 0 | 0 | 0 | 0 | -4508509.77 | 0 | [6 empty] | WG1 | 100%
46159 | Gailes SPS Refurb - SPS000198 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-03-31 | 2011-07-18 | 2014-10-30 | 2014-10-30 | North Ayrshire | 10217887.65 | 0 | 335374.86 | -14136.85 | 0 | 0 | 0 | 0 | 321238.01 | 0 | 0 | 0 | 10539125.66 | 0 | 0 | 0 | 0 | 10539125.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511267 | Gailes WWPS - Rising Main Burst repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2021-02-17 | 2021-03-17 | 2021-10-22 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17828.29 | 17828.29 | 82549.48 | 0 | 0 | 100377.77 | 0 | 0 | 0 | 0 | 100377.77 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510337 | Gairloch WwTW - Disc Filter Backwash System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-06-23 | 2022-09-15 | 2023-04-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8495.85 | 8495.85 | 131504.15 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 140000 | 90601.29 | [5 empty] | N | WWNI | 100%
403894 | Gairloch WWTW - Low Carbon Treatment - SR15 Capital Maintenance | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS5 | 2017-04-30 | 2017-08-01 | 2019-01-28 | 2020-02-29 | 2020-02-29 | Highland | 9120 | 0 | 142318 | 64871.92 | 345611.25 | 655481.17 | 2408265 | 274814.36 | 3891361.7 | 8386.9 | 3572.8194 | 4959.6816 | 3908868.6 | 1386.8622 | 0 | 0 | 1386.8622 | 3910255.4622 | 90601.29 | [5 empty] | Y | EC02A | 42.6% | CM_WWNI | 57.4% | [36 empty] | 1 | [28 empty] | 0
403213 | Gala WWTW - Design Supply and Install Combined Heat and Power (CHP) System | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-01-21 | 2015-02-26 | 2015-02-26 | 2015-03-25 | 2015-03-25 | Scottish Borders | 849238 | 0 | 228720 | 68561 | 3495 | 2367.28 | -8482.33 | 0 | 294660.95 | 0 | 0 | 0 | 1143898.95 | 0 | 0 | 0 | 0 | 1143898.95 | 0 | [5 empty] | N | CC1W | 100%
500133 | Galashiels DOA (DOA000032) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-26 | 2016-12-19 | 2017-01-13 | 2018-07-12 | 2018-08-08 | Scottish Borders | 0 | 0 | 19895 | 33649 | 57826 | -57.4 | 0 | 0 | 111312.6 | 0 | 0 | 0 | 111312.6 | 0 | 0 | 0 | 0 | 111312.6 | 336967.95 | [5 empty] | N | EC01D | 26.93% | CS16D | 73.07%
501405 | Galashiels Langshaw TWP NT516363 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2018-05-31 | 2027-10-18 | 2028-02-21 | 2028-06-30 |  | Scottish Borders | 0 | 0 | 0 | 6324.78 | 595.82 | 2207.44 | 52.79 | 0 | 9180.83 | -40.69 | 0 | 0 | 9140.14 | 0 | 0 | 0 | 0 | 9140.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503235 | Galashiels Manse Street Infra | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | WINF | SOSI | MS3 | 2018-05-31 | 2019-03-29 | 2019-04-29 | 2022-11-30 | 2023-03-02 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 1023930.42 | 6108422.09 | 177734.49 | 7310087 | 1139013.88 | 330309.6762 | 488843.4568 | 8449100.88 | 158533.7806 | 0 | 279510.1283 | 438043.9089 | 8887144.7889 | 2430937.3 | [5 empty] | N | DW25P | 10.73% | WR1 | 18.27% | CM_WSI | 71%
500245 | Galashiels Manse Street WTW | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | SEPA | NONINF | SOSI | MS3 | 2016-12-23 | 2018-09-28 | 2019-03-04 | 2022-08-17 | 2023-01-17 | Scottish Borders | 0 | 0 | 67704.37 | 390007.15 | 625335.21 | 1161161.07 | 848233.19 | 3735516.46 | 6827957.44 | 4330910 | 1641414.89 | 2370191.8647 | 11158867.44 | 728776.9747 | 0 | 832843.3198 | 1561620.2945 | 12720487.7345 | 2549959.88 |  |  |  |  | 378.9998 | N | CM_WSI | 13.3% | DW25P | 14% | WR1 | 23.9% | CM_WSNI | 48.8%
400063 | Galashiels STC Refurb STC000089 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-14 | 2011-05-03 | 2011-08-01 | 2015-08-27 |  | Scottish Borders | 2913508.47 | 0 | -179181.13 | 270 | 589.78 | 0 | 0 | 0 | -178321.35 | 0 | 0 | 0 | 2735187.12 | 0 | 0 | 0 | 0 | 2735187.12 | 90601.29 |  |  |  |  | 27876 | N | CM_WWNI | 100%
30290 | Galashiels STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-29 | 2011-05-05 | 2011-08-01 | 2015-12-11 | 2016-02-25 | Scottish Borders | 4138179.87 | 0 | 143137.41 | 11113.17 | -2910.39 | 0 | 0 | 0 | 151340.19 | 0 | 0 | 0 | 4289520.06 | 0 | 0 | 0 | 0 | 4289520.06 | 119362.42 |  |  |  |  | 27879.5018 | N | CM_WWNI | 40.36% | EC01A | 59.64%
508849 | Galashiels WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-08-08 | 2025-06-02 | 2025-09-02 | 2026-10-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73632 | 73632 | 1926367.97 | 0 | 0 | 1999999.97 | 0 | 0 | 0 | 0 | 1999999.97 | 122419.09 | [5 empty] | N | SG1 | 100%
503259 | Galashiels WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS7 | 2020-11-11 | 2020-11-11 | 2021-01-05 | 2021-01-08 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 68097.92 | 1467.32 | -23600.45 | 45964.79 | 0 | 0 | 0 | 45964.79 | 0 | 0 | 0 | 0 | 45964.79 | 122419.09 | [5 empty] | N | SG1 | 100%
503290 | Galashiels WWTW - Lagoon Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2023-08-08 | 2025-06-02 | 2025-08-29 | 2026-10-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 21883.55 | 96.89 | 8663.57 | 30644 | 1969356.67 | 0 | 0 | 2000000.67 | 0 | 0 | 0 | 0 | 2000000.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401374 | Gap Sites and Vacant Properties Incentive Process | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2010-09-07 | 2011-02-21 | 2011-04-29 | 2015-07-31 | 2011-03-14 | Scottish Water Wide | 960799 | 0 | -8957.13 | 0 | 0 | 0 | 0 | 0 | -8957.13 | 0 | 0 | 0 | 951841.87 | 0 | 0 | 0 | 0 | 951841.87 | 0 | [5 empty] | N | CS20 | 100%
501576 | Gaps3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-01-18 | 2016-01-18 | 2016-02-01 | 2017-03-31 |  | Scottish Water Wide | 0 | 0 | 2228941.22 | 1162511.88 | -685647.93 | 0 | 0 | 0 | 2705805.17 | 0 | 0 | 0 | 2705805.17 | 0 | 0 | 0 | 0 | 2705805.17 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502787 | Garbethill 30inch Trunk mains (local network reinforcement) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2017-06-30 | 2017-10-30 | 2017-10-31 | 2018-02-28 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 2329220.04 | -427932.15 | -132776.02 | 0 | 1768511.88 | 199119.04 | 0 | 0 | 1967630.91 | 0 | 0 | 0 | 0 | 1967630.91 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402213 | Garbethill inlet main - Mitigating Risk of Failure | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-18 | 2015-03-24 | 2015-04-29 | 2015-04-02 |  | North Lanarkshire | 70000 | 0 | -1861.64 | 0 | 0 | 0 | 0 | 0 | -1861.64 | 0 | 0 | 0 | 68138.36 | 0 | 0 | 0 | 0 | 68138.36 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502396 | Garbethill Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2017-06-21 | 2024-07-17 | 2024-08-19 | 2025-03-06 |  | East Dunbartonshire | 0 | 0 | 0 | 7129.27 | 20076.73 | 82222.39 | 8604.18 | -0.48 | 118032.09 | 563573.29 | 0 | 0 | 681605.38 | 0 | 0 | 0 | 0 | 681605.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503413 | Garbethill WSZ Trunk Main Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS3 | 2020-03-26 | 2020-12-21 | 2021-03-24 | 2021-09-30 | 2022-09-30 | Moray | 0 | 0 | 0 | 0 | 0 | 91514.56 | 202276.46 | 249964.21 | 543755.23 | 397200.77 | 397200.7725 | 497603.8986 | 940956 | 100403.1261 | 0 | -1.1642e-10 | 100403.1261 | 1041359.1261 | 539345.26 | [5 empty] | Y | DW5 | 100% | [23 empty] | 83.9 | [43 empty] | 0
503381 | Gardenstown WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-05-13 | 2028-03-21 | 2028-07-24 | 2029-01-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 76307.53 | 5609 | 0.47 | 81917 | 0 | 0 | 0 | 81917 | 0 | 0 | 0 | 0 | 81917 | 122419.09 | [5 empty] | N | SG1 | 100%
403611 | Garlieston Harbour WWTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-11-07 | 2015-02-10 | 2015-07-27 | 2016-06-06 | 2016-06-06 | Dumfries and Galloway | 155449 | 0 | 383756 | 5623.52 | 0 | -828.22 | 0 | 0 | 388551.3 | 0 | 0 | 0 | 544000.3 | 0 | 0 | 0 | 0 | 544000.3 | 0 | [5 empty] | N | SG1 | 100%
403254 | Garmouth SPS000832 & Storm SPS000833 Screens Pumps and Telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2013-01-22 | 2016-03-29 | 2016-06-13 | 2016-11-03 |  | Moray | 19920.46 | 0 | 43801.33 | 204957.16 | -976.95 | -100.61 | 0 | 0 | 247680.93 | 0 | 0 | 0 | 267601.39 | 0 | 0 | 0 | 0 | 267601.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503316 | Garmouth ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2021-01-14 | 2021-01-14 | 2021-01-14 | 2021-02-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 31602.89 | 16193.97 | -7714.73 | 40082.13 | 0 | 0 | 0 | 40082.13 | 0 | 0 | 0 | 0 | 40082.13 | 122419.09 | [5 empty] | N | SG1 | 100%
502407 | Garmouth WwTW Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2017-07-25 | 2021-10-22 | 2022-06-14 | 2022-12-28 |  | Moray | 0 | 0 | 0 | 7070.44 | 2052.89 | 0 | 8768.36 | 63848.49 | 81740.18 | 112521.01 | 0 | 0 | 194261.19 | 0 | 0 | 0 | 0 | 194261.19 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510269 | Garnock Valley Sewer River Caaf Erosion Protection | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-02-21 | 2023-08-16 | 2023-11-14 | 2024-09-10 | 2024-09-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36982.53 | 36982.53 | 263017.47 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | [5 empty] | N | SR21_WW | 100%
501085 | Gartcarron WOA Drymen WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-04-18 | 2018-03-30 | 2018-03-30 | 2018-11-26 |  | Stirling | 0 | 0 | 26352 | 4206 | 167697.57 | 720960.35 | 28028.17 | -13451.12 | 933792.96 | 0 | 0 | 0 | 933792.96 | 0 | 0 | 0 | 0 | 933792.96 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501084 | Gartcarron WOA Gartcarron WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 |  | Stirling | 0 | 0 | 529.62 | -529.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501086 | Gartcarron WOA Low Lettre WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-04-13 | 2016-12-28 | 2017-03-06 | 2018-02-15 |  | Stirling | 0 | 0 | 23904 | 102270 | 568645.8 | -21728.08 | -3970.02 | 0 | 669121.7 | 0 | 0 | 0 | 669121.7 | 0 | 0 | 0 | 0 | 669121.7 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401412 | Gartcarron WTW Closure | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-10-13 | 2011-06-01 | 2011-06-15 | 2012-03-30 |  | Stirling | 4664274.29 | 0 | 495 | 0 | 0 | 0 | 0 | 0 | 495 | 0 | 0 | 0 | 4664769.29 | 0 | 0 | 0 | 0 | 4664769.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
45642 | Gartcarron WTW Refurb - WTW000633 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-24 | 2011-06-30 | 2011-06-30 | 2011-03-31 |  | Stirling | 138193.93 | 0 | -378.73 | 0 | 0 | 0 | 0 | 0 | -378.73 | 0 | 0 | 0 | 137815.2 | 0 | 0 | 0 | 0 | 137815.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511231 | Garthamlock Water Tower - Crash Barrier Scaffold | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-02-18 | 2022-01-28 | 2022-09-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.92 | 1285.92 | 15834.08 | 0 | 0 | 17120 | 0 | 0 | 0 | 0 | 17120 | 311236.79 | [5 empty] | N | WSI | 100%
402599 | Garthdee Syphon Flow Control and Screen | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2012-03-27 | 2027-12-27 | 2028-04-06 | 2029-07-03 |  | All East Unitary Authorities | 55600 | 0 | -476.57 | 19442.96 | 59472.45 | 45159.2 | 1045.41 | 13.91 | 124657.35 | 2371185.83 | 0 | 0 | 2551443.17 | 0 | 0 | 0 | 0 | 2551443.17 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403004 | Gartly SPS pump - sewer replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-04 | 2013-03-22 | 2013-05-20 | 2013-08-01 |  | Aberdeenshire | 66053.36 | 0 | -2120.07 | 0 | 0 | 0 | 0 | 0 | -2120.07 | 0 | 0 | 0 | 63933.29 | 0 | 0 | 0 | 0 | 63933.29 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502618 | Gartmore WSZ - Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2020-09-22 | 2020-09-22 | 2028-06-13 | 2021-01-25 |  | Stirling | 0 | 0 | 0 | 7600 | 0 | -93.43 | 5068.83 | -5068.83 | 7506.57 | 0 | 0 | 0 | 7506.57 | 0 | 0 | 0 | 0 | 7506.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402347 | Gartmorn Reservoir - Improving scour capacity | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-10-20 | 2012-11-22 | 2013-01-14 | 2013-08-07 | 2013-08-07 | Clackmannanshire | 662764 | 0 | -833.9 | 0 | 0 | 0 | 0 | 0 | -833.9 | 0 | 0 | 0 | 661930.1 | 0 | 0 | 0 | 0 | 661930.1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
30293 | Gartocharn STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2011-08-22 | 2011-09-30 | 2013-03-20 | 2013-03-25 | West Dunbartonshire | 458320.82 | 0 | -4747.76 | 0 | 0 | 0 | 0 | 0 | -4747.76 | 0 | 0 | 0 | 453573.06 | 0 | 0 | 0 | 0 | 453573.06 | 119362.42 | [5 empty] | N | EC04A | 20% | CM_WWNI | 80%
501531 | Gartshore TWS Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-09-21 | 2030-01-25 | 2030-09-11 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904141.92 | 0 | 0 | 904141.92 | 0 | 0 | 0 | 0 | 904141.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500808 | Garve RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2017-03-23 | 2017-05-19 | 2017-12-31 | 2018-06-30 | Highland | 0 | 0 | 2010 | 174.7 | 6379.57 | 4227.63 | 0 | 0 | 12791.9 | 0 | 0 | 0 | 12791.9 | 0 | 0 | 0 | 0 | 12791.9 | 19711.21 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 5.52 | [43 empty] | 0
46852 | Garve WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-29 | 2011-06-27 | 2014-01-06 | 2014-02-17 | Highland | 1488201.42 | 0 | -42102.16 | 774.7 | 0 | 0 | 0 | 0 | -41327.46 | 0 | 0 | 0 | 1446873.96 | 0 | 0 | 0 | 0 | 1446873.96 | 28761.13 | [5 empty] | N | DW23 | 100%
403144 | Gatehead - Irvine Valley Sewer River Bank Stabilisation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-04 | 2013-12-04 | 2014-02-28 | 2014-12-01 |  | East Ayrshire | 144925 | 0 | 0 | -1861.47 | 0 | 0 | 0 | 0 | -1861.47 | 0 | 0 | 0 | 143063.53 | 0 | 0 | 0 | 0 | 143063.53 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500143 | Gatehouse Of Fleet DOA (DOA000098) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-09-27 | 2015-10-19 | 2016-10-31 | 2016-12-31 | Dumfries and Galloway | 0 | 0 | 47971 | 33479.98 | 0 | 0 | 0 | 0 | 81450.98 | 0 | 0 | 0 | 81450.98 | 0 | 0 | 0 | 0 | 81450.98 | 72047.27 | [5 empty] | Y | CS11 | 40.64% | CS16D | 59.36% | [37 empty] | 1 | [27 empty] | 0
45631 | Gatehouse STW Refurb - STW000312 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-18 | 2011-02-14 | 2011-03-31 | 2013-03-26 |  | Dumfries and Galloway | 1560675.11 | 0 | 17638.04 | -114.55 | 0 | 0 | 0 | 0 | 17523.49 | 0 | 0 | 0 | 1578198.6 | 0 | 0 | 0 | 0 | 1578198.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
49030 | General Programme Risk | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS3 |  |  | 2010-04-01 | 2021-03-31 |  | Scottish Water Wide | 0 | 0 | -4000000 | 0 | 0 | 0 | 0 | 0 | -4000000 | 0 | 0 | 0 | -4000000 | 0 | 0 | 0 | 0 | -4000000 | 28761.13 | [5 empty] | N | RISK | 100%
505570 | Generator Battery Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-09 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 13084.11 | 40250.79 | 53334.9 | 146665.1 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500134 | Gifford DOA (DOA000514) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-05-30 | 2016-08-01 | 2019-03-31 | 2019-07-31 | East Lothian | 0 | 0 | 12005 | 15136 | 17083 | 37454 | 10661.06 | 0 | 92339.06 | 0 | 0 | 0 | 92339.06 | 0 | 0 | 0 | 0 | 92339.06 | 87570.01 | [5 empty] | Y | EC01G | 13.52% | EC01D | 86.48% | [38 empty] | 1 | [26 empty] | 0
503311 | Gifford WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-04-01 | 2028-09-20 | 2029-01-18 | 2030-01-21 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 69110.49 | 7154.05 | 614.78 | 76879.32 | 385.21 | 0 | 0 | 77264.53 | 0 | 0 | 0 | 0 | 77264.53 | 122419.09 | [5 empty] | N | SG1 | 100%
505537 | Gigha WTW Membrane Failures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-12-27 | 2023-07-24 | 2023-10-24 | 2024-09-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1923.72 | 5399.66 | 7323.38 | 442676.62 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 450000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507797 | Gigha WTW - PLC Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-10-05 | 2023-08-22 | 2024-01-30 | 2025-08-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5353.16 | 5353.16 | 494702.5 | 0 | 0 | 500055.66 | 0 | 0 | 0 | 0 | 500055.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506777 | Gilmerton DSR 2 Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-06-03 | 2023-07-21 | 2023-10-24 | 2024-09-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2229.12 | 2229.12 | 485770.88 | 0 | 0 | 488000 | 0 | 0 | 0 | 0 | 488000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500146 | Girvan DOA (DOA002467) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-03-30 | 2016-04-25 | 2018-07-26 | 2019-01-31 | South Ayrshire | 0 | 0 | 23967.68 | 109655.41 | 66195.91 | 63377.69 | 0 | 0 | 263196.69 | 0 | 0 | 0 | 263196.69 | 0 | 0 | 0 | 0 | 263196.69 | 4617.88 | [5 empty] | N | CS16D | 45.51% | EC01G | 54.49%
501309 | Girvan Private Wire Project | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater |  | SWD | Energy efficiency | MS7 | 2015-11-25 | 2015-11-25 | 2016-07-19 | 2020-06-09 | 2028-04-03 | South Ayrshire | 0 | 0 | 7602 | 36398 | -30.12 | 35.49 | 0 | 0 | 44005.37 | 0 | 0 | 0 | 44005.37 | 0 | 0 | 0 | 0 | 44005.37 | 1280912.62 | [5 empty] | N | I2S_WWNI | 100%
507171 | Girvan STC - Replacement Thermoblender heating element | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-07-27 | 2021-02-16 | 2021-09-17 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30985.14 | 30985.14 | 0 | 0 | 0 | 30985.14 | 0 | 0 | 0 | 0 | 30985.14 | 209381.79 | [5 empty] | N | Ww3 | 100%
500590 | GIS and Assets Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-09-01 | 2016-08-18 | 2016-08-18 | 2017-10-16 |  | Scottish Water Wide | 0 | 0 | 281487.9 | 262956.1 | 142592.59 | 0.15 | 0 | 0 | 687036.74 | 0 | 0 | 0 | 687036.74 | 0 | 0 | 0 | 0 | 687036.74 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500904 | GIS and Modelling Systems Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-09-17 | 2016-09-23 | 2016-09-23 | 2018-07-12 |  | Scottish Water Wide | 0 | 0 | 2900124 | 2616598.85 | 1826234.73 | 152793.95 | 0 | 0 | 7495751.53 | 0 | 0 | 0 | 7495751.53 | 0 | 0 | 0 | 0 | 7495751.53 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500192 | Gladhouse Birds and Habitats Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWD | Environmental Studies | MS7 | 2015-03-20 | 2016-09-27 | 2016-09-27 | 2017-12-31 | 2017-12-31 | Midlothian | 0 | 0 | 1928 | 8901 | 3079.57 | 41.28 | -1664.05 | 0 | 12285.8 | 0 | 0 | 0 | 12285.8 | 0 | 0 | 0 | 0 | 12285.8 | 18948.39 | [5 empty] | Y | EC08C | 100% | [40 empty] | 1 | [26 empty] | 0
503487 | Gladhouse MIOS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2019-10-04 | 2023-03-09 | 2023-07-12 | 2025-02-13 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 158589.9 | 202655.1 | 361245 | 4716329.32 | 0 | 0 | 5077574.32 | 0 | 0 | 0 | 0 | 5077574.32 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501401 | Gladhouse WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2027-04-01 | 2028-04-12 | 2028-08-16 | 2029-04-02 |  | Midlothian | 0 | 0 | 0 | 1687.85 | 0 | 995.51 | 412.82 | -3096.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
506521 | Glaisnock DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-08-26 | 2022-10-10 | 2023-01-09 | 2023-12-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2873.48 | 2873.48 | 119945.57 | 0 | 0 | 122819.05 | 0 | 0 | 0 | 0 | 122819.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511591 | Glaisnock Water Sewer - Scoping Survey | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-03-05 | 2021-09-24 | 2022-05-09 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1251.32 | 1251.32 | 8999.97 | 0 | 0 | 10251.29 | 0 | 0 | 0 | 0 | 10251.29 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500234 | Glamis WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2017-08-15 | 2027-04-01 | 2027-04-01 | 2020-04-28 |  | Angus | 0 | 0 | 49905.57 | 27672.17 | 7625.37 | 0 | 85203.11 | -84241.05 | 86165.17 | 0 | 0 | 0 | 86165.17 | 0 | 0 | 0 | 0 | 86165.17 | 122419.09 | [5 empty] | N | SG1 | 100%
500701 | Glascoego Trunk Main Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-06-17 | 2027-07-06 | 2027-09-01 | 2028-04-21 |  | Aberdeenshire | 0 | 0 | 8759 | 111388 | 28101 | -5690 | -4395.11 | -25.16 | 138137.73 | 321806.27 | 0 | 0 | 459944 | 0 | 0 | 0 | 0 | 459944 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502086 | Glasgow Airport 18inch Spun Iron Main Diversion | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2016-04-08 | 2018-08-14 | 2018-09-11 | 2019-04-30 |  | Renfrewshire | 0 | 0 | 0 | 92360 | 251602 | 3061857.49 | -2410.28 | 4738.79 | 3408148 | 0 | 0 | 0 | 3408148 | 0 | 0 | 0 | 0 | 3408148 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400526 | Glasgow Byres Road (Oxfam)- Internal Flooding | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-03-31 | 2012-05-22 | 2012-06-18 | 2013-01-30 | 2013-01-30 | Glasgow City | 26440.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26440.96 | 0 | 0 | 0 | 0 | 26440.96 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
401880 | Glasgow City Centre Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-02 | 2012-08-30 | 2012-08-29 | 2015-03-26 |  | Glasgow City | 4527120 | 0 | -173603.53 | 182.95 | 0 | 0 | 0 | 0 | -173420.58 | 0 | 0 | 0 | 4353699.42 | 0 | 0 | 0 | 0 | 4353699.42 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401478 | Glasgow Sludge Contingency Plan | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-11-18 | 2012-05-29 | 2012-09-18 | 2013-11-18 |  | Glasgow City | 3148288 | 0 | -7297.14 | 0 | 0 | 0 | 0 | 0 | -7297.14 | 0 | 0 | 0 | 3140990.86 | 0 | 0 | 0 | 0 | 3140990.86 | 90601.29 |  |  |  |  | 68697 | N | CM_WWNI | 100%
403738 | Glasgow Sludge Main Rehabiliation Project | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-04-03 | 2014-04-14 | 2014-04-14 | 2019-08-06 |  | Glasgow City | 259090.26 | 0 | 49249.74 | 18500.26 | -65514.41 | 0 | 0 | 0 | 2235.59 | 0 | 0 | 0 | 261325.85 | 0 | 0 | 0 | 0 | 261325.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501189 | Glasgow Sludge Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2015-10-29 | 2017-08-30 | 2017-08-31 | 2018-03-23 |  | Glasgow City | 0 | 0 | 507137.65 | 268501.88 | 1429607.7 | -254722.91 | 1773.88 | -605.7 | 1951692.5 | 0 | 0 | 0 | 1951692.5 | 0 | 0 | 0 | 0 | 1951692.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502601 | Glasgow Sludge Main Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-02-02 | 2018-09-17 | 2018-09-17 | 2019-08-06 |  | Renfrewshire | 0 | 0 | 0 | 23505 | 225098 | 850357.2 | 0 | 0 | 1098960.2 | 0 | 0 | 0 | 1098960.2 | 0 | 0 | 0 | 0 | 1098960.2 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506177 | Glasgow Sludge Main Resilience - investigation and cut outs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-05-15 | 2020-09-03 | 2021-07-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153932 | 153932 | 46068.32 | 0 | 0 | 200000.32 | 0 | 0 | 0 | 0 | 200000.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
46388 | Glasgow Strategic Study - Daldowie Catchment Planning Study | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-10-28 | 2009-10-28 | 2019-03-04 | 2011-03-14 | Glasgow City | 2746876.29 | 0 | 2224.16 | 275.68 | 364.08 | 531.78 | 0 | 0 | 3395.7 | 0 | 0 | 0 | 2750271.99 | 0 | 0 | 0 | 0 | 2750271.99 | 86283.39 | [5 empty] | N | EC04C | 32.82% | EC10E | 32.82% | EC01D | 34.37%
46389 | Glasgow Strategic Study - Dalmarnock Catchment Planning Study | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-08-28 | 2009-08-28 | 2018-08-23 | 2011-03-14 | Glasgow City | 695000 | 0 | 27 | 0 | 0 | -201.83 | 36.94 | 0 | -137.89 | 0 | 0 | 0 | 694862.11 | 0 | 0 | 0 | 0 | 694862.11 | 86283.39 | [5 empty] | N | EC04C | 33.33% | EC10E | 33.33% | EC01D | 33.33%
46387 | Glasgow Strategic Study - Dalmuir Catchment Planning Study | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-10-14 | 2009-10-14 | 2015-08-10 | 2011-03-14 | Glasgow City | 1923834.76 | 0 | 34045.46 | 0 | 0 | 0 | 0 | 0 | 34045.46 | 0 | 0 | 0 | 1957880.22 | 0 | 0 | 0 | 0 | 1957880.22 | 86283.39 | [5 empty] | N | EC04C | 33% | EC10E | 33% | EC01D | 34%
46385 | Glasgow Strategic Study - Shieldhall Catchment Planning Study | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-10-14 | 2009-10-14 | 2015-08-10 | 2011-03-14 | Glasgow City | 2130095 | 0 | 61629.08 | 0 | 0 | 0 | 0 | 0 | 61629.08 | 0 | 0 | 0 | 2191724.08 | 0 | 0 | 0 | 0 | 2191724.08 | 86283.39 | [5 empty] | N | EC04C | 33.33% | EC10E | 33.33% | EC01D | 33.33%
401502 | Glasgow Trunk Mains Meter and PRV Installations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-20 | 2011-06-22 | 2011-10-31 | 2014-12-12 |  | Glasgow City | 2155205 | 0 | 2004 | 35456.61 | 52176.37 | 8054.96 | 0 | 0 | 97691.94 | 0 | 0 | 0 | 2252896.94 | 0 | 0 | 0 | 0 | 2252896.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402244 | Glasgow Trunk Mains Rehab - C4 and M2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-05 | 2012-04-24 | 2012-05-21 | 2015-05-25 |  | Glasgow City | 1577382 | 0 | -41130 | -8956.61 | 5461.71 | -124.78 | 0 | 0 | -44749.68 | 0 | 0 | 0 | 1532632.32 | 0 | 0 | 0 | 0 | 1532632.32 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46868 | Glassford WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-05-07 | 2011-09-28 | 2011-10-24 | 2012-04-04 | 2012-12-24 | South Lanarkshire | 1886130 | 0 | 120870 | -3999.51 | 42193.9 | 0 | 0 | 0 | 159064.39 | 0 | 0 | 0 | 2045194.39 | 0 | 0 | 0 | 0 | 2045194.39 | 28761.13 | [5 empty] | N | DW3C | 100%
503474 | Glebe Tunnel - Structural Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-23 | 2022-04-22 | 2022-07-01 | 2023-02-02 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2079.09 | 2079.09 | 719938.16 | 0 | 0 | 722017.25 | 0 | 0 | 0 | 0 | 722017.25 | 622473.57 | [5 empty] | N | CM_WSI | 4.762% | CM_M&G | 95.24%
511053 | Glen Finglas DIR - SR21 Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-11-29 | 2023-06-07 | 2023-09-05 | 2024-08-12 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917 | 917 | 549083.31 | 0 | 0 | 550000.31 | 0 | 0 | 0 | 0 | 550000.31 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506681 | Glen Finglas Reservoir Pressure Relief Hole Cleaning | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-06-16 | 2020-12-02 | 2021-04-28 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20056 | 20056 | 5104.51 | 0 | 0 | 25160.51 | 0 | 0 | 0 | 0 | 25160.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508665 | Glen Ogil Reservoir MIOS Study | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 |  | 2020-09-14 | 2021-01-05 | 2021-10-11 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7156 | 7156 | 7843.99 | 0 | 0 | 14999.99 | 0 | 0 | 0 | 0 | 14999.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402965 | Glen Road Shotts | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2014-04-23 | 2014-04-23 | 2014-04-23 | 2015-06-16 | North Lanarkshire | 24435.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24435.1 | 0 | 0 | 0 | 0 | 24435.1 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503605 | Glenbervie Place - Sewer Replacement & Lining | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-07-26 | 2020-09-30 | 2020-11-02 | 2021-06-10 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 30279.53 | 437806.47 | 468086 | 81213.36 | 0 | 0 | 549299.36 | 0 | 0 | 0 | 0 | 549299.36 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508138 | Glenburn Reservoir Proactive Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-08-19 | 2020-12-14 | 2021-08-02 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226690 | 226690 | 8310.45 | 0 | 0 | 235000.45 | 0 | 0 | 0 | 0 | 235000.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502551 | Glencaple ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2019-12-18 | 2022-07-29 | 2022-12-01 | 2023-06-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 31033.94 | 50651.09 | 17753.07 | 68924.08 | 16731.82 | 185094 | 946073 | 0 | 0 | 1131167 | 0 | 0 | 0 | 0 | 1131167 | 122419.09 | [5 empty] | N | SG1 | 100%
508428 | Glenconvinth BT cable replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-09-07 | 2021-10-11 | 2022-05-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 804 | 804 | 9195.75 | 0 | 0 | 9999.75 | 0 | 0 | 0 | 0 | 9999.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503989 | Glenconvinth Sample tap DSR 1993 NH505376-WN | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2019-11-27 | 2020-05-25 | 2020-08-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 24568.17 | 27568.17 | 0 | 0 | 0 | 27568.17 | 0 | 0 | 0 | 0 | 27568.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501230 | Glenconvinth WOA CM SR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2017-01-31 | 2017-01-31 | Highland | 0 | 0 | 0 | 17.75 | 0 | 0 | 0 | 0 | 17.75 | 0 | 0 | 0 | 17.75 | 0 | 0 | 0 | 0 | 17.75 | 0 | [5 empty] | Y | DW25D | 100% | [22 empty] | 1 | [44 empty] | 0
501547 | Glenconvinth WOA- Kirtarlity 6 inch Main Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-01-26 | 2016-09-26 | 2016-11-28 | 2017-08-17 |  | Highland | 0 | 0 | 13716 | 65778.53 | 122665.06 | 9805.03 | -287.96 | 0 | 211676.66 | 0 | 0 | 0 | 211676.66 | 0 | 0 | 0 | 0 | 211676.66 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502571 | Glenconvinth WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-04 | 2019-04-04 | Highland | 0 | 0 | 0 | 20930.23 | 671.68 | 1536.09 | -20633.2 | 0 | 2504.8 | 0 | 0 | 0 | 2504.8 | 0 | 0 | 0 | 0 | 2504.8 | 122419.09 | [5 empty] | N | WG1 | 100%
401312 | Glencorse - Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2013-11-29 | 2014-01-24 | 2015-03-31 | 2015-03-30 | Midlothian | 948556 | 0 | 0 | -7600.43 | 0 | 0 | 0 | 0 | -7600.43 | 0 | 0 | 0 | 940955.57 | 0 | 0 | 0 | 0 | 940955.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
31851 | Glencorse New WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2005-10-03 | 2008-07-31 | 2008-08-12 | 2012-02-10 | 2012-02-17 | Midlothian | 103900000 | 0 | 397722.57 | 1076650.43 | 1301070.77 | 952174.72 | 622570.95 | 417878.71 | 4768068.15 | 0 | 0 | 0 | 108668068.15 | 0 | 0 | 0 | 0 | 108668068.15 | 464156.14 | [5 empty] | N | WSNI | 1.754% | WG1 | 4.618% | DW3G | 8.071% | DW4A | 8.071% | DW3J | 13.32% | DW13 | 21.39% | DW3A | 21.39% | DW3B | 21.39%
511057 | Glencorse Reservoir - Workplace H&S Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-05-24 | 2021-08-13 | 2022-03-28 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341.76 | 341.76 | 175000 | 0 | 0 | 175341.76 | 0 | 0 | 0 | 0 | 175341.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403324 | Glencorse WOA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-01 | 2014-08-20 | 2014-08-13 | 2014-08-14 |  | Midlothian | 79943.79 | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 116 | 0 | 0 | 0 | 80059.79 | 0 | 0 | 0 | 0 | 80059.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501236 | Glencorse WOA East Craigs-N. Corstorphine WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 41.59 | 0 | 0 | 0 | 41.59 | 0 | 0 | 0 | 41.59 | 0 | 0 | 0 | 0 | 41.59 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500025 | Glencorse WOA Hillend Low WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-13 | 2016-09-23 | 2017-10-30 | 2018-09-18 |  | City of Edinburgh | 0 | 0 | 59791 | 145842 | 590442 | 134757.78 | 4825.04 | -966.69 | 934691.13 | 0 | 0 | 0 | 934691.13 | 0 | 0 | 0 | 0 | 934691.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501139 | Glencorse WOA Hutchison WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501235 | Glencorse WOA Marchbank Torduff WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 |  | City of Edinburgh | 0 | 0 | 14734.88 | -14734.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
500024 | Glencorse WOA Morningside-Grange WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-03-05 | 2016-10-21 | 2017-08-28 | 2019-02-28 |  | City of Edinburgh | 0 | 0 | 31419 | 126405 | 848301.55 | 341694.64 | 4469.17 | 49.8 | 1352339.16 | 0 | 0 | 0 | 1352339.16 | 0 | 0 | 0 | 0 | 1352339.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501126 | Glencorse WOA Murrayfield-Ravelston WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-04 | 2028-03-31 | 2028-05-10 | 2029-02-08 |  | City of Edinburgh | 0 | 0 | 22032 | 2800 | 1000 | 6524.5 | 493.17 | 0 | 32849.67 | 401898.9 | 0 | 0 | 434748.57 | 0 | 0 | 0 | 0 | 434748.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501127 | Glencorse WOA North East Edinburgh WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501128 | Glencorse WOA Old Town-Canongate WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2016-04-11 | 2022-08-02 | 2022-08-24 | 2023-10-27 |  | City of Edinburgh | 0 | 0 | 0 | 31526 | 102465 | 13145.02 | 138.05 | -5075.11 | 142198.96 | 0 | 0 | 0 | 142198.96 | 0 | 0 | 0 | 0 | 142198.96 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505008 | Glencorse WTW Air Compressors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-21 |  | 2020-06-18 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 8280 | 116079.64 | 124359.64 | 44000.01 | 0 | 0 | 168359.65 | 0 | 0 | 0 | 0 | 168359.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502776 | Glencraig Rising Main Lochgelly | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2018-05-30 | 2019-03-13 | 2019-06-17 | 2019-09-18 |  | Fife | 0 | 0 | 0 | 0 | 27998.66 | 62276.34 | 39800.46 | 1182.54 | 131258 | 0 | 0 | 0 | 131258 | 0 | 0 | 0 | 0 | 131258 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502621 | Glendale WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-06 | 2020-04-06 | 2020-04-06 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 20930.23 | 499.08 | 2351.08 | 4324.28 | -22086.08 | 6018.6 | 0 | 0 | 0 | 6018.6 | 0 | 0 | 0 | 0 | 6018.6 | 122419.09 | [5 empty] | N | WG1 | 100%
45328 | Glendale WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-23 | 2011-06-06 | 2011-12-12 | 2012-02-06 | Highland | 43143.52 | 0 | 27.72 | 0 | 0 | 0 | 0 | 0 | 27.72 | 0 | 0 | 0 | 43171.24 | 0 | 0 | 0 | 0 | 43171.24 | 28761.13 | [5 empty] | N | DW13 | 100%
502730 | Glendessary Street Caol Sewer Cross Connections | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-05-30 | 2019-01-31 | 2019-02-18 | 2019-07-08 |  | Highland | 0 | 0 | 0 | 0 | 12917.31 | 32651.53 | 71580.67 | -353.44 | 116796.07 | 0 | 0 | 0 | 116796.07 | 0 | 0 | 0 | 0 | 116796.07 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403018 | Glendevon & Glenfarg WTW Sludge Presses Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-10-26 | 2013-03-28 | 2013-08-26 | 2014-04-28 |  | Fife | 784363 | 0 | -3490.66 | 288.24 | 0 | 0 | 0 | 0 | -3202.42 | 0 | 0 | 0 | 781160.58 | 0 | 0 | 0 | 0 | 781160.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500861 | Glendevon _ Glenfarg RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2015-11-04 | 2018-09-05 | 2018-11-29 | 2019-06-30 | 2020-06-30 | Fife | 0 | 0 | 15428 | -3169.22 | 19000 | 146248.24 | 85072.28 | 6747.7 | 269327 | 0 | 0 | 0 | 269327 | 0 | 0 | 0 | 0 | 269327 | 508161.63 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 113.26 | [43 empty] | 0
509553 | Glendevon CWT Site Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-11-02 | 2020-11-12 | 2022-05-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41077 | 41077 | 169185.18 | 0 | 0 | 210262.18 | 0 | 0 | 0 | 0 | 210262.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506056 | Glendevon DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-08-12 | 2022-08-15 | 2022-11-15 | 2023-10-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19086 | 19086 | 557913.99 | 0 | 0 | 576999.99 | 0 | 0 | 0 | 0 | 576999.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506663 | Glendevon Lower Spillway Drone Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-05-26 | 2021-02-25 | 2021-02-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7116 | 7116 | 0 | 0 | 0 | 7116 | 0 | 0 | 0 | 0 | 7116 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46345 | Glendevon Raw Water System - Cap Maint | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-05-07 | 2012-09-28 | 2012-11-21 | 2014-03-28 |  | Fife | 620245 | 0 | 2526 | -2959.85 | 0 | 0 | 0 | 0 | -433.85 | -2526 | 0 | 0 | 617285.15 | 0 | 0 | 0 | 0 | 617285.15 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501035 | Glendevon WOA Craigbeath WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2016-04-04 | 2023-04-17 | 2023-05-16 | 2024-04-16 |  | Perth and Kinross | 0 | 0 | 16995.35 | 9411.71 | 174592.94 | 9084.79 | 6624.91 | -1553.65 | 215156.05 | -0.01 | 0 | 0 | 215156.04 | 0 | 0 | 0 | 0 | 215156.04 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501036 | Glendevon WOA Ferryhills WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501034 | Glendevon WOA Fordell WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501031 | Glendevon WOA Glassiebarns WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  | Perth and Kinross | 0 | 0 | 59.3 | -59.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501032 | Glendevon WOA Gowerfield WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501033 | Glendevon WOA Hoodshill WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501030 | Glendevon WOA Limekilns WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501024 | Glendevon WOA Lochgelly South Street WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501025 | Glendevon WOA Lochgelly Spion Kop WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501026 | Glendevon WOA Redcraigs WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501065 | Glendevon WOA Torbain WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501023 | Glendevon WOA Townhill WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
503503 | Glendevon WOA-WI-Longannet 15inch Inlet Main - Burst frequency | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-11-23 | 2022-09-12 | 2022-12-13 | 2023-07-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 1040.23 | 1179.01 | 2219.24 | 1329186.67 | 0 | 0 | 1331405.91 | 0 | 0 | 0 | 0 | 1331405.91 | 311236.79 | [5 empty] | N | CM_M&G | 100%
501298 | Glendevon WTW - Alterations to Lime Dosing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-03-28 | 2018-06-28 | 2018-10-23 | 2020-01-31 |  | Fife | 0 | 0 | 3827.64 | 16582.25 | 5034.09 | 189797.26 | 387025.24 | 3301.52 | 605568 | 2305.75 | 0 | 0 | 607873.75 | 0 | 0 | 0 | 0 | 607873.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501600 | Glendevon WTW - Quality (Reduce high Production risks in DWSP) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS3 | 2017-03-21 | 2020-06-24 | 2020-09-29 | 2021-07-12 | 2021-10-12 | Fife | 0 | 0 | 0 | 72050.45 | 5656.77 | 535.47 | 40755.53 | 226077.66 | 345075.88 | 87833.47 | 87833.47 | 116722.6013 | 432909.35 | 28889.1313 | 0 | 0 | 28889.1313 | 461798.4813 | 1221777.68 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
501226 | Glendevon WTW - Quality (Reduce Transmission risks in DWSP) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS6 | 2017-03-15 | 2018-03-30 | 2018-07-19 | 2019-09-30 | 2020-03-31 | Fife | 0 | 0 | 2511.63 | 16007.42 | 182563.29 | 684566.82 | 402429.04 | -5205.2 | 1282873 | 13127 | 13127 | 18222.5108 | 1296000 | 5095.5108 | 0 | 0 | 5095.5108 | 1301095.5108 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
505771 | Glendevon WTW - Replacement Hypochlorite Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-04-24 | 2020-06-22 | 2020-09-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78755.66 | 78755.66 | 0 | 0 | 0 | 78755.66 | 0 | 0 | 0 | 0 | 78755.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402211 | Glendevon WTW Filter No6 Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-09-20 | 2013-04-12 | 2013-09-12 | 2014-03-10 |  | Fife | 423456.31 | 0 | 6.69 | -2112.11 | 0 | 0 | 0 | 0 | -2105.42 | 0 | 0 | 0 | 421350.89 | 0 | 0 | 0 | 0 | 421350.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500242 | Glendevon-Glenfarg-Kinnesswood- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS6 | 2015-03-20 | 2017-03-30 | 2017-06-27 | 2019-02-28 | 2019-09-30 | Fife | 0 | 0 | 4244 | 21380 | 151683.37 | 255944.63 | 61494.55 | 3877.69 | 498624.24 | 2500 | 2500 | 3470.4256 | 501124.24 | 970.4256 | 0 | 0 | 970.4256 | 502094.6656 | 340094.05 | [5 empty] | Y | DW5 | 100% | [19 empty] | 1 | [47 empty] | 0
500918 | Glendye - Belts of Collonach & Woodlands TM Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2015-09-07 | 2017-09-29 | 2017-10-02 | 2022-05-31 |  | Aberdeenshire | 0 | 0 | 11620 | 94891 | 438137 | 59266.65 | 75597.96 | 137927.39 | 817440 | 297802.22 | 0 | 0 | 1115242.22 | 0 | 0 | 411784.78 | 411784.78 | 1527027 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500243 | Glendye - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS6 | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-05-31 | 2020-01-31 | Aberdeenshire | 0 | 0 | 4285 | -1476.16 | 79399.59 | 713762.33 | 175793.45 | 10289.8 | 982054 | 0 | 0 | 0 | 982054 | 0 | 0 | 0 | 0 | 982054 | 1616482.73 | [5 empty] | N | DW5 | 100%
500886 | Glendye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-06-01 | 2017-12-20 | 2018-03-20 | 2019-03-31 | 2020-02-29 | Aberdeenshire | 0 | 0 | 2426.79 | 2573.21 | 14086.92 | 17056.43 | 27062.19 | 30707.53 | 93913.06 | 0 | 0 | 0 | 93913.06 | 0 | 0 | 0 | 0 | 93913.06 | 113115.57 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 25.74 | [43 empty] | 0
500037 | Glendye to Sunnyside Trunk Main Network Refurbishment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-01 | 2028-02-07 | 2028-05-03 | 2029-01-24 |  | Aberdeenshire | 0 | 0 | 10650 | 0 | 267.79 | 435.03 | 10971 | -10971 | 11352.82 | 2428067.28 | 0 | 0 | 2439420.1 | 0 | 0 | 0 | 0 | 2439420.1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46255 | Glenfarg Reservoir - Spillway and valve repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-22 | 2010-06-28 | 2010-10-25 | 2011-07-28 | 2011-07-28 | Fife | 132219.21 | 0 | -1.8 | 0 | 0 | 0 | 0 | 0 | -1.8 | 0 | 0 | 0 | 132217.41 | 0 | 0 | 0 | 0 | 132217.41 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501063 | Glenfarg WOA Kinghorn WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-04 | 2027-11-02 | 2027-12-27 | 2028-06-13 |  | Fife | 0 | 0 | 22464 | 16972 | 0 | -4495 | -629.17 | 0 | 34311.83 | 563226.19 | 0 | 0 | 597538.02 | 0 | 0 | 0 | 0 | 597538.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500974 | Glenfarg WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-09-17 | 2015-09-17 | 2015-11-26 | 2018-02-19 |  | Fife | 0 | 0 | 53357 | 851167.44 | 361386.6 | 35853.14 | 953.88 | 412.94 | 1303131 | 86.88 | 0 | 0 | 1303217.88 | 0 | 0 | 0 | 0 | 1303217.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501221 | Glenfarg WTW - Quality (Reduction of risks identified in Drinking Water Safety Plan - Distribution) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-11-17 | 2015-11-17 | 2016-02-01 | 2018-11-30 | 2019-06-30 | Fife | 0 | 0 | 615.71 | 2360.05 | 8116.15 | 13935.94 | 1972.15 | -973.77 | 26026.24 | 0 | 0 | 0 | 26026.24 | 0 | 0 | 0 | 0 | 26026.24 | 0 | [5 empty] | Y | DW25D | 100% | [22 empty] | 1 | [44 empty] | 0
503570 | Glenfarg WTW - RGF Media Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2021-07-12 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 329177.54 | 100866.46 | 430044 | 80956.15 | 0 | 0 | 511000.15 | 0 | 0 | 0 | 0 | 511000.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502128 | Glenfarg WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-04-23 | 2020-04-23 | 2020-04-23 | 2020-04-23 |  | Perth and Kinross | 0 | 0 | 0 | 23851.73 | 7666.01 | 7527.14 | 1616.08 | 19700.12 | 60361.08 | -19700.12 | 0 | 0 | 40660.96 | 0 | 0 | 0 | 0 | 40660.96 | 122419.09 | [5 empty] | N | SG1 | 100%
30308 | Glenfinnan WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-03-31 | 2011-08-29 | 2013-02-07 | 2013-02-21 | Highland | 1276327.51 | 0 | -1350.11 | 0 | 0 | 0 | 0 | 0 | -1350.11 | 0 | 0 | 0 | 1274977.4 | 0 | 0 | 0 | 0 | 1274977.4 | 28761.13 | [5 empty] | N | DW23 | 100%
503427 | Glengap Lochinvar and Boreholes WRZ - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2020-12-11 | 2021-07-19 | 2021-10-18 | 2022-05-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG1 | 100%
300034 | Glengap WFD Compliance - Loch Whinyeon Compensation Structure | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-04-23 | 2012-12-17 | 2013-02-18 | 2014-06-25 | 2011-03-14 | Dumfries and Galloway | 157181.84 | 0 | 121.45 | 213 | 0 | 0 | 0 | 0 | 334.45 | 0 | 0 | 0 | 157516.29 | 0 | 0 | 0 | 0 | 157516.29 | 28761.13 | [5 empty] | N | DW7 | 100%
506207 | Glengap WTW - DAF Scraper Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-05 | 2021-02-11 | 2021-09-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56300 | 56300 | 62353.89 | 0 | 0 | 118653.89 | 0 | 0 | 0 | 0 | 118653.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501213 | Glengap WTW - Improving WQ in Network (OMG5) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-01-28 | 2016-03-04 | 2016-03-07 | 2016-03-31 | 2016-08-31 | Dumfries and Galloway | 0 | 0 | 3079 | -2656.86 | 0 | 0 | 0 | 0 | 422.14 | 0 | 0 | 0 | 422.14 | 0 | 0 | 0 | 0 | 422.14 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
506213 | Glengap WTW - Ortho Bund Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-05-05 | 2020-07-03 | 2020-10-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19020.57 | 19020.57 | 0 | 0 | 0 | 19020.57 | 0 | 0 | 0 | 0 | 19020.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506212 | Glengap WTW - Sludge Tank Platform | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-05 | 2021-02-08 | 2021-04-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64285 | 64285 | 13051.24 | 0 | 0 | 77336.24 | 0 | 0 | 0 | 0 | 77336.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509986 | Glengap WTW - Various PLC Software Modifications | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-08 | 2021-05-21 | 2021-07-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234.86 | 234.86 | 0 | 0 | 0 | 234.86 | 0 | 0 | 0 | 0 | 234.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506337 | Glengavel DIR Leakage Monitoring Improvements | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS2 |  | 2020-09-24 | 2021-07-12 | 2021-12-30 | 2021-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28743 | 28743 | 43273.18 | 43273.18 | 60070.5409 | 72016.18 | 16797.3609 | 0 | 0 | 16797.3609 | 88813.5409 | 2601944.88 | [5 empty] | N | CS22 | 100%
500897 | Glenhead - Braeface Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2015-10-30 | 2024-08-26 | 2024-09-24 | 2025-02-28 |  | Falkirk | 0 | 0 | 10709 | 77549.04 | 113553.01 | 77712.74 | 0 | 27203.13 | 306726.92 | 1331736.01 | 0 | 0 | 1638462.93 | 0 | 0 | 0 | 0 | 1638462.93 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510077 | Glenlatterach CWT CCT Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-06-03 | 2023-11-21 | 2024-02-01 | 2024-11-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482.52 | 1482.52 | 690004.99 | 0 | 0 | 691487.5 | 0 | 0 | 0 | 0 | 691487.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
46254 | Glenlatterach Reservoir - Spillway Channel | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-22 | 2010-06-28 | 2010-11-09 | 2011-05-23 | 2011-05-23 | Moray | 118092.06 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 118143.06 | 0 | 0 | 0 | 0 | 118143.06 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401080 | Glenlatterach WSZ Low Pressure Enhancement WSZ000718 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-06-21 | 2012-06-13 | 2012-07-19 | 2014-01-16 | 2014-01-31 | Moray | 106158.78 | 0 | 1579.22 | -1361.79 | 0 | 0 | 0 | 0 | 217.43 | 0 | 0 | 0 | 106376.21 | 0 | 0 | 0 | 0 | 106376.21 | 0 | [5 empty] | N | CS1 | 100%
500917 | Glenlatterach WTW - SCADA-PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-10-30 | 2016-09-23 | 2016-11-28 | 2018-04-06 |  | Aberdeenshire | 0 | 0 | 59148 | 746516.61 | 657914.09 | -4990.56 | 21.53 | 0 | 1458609.67 | 0 | 0 | 0 | 1458609.67 | 0 | 0 | 0 | 0 | 1458609.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503589 | Glenlatterach WTW - Sewer Connection Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2020-03-04 | 2020-06-29 | 2020-08-24 | 2021-02-17 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 28410.06 | 355213.36 | 383623.43 | 0 | 0 | 0 | 383623.43 | 0 | 0 | 0 | 0 | 383623.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504767 | GLENLATTERACH WTW Commissioning of Sodium Hypochlorite Dosing Equipment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2020-02-20 | 2020-07-29 | 2021-05-10 | 2021-12-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1525.11 | 32722.89 | 34248 | 339397.87 | 0 | 0 | 373645.87 | 0 | 0 | 0 | 0 | 373645.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501217 | Glenlatterach WTW Manganese Removal | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS3 | 2016-03-29 | 2018-03-01 | 2018-03-27 | 2021-08-24 | 2022-09-23 | Aberdeenshire | 0 | 0 | 97779.24 | 503715.93 | 1031731.15 | 789985.27 | 3800709.41 | 2443068.4 | 8666989.4 | 935837 | 701877.75 | 1469039.6797 | 9602826.4 | 767161.9297 | 0 | 224293.4 | 991455.3297 | 10594281.7297 | 4931715.42 |  |  |  |  | 59511.7502 | Y | DW25P | 1.275% | DW3G | 6.225% | CM_WSNI | 25% | DW3C | 67.5% | [12 empty] | 1 | [48 empty] | 0
45598 | Glenlatterach WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-10-03 | 2014-03-21 | 2014-03-21 | Moray | 926687.37 | 0 | 3870.13 | -1265.25 | 0 | 0 | 0 | 0 | 2604.88 | 0 | 0 | 0 | 929292.25 | 0 | 0 | 0 | 0 | 929292.25 | 147783.71 |  |  |  |  | 30204 | N | CM_WSNI | 30% | DW1A | 70%
403831 | Glenloin Crescent (Succoth) ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-02-28 | 2022-01-17 | 2022-04-11 | 2022-09-09 |  | Argyll and Bute-Cowal & Bute | 4283.7 | 0 | 5779.93 | 2685.27 | 247.81 | 11924.41 | 15652.16 | 34835.73 | 71125.3 | 594771.27 | 0 | 0 | 670180.27 | 0 | 0 | 0 | 0 | 670180.27 | 0 | [5 empty] | N | SG1 | 100%
501668 | Glenochar to Gair trunk main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-11-01 | 2017-11-01 | 2017-11-01 | 2017-11-01 |  | South Lanarkshire | 0 | 0 | 0 | 4899.67 | 1915.04 | 0 | 0 | 0 | 6814.71 | 0 | 0 | 0 | 6814.71 | 0 | 0 | 0 | 0 | 6814.71 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500935 | Glensburgh Submarine PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-09-07 | 2018-03-29 | 2018-05-31 | 2018-11-30 |  | All West Unitary Authorities | 0 | 0 | 45520 | 55883 | 140910 | 441142 | 2912 | -14213.39 | 672153.61 | 0 | 0 | 0 | 672153.61 | 0 | 0 | 0 | 0 | 672153.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510106 | Glensherup Reservoir - MIOS Site Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-04-12 | 2021-07-02 | 2022-02-14 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415.17 | 415.17 | 12928.62 | 0 | 0 | 13343.79 | 0 | 0 | 0 | 0 | 13343.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508051 | Glensherup Reservoir MIOS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-09-28 | 2023-04-26 | 2023-07-25 | 2024-06-11 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3657 | 3657 | 396342.62 | 0 | 0 | 399999.62 | 0 | 0 | 0 | 0 | 399999.62 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501502 | GLENTROOL WWTW NX357781 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-10-03 | 2028-05-12 | 2028-09-08 | 2029-05-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 6130.29 | 41.59 | 0 | 0 | 0 | 6171.88 | 358770.12 | 0 | 0 | 364942 | 0 | 0 | 0 | 0 | 364942 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510120 | GLL Crosbie DSR BypassB | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2021-02-17 | 2021-03-01 | 2021-11-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60026.59 | 60026.59 | 190000 | 0 | 0 | 250026.59 | 0 | 0 | 0 | 0 | 250026.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510117 | GLL Simple Ground Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2021-01-08 | 2021-01-25 | 2022-05-13 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41026.59 | 41026.59 | 189000 | 0 | 0 | 230026.59 | 0 | 0 | 0 | 0 | 230026.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510027 | GLL South Moorhouse TWS 1 Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-12-16 | 2021-01-25 | 2022-04-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97827.59 | 97827.59 | 152198.62 | 0 | 0 | 250026.21 | 0 | 0 | 0 | 0 | 250026.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510098 | GLL SW Batch 1 Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-04-02 | 2021-05-10 | 2021-11-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12053.18 | 12053.18 | 135933.15 | 0 | 0 | 147986.33 | 0 | 0 | 0 | 0 | 147986.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510123 | GLL SW Batch 2 Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-06-21 | 2021-08-02 | 2022-04-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10026.59 | 10026.59 | 240000 | 0 | 0 | 250026.59 | 0 | 0 | 0 | 0 | 250026.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502352 | Golspie WTW Sludge Removal & Lagoon modifications | IR18 | Protecting and enhancing the environment | Sludge |  |  | Wastewater | SEPA | SWMD | Sludge | MS6 | 2016-11-07 | 2018-01-29 | 2018-03-23 | 2018-12-31 | 2019-01-31 | Highland | 0 | 0 | 0 | 6342.76 | 54845.1 | 173810.65 | 0 | 0.5 | 234999 | 0 | 0 | 0 | 234999 | 0 | 0 | 0 | 0 | 234999 | 1024271.42 | [5 empty] | Y | LA01 | 100% | [41 empty] | 1 | [25 empty] | 0
506398 | Gonfirth DSR 2 Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-07-22 | 2022-02-07 | 2022-07-08 | 2023-06-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302 | 2302 | 204023.97 | 0 | 0 | 206325.97 | 0 | 0 | 0 | 0 | 206325.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503134 | Gorbals High Reservoir | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-07-27 | 2022-04-08 | 2022-08-08 | 2023-03-20 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 42082.73 | 32233.74 | 5607.54 | 79924.01 | 230085.73 | 0 | 0 | 310009.74 | 0 | 0 | 0 | 0 | 310009.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
45517 | Gorbals Pollocktown TWP Refurb - TWP000109 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-19 | 2011-12-23 | 2011-12-19 |  | East Renfrewshire | 167067.99 | 0 | 688.99 | 0 | 0 | 0 | 0 | 0 | 688.99 | 0 | 0 | 0 | 167756.98 | 0 | 0 | 0 | 0 | 167756.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502712 | Gorbals Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2019-02-28 | 2019-02-28 | 2019-02-28 | 2019-01-21 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 17241.43 | 979.38 | 0 | 0 | 18220.81 | 0 | 0 | 0 | 18220.81 | 0 | 0 | 0 | 0 | 18220.81 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500251 | Gorbals SR & Thornliebank WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | WWINF | Water Non infrastructure | MS3 | 2015-06-08 | 2017-03-31 | 2017-03-31 | 2022-01-21 |  | East Renfrewshire | 0 | 0 | 22000 | 456411 | 740557.02 | 2687.98 | 0 | -24894 | 1196762 | 0 | 0 | 0 | 1196762 | 0 | 0 | 0 | 0 | 1196762 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
509410 | Gorebridge Wwtw - Interim SAF | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-02-27 | 2025-01-13 | 2025-06-23 | 2027-01-04 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199289.43 | 199289.43 | 150710.57 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000 | 122419.09 | [5 empty] | N | SG1 | 100%
502825 | Gorebridge WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-06-23 | 2023-10-11 | 2024-02-01 | 2025-01-21 |  | Midlothian | 0 | 0 | 0 | 0 | 61544.66 | 9720.66 | 80401.09 | 33586.61 | 185253.01 | 1814747 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 122419.09 | [5 empty] | N | SG1 | 100%
504492 | Gorebridge WWTW (South) Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-04 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | -92764.33 | 7235.67 | 93345.71 | 0 | 0 | 100581.38 | 0 | 0 | 0 | 0 | 100581.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504606 | Gorthlec Mains rehab | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-01-14 | 2020-09-21 | 2020-12-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5623.47 | 40327.79 | 45951.26 | 0 | 0 | 0 | 45951.26 | 0 | 0 | 0 | 0 | 45951.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403576 | Gourdie WSZ000731 Low Pressure Enhancement | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-09-25 | 2014-02-04 | 2014-02-10 | 2014-07-17 | 2014-03-26 | Angus | 86889 | 0 | 0 | -5939.27 | 0 | 0 | 0 | 0 | -5939.27 | 0 | 0 | 0 | 80949.73 | 0 | 0 | 0 | 0 | 80949.73 | 0 | [5 empty] | N | CS1 | 100%
45332 | Govig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-07-26 | 2012-08-08 | 2012-08-08 | 2011-03-14 | Na H-Eileanan an Iar | 71484.17 | 0 | 1517.95 | 0 | 0 | 0 | 0 | 0 | 1517.95 | 0 | 0 | 0 | 73002.12 | 0 | 0 | 0 | 0 | 73002.12 | 0 | [5 empty] | N | DW13 | 100%
506252 | Gowanbank TWP - Replacement No 4 Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-04-22 | 2021-04-06 | 2021-11-16 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78740 | 78740 | 61634.12 | 0 | 0 | 140374.12 | 0 | 0 | 0 | 0 | 140374.12 | 119022.58 | [5 empty] | N | WSNI | 100%
511059 | Grampian Reservoirs - Vegetation Clearance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-03-03 | 2021-06-23 | 2022-02-03 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4182.13 | 4182.13 | 7817.87 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 12000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402480 | Grangemouth Integrated Catchment Study (Dalderse Kinneil Kerse and BoNess Sewer Catchment Areas) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-01-30 | 2013-01-30 | 2015-03-26 | 2015-04-01 | Scottish Water Wide | 1350922 | 0 | 396328.45 | 32046.68 | 0 | 0 | 0 | 0 | 428375.13 | 0 | 0 | 0 | 1779297.13 | 0 | 0 | 0 | 0 | 1779297.13 | 0 | [5 empty] | N | CS16S | 100%
506044 | Grangemouth Rising Main to Kinneil Kerse Burst | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-04-03 | 2020-05-20 | 2020-10-30 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183578.83 | 183578.83 | 0 | 0 | 0 | 183578.83 | 0 | 0 | 0 | 0 | 183578.83 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504175 | Grangepans WWPS - Major Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-12 |  | 2021-09-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5771.03 | 97712.97 | 103484 | 320127.58 | 0 | 0 | 423611.58 | 0 | 0 | 0 | 0 | 423611.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512083 | Grangepans WWPS - Major Refurbishment. | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414000 | 0 | 0 | 414000 | 0 | 0 | 0 | 0 | 414000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508862 | Greenbank DSR - Embankment Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-14 | 2021-04-22 | 2021-12-03 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4404 | 4404 | 15595.53 | 0 | 0 | 19999.53 | 0 | 0 | 0 | 0 | 19999.53 | 119022.58 | [5 empty] | N | WSNI | 100%
501265 | Greengairs STW Overland Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-02-10 | 2017-10-24 | 2018-01-08 | 2018-05-24 |  | South Lanarkshire | 0 | 0 | 3595 | 76405 | 221039 | 36680 | 781 | 5253.17 | 343753.17 | 0 | 0 | 0 | 343753.17 | 0 | 0 | 0 | 0 | 343753.17 | 209381.79 | [5 empty] | N | CM_WWI | 100%
30316 | Greengairs STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2010-09-20 | 2011-02-01 | 2012-03-16 | 2012-03-26 | North Lanarkshire | 1400389.36 | 0 | 150.28 | 0 | 0 | 0 | 0 | 0 | 150.28 | 0 | 0 | 0 | 1400539.64 | 0 | 0 | 0 | 0 | 1400539.64 | 119362.42 | [5 empty] | N | EC10A | 46.21% | CM_WWNI | 53.79%
501113 | Greenholm Street Cumnock Stabilise River Bank | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-10-21 | 2018-07-31 | 2018-08-28 | 2018-11-29 |  | East Ayrshire | 0 | 0 | 11290 | 8843 | 142631 | 430250 | 3231.07 | -3644.84 | 592600.23 | 0 | 0 | 0 | 592600.23 | 0 | 0 | 0 | 0 | 592600.23 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503226 | Greenlaw WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-14 | 2029-06-11 | 2030-06-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 83505.79 | 3715.09 | 0.12 | 87221 | 0 | 0 | 0 | 87221 | 0 | 0 | 0 | 0 | 87221 | 122419.09 | [5 empty] | N | SG1 | 100%
501671 | Greenock No.8-Oveton Basin (FRMA (EN)) | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water |  | SWMD | Flood Risk Management Act | MS6 | 2018-07-12 | 2019-06-17 | 2019-08-12 | 2020-02-27 | 2021-04-01 | Inverclyde | 0 | 0 | 0 | 0 | 6782.14 | 24976.65 | 278922.6 | -17592.42 | 293088.96 | 0 | 0 | 0 | 293088.96 | 0 | 0 | 0 | 0 | 293088.96 | 980126.37 | [5 empty] | N | WR6 | 100%
502903 | Greenock RSZ - DW5 Intervention - Phase1 | IR18 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS6 | 2017-09-27 | 2018-04-30 | 2018-04-30 | 2019-09-30 | 2021-03-31 | Inverclyde | 0 | 0 | 0 | 0 | 82141 | 461826.18 | 36275.6 | 3534.97 | 583777.75 | 3723.03 | 0 | 0 | 587500.78 | 0 | 1026.9079 | 0 | 1026.9079 | 588527.6879 | 1099483.85 | [5 empty] | Y | DW5FS | 18.88% | DW5MR | 81.12% | [17 empty] | 1 | [47 empty] | 0
502606 | Greenock RSZ - DW5 Interventions Phase 2 | IR18 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS4 | 2018-06-28 | 2019-06-12 | 2019-06-17 | 2020-02-05 | 2021-05-10 | Inverclyde | 0 | 0 | 0 | 46297 | 236920.4 | 63744.91 | 446772.57 | 25057.22 | 818792.09 | 6515.6 | 72540.2152 | 72540.2152 | 825307.69 | 0 | 66024.6152 | 0.000552 | 66024.6158 | 891332.3058 | 3810169.77 | [5 empty] | N | DW5MR | 100%
501574 | Greenock WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS4 | 2017-03-31 | 2019-06-27 | 2019-06-27 | 2020-09-24 | 2021-04-29 | Inverclyde | 0 | 0 | 5847 | 10278.37 | 728.35 | 907.45 | -692.08 | 0 | 17069.08 | 0 | 0 | 0 | 17069.08 | 0 | 0 | 1365.5264 | 1365.5264 | 18434.6064 | 249310.15 | [5 empty] | N | DW25T | 100%
500660 | Greenock WTW Ortho | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2015-10-30 | 2017-05-16 | 2017-07-12 | 2018-12-11 |  | Renfrewshire | 0 | 0 | 29246 | 125279.79 | 791345.19 | 611519.92 | 9322.28 | -5436.78 | 1561276.4 | 0 | 0 | 0 | 1561276.4 | 0 | 0 | 0 | 0 | 1561276.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503533 | Greenock WTW Sludge Press & Conveyor Refurbishment-Replacement H&S Escalation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-09-04 | 2020-09-04 | 2020-09-04 | 2020-09-02 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 10567.03 | 12324.3 | -5973.23 | 16918.11 | 0 | 0 | 0 | 16918.11 | 0 | 0 | 0 | 0 | 16918.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502972 | Greenock WTW Sludge Presses & Conveyor Refurbishment-Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-08-06 | 2022-04-08 | 2022-08-09 | 2023-03-21 |  | Inverclyde | 0 | 0 | 0 | 0 | 16358.8 | 5717.55 | 14320.12 | -3303.46 | 33093 | 266906.45 | 0 | 0 | 299999.45 | 0 | 0 | 0 | 0 | 299999.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511020 | Greenside Reservoir Access | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-02-25 | 2021-08-13 | 2022-03-28 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 2000 | 0 | 0 | 2130.84 | 0 | 0 | 0 | 0 | 2130.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401346 | Greentoft WSZ Low Pressure Enhancement WSZ000751 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-12-12 | 2013-01-21 | 2013-03-01 | 2013-03-15 | Orkney Islands | 15500 | 0 | -561.65 | 0 | 0 | 0 | 0 | 0 | -561.65 | 0 | 0 | 0 | 14938.35 | 0 | 0 | 0 | 0 | 14938.35 | 0 | [5 empty] | N | CS1 | 100%
45798 | Gregory Place Lossie SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2013-01-23 | 2013-01-23 | 2013-01-23 | 2013-01-23 | Scottish Water Wide | 17007.91 | 0 | 3891.32 | 0 | 0 | 0 | 0 | 0 | 3891.32 | 0 | 0 | 0 | 20899.23 | 0 | 0 | 0 | 0 | 20899.23 | 28761.13 | [5 empty] | N | WQ01C | 100%
500203 | Gremista WWPS 1995 HU463429 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-03-24 | 2017-03-30 | 2017-06-07 | 2018-10-18 |  | Shetland Islands | 0 | 0 | 88503 | 114368 | 774720 | 97892 | 791 | -14419.3 | 1061854.7 | 0 | 0 | 0 | 1061854.7 | 0 | 0 | 0 | 0 | 1061854.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500136 | Gretna DOA (DOA000114) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-03-29 | 2016-08-01 | 2018-12-11 | 2019-03-29 | Dumfries and Galloway | 0 | 0 | 24619 | 15708.33 | 67359 | 28500 | -8870.29 | 0 | 127316.04 | 0 | 0 | 0 | 127316.04 | 0 | 0 | 0 | 0 | 127316.04 | 97210.51 | [5 empty] | N | CS16D | 22% | EC01D | 38% | EC01G | 40%
400674 | Gretna Water Supply - Phase 1 Intervention | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-01-21 | 2009-10-30 | 2009-10-30 | 2011-06-29 | 2013-06-26 | Dumfries and Galloway | 830627.5 | 0 | -1223.88 | 0 | 0 | 0 | 0 | 0 | -1223.88 | 0 | 0 | 0 | 829403.62 | 0 | 0 | 0 | 0 | 829403.62 | 473527.16 | [5 empty] | N | CS1 | 15.35% | WG5 | 84.65%
503455 | Gretna WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-05-01 | 2020-05-01 | 2027-04-01 | 2020-06-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 59441.86 | 17391.48 | 1822.65 | 78655.98 | 0 | 0 | 0 | 78655.98 | 0 | 0 | 0 | 0 | 78655.98 | 122419.09 | [5 empty] | N | SG1 | 100%
507922 | Greyrigg DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-07-01 | 2023-08-18 | 2023-11-21 | 2024-10-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 897.16 | 897.16 | 299073.93 | 0 | 0 | 299971.09 | 0 | 0 | 0 | 0 | 299971.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502548 | Ground Mics and Correlators - FOP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-10-06 |  | Scottish Water Wide | 0 | 0 | 0 | 93660 | 3752.29 | 0 | 0 | 0 | 97412.29 | 0 | 0 | 0 | 97412.29 | 0 | 0 | 0 | 0 | 97412.29 | 119022.58 | [5 empty] | N | CM_M&G | 100%
402625 | Growth costs for Legacy CC projects | Q&S4 | Supporting economic development | RCC |  |  | General |  | SWD | RCC | MS7 | 2012-03-14 | 2013-02-06 | 2013-02-06 | 2015-10-19 | 2016-07-11 | Scottish Water Wide | 3793615.62 | 0 | 0 | 411.54 | 0 | 0 | 0 | 0 | 411.54 | 0 | 0 | 0 | 3794027.16 | 0 | 0 | 0 | 0 | 3794027.16 | 0 | [5 empty] | N | SG2 | 50% | WG2 | 50%
511528 | Gryfe No.1 Proactive Maintenance (MA004) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 |  | 2021-11-08 | 2022-01-28 | 2022-09-12 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000.02 | 0 | 0 | 25000.02 | 0 | 0 | 0 | 0 | 25000.02 | 0 | [5 empty] | N | SR21_WA | 100%
511530 | Gryfe No.2 Proactive Maintenance (MA004) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 |  | 2021-10-25 | 2022-01-14 | 2022-08-29 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | [5 empty] | N | SR21_WA | 100%
402180 | Gryfe No1 Drainage - Pitching Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-03-21 | 2012-06-18 | 2014-02-24 | 2014-02-24 | North Ayrshire | 124832.25 | 0 | 145.32 | 0 | 0 | 0 | 0 | 0 | 145.32 | 0 | 0 | 0 | 124977.57 | 0 | 0 | 0 | 0 | 124977.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402181 | Gryfe No2 Remedial Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-12-03 | 2013-07-15 | 2014-10-27 | 2014-10-28 | North Ayrshire | 446170.39 | 0 | -1908.8 | 796.86 | 0 | 0 | 0 | 0 | -1111.94 | 0 | 0 | 0 | 445058.45 | 0 | 0 | 0 | 0 | 445058.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506599 | Gryffe Valley Trunk Sewer - Inspection | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-05-20 | 2020-08-12 | 2021-01-18 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23599 | 23599 | 0 | 0 | 0 | 23599 | 0 | 0 | 0 | 0 | 23599 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501651 | GSMS Dalmarnock to Daldowie | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-22 | 2018-02-23 | 2018-03-19 | 2018-11-23 |  | Glasgow City | 0 | 0 | 327.1 | 12345.8 | 23355.34 | 246058.52 | -30051.56 | 0 | 252035.2 | 0 | 0 | 0 | 252035.2 | 0 | 0 | 0 | 0 | 252035.2 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501705 | GSMS Dalmuir to Shieldhall Valve Chamber Inspections | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-07-19 | 2021-06-29 | 2021-08-26 | 2021-11-25 |  | Glasgow City | 0 | 0 | 0 | 2366.16 | 30.82 | 147.87 | 6759.69 | 6643.46 | 15948 | 36379 | 0 | 0 | 52327 | 0 | 0 | 0 | 0 | 52327 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501706 | GSMS Laighpark to Shieldhall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2016-11-07 | 2021-08-16 | 2021-09-14 | 2022-03-17 |  | Renfrewshire | 0 | 0 | 0 | 2913.38 | 442.76 | 340.64 | 4248.42 | 2705.8 | 10651 | 42259.17 | 0 | 0 | 52910.17 | 0 | 0 | 0 | 0 | 52910.17 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403428 | GSS Implementation Support (UIDs & Flooding) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2013-03-26 | 2013-03-26 | 2013-04-03 | 2020-12-15 | 2021-02-01 | Glasgow City | 228490.56 | 0 | 95158.44 | 95378.7 | 29822 | 51150.31 | 0 | -26716.45 | 244792.99 | 0 | 0 | 0 | 473283.55 | 0 | 0 | 0 | 0 | 473283.55 | 0 | [5 empty] | N | EC01B | 100%
46416 | GSS Small Miscellaneous Projects Purchases | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2009-07-21 | 2012-12-07 | 2012-12-24 | 2018-06-22 | 2011-03-14 | Glasgow City | 110271.89 | 0 | 16340.24 | 0 | 0 | 0 | 0 | 0 | 16340.24 | 0 | 0 | 0 | 126612.13 | 0 | 0 | 0 | 0 | 126612.13 | 86283.39 | [5 empty] | N | EC04C | 0.976% | EC01D | 33.13% | EC10E | 65.89%
503283 | Guardbridge STW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-03-10 | 2025-01-03 | 2025-04-08 | 2026-05-13 |  | Fife | 0 | 0 | 0 | 0 | 0 | 71970.39 | 67103.55 | -20818.94 | 118255 | 1961186.98 | 0 | 0 | 2079441.98 | 0 | 0 | 0 | 0 | 2079441.98 | 122419.09 | [5 empty] | N | SG1 | 100%
404091 | Guardbridge Water Mains Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-12-15 | 2016-12-15 | Fife | 0 | 0 | 0 | 171778.98 | 0 | 0 | 0 | 0 | 171778.98 | 0 | 0 | 0 | 171778.98 | 0 | 0 | 0 | 0 | 171778.98 | 0 | [5 empty] | N | WG5 | 100%
502711 | Guershader Stornoway Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-10-20 | 2018-11-29 | 2019-03-11 | 2019-09-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 19272 | 176055 | 61273 | 1039.94 | 257639.94 | 400 | 0 | 0 | 258039.94 | 0 | 0 | 0 | 0 | 258039.94 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402143 | Guildtown WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-05-27 | 2015-03-23 | 2015-07-13 | 2016-09-27 | 2016-09-27 | Perth and Kinross | 335118 | 0 | 1555475 | 249137.56 | 100000 | 8872.35 | 0 | 0 | 1913484.91 | 0 | 0 | 0 | 2248602.91 | 0 | 0 | 0 | 0 | 2248602.91 | 0 | [5 empty] | N | SG1 | 100%
503064 | Gulberwick SPS - Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2020-09-30 | 2022-12-27 | 2023-03-23 | 2024-05-14 |  | Shetland Islands | 0 | 0 | 0 | 0 | 31039.13 | 3657.63 | 36197.95 | 102213.3 | 173108 | 1684735.13 | 0 | 0 | 1857843.13 | 0 | 0 | 0 | 0 | 1857843.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502290 | Gullane WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | East Lothian | 0 | 0 | 0 | 36444.74 | 874.75 | 0 | 0 | 0 | 37319.49 | 0 | 0 | 0 | 37319.49 | 0 | 0 | 0 | 0 | 37319.49 | 122419.09 | [5 empty] | N | SG1 | 100%
400920 | GWS000367 - Ancum Loch GWS (North Ronaldsay) - Construct New Borehole | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-19 | 2013-02-26 | 2013-06-24 | 2017-02-16 |  | Orkney Islands | 388207 | 0 | 2624 | 40096.64 | 11000 | 0 | -6018.84 | 0 | 47701.8 | 0 | 0 | 0 | 435908.8 | 0 | 0 | 0 | 0 | 435908.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502790 | Haddington 15 Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-12-15 | 2022-10-18 | 2022-12-21 | 2023-07-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 31363.42 | 30636.58 | 110.82 | -38920.7 | 23190.12 | 2846514.9 | 0 | 0 | 2869705.02 | 0 | 0 | 0 | 0 | 2869705.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500149 | Haddington DOA (DOA000513) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-12 | 2017-08-31 | 2017-09-30 | East Lothian | 0 | 0 | 56880 | 118965 | 36303 | -20580.98 | 0 | 0 | 191567.02 | 0 | 0 | 0 | 191567.02 | 0 | 0 | 0 | 0 | 191567.02 | 72047.27 | [5 empty] | Y | CS11 | 50% | CS16D | 50% | [37 empty] | 1 | [27 empty] | 0
502418 | Haddington Strategic Drainage Study | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS5 | 2017-03-30 | 2017-03-30 | 2018-09-11 | 2018-11-26 | 2018-11-26 | East Lothian | 0 | 0 | 0 | 0 | 31532.71 | 0 | 0 | -31477.61 | 55.1 | 0 | 0 | 0 | 55.1 | 0 | 0 | 0 | 0 | 55.1 | 122419.09 | [5 empty] | N | SG1 | 100%
501152 | Haddington STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS4 | 2016-03-02 | 2018-09-27 | 2018-11-26 | 2021-03-31 |  | East Lothian | 0 | 0 | 3848.36 | 202439.78 | 172677.93 | 625447.04 | 745191.17 | 93311.72 | 1842916 | 54826.6 | 0 | 0 | 1897742.6 | 0 | 0 | 189774.4 | 189774.4 | 2087517 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
30321 | Haddington STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-08-08 | 2010-06-28 | 2011-03-03 | 2012-09-27 | 2012-11-23 | East Lothian | 1501900.87 | 0 | 1265.43 | 0 | 0 | 0 | 0 | 0 | 1265.43 | 0 | 0 | 0 | 1503166.3 | 0 | 0 | 0 | 0 | 1503166.3 | 119362.42 | [5 empty] | N | CM_WWNI | 20% | EC01A | 80%
502956 | Haddington WWTW - Demolish inlet building | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-11-20 | 2017-11-20 | 2017-12-11 | 2018-05-28 |  | East Lothian | 0 | 0 | 0 | 0 | 350476.64 | 95710.36 | -8000 | 0 | 438187 | 0 | 0 | 0 | 438187 | 0 | 0 | 0 | 0 | 438187 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403968 | Haddington WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS4 | 2016-07-19 | 2018-09-26 | 2018-11-26 | 2021-03-31 |  | East Lothian | 14875.16 | 0 | 14622.85 | 230898.42 | 165329.94 | 669050.65 | 1262901.32 | 231973.66 | 2574776.84 | 86132.43 | 0 | 0 | 2675784.43 | 0 | 0 | 272227.57 | 272227.57 | 2948012 | 0 | [5 empty] | N | SG1 | 100%
501798 | Haddington WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-06-29 | 2020-03-31 | 2020-08-31 | 2021-07-16 |  | East Lothian | 0 | 0 | 0 | 1607.44 | 5297.36 | 0 | 15942.2 | 59775.19 | 82622.19 | 74464.33 | 0 | 0 | 157086.52 | 0 | 0 | 0 | 0 | 157086.52 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501591 | Halkirk - surface water removal and grade 5 sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2016-05-10 | 2021-10-25 | 2022-01-10 | 2022-06-02 |  | Highland | 0 | 0 | 0 | 27076 | 17694 | 0 | -17334.21 | 0.01 | 27435.8 | 57646.2 | 0 | 0 | 85082 | 0 | 0 | 0 | 0 | 85082 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500137 | Halkirk DOA (DOA000726) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-02-26 | 2019-06-27 | Highland | 0 | 0 | 10823 | 14030 | 16982 | 52826.84 | 8646.08 | 0 | 103307.92 | 0 | 0 | 0 | 103307.92 | 0 | 0 | 0 | 0 | 103307.92 | 36588.55 | [5 empty] | N | EC01G | 15.73% | CS16D | 37.26% | EC01D | 47.01%
505208 | Hamilton Drive SPS Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2020-02-28 | 2022-01-31 | 2022-06-01 | 2022-11-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160.49 | 2160.49 | 248000.02 | 0 | 0 | 250160.51 | 0 | 0 | 0 | 0 | 250160.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
32104 | Hamilton STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-10-01 | 2010-08-23 | 2010-09-27 | 2012-02-06 | 2012-03-16 | South Lanarkshire | 3975719.73 | 0 | 5339.68 | -5339.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3975719.73 | 0 | 0 | 0 | 0 | 3975719.73 | 0 | [5 empty] | N | EC01A | 22.39% | CM_WWNI | 77.61%
501164 | Hamilton Upper Muir SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2016-02-22 | 2017-09-04 | 2017-12-04 | 2018-09-27 |  | South Lanarkshire | 0 | 0 | 602.52 | 89528.48 | 540862 | 29559.65 | 0.35 | -10979.58 | 649573.42 | 0 | 0 | 0 | 649573.42 | 0 | 0 | 0 | 0 | 649573.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502232 | Hamilton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-10-31 | 2018-10-31 | 2018-12-17 | 2019-08-28 | 2019-08-28 | South Lanarkshire | 0 | 0 | 0 | 21336.24 | 14880.39 | 73042.18 | 245316 | 107.65 | 354682.46 | 0 | 0 | 0 | 354682.46 | 0 | 0 | 0 | 0 | 354682.46 | 122419.09 | [5 empty] | N | SG1 | 100%
501635 | Happendon - Camps TM Douglas Water Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-30 | 2017-08-22 | 2017-08-24 | 2021-06-30 |  | South Lanarkshire | 0 | 0 | 3925 | 777237.72 | 430095.63 | 3122667.37 | 3675553.13 | 1818649.15 | 9828128 | 150382.25 | 0 | 0 | 9978510.25 | 0 | 0 | 16489.75 | 16489.75 | 9995000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508058 | Harelaw (Paisley) Vegetation Clearance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-19 | 2021-09-09 | 2022-04-22 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3389 | 3389 | 6610.89 | 0 | 0 | 9999.89 | 0 | 0 | 0 | 0 | 9999.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507901 | Harelaw Reservoir Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-08-19 | 2021-03-23 | 2021-11-03 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6426.76 | 6426.76 | 69225.44 | 0 | 0 | 75652.2 | 0 | 0 | 0 | 0 | 75652.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502275 | Harperleas Reservoir IOS and Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2018-06-29 | 2019-04-30 | 2019-05-27 | 2019-09-27 |  | Fife | 0 | 0 | 0 | 8571.33 | 2496.77 | 10046.78 | 113713.24 | 0 | 134828.12 | 0 | 0 | 0 | 134828.12 | 0 | 0 | 0 | 0 | 134828.12 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46156 | Harthill STW Refurb - STW000361 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2010-11-15 | 2011-01-19 | 2012-03-14 |  | North Lanarkshire | 914721.47 | 0 | 3633.3 | -3633.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 914721.47 | 0 | 0 | 0 | 0 | 914721.47 | 0 | [5 empty] | N | CM_WWNI | 100%
505199 | Harvesters SPS - Assess options to bring station back into operation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-11-02 | 2023-06-01 | 2023-08-30 | 2024-07-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34193.24 | 34193.24 | 415806.76 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 450000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500820 | Hatton - Tay Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-21 | 2017-01-31 | 2017-01-31 | 2016-12-16 | 2017-01-31 | Dundee City | 0 | 0 | 5211.19 | 533.7 | -92.87 | 0 | 0 | 0 | 5652.02 | 0 | 0 | 0 | 5652.02 | 0 | 0 | 0 | 0 | 5652.02 | 106252.93 | [5 empty] | N | FL_DD | 100%
403005 | Hatton of Cruden Bridgend Septic Tank - Soakaway | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-10-29 | 2013-03-28 | 2013-04-24 | 2013-06-13 |  | Aberdeenshire | 40227.43 | 0 | -927.36 | 0 | 0 | 0 | 0 | 0 | -927.36 | 0 | 0 | 0 | 39300.07 | 0 | 0 | 0 | 0 | 39300.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500235 | Hatton of Cruden WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS3 | 2019-03-25 | 2020-09-24 | 2021-02-22 | 2022-01-31 |  | Aberdeenshire | 0 | 0 | 63480.51 | 41516.5 | 23116.55 | 23988.71 | 285667.39 | 827945.9 | 1265715.55 | 1300129.12 | 0 | 0 | 2565844.67 | 0 | 0 | 91199.33 | 91199.33 | 2657044 | 122419.09 | [5 empty] | N | SG1 | 100%
502821 | Hatton of Fintray WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-04-10 | 2018-04-10 | 2018-04-10 | 2018-04-10 | 2018-04-10 | Aberdeenshire | 0 | 0 | 0 | 0 | 63695.07 | 120.3 | 0 | 0 | 63815.37 | 0 | 0 | 0 | 63815.37 | 0 | 0 | 0 | 0 | 63815.37 | 122419.09 | [5 empty] | N | SG1 | 100%
34798 | Hawick - Alemoor WRZ-WFD Compliance | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-19 | 2011-03-21 | 2011-03-21 | 2011-03-31 | 2011-03-31 | Scottish Borders | 192450 | 0 | 7550 | -1747.69 | 0 | 0 | 0 | 0 | 5802.31 | 0 | 0 | 0 | 198252.31 | 0 | 0 | 0 | 0 | 198252.31 | 28761.13 | [5 empty] | N | DW7 | 100%
501945 | Hawick Duke Street Syphon | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-06-03 | 2016-08-10 | 2016-08-10 | 2017-02-09 |  | Scottish Borders | 0 | 0 | 0 | 1405606.4 | 419775.19 | -16432.47 | 100.23 | 0 | 1809049.35 | 0 | 0 | 0 | 1809049.35 | 0 | 0 | 0 | 0 | 1809049.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400065 | Hawick STC Refurb000090 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-14 | 2011-05-03 | 2011-08-01 | 2016-12-15 |  | Scottish Borders | 1878109.62 | 0 | 101674.99 | -9730.27 | -31.19 | 98.34 | 0 | 0 | 92011.87 | 0 | 0 | 0 | 1970121.49 | 0 | 0 | 0 | 0 | 1970121.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
30322 | Hawick STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-29 | 2011-05-05 | 2011-08-01 | 2015-11-03 | 2015-05-29 | Scottish Borders | 2352426.24 | 0 | 77936.54 | -2507.44 | -431.83 | 0 | 0 | 0 | 74997.27 | 0 | 0 | 0 | 2427423.51 | 0 | 0 | 0 | 0 | 2427423.51 | 119362.42 | [5 empty] | N | CM_WWNI | 50% | EC01A | 50%
500950 | Health & Safety - Fitting of Machine Guards | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-09-10 | 2015-09-10 | 2015-09-10 | 2018-10-04 |  | Scottish Water Wide | 0 | 0 | 73616.97 | 6781.74 | 62.39 | 0 | 0 | 0 | 80461.1 | 0 | 0 | 0 | 80461.1 | 0 | 0 | 0 | 0 | 80461.1 | 328404.37 | [5 empty] | N | CM_M&G | 100%
403718 | Health and Safety at Reservoirs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-27 | 2014-05-29 | 2014-06-03 | 2016-03-23 |  | Scottish Water Wide | 2127956 | 0 | 82000 | -8500.44 | 1484.97 | 0 | 0 | 0 | 74984.53 | 0 | 0 | 0 | 2202940.53 | 0 | 0 | 0 | 0 | 2202940.53 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400999 | Heldale Loch RWP Replace Raw Water Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-04-21 | 2012-06-07 | 2013-01-08 | 2013-12-10 |  | Orkney Islands | 331691 | 0 | -373.11 | -88.68 | 0 | 0 | 0 | 0 | -461.79 | 0 | 0 | 0 | 331229.21 | 0 | 0 | 0 | 0 | 331229.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403787 | Helensburgh No.1 & 2 IoS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-05-19 | 2015-06-12 | 2015-06-15 | 2015-06-15 |  | Argyll and Bute-Cowal & Bute | 6220 | 0 | -1593.3 | 0 | 0 | 0 | 0 | 0 | -1593.3 | 0 | 0 | 0 | 4626.7 | 0 | 0 | 0 | 0 | 4626.7 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505788 | Helensburgh No1 Spillway Leakage works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-03-31 | 2020-08-07 | 2020-12-21 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 65000 | 0 | 0 | 0 | 65000 | 0 | 0 | 0 | 0 | 65000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501167 | Helensburgh WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS1 | 2016-07-20 | 2027-04-15 | 2027-04-15 | 2028-09-14 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 53942.64 | 312644.74 | -19067.38 | 0 | -34762.52 | 312757.48 | 2616790.52 | 0 | 0 | 2929548 | 0 | 0 | 0 | 0 | 2929548 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506992 | Helensburgh WWTW - Extensive Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-09-22 | 2021-09-02 | 2022-05-20 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29606 | 29606 | 105393.86 | 0 | 0 | 134999.86 | 0 | 0 | 0 | 0 | 134999.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507311 | Helensburgh WWTW - Poly System Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2020-06-30 | 2020-07-24 | 2021-11-15 | 2022-05-12 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103362 | 103362 | 280637.6 | 0 | 0 | 383999.6 | 0 | 0 | 0 | 0 | 383999.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503932 | Helensburgh WwTW - Replace 2 Washpactor Units | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-05-05 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWNI | 100%
504972 | Helenton Farm Symington - Scour Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-02-17 |  | 2020-11-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 102946.87 | 189975.13 | 292922 | 13497.23 | 0 | 0 | 306419.23 | 0 | 0 | 0 | 0 | 306419.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45039 | Heriot WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-09-28 | 2012-07-09 | 2013-03-28 | 2013-11-21 | Scottish Borders | 933948.27 | 0 | -496.53 | 0 | 0 | 0 | 0 | 0 | -496.53 | 0 | 0 | 0 | 933451.74 | 0 | 0 | 0 | 0 | 933451.74 | 28761.13 | [5 empty] | N | DW23 | 100%
502361 | Herrick WTW - RGF Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-09-14 | 2020-09-18 | 2027-04-01 | 2016-12-20 |  | Aberdeenshire | 0 | 0 | 0 | 40186.05 | 0 | 0 | 0 | 0 | 40186.05 | 0 | 0 | 0 | 40186.05 | 0 | 0 | 0 | 0 | 40186.05 | 238045.17 | [5 empty] | N | CM_WSI | 12.5% | CM_WSNI | 87.5%
501110 | Herricks WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-02 | 2028-11-23 | 2029-03-28 | 2030-06-19 |  | Aberdeenshire | 0 | 0 | 23339.61 | 120920.78 | 11583.01 | 41175.22 | 1981.38 | -317.56 | 198682.44 | 2999982.07 | 0 | 0 | 3198664.51 | 0 | 0 | 0 | 0 | 3198664.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503422 | Herricks WTW - Interim THM and Cryptosporidium measures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2018-10-31 | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | Moray | 0 | 0 | 0 | 0 | 0 | 39230.01 | 65485.76 | 0 | 104715.77 | 0 | 0 | 0 | 104715.77 | 0 | 0 | 0 | 0 | 104715.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501233 | Herricks WTW - QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2018-03-22 | 2020-02-28 | 2020-02-28 | 2021-04-30 | 2021-07-23 | Aberdeenshire | 0 | 0 | 2424.81 | 31934.21 | 66689.69 | 71488.29 | 303121 | 733657 | 1209315 | 168332 | 168332 | 378872.6758 | 1377647 | 210540.6758 | 0 | 0 | 210540.6758 | 1588187.6758 | 3547.71 | [5 empty] | N | DW25D | 33% | DW25P | 67%
503590 | High Boxton Pipe and Pump Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-09-30 | 2019-09-30 | 2019-12-11 | 2021-11-11 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 217700.82 | 190742.63 | 408443.45 | 176232.12 | 0 | 0 | 584675.57 | 0 | 0 | 0 | 0 | 584675.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402993 | High Street Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-02 | 2013-03-15 | 2013-06-03 | 2013-10-25 | 2013-10-25 | Glasgow City | 52853 | 0 | -957.31 | 0 | 0 | 0 | 0 | 0 | -957.31 | 0 | 0 | 0 | 51895.69 | 0 | 0 | 0 | 0 | 51895.69 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
403436 | High Street Strichen Fraserburgh | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-04-16 | 2014-08-21 | 2014-08-28 | 2014-10-28 | 2014-10-28 | Aberdeenshire | 74956 | 0 | -1393.93 | 599.83 | -276.31 | 0 | 0 | 0 | -1070.41 | 0 | 0 | 0 | 73885.59 | 0 | 0 | 0 | 0 | 73885.59 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
402529 | High Voltage Switchgear Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-05-14 | 2012-12-20 | 2013-04-25 | 2014-07-31 |  | All South Unitary Authorities | 549729 | 0 | 0 | -25780.55 | 0 | 0 | 0 | 0 | -25780.55 | 0 | 0 | 0 | 523948.45 | 0 | 0 | 0 | 0 | 523948.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500920 | Highland Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2018-02-23 | 2018-02-01 | 2018-02-01 | 2018-02-01 | Highland | 0 | 0 | 4904.29 | 1471.49 | -4483.58 | 0 | 0 | 0 | 1892.2 | 0 | 0 | 0 | 1892.2 | 0 | 0 | 0 | 0 | 1892.2 | 106252.93 | [5 empty] | N | FL_DD | 100%
503292 | Highland PFI Transition Plan | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2018-08-23 | 2022-08-11 | 2022-08-22 | 2023-09-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 10713.01 | 28011.36 | 20497.64 | 59222 | 840777.86 | 0 | 0 | 899999.86 | 0 | 0 | 0 | 0 | 899999.86 | 390584.36 | [5 empty] | N | CM_WWI | 20% | CM_WWNI | 80%
500865 | Hillend RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-09-06 | 2018-09-04 | 2018-11-29 | 2019-09-30 | 2020-01-31 | City of Edinburgh | 0 | 0 | 5818.45 | 8144.52 | 36650.36 | 95442.32 | 44550.87 | 800.06 | 191406.58 | 0 | 0 | 0 | 191406.58 | 0 | 0 | 0 | 0 | 191406.58 | 396328.86 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 48.75 | [43 empty] | 0
501733 | Hillfarm DSR Mainout | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2028-07-31 | 2029-05-16 | 2029-09-19 | 2030-01-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99999.97 | 0 | 0 | 99999.97 | 0 | 0 | 0 | 0 | 99999.97 | 4989107.96 | [5 empty] | N | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 28.57% | CM_WSI | 47.62%
500937 | Hillfoot SPS RM Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-09-02 | 2017-01-19 | 2017-02-27 | 2017-05-31 |  | East Dunbartonshire | 0 | 0 | 12500 | 104277.85 | 38168.15 | 0 | -2285.74 | 0 | 152660.26 | 0 | 0 | 0 | 152660.26 | 0 | 0 | 0 | 0 | 152660.26 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45797 | Hillfoot SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-06-13 | 2011-09-19 | 2014-06-09 | 2014-08-06 | East Dunbartonshire | 645407.49 | 0 | 248.91 | 0 | 0 | 0 | 0 | 0 | 248.91 | 0 | 0 | 0 | 645656.4 | 0 | 0 | 0 | 0 | 645656.4 | 28761.13 | [5 empty] | N | WQ01C | 100%
506057 | Hillhead Mauchline DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-08-05 | 2022-09-26 | 2023-01-03 | 2023-11-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4979.76 | 4979.76 | 196020.24 | 0 | 0 | 201000 | 0 | 0 | 0 | 0 | 201000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503149 | HL - Charley Horse Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0.42 | 208.72 | -72.86 | -136.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
503145 | HL - Pipebridge Remedial Work Holding Line | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | GW2 | 2021-05-05 | 2021-05-05 | 2021-05-05 | 2021-05-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_M&G | 100%
503086 | HL - Property Facilities Statutory Compliance Holding Line | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | GW2 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 2255.01 | -2255.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_M&G | 100%
503151 | HL -Development to CX2 Wastewater Holding Line | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | -3.64 | 0 | 7.28 | 0 | 0 | 7.28 | 0 | 0 | 0 | 0 | 7.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403505 | HL SVCW - CMC Reservoir Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-07-16 | 2013-07-16 | 2013-07-18 | 2019-09-03 |  | Scottish Water Wide | 674967 | 0 | 510718 | -21985.32 | 19900.3 | 0 | 0 | 0 | 508632.98 | 0 | 0 | 0 | 1183599.98 | 0 | 0 | 0 | 0 | 1183599.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403535 | HL SVCW CMC East Inf | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-07-16 | 2013-07-16 | 2013-08-30 | 2016-02-05 |  | All East Unitary Authorities | 133628 | 0 | 10515.11 | 0 | 0 | 0 | 0 | 0 | 10515.11 | 0 | 0 | 0 | 144143.11 | 0 | 0 | 0 | 0 | 144143.11 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403536 | HL SVCW CMC East Non Inf | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-07-16 | 2013-07-16 | 2013-07-16 | 2018-11-05 |  | All East Unitary Authorities | 292688 | 0 | 196191 | 0.06 | 79.86 | 111.5 | 0 | 0 | 196382.41 | 0 | 0 | 0 | 489070.41 | 0 | 0 | 0 | 0 | 489070.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506690 | Holemill WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-05-28 | 2023-02-13 | 2023-05-15 | 2024-01-08 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47430.29 | 47430.29 | 727494.71 | 0 | 0 | 774925 | 0 | 0 | 0 | 0 | 774925 | 122419.09 | [5 empty] | N | SG1 | 100%
511547 | Holl Reservoir - Secondary Supply Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9999.99 | 0 | 0 | 9999.99 | 0 | 0 | 0 | 0 | 9999.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502304 | Holl Reservoir IOS and Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2017-04-25 | 2018-04-30 | 2018-06-25 | 2020-12-07 |  | Fife | 0 | 0 | 0 | 15537.25 | 29859.75 | 369319.45 | 48510.81 | -6684.32 | 456542.95 | 22684.28 | 0 | 0 | 479227.23 | 0 | 0 | 0 | 0 | 479227.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508271 | Holl Reservoir Outlet Main Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-09-02 | 2020-12-11 | 2021-03-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8670.75 | 8670.75 | 0 | 0 | 0 | 8670.75 | 0 | 0 | 0 | 0 | 8670.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402501 | Home Farm Denny Gravity Sewer Remedial Work | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-01-27 | 2012-12-21 | 2013-03-22 | 2014-04-02 |  | Falkirk | 208639.33 | 0 | 171.3 | 0 | 0 | 0 | 0 | 0 | 171.3 | 0 | 0 | 0 | 208810.63 | 0 | 0 | 0 | 0 | 208810.63 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402897 | Hopes Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-20 | 2013-10-30 | 2014-02-11 | 2015-04-14 |  | Scottish Borders | 188319.19 | 0 | 77887.28 | 0 | 0 | 0 | 0 | 0 | 77887.28 | 0 | 0 | 0 | 266206.47 | 0 | 0 | 0 | 0 | 266206.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500476 | Hopes WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2017-04-24 | 2017-04-24 | 2017-06-07 | 2017-06-30 | 2017-08-31 | East Lothian | 0 | 0 | 9164.03 | 14348.14 | 2249.87 | 0 | 0 | 0 | 25762.04 | 0 | 0 | 0 | 25762.04 | 0 | 0 | 0 | 0 | 25762.04 | 298015.2 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
403485 | Horizons Hydros | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2013-05-07 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | Scottish Water Wide | 52616 | 0 | 59901 | -112517 | 2507.14 | 15448.51 | 0 | 0 | -34660.35 | 0 | 0 | 0 | 17955.65 | 0 | 0 | 0 | 0 | 17955.65 | 0 | [5 empty] | N | CC1W | 100%
506686 | Howden Borehole 5 Testing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-05-29 | 2021-01-11 | 2021-08-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48907 | 48907 | 12942.45 | 0 | 0 | 61849.45 | 0 | 0 | 0 | 0 | 61849.45 | 311236.79 | [5 empty] | N | CM_M&G | 100%
502970 | Howden GWS - Borehole Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-01 | 2028-11-22 | 2029-03-08 | 2030-06-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 60911.02 | 11046.71 | 71946.9 | -3167.15 | 140737.48 | 749262.52 | 0 | 0 | 890000 | 0 | 0 | 0 | 0 | 890000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503266 | Howden WTW Chloramination | IR18 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS4 | 2017-08-29 | 2018-12-20 | 2019-03-20 | 2020-12-31 | 2022-02-28 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 441754.02 | 1084824.98 | 328958.49 | 1855537.49 | -2383.49 | 145868.8294 | 145868.8294 | 1853154 | 0 | 148252.32 | 0 | 148252.32 | 2001406.32 | 947737.62 | [5 empty] | Y | DW2 | 100% | [18 empty] | 1 | [48 empty] | 0
400832 | Howden WTW New CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-05-18 | 2012-04-24 | 2012-06-11 | 2016-03-03 |  | Scottish Borders | 1461421.17 | 0 | 98345.59 | 6305.52 | 5432.16 | 0 | 0 | 0 | 110083.27 | 0 | 0 | 0 | 1571504.44 | 0 | 0 | 0 | 0 | 1571504.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500815 | Howes Way Carstairs | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2015-08-24 | 2015-09-22 | 2015-09-23 | 2020-12-04 | 2021-02-01 | South Lanarkshire | 0 | 0 | 34000 | 37000.44 | 4083.71 | 7147.61 | 12768.24 | 19382.65 | 114382.65 | 0 | 0 | 0 | 114382.65 | 0 | 0 | 0 | 0 | 114382.65 | 904764.02 | [5 empty] | N | FL_NAMED | 100%
500217 | Hoy Calder - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | Highland | 0 | 0 | 12402 | -8517.05 | 47460.76 | 3651.45 | 0 | 0 | 54997.16 | 0 | 0 | 0 | 54997.16 | 0 | 0 | 0 | 0 | 54997.16 | 1805010.12 | [5 empty] | N | DW5 | 100%
500862 | Hoy Calder RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-07-21 | 2018-06-27 | 2018-10-03 | 2019-01-31 | 2019-09-30 | Highland | 0 | 0 | 39033.81 | 12866.89 | 6598.03 | 126457.75 | 15323.24 | 849.13 | 201128.85 | 0 | 0 | 0 | 201128.85 | 0 | 0 | 0 | 0 | 201128.85 | 2663808.28 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 70.14 | [43 empty] | 0
501830 | HR - Human Capital Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-02-17 | 2019-03-04 | 2019-03-04 | 2020-12-11 |  | Scottish Water Wide | 0 | 0 | 0 | 69831.63 | 286057.4 | 3303572.17 | 2134347.33 | 2266785.63 | 8060594.16 | 0 | 0 | 0 | 8060594.16 | 0 | 0 | 0 | 0 | 8060594.16 | 306661.32 | [5 empty] | N | CM_M&G | 100%
402594 | HS Focused Delivery CID WWNI | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-04-02 | 2017-07-03 |  | All East Unitary Authorities | 1112873 | 0 | -52496 | 2089.17 | 7109.53 | 0 | 0 | 0 | -43297.3 | 0 | 0 | 0 | 1069575.7 | 0 | 0 | 0 | 0 | 1069575.7 | 209381.79 | [5 empty] | N | CM_M&G | 100%
401233 | Human Resources Information System (HRIS) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-10-07 | 2011-08-09 | 2011-08-16 | 2015-07-24 |  | Scottish Water Wide | 4919789 | 0 | -14799.73 | 0 | 0 | 0 | 0 | 0 | -14799.73 | 0 | 0 | 0 | 4904989.27 | 0 | 0 | 0 | 0 | 4904989.27 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501356 | Humbie SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-08-10 |  | West Lothian | 0 | 0 | 0 | 0 | 22846.86 | 3012.81 | 1750.44 | -1750.44 | 25859.67 | 0 | 0 | 0 | 25859.67 | 0 | 0 | 0 | 0 | 25859.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501666 | Hungry Snout | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water | SEPA | NONINF | Water Non infrastructure | MS3 | 2016-04-25 | 2018-09-06 | 2018-09-28 | 2021-06-25 | 2021-07-15 | Scottish Borders | 0 | 0 | 0 | 145156.39 | 297675.17 | 1095145.57 | 1196978.87 | 212727 | 2947683 | 209610 | 0 | 0 | 3157293 | 0 | 0 | 184560 | 184560 | 3341853 | 119022.58 | [5 empty] | Y | CM_WSNI | 100% | [67 empty] | 0
500138 | Huntly DOA (DOA000367) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-02-26 | 2016-04-20 | 2019-03-25 | 2019-06-18 | Aberdeenshire | 0 | 0 | 28827 | 5635 | 38771.25 | 44456 | 10729.57 | 0 | 128418.82 | 0 | 0 | 0 | 128418.82 | 0 | 0 | 0 | 0 | 128418.82 | 153078.25 | [5 empty] | N | EC01G | 0.298% | CS16D | 31.84% | EC01D | 67.86%
46581 | Huntly STW Refurb - STW001398 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2009-04-28 | 2012-07-10 | 2012-11-26 | 2014-05-06 | 2014-05-06 | Aberdeenshire | 3593953.37 | 0 | 105577.13 | -7565.74 | 0 | 0 | 0 | 0 | 98011.39 | 0 | 0 | 0 | 3691964.76 | 0 | 0 | 0 | 0 | 3691964.76 | 213020.38 | [5 empty] | N | CM_WWNI | 40% | SG1 | 60%
507197 | Huntly WWTW PST Scraper Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-06-25 | 2021-04-26 | 2021-09-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58315 | 58315 | 48684.72 | 0 | 0 | 106999.72 | 0 | 0 | 0 | 0 | 106999.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507200 | Huntly WWTW Tanker Discharge Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-07-13 | 2021-03-29 | 2021-07-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96529 | 96529 | 142738.12 | 0 | 0 | 239267.12 | 0 | 0 | 0 | 0 | 239267.12 | 209381.79 | [5 empty] | N | Ww3 | 100%
402777 | Hurlford Irvine Valley Sewer Renewal | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-08-06 | 2013-07-24 | 2013-09-02 | 2014-12-01 |  | East Ayrshire | 1507080 | 0 | 0 | -24812.7 | 0 | 0 | 0 | 0 | -24812.7 | 0 | 0 | 0 | 1482267.3 | 0 | 0 | 0 | 0 | 1482267.3 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45334 | Hushinish WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-07-26 | 2012-08-08 | 2012-08-08 | 2011-03-14 | Na H-Eileanan an Iar | 81297.87 | 0 | 1482.91 | 0 | 0 | 0 | 0 | 0 | 1482.91 | 0 | 0 | 0 | 82780.78 | 0 | 0 | 0 | 0 | 82780.78 | 0 | [5 empty] | N | DW13 | 100%
502262 | HV Asset Replacement Phase 1 - Albert Rd PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2017-04-28 | 2018-09-13 | 2018-09-14 | 2019-06-12 |  | City of Edinburgh | 0 | 0 | 0 | 2141.96 | 72841.04 | 369885 | 23087.61 | 44.39 | 468000 | 0 | 0 | 0 | 468000 | 0 | 0 | 0 | 0 | 468000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502263 | HV Asset Replacement Phase 1 - Dalgrain PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 | 2021-03-30 | 2021-03-30 | 2027-04-01 | 2027-04-01 |  | Falkirk | 0 | 0 | 0 | 20465 | 50987.75 | 28420.45 | 31706.43 | 875.31 | 132454.94 | 0 | 0 | 0 | 132454.94 | 0 | 0 | 0 | 0 | 132454.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502265 | HV Asset Replacement Phase 1 - Gailes PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2017-04-28 | 2019-03-07 | 2019-03-08 | 2020-03-03 |  | North Ayrshire | 0 | 0 | 0 | 6300 | 102632 | 196031 | 754858 | 72613 | 1132434 | 0 | 0 | 0 | 1132434 | 0 | 0 | 0 | 0 | 1132434 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502266 | HV Asset Replacement Phase 1 - Hamilton STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-28 | 2017-06-19 | 2017-06-19 | 2017-06-19 |  | South Lanarkshire | 0 | 0 | 0 | 243.09 | 8.9 | 0 | 0 | 0 | 251.99 | 0 | 0 | 0 | 251.99 | 0 | 0 | 0 | 0 | 251.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502267 | HV Asset Replacement Phase 1 - Laighpark WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS4 | 2017-04-06 | 2019-04-16 | 2019-05-13 | 2021-03-22 |  | Renfrewshire | 0 | 0 | 0 | 28500 | 115138 | 259816 | 1585211.42 | 730678.59 | 2719344 | 12966 | 0 | 0 | 2732310 | 0 | 0 | 67690 | 67690 | 2800000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502268 | HV Asset Replacement Phase 1 - Shieldhall WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2017-04-24 | 2019-03-07 | 2019-03-15 | 2022-04-14 |  | Glasgow City | 0 | 0 | 0 | 38873.16 | 227005.74 | 495632.21 | 1121519.57 | -6368.68 | 1876662 | 671606.44 | 0 | 0 | 2548268.44 | 0 | 0 | 451731.56 | 451731.56 | 3000000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502269 | HV Asset Replacement Phase 1 - Stevenston Point WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS4 | 2017-04-05 | 2019-03-26 | 2019-03-28 | 2021-03-22 |  | North Ayrshire | 0 | 0 | 0 | 11816 | 87054 | 403331 | 1707641.95 | 380793.73 | 2590636.68 | 27263 | 0 | 0 | 2617899.68 | 0 | 0 | 82100.32 | 82100.32 | 2700000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501147 | HV Policy Development | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-10-08 | 2015-10-08 | 2016-02-01 | 2020-05-25 |  | Scottish Water Wide | 0 | 0 | 25784 | 16033.35 | 94000 | 0 | 7538.92 | -30674.93 | 112681.34 | 0 | 0 | 0 | 112681.34 | 0 | 0 | 0 | 0 | 112681.34 | 419247.74 | [5 empty] | N | CM_WSNI | 38.67% | CM_WWNI | 61.33%
503044 | Hydraulic Modelling Enabling Works | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWMD | DWQ - Preparing for Future Investment | MS3 | 2018-05-17 | 2018-11-27 | 2018-12-10 | 2021-07-23 | 2021-10-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 168393.29 | 149224.34 | 2080.14 | 319697.77 | 0 | 0 | 0 | 319697.77 | 0 | 0 | 0 | 0 | 319697.77 | 1570056.27 | [5 empty] | N | CS16S | 100%
402453 | Hydro Generation Cluster 1 of 3 - Lomond Schemes | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS5 | 2011-08-30 | 2012-09-28 | 2013-01-29 | 2015-03-24 | 2015-03-24 | Scottish Water Wide | 9067418 | 0 | 172663.15 | 61754.85 | 160835 | 155859 | 313836.75 | 244822.12 | 1109770.87 | -384010.87 | -384010.865 | -533072.4568 | 9793178 | -149061.5918 | 0 | 0 | -149061.5918 | 9644116.4082 | 0 | [5 empty] | N | CC1W | 100%
402999 | Hydro Generation Cluster 1A (Glendevon & Glencorse) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-28 | 2012-10-31 | 2012-11-30 | 2015-03-30 | 2015-03-30 | Scottish Water Wide | 4434154 | 0 | -17058.99 | 15064.99 | 88578 | 7499.13 | 0 | 0 | 94083.13 | 0 | 0 | 0 | 4528237.13 | 0 | 0 | 0 | 0 | 4528237.13 | 0 | [5 empty] | N | CC1W | 100%
402454 | Hydro Generation Cluster 2 of 3 Katrine Catchment | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-08-30 | 2012-09-28 | 2012-10-25 | 2015-10-08 | 2015-10-08 | Scottish Water Wide | 1280300 | 0 | -83872.78 | 1763.15 | 0 | 0 | 0 | 0 | -82109.63 | 0 | 0 | 0 | 1198190.37 | 0 | 0 | 0 | 0 | 1198190.37 | 0 | [5 empty] | N | CC1W | 100%
402455 | Hydro Generation Cluster 3 of 3 South and West Sites | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-08-30 | 2012-09-28 | 2012-10-25 | 2014-12-18 | 2015-01-30 | Scottish Water Wide | 6749999 | 0 | 2493.21 | 81281.79 | 44226 | 25394.11 | 0 | 0 | 153395.11 | 0 | 0 | 0 | 6903394.11 | 0 | 0 | 0 | 0 | 6903394.11 | 0 | [5 empty] | N | CC1W | 100%
506861 | Hyperion Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2020-06-04 | 2020-07-14 | 2020-07-14 | 2021-04-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899331.04 | 899331.04 | -6807.42 | 0 | 0 | 892523.62 | 0 | 0 | 0 | 0 | 892523.62 | 613322.63 | [5 empty] | N | CM_M&G | 100%
402893 | ICAT Improvement Project | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWD | Wastewater non infrastructure | MS7 | 2012-08-31 | 2013-01-09 | 2013-02-05 | 2015-02-09 |  | Scottish Water Wide | 375097.32 | 0 | -11258.8 | 0 | 0 | 0 | 0 | 0 | -11258.8 | 0 | 0 | 0 | 363838.52 | 0 | 0 | 0 | 0 | 363838.52 | 209623.87 | [5 empty] | N | CM_WSNI | 50% | CM_WWNI | 50%
504785 | ICF - Aviemore Dalnabay - Sewer upsizing | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 |  | 2020-04-20 |  |  |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88999.95 | 0 | 0 | 88999.95 | 0 | 0 | 0 | 0 | 88999.95 | 1470767.03 | [5 empty] | N | SG5 | 100%
504779 | ICF - Avoch Memorial Field - Strategic Surface Water Removal Project | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 |  | 2020-03-04 |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 69758.74 | 0 | 69758.74 | 0 | 0 | 0 | 69758.74 | 0 | 0 | 0 | 0 | 69758.74 | 1470767.03 | [5 empty] | N | SG5 | 100%
503614 | ICF - Bathgate Alternative Feed - Section bisecting Garden District - Redheughs Village. W | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW2 | 2021-05-05 | 2022-01-17 | 2022-02-14 | 2023-09-08 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 10583.12 | 2741.88 | 13325 | 486674.47 | 0 | 0 | 499999.47 | 0 | 0 | 0 | 0 | 499999.47 | 444766.03 | [5 empty] | N | WG5 | 100%
504782 | ICF - Broxden Perth Wastewater | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 |  | 2020-06-30 |  |  |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314580 | 0 | 0 | 314580 | 0 | 0 | 0 | 0 | 314580 | 1470767.03 | [5 empty] | N | SG5 | 100%
507437 | ICF - Coatbridge to Daldowie Waste strategic network upgrades | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 |  | 2020-07-13 |  | 2021-06-25 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6803.74 | 6803.74 | 97196.26 | 0 | 0 | 104000 | 0 | 0 | 0 | 0 | 104000 | 1470767.03 | [5 empty] | N | SG5 | 100%
510410 | ICF - Drumnadrochit Water Main Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS2 |  | 2021-03-15 |  | 2026-12-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401250 | 0 | 0 | 401250 | 0 | 0 | 0 | 0 | 401250 | 444766.03 | [5 empty] | N | WG5 | 100%
503450 | ICF - Dunbeg Development - Strategic Wastewater Solution | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2019-09-18 | 2019-09-18 | 2020-09-10 | 2022-02-28 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 32710.28 | 6878.24 | 39588.52 | 560411.5 | 0 | 0 | 600000.02 | 0 | 0 | 0 | 0 | 600000.02 | 1470767.03 | [5 empty] | N | SG5 | 100%
503705 | ICF - East Calder - Pumpherston Road NIA0179.D01 - WW | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | GW2 | 2021-04-05 | 2021-09-10 | 2021-11-23 | 2023-06-27 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 27.55 | 0 | 27.55 | 550000 | 0 | 0 | 550027.55 | 0 | 0 | 0 | 0 | 550027.55 | 1470767.03 | [5 empty] | N | SG5 | 100%
507455 | ICF - Ellon - Bridge of Don (Aberdeen) Development Corridor - Balmedie to Blackdog Section. Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 |  | 2020-07-24 | 2020-07-24 | 2024-04-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365471.96 | 365471.96 | 3134528.04 | 0 | 0 | 3500000 | 0 | 0 | 280000 | 280000 | 3780000 | 444766.03 | [5 empty] | N | WG5 | 100%
503707 | ICF - Falkirk Strategic NIA Waste Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2020-10-01 | 2021-07-26 | 2021-07-26 | 2022-07-11 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4374720 | 0 | 0 | 4374720 | 0 | 0 | 0 | 0 | 4374720 | 1470767.03 | [5 empty] | N | SG5 | 100%
507469 | ICF - Falkirk Strategic Waste | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | [5 empty] | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3499999.99 | 0 | 0 | 3499999.99 | 0 | 0 | 0 | 0 | 3499999.99 | 1470767.03 | [5 empty] | N | SG5 | 100%
506865 | ICF - Forres Strategic Wastewater upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 |  | 2020-06-30 | 2020-06-30 | 2022-02-18 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166.34 | 166.34 | 1284000 | 0 | 0 | 1284166.34 | 0 | 0 | 102733.3072 | 102733.3072 | 1386899.6472 | 1470767.03 | [5 empty] | N | SG5 | 100%
506864 | ICF - Forres Strategic Water upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 |  | 2020-06-30 | 2020-06-30 | 2022-02-18 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 1500000 | 0 | 0 | 120000 | 120000 | 1620000 | 444766.03 | [5 empty] | N | WG5 | 100%
505032 | ICF - Grandholm Aberdeen - Water Main Installation. | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS3 | 2020-03-23 | 2020-07-09 | 2020-07-27 | 2021-09-10 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2273304.87 | 2273304.87 | 1155433 | 0 | 0 | 3428737.87 | 0 | 0 | 1071262.13 | 1071262.13 | 4500000 | 444766.03 | [5 empty] | N | WG5 | 100%
503439 | ICF - Greenlaw - Newton Mearns | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2019-03-26 | 2019-03-26 | 2019-07-10 | 2021-04-14 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 1253928.81 | 81830.8 | 6150.82 | 1341910.43 | 0 | 0 | 0 | 1341910.43 | 0 | 0 | 0 | 0 | 1341910.43 | 1470767.03 | [5 empty] | N | SG5 | 100%
507506 | ICF - Huntingtower - Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS2 |  | 2020-08-12 |  | 2024-12-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000 | 444766.03 | [5 empty] | N | WG5 | 100%
506230 | ICF - Imereval - Wastewater Strategic project | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 |  | 2020-04-30 |  | 2022-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74900 | 0 | 0 | 74900 | 0 | 0 | 0 | 0 | 74900 | 1470767.03 | [5 empty] | N | SG5 | 100%
506869 | ICF - Kirkwall Balfour Hospital Strategic Surface Water Removal Project | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 |  | 2020-06-30 |  | 2021-12-16 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495142.88 | 0 | 0 | 495142.88 | 0 | 0 | 0 | 0 | 495142.88 | 1470767.03 | [5 empty] | N | SG5 | 100%
506867 | ICF - Kirkwall Lidl Option - Strategic Surface Water Removal Project | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 |  | 2020-06-22 |  | 2022-02-28 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3984.75 | 3984.75 | 56925 | 0 | 0 | 60909.75 | 0 | 0 | 0 | 0 | 60909.75 | 1470767.03 | [5 empty] | N | SG5 | 100%
503449 | ICF - maidenhill Newton Mearns WW | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2019-02-25 | 2019-02-25 | 2019-04-01 | 2021-05-04 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 1225233.64 | 4921.83 | 0 | 1230155.47 | 0 | 0 | 0 | 1230155.47 | 0 | 0 | 0 | 0 | 1230155.47 | 1470767.03 | [5 empty] | N | SG5 | 100%
507451 | ICF - NGIWMS Agreement with Glasgow Council | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 |  | 2020-07-30 | 2020-07-30 | 2024-07-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362237.43 | 362237.43 | 5107762.57 | 0 | 0 | 5470000 | 0 | 0 | 437600 | 437600 | 5907600 | 1470767.03 | [5 empty] | N | SG5 | 100%
503522 | ICF - Perth Drainage - 2018 - 2028 development enablement WW | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | GW2 | 2021-06-07 | 2022-01-03 | 2022-04-18 | 2025-11-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 60511.32 | 192.86 | 60704.17 | 2939350.93 | 0 | 0 | 3000055.1 | 0 | 0 | 0 | 0 | 3000055.1 | 1470767.03 | [5 empty] | N | SG5 | 100%
504776 | ICF - Sandwick - Shetland - Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS2 |  | 2020-04-27 |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 444766.03 | [5 empty] | N | WG5 | 100%
512120 | ICF - SR21 Strategic Development overhead | Q&S4 | Supporting economic development | Infra Charge |  |  | General |  | SWD | Infra Charge | MSU |  | 2021-05-01 |  | 2027-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 0 | 12000000 | 0 | 0 | 0 | 0 | 12000000 | 0 | [5 empty] | N | SG5 | 50% | WG5 | 50%
503448 | ICF - St Leonard s Place Dundee - Surface Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | GW2 | 2022-11-15 | 2022-11-15 | 2022-12-27 | 2023-03-29 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 27489.52 | 460.48 | 27950 | 791209.27 | 0 | 0 | 819159.27 | 0 | 0 | 0 | 0 | 819159.27 | 1470767.03 | [5 empty] | N | SG5 | 100%
507326 | ICF - Stratton Farm Inverness. - Strategic Water Main Upgrade | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS2 |  | 2020-07-06 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369138.6 | 369138.6 | 130861.4 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 444766.03 | [5 empty] | N | WG5 | 100%
503709 | ICF - West Edinburgh Strategic Approach - WW | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | GW2 | 2021-06-25 | 2022-01-06 | 2022-03-18 | 2023-05-25 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 43.06 | 0 | 43.06 | 6999999.93 | 0 | 0 | 7000042.99 | 0 | 0 | 0 | 0 | 7000042.99 | 1470767.03 | [5 empty] | N | SG5 | 100%
503456 | ICF- Aberdeen - Nigg Harbour Development -Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS0 | 2019-08-01 | 2021-08-16 | 2021-09-02 | 2022-03-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3271.03 | 9345.97 | 12617 | 487383.18 | 0 | 0 | 500000.18 | 0 | 0 | 0 | 0 | 500000.18 | 444766.03 | [5 empty] | N | WG5 | 100%
506161 | ICF Mauricewood DSR - Growth | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW0 | 2022-02-24 | 2024-01-11 | 2024-06-20 | 2026-01-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270 | 11270 | 1488720.45 | 0 | 0 | 1499990.45 | 0 | 0 | 0 | 0 | 1499990.45 | 0 | [5 empty] | N | WG5 | 100%
503549 | ICF-Armadale 12inch Trunk Main Replacement - Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2019-04-11 | 2019-04-11 | 2019-09-23 | 2021-06-30 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 857047.3 | 252479.71 | 1109527.01 | -252480.15 | 0 | 0 | 857046.86 | 0 | 0 | 0 | 0 | 857046.86 | 444766.03 | [5 empty] | N | WG5 | 100%
505062 | ICF-Balance of Funding - 3rd Party support | Q&S4 | Supporting economic development | Infra Charge |  |  | General |  | SWD | Infra Charge | MS2 |  | 2020-04-20 |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52916.74 | 52916.74 | 5366.82 | 0 | 0 | 58283.56 | 0 | 0 | 0 | 0 | 58283.56 | 1915533.05 | [5 empty] | N | SG5 | 50% | WG5 | 50%
504271 | ICF-Winchburgh Village Development | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 |  | 2020-02-11 |  |  |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 781418.02 | 363462.28 | 1144880.3 | 555119.7 | 0 | 0 | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | [5 empty] | N | SG5 | 100%
500675 | Identity and Access Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-05 | 2017-01-31 | 2017-01-31 | 2018-04-15 |  | Scottish Water Wide | 0 | 0 | 237418 | 1113994.05 | 145800.67 | 11566.97 | 0 | 0 | 1508779.69 | 0 | 0 | 0 | 1508779.69 | 0 | 0 | 0 | 0 | 1508779.69 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500262 | IDP - Wastewater Infra Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2017-05-26 |  | All East Unitary Authorities | 0 | 0 | 6404.59 | -6404.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWI | 100%
500293 | IDP - Economic Level of Leakage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-01-31 |  | Scottish Water Wide | 0 | 0 | 37812.79 | -37812.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
500295 | IDP - Leakage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-03-31 |  | Scottish Water Wide | 0 | 0 | 197423 | 10906.72 | 0 | 0 | 0 | 0 | 208329.72 | 0 | 0 | 0 | 208329.72 | 0 | 0 | 0 | 0 | 208329.72 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403845 | IDP - Leakage - 4038450000 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2015-11-13 |  | Scottish Water Wide | 135796.78 | 0 | 41182.86 | 0 | 0 | 0 | 0 | 0 | 41182.86 | 0 | 0 | 0 | 176979.64 | 0 | 0 | 0 | 0 | 176979.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500294 | IDP - Leakage - Research and Innovation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2017-05-18 |  | Scottish Water Wide | 0 | 0 | 90122 | 5062.93 | 32003.15 | 0 | 0 | 0 | 127188.08 | 0 | 0 | 0 | 127188.08 | 0 | 0 | 0 | 0 | 127188.08 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404120 | IDP - Property Emergency Remedial Work - 14-15 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-08-04 |  | Scottish Water Wide | 320000 | 0 | -7745.71 | 0 | 0 | 0 | 0 | 0 | -7745.71 | 0 | 0 | 0 | 312254.29 | 0 | 0 | 0 | 0 | 312254.29 | 306661.32 | [5 empty] | N | CM_M&G | 100%
500296 | IDP - Reservoirs - FRMA | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water |  | SWD | Flood Risk Management Act | MS7 | 2015-04-16 | 2015-04-16 | 2016-01-06 | 2016-01-06 | 2016-01-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WR6 | 100%
500297 | IDP - Reservoirs - Interest of Safety | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-01-05 | 2016-01-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
403861 | IDP - Reservoirs FRMA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2017-01-31 |  | Scottish Water Wide | 50000 | 0 | 78348.08 | 51311.29 | 98.34 | 0 | 0 | 0 | 129757.71 | 0 | 0 | 0 | 179757.71 | 0 | 0 | 0 | 0 | 179757.71 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403846 | IDP - Reservoirs interest of safety | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2017-01-31 |  | Scottish Water Wide | 60000 | 0 | 178885.68 | 85973.17 | 0 | 0 | 0 | 0 | 264858.85 | 0 | 0 | 0 | 324858.85 | 0 | 0 | 0 | 0 | 324858.85 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500292 | IDP - UID Storage Assets - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-11-15 |  | Scottish Water Wide | 0 | 0 | 182491 | 21721.4 | 0 | 0 | 0 | 0 | 204212.4 | 0 | 0 | 0 | 204212.4 | 0 | 0 | 0 | 0 | 204212.4 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502176 | IDP - Wastewater Central - Infra Assets - Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-18 |  | Scottish Water Wide | 0 | 0 | 0 | 703722.47 | 11871.62 | 23.76 | 0 | 0 | 715617.85 | 0 | 0 | 0 | 715617.85 | 0 | 0 | 0 | 0 | 715617.85 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502177 | IDP - Wastewater Central - Non-Infra Assets - Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-08-22 | 2017-08-22 | 2017-08-22 | 2017-07-21 |  | Scottish Water Wide | 0 | 0 | 0 | 675131.21 | 3758.1 | 0 | 0 | 0 | 678889.31 | 0 | 0 | 0 | 678889.31 | 0 | 0 | 0 | 0 | 678889.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502677 | IDP - Wastewater Central Infra Assets - Yr 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 | 2021-03-03 | 2021-02-28 | 2021-03-17 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 96515.68 | 32885.42 | 15893.97 | -43308 | 101987.07 | 47800.8 | 0 | 0 | 149787.87 | 0 | 0 | 0 | 0 | 149787.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502678 | IDP - Wastewater Central Non Infra Assets - Yr 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-07-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 123080.32 | 12519.14 | -14669.48 | 0 | 120929.98 | 0 | 0 | 0 | 120929.98 | 0 | 0 | 0 | 0 | 120929.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502178 | IDP - Wastewater East - Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-06 | 2020-03-15 | 2020-01-06 | 2020-03-15 |  | All East Unitary Authorities | 0 | 0 | 0 | 485612.9 | 23701.33 | 13396.42 | 46107.59 | 53221.18 | 622039.42 | 0 | 0 | 0 | 622039.42 | 0 | 0 | 0 | 0 | 622039.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502679 | IDP - Wastewater East - Yr 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-15 | 2020-03-13 | 2020-01-15 | 2020-03-13 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 103428.15 | 21824.17 | 6706.12 | 0 | 131958.44 | 0 | 0 | 0 | 131958.44 | 0 | 0 | 0 | 0 | 131958.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500268 | IDP - Wastewater Infra Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 |  | All West Unitary Authorities | 0 | 0 | 41770 | -40282.65 | 813.24 | 0 | 0 | 0 | 2300.59 | 0 | 0 | 0 | 2300.59 | 0 | 0 | 0 | 0 | 2300.59 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502180 | IDP - Wastewater South - Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-07 | 2020-03-12 | 2020-01-15 | 2020-03-12 |  | All South Unitary Authorities | 0 | 0 | 0 | 174480.13 | 10821.61 | 95.93 | 0.01 | 0 | 185397.67 | 0 | 0 | 0 | 185397.67 | 0 | 0 | 0 | 0 | 185397.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502680 | IDP - Wastewater South - Yr 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-15 | 2020-03-13 | 2020-01-15 | 2020-03-13 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 107697.83 | 0 | 0 | 0 | 107697.83 | 0 | 0 | 0 | 107697.83 | 0 | 0 | 0 | 0 | 107697.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502181 | IDP - Wastewater West - Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-15 | 2020-03-12 | 2020-01-15 | 2020-03-12 |  | All West Unitary Authorities | 0 | 0 | 0 | 234149.86 | 7726.48 | 967.86 | 73.88 | 0 | 242918.08 | 0 | 0 | 0 | 242918.08 | 0 | 0 | 0 | 0 | 242918.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502681 | IDP - Wastewater West - Yr 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-01-15 | 2020-03-13 | 2020-01-15 | 2020-03-13 |  | All West Unitary Authorities | 0 | 0 | 0 | 623.08 | 76847.22 | 147.51 | 0 | 0 | 77617.81 | 0 | 0 | 0 | 77617.81 | 0 | 0 | 0 | 0 | 77617.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500298 | IDP - Water Balance Data Studies and Improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2017-05-18 |  | Scottish Water Wide | 0 | 0 | 300976 | 39504.94 | 96617.57 | 0 | 0 | 0 | 437098.51 | 0 | 0 | 0 | 437098.51 | 0 | 0 | 0 | 0 | 437098.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502170 | IDP - Water Central - Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-07-20 | 2017-07-20 | 2017-07-20 | 2017-04-03 |  | Scottish Water Wide | 0 | 0 | 0 | 1094408.92 | -152099.26 | 0 | 0 | 0 | 942309.66 | 0 | 0 | 0 | 942309.66 | 0 | 0 | 0 | 0 | 942309.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502682 | IDP - Water Central - Yr 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-05-09 | 2019-05-09 | 2019-05-09 | 2019-04-30 |  | Scottish Water Wide | 0 | 0 | 0 | 108000 | 98593.79 | 17086.71 | -24710.03 | 0 | 198970.48 | 0 | 0 | 0 | 198970.48 | 0 | 0 | 0 | 0 | 198970.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502171 | IDP - Water East - Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-09-19 | 2019-09-19 | 2019-09-19 | 2019-09-09 |  | All East Unitary Authorities | 0 | 0 | 0 | 428530.5 | 114845.23 | 0 | 43928.34 | 0 | 587304.07 | 0 | 0 | 0 | 587304.07 | 0 | 0 | 0 | 0 | 587304.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502683 | IDP - Water East - Yr 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-09-12 |  | Scottish Water Wide | 0 | 0 | 0 | 177120 | 177433.33 | 230400 | -126966.55 | 0 | 457986.78 | 0 | 0 | 0 | 457986.78 | 0 | 0 | 0 | 0 | 457986.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500287 | IDP - Water Infra Assets Central - SR15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-12-08 |  | Scottish Water Wide | 0 | 0 | 416621.26 | 52520.63 | 0 | 0 | 0 | 0 | 469141.89 | 0 | 0 | 0 | 469141.89 | 0 | 0 | 0 | 0 | 469141.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500274 | IDP - Water Infra Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2015-11-03 | 2016-06-06 |  | All East Unitary Authorities | 0 | 0 | 12025.09 | 3102.25 | 94.5 | 8.26 | 0 | 0 | 15230.1 | 0 | 0 | 0 | 15230.1 | 0 | 0 | 0 | 0 | 15230.1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500278 | IDP - Water Infra Assets North - SR15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-09-26 |  | All North Unitary Authorities | 0 | 0 | 60060.58 | 53030.86 | -19320.57 | 0 | 0 | 0 | 93770.87 | 0 | 0 | 0 | 93770.87 | 0 | 0 | 0 | 0 | 93770.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500282 | IDP - Water Infra Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2017-02-01 |  | All West Unitary Authorities | 0 | 0 | 63235 | 33163.69 | 1913.14 | 0 | 0 | 0 | 98311.83 | 0 | 0 | 0 | 98311.83 | 0 | 0 | 0 | 0 | 98311.83 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502172 | IDP - Water North - Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-07-21 |  | All North Unitary Authorities | 0 | 0 | 0 | 422624.76 | 17903.78 | 0 | 0 | 0 | 440528.54 | 0 | 0 | 0 | 440528.54 | 0 | 0 | 0 | 0 | 440528.54 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502684 | IDP - Water North - Yr 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-07-17 | 2019-07-17 | 2019-06-20 | 2019-06-20 |  | All North Unitary Authorities | 0 | 0 | 0 | 177120 | 115277.12 | 114346.62 | 19510 | 0 | 426253.74 | 0 | 0 | 0 | 426253.74 | 0 | 0 | 0 | 0 | 426253.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502173 | IDP - Water South - Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-06-20 |  | All South Unitary Authorities | 0 | 0 | 0 | 471509.52 | 62195.87 | 0 | 0 | 0 | 533705.39 | 0 | 0 | 0 | 533705.39 | 0 | 0 | 0 | 0 | 533705.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502685 | IDP - Water South - Yr 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-07-01 | 2019-07-31 | 2019-07-31 | 2019-07-01 |  | All South Unitary Authorities | 0 | 0 | 0 | 177120 | 253315.88 | 180044.27 | 27586.78 | -610.14 | 637456.79 | 0 | 0 | 0 | 637456.79 | 0 | 0 | 0 | 0 | 637456.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502174 | IDP - Water West - Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-03-31 |  | All West Unitary Authorities | 0 | 0 | 0 | 534693.1 | 108739.39 | 0 | 0 | 0 | 643432.49 | 0 | 0 | 0 | 643432.49 | 0 | 0 | 0 | 0 | 643432.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502676 | IDP - Water West - Yr 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-09-11 | 2019-09-11 | 2019-09-11 | 2019-06-19 |  | All West Unitary Authorities | 0 | 0 | 0 | 177120 | 275319.9 | 260981.9 | 150408.34 | 0 | 863830.13 | 0 | 0 | 0 | 863830.13 | 0 | 0 | 0 | 0 | 863830.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500275 | IDP - WPS Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2015-11-03 | 2016-06-06 |  | All East Unitary Authorities | 0 | 0 | 157872.26 | 19120.14 | 0 | 0 | 0 | 0 | 176992.4 | 0 | 0 | 0 | 176992.4 | 0 | 0 | 0 | 0 | 176992.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500279 | IDP - WPS Assets North - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-08-18 |  | All North Unitary Authorities | 0 | 0 | 43980 | -2389.4 | 0 | 0 | 0 | 0 | 41590.6 | 0 | 0 | 0 | 41590.6 | 0 | 0 | 0 | 0 | 41590.6 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
500291 | IDP - WPS Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-09-14 |  | All South Unitary Authorities | 0 | 0 | 95111.44 | 56350.95 | 0 | 0 | 0 | 0 | 151462.39 | 0 | 0 | 0 | 151462.39 | 0 | 0 | 0 | 0 | 151462.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500283 | IDP - WPS Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2017-02-01 |  | All West Unitary Authorities | 0 | 0 | 147862 | -29745.92 | 0 | 0 | 0 | 0 | 118116.08 | 0 | 0 | 0 | 118116.08 | 0 | 0 | 0 | 0 | 118116.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500276 | IDP - WSR Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2015-11-03 | 2016-06-06 |  | All East Unitary Authorities | 0 | 0 | 32673 | -554.38 | 0 | 0 | 0 | 0 | 32118.62 | 0 | 0 | 0 | 32118.62 | 0 | 0 | 0 | 0 | 32118.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500280 | IDP - WSR Assets North - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-08-18 |  | All North Unitary Authorities | 0 | 0 | 33996 | 701.08 | 0 | 0 | 0 | 0 | 34697.08 | 0 | 0 | 0 | 34697.08 | 0 | 0 | 0 | 0 | 34697.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500289 | IDP - WSR Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-11-03 |  | All South Unitary Authorities | 0 | 0 | 83070.02 | 11610.56 | 0 | 0 | 0 | 0 | 94680.58 | 0 | 0 | 0 | 94680.58 | 0 | 0 | 0 | 0 | 94680.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500284 | IDP - WSR Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-12-13 |  | All West Unitary Authorities | 0 | 0 | 239540 | 63337.64 | 268.31 | 0 | 704.26 | 0 | 303850.21 | 0 | 0 | 0 | 303850.21 | 0 | 0 | 0 | 0 | 303850.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500286 | IDP - WTW Assets Central - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-01-06 | 2016-12-08 |  | Scottish Water Wide | 0 | 0 | 1081651.52 | 247985.14 | -530.4 | 0 | -121.63 | 0 | 1328984.63 | 0 | 0 | 0 | 1328984.63 | 0 | 0 | 0 | 0 | 1328984.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500277 | IDP - WTW Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2016-06-06 |  | All East Unitary Authorities | 0 | 0 | 593688.69 | 23897.7 | 4920.54 | 7602.6 | 0 | 0 | 630109.53 | 0 | 0 | 0 | 630109.53 | 0 | 0 | 0 | 0 | 630109.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500281 | IDP - WTW Assets North - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-09-18 | 2016-08-18 |  | All North Unitary Authorities | 0 | 0 | 365517.58 | 29930.32 | 0 | 0 | 0 | 0 | 395447.9 | 0 | 0 | 0 | 395447.9 | 0 | 0 | 0 | 0 | 395447.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500288 | IDP - WTW Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-02-02 | 2016-11-03 |  | All South Unitary Authorities | 0 | 0 | 511637.9 | 585542.53 | 106.31 | 0 | 0 | 0 | 1097286.74 | 0 | 0 | 0 | 1097286.74 | 0 | 0 | 0 | 0 | 1097286.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500285 | IDP - WTW Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2016-12-19 |  | All West Unitary Authorities | 0 | 0 | 453258 | -200263.09 | 0 | 0 | 0 | 0 | 252994.91 | 0 | 0 | 0 | 252994.91 | 0 | 0 | 0 | 0 | 252994.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500271 | IDP - WW Infra Assets Central - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2017-05-12 | 2017-05-18 |  | Scottish Water Wide | 0 | 0 | 1033259.2 | -24561.78 | 6945.26 | 385.75 | 0 | 0 | 1016028.43 | 0 | 0 | 0 | 1016028.43 | 0 | 0 | 0 | 0 | 1016028.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500265 | IDP - WW Infra Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 |  | All South Unitary Authorities | 0 | 0 | 8909.96 | 2720.06 | 0 | 0 | 0 | 0 | 11630.02 | 0 | 0 | 0 | 11630.02 | 0 | 0 | 0 | 0 | 11630.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500272 | IDP - WWPS Assets Central - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-11-01 | 2016-11-01 |  | Scottish Water Wide | 0 | 0 | 268531.28 | 114268.44 | 6398.26 | 0 | 0 | 0 | 389197.98 | 0 | 0 | 0 | 389197.98 | 0 | 0 | 0 | 0 | 389197.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500263 | IDP - WWPS Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2017-01-30 | 2017-01-30 |  | All East Unitary Authorities | 0 | 0 | 100985 | -62109.66 | 0 | 0 | 0 | 0 | 38875.34 | 0 | 0 | 0 | 38875.34 | 0 | 0 | 0 | 0 | 38875.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500266 | IDP - WWPS Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 |  | All South Unitary Authorities | 0 | 0 | 158609.82 | 69747.56 | 228.75 | 0 | 172.24 | 0 | 228758.37 | 0 | 0 | 0 | 228758.37 | 0 | 0 | 0 | 0 | 228758.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500269 | IDP - WWPS Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 |  | All West Unitary Authorities | 0 | 0 | 255942.21 | 60646.06 | 234.58 | 637.53 | 0 | 0 | 317460.38 | 0 | 0 | 0 | 317460.38 | 0 | 0 | 0 | 0 | 317460.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500273 | IDP - WWTW Assets Central - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-07-20 | 2016-11-01 |  | Scottish Water Wide | 0 | 0 | 399834.33 | 53662.25 | -106283.44 | 0 | 838.16 | 0 | 348051.3 | 0 | 0 | 0 | 348051.3 | 0 | 0 | 0 | 0 | 348051.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500264 | IDP - WWTW Assets East - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-02-02 | 2017-01-31 |  | All East Unitary Authorities | 0 | 0 | 330052 | -203269.31 | -2930.31 | 0 | 0 | 0 | 123852.38 | 0 | 0 | 0 | 123852.38 | 0 | 0 | 0 | 0 | 123852.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500267 | IDP - WWTW Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-01-06 |  | All South Unitary Authorities | 0 | 0 | 456568.9 | 279224.69 | 722.23 | 5699.56 | 0 | 0 | 742215.38 | 0 | 0 | 0 | 742215.38 | 0 | 0 | 0 | 0 | 742215.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500270 | IDP - WWTW Assets West - SR15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-01 | 2015-07-13 | 2015-07-13 | 2017-01-06 |  | All West Unitary Authorities | 0 | 0 | 289496.83 | 35341.45 | 1778.92 | 0 | 0 | 0 | 326617.2 | 0 | 0 | 0 | 326617.2 | 0 | 0 | 0 | 0 | 326617.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403836 | IDP Infra Assets Central 14-15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-17 | 2014-06-17 | 2014-06-17 | 2016-12-07 |  | Scottish Water Wide | 403503 | 0 | 30983 | -2011.25 | 0 | 0 | 0 | 0 | 28971.75 | 0 | 0 | 0 | 432474.75 | 0 | 0 | 0 | 0 | 432474.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403837 | IDP Infra Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-06-23 |  | All East Unitary Authorities | 12629 | 0 | 12371 | -15475.14 | 0 | 0 | 0 | 0 | -3104.14 | 0 | 0 | 0 | 9524.86 | 0 | 0 | 0 | 0 | 9524.86 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403838 | IDP Infra Assets North 14-15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-08 |  | All North Unitary Authorities | 24128.76 | 0 | 81354.24 | -64981.05 | 0 | 0 | 0 | 0 | 16373.19 | 0 | 0 | 0 | 40501.95 | 0 | 0 | 0 | 0 | 40501.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403840 | IDP Infra Assets West 14-15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-05-09 |  | All West Unitary Authorities | 20521.67 | 0 | 3716.03 | 116.15 | 0 | 0 | 0 | 0 | 3832.18 | 11489.99 | 0 | 0 | 35843.84 | 0 | 0 | 0 | 0 | 35843.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501783 | IDP Leakage Yr2 to IDP Leakage Yrs 2-4 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2020-04-03 | 2020-02-26 | 2020-05-29 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 499613 | 172485 | 113926 | 439621 | 76972 | 1302617 | 55584 | 0 | 0 | 1358201 | 0 | 0 | 0 | 0 | 1358201 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403841 | IDP UID Storage Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-06 |  | All East Unitary Authorities | 54389.62 | 0 | 78615.37 | 12334.62 | 0 | 0 | 0 | 0 | 90949.99 | 0 | 0 | 0 | 145339.61 | 0 | 0 | 0 | 0 | 145339.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403842 | IDP UID Storage Assets North 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2015-11-05 |  | All North Unitary Authorities | 34982.7 | 0 | -1120.29 | 0 | 0 | 0 | 0 | 0 | -1120.29 | 0 | 0 | 0 | 33862.41 | 0 | 0 | 0 | 0 | 33862.41 | 209623.87 | [5 empty] | N | CM_WSNI | 43.87% | CM_WWNI | 56.13%
500290 | IDP -Water Infra Assets South - SR15 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-11-03 |  | All South Unitary Authorities | 0 | 0 | 41385.94 | 129720.26 | 0 | 0 | 0 | 0 | 171106.2 | 0 | 0 | 0 | 171106.2 | 0 | 0 | 0 | 0 | 171106.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403833 | IDP WPS Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-06-07 |  | All East Unitary Authorities | 36435.57 | 0 | -2408.57 | -1012.73 | 0 | 0 | 0 | 0 | -3421.3 | 0 | 0 | 0 | 33014.27 | 0 | 0 | 0 | 0 | 33014.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403834 | IDP WPS Assets North 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-08 |  | All North Unitary Authorities | 29931.93 | 0 | 56849.28 | 604.44 | 0 | 0 | 0 | 0 | 57453.72 | 0 | 0 | 0 | 87385.65 | 0 | 0 | 0 | 0 | 87385.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403835 | IDP WPS Assets South 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-19 |  | All South Unitary Authorities | 21760.52 | 0 | 36663.48 | -5894.4 | 226.51 | 0 | 0 | 0 | 30995.59 | 0 | 0 | 0 | 52756.11 | 0 | 0 | 0 | 0 | 52756.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403832 | IDP WPS Assets West 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-05-10 |  | All West Unitary Authorities | 45329.9 | 0 | 5112.04 | 1250.85 | 0 | 0 | 0 | 0 | 6362.89 | 0 | 0 | 0 | 51692.79 | 0 | 0 | 0 | 0 | 51692.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403847 | IDP WSR Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-06-07 |  | All East Unitary Authorities | 21309.06 | 0 | 50111.4 | 10.09 | 0 | 0 | 0 | 0 | 50121.49 | 0 | 0 | 0 | 71430.55 | 0 | 0 | 0 | 0 | 71430.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403848 | IDP WSR Assets North 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-08-15 |  | All North Unitary Authorities | 47409.54 | 0 | 35152.46 | 2359.99 | 0 | 0 | 0 | 74.82 | 37587.27 | 0 | 0 | 0 | 84996.81 | 0 | 0 | 0 | 0 | 84996.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403849 | IDP WSR Assets South 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-19 |  | All South Unitary Authorities | 46766.9 | 0 | 22472.46 | 342.38 | 264.7 | 0 | 0 | 0 | 23079.54 | 0 | 0 | 0 | 69846.44 | 0 | 0 | 0 | 0 | 69846.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403850 | IDP WSR Assets West 14-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-05-09 |  | All West Unitary Authorities | 58090.12 | 0 | 6425.27 | 0 | 0 | 0 | 0 | 0 | 6425.27 | 0 | 0 | 0 | 64515.39 | 0 | 0 | 0 | 0 | 64515.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403851 | IDP WW Infra Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-06 |  | All East Unitary Authorities | 9479.95 | 0 | 10795.12 | 7173.08 | 0 | 0 | 0 | 0 | 17968.2 | 0 | 0 | 0 | 27448.15 | 0 | 0 | 0 | 0 | 27448.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403852 | IDP WW Infra Assets North 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-01-13 |  | All North Unitary Authorities | 624 | 0 | 423.12 | 0 | 0 | 0 | 0 | 0 | 423.12 | 0 | 0 | 0 | 1047.12 | 0 | 0 | 0 | 0 | 1047.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403853 | IDP WW Infra Assets Scotland Wide 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-09-01 |  | Scottish Water Wide | 371310.51 | 0 | 415764.61 | 15702.21 | 0 | 0 | 0 | 0 | 431466.82 | 0 | 0 | 0 | 802777.33 | 0 | 0 | 0 | 0 | 802777.33 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403854 | IDP WW Infra Assets South 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All South Unitary Authorities | 341.73 | 0 | 415.07 | -106.07 | 0 | 0 | 0 | 0 | 309 | 0 | 0 | 0 | 650.73 | 0 | 0 | 0 | 0 | 650.73 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403839 | IDP WW Infra Assets South 14-15 - 4038390000 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-19 |  | All South Unitary Authorities | 8847.03 | 0 | 626.04 | -388.18 | 0 | 0 | 0 | 0 | 237.86 | 0 | 0 | 0 | 9084.89 | 0 | 0 | 0 | 0 | 9084.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403855 | IDP WW Infra Assets West 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All West Unitary Authorities | 10539.69 | 0 | 7391.5 | 422.22 | 0 | 0 | 0 | 0 | 7813.72 | 0 | 0 | 0 | 18353.41 | 0 | 0 | 0 | 0 | 18353.41 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403856 | IDP WWPS Assets East 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-06 |  | All East Unitary Authorities | 135598.35 | 0 | 125725.88 | 15559.85 | 202.15 | 0 | 0 | 0 | 141487.88 | 0 | 0 | 0 | 277086.23 | 0 | 0 | 0 | 0 | 277086.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403858 | IDP WWPS Assets Scotland Wide 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-09-15 |  | Scottish Water Wide | 4544.36 | 0 | 1070.55 | 0 | 0 | 0 | 0 | 0 | 1070.55 | 0 | 0 | 0 | 5614.91 | 0 | 0 | 0 | 0 | 5614.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403859 | IDP WWPS Assets South 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All South Unitary Authorities | 41151.62 | 0 | 80070.25 | 1621.81 | 0 | 0 | 0 | 0 | 81692.06 | 0 | 0 | 0 | 122843.68 | 0 | 0 | 0 | 0 | 122843.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403860 | IDP WWPS Assets West 14-15 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All West Unitary Authorities | 57501.5 | 0 | 91866.5 | 416.42 | 315 | 0 | 0 | 0 | 92597.92 | 0 | 0 | 0 | 150099.42 | 0 | 0 | 0 | 0 | 150099.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402080 | IFOC Flooding Management Action Plan (FMAP) Process Phase 2 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-04-20 | 2011-06-14 | 2011-06-14 | 2012-05-25 |  | Scottish Water Wide | 1683555.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683555.13 | 0 | 0 | 0 | 0 | 1683555.13 | 0 | [6 empty] | CM_WWI | 100%
402522 | IFOC Flooding Management Action Plan (FMAP) Process Phase 3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-26 | 2012-04-24 | 2012-04-24 | 2013-08-14 |  | Scottish Water Wide | 1737334 | 0 | 23.63 | 0 | 0 | 0 | 0 | 0 | 23.63 | 0 | 0 | 0 | 1737357.63 | 0 | 0 | 0 | 0 | 1737357.63 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403354 | IFOC Flooding Management Action Plan (FMAP) Process Phase 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-18 | 2013-05-29 | 2013-05-29 | 2014-05-08 |  | Scottish Water Wide | 1686883 | 0 | 0 | -1126.16 | 0 | 0 | 0 | 0 | -1126.16 | 0 | 0 | 0 | 1685756.84 | 0 | 0 | 0 | 0 | 1685756.84 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403355 | IFOC Flooding Management Action Plan (FMAP) Process Phase 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-09-09 | 2014-03-25 | 2014-03-26 | 2015-09-21 |  | Scottish Water Wide | 1683000 | 0 | 53393.07 | 2197.4 | 102.59 | 0 | 0 | 0 | 55693.06 | 0 | 0 | 0 | 1738693.06 | 0 | 0 | 0 | 0 | 1738693.06 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510356 | IFOS - Main Street Edinburgh - 1986-11 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-04-11 | 2022-08-16 | 2022-10-17 | 2023-09-22 | 2023-09-25 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20930.23 | 20930.23 | 279069.77 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 180449.74 | [5 empty] | N | FL_DD | 100%
511080 | IFOS - Pettycur Road Kinghorn - 2101_1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-04-18 | 2023-10-25 | 2024-01-23 | 2024-12-30 | 2024-12-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000.14 | 0 | 0 | 300000.14 | 0 | 0 | 0 | 0 | 300000.14 | 180449.74 | [5 empty] | N | FL_DD | 100%
510273 | IFOS - Broomfield crescent Edinburgh - 1986-10 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-04-11 | 2022-08-16 | 2022-10-17 | 2023-09-22 | 2023-09-25 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 180449.74 | [5 empty] | N | FL_DD | 100%
508739 | IFOS - Buchlyvie Road Paisley APNRV | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS2 |  | 2020-11-20 | 2021-08-06 | 2021-10-18 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18438 | 18438 | 186562.5 | 0 | 0 | 205000.5 | 0 | 0 | 0 | 0 | 205000.5 | 175086.76 | [5 empty] | N | FL_DD | 100%
509856 | IFOS - Burn Place Dingwall 1180-3 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-03-24 | 2022-07-29 | 2022-09-29 | 2023-09-06 | 2023-09-07 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1799999.96 | 0 | 0 | 1799999.96 | 0 | 0 | 0 | 0 | 1799999.96 | 180449.74 | [5 empty] | N | FL_DD | 100%
507209 | IFOS - Burn Road Inverness - CSO | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-05-24 | 2022-09-28 | 2022-11-29 | 2023-10-17 | 2023-10-18 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114354 | 114354 | 685646.39 | 0 | 0 | 800000.39 | 0 | 0 | 0 | 0 | 800000.39 | 175086.76 | [5 empty] | N | FL_DD | 100%
503540 | IFOS - Carnegies Brae Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-05-05 | 2022-09-12 | 2022-11-14 | 2023-09-29 | 2024-01-01 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 44167.39 | 66769.61 | 110937 | 789063 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000 | 175086.76 | [5 empty] | N | FL_DD | 100%
505936 | IFOS - Culcabock Road Inverness - 1223_2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-07-08 | 2024-05-10 | 2024-08-09 | 2024-12-13 | 2024-12-16 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42959 | 42959 | 32041.32 | 0 | 0 | 75000.32 | 0 | 0 | 0 | 0 | 75000.32 | 175086.76 | [5 empty] | N | FL_DD | 100%
511313 | IFOS - Culduthel Road Inverness - 1223-3 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 | 2024-11-15 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2943.93 | 2943.93 | 47056.07 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 175086.76 | [5 empty] | N | FL_DD | 100%
508221 | IFOS - David Dale Avenue Stewarton | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-09-22 | 2023-01-27 | 2023-03-30 | 2024-10-10 | 2025-01-10 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97708.86 | 97708.86 | -97708.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | FL_DD | 100%
505339 | IFOS - East Shore Pittenweem - E1382 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-10-07 | 2022-03-14 | 2022-05-13 | 2023-03-31 | 2023-04-03 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8343.6 | 8343.6 | 991656.4 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 180449.74 | [5 empty] | N | FL_DD | 100%
510851 | IFOS - Elmwood Ave Newton Mearns - 642-1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-03-28 | 2023-10-04 | 2024-01-02 | 2024-12-09 | 2024-12-10 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000.06 | 0 | 0 | 300000.06 | 0 | 0 | 0 | 0 | 300000.06 | 180449.74 | [5 empty] | N | FL_DD | 100%
507220 | IFOS - Empire Way and Dominion Road Gretna - 347-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-05-20 | 2022-09-26 | 2022-11-25 | 2023-10-13 | 2023-10-16 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63234.79 | 63234.79 | 37193.1 | 0 | 0 | 100427.89 | 0 | 0 | 0 | 0 | 100427.89 | 175086.76 | [5 empty] | N | FL_DD | 100%
508791 | IFOS - Factory Lane Avoch | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2023-02-20 | 2023-06-27 | 2023-08-28 | 2025-03-10 | 2025-06-10 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210.42 | 1210.42 | 298953.09 | 0 | 0 | 300163.51 | 0 | 0 | 0 | 0 | 300163.51 | 180449.74 | [5 empty] | N | FL_DD | 100%
505710 | IFOS - Glengate Kirriemuir - 1759_1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-11-25 | 2023-03-27 | 2023-05-26 | 2024-04-12 | 2024-04-15 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65456 | 65456 | 34543.49 | 0 | 0 | 99999.49 | 0 | 0 | 0 | 0 | 99999.49 | 180449.74 | [5 empty] | N | FL_DD | 100%
505480 | IFOS - Happer Crescent Glenrothes - 1983_1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-01-24 | 2023-12-11 | 2024-05-20 | 2025-12-01 | 2026-03-03 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10009 | 10009 | 64991.55 | 0 | 0 | 75000.55 | 0 | 0 | 0 | 0 | 75000.55 | 175086.76 | [5 empty] | N | FL_DD | 100%
507201 | IFOS - Haugh Road Dalbeattie - 271-1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2023-02-08 | 2024-12-11 | 2025-03-12 | 2025-07-16 | 2025-07-17 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50828.52 | 50828.52 | 24171.48 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 75000 | 180449.74 | [5 empty] | N | FL_DD | 100%
505898 | IFOS - Hill St Portknockie - 1375_1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-03-28 | 2024-01-29 | 2024-04-15 | 2024-08-19 | 2024-08-20 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76290 | 76290 | -1290.14 | 0 | 0 | 74999.86 | 0 | 0 | 0 | 0 | 74999.86 | 175086.76 | [5 empty] | N | FL_DD | 100%
509858 | IFOS - Laggan Road Inverness NW31 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-03-24 | 2022-07-29 | 2022-09-29 | 2023-09-06 | 2023-09-07 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000.06 | 0 | 0 | 300000.06 | 0 | 0 | 0 | 0 | 300000.06 | 180449.74 | [5 empty] | N | FL_DD | 100%
505342 | IFOS - Mid Shore Pittenweem - E1382 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS2 | 2020-12-15 | 2021-01-15 | 2021-09-13 | 2021-11-12 | 2021-11-15 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14546 | 14546 | 50453.54 | 0 | 0 | 64999.54 | 0 | 0 | 0 | 0 | 64999.54 | 180449.74 | [5 empty] | N | FL_DD | 100%
511478 | IFOS - Moncrieff Avenue Lenzie - W481 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 |  | 2021-06-07 | 2021-06-14 | 2021-08-13 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000.02 | 0 | 0 | 45000.02 | 0 | 0 | 0 | 0 | 45000.02 | 175086.76 | [5 empty] | N | FL_DD | 100%
507447 | IFOS - Old Lanark Road Carluke 503_1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2023-01-18 | 2024-12-04 | 2025-05-14 | 2026-11-25 | 2027-02-25 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3545 | 3545 | 296454.38 | 0 | 0 | 299999.38 | 0 | 0 | 0 | 0 | 299999.38 | 180449.74 | [5 empty] | N | FL_DD | 100%
509854 | IFOS - Park Street and High Street Dingwall | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-03-24 | 2022-07-29 | 2022-09-29 | 2023-09-06 | 2023-09-07 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000 | 180449.74 | [5 empty] | N | FL_DD | 100%
510134 | IFOS - Peatville Terrace Edinburgh - E1537 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-04-12 | 2022-08-17 | 2022-10-18 | 2023-09-25 | 2023-09-26 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299999.92 | 0 | 0 | 299999.92 | 0 | 0 | 0 | 0 | 299999.92 | 180449.74 | [5 empty] | N | FL_DD | 100%
505458 | IFOS - Sandsherd Fowlis Road - NE539 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-04-04 | 2024-02-19 | 2024-07-29 | 2026-02-09 | 2026-05-12 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 86.12 | 14913.88 | 15000 | 60000.04 | 0 | 0 | 75000.04 | 0 | 0 | 0 | 0 | 75000.04 | 180449.74 | [5 empty] | N | FL_DD | 100%
509897 | IFOS - St Bridgets Brae Dalgety Bay - 1984-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2023-04-25 | 2024-10-31 | 2025-01-29 | 2026-01-06 | 2026-01-07 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20500 | 20500 | 279500 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 180449.74 | [5 empty] | N | FL_DD | 100%
503936 | IFOS - The Vennel Forfar - NE76 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-07-06 | 2022-12-06 | 2023-04-07 | 2023-12-01 | 2024-03-04 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346.06 | 6346.06 | 85000.14 | 0 | 0 | 91346.2 | 0 | 0 | 0 | 0 | 91346.2 | 175086.76 | [5 empty] | N | FL_DD | 100%
510407 | IFOS - Thornwood grove Hawick 1990-3 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-04-25 | 2022-08-30 | 2022-10-31 | 2023-10-06 | 2023-10-09 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000.06 | 0 | 0 | 300000.06 | 0 | 0 | 0 | 0 | 300000.06 | 180449.74 | [5 empty] | N | FL_DD | 100%
511102 | IFOS - Victoria Road Kirkcaldy - 1982_2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-04-18 | 2023-10-25 | 2024-01-23 | 2024-12-30 | 2024-12-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000.14 | 0 | 0 | 300000.14 | 0 | 0 | 0 | 0 | 300000.14 | 180449.74 | [5 empty] | N | FL_DD | 100%
503743 | IFOS (1769-1) - Muir Street Forfar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-11-05 | 2022-07-20 | 2022-10-10 | 2023-02-22 | 2023-04-17 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 20700 | -6361 | 14339 | 61046.58 | 0 | 0 | 75385.58 | 0 | 0 | 0 | 0 | 75385.58 | 175086.76 | [5 empty] | N | FL_DD | 100%
503596 | IFOS (225-2) - Dumbarton Road Glasgow (Dalmuir) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS2 | 2020-03-03 | 2020-03-20 | 2022-04-04 | 2022-07-06 | 2021-07-12 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 25924.67 | 8802.33 | 34727 | 40272.59 | 0 | 0 | 74999.59 | 0 | 0 | 0 | 0 | 74999.59 | 175086.76 | [5 empty] | N | FL_DD | 100%
503616 | IFOS (506-1) - Academy Road Irvine (Meadowhead) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS4 | 2020-07-09 | 2020-07-27 | 2020-12-07 | 2021-01-25 | 2021-04-01 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 23765.53 | 41826.25 | 65591.78 | 0 | 0 | 0 | 65591.78 | 0 | 0 | 0 | 0 | 65591.78 | 175086.76 | [5 empty] | N | FL_DD | 100%
503599 | IFOS (642-3) - Arthurlie Avenue Barrhead (Shieldhall) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS4 | 2020-03-03 | 2020-03-20 | 2021-02-08 | 2021-03-19 | 2021-07-13 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 25924.67 | 23252.66 | 49177.33 | 800 | 0 | 0 | 49977.33 | 0 | 0 | 0 | 0 | 49977.33 | 175086.76 | [5 empty] | N | FL_DD | 100%
507089 | IFOS- E of Scotland Farmers Ltd Forfar Road Coupar Angus-1731/1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2023-02-01 | 2024-12-18 | 2025-05-28 | 2026-12-09 | 2027-03-11 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16929 | 16929 | 283070.81 | 0 | 0 | 299999.81 | 0 | 0 | 0 | 0 | 299999.81 | 180449.74 | [5 empty] | N | FL_DD | 100%
503796 | IFOS High Street Kirkcaldy E1441 | IR18 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-03-21 | 2022-07-26 | 2022-09-26 | 2023-08-14 | 2023-08-15 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66281.99 | 66281.99 | 33743.8 | 0 | 0 | 100025.79 | 0 | 9307.4121 | 0 | 9307.4121 | 109333.2021 | 4339404.28 | [5 empty] | N | FL_DD | 100%
503698 | IFOS W628 - Muirpark Terrace Bishopbriggs (Dalmuir) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-09-02 | 2023-04-12 | 2023-08-15 | 2025-03-10 | 2025-05-01 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 24738.02 | 18255.98 | 42994 | 557005.58 | 0 | 0 | 599999.58 | 0 | 0 | 0 | 0 | 599999.58 | 175086.76 | [5 empty] | N | FL_DD | 100%
510956 | IFOS-Edward Street Dunoon - 266_2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2022-04-04 | 2023-10-11 | 2024-01-09 | 2024-12-16 | 2024-12-17 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 180449.74 | [5 empty] | N | FL_DD | 100%
501148 | Implementation of temporary solutions to internally affected properties | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2016-02-17 | 2016-02-17 | 2016-04-21 | 2016-11-29 | 2016-11-29 | Scottish Water Wide | 0 | 0 | 0 | 166282.93 | 370 | -5493.28 | 0 | 0 | 161159.65 | 0 | 0 | 0 | 161159.65 | 0 | 0 | 0 | 0 | 161159.65 | 175086.76 | [5 empty] | N | FL_DD | 100%
502936 | Implementation of temporary solutions to internally flooding affected properties Year 3 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-10-18 | 2017-10-18 | 2017-11-30 | 2019-04-29 | 2019-04-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 17155.14 | 195610.95 | -12178.59 | -1814.64 | 198772.86 | 0 | 0 | 0 | 198772.86 | 0 | 0 | 0 | 0 | 198772.86 | 175086.76 | [5 empty] | N | FL_DD | 100%
503577 | Implementation of temporary solutions to internally flooding affected properties Year 5 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS4 | 2019-05-22 | 2019-05-22 | 2019-07-24 | 2020-12-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 226355.14 | 39504.96 | 265860.1 | 1999.97 | 0 | 0 | 267860.07 | 0 | 0 | 0 | 0 | 267860.07 | 175086.76 | [5 empty] | N | FL_DD | 100%
505614 | Implementation of temporary solutions to internally flooding affected properties Year 6 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2020-03-13 | 2020-03-26 | 2021-02-02 | 2021-10-01 | 2022-01-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283846 | 283846 | 116153.88 | 0 | 0 | 399999.88 | 0 | 0 | 0 | 0 | 399999.88 | 175086.76 | [5 empty] | N | FL_DD | 100%
502423 | Implementation of temporary solutions to internally flooding affected properties Yr 2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-01-25 | 2017-01-25 | 2017-03-20 | 2018-03-02 | 2018-03-02 | Scottish Water Wide | 0 | 0 | 0 | 34559.14 | 178775 | -20286.73 | 0 | 0 | 193047.42 | 0 | 0 | 0 | 193047.42 | 0 | 0 | 0 | 0 | 193047.42 | 175086.76 | [5 empty] | N | FL_DD | 100%
403352 | Implementation of Temporary Solutions to Properties Affected by Internal Flooding Phase 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-15 | 2013-04-15 | 2013-04-15 | 2014-09-01 |  | Scottish Water Wide | 250000 | 0 | 0 | -3483.66 | 0 | 0 | 0 | 0 | -3483.66 | 0 | 0 | 0 | 246516.34 | 0 | 0 | 0 | 0 | 246516.34 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403353 | Implementation of Temporary Solutions to Properties Affected by Internal Flooding Phase 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-22 | 2014-03-25 | 2014-03-26 | 2015-12-04 |  | Scottish Water Wide | 244939 | 0 | 23210 | 0 | 0 | 0 | 0 | 0 | 23210 | 0 | 0 | 0 | 268149 | 0 | 0 | 0 | 0 | 268149 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403618 | Implementation of Temporary Solutions to Properties Affected by Internal Flooding Phase 6 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-11-11 | 2013-11-22 | 2013-11-22 | 2015-12-15 |  | Scottish Water Wide | 250039.62 | 0 | 5034.26 | 3015.57 | -214 | 0 | 0 | 0 | 7835.83 | 0 | 0 | 0 | 257875.45 | 0 | 0 | 0 | 0 | 257875.45 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400107 | Improvement To S-D Balance - Ardrishaig WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-09-28 | 2013-07-29 | 2014-03-19 | 2014-03-26 | Argyll and Bute-North Argyll | 927418 | 0 | 171.28 | 45 | 9237.5 | 0 | 0 | 0 | 9453.78 | 0 | 0 | 0 | 936871.78 | 0 | 0 | 0 | 0 | 936871.78 | 0 | [5 empty] | N | WG4 | 100%
45389 | Improvement To S-D Balance - Auchneel Barclyle Palnure Penwhirn WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-07-20 | 2012-08-20 | 2014-08-29 | 2014-09-29 | Dumfries and Galloway | 8257963 | 0 | 5322 | -3611.08 | 286 | 0 | 0 | 0 | 1996.92 | 0 | 0 | 0 | 8259959.92 | 0 | 0 | 0 | 0 | 8259959.92 | 0 | [5 empty] | N | WG4 | 100%
45390 | Improvement To S-D Balance - Black Esk Kettleton Moffat Winterhope and Langholm WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-09-26 | 2013-01-16 | 2014-06-20 | 2014-06-30 | Dumfries and Galloway | 8875802 | 0 | 95146.27 | 10288.93 | 3.71 | 0 | 0 | 0 | 105438.91 | 0 | 0 | 0 | 8981240.91 | 0 | 0 | 0 | 0 | 8981240.91 | 0 |  |  |  |  | 42445.6258 | N | WG4 | 100%
45395 | Improvement To S-D Balance - Bonar Bridge WRZ | Q&S3B | Completion | OMG180 |  |  | Water | DWQR | SWMD | OMG180 | MS7 | 2008-07-16 | 2015-03-11 | 2015-03-23 | 2017-03-31 | 2017-03-31 | Highland | 1433616.26 | 0 | 127784.74 | 766588.79 | 183701.49 | 41076.06 | -6087.41 | 0 | 1113063.67 | 0 | 0 | 0 | 2546679.93 | 0 | 0 | 0 | 0 | 2546679.93 | 0 | [5 empty] | Y | WG4 | 100% | [20 empty] | 1 | [46 empty] | 0
45385 | Improvement To S-D Balance - Broadford WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-06-20 | 2013-09-02 | 2014-12-05 | 2015-02-09 | Highland | 2636329 | 0 | 131721 | 15956.57 | 0 | 0 | 0 | 0 | 147677.57 | 0 | 0 | 0 | 2784006.57 | 0 | 0 | 0 | 0 | 2784006.57 | 0 | [5 empty] | N | WG4 | 100%
400103 | Improvement To S-D Balance - Carbost WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-06-18 | 2012-10-29 | 2013-03-25 | 2013-03-28 | Highland | 654891.77 | 0 | -2720.25 | 0 | 0 | 0 | 0 | 0 | -2720.25 | 0 | 0 | 0 | 652171.52 | 0 | 0 | 0 | 0 | 652171.52 | 119022.58 | [5 empty] | N | CM_WSNI | 21.83% | WG4 | 78.17%
45388 | Improvement To S-D Balance - Fife WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2011-08-08 | 2011-08-16 | 2014-02-06 | 2014-03-19 | Fife | 3913359 | 0 | 19324.46 | 0 | 0 | 0 | 0 | 0 | 19324.46 | 0 | 0 | 0 | 3932683.46 | 0 | 0 | 0 | 0 | 3932683.46 | 0 | [5 empty] | N | WG4 | 100%
45384 | Improvement To S-D Balance - Gorthleck WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-03-27 | 2012-06-04 | 2014-02-03 | 2014-03-19 | Highland | 4463646 | 0 | -9351.44 | 0 | 0 | 0 | 0 | 0 | -9351.44 | 0 | 0 | 0 | 4454294.56 | 0 | 0 | 0 | 0 | 4454294.56 | 0 | [5 empty] | N | WG4 | 100%
400106 | Improvement To S-D Balance - Inveraray WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-09-11 | 2013-07-29 | 2014-03-28 | 2014-03-31 | Argyll and Bute-North Argyll | 3027762 | 0 | -9896 | -18000.01 | 16146.89 | 2026.11 | 55.41 | 0 | -9667.61 | 0 | 0 | 0 | 3018094.39 | 0 | 0 | 0 | 0 | 3018094.39 | 0 | [5 empty] | N | WG4 | 100%
45383 | Improvement To S-D Balance - Inverness and Nairn WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2017-09-27 | 2017-07-03 | 2017-06-01 | 2017-07-03 | Highland | 1207584 | 0 | 443800 | 1204130.21 | 129429.82 | 0 | 0 | 0 | 1777360.03 | 0 | 0 | 0 | 2984944.03 | 0 | 0 | 0 | 0 | 2984944.03 | 0 | [5 empty] | N | WG4 | 100%
45392 | Improvement To S-D Balance - Killin WRZ | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-08-31 | 2012-12-03 | 2014-03-28 | 2014-03-31 | Stirling | 1613978 | 0 | -7128 | 790.7 | 0 | 0 | 0 | 0 | -6337.3 | 0 | 0 | 0 | 1607640.7 | 0 | 0 | 0 | 0 | 1607640.7 | 0 | [5 empty] | N | WG4 | 100%
400105 | Improvement To S-D Balance - Tarbert (Western Isles) | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-03-13 | 2012-07-23 | 2012-12-14 | 2013-03-28 | Na H-Eileanan an Iar | 891281.46 | 0 | 11422.65 | 0 | 0 | 0 | 0 | 0 | 11422.65 | 0 | 0 | 0 | 902704.11 | 0 | 0 | 0 | 0 | 902704.11 | 0 | [5 empty] | N | WG4 | 100%
500042 | Improvement to Supply/Demand Balance - South Uist WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS7 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-25 | 2016-08-26 | Na H-Eileanan an Iar | 0 | 0 | 27596 | -27596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG4 | 100%
500043 | Improvement to Supply-Demand Balance - Benbecula WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | NONINF | SOSI | MS6 | 2016-03-29 | 2017-12-22 | 2017-12-22 | 2019-06-30 | 2019-06-30 | Na H-Eileanan an Iar | 302.76 | 302.76 | 43756.68 | 237292.44 | 526588.9 | 513198.19 | 77842.77 | -36283.73 | 1362395.25 | -7043.55 | -7043.549 | -9777.6451 | 1355654.46 | -2734.0961 | 0 | 0 | -2734.0961 | 1352920.3639 | 761457.15 |  |  |  |  | 15247.05 | Y | WG4 | 100% | [25 empty] | 1 | [41 empty] | 0
500041 | Improvement to Supply-Demand Balance - Lochinver WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | SWMD | SOSI | MS6 | 2016-10-10 | 2017-09-29 | 2018-02-26 | 2018-09-30 | 2019-01-31 | Highland | 127.3 | 127.3 | 15472.7 | 19109.32 | 214411.51 | 490774.52 | -3616.55 | 221.63 | 736373.13 | 0 | 0 | 0 | 736500.43 | 0 | 0 | 0 | 0 | 736500.43 | 1062422.7 | [5 empty] | Y | WG4 | 100% | [25 empty] | 1 | [41 empty] | 0
500048 | Improvement to Supply-Demand Balance - Mallaig WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | SWD | SOSI | MS7 | 2015-02-23 | 2015-03-18 | 2015-03-18 | 2015-04-30 | 2015-12-31 | Highland | 0 | 0 | 1150 | -895.75 | 0 | 0 | 0 | 0 | 254.25 | 0 | 0 | 0 | 254.25 | 0 | 0 | 0 | 0 | 254.25 | 375898.29 | [5 empty] | Y | WG4 | 100% | [25 empty] | 1 | [41 empty] | 0
500032 | Improvement to Supply-Demand Balance - North Hoy WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | SWMD | SOSI | MS6 | 2017-03-31 | 2017-12-22 | 2018-03-26 | 2018-12-19 | 2019-03-27 | Orkney Islands | 24.93 | 24.93 | 47754.46 | 131072.47 | 1567095.98 | 206236.33 | 92321.01 | 7951.18 | 2052431.43 | 0 | 0 | 0 | 2052456.36 | 0 | 0 | 0 | 0 | 2052456.36 | 4557528.27 | [5 empty] | N | WG4 | 100%
500033 | Improvement to Supply-Demand Balance - Sandy Loch WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS7 | 2019-09-25 | 2019-09-16 | 2019-09-16 | 2019-08-16 | 2019-08-16 | Shetland Islands | 686.11 | 686.11 | 42999.07 | -43685.18 | 394.84 | 0 | 160 | 0 | -131.27 | 0 | 0 | 0 | 554.84 | 0 | 0 | 0 | 0 | 554.84 | 3250279.58 | [5 empty] | N | WG4 | 100%
500046 | Improvement to Supply-Demand Balance - Stornoway WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | WINF | SOSI | MS0 | 2018-09-28 | 2022-03-14 | 2022-10-07 | 2023-11-01 | 2024-01-30 | Na H-Eileanan an Iar | 0 | 0 | 53505.94 | 61798.03 | 40362.52 | 72120.81 | 162207.05 | 190235.54 | 580229.88 | 2927244.35 | 2927244.35 | 4063513.5085 | 3507474.23 | 1136269.1585 | 0 | 0 | 1136269.1585 | 4643743.3885 | 969103.43 | [5 empty] | Y | WG4 | 100% | [25 empty] | 1 | [41 empty] | 0
500034 | Improvement to Supply-Demand Balance - Tullich WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | SWMD | SOSI | MS6 | 2016-10-31 | 2018-03-21 | 2018-06-26 | 2019-03-31 | 2019-09-30 | Argyll and Bute-North Argyll | 105.42 | 105.42 | 11237.68 | 31714.6 | 23573.82 | 201544.43 | -953.63 | 0 | 267116.9 | 0 | 0 | 0 | 267222.32 | 0 | 0 | 0 | 0 | 267222.32 | 696780.05 | [5 empty] | Y | WG4 | 100% | [25 empty] | 1 | [41 empty] | 0
500044 | Improvement to Supply-Demand Balance - Waternish WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | SWD | SOSI | MS7 | 2018-09-28 | 2018-12-17 | 2018-12-17 | 2018-12-31 | 2019-03-31 | Highland | 148.01 | 148.01 | 10265.99 | 0 | 963.75 | 7934.54 | 36383.22 | 0 | 55547.5 | 0 | 0 | 0 | 55695.51 | 0 | 0 | 0 | 0 | 55695.51 | 555910.14 | [5 empty] | Y | WG4 | 100% | [25 empty] | 1 | [41 empty] | 0
500045 | Improvement to Supply-Demand Balance - West Lewis WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS5 | 2016-03-29 | 2021-04-01 | 2019-05-20 | 2019-05-20 | 2019-05-20 | Na H-Eileanan an Iar | 471.4 | 471.4 | 54181.41 | 395305.6 | 226128.06 | 11180.7 | 0 | 25893.71 | 712689.48 | 36839.12 | 36839.117 | 51138.9661 | 750000 | 14299.8491 | 0 | 0 | 14299.8491 | 764299.8491 | 258568.71 | [5 empty] | N | WG4 | 100%
402842 | Improvement work to various WwTWs to improve CAS compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-09-14 | 2015-05-11 | 2015-01-12 | 2015-09-18 |  | Scottish Water Wide | 370193.69 | 0 | 317710.15 | 91.88 | 529.69 | 0 | 0 | 0 | 318331.72 | 0 | 0 | 0 | 688525.41 | 0 | 0 | 0 | 0 | 688525.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS6 | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-09-06 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 3426.41 | 258352.68 | 1699284.75 | 803926.7 | 103314.09 | -57046.54 | 2811258.09 | 6982.08 | 4349.1376 | 6037.3435 | 2818240.17 | 1688.2059 | 0 | 0 | 1688.2059 | 2819928.3759 | 1041848.81 | [5 empty] | N | CM_WSNI | 37.71% | DW25T | 62.29%
501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-08-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 24418 | 4917 | -20331.05 | 0 | 9003.95 | 0 | 0 | 0 | 9003.95 | 0 | 0 | 0 | 0 | 9003.95 | 922826.22 | [5 empty] | N | DW25T | 100%
501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS3 | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2022-01-21 | 2022-03-01 | Scottish Water Wide | 0 | 0 | 15069.77 | 24435.68 | 345517.01 | 1121617.78 | 885260.58 | 330251.71 | 2722152.53 | 957307.19 | 622249.6735 | 759371.2652 | 3679459.72 | 137121.5917 | 0 | 28827.1496 | 165948.7413 | 3845408.4613 | 1041848.81 | [5 empty] | N | CM_WSNI | 35% | DW25T | 65%
501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-27 | 2018-12-14 | Scottish Water Wide | 0 | 0 | 15069.77 | 23441.86 | -2511.63 | 0 | -5895.75 | 0 | 30104.25 | 0 | 0 | 0 | 30104.25 | 0 | 0 | 0 | 0 | 30104.25 | 922826.22 | [5 empty] | N | DW25T | 100%
501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS3 | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2021-04-30 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 32167.33 | 43960.24 | 0 | 0 | -20513 | 55614.57 | 11600.76 | 11600.76 | 20094.597 | 67215.33 | 8493.837 | 0 | 0.003 | 8493.84 | 75709.17 | 922826.22 | [5 empty] | N | DW25T | 100%
501116 | Improving resilience of supplies - Backies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | SWD | Supply Resilience | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-31 | 2016-05-31 | Highland | 0 | 0 | 7116.28 | 0 | 0 | 0 | 0 | 0 | 7116.28 | 0 | 0 | 0 | 7116.28 | 0 | 0 | 0 | 0 | 7116.28 | 1989709.51 | [5 empty] | Y | CS16WR | 100% | [24 empty] | 1 | [42 empty] | 0
501115 | Improving resilience of supplies - Howden | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | WINF | Supply Resilience | MS6 | 2016-09-20 | 2018-03-29 | 2018-03-29 | 2019-06-30 | 2019-09-30 | Scottish Borders | 0 | 0 | 21600 | 133675 | 569454 | 2709796.42 | 184181.6 | -149941.93 | 3468765.09 | 149941.93 | 74970.9636 | 104072.461 | 3618707.02 | 29101.4974 | 0 | 0 | 29101.4974 | 3647808.5174 | 2434475.54 | [5 empty] | Y | CS16WR | 50% | WG5 | 50% | [22 empty] | 1 | [42 empty] | 0
501041 | Improving Resilience of Supplies - Kirbister | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | SWD | Supply Resilience | MS7 | 2016-02-29 | 2016-03-11 | 2016-03-11 | 2016-03-31 | 2016-05-31 | Orkney Islands | 0 | 0 | 7027.31 | 0 | 0 | 0 | 0 | 0 | 7027.31 | 0 | 0 | 0 | 7027.31 | 0 | 0 | 0 | 0 | 7027.31 | 1989709.51 | [5 empty] | Y | CS16WR | 100% | [24 empty] | 1 | [42 empty] | 0
500973 | Improving Resilience of Supplies - Westray | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | NONINF | Supply Resilience | MS7 | 2016-03-17 | 2017-03-31 | 2017-06-30 | 2018-12-31 | 2019-03-31 | Orkney Islands | 0 | 0 | 13249.92 | 595494.23 | 314930.7 | 699443.05 | 12952.1 | -40256.91 | 1595813.09 | 0 | 0 | 0 | 1595813.09 | 0 | 0 | 0 | 0 | 1595813.09 | 1989709.51 | [5 empty] | Y | CS16WR | 100% | [24 empty] | 1 | [42 empty] | 0
500733 | Improving resilience of supplies at Invercannie | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | SWD | Supply Resilience | MS7 | 2015-08-25 | 2016-03-22 | 2016-03-22 | 2016-12-31 | 2017-03-31 | All North Unitary Authorities | 0 | 0 | 35000 | -8280.32 | -3471.55 | 0 | 10.74 | 0 | 23258.87 | 0 | 0 | 0 | 23258.87 | 0 | 0 | 0 | 0 | 23258.87 | 1989709.51 | [5 empty] | Y | CS16WR | 100% | [24 empty] | 1 | [42 empty] | 0
401262 | Incentivising Developers to Adopt Water Efficiency Measures | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-09-15 | 2015-03-11 | 2015-03-11 | 2015-07-13 | 2015-07-13 | Scottish Water Wide | 958741 | 0 | 7703.71 | 0 | 0 | 0 | 0 | 0 | 7703.71 | 0 | 0 | 0 | 966444.71 | 0 | 0 | 0 | 0 | 966444.71 | 0 | [5 empty] | N | CS18W | 100%
510110 | Inchgarth Fencing Repairs and vegetation clearance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-12-17 | 2021-06-21 | 2022-02-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1277 | 1277 | 8722.84 | 0 | 0 | 9999.84 | 0 | 0 | 0 | 0 | 9999.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510995 | Inchgarth RWI - Intake Baskets Remedial Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24331.87 | 24331.87 | 475668.13 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 119022.58 | [5 empty] | N | CM_WSI | 100%
501257 | Inchgarth RWI High-Lift Pumps - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS4 | 2016-08-15 | 2018-05-31 | 2018-06-05 | 2020-12-07 |  | Aberdeenshire | 0 | 0 | 22853.75 | 23497.75 | 601684.13 | 923785.01 | 642794.6 | 197825.76 | 2412441 | 69745.79 | 0 | 0 | 2482186.79 | 0 | 0 | 0 | 0 | 2482186.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
46198 | Inchgarth RWI Refurb - RWI000723 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2010-09-27 | 2011-05-30 | 2011-12-23 |  | Aberdeenshire | 1059999.17 | 0 | 72.76 | 0 | 0 | 0 | 0 | 0 | 72.76 | 0 | 0 | 0 | 1060071.93 | 0 | 0 | 0 | 0 | 1060071.93 | 119022.58 | [5 empty] | N | CM_WSI | 100%
502630 | Inchgarth RWP - Replace Permanent Standby Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-03-14 | 2017-07-28 | 2017-09-11 | 2018-05-03 |  | Aberdeen City | 0 | 0 | 0 | 5981.31 | 1792983.87 | 48637.64 | 636.94 | 1506.24 | 1849746 | 857.1 | 0 | 0 | 1850603.1 | 0 | 0 | 0 | 0 | 1850603.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503370 | Inchinnan WwPS - Replacement Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2020-05-27 | 2021-11-09 | 2022-03-14 | 2022-12-08 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 12383.48 | 19956.56 | 17780.96 | 50121 | 515601.5 | 0 | 0 | 565722.5 | 0 | 0 | 0 | 0 | 565722.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
45335 | Inchlaggan WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-11-18 | 2012-03-09 | 2012-03-30 | Highland | 41220.72 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 41241.72 | 0 | 0 | 0 | 0 | 41241.72 | 28761.13 | [5 empty] | N | DW13 | 100%
506794 | Inchmarlo Firbog DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-10 | 2021-08-06 | 2022-03-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503275 | Inchmarlo WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2020-10-30 | 2022-12-27 | 2023-03-28 | 2024-05-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 83449.24 | 33509.88 | 53106.88 | 170066 | 2564692.2 | 0 | 0 | 2734758.2 | 0 | 0 | 0 | 0 | 2734758.2 | 122419.09 | [5 empty] | N | SG1 | 100%
505534 | Industrial Emissions Directive (IED) - Study | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS2 | 2020-03-13 | 2020-06-05 | 2021-07-14 | 2022-01-12 | 2022-04-14 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 9813.08 | 461791.33 | 471604.41 | 150395.59 | 0 | 0 | 622000 | 0 | 0 | 0 | 0 | 622000 | 0 | [5 empty] | N | SR21_WW | 100%
500591 | Industry Applications Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-11-18 | 2016-06-30 | 2016-06-30 | 2021-06-30 |  | Scottish Water Wide | 0 | 0 | 185131 | 339196.8 | 194102.15 | 166354.73 | -5651.79 | 12417.42 | 891550.31 | 0 | 0 | 0 | 891550.31 | 0 | 0 | 0 | 0 | 891550.31 | 613322.63 | [5 empty] | N | CM_M&G | 100%
504066 | Information Compliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2020-01-06 | 2020-03-20 | 2020-03-20 | 2020-09-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 435922.5 | 152430.74 | 588353.24 | 0 | 0 | 0 | 588353.24 | 0 | 0 | 0 | 0 | 588353.24 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500593 | Information Management Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-09-17 | 2016-12-22 | 2016-12-22 | 2021-03-02 |  | Scottish Water Wide | 0 | 0 | 496728 | 121999.92 | 330491.88 | 105818.78 | 58853.73 | 0 | 1113892.31 | 0 | 0 | 0 | 1113892.31 | 0 | 0 | 0 | 0 | 1113892.31 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500676 | Information Management SharePoint Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-05 | 2017-09-01 | 2017-09-01 | 2020-03-03 |  | Scottish Water Wide | 0 | 0 | 382234.46 | 1059259.67 | 1270328.94 | 730971.26 | 432055.35 | 82334.3 | 3957183.98 | 0 | 0 | 0 | 3957183.98 | 0 | 0 | 0 | 0 | 3957183.98 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503357 | INFRA - Banchory Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2019-03-11 | 2019-03-11 | 2020-01-30 | 2021-04-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 29439.25 | 362000 | 218560.75 | 610000 | 0 | 0 | 0 | 610000 | 0 | 0 | 0 | 0 | 610000 | 444766.03 | [5 empty] | N | WG5 | 100%
503435 | INFRA - Banknock | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2019-04-08 | 2019-04-08 | 2020-02-13 | 2022-06-28 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 47223.32 | 27.55 | 47250.87 | 700179.29 | 0 | 0 | 747430.16 | 0 | 0 | 0 | 0 | 747430.16 | 1470767.03 | [5 empty] | N | SG5 | 100%
503436 | INFRA - Elgin - Waste | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS0 | 2019-07-31 | 2021-09-06 | 2021-09-28 | 2022-10-07 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 13084.11 | 220.4 | 13304.51 | 1986695.44 | 0 | 0 | 1999999.95 | 0 | 0 | 0 | 0 | 1999999.95 | 1470767.03 | [5 empty] | N | SG5 | 100%
503360 | INFRA - Johnshaven & St Cyrus Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW2 | 2022-11-22 | 2023-01-11 | 2023-03-08 | 2025-09-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 40204.52 | 179.08 | 40383.6 | 1959616.68 | 0 | 0 | 2000000.28 | 0 | 0 | 0 | 0 | 2000000.28 | 444766.03 | [5 empty] | N | WG5 | 100%
503518 | INFRA -SR15 Development - Programme Overhead | Q&S4 | Supporting economic development | Infra Charge |  |  | General |  | SWD | Infra Charge | MS3 | 2019-05-14 | 2019-05-14 | 2019-06-28 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 6757778.67 | 2322508.67 | 9080287.34 | 0 | 0 | 0 | 9080287.34 | 0 | 0 | 0 | 0 | 9080287.34 | 1915533.05 | [5 empty] | N | SG5 | 50% | WG5 | 50%
503362 | Infra-Kingdom Park | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2019-03-28 | 2019-03-28 | 2020-02-13 | 2022-05-05 |  | Fife | 0 | 0 | 0 | 0 | 0 | 60797 | 134768.47 | 696730.13 | 892295.6 | 607789.82 | 0 | 0 | 1500085.42 | 0 | 0 | 120006.8325 | 120006.8325 | 1620092.2525 | 0 | [5 empty] | N | SG5 | 100%
503358 | INFRA-Newmills - Edinburgh | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2019-05-28 | 2019-05-28 | 2019-05-28 | 2021-06-30 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 455541.4 | 202536.89 | 658078.29 | 0 | 0 | 0 | 658078.29 | 0 | 0 | 0 | 0 | 658078.29 | 444766.03 | [5 empty] | N | WG5 | 100%
500954 | Infrastructure Monitoring Tools Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-23 | 2015-12-14 | 2015-12-14 | 2017-06-23 |  | Scottish Water Wide | 0 | 0 | 286124 | 52979.45 | 0 | 0 | 0 | 0 | 339103.45 | 0 | 0 | 0 | 339103.45 | 0 | 0 | 0 | 0 | 339103.45 | 306661.32 | [5 empty] | N | CM_M&G | 100%
403909 | Infrastructure Prog Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-09-05 | 2014-09-05 | 2014-09-05 | 2015-06-30 |  | Scottish Water Wide | 261711 | 0 | 4072.61 | 0 | 0 | 0 | 0 | 0 | 4072.61 | 0 | 0 | 0 | 265783.61 | 0 | 0 | 0 | 0 | 265783.61 | 613322.63 | [5 empty] | N | CM_M&G | 100%
508494 | Infrastructure Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS0 | 2020-12-09 | 2021-06-07 | 2021-10-06 | 2024-05-29 | 2024-05-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86397 | 86397 | 537150.63 | 0 | 0 | 623547.63 | 0 | 0 | 0 | 0 | 623547.63 | 0 | [5 empty] | N | SR21_SS | 100%
510727 | Infrastructure Tactical Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | GW0 | 2021-04-30 | 2021-08-02 | 2021-09-06 | 2021-11-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 30000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501532 | Innellan Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-06-07 | 2029-10-11 | 2030-02-20 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237339.99 | 0 | 0 | 237339.99 | 0 | 0 | 0 | 0 | 237339.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502572 | Innerleithen WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-07-06 | 2020-07-06 | 2020-07-06 | 2020-07-13 |  | Scottish Borders | 0 | 0 | 0 | 20930.23 | 2091.45 | 45128.41 | 3442.97 | 43.06 | 71636.12 | 0 | 0 | 0 | 71636.12 | 0 | 0 | 0 | 0 | 71636.12 | 122419.09 | [5 empty] | N | WG1 | 100%
45409 | Innerleithen WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-03-16 | 2011-10-03 | 2015-03-27 | 2015-12-17 | Scottish Borders | 4230414.8 | 0 | 217150.56 | 33919.75 | -32156.47 | -9436.03 | 0 | 0 | 209477.81 | 0 | 0 | 0 | 4439892.61 | 0 | 0 | 0 | 0 | 4439892.61 | 57522.26 |  |  |  |  | 31638 | N | CS16W | 1.577% | DW23 | 98.42%
501512 | INSH WWTW 1996 NH809016 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2020-03-24 | 2021-12-01 | 2022-01-10 | 2022-06-10 |  | Highland | 0 | 0 | 0 | 0 | 25324.23 | 28245.63 | 14776.7 | 80882.54 | 149229.1 | 525770.89 | 0 | 0 | 674999.99 | 0 | 0 | 0 | 0 | 674999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403960 | Installation of Auto-samplers | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2014-11-10 | 2015-04-20 | 2015-05-11 | 2017-03-08 | 2017-04-13 | Scottish Water Wide | 85123 | 0 | 2573932 | 291248 | 38056 | -4671.37 | 0 | 0 | 2898564.64 | 0 | 0 | 0 | 2983687.64 | 0 | 0 | 0 | 0 | 2983687.64 | 0 | [5 empty] | N | EC01A | 100%
500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water | SW | SWD | Renewable power | MS7 | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2018-05-11 | 2018-05-11 | Scottish Water Wide | 0 | 0 | 791122.51 | 793.12 | 0 | 0 | 0 | 0 | 791915.63 | 0 | 0 | 0 | 791915.63 | 0 | 0 | 0 | 0 | 791915.63 | 1525750.06 | [5 empty] | N | I2S_WI | 100%
401676 | Intelligent Control Centre - Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-02-04 | 2012-09-05 | 2012-09-18 | 2016-08-08 |  | Scottish Water Wide | 15017167 | 0 | 207275 | -1133.9 | 35.59 | 0 | 0 | 0 | 206176.69 | 0 | 0 | 0 | 15223343.69 | 0 | 0 | 0 | 0 | 15223343.69 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503395 | Interim THM and Cryptosporidium measures - MD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-09-06 | 2019-06-20 | 2019-05-21 | 2019-05-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
503394 | Interim THM and Cryptosporidium Measures - SWD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-08-24 | 2018-09-04 | 2018-09-04 | 2021-06-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 233115.61 | 503240.61 | 76095.78 | 812452 | 17548.42 | 0 | 0 | 830000.42 | 0 | 0 | 0 | 0 | 830000.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402351 | Internal Flooding Aberdeen Harbour Area | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-09-20 | 2012-06-27 | 2012-08-27 | 2013-02-27 | 2013-02-27 | Aberdeen City | 92563.76 | 0 | 85.66 | 0 | 0 | 0 | 0 | 0 | 85.66 | 0 | 0 | 0 | 92649.42 | 0 | 0 | 0 | 0 | 92649.42 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
402390 | Internal Flooding Ardgay Street Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2014-07-22 | 2014-07-30 | 2014-09-22 | 2014-09-22 | Glasgow City | 322018 | 0 | 0 | 0 | 0 | -921.74 | 0 | 0 | -921.74 | 0 | 0 | 0 | 321096.26 | 0 | 0 | 0 | 0 | 321096.26 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
402448 | Internal Flooding at Burns Statue Square Ayr | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-05 | 2012-09-14 | 2012-11-21 | 2013-12-10 | 2013-12-10 | South Ayrshire | 20111 | 0 | -215.05 | 0 | 0 | 0 | 0 | 0 | -215.05 | 0 | 0 | 0 | 19895.95 | 0 | 0 | 0 | 0 | 19895.95 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
402449 | Internal Flooding at City Road Dundee | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-05 | 2012-06-27 | 2012-08-27 | 2012-12-20 | 2012-12-20 | Dundee City | 27349.74 | 0 | 46.35 | 0 | 0 | 0 | 0 | 0 | 46.35 | 0 | 0 | 0 | 27396.09 | 0 | 0 | 0 | 0 | 27396.09 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
402442 | Internal Flooding at Don Street Forfar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2011-12-07 | 2015-01-09 | 2015-01-26 | 2015-03-13 | 2015-03-13 | Angus | 191645 | 191645 | -16175.5 | 0 | 48.04 | 0 | 0 | 0 | -16127.46 | 0 | 0 | 0 | 175517.54 | 0 | 0 | 0 | 0 | 175517.54 | 180449.74 | [5 empty] | N | FL_DD | 100%
402445 | Internal Flooding at Rattray Gardens Bathgate | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-02 | 2013-07-22 | 2013-10-14 | 2014-06-30 | 2014-06-30 | West Lothian | 522906.49 | 0 | 1516.7 | 0 | 0 | 0 | 0 | 0 | 1516.7 | 0 | 0 | 0 | 524423.19 | 0 | 0 | 0 | 0 | 524423.19 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
402657 | Internal Flooding at Roseangle Dundee | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-05-18 | 2013-07-12 | 2013-07-29 | 2016-11-25 | 2016-11-25 | Dundee City | 106546 | 0 | 5170 | -1282.98 | -16369.3 | 0 | 0 | 0 | -12482.28 | 0 | 0 | 0 | 94063.72 | 0 | 0 | 0 | 0 | 94063.72 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
402655 | Internal Flooding at Russel Drive Bearsden | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2012-04-23 | 2019-06-12 | 2019-06-12 | 2019-06-12 | 2021-04-01 | Glasgow City | 57171 | 57171 | 0 | 3829 | 2000 | 2000 | 22730.69 | -239.23 | 30320.46 | 0 | 0 | 0 | 87491.46 | 0 | 0 | 0 | 0 | 87491.46 | 180449.74 | [5 empty] | N | FL_DD | 100%
402447 | Internal Flooding at Townhead Catrine Mauchline | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-05 | 2013-06-20 | 2014-01-27 | 2014-03-28 | 2014-03-28 | East Ayrshire | 207982 | 0 | -2322.39 | 0 | 53.04 | 0 | 0 | 0 | -2269.35 | 0 | 0 | 0 | 205712.65 | 0 | 0 | 0 | 0 | 205712.65 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
403292 | Internal Sewer Flooding APRNV Programme Phase1 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-02-20 | 2013-03-20 | 2013-04-25 | 2015-11-02 | 2016-01-05 | Scottish Water Wide | 1956539 | 0 | 29488 | 45029.29 | -625.1 | 0 | 0 | 0 | 73892.19 | 0 | 0 | 0 | 2030431.19 | 0 | 0 | 0 | 0 | 2030431.19 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
500715 | Interruptions to Supply Proactive Management | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWD | Interruptions to Supply | MS7 | 2015-06-30 | 2015-06-30 | 2016-02-01 | 2018-10-31 | 2018-10-31 | Scottish Water Wide | 0 | 0 | 365730 | 194009.85 | 138748.36 | 0 | 0 | 0 | 698488.21 | 0 | 0 | 0 | 698488.21 | 0 | 0 | 0 | 0 | 698488.21 | 941431.82 | [5 empty] | N | CS12 | 100%
507210 | Inveraray Saline Intrusion Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2020-09-16 | 2021-02-23 | 2021-02-23 | 2022-04-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 30000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403515 | Inveraray STW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-06-26 | 2015-02-16 | 2015-06-02 | 2015-10-07 | 2015-10-07 | Argyll and Bute-North Argyll | 40890 | 0 | 150152 | 812.93 | -346 | 0 | 0 | 0 | 150618.93 | 0 | 0 | 0 | 191508.93 | 0 | 0 | 0 | 0 | 191508.93 | 0 | [5 empty] | N | SG1 | 100%
502882 | Inveraray WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-05-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 21238 | 1824.51 | -19016.59 | 0 | 4045.92 | 0 | 0 | 0 | 4045.92 | 0 | 0 | 0 | 0 | 4045.92 | 122419.09 | [5 empty] | N | WG1 | 100%
500826 | Inverasdale RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-11-17 | 2016-03-25 | 2016-10-03 | 2017-06-30 | 2018-03-31 | Highland | 0 | 0 | 5471.98 | 15794.66 | 25561.64 | 4438.09 | 12564.52 | 0 | 63830.89 | 0 | 0 | 0 | 63830.89 | 0 | 0 | 0 | 0 | 63830.89 | 56543 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 26.77 | [43 empty] | 0
34831 | Invercannie - Mannofield WRZ-WFD Compliance | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-15 | 2010-11-05 | 2011-01-06 | 2012-03-23 | 2012-03-23 | Aberdeenshire | 4773284 | 0 | 448.31 | 0 | 0 | 0 | 0 | 0 | 448.31 | 0 | 0 | 0 | 4773732.31 | 0 | 0 | 0 | 0 | 4773732.31 | 147783.71 | [5 empty] | N | WSNI | 20.96% | WR1 | 79.04%
501619 | Invercannie 1866 - Uppermill of Crathes Culvert Crossing Repairs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWMD | DWQ Compliance | MS6 | 2016-03-25 | 2016-06-01 | 2016-06-01 | 2016-12-31 |  | Aberdeenshire | 0 | 0 | 2323.88 | 63676.12 | 0 | 2520 | 1712.21 | 2260.02 | 72492.23 | 0 | 0 | 0 | 72492.23 | 0 | 0 | 0 | 0 | 72492.23 | 401415.27 | [5 empty] | Y | DW25P | 100% | [67 empty] | 0
503479 | Invercannie 1866 Aqueduct - Vegetation Intrusion | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-11-15 | 2022-08-04 | 2022-10-12 | 2023-02-28 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403952 | Invercannie East DIR Cleaning Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-10-06 | 2014-10-06 | 2014-11-03 | 2015-02-05 |  | Aberdeenshire | 145523 | 0 | 9620 | 0.04 | -599.35 | 0 | 0 | 0 | 9020.69 | 0 | 0 | 0 | 154543.69 | 0 | 0 | 0 | 0 | 154543.69 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509158 | Invercannie Mannofield to Turriff Resilience | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-08-25 | 2024-12-26 | 2025-03-31 | 2027-06-09 | 2028-06-09 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25564.95 | 25564.95 | 4974435.05 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | [5 empty] | N | SR21_WA | 100%
503123 | Invercannie WTW - Augmentation 5mld | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-10-29 | 2020-10-29 | 2020-11-02 | 2020-11-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 2989.2 | 58205.73 | 69295.85 | 4623.98 | 135114.74 | 0 | 0 | 0 | 135114.74 | 0 | 0 | 0 | 0 | 135114.74 | 0 | [5 empty] | N | WG1 | 100%
502330 | Invercannie WTW - Catchment Survey and Monitoring | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-29 | 2016-09-29 | 2017-08-01 | 2020-12-09 | 2021-02-11 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 74.17 | 300.01 | 0 | 374.17 | 0 | 0 | 0 | 374.17 | 0 | 0 | 0 | 0 | 374.17 | 128372.27 | [5 empty] | N | DW25P | 100%
502166 | Invercannie WTW - Cleaning of Invercannie West DIR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS7 | 2016-03-25 | 2016-06-01 | 2016-06-01 | 2016-12-31 | 2020-05-07 | Aberdeenshire | 0 | 0 | 0 | 40126.31 | 1077618.96 | 149677.34 | 1590.13 | -11637.77 | 1257374.97 | 0 | 0 | 0 | 1257374.97 | 0 | 0 | 0 | 0 | 1257374.97 | 128372.27 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
502756 | Invercannie WTW - CWT | IR18 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | MPT | DWQ Compliance | MS7 | 2019-01-22 | 2020-07-01 | 2020-07-03 | 2020-07-03 | 2020-12-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 177570.91 | 489468.18 | -667039.08 | 4624 | 4624 | 0 | 0 | 0 | 4624 | 0 | 0 | 0 | 0 | 4624 | 8695235.16 | [5 empty] | N | DW25P | 100%
502480 | Invercannie WTW - PLC Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-02-23 | 2017-02-23 | 2017-04-12 | 2019-02-19 |  | Aberdeenshire | 0 | 0 | 0 | 300779.3 | 1217634.86 | 565517.41 | 2836.14 | -1135.27 | 2085632.44 | 0 | 0 | 0 | 2085632.44 | 0 | 0 | 0 | 0 | 2085632.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401872 | Invercannie WTW and 1924 Aqueduct Investigation - Intervention Development | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-23 | 2012-09-27 | 2012-10-17 | 2014-08-29 |  | Aberdeenshire | 77235 | 0 | 3848 | -214.01 | 0 | 0 | 0 | 0 | 3633.99 | 0 | 0 | 0 | 80868.99 | 0 | 0 | 0 | 0 | 80868.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501243 | Invercannie WTW Pre-Treatment CWT and CM | IR18 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS3 | 2019-02-08 | 2020-02-28 | 2020-03-16 | 2023-01-05 | 2024-03-14 | Aberdeenshire | 0 | 0 | 158593.32 | 27727.57 | 268382.76 | 444017.61 | 7997042.98 | 20468045.44 | 29363809.68 | 26898216 | 30636190.32 | 30636190.32 | 56262025.68 | 0 | 3737974.32 | 0 | 3737974.32 | 60000000 | 6784612.62 | [5 empty] | N | DW23 | 100%
503838 | Inverclyde DOA - SIlverwells Culvert Flows Diversion | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-10-30 | 2020-12-02 | 2021-07-06 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 5435.18 | 20681.82 | 26117 | 38883 | 0 | 0 | 65000 | 0 | 0 | 0 | 0 | 65000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500140 | Inverclyde DOA (DOA000454) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS5 | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2020-06-30 | 2020-10-30 | Inverclyde | 0 | 0 | 49028 | 451618 | 215673.38 | 215043.9 | 150626.62 | 61091.1 | 1143081 | 36919.26 | 36919.26 | 51250.2182 | 1180000.26 | 14330.9582 | 0 | 0 | 14330.9582 | 1194331.2182 | 485999.5 | [5 empty] | N | EC01G | 2.1% | EC01D | 19.34% | CS11 | 21.15% | CS16D | 57.41%
506600 | Inverclyde DOA Pembroke Road - Sewer Trap Repair/replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-05-20 | 2020-07-13 | 2021-02-22 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68333 | 68333 | 26667.32 | 0 | 0 | 95000.32 | 0 | 0 | 0 | 0 | 95000.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506776 | Inverclyde DOA Skelmorlie - Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-06-03 | 2020-07-15 | 2020-07-20 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85886.22 | 85886.22 | 0 | 0 | 0 | 85886.22 | 0 | 0 | 0 | 0 | 85886.22 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506607 | Invergarry Pipe Bridge Diversion | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-05-19 | 2020-11-27 | 2021-05-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172937 | 172937 | 999.99 | 0 | 0 | 173936.99 | 0 | 0 | 0 | 0 | 173936.99 | 311236.79 | [5 empty] | N | WSI | 100%
500827 | Invergarry RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2017-03-23 | 2017-06-02 | 2017-12-31 | 2018-06-30 | Highland | 0 | 0 | 3000 | -689.01 | 10352.03 | 11494.28 | 0 | -1391.87 | 22765.43 | 0 | 0 | 0 | 22765.43 | 0 | 0 | 0 | 0 | 22765.43 | 21335.14 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 3.36 | [43 empty] | 0
508851 | Invergarry Site drainage improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-09-28 | 2021-07-12 | 2022-02-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1580 | 1580 | 18420.23 | 0 | 0 | 20000.23 | 0 | 0 | 0 | 0 | 20000.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502314 | Invergowrie Burnside Road SPS and Tayport WWTW River Modelling | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-10-31 | 2017-05-31 | 2017-07-27 | 2018-06-29 |  | All East Unitary Authorities | 0 | 0 | 0 | 4602.93 | 96498 | 36524.58 | 0 | 0 | 137625.51 | 0 | 0 | 0 | 137625.51 | 0 | 0 | 0 | 0 | 137625.51 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45811 | Invergowrie SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-12-05 | 2012-02-13 | 2012-08-01 | 2012-08-21 | Perth and Kinross | 171036.3 | 0 | 14.5 | 0 | 0 | 0 | 0 | 0 | 14.5 | 0 | 0 | 0 | 171050.8 | 0 | 0 | 0 | 0 | 171050.8 | 28761.13 | [5 empty] | N | WQ01C | 100%
400720 | Inverkeilor WWTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2012-01-23 | 2012-06-04 | 2014-12-04 | 2014-12-04 | Angus | 734267 | 0 | -15237.57 | 5654.79 | 8071.21 | 1342.72 | 0 | 0 | -168.85 | 0 | 0 | 0 | 734098.15 | 0 | 0 | 0 | 0 | 734098.15 | 122419.09 | [5 empty] | N | SG1 | 100%
402607 | Inverkeilor WwTW Access Improvements | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2013-01-22 | 2013-04-08 | 2013-09-05 |  | All East Unitary Authorities | 110195.31 | 0 | -1083.36 | 0 | 0 | 0 | 0 | 0 | -1083.36 | 0 | 0 | 0 | 109111.95 | 0 | 0 | 0 | 0 | 109111.95 | 209381.79 | [5 empty] | N | CM_M&G | 100%
400060 | Inverkeithing Preston Crescent SPS Refurb SPS001587 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2012-02-06 | 2012-04-24 | 2013-03-28 |  | Fife | 651072.18 | 0 | 46529.52 | -3.81 | 0 | 0 | 0 | 0 | 46525.71 | 0 | 0 | 0 | 697597.89 | 0 | 0 | 0 | 0 | 697597.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502879 | Invermoriston WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-05-09 | 2019-05-09 | 2019-05-09 | 2019-04-04 | 2019-04-04 | Highland | 0 | 0 | 0 | 0 | 21341.97 | 1526.48 | -20968.36 | 0 | 1900.1 | 0 | 0 | 0 | 1900.1 | 0 | 0 | 0 | 0 | 1900.1 | 122419.09 | [5 empty] | N | WG1 | 100%
500218 | Inverness - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS3 | 2015-03-23 | 2019-09-30 | 2020-08-17 | 2021-12-31 | 2022-06-17 | Highland | 0 | 0 | 10902 | -2352.37 | 47394.09 | 53357.84 | 167041.12 | 932474.42 | 1208817.1 | 588720.9 | 588720.8951 | 847556.5077 | 1797538 | 258835.6126 | 0 | 4.6566e-10 | 258835.6126 | 2056373.6126 | 1519613.06 | [5 empty] | Y | DW5FS | 8.988% | DW5 | 91.01% | [17 empty] | 1 | [47 empty] | 0
509586 | Inverness area safety shower heating element repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-11-04 | 2021-10-11 | 2022-05-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 926 | 926 | 9074.43 | 0 | 0 | 10000.43 | 0 | 0 | 0 | 0 | 10000.43 | 119022.58 | [5 empty] | N | CM_M&G | 100%
402060 | Inverness Campus Link Main | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2011-06-07 | 2011-12-23 | 2011-12-23 | 2013-10-01 |  | Highland | 86314 | 0 | -20403.72 | 0 | 0 | 0 | 0 | 0 | -20403.72 | 0 | 0 | 0 | 65910.28 | 0 | 0 | 0 | 0 | 65910.28 | 0 | [5 empty] | N | WG5 | 100%
500150 | Inverness DOA (DOA002372) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS7 | 2015-03-27 | 2017-02-28 | 2017-03-21 | 2020-03-31 | 2020-01-31 | Highland | 0 | 0 | 36582 | 113398 | 350757.87 | 185040.98 | 44805.26 | 0 | 730584.11 | 0 | 0 | 0 | 730584.11 | 0 | 0 | 0 | 0 | 730584.11 | 277404.61 | [5 empty] | N | CS16D | 100%
501623 | Inverness Opa Area- Rail Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2016-08-23 | 2027-06-23 | 2027-09-16 | 2028-03-10 |  | Highland | 0 | 0 | 0 | 5868.58 | 7634.71 | 8.84 | 0 | -7411.56 | 6100.57 | 7411.57 | 0 | 0 | 13512.13 | 0 | 0 | 0 | 0 | 13512.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500828 | Inverness RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-07-25 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 0 | 5225.07 | 2774.93 | 0 | -147.16 | 0 | 0 | 7852.84 | 0 | 0 | 0 | 7852.84 | 0 | 0 | 0 | 0 | 7852.84 | 240041.94 | [5 empty] | N | DW5FS | 100%
503167 | Inverness RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-31 | 2020-03-27 | 2020-03-27 | 2020-05-13 | 2021-04-01 | Highland | 0 | 0 | 0 | 0 | 0 | 20031.71 | 0 | 0 | 20031.71 | 0 | 0 | 0 | 20031.71 | 0 | 0 | 0 | 0 | 20031.71 | 759806.53 | [5 empty] | N | DW5FS | 100%
403559 | Inverness Slackbuie Link Main | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2013-08-27 | 2014-09-18 | 2014-10-07 | 2015-09-09 | 2015-09-09 | Highland | 216238 | 0 | 18838.91 | 0 | 0 | 0 | 0 | 0 | 18838.91 | 0 | 0 | 0 | 235076.91 | 0 | 0 | 0 | 0 | 235076.91 | 0 | [5 empty] | N | WG5 | 100%
503247 | Inverness WOA - Inverness Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-01 | 2027-06-23 | 2027-08-05 | 2027-11-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 54669.37 | 15286.57 | 0 | 69955.94 | 959444.01 | 0 | 0 | 1029399.95 | 0 | 0 | 0 | 0 | 1029399.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500735 | Inverness WOA - Urchany & Raitloan SR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS6 | 2015-08-26 | 2018-03-01 | 2018-03-19 | 2020-03-12 | 2020-06-08 | Highland | 0 | 0 | 125135 | 127146.1 | 852359.46 | 2195642.07 | 555395.4 | -42145.03 | 3813533 | 34526 | 34526 | 47927.9659 | 3848059 | 13401.9659 | 0 | 0 | 13401.9659 | 3861460.9659 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
502784 | Inverness WOA- Scorguie SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2020-06-30 | 2022-07-08 | 2022-10-26 | 2023-10-17 |  | Highland | 0 | 0 | 0 | 0 | 30753.52 | 18434.53 | 341.1 | -341.1 | 49188.05 | 1150811.95 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508973 | Inverness WTW Acid room works phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-01 | 2021-10-11 | 2022-05-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11294 | 11294 | 68705.93 | 0 | 0 | 79999.93 | 0 | 0 | 0 | 0 | 79999.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507484 | Inverness WTW lime slurry tank repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-08 | 2021-10-11 | 2022-05-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579.39 | 1579.39 | 13420.61 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502632 | Inverness WTW- PLC s replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2020-07-21 | 2022-07-12 | 2022-10-07 | 2024-05-28 |  | Highland | 0 | 0 | 0 | 0 | 19096.2 | 46860.77 | 91584.61 | -25807.58 | 131734 | 1958266.19 | 0 | 0 | 2090000.19 | 0 | 0 | 0 | 0 | 2090000.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504018 | Inverness WTW Regulatory sample tap replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2019-12-05 | 2020-07-06 | 2020-09-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 21900.23 | 24400.23 | 0 | 0 | 0 | 24400.23 | 0 | 0 | 0 | 0 | 24400.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401919 | Inversnaid WwTW SAF Installation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-05-11 | 2013-06-26 | 2013-06-26 | 2014-06-24 |  | Stirling | 259474.94 | 0 | 97.06 | 0 | 0 | 0 | 0 | 0 | 97.06 | 0 | 0 | 0 | 259572 | 0 | 0 | 0 | 0 | 259572 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506511 | Inverurie Bourtie DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-11-16 | 2023-01-02 | 2023-04-14 | 2024-03-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4283.5 | 4283.5 | 345716.5 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
45010 | Inverurie New STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-11-24 | 2015-08-21 | 2015-02-06 | 2015-02-06 | 2015-02-06 | Aberdeenshire | 841736.06 | 0 | 472.83 | 0 | 0 | 0 | 0 | 0 | 472.83 | 0 | 0 | 0 | 842208.89 | 0 | 0 | 0 | 0 | 842208.89 | 28761.13 | [5 empty] | N | EC01A | 100%
506799 | Inverurie Pineshaw DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-10 | 2021-08-06 | 2022-03-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501174 | Inverurie STC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-06-23 | 2018-03-20 | 2018-03-20 | 2017-05-25 |  | Aberdeenshire | 0 | 0 | 0 | 29755.88 | -7554.89 | 0 | 0 | 0 | 22200.99 | 0 | 0 | 0 | 22200.99 | 0 | 0 | 0 | 0 | 22200.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
30394 | Inverurie STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-05 | 2015-08-21 | 2015-02-06 | 2015-02-06 | 2015-02-06 | Aberdeenshire | 2014773.91 | 0 | -8704.1 | 0 | 0 | 0 | 0 | 0 | -8704.1 | 0 | 0 | 0 | 2006069.81 | 0 | 0 | 0 | 0 | 2006069.81 | 28761.13 | [5 empty] | N | EC01A | 100%
403935 | Inverurie STW Upgrade (Transfer from 30394 and 45010) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS5 | 2009-06-05 | 2017-02-23 | 2017-04-03 | 2020-03-31 | 2020-03-31 | Aberdeenshire | 147386 | 0 | 746158 | 1651782.48 | 8299679.17 | 9718823.12 | 2470102.27 | 417344.86 | 23303889.9 | 70351.58 | 32361.7268 | 44923.5862 | 23521627.48 | 12561.8594 | 0 | 0 | 12561.8594 | 23534189.3394 | 90601.29 |  |  |  |  | 79416.804 | N | SG1 | 19% | CM_WWNI | 35% | EC01A | 46%
502424 | Inverurie Uryside Phase 2 SR | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2020-09-25 | 2020-09-25 | 2020-10-21 | 2020-10-21 |  | Aberdeenshire | 0 | 0 | 0 | 39204.71 | 6913.69 | 11423.74 | 18103.09 | -3368.02 | 72277.2 | 0 | 0 | 0 | 72277.2 | 0 | 0 | 0 | 0 | 72277.2 | 444766.03 | [5 empty] | N | WG5 | 100%
502323 | Inverurie Uryside Phase 2 SR - Developer design | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW0 | 2021-04-07 | 2021-04-21 | 2021-04-21 | 2021-04-21 |  | Aberdeenshire | 0 | 0 | 0 | 85448.37 | -31.5 | 2314.58 | -1989.88 | 85741.43 | 171483 | 0 | 0 | 0 | 171483 | 0 | 0 | 0 | 0 | 171483 | 444766.03 | [5 empty] | N | WG5 | 100%
511923 | Investigation at Corsehouse WTW Sludge removal and H&S of Lagoons_Washwater tanks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-24 | 2022-03-04 | 2022-10-17 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559.13 | 1559.13 | 9140.87 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 119022.58 | [5 empty] | N | WSNI | 100%
503504 | Investigation into Helensburgh trunk main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-28 | 2022-02-28 | 2022-05-06 | 2022-09-20 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198758.77 | 0 | 0 | 198758.77 | 0 | 0 | 0 | 0 | 198758.77 | 311236.79 | [5 empty] | N | CM_M&G | 100%
509750 | Investigation on Balmuidy Main Glasgow | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-11-20 | 2021-01-21 | 2021-06-07 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4256.68 | 4256.68 | 18835.89 | 0 | 0 | 23092.57 | 0 | 0 | 0 | 0 | 23092.57 | 311236.79 | [5 empty] | N | WSI | 100%
510928 | Investigation on Sludge removal and Washwater tanks made safe-Corsehouse WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-01 |  | 2021-04-27 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8560 | 0 | 0 | 8560 | 0 | 0 | 0 | 0 | 8560 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402648 | IPM Commercial Support | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS7 | 2012-03-29 | 2012-03-29 | 2012-04-02 | 2016-10-26 |  | Scottish Water Wide | 230600.53 | 0 | 100000.47 | -46213.31 | 0 | 0 | 0 | 0 | 53787.16 | 0 | 0 | 0 | 284387.69 | 0 | 0 | 0 | 0 | 284387.69 | 730242.44 | [5 empty] | N | WSI | 4.826% | WWNI | 4.826% | WWI | 45.17% | WSNI | 45.17%
503084 | IR18 - 59032 - Dry Weather Flow Studies | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2019-07-09 | 2020-09-24 | 2020-12-17 | 2022-02-03 | 2022-05-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 27388 | 98808.08 | 126196.08 | 288470.31 | 0 | 0 | 414666.39 | 0 | 79567.5665 | 0 | 79567.5665 | 494233.9565 | 649102.99 | [5 empty] | N | EC10E | 100%
503094 | IR18 - 59034 - Legacy sludge requirement at Operational Sites | IR18 | Protecting and enhancing the environment | Sludge |  |  | Wastewater | SEPA | SWD | Sludge | MS3 | 2018-10-30 | 2020-03-12 | 2020-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 8431.2 | 26528.5 | 33926.05 | 68885.75 | 6114.25 | 12114.251 | 12114.251 | 75000 | 0 | 6000 | 0 | 6000 | 81000 | 429303.62 | [5 empty] | Y | LA01_S | 100% | [40 empty] | 1 | [26 empty] | 0
503136 | IR18 - 59044 - WFD - Priority Substances Intervention Development | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS2 | 2020-09-30 | 2020-09-30 | 2021-05-05 | 2021-05-05 | 2021-05-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 53568.55 | -8777.85 | 44790.7 | 313209.3 | 0 | 0 | 358000 | 0 | 86391.2193 | 0 | 86391.2193 | 444391.2193 | 101413.84 | [5 empty] | N | EC23B_ID | 100%
503137 | IR18 - 59048 - WFD - WwTW Intervention Development | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | GW2 | 2022-07-29 | 2024-01-04 | 2024-05-01 | 2024-12-17 | 2025-03-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 20233.34 | 9969.66 | 30203 | 733796.9 | 0 | 0 | 763999.9 | 0 | 202400.1487 | 0 | 202400.1487 | 966400.0487 | 108174.77 | [5 empty] | N | EC10A_ID | 100%
503140 | IR18 - 59061 - Event and Duration Monitoring Intervention Development | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2021-03-01 | 2021-03-01 | 2021-03-01 | 2021-03-03 | 2023-09-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 86500 | 11065.07 | 516.72 | 98081.79 | 0 | 0 | 0 | 98081.79 | 0 | 0 | 0 | 0 | 98081.79 | 226231.33 | [5 empty] | N | CS29_ID | 100%
503124 | IR18 - 59066 - Glasgow Sludge Main Resilience Study | IR18 | Improving the customer experience | Customer Experience Studies |  |  | Wastewater | SEPA | SWMD | Customer Experience Studies | MS7 | 2018-09-28 | 2019-03-25 | 2019-03-27 | 2019-05-31 | 2019-08-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 134124.04 | 41678.26 | 0 | 175802.3 | 0 | 0 | 0 | 175802.3 | 0 | 0 | 0 | 0 | 175802.3 | 221290.52 | [5 empty] | Y | CS16SR | 100% | [40 empty] | 1 | [26 empty] | 0
503077 | IR18 - 59076 - CAS Compliance Study | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2018-10-31 | 2020-05-28 | 2020-05-25 | 2024-09-16 | 2024-09-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 15583 | 214781.04 | 405127.97 | 635492 | 714508.5 | 0 | 0 | 1350000.5 | 0 | 197079.9095 | 0 | 197079.9095 | 1547080.4095 | 1181691.4 | [5 empty] | N | WQ01_S | 100%
503083 | IR18 - 59077 - Inner Clyde Estuary Modelling | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS4 | 2018-07-13 | 2019-06-26 | 2019-07-08 | 2021-03-31 | 2021-09-15 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 72831.78 | 1239340.12 | 176366.1 | 1488538 | 51462.39 | 56462 | 56462 | 1540000.39 | 0 | 4999.61 | 0 | 4999.61 | 1545000 | 1272420.52 | [5 empty] | Y | EC01D | 50% | EC10E | 50% | [38 empty] | 1 | [26 empty] | 0
503400 | IR18 - Barra - Distribution Flushing | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS5 | 2019-03-27 | 2019-09-30 | 2020-01-06 | 2020-03-31 | 2020-06-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 9600 | 119492.35 | 68589.65 | 197682 | 0 | 0 | 0 | 197682 | 0 | 0 | 0 | 0 | 197682 | 231573.17 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 55.52 | [43 empty] | 0
503126 | IR18 - Boardhouse WTW Inlet Screen | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS0 | 2018-12-20 | 2022-09-09 | 2022-12-09 | 2023-06-08 | 2023-09-06 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 55998.21 | 36414.16 | 44849.79 | 137262.16 | 406762.79 | 0 | 0 | 544024.95 | 0 | 112195.6895 | 0 | 112195.6895 | 656220.6395 | 693889.29 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
503139 | IR18 - Event and Duration Monitoring Phase 1 | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS7 | 2018-11-21 | 2020-02-20 | 2020-04-08 | 2020-02-20 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 5050.47 | 215.3 | 0 | 5265.77 | 0 | 0 | 0 | 5265.77 | 0 | 0 | 0 | 0 | 5265.77 | 284605.17 | [5 empty] | N | CS29 | 100%
503178 | IR18 - External Flooding Carstairs | IR18 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater | SW | SWD | Flooding Demand Driven | GW2 | 2021-05-10 | 2021-08-24 | 2021-11-01 | 2022-09-16 | 2022-12-19 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23738 | 23738 | 384262.21 | 0 | 0 | 408000.21 | 0 | 105989.4481 | 0 | 105989.4481 | 513989.6581 | 472726.74 | [5 empty] | N | FL_DD | 100%
503177 | IR18 - External Flooding Clarkston | IR18 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater | SW | WWINF | Flooding Demand Driven | MS3 | 2019-03-05 | 2020-03-30 | 2020-11-09 | 2021-09-07 | 2021-12-08 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 12571.94 | 189244.06 | 870705 | 1072521 | 134053 | 156651 | 156651 | 1206574 | 0 | 22598 | 0 | 22598 | 1229172 | 724670.43 |  |  |  |  | 1200 | N | FL_DD | 100%
503334 | IR18 - Intelligent Water Networks - Improvements to Interruptions to Supply and Low Pressure Managem | IR18 | Improving drinking water availability and resilience of service | Pressure |  |  | Water |  | SWD | Pressure | GW2 | 2021-10-13 | 2022-05-06 | 2022-07-04 | 2023-11-27 | 2024-02-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 97394.8 | 680.88 | 98075.68 | 3347924.27 | 0 | 0 | 3445999.95 | 0 | 923444.0348 | 0 | 923444.0348 | 4369443.9848 | 130947.15 | [5 empty] | N | CS1 | 100%
503176 | IR18 - Internal Sewer Flooding - SR21 cost surety (holding line) | IR18 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-08-13 | 2021-10-04 | 2021-10-13 | 2021-11-24 | 2021-11-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 793.87 | 35878.14 | 36672 | 21328.37 | 0 | 0 | 58000.37 | 0 | 5882.9156 | 0 | 5882.9156 | 63883.2856 | 4391785.23 | [5 empty] | N | FL_DD | 100%
503179 | IR18 - Interventions from Aberdeen ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW1 | 2021-08-23 | 2023-02-17 | 2023-04-17 | 2023-07-07 | 2024-07-05 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 7000 | 26175.21 | 183428.79 | 216604 | 338395.99 | 0 | 0 | 554999.99 | 0 | 93338.3593 | 0 | 93338.3593 | 648338.3493 | 995091.55 | [5 empty] | N | CS16D_ID | 100%
503184 | IR18 - Interventions from Edinburgh ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW1 | 2021-08-23 | 2023-02-17 | 2023-04-17 | 2023-07-07 | 2024-07-05 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 7000 | 32651.32 | 234507.06 | 274158.38 | 280841.62 | 0 | 0 | 555000 | 0 | 77463.3776 | 0 | 77463.3776 | 632463.3776 | 559320.1 | [5 empty] | N | CS16D_ID | 100%
503182 | IR18 - Interventions from Falkirk ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS7 | 2021-01-21 | 2021-01-21 | 2021-03-01 | 2021-03-01 | 2021-06-21 | Falkirk | 0 | 0 | 0 | 0 | 0 | 7000 | 9733.45 | -4480.05 | 12253.4 | 0 | 0 | 0 | 12253.4 | 0 | 0 | 0 | 0 | 12253.4 | 559320.1 | [5 empty] | N | CS16D_ID | 100%
503181 | IR18 - Interventions from Meadowhead ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW1 | 2021-08-12 | 2022-02-02 | 2022-03-31 | 2022-06-28 | 2022-09-28 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 7076.05 | 10797.67 | 110717.28 | 128591 | 426408.54 | 0 | 0 | 554999.54 | 0 | 117614.4951 | 0 | 117614.4951 | 672614.0351 | 559320.1 | [5 empty] | N | CS16D_ID | 100%
503183 | IR18 - Interventions from SR15 ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2022-04-13 | 2023-10-10 | 2023-12-06 | 2024-02-27 | 2025-02-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 26168.22 | 21310.19 | -14023.3 | 33455.11 | 1829521.59 | 0 | 0 | 1862976.7 | 0 | 504629.3352 | 0 | 504629.3352 | 2367606.0352 | 423578.06 | [5 empty] | N | CS16D_ID | 100%
503180 | IR18 - Interventions from Tayside ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW1 | 2021-08-11 | 2023-02-07 | 2023-04-05 | 2023-06-27 | 2024-06-25 | Dundee City | 0 | 0 | 0 | 0 | 0 | 7076.05 | 25856.48 | 271265.01 | 304197.54 | 250962.38 | 0 | 0 | 555159.92 | 0 | 69221.9101 | 0 | 69221.9101 | 624381.8301 | 559320.1 | [5 empty] | N | CS16D_ID | 100%
503249 | IR18 Investigate Future Changes in the Occurrance of Algal Blooms | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS3 | 2018-06-05 | 2019-09-18 | 2019-09-18 | 2021-04-21 | 2021-04-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 4396.71 | 31713.32 | -26163.93 | 9946.1 | 127139.34 | 138106.1752 | 138106.1752 | 137085.44 | 0 | 10966.8352 | 0 | 10966.8352 | 148052.2752 | 158480.25 | [5 empty] | Y | DW25PS | 100% | [64 empty] | 1 |  |  | 0
503185 | IR18 - Masterplanning for Aberdeen ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2021-04-01 | 2021-06-22 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 1478.77 | 11614.69 | 31906.54 | 45000 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 45000 | 110645.26 | [5 empty] | N | CS27 | 100%
503187 | IR18 - Masterplanning for Edinburgh ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2021-01-26 | 2021-04-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 1478.77 | 72381.75 | 26639.48 | 100500 | 0 | 0 | 0 | 100500 | 0 | 0 | 0 | 0 | 100500 | 110645.26 | [5 empty] | N | CS27 | 100%
503188 | IR18 - Masterplanning for Falkirk ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS3 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2021-06-16 | 2021-06-17 | Falkirk | 0 | 0 | 0 | 0 | 0 | 1478.77 | 40208.33 | 30312.9 | 72000 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 72000 | 110645.26 | [5 empty] | N | CS27 | 100%
503189 | IR18 - Masterplanning for Meadowhead ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2021-01-29 | 2021-06-17 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 1478.77 | 44029 | 31992.23 | 77500 | 1500 | 0 | 0 | 79000 | 0 | 413.7388 | 0 | 413.7388 | 79413.7388 | 110645.26 | [5 empty] | N | CS27 | 100%
503190 | IR18 - Masterplanning for SR15 ICS Catchments | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2021-01-26 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2721.5 | 22629.35 | 19649.15 | 45000 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 45000 | 87023.55 | [5 empty] | N | CS27 | 100%
503186 | IR18 - Masterplanning for Tayside ICS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS4 | 2019-02-21 | 2019-07-17 | 2019-07-18 | 2021-04-01 | 2021-06-17 | Dundee City | 0 | 0 | 0 | 0 | 0 | 2744.29 | 38546.61 | 38709.1 | 80000 | 1999.98 | 0 | 0 | 81999.98 | 0 | 551.6462 | 0 | 551.6462 | 82551.6262 | 110645.26 | [5 empty] | N | CS27 | 100%
503191 | IR18 - Options for Flood Risk Reduction (Stormwater Strategy) | IR18 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2019-07-11 | 2019-07-11 | 2019-08-28 | 2022-07-15 | 2022-08-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 230991.04 | 221500.96 | 452492 | 1688507.56 | 0 | 0 | 2140999.56 | 0 | 465734.0215 | 0 | 465734.0215 | 2606733.5815 | 1106452.62 | [5 empty] | N | CS16D_ID | 100%
503246 | IR18 - Sewer Monitoring Demonstrator (Intelligent Networks) | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2018-07-30 | 2020-06-05 | 2020-06-05 | 2021-03-25 | 2021-07-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 58372.9 | 297644.08 | 108293.03 | 464310 | 12758.39 | 0 | 0 | 477068.39 | 0 | 3519.0937 | 0 | 3519.0937 | 480587.4837 | 413580.79 | [5 empty] | N | EC01M | 100%
503237 | IR18 THM- TOC Catchment Manangement - Forehill | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS5 | 2018-06-21 | 2019-06-28 | 2019-06-28 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 16302.93 | 240871.55 | -181549.48 | 75625 | 0 | 6050 | 6050 | 75625 | 0 | 6050 | 0 | 6050 | 81675 | 250727.71 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
503248 | IR18 THM- TOC Catchment Manangement Study -Pateshill | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water | DWQR | SWD | DWQ - Preparing for Future Investment | MS4 | 2018-06-05 | 2019-01-08 | 2019-04-26 | 2021-03-31 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 24347.35 | 49255.68 | -47436.84 | 26166.19 | 153833.81 | 168233.81 | 168233.81 | 180000 | 0 | 14400 | 0 | 14400 | 194400 | 208031.69 | [5 empty] | Y | DW25PS | 100% | [64 empty] | 1 |  |  | 0
503129 | IR18 - WFD - Priority Substances Study (59059) | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS7 | 2019-09-26 | 2020-09-30 | 2021-02-03 | 2021-02-03 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 14212.01 | -14212.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | EC23A | 100%
502648 | IR18 Allowance - Ardrishaig WTW | IR18 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS3 | 2018-03-30 | 2020-01-31 | 2020-03-16 | 2022-06-01 | 2023-08-15 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 45494.62 | 116467.18 | 1290176.2 | 2276002 | 3728140 | 3370140 | 4771860 | 4771860 | 7098280 | 0 | 1401720 | 0 | 1401720 | 8500000 | 3246734.22 | [5 empty] | Y | DW2 | 100% | [18 empty] | 1 | [48 empty] | 0
502652 | IR18 Allowance - Barra WTW | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS0 | 2018-06-30 | 2021-07-05 | 2021-08-16 | 2022-04-11 | 2022-07-12 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 7268.99 | 4177.09 | 2759.57 | 19076.35 | 33282 | 411047.21 | 0 | 0 | 444329.21 | 0 | 113377.4433 | 0 | 113377.4433 | 557706.6533 | 483284.82 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
502386 | IR18 Allowance - Black Esk - Fish Pass | IR18 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS7 | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-05-17 | 2019-05-17 | Dumfries and Galloway | 0 | 0 | 0 | 17700 | 20300 | -8718.2 | 51.97 | 0 | 29333.77 | 0 | 0 | 0 | 29333.77 | 0 | 0 | 0 | 0 | 29333.77 | 26377.73 | [5 empty] | N | WR2A | 100%
502411 | IR18 Allowance - Caddon Water Intake - Fish Pass | IR18 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWMD | WFD | MS0 | 2018-07-25 | 2023-10-02 | 2023-12-01 | 2024-02-29 | 2024-05-29 | Scottish Borders | 0 | 0 | 0 | 20900 | 24841.9 | 27530.2 | 28131.08 | 40572.82 | 141976 | 304802.49 | 0 | 0 | 446778.49 | 0 | 84072.4038 | 0 | 84072.4038 | 530850.8938 | 457430.11 | [5 empty] | N | WR2A_ID | 100%
502381 | IR18 Allowance - Corsehouse - Abstraction Improvement | IR18 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS7 | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-05-09 | 2019-05-09 | South Ayrshire | 0 | 0 | 0 | 7900 | 3721.81 | 0 | 0 | 0 | 11621.81 | 0 | 0 | 0 | 11621.81 | 0 | 0 | 0 | 0 | 11621.81 | 131990.95 | [5 empty] | N | WR1 | 100%
502563 | IR18 Allowance - Dye Water Fish Pass | IR18 | Protecting and enhancing the environment | WFD |  |  | Water | SEPA | SWMD | WFD | MS2 | 2018-10-26 | 2020-03-23 | 2021-07-20 | 2022-01-18 | 2022-04-19 | East Lothian | 0 | 0 | 0 | 15550 | 5069.87 | 8271.7 | 48290.73 | 17741.7 | 94924 | 135445.26 | 145076 | 145076 | 230369.26 | 0 | 9630.74 | 5.8208e-11 | 9630.74 | 240000 | 26377.73 | [5 empty] | Y | WR2A | 100% | [37 empty] | 1 | [29 empty] | 0
502382 | IR18 Allowance - East Berwickshire - Abstraction Improvement | IR18 | Protecting and enhancing the environment | WFD |  |  | Water | SEPA | SWMD | WFD | MS3 | 2019-01-31 | 2020-03-27 | 2020-06-08 | 2021-10-29 | 2022-01-31 | Scottish Borders | 0 | 0 | 0 | 7900 | 1888.82 | 7025.81 | 36284.61 | 345400.76 | 398500 | 44976.47 | 64500 | 64500 | 443476.47 | 0 | 19523.53 | 5.8208e-11 | 19523.53 | 463000 | 385236.73 |  |  |  |  | 49524.9996 | Y | WR1 | 100% | [37 empty] | 1 | [29 empty] | 0
502220 | IR18 Allowance - Edgehead Septic Tank | IR18 | Protecting and enhancing the environment | WFD |  |  | Wastewater | SEPA | WWINF | WFD | MS1 | 2017-11-30 | 2021-06-14 | 2021-09-08 | 2022-09-23 | 2023-01-09 | Midlothian | 0 | 0 | 0 | 82593.19 | 46293.4 | 222374.46 | 295294.95 | 198762 | 845318 | 1657394.43 | 0 | 0 | 2502712.43 | 0 | 457152.2162 | 0 | 457152.2162 | 2959864.6462 | 596457.04 |  |  |  |  | 9999.9996 | Y | EC10A | 100% | [37 empty] | 1 | [29 empty] | 0
502383 | IR18 Allowance - Fife - Abstraction Improvement | IR18 | Protecting and enhancing the environment | WFD |  |  | Water | SEPA | SWMD | WFD | MS3 | 2019-03-11 | 2020-12-18 | 2021-03-08 | 2021-12-20 | 2022-03-15 | Fife | 0 | 0 | 0 | 10779 | 2862.6 | 11358.4 | 6117.07 | 26444.93 | 57562 | 57706.05 | 57707.0045 | 57707.0045 | 115268.05 | 0 | 0.9545 | -0.0045 | 0.95 | 115269 | 725893.39 | [5 empty] | Y | WR1 | 100% | [37 empty] | 1 | [29 empty] | 0
502380 | IR18 Allowance - Forth Valley - Abstraction Improvement | IR18 | Protecting and enhancing the environment | WFD |  |  | Water | SEPA | SWD | WFD | MS3 | 2019-02-26 | 2019-03-25 | 2019-03-25 | 2021-04-01 | 2021-04-01 | Perth and Kinross | 0 | 0 | 0 | 4000 | 2450.25 | 4436.13 | 24196.68 | -18331.67 | 16751.39 | 0 | 1340.1112 | 1340.1112 | 16751.39 | 0 | 1340.1112 | 0 | 1340.1112 | 18091.5012 | 213269.29 | [5 empty] | Y | WR1 | 100% | [37 empty] | 1 | [29 empty] | 0
502384 | IR18 Allowance - Glenleith - Fish Pass | IR18 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS7 | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-05-09 | 2019-05-09 | Dumfries and Galloway | 0 | 0 | 0 | 2274 | 17726 | 0 | -15498.05 | 0 | 4501.95 | 0 | 0 | 0 | 4501.95 | 0 | 0 | 0 | 0 | 4501.95 | 26377.73 | [5 empty] | N | WR2A | 100%
502385 | IR18 Allowance - Loch Venachar - Fish Pass | IR18 | Protecting and enhancing the environment | WFD |  |  | Water | SEPA | SWMD | WFD | MS6 | 2018-09-28 | 2020-03-27 | 2020-06-22 | 2020-12-31 | 2020-12-31 | Stirling | 0 | 0 | 0 | 7950 | 1143.4 | 5673.59 | 39992.73 | 67063.75 | 121823.47 | 0 | 0 | 0 | 121823.47 | 0 | 0 | 0 | 0 | 121823.47 | 158341.74 | [5 empty] | Y | WR2A | 100% | [37 empty] | 1 | [29 empty] | 0
502213 | IR18 Allowance - Longriggend WWTW | IR18 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS7 | 2017-11-14 | 2019-06-21 | 2019-06-21 | 2019-04-03 | 2019-04-03 | North Lanarkshire | 0 | 0 | 0 | 128544.83 | 56371.51 | 14822.43 | 525.04 | -10261.95 | 190001.87 | 10261.6 | 0 | 0 | 200263.47 | 0 | 2830.4157 | 0 | 2830.4157 | 203093.8857 | 213455.65 | [5 empty] | N | EC10A | 100%
502212 | IR18 Allowance - Newton Septic Tank | IR18 | Protecting and enhancing the environment | WFD |  |  | Wastewater | SEPA | WWINF | WFD | MS0 | 2017-11-30 | 2021-09-02 | 2021-11-12 | 2022-06-08 | 2022-09-12 | City of Edinburgh | 0 | 0 | 0 | 65632.35 | 33482.65 | 78708.52 | 62650.95 | 353033.72 | 593508.19 | 1321858 | 0 | 0 | 1915366.19 | 0 | 364602.5977 | 0 | 364602.5977 | 2279968.7877 | 1046890.41 | [5 empty] | Y | EC10A | 100% | [37 empty] | 1 | [29 empty] | 0
502650 | IR18 Allowance - Tarbert WTW | IR18 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS3 | 2017-09-15 | 2019-09-30 | 2019-10-29 | 2022-06-16 | 2023-09-14 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 27062.79 | 136518.6 | 507784.07 | 1947896.54 | 1880563 | 4499825 | 1110796 | 1929623 | 1929623 | 5610621 | 0 | 818827 | 0 | 818827 | 6429448 | 3453376.49 | [5 empty] | Y | DW2 | 100% | [18 empty] | 1 | [48 empty] | 0
502731 | IR18 Allowance - Turriff WRZ Abstraction Impact Monitoring | IR18 | Protecting and enhancing the environment | WFD |  |  | Water | SEPA | SWD | WFD | MS5 | 2018-07-02 | 2020-12-01 | 2019-08-16 | 2019-08-31 | 2019-08-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 9566.31 | 5123.95 | 59489.74 | -65540.23 | 8639.77 | 0 | 0 | 0 | 8639.77 | 0 | 0 | 0 | 0 | 8639.77 | 131990.95 | [5 empty] | Y | WR1 | 100% | [37 empty] | 1 | [29 empty] | 0
503491 | IR18 Allowance Upperton (Longriggend) WWTW (recycled) | IR18 | Protecting and enhancing the environment | WFD |  |  | Wastewater | SEPA | SWD | WFD | MS0 | 2017-11-14 | 2023-09-11 | 2023-12-12 | 2024-12-24 | 2025-03-26 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 45048.56 | 25609.33 | 44727.11 | 115385 | 1619537.36 | 0 | 0 | 1734922.36 | 0 | 446710.2579 | 0 | 446710.2579 | 2181632.6179 | 213455.65 | [5 empty] | Y | EC10A | 100% | [37 empty] | 1 | [29 empty] | 0
503113 | IR18 Blairlinnans & Milngavie Connectivity | IR18 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW1 | 2021-06-30 | 2023-04-25 | 2023-07-12 | 2024-02-13 | 2024-05-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 206449.82 | 75688.2 | 34427.92 | 316565.94 | 348878.07 | 0 | 0 | 665444 | 0 | 96229.5865 | 0 | 96229.5865 | 761673.5865 | 801392.57 | [5 empty] | N | CS16WRID | 100%
502326 | IR18 CAS Compliance at WWTW and Network Assets | IR18 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWD | Compliance Assessment Scheme | MS7 | 2019-05-29 | 2019-05-29 | 2019-05-29 | 2019-05-09 | 2019-05-09 | Scottish Water Wide | 0 | 0 | 0 | 140980.02 | 63551.84 | -56151.84 | 715.14 | 0 | 149095.16 | 0 | 0 | 0 | 149095.16 | 0 | 0 | 0 | 0 | 149095.16 | 717445.56 | [5 empty] | N | WQ01D | 30.43% | WQ01E | 69.57%
502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | IR18 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater | SEPA | SWMD | Compliance Assessment Scheme | MS3 | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-09-06 | 2021-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 2604.35 | 72751.05 | 159070.81 | 386285.25 | 620711.46 | 110855.55 | 164288.54 | 164288.54 | 731567.01 | 0 | 53432.99 | -1.1642e-10 | 53432.99 | 785000 | 406153.51 | [5 empty] | N | WQ01E | 100%
502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | IR18 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater | SEPA | SWMD | Compliance Assessment Scheme | MS3 | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-09-29 | 2021-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 3596.88 | 76342.3 | 318056.23 | 454538.78 | 852534.19 | 229831.03 | 322465.81 | 322465.81 | 1082365.22 | 0 | 92634.78 | 4.6566e-10 | 92634.78 | 1175000 | 406153.51 | [5 empty] | N | WQ01E | 100%
502946 | IR18 CAS Compliance Improvements - WWTW East Complex | IR18 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater | SEPA | SWMD | Compliance Assessment Scheme | MS3 | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-12-03 | 2022-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 3781.74 | 75752.48 | 245258.29 | 324085.12 | 648877.63 | 512784.23 | 576122.37 | 576122.37 | 1161661.86 | 0 | 63338.14 | 0 | 63338.14 | 1225000 | 311292.06 | [5 empty] | N | WQ01D | 100%
502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | IR18 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater | SEPA | SWMD | Compliance Assessment Scheme | MS3 | 2018-02-23 | 2019-12-18 | 2020-03-16 | 2021-09-06 | 2021-12-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 764.42 | 71108.7 | 200796.79 | 410355.32 | 683025.23 | 30558.6 | 36974.768 | 36974.768 | 713583.83 | 0 | 43390.936 | -36974.766 | 6416.17 | 720000 | 717445.56 | [5 empty] | N | WQ01D | 14.04% | WQ01E | 85.96%
502947 | IR18 CAS Compliance Improvements - WWTW North Complex | IR18 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater | SEPA | SWMD | Compliance Assessment Scheme | MS3 | 2018-03-22 | 2019-12-18 | 2020-03-16 | 2021-07-26 | 2021-10-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1330.51 | 37838.4 | 93934.69 | 239016.86 | 372120.46 | 3993.55 | 17879.54 | 17879.54 | 376114.01 | 0 | 13885.99 | 0 | 13885.99 | 390000 | 311292.06 | [5 empty] | N | WQ01D | 100%
503118 | IR18 Cyber Security Governance Line | IR18 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-08-23 | 2019-02-27 | 2019-02-27 | 2021-07-28 | 2021-07-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 154907.52 | 192760.91 | 186338.78 | 534007.21 | 3050.58 | 0 | 0 | 537057.79 | 0 | 841.4278 | 0 | 841.4278 | 537899.2178 | 2117982 | [5 empty] | N | CS24S | 50% | CS24W | 50%
503434 | IR18 Daer CWT | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2015-10-30 | 2019-09-30 | 2020-10-29 | 2022-01-31 | 2022-05-03 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 17126 | 221999 | 114433 | 353558 | 1367523.95 | 1539632 | 1539632 | 1721081.95 | 0 | 172108.05 | 6.9849e-10 | 172108.05 | 1893190 | 645915.7 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
503243 | IR18 Daer WTW Bacti Risk Reduction Study | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water | DWQR | SWD | DWQ - Preparing for Future Investment | MS5 | 2018-06-05 | 2019-03-12 | 2019-03-18 | 2021-03-31 | 2021-03-31 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 25836.58 | 67171.8 | -45906.5 | 47101.88 | 113403.5 | 126243.9303 | 126243.9303 | 160505.38 | 0 | 12840.4303 | -0.00102 | 12840.4293 | 173345.8093 | 214795.96 | [5 empty] | Y | DW25PS | 100% | [64 empty] | 1 |  |  | 0
509411 | IR18 Disinfection Improvements East - Mainland | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-18 | 2021-07-16 | 2022-02-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16322.9 | 16322.9 | 232796.35 | 0 | 0 | 249119.25 | 0 | 64211.2495 | 0 | 64211.2495 | 313330.4995 | 158124.78 | [5 empty] | N | DW25P | 100%
509406 | IR18 Disinfection Improvements - East - Orkney | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-02 | 2021-07-16 | 2022-02-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7081.83 | 7081.83 | 101168.98 | 0 | 0 | 108250.81 | 0 | 27905.0192 | 0 | 27905.0192 | 136155.8292 | 158124.78 | [5 empty] | N | DW25P | 100%
509408 | IR18 Disinfection Improvements - East - Shetland | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-18 | 2021-07-16 | 2022-02-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6706 | 6706 | 83575.47 | 0 | 0 | 90281.47 | 0 | 23052.2745 | 0 | 23052.2745 | 113333.7445 | 158124.78 | [5 empty] | N | DW25P | 100%
503430 | IR18 Disinfection Improvements - Minor Upgrades | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | GW2 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 21286.05 | 35356.56 | 3701.84 | 60344.45 | 0 | 0 | 0 | 60344.45 | 0 | 0 | 0 | 0 | 60344.45 | 574960.8 | [5 empty] | N | DW25P | 100%
509415 | IR18 Disinfection Improvements - North 1 | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-18 | 2022-05-13 | 2022-12-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6829 | 6829 | 96022.66 | 0 | 0 | 102851.66 | 0 | 26485.5312 | 0 | 26485.5312 | 129337.1912 | 158124.78 | [5 empty] | N | DW25P | 100%
509417 | IR18 Disinfection Improvements - North 2 - Wester Ross North | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-18 | 2022-05-13 | 2022-12-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9539 | 9539 | 134740.17 | 0 | 0 | 144279.17 | 0 | 37164.821 | 0 | 37164.821 | 181443.991 | 158124.78 | [5 empty] | N | DW25P | 100%
509419 | IR18 Disinfection Improvements North 3 Wester Ross South | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-25 | 2022-05-13 | 2022-12-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12635 | 12635 | 176039.26 | 0 | 0 | 188674.26 | 0 | 48556.1773 | 0 | 48556.1773 | 237230.4373 | 158124.78 | [5 empty] | N | DW25P | 100%
509422 | IR18 Disinfection Improvements North 4 Skye & Wester Ross | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-18 | 2022-05-13 | 2022-12-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15242 | 15242 | 216209.2 | 0 | 0 | 231451.2 | 0 | 59636.0849 | 0 | 59636.0849 | 291087.2849 | 158124.78 | [5 empty] | N | DW25P | 100%
509424 | IR18 Disinfection Improvements North 5 Outer Hebrides | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-18 | 2022-05-13 | 2022-12-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8815 | 8815 | 124396.7 | 0 | 0 | 133211.7 | 0 | 34311.8247 | 0 | 34311.8247 | 167523.5247 | 158124.78 | [5 empty] | N | DW25P | 100%
509427 | IR18 Disinfection Improvements - North 6 - Argyle | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-18 | 2022-05-13 | 2022-12-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10050 | 10050 | 142036.41 | 0 | 0 | 152086.41 | 0 | 39177.3126 | 0 | 39177.3126 | 191263.7226 | 158124.78 | [5 empty] | N | DW25P | 100%
509429 | IR18 Disinfection Improvements - South | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-18 | 2022-09-15 | 2023-04-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10577.52 | 10577.52 | 151107.33 | 0 | 0 | 161684.85 | 0 | 41679.3067 | 0 | 41679.3067 | 203364.1567 | 158124.78 | [5 empty] | N | DW25P | 100%
509430 | IR18 Disinfection Improvements - West | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 |  | 2021-02-18 | 2021-09-23 | 2022-04-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8044.01 | 8044.01 | 114213.41 | 0 | 0 | 122257.42 | 0 | 31503.0101 | 0 | 31503.0101 | 153760.4301 | 158124.78 | [5 empty] | N | DW25P | 100%
509404 | IR18 Disinfection Improvements Fin. Man. | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS2 |  | 2021-01-28 |  | 2021-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19844 | 19844 | 277598.57 | 0 | 0 | 297442.57 | 0 | 76568.8596 | 0 | 76568.8596 | 374011.4296 | 574960.8 | [5 empty] | N | DW25P | 100%
503437 | IR18 Drinking Water Quality Provision of Sampling Points | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | GW1 | 2021-06-01 | 2023-02-16 | 2023-05-22 | 2024-10-15 | 2025-01-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 22596.28 | 23957.89 | -16073.17 | 30481 | 2128519.09 | 0 | 0 | 2159000.09 | 0 | 587100.5728 | 0 | 587100.5728 | 2746100.6628 | 38383.47 | [5 empty] | N | DW25PS | 47% | DW25TS | 53%
503175 | IR18- External sewer Flooding SR21 Cost surety | IR18 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-04-01 | 2022-05-10 | 2022-05-20 | 2022-07-01 | 2022-07-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 460465.12 | 0 | 460465.12 | 639534.9 | 0 | 0 | 1100000.02 | 0 | 176400.2531 | 0 | 176400.2531 | 1276400.2731 | 1157865.87 | [5 empty] | N | FL_DD | 100%
503252 | IR18 Impact of Future Drinking Water Directive Changes - Sampling Programme | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-06-15 | 2019-06-27 | 2019-07-01 | 2023-08-04 | 2023-11-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 15709.22 | 112563.61 | -61564.23 | 66708.61 | 686324.62 | 0 | 0 | 753033.23 | 0 | 189306.067 | 0 | 189306.067 | 942339.297 | 176850.45 | [5 empty] | N | DW25PS | 100%
503103 | IR18 Inverness and Nairn - Growth and Resilience | IR18 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | MPT | SOSI | MS3 | 2018-06-26 | 2021-03-24 | 2021-03-25 | 2021-10-05 | 2021-10-06 | Highland | 0 | 0 | 0 | 0 | 0 | 470529.39 | 1253970.91 | 837625.53 | 2562125.82 | 136358.15 | 0 | 0 | 2698483.97 | 0 | 37611.1017 | 0 | 37611.1017 | 2736095.0717 | 5380159.47 | [5 empty] | N | CS16WR | 20% | WG4 | 20% | WG1 | 60%
503236 | IR18- Investigation of Long Term DOC increases in Drinking Water Catchments | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water | DWQR | SWD | DWQ - Preparing for Future Investment | MS5 | 2018-06-14 | 2018-10-24 | 2019-04-26 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 126203.84 | 79437.79 | 249.51 | 205891.14 | 32556.86 | 51632.6996 | 51632.6996 | 238448 | 0 | 19075.8396 | -0.005 | 19075.8346 | 257523.8346 | 315166.55 | [5 empty] | Y | DW25PS | 100% | [64 empty] | 1 |  |  | 0
502905 | IR18 Kirk Yetholm STW Quality Enhancement | IR18 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | GW1 | 2022-04-13 | 2022-04-11 | 2022-08-02 | 2023-07-21 | 2023-10-23 | Scottish Borders | 0 | 0 | 0 | 0 | 29815.23 | 12454.62 | 38945.91 | 113432.21 | 194647.97 | 2000352.03 | 0 | 0 | 2195000 | 0 | 551748.7852 | 0 | 551748.7852 | 2746748.7852 | 46501.53 | [5 empty] | N | EC01A | 100%
503505 | IR18 Larchfield WOA lead reduction | IR18 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS0 | 2020-08-14 | 2022-04-22 | 2022-07-28 | 2023-02-08 | 2023-05-11 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 11252.09 | 85693.57 | 99527.34 | 196473 | 2387122.83 | 0 | 0 | 2583595.83 | 0 | 658430.1674 | 0 | 658430.1674 | 3242025.9974 | 361769.97 | [5 empty] | N | DW1A | 100%
503121 | IR18 Legacy Infrastructure | IR18 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-11-21 | 2020-01-31 | 2020-01-31 | 2021-07-28 | 2021-08-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 551169.33 | 2726448.8 | 1952084.87 | 5229703 | 203247.99 | 637884.0692 | 637884.0692 | 5432950.99 | 0 | 434636.0792 | -9.3132e-10 | 434636.0792 | 5867587.0692 | 2117982 |  |  |  |  | 32513.0004 | N | CS24S | 50% | CS24W | 50%
503128 | IR18 Legacy Sludge - Intervention Development | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS5 | 2019-07-17 | 2019-05-31 | 2019-07-17 | 2019-07-11 | 2019-07-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 387264.11 | 61818.07 | -14425.1 | 434657.08 | 0 | 0 | 0 | 434657.08 | 0 | 0 | 0 | 0 | 434657.08 | 1936292.09 | [5 empty] | N | LA01_ID | 100%
503332 | IR18 Mannofield WTW - Raw Water Blending | IR18 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS0 | 2020-10-09 | 2021-12-20 | 2022-01-07 | 2022-06-24 | 2022-09-26 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 60310.05 | 26662.62 | 86972.67 | 367508.33 | 0 | 0 | 454481 | 0 | 101368.2942 | 0 | 101368.2942 | 555849.2942 | 1295905.08 | [5 empty] | N | DW23 | 100%
503120 | IR18 Network Segregation Datacentre | IR18 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-11-12 | 2020-12-08 | 2020-12-08 | 2021-07-28 | 2021-07-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 50434.58 | 139024.48 | 754582.94 | 944042 | 490874.02 | 605667.3016 | 605667.3016 | 1434916.02 | 0 | 114793.2816 | -2.3283e-10 | 114793.2816 | 1549709.3016 | 2117982 |  |  |  |  | 110000.0004 | N | CS24S | 50% | CS24W | 50%
503119 | IR18 Network Segregation Treatment | IR18 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-11-12 | 2020-09-11 | 2020-10-05 | 2021-07-28 | 2021-07-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 42897.58 | 305055.41 | 1909114.01 | 2257067 | 325612.33 | 532226.6764 | 532226.6764 | 2582679.33 | 0 | 206614.3464 | 0 | 206614.3464 | 2789293.6764 | 2117982 |  |  |  |  | 17000.0004 | N | CS24S | 50% | CS24W | 50%
503204 | IR18 Operational Technology | IR18 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-12-12 | 2018-12-12 | 2018-12-12 | 2021-06-17 | 2021-06-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 263401.77 | 229477.19 | 355398.04 | 848277 | 118095.63 | 0 | 0 | 966372.63 | 0 | 32573.8267 | 0 | 32573.8267 | 998946.4567 | 2117982 | [5 empty] | N | CS24S | 50% | CS24W | 50%
503052 | IR18 Pateshill WTW Study | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2018-02-02 | 2018-06-26 | 2018-08-01 | 2020-02-28 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1643.29 | 20667.1 | 70334.92 | -68883.43 | 23761.88 | 0 | 0 | 0 | 23761.88 | 0 | 0 | 0 | 0 | 23761.88 | 168058.32 | [5 empty] | N | DW25PS | 100%
503109 | IR18- Rawburn WTW Nitrite Study | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water | DWQR | SWD | DWQ - Preparing for Future Investment | MS7 | 2018-03-26 | 2018-06-26 | 2018-08-09 | 2020-02-26 | 2020-06-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 29227.36 | 63730.78 | -67729.28 | 25228.86 | 0 | 0 | 0 | 25228.86 | 0 | 0 | 0 | 0 | 25228.86 | 167890.55 | [5 empty] | Y | DW25PS | 100% | [64 empty] | 1 |  |  | 0
503114 | IR18 Resilience - Glencorse and East Lothian Connectivity | IR18 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW0 | 2022-10-25 | 2023-09-25 | 2023-12-13 | 2024-09-18 | 2024-12-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 214376.96 | 175905.38 | -163709.91 | 226572.43 | 1015427.57 | 0 | 0 | 1242000 | 0 | 280081.1657 | 0 | 280081.1657 | 1522081.1657 | 90216.65 | [5 empty] | N | CS16WRID | 100%
503115 | IR18 Resilience - Glenlaterrach to Badentinnan Connectivity | IR18 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW0 | 2022-10-26 | 2023-12-26 | 2024-03-15 | 2025-04-15 | 2025-07-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 375169.32 | 138764.68 | -130448.8 | 383485.2 | 1911600.66 | 0 | 0 | 2295085.86 | 0 | 527268.8639 | 0 | 527268.8639 | 2822354.7239 | 45578.23 | [5 empty] | N | CS16WRID | 100%
503117 | IR18 Resilience- Pan Scotland Resilience - Interim Risk Reduction Development | IR18 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS0 | 2021-01-08 | 2022-10-27 | 2023-01-18 | 2023-08-15 | 2023-11-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 85195.93 | 59493.06 | -39344.74 | 105344.24 | 372847.89 | 0 | 0 | 478192.13 | 0 | 102841.0837 | 0 | 102841.0837 | 581033.2137 | 553226.31 | [5 empty] | N | CS16WRID | 100%
503116 | IR18 Resilience - Perth and Turrett Connectivity | IR18 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2020-02-26 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 215768.99 | 0 | 0 | 215768.99 | 0 | 0 | 0 | 215768.99 | 0 | 0 | 0 | 0 | 215768.99 | 90216.65 | [5 empty] | N | CS16WRID | 100%
50043 | IR18 Risk | IR18 | IR18 Allowance | IR18 |  |  | General |  | SWD | IR18 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SR15_IR18_IR18 | 100%
503051 | IR18 Roberton WTW Study | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2018-02-27 | 2018-06-05 | 2018-08-06 | 2020-02-26 | 2020-06-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1476.93 | 64523.08 | 26042.44 | -70026.62 | 22015.82 | 0 | 0 | 0 | 22015.82 | 0 | 0 | 0 | 0 | 22015.82 | 168058.32 | [5 empty] | Y | DW25PS | 100% | [64 empty] | 1 |  |  | 0
510635 | IR18 Sandy Loch Disinfection Improvements - Delivery of high priority significant improvements | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | GW2 | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000.04 | 0 | 0 | 2000000.04 | 0 | 551651.6975 | 0 | 551651.6975 | 2551651.7375 | 788701.34 | [5 empty] | N | DW25P_ID | 100%
503291 | IR18 Security Operations Tools | IR18 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2019-02-06 | 2020-02-12 | 2020-02-12 | 2021-07-28 | 2021-08-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 67237.33 | 733703.66 | 898287.02 | 1699228 | 260787.01 | 417588.2108 | 417588.2108 | 1960015.01 | 0 | 156801.2008 | 0 | 156801.2008 | 2116816.2108 | 2117982 |  |  |  |  | 316881 | N | CS24S | 50% | CS24W | 50%
503241 | IR18 Single Supplies (Non Regulatory Zones) Improvement Study | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-06-21 | 2018-10-31 | 2019-04-01 | 2022-10-17 | 2022-10-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 134215.51 | 53519.96 | 80381.58 | 268117.04 | 1387447.83 | 0 | 0 | 1655564.87 | 0 | 382693.9676 | 0 | 382693.9676 | 2038258.8376 | 1916603.36 | [5 empty] | N | DW25PS | 100%
503048 | IR18 Study into Lead Concentrations at Schools and Nurseries | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-02-20 | 2018-09-03 | 2019-02-20 | 2023-09-27 | 2023-11-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 5926.68 | 78568.95 | 239038.41 | 67538.19 | 391072.23 | 188585.77 | 0 | 0 | 579658 | 0 | 52016.8286 | 0 | 52016.8286 | 631674.8286 | 231573.17 | [5 empty] | N | DW25PS | 100%
503110 | IR18 Tighnabruaich Lead Comms Investigation and Replacement | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS3 | 2018-03-26 | 2018-10-16 | 2018-10-25 | 2023-04-27 | 2023-07-20 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 30000 | 122336.38 | 180691.86 | 333028.24 | 1073465.62 | 2666971.76 | 2666971.76 | 1406493.86 | 0 | 1593506.14 | 2.3283e-10 | 1593506.14 | 3000000 | 276201.26 | [5 empty] | Y | DW25DS | 100% | [64 empty] | 1 |  |  | 0
503195 | IR18 Water Quality Improvement - Camps RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS3 | 2018-12-20 | 2019-10-01 | 2019-09-30 | 2022-08-30 | 2022-05-17 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 267807 | 602957.58 | 211345.43 | 1082110.01 | 1103094.95 | 1103094.95 | 1360531.3689 | 2185204.96 | 257436.4189 | 0 | -0.005 | 257436.4139 | 2442641.3739 | 0 | [5 empty] | N | DW5FS | 46.79% | DW5MR | 53.21%
503196 | IR18 Water Quality Improvement - Corsehouse RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS5 | 2018-09-17 | 2018-12-20 | 2019-03-28 | 2019-12-03 | 2021-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 223050.53 | 305780.54 | 16962.93 | 545794 | 2279.27 | 2279.27 | 3164.0148 | 548073.27 | 884.7448 | 0 | 0 | 884.7448 | 548958.0148 | 0 | [5 empty] | Y | DW5MR | 6.825% | DW5FS | 93.18% | [21 empty] | 128.982 | [43 empty] | 0
503197 | IR18 Water Quality Improvement - Pateshill RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS3 | 2018-12-10 | 2019-12-31 | 2020-01-27 | 2021-09-30 | 2022-09-30 | West Lothian | 0 | 0 | 0 | 0 | 0 | 194699.64 | 450548.39 | 628207.97 | 1273456 | 327752.88 | 327752.88 | 451839.34 | 1601208.88 | 124086.46 | 0 | 2.3283e-10 | 124086.46 | 1725295.34 | 0 | [5 empty] | N | DW5MR | 48.96% | DW5FS | 51.04%
503198 | IR18 Water Quality Improvement - Rawburn RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS3 | 2018-11-30 | 2019-10-01 | 2020-01-24 | 2021-09-30 | 2022-09-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 247014.19 | 591559.37 | 374473.44 | 1213047 | 472490.2 | 472490.2 | 620235.5931 | 1685537.2 | 147745.3931 | 0 | 0 | 147745.3931 | 1833282.5931 | 0 | [5 empty] | N | DW5MR | 15.44% | DW5FS | 84.56%
503199 | IR18 Water Quality Improvement - Roberton RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS3 | 2018-10-26 | 2019-12-20 | 2020-02-13 | 2021-09-30 | 2022-09-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 275000 | 411014.49 | 595694.48 | 1281708.97 | 809129.17 | 809129.1695 | 1022359.6119 | 2090838.14 | 213230.4424 | 0 | 2.3283e-10 | 213230.4424 | 2304068.5824 | 0 | [5 empty] | N | DW5MR | 15% | DW5FS | 85%
503200 | IR18 Water Quality Improvement - Spynie RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS3 | 2018-12-20 | 2019-09-30 | 2019-09-30 | 2021-06-17 | 2021-09-23 | Moray | 0 | 0 | 0 | 0 | 0 | 181983.16 | 388906.96 | 44541.16 | 615431.28 | 140515.72 | 140515.7232 | 253443.8983 | 755947 | 112928.1751 | 0 | 0 | 112928.1751 | 868875.1751 | 0 | [5 empty] | N | DW5MR | 30.15% | DW5FS | 69.85%
500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-03-31 | 2020-07-06 | Fife | 0 | 0 | 59488.58 | 471786.42 | 188739 | 179929 | 175766.94 | 78277.22 | 1153987.16 | 0 | 0 | 0 | 1153987.16 | 0 | 0 | 0 | 0 | 1153987.16 | 638986.22 | [5 empty] | N | EC01G | 0.89% | CS11 | 17.02% | CS16D | 39.26% | EC01D | 42.83%
503215 | Iron Mill Bay WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-04-04 | 2024-02-07 | 2024-05-14 | 2026-08-21 |  | Fife | 0 | 0 | 0 | 0 | 0 | 72338.92 | 28466.11 | 40755.13 | 141560.15 | 14858439.85 | 0 | 0 | 15000000 | 0 | 0 | 0 | 0 | 15000000 | 122419.09 | [5 empty] | N | SG1 | 100%
504323 | Ironmill Bay Diffuser Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-11 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235145.87 | 235145.87 | 0 | 0 | 0 | 235145.87 | 0 | 0 | 0 | 0 | 235145.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402601 | Ironmill Bay WWTP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-29 | 2012-12-13 | 2013-01-30 | 2015-03-20 |  | All East Unitary Authorities | 841219 | 0 | 6572 | -94.89 | 1203.64 | 0 | 0 | 0 | 7680.75 | 0 | 0 | 0 | 848899.75 | 0 | 0 | 0 | 0 | 848899.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501010 | Ironmill Bay WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-10-07 | 2020-06-29 | 2020-08-27 | 2020-08-27 |  | Fife | 0 | 0 | 28951 | 81470.98 | 616.8 | -5504.25 | 122704.69 | -176338.32 | 51900.9 | 0 | 0 | 0 | 51900.9 | 0 | 0 | 0 | 0 | 51900.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500485 | Ironworks | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-28 | 2015-04-28 | 2015-04-28 | 2016-09-27 |  | Scottish Water Wide | 0 | 0 | 9894141.74 | -73613.6 | 0 | 0 | 0 | 0 | 9820528.14 | 0 | 0 | 0 | 9820528.14 | 0 | 0 | 0 | 0 | 9820528.14 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502197 | Ironworks - Capital maintenance - 2016-17 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2017-07-29 |  | Scottish Water Wide | 0 | 0 | 0 | 8700000 | 187192.13 | 12509.91 | -12509.91 | 0 | 8887192.13 | 0 | 0 | 0 | 8887192.13 | 0 | 0 | 0 | 0 | 8887192.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502637 | Ironworks - Capital maintenance - 2017-18 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-03-23 | 2017-03-23 | 2017-04-03 | 2018-04-30 |  | Scottish Water Wide | 0 | 0 | 0 | 653551.4 | 8246524.6 | 125925.58 | 0 | 0 | 9026001.58 | 0 | 0 | 0 | 9026001.58 | 0 | 0 | 0 | 0 | 9026001.58 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503085 | Ironworks - Capital maintenance - 2018-19 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2018-03-26 | 2018-03-26 | 2018-04-02 | 2019-04-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 9200000 | -309847.06 | 0 | 8890152.94 | 0 | 0 | 0 | 8890152.94 | 0 | 0 | 0 | 0 | 8890152.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503557 | Ironworks - Capital maintenance - 2019-20 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2019-03-27 | 2019-03-27 | 2019-04-26 | 2020-09-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8642930.5 | 924526.8 | 9567457.3 | 0 | 0 | 0 | 9567457.3 | 0 | 0 | 0 | 0 | 9567457.3 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505557 | Ironworks - Capital maintenance - 2020 - 21 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2020-03-19 | 2020-04-15 | 2020-04-20 | 2021-08-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9675125 | 9675125 | 0 | 0 | 0 | 9675125 | 0 | 0 | 0 | 0 | 9675125 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402101 | Ironworks Backlog Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWMD | Water infrastructure | MS7 | 2011-12-06 | 2012-07-20 | 2012-07-30 | 2014-05-27 |  | Scottish Water Wide | 2136640 | 0 | 26732 | 6332.38 | 0 | 0 | 0 | 0 | 33064.38 | 0 | 0 | 0 | 2169704.38 | 0 | 0 | 0 | 0 | 2169704.38 | 520618.57 | [5 empty] | N | CM_WSI | 50% | CM_WWI | 50%
511695 | Ironworks Capital Maintenance 2021-22 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS1 | 2021-03-24 | 2021-04-26 | 2021-04-27 | 2022-06-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9400000.05 | 0 | 0 | 9400000.05 | 0 | 0 | 0 | 0 | 9400000.05 | 209381.79 | [5 empty] | N | CM_WSI | 100%
402574 | Ironworks Replacement Programme - 2014-15 investment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-03-12 | 2014-03-11 | 2014-03-11 | 2016-05-19 |  | Scottish Water Wide | 9933487 | 0 | 178688 | -228000.92 | 0 | 0 | 0 | 0 | -49312.92 | 0 | 0 | 0 | 9884174.08 | 0 | 0 | 0 | 0 | 9884174.08 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502390 | Ironworks SR15 Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-01 | 2022-03-01 | 2022-05-20 | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 13.46 | -13.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
403545 | Irvine BW scoping of capex 3 costs Gailes ps | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS6 | 2013-09-23 | 2017-06-05 | 2018-01-22 | 2019-02-28 | 2019-02-28 | North Ayrshire | 13361 | 0 | -2413 | 109777 | 650766 | 78599 | 18085.03 | -21062.92 | 833751.11 | 21064.89 | 21064.8932 | 29241.658 | 868177 | 8176.7648 | 0 | 0 | 8176.7648 | 876353.7648 | 0 | [5 empty] | N | EC16A | 100%
400071 | Irvine Harbour SPS Refurb SPS000257 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-09-29 | 2011-10-27 | 2011-10-31 | 2011-12-14 |  | North Ayrshire | 123162.48 | 0 | 98.96 | 0 | 0 | 0 | 0 | 0 | 98.96 | 0 | 0 | 0 | 123261.44 | 0 | 0 | 0 | 0 | 123261.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402476 | Irvine to Ayr Integrated Catchment Study (Meadowhead Sewer Catchment Area) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-02-06 | 2013-02-06 | 2015-03-26 | 2015-03-31 | Scottish Water Wide | 1630748 | 0 | 629 | 2694.83 | 1272.35 | 0 | 0 | 0 | 4596.18 | 0 | 0 | 0 | 1635344.18 | 0 | 0 | 0 | 0 | 1635344.18 | 0 | [5 empty] | N | CS16S | 100%
501012 | Irvine Valley Galston to Gateshead Sewer Inspections | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-09-30 | 2016-06-29 | 2016-06-29 | 2017-04-24 |  | East Ayrshire | 0 | 0 | 2000 | 43000 | 1477.4 | 0 | 0 | 0 | 46477.4 | 0 | 0 | 0 | 46477.4 | 0 | 0 | 0 | 0 | 46477.4 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403752 | IT Assets Capex Allowance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-03-17 | 2014-03-17 | 2014-04-04 | 2016-02-08 |  | Scottish Water Wide | 464158 | 0 | 114216.75 | 0 | 0 | 0 | 0 | 0 | 114216.75 | 0 | 0 | 0 | 578374.75 | 0 | 0 | 0 | 0 | 578374.75 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500644 | IT Assets Capex Allowance in SR15 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS4 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2021-03-02 |  | Scottish Water Wide | 0 | 0 | 371744 | 662846.94 | 681827.3 | 710142.67 | 582430.56 | 328003.32 | 3336994.79 | 0 | 0 | 0 | 3336994.79 | 0 | 0 | 0 | 0 | 3336994.79 | 613322.63 | [5 empty] | N | CM_M&G | 100%
401603 | ITS Contingency Plans-Water Area Studies | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-10 | 2011-01-18 | 2011-04-29 | 2015-07-07 |  | Scottish Water Wide | 1503807 | 0 | -148.84 | 0 | 0 | 0 | 0 | 0 | -148.84 | 0 | 0 | 0 | 1503658.16 | 0 | 0 | 0 | 0 | 1503658.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401604 | ITS Emergency Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-10 | 2011-03-16 | 2011-04-07 | 2016-05-05 |  | Scottish Water Wide | 1843779 | 0 | -39957.47 | 0 | 0 | 0 | 0 | 0 | -39957.47 | 0 | 0 | 0 | 1803821.53 | 0 | 0 | 0 | 0 | 1803821.53 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500713 | ITS Emergency Equipment - 5007130000 | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWD | Interruptions to Supply | MS7 | 2015-06-29 | 2015-06-29 | 2016-02-26 | 2020-09-16 | 2021-06-09 | Scottish Water Wide | 0 | 0 | 535584.07 | 138920.93 | 78824.77 | 124333.41 | 23497.14 | 3817.85 | 904978.17 | 0 | 0 | 0 | 904978.17 | 0 | 0 | 0 | 0 | 904978.17 | 941431.82 | [5 empty] | N | CS12 | 100%
401605 | ITS End to End Process Development | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-10 | 2013-03-20 | 2013-04-23 | 2016-05-05 |  | Scottish Water Wide | 1740486.5 | 0 | 781163.5 | -524533.68 | 0 | 0 | 0 | 0 | 256629.82 | 0 | 0 | 0 | 1997116.32 | 0 | 0 | 0 | 0 | 1997116.32 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500714 | ITS Network Contingency Plan Development | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWD | Interruptions to Supply | MS7 | 2015-06-30 | 2015-06-30 | 2016-02-04 | 2019-01-25 | 2019-01-25 | Scottish Water Wide | 0 | 0 | 489674 | 467544.3 | 141668.28 | 0 | 0 | 0 | 1098886.58 | 0 | 0 | 0 | 1098886.58 | 0 | 0 | 0 | 0 | 1098886.58 | 941431.82 | [5 empty] | N | CS12 | 100%
401602 | ITS Root Cause Analysis | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-02 | 2011-01-17 | 2011-04-29 | 2015-08-12 |  | Scottish Water Wide | 300470.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300470.18 | 0 | 0 | 0 | 0 | 300470.18 | 0 | [6 empty] | CM_WSI | 100%
501267 | IVS Drybridge Sinkholes | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-12-03 | 2020-06-29 | 2019-11-29 | 2019-09-23 |  | South Ayrshire | 0 | 0 | 8024.88 | 59471.12 | 104498 | 143 | -42423.82 | 4851.31 | 134564.49 | 0 | 0 | 0 | 134564.49 | 0 | 0 | 0 | 0 | 134564.49 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501562 | James St - Taymouth Terr - Burnside St Carnoustie Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2016-08-29 | 2021-11-15 | 2022-01-24 | 2022-06-28 |  | Angus | 0 | 0 | 0 | 12650 | -8861.81 | 0 | -550.66 | 0 | 3237.53 | 755020.46 | 0 | 0 | 758257.99 | 0 | 0 | 0 | 0 | 758257.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502638 | Jamestown Auchincarroch Rd - Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2020-09-25 | 2020-10-14 | 2028-05-02 | 2021-01-29 |  | West Dunbartonshire | 0 | 0 | 0 | 17120.93 | 279.07 | 2060.01 | 6202.98 | -6202.98 | 19460.01 | 0 | 0 | 0 | 19460.01 | 0 | 0 | 0 | 0 | 19460.01 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508722 | Jaw Reservoir Drawdown Works - Phase 1 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-09-30 | 2021-04-14 | 2021-11-25 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4931.45 | 4931.45 | 70072.8 | 0 | 0 | 75004.25 | 0 | 0 | 0 | 0 | 75004.25 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502718 | Jedburgh WWTW - Replace Screw pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-04-10 | 2017-04-10 | 2017-04-24 | 2018-04-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 277200 | -1400 | 0 | 0 | 275800 | 0 | 0 | 0 | 275800 | 0 | 0 | 0 | 0 | 275800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502578 | Johnstone Black Cart Aerial Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-08-28 | 2020-02-21 | 2020-03-16 | 2022-02-23 |  | Renfrewshire | 0 | 0 | 0 | 4601.65 | 11604.19 | 65346.16 | 402777.18 | 398685.82 | 883015 | 613544 | 0 | 0 | 1496559 | 0 | 0 | 38040 | 38040 | 1534599 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504202 | Joppa SPS - mine water dispersion modelling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-02-24 | 2020-06-02 | 2020-10-09 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 22181.96 | 23181.96 | 0 | 0 | 0 | 23181.96 | 0 | 0 | 0 | 0 | 23181.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402674 | Joppa SPS Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-05-16 | 2013-02-27 | 2013-03-25 | 2014-03-31 |  | City of Edinburgh | 315892 | 0 | 1369 | -2335.97 | 0 | 0 | 0 | 0 | -966.97 | 0 | 0 | 0 | 314925.03 | 0 | 0 | 0 | 0 | 314925.03 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506445 | JUNCTION DOCK (GRANGEMOUTH) WWPS NS948833 CAPITAL MAINTENANCE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-08-25 | 2020-10-06 | 2021-08-26 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64722 | 64722 | 35277.68 | 0 | 0 | 99999.68 | 0 | 0 | 0 | 0 | 99999.68 | 90601.29 | [5 empty] | N | WWNI | 100%
508439 | Juniper House Building Purchase (FOP) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2020-09-01 | 2020-09-11 | 2020-09-21 | 2021-03-16 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4190953.56 | 4190953.56 | 0 | 0 | 0 | 4190953.56 | 0 | 0 | 0 | 0 | 4190953.56 | 613322.63 | [5 empty] | N | CM_M&G | 100%
45606 | Kaim (New) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-08-29 | 2015-03-25 | 2015-06-02 | Renfrewshire | 574766.94 | 0 | 26978.6 | 16.55 | 0 | 0 | 0 | 0 | 26995.15 | 0 | 0 | 0 | 601762.09 | 0 | 0 | 0 | 0 | 601762.09 | 28761.13 | [5 empty] | N | DW1A | 100%
504170 | Kaim Spillway Channel Proactive Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-01-07 | 2021-05-01 | 2022-03-10 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 21582.92 | 22532.92 | 0 | 0 | 0 | 22532.92 | 0 | 0 | 0 | 0 | 22532.92 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502365 | Katrine Aqueduct- Balfron Station Pipe Bridge Emergency Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-10-18 | 2016-10-18 | 2017-03-10 | 2018-08-29 |  | Stirling | 0 | 0 | 0 | 348411.21 | 1587519.12 | 1074872.11 | 21036.19 | -240495.42 | 2791343.22 | 0 | 0 | 0 | 2791343.22 | 0 | 0 | 0 | 0 | 2791343.22 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45652 | Katrine Aqueduct Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2012-06-20 | 2012-09-03 | 2014-03-24 |  | East Dunbartonshire | 6852331.91 | 0 | 1214.09 | -266.95 | 0 | 0 | 0 | 0 | 947.14 | 0 | 0 | 0 | 6853279.05 | 0 | 0 | 0 | 0 | 6853279.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500775 | Keith Balloch Rd WWPS 1978 NJ434506 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-07-24 | 2017-01-30 | 2017-04-28 | 2017-08-17 |  | Aberdeenshire | 0 | 0 | 8332.08 | 235336.92 | 66148 | 0 | -20673.91 | 0 | 289143.09 | 0 | 0 | 0 | 289143.09 | 0 | 0 | 0 | 0 | 289143.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403006 | Keith Regent St Sewer Replace-reroute | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-30 | 2015-12-15 | 2015-12-16 | 2015-12-18 |  | Moray | 864.49 | 0 | 15341.72 | 521.21 | 0 | 0 | 0.15 | 0 | 15863.08 | 0 | 0 | 0 | 16727.57 | 0 | 0 | 0 | 0 | 16727.57 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501561 | Keith River Isla Sewer Crossing | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-05-30 | 2019-01-17 | 2019-06-26 | 2020-01-29 |  | Moray | 0 | 0 | 0 | 9769.62 | 11224.38 | 93353 | 86210 | 1658.83 | 202215.83 | 591 | 0 | 0 | 202806.83 | 0 | 0 | 0 | 0 | 202806.83 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503217 | Keith WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-08-31 | 2025-07-14 | 2025-10-16 | 2027-02-10 |  | Moray | 0 | 0 | 0 | 0 | 0 | 43006.42 | 20449.07 | 29930.51 | 93386 | 3406614.19 | 0 | 0 | 3500000.19 | 0 | 0 | 0 | 0 | 3500000.19 | 122419.09 | [5 empty] | N | SG1 | 100%
507737 | Keith WWTW Washwater System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-07-28 | 2021-03-15 | 2022-02-15 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25849 | 25849 | 134651.4 | 0 | 0 | 160500.4 | 0 | 0 | 0 | 0 | 160500.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
36072 | Keithhill Tank - Abandonment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2007-07-02 | 2007-07-02 | 2008-02-07 | 2015-04-21 |  | East Lothian | 86265 | 0 | -16375 | -2391.79 | 0 | 0 | 0 | 0 | -18766.79 | 0 | 0 | 0 | 67498.21 | 0 | 0 | 0 | 0 | 67498.21 | 119022.58 | [5 empty] | N | WSNI | 100%
500198 | Kelso WWTW Odour Upgrade | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater | SEPA | SWMD | Odour | MS6 | 2015-08-26 | 2017-03-23 | 2017-03-27 | 2018-03-31 | 2018-12-31 | Scottish Borders | 0 | 0 | 18160 | 85902.15 | 483157.03 | 82853.1 | 23742 | -0.28 | 693814 | 0 | 0 | 0 | 693814 | 0 | 0 | 0 | 0 | 693814 | 348349.33 | [5 empty] | Y | CS2 | 100% | [46 empty] | 1 | [20 empty] | 0
500498 | Kelty SST - SR15 CM | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2015-06-02 | 2018-03-29 | 2018-06-29 | 2021-02-26 |  | Fife | 0 | 0 | 77186 | 17914 | 223857 | 940527 | 230835.48 | 258559.52 | 1748879 | 2500 | 0 | 0 | 1751379 | 0 | 0 | 0 | 0 | 1751379 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510328 | Kelvinside Terrace South - Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-12-22 | 2022-01-28 | 2022-09-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695.32 | 695.32 | 99999.99 | 0 | 0 | 100695.31 | 0 | 0 | 0 | 0 | 100695.31 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45410 | Kenmore Borehole WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2013-02-18 | 2013-02-26 | 2013-11-28 | 2015-12-22 | Perth and Kinross | 657833.69 | 0 | 20733.15 | 0 | 0 | 0 | 0 | 0 | 20733.15 | 0 | 0 | 0 | 678566.84 | 0 | 0 | 0 | 0 | 678566.84 | 28761.13 | [5 empty] | N | DW23 | 100%
503312 | Kennedy WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-03-05 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 30670.13 | 0 | 0 | 30670.13 | 0 | 0 | 0 | 30670.13 | 0 | 0 | 0 | 0 | 30670.13 | 122419.09 | [5 empty] | N | SG1 | 100%
403782 | Kennethmont WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2017-02-17 | 2021-07-12 | 2021-10-11 | 2022-11-10 |  | Aberdeenshire | 9738 | 0 | 4161.52 | 7031.98 | 12806.56 | 7265.99 | 135240.06 | 39815.66 | 206321.77 | 1657983.98 | 0 | 0 | 1874043.75 | 0 | 0 | 0 | 0 | 1874043.75 | 0 | [5 empty] | N | SG1 | 100%
501731 | Kerse TWS Refurb | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS0 | 2018-09-27 | 2021-09-27 | 2021-11-17 | 2023-07-07 | 2023-11-23 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 29674.86 | 399984.14 | 184394.72 | 614053.72 | 5071838 | 0 | 0 | 5685891.72 | 0 | 1398943.993 | 0 | 1398943.993 | 7084835.713 | 1781526.09 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
504813 | Kessock Bridge pumping main investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-01-24 |  | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020.98 | 1020.98 | 4014.24 | 0 | 0 | 5035.22 | 0 | 0 | 0 | 0 | 5035.22 | 311236.79 | [5 empty] | N | WSI | 100%
502305 | Kettleton CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2020-10-20 | 2022-11-10 | 2023-02-07 | 2026-01-05 |  | Dumfries and Galloway | 0 | 0 | 0 | 36995.83 | 79190.13 | 52002.04 | 116812 | 146416 | 431416 | 6116834.02 | 0 | 0 | 6548250.02 | 0 | 0 | 0 | 0 | 6548250.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503480 | Kettleton Impounding Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-07-21 | 2022-04-22 | 2022-07-25 | 2023-03-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 774.2 | 2453.8 | 3228 | 498188.55 | 0 | 0 | 501416.55 | 0 | 0 | 0 | 0 | 501416.55 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400730 | Kilbirnie Mill Court - Internal Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2010-04-16 | 2011-11-15 | 2011-11-15 | 2016-12-19 | 2016-12-19 | North Ayrshire | 146717 | 146717 | 1272922 | 202361 | 0 | -11617.57 | 0 | 0 | 1463665.44 | 0 | 0 | 0 | 1610382.44 | 0 | 0 | 0 | 0 | 1610382.44 | 180449.74 | [5 empty] | N | FL_DD | 100%
45338 | Kilchoan WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-03-29 | 2011-11-02 | 2013-07-12 | 2013-08-16 | Highland | 3068040.71 | 0 | -16125.02 | 0 | 1308 | 0 | 0 | 0 | -14817.02 | 0 | 0 | 0 | 3053223.69 | 0 | 0 | 0 | 0 | 3053223.69 | 86283.39 | [5 empty] | N | DW3F | 3.277% | DW13 | 9.83% | DW23 | 86.89%
501735 | Kildoon Low DSR Mainout | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2028-07-24 | 2029-05-09 | 2029-09-12 | 2030-01-22 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000.03 | 0 | 0 | 100000.03 | 0 | 0 | 0 | 0 | 100000.03 | 4989107.96 | [5 empty] | N | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 28.57% | CM_WSI | 47.62%
30406 | Killearn STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-14 | 2011-08-22 | 2011-09-30 | 2012-03-22 | 2013-03-25 | Stirling | 605665.56 | 0 | -5248.87 | 0 | 0 | 0 | 0 | 0 | -5248.87 | 0 | 0 | 0 | 600416.69 | 0 | 0 | 0 | 0 | 600416.69 | 148123.55 | [5 empty] | N | EC10A | 8% | EC04A | 8.001% | CM_WWNI | 84%
505083 | Killearn WwTW - New Access Bridge Replacement - 320k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2020-02-28 | 2021-01-29 | 2021-03-17 | 2022-01-05 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 184.7 | 99900.74 | 100085.44 | 220000 | 0 | 0 | 320085.44 | 0 | 0 | 0 | 0 | 320085.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500219 | Killiecrankie - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-03-31 | 2016-03-31 | 2017-02-28 | 2017-10-31 | Perth and Kinross | 0 | 0 | 5176 | 4657.15 | 4146.38 | 1208.12 | 0 | 0 | 15187.65 | 0 | 0 | 0 | 15187.65 | 0 | 0 | 0 | 0 | 15187.65 | 164281.32 | [5 empty] | Y | DW5FS | 100% | [19 empty] | 1 | [47 empty] | 0
504608 | KILLIECRANKIE WTW-DIRTY WASHWATER TANK NO1 - MIXER (5267) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-13 |  | 2020-02-21 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 3320.6 | 0 | 3320.6 | 0 | 0 | 0 | 3320.6 | 0 | 0 | 0 | 0 | 3320.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500829 | Killin RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-24 | 2017-04-13 | 2017-05-31 | 2017-09-30 | 2018-06-30 | Stirling | 0 | 0 | 1730 | 852 | 20034.12 | 3339.88 | 29304.4 | -26997.09 | 28263.31 | 0 | 0 | 0 | 28263.31 | 0 | 0 | 0 | 0 | 28263.31 | 53108.65 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 6.06 | [43 empty] | 0
502577 | Killin WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-09 | 2019-04-24 | 2019-04-24 | 2019-01-23 | 2019-01-23 | Stirling | 0 | 0 | 0 | 20930.23 | 238.73 | 118.3 | 0 | 0 | 21287.26 | 0 | 0 | 0 | 21287.26 | 0 | 0 | 0 | 0 | 21287.26 | 122419.09 | [5 empty] | N | WG1 | 100%
511071 | Killylour WTW - Chemical Store Provision | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-24 | 2021-08-13 | 2022-03-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9261.76 | 9261.76 | 130738.24 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 140000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507999 | Killylour WTW - Ventilation System Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-08-11 | 2021-04-05 | 2021-10-05 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24803 | 24803 | 58697.48 | 0 | 0 | 83500.48 | 0 | 0 | 0 | 0 | 83500.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401043 | Killylour WTW Strategic Solution | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-09-27 | 2012-09-27 | 2016-05-27 | 2016-06-21 | Dumfries and Galloway | 11920420 | 0 | 785534 | 469991 | 99306 | 10015 | 9845.8 | 2393.94 | 1377085.74 | 0 | 0 | 0 | 13297505.74 | 0 | 0 | 0 | 0 | 13297505.74 | 119022.58 |  |  |  |  | 272088.5088 | N | DW1A | 1.7% | WG1 | 11.9% | DW3B | 12.9% | DW13 | 13% | DW3G | 13% | DW4 | 13% | CM_WSNI | 34.5%
500750 | Kilmaluag WTW CWT Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS7 | 2015-08-26 | 2017-05-15 | 2017-09-11 | 2018-08-30 |  | Highland | 0 | 0 | 111237 | 219645.37 | 793610.73 | 215877.68 | 328.22 | -34993.12 | 1305705.88 | 0 | 0 | 0 | 1305705.88 | 0 | 0 | 0 | 0 | 1305705.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
46841 | Kilmaluag WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-03-27 | 2012-04-30 | 2012-11-14 | 2012-11-14 | Highland | 232517.46 | 0 | -736.3 | -5361.73 | 0 | 0 | 0 | 0 | -6098.03 | 0 | 0 | 0 | 226419.43 | 0 | 0 | 0 | 0 | 226419.43 | 28761.13 | [5 empty] | N | DW23 | 100%
500220 | Kilmelford - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-05-25 | 2016-06-25 | 2017-01-31 | 2017-07-31 | Highland | 0 | 0 | 269.54 | 3190.9 | 0 | 1243.34 | 0 | 0 | 4703.78 | 0 | 0 | 0 | 4703.78 | 0 | 0 | 0 | 0 | 4703.78 | 5104.06 | [5 empty] | Y | DW5FS | 100% | [19 empty] | 1 | [47 empty] | 0
500689 | Kilmory STW - Welfare Facilities Block | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS6 | 2015-07-28 | 2017-03-15 | 2018-09-03 | 2020-03-24 |  | Scottish Water Wide | 0 | 0 | 3554 | 28491.06 | 19007.58 | 228201.94 | -939.3 | 4166.12 | 282481.4 | 0 | 0 | 0 | 282481.4 | 0 | 0 | 0 | 0 | 282481.4 | 306661.32 | [5 empty] | N | CM_M&G | 100%
502366 | Kilmuir WOA AC Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-01-20 | 2020-04-08 | 2028-06-13 | 2020-05-22 |  | Highland | 0 | 0 | 0 | 0 | 3087.85 | 0 | 459.5 | -459.5 | 3087.85 | 0 | 0 | 0 | 3087.85 | 0 | 0 | 0 | 0 | 3087.85 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45341 | Kilmuir WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-09-28 | 2011-11-14 | 2016-09-26 | 2016-09-30 | Highland | 4167788.17 | 0 | 1636969.05 | 1492748.69 | 75875.6 | -16663.6 | 0 | 0 | 3188929.74 | 0 | 0 | 0 | 7356717.91 | 0 | 0 | 0 | 0 | 7356717.91 | 28761.13 |  |  |  |  | 70000 | N | DW23 | 100%
403974 | Kilmun Alderburn Place UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2019-08-31 | 2019-12-31 | Argyll and Bute-Cowal & Bute | 4700.32 | 4700.32 | 23949.68 | 185284 | 281842 | 14004 | -157871 | 0 | 347208.68 | 1091 | 1091 | 1514.4937 | 353000 | 423.4937 | 0 | 0 | 423.4937 | 353423.4937 | 0 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
403975 | Kilmun Hillrig UNS SO - Kilmun Inveroch CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2018-07-06 | 2018-03-29 | Argyll and Bute-Cowal & Bute | 294.85 | 294.85 | 73301.15 | 378245 | 719971 | -365685 | 267.76 | -6805.35 | 799294.56 | 0 | 0 | 0 | 799589.41 | 0 | 0 | 0 | 0 | 799589.41 | 0 | [5 empty] | N | EC01A | 100%
402958 | Kilpatrick Avenue Paisley | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2012-10-02 | 2014-09-30 | 2014-11-17 | 2015-04-01 | 2015-04-01 | Renfrewshire | 324721 | 324721 | 15279 | 245.36 | 0 | 4009.02 | 0 | 0 | 19533.38 | 0 | 0 | 0 | 344254.38 | 0 | 0 | 0 | 0 | 344254.38 | 180449.74 | [5 empty] | N | FL_DD | 100%
505931 | Kilsyth Garrell Rd SST - Bldg Demolition - 250320 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-04-02 | 2020-09-10 | 2020-11-02 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29379.55 | 29379.55 | 0 | 0 | 0 | 29379.55 | 0 | 0 | 0 | 0 | 29379.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502402 | Kiltarlity WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2019-12-18 | 2021-11-15 | 2021-12-27 | 2022-11-11 |  | Highland | 0 | 0 | 0 | 21430.58 | 5013.34 | 18811.55 | 94291.63 | 273247.91 | 412795 | 1317507 | 0 | 0 | 1730302 | 0 | 0 | 0 | 0 | 1730302 | 122419.09 | [5 empty] | N | SG1 | 100%
403976 | Kimun 1 Duncans Cottage Cottage UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-03-28 | 2018-03-29 | Argyll and Bute-Cowal & Bute | 4729.75 | 4729.75 | 1061.04 | 2209.21 | -2000 | -3298.44 | 0 | 0 | -2028.19 | 0 | 0 | 0 | 2701.56 | 0 | 0 | 0 | 0 | 2701.56 | 0 | [5 empty] | N | EC01A | 100%
400524 | Kincardine Kirk Street - Sewer Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2010-03-31 | 2014-11-28 | 2015-01-05 | 2015-12-23 | 2015-12-23 | Fife | 350297 | 350297 | 982705 | 56000.34 | 13679.71 | 0 | 0 | 0 | 1052385.05 | 0 | 0 | 0 | 1402682.05 | 0 | 0 | 0 | 0 | 1402682.05 | 180449.74 | [5 empty] | N | FL_DD | 100%
502260 | Kincardine O Neil WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-04-15 | 2019-04-15 | Aberdeenshire | 0 | 0 | 0 | 35402.3 | 3385.67 | 138.98 | 0 | 0 | 38926.95 | 0 | 0 | 0 | 38926.95 | 0 | 0 | 0 | 0 | 38926.95 | 122419.09 | [5 empty] | N | SG1 | 100%
501312 | Kincardine WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-12-03 | 2018-12-03 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Fife | 0 | 0 | 13086.25 | 60700.75 | 1458.44 | 3365.37 | 0 | 0 | 78610.81 | 0 | 0 | 0 | 78610.81 | 0 | 0 | 0 | 0 | 78610.81 | 122419.09 | [5 empty] | N | SG1 | 100%
500497 | Kincardine WwTW - SR15 CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS4 | 2015-06-02 | 2018-09-27 | 2019-01-28 | 2020-11-25 |  | Fife | 0 | 0 | 181182 | 192042.71 | 75555.29 | 383995.19 | 1215272.13 | 520990.68 | 2569038 | 24272 | 0 | 0 | 2593310 | 0 | 0 | 0 | 0 | 2593310 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505675 | Kinfauns Drive Drumchapel Subsidence - Sewer and Water Main Replacement Value 500K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2020-04-07 | 2020-05-01 | 2020-05-10 | 2021-12-16 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 2342.46 | 1712055.54 | 1714398 | 708560.65 | 0 | 0 | 2422958.65 | 0 | 0 | 0 | 0 | 2422958.65 | 520618.57 | [5 empty] | N | CM_WSI | 50% | CM_WWI | 50%
503500 | King George V Tunnel - Structural Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-23 | 2022-02-28 | 2022-05-06 | 2022-09-20 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407.19 | 2407.19 | 686094.83 | 0 | 0 | 688502.02 | 0 | 0 | 0 | 0 | 688502.02 | 311236.79 | [5 empty] | N | CM_M&G | 100%
502338 | Kinghorn Bathing Water - Catchment Network Improvements | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS6 | 2016-11-15 | 2018-03-20 | 2018-03-20 | 2018-09-30 | 2018-11-30 | Fife | 0 | 0 | 0 | 34171 | 186306 | 759431 | 44825 | 19863.8 | 1044596.8 | 0 | 0 | 0 | 1044596.8 | 0 | 0 | 0 | 0 | 1044596.8 | 57965.33 | [5 empty] | Y | EC16 | 100% | [65 empty] | 1 |  | 0
403506 | Kingsbarns WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-06-26 | 2015-04-20 | 2015-05-18 | 2016-03-15 | 2016-03-15 | Fife | 108648 | 0 | 463086 | 1080.82 | 0 | -12432.8 | 0 | 0 | 451734.02 | 0 | 0 | 0 | 560382.02 | 0 | 0 | 0 | 0 | 560382.02 | 0 | [5 empty] | N | SG1 | 100%
505296 | Kingussie WwTW - Caustic Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-05-19 | 2022-08-12 | 2022-11-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5277.75 | 5277.75 | 44672.91 | 0 | 0 | 49950.66 | 0 | 0 | 0 | 0 | 49950.66 | 90601.29 | [5 empty] | N | WWNI | 100%
400724 | Kingussie WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-01 | 2012-02-07 | 2012-07-09 | 2014-07-10 | 2014-07-10 | Highland | 4770864.63 | 0 | 38309.75 | -24810.42 | 0 | 0 | 0 | 0 | 13499.33 | 0 | 0 | 0 | 4784363.96 | 0 | 0 | 0 | 0 | 4784363.96 | 0 | [5 empty] | N | SG1 | 100%
502841 | Kinlochbervie WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2021-01-29 |  | Highland | 0 | 0 | 0 | 0 | 20930.23 | 1500.85 | -18698.9 | 0 | 3732.18 | 0 | 0 | 0 | 3732.18 | 0 | 0 | 0 | 0 | 3732.18 | 122419.09 | [5 empty] | N | WG1 | 100%
45033 | Kinlochewe WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-03-29 | 2011-06-24 | 2013-02-28 | 2013-03-27 | Highland | 3134690.02 | 0 | -3396 | 0 | 0 | 0 | 0 | 0 | -3396 | 0 | 0 | 0 | 3131294.02 | 0 | 0 | 0 | 0 | 3131294.02 | 28761.13 | [5 empty] | N | DW23 | 100%
46835 | Kinlochleven (New) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-18 | 2011-05-02 | 2011-09-13 | 2011-12-07 | Highland | 38613.63 | 0 | 89.47 | 0 | 0 | 0 | 0 | 0 | 89.47 | 0 | 0 | 0 | 38703.1 | 0 | 0 | 0 | 0 | 38703.1 | 28761.13 | [5 empty] | N | DW13 | 100%
504245 | Kinlochleven CWT drainage improvements and capital maintainance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2019-12-09 |  | 2020-04-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 60410.36 | 5435.88 | 65846.24 | 55462.18 | 0 | 0 | 121308.42 | 0 | 0 | 0 | 0 | 121308.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507099 | Kinlochleven CWT Emergency Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2020-06-19 | 2020-09-25 | 2020-11-23 | 2021-03-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308128 | 308128 | 3872 | 0 | 0 | 312000 | 0 | 0 | 0 | 0 | 312000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510385 | Kinlochleven WTW - CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-11-18 | 2023-05-29 | 2023-08-25 | 2024-08-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24488.99 | 24488.99 | 1775511.01 | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 1800000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502880 | Kinlochleven WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-05-07 |  | Highland | 0 | 0 | 0 | 0 | 21034.21 | 1135.29 | -20037.96 | 0 | 2131.54 | 0 | 0 | 0 | 2131.54 | 0 | 0 | 0 | 0 | 2131.54 | 122419.09 | [5 empty] | N | WG1 | 100%
45549 | Kinneff STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2010-12-21 | 2011-09-19 | 2013-02-26 | 2013-03-25 | Aberdeenshire | 807699.15 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 807701.15 | 0 | 0 | 0 | 0 | 807701.15 | 119362.42 | [5 empty] | N | WQ01 | 40% | CM_WWNI | 60%
510941 | Kinneil Kerse AAD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39999999.96 | 0 | 0 | 39999999.96 | 0 | 0 | 0 | 0 | 39999999.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501106 | Kinneil Kerse Aesthetic and Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-08-31 | 2017-01-27 | 2018-06-30 | 2018-11-30 | Falkirk | 0 | 0 | 579 | 7903.25 | 10878.75 | 3321.59 | 0 | 0 | 22682.59 | 0 | 0 | 0 | 22682.59 | 0 | 0 | 0 | 0 | 22682.59 | 53454.76 | [5 empty] | Y | EC10E | 46.28% | EC01G | 53.72% | [38 empty] | 1 | [26 empty] | 0
502886 | Kinneil Kerse STrC Sludge Import Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2028-06-14 | 2028-10-04 | 2029-05-23 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374999.97 | 0 | 0 | 374999.97 | 0 | 0 | 0 | 0 | 374999.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500579 | Kinneil Kerse WwTW - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-08-25 | 2018-11-30 | 2018-12-18 | 2022-03-31 |  | Falkirk | 0 | 0 | 45317 | 217943.27 | 124637.36 | 1440188.87 | 2523527.02 | 1157938.48 | 5509552 | 1795193 | 0 | 0 | 7304745 | 0 | 0 | 695255 | 695255 | 8000000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510099 | Kinneil Kerse WWTW - investigation study of the air valves on the rising main feed to the WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-12-07 | 2021-04-07 | 2021-11-18 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1313 | 1313 | 9476.72 | 0 | 0 | 10789.72 | 0 | 0 | 0 | 0 | 10789.72 | 209381.79 | [5 empty] | N | Ww3 | 100%
501207 | Kinnesswood WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-12-20 | 2019-12-31 | 2019-12-31 | 2019-07-31 | 2020-02-29 | Fife | 0 | 0 | 18500.42 | 118321.96 | 35276.82 | 9497.95 | 59235.6 | -53374.42 | 187458.33 | 0 | 0 | 0 | 187458.33 | 0 | 0 | 0 | 0 | 187458.33 | 1272850.32 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
506953 | Kinning Park PS Building H&S | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-06-12 | 2020-10-08 | 2021-05-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75404 | 75404 | 34839.12 | 0 | 0 | 110243.12 | 0 | 0 | 0 | 0 | 110243.12 | 209381.79 | [5 empty] | N | CM_M&G | 100%
501269 | Kinning Park SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-09-29 |  | Glasgow City | 0 | 0 | 41860 | 2867.69 | 147.51 | 0 | 0 | 0 | 44875.2 | 0 | 0 | 0 | 44875.2 | 0 | 0 | 0 | 0 | 44875.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502902 | Kinning Park WWPS-Capital Maintenance(SR15) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2023-02-17 | 2025-02-05 | 2025-05-02 | 2026-12-28 |  | Glasgow City | 0 | 0 | 0 | 0 | 144835.69 | 3605.9 | 20624.94 | 17342.47 | 186409 | 6813590.91 | 0 | 0 | 6999999.91 | 0 | 0 | 0 | 0 | 6999999.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500151 | Kinross DOA (DOA000260) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater | SEPA | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-12 | 2016-10-31 | 2016-12-31 | Perth and Kinross | 0 | 0 | 27843 | 61747.18 | 0 | 20.64 | 0 | 0 | 89610.82 | 0 | 0 | 0 | 89610.82 | 0 | 0 | 0 | 0 | 89610.82 | 72047.27 | [5 empty] | Y | CS16D | 44.91% | CS11 | 55.09% | [37 empty] | 1 | [27 empty] | 0
45795 | Kinross South SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-09-01 | 2012-01-20 | 2013-03-28 | 2013-09-12 | Perth and Kinross | 1805160.73 | 0 | 21863.32 | 51855.71 | 0 | 0 | 0 | 0 | 73719.03 | 0 | 0 | 0 | 1878879.76 | 0 | 0 | 0 | 0 | 1878879.76 | 28761.13 | [5 empty] | N | WQ01C | 100%
46363 | Kinross WWTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2009-07-29 | 2012-01-24 | 2012-05-28 | 2015-01-06 | 2015-01-06 | Perth and Kinross | 3112638 | 0 | 8077.19 | 29299.51 | 30.81 | 0 | 0 | 0 | 37407.51 | 0 | 0 | 0 | 3150045.51 | 0 | 0 | 0 | 0 | 3150045.51 | 122419.09 | [5 empty] | N | SG1 | 100%
500794 | Kintore Strategic Wastewater Solution | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-22 | 2020-12-08 | 2021-02-16 | 2020-12-09 |  | Aberdeenshire | 0 | 0 | 3271.03 | 1566.9 | 0 | 0 | 39452.54 | -43826.19 | 464.28 | 0 | 0 | 0 | 464.28 | 0 | 0 | 0 | 0 | 464.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501157 | Kippen STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-04-25 | 2027-06-09 | 2027-10-21 | 2028-05-15 |  | Stirling | 0 | 0 | 0 | 42868.62 | -5664.12 | 0 | -4543.69 | 1409.76 | 34070.57 | 520929.43 | 0 | 0 | 555000 | 0 | 0 | 0 | 0 | 555000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
45560 | Kippen STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2011-06-01 | 2011-07-28 | 2012-03-28 | 2012-03-31 | Stirling | 1049400.59 | 0 | 401.94 | 0 | 0 | 0 | 0 | 0 | 401.94 | 0 | 0 | 0 | 1049802.53 | 0 | 0 | 0 | 0 | 1049802.53 | 119362.42 | [5 empty] | N | CM_WWNI | 8.612% | WQ01 | 91.39%
503285 | Kippen WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-04-15 | 2019-04-15 | Stirling | 0 | 0 | 0 | 0 | 0 | 78314.46 | 0 | 0 | 78314.46 | 0 | 0 | 0 | 78314.46 | 0 | 0 | 0 | 0 | 78314.46 | 122419.09 | [5 empty] | N | SG1 | 100%
504435 | Kippford Sep - Temporary Chemical Dosing | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 |  | 2020-09-30 | 2020-12-14 | 2020-12-22 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.12 | 56.12 | 0 | 0 | 0 | 56.12 | 0 | 0 | 0 | 0 | 56.12 | 1484266.33 | [5 empty] | N | EC16 | 100%
503310 | Kippford ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-08-20 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 30495.35 | 531.58 | 0 | 31026.93 | 0 | 0 | 0 | 31026.93 | 0 | 0 | 0 | 0 | 31026.93 | 122419.09 | [5 empty] | N | SG1 | 100%
504188 | Kippford Temporary Dosing Installation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-05-21 | 2020-07-06 | 2023-11-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 10582.15 | 140435.85 | 151018 | 131140.55 | 0 | 0 | 282158.55 | 0 | 0 | 0 | 0 | 282158.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501252 | Kirbister WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-07-27 | 2028-06-08 | 2028-10-11 | 2029-02-23 |  | Orkney Islands | 0 | 0 | 3837.43 | 3043.46 | 778.19 | 2071.33 | 2614.75 | 0 | 12345.16 | 159655.01 | 0 | 0 | 172000.17 | 0 | 0 | 0 | 0 | 172000.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503244 | Kirbister WTW - Poly dosing unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2020-05-05 | 2021-09-28 | 2021-11-29 | 2022-05-20 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 24246.42 | 4115.49 | 34969.09 | 63331 | 536669.12 | 0 | 0 | 600000.12 | 0 | 0 | 0 | 0 | 600000.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501228 | Kirbister WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2017-03-21 | 2019-06-28 | 2019-06-28 | 2019-06-30 | 2019-06-30 | Orkney Islands | 0 | 0 | 6117.97 | 58678.96 | -1342.57 | 1244.37 | 1822.69 | 1746.16 | 68267.58 | 0 | 0 | 0 | 68267.58 | 0 | 0 | 0 | 0 | 68267.58 | 185655.66 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
502566 | Kirbister WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS4 | 2021-01-05 | 2021-01-05 | 2021-01-18 | 2021-01-18 |  | Orkney Islands | 0 | 0 | 0 | 20930.23 | 5186.78 | 117888.2 | 20797.9 | 4871.36 | 169674.46 | 0 | 0 | 0 | 169674.46 | 0 | 0 | 0 | 0 | 169674.46 | 122419.09 | [5 empty] | N | WG1 | 100%
402579 | Kirbister WTW Provision of Pre-Treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-05-10 | 2014-07-29 | 2014-09-01 | 2015-05-25 |  | Orkney Islands | 164189 | 0 | 40176 | 82.08 | -490.17 | 0 | 0 | 0 | 39767.91 | 0 | 0 | 0 | 203956.91 | 0 | 0 | 0 | 0 | 203956.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500767 | Kirk Street Peterhead Reline Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-24 | 2016-04-29 | 2016-05-25 | 2017-05-24 |  | Aberdeenshire | 0 | 0 | 12000 | 81006 | 24295 | 5388.15 | -3275.25 | 0 | 119413.9 | 0 | 0 | 0 | 119413.9 | 0 | 0 | 0 | 0 | 119413.9 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500196 | Kirk Yetholm WWTW Relocation | IR18 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2015-09-18 | 2018-03-22 | 2018-03-22 | 2018-02-05 | 2018-03-22 | Scottish Borders | 0 | 0 | 18094 | -3623.38 | 4166.19 | 0 | 0 | 0 | 18636.81 | 0 | 0 | 0 | 18636.81 | 0 | 0 | 0 | 0 | 18636.81 | 46501.53 | [5 empty] | N | EC01A | 100%
46158 | Kirkcaldy Buchanan Court SPS Refurb - SPS001615 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2010-11-29 | 2011-06-27 | 2012-01-26 |  | Fife | 533572.99 | 0 | 43.68 | 0 | 0 | 0 | 0 | 0 | 43.68 | 0 | 0 | 0 | 533616.67 | 0 | 0 | 0 | 0 | 533616.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403749 | Kirkcaldy BW Investigation of Options | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2014-03-27 | 2014-10-29 | 2014-11-03 | 2016-03-31 | 2016-03-31 | Fife | 232937 | 0 | 119503 | 11180.6 | 0 | 0 | 0 | 0 | 130683.6 | 0 | 0 | 0 | 363620.6 | 0 | 0 | 0 | 0 | 363620.6 | 115930.67 | [5 empty] | Y | EC16 | 100% | [65 empty] | 1 |  | 0
501102 | Kirkcaldy Catchment (DAS) & Aesthetic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2013-09-09 | 2014-05-30 | 2014-06-23 | 2017-01-31 | 2017-03-31 | Fife | 0 | 0 | 3144 | 27070 | 2019.86 | 0 | 0 | 0 | 32233.86 | 0 | 0 | 0 | 32233.86 | 0 | 0 | 0 | 0 | 32233.86 | 95355.88 | [5 empty] | Y | EC01G | 15% | EC01D | 85% | [38 empty] | 1 | [26 empty] | 0
46155 | Kirkcaldy Charlotte Street SPS Refurb - SPS001812 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-09-09 | 2011-03-30 | 2011-03-31 |  | Fife | 132499.81 | 0 | -52.52 | 0 | 0 | 0 | 0 | 0 | -52.52 | 0 | 0 | 0 | 132447.29 | 0 | 0 | 0 | 0 | 132447.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46219 | Kirkcaldy STC Refurb - STC000097 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2011-03-30 | 2011-09-23 | 2012-08-14 |  | Fife | 322993.93 | 0 | 18.19 | 0 | 0 | 0 | 0 | 0 | 18.19 | 0 | 0 | 0 | 323012.12 | 0 | 0 | 0 | 0 | 323012.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
45635 | Kirkcaldy STW Refurb - STW001982 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-03-31 | 2011-09-20 | 2013-10-31 |  | Fife | 2149017.14 | 0 | 32458.08 | -652.43 | 0 | 0 | 0 | 0 | 31805.65 | 0 | 0 | 0 | 2180822.79 | 0 | 0 | 0 | 0 | 2180822.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501746 | KIRKCALDY WWTW 1987 NT287923 Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2020-01-16 | 2020-12-22 | 2021-03-16 | 2021-08-31 |  | Fife | 0 | 0 | 0 | 3632.58 | 0 | 0 | 16342.25 | 93928.17 | 113903 | 165490.39 | 0 | 0 | 279393.39 | 0 | 0 | 0 | 0 | 279393.39 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501153 | Kirkconnel STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-12-10 | 2018-12-12 | 2019-01-07 | 2021-09-28 |  | Dumfries and Galloway | 0 | 0 | 20632 | 211214.27 | 110259.44 | 480178.54 | 1514666.25 | 57864.5 | 2394815 | 639202.96 | 0 | 0 | 3034017.96 | 0 | 0 | 294374.04 | 294374.04 | 3328392 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46335 | Kirkconnel STW - STW000435 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-25 | 2010-12-23 | 2011-02-28 | 2015-06-23 |  | Dumfries and Galloway | 1409351.23 | 0 | 67676.99 | 3305.3 | 1372.06 | 0 | 0 | 0 | 72354.35 | 0 | 0 | 0 | 1481705.58 | 0 | 0 | 0 | 0 | 1481705.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503809 | Kirkcudbright - Harbour Sq CSO and Beaconsfield Pl Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2022-02-15 | 2022-06-22 | 2022-08-23 | 2023-07-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 27480.9 | 265186.03 | 292666.94 | -12666.94 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 280000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506512 | Kirkhill WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-07-03 | 2025-04-28 | 2025-07-28 | 2026-08-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62701 | 62701 | 1937299.44 | 0 | 0 | 2000000.44 | 0 | 0 | 0 | 0 | 2000000.44 | 122419.09 | [5 empty] | N | SG1 | 100%
503218 | Kirkinner WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2027-09-02 | 2029-02-14 | 2029-06-13 | 2030-06-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 67002.51 | 1364.05 | -12.35 | 68354.21 | 0 | 0 | 0 | 68354.21 | 0 | 0 | 0 | 0 | 68354.21 | 122419.09 | [5 empty] | N | SG1 | 100%
501287 | Kirkland Methil Pipebridge Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-07-07 | 2018-02-26 | 2018-02-27 | 2019-04-15 |  | Fife | 0 | 0 | 0 | 104370 | 833616 | 3189428 | 109094.68 | 47759.26 | 4284267.94 | 0 | 0 | 0 | 4284267.94 | 0 | 0 | 0 | 0 | 4284267.94 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501070 | Kirkmichael WTW - CM | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS3 | 2020-06-29 | 2020-06-30 | 2020-06-30 | 2021-10-22 | 2021-11-22 | Perth and Kinross | 0 | 0 | 13344.84 | 122988.01 | 13783.99 | 21959.5 | 102279.6 | -36069.11 | 238286.83 | 61723.28 | 85724.0898 | 85724.0898 | 300010.11 | 0 | 24000.8088 | 0 | 24000.8088 | 324010.9188 | 451950.83 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
501353 | KIRKMICHAEL WWTW NS336086 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2016-07-11 | 2021-10-11 | 2022-03-25 | 2023-02-09 |  | South Ayrshire | 0 | 0 | 0 | 42579.77 | 81481.19 | -12008.25 | 5353.55 | 970.74 | 118377 | 1441167.7 | 0 | 0 | 1559544.7 | 0 | 0 | 0 | 0 | 1559544.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46177 | Kirkoswald Sewage Pumping Station | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-06-27 | 2011-09-19 | 2012-06-27 | 2012-09-07 | South Ayrshire | 692270.12 | 0 | 1127.98 | 0 | 0 | 0 | 0 | 0 | 1127.98 | 0 | 0 | 0 | 693398.1 | 0 | 0 | 0 | 0 | 693398.1 | 28761.13 | [5 empty] | N | WQ01C | 100%
45538 | Kirkpatrick Fleming STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-03-21 | 2011-10-12 | 2012-08-30 | 2013-01-21 | Dumfries and Galloway | 821788.19 | 0 | 2090.06 | 0 | 0 | 0 | 0 | 0 | 2090.06 | 0 | 0 | 0 | 823878.25 | 0 | 0 | 0 | 0 | 823878.25 | 151180.22 | [5 empty] | N | SG1 | 16.45% | WQ01 | 83.55%
500144 | Kirkwall DOA (DOA000561) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-02-26 | 2016-04-19 | 2019-01-01 | 2019-03-28 | Orkney Islands | 0 | 0 | 36113 | 4093 | 40463 | 15400 | -12894.42 | 0 | 83174.58 | 0 | 0 | 0 | 83174.58 | 0 | 0 | 0 | 0 | 83174.58 | 9550.69 | [5 empty] | N | EC01D | 25.5% | CS16D | 74.5%
504760 | Kirkwall Head of Work STC - Lime Plant Modifications | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-08-04 | 2022-09-23 | 2023-02-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 817.76 | 26178.24 | 26996 | 83004.51 | 0 | 0 | 110000.51 | 0 | 0 | 0 | 0 | 110000.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509520 | Kirkwall Head of Work WwTW - Replace SCADA | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-07-29 | 2023-04-10 | 2023-11-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2163 | 2163 | 197837.43 | 0 | 0 | 200000.43 | 0 | 0 | 0 | 0 | 200000.43 | 90601.29 | [5 empty] | N | WWNI | 100%
500777 | Kirkwall WWTW 2003 HY475137 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-08-20 | 2027-04-22 | 2027-06-22 | 2027-11-26 |  | Orkney Islands | 0 | 0 | 22822 | 70421.98 | -4847.98 | 0 | -5191.88 | 0 | 83204.12 | 16834.88 | 0 | 0 | 100039 | 0 | 0 | 0 | 0 | 100039 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
30425 | Kirriemuir STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-07-24 | 2011-09-21 | 2011-11-08 | 2014-07-31 | 2014-08-26 | Angus | 3697297.02 | 0 | 21146.29 | -31175.6 | 7050.58 | 0 | 0 | 0 | -2978.73 | 0 | 0 | 0 | 3694318.29 | 0 | 0 | 0 | 0 | 3694318.29 | 119362.42 | [5 empty] | N | CM_WWNI | 10% | EC04A | 90%
45800 | Kirtlebridge Marquiss SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2011-07-28 | 2011-09-05 | 2013-03-01 | 2013-03-26 | Dumfries and Galloway | 3294058.06 | 0 | -1356.44 | 0 | 0 | 0 | 0 | 0 | -1356.44 | 0 | 0 | 0 | 3292701.62 | 0 | 0 | 0 | 0 | 3292701.62 | 119362.42 | [5 empty] | N | CM_WWNI | 5% | WQ01C | 95%
501728 | Knockdon SR to Bellshill SR - Loch Doon Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-04-01 | 2027-12-10 | 2028-03-03 | 2028-07-18 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4429 | 4429 | 194441.39 | 0 | 0 | 198870.39 | 0 | 0 | 0 | 0 | 198870.39 | 4989107.96 | [5 empty] | N | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 28.57% | CM_WSI | 47.62%
508056 | Knockendon Reservoir Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-19 | 2021-08-12 | 2022-03-25 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6633.78 | 6633.78 | 93457.93 | 0 | 0 | 100091.71 | 0 | 0 | 0 | 0 | 100091.71 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402182 | Knockendon Reservoir Spillway Repair- Drainage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-03-27 | 2012-06-11 | 2013-03-08 | 2013-03-08 | North Ayrshire | 404614.81 | 0 | 118.17 | 0 | 0 | 0 | 0 | 0 | 118.17 | 0 | 0 | 0 | 404732.98 | 0 | 0 | 0 | 0 | 404732.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503432 | Knockendon VT Bridge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 | 2019-10-02 | 2021-03-05 | 2021-09-10 | 2022-09-23 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 10046.51 | 7500.83 | 44196.09 | 61743.43 | 545580.57 | 0 | 0 | 607324 | 0 | 0 | 0 | 0 | 607324 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501237 | Knockfell SR - Outlet Trunk Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2016-04-06 | 2021-04-12 | 2021-03-31 | 2021-10-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 33190.8 | 49740.83 | 109998.33 | 139596.75 | 303386.73 | 635913.44 | 1683747.36 | 0 | 0 | 2319660.8 | 0 | 0 | 0 | 0 | 2319660.8 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401013 | Knockjarder Service Reservoir Outlet Mains Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-05-31 | 2010-12-20 | 2011-02-07 | 2015-07-20 |  | South Ayrshire | 1318123 | 0 | 32000 | 11797.93 | -52550.98 | 0 | 0 | 0 | -8753.05 | 0 | 0 | 0 | 1309369.95 | 0 | 0 | 0 | 0 | 1309369.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508263 | Knocknairshill Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-09-08 | 2021-06-11 | 2022-01-24 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3652.94 | 3652.94 | 41945.55 | 0 | 0 | 45598.49 | 0 | 0 | 0 | 0 | 45598.49 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402183 | Knocknairshill Reservoir Spillway - Pitching Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2011-11-10 | 2011-11-14 | 2012-03-01 | 2012-03-21 | Inverclyde | 335439.09 | 0 | 43.68 | 0 | 0 | 0 | 0 | 0 | 43.68 | 0 | 0 | 0 | 335482.77 | 0 | 0 | 0 | 0 | 335482.77 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402896 | Knowesdean Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-23 | 2013-12-17 | 2014-02-11 | 2014-10-21 | 2015-02-02 | Scottish Borders | 154029.62 | 0 | 205.43 | 0 | 0 | 0 | 0 | 0 | 205.43 | 0 | 0 | 0 | 154235.05 | 0 | 0 | 0 | 0 | 154235.05 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500831 | Kyle of Lochalsh RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-01-20 | 2016-03-30 | 2016-06-22 | 2017-01-31 | 2017-11-30 | Highland | 0 | 0 | 4445.71 | 8896.29 | 3042.01 | 1205.05 | 8923.59 | 0 | 26512.65 | 0 | 0 | 0 | 26512.65 | 0 | 0 | 0 | 0 | 26512.65 | 56616.84 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 20.53 | [43 empty] | 0
503364 | Kyle of Lochalsh WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-05-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 20093.02 | -20093.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG1 | 100%
502908 | Kyle of Lochalsh WTW pH Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-04-23 |  | Highland | 0 | 0 | 0 | 0 | 21935.36 | 123.03 | -20117.96 | 0 | 1940.43 | 0 | 0 | 0 | 1940.43 | 0 | 0 | 0 | 0 | 1940.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504482 | Kyle WTW - pH Correction | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-06-19 | 2020-06-19 | 2020-06-19 | 2020-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 446.12 | 0 | 446.12 | 0 | 0 | 0 | 446.12 | 0 | 0 | 0 | 0 | 446.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500830 | Kylesku RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2017-03-23 | 2017-04-18 | 2017-06-30 | 2018-03-31 | Highland | 0 | 0 | 3140 | 6229.9 | 7656.63 | 500.65 | 0 | 0 | 17527.18 | 0 | 0 | 0 | 17527.18 | 0 | 0 | 0 | 0 | 17527.18 | 11817.97 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 3.34 | [43 empty] | 0
502840 | Kylesku WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2021-01-29 |  | Highland | 0 | 0 | 0 | 0 | 20930.23 | 1545.39 | -19817.55 | 0 | 2658.07 | 0 | 0 | 0 | 2658.07 | 0 | 0 | 0 | 0 | 2658.07 | 122419.09 | [5 empty] | N | WG1 | 100%
503837 | Labsense Coagulation Chemistry Analysers 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-17 |  | 2020-04-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 59920.23 | 0 | 59920.23 | 0 | 0 | 0 | 59920.23 | 0 | 0 | 0 | 0 | 59920.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501533 | Ladykirk Raith TWS Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-08-23 | 2029-12-27 | 2030-08-13 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488915.04 | 0 | 0 | 488915.04 | 0 | 0 | 0 | 0 | 488915.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506447 | LADYSNEUK (STIRLING) WWPS ACCESS IMPROVEMENTS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-09-07 | 2021-03-18 | 2021-07-29 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32760 | 32760 | 17240 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 209381.79 | [5 empty] | N | WWI | 100%
503075 | Ladysneuk SPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2020-07-03 | 2021-11-22 | 2022-01-17 | 2022-07-19 |  | Stirling | 0 | 0 | 0 | 0 | 12898.17 | 11257.12 | 1646.75 | 42924.96 | 68727 | 599839.31 | 0 | 0 | 668566.31 | 0 | 0 | 0 | 0 | 668566.31 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508092 | Laggan Bridge Borehole casing repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-10 | 2021-04-12 | 2021-11-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85550 | 85550 | 252.45 | 0 | 0 | 85802.45 | 0 | 0 | 0 | 0 | 85802.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404133 | Laggan Bridge WTW - Cartridge Filter and UV | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS4 | 2017-04-28 | 2018-08-28 | 2018-10-11 | 2020-02-24 | 2021-07-14 | Highland | 0 | 0 | 0 | 0 | 48029.2 | 481961.44 | 146820.93 | 123700.43 | 800512 | 196254.57 | 196254.57 | 272434.7547 | 996766.57 | 76180.1847 | 0 | 0 | 76180.1847 | 1072946.7547 | 0 | [5 empty] | N | DW23 | 100%
502573 | Laggan Bridge WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-04-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 20930.23 | 671.68 | 1194.7 | -18475.49 | 0 | 4321.12 | 0 | 0 | 0 | 4321.12 | 0 | 0 | 0 | 0 | 4321.12 | 122419.09 | [5 empty] | N | WG1 | 100%
502839 | Laid WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-04 | 2019-04-04 | Highland | 0 | 0 | 0 | 0 | 21346.13 | 1290.63 | -19701.53 | 0 | 2935.23 | 0 | 0 | 0 | 2935.23 | 0 | 0 | 0 | 0 | 2935.23 | 122419.09 | [5 empty] | N | WG1 | 100%
46193 | Laighpark (Paisley) STW Refurb - STW000455 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-09-23 | 2011-09-23 | 2013-12-20 |  | Renfrewshire | 5855436.22 | 0 | -68728.56 | 0 | 0 | 0 | 0 | 0 | -68728.56 | 0 | 0 | 0 | 5786707.66 | 0 | 0 | 0 | 0 | 5786707.66 | 90601.29 |  |  |  |  | 20230 | N | CM_WWNI | 100%
511942 | Laighpark Paisley WWTW - Sludge Pumps intrusive inspection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-26 | 2022-03-14 | 2022-10-24 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1172.43 | 1172.43 | 8827.57 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501719 | Laighpark Paisley WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-10-31 | 2018-08-14 | 2018-11-05 | 2021-07-01 |  | Renfrewshire | 0 | 0 | 0 | 15850.44 | 195135.33 | 1076591.23 | 241161 | 113010 | 1641748 | 2550 | 0 | 0 | 1644298 | 0 | 0 | 0 | 0 | 1644298 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502733 | Laighpark WWTW - Intermediate Lift Screw Pump Failure | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-04-25 | 2017-07-12 | 2017-08-07 | 2018-02-07 |  | Glasgow City | 0 | 0 | 0 | 0 | 2250180.95 | -43342.27 | -20586.74 | 0.01 | 2186251.95 | 0 | 0 | 0 | 2186251.95 | 0 | 0 | 0 | 0 | 2186251.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402641 | Laighpark WwTW Aeration Lane cleaning | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-06-18 | 2012-06-18 | 2012-07-30 | 2016-06-30 |  | East Renfrewshire | 38932.3 | 0 | -0.3 | -6367.51 | 0 | 0 | 0 | 0 | -6367.81 | 0 | 0 | 0 | 32564.49 | 0 | 0 | 0 | 0 | 32564.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501399 | LAIRDS CAST TWP 2001 NO678963 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-06-30 |  | Aberdeenshire | 0 | 0 | 2121.87 | 79.8 | 0 | 0 | 0 | 0 | 2201.67 | 0 | 0 | 0 | 2201.67 | 0 | 0 | 0 | 0 | 2201.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402946 | Lambert Drive Dunfermline | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-09-28 | 2012-12-04 | 2013-02-18 | 2013-03-25 | 2013-03-25 | Fife | 30195 | 0 | -472.46 | 0 | 0 | 0 | 0 | 0 | -472.46 | 0 | 0 | 0 | 29722.54 | 0 | 0 | 0 | 0 | 29722.54 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
503501 | Lambhill Tunnel - Structural Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-23 | 2022-04-01 | 2022-07-01 | 2023-04-03 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2215.34 | 2215.34 | 1233148.83 | 0 | 0 | 1235364.17 | 0 | 0 | 0 | 0 | 1235364.17 | 311236.79 | [5 empty] | N | CM_M&G | 100%
503720 | Lamlash DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-10-04 | 2019-10-04 | 2020-02-05 | 2021-11-18 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 395325.16 | 191923.84 | 587249 | 168877.1 | 0 | 0 | 756126.1 | 0 | 0 | 0 | 0 | 756126.1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
512259 | LAMLASH WWPS 3 2006 NS026309 - Capital ancillary maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-08-02 | 2021-10-22 | 2022-06-06 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29999.97 | 0 | 0 | 29999.97 | 0 | 0 | 0 | 0 | 29999.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503378 | Lamlash WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-05-28 | 2020-05-28 | 2020-08-28 | 2020-08-28 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 65637.27 | 10654.75 | -9170.55 | 67121.48 | 0 | 0 | 0 | 67121.48 | 0 | 0 | 0 | 0 | 67121.48 | 122419.09 | [5 empty] | N | SG1 | 100%
501693 | Lanark Rd Kirkmuirhill Pipe Bridge Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-07-05 | 2018-12-05 | 2019-02-25 | 2019-07-08 |  | South Lanarkshire | 0 | 0 | 0 | 18862.98 | 90485.02 | 314047 | 8805.75 | 1322.21 | 433522.95 | 0 | 0 | 0 | 433522.95 | 0 | 0 | 0 | 0 | 433522.95 | 209381.79 | [5 empty] | N | CM_WWI | 100%
30434 | Lanark STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-20 | 2010-12-30 | 2011-01-18 | 2012-01-01 | 2012-03-21 | South Lanarkshire | 2177233.5 | 0 | 1197.87 | 0 | 0 | 0 | 0 | 0 | 1197.87 | 0 | 0 | 0 | 2178431.37 | 0 | 0 | 0 | 0 | 2178431.37 | 119362.42 | [5 empty] | N | EC01A | 30.82% | CM_WWNI | 69.18%
503070 | Lanark WWTW - RAS Screw Pumps Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-07-21 | 2028-03-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86.12 | 86.12 | 315999.93 | 0 | 0 | 316086.05 | 0 | 0 | 0 | 0 | 316086.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501194 | Land Acquisition Run off and Compensation Liabilities | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-11-27 | 2015-11-27 | 2016-02-12 | 2021-11-12 |  | Scottish Water Wide | 0 | 0 | 298491.68 | 894180.67 | 603924.65 | 1122274.71 | 633526.5 | 373932.01 | 3926330.22 | 208939.31 | 0 | 0 | 4135269.53 | 0 | 0 | 0 | 0 | 4135269.53 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500145 | Langholm DOA (DOA000075) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-05-26 | 2016-06-20 | 2018-12-01 | 2019-07-04 | Dumfries and Galloway | 0 | 0 | 12754 | 15157.18 | 97773.82 | 8161 | 8232.76 | 0 | 142078.76 | 0 | 0 | 0 | 142078.76 | 0 | 0 | 0 | 0 | 142078.76 | 73760.57 | [5 empty] | N | EC01G | 8.062% | EC01D | 42.68% | CS16D | 49.26%
503700 | Larchfield Borehole WTW - UV Plant Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-12-03 | 2021-06-07 | 2021-08-23 | 2022-04-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20724.63 | 20724.63 | 415340.71 | 0 | 0 | 436065.34 | 0 | 0 | 0 | 0 | 436065.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500147 | Largoward DOA (DOA000249) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-05-30 | 2016-08-19 | 2019-05-31 | 2019-07-31 | Fife | 0 | 0 | 13245 | 11894 | 11838 | 40966.84 | 6545.43 | 0 | 84489.27 | 0 | 0 | 0 | 84489.27 | 0 | 0 | 0 | 0 | 84489.27 | 112176.2 | [5 empty] | Y | EC01G | 25.04% | EC01D | 74.96% | [38 empty] | 1 | [26 empty] | 0
402837 | Largs Bathing Water Compliance | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2012-08-31 | 2019-07-31 | 2019-07-17 | 2019-07-24 | 2019-07-24 | Argyll and Bute-Cowal & Bute | 32664.39 | 0 | 4584.61 | 0.25 | -4302 | 334.77 | 0 | 0 | 617.63 | 0 | 0 | 0 | 33282.02 | 0 | 0 | 0 | 0 | 33282.02 | 0 | [5 empty] | N | EC02B | 100%
512073 | Largs DOA - Replacement of assumed failed pipe coupling on Buchanan Street PS Rising Ma | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-04-01 | 2021-09-24 | 2022-05-09 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39999.96 | 0 | 0 | 39999.96 | 0 | 0 | 0 | 0 | 39999.96 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500152 | Largs DOA (DOA002517) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-28 | 2018-03-29 | 2018-06-25 | North Ayrshire | 0 | 0 | 36102 | 130135 | 61859.29 | -16.85 | 0 | 0 | 228079.44 | 0 | 0 | 0 | 228079.44 | 0 | 0 | 0 | 0 | 228079.44 | 4617.88 | [5 empty] | N | CS16D | 32.24% | EC01G | 67.76%
403548 | Largs Pencil BW Scoping of Cx 3 Costs for Fairlie WWTW and Anthony Road CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS6 | 2013-11-29 | 2018-09-25 | 2018-12-19 | 2020-08-26 | 2021-03-01 | North Ayrshire | 88297.88 | 0 | 73202.12 | 137298 | 102940.3 | 1414236.7 | 743644 | 36191 | 2507512.12 | 2500 | 2500 | 3470.4256 | 2598310 | 970.4256 | 0 | 0 | 970.4256 | 2599280.4256 | 0 |  |  |  |  | 3205.6452 | N | EC16 | 100%
503272 | Largs WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2024-04-24 | 2026-02-20 | 2026-05-25 | 2027-06-18 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 77263.27 | 5527.39 | 0.34 | 82791 | 0 | 0 | 0 | 82791 | 0 | 0 | 0 | 0 | 82791 | 122419.09 | [5 empty] | N | SG1 | 100%
506907 | Larkfield SR - Secondary Disinfection & H&S Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-02 | 2021-06-10 | 2022-01-21 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11998.16 | 11998.16 | 137758.01 | 0 | 0 | 149756.17 | 0 | 0 | 0 | 0 | 149756.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502091 | Larrchfield | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2020-08-31 | 2020-12-23 | 2021-01-19 |  |  | Dumfries and Galloway | 0 | 0 | 0 | 20306.83 | 14658.54 | 0 | 11078.55 | -9449.58 | 36594.34 | 9905.66 | 0 | 0 | 46500 | 0 | 0 | 0 | 0 | 46500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500248 | Latch Inlet Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-06-02 | 2027-06-08 | 2027-07-07 | 2028-01-10 |  | West Lothian | 0 | 0 | 1109 | 50133 | 4862 | -332 | -10073.59 | 0 | 45698.41 | 219334.59 | 0 | 0 | 265033 | 0 | 0 | 0 | 0 | 265033 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503107 | Laurencekirk SR - Growth & CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-10-29 | 2023-06-01 | 2023-09-28 | 2024-12-20 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 26657.92 | 8432.66 | 35090.58 | 3964909.42 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 563788.61 | [5 empty] | N | CM_WSNI | 50% | WG5 | 50%
402428 | Laurencekirk WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-10-17 | 2013-07-24 | 2013-11-04 | 2014-08-07 | 2014-08-07 | Angus | 951313 | 0 | 98025.22 | 0 | 0 | 0 | 0 | 0 | 98025.22 | 0 | 0 | 0 | 1049338.22 | 0 | 0 | 0 | 0 | 1049338.22 | 0 | [5 empty] | N | SG1 | 100%
507440 | Law Hill Cottages Troon - Low Pressure Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-11-25 | 2021-01-21 | 2021-12-24 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1667 | 1667 | 3333.33 | 0 | 0 | 5000.33 | 0 | 0 | 0 | 0 | 5000.33 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403412 | LCMS/MS and GCMS/MS System | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2013-12-24 | 2013-12-24 | 2016-02-02 | 2016-04-04 | 2016-04-28 | Scottish Water Wide | 358873.93 | 0 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0.07 | 0 | 0 | 0 | 358874 | 0 | 0 | 0 | 0 | 358874 | 0 | [5 empty] | N | CS20 | 100%
503486 | Lead Pipe Removal Pilot | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-02-21 | 2019-04-30 | 2019-05-15 | 2024-04-02 | 2024-06-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2851.61 | 101442.99 | -47925.4 | 56369.2 | 552458 | 0 | 0 | 608827.2 | 0 | 152382.1937 | 0 | 152382.1937 | 761209.3937 | 19191.74 | [5 empty] | N | DW25TS | 100%
400562 | Lead Water East Other | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-09-07 | 2015-09-24 | All East Unitary Authorities | 79483.85 | 0 | -1122.37 | 0 | 0 | 0 | 0 | 0 | -1122.37 | 0 | 0 | 0 | 78361.48 | 0 | 0 | 0 | 0 | 78361.48 | 28761.13 | [5 empty] | N | DW1B | 100%
400564 | Lead Water North Other | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-09-07 | 2015-09-17 | All North Unitary Authorities | 200377 | 0 | -8680.28 | 0 | 0 | 0 | 0 | 0 | -8680.28 | 0 | 0 | 0 | 191696.72 | 0 | 0 | 0 | 0 | 191696.72 | 28761.13 | [5 empty] | N | DW1B | 100%
400569 | Lead Water West Other | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-09-07 | 2015-09-11 | All West Unitary Authorities | 15057.35 | 0 | -1228.24 | 0 | 0 | 0 | 0 | 0 | -1228.24 | 0 | 0 | 0 | 13829.11 | 0 | 0 | 0 | 0 | 13829.11 | 28761.13 | [5 empty] | N | DW1B | 100%
30439 | Leadhills STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2012-01-23 | 2013-05-14 | 2013-05-22 | 2013-05-22 | South Lanarkshire | 262701.69 | 0 | 366.87 | 0 | 0 | 0 | 0 | 0 | 366.87 | 0 | 0 | 0 | 263068.56 | 0 | 0 | 0 | 0 | 263068.56 | 57522.26 | [5 empty] | N | EC04A | 23.19% | EC10A | 76.81%
500148 | Leadhills W DOA (DOA002386) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-05-30 | 2016-07-29 | 2019-03-31 | 2019-06-30 | South Lanarkshire | 0 | 0 | 4037 | 12977 | 20750 | 41962.83 | -236.82 | 0 | 79490.01 | 0 | 0 | 0 | 79490.01 | 0 | 0 | 0 | 0 | 79490.01 | 24464.77 | [5 empty] | Y | EC01D | 100% | [40 empty] | 1 | [26 empty] | 0
510924 | Leakage and Structural Investigation on Water PBS for M Mains (Milngavie-Glasgow rd Milngavie) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85532.19 | 85532.19 | 764965.86 | 0 | 0 | 850498.05 | 0 | 0 | 0 | 0 | 850498.05 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402500 | Leakage Assets Representation in GIS and Ellipse | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-01-16 | 2012-12-07 | 2012-12-07 | 2015-08-07 |  | Scottish Water Wide | 337450 | 0 | -378.42 | 526.68 | 0 | 0 | 0 | 0 | 148.26 | 0 | 0 | 0 | 337598.26 | 0 | 0 | 0 | 0 | 337598.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400800 | Leakage East FLA Distribution Metering | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-01 | 2010-05-04 | 2016-10-20 |  | City of Edinburgh | 1760000 | 0 | 54388.64 | -36079.88 | 0 | 0 | 0 | 0 | 18308.76 | 0 | 0 | 0 | 1778308.76 | 0 | 0 | 0 | 0 | 1778308.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400759 | Leakage East FLA DMA Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | City of Edinburgh | 1405375.69 | 0 | 2955.12 | 0 | 0 | 0 | 0 | 0 | 2955.12 | 0 | 0 | 0 | 1408330.81 | 0 | 0 | 0 | 0 | 1408330.81 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400757 | Leakage East FLA Loggers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-12-14 |  | City of Edinburgh | 1310000 | 0 | 3898.13 | 0 | 0 | 0 | 0 | 0 | 3898.13 | 0 | 0 | 0 | 1313898.13 | 0 | 0 | 0 | 0 | 1313898.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402046 | Leakage Planning DI Telemetry Improvements Water Balance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-05-27 | 2014-10-20 | 2014-10-20 | 2015-09-18 |  | Scottish Water Wide | 26380 | 0 | -3221.85 | 0 | 0 | 0 | 0 | 0 | -3221.85 | 0 | 0 | 0 | 23158.15 | 0 | 0 | 0 | 0 | 23158.15 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502720 | Leakage SR15 Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2021-04-15 | 2020-12-01 | 2021-04-15 | 2020-08-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
400572 | Leakage Water Mains Replacement | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-10-19 |  | Scottish Water Wide | 1733264.37 | 0 | -204424 | 0 | 0 | 0 | 0 | 0 | -204424 | 0 | 0 | 0 | 1528840.37 | 0 | 0 | 0 | 0 | 1528840.37 | 28761.13 | [5 empty] | N | DW1B | 100%
400760 | Leakage West FLA Distribution Metering | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 1400000 | 0 | 68044.17 | 0 | 0 | 0 | 0 | 0 | 68044.17 | 0 | 0 | 0 | 1468044.17 | 0 | 0 | 0 | 0 | 1468044.17 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400758 | Leakage West FLA DMA Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 530000 | 0 | -16882.91 | 0 | 0 | 0 | 0 | 0 | -16882.91 | 0 | 0 | 0 | 513117.09 | 0 | 0 | 0 | 0 | 513117.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400756 | Leakage West FLA Loggers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 817000 | 0 | -78770.04 | 0 | 0 | 0 | 0 | 0 | -78770.04 | 0 | 0 | 0 | 738229.96 | 0 | 0 | 0 | 0 | 738229.96 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502792 | Lease line telecoms OFCOM deregulation | IR18 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS4 | 2018-01-31 | 2019-07-11 | 2019-07-11 | 2021-03-02 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 173511.81 | 418509.05 | 2684981.12 | 1996009.82 | 5273011.8 | 0 | 421840.9443 | 421840.9443 | 5273011.8 | 0 | 421840.9443 | 0.00398 | 421840.9483 | 5694852.7483 | 4288576.06 |  |  |  |  | -62698.9251 | N | CS28S | 50% | CS28W | 50%
503208 | LED Lighting Programme (FOP Funded) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS3 | 2018-07-26 | 2018-07-26 | 2018-11-01 | 2021-06-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 304417.39 | 124575.71 | 41583.9 | 470577 | 20777.47 | 0 | 0 | 491354.47 | 0 | 0 | 0 | 0 | 491354.47 | 209623.87 | [5 empty] | N | CM_WSNI | 50% | CM_WWNI | 50%
402864 | Ledard Road Battlefield Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2013-05-21 | 2013-09-10 | 2014-02-10 | 2014-02-10 | Glasgow City | 49175 | 0 | -188.54 | 0 | 0 | 0 | 0 | 0 | -188.54 | 0 | 0 | 0 | 48986.46 | 0 | 0 | 0 | 0 | 48986.46 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
501272 | Legacy Comms fails improvement programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-11-16 | 2015-11-16 | 2016-03-01 | 2016-12-15 |  | Scottish Water Wide | 0 | 0 | 135992.95 | 76990.95 | 0 | 0 | 0 | 0 | 212983.9 | 0 | 0 | 0 | 212983.9 | 0 | 0 | 0 | 0 | 212983.9 | 613322.63 | [5 empty] | N | CM_WWNI | 20% | CM_WSNI | 80%
500946 | Legacy Hydro refurbishments (3 sites) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-10-21 | 2016-11-18 | 2017-07-24 | 2020-02-12 |  | Scottish Water Wide | 0 | 0 | 7736.3 | 165355.7 | 315479.48 | 82069.52 | 83845.19 | 217.81 | 654704 | 296.28 | 0 | 0 | 655000.28 | 0 | 0 | 0 | 0 | 655000.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
38008 | Legacy Pumping Station Adoption - Phase 2 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWMD | RCC | MS7 | 2009-06-01 | 2009-06-16 | 2009-06-15 | 2013-11-19 | 2011-03-14 | Scottish Water Wide | 467667.65 | 0 | -305746.56 | 0 | 0 | 0 | 0 | 0 | -305746.56 | 0 | 0 | 0 | 161921.09 | 0 | 0 | 0 | 0 | 161921.09 | 1011948.65 | [5 empty] | N | SG2 | 100%
400743 | Legacy Pumping Station Adoption - Phase 3 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2007-03-08 | 2010-03-31 | 2010-04-06 | 2018-08-16 | 2015-09-24 | Scottish Water Wide | 5438129 | 0 | 663990.98 | 359368.9 | 303888.05 | 65684.47 | 39.9 | 34.02 | 1393006.32 | 0 | 0 | 0 | 6831135.32 | 0 | 0 | 0 | 0 | 6831135.32 | 0 | [5 empty] | N | SG5 | 100%
403162 | Legacy Road Defects | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-26 | 2013-12-19 | 2014-01-31 | 2015-03-04 |  | Scottish Water Wide | 700142 | 0 | 19858 | 0 | 107545.76 | 0 | 0 | 0 | 127403.76 | 0 | 0 | 0 | 827545.76 | 0 | 0 | 0 | 0 | 827545.76 | 730242.44 | [5 empty] | N | WSI | 0.3021% | WSNI | 0.3021% | WWNI | 0.3021% | WWI | 99.09%
503092 | Legbrannock DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2020-05-08 | 2022-02-28 | 2022-06-22 | 2023-02-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 15869.3 | 11599.43 | 17137.65 | 16079.62 | 60686 | 1023390.42 | 0 | 0 | 1084076.42 | 0 | 0 | 0 | 0 | 1084076.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507154 | Lerwick DOA Rising Mains Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS1 | 2020-07-03 | 2021-04-12 | 2021-08-11 | 2022-02-09 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36967 | 36967 | 56032.98 | 0 | 0 | 92999.98 | 0 | 0 | 0 | 0 | 92999.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500155 | Lesmahagow DOA (DOA000597) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater | SEPA | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-10-29 | 2015-12-14 | 2017-03-31 | 2017-05-31 | South Lanarkshire | 0 | 0 | 59345 | 52490.81 | -539.46 | 123.84 | 0 | 0 | 111420.19 | 0 | 0 | 0 | 111420.19 | 0 | 0 | 0 | 0 | 111420.19 | 558366.35 | [5 empty] | Y | CS15 | 27.34% | CS11 | 27.88% | CS16D | 44.78% | [35 empty] | 1 | [27 empty] | 0
502812 | Lesmahagow WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-08-11 | 2022-11-29 | 2023-03-22 | 2024-03-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 77870.1 | 19160.03 | 10271.36 | 25185.97 | 132487.45 | 25238.14 | 0 | 0 | 157725.59 | 0 | 0 | 0 | 0 | 157725.59 | 122419.09 | [5 empty] | N | SG1 | 100%
45554 | Letham STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2010-09-20 | 2011-03-14 | 2012-03-23 | 2012-03-26 | Fife | 528482.63 | 0 | 187.98 | 0 | 0 | 0 | 0 | 0 | 187.98 | 0 | 0 | 0 | 528670.61 | 0 | 0 | 0 | 0 | 528670.61 | 119362.42 | [5 empty] | N | CM_WWNI | 10.08% | WQ01 | 89.92%
502883 | LETHAM TERRACE SPS CSO OUTFALL | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2022-01-19 | 2023-07-18 | 2023-10-10 | 2024-08-27 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 14874.24 | 64312.58 | 79186.82 | 270813.18 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503329 | Letham WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-12-18 | 2019-12-18 | 2019-09-03 | 2019-09-03 | 2019-09-03 | Angus | 0 | 0 | 0 | 0 | 0 | 75284.35 | -47335.48 | 0 | 27948.87 | 0 | 0 | 0 | 27948.87 | 0 | 0 | 0 | 0 | 27948.87 | 122419.09 | [5 empty] | N | SG1 | 100%
501181 | LETHAM WWTW 1940 NO537489 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-02-17 | 2027-04-01 | 2027-07-19 | 2028-07-13 |  | Angus | 0 | 0 | 5311.04 | 107085.66 | 47777.96 | 4932.51 | 4017.97 | -22705.93 | 146419.21 | 898195.79 | 0 | 0 | 1044615 | 0 | 0 | 0 | 0 | 1044615 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401338 | Lettoch WSZ Low Pressure Enhancement WSZ000980 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-02-29 | 2012-08-27 | 2013-04-18 | 2013-04-18 | Highland | 123010 | 0 | -664.47 | 0 | 0 | 0 | 0 | 0 | -664.47 | 0 | 0 | 0 | 122345.53 | 0 | 0 | 0 | 0 | 122345.53 | 0 | [5 empty] | N | CS1A | 30% | CS1 | 70%
500154 | Leven Valley DOA (DOA002460) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS5 | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2021-01-28 | 2021-03-24 | Fife | 0 | 0 | 13243 | 108441.15 | 371383.85 | 395785 | 290598.93 | 259758.07 | 1439210 | 38054 | 38054 | 65901.712 | 1477264 | 27847.712 | 0 | 0 | 27847.712 | 1505111.712 | 331825.1 | [5 empty] | N | EC01G | 0.65% | EC01D | 2.43% | EC10E | 9.73% | CS16D | 87.19%
505878 | Levenmouth DOA - Remove blockage from sewer and rehabilitate as necessary | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-03-31 | 2020-06-22 | 2020-07-30 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 53.41 | 6513.15 | 6566.56 | 0 | 0 | 0 | 6566.56 | 0 | 0 | 0 | 0 | 6566.56 | 209381.79 | [5 empty] | N | WWI | 100%
501745 | LEVENMOUTH PFI - LEVENMOUTH WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2020-01-16 | 2020-12-22 | 2021-03-16 | 2021-09-24 |  | Fife | 0 | 0 | 0 | 5499.61 | 0 | 0 | 40695.39 | 119456.3 | 165651.3 | 296460.85 | 0 | 0 | 462112.15 | 0 | 0 | 0 | 0 | 462112.15 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505978 | Liberton TMs NDT investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-09-23 | 2021-04-12 | 2021-05-17 | 2021-10-29 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 42807.18 | 43107.18 | 510258.95 | 0 | 0 | 553366.13 | 0 | 0 | 0 | 0 | 553366.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503127 | Liberton Trunk Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2020-09-21 | 2020-09-21 | 2021-02-26 | 2021-02-26 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 278048.32 | 150745.61 | 25360.23 | -136013.33 | 318140.83 | 0 | 0 | 0 | 318140.83 | 0 | 0 | 0 | 0 | 318140.83 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502224 | Limekilns Main St SPS Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-03-29 | 2019-04-29 | 2019-06-17 | 2019-10-11 |  | Fife | 0 | 0 | 0 | 4983.09 | 9369.91 | 65944 | 347563 | -3860 | 424000 | 0 | 0 | 0 | 424000 | 0 | 0 | 0 | 0 | 424000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402492 | LIMS Enhancements - Tranche 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-12-19 | 2013-04-22 | 2013-04-22 | 2015-05-13 |  | Scottish Water Wide | 2341014 | 0 | 853.12 | 0 | 0 | 0 | 0 | 0 | 853.12 | 0 | 0 | 0 | 2341867.12 | 0 | 0 | 0 | 0 | 2341867.12 | 306661.32 | [5 empty] | N | CM_M&G | 100%
501818 | LIMS Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-08-21 | 2018-03-27 | 2018-03-27 | 2021-07-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 332879.82 | 558676.08 | 171151.26 | 205194.84 | 1267902 | 0 | 0 | 0 | 1267902 | 0 | 0 | 101432.16 | 101432.16 | 1369334.16 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500156 | Lincluden DOA (DOA000122) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-22 | 2017-11-28 | 2018-03-29 | Dumfries and Galloway | 0 | 0 | 27658 | 67082.92 | 19917.08 | -1518.12 | 0 | 0 | 113139.88 | 0 | 0 | 0 | 113139.88 | 0 | 0 | 0 | 0 | 113139.88 | 57309.56 | [5 empty] | N | CS16D | 5.303% | EC01D | 94.7%
507264 | Link of 4in CI mains on Mireton Street Glasgow | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-06-25 | 2020-07-15 | 2020-09-03 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15343.7 | 15343.7 | 0 | 0 | 0 | 15343.7 | 0 | 0 | 0 | 0 | 15343.7 | 311236.79 | [5 empty] | N | WSI | 100%
500159 | Linlithgow DOA (DOA000533) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS7 | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2019-01-28 | 2019-06-11 | West Lothian | 0 | 0 | 21427 | 174286 | 88043 | 67069 | 28805.2 | -17660.99 | 361969.21 | 0 | 0 | 0 | 361969.21 | 0 | 0 | 0 | 0 | 361969.21 | 350862.86 | [5 empty] | N | EC01D | 26.88% | CS16D | 73.12%
30446 | Linlithgow STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-23 | 2010-09-20 | 2011-03-28 | 2016-02-04 | 2016-02-04 | West Lothian | 2701382.5 | 0 | 30316.5 | -50865.97 | 0 | 0 | 0 | 0 | -20549.47 | 0 | 0 | 0 | 2680833.03 | 0 | 0 | 0 | 0 | 2680833.03 | 148123.55 | [5 empty] | N | EC01A | 15% | CM_WWNI | 30% | EC04A | 55%
511963 | Linthaugh Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-06-21 | 2022-12-28 | 2023-03-28 | 2024-03-04 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586084.2 | 0 | 0 | 586084.2 | 0 | 0 | 0 | 0 | 586084.2 | 209381.79 | [5 empty] | N | WWI | 100%
403066 | Lintrathen - Kirkmichael Water Pumping scheme | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-20 | 2014-04-22 | 2014-04-22 | 2014-04-22 |  | Perth and Kinross | 3308.04 | 0 | -46.5 | 0 | 0 | 0 | 0 | 0 | -46.5 | 0 | 0 | 0 | 3261.54 | 0 | 0 | 0 | 0 | 3261.54 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500479 | Lintrathen Network Hydro Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2015-05-18 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | Angus | 0 | 0 | 32623 | -6612.25 | 0 | 0 | 0 | 0 | 26010.75 | 0 | 0 | 0 | 26010.75 | 0 | 0 | 0 | 0 | 26010.75 | 1525750.06 | [5 empty] | N | I2S_WI | 100%
503263 | Lintrathen Raw Water Tunnel Refurbishment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2027-05-05 | 2028-02-24 | 2028-05-04 | 2028-12-01 |  | Angus | 0 | 0 | 0 | 0 | 0 | 17859.81 | 925.3 | -925.3 | 17859.81 | 581214.95 | 0 | 0 | 599074.76 | 0 | 0 | 0 | 0 | 599074.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501055 | Lintrathen WOA Alyth Loyal WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2016-05-31 | 2022-07-25 | 2022-09-16 | 2023-10-10 |  | Perth and Kinross | 0 | 0 | 6823.26 | 37854.91 | 93871.83 | 57517.17 | 0 | -5806.57 | 190260.6 | 0.01 | 0 | 0 | 190260.61 | 0 | 0 | 0 | 0 | 190260.61 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501056 | Lintrathen WOA Baggerton WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501057 | Lintrathen WOA Balkiellie New WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501054 | Lintrathen WOA Balmashanner WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501051 | Lintrathen WOA Blairgowrie Burnhead WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501052 | Lintrathen WOA Cairnhall Pump Station WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501053 | Lintrathen WOA Coupar Angus WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501050 | Lintrathen WOA Kingoldrum WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
500020 | Lintrathen WOA Maisondieu WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-10 | 2015-11-27 | 2015-11-30 | 2016-04-01 |  | Perth and Kinross | 4636 | 0 | 96788.19 | 14215.15 | 8043.41 | 7093.44 | -8292.53 | 11088.26 | 128935.92 | 0 | 0 | 0 | 133571.92 | 0 | 0 | 0 | 0 | 133571.92 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500021 | Lintrathen WOA Meikle Tullo WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-09 | 2016-01-29 | 2016-03-02 | 2017-03-23 |  | Aberdeenshire | 1455 | 0 | 178066 | 304091.41 | 41387.59 | 3833.46 | 4884.01 | 0 | 532262.47 | 0 | 0 | 0 | 533717.47 | 0 | 0 | 0 | 0 | 533717.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501044 | Lintrathen WOA Rattray WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501045 | Lintrathen WOA Stanley WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501046 | Lintrathen WOA West Ballochy WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501043 | Lintrathen WOA Wuddylaw WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501216 | Lintrathen WTW - QUALITY (Disinfection) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS3 | 2018-11-23 | 2020-09-29 | 2020-12-14 | 2021-11-18 | 2022-02-18 | Angus | 0 | 0 | 5023.26 | 1774.08 | 3840.39 | 8019.19 | 39593.95 | 126776.93 | 185027.79 | 305141.49 | 305141.49 | 380961.2105 | 490169.28 | 75819.7205 | 0 | 0 | 75819.7205 | 565989.0005 | 449492.43 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
501227 | Lintrathen WTW - QUALITY (Reduction of risks identified in Drinking Water Safety Plan - Transmission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS5 | 2015-11-18 | 2016-01-07 | 2016-04-01 | 2021-03-31 | 2021-03-31 | Angus | 0 | 0 | 0 | 71 | 1905.95 | 4565.25 | 1513.5 | 4081.09 | 12136.78 | 431.4 | 431.4 | 1552.7525 | 12568.18 | 1121.3525 | 0 | -0.0025 | 1121.35 | 13689.53 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
45619 | Lintrathen WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-04-01 | 2012-12-06 | 2013-01-18 | Angus | 470857.25 | 0 | -288 | 0 | 0 | 0 | 0 | 0 | -288 | 0 | 0 | 0 | 470569.25 | 0 | 0 | 0 | 0 | 470569.25 | 28761.13 | [5 empty] | N | DW1A | 100%
503424 | Linwood WwPS - Emergency Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2018-12-20 | 2019-06-28 | 2019-07-01 | 2021-02-22 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 280465 | 1410530.83 | 209178.33 | 1900174.16 | 293237.27 | 0 | 0 | 2193411.43 | 0 | 0 | -0.43 | -0.43 | 2193411 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505573 | Linwood WWPS Burst 900 DIA Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-03-11 |  | 2020-05-14 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 39115 | 259225.36 | 298340.36 | 0 | 0 | 0 | 298340.36 | 0 | 0 | 0 | 0 | 298340.36 | 209381.79 | [5 empty] | N | WWI | 100%
509632 | Little Denny DSR TWS Asset Repair Mission | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-11-24 | 2024-01-11 | 2024-04-22 | 2025-03-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000.11 | 0 | 0 | 300000.11 | 0 | 0 | 0 | 0 | 300000.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503383 | Livingston WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-05-13 | 2028-03-21 | 2028-07-24 | 2029-01-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 83748.31 | 2943.83 | -0.14 | 86692 | 0 | 0 | 0 | 86692 | 0 | 0 | 0 | 0 | 86692 | 122419.09 | [5 empty] | N | SG1 | 100%
402885 | Loch Arklet - Remedial works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-11-12 | 2014-06-20 | 2014-06-30 | 2015-08-05 |  | Stirling | 4921681.17 | 0 | 635551.3 | 18088.46 | 18407.5 | -44348.8 | 0 | 0 | 627698.46 | 0 | 0 | 0 | 5549379.63 | 0 | 0 | 0 | 0 | 5549379.63 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508144 | Loch Arklet and Loch Katrine Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-19 | 2021-10-01 | 2022-05-16 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13630.25 | 13630.25 | 186915.97 | 0 | 0 | 200546.22 | 0 | 0 | 0 | 0 | 200546.22 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508169 | Loch Arklet Inclinometer Readings | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-08-19 | 2020-11-10 | 2021-12-15 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3856 | 3856 | 644.24 | 0 | 0 | 4500.24 | 0 | 0 | 0 | 0 | 4500.24 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507199 | Loch Arklet Spillway Pier Crack Repair | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-06-29 | 2020-10-12 | 2021-07-16 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35604 | 35604 | 4395.75 | 0 | 0 | 39999.75 | 0 | 0 | 0 | 0 | 39999.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401352 | Loch Ascog Remedial Work To Low Level Outlet Pipe | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-26 | 2013-05-20 | 2013-06-28 | 2014-12-01 | 2014-05-26 | Argyll and Bute-North Argyll | 844436.38 | 0 | 1424 | 33.75 | 0 | 0 | 0 | 0 | 1457.75 | 0 | 0 | 0 | 845894.13 | 0 | 0 | 0 | 0 | 845894.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501572 | Loch Ascog WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS5 | 2018-03-15 | 2019-03-08 | 2019-03-25 | 2020-08-31 | 2021-03-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 2930.23 | 2694.42 | 4567.63 | 141103.23 | 867221.49 | 45165 | 1063682 | 9862.92 | 9862.92 | 13691.4121 | 1073544.92 | 3828.4921 | 0 | 0 | 3828.4921 | 1077373.4121 | 146343.21 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
403276 | Loch Ascog WTW - SR06 defects remedials | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-31 | 2014-10-01 | 2014-10-01 | 2014-10-01 |  | Argyll and Bute-Cowal & Bute | 67921.36 | 0 | 614.97 | 0 | 0 | 0 | 0 | 0 | 614.97 | 0 | 0 | 0 | 68536.33 | 0 | 0 | 0 | 0 | 68536.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507429 | Loch Ashie intake screen lifting investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-06 | 2021-08-16 | 2022-03-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4648 | 4648 | 15351.66 | 0 | 0 | 19999.66 | 0 | 0 | 0 | 0 | 19999.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402059 | Loch Calder Hoy sludge building Asbestos Electrical and Building HS Issues | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-04-06 | 2014-04-30 | 2014-06-30 | 2015-03-09 |  | Highland | 538209 | 0 | 7936.47 | 82.19 | 0 | 0 | 0 | 0 | 8018.66 | 0 | 0 | 0 | 546227.66 | 0 | 0 | 0 | 0 | 546227.66 | 119022.58 |  |  |  |  | 20056 | N | CM_M&G | 100%
507568 | Loch Calder WOA - Burn of Houstry River Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2021-02-10 | 2023-01-19 | 2023-06-29 | 2025-01-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29933 | 29933 | 90067.75 | 0 | 0 | 120000.75 | 0 | 0 | 0 | 0 | 120000.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501061 | Loch Calder WOA Apigill (Loch Leacach) WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-04 | 2028-03-08 | 2028-06-16 | 2029-02-02 |  | Highland | 0 | 0 | 15488.37 | 22693.63 | 250 | 4487.22 | 1584.41 | -385.72 | 44117.91 | 684765.6 | 0 | 0 | 728883.51 | 0 | 0 | 0 | 0 | 728883.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501062 | Loch Calder WOA Bettyhill (Swordly) WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  | Highland | 0 | 0 | 669.77 | -669.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
500019 | Loch Calder WOA Heathfield WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2027-05-06 | 2028-06-01 | 2029-02-28 |  | Highland | 1377 | 0 | 46260 | 3557 | 16501 | 20429.47 | -2530.52 | 0 | 84216.95 | 1580986.05 | 0 | 0 | 1666580 | 0 | 0 | 0 | 0 | 1666580 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501060 | Loch Calder WOA Melvich/Strathy WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
500756 | Loch Calder WOA Oust WZS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-08-10 | 2027-05-05 | 2027-06-24 | 2027-12-01 |  | Highland | 0 | 0 | 12336 | 4650 | 3359.56 | 832.44 | 7392.52 | -8161.12 | 20409.4 | 515213.6 | 0 | 0 | 535623 | 0 | 0 | 0 | 0 | 535623 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501260 | Loch Calder WOA Skaill SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-11-09 | 2020-03-30 | 2020-03-30 | 2020-04-30 |  | Highland | 0 | 0 | 19624 | 77616.49 | -0.49 | -5743.46 | -3994.77 | -2246.52 | 85255.25 | 0 | 0 | 0 | 85255.25 | 0 | 0 | 0 | 0 | 85255.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501261 | Loch Calder WOA Thusater & Ramscraig SRs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-11-09 | 2020-03-30 | 2020-03-30 | 2020-04-30 |  | Highland | 0 | 0 | 20908 | 120422.68 | 6352.32 | -6152.14 | 7252.03 | -16865.67 | 131917.22 | 0 | 0 | 0 | 131917.22 | 0 | 0 | 0 | 0 | 131917.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500785 | Loch Calder WOA Wick Airport Iron Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-07-30 | 2016-12-15 | 2019-08-26 | 2019-08-26 |  | Highland | 0 | 0 | 29700 | 11971 | 15859 | 1267.37 | -24741.74 | 0 | 34055.63 | 0 | 0 | 0 | 34055.63 | 0 | 0 | 0 | 0 | 34055.63 | 311236.79 | [5 empty] | N | CM_WSI | 100%
512081 | Loch Calder WTW - Hoy PS Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000.04 | 0 | 0 | 500000.04 | 0 | 0 | 0 | 0 | 500000.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506910 | Loch Calder WTW - PLC Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-10-04 | 2023-08-07 | 2023-11-09 | 2025-05-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24954.25 | 24954.25 | 2775101.43 | 0 | 0 | 2800055.68 | 0 | 0 | 0 | 0 | 2800055.68 | 119022.58 | [5 empty] | N | WSNI | 100%
505819 | Loch Calder WTW - Run to Waste | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-08-23 | 2023-03-27 | 2023-06-19 | 2024-06-03 | 2025-06-03 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20706.18 | 20706.18 | 479293.82 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WA | 100%
504995 | Loch Calder WTW - Treated Water Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-05-05 | 2022-01-17 | 2022-07-18 | 2024-01-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 21976.74 | 13218.44 | 35195.18 | 1273384.19 | 0 | 0 | 1308579.37 | 0 | 0 | 0 | 0 | 1308579.37 | 119022.58 | [5 empty] | N | WSNI | 100%
500742 | Loch Calder WTW Disinfection Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-08-25 | 2018-11-29 | 2018-12-10 | 2021-04-30 |  | Highland | 0 | 0 | 33184 | 90616.72 | 165287.6 | 683823.37 | 458358.9 | 340254.41 | 1771525 | 0 | 0 | 0 | 1771525 | 0 | 0 | 140581 | 140581 | 1912106 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500754 | Loch Calder WTW Power Quality Filters and Power Correction Filters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS7 | 2015-08-24 | 2016-09-08 | 2016-11-22 | 2017-07-31 |  | Highland | 0 | 0 | 29132 | 242773.04 | 12877.36 | 13192.1 | 3371.35 | -19205.66 | 282140.19 | 0 | 0 | 0 | 282140.19 | 0 | 0 | 0 | 0 | 282140.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502588 | Loch Calder WTW Relocation of Sludge Blowers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-04-27 | 2020-04-27 | 2019-06-28 | 2019-06-28 |  | Highland | 0 | 0 | 0 | 12682.18 | 35274.87 | 574.41 | 17115.35 | 0 | 65646.81 | 0 | 0 | 0 | 65646.81 | 0 | 0 | 0 | 0 | 65646.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500894 | Loch Coulter Additional Scour Capacity | IR18 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water | DWQR | SWMD | Reservoirs | MS7 | 2016-08-30 | 2017-03-27 | 2017-06-12 | 2017-09-30 | 2020-07-31 | Stirling | 0 | 0 | 12882.16 | 11217.33 | 129321.2 | 9.11 | 18.47 | 0 | 153448.27 | 0 | 0 | 0 | 153448.27 | 0 | 0 | 0 | 0 | 153448.27 | 165739.68 | [5 empty] | Y | WR6 | 100% | [30 empty] | 1 | [36 empty] | 0
402174 | Loch Coulter Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-11 | 2012-08-29 | 2012-11-16 | 2014-10-28 | 2014-10-28 | Scottish Water Wide | 354500.37 | 0 | -4497.15 | -483.48 | 0 | 0 | 0 | 0 | -4980.63 | 0 | 0 | 0 | 349519.74 | 0 | 0 | 0 | 0 | 349519.74 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506785 | Loch Craig Culvert and VT Roof works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-05-26 |  | 2021-08-18 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1194.68 | 1194.68 | 188805.32 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 190000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403795 | Loch Drunkie IoS Measures | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-05-19 | 2016-03-18 | 2016-03-28 | 2016-04-08 |  | Stirling | 26116.12 | 0 | 44802.16 | 0 | 0 | 0 | 0 | 0 | 44802.16 | 0 | 0 | 0 | 70918.28 | 0 | 0 | 0 | 0 | 70918.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503528 | Loch Drunkie Pipe Lining | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2019-06-12 | 2019-06-12 | 2019-07-15 | 2020-10-19 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 561648.05 | -12430.05 | 549218 | 2000.16 | 0 | 0 | 551218.16 | 0 | 0 | 0 | 0 | 551218.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508141 | Loch Drunkie Veg removal and pitching repair | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-19 | 2021-06-10 | 2022-01-21 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.31 | 981.31 | 13000 | 0 | 0 | 13981.31 | 0 | 0 | 0 | 0 | 13981.31 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501642 | Loch Eck | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS4 | 2017-03-29 | 2018-12-21 | 2019-08-23 | 2021-03-31 | 2021-06-02 | Argyll and Bute-Cowal & Bute | 0 | 0 | 2511.63 | 10076.66 | 14013.35 | 5020.97 | 389.76 | 0 | 32012.37 | 0 | 0 | 2560.9897 | 32012.37 | 2560.9897 | 0 | 0.001 | 2560.9907 | 34573.3607 | 133039.29 | [5 empty] | N | DW25P | 100%
507355 | Loch Eck - Closed Loop Cycle | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2020-10-09 | 2020-10-09 | 2025-06-23 | 2027-01-04 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1053.18 | 1053.18 | 2116571.91 | 0 | 0 | 2117625.09 | 0 | 0 | 0 | 0 | 2117625.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404082 | Loch Eck Caustic and Hypo Dosing Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-01-27 | 2019-01-28 | 2019-02-28 | 2021-05-17 |  | Argyll and Bute-Cowal & Bute | 6104 | 0 | 213592 | 272674.27 | 239157.51 | 980714.14 | 1352149.93 | 916271.55 | 3974559.4 | 128990.66 | 0 | 0 | 4109654.06 | 0 | 0 | 65345.94 | 65345.94 | 4175000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501305 | Loch Eck incident - filter refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-12-23 | 2015-12-23 | 2016-02-01 | 2016-06-13 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 814140.26 | 62332.93 | 124.77 | 0 | 0 | 0 | 876597.96 | 0 | 0 | 0 | 876597.96 | 0 | 0 | 0 | 0 | 876597.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501306 | Loch Eck incident - operational interventions | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-12-23 | 2015-12-23 | 2016-04-28 | 2019-07-29 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 257453.52 | 75521.46 | 0 | 5428.27 | 0 | 0 | 338403.25 | 0 | 0 | 0 | 338403.25 | 0 | 0 | 0 | 0 | 338403.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501307 | Loch Eck Incident - Temporary treatment | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | SWMD | Supply Resilience | MS7 | 2015-12-23 | 2015-12-23 | 2016-02-01 | 2016-03-31 | 2016-03-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 275834 | -22546.83 | 0 | 0 | 0 | 0 | 253287.17 | 0 | 0 | 0 | 253287.17 | 0 | 0 | 0 | 0 | 253287.17 | 757868.2 | [5 empty] | Y | CM_WSNI | 30% | CS16WR | 70% | [22 empty] | 1 | [42 empty] | 0
500039 | Loch Eck WOA Strachur New WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-04-09 | 2015-11-17 | 2015-11-17 | 2015-11-17 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 627.97 | 0 | 0 | 0 | 0 | 0 | 627.97 | 0 | 0 | 0 | 627.97 | 0 | 0 | 0 | 0 | 627.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46312 | Loch Eck WTW - Mn Removal | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-11-07 | 2010-08-16 | 2010-09-14 | 2013-01-14 | 2013-03-28 | Argyll and Bute-Cowal & Bute | 6902178.02 | 0 | 58596.47 | 26155.33 | 0 | 0 | 0 | 0 | 84751.8 | 0 | 0 | 0 | 6986929.82 | 0 | 0 | 0 | 0 | 6986929.82 | 0 | [5 empty] | N | DW3C | 100%
508157 | Loch Finlas Alexandria (Luss) Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-31 | 2021-05-06 | 2021-12-17 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30647.22 | 30647.22 | 199352.78 | 0 | 0 | 230000 | 0 | 0 | 0 | 0 | 230000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507115 | Loch Glow Pitching and Spillway Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-06-16 |  | 2021-07-15 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568.02 | 568.02 | 11501.64 | 0 | 0 | 12069.66 | 0 | 0 | 0 | 0 | 12069.66 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403679 | Loch Goin Reservoir - Draw Down | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-03 | 2015-06-22 | 2015-07-20 | 2015-11-10 |  | East Ayrshire | 39781 | 0 | 268451 | 39844.62 | -282.78 | 0 | 0 | 0 | 308012.84 | 0 | 0 | 0 | 347793.84 | 0 | 0 | 0 | 0 | 347793.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505337 | Loch Horn - Repairs to Access Track | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-02-24 |  | 2020-09-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 10166.67 | 19270.84 | 29437.51 | 0 | 0 | 0 | 29437.51 | 0 | 0 | 0 | 0 | 29437.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403717 | Loch Katrine Concrete Buttress | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-27 | 2015-01-29 | 2015-04-20 | 2016-03-11 |  | Argyll and Bute-North Argyll | 93778 | 0 | 774209 | 0 | 0 | -4605.68 | 0 | 0 | 769603.32 | 0 | 0 | 0 | 863381.32 | 0 | 0 | 0 | 0 | 863381.32 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503780 | Loch Katrine Landslips Incident | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS3 | 2019-11-01 | 2019-11-01 | 2020-02-06 | 2021-10-22 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 972207.84 | 2691591.27 | 3663799.11 | 379521.42 | 0 | 0 | 4043320.53 | 0 | 0 | 0 | 0 | 4043320.53 | 306661.32 | [5 empty] | N | CM_M&G | 100%
507502 | Loch Katrine New Aqueduct Section 9 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2022-02-04 | 2023-12-22 | 2024-05-31 | 2025-12-12 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20072000.02 | 0 | 0 | 20072000.02 | 0 | 0 | 0 | 0 | 20072000.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
1286 | Loch Katrine Water Supply Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2001-12-14 | 2004-04-28 | 2004-03-22 | 2007-10-12 | 2008-04-22 | East Dunbartonshire | 120381045.78 | 0 | 4873.68 | 266.25 | 0 | 0 | 0 | 0 | 5139.93 | 0 | 0 | 0 | 120386185.71 | 0 | 0 | 0 | 0 | 120386185.71 | 86283.39 | [5 empty] | N | DW1 | 33.33% | DW4 | 33.33% | DW3 | 33.34%
511469 | Loch Lee Proactive Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-05-24 | 2021-08-13 | 2022-03-28 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403164 | Loch Lee Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-07 | 2014-06-25 | 2014-06-25 | 2014-11-17 | 2014-11-17 | Angus | 766237.65 | 0 | 71820.14 | -892.53 | 0 | 0 | 0 | 0 | 70927.61 | 0 | 0 | 0 | 837165.26 | 0 | 0 | 0 | 0 | 837165.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500107 | Loch Lomond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-19 | 2019-08-28 | Scottish Water Wide | 0 | 0 | 8923 | 84596.82 | 252787.18 | 172653 | 10153.93 | 0 | 529113.93 | 0 | 0 | 0 | 529113.93 | 0 | 0 | 0 | 0 | 529113.93 | 0 | [5 empty] | N | CS16D | 25.46% | EC10H | 74.54%
404131 | Loch Maree | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2016-06-23 | 2016-10-10 | 2016-10-31 | 2018-03-01 | 2018-03-30 | Highland | 0 | 0 | 0 | 3283025.81 | 2547613.51 | 109665.25 | 9929.44 | -1557.61 | 5948676.4 | 0 | 0 | 0 | 5948676.4 | 0 | 0 | 0 | 0 | 5948676.4 | 0 |  |  |  |  | 43200 | N | DW23 | 50% | DW3A | 50%
45396 | Loch Maree Strategic Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-07-16 | 2009-11-02 | 2011-03-28 | 2016-07-07 | 2016-07-07 | Highland | 8254375.06 | 0 | 2493608.96 | 475527.38 | 184077.34 | 21.29 | 0 | 0 | 3153234.97 | 0 | 0 | 0 | 11407610.03 | 0 | 0 | 0 | 0 | 11407610.03 | 28761.13 |  |  |  |  | 40008 | N | WG1 | 50% | WG4 | 50%
505055 | Loch Nell Abstraction Meter Installation (2) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-02-17 | 2021-01-18 | 2021-04-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2679.85 | 69509.51 | 72189.36 | 0 | 0 | 0 | 72189.36 | 0 | 0 | 0 | 0 | 72189.36 | 119022.58 | [5 empty] | N | WSNI | 100%
508479 | Loch Righeachan Proactive Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-09-03 | 2021-03-22 | 2021-06-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10183 | 10183 | 22388.28 | 0 | 0 | 32571.28 | 0 | 0 | 0 | 0 | 32571.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45505 | Loch Ryan Shellfish Waters improvement Scheme Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater | DWQR | SWMD | Non OMG180 | MS6 | 2008-11-20 | 2010-06-14 | 2011-01-18 | 2015-03-31 | 2016-03-31 | Dumfries and Galloway | 47476169 | 0 | 669547.98 | 589133.02 | 152614 | 297435.41 | 122061.74 | 23551.44 | 1854343.59 | -10673.18 | -10653.5423 | -14788.9305 | 49319839.41 | -4135.3882 | 0 | 0 | -4135.3882 | 49315704.0218 | 368759.05 |  |  |  |  | 374726 | Y | CM_WSI | 0.184% | EC01A | 49.91% | EC03A | 49.91% | [20 empty] | 1 | [42 empty] | 0
503251 | Loch Tay Strategic Scheme | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-02-19 | 2020-02-19 | 2020-10-01 | 2020-10-21 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 32629.24 | 368.29 | 0 | 32997.53 | 0 | 0 | 0 | 32997.53 | 0 | 0 | 0 | 0 | 32997.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507801 | Loch Thom and Compensation Reservoir Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-07-30 | 2020-10-14 | 2021-11-03 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65139 | 65139 | 109000.01 | 0 | 0 | 174139.01 | 0 | 0 | 0 | 0 | 174139.01 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502329 | Loch Thom MIOS Drawdown & Freebaoard Enhancement | IR18 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water | DWQR | SWMD | Reservoirs | MS3 | 2018-07-31 | 2019-07-23 | 2019-09-12 | 2021-08-09 | 2021-11-09 | Inverclyde | 0 | 0 | 0 | 38455.43 | 5660.8 | 230589.15 | 2334209.19 | 4502748.44 | 7111663 | 1038000.13 | 1388337 | 1388337 | 8149663.13 | 0 | 350336.87 | 9.3132e-10 | 350336.87 | 8500000 | 880386.96 | [5 empty] | Y | WR6 | 100% | [30 empty] | 1 | [36 empty] | 0
507629 | Loch Turret Access Road Improvements | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | MS7 |  | 2020-08-20 | 2020-09-01 | 2021-02-23 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42849.18 | 42849.18 | 0 | 0 | 0 | 42849.18 | 0 | 0 | 0 | 0 | 42849.18 | 2601944.88 | [5 empty] | N | CS22 | 100%
501568 | Loch Turret Drawdown Enhancement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-05-20 | 2018-01-23 | 2018-02-08 | 2018-08-10 |  | Perth and Kinross | 0 | 0 | 10754.35 | 14061.07 | 102799 | 59719.46 | 0 | -1099.88 | 186234 | 0 | 0 | 0 | 186234 | 0 | 0 | 0 | 0 | 186234 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502558 | Loch Turret IOS Works - Actuators | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2018-01-26 | 2018-01-26 | 2018-03-07 | 2018-04-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 39626.17 | 319000.96 | 1840 | -0.13 | 360467 | 0 | 0 | 0 | 360467 | 0 | 0 | 0 | 0 | 360467 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500191 | Loch Venachar Improvements to Compensation Releases | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water | SEPA | SWD | WFD | MS5 | 2015-03-20 | 2018-09-26 | 2018-10-01 | 2019-03-31 | 2019-03-31 | Stirling | 0 | 0 | 2325 | 458 | 4286 | 141 | 10024.34 | -10545.12 | 6689.22 | 0 | 0 | 0 | 6689.22 | 0 | 0 | 0 | 0 | 6689.22 | 99661.84 | [5 empty] | Y | WR2A | 100% | [37 empty] | 1 | [29 empty] | 0
501634 | Lochaline WTW - WQ Upgrade - Early Delivery Elements | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS7 | 2016-03-31 | 2016-09-29 | 2016-09-30 | 2017-10-31 | 2019-03-31 | Highland | 0 | 0 | 20607 | 3751345.93 | 823117.05 | 538228.25 | 7469.42 | -139412.94 | 5001354.7 | 0 | 0 | 0 | 5001354.7 | 0 | 0 | 0 | 0 | 5001354.7 | 3710243.92 | [5 empty] | Y | DW23 | 100% | [18 empty] | 1 | [48 empty] | 0
46176 | Lochans STW Refurb - STW000471 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-29 | 2014-05-28 | 2014-08-01 | 2014-09-12 |  | Dumfries and Galloway | 610873.75 | 0 | 473.75 | 0 | 0 | 0 | 0 | 0 | 473.75 | 0 | 0 | 0 | 611347.5 | 0 | 0 | 0 | 0 | 611347.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503309 | Lochans WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-06-02 | 2020-06-02 | 2020-08-28 | 2020-08-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 30748.66 | 15744.61 | -13908.75 | 32584.52 | 0 | 0 | 0 | 32584.52 | 0 | 0 | 0 | 0 | 32584.52 | 122419.09 | [5 empty] | N | SG1 | 100%
46850 | Lochcarron WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-16 | 2011-07-12 | 2013-05-20 | 2013-09-30 | Highland | 3736788.25 | 0 | 6078.23 | 0 | 0 | 0 | 0 | 0 | 6078.23 | 0 | 0 | 0 | 3742866.48 | 0 | 0 | 0 | 0 | 3742866.48 | 28761.13 | [5 empty] | N | DW23 | 100%
511243 | Lochcarron WwTW - SHT Roof Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-04-01 | 2022-06-23 | 2023-02-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308.41 | 1308.41 | 133691.59 | 0 | 0 | 135000 | 0 | 0 | 0 | 0 | 135000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46869 | Lochenkit WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-05-07 | 2013-07-17 | 2013-07-17 | 2016-03-17 | 2016-05-27 | Dumfries and Galloway | 3757654 | 0 | 8135 | 21576 | 18827.62 | 21276.11 | 0 | 0 | 69814.73 | 0 | 0 | 0 | 3827468.73 | 0 | 0 | 0 | 0 | 3827468.73 | 115044.52 | [5 empty] | N | DW9A | 0.265% | DW3G | 33.23% | DW3A | 33.25% | DW3F | 33.25%
402838 | Lochgair WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-08-21 | 2016-05-30 | 2016-09-08 | 2017-02-24 | 2017-02-24 | Argyll and Bute-North Argyll | 48500 | 0 | 27048.37 | 382722.89 | 33529.82 | -14659.04 | 55.41 | 0 | 428697.45 | 0 | 0 | 0 | 477197.45 | 0 | 0 | 0 | 0 | 477197.45 | 0 | [5 empty] | N | SG1 | 100%
500813 | Lochgelly Spion Kop WSZ Low Pressure Enhancement | IR18 | Improving drinking water availability and resilience of service | Pressure |  |  | Water |  | SWMD | Pressure | MS7 | 2015-08-07 | 2017-08-18 | 2017-10-02 | 2017-11-07 | 2017-11-07 | Fife | 0 | 0 | 4525.56 | 22464.67 | 33779.77 | -2158.18 | 1446.17 | -1029.45 | 59028.54 | 0 | 0 | 0 | 59028.54 | 0 | 0 | 0 | 0 | 59028.54 | 364502.97 | [5 empty] | N | CS1B | 14.49% | CS1 | 85.51%
503099 | Lochgelly Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS6 | 2018-12-21 | 2019-08-06 | 2019-08-19 | 2020-03-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 20324.39 | 354898.17 | 44736.31 | 419958.87 | 1000.08 | 0 | 0 | 420958.95 | 0 | 0 | 0 | 0 | 420958.95 | 444766.03 | [5 empty] | N | WG5 | 100%
501662 | Lochgilphead- Remove Dual MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-09-20 | 2018-02-27 | 2018-03-21 | 2021-05-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 7020.53 | 191786.47 | 456186 | 28948 | 60653 | 744594 | 95002 | 0 | 0 | 839596 | 0 | 0 | 0 | 0 | 839596 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509206 | Lochgoilhead DOA - Sewer Protection at River Goil Crossing | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-10-26 | 2022-04-06 | 2022-11-17 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3140.19 | 3140.19 | -3140.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWI | 100%
501571 | Lochgoilhead WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS5 | 2016-03-29 | 2016-10-24 | 2017-02-03 | 2018-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 2511.63 | 17.09 | 454.02 | 833.51 | -309.14 | 0 | 3507.11 | 0 | 0 | 0 | 3507.11 | 0 | 0 | 0 | 0 | 3507.11 | 72374.96 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
501360 | Lochgoilhead WTW - 500766 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS7 | 2016-03-29 | 2016-10-24 | 2017-02-03 | 2018-01-30 | 2019-08-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 142 | 39477.05 | 139961.96 | 5028.46 | 342.07 | 0 | 184951.54 | 0 | 0 | 0 | 184951.54 | 0 | 0 | 0 | 0 | 184951.54 | 72374.96 | [5 empty] | N | DW25P | 100%
511968 | Lochgoilhead WTW - raw main section replacment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2021-04-01 | 2022-11-11 | 2023-02-09 | 2024-01-17 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2093.02 | 2093.02 | 97906.98 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 119022.58 | [5 empty] | N | WSNI | 100%
502574 | Lochgoilhead WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-09-02 | 2020-09-02 | 2020-12-01 | 2020-12-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 20930.23 | 0 | 5171.84 | 9954.82 | -2952.47 | 33104.41 | 0 | 0 | 0 | 33104.41 | 0 | 0 | 0 | 0 | 33104.41 | 122419.09 | [5 empty] | N | WG1 | 100%
503132 | Lochgoilhead WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS0 | 2021-03-30 | 2023-01-12 | 2023-04-24 | 2024-03-29 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 28088.63 | 6409.82 | 102801.56 | 137300 | 1232699.99 | 0 | 0 | 1369999.99 | 0 | 0 | 0 | 0 | 1369999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402184 | Lochgoin Outlet Pipe Lining | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-09-07 | 2013-03-04 | 2014-02-27 | 2014-02-27 | North Ayrshire | 395929.97 | 0 | 167.23 | 0 | 0 | 0 | 0 | 0 | 167.23 | 0 | 0 | 0 | 396097.2 | 0 | 0 | 0 | 0 | 396097.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502395 | Lochgreen Rd - Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2020-09-22 | 2020-10-14 | 2028-04-17 | 2021-01-25 |  | Falkirk | 0 | 0 | 0 | 7000 | 13292.48 | 5801.86 | 181.34 | -172.11 | 26103.58 | 0 | 0 | 0 | 26103.58 | 0 | 0 | 0 | 0 | 26103.58 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403046 | Lochieport AC Mains Replacement and Iron Specials Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-22 | 2013-01-14 | 2013-09-02 |  | Na H-Eileanan an Iar | 303015 | 0 | 11921.76 | 0 | 0 | 0 | 0 | 0 | 11921.76 | 0 | 0 | 0 | 314936.76 | 0 | 0 | 0 | 0 | 314936.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500832 | Lochinvar RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2015-10-28 | 2017-12-21 | 2018-02-13 | 2019-03-31 | 2020-02-29 | Dumfries and Galloway | 0 | 0 | 145996 | -4380.77 | 38810.28 | 155408.67 | 20331.07 | -16499.32 | 339665.93 | 0 | 0 | 0 | 339665.93 | 0 | 0 | 0 | 0 | 339665.93 | 599034.52 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 115.09 | [43 empty] | 0
509989 | Lochinvar WTW - Sludge Press Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-08 | 2021-07-12 | 2022-02-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18551 | 18551 | 224152.04 | 0 | 0 | 242703.04 | 0 | 0 | 0 | 0 | 242703.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506428 | Lochinvar WTW Service Water Feed Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-04 |  | 2020-07-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6931.48 | 6931.48 | 0 | 0 | 0 | 6931.48 | 0 | 0 | 0 | 0 | 6931.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502837 | Lochinver WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-26 | 2020-03-26 | 2020-05-07 | 2020-05-07 |  | Highland | 0 | 0 | 0 | 0 | 21346.13 | 1340.34 | -19665.74 | 0 | 3020.73 | 0 | 0 | 0 | 3020.73 | 0 | 0 | 0 | 0 | 3020.73 | 122419.09 | [5 empty] | N | WG1 | 100%
402627 | Lochmaben WwTW Electrical Distribution Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-04-16 | 2013-01-08 | 2013-06-03 | 2014-02-04 |  | Dumfries and Galloway | 329482 | 0 | 435.53 | 0 | 0 | 0 | 0 | 0 | 435.53 | 0 | 0 | 0 | 329917.53 | 0 | 0 | 0 | 0 | 329917.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403903 | Lochmaddy WTW - WQ - DW3 DW13 DW23 | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWMD | Non OMG180 | MS6 | 2011-03-29 | 2016-02-29 | 2017-07-21 | 2019-06-30 | 2019-08-31 | Na H-Eileanan an Iar | 124155 | 62077.5 | 789610 | 533484.34 | 6194438.82 | 4250210.23 | 463192.66 | 34569.95 | 12265506 | 21285.51 | 10664.0405 | 14803.5037 | 12410946.51 | 4139.4632 | 0 | 0 | 4139.4632 | 12415085.9732 | 5162361.58 |  |  |  |  | 133437 | Y | DW25 | 8.1% | DW13 | 14% | DW23 | 14% | DW3G | 14% | CM_WSNI | 49.9% | [12 empty] | 1 | [46 empty] | 0
46870 | Lochmaddy WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-05-28 | 2015-03-27 | 2014-11-28 | 2014-11-28 | 2014-11-28 | Na H-Eileanan an Iar | 877949.16 | 0 | 3032.46 | -1594.22 | 0 | 0 | 0 | 0 | 1438.24 | 0 | 0 | 0 | 879387.4 | 0 | 0 | 0 | 0 | 879387.4 | 28761.13 | [5 empty] | N | DW3G | 100%
508076 | Lochwinnoch Wwtw - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-06-01 | 2025-03-27 | 2025-06-27 | 2026-08-07 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66918 | 66918 | 1933082.42 | 0 | 0 | 2000000.42 | 0 | 0 | 0 | 0 | 2000000.42 | 0 | [5 empty] | N | SG1 | 100%
505641 | Lochwinnoch WwTW - Inlet Screw Pumps Refurbishment - 500k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2020-08-06 | 2021-06-21 | 2021-08-20 | 2022-02-18 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17028.26 | 17028.26 | 2103736.07 | 0 | 0 | 2120764.33 | 0 | 0 | 0 | 0 | 2120764.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509156 | Lock Eck WTW - Flow Monitoring and Rain Gauge Survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-11-12 | 2021-03-03 | 2021-10-11 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7273 | 7273 | 12727.52 | 0 | 0 | 20000.52 | 0 | 0 | 0 | 0 | 20000.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501248 | Lockenkit Trunk Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-12-07 | 2016-07-19 | 2016-08-22 | 2017-05-23 |  | Dumfries and Galloway | 0 | 0 | 7799 | 315643.03 | 74820.3 | 385 | 62 | -1386.6 | 397322.73 | 0 | 0 | 0 | 397322.73 | 0 | 0 | 0 | 0 | 397322.73 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500161 | Lockerbie DOA (DOA000076) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-05-30 | 2016-08-05 | 2019-06-01 | 2019-07-04 | Dumfries and Galloway | 0 | 0 | 11300 | 21721 | 19810.63 | 76500 | -7141.45 | 0 | 122190.18 | 0 | 0 | 0 | 122190.18 | 0 | 0 | 0 | 0 | 122190.18 | 76247.31 | [5 empty] | N | EC01G | 2.269% | CS16D | 22.99% | EC10E | 27.05% | EC01D | 47.7%
500496 | Lockerbie WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS4 | 2015-07-21 | 2018-10-30 | 2018-10-30 | 2021-03-26 |  | Dumfries and Galloway | 0 | 0 | 44415 | 307872.31 | 162492.04 | 858332.62 | 1213889.99 | 265876.1 | 2852878.06 | 67553.94 | 0 | 0 | 2920432 | 0 | 0 | 290618 | 290618 | 3211050 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503387 | Lockerbie WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-05-08 | 2025-02-27 | 2025-05-30 | 2026-07-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 76108.55 | 8095.04 | 31384.42 | 115588.01 | 1884411.99 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 122419.09 | [5 empty] | N | SG1 | 100%
503665 | Lockerbie WwTW CSOs Intervention Developments | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2022-06-06 | 2022-10-10 | 2022-12-12 | 2024-07-05 | 2024-08-28 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 14341.8 | 27158.2 | 41500 | 358499.95 | 0 | 0 | 399999.95 | 0 | 98883.551 | 0 | 98883.551 | 498883.501 | 354277.77 | [5 empty] | N | EC01F_ID | 50% | EC10B_ID | 50%
502127 | Logistics - Emergency Equipment | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2016-04-08 | 2016-04-08 | 2016-04-08 | 2017-03-30 |  | Scottish Water Wide | 0 | 0 | 0 | 1046258 | -15856 | 0 | 0 | 0 | 1030402 | 0 | 0 | 0 | 1030402 | 0 | 0 | 0 | 0 | 1030402 | 306661.32 | [5 empty] | N | CM_M&G | 100%
401016 | Logistics - Plant Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-21 | 2010-06-14 | 2010-06-21 | 2016-06-23 |  | Scottish Water Wide | 1153954.54 | 0 | -23570 | -11683.9 | 0 | 0 | 0 | 0 | -35253.9 | 0 | 0 | 0 | 1118700.64 | 0 | 0 | 0 | 0 | 1118700.64 | 613322.63 | [5 empty] | N | CM_M&G | 100%
402042 | Logistics - Vehicle Replacement LCV - Tranche 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-03-10 | 2011-03-31 | 2011-05-03 | 2016-06-23 |  | Scottish Water Wide | 8844315.74 | 0 | -53785.54 | 0 | 0 | 0 | 0 | 0 | -53785.54 | 0 | 0 | 0 | 8790530.2 | 0 | 0 | 0 | 0 | 8790530.2 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403467 | Logistics - Vehicle Replacement LCV - Tranche 3 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2013-04-30 | 2013-04-30 | 2013-05-07 | 2016-06-23 |  | Scottish Water Wide | 5935188 | 0 | -785393.05 | -23064.31 | 0 | 0 | 0 | 0 | -808457.36 | 0 | 0 | 0 | 5126730.64 | 0 | 0 | 0 | 0 | 5126730.64 | 306661.32 | [5 empty] | N | CM_M&G | 100%
401017 | Logistics - Vehicle Replacement LGV | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-21 | 2010-06-14 | 2010-06-21 | 2016-06-23 |  | Scottish Water Wide | 5615967.07 | 0 | 666546.32 | -26464.71 | 0 | 0 | 0 | 0 | 640081.61 | 0 | 0 | 0 | 6256048.68 | 0 | 0 | 0 | 0 | 6256048.68 | 613322.63 | [5 empty] | N | CM_M&G | 100%
401069 | Logistics - Vehicle Telematics | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-06-28 | 2015-03-17 | 2015-03-17 | 2016-06-23 |  | Scottish Water Wide | 96405 | 0 | -49689.01 | 373.95 | 0 | 0 | 0 | 0 | -49315.06 | 0 | 0 | 0 | 47089.94 | 0 | 0 | 0 | 0 | 47089.94 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501203 | Lomond Hills WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS4 | 2016-08-26 | 2018-08-01 | 2018-08-31 | 2021-03-12 |  | Fife | 0 | 0 | 5978.09 | 84186.42 | 292354.42 | 555670.51 | 1242617.69 | 696646.87 | 2877454 | 59034 | 0 | 0 | 2936488 | 0 | 0 | 293649 | 293649 | 3230137 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503105 | Lomond Hills WTW - Local water supply imrovements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2018-05-28 | 2018-05-29 | 2018-06-18 | 2018-06-18 |  | Fife | 0 | 0 | 0 | 0 | 0 | 339627.81 | 0 | 0 | 339627.81 | 0 | 0 | 0 | 339627.81 | 0 | 0 | 0 | 0 | 339627.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500972 | Lomond Hills WTW - Mn | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-11-03 | 2015-11-06 | 2015-12-14 | 2016-06-30 | 2016-09-30 | Fife | 0 | 0 | 32100.94 | 41913.47 | 63 | 321.9 | -12099.47 | 0 | 62299.84 | 0 | 0 | 0 | 62299.84 | 0 | 0 | 0 | 0 | 62299.84 | 790368.92 | [5 empty] | Y | DW3C | 100% | [18 empty] | 1 | [48 empty] | 0
500494 | Lomond Scheme Flowmeter Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-05-28 | 2018-03-30 | 2018-06-28 | 2021-12-15 |  | All West Unitary Authorities | 0 | 0 | 90181 | 102346.02 | 167120.91 | 922759.62 | 504940.45 | -226403 | 1560945 | 871642 | 0 | 0 | 2432587 | 0 | 0 | 0 | 0 | 2432587 | 476090.34 | [5 empty] | N | CM_WSNI | 100%
502324 | London Road Glasgow Sewer Rehabilitation - Lift and relay section of sewer and water main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-09-02 | 2016-09-14 | 2016-09-28 | 2017-05-05 |  | Glasgow City | 0 | 0 | 0 | 1392865.62 | -19722.01 | 680.42 | 4127.46 | 0 | 1377951.49 | 0 | 0 | 0 | 1377951.49 | 0 | 0 | 0 | 0 | 1377951.49 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403941 | London Road Legal Costs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2020-10-01 |  | Glasgow City | 11754.35 | 0 | 829.65 | 6199.85 | 22874.84 | 2226.9 | 0 | 0 | 32131.23 | 0 | 0 | 0 | 43885.58 | 0 | 0 | 0 | 0 | 43885.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403122 | London Road Sewer Repair (near to junction with Kerrydale Street) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-22 | 2013-02-20 | 2013-02-20 | 2014-03-14 |  | Glasgow City | 2031916.02 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 2032066.02 | 0 | 0 | 0 | 0 | 2032066.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503718 | London Road Water Mains replacement & investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2020-05-28 | 2020-07-14 | 2020-08-10 | 2020-12-04 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 51471.67 | 343831.61 | 395303.28 | 0 | 0 | 0 | 395303.28 | 0 | 0 | 0 | 0 | 395303.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502280 | Londornoch WTW Sludge Lagoon Upgrade | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater | SEPA | SWMD | Sludge | MS3 | 2017-08-18 | 2020-03-31 | 2020-12-18 | 2022-03-07 | 2022-05-24 | Highland | 0 | 0 | 0 | 23204.84 | 97916.77 | 112919.88 | 145721.09 | 930535.42 | 1310298 | 1950329.16 | 1950329.16 | 2451685.5245 | 3260627.16 | 501356.3645 | 0 | 0 | 501356.3645 | 3761983.5245 | 312056.86 |  |  |  |  | 44570.0004 | Y | LA01 | 100% | [41 empty] | 1 | [25 empty] | 0
502669 | Lone Worker | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-04-27 | 2017-04-27 | 2017-04-27 | 2019-05-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 145865.69 | 40634.55 | 9290.1 | 0 | 195790.34 | 0 | 0 | 0 | 195790.34 | 0 | 0 | 0 | 0 | 195790.34 | 306661.32 | [5 empty] | N | CM_M&G | 100%
404105 | Long Loch Outlet Pipe Refurbishment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-03-06 | 2015-05-19 | 2015-05-27 | 2015-05-28 |  | East Renfrewshire | 19.98 | 0 | 338622.1 | 0 | 0 | 0 | 0 | 0 | 338622.1 | 0 | 0 | 0 | 338642.08 | 0 | 0 | 0 | 0 | 338642.08 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402606 | Longforgan Station Rd SPS Access Improvements | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2012-11-20 | 2013-01-07 | 2015-04-01 |  | All East Unitary Authorities | 125354 | 0 | 2143.35 | 299.59 | 14.84 | 0 | 0 | 0 | 2457.78 | 0 | 0 | 0 | 127811.78 | 0 | 0 | 0 | 0 | 127811.78 | 209381.79 | [5 empty] | N | CM_M&G | 100%
501749 | Longforgan trunk sewer - Reline sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2020-06-29 | 2021-09-10 | 2021-11-29 | 2022-04-29 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 4798.67 | 18361.25 | 23159.92 | 227200.53 | 0 | 0 | 250360.45 | 0 | 0 | 0 | 0 | 250360.45 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500236 | Longside WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-07-27 | Aberdeenshire | 0 | 0 | 43391.93 | 0 | 0 | 0 | 0 | 0 | 43391.93 | 0 | 0 | 0 | 43391.93 | 0 | 0 | 0 | 0 | 43391.93 | 122419.09 | [5 empty] | N | SG1 | 100%
503443 | Loon Burn Pipe Bridge Penicuik | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2020-05-20 | 2020-05-20 | 2020-06-05 | 2020-06-05 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 12365.91 | 15801.99 | -5164.63 | 23003.27 | 0 | 0 | 0 | 23003.27 | 0 | 0 | 0 | 0 | 23003.27 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503173 | Lossie Wynd - Mains Refurbishment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-06-18 | 2028-04-20 | 2028-07-12 | 2029-02-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791139.82 | 0 | 0 | 1791139.82 | 0 | 0 | 0 | 0 | 1791139.82 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502205 | Lossie Wynd Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-09-22 | 2019-09-30 | 2019-09-25 | 2019-09-25 |  | Aberdeenshire | 0 | 0 | 0 | 16896.43 | 5114.75 | 6398.49 | 1302.38 | 0 | 29712.04 | 0 | 0 | 0 | 29712.04 | 0 | 0 | 0 | 0 | 29712.04 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507495 | Lossiemouth Coulardbank Storm 1 PS Network connectivity survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-07-29 | 2020-12-02 | 2021-03-11 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13471.37 | 13471.37 | 0 | 0 | 0 | 13471.37 | 0 | 0 | 0 | 0 | 13471.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505292 | Lossiemouth Coulardbank Storm No. 1 Pump No. 2 investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-02-21 |  | 2020-05-27 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 4351.33 | -4251.23 | 100.1 | 0 | 0 | 0 | 100.1 | 0 | 0 | 0 | 0 | 100.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503032 | Lossiemouth DSRs CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-11-11 | 2023-01-20 | 2023-05-25 | 2024-08-16 |  | Moray | 0 | 0 | 0 | 0 | 0 | 66861.77 | 18276.24 | 15769.29 | 100907.3 | 2149092.7 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 2250000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402802 | Lossiemouth WSZ Low Pressure Enhancement | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-23 | 2013-01-24 | 2013-02-11 | 2013-03-31 | 2013-03-31 | Moray | 333936.25 | 0 | 585.56 | 0 | 0 | 0 | 0 | 0 | 585.56 | 0 | 0 | 0 | 334521.81 | 0 | 0 | 0 | 0 | 334521.81 | 0 | [5 empty] | N | CS1 | 100%
403409 | Lothianburn PRV Hydro | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-03-01 | 2015-06-10 | 2015-06-10 | 2015-06-10 | 2015-06-10 | City of Edinburgh | 560826.99 | 0 | -380973.56 | 0 | 0 | 0 | 0 | 0 | -380973.56 | 0 | 0 | 0 | 179853.43 | 0 | 0 | 0 | 0 | 179853.43 | 0 | [5 empty] | N | CC1W | 100%
503734 | Low and High Askomil Mains Rehabilitation (2 No. DMAs) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 | 2019-09-30 | 2021-02-26 | 2021-05-10 | 2021-12-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 20022.38 | 98809.62 | 118832 | 610691.16 | 0 | 0 | 729523.16 | 0 | 0 | 0 | 0 | 729523.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502616 | Low Askomil Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2020-09-22 | 2020-09-22 | 2020-10-27 | 2020-10-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 5144 | 0 | -4.69 | 80 | 0 | 5219.31 | 0 | 0 | 0 | 5219.31 | 0 | 0 | 0 | 0 | 5219.31 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500480 | Lower Glendevon Reservoir Hydro Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2015-05-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | Fife | 0 | 0 | 40100.85 | 54.86 | 0 | 0 | 0 | 0 | 40155.71 | 0 | 0 | 0 | 40155.71 | 0 | 0 | 0 | 0 | 40155.71 | 1525750.06 | [5 empty] | N | I2S_WI | 100%
502190 | Lower Largo Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-08-29 | 2018-01-29 | 2018-03-26 | 2018-07-27 |  | Fife | 0 | 0 | 0 | 12095 | 222361 | 419062.93 | 1441.82 | -3085.76 | 651874.99 | 0 | 0 | 0 | 651874.99 | 0 | 0 | 0 | 0 | 651874.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501313 | Lower Largo WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-08-30 | Fife | 0 | 0 | 10465.12 | 3234.3 | 0 | 0 | 0 | 0 | 13699.42 | 0 | 0 | 0 | 13699.42 | 0 | 0 | 0 | 0 | 13699.42 | 122419.09 | [5 empty] | N | SG1 | 100%
506424 | LPNS Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS2 | 2020-10-07 | 2020-11-23 | 2021-04-06 | 2021-04-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464543 | 464543 | 0 | 0 | 0 | 464543 | 0 | 0 | 0 | 0 | 464543 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502800 | LRC3 Permament Chemical Dosing | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2017-07-27 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | Glasgow City | 0 | 0 | 0 | 0 | 447693.52 | -447248.4 | 0 | 0 | 445.12 | 0 | 0 | 0 | 445.12 | 0 | 0 | 0 | 0 | 445.12 | 15547843.63 | [5 empty] | N | EC01A | 100%
502963 | LTRAP MD Long Term Redundant Assets - East Area | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS0 | 2017-11-09 | 2021-06-21 | 2021-08-23 | 2022-09-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 4754.03 | 36211.75 | 13559.34 | 6763.6 | 61288.72 | 153869.75 | 0 | 0 | 215158.47 | 0 | 0 | 0 | 0 | 215158.47 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502964 | LTRAP MD Long Term Redundant Assets - North Area | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS3 | 2017-11-09 | 2019-12-09 | 2020-08-24 | 2022-05-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 8432.5 | 55304.82 | 6802.63 | 26283.05 | 96823 | 237415.51 | 0 | 0 | 334238.51 | 0 | 0 | 0 | 0 | 334238.51 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502965 | LTRAP MD Long Term Redundant Assets - South Area | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS0 | 2017-11-09 | 2021-12-20 | 2022-03-07 | 2022-06-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 17056.54 | 11932.59 | 2799.52 | 13442.35 | 45231 | 289044.86 | 0 | 0 | 334275.86 | 0 | 0 | 0 | 0 | 334275.86 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502966 | LTRAP MD Long Term Redundant Assets - West Area | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS3 | 2017-11-10 | 2020-01-21 | 2020-02-03 | 2022-01-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 16124.79 | 23852.91 | 23410.65 | 75419.65 | 138808 | 286316.98 | 0 | 0 | 425124.98 | 0 | 0 | 0 | 0 | 425124.98 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502897 | LTRAP SWD Long Term Redundant Assets | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-10-09 | 2017-10-09 | 2018-04-02 | 2021-06-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 17970 | 12530 | 24261.44 | 38334.56 | 93096 | 98674 | 0 | 0 | 191770 | 0 | 0 | 0 | 0 | 191770 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501593 | LUGAR WWPS NS585207 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS4 | 2016-07-19 | 2018-12-05 | 2019-02-11 | 2021-04-01 |  | East Ayrshire | 0 | 0 | 0 | 88307 | 125426 | 729553 | 727500 | 376866 | 2047652 | 43444 | 0 | 0 | 2091096 | 0 | 0 | 158904 | 158904 | 2250000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401331 | Lybster - Young Crescent - Sewer Flooding | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-24 | 2014-01-29 | 2014-04-25 | 2015-01-26 | 2015-01-26 | Highland | 463211 | 0 | 25154 | -1054.84 | 0 | 0 | 0 | 0 | 24099.16 | 0 | 0 | 0 | 487310.16 | 0 | 0 | 0 | 0 | 487310.16 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
500157 | Lybster DOA (DOA001064) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-09-27 | 2017-03-01 | 2017-04-24 | 2017-04-24 | Highland | 0 | 0 | 13260 | 743.08 | -4250.7 | 0 | 0 | 0 | 9752.38 | 0 | 0 | 0 | 9752.38 | 0 | 0 | 0 | 0 | 9752.38 | 72047.27 | [5 empty] | N | CS11 | 100%
45545 | Lyne of Skene STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-08-22 | 2011-11-28 | 2012-09-30 | 2013-01-24 | Aberdeenshire | 571660.02 | 0 | 1298.08 | 0 | 0 | 0 | 0 | 0 | 1298.08 | 0 | 0 | 0 | 572958.1 | 0 | 0 | 0 | 0 | 572958.1 | 28761.13 | [5 empty] | N | WQ01 | 100%
503719 | M1 and C1 WSZ Cluster Various DMAs Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-10-03 | 2020-03-02 | 2020-03-09 | 2021-11-17 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 141687.14 | 739294.21 | 880981.35 | 243245.08 | 0 | 0 | 1124226.43 | 0 | 0 | 0 | 0 | 1124226.43 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500221 | Maaruig - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-03-30 | 2016-06-23 | 2017-01-31 | 2018-02-28 | Highland | 0 | 0 | 193.5 | 2448.07 | 302.75 | 1272.85 | 0 | 0 | 4217.17 | 0 | 0 | 0 | 4217.17 | 0 | 0 | 0 | 0 | 4217.17 | 5495.73 | [5 empty] | Y | DW5FS | 100% | [19 empty] | 1 | [47 empty] | 0
45353 | Maaruig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-14 | 2011-10-03 | 2013-01-07 | 2013-01-31 | Na H-Eileanan an Iar | 945001.43 | 0 | 2556.53 | 0 | 0 | 0 | 0 | 0 | 2556.53 | 0 | 0 | 0 | 947557.96 | 0 | 0 | 0 | 0 | 947557.96 | 28761.13 | [5 empty] | N | DW23 | 100%
509112 | MacDuff Low DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-09-14 | 2023-11-01 | 2024-02-09 | 2025-01-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 837.21 | 837.21 | 483121.31 | 0 | 0 | 483958.52 | 0 | 0 | 0 | 0 | 483958.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501277 | Macritch Hill Windfarm | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS7 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2018-09-03 | 2018-09-03 | Angus | 0 | 0 | 14278.04 | -12614.89 | 2538.92 | 0 | 0 | 0 | 4202.07 | 0 | 0 | 0 | 4202.07 | 0 | 0 | 0 | 0 | 4202.07 | 0 | [5 empty] | N | I2S_WI | 100%
501225 | Mahon Court Bridgeburn Drive Moodiesburn Replace Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-02-22 | 2018-04-30 | 2018-06-11 | 2018-12-21 |  | North Lanarkshire | 0 | 0 | 5630.61 | 134369.39 | 169757 | 781213.97 | 11029.03 | -11788.64 | 1090211.36 | 0 | 0 | 0 | 1090211.36 | 0 | 0 | 0 | 0 | 1090211.36 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511465 | Main Road Maddiston Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-03-01 | 2023-09-07 | 2023-12-06 | 2024-11-12 | 2024-11-13 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16186.81 | 16186.81 | 324862.19 | 0 | 0 | 341049 | 0 | 0 | 0 | 0 | 341049 | 0 | [5 empty] | N | SR21_WW | 100%
503230 | Main Street Kirkconnel Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2020-02-21 | 2021-07-12 | 2021-08-30 | 2022-03-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 11847.83 | 29027.8 | 119997.37 | 160873 | 884544.06 | 0 | 0 | 1045417.06 | 0 | 0 | 0 | 0 | 1045417.06 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506085 | Mains Cleaning - Planned Preventative Maintenance Year 6 (2020 - 2021) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2020-12-22 | 2021-02-10 | 2021-02-12 | 2021-12-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714871.99 | 714871.99 | 876120.01 | 0 | 0 | 1590992 | 0 | 0 | 0 | 0 | 1590992 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46225 | Mains Investigations - Raw Water Mains Investigations | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-01 | 2012-06-30 | 2012-06-30 | 2014-03-05 |  | Scottish Water Wide | 523461.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523461.15 | 0 | 0 | 0 | 0 | 523461.15 | 0 | [6 empty] | CM_WSI | 100%
46226 | Mains Investigations - Trunk Mains Investigations Programme Build Up | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-01 | 2012-07-18 | 2012-07-23 | 2015-06-30 |  | Scottish Water Wide | 2052507 | 0 | 126185.54 | -112266.66 | 0 | 0 | 0 | 0 | 13918.88 | 0 | 0 | 0 | 2066425.88 | 0 | 0 | 0 | 0 | 2066425.88 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503735 | Mains of Moyness - Non DMA Mains Rehabilitation (Phase 1) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2019-09-30 | 2021-06-21 | 2021-08-16 | 2022-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 18103.65 | 37548.64 | 55652.29 | 680770.67 | 0 | 0 | 736422.96 | 0 | 0 | 0 | 0 | 736422.96 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46677 | Mains Rehab - WOA000011 Alnwickhill Schemes within 2 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-19 | 2012-03-26 | 2012-05-28 | 2013-09-13 |  | City of Edinburgh | 300370 | 0 | -509.56 | 0 | 0 | 0 | 0 | 0 | -509.56 | 0 | 0 | 0 | 299860.44 | 0 | 0 | 0 | 0 | 299860.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46076 | Mains Rehab - WOA000029 Back and Tolsta Schemes within WSZ000100 Back | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-06-10 | 2013-03-25 | 2013-04-25 | 2014-11-03 |  | Na H-Eileanan an Iar | 384000 | 0 | 0 | -492.87 | 0 | 0 | 0 | 0 | -492.87 | 0 | 0 | 0 | 383507.13 | 0 | 0 | 0 | 0 | 383507.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46141 | Mains Rehab - WOA000033 Badentinan 2 Schemes within 2 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-10-28 | 2011-11-21 | 2013-01-28 |  | Aberdeenshire | 455036 | 0 | -1144.49 | 0 | 0 | 0 | 0 | 0 | -1144.49 | 0 | 0 | 0 | 453891.51 | 0 | 0 | 0 | 0 | 453891.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46679 | Mains Rehab - WOA000054 Black Esk 14 Schemes within 12 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-12 | 2012-09-26 | 2012-11-19 | 2014-02-26 |  | Dumfries and Galloway | 2386023.73 | 0 | 1542.16 | 0 | 0 | 0 | 0 | 0 | 1542.16 | 0 | 0 | 0 | 2387565.89 | 0 | 0 | 0 | 0 | 2387565.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46655 | Mains Rehab - WOA000093 Clatto Schemes within 6 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-19 | 2012-10-26 | 2012-11-12 | 2013-07-11 |  | Angus | 355920 | 0 | 34.33 | 0 | 0 | 0 | 0 | 0 | 34.33 | 0 | 0 | 0 | 355954.33 | 0 | 0 | 0 | 0 | 355954.33 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46171 | Mains Rehab - WOA000137 Eela Water 7 Schemes within 6 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-08-08 | 2012-08-29 | 2012-09-24 | 2013-05-17 |  | Shetland Islands | 420000 | 0 | -11611.7 | 0 | 0 | 0 | 0 | 0 | -11611.7 | 0 | 0 | 0 | 408388.3 | 0 | 0 | 0 | 0 | 408388.3 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46136 | Mains Rehab - WOA000166 Glengap - Ringford 3 Schemes within 1 WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2012-09-21 | 2012-11-19 | 2013-07-15 |  | Dumfries and Galloway | 563338 | 0 | -921.46 | 0 | 0 | 0 | 0 | 0 | -921.46 | 0 | 0 | 0 | 562416.54 | 0 | 0 | 0 | 0 | 562416.54 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46072 | Mains Rehab - WOA000177 Glengap 3 Schemes within 2 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-06-10 | 2012-09-26 | 2013-02-25 | 2014-01-21 | 2014-02-03 | Dumfries and Galloway | 1013817 | 0 | 4420.37 | 0 | 0 | 0 | 0 | 0 | 4420.37 | 0 | 0 | 0 | 1018237.37 | 0 | 0 | 0 | 0 | 1018237.37 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46145 | Mains Rehab - WOA000179 Glenlatterach and Badentinan 6 Schemes within 3 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2013-06-19 | 2013-06-28 | 2017-09-28 |  | Moray | 1407177 | 0 | 0 | 128759.04 | 204063.96 | 5237 | 35158.65 | -31155.53 | 342063.12 | 0 | 0 | 0 | 1749240.12 | 0 | 0 | 0 | 0 | 1749240.12 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46071 | Mains Rehab - WOA000199 Invercannie and Mannofield 18 Schemes within 11 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-06-26 | 2010-11-15 | 2011-03-07 | 2020-10-30 |  | Aberdeen City | 874096 | 0 | -71791 | 5545 | 69038.02 | 198616.78 | 48274.76 | -55029.37 | 194654.19 | 0 | 0 | 0 | 1068750.19 | 0 | 0 | 0 | 0 | 1068750.19 | 622473.57 | [5 empty] | N | CM_WSI | 100%
46135 | Mains Rehab - WOA000200 Invercannie 2 Schemes within 2 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-10-28 | 2011-03-07 | 2013-04-25 |  | Aberdeenshire | 425106 | 0 | -1635.83 | 0 | 0 | 0 | 0 | 0 | -1635.83 | 0 | 0 | 0 | 423470.17 | 0 | 0 | 0 | 0 | 423470.17 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45657 | Mains Rehab - WOA000209 Kettleton 12 Schemes within 7 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2009-03-12 | 2012-09-26 | 2013-01-28 | 2019-03-12 |  | Dumfries and Galloway | 3230378 | 0 | 42743.65 | 1567.53 | 30689 | 7615.96 | 33829.97 | 6114.89 | 122561 | 2314.99 | 0 | 0 | 3355253.99 | 0 | 0 | 0 | 0 | 3355253.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46139 | Mains Rehab - WOA000213 Killiecrankie 4 Schemes within 3 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-10-25 | 2011-03-21 | 2012-11-20 |  | Perth and Kinross | 206000 | 0 | -3660.02 | 0 | 0 | 0 | 0 | 0 | -3660.02 | 0 | 0 | 0 | 202339.98 | 0 | 0 | 0 | 0 | 202339.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46689 | Mains Rehab - WOA000215 Killylours - Terregles 8 Schemes within 5 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-19 | 2012-09-26 | 2013-01-25 | 2014-07-07 | 2014-10-01 | Dumfries and Galloway | 662664 | 0 | -2926.11 | 71 | 0 | 0 | 0 | 0 | -2855.11 | 0 | 0 | 0 | 659808.89 | 0 | 0 | 0 | 0 | 659808.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46690 | Mains Rehab - WOA000215 Killylours - Terregles Scheme within DMA002096 Terregles Road | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-30 | 2013-03-06 | 2013-06-18 | 2014-05-23 | 2014-08-14 | Dumfries and Galloway | 453109 | 0 | -570.16 | 71 | 0 | 0 | 0 | 0 | -499.16 | 0 | 0 | 0 | 452609.84 | 0 | 0 | 0 | 0 | 452609.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46672 | Mains Rehab - WOA000224 Kirbister and Boardhouse 5 Schemes within 4 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-08-08 | 2012-10-17 | 2012-11-05 | 2015-08-24 |  | Orkney Islands | 1098985 | 0 | -12669 | 2474.6 | 12012.89 | 0 | 0 | 0 | 1818.49 | 0 | 0 | 0 | 1100803.49 | 0 | 0 | 0 | 0 | 1100803.49 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46070 | Mains Rehab - WOA000246 Lochinvar 7 Schemes within 3 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-06-26 | 2012-09-26 | 2012-11-19 | 2017-03-03 |  | Dumfries and Galloway | 4168789 | 0 | 10234 | 157961.7 | 24486.04 | 124757.63 | 27869.92 | 0 | 345309.29 | 0 | 0 | 0 | 4514098.29 | 0 | 0 | 0 | 0 | 4514098.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46169 | Mains Rehab - WOA000275 Ness 2 Schemes within 2 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2012-10-24 | 2012-10-30 | 2013-09-16 |  | Na H-Eileanan an Iar | 319626.61 | 0 | 65.62 | 0 | 0 | 0 | 0 | 0 | 65.62 | 0 | 0 | 0 | 319692.23 | 0 | 0 | 0 | 0 | 319692.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46146 | Mains Rehab - WOA000295 Perth (Gowans Terrace) 8 Schemes within 4 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-11-05 | 2011-03-21 | 2012-08-23 |  | Perth and Kinross | 947796 | 0 | -3555.72 | 0 | 0 | 0 | 0 | 0 | -3555.72 | 0 | 0 | 0 | 944240.28 | 0 | 0 | 0 | 0 | 944240.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46147 | Mains Rehab - WOA000318 Sandy Loch 5 Schemes within 3 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2012-02-29 | 2012-04-16 | 2013-02-28 |  | Shetland Islands | 382746 | 0 | -2634.13 | 0 | 0 | 0 | 0 | 0 | -2634.13 | 0 | 0 | 0 | 380111.87 | 0 | 0 | 0 | 0 | 380111.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46663 | Mains Rehab - WOA000374 Turret (Tayside) 4 Schemes within 4 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-27 | 2012-08-29 | 2012-09-24 | 2013-10-22 |  | Perth and Kinross | 1239159 | 0 | 2415.68 | 0 | 0 | 0 | 0 | 0 | 2415.68 | 0 | 0 | 0 | 1241574.68 | 0 | 0 | 0 | 0 | 1241574.68 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45654 | Mains Rehab - WOA000375 Turriff 9 Schemes within 6 WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-12 | 2012-08-29 | 2012-09-03 | 2013-06-24 |  | Aberdeenshire | 803271 | 0 | -1755.22 | 0 | 0 | 0 | 0 | 0 | -1755.22 | 0 | 0 | 0 | 801515.78 | 0 | 0 | 0 | 0 | 801515.78 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46702 | Mains Rehab - WSZ000318 Camps Happendon to Carluke SR (Trunk Main) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-30 | 2013-07-31 | 2013-09-16 | 2014-07-15 |  | South Lanarkshire | 2047099 | 0 | 4617 | 1560.21 | 0 | 0 | 0 | 0 | 6177.21 | 0 | 0 | 0 | 2053276.21 | 0 | 0 | 0 | 0 | 2053276.21 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502672 | Mains Rehab Farquhar Terrace South Queensferry | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2017-06-28 | 2017-06-28 | 2017-09-29 | 2018-08-24 |  | West Lothian | 0 | 0 | 0 | 0 | 361334.47 | 14574.08 | 243.88 | 373.57 | 376526 | 382.95 | 0 | 0 | 376908.95 | 0 | 0 | 0 | 0 | 376908.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503035 | Mains Rehab Hardhill Drive Bathgate | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2018-02-20 | 2018-07-11 | 2018-07-12 | 2018-10-01 |  | West Lothian | 0 | 0 | 0 | 0 | 2204.74 | 343195.65 | 1537.87 | 1986.74 | 348925 | 3475.92 | 0 | 0 | 352400.92 | 0 | 0 | 0 | 0 | 352400.92 | 119022.58 | [5 empty] | N | CM_M&G | 100%
500163 | Mallaig DOA (DOA000323) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-05-30 | 2016-08-19 | 2019-02-28 | 2019-06-30 | Highland | 0 | 0 | 11027 | 19421 | 42019 | 77480 | -228.73 | 0 | 149718.27 | 0 | 0 | 0 | 149718.27 | 0 | 0 | 0 | 0 | 149718.27 | 88744.54 | [5 empty] | Y | EC01G | 14.83% | EC01D | 85.17% | [38 empty] | 1 | [26 empty] | 0
504176 | Mallaig WOA - Intake Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-10-11 | 2024-01-15 | 2024-04-11 | 2025-10-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1270.38 | 1287.88 | 2558.26 | 1712281.61 | 0 | 0 | 1714839.87 | 0 | 0 | 0 | 0 | 1714839.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504998 | Mallaig WTW - Filtomats | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-09-13 | 2023-05-08 | 2023-08-01 | 2024-09-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2178.38 | 9286.55 | 11464.93 | 866235.95 | 0 | 0 | 877700.88 | 0 | 0 | 0 | 0 | 877700.88 | 119022.58 | [5 empty] | N | WSNI | 100%
511201 | Mallaig WTW - PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-06-01 | 2023-12-08 | 2024-03-07 | 2025-02-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000.04 | 0 | 0 | 500000.04 | 0 | 0 | 0 | 0 | 500000.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502674 | Mallaig WTW Prefiltration | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 |  | Highland | 0 | 0 | 0 | 0 | 61811.81 | 0 | 0 | 0 | 61811.81 | 0 | 0 | 0 | 61811.81 | 0 | 0 | 0 | 0 | 61811.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500075 | Mannofield Coagulant Change Trial and Monitoring | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-09 | 2015-03-20 | 2015-03-20 | 2016-02-26 | 2016-02-26 | Aberdeen City | 11002 | 11002 | 2561.5 | 0 | 0 | 0 | 0 | 0 | 2561.5 | 0 | 0 | 0 | 13563.5 | 0 | 0 | 0 | 0 | 13563.5 | 56021.66 | [5 empty] | N | DW3C_S | 100%
500209 | Mannofield East - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2017-12-22 | 2017-12-27 | 2018-03-23 | 2018-03-28 | Aberdeen City | 0 | 0 | 1490 | 1413 | 68175.68 | 0 | 0 | 0 | 71078.68 | 0 | 0 | 0 | 71078.68 | 0 | 0 | 0 | 0 | 71078.68 | 491407.97 | [5 empty] | N | DW5FS | 34% | DW5 | 66%
508053 | Mannofield East Reservoir MIOS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-09-02 | 2021-04-23 | 2021-02-25 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3271.03 | 3271.03 | 0 | 0 | 0 | 3271.03 | 0 | 0 | 0 | 0 | 3271.03 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500833 | Mannofield East RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-03-07 | 2017-12-21 | 2018-03-23 | 2019-12-31 | 2020-09-30 | Aberdeen City | 0 | 0 | 26277.48 | 28355.52 | 230298.72 | 212543.66 | 280522.96 | 24060.66 | 802059 | 2000 | 2000 | 2776.3405 | 804059 | 776.3405 | 0 | 0 | 776.3405 | 804835.3405 | 1119988.24 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 213.34 | [43 empty] | 0
500834 | Mannofield North RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-09-20 | 2018-09-18 | 2018-11-30 | 2019-09-30 | 2020-06-30 | Aberdeen City | 0 | 0 | 25559.07 | 15355.22 | 39111.93 | 105280.83 | 70204.38 | 6675.72 | 262187.15 | 833.33 | 833.33 | 1156.8039 | 263020.48 | 323.4739 | 0 | 0 | 323.4739 | 263343.9539 | 1187753.42 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 86.49 | [43 empty] | 0
500205 | Mannofield West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2018-03-30 | 2018-03-30 | 2018-10-31 | 2019-06-30 | Aberdeen City | 0 | 0 | 3854 | 2406 | 149054 | 77028.66 | -46740.9 | -2694.21 | 182907.55 | 0 | 0 | 0 | 182907.55 | 0 | 0 | 0 | 0 | 182907.55 | 1880301.15 | [5 empty] | Y | DW5FS | 100% | [19 empty] | 1 | [47 empty] | 0
508054 | Mannofield West Reservoir MIOS Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-09-02 | 2021-04-23 | 2021-12-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16343 | 16343 | 58657.33 | 0 | 0 | 75000.33 | 0 | 0 | 0 | 0 | 75000.33 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500835 | Mannofield West RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-03-07 | 2018-03-28 | 2018-06-19 | 2020-03-10 | 2020-09-29 | Aberdeen City | 0 | 0 | 24086.41 | 15578.59 | 267817.87 | 163863.62 | 277651.45 | 111034.06 | 860032 | 2000 | 2000 | 2776.3405 | 862032 | 776.3405 | 0 | 0 | 776.3405 | 862808.3405 | 1122593.17 | [5 empty] | N | DW5FS | 100%
502555 | Mannofield WTW - Commissioning of Sodium Hypochlorite Dosing Kiosk | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWMD | DWQ Compliance | MS6 | 2016-03-31 | 2017-12-12 | 2017-12-12 | 2018-09-30 | 2019-03-31 | Aberdeen City | 0 | 0 | 0 | 6740.69 | 69935.22 | 225792.53 | 225 | 801.56 | 303495 | 845.9 | 845.9 | 1174.2532 | 304340.9 | 328.3532 | 0 | 0 | 328.3532 | 304669.2532 | 401415.27 | [5 empty] | Y | DW25P | 100% | [18 empty] | 1 | [48 empty] | 0
502211 | Mannofield WTW - Hydrocarbon Monitor | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-06-21 | 2017-08-15 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | DW25P | 100%
502373 | Mannofield WTW - Inchgarth Reservoir Investigations | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS3 | 2019-03-06 | 2020-03-25 | 2020-11-03 | 2021-08-31 | 2021-11-29 | Aberdeen City | 0 | 0 | 0 | 51929.3 | 62957.19 | 6238.51 | 6009.5 | 52798.51 | 179933 | 85566.62 | 85566.62 | 118781.0359 | 265499.62 | 33214.4159 | 0 | 0 | 33214.4159 | 298714.0359 | 401415.27 | [5 empty] | N | DW25P | 100%
501297 | Mannofield WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2016-03-31 | 2021-09-27 | 2021-10-04 | 2023-09-08 | 2023-12-15 | Aberdeen City | 0 | 0 | 8707.77 | 2807.07 | 3217.71 | 5366.37 | 10658.77 | 2238.32 | 32996 | 19990.92 | 19990.92 | 27750.8003 | 52986.92 | 7759.8803 | 0 | 0 | 7759.8803 | 60746.8003 | 401415.27 | [5 empty] | N | DW25P | 100%
502653 | Mannofield WTW - RGF Controls Software Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-04-10 | 2017-08-24 | 2017-10-03 | 2018-03-16 |  | Aberdeen City | 0 | 0 | 0 | 0 | 320759.47 | 2956.94 | -248.29 | 0 | 323468.13 | 0 | 0 | 0 | 323468.13 | 0 | 0 | 0 | 0 | 323468.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502312 | Mannofield WTW -Improvements to Network Assets (SR Isolation Valves) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS0 | 2017-03-23 | 2022-10-21 | 2023-01-12 | 2024-01-09 | 2024-04-09 | Aberdeen City | 0 | 0 | 0 | 4850.33 | 5970.72 | 30182.8 | 130350.65 | 89860.5 | 261215 | 601569.23 | 601569.23 | 835080.5058 | 862784.23 | 233511.2758 | 0 | 0 | 233511.2758 | 1096295.5058 | 0 | [5 empty] | N | DW25T | 100%
502236 | Mannofield WTW -Improvements to SR s | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2016-05-30 | 2016-05-30 | 2016-09-05 | 2022-12-16 | 2023-03-03 | Aberdeen City | 0 | 0 | 0 | 35209.46 | 3323.55 | 438.78 | 9070.15 | 1144.06 | 49186 | 814.15 | 814.15 | 1130.1788 | 50000.15 | 316.0288 | 0 | 0 | 316.0288 | 50316.1788 | 401415.27 | [5 empty] | N | DW25P | 100%
502243 | Mannofield WTW -Improvements to Treatment Process | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water | DWQR | NONINF | Water Non infrastructure | MS0 | 2017-03-31 | 2021-12-20 | 2022-01-07 |  | 2022-12-22 | Aberdeen City | 0 | 0 | 0 | 115578.93 | 137340.58 | 14528.35 | 321711.45 | 77947.05 | 667106.36 | 2580842.93 | 0 | 0 | 3247949.29 | 0 | 0 | 0 | 0 | 3247949.29 | 119022.58 | [5 empty] | Y | CM_WSNI | 100% | [22 empty] | 1 | [44 empty] | 0
501250 | Mannofield WTW SCADA-PLC Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-23 | 2015-11-23 | 2015-12-01 | 2017-06-01 |  | Aberdeen City | 0 | 0 | 731045 | 762009.44 | 25517.02 | 2334.22 | -798.23 | 0 | 1520107.45 | 0 | 0 | 0 | 1520107.45 | 0 | 0 | 0 | 0 | 1520107.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500836 | Mannofield-Turiff-Invercannie RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-10-31 | 2018-11-21 | 2018-11-21 | 2018-11-30 | 2018-11-30 | Aberdeen City | 0 | 0 | 12297.55 | 9157.79 | 9640.3 | 2336.14 | 0 | 0 | 33431.78 | 0 | 0 | 0 | 33431.78 | 0 | 0 | 0 | 0 | 33431.78 | 469821.8 | [5 empty] | N | DW5FS | 100%
402964 | Manse Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2012-10-01 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 2021-04-01 | City of Edinburgh | 41239 | 41239 | 11000 | 49253.12 | 24707.88 | 29074 | 18719.43 | 0 | 132754.43 | 0 | 0 | 0 | 173993.43 | 0 | 0 | 0 | 0 | 173993.43 | 180449.74 | [5 empty] | N | FL_DD | 100%
30509 | Manse Street Galashiels Water WTW - Upgrade | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2005-12-01 | 2007-09-26 | 2008-01-25 | 2008-01-25 | 2008-06-12 | Scottish Borders | 185895.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185895.93 | 0 | 0 | 0 | 0 | 185895.93 | 0 | [6 empty] | DW13 | 33.33% | DW3B | 33.33% | DW4A | 33.33%
45643 | Manse Street Galashiels WTW Refurb - WTW000681 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2012-01-30 | 2012-02-07 | 2012-01-31 |  | Scottish Borders | 281569.05 | 0 | 639.79 | 0 | 0 | 0 | 0 | 0 | 639.79 | 0 | 0 | 0 | 282208.84 | 0 | 0 | 0 | 0 | 282208.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500837 | Manse Street RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-01-12 | 2017-03-23 | 2017-05-01 | 2018-10-31 | 2019-05-31 | Scottish Borders | 0 | 0 | 7616.67 | 33053.22 | 49167.6 | 59880.69 | -6975.2 | 0 | 142742.98 | 0 | 0 | 0 | 142742.98 | 0 | 0 | 0 | 0 | 142742.98 | 238122.94 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 37.76 | [43 empty] | 0
510567 | Manse Street WTW - Clarified Turbidity Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-22 | 2021-08-09 | 2021-12-13 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381 | 381 | 21119.17 | 0 | 0 | 21500.17 | 0 | 0 | 0 | 0 | 21500.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508161 | Mar Place Alloa - Sewer Blockage | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-09-22 | 2021-03-18 | 2022-04-08 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8435.89 | 8435.89 | 21609.01 | 0 | 0 | 30044.9 | 0 | 0 | 0 | 0 | 30044.9 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500206 | Marchbank B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS4 | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2019-12-23 | 2021-04-01 | City of Edinburgh | 0 | 0 | 50989 | 124821.68 | 313228.22 | 666744.54 | 69011.58 | -9334.02 | 1215461 | 3000 | 3000 | 101282.8471 | 1218461 | 98282.8471 | 0 | 0.0029 | 98282.85 | 1316743.85 | 3028853.1 | [5 empty] | N | DW5 | 100%
500838 | Marchbank B RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-08-03 | 2017-09-29 | 2017-10-02 | 2018-08-31 | 2019-03-31 | Midlothian | 0 | 0 | 1739.39 | 851.34 | 51301.9 | 108361.95 | -9625.08 | 0 | 152629.5 | 0 | 0 | 0 | 152629.5 | 0 | 0 | 0 | 0 | 152629.5 | 40226.72 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 6.28 | [43 empty] | 0
501080 | Marchbank WOA Marchbank Hermiston WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-28 | 2027-12-08 | 2028-01-31 | 2028-06-28 |  | West Lothian | 0 | 0 | 24192 | -7710 | 0 | 481 | 391.17 | -11.83 | 17342.34 | 0 | 0 | 0 | 17342.34 | 0 | 0 | 0 | 0 | 17342.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501079 | Marchbank WOA Marchbank Torduff WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2016-04-01 | 2024-07-17 | 2024-08-15 | 2025-03-21 |  | City of Edinburgh | 0 | 0 | 23832 | 57340 | 47222 | -27721.18 | 0 | -26181.14 | 74491.68 | 0.01 | 0 | 0 | 74491.69 | 0 | 0 | 0 | 0 | 74491.69 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402851 | Marchmont Crescent Edinburgh | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2012-11-27 | 2012-12-17 | 2013-03-28 | 2013-03-28 | City of Edinburgh | 89562.86 | 0 | 274.14 | 0 | 0 | 0 | 0 | 0 | 274.14 | 0 | 0 | 0 | 89837 | 0 | 0 | 0 | 0 | 89837 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
403527 | Marchmont Road Warrender Park Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2013-07-18 | 2019-07-31 | 2019-08-05 | 2019-08-15 | 2019-08-15 | City of Edinburgh | 318833 | 318833 | 39461 | 200122.78 | -76968.78 | 47293 | 8275 | -497.03 | 217685.97 | 0 | 0 | 0 | 536518.97 | 0 | 0 | 0 | 0 | 536518.97 | 180449.74 | [5 empty] | N | FL_DD | 100%
400814 | Marybank WWTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-05-07 | 2011-10-11 | 2013-10-23 | 2014-09-26 | 2014-09-26 | Highland | 468782 | 0 | 43218 | -3838.46 | 0 | 0 | 0 | 0 | 39379.54 | 0 | 0 | 0 | 508161.54 | 0 | 0 | 0 | 0 | 508161.54 | 0 | [5 empty] | N | SG1 | 100%
502828 | Marykirk WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-03-31 | 2024-03-22 | 2024-06-20 | 2025-07-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 62575.95 | 7446.41 | 53204.8 | 65159.85 | 188387 | 1888999.42 | 0 | 0 | 2077386.42 | 0 | 0 | 0 | 0 | 2077386.42 | 122419.09 | [5 empty] | N | SG1 | 100%
500158 | Mauchline DOA (DOA000137) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-04-29 | 2016-06-29 | 2018-02-28 | 2018-03-31 | East Ayrshire | 0 | 0 | 1669 | 15230 | 13078.58 | 0 | 0 | 0 | 29977.58 | 0 | 0 | 0 | 29977.58 | 0 | 0 | 0 | 0 | 29977.58 | 4617.88 | [5 empty] | Y | EC01G | 100% | [40 empty] | 1 | [26 empty] | 0
45539 | Mauchline STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-01 | 2012-09-18 | 2014-01-09 | 2015-03-23 | 2015-03-31 | East Ayrshire | 3452973.92 | 0 | 147377.27 | 2954.47 | -650.8 | 0 | 0 | 0 | 149680.94 | 0 | 0 | 0 | 3602654.86 | 0 | 0 | 0 | 0 | 3602654.86 | 119362.42 | [5 empty] | N | CM_WWNI | 40.02% | WQ01 | 59.98%
503545 | Mauchline WwTW Bathing Water Improvement | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater | SEPA | WWINF | Revised Bathing Waters Directive | MS3 | 2019-07-09 | 2020-06-29 | 2020-09-07 | 2021-07-01 | 2021-10-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 225763 | 1201885 | 1427648 | 372869 | 408552 | 408552 | 1800517 | 0 | 35683 | 0 | 35683 | 1836200 | 1035209.71 |  |  |  |  | 32700 | Y | EC16B | 100% | [38 empty] | 1 | [28 empty] | 0
30512 | Mauldslie (Carluke) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-20 | 2010-08-23 | 2010-09-27 | 2012-02-01 | 2012-03-05 | South Lanarkshire | 2322396.25 | 0 | 36488.35 | 0 | 0 | 0 | 0 | 0 | 36488.35 | 0 | 0 | 0 | 2358884.6 | 0 | 0 | 0 | 0 | 2358884.6 | 119362.42 | [5 empty] | N | EC01A | 40% | CM_WWNI | 60%
503418 | Mauldslie Access Road & Bridge Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2021-09-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 891082.96 | 557417.04 | 1448500 | 201500 | 0 | 0 | 1650000 | 0 | 0 | 50000 | 50000 | 1700000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502317 | Mauldslie WwTW - Secondary Treatment Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-07-31 | 2018-07-31 | 2018-07-31 | 2018-07-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 52325.58 | 0 | 0 | 0 | 52325.58 | 0 | 0 | 0 | 52325.58 | 0 | 0 | 0 | 0 | 52325.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508486 | Mauricewood Risk Management Plan | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2020-11-02 | 2021-04-12 | 2021-08-11 | 2022-02-09 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10189.03 | 10189.03 | 29810.97 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506741 | May Street WWPS - Replacement pumps & Control. | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-09-07 | 2020-12-08 | 2021-12-13 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55470 | 55470 | 64529.64 | 0 | 0 | 119999.64 | 0 | 0 | 0 | 0 | 119999.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402603 | MCC Controls Aberdeenshire | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2013-07-03 | 2013-09-17 | 2016-11-25 |  | All East Unitary Authorities | 180124 | 0 | 53914.8 | 5943.55 | 341.85 | 0 | 0 | 0 | 60200.2 | 0 | 0 | 0 | 240324.2 | 0 | 0 | 0 | 0 | 240324.2 | 209381.79 | [5 empty] | N | CM_M&G | 100%
502350 | MCC SR15- East SPS MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2020-05-19 |  | All East Unitary Authorities | 0 | 0 | 0 | 34200 | 184.6 | 89.25 | 38181.11 | -72183.93 | 471.03 | 0 | 0 | 0 | 471.03 | 0 | 0 | 0 | 0 | 471.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502339 | MCC SR15 East WWTW MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-03-06 | 2020-03-06 | 2028-04-03 | 2020-05-19 |  | All East Unitary Authorities | 0 | 0 | 0 | 38620.47 | 190.89 | 43.72 | 4192.3 | -42643.85 | 403.52 | 0 | 0 | 0 | 403.52 | 0 | 0 | 0 | 0 | 403.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502342 | MCC SR15- Hamilton WWTW MCC Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS0 | 2020-04-28 | 2021-04-19 | 2021-06-14 | 2022-02-22 |  | South Lanarkshire | 0 | 0 | 0 | 24773.02 | 50153.65 | -3348.29 | 18482.75 | 206168.41 | 296229.54 | 788729.91 | 0 | 0 | 1084959.45 | 0 | 0 | 0 | 0 | 1084959.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502355 | MCC SR15- Shieldhall WWTW MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS0 | 2020-06-24 | 2022-07-22 | 2022-11-24 | 2023-11-08 |  | Glasgow City | 0 | 0 | 0 | 29521.37 | 157120.27 | 13813.51 | 12776.8 | 225971.05 | 439203 | 4126429 | 0 | 0 | 4565632 | 0 | 0 | 0 | 0 | 4565632 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502356 | MCC SR15- Shieldhall WWTW MCC Replacement Phase 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS0 | 2020-04-29 | 2022-11-21 | 2023-03-24 | 2024-03-21 |  | Glasgow City | 0 | 0 | 0 | 38700 | 1858 | 242409.45 | 50510.61 | 233566.95 | 567045 | 6003736.02 | 0 | 0 | 6570781.02 | 0 | 0 | 0 | 0 | 6570781.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502343 | MCC SR15- South SPS MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-03-06 | 2020-03-06 | 2028-04-14 | 2020-05-28 |  | All South Unitary Authorities | 0 | 0 | 0 | 23860.47 | 190.89 | 43.72 | 26678.13 | -50369.68 | 403.52 | 0 | 0 | 0 | 403.52 | 0 | 0 | 0 | 0 | 403.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502340 | MCC SR15- South WWTW MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2020-05-19 |  | All South Unitary Authorities | 0 | 0 | 0 | 38620.47 | 307.87 | 1089.9 | 4438.27 | -40063.08 | 4393.42 | 0 | 0 | 0 | 4393.42 | 0 | 0 | 0 | 0 | 4393.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502341 | MCC SR15- West WWTW MCC Replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2020-05-19 |  | All West Unitary Authorities | 0 | 0 | 0 | 38842.4 | 454.1 | 43.72 | 4154.21 | -42256.46 | 1237.96 | 0 | 0 | 0 | 1237.96 | 0 | 0 | 0 | 0 | 1237.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500436 | MD SVCW SR 15 Waste East Infra | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-14 | 2015-05-14 | 2015-05-14 | 2018-06-21 |  | All East Unitary Authorities | 0 | 0 | 134279 | 638692.24 | 479937.18 | -49306.66 | 0 | 0 | 1203601.76 | 0 | 0 | 0 | 1203601.76 | 0 | 0 | 0 | 0 | 1203601.76 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500796 | Meadow Road WwPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-08-13 | 2016-04-29 | 2016-05-25 | 2016-08-01 |  | Fife | 0 | 0 | 3180.17 | 24605.83 | 0 | 3600.07 | 0 | 0 | 31386.07 | 0 | 0 | 0 | 31386.07 | 0 | 0 | 0 | 0 | 31386.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403169 | Meadowbank Avenue Meadowbank Place Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-11-26 | 2015-08-31 | 2015-08-31 | 2015-09-02 | 2015-09-02 | City of Edinburgh | 168947 | 168947 | -168800.88 | -0.21 | 0 | 0 | 0 | 0 | -168801.09 | 0 | 0 | 0 | 145.91 | 0 | 0 | 0 | 0 | 145.91 | 180449.74 | [5 empty] | N | FL_DD | 100%
501103 | Meadowhead DAS Aesthetic and ICM WQ Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2017-03-28 | 2017-03-28 | 2018-06-30 | 2018-12-31 | East Ayrshire | 0 | 0 | 715 | 56584 | 220843.51 | 130823.36 | 3316.65 | 0 | 412282.52 | 0 | 0 | 0 | 412282.52 | 0 | 0 | 0 | 0 | 412282.52 | 102291.65 | [5 empty] | Y | EC10E | 2.979% | EC01G | 19.4% | EC01D | 77.62% | [36 empty] | 1 | [26 empty] | 0
505606 | Meadowhead Grit Rake Refurbishment (4 no) - 500k | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2020-03-25 | 2021-02-24 | 2021-03-15 | 2022-04-28 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146000 | 146000 | 379912 | 0 | 0 | 525912 | 0 | 0 | 0 | 0 | 525912 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500822 | Meadowhead Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2015-12-16 | 2015-12-16 | 2019-03-06 | 2019-03-06 | North Ayrshire | 0 | 0 | 138784.81 | 41429.7 | 13260.1 | -87399.7 | 0 | 0 | 106074.91 | 0 | 0 | 0 | 106074.91 | 0 | 0 | 0 | 0 | 106074.91 | 106252.93 | [5 empty] | N | FL_DD | 100%
403755 | Meadowhead Inlet Works Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-03-05 | 2014-05-28 | 2014-05-20 | 2016-06-24 |  | North Ayrshire | 1968942 | 0 | 734102 | -16083.83 | -3177.12 | 0 | 0 | 0 | 714841.05 | 0 | 0 | 0 | 2683783.05 | 0 | 0 | 0 | 0 | 2683783.05 | 90601.29 |  |  |  |  | 10865 | N | CM_WWNI | 100%
503353 | Meadowhead IW - Refurbishment of 4 No. Grit rakes (M&E) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-07-16 | 2028-03-03 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 90601.29 | [5 empty] | N | CM_WWI | 100%
501169 | Meadowhead STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-07-19 | 2018-08-31 | 2019-01-29 | 2021-04-01 |  | North Ayrshire | 0 | 0 | 0 | 75934.72 | 264799.96 | 644526.29 | 1510771.03 | 253490.06 | 2749522.06 | 34237.94 | 0 | 0 | 2783760 | 0 | 0 | 270598 | 270598 | 3054358 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507147 | Meadowhead WWTW - Replacement of Washpactors 1 and 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2020-06-29 | 2020-07-24 | 2021-03-18 | 2021-10-28 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128713 | 128713 | 281287.45 | 0 | 0 | 410000.45 | 0 | 0 | 0 | 0 | 410000.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501739 | Meadowhead WwTW HCS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-11-22 | 2018-03-23 | 2018-03-26 | 2021-06-24 |  | North Ayrshire | 0 | 0 | 0 | 8150.38 | 281060.11 | 779583.51 | 177482.29 | 66959.01 | 1313235.3 | 0 | 0 | 0 | 1313235.3 | 0 | 0 | 86764.7 | 86764.7 | 1400000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509233 | Meavaig WTW - PLC | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-01-03 | 2023-11-20 | 2024-04-29 | 2025-11-10 | 2026-02-10 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5254 | 5254 | 244745.39 | 0 | 0 | 249999.39 | 0 | 0 | 0 | 0 | 249999.39 | 0 | [5 empty] | N | SR21_WA | 100%
502873 | Meavaig WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-03 | 2020-04-08 | 2020-04-03 | 2020-05-07 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 21238 | 1387.35 | -18849.74 | 0 | 3775.61 | 0 | 0 | 0 | 3775.61 | 0 | 0 | 0 | 0 | 3775.61 | 122419.09 | [5 empty] | N | WG1 | 100%
46836 | Meavaig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-07-26 | 2012-08-08 | 2012-08-08 | 2011-03-14 | Na H-Eileanan an Iar | 62811.62 | 0 | 1099.5 | 0 | 0 | 0 | 0 | 0 | 1099.5 | 0 | 0 | 0 | 63911.12 | 0 | 0 | 0 | 0 | 63911.12 | 28761.13 | [5 empty] | N | DW13 | 100%
400104 | Medowhead STW Inlet Works Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-03-26 | 2014-10-27 | 2014-10-21 | 2014-10-21 | 2014-10-21 | North Ayrshire | 740196.96 | 0 | 12589.77 | -12667.92 | 0 | 0 | 0 | 0 | -78.15 | 0 | 0 | 0 | 740118.81 | 0 | 0 | 0 | 0 | 740118.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501869 | Megget E - Replacement of 300m of 900mm dia plus option to reline existing | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 2020-04-27 | 2021-04-01 | Midlothian | 0 | 0 | 0 | 0 | 14403.05 | 1121.71 | 0 | 0 | 15524.76 | 0 | 0 | 0 | 15524.76 | 0 | 0 | 0 | 0 | 15524.76 | 5935596.51 | [5 empty] | N | CS16WR | 100%
502789 | Megget Aqueduct to Bonnycraig RWM - Manor Water Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2028-04-21 | 2028-12-07 | 2029-02-09 | 2029-07-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 12252.49 | 12747.51 | 0 | -11916.86 | 13083.14 | 202256.92 | 0 | 0 | 215340.06 | 0 | 0 | 0 | 0 | 215340.06 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403141 | Megget Reservoir - Interests of Safety work | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-07 | 2013-09-27 | 2013-10-03 | 2014-02-18 | 2014-02-18 | Scottish Borders | 263670.43 | 0 | 879.93 | 0 | 0 | 0 | 0 | 0 | 879.93 | 0 | 0 | 0 | 264550.36 | 0 | 0 | 0 | 0 | 264550.36 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403678 | Megget Reservoir - Rip Rap Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-03 | 2014-08-22 | 2014-09-30 | 2014-12-12 | 2014-12-19 | Scottish Borders | 218316 | 0 | -16806.22 | 0 | 0 | 0 | 0 | 0 | -16806.22 | 0 | 0 | 0 | 201509.78 | 0 | 0 | 0 | 0 | 201509.78 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500684 | Megray Inlet Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2015-06-08 | 2018-11-30 | 2022-05-17 | 2022-06-27 |  | Aberdeenshire | 0 | 0 | 40054 | 143098 | 77582.72 | 105972.42 | 0 | -0.14 | 366707 | 625721.9 | 0 | 0 | 992428.9 | 0 | 0 | 0 | 0 | 992428.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503317 | Meigle WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-11-24 | 2024-09-10 | 2024-12-09 | 2025-12-05 |  | Angus | 0 | 0 | 0 | 0 | 0 | 36358.8 | 38928.12 | 66165.08 | 141452 | 2640948.33 | 0 | 0 | 2782400.33 | 0 | 0 | 0 | 0 | 2782400.33 | 122419.09 | [5 empty] | N | SG1 | 100%
500790 | Meigle WwTW & SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-09-07 | 2027-07-14 | 2027-09-23 | 2028-08-09 |  | Perth and Kinross | 0 | 0 | 38927 | 290174.81 | 1405.99 | 0 | -18908.49 | -10563.54 | 301035.77 | 2355621.63 | 0 | 0 | 2656657.4 | 0 | 0 | 0 | 0 | 2656657.4 | 181202.57 | [5 empty] | N | CM_WWNI | 100%
502969 | Meikle Tullo WSZ - Memus Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2019-12-11 | 2019-12-11 | 2020-10-21 | 2020-10-21 |  | Angus | 0 | 0 | 0 | 0 | 7178.94 | 7221.06 | -2763.56 | 67.41 | 11703.85 | 0 | 0 | 0 | 11703.85 | 0 | 0 | 0 | 0 | 11703.85 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401600 | Meikle Wartle WWTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-05-12 | 2013-12-11 | 2014-02-24 | 2018-04-11 | 2018-04-11 | Aberdeenshire | 1047156.05 | 0 | 30092.95 | 11999.63 | 36768.6 | 0 | 0 | 0 | 78861.18 | 0 | 0 | 0 | 1126017.23 | 0 | 0 | 0 | 0 | 1126017.23 | 0 | [5 empty] | N | SG1 | 100%
500165 | Melrose DOA (DOA000072) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-11-28 | 2017-01-23 | 2018-12-11 | 2019-03-22 | Scottish Borders | 0 | 0 | 13273 | 41433 | 69908 | 39500 | -6043.1 | 0 | 158070.9 | 0 | 0 | 0 | 158070.9 | 0 | 0 | 0 | 0 | 158070.9 | 60738.27 | [5 empty] | N | EC01G | 8.713% | CS16D | 42.78% | EC01D | 48.5%
503308 | Melrose WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-21 | 2029-06-21 | 2030-06-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 27021.53 | 6606.13 | 14495.34 | 48123 | 0 | 0 | 0 | 48123 | 0 | 0 | 0 | 0 | 48123 | 122419.09 | [5 empty] | N | SG1 | 100%
502539 | Membrane Cleaning - Dunbar WWTW - MBR Tank 2 & 4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-27 | 2017-06-27 | 2017-06-28 | 2017-08-15 |  | East Lothian | 0 | 0 | 0 | 36636 | 1220212.63 | 0 | 0 | 0 | 1256848.63 | 0 | 0 | 0 | 1256848.63 | 0 | 0 | 0 | 0 | 1256848.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401029 | Membrane Replacement SR10 - Phase1 High Priority | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-06-21 | 2010-06-21 | 2010-07-19 | 2012-01-31 |  | Scottish Water Wide | 1180786.8 | 0 | -351.8 | 0 | 0 | 0 | 0 | 0 | -351.8 | 0 | 0 | 0 | 1180435 | 0 | 0 | 0 | 0 | 1180435 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400551 | Meter Maintenance and Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-06-07 | 2010-06-14 | 2015-09-01 |  | Scottish Water Wide | 10235403.83 | 0 | -141732.59 | -79630.81 | -31414.75 | 6000 | 0 | 0 | -246778.15 | 0 | 0 | 0 | 9988625.68 | 0 | 0 | 0 | 0 | 9988625.68 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402257 | Metering Commission Market Changes | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-08-01 | 2013-05-29 | 2013-05-30 | 2016-08-08 | 2016-10-03 | Scottish Water Wide | 4125000 | 0 | 0 | -52307.22 | 0 | 0 | 0 | 0 | -52307.22 | 0 | 0 | 0 | 4072692.78 | 0 | 0 | 0 | 0 | 4072692.78 | 0 | [5 empty] | N | CS20 | 100%
503220 | Methlick WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-14 | 2029-06-15 | 2030-06-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 86256.55 | 11597.62 | 25193.83 | 123048 | 145.86 | 0 | 0 | 123193.86 | 0 | 0 | 0 | 0 | 123193.86 | 122419.09 | [5 empty] | N | SG1 | 100%
403680 | Methven - Lyndoch Road additional capacity | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2014-02-18 | 2014-02-18 | 2014-02-18 | 2015-10-12 | 2017-03-29 | Scottish Water Wide | 456837 | 0 | -333227.7 | -70000 | 62.39 | 0 | 0 | 0 | -403165.32 | 0 | 0 | 0 | 53671.69 | 0 | 0 | 0 | 0 | 53671.69 | 0 | [5 empty] | N | WG5 | 100%
508109 | Microsoft Teams | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS2 | 2020-10-29 | 2021-03-24 | 2021-04-19 | 2021-05-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571273 | 571273 | 674656.96 | 0 | 0 | 1245929.96 | 0 | 0 | 99674.3968 | 99674.3968 | 1345604.3568 | 306661.32 | [5 empty] | N | CM_M&G | 100%
400090 | Mid Tolsta STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-11-16 | 2013-01-07 | 2013-05-28 | 2014-03-31 | 2014-03-31 | Na H-Eileanan an Iar | 773340.05 | 0 | 10677.32 | 0 | 0 | 0 | 0 | 0 | 10677.32 | 0 | 0 | 0 | 784017.37 | 0 | 0 | 0 | 0 | 784017.37 | 28761.13 | [5 empty] | N | EC10A | 50% | WQ01 | 50%
402701 | Midfield Unst WSZ Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2012-10-09 | 2014-06-27 | 2014-08-29 | 2021-07-23 |  | Shetland Islands | 240764 | 0 | 141575 | 15760.72 | 10112.57 | 0 | 0 | -0.29 | 167448 | 0 | 0 | 0 | 408212 | 0 | 0 | 0 | 0 | 408212 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45561 | Milesmark STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2011-09-06 | 2013-01-14 | 2013-10-31 | 2013-11-08 | Fife | 1584207.38 | 0 | 12081.18 | 20272.95 | 29614.25 | -25750 | 0 | 0 | 36218.38 | 0 | 0 | 0 | 1620425.76 | 0 | 0 | 0 | 0 | 1620425.76 | 119362.42 | [5 empty] | N | CM_WWNI | 12.22% | WQ01 | 87.78%
501556 | Mill Street Dingwall Relay Sewe | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2016-05-04 | 2021-11-15 | 2022-01-17 | 2022-05-27 |  | Highland | 0 | 0 | 0 | 73700 | 26272.09 | 9177.39 | 0 | -267.36 | 108882.12 | 158289.89 | 0 | 0 | 267172 | 0 | 0 | 0 | 0 | 267172 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500971 | Millburn Avenue Coaltown of Balgonie | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-10-12 | 2016-08-30 | 2016-09-26 | 2016-11-21 |  | Fife | 0 | 0 | 4172.5 | 73266.5 | 1799 | -1865.77 | 0 | 0 | 77372.23 | 0 | 0 | 0 | 77372.23 | 0 | 0 | 0 | 0 | 77372.23 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503112 | Millglen Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | North Ayrshire | 0 | 0 | 0 | 0 | 6697.67 | 278.85 | 87.99 | 0 | 7064.51 | 0 | 0 | 0 | 7064.51 | 0 | 0 | 0 | 0 | 7064.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505236 | Millholm WWPS - conversion to wet well submersible station | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2020-02-28 | 2021-02-26 | 2021-03-10 | 2021-08-11 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148689.81 | 148689.81 | 101310.19 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500160 | Millport DOA (DOA000937) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SW | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-02-26 | 2016-07-01 | 2017-09-30 | 2018-01-31 | North Ayrshire | 0 | 0 | 14828 | 88779 | 27851 | -3555.34 | 0 | 0 | 127902.67 | 0 | 0 | 0 | 127902.67 | 0 | 0 | 0 | 0 | 127902.67 | 4617.88 | [5 empty] | Y | EC01G | 100% | [40 empty] | 1 | [26 empty] | 0
503826 | Millport WwTW - FE Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2021-07-15 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 3640.19 | 48111.81 | 51752 | 0 | 0 | 0 | 51752 | 0 | 0 | 0 | 0 | 51752 | 90601.29 | [5 empty] | N | WWNI | 100%
503280 | Millport WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-10-13 | 2025-08-08 | 2025-11-10 | 2026-12-04 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 77728.06 | 3854.89 | 12209.05 | 93792 | 0 | 0 | 0 | 93792 | 0 | 0 | 0 | 0 | 93792 | 122419.09 | [5 empty] | N | SG1 | 100%
504490 | Milnathort WWTW (East) Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-04 |  | 2021-05-01 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | -92668.92 | 7331.08 | 92668.92 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505626 | Milngavie & Balmore WOA-WI-Park Circus | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-11-29 | 2023-10-16 | 2024-03-25 | 2025-10-06 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2721 | 2721 | 297279.29 | 0 | 0 | 300000.29 | 0 | 0 | 0 | 0 | 300000.29 | 119022.58 | [5 empty] | N | WSNI | 100%
500007 | Milngavie C2 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS7 | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-06-29 | 2019-03-01 | Glasgow City | 332.03 | 212.199 | 128254.97 | 7761 | 199420 | 336716.28 | 3347.57 | -1183.24 | 674316.58 | 0 | 0 | 0 | 674648.61 | 0 | 0 | 0 | 0 | 674648.61 | 1006806.03 | [5 empty] | N | CM_WSI | 29% | DW5 | 71%
500839 | Milngavie C2 RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2015-10-28 | 2017-03-23 | 2017-03-31 | 2018-03-31 | 2020-02-29 | Glasgow City | 0 | 0 | 18193 | 40657.62 | 152632.69 | 44644.09 | 4283.07 | -20404.74 | 240005.73 | 0 | 0 | 0 | 240005.73 | 0 | 0 | 0 | 0 | 240005.73 | 189290.41 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 25.05 | [43 empty] | 0
500008 | Milngavie C3 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS7 | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2018-05-09 | 2021-04-01 | Glasgow City | 332.03 | 270.1871 | 136786.97 | 234253 | 574625 | 360420.76 | 8624.9 | 0 | 1314710.62 | 0 | 0 | 0 | 1315042.65 | 0 | 0 | 0 | 0 | 1315042.65 | 1747057.34 | [5 empty] | N | DW5 | 46.08% | DW5FS | 53.92%
503168 | Milngavie C3 RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-02-28 | 2016-03-31 | 2016-08-22 | 2020-06-10 | 2021-04-01 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 54152.01 | 2000.01 | -2000 | 54152.01 | 0 | 0 | 0 | 54152.01 | 0 | 0 | 0 | 0 | 54152.01 | 873528.67 | [5 empty] | N | DW5FS | 100%
500009 | Milngavie C4 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS7 | 2015-02-23 | 2016-03-30 | 2016-05-02 | 2017-09-25 | 2018-12-19 | Glasgow City | 332.03 | 332.03 | 60038.97 | 214299 | 172131 | 320158.41 | -86611.22 | 0 | 680016.16 | 0 | 0 | 0 | 680348.19 | 0 | 0 | 0 | 0 | 680348.19 | 539345.26 | [5 empty] | N | DW5 | 100%
500840 | Milngavie C4 RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2015-12-10 | 2017-03-23 | 2017-03-24 | 2019-01-31 | 2019-08-31 | Glasgow City | 0 | 0 | 5268 | 29890.62 | 80702.37 | 53231.09 | 4061.72 | -12421.85 | 160731.95 | 2404.56 | 2404.5565 | 3337.9338 | 163136.51 | 933.3773 | 0 | 0 | 933.3773 | 164069.8873 | 33798.86 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 16.59 | [43 empty] | 0
503169 | Milngavie C4 RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-02-28 | 2016-03-30 | 2016-03-30 | 2020-06-02 | 2021-04-01 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 62977 | 2000 | -2000.01 | 62977 | 0 | 0 | 0 | 62977 | 0 | 0 | 0 | 0 | 62977 | 539345.26 | [5 empty] | N | DW5FS | 100%
508743 | Milngavie CWT Investigation Works - Phase 1 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-09-24 | 2021-06-21 | 2022-02-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3683.77 | 3683.77 | 46453.8 | 0 | 0 | 50137.57 | 0 | 0 | 0 | 0 | 50137.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500010 | Milngavie M1 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS7 | 2015-02-25 | 2016-03-31 | 2016-06-20 | 2019-03-22 | 2021-04-01 | Glasgow City | 332.03 | 217.2593 | 187144.97 | 591927.09 | 275470.71 | 96295.7 | 6731.94 | -148.12 | 1157422.29 | 0 | 0 | 0 | 1157754.32 | 0 | 0 | 0 | 0 | 1157754.32 | 1725850.42 | [5 empty] | N | CM_WSI | 34.57% | DW5 | 65.43%
503170 | Milngavie M1 RSZ Trunk Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS4 | 2015-02-28 | 2016-03-31 | 2016-03-31 | 2020-03-31 | 2021-06-15 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 49085.77 | 2471.03 | 15388.21 | 66945.01 | 44852.34 | 44852.34 | 65845.9645 | 111797.35 | 20993.6245 | 0 | -0.0045 | 20993.62 | 132790.97 | 1414613.63 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 42.03 | [43 empty] | 0
500863 | Milngavie M4C RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-09-20 | 2018-06-27 | 2018-09-12 | 2019-03-31 | 2019-08-31 | Glasgow City | 0 | 0 | 18259.61 | 28121.72 | 58974.12 | 134780.58 | 13009.48 | -8447.32 | 244698.19 | 0 | 0 | 0 | 244698.19 | 0 | 0 | 0 | 0 | 244698.19 | 1058349.63 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 54.03 | [43 empty] | 0
500887 | Milngavie South Moorhouse RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-10-13 | 2018-09-21 | 2018-10-25 | 2019-06-30 | 2020-02-29 | East Renfrewshire | 0 | 0 | 6404.84 | 2646.27 | 6920.97 | 93249.68 | 14297.66 | -10961.26 | 112558.16 | 2500 | 2500 | 3470.4256 | 115058.16 | 970.4256 | 0 | 0 | 970.4256 | 116028.5856 | 503405.31 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 47.59 | [43 empty] | 0
509228 | Milngavie WOA - Investigations on Neilston Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-10-15 | 2021-02-08 | 2021-08-06 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11497 | 11497 | 81588.06 | 0 | 0 | 93085.06 | 0 | 0 | 0 | 0 | 93085.06 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503475 | Milngavie WOA - Keppochhill Road DMA - Borron Tunnel Condition | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-23 | 2022-04-01 | 2022-06-30 | 2024-01-25 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2161.94 | 2161.94 | 264946.26 | 0 | 0 | 267108.2 | 0 | 0 | 0 | 0 | 267108.2 | 622473.57 | [5 empty] | N | CM_WSI | 4.762% | CM_M&G | 95.24%
504919 | Milngavie WOA - M1 PRV Design & Installation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-01-30 |  | 2020-08-21 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | 1025772 | 1053272 | 7886.68 | 0 | 0 | 1061158.68 | 0 | 0 | 0 | 0 | 1061158.68 | 119022.58 | [5 empty] | N | WSNI | 100%
501074 | Milngavie WOA C2 Craigmaddie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-27 | 2028-04-03 | 2028-05-16 | 2029-07-24 |  | Glasgow City | 0 | 0 | 61056 | 14211.95 | 4143 | 12425.59 | -17153.66 | -12.2 | 74670.68 | 2063372.32 | 0 | 0 | 2138043 | 0 | 0 | 0 | 0 | 2138043 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501073 | Milngavie WOA C3 Craigmaddie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
501072 | Milngavie WOA C5 Craigmaddie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-13 | 2031-09-16 | 2031-10-29 | 2032-04-05 |  | Glasgow City | 0 | 0 | 9720 | 17227.58 | 26577.42 | 54627.77 | 0 | 0.23 | 108153 | 271575.4 | 0 | 0 | 379728.4 | 0 | 0 | 0 | 0 | 379728.4 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501071 | Milngavie WOA M2 Mugdock WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-27 | 2028-03-09 | 2028-04-26 | 2029-03-06 |  | Glasgow City | 0 | 0 | 37440 | 42780 | 6000 | 106606 | -114553.77 | 0 | 78272.23 | 1453556.76 | 0 | 0 | 1531828.99 | 0 | 0 | 0 | 0 | 1531828.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501075 | Milngavie WOA M4 Mugdock C WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
506397 | Milngavie WTW - Design & Works to reroute lime dosing pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-22 | 2020-11-05 | 2022-02-10 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9399.47 | 9399.47 | 60831.36 | 0 | 0 | 70230.83 | 0 | 0 | 0 | 0 | 70230.83 | 119022.58 | [5 empty] | N | WSNI | 100%
505390 | Milngavie WTW - Drainage Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-03-26 |  | 2021-02-17 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 2090.51 | 12107.61 | 14198.12 | 0 | 0 | 0 | 14198.12 | 0 | 0 | 0 | 0 | 14198.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506257 | Milngavie WTW - NRVs/VSDs Install | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-28 | 2020-09-10 | 2021-12-02 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79350 | 79350 | 160650 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 240000 | 119022.58 | [5 empty] | N | Wa6 | 100%
505707 | Milngavie WTW Drainage Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MSU |  | 2020-09-01 |  | 2021-04-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
507862 | Milngavie WTW Filter Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-05-26 | 2024-04-11 | 2024-09-19 | 2026-04-02 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WSNI | 100%
403966 | Milngavie WTW Filters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2014-10-16 | 2015-06-25 | 2015-06-25 | 2016-07-21 |  | East Renfrewshire | 594719 | 0 | 1276918 | 223864.73 | 79588 | -2685.72 | 2333.45 | 982.56 | 1581001.02 | 0 | 0 | 0 | 2175720.02 | 0 | 0 | 0 | 0 | 2175720.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508081 | Milngavie WTW Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-07-26 | 2024-05-27 | 2024-08-28 | 2026-12-16 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2068239.92 | 2068239.92 | 12932671.19 | 0 | 0 | 15000911.11 | 0 | 0 | 0 | 0 | 15000911.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502793 | Milroy Gardens Pipe Bridge Bellshill | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-02-26 | 2020-09-18 | 2020-12-07 | 2021-08-19 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 16244.04 | 25656.96 | 69302.42 | 325809.58 | 437013 | 208578.32 | 0 | 0 | 645591.32 | 0 | 0 | 0 | 0 | 645591.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502974 | Milton of Panholes WwTW - Growth - Interim Solution | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater | SW | SWD | Strategic Capacity | MS7 | 2020-05-15 | 2020-05-15 | 2020-05-15 | 2021-01-15 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730.46 | 1730.46 | 0 | 0 | 0 | 1730.46 | 0 | 0 | 0 | 0 | 1730.46 | 122419.09 | [5 empty] | N | SG1 | 100%
501109 | Mini Excavators trailers and breakers | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-10-13 | 2015-10-13 | 2015-10-13 | 2016-06-30 |  | Scottish Water Wide | 0 | 0 | 987186.22 | 506 | 0 | 0 | 0 | 0 | 987692.22 | 0 | 0 | 0 | 987692.22 | 0 | 0 | 0 | 0 | 987692.22 | 306661.32 | [5 empty] | N | CM_M&G | 100%
506225 | Minishant Secondary Treatment | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWMD | Revised Bathing Waters Directive | GW1 | 2021-10-28 | 2023-09-14 | 2024-02-22 | 2025-09-04 | 2025-12-05 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181896 | 181896 | 80248.74 | 0 | 0 | 262144.74 | 0 | 22134.6764 | 0 | 22134.6764 | 284279.4164 | 1035209.71 | [5 empty] | N | EC16B | 100%
500230 | Mintlaw WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS1 | 2018-04-27 | 2021-07-12 | 2021-11-22 | 2023-02-24 |  | Aberdeenshire | 0 | 0 | 64339.51 | 20868.31 | 39931.07 | 27352.65 | 136090.94 | 124202.52 | 412785 | 3322338.42 | 0 | 0 | 3735123.42 | 0 | 0 | 0 | 0 | 3735123.42 | 213020.38 | [5 empty] | N | CM_WWNI | 14% | SG1 | 86%
510253 | Mishnish Lochs SVCD Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-01-18 | 2021-09-09 | 2022-04-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14251.64 | 14251.64 | 185730.9 | 0 | 0 | 199982.54 | 0 | 0 | 0 | 0 | 199982.54 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504399 | Mission Emergency Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-01-27 | 2020-02-03 | 2020-12-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 293368.32 | 310368.32 | 2951.38 | 0 | 0 | 313319.69 | 0 | 0 | 0 | 0 | 313319.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500501 | Mobile Turbo Actiflo Water Treatment Unit | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2015-06-08 | 2015-06-08 | 2015-06-08 | 2016-09-08 | 2016-09-08 | Scottish Water Wide | 0 | 0 | 329499 | 249835.18 | 0 | 196.08 | 0 | 0 | 579530.26 | 0 | 0 | 0 | 579530.26 | 0 | 0 | 0 | 0 | 579530.26 | 638845.62 | [5 empty] | N | CS16WR | 100%
403898 | Mobilisation of Amey Black & Veatch (aBV) Wastewater Alliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | WWINF | Management and General | MS3 | 2014-07-25 | 2014-10-08 | 2014-10-08 | 2021-05-01 |  | Scottish Water Wide | 1544206.72 | 772103.36 | 1101002.28 | -1476785.52 | -1018423.48 | 0 | 0 | -64609.8 | -1458816.52 | 64609.8 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403884 | Mobilisation of Caledonia Water Alliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | WINF | Management and General | MS3 | 2014-07-25 | 2014-10-08 | 2014-10-08 | 2021-06-30 |  | Scottish Water Wide | 2200000 | 1100000 | 0 | 2526911.48 | 376948.12 | -3341838.6 | 204796.84 | -287225.84 | -520408 | 163150.84 | 0 | 0 | 1842742.84 | 0 | 0 | 0 | 0 | 1842742.84 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500942 | Mobilisation of ESD Non Infra Alliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | NONINF | Management and General | MS3 | 2015-09-30 | 2015-10-21 | 2015-12-01 | 2022-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 1538913.88 | 2184600.95 | -2174084.69 | 383813.11 | 902453.15 | 2835696.4 | 896354.6 | 0 | 0 | 3732051 | 0 | 0 | 0 | 0 | 3732051 | 613322.63 | [5 empty] | N | QS4EQS | 50% | QS4EQW | 50%
508280 | Moffat WTW - Inadequate Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-09-14 | 2021-02-19 | 2021-04-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296 | 1296 | 3703.7 | 0 | 0 | 4999.7 | 0 | 0 | 0 | 0 | 4999.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511933 | Moffat WTW - Welfare Facilities Provision | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84.12 | 84.12 | 67415.88 | 0 | 0 | 67500 | 0 | 0 | 0 | 0 | 67500 | 119022.58 | [5 empty] | N | WSNI | 100%
502609 | Monifeith Bathing Water Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2017-03-15 | 2017-06-16 | 2017-06-16 | 2017-11-30 | 2018-03-31 | Angus | 0 | 0 | 0 | 314.02 | 30565.42 | -1456.41 | 0 | 0 | 29423.03 | 0 | 0 | 0 | 29423.03 | 0 | 0 | 0 | 0 | 29423.03 | 0 | [5 empty] | Y | EC16 | 100% | [38 empty] | 1 | [28 empty] | 0
502646 | Monitoring and Reporting of Scottish Water Assets impacting bathing waters part 2 | IR18 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS6 | 2017-04-11 | 2017-04-11 | 2017-06-26 | 2018-08-17 | 2018-08-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 357386.81 | 7656.34 | 0 | -47.36 | 364995.79 | 0 | 0 | 0 | 364995.79 | 0 | 0 | 0 | 0 | 364995.79 | 0 | [5 empty] | N | EC16 | 100%
403546 | Monitoring and Reporting of Scottish Water Assets Impacting BW Quality | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-30 | 2016-01-18 | 2016-02-29 | 2016-12-01 | 2017-02-01 | Scottish Water Wide | 69955 | 0 | 80379 | 142500.64 | 12766 | 66.95 | 0 | 0 | 235712.59 | 0 | 0 | 0 | 305667.59 | 0 | 0 | 0 | 0 | 305667.59 | 0 | [5 empty] | N | EC16 | 100%
503691 | Monitoring Disinfection By-products in Chloraminated Supplies | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2019-09-16 | 2019-09-16 | 2019-09-17 | 2020-12-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | -2384.85 | 217615.15 | 0 | 0 | 0 | 217615.15 | 0 | 0 | 0 | 0 | 217615.15 | 306661.32 | [5 empty] | N | CM_M&G | 100%
502221 | Montgarrie ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS2 | 2017-11-27 | 2020-03-31 | 2022-04-04 | 2023-04-21 |  | Aberdeenshire | 0 | 0 | 0 | 36096.34 | 27842.56 | 76651.28 | 122057.14 | -27886.32 | 234761 | 589181.39 | 0 | 0 | 823942.39 | 0 | 0 | 0 | 0 | 823942.39 | 122419.09 | [5 empty] | N | SG1 | 100%
502954 | Montrose WwTW - Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-11-27 | 2018-03-14 | 2018-03-26 | 2018-06-29 |  | Angus | 0 | 0 | 0 | 0 | 179401.67 | 820806.03 | 1053.46 | -1502.46 | 999758.7 | 0 | 0 | 0 | 999758.7 | 0 | 0 | 0 | 0 | 999758.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500499 | Montrose WwTW - SR15 CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS4 | 2015-05-21 | 2019-09-23 | 2019-10-28 | 2021-02-26 |  | Angus | 0 | 0 | 143901 | 122582.39 | 88815.87 | 243720.59 | 400407.15 | -88158.41 | 911268.59 | 97742.41 | 0 | 0 | 1009011 | 0 | 0 | 0 | 0 | 1009011 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506522 | Montrose WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-07-03 | 2025-04-24 | 2025-07-23 | 2026-08-27 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84261 | 84261 | 1915739.41 | 0 | 0 | 2000000.41 | 0 | 0 | 0 | 0 | 2000000.41 | 122419.09 | [5 empty] | N | SG1 | 100%
502334 | Monymusk WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-04-24 | 2019-04-15 | Aberdeenshire | 0 | 0 | 0 | 38549.52 | 2466.9 | 0 | 0 | 0 | 41016.42 | 0 | 0 | 0 | 41016.42 | 0 | 0 | 0 | 0 | 41016.42 | 122419.09 | [5 empty] | N | SG1 | 100%
500926 | Moray Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2018-11-30 | 2018-11-30 | 2018-11-30 | 2018-11-30 | Moray | 0 | 0 | 6000 | 4712.79 | -2979.67 | -701.67 | 0 | 0 | 7031.45 | 0 | 0 | 0 | 7031.45 | 0 | 0 | 0 | 0 | 7031.45 | 106252.93 | [5 empty] | N | FL_DD | 100%
501022 | Morebattle STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2015-12-14 | 2021-11-04 | 2022-01-10 | 2023-08-25 |  | Scottish Borders | 0 | 0 | 20575 | 269789.31 | 96827.67 | 59950.61 | 309005.15 | 472993.26 | 1229141 | 1684871.96 | 0 | 0 | 2914012.96 | 0 | 0 | 0 | 0 | 2914012.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402712 | Morphie WSZ Low Pressure Enhancement WSZ001115 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-03 | 2014-12-05 | 2014-12-16 | 2015-06-25 | 2015-03-23 | Aberdeenshire | 61387 | 0 | 2983 | -0.11 | -342.47 | 0 | 0 | 0 | 2640.42 | 0 | 0 | 0 | 64027.42 | 0 | 0 | 0 | 0 | 64027.42 | 0 | [5 empty] | N | CS1 | 100%
403434 | Moss Street Keith | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-04-16 | 2014-09-03 | 2014-10-10 | 2015-05-22 | 2015-05-22 | Moray | 804635 | 804635 | 139977.66 | 29.67 | 658.56 | 0 | 0 | 0 | 140665.89 | 0 | 0 | 0 | 945300.89 | 0 | 0 | 0 | 0 | 945300.89 | 180449.74 | [5 empty] | N | FL_DD | 100%
45806 | Motehill SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-05-27 | 2011-02-21 | 2012-01-11 | 2012-03-23 | Scottish Water Wide | 3983.13 | 0 | 365.87 | 0 | 0 | 0 | 0 | 0 | 365.87 | 0 | 0 | 0 | 4349 | 0 | 0 | 0 | 0 | 4349 | 28761.13 | [5 empty] | N | WQ01C | 100%
504952 | Mount Pleasant Pipebridge - Riverbank Protection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MSU |  | 2021-04-01 |  | 2021-10-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27212 | 0 | 0 | 27212 | 0 | 0 | 0 | 0 | 27212 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506026 | Mount Pleasant Pipebridge - Riverbank Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-04-15 | 2021-06-21 | 2021-10-08 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 25000.02 | 0 | 0 | 35000.02 | 0 | 0 | 0 | 0 | 35000.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
50033 | Moved OMG 10 Security Outputs | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | SWD | Non OMG180 | MS3 | 2015-03-31 | 2016-03-31 | 2016-03-31 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | DW9 | 100% | [67 empty] | 0
403602 | Mowbray Gardens Crossgates Cowdenbeath | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2013-10-23 | 2015-02-27 | 2015-03-31 | 2015-07-23 | 2015-07-23 | Fife | 98510 | 98510 | 264270.66 | 5919.34 | 0 | 69265.89 | 0 | 0 | 339455.89 | 0 | 0 | 0 | 437965.89 | 0 | 0 | 0 | 0 | 437965.89 | 180449.74 | [5 empty] | N | FL_DD | 100%
501714 | MSI PFI Inverclyde WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-07-29 | 2020-06-30 | 2020-08-31 | 2021-08-12 |  | Inverclyde | 0 | 0 | 0 | 33248 | -8828 | 0 | 11741 | 362886.17 | 399047.17 | 404227.83 | 0 | 0 | 803275 | 0 | 0 | 0 | 0 | 803275 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403047 | Muchalls Marine Terrace rising main and BPT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-06 | 2013-06-27 | 2013-07-29 | 2014-04-08 |  | Aberdeenshire | 83300.92 | 0 | 0.08 | -718.3 | 0 | 0 | 0 | 0 | -718.22 | 0 | 0 | 0 | 82582.7 | 0 | 0 | 0 | 0 | 82582.7 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45555 | Muckhart STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2011-06-01 | 2011-07-28 | 2012-04-07 | 2013-02-06 | Clackmannanshire | 786725.35 | 0 | 2001.54 | 0 | 0 | 0 | 0 | 0 | 2001.54 | 0 | 0 | 0 | 788726.89 | 0 | 0 | 0 | 0 | 788726.89 | 119362.42 | [5 empty] | N | CM_WWNI | 6.398% | WQ01 | 93.6%
503603 | Muckhart WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-05-25 | 2023-04-14 | 2023-07-28 | 2024-08-16 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 83163.11 | 82935.87 | 166098.98 | 1037498.02 | 0 | 0 | 1203597 | 0 | 0 | 0 | 0 | 1203597 | 122419.09 | [5 empty] | N | SG1 | 100%
504655 | Mugdock Reservoir Vegetation Clearance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-09-29 | 2020-11-19 | 2021-10-04 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 107.65 | 143576.35 | 143684 | 96316.2 | 0 | 0 | 240000.2 | 0 | 0 | 0 | 0 | 240000.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503739 | Muir of Ord - Leanaig to Tore DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-09-30 | 2019-09-30 | 2019-11-11 | 2021-11-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 142498.5 | 65506.5 | 208005 | 361995.51 | 0 | 0 | 570000.51 | 0 | 0 | 0 | 0 | 570000.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505109 | Muir of Ord WwTW - Install MLSS Equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-09-17 | 2021-09-21 | 2022-01-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6006 | 6006 | 28848.41 | 0 | 0 | 34854.41 | 0 | 0 | 0 | 0 | 34854.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502421 | Muirdrum WwTW Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2021-04-01 | 2021-04-01 | 2020-09-04 | 2020-04-21 |  | Angus | 0 | 0 | 0 | 15069.77 | 628.53 | 4087.27 | 0 | 322.02 | 20107.59 | 0 | 0 | 0 | 20107.59 | 0 | 0 | 0 | 0 | 20107.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS5 | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-01 | 2019-03-01 | Renfrewshire | 0 | 0 | 44645 | 187355 | 305651.58 | 559147.36 | 339665.02 | 29769.05 | 1466233 | 1178867.56 | 1178867.56 | 1692121.7457 | 2645100.56 | 513254.1857 | 0 | -4.6566e-10 | 513254.1857 | 3158354.7457 | 3607589.06 | [5 empty] | N | DW5FS | 100%
501535 | Muirdykes No2 Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-17 | 2029-09-24 | 2030-01-28 | 2030-09-12 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860519.11 | 0 | 0 | 860519.11 | 0 | 0 | 0 | 0 | 860519.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501536 | Muirdykes No3 Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-09-21 | 2030-01-25 | 2030-09-11 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417966.04 | 0 | 0 | 417966.04 | 0 | 0 | 0 | 0 | 417966.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507224 | Muirdykes to Stanely SR Trunk Main - Landslip | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-27 | 2021-07-08 | 2021-11-12 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8351 | 8351 | 13048.54 | 0 | 0 | 21399.54 | 0 | 0 | 0 | 0 | 21399.54 | 311236.79 | [5 empty] | N | CM_M&G | 100%
501069 | Muirdykes WOA Foxbar Hollowhouse WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-06-01 | 2028-04-27 | 2028-06-20 | 2029-07-17 |  | East Renfrewshire | 0 | 0 | 88272 | 12853 | 7283 | 1719.56 | 14585.1 | -13223.41 | 111489.25 | 2290372.75 | 0 | 0 | 2401862 | 0 | 0 | 0 | 0 | 2401862 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501068 | Muirdykes WOA Stanely WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-12 | 2016-04-12 | 2016-04-12 | 2016-04-12 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
403955 | Muirdykes WTW | Q&S3B | Completion | OMG180 |  |  | Water | DWQR | SWD | OMG180 | MS5 | 2015-01-28 | 2015-07-31 | 2015-08-24 | 2017-12-31 | 2018-12-31 | Renfrewshire | 13000 | 0 | 4236033.98 | 10772967 | 1092460.44 | 109.29 | 830331.23 | 4122.99 | 16936024.92 | -19802.81 | -19802.8125 | -27489.6751 | 16929222.11 | -7686.8626 | 0 | 0 | -7686.8626 | 16921535.2474 | 12121303 |  |  |  |  | 179670 | Y | DW3C | 0.14% | DW3H | 0.31% | DW23 | 99.55% | [16 empty] | 1 | [46 empty] | 0
500575 | Muirdykes WTW CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-06-01 | 2021-01-15 | 2021-03-31 | 2022-08-22 |  | Renfrewshire | 0 | 0 | 22338.8 | 119869.52 | 111428.68 | -127103.62 | 217242 | 129635.62 | 473411 | 1252538.25 | 0 | 0 | 1725949.25 | 0 | 0 | 215616.75 | 215616.75 | 1941566 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510833 | Muirdykes WTW Defects | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-01-03 | 2023-07-12 | 2023-10-10 | 2024-09-16 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1698959.35 | 0 | 0 | 1698959.35 | 0 | 0 | 0 | 0 | 1698959.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500914 | Muiresk (Turriff WTW) RWP - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-11-06 | 2020-12-08 | 2021-01-05 | 2021-01-06 |  | Aberdeenshire | 0 | 0 | 5904.44 | 44390.19 | -4838.16 | 9042.77 | 24956.49 | -7443.94 | 72011.79 | 0 | 0 | 0 | 72011.79 | 0 | 0 | 0 | 0 | 72011.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507203 | Muirhead Reservoir Spillway Wall Repair | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS2 |  | 2020-09-22 | 2021-08-03 | 2022-03-29 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13084.11 | 13084.11 | 186915.89 | 186915.89 | 259471.0769 | 200000 | 72555.1869 | 0 | 0 | 72555.1869 | 272555.1869 | 2601944.88 | [5 empty] | N | CS22 | 100%
45793 | Muirhead SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2010-12-21 | 2011-03-25 | 2011-12-19 | 2012-01-31 | Angus | 565017.8 | 0 | 175.52 | 0 | 0 | 0 | 0 | 0 | 175.52 | 0 | 0 | 0 | 565193.32 | 0 | 0 | 0 | 0 | 565193.32 | 148123.55 | [5 empty] | N | CM_WWNI | 5.014% | WQ01B | 5.015% | WQ01C | 89.97%
503207 | Mulben Craighead ST ecological treatment system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2018-09-05 | 2022-04-22 | 2023-01-16 | 2023-11-06 |  | Moray | 0 | 0 | 0 | 0 | 0 | 26314.1 | 42708.1 | 26118.21 | 95140.41 | 109552.38 | 0 | 0 | 204692.79 | 0 | 0 | 0 | 0 | 204692.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501120 | MULTIPLE - CHEMICAL DOSING PROGRAMME Phase 1 Year 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWMD | Water Non infrastructure | MS7 | 2015-11-05 | 2018-12-10 | 2018-12-11 | 2018-12-12 |  | Scottish Water Wide | 0 | 0 | 30896 | 62243.94 | 75423.23 | 11889.09 | 0 | 0 | 180452.26 | 0 | 0 | 0 | 180452.26 | 0 | 0 | 0 | 0 | 180452.26 | 328404.37 | [5 empty] | N | CM_M&G | 49.14% | CM_WSNI | 50.86%
500028 | Multiple - GAC Replacement Programme - Phase 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-02-27 | 2015-04-28 | 2015-06-23 | 2017-10-09 |  | Scottish Water Wide | 0 | 0 | 1550664 | 1276315.48 | 312182.12 | -1158.51 | 0 | 0 | 3138003.09 | 0 | 0 | 0 | 3138003.09 | 0 | 0 | 0 | 0 | 3138003.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501772 | Multiple - GAC Replacement Programme Phase 2 Years 3 - 4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-12-08 | 2017-03-22 | 2017-07-27 | 2019-09-03 |  | Scottish Water Wide | 0 | 0 | 0 | 254977.55 | 1114203.37 | 1380331.58 | 193301.98 | 233.99 | 2943048.48 | 0 | 0 | 0 | 2943048.48 | 0 | 0 | 0 | 0 | 2943048.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502245 | MULTIPLE - GAC REPLACEMENT PROGRAMME Phase 3 Years 5 & 6 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-04-15 | 2019-04-15 | 2019-05-02 | 2021-08-27 |  | Scottish Water Wide | 0 | 0 | 0 | 3284.15 | -17.83 | 4114.81 | 1129363.44 | 1435422.87 | 2572167.44 | 55467.52 | 0 | 0 | 2627634.96 | 0 | 0 | 0 | 0 | 2627634.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502175 | Multiple - High Voltage Programme Phase 1 (Lomond Scheme) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-04-25 | 2027-08-06 | 2027-08-06 | 2028-09-29 |  | Scottish Water Wide | 0 | 0 | 0 | 159385.81 | 313796.99 | 14013.06 | 0 | -72094.38 | 415101.48 | 7584898.52 | 0 | 0 | 8000000 | 0 | 0 | 0 | 0 | 8000000 | 357067.75 | [5 empty] | N | CM_WSNI | 100%
501675 | MULTIPLE - HIGH VOLTAGE PROGRAMME Phase 2 (Mannofield) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2016-10-14 | 2016-10-14 | 2017-05-29 | 2022-11-22 |  | Aberdeen City | 0 | 0 | 0 | 0 | 3582.97 | 3192.16 | 2742.3 | 1599.57 | 11117 | 38883.24 | 0 | 0 | 50000.24 | 0 | 0 | 0 | 0 | 50000.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500029 | Multiple - Membrane Programme Phase 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-02-27 | 2015-04-28 | 2015-07-07 | 2018-06-18 |  | Scottish Water Wide | 135.86 | 0 | 4177771.14 | 1928293.73 | 1073446.9 | 7997.69 | 298114.1 | 0 | 7485623.56 | 0 | 0 | 0 | 7485759.42 | 0 | 0 | 0 | 0 | 7485759.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501771 | Multiple - Membrane Programme Phase 2 Years 3 & 4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-12-28 | 2017-05-31 | 2017-06-26 | 2019-07-05 |  | Scottish Water Wide | 0 | 0 | 0 | 67764.79 | 4358385.76 | 4387706.85 | 1044707.65 | 259.85 | 9858824.9 | 0 | 0 | 0 | 9858824.9 | 0 | 0 | 0 | 0 | 9858824.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502244 | Multiple - Membrane Programme Phase 3 Years 5 & 6 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-04-17 | 2019-04-17 | 2019-05-08 | 2021-09-23 |  | Scottish Water Wide | 0 | 0 | 0 | 8992.45 | 972.02 | 5090.89 | 3922739.53 | 8172875.48 | 12110670.36 | 692807.12 | 0 | 0 | 12803477.48 | 0 | 0 | 0 | 0 | 12803477.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503713 | Multiple sites Chemical Dosing H&S Programme Programme Costs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2020-03-19 | 2022-07-15 | 2022-10-31 | 2023-03-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2003.12 | 152139.89 | 154143.01 | 970856.99 | 0 | 0 | 1125000 | 0 | 0 | 0 | 0 | 1125000 | 328404.37 | [5 empty] | N | CM_M&G | 14.3% | CM_WSNI | 85.7%
501752 | MULTIPLE SITES - CHEMICAL DOSING PROGRAMME Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2016-03-21 | 2021-03-25 | 2020-12-04 | 2022-05-09 |  | Scottish Water Wide | 0 | 0 | 15426.5 | 6578.3 | 3226 | 146024.06 | 292494.79 | -200813.25 | 262936.4 | -1644.68 | 0 | 0 | 261291.72 | 0 | 0 | 0 | 0 | 261291.72 | 328404.37 | [5 empty] | N | CM_M&G | 16.67% | CM_WSNI | 83.33%
501753 | MULTIPLE SITES - CHEMICAL DOSING PROGRAMME Phase 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-01 |  |  | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 28856.57 | 4496.19 | 161677.07 | 276097.6 | 669214.46 | 1140341.88 | -5167.09 | 0 | 0 | 1135174.79 | 0 | 0 | 0 | 0 | 1135174.79 | 328404.37 | [5 empty] | N | CM_M&G | 9.677% | CM_WSNI | 90.32%
501754 | MULTIPLE SITES - CHEMICAL DOSING PROGRAMME Phase 4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 62288.37 | 349.36 | 2895.31 | 80862.58 | -80862.58 | 65533.04 | 0 | 0 | 0 | 65533.04 | 0 | 0 | 0 | 0 | 65533.04 | 328404.37 | [5 empty] | N | CM_M&G | 6.452% | CM_WSNI | 93.55%
501755 | MULTIPLE SITES - CHEMICAL DOSING PROGRAMME Phase 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 50857.53 | 438.51 | 1523.26 | 69160.42 | -69160.42 | 52819.3 | 0 | 0 | 0 | 52819.3 | 0 | 0 | 0 | 0 | 52819.3 | 328404.37 | [5 empty] | N | CM_WWI | 32.99% | CM_WSNI | 67.01%
510095 | Multiple Sites - North Wastewater Non-Inf - Replace Telemetry Outstations | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-12-07 | 2021-10-11 | 2022-05-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6333 | 6333 | 83667.4 | 0 | 0 | 90000.4 | 0 | 0 | 0 | 0 | 90000.4 | 90601.29 | [5 empty] | N | WWNI | 100%
511641 | Multiple Sites - South - Auto Shutdown on Low Chlorine Pre CCT Feasability Study | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-11 | 2021-09-15 | 2022-04-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 30000 | 0 | 0 | 30130.84 | 0 | 0 | 0 | 0 | 30130.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509205 | Munnoch Reservoir - Investigation Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-10-13 | 2021-02-17 | 2021-10-11 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152349 | 152349 | 76749.65 | 0 | 0 | 229098.65 | 0 | 0 | 0 | 0 | 229098.65 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503091 | Murray TWP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 | 2020-12-07 | 2020-12-07 | 2021-02-02 | 2021-02-26 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 16137.21 | 897.38 | 4743.25 | -21600.61 | 177.23 | 16130.29 | 0 | 0 | 16307.52 | 0 | 0 | 0 | 0 | 16307.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502614 | Murrayshall Scone Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 |  | Perth and Kinross | 0 | 0 | 0 | 3696.28 | 27494.71 | 10969.45 | 0 | 0 | 42160.44 | 0 | 0 | 0 | 42160.44 | 0 | 0 | 0 | 0 | 42160.44 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500249 | Myreside to Morham Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2015-06-09 | 2019-03-20 | 2019-04-29 | 2021-01-15 |  | East Lothian | 0 | 0 | 65357 | 55269.08 | 97403.45 | 258941.77 | 1504642.54 | 288696.68 | 2270310.52 | 0 | 0 | 0 | 2270310.52 | 0 | 0 | 0 | 0 | 2270310.52 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504588 | N TWS & WTW sample tap investigations & resolution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-02-07 | 2020-12-18 | 2021-03-08 | 2023-11-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3962.59 | 188398.77 | 192361.36 | 915992.88 | 0 | 0 | 1108354.24 | 0 | 0 | 0 | 0 | 1108354.24 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
501665 | N Uist - Ashdail Cottages Sewer Rehab - Replace PF sewers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater | SEPA | SWD | Wastewater infrastructure | MS2 | 2016-08-31 | 2017-03-27 | 2027-07-08 | 2027-04-01 | 2027-04-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 17170.11 | 3623.98 | 0 | 3977.24 | -3977.24 | 20794.09 | 119211.75 | 0 | 0 | 140005.84 | 0 | 0 | 0 | 0 | 140005.84 | 209381.79 | [5 empty] | Y | CM_WWI | 100% | [67 empty] | 0
505110 | N/W/NI/100220-Aultbea WTW- Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-02-19 | 2020-11-09 | 2020-11-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1174.04 | 2275.34 | 3449.38 | 0 | 0 | 0 | 3449.38 | 0 | 0 | 0 | 0 | 3449.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506410 | N/W/NI/300420- Ullapool WTW SCADA Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-05-11 | 2020-07-27 | 2020-12-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209.82 | 2209.82 | 0 | 0 | 0 | 2209.82 | 0 | 0 | 0 | 0 | 2209.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505148 | N/W/NI-100220-Multiple North Sites- Outstation Replacements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS2 |  | 2020-02-17 | 2021-07-12 | 2022-03-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3207.22 | 27812.79 | 31020.01 | 124890 | 0 | 0 | 155910.01 | 0 | 0 | 0 | 0 | 155910.01 | 306661.32 | [5 empty] | N | CM_WWNI | 100%
504277 | N_W_NI_101219_Colonsay WTW_Audit risks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2019-12-16 | 2021-05-01 | 2021-03-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2526.71 | 34174.22 | 36700.93 | 0 | 0 | 0 | 36700.93 | 0 | 0 | 0 | 0 | 36700.93 | 119022.58 | [5 empty] | N | WSNI | 100%
501175 | N179 Merchant Quarter Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2016-10-17 | 2018-08-13 | 2018-08-20 | 2018-08-22 | 2018-08-22 | Aberdeen City | 0 | 0 | 26930 | 454433.2 | -118577.2 | -354921.46 | 1388.61 | 0 | 9253.15 | 0 | 0 | 0 | 9253.15 | 0 | 0 | 0 | 0 | 9253.15 | 175086.76 | [5 empty] | N | FL_DD | 100%
500162 | Nairn DOA (DOA000470) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-23 | 2017-12-21 | 2018-03-29 | Highland | 0 | 0 | 45798 | 145814 | 67183 | -2328.05 | 0 | 0 | 256466.95 | 0 | 0 | 0 | 256466.95 | 0 | 0 | 0 | 0 | 256466.95 | 4617.88 | [5 empty] | N | EC01G | 41.75% | CS16D | 58.25%
503264 | Nairn Moss Side Road Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2018-06-26 | 2018-08-27 | 2018-09-24 | 2019-09-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 475300.84 | 50485.05 | -5181.38 | 520604.51 | 0 | 0 | 0 | 520604.51 | 0 | 0 | 0 | 0 | 520604.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500188 | Nairn odour (STW003728) | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater | SEPA | SWD | Odour | MS7 | 2015-03-16 | 2015-06-26 | 2015-06-29 | 2015-06-30 | 2015-06-30 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | CS2 | 100% | [46 empty] | 1 | [20 empty] | 0
46359 | Nairn WWTP Refurb - STW001283 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-28 | 2012-01-17 | 2011-10-10 | 2013-05-08 |  | Highland | 1214920.55 | 0 | -364.04 | 0 | 0 | 0 | 0 | 0 | -364.04 | 0 | 0 | 0 | 1214556.51 | 0 | 0 | 0 | 0 | 1214556.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500586 | Nairn WWTW - Ventilation Project | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-06-19 | 2015-07-24 | 2015-08-31 | 2015-12-10 |  | Highland | 0 | 0 | 254887.96 | 0 | 0 | 0 | 0 | 0 | 254887.96 | 0 | 0 | 0 | 254887.96 | 0 | 0 | 0 | 0 | 254887.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504628 | Nam Bat DSR Power Supply | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-15 | 2021-01-11 | 2022-04-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3504.76 | 61863.24 | 65368 | 20280.62 | 0 | 0 | 85648.62 | 0 | 0 | 0 | 0 | 85648.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403425 | National Operations Centre - Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-04-30 | 2013-04-30 | 2013-05-02 | 2015-07-27 |  | Scottish Water Wide | 5296295.2 | 0 | -2547.01 | 0 | 5433 | 0 | 0 | 0 | 2885.99 | 0 | 0 | 0 | 5299181.19 | 0 | 0 | 0 | 0 | 5299181.19 | 306661.32 | [5 empty] | N | CM_M&G | 100%
508589 | NE Private Water Supplies | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2020-12-14 | 2021-01-08 | 2021-02-24 | 2021-12-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25250 | 25250 | 99749.94 | 0 | 0 | 124999.94 | 0 | 0 | 0 | 0 | 124999.94 | 119022.58 | [5 empty] | N | CM_WSI | 100%
501015 | NE176 - Kings Gate Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2018-01-29 | 2019-02-12 | 2019-04-08 | 2019-07-30 | 2019-07-30 | Aberdeen City | 0 | 0 | 38030 | 24065.42 | 33343.78 | 138118.8 | 276543.16 | 2181.84 | 512283 | 0 | 0 | 0 | 512283 | 0 | 0 | 0 | 0 | 512283 | 180449.74 | [5 empty] | N | FL_DD | 100%
503289 | NE179 Merchant Quarter Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS1 | 2020-02-18 | 2021-07-26 | 2022-01-10 | 2022-12-23 | 2023-03-27 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 543000 | 914286.92 | 812330.5 | 2269617.42 | 3667578.58 | 0 | 0 | 5937196 | 0 | 0 | 0 | 0 | 5937196 | 175086.76 |  |  |  |  | 3020.0003 | N | FL_DD | 100%
501636 | NE18 - Marshall Place Scott Street Perth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-01-19 | 2022-05-30 | 2022-08-01 | 2023-07-14 | 2023-09-29 | Perth and Kinross | 0 | 0 | 21530 | 794.22 | 1675.78 | 9000 | 20227.27 | 16016.73 | 69244 | 530756.42 | 0 | 0 | 600000.42 | 0 | 0 | 0 | 0 | 600000.42 | 175086.76 | [5 empty] | N | FL_DD | 100%
500747 | NE188 - Fiskens Kia Queenswell Road Forfar - NR | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater | SW | SWD | Flooding Demand Driven | MS7 | 2020-01-06 | 2020-01-15 | 2020-03-17 | 2020-01-22 | 2021-04-01 | Angus | 0 | 0 | 22000 | 37647.26 | 16790.45 | 26562.29 | -102999 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 180449.74 | [5 empty] | N | FL_DD | 100%
502348 | NE205 Brunswick Place Aberdeen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-04-26 | 2023-01-27 | 2023-04-28 | 2024-01-18 | 2024-04-18 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 105000 | 152919.69 | 40651.34 | 298571.03 | 719567.97 | 0 | 0 | 1018139 | 0 | 0 | 0 | 0 | 1018139 | 175086.76 | [5 empty] | N | FL_DD | 100%
500746 | NE21 - Church Street-Feus Road Perth - NR | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-09-10 | 2022-07-26 | 2022-10-19 | 2023-05-22 | 2023-08-14 | Perth and Kinross | 0 | 0 | 23000 | 31382.88 | 16580.8 | 48606.61 | 20033.1 | 51847.61 | 191451 | 458549.17 | 0 | 0 | 650000.17 | 0 | 0 | 0 | 0 | 650000.17 | 180449.74 | [5 empty] | N | FL_DD | 100%
502347 | NE210 5-7 Main Road Cardenden Lochgelly | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-01-16 | 2019-01-16 | Fife | 0 | 0 | 0 | 0 | 22000 | -16737.42 | 6243.19 | 0 | 11505.77 | 0 | 0 | 0 | 11505.77 | 0 | 0 | 0 | 0 | 11505.77 | 180449.74 | [5 empty] | N | FL_DD | 100%
502889 | NE223 South Street Perth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-02-16 | 2022-12-30 | 2023-03-27 | 2023-11-01 | 2024-01-18 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 52000 | 17923.05 | 63005.81 | 132928.86 | 167071.14 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 175086.76 | [5 empty] | N | FL_DD | 100%
500500 | NE235 - Mercat Centre and Esplanade Kirkcaldy | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-08-12 | 2019-08-12 | 2019-07-18 | 2019-07-18 | 2019-07-18 | Fife | 0 | 0 | 20500 | 4681.78 | 29818.22 | 11000 | -46402.2 | 0 | 19597.8 | 0 | 0 | 0 | 19597.8 | 0 | 0 | 0 | 0 | 19597.8 | 279997.17 | [5 empty] | N | FL_NAMED | 100%
501018 | NE244 - Bayview Court Seatown Cullen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-11-27 | 2019-04-11 | 2019-04-11 | 2019-01-16 | 2018-01-16 | Moray | 0 | 0 | 26893 | 39072.99 | 38223.01 | -104188 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 180449.74 | [5 empty] | N | FL_DD | 100%
500677 | NE261 - Albert Street Dundee | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-23 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | Dundee City | 0 | 0 | 42930 | 12119.4 | -55049.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | FL_DD | 100%
503602 | NE297 - Lochside Road Forfar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-07-06 | 2023-02-13 | 2023-06-16 | 2025-01-09 | 2025-03-04 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 16840.55 | 10159.45 | 27000 | 54694.02 | 0 | 0 | 81694.02 | 0 | 0 | 0 | 0 | 81694.02 | 175086.76 | [5 empty] | N | FL_DD | 100%
500089 | NE347 - Links Street Kirkcaldy | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-04-08 | 2019-04-08 | 2019-04-08 | 2019-01-21 | 2019-01-21 | Fife | 0 | 0 | 10025 | 13092.19 | 17132.81 | -40249 | 5818.25 | 0 | 5819.25 | -5818.25 | -5818.25 | -8076.7215 | 1 | -2258.4715 | 0 | 0 | -2258.4715 | -2257.4715 | 1834034.34 | [5 empty] | N | FL_NAMED | 100%
502890 | NE531 Dundonald Street Dundee | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-06-29 | 2022-05-24 | 2022-08-05 | 2023-03-09 | 2023-06-09 | Dundee City | 0 | 0 | 0 | 0 | 0 | 81000 | 19000 | 0 | 100000 | 19999.98 | 0 | 0 | 119999.98 | 0 | 0 | 0 | 0 | 119999.98 | 175086.76 | [5 empty] | N | FL_DD | 100%
500998 | NE538 - Peel Cottage Station Road Longforgan Dundee | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS4 | 2019-07-11 | 2020-03-31 | 2020-10-05 | 2021-02-24 | 2021-04-01 | Perth and Kinross | 0 | 0 | 22430 | 32002.89 | 45567.11 | 43000 | 153282 | 343903 | 640185 | 3654 | 0 | 0 | 643839 | 0 | 0 | 0 | 0 | 643839 | 180449.74 | [5 empty] | N | FL_DD | 100%
503697 | NE60 Cavendish Avenue area Perth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-09-10 | 2023-05-25 | 2023-09-27 | 2025-04-22 | 2025-06-13 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 12067.27 | 20514.73 | 32582 | 1167417.84 | 0 | 0 | 1199999.84 | 0 | 0 | 0 | 0 | 1199999.84 | 106252.93 | [5 empty] | N | FL_DD | 100%
501254 | NE707 - Loch Leven Fisheries Pier Road Kinross | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2017-08-07 | 2018-01-29 | 2018-01-30 | 2018-02-08 | 2018-02-08 | Perth and Kinross | 0 | 0 | 29930 | 24915.34 | 10650.49 | -65375.98 | 0 | 0 | 119.85 | 0 | 0 | 0 | 119.85 | 0 | 0 | 0 | 0 | 119.85 | 42315.92 | [5 empty] | N | FL_NAMED | 100%
500656 | NE8 - Dundee Loan Forfar | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2016-11-21 | 2016-11-21 | 2016-11-18 | 2016-06-28 | 2016-11-18 | Scottish Water Wide | 0 | 0 | 60770 | -60770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CS11 | 100%
502888 | NE85 Lynedoch Road | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2019-09-24 | 2019-09-24 | 2019-08-14 | 2019-08-14 | 2019-08-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 61000 | -60999 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | [5 empty] | N | CS11A | 100%
503726 | Neilston and Uplawmoor Rd - Neilston High DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-10-03 | 2020-07-31 | 2020-08-03 | 2021-10-06 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 88899.52 | 1163290.48 | 1252190 | 498808.76 | 0 | 0 | 1750998.76 | 0 | 0 | 175100.24 | 175100.24 | 1926099 | 311236.79 |  |  | 3287238.65 |  |  | N | CM_WSI | 100%
502971 | Neilston Main Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-04-01 | 2028-01-26 | 2028-04-27 | 2029-05-23 |  | Glasgow City | 0 | 0 | 0 | 0 | 24867.85 | 7699.07 | 22497.67 | -16192.66 | 38871.93 | 2161127.98 | 0 | 0 | 2199999.91 | 0 | 0 | 0 | 0 | 2199999.91 | 311236.79 | [5 empty] | N | CM_WSI | 100%
30535 | Neilston STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-15 | 2015-03-12 | 2015-03-12 | 2015-03-12 | 2015-03-12 | East Renfrewshire | 962475.53 | 0 | 1008 | 0 | 0 | 0 | 0 | 0 | 1008 | 0 | 0 | 0 | 963483.53 | 0 | 0 | 0 | 0 | 963483.53 | 28761.13 | [5 empty] | N | EC04A | 100%
500026 | Neilston WOA Neilston Low CWT WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-23 | 2016-08-01 | 2016-09-12 | 2017-05-17 |  | Glasgow City | 332.03 | 0 | 75903.97 | 470076 | 51298 | 19882.82 | 1159.38 | 0 | 618320.17 | 0 | 0 | 0 | 618652.2 | 0 | 0 | 0 | 0 | 618652.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502137 | Neilston WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-24 | 2016-07-06 | 2016-07-07 | 2016-09-30 | 2016-09-30 | East Renfrewshire | 0 | 0 | 0 | 3069.53 | 245.28 | 0 | 0 | 0 | 3314.81 | 0 | 0 | 0 | 3314.81 | 0 | 0 | 0 | 0 | 3314.81 | 4434.64 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
503135 | Neilston WTW - New Service Reservoir | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-04-01 | 2028-06-07 | 2028-10-09 | 2029-05-21 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 8447.47 | 39986.78 | 3852.88 | 52287.13 | 228712.88 | 0 | 0 | 281000 | 0 | 0 | 0 | 0 | 281000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401917 | Neilston WTW Closure Strategic Solution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-02-04 | 2011-12-20 | 2012-02-20 | 2014-11-05 | 2014-11-05 | East Renfrewshire | 4082651.78 | 0 | 130122.58 | 122432.28 | -111378.87 | -68996.14 | 144.23 | 0 | 72324.08 | 0 | 0 | 0 | 4154975.86 | 0 | 0 | 0 | 0 | 4154975.86 | 357067.75 | [5 empty] | N | CM_WSNI | 100%
45641 | Neilston WTW Refurb - WTW000188 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-24 | 2011-06-30 | 2011-06-30 | 2011-03-31 |  | East Renfrewshire | 232473.21 | 0 | 6341.81 | 0 | 0 | 0 | 0 | 0 | 6341.81 | 0 | 0 | 0 | 238815.02 | 0 | 0 | 0 | 0 | 238815.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403937 | Neilston WwTW | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS5 | 2009-05-15 | 2016-08-31 | 2017-02-27 | 2018-11-29 | 2019-03-13 | East Renfrewshire | 144852 | 0 | 312945 | 836831.9 | 3770911.19 | 1156812.64 | -45641.81 | -33215.92 | 5998643 | 0 | 0 | 0 | 6143495 | 0 | 0 | 0 | 0 | 6143495 | 90601.29 | [5 empty] | N | EC04A | 24.92% | EC10A | 24.92% | CM_WWNI | 50.16%
503315 | Neilston WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-21 | 2029-06-21 | 2030-06-19 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 18173.47 | 5892.6 | -0.07 | 24066 | 0 | 0 | 0 | 24066 | 0 | 0 | 0 | 0 | 24066 | 122419.09 | [5 empty] | N | SG1 | 100%
503968 | Neilston WwTW - RAS & Interstage Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 | 2019-12-19 | 2021-01-29 | 2021-05-06 | 2021-12-22 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 4531.54 | 188496.46 | 193028 | 556972.07 | 0 | 0 | 750000.07 | 0 | 0 | 0 | 0 | 750000.07 | 209381.79 | [5 empty] | N | Ww3 | 100%
502603 | Ness Castle and Ness Side - Strategic Water Supply Infrastructure (Inverness) | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS5 | 2017-10-19 | 2017-10-19 | 2018-04-02 | 2018-10-25 | 2018-10-25 | Highland | 0 | 0 | 0 | 0 | 284154.57 | -13639.18 | 0 | 0 | 270515.39 | 0 | 0 | 0 | 270515.39 | 0 | 0 | 0 | 0 | 270515.39 | 444766.03 | [5 empty] | N | WG5 | 100%
400115 | Ness Cluster 2 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-23 | 2012-09-21 | 2012-10-22 | 2013-06-10 |  | Na H-Eileanan an Iar | 465006 | 0 | -1896.05 | 0 | 0 | 0 | 0 | 0 | -1896.05 | 0 | 0 | 0 | 463109.95 | 0 | 0 | 0 | 0 | 463109.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400117 | Ness Cluster 4 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-23 | 2012-09-14 | 2012-10-31 | 2013-08-05 |  | Na H-Eileanan an Iar | 928392 | 0 | -1214.42 | 0 | 0 | 0 | 0 | 0 | -1214.42 | 0 | 0 | 0 | 927177.58 | 0 | 0 | 0 | 0 | 927177.58 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400118 | Ness Cluster 5 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-23 | 2011-12-23 | 2012-01-18 | 2017-02-01 |  | Na H-Eileanan an Iar | 213643 | 0 | -8751 | 52905.9 | 6642.99 | -778.4 | 0 | 0 | 50019.49 | 0 | 0 | 0 | 263662.49 | 0 | 0 | 0 | 0 | 263662.49 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403649 | Ness Side Developments Inverness Strategic Wastewater Solution | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2014-01-13 | 2014-02-06 | 2014-02-06 | 2017-11-16 | 2017-11-16 | Highland | 495024 | 0 | 0 | -456353.52 | -11251.95 | -281.28 | 0 | 0 | -467886.75 | 0 | 0 | 0 | 27137.25 | 0 | 0 | 0 | 0 | 27137.25 | 0 | [5 empty] | N | SG5 | 100%
502134 | Ness WTW WQ SRs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-24 | 2016-03-29 | 2016-03-29 | 2016-07-31 | 2016-09-30 | Na H-Eileanan an Iar | 0 | 0 | 65.42 | 104.82 | 196.68 | 0 | 0 | 0 | 366.92 | 0 | 0 | 0 | 366.92 | 0 | 0 | 0 | 0 | 366.92 | 1530909.4 | [5 empty] | Y | DW25P | 100% | [22 empty] | 1 | [44 empty] | 0
502040 | NETCOM Foundations Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2018-03-28 |  | Scottish Water Wide | 0 | 0 | 508698 | 511912.53 | 353424.25 | -1809.01 | 0 | 0 | 1372225.77 | 0 | 0 | 0 | 1372225.77 | 0 | 0 | 0 | 0 | 1372225.77 | 306661.32 | [5 empty] | N | CM_M&G | 100%
504966 | Nethan Bridge Camps TM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-12-23 | 2023-11-09 | 2024-04-18 | 2025-10-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2500.92 | 69252.14 | 71753.06 | 2928464.76 | 0 | 0 | 3000217.82 | 0 | 0 | 0 | 0 | 3000217.82 | 311236.79 | [5 empty] | N | WSI | 100%
502540 | Nether Knox Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-02-02 | 2017-11-17 | 2018-05-29 | 2019-05-09 |  | Angus | 0 | 0 | 0 | 440.51 | 5525.79 | 16314.4 | 3766.64 | 0 | 26047.34 | 0 | 0 | 0 | 26047.34 | 0 | 0 | 0 | 0 | 26047.34 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500050 | Nether Knox WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-07-27 | Aberdeenshire | 0 | 0 | 32482.18 | 24117.86 | 7.41 | 0 | 0 | 0 | 56607.45 | 0 | 0 | 0 | 56607.45 | 0 | 0 | 0 | 0 | 56607.45 | 122419.09 | [5 empty] | N | SG1 | 100%
30537 | Netherburn STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS6 | 2008-07-15 | 2012-09-05 | 2012-10-29 | 2018-04-30 | 2016-02-24 | South Lanarkshire | 2223247.7 | 0 | 90421.38 | 127647.15 | 1368310.28 | -277272.29 | 347102.89 | -50776.11 | 1605433.3 | 177448.44 | 177448.44 | 246328.6446 | 4006129.44 | 68880.2046 | 0 | 0 | 68880.2046 | 4075009.6446 | 28761.13 | [5 empty] | N | EC04A | 100%
503923 | Nethermains WwPS - Abandonment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2019-12-05 |  | 2022-04-06 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 35643.93 | 43983.07 | 79627 | 0 | 0 | 0 | 79627 | 0 | 0 | 0 | 0 | 79627 | 209381.79 | [5 empty] | N | Ww3 | 100%
500811 | Network Model Building Developer Support (Waste) | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS3 | 2015-09-28 | 2015-12-21 | 2015-12-21 | 2022-06-06 |  | Scottish Water Wide | 0 | 0 | 193828 | 338947.83 | 197548.17 | 201000 | 334241 | 687526.92 | 1953091.92 | 552435 | 0 | 0 | 2505526.92 | 0 | 0 | 0 | 0 | 2505526.92 | 1470767.03 | [5 empty] | N | SG5 | 100%
500895 | Network Model Building Developer Support (Water) | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS3 | 2015-09-24 | 2015-12-23 | 2015-12-24 | 2021-10-22 |  | Scottish Water Wide | 0 | 0 | 32570 | 18868 | 220224.54 | 506228.26 | 1003809.3 | 1270381.54 | 3052081.64 | 145918.36 | 0 | 0 | 3198000 | 0 | 0 | 0 | 0 | 3198000 | 444766.03 | [5 empty] | N | WG5 | 100%
401391 | Network Model Building Developer Support Wastewater | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2010-09-15 | 2011-03-18 | 2011-03-18 | 2015-08-20 | 2015-10-28 | Scottish Water Wide | 287479 | 0 | 12986 | 1412.92 | 0 | 0 | 0 | 0 | 14398.92 | 0 | 0 | 0 | 301877.92 | 0 | 0 | 0 | 0 | 301877.92 | 0 | [5 empty] | N | SG5 | 100%
401392 | Network Model Building Developer Support Water | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2010-09-24 | 2011-03-17 | 2011-03-17 | 2015-08-24 | 2015-10-28 | Scottish Water Wide | 178070 | 0 | 11940.06 | 713.91 | 0 | 0 | 0 | 0 | 12653.97 | 0 | 0 | 0 | 190723.97 | 0 | 0 | 0 | 0 | 190723.97 | 0 | [5 empty] | N | WG5 | 100%
401951 | Network Model Data Management - FTP Setup | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2011-03-21 | 2018-01-29 | 2018-01-29 | 2018-01-29 |  | Scottish Water Wide | 36.59 | 0 | 3463.41 | 0 | -100.31 | 0 | 0 | 0 | 3363.1 | 0 | 0 | 0 | 3399.69 | 0 | 0 | 0 | 0 | 3399.69 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402000 | Network Model Data Management - HYRAD Development | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2011-03-21 | 2020-02-14 | 2020-02-14 | 2020-02-14 |  | Scottish Water Wide | 42269.05 | 0 | 17730.95 | 0 | -17730.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42269.05 | 0 | 0 | 0 | 0 | 42269.05 | 0 | [5 empty] | N | CM_WWI | 100%
45564 | Network Non-Sanitary License (Essential) Requirements | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-01 | 2011-09-21 | 2011-09-23 | 2015-03-31 | 2015-05-29 | Scottish Water Wide | 4569041.04 | 0 | 7238.54 | -6011.41 | 372.15 | 0 | 0 | 0 | 1599.28 | 0 | 0 | 0 | 4570640.32 | 0 | 0 | 0 | 0 | 4570640.32 | 28761.13 | [5 empty] | N | WQ01B | 100%
500592 | Networks and Communications Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-14 | 2016-06-30 | 2016-06-30 | 2018-03-28 |  | Scottish Water Wide | 0 | 0 | 213349 | 380145.06 | 290162.9 | 0 | 0 | 0 | 883656.96 | 0 | 0 | 0 | 883656.96 | 0 | 0 | 0 | 0 | 883656.96 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500993 | New Aberdour WWTW - screen replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-10-07 | 2016-10-27 | 2017-03-17 | 2017-11-24 |  | Aberdeenshire | 0 | 0 | 2127 | 14132 | 56241 | 0 | 0 | -955.73 | 71544.27 | -0.02 | 0 | 0 | 71544.25 | 0 | 0 | 0 | 0 | 71544.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500164 | New Cumnock DOA (DOA000138) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-09 | 2018-03-12 | 2018-03-12 | East Ayrshire | 0 | 0 | 41549 | 82887 | 17760 | 12584.16 | 0 | 0 | 154780.16 | 0 | 0 | 0 | 154780.16 | 0 | 0 | 0 | 0 | 154780.16 | 72047.27 | [5 empty] | N | CS11 | 100%
500167 | New Galloway DOA (DOA001211) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-06-21 | 2016-09-07 | 2019-06-30 | 2019-09-30 | Dumfries and Galloway | 0 | 0 | 10409 | 12925 | 12502 | 52000 | -1105.04 | 0 | 86730.96 | 0 | 0 | 0 | 86730.96 | 0 | 0 | 0 | 0 | 86730.96 | 82660.07 | [5 empty] | Y | EC01G | 7.63% | EC01D | 92.37% | [38 empty] | 1 | [26 empty] | 0
502816 | New Galloway ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2027-04-01 | 2027-04-01 | 2020-08-28 | 2020-08-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 77047.47 | 27924.53 | 2236.26 | 744.08 | 107952.33 | 0 | 0 | 0 | 107952.33 | 0 | 0 | 0 | 0 | 107952.33 | 122419.09 | [5 empty] | N | SG1 | 100%
403330 | New Road - Stirling Road Milnathort | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2013-02-18 | 2016-02-15 | 2016-02-16 | 2016-07-18 | 2016-07-18 | Perth and Kinross | 196881 | 196881 | 1267417 | 58388.33 | -1686.33 | -15926.94 | 0 | 0 | 1308192.06 | 0 | 0 | 0 | 1505073.06 | 0 | 0 | 0 | 0 | 1505073.06 | 474995.67 | [5 empty] | N | FL_NAMED | 100%
511494 | New SR-TM Meters RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-23 | 2023-02-16 | 2024-01-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13607.48 | 13607.48 | 194392.52 | 0 | 0 | 208000 | 0 | 0 | 0 | 0 | 208000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501664 | New Valley Stornoway Phase 1 Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-22 | 2017-03-22 | 2017-06-12 | 2017-09-11 |  | Na H-Eileanan an Iar | 0 | 0 | 1267 | 20969.46 | 69556.02 | 0 | 0 | 0 | 91792.48 | 0 | 0 | 0 | 91792.48 | 0 | 0 | 0 | 0 | 91792.48 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500166 | Newbie DOA (DOA002071) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-20 | 2015-09-27 | 2017-03-01 | 2017-04-14 | 2017-04-14 | Dumfries and Galloway | 0 | 0 | 15244 | -4313.77 | -2077.22 | 0 | 0 | 0 | 8853.01 | 0 | 0 | 0 | 8853.01 | 0 | 0 | 0 | 0 | 8853.01 | 558366.35 | [5 empty] | N | CS15 | 49.17% | CS11 | 50.83%
503372 | Newburgh WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-08-02 | 2025-06-02 | 2025-09-01 | 2026-09-25 |  | Fife | 0 | 0 | 0 | 0 | 0 | 76428.31 | 5134.2 | 0.49 | 81563 | 1918437.48 | 0 | 0 | 2000000.48 | 0 | 0 | 0 | 0 | 2000000.48 | 122419.09 | [5 empty] | N | SG1 | 100%
502408 | Newburgh WwTW - SR15 CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2021-05-21 | 2023-02-22 | 2023-05-25 | 2024-03-27 |  | Fife | 0 | 0 | 0 | 13934.19 | 13400.57 | 28252.3 | 9641.82 | 343.12 | 65572 | 296739.49 | 0 | 0 | 362311.49 | 0 | 0 | 0 | 0 | 362311.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
45718 | Newcastleton WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-19 | 2011-07-28 | 2011-10-17 | 2016-03-17 | 2016-03-30 | Scottish Borders | 3066864.75 | 0 | 435815.96 | 108168.08 | -9281.89 | -6038.32 | 0 | 0 | 528663.83 | 0 | 0 | 0 | 3595528.58 | 0 | 0 | 0 | 0 | 3595528.58 | 28761.13 |  |  |  |  | 29173.6326 | N | DW23 | 100%
503106 | Newfield Trunk Main Reinforcement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2018-05-17 | 2019-08-27 | 2019-11-11 | 2021-03-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 95443.07 | 925071.09 | 495364.05 | 1515878.2 | 77736.25 | 0 | 0 | 1593614.45 | 0 | 0 | 56385.55 | 56385.55 | 1650000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511958 | Newlands Glen Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-12-02 | 2023-06-12 | 2023-09-08 | 2024-08-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 599799.95 | 0 | 0 | 599999.95 | 0 | 0 | 0 | 0 | 599999.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500731 | Newmachar WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS1 | 2017-08-18 | 2021-06-04 | 2021-07-12 | 2023-03-20 |  | Aberdeenshire | 0 | 0 | 21155.09 | 89337.45 | 211089.81 | 389838.85 | 298899.05 | 383192.46 | 1393512.71 | 4138759 | 0 | 0 | 5532271.71 | 0 | 0 | 0 | 0 | 5532271.71 | 213020.38 | [5 empty] | N | CM_WWNI | 3% | SG1 | 97%
501694 | Newmains River Crossings | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-03-29 | 2020-02-11 | 2020-07-27 | 2021-07-20 |  | North Lanarkshire | 0 | 0 | 0 | 46991.03 | 65450.97 | 195173 | 849291.26 | 2191621.82 | 3348528.08 | 1219027 | 0 | 0 | 4567555.08 | 0 | 0 | 101865.92 | 101865.92 | 4669421 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506395 | Newmill WWTW Demolition investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-06-15 | 2020-08-12 | 2020-09-01 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6040.43 | 6040.43 | 0 | 0 | 0 | 6040.43 | 0 | 0 | 0 | 0 | 6040.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500208 | Newmore - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2018-06-27 | 2018-06-29 | 2019-02-28 | 2020-01-31 | Highland | 0 | 0 | 6891 | -5257.45 | 36980.45 | 116586.55 | -14384.8 | -258.9 | 140556.85 | 0 | 0 | 0 | 140556.85 | 0 | 0 | 0 | 0 | 140556.85 | 960709.78 | [5 empty] | Y | DW5 | 100% | [19 empty] | 1 | [47 empty] | 0
507489 | Newmore Actiflow and BPT Health and Safety improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-08 | 2021-07-12 | 2021-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9835.38 | 9835.38 | 189891.38 | 0 | 0 | 199726.76 | 0 | 0 | 0 | 0 | 199726.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500705 | Newmore Raw Main Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-07-10 | 2015-07-30 | 2015-08-11 | 2016-01-01 |  | Highland | 0 | 0 | 705064.64 | 0 | 0 | 0 | 0 | 0 | 705064.64 | 0 | 0 | 0 | 705064.64 | 0 | 0 | 0 | 0 | 705064.64 | 311236.79 | [5 empty] | N | CM_M&G | 100%
505287 | Newmore Raw water losses investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-02-23 | 2020-12-04 | 2021-05-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 456.28 | 17314.08 | 17770.36 | 7317.9 | 0 | 0 | 25088.26 | 0 | 0 | 0 | 0 | 25088.26 | 119022.58 | [5 empty] | N | CM_WSI | 100%
500866 | Newmore RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-08 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 0 | 6715.98 | 4512.65 | 934.8 | -805.05 | 0 | 0 | 11358.38 | 0 | 0 | 0 | 11358.38 | 0 | 0 | 0 | 0 | 11358.38 | 514358.04 | [5 empty] | N | DW5FS | 100%
506308 | Newmore sludge tank removal | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-01 | 2021-03-08 | 2021-06-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47563 | 47563 | 900 | 0 | 0 | 48463 | 0 | 0 | 0 | 0 | 48463 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512183 | Newmore TWP - MCC Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-04-04 | 2023-10-11 | 2024-01-09 | 2024-12-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000.04 | 0 | 0 | 950000.04 | 0 | 0 | 0 | 0 | 950000.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506263 | Newmore WOA RWM Diversion | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-12-10 | 2023-02-09 | 2023-07-06 | 2024-09-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20523 | 20523 | 906077.06 | 0 | 0 | 926600.06 | 0 | 0 | 0 | 0 | 926600.06 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501370 | Newmore WOA Lamington PS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-05-11 | 2020-07-14 | 2028-02-04 | 2020-08-11 |  | Highland | 0 | 0 | 0 | 81345.57 | 3191.68 | 0 | -14290.59 | 5392.09 | 75638.75 | 0 | 0 | 0 | 75638.75 | 0 | 0 | 0 | 0 | 75638.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502757 | Newmore WTW- Caustic and Alum Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-05-23 | 2017-08-29 | 2017-09-18 | 2020-03-17 |  | Highland | 0 | 0 | 0 | 0 | 1045148.6 | 476227.71 | 144739.44 | 3772.25 | 1669888 | 4818.06 | 0 | 0 | 1674706.06 | 0 | 0 | 0 | 0 | 1674706.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506250 | Newmore WTW filter media refurbishment phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-04-22 | 2021-03-19 | 2021-03-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51847 | 51847 | -13268.81 | 0 | 0 | 38578.19 | 0 | 0 | 0 | 0 | 38578.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503206 | Newmore WTW Filtralite Media Change | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-05-14 | 2020-05-14 | 2020-05-15 | 2020-06-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 21094.27 | 7468.05 | -26480.65 | 2081.68 | 0 | 0 | 0 | 2081.68 | 0 | 0 | 0 | 0 | 2081.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402067 | Newmore WTW Long Blue Pipe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-05-04 | 2011-12-21 | 2012-01-30 | 2013-12-03 |  | Highland | 142274 | 0 | -185.6 | 0 | 0 | 0 | 0 | 0 | -185.6 | 0 | 0 | 0 | 142088.4 | 0 | 0 | 0 | 0 | 142088.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401343 | Newport WSZ Low Pressure Enhancement WSZ001168 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-02-22 | 2012-08-27 | 2013-11-19 | 2013-03-31 | Fife | 138307.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138307.6 | 0 | 0 | 0 | 0 | 138307.6 | 0 | [6 empty] | CS1 | 100%
401234 | Newstead WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-09-01 | 2015-10-26 | 2016-01-11 | 2018-04-24 | 2018-04-24 | Scottish Borders | 256722 | 0 | 175202 | 623854.82 | 107979.67 | 1600.12 | 161.2 | 0 | 908797.8 | 0 | 0 | 0 | 1165519.8 | 0 | 0 | 0 | 0 | 1165519.8 | 0 | [5 empty] | N | SG1 | 100%
502796 | Newton Avenue (Pipe bridge) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-07-26 | 2017-07-26 | 2018-01-30 | 2018-10-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 236825.81 | 531527.26 | 4898.74 | 0 | 773251.81 | 0 | 0 | 0 | 773251.81 | 0 | 0 | 0 | 0 | 773251.81 | 209381.79 | [5 empty] | N | CM_WWI | 100%
300032 | Newton Stewart WwTW - Sludge and HS | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-05-11 | 2014-04-25 | 2014-11-24 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 499376 | 0 | 767727 | 47798.05 | 374.24 | -113.78 | 0 | 0 | 815785.51 | 0 | 0 | 0 | 1315161.51 | 0 | 0 | 0 | 0 | 1315161.51 | 28761.13 | [5 empty] | N | WQ01 | 100%
501727 | Newtonloan to Dalhousie Castle Trunk Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-07-23 | 2028-06-01 | 2028-08-29 | 2029-03-29 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435821.85 | 0 | 0 | 435821.85 | 0 | 0 | 0 | 0 | 435821.85 | 4989107.96 | [5 empty] | N | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 28.57% | CM_WSI | 47.62%
500068 | Newtown St Boswells WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2017-11-09 | 2020-03-18 | 2020-03-18 | 2021-06-18 |  | Scottish Borders | 0 | 0 | 46006.3 | 20969.55 | 52573.93 | 14567.8 | 212699.22 | 1181469.87 | 1528286.67 | 406.01 | 0 | 0 | 1528692.68 | 0 | 0 | 46307.32 | 46307.32 | 1575000 | 122419.09 | [5 empty] | N | SG1 | 100%
501779 | Nigg and Persley WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2020-01-16 | 2021-02-22 | 2021-04-12 | 2021-09-30 |  | Aberdeenshire | 0 | 0 | 0 | 4186.05 | 80.86 | 0 | 28521.09 | 104410 | 137198 | 368335.96 | 0 | 0 | 505533.96 | 0 | 0 | 0 | 0 | 505533.96 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400284 | Nith Cluster 1 Capital maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-17 | 2012-02-28 | 2012-04-02 | 2013-03-06 |  | South Lanarkshire | 640273 | 0 | 1722 | -1163.97 | 0 | 0 | 0 | 0 | 558.03 | 0 | 0 | 0 | 640831.03 | 0 | 0 | 0 | 0 | 640831.03 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400285 | Nith Cluster 2 Capital Maintenance - Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-17 | 2012-09-21 | 2013-05-28 | 2014-07-07 |  | South Lanarkshire | 428665 | 0 | 13428 | -5899.02 | 0 | 0 | 0 | 0 | 7528.98 | 0 | 0 | 0 | 436193.98 | 0 | 0 | 0 | 0 | 436193.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401499 | Nith Leakage Region New and Replacement Leakage Assets | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2010-10-20 | 2012-06-14 | 2012-08-27 | 2021-01-12 |  | All South Unitary Authorities | 138815 | 0 | 13098 | 12003.59 | 40027.41 | 131792.51 | 25933.85 | -472.36 | 222383 | 4633.34 | 0 | 0 | 365831.34 | 0 | 0 | 0 | 0 | 365831.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401459 | NM CID Cap Maint Completion transfer to SR10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-10-06 | 2011-01-11 | 2011-04-29 | 2018-10-08 |  | Scottish Water Wide | 909744.8 | 0 | 0.2 | -118931.62 | 0 | 0 | 0 | 0 | -118931.42 | 0 | 0 | 0 | 790813.38 | 0 | 0 | 0 | 0 | 790813.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
300011 | NM CID Enviro Completion costs on non migrated projects | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-10-28 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 347516.84 | 0 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0.16 | 0 | 0 | 0 | 347517 | 0 | 0 | 0 | 0 | 347517 | 0 | [5 empty] | N | EC01 | 100%
401461 | NM CID Growth Completion transfer into Sr10 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2010-10-06 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 37133 | 0 | 0 | -3556.16 | 0 | 0 | 0 | 0 | -3556.16 | 0 | 0 | 0 | 33576.84 | 0 | 0 | 0 | 0 | 33576.84 | 0 | [5 empty] | N | SG1 | 100%
401460 | NM SWD Cap Maint Completion transfer into Sr10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-10-01 | 2019-03-28 | 2019-03-28 | 2018-10-08 |  | Scottish Water Wide | 308210.28 | 0 | -0.28 | 0 | 0 | 0 | 0 | 0 | -0.28 | 0 | 0 | 0 | 308210 | 0 | 0 | 0 | 0 | 308210 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401462 | NM SWD Growth Completion transfer into Sr10 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2010-10-01 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 130463 | 0 | 0 | 38949.5 | 0 | 0 | 0 | 0 | 38949.5 | 0 | 0 | 0 | 169412.5 | 0 | 0 | 0 | 0 | 169412.5 | 0 | [5 empty] | N | SG1 | 100%
49602 | NONINF - Investment Profile Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | General |  | NONINF | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | RISK | 100%
402638 | North Area Future Projects Block Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-04-16 | 2012-04-16 | 2012-05-01 | 2015-11-10 |  | All North Unitary Authorities | 42000 | 0 | -41999 | 0 | 0 | 0 | 0 | 0 | -41999 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 311236.79 | [5 empty] | N | CM_WWI | 100%
511108 | North Berwick - Inlet Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780000 | 0 | 0 | 780000 | 0 | 0 | 0 | 0 | 780000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501108 | North Berwick Catchment Study (DAS) | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2017-02-27 | 2017-06-22 | 2018-07-31 | 2019-01-31 | East Lothian | 0 | 0 | 600 | 9728.23 | 31652.77 | 19464 | -169.67 | 0 | 61275.33 | 0 | 0 | 0 | 61275.33 | 0 | 0 | 0 | 0 | 61275.33 | 9787.75 | [5 empty] | Y | EC01D | 100% | [40 empty] | 1 | [26 empty] | 0
500963 | North Berwick WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | East Lothian | 0 | 0 | 87789.66 | 141648.39 | 16435.89 | 1608.74 | 3355.94 | 0 | 250838.61 | 0 | 0 | 0 | 250838.61 | 0 | 0 | 0 | 0 | 250838.61 | 122419.09 | [5 empty] | N | SG1 | 100%
403531 | North Berwick WwTW - Growth - 4035310000 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2015-03-02 | 2015-03-03 | 2015-03-04 | 2015-03-04 | 2015-03-04 | East Lothian | 75343.95 | 0 | 0 | 124.25 | 0 | 82.56 | 0 | 0 | 206.81 | 0 | 0 | 0 | 75550.76 | 0 | 0 | 0 | 0 | 75550.76 | 0 | [5 empty] | N | SG1 | 100%
510933 | North Berwick WWTW - Replacement screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2021-01-29 | 2021-09-13 | 2021-12-09 | 2022-11-16 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 777500.04 | 0 | 0 | 780000.04 | 0 | 0 | 0 | 0 | 780000.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503060 | North Berwick WWTW Intervention Development | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW1 | 2022-03-16 | 2023-12-29 | 2024-04-02 | 2025-03-14 | 2025-06-16 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 1010526.97 | 201604.48 | 77148.55 | 1289280 | 63210 | 0 | 0 | 1352490 | 0 | 17434.9515 | 0 | 17434.9515 | 1369924.9515 | 2205512.72 | [5 empty] | N | EC01A_ID | 100%
507785 | North Building Condition Interventions | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS2 |  | 2020-07-27 | 2022-05-13 | 2022-12-26 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279.92 | 279.92 | 0 | 0 | 0 | 279.92 | 0 | 0 | 0 | 0 | 279.92 | 306661.32 | [5 empty] | N | CM_M&G | 100%
403598 | North CMC Inf SV Delivery | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-09-25 | 2013-09-25 | 2014-01-15 | 2015-01-23 |  | Highland | 14404.92 | 0 | 0 | 0 | 8.84 | 0 | 0 | 0 | 8.84 | 0 | 0 | 0 | 14413.76 | 0 | 0 | 0 | 0 | 14413.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500755 | North Coast SCADA Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS1 | 2016-06-28 | 2021-04-26 | 2021-09-01 | 2023-08-15 |  | Highland | 0 | 0 | 0 | 22086.21 | 67342.95 | 26493.68 | 124446.53 | 372961.07 | 613330.44 | 1615053.54 | 0 | 0 | 2228383.98 | 0 | 0 | 0 | 0 | 2228383.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504791 | North Court Lane Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-01-31 |  | 2020-09-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 64523.81 | -21053.81 | 43470 | 58362 | 0 | 0 | 101832 | 0 | 0 | 0 | 0 | 101832 | 209381.79 | [5 empty] | N | CM_WWI | 100%
404137 | North Harris improvement scheme | Q&S3B | Completion | OMG180 |  |  | Water | DWQR | SWMD | OMG180 | MS6 | 2015-02-06 | 2019-03-20 | 2019-03-20 | 2020-10-31 | 2021-03-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 83414.63 | 2567597.37 | 1584714.83 | 603426.49 | 4839153.32 | 51322.54 | 51322.54 | 71244.423 | 4890475.86 | 19921.883 | 0 | 0 | 19921.883 | 4910397.743 | 4879540 |  |  |  |  | 10991.5 | Y | DW13 | 100% | [20 empty] | 1 | [46 empty] | 0
404097 | North Harris Regional Scheme | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS7 | 2015-02-06 | 2019-01-30 | 2019-01-30 | 2019-01-30 | 2019-01-30 | Na H-Eileanan an Iar | 12804.88 | 0 | 155131.12 | -213593.29 | 45755.63 | 27369.83 | 1511.25 | 0 | 16174.54 | 0 | 0 | 0 | 28979.42 | 0 | 0 | 0 | 0 | 28979.42 | 0 | [5 empty] | N | DW13 | 100%
500927 | North Lanarkshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-03-13 | 2017-03-13 | 2016-12-08 | 2017-03-13 | All West Unitary Authorities | 0 | 0 | 6000 | -452.9 | 0 | 0 | 0 | 0 | 5547.1 | 0 | 0 | 0 | 5547.1 | 0 | 0 | 0 | 0 | 5547.1 | 106252.93 | [5 empty] | N | FL_DD | 100%
501098 | North Lanarkshire Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-09-27 | 2016-09-29 | 2019-08-31 | 2019-08-31 | North Lanarkshire | 0 | 0 | 3934 | 43642.05 | 7223.95 | 26700 | 8500 | 2074.72 | 92074.72 | 0 | 0 | 0 | 92074.72 | 0 | 0 | 0 | 0 | 92074.72 | 0 | [5 empty] | Y | EC10D | 100% | [40 empty] | 2 | [26 empty] | 0
500867 | North Lochs RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS5 | 2016-09-06 | 2018-09-20 | 2018-12-10 | 2019-09-30 | 2020-07-27 | Na H-Eileanan an Iar | 0 | 0 | 4388.67 | 16878.57 | 16737.51 | 166645.22 | 128931.03 | 15498.12 | 349079.12 | 0 | 0 | 0 | 349079.12 | 0 | 0 | 0 | 0 | 349079.12 | 251515.97 | [5 empty] | N | DW5FS | 100%
502552 | North Middleton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-01 | 2018-08-01 | 2018-07-31 | 2018-07-31 | 2018-07-31 | Midlothian | 0 | 0 | 0 | 38756.46 | 20101.52 | -10884.64 | 0 | 0 | 47973.34 | 0 | 0 | 0 | 47973.34 | 0 | 0 | 0 | 0 | 47973.34 | 122419.09 | [5 empty] | N | SG1 | 100%
512040 | North Middleton WWTW - Inlet Screen Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39999.96 | 0 | 0 | 39999.96 | 0 | 0 | 0 | 0 | 39999.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501409 | North Pentland Springs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2027-04-01 | 2028-01-17 | 2028-05-22 | 2028-09-29 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1499709.85 | 0 | 0 | 1499709.85 | 0 | 0 | 0 | 0 | 1499709.85 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511463 | North Repair-Refurb-Replace DMA Meters and Loggers RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-23 | 2021-04-01 | 2022-07-01 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18971.96 | 18971.96 | 271028.04 | 0 | 0 | 290000 | 0 | 0 | 0 | 0 | 290000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505616 | North Res CM Loch Lunndaidh Access Track Repair | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-10 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1079.44 | 0 | 1079.44 | 15420.56 | 0 | 0 | 16500 | 0 | 0 | 0 | 0 | 16500 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501040 | North Ronaldsay WTW Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS3 | 2018-03-30 | 2019-06-28 | 2019-09-30 | 2021-05-18 | 2021-08-18 | Orkney Islands | 0 | 0 | 4293.78 | 11.86 | 8280.65 | 51690.12 | 354656.7 | 437869.84 | 856802.96 | 135298.82 | 135298.824 | 261371.4442 | 992101.78 | 126072.6202 | 0 | 0 | 126072.6202 | 1118174.4002 | 292002.14 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
45035 | North Ronaldsay WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2012-09-11 | 2013-01-21 | 2013-07-11 | 2015-12-15 | Orkney Islands | 229994.37 | 0 | -1068.33 | 0 | 0 | 0 | 0 | 0 | -1068.33 | 0 | 0 | 0 | 228926.04 | 0 | 0 | 0 | 0 | 228926.04 | 28761.13 | [5 empty] | N | DW23 | 100%
402166 | North Taing WWPS Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-09-12 | 2013-06-26 | 2013-08-29 | 2014-06-25 |  | Shetland Islands | 315974 | 0 | 0 | -1845.69 | 0 | 0 | 0 | 0 | -1845.69 | 0 | 0 | 0 | 314128.31 | 0 | 0 | 0 | 0 | 314128.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402175 | North Third Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-11 | 2012-08-29 | 2012-11-16 | 2014-09-16 | 2014-09-16 | Scottish Water Wide | 520747.18 | 0 | 6611.33 | -11908.06 | 0 | 0 | 0 | 0 | -5296.73 | 0 | 0 | 0 | 515450.45 | 0 | 0 | 0 | 0 | 515450.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500482 | North Third Reservoir Hydro Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water | SW | SWMD | Renewable power | MS7 | 2015-05-18 | 2015-06-30 | 2015-08-24 | 2017-03-31 | 2017-03-31 | Stirling | 0 | 0 | 1711983.15 | 165771.85 | 79808.11 | 8120.83 | -27704.27 | 0 | 1937979.67 | 0 | 0 | 0 | 1937979.67 | 0 | 0 | 0 | 0 | 1937979.67 | 1525750.06 | [5 empty] | Y | I2S_WI | 100% | [60 empty] | 0.59 | [6 empty] | 0
507382 | North WTWs - Mitsubishi PLC Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-12-07 | 2024-02-20 | 2024-05-21 | 2026-04-03 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56291.69 | 56291.69 | 5943939.98 | 0 | 0 | 6000231.67 | 0 | 0 | 0 | 0 | 6000231.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507378 | North WTWs - Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-01-03 | 2023-08-28 | 2023-11-27 | 2025-01-14 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20227.62 | 20227.62 | 979772.38 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505048 | Northmavine CWT Inspection | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-11 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1982.75 | 24523.88 | 26506.63 | 33493.37 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 60000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507198 | Northmavine Pump Control Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-06-17 | 2020-09-09 | 2020-10-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18816.33 | 18816.33 | 0 | 0 | 0 | 18816.33 | 0 | 0 | 0 | 0 | 18816.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402698 | Northmavine WSZ Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-07-23 | 2013-07-29 | 2013-09-09 | 2014-04-03 |  | Shetland Islands | 311693 | 0 | 11988.21 | -101.07 | 0 | 0 | 0 | 0 | 11887.14 | 0 | 0 | 0 | 323580.14 | 0 | 0 | 0 | 0 | 323580.14 | 311236.79 | [5 empty] | N | CM_WSI | 100%
33155 | NRSWA - Service Relocate - Edinburgh Tram Lines - Mains Diversion | Q&S4 | Supporting economic development | NRSWA |  |  | General |  | SWMD | NRSWA | MS7 | 2006-01-20 | 2008-07-08 | 2010-04-27 | 2010-05-03 |  | City of Edinburgh | 7867844 | 0 | -250000 | 0 | 0 | 0 | 0 | 0 | -250000 | 0 | 0 | 0 | 7617844 | 0 | 0 | 0 | 0 | 7617844 | 0 | [5 empty] | N | CM_WSI | 50% | CM_WWI | 50%
510133 | NRSWA (Water) Comrie Flood Protection Scheme | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MSU | 2021-04-01 | 2021-07-19 | 2021-08-20 | 2022-07-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 180000 | 38730.22 | [5 empty] | N | CS23W | 100%
401081 | NRSWA C3 Non Rechargeable Sewer Estimates Scotland Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2010-06-24 | 2010-06-24 | 2005-02-21 | 2015-08-28 |  | Scottish Water Wide | 78400 | 0 | -12074.6 | 0 | 0 | 0 | 0 | 0 | -12074.6 | 0 | 0 | 0 | 66325.4 | 0 | 0 | 0 | 0 | 66325.4 | 0 | [5 empty] | N | CM_WWI | 100%
401082 | NRSWA C3 Non Rechargeable Water Estimates Scotland Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2010-06-24 | 2010-06-24 | 2005-02-21 | 2015-08-28 |  | Scottish Water Wide | 316229 | 0 | 26947.1 | 0 | 0 | 0 | 0 | 0 | 26947.1 | 0 | 0 | 0 | 343176.1 | 0 | 0 | 0 | 0 | 343176.1 | 0 | [5 empty] | N | CM_WSI | 100%
400324 | NRSWA C3 Service Relocate Edinburgh Tram Lines Mains Diversion | Q&S4 | Supporting economic development | NRSWA |  |  | General |  | SWMD | NRSWA | MS3 | 2006-01-20 | 2008-06-18 | 2010-12-01 | 2023-04-14 |  | City of Edinburgh | 3635779 | 0 | -73716.56 | 102647.56 | 21628.23 | 45367.77 | 334148.9 | 65805.1 | 495881 | 478788.83 | 0 | 0 | 4610448.83 | 0 | 0 | 0.17 | 0.17 | 4610449 | 0 | [5 empty] | N | SR15_SED_NRSW | 100%
402232 | NRSWA C4 - A92 Courthill to Hawkhill Bends Improvement Angus | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-06-23 |  |  | 2011-12-07 |  | Angus | 2527.26 | 0 | 0 | 0 | 0 | 35.22 | 0 | 0 | 35.22 | 0 | 0 | 0 | 2562.48 | 0 | 0 | 0 | 0 | 2562.48 | 0 | [5 empty] | N | CM_WSI | 100%
402102 | NRSWA C4 - Elgin Flood Scheme | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-04-26 |  |  | 2013-07-10 |  | Moray | 249611.31 | 0 | 83637.89 | 18136.03 | 271.03 | 183.66 | 0 | 0 | 102228.61 | 0 | 0 | 0 | 351839.92 | 0 | 0 | 0 | 0 | 351839.92 | 0 | [5 empty] | N | CM_WWI | 100%
502832 | NRSWA C4 Estimate for C4 Design Only Hawick Flood Scheme | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2017-07-25 | 2018-03-29 | 2018-08-23 | 2022-12-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 45177.25 | 36436.75 | 314.53 | 3628.47 | 85557 | 37303.37 | 0 | 0 | 122860.37 | 0 | 0 | 0 | 0 | 122860.37 | 38730.22 | [5 empty] | N | CS23W | 100%
403062 | NRSWA C4 Sewer Detailed Estimates - Scottish Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-10-23 |  |  | 2015-08-28 |  | Scottish Water Wide | 64356 | 0 | -11793.29 | 0 | 0 | 0 | 0 | 0 | -11793.29 | 0 | 0 | 0 | 52562.71 | 0 | 0 | 0 | 0 | 52562.71 | 0 | [5 empty] | N | CM_WWI | 100%
500783 | NRSWA C4 Sewer Detailed Estimates - Scottish Water Wide - 5007830000 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS7 | 2015-08-24 | 2019-09-25 | 2019-09-13 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 0 | 57103 | 46133.64 | 36345.5 | 4505.71 | -42366.93 | 0 | 101720.92 | 0 | 0 | 0 | 101720.92 | 0 | 0 | 0 | 0 | 101720.92 | 2566127.23 | [5 empty] | N | CS23S | 100%
503299 | NRSWA C4 Sewer Detailed Estimates-SR18 Scotland Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-06-02 | 2021-06-02 | 2021-06-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 57992.84 | 25891.02 | 17959.14 | 101843 | 0 | 0 | 0 | 101843 | 0 | 0 | 0 | 0 | 101843 | 2566127.23 | [5 empty] | N | CS23S | 100%
400744 | NRSWA C4 Sewers M8 Baillieston Newhouse | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2009-04-21 | 2012-08-15 | 2012-12-17 | 2014-10-23 |  | North Lanarkshire | 149438.69 | 0 | 0 | 0 | 0 | 85.16 | 0 | 0 | 85.16 | 0 | 0 | 0 | 149523.85 | 0 | 0 | 0 | 0 | 149523.85 | 0 | [5 empty] | N | CM_WWI | 100%
402917 | NRSWA C4 Water - Muir of Ord Railway Bridge | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-08-27 |  |  | 2013-04-10 |  | Highland | 1182.25 | 0 | 0 | 0 | 0 | 26.42 | 0 | 0 | 26.42 | 0 | 0 | 0 | 1208.67 | 0 | 0 | 0 | 0 | 1208.67 | 0 | [5 empty] | N | CM_WSI | 100%
503453 | NRSWA C4 Water (Design Only) - Grandholme Link Trunk Main Haudagain Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-02-22 | 2019-03-25 | 2019-06-10 | 2020-03-31 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 11876.7 | 98382.13 | 0 | 110258.83 | 0 | 0 | 0 | 110258.83 | 0 | 0 | 0 | 0 | 110258.83 | 38730.22 | [5 empty] | N | CS23W | 100%
500782 | NRSWA C4 Water Detailed Estimates - Scottish Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS7 | 2015-09-04 | 2019-09-25 | 2019-09-13 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 0 | 73930 | 328156.79 | 216767.27 | 446.46 | -275804.4 | 1034.48 | 344530.6 | 0 | 0 | 0 | 344530.6 | 0 | 0 | 0 | 0 | 344530.6 | 38730.22 | [5 empty] | N | CS23W | 100%
403063 | NRSWA C4 Water Detailed Estimates - Scottish Water Wide - 4030630000 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-10-23 | 2012-11-05 | 2013-01-11 | 2015-08-28 |  | Scottish Water Wide | 264292.42 | 0 | 106363.72 | 272.19 | 361.83 | 1984.14 | 0 | 0 | 108981.88 | 0 | 0 | 0 | 373274.3 | 0 | 0 | 0 | 0 | 373274.3 | 0 | [5 empty] | N | CM_WSI | 100%
503298 | NRSWA C4 Water Detailed Estimates-SR18 Scotland Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-05-24 | 2021-05-24 | 2021-05-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 152703.09 | 119915.67 | 62524.19 | 335142.95 | 65716.15 | 0 | 0 | 400859.1 | 0 | 0 | 0 | 0 | 400859.1 | 38730.22 | [5 empty] | N | CS23W | 100%
402196 | NRSWA C5 - Construction Sewers - M80 Post-Construction CCTV | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-06-15 | 2011-10-31 | 2012-01-09 | 2015-06-30 |  | North Lanarkshire | 131668 | 0 | 44945.24 | 0 | 0 | 0 | 0 | 0 | 44945.24 | 0 | 0 | 0 | 176613.24 | 0 | 0 | 0 | 0 | 176613.24 | 0 | [5 empty] | N | CM_WWI | 100%
402608 | NRSWA C5 - EGIP B9124 Galamuir Rd Alloa Bridge 31 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-03-30 | 2012-08-29 | 2012-12-03 | 2014-10-20 |  | Stirling | 61810.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61810.68 | 0 | 0 | 0 | 0 | 61810.68 | 0 | [6 empty] | CM_WSI | 100%
403557 | NRSWA C5 - EGIP Langmuir Road Bargeddie Bridge 021 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-08-20 | 2014-04-17 | 2014-04-25 | 2014-12-09 |  | North Lanarkshire | 50870 | 0 | -336.17 | 0 | 0 | 0 | 0 | 0 | -336.17 | 0 | 0 | 0 | 50533.83 | 0 | 0 | 0 | 0 | 50533.83 | 0 | [5 empty] | N | CM_WSI | 100%
403584 | NRSWA C5 - EGIP Main Street Larbert - Bridge 132-041 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-09-03 | 2014-04-02 | 2014-04-04 | 2015-01-27 |  | Falkirk | 196421 | 0 | 959.14 | 0 | 0 | 0 | 0 | 0 | 959.14 | 0 | 0 | 0 | 197380.14 | 0 | 0 | 0 | 0 | 197380.14 | 0 | [5 empty] | N | CM_WSI | 100%
402702 | NRSWA C5 Const Sewer - Edinburgh Gateway | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-06-05 | 2014-01-21 | 2014-06-16 | 2015-08-03 |  | City of Edinburgh | 2514139 | 0 | 39063 | -0.04 | -43418.63 | 0 | 0 | 0 | -4355.67 | 0 | 0 | 0 | 2509783.33 | 0 | 0 | 0 | 0 | 2509783.33 | 0 | [5 empty] | N | CM_WWI | 100%
402651 | NRSWA C5 Const Sewer - Forth Crossing SW-D10 Ferrytoll Road Rosyth | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-04-30 | 2012-11-30 | 2012-12-10 | 2014-04-01 |  | City of Edinburgh | 248616.33 | 0 | 6862.93 | 0 | 0 | 0 | 0 | 0 | 6862.93 | 0 | 0 | 0 | 255479.26 | 0 | 0 | 0 | 0 | 255479.26 | 0 | [5 empty] | N | CM_WWI | 100%
402267 | NRSWA C5 Construction - Forth Street Culvert Dunfermline | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-07-21 | 2012-11-16 | 2012-11-30 | 2015-02-02 |  | Fife | 181333 | 0 | -3078.09 | 0 | 0 | 0 | 0 | 0 | -3078.09 | 0 | 0 | 0 | 178254.91 | 0 | 0 | 0 | 0 | 178254.91 | 0 | [5 empty] | N | CM_WSI | 100%
402494 | NRSWA C5 Construction - The Helix Canal Project Falkirk | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-01-26 | 2012-02-19 | 2012-03-12 | 2014-12-01 |  | Falkirk | 62272 | 0 | 881.95 | 4.45 | 0 | 0 | 0 | 0 | 886.4 | 0 | 0 | 0 | 63158.4 | 0 | 0 | 0 | 0 | 63158.4 | 0 | [5 empty] | N | CM_WSI | 100%
403203 | NRSWA C5 Construction Sewer - Borders Rail Link SW-S2 & S3 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-12-17 | 2013-08-20 | 2013-08-28 | 2016-01-20 |  | Scottish Borders | 1620673 | 0 | 156998.7 | -52485.44 | 0 | 0 | 0 | 0 | 104513.26 | 0 | 0 | 0 | 1725186.26 | 0 | 0 | 0 | 0 | 1725186.26 | 0 | [5 empty] | N | CM_WWI | 100%
403574 | NRSWA C5 Construction Sewer - Borders Rail Link SW-S30 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-08-21 | 2014-02-28 | 2014-03-06 | 2014-10-07 |  | Scottish Borders | 4994.24 | 0 | 1143 | 0 | 0 | 0 | 0 | 0 | 1143 | 0 | 0 | 0 | 6137.24 | 0 | 0 | 0 | 0 | 6137.24 | 0 | [5 empty] | N | CM_WWI | 100%
403421 | NRSWA C5 Construction Sewer - Borders Rail Link SW-S69 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-03-15 | 2013-12-16 | 2014-02-20 | 2015-03-19 |  | Scottish Borders | 632218.27 | 0 | 226594.31 | 0 | 0 | 0 | 0 | 0 | 226594.31 | 0 | 0 | 0 | 858812.58 | 0 | 0 | 0 | 0 | 858812.58 | 0 | [5 empty] | N | CM_WWI | 100%
403612 | NRSWA C5 Construction Sewer - Forth Crossing SWD12 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-10-22 | 2014-10-08 | 2014-10-13 | 2016-02-01 |  | City of Edinburgh | 133491 | 0 | 534515 | 134264.43 | 22481.88 | -28405.8 | 207.6 | 0 | 663063.11 | 0 | 0 | 0 | 796554.11 | 0 | 0 | 0 | 0 | 796554.11 | 0 | [5 empty] | N | CM_WWI | 100%
402820 | NRSWA C5 Construction Sewer - M8 Improvements SWS 03 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2013-05-13 | 2013-05-20 | 2014-12-10 |  | North Lanarkshire | 818395 | 0 | -508.38 | 0 | 0 | 0 | 0 | 0 | -508.38 | 0 | 0 | 0 | 817886.62 | 0 | 0 | 0 | 0 | 817886.62 | 0 | [5 empty] | N | CM_WWI | 100%
403711 | NRSWA C5 Construction Sewer - M8 Improvements SWS 03 Phase 2 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2014-03-07 | 2014-04-25 | 2014-06-03 | 2014-12-10 |  | North Lanarkshire | 1243427.56 | 0 | 0 | -37131.72 | 0 | 0 | 0 | 0 | -37131.72 | 0 | 0 | 0 | 1206295.84 | 0 | 0 | 0 | 0 | 1206295.84 | 0 | [5 empty] | N | CM_WWI | 100%
402819 | NRSWA C5 Construction Sewer - M8 Improvements SWS 05 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2013-09-25 | 2013-10-07 | 2016-08-22 |  | North Lanarkshire | 395352 | 0 | 1011323 | -81952.5 | 0 | 0 | 0 | 0 | 929370.5 | 0 | 0 | 0 | 1324722.5 | 0 | 0 | 0 | 0 | 1324722.5 | 0 | [5 empty] | N | CM_WWI | 100%
402818 | NRSWA C5 Construction Sewer - M8 Improvements SWS 06 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-01-21 | 2014-08-18 | 2015-02-16 |  | North Lanarkshire | 450526 | 0 | -78961.1 | 0 | 0 | 0 | 0 | 0 | -78961.1 | 0 | 0 | 0 | 371564.9 | 0 | 0 | 0 | 0 | 371564.9 | 0 | [5 empty] | N | CM_WWI | 100%
402817 | NRSWA C5 Construction Sewer - M8 Improvements SWS 07 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2013-03-27 | 2013-04-29 | 2015-02-16 |  | North Lanarkshire | 848731.31 | 0 | 1488.73 | 0 | 0 | 0 | 0 | 0 | 1488.73 | 0 | 0 | 0 | 850220.04 | 0 | 0 | 0 | 0 | 850220.04 | 0 | [5 empty] | N | CM_WWI | 100%
402805 | NRSWA C5 Construction Sewer - M8 Improvements SWS 15 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-09-15 | 2015-01-26 | 2015-10-07 |  | North Lanarkshire | 696853 | 0 | 707751.96 | 166.08 | 0 | 0 | 0 | 0 | 707918.04 | 0 | 0 | 0 | 1404771.04 | 0 | 0 | 0 | 0 | 1404771.04 | 0 | [5 empty] | N | CM_WWI | 100%
402804 | NRSWA C5 Construction Sewer - M8 Improvements SWS 16 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2015-09-30 | 2015-09-30 | 2017-12-08 |  | North Lanarkshire | 279209 | 0 | 50217 | 203062 | 1435178.3 | 1717.28 | 0 | 0 | 1690174.58 | 0 | 0 | 0 | 1969383.58 | 0 | 0 | 0 | 0 | 1969383.58 | 0 | [5 empty] | N | CM_WWI | 100%
402803 | NRSWA C5 Construction Sewer - M8 Improvements SWS 17 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-09-18 | 2015-01-23 | 2015-09-08 |  | North Lanarkshire | 482544 | 0 | 549610.81 | 0 | 0 | 0 | 0 | 0 | 549610.81 | 0 | 0 | 0 | 1032154.81 | 0 | 0 | 0 | 0 | 1032154.81 | 0 | [5 empty] | N | CM_WWI | 100%
402812 | NRSWA C5 Construction Sewer - M8 Improvements SWS 20A | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-08-07 | 2014-09-15 | 2014-11-20 |  | North Lanarkshire | 52660 | 0 | -13887.54 | 0 | 0 | 0 | 0 | 0 | -13887.54 | 0 | 0 | 0 | 38772.46 | 0 | 0 | 0 | 0 | 38772.46 | 0 | [5 empty] | N | CM_WWI | 100%
402809 | NRSWA C5 Construction Sewer - M8 Improvements SWS 23 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-11-06 | 2015-05-18 | 2015-07-01 |  | North Lanarkshire | 51923 | 0 | 4461.95 | 0 | 0 | 0 | 0 | 0 | 4461.95 | 0 | 0 | 0 | 56384.95 | 0 | 0 | 0 | 0 | 56384.95 | 0 | [5 empty] | N | CM_WWI | 100%
402808 | NRSWA C5 Construction Sewer - M8 Improvements SWS 29 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2015-03-17 | 2015-07-31 | 2017-03-01 |  | North Lanarkshire | 86749.38 | 0 | 308022.62 | 1393267 | -53896.84 | 1043.8 | 0 | 0 | 1648436.58 | 0 | 0 | 0 | 1735185.96 | 0 | 0 | 0 | 0 | 1735185.96 | 0 | [5 empty] | N | CM_WWI | 100%
402806 | NRSWA C5 Construction Sewer - M8 Improvements SWS 30A | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-24 | 2014-09-22 | 2016-08-22 |  | North Lanarkshire | 342.94 | 0 | 74.98 | 291.2 | 0 | 0 | 0 | 0 | 366.18 | 0 | 0 | 0 | 709.12 | 0 | 0 | 0 | 0 | 709.12 | 0 | [5 empty] | N | CM_WWI | 100%
403489 | NRSWA C5 Construction Sewer - Maitland Street Culvert Leven Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-05-08 | 2014-05-20 | 2014-06-18 | 2015-03-13 |  | Fife | 19159 | 0 | 911.46 | 0 | 0 | 0 | 0 | 0 | 911.46 | 0 | 0 | 0 | 20070.46 | 0 | 0 | 0 | 0 | 20070.46 | 0 | [5 empty] | N | CM_WWI | 100%
403518 | NRSWA C5 Construction Sewer - Third Don Crossing Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-07-11 | 2014-09-08 | 2014-11-24 | 2016-06-24 |  | Aberdeen City | 171725 | 0 | 31045 | -275.95 | 0 | 0 | 0 | 0 | 30769.05 | 0 | 0 | 0 | 202494.05 | 0 | 0 | 0 | 0 | 202494.05 | 0 | [5 empty] | N | CM_WWI | 100%
403620 | NRSWA C5 Construction Sewer Borders Rail Link SW-S8a | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-12-10 | 2014-07-22 | 2014-08-05 | 2014-08-08 |  | Scottish Borders | 308.66 | 0 | 0 | 0 | 0 | -278.85 | 0 | 0 | -278.85 | 0 | 0 | 0 | 29.81 | 0 | 0 | 0 | 0 | 29.81 | 0 | [5 empty] | N | CM_WWI | 100%
403621 | NRSWA C5 Construction Sewer Borders Rail Link SW-S8b and c | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-12-10 | 2014-05-30 | 2014-06-09 | 2014-12-03 |  | Scottish Borders | 210336 | 0 | -26756.92 | 0 | 0 | 0 | 0 | 0 | -26756.92 | 0 | 0 | 0 | 183579.08 | 0 | 0 | 0 | 0 | 183579.08 | 0 | [5 empty] | N | CM_WWI | 100%
500691 | NRSWA C5 Construction Sewers - Borders Rail Link Remedial Works | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-06-09 | 2015-08-26 | 2015-09-22 | 2016-06-29 | 2016-07-22 | Scottish Borders | 0 | 0 | 115651.89 | 3136.1 | 0 | 0 | 0 | 0 | 118787.99 | 0 | 0 | 0 | 118787.99 | 0 | 0 | 0 | 0 | 118787.99 | 0 | [5 empty] | N | CM_WWI | 100%
403651 | NRSWA C5 Construction Sewers-Aberdeen Western Peripheral Route Holding Line | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | WINF | NRSWA | MS4 | 2014-01-20 | 2015-04-30 | 2015-08-31 | 2019-09-26 |  | Aberdeen City | 236758.42 | 0 | 598351.58 | 67232.39 | 293124.16 | 750540.64 | 312537.17 | 309812.26 | 2331598.2 | 0 | 0 | 0 | 2568356.62 | 0 | 0 | 0 | 0 | 2568356.62 | 0 | [5 empty] | N | CM_WWI | 100%
402534 | NRSWA C5 Construction Water - A92 Hawkhill Bends Angus | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-02-07 | 2012-04-18 | 2012-04-23 | 2013-06-28 |  | Angus | 64087.6 | 0 | 575.88 | 0 | 0 | 0 | 0 | 0 | 575.88 | 0 | 0 | 0 | 64663.48 | 0 | 0 | 0 | 0 | 64663.48 | 0 | [5 empty] | N | CM_WSI | 100%
403521 | NRSWA C5 Construction Water - A96 Park & Choose Dyce Drive Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-03-17 | 2014-06-16 | 2016-04-07 |  | Aberdeen City | 53008 | 0 | 276818 | -15058.63 | 0 | 0 | 0 | 0 | 261759.37 | 0 | 0 | 0 | 314767.37 | 0 | 0 | 0 | 0 | 314767.37 | 0 | [5 empty] | N | CM_WSI | 100%
403319 | NRSWA C5 Construction Water - Aimer Street Lochee Dundee | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-02-04 | 2013-05-15 | 2013-05-28 | 2016-09-28 |  | Dundee City | 12008 | 0 | 461 | 727.74 | 9880.16 | 0 | 0 | 0 | 11068.9 | 0 | 0 | 0 | 23076.9 | 0 | 0 | 0 | 0 | 23076.9 | 0 | [5 empty] | N | CM_WSI | 100%
401714 | NRSWA C5 Construction Water - Borders Rail Link - SW-W11-W13 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2010-12-14 | 2011-08-01 | 2012-05-25 | 2014-11-18 |  | Scottish Borders | 1012352 | 0 | -16339.3 | 0 | 0 | 0 | 0 | 0 | -16339.3 | 0 | 0 | 0 | 996012.7 | 0 | 0 | 0 | 0 | 996012.7 | 0 | [5 empty] | N | CM_WSI | 100%
403708 | NRSWA C5 Construction Water - Borders Rail Link - SW-W11-W13 (Ph.2) | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-02-04 | 2014-03-25 | 2014-03-31 | 2014-11-18 |  | Scottish Borders | 582388.63 | 0 | -12482.62 | 0 | 0 | 0 | 0 | 0 | -12482.62 | 0 | 0 | 0 | 569906.01 | 0 | 0 | 0 | 0 | 569906.01 | 0 | [5 empty] | N | CM_WSI | 100%
403211 | NRSWA C5 Construction Water - Borders Rail Link SW-W14 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-12-17 | 2013-11-12 | 2013-12-12 | 2015-08-05 |  | Scottish Borders | 388894 | 0 | 4819.8 | 128 | 0 | 0 | 0 | 0 | 4947.8 | 0 | 0 | 0 | 393841.8 | 0 | 0 | 0 | 0 | 393841.8 | 0 | [5 empty] | N | CM_WSI | 100%
403818 | NRSWA C5 Construction Water - Bute Drive Perth Junction Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-05-27 | 2014-10-09 | 2014-10-20 | 2015-06-01 |  | Perth and Kinross | 35380 | 0 | 759.77 | 0 | 0 | 0 | 0 | 0 | 759.77 | 0 | 0 | 0 | 36139.77 | 0 | 0 | 0 | 0 | 36139.77 | 0 | [5 empty] | N | CM_WSI | 100%
403524 | NRSWA C5 Construction Water - Duddingston Road Rail Bridge Edinburgh | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-03-27 | 2014-04-28 | 2015-03-13 |  | City of Edinburgh | 43470.95 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 43491.39 | 0 | 0 | 0 | 0 | 43491.39 | 0 | [5 empty] | N | CM_WSI | 100%
403381 | NRSWA C5 Construction Water - Hatton Mill Bridge Hatton Aberdeenshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-02-21 | 2013-04-25 | 2013-04-29 | 2013-09-25 |  | Aberdeenshire | 24064 | 0 | 0 | 0 | 0 | 10.33 | 0 | 0 | 10.33 | 0 | 0 | 0 | 24074.33 | 0 | 0 | 0 | 0 | 24074.33 | 0 | [5 empty] | N | CM_WSI | 100%
403871 | NRSWA C5 Construction Water - High Park Culvert Turnberry South Ayrshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-06-30 | 2014-08-29 | 2014-09-26 | 2015-04-24 |  | South Ayrshire | 27667 | 0 | -127.92 | 0 | 0 | 0 | 0 | 0 | -127.92 | 0 | 0 | 0 | 27539.08 | 0 | 0 | 0 | 0 | 27539.08 | 0 | [5 empty] | N | CM_WSI | 100%
403872 | NRSWA C5 Construction Water - Locharbriggs Retaining Wall Dumfries | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-06-30 | 2014-08-29 | 2015-01-23 | 2015-03-17 |  | Dumfries and Galloway | 23689 | 0 | 13945.83 | 0 | 0 | 0 | 0 | 0 | 13945.83 | 0 | 0 | 0 | 37634.83 | 0 | 0 | 0 | 0 | 37634.83 | 0 | [5 empty] | N | CM_WSI | 100%
403484 | NRSWA C5 Construction Water - M8 Improvements SWW 05 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-05-10 | 2014-06-27 | 2014-08-13 | 2015-09-10 |  | North Lanarkshire | 70808 | 0 | 103213 | 0 | 0 | 0 | 0 | 0 | 103213 | 0 | 0 | 0 | 174021 | 0 | 0 | 0 | 0 | 174021 | 0 | [5 empty] | N | CM_WSI | 100%
402790 | NRSWA C5 Construction Water - M8 Improvements SWW 11 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-02-19 | 2014-05-12 | 2015-12-01 |  | North Lanarkshire | 66555 | 0 | 80910.56 | 0 | 0 | 0 | 0 | 0 | 80910.56 | 0 | 0 | 0 | 147465.56 | 0 | 0 | 0 | 0 | 147465.56 | 0 | [5 empty] | N | CM_WSI | 100%
402794 | NRSWA C5 Construction Water - M8 Improvements SWW 12 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-04-11 | 2014-07-07 | 2015-12-21 |  | North Lanarkshire | 117997 | 0 | 69638.01 | 468.13 | 0 | 0 | 0 | 0 | 70106.14 | 0 | 0 | 0 | 188103.14 | 0 | 0 | 0 | 0 | 188103.14 | 0 | [5 empty] | N | CM_WSI | 100%
403483 | NRSWA C5 Construction Water - M8 Improvements SWW 13 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-05-10 | 2014-07-17 | 2014-07-18 | 2016-07-28 |  | North Lanarkshire | 307941 | 0 | 252602.73 | 561747.93 | 0 | 0 | 0 | 0 | 814350.66 | 0 | 0 | 0 | 1122291.66 | 0 | 0 | 0 | 0 | 1122291.66 | 0 | [5 empty] | N | CM_WSI | 100%
402795 | NRSWA C5 Construction Water - M8 Improvements SWW 14 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-05-12 | 2015-12-01 |  | North Lanarkshire | 378919 | 0 | 402354.96 | -128.87 | 0 | 0 | 0 | 0 | 402226.09 | 0 | 0 | 0 | 781145.09 | 0 | 0 | 0 | 0 | 781145.09 | 0 | [5 empty] | N | CM_WSI | 100%
402793 | NRSWA C5 Construction Water - M8 Improvements SWW 15 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-05-05 | 2015-12-14 |  | North Lanarkshire | 168811 | 0 | -7932 | 5898.38 | 0 | 0 | 0 | 0 | -2033.62 | 0 | 0 | 0 | 166777.38 | 0 | 0 | 0 | 0 | 166777.38 | 0 | [5 empty] | N | CM_WSI | 100%
402797 | NRSWA C5 Construction Water - M8 Improvements SWW 16 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-06-02 | 2015-04-21 |  | North Lanarkshire | 109102 | 0 | 9916.27 | 0 | 0 | 0 | 0 | 0 | 9916.27 | 0 | 0 | 0 | 119018.27 | 0 | 0 | 0 | 0 | 119018.27 | 0 | [5 empty] | N | CM_WSI | 100%
402798 | NRSWA C5 Construction Water - M8 Improvements SWW 17 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-07-01 | 2015-06-22 | 2016-09-19 |  | North Lanarkshire | 203092.27 | 0 | 1234625.92 | 158723.06 | 0 | 0 | 0 | 0 | 1393348.98 | 0 | 0 | 0 | 1596441.25 | 0 | 0 | 0 | 0 | 1596441.25 | 0 | [5 empty] | N | CM_WSI | 100%
402786 | NRSWA C5 Construction Water - M8 Improvements SWW 2 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-10 | 2014-11-25 | 2015-01-12 | 2016-09-19 |  | North Lanarkshire | 61016.23 | 0 | 105306.77 | 175746.35 | 0 | 0 | 0 | 0 | 281053.12 | 0 | 0 | 0 | 342069.35 | 0 | 0 | 0 | 0 | 342069.35 | 0 | [5 empty] | N | CM_WSI | 100%
402800 | NRSWA C5 Construction Water - M8 Improvements SWW 20 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-10-28 | 2014-10-30 | 2015-09-16 |  | North Lanarkshire | 146485 | 0 | 139068.3 | 36380.86 | 45.17 | 0 | 0 | 0 | 175494.33 | 0 | 0 | 0 | 321979.33 | 0 | 0 | 0 | 0 | 321979.33 | 0 | [5 empty] | N | CM_WSI | 100%
402801 | NRSWA C5 Construction Water - M8 Improvements SWW 21 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-06-30 | 2014-07-21 | 2015-02-23 |  | North Lanarkshire | 13798.59 | 0 | 5709.83 | 0 | 0 | 0 | 0 | 0 | 5709.83 | 0 | 0 | 0 | 19508.42 | 0 | 0 | 0 | 0 | 19508.42 | 0 | [5 empty] | N | CM_WSI | 100%
402799 | NRSWA C5 Construction Water - M8 Improvements SWW 22 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2015-03-16 | 2015-08-12 | 2016-02-10 |  | North Lanarkshire | 31079.34 | 0 | 93575.66 | 1977.86 | 0 | 0 | 0 | 0 | 95553.52 | 0 | 0 | 0 | 126632.86 | 0 | 0 | 0 | 0 | 126632.86 | 0 | [5 empty] | N | CM_WSI | 100%
403634 | NRSWA C5 Construction Water - M8 Improvements SWW 23 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-16 | 2015-02-23 | 2016-02-22 | 2016-11-11 |  | North Lanarkshire | 35529 | 0 | 2893 | 35457.24 | 20515.6 | 0 | 0 | 0 | 58865.84 | 0 | 0 | 0 | 94394.84 | 0 | 0 | 0 | 0 | 94394.84 | 0 | [5 empty] | N | CM_WSI | 100%
403635 | NRSWA C5 Construction Water - M8 Improvements SWW 24 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-16 | 2014-12-05 | 2015-02-27 | 2015-10-10 |  | North Lanarkshire | 40821 | 0 | 170535.88 | 0 | 0 | 0 | 0 | 0 | 170535.88 | 0 | 0 | 0 | 211356.88 | 0 | 0 | 0 | 0 | 211356.88 | 0 | [5 empty] | N | CM_WSI | 100%
402787 | NRSWA C5 Construction Water - M8 Improvements SWW 3 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-19 | 2013-08-21 | 2013-09-19 | 2015-04-21 |  | North Lanarkshire | 149199.15 | 0 | -7119.32 | 0 | 0 | 0 | 0 | 0 | -7119.32 | 0 | 0 | 0 | 142079.83 | 0 | 0 | 0 | 0 | 142079.83 | 0 | [5 empty] | N | CM_WSI | 100%
403784 | NRSWA C5 Construction Water - M8 Improvements SWW 3 (Perm) | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-05-13 | 2015-01-27 | 2015-07-30 | 2016-05-31 |  | North Lanarkshire | 10919 | 0 | 137193 | 162253.08 | 0 | 0 | 0 | 0 | 299446.08 | 0 | 0 | 0 | 310365.08 | 0 | 0 | 0 | 0 | 310365.08 | 0 | [5 empty] | N | CM_WSI | 100%
403633 | NRSWA C5 Construction Water - M8 Improvements SWW 34 35 & 36 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-16 | 2015-01-29 | 2015-01-28 | 2015-12-21 |  | North Lanarkshire | 493356 | 0 | 834996.97 | 0 | 0 | 0 | 0 | 0 | 834996.97 | 0 | 0 | 0 | 1328352.97 | 0 | 0 | 0 | 0 | 1328352.97 | 0 | [5 empty] | N | CM_WSI | 100%
403869 | NRSWA C5 Construction Water - M8 Improvements SWW 38 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-06-30 | 2015-02-27 | 2015-03-16 | 2015-09-16 |  | North Lanarkshire | 155535.02 | 0 | 195444.44 | 0 | 422.45 | 0 | 0 | 0 | 195866.89 | 0 | 0 | 0 | 351401.91 | 0 | 0 | 0 | 0 | 351401.91 | 0 | [5 empty] | N | CM_WSI | 100%
402785 | NRSWA C5 Construction Water - M8 Improvements SWW 4 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-06-29 | 2014-08-05 | 2014-11-03 | 2015-10-10 |  | North Lanarkshire | 87941 | 0 | 8281.46 | 0 | 0 | 0 | 0 | 0 | 8281.46 | 0 | 0 | 0 | 96222.46 | 0 | 0 | 0 | 0 | 96222.46 | 0 | [5 empty] | N | CM_WSI | 100%
402788 | NRSWA C5 Construction Water - M8 Improvements SWW 6 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-02-13 | 2014-06-23 | 2015-07-08 |  | North Lanarkshire | 353562 | 0 | 199010.19 | 0 | 0 | 0 | 0 | 0 | 199010.19 | 0 | 0 | 0 | 552572.19 | 0 | 0 | 0 | 0 | 552572.19 | 0 | [5 empty] | N | CM_WSI | 100%
402789 | NRSWA C5 Construction Water - M8 Improvements SWW 7 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-02-27 | 2014-06-30 | 2016-02-18 |  | North Lanarkshire | 266427 | 0 | 345968.31 | 24522.29 | 0 | 0 | 0 | 0 | 370490.6 | 0 | 0 | 0 | 636917.6 | 0 | 0 | 0 | 0 | 636917.6 | 0 | [5 empty] | N | CM_WSI | 100%
402791 | NRSWA C5 Construction Water - M8 Improvements SWW 8 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2013-09-24 | 2013-10-07 | 2015-01-15 |  | North Lanarkshire | 1293564 | 0 | -242038.84 | 0 | 0 | 0 | 0 | 0 | -242038.84 | 0 | 0 | 0 | 1051525.16 | 0 | 0 | 0 | 0 | 1051525.16 | 0 | [5 empty] | N | CM_WSI | 100%
403742 | NRSWA C5 Construction Water - M8 Improvements SWW 8 Phase 2 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-03-07 | 2014-04-29 | 2014-05-22 | 2015-01-26 |  | North Lanarkshire | 660774 | 0 | 595.74 | 0 | 0 | 0 | 0 | 0 | 595.74 | 0 | 0 | 0 | 661369.74 | 0 | 0 | 0 | 0 | 661369.74 | 0 | [5 empty] | N | CM_WSI | 100%
402792 | NRSWA C5 Construction Water - M8 Improvements SWW 9 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-05-12 | 2017-03-08 |  | North Lanarkshire | 275547 | 0 | 57936 | -18696 | 62051.85 | 0 | 0 | 0 | 101291.85 | 0 | 0 | 0 | 376838.85 | 0 | 0 | 0 | 0 | 376838.85 | 0 | [5 empty] | N | CM_WSI | 100%
403488 | NRSWA C5 Construction Water - Maitland Street Culvert Leven Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-05-08 | 2014-05-20 | 2014-06-09 | 2015-07-06 |  | Fife | 36261 | 0 | 673.01 | 0 | 0 | 0 | 0 | 0 | 673.01 | 0 | 0 | 0 | 36934.01 | 0 | 0 | 0 | 0 | 36934.01 | 0 | [5 empty] | N | CM_WSI | 100%
403525 | NRSWA C5 Construction Water - Peffermill Road Rail Bridge Edinburgh | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-03-27 | 2014-06-09 | 2015-11-02 |  | City of Edinburgh | 130465 | 0 | 61267.1 | 0 | 0 | 0 | 0 | 0 | 61267.1 | 0 | 0 | 0 | 191732.1 | 0 | 0 | 0 | 0 | 191732.1 | 0 | [5 empty] | N | CM_WSI | 100%
403534 | NRSWA C5 Construction Water - Port-na-Craig Footbridge Pitlochry | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-07-11 | 2014-03-03 | 2014-03-13 | 2015-02-02 |  | Perth and Kinross | 23185.95 | 0 | 445.95 | 0 | 0 | 0 | 0 | 0 | 445.95 | 0 | 0 | 0 | 23631.9 | 0 | 0 | 0 | 0 | 23631.9 | 0 | [5 empty] | N | CM_WSI | 100%
403519 | NRSWA C5 Construction Water - Third Don Crossing Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-09-11 | 2014-11-24 | 2016-06-29 |  | Aberdeen City | 246797 | 0 | 87388 | 48234.58 | 273.45 | 0 | 0 | 0 | 135896.03 | 0 | 0 | 0 | 382693.03 | 0 | 0 | 0 | 0 | 382693.03 | 0 | [5 empty] | N | CM_WSI | 100%
403905 | NRSWA C5 Construction Water - Townhead St-Low Patrick St Hamilton | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-08-20 | 2014-09-19 | 2014-12-05 | 2015-03-12 |  | South Lanarkshire | 8327 | 0 | -1396.18 | 0 | 0 | 0 | 0 | 0 | -1396.18 | 0 | 0 | 0 | 6930.82 | 0 | 0 | 0 | 0 | 6930.82 | 0 | [5 empty] | N | CM_WSI | 100%
403652 | NRSWA C5 Construction Water Aberdeen Western Peripheral Route Holding Line | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS4 | 2014-01-16 | 2015-04-28 | 2015-06-29 | 2020-03-16 |  | Aberdeen City | 800753 | 0 | 3456914.85 | 2568606.87 | 2709028.28 | 1572245.43 | 167314.06 | 33769.5 | 10507878.99 | -10050.74 | 0 | 0 | 11298581.25 | 0 | 0 | 0 | 0 | 11298581.25 | 0 | [5 empty] | N | CM_WSI | 100%
403622 | NRSWA C5 Construction Water Borders Rail Link SW-W16a | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-10 | 2014-07-22 | 2014-08-15 | 2015-06-25 |  | Scottish Borders | 18526 | 0 | -7844.14 | 0 | 0 | 0 | 0 | 0 | -7844.14 | 0 | 0 | 0 | 10681.86 | 0 | 0 | 0 | 0 | 10681.86 | 0 | [5 empty] | N | CM_WSI | 100%
403260 | NRSWA C5 Construction Water Dura Den Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-01-15 | 2014-02-13 | 2014-02-26 | 2015-09-01 |  | Fife | 89591 | 0 | -3016.5 | 0 | 0 | 0 | 0 | 0 | -3016.5 | 0 | 0 | 0 | 86574.5 | 0 | 0 | 0 | 0 | 86574.5 | 0 | [5 empty] | N | CM_WSI | 100%
402739 | NRSWA C5 Construction Water Matthews Burn Culvert Darvel | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-09-04 | 2012-12-12 | 2013-01-07 | 2013-09-24 |  | East Ayrshire | 68672 | 0 | -2327.66 | 0 | 0 | 0 | 0 | 0 | -2327.66 | 0 | 0 | 0 | 66344.34 | 0 | 0 | 0 | 0 | 66344.34 | 0 | [5 empty] | N | CM_WSI | 100%
403932 | NRSWA C5 Construction Water-A749 Western Rd-East Kilbride Rd Cambuslang | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-10-10 | 2015-01-22 | 2015-02-12 | 2016-02-01 |  | South Lanarkshire | 47986.53 | 0 | 217.45 | 0 | 0 | 0 | 0 | 0 | 217.45 | 0 | 0 | 0 | 48203.98 | 0 | 0 | 0 | 0 | 48203.98 | 0 | [5 empty] | N | CM_WSI | 100%
500692 | NRSWA C5 Construction Water-A917 Kilrenny Burn Bridge Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-09 | 2015-09-30 | 2016-08-18 | 2017-05-04 | 2017-05-04 | Fife | 0 | 0 | 21180 | -11838.08 | -4107.04 | 0 | 0 | 0 | 5234.88 | 0 | 0 | 0 | 5234.88 | 0 | 0 | 0 | 0 | 5234.88 | 0 | [5 empty] | N | CM_WSI | 100%
403806 | NRSWA C5 Construction Water-A96 Inveramsay Bridge Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-05-19 | 2014-11-20 | 2014-12-24 | 2015-10-22 |  | Aberdeenshire | 17336 | 0 | 13787.42 | 0 | 0 | 0 | 0 | 0 | 13787.42 | 0 | 0 | 0 | 31123.42 | 0 | 0 | 0 | 0 | 31123.42 | 0 | [5 empty] | N | CM_WSI | 100%
404011 | NRSWA C5 Construction Water-EGIP 2015 Bridges | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-12-08 | 2015-05-11 | 2015-05-19 | 2016-12-23 |  | Falkirk | 23973 | 0 | 117540 | 26725.8 | 17444.39 | 0 | 0 | 0 | 161710.19 | 0 | 0 | 0 | 185683.19 | 0 | 0 | 0 | 0 | 185683.19 | 0 | [5 empty] | N | CM_WSI | 100%
403933 | NRSWA C5 Construction Water-Nairn Cemetery | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-10-29 | 2015-03-31 | 2015-06-01 | 2015-10-27 |  | Highland | 15150 | 0 | 21737.34 | 0 | 0 | 0 | 0 | 0 | 21737.34 | 0 | 0 | 0 | 36887.34 | 0 | 0 | 0 | 0 | 36887.34 | 0 | [5 empty] | N | CM_WSI | 100%
404012 | NRSWA C5 Construction Water-Shotts Line 2015 Bridges | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-12-10 | 2015-05-11 | 2015-05-12 | 2017-10-11 |  | North Lanarkshire | 1850 | 0 | 244422 | 438877 | 205311.01 | 52.47 | 0 | 0 | 888662.48 | 0 | 0 | 0 | 890512.48 | 0 | 0 | 0 | 0 | 890512.48 | 0 | [5 empty] | N | CM_WSI | 100%
501176 | NRSWA C5 Water - Culvert Replacement at Ballygrant Islay | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-10-28 | 2016-09-26 | 2016-09-27 | 2017-03-27 | 2017-03-27 | Argyll and Bute-North Argyll | 0 | 0 | 14000 | 31250.88 | -359.6 | 0 | 0 | 0 | 44891.28 | 0 | 0 | 0 | 44891.28 | 0 | 0 | 0 | 0 | 44891.28 | 38730.22 | [5 empty] | N | CS23W | 100%
403438 | NRSWA C5 Water A75 Hardgrove to Kinmount Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-03-29 | 2013-11-21 | 2013-11-21 | 2016-03-24 |  | Dumfries and Galloway | 255314 | 0 | 174943 | 752.25 | 0 | 0 | 0 | 0 | 175695.25 | 0 | 0 | 0 | 431009.25 | 0 | 0 | 0 | 0 | 431009.25 | 0 | [5 empty] | N | CM_WSI | 100%
403326 | NRSWA C5 Water A77 Symington to Bogend Toll Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-01-28 | 2013-09-18 | 2013-10-28 | 2015-04-22 |  | South Ayrshire | 317957 | 0 | -22017.24 | 0 | 0 | 0 | 0 | 0 | -22017.24 | 0 | 0 | 0 | 295939.76 | 0 | 0 | 0 | 0 | 295939.76 | 0 | [5 empty] | N | CM_WSI | 100%
403075 | NRSWA C5 Water EGIP Beancross Rd Grangemouth (GMH-OB078-005-SWW7) | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-10-25 | 2014-02-27 | 2014-06-17 | 2014-12-17 |  | Falkirk | 44926 | 0 | 220.1 | 0 | 0 | 0 | 0 | 0 | 220.1 | 0 | 0 | 0 | 45146.1 | 0 | 0 | 0 | 0 | 45146.1 | 0 | [5 empty] | N | CM_WSI | 100%
401453 | NRSWA C5 Water Wilsonville - Caw Bridges West Lothian | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2010-09-24 | 2011-11-01 | 2011-10-31 | 2012-06-19 |  | West Lothian | 21041.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21041.64 | 0 | 0 | 0 | 0 | 21041.64 | 0 | [6 empty] | CM_WSI | 100%
404113 | NRSWA C7 Construction Sewer - Dunlappie Road Culvert Edzell | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-03-03 | 2015-09-14 | 2015-09-14 | 2015-09-09 |  | Angus | 47.16 | 0 | 326.18 | 0 | 0 | 0 | 0 | 0 | 326.18 | 0 | 0 | 0 | 373.34 | 0 | 0 | 0 | 0 | 373.34 | 0 | [5 empty] | N | CM_WWI | 100%
404016 | NRSWA C7 Construction Sewer AWPR SWD03 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | WINF | NRSWA | MS6 | 2014-12-05 | 2015-05-29 | 2016-08-22 | 2017-08-31 |  | Aberdeen City | 29431 | 0 | 31033 | 357429.52 | 141873.83 | -54910.91 | -14120.93 | 11118.06 | 472422.57 | 0 | 0 | 0 | 501853.57 | 0 | 0 | 0 | 0 | 501853.57 | 0 | [5 empty] | N | CM_WWI | 100%
500693 | NRSWA C7 Construction Water - A702 Mauricewood Roundabout Penicuick | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-05 | 2015-09-24 | 2015-11-30 | 2017-11-15 | 2017-11-15 | Midlothian | 0 | 0 | 618815 | 1448319.37 | 1894699.53 | 29375.28 | 0 | 0 | 3991209.18 | 0 | 0 | 0 | 3991209.18 | 0 | 0 | 0 | 0 | 3991209.18 | 38730.22 | [5 empty] | N | CS23W | 100%
404129 | NRSWA C7 Construction Water - A905 Lower Polmaise Junction Stirling | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-07-07 | 2015-07-27 | 2015-11-23 |  | Stirling | 0 | 0 | 92121.18 | 0 | 0 | 0 | 0 | 0 | 92121.18 | 0 | 0 | 0 | 92121.18 | 0 | 0 | 0 | 0 | 92121.18 | 0 | [5 empty] | N | CM_WSI | 100%
404128 | NRSWA C7 Construction Water - A96 Keith Rail Bridge Moray | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-09-28 | 2015-10-26 | 2019-02-28 |  | Moray | 0 | 0 | 68865 | -46982 | 0 | 77868.88 | 18.47 | 0 | 99770.35 | 0 | 0 | 0 | 99770.35 | 0 | 0 | 0 | 0 | 99770.35 | 0 | [5 empty] | N | CM_WSI | 100%
404111 | NRSWA C7 Construction Water - Arrochar Street Glasgow | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-03-03 | 2015-07-23 | 2015-08-17 | 2015-08-14 |  | Glasgow City | 86.46 | 0 | 584.73 | 0 | 0 | 0 | 0 | 0 | 584.73 | 0 | 0 | 0 | 671.19 | 0 | 0 | 0 | 0 | 671.19 | 0 | [5 empty] | N | CM_WSI | 100%
404014 | NRSWA C7 Construction Water - AWPR 1866 Aqueduct | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS6 | 2014-12-09 | 2015-12-16 | 2016-01-05 | 2018-11-16 |  | Aberdeen City | 215249 | 0 | 1053507.57 | 171917.24 | 479055.19 | -137767.34 | -142558.06 | 10083.4 | 1434238 | 0 | 0 | 0 | 1649487 | 0 | 0 | 0 | 0 | 1649487 | 0 | [5 empty] | N | CM_WSI | 100%
404015 | NRSWA C7 Construction Water - AWPR SWW19 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS6 | 2014-12-08 | 2015-05-19 | 2016-01-15 | 2018-01-10 |  | Aberdeen City | 29699 | 0 | 31102 | 851577.02 | 118239.32 | 53489.16 | -1859.39 | 1885.89 | 1054434 | 0 | 0 | 0 | 1084133 | 0 | 0 | 0 | 0 | 1084133 | 0 | [5 empty] | N | CM_WSI | 100%
404114 | NRSWA C7 Construction Water - Dunlappie Road Culvert Edzell | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-05-18 | 2015-08-18 | 2015-10-12 | 2016-04-25 |  | Angus | 0 | 0 | 37204 | -2482.88 | 546.9 | 0 | 0 | 0 | 35268.02 | 0 | 0 | 0 | 35268.02 | 0 | 0 | 0 | 0 | 35268.02 | 0 | [5 empty] | N | CM_WSI | 100%
404127 | NRSWA C7 Construction Water - Gogar Pedestrian Underpass | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-09-30 | 2015-09-30 | 2016-11-22 |  | City of Edinburgh | 0 | 0 | 182820 | 82020.58 | 621.28 | 0 | 0 | 0 | 265461.86 | 0 | 0 | 0 | 265461.86 | 0 | 0 | 0 | 0 | 265461.86 | 0 | [5 empty] | N | CM_WSI | 100%
404126 | NRSWA C7 Construction Water - Inverness Western Link Road | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-07-30 | 2015-07-31 | 2015-10-06 |  | Highland | 0 | 0 | 57508.66 | 0 | 0 | 0 | 0 | 0 | 57508.66 | 0 | 0 | 0 | 57508.66 | 0 | 0 | 0 | 0 | 57508.66 | 0 | [5 empty] | N | CM_WSI | 100%
404119 | NRSWA C7 Construction Water - Inverness Western Link Road - 4041190000 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-03-30 | 2015-09-30 | 2015-10-01 | 2016-08-09 | 2016-09-21 | Highland | 0 | 0 | 785867.13 | 29265.61 | 282.88 | 0 | 0 | 0 | 815415.62 | 0 | 0 | 0 | 815415.62 | 0 | 0 | 0 | 0 | 815415.62 | 0 | [5 empty] | N | CM_WSI | 100%
404088 | NRSWA C7 Construction Water-A9 Dualling Kincraig to Dalraddy | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-01-27 | 2015-08-31 | 2015-09-01 | 2016-07-07 |  | Highland | 5000 | 0 | 793732.11 | 123403.86 | -6719.05 | 27949.95 | 499.28 | 0 | 938866.15 | 0 | 0 | 0 | 943866.15 | 0 | 0 | 0 | 0 | 943866.15 | 0 | [5 empty] | N | CM_WSI | 100%
404013 | NRSWA C7 Construction Water-AWPR 1924 Aqueduct | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS6 | 2014-12-02 | 2015-08-10 | 2015-08-10 | 2018-02-23 |  | Aberdeen City | 404227 | 0 | 870325.07 | 2315805.62 | -538575.69 | -317925.23 | -91773.29 | 7382.52 | 2245239 | 0 | 0 | 0 | 2649466 | 0 | 0 | 0 | 0 | 2649466 | 0 | [5 empty] | N | CM_WSI | 100%
404107 | NRSWA C7 Construction Water-Forth Replacement Crossing SWW25 Remedial Works | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-03-03 | 2015-06-24 | 2015-06-24 | 2016-10-10 |  | City of Edinburgh | 70.74 | 0 | 43872.26 | 10654.21 | 273.45 | 0 | 0 | 0 | 54799.92 | 0 | 0 | 0 | 54870.66 | 0 | 0 | 0 | 0 | 54870.66 | 0 | [5 empty] | N | CM_WSI | 100%
404087 | NRSWA C7 Construction Water-Station Road Polmont | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-01-27 | 2015-04-29 | 2015-05-15 | 2015-10-14 |  | Falkirk | 1503.56 | 0 | 42243.79 | 0 | 0 | 0 | 0 | 0 | 42243.79 | 0 | 0 | 0 | 43747.35 | 0 | 0 | 0 | 0 | 43747.35 | 0 | [5 empty] | N | CM_WSI | 100%
502413 | NRSWA Construction PIF Water Freuchie Bridge Replacement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-12-09 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | Fife | 0 | 0 | 0 | 1693 | -275.79 | 0 | 0 | 0 | 1417.21 | 0 | 0 | 0 | 1417.21 | 0 | 0 | 0 | 0 | 1417.21 | 38730.22 | [5 empty] | N | CS23W | 100%
501320 | NRSWA Construction Sewer - A9-A85 Crieff Road Junctions | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-12-16 | 2016-11-30 | 2017-01-06 | 2018-03-23 | 2018-03-23 | Perth and Kinross | 0 | 0 | 974.97 | 413509.03 | 788194 | -470860.68 | 0 | 0 | 731817.32 | 0 | 0 | 0 | 731817.32 | 0 | 0 | 0 | 0 | 731817.32 | 2566127.23 | [5 empty] | N | CS23S | 100%
501319 | NRSWA Construction Sewer - Aberdeen Bypass - SWD09 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | WINF | NRSWA | MS6 | 2016-02-26 | 2016-08-15 | 2016-08-29 | 2019-05-29 | 2019-08-07 | Aberdeen City | 0 | 0 | 20998.05 | 597152.6 | 84515.41 | 170034.61 | -290106.42 | 1527.75 | 584122 | 0 | 0 | 0 | 584122 | 0 | 0 | 0 | 0 | 584122 | 2566127.23 | [5 empty] | N | CS23S | 100%
501631 | NRSWA Construction Sewer - Aberdeen Inverness Rail Enhancement - Elgin | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-07-29 | 2016-08-31 | 2017-03-15 | 2017-03-15 | Moray | 0 | 0 | 13506 | -5898.77 | -922.7 | 0 | 0 | 0 | 6684.53 | 0 | 0 | 0 | 6684.53 | 0 | 0 | 0 | 0 | 6684.53 | 2566127.23 | [5 empty] | N | CS23S | 100%
501630 | NRSWA Construction Sewer - Aberdeen Inverness Rail Enhancement - Forres | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-02-08 | 2016-07-29 | 2016-09-05 | 2017-03-15 | 2017-03-15 | Moray | 0 | 0 | 2879 | 22357.96 | 66951.81 | 0 | 0 | 0 | 92188.77 | 0 | 0 | 0 | 92188.77 | 0 | 0 | 0 | 0 | 92188.77 | 2566127.23 | [5 empty] | N | CS23S | 100%
502126 | NRSWA Construction Sewer - Almondbank Flood Prevention Scheme | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-03-02 | 2016-11-30 | 2017-02-20 | 2017-12-08 | 2017-12-08 | Perth and Kinross | 0 | 0 | 1000 | 56512.89 | 226563.59 | 27419.85 | 0 | 0 | 311496.33 | 0 | 0 | 0 | 311496.33 | 0 | 0 | 0 | 0 | 311496.33 | 2566127.23 | [5 empty] | N | CS23S | 100%
502253 | NRSWA Construction Sewer - Littlemill Bridge Replacement Rankinston East Ayrshire | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-06-29 | 2017-12-18 | 2018-06-25 | 2021-02-03 |  | East Ayrshire | 0 | 0 | 0 | 723.75 | 50110.25 | -17834 | 4029.61 | 841.15 | 37870.76 | 0 | 0 | 0 | 37870.76 | 0 | 0 | 0 | 0 | 37870.76 | 2566127.23 | [5 empty] | N | CS23S | 100%
501624 | NRSWA Construction Sewer - M8 Motorway - SWS20B | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-07-27 | 2016-07-27 | 2017-03-01 | 2017-03-01 | South Lanarkshire | 0 | 0 | 6655 | 982933.2 | 17098.7 | 169.33 | 0 | 0 | 1006856.23 | 0 | 0 | 0 | 1006856.23 | 0 | 0 | 0 | 0 | 1006856.23 | 2566127.23 | [5 empty] | N | CS23S | 100%
500988 | NRSWA Construction Sewer - M8 Motorway Ancillary Works | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-11-29 | 2016-11-30 | 2018-12-18 | 2018-12-18 | North Lanarkshire | 0 | 0 | 2763.28 | 307308.52 | 92176.62 | 68797.73 | 79.94 | 0 | 471126.09 | 0 | 0 | 0 | 471126.09 | 0 | 0 | 0 | 0 | 471126.09 | 2566127.23 | [5 empty] | N | CS23S | 100%
502561 | NRSWA Construction Sewer - M9 Junction 5 Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-02-06 | 2017-09-14 | 2017-09-21 | 2018-03-16 | 2018-03-16 | Falkirk | 0 | 0 | 0 | 686.51 | 12376.39 | -1505.38 | 0 | 0 | 11557.52 | 0 | 0 | 0 | 11557.52 | 0 | 0 | 0 | 0 | 11557.52 | 2566127.23 | [5 empty] | N | CS23S | 100%
502547 | NRSWA Construction Sewer - Sauchiehall St Glasgow - Streetscape Works | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-01-31 | 2017-09-26 | 2017-09-29 | 2018-05-04 | 2018-05-04 | Glasgow City | 0 | 0 | 0 | 397.56 | 54893.44 | -44441.82 | 0 | 0 | 10849.18 | 0 | 0 | 0 | 10849.18 | 0 | 0 | 0 | 0 | 10849.18 | 2566127.23 | [5 empty] | N | CS23S | 100%
502807 | NRSWA Construction Sewer A9 Dualling Luncarty to Birnam | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS3 | 2017-07-25 | 2018-03-29 | 2018-03-30 | 2021-08-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 68338 | 85958.23 | 235820.98 | 78883.27 | 469000.48 | 90347 | 0 | 0 | 559347.48 | 0 | 0 | 0 | 0 | 559347.48 | 2566127.23 | [5 empty] | N | CS23S | 100%
503147 | NRSWA Construction Sewer A90-A96 Haudagain Improvement Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2018-03-29 | 2018-07-23 | 2018-08-17 | 2021-01-29 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 74469.45 | 125640.44 | 246121.63 | 446231.52 | 0 | 0 | 0 | 446231.52 | 0 | 0 | 0 | 0 | 446231.52 | 2566127.23 | [5 empty] | N | CS23S | 100%
502863 | NRSWA Construction Sewer B9090 Realignment Clephanton | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater | SW | SWMD | NRSWA | MS7 | 2018-04-11 | 2018-05-23 | 2018-06-04 | 2018-11-30 | 2018-11-30 | Highland | 0 | 0 | 0 | 0 | 0 | 5116.33 | 0 | 0 | 5116.33 | 0 | 0 | 0 | 5116.33 | 0 | 0 | 0 | 0 | 5116.33 | 2566127.23 | [5 empty] | N | CS23S | 100%
503607 | NRSWA Construction Sewer Carman Road Rail Bridge West Dunbartonshire | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MSU | 2020-03-02 | 2020-04-06 | 2020-04-23 | 2020-09-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CS23S | 100%
502866 | NRSWA Construction Sewer Greenhills Road Widening East Kilbride | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS3 | 2018-01-31 | 2018-04-11 | 2018-06-26 | 2021-10-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 37720.03 | 453779.97 | 2382122.57 | 42384.43 | 2916007 | 219000 | 0 | 0 | 3135007 | 0 | 0 | 64993 | 64993 | 3200000 | 2566127.23 | [5 empty] | N | CS23S | 100%
502797 | NRSWA Construction Sewer Kirk Rd Widening Dunbeg Oban | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2018-03-29 | 2018-03-30 | 2018-10-26 | 2018-10-26 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 29862.91 | 163072 | 16365.89 | 0 | 209300.8 | 0 | 0 | 0 | 209300.8 | 0 | 0 | 0 | 0 | 209300.8 | 2566127.23 | [5 empty] | N | CS23S | 100%
502906 | NRSWA Construction Sewer Station Hotel Guild St Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-10-25 | 2018-03-27 | 2018-03-29 | 2018-09-27 | 2018-09-27 | Aberdeen City | 0 | 0 | 0 | 0 | 26800 | 143084.11 | 0 | 0 | 169884.11 | 0 | 0 | 0 | 169884.11 | 0 | 0 | 0 | 0 | 169884.11 | 2566127.23 | [5 empty] | N | CS23S | 100%
402335 | NRSWA Construction Sewers Forth Crossing SW-D3A | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-09-12 | 2012-05-16 | 2012-08-13 | 2015-05-04 |  | Fife | 3657684 | 0 | 7000 | 13133.6 | 0 | 0 | 0 | 0 | 20133.6 | 0 | 0 | 0 | 3677817.6 | 0 | 0 | 0 | 0 | 3677817.6 | 0 | [5 empty] | N | CM_WWI | 100%
402336 | NRSWA Construction Sewers Forth Crossing SW-D9A - B | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-09-12 | 2012-08-29 | 2012-11-19 | 2013-11-14 |  | City of Edinburgh | 409918 | 0 | -10778.56 | 0 | 0 | 0 | 0 | 0 | -10778.56 | 8778.64 | 0 | 0 | 407918.08 | 0 | 0 | 0 | 0 | 407918.08 | 0 | [5 empty] | N | CM_WWI | 100%
501625 | NRSWA Construction Water - A70 Glenbuck Road Realignment | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-01-25 | 2016-06-29 | 2016-06-30 | 2019-08-29 | 2019-08-29 | East Ayrshire | 0 | 0 | 23053 | 259685.44 | 99482.56 | 104298.53 | 97402.64 | 0 | 583922.17 | 0 | 0 | 0 | 583922.17 | 0 | 0 | 0 | 0 | 583922.17 | 38730.22 | [5 empty] | N | CS23W | 100%
501944 | NRSWA Construction Water - A71 Darvel Landslip Remedial Works | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-05-30 | 2016-06-28 | 2017-01-09 | 2017-01-09 | East Ayrshire | 0 | 0 | 2000 | 103028.74 | 0 | 0 | 0 | 0 | 105028.74 | 0 | 0 | 0 | 105028.74 | 0 | 0 | 0 | 0 | 105028.74 | 38730.22 | [5 empty] | N | CS23W | 100%
503346 | NRSWA Construction Water - A736 Brackenburn Bridge Kilmaurs | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-09-17 | 2018-11-26 | 2018-11-29 | 2019-03-11 | 2019-03-11 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 41499.35 | 10489.08 | 0 | 51988.43 | 0 | 0 | 0 | 51988.43 | 0 | 0 | 0 | 0 | 51988.43 | 38730.22 | [5 empty] | N | CS23W | 100%
502875 | NRSWA Construction Water - A827 West of Fearnan Culvert Replacement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-12-13 | 2018-01-31 | 2018-02-12 | 2018-05-17 | 2018-05-17 | Perth and Kinross | 0 | 0 | 0 | 0 | 26699.06 | 7720.64 | 0 | 0 | 34419.69 | 0 | 0 | 0 | 34419.69 | 0 | 0 | 0 | 0 | 34419.69 | 38730.22 | [5 empty] | N | CS23W | 100%
502634 | NRSWA Construction Water - A835 Leckmelm Culvert Replacement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-17 | 2017-05-31 | 2017-05-31 | 2018-10-22 | 2018-10-22 | Highland | 0 | 0 | 0 | 201.9 | 78112.3 | 115467.18 | 0 | 0 | 193781.38 | 0 | 0 | 0 | 193781.38 | 0 | 0 | 0 | 0 | 193781.38 | 38730.22 | [5 empty] | N | CS23W | 100%
503351 | NRSWA Construction Water - A887 Lagain Bhain Bridge Replacement Invermoriston | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-08-24 | 2018-12-21 | 2018-12-21 | 2021-02-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 29852.23 | 16352.89 | -5977.39 | 40227.74 | 0 | 0 | 0 | 40227.74 | 0 | 0 | 0 | 0 | 40227.74 | 38730.22 | [5 empty] | N | CS23W | 100%
502289 | NRSWA Construction Water - A913 Burnside Bridge Replacement Newburgh Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-07-26 | 2017-02-28 | 2017-02-28 | 2017-08-14 | 2017-08-14 | Fife | 0 | 0 | 0 | 25576 | 25313.18 | 0 | 0 | 0 | 50889.18 | 0 | 0 | 0 | 50889.18 | 0 | 0 | 0 | 0 | 50889.18 | 38730.22 | [5 empty] | N | CS23W | 100%
501263 | NRSWA Construction Water - A9-A85 Crieff Road Junctions | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-15 | 2016-11-30 | 2016-12-20 | 2018-02-07 | 2018-02-07 | Perth and Kinross | 0 | 0 | 11764 | 92967.83 | 240763.72 | 385338.82 | 1628.16 | 0 | 732462.53 | 0 | 0 | 0 | 732462.53 | 0 | 0 | 0 | 0 | 732462.53 | 38730.22 | [5 empty] | N | CS23W | 100%
502125 | NRSWA Construction Water - Almondbank Flood Prevention Scheme | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-02 | 2016-08-24 | 2016-09-26 | 2018-10-10 | 2018-10-10 | Perth and Kinross | 0 | 0 | 1000 | 341808 | 418205 | 32809.31 | 0 | 0 | 793822.31 | 0 | 0 | 0 | 793822.31 | 0 | 0 | 0 | 0 | 793822.31 | 38730.22 | [5 empty] | N | CS23W | 100%
502045 | NRSWA Construction Water - B714 Girthill to Yonderhouses Road Realignment | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-10-31 | 2017-07-10 | 2017-07-26 | 2017-07-26 | North Ayrshire | 0 | 0 | 1000 | 34540.19 | 6190.18 | 0 | 0 | 0 | 41730.37 | 0 | 0 | 0 | 41730.37 | 0 | 0 | 0 | 0 | 41730.37 | 38730.22 | [5 empty] | N | CS23W | 100%
502728 | NRSWA Construction Water - B792 Inchmuir Road Bathgate | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2017-09-04 | 2017-09-12 | 2017-09-14 | 2017-09-14 | West Lothian | 0 | 0 | 0 | 0 | 5430.52 | 0 | 0 | 0 | 5430.52 | 0 | 0 | 0 | 5430.52 | 0 | 0 | 0 | 0 | 5430.52 | 38730.22 | [5 empty] | N | CS23W | 100%
503399 | NRSWA Construction Water - B936 Freuchie Bridge Deck Replacement Freuchie Fife | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-09-18 | 2018-10-17 | 2018-11-05 | 2019-01-03 | 2019-01-03 | Fife | 0 | 0 | 0 | 0 | 0 | 14310.48 | 0 | 0 | 14310.48 | 0 | 0 | 0 | 14310.48 | 0 | 0 | 0 | 0 | 14310.48 | 38730.22 | [5 empty] | N | CS23W | 100%
503348 | NRSWA Construction Water - B966 Abbeyton Bridge Fordoun Aberdeenshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-08-24 | 2019-02-26 | 2019-03-28 | 2021-02-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 32194.49 | 43540.7 | -38024.78 | 37710.41 | 0 | 0 | 0 | 37710.41 | 0 | 0 | 0 | 0 | 37710.41 | 38730.22 | [5 empty] | N | CS23W | 100%
503345 | NRSWA Construction Water - Baldovan Road Culvert Dundee | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-08-24 | 2018-12-20 | 2018-12-21 | 2020-05-29 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 24491.66 | 19899.17 | -11040.34 | 33350.49 | 0 | 0 | 0 | 33350.49 | 0 | 0 | 0 | 0 | 33350.49 | 38730.22 | [5 empty] | N | CS23W | 100%
502884 | NRSWA Construction Water - Balgownie Drive Retaining Wall Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-11-23 | 2018-01-08 | 2018-01-29 | 2018-09-27 | 2018-09-27 | Aberdeen City | 0 | 0 | 0 | 0 | 25685.52 | 91802.02 | 0 | 0 | 117487.54 | 0 | 0 | 0 | 117487.54 | 0 | 0 | 0 | 0 | 117487.54 | 38730.22 | [5 empty] | N | CS23W | 100%
503566 | NRSWA Construction Water - Balgraystone Road Improvements Barrhead | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-05-30 | 2019-07-23 | 2019-08-09 | 2020-02-26 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 11529.77 | 0 | 11529.77 | 0 | 0 | 0 | 11529.77 | 0 | 0 | 0 | 0 | 11529.77 | 38730.22 | [5 empty] | N | CS23W | 100%
501627 | NRSWA Construction Water - Bishopbriggs Relief Road | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-06-30 | 2016-06-30 | 2017-01-30 | 2017-01-30 | East Dunbartonshire | 0 | 0 | 2438 | 182099.91 | -1240.72 | 0 | 0 | 0 | 183297.19 | 0 | 0 | 0 | 183297.19 | 0 | 0 | 0 | 0 | 183297.19 | 38730.22 | [5 empty] | N | CS23W | 100%
501626 | NRSWA Construction Water - Bush Bridge Replacement Craigellachie | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-05-30 | 2016-06-27 | 2017-01-26 | 2017-01-26 | Moray | 0 | 0 | 1219 | 43251.73 | -34848.99 | 0 | 0 | 0 | 9621.74 | 0 | 0 | 0 | 9621.74 | 0 | 0 | 0 | 0 | 9621.74 | 38730.22 | [5 empty] | N | CS23W | 100%
501629 | NRSWA Construction Water - Cathkin Relief Road | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-01-25 | 2016-06-30 | 2016-06-30 | 2017-03-29 | 2017-03-29 | South Lanarkshire | 0 | 0 | 22134 | 249939.19 | 51010.24 | 0 | 0 | 0 | 323083.43 | 0 | 0 | 0 | 323083.43 | 0 | 0 | 0 | 0 | 323083.43 | 38730.22 | [5 empty] | N | CS23W | 100%
501751 | NRSWA Construction Water - Chambers Street Statues Edinburgh | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-03-30 | 2016-04-22 | 2017-02-08 | 2017-02-08 | City of Edinburgh | 0 | 0 | 355.68 | 24952.64 | 2648.27 | 0 | 0 | 0 | 27956.59 | 0 | 0 | 0 | 27956.59 | 0 | 0 | 0 | 0 | 27956.59 | 38730.22 | [5 empty] | N | CS23W | 100%
503352 | NRSWA Construction Water - Chapleton Bridge Widening Port Glasgow | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-08-24 | 2018-11-26 | 2018-11-29 | 2019-04-26 | 2019-04-26 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 40000 | -7407.54 | 0 | 32592.46 | 0 | 0 | 0 | 32592.46 | 0 | 0 | 0 | 0 | 32592.46 | 38730.22 | [5 empty] | N | CS23W | 100%
503446 | NRSWA Construction Water - Corran Bridge Lochgilphead | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2019-02-26 | 2019-08-05 | 2019-08-12 | 2021-05-14 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 457.94 | 14092.93 | 42249.13 | 56800 | 3200.36 | 0 | 0 | 60000.36 | 0 | 0 | 0 | 0 | 60000.36 | 38730.22 | [5 empty] | N | CS23W | 100%
500986 | NRSWA Construction Water - Cowlairs Rail Bridge Glasgow | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-05-23 | 2016-06-22 | 2019-01-10 | 2019-01-10 | Glasgow City | 0 | 0 | 3770.87 | 273611.53 | -40396 | 33756.71 | 0 | 0 | 270743.11 | 0 | 0 | 0 | 270743.11 | 0 | 0 | 0 | 0 | 270743.11 | 38730.22 | [5 empty] | N | CS23W | 100%
503396 | NRSWA Construction Water - Craigend Bridge Coulter Biggar | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-11-28 | 2019-02-26 | 2019-02-26 | 2019-09-09 | 2019-09-13 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 22500.08 | 5645.67 | 0 | 28145.75 | 0 | 0 | 0 | 28145.75 | 0 | 0 | 0 | 0 | 28145.75 | 38730.22 | [5 empty] | N | CS23W | 100%
502544 | NRSWA Construction Water - Duck Bay (Loch Lomond) South Access Bridge Repairs | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-01-19 | 2017-05-29 | 2017-06-09 | 2017-08-23 | 2017-08-23 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 410 | 27284.18 | 0 | 0 | 0 | 27694.18 | 0 | 0 | 0 | 27694.18 | 0 | 0 | 0 | 0 | 27694.18 | 38730.22 | [5 empty] | N | CS23W | 100%
502000 | NRSWA Construction Water - EGIP Cleland Station Bridge Cleland | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-06-30 | 2016-07-28 | 2017-01-19 | 2017-01-19 | North Lanarkshire | 0 | 0 | 1000 | 97445 | -1390.99 | 0 | 0 | 0 | 97054.01 | 0 | 0 | 0 | 97054.01 | 0 | 0 | 0 | 0 | 97054.01 | 38730.22 | [5 empty] | N | CS23W | 100%
502545 | NRSWA Construction Water - EGIP Falkirk - Dunblane Bridge Replacements | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-08 | 2017-09-14 | 2017-09-21 | 2019-01-07 | 2019-01-07 | Stirling | 0 | 0 | 0 | 2274.83 | 233841.31 | 140172.9 | 0 | 0 | 376289.04 | 0 | 0 | 0 | 376289.04 | 0 | 0 | 0 | 0 | 376289.04 | 38730.22 | [5 empty] | N | CS23W | 100%
502560 | NRSWA Construction Water - Feabuie Culvert Replacement Culloden Inverness | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-06 | 2017-08-28 | 2017-09-18 | 2018-04-19 | 2018-04-19 | Highland | 0 | 0 | 0 | 569.85 | 35547.15 | -14686.18 | 0 | 0 | 21430.83 | 0 | 0 | 0 | 21430.83 | 0 | 0 | 0 | 0 | 21430.83 | 38730.22 | [5 empty] | N | CS23W | 100%
503547 | NRSWA Construction Water - Glasgow Airport Investment Area | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-06-25 | 2019-07-26 | 2019-09-02 | 2020-08-14 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 37000 | -5215.3 | 31784.7 | 0 | 0 | 0 | 31784.7 | 0 | 0 | 0 | 0 | 31784.7 | 38730.22 | [5 empty] | N | CS23W | 100%
504548 | NRSWA Construction Water - Grandholme Pipeline | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MSU | 2020-03-02 | 2020-03-16 | 2020-04-15 | 2021-02-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 861.2 | -861.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CS23W | 100%
500961 | NRSWA Construction Water - Huntly Flood Scheme Aberdeenshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-08-29 | 2016-08-31 | 2016-11-25 | 2016-11-25 | Aberdeen City | 0 | 0 | 6312 | 109442.57 | 1196.61 | 0 | 0 | 0 | 116951.18 | 0 | 0 | 0 | 116951.18 | 0 | 0 | 0 | 0 | 116951.18 | 38730.22 | [5 empty] | N | CS23W | 100%
503350 | NRSWA Construction Water - Inverness West Link Road Phase 2 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-08-24 | 2018-12-21 | 2018-12-21 | 2020-03-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 16000 | 66568.11 | 0 | 82568.11 | 0 | 0 | 0 | 82568.11 | 0 | 0 | 0 | 0 | 82568.11 | 38730.22 | [5 empty] | N | CS23W | 100%
502189 | NRSWA Construction Water - Kirkill Culvert Replacement Nr Mouswald Dumfries | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-30 | 2016-08-24 | 2016-08-24 | 2016-08-25 | 2016-08-25 | Dumfries and Galloway | 0 | 0 | 0 | 338.87 | 0 | 0 | 0 | 0 | 338.87 | 0 | 0 | 0 | 338.87 | 0 | 0 | 0 | 0 | 338.87 | 38730.22 | [5 empty] | N | CS23W | 100%
500905 | NRSWA Construction Water - Kirkland Brae Tinwald Locharbriggs Dumfries. | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS7 | 2015-12-11 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | Dumfries and Galloway | 0 | 0 | 2159 | 100771.11 | 0 | 0 | 0 | 0 | 102930.11 | 0 | 0 | 0 | 102930.11 | 0 | 0 | 0 | 0 | 102930.11 | 38730.22 | [5 empty] | N | CS23W | 100%
502092 | NRSWA Construction Water - Lampits Road Bus Laybys Carstairs | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-17 | 2016-08-16 | 2016-09-22 | 2017-02-10 | 2017-02-10 | South Lanarkshire | 0 | 0 | 459.38 | 3901.87 | 17490.78 | 0 | 0 | 0 | 21852.03 | 0 | 0 | 0 | 21852.03 | 0 | 0 | 0 | 0 | 21852.03 | 38730.22 | [5 empty] | N | CS23W | 100%
502252 | NRSWA Construction Water - Littlemill Bridge Replacement Rankinston East Ayrshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-06-29 | 2017-12-18 | 2018-06-25 | 2021-02-03 |  | East Ayrshire | 0 | 0 | 0 | 1126.58 | 52223.42 | -8349.71 | 3631.92 | 441.14 | 49073.35 | 0 | 0 | 0 | 49073.35 | 0 | 0 | 0 | 0 | 49073.35 | 38730.22 | [5 empty] | N | CS23W | 100%
501628 | NRSWA Construction Water - Lochwinnoch Bridge Replacement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-01-25 | 2016-06-14 | 2016-06-29 | 2017-01-30 | 2017-01-30 | Renfrewshire | 0 | 0 | 3311 | 132544 | 10325.56 | 0 | 0 | 0 | 146180.56 | 0 | 0 | 0 | 146180.56 | 0 | 0 | 0 | 0 | 146180.56 | 38730.22 | [5 empty] | N | CS23W | 100%
502559 | NRSWA Construction Water - M9 Junction 5 Improvement | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-09 | 2017-12-21 | 2017-12-22 | 2018-03-16 | 2018-03-16 | Falkirk | 0 | 0 | 0 | 509.66 | 214613.32 | -83506.39 | 0 | 0 | 131616.59 | 0 | 0 | 0 | 131616.59 | 0 | 0 | 0 | 0 | 131616.59 | 38730.22 | [5 empty] | N | CS23W | 100%
503361 | NRSWA Construction Water - Muir Street Extension Motherwell | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MSU | 2020-09-08 | 2020-11-23 | 2021-03-25 | 2021-07-16 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 118.42 | -118.42 | 0 | 304.72 | 0 | 0 | 304.72 | 0 | 0 | 0 | 0 | 304.72 | 38730.22 | [5 empty] | N | CS23W | 100%
500960 | NRSWA Construction Water - Park Farm Road Bridge Linlithgow | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-02-16 | 2016-02-25 | 2016-06-27 | 2016-07-12 | West Lothian | 0 | 0 | 33673 | 21845.08 | 546.9 | 0 | 0 | 0 | 56064.98 | 0 | 0 | 0 | 56064.98 | 0 | 0 | 0 | 0 | 56064.98 | 38730.22 | [5 empty] | N | CS23W | 100%
502546 | NRSWA Construction Water - Sauchiehall St Glasgow - Streetscape Works | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-01-31 | 2017-07-31 | 2017-08-14 | 2018-07-09 | 2018-07-09 | Glasgow City | 0 | 0 | 0 | 574.41 | 169362.59 | -7381.66 | 0 | 0 | 162555.34 | 0 | 0 | 0 | 162555.34 | 0 | 0 | 0 | 0 | 162555.34 | 38730.22 | [5 empty] | N | CS23W | 100%
501321 | NRSWA Construction Water - Seatown Footbridge Cullen Moray | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-12-15 | 2016-03-16 | 2016-04-28 | 2016-09-29 | 2016-10-14 | Moray | 0 | 0 | 3733 | 38364.63 | 334.04 | 0 | 0 | 0 | 42431.67 | 0 | 0 | 0 | 42431.67 | 0 | 0 | 0 | 0 | 42431.67 | 38730.22 | [5 empty] | N | CS23W | 100%
503349 | NRSWA Construction Water - Skolie Burn Bridge Replacement Loganlea | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-08-24 | 2018-12-18 | 2019-02-08 | 2020-10-06 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 6500 | 36409.48 | 2947.78 | 45857.26 | 0 | 0 | 0 | 45857.26 | 0 | 0 | 0 | 0 | 45857.26 | 38730.22 | [5 empty] | N | CS23W | 100%
502093 | NRSWA Construction Water - Taychreggan Retaining Wall Appin Argyll | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-11 | 2016-08-29 | 2016-10-27 | 2017-03-28 | 2017-03-28 | Argyll and Bute-North Argyll | 0 | 0 | 499.11 | 20762.39 | 12801.7 | 0 | 0 | 0 | 34063.2 | 0 | 0 | 0 | 34063.2 | 0 | 0 | 0 | 0 | 34063.2 | 38730.22 | [5 empty] | N | CS23W | 100%
503406 | NRSWA Construction Water - Westburn Roundabout Cambuslang | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-12-21 | 2019-04-29 | 2019-05-01 | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 19284.11 | 238517.58 | 64.59 | 257866.28 | 0 | 0 | 0 | 257866.28 | 0 | 0 | 0 | 0 | 257866.28 | 38730.22 | [5 empty] | N | CS23W | 100%
503620 | NRSWA Construction Water A811 Lomond Rd Bridge Balloch | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-10-03 | 2020-03-31 | 2019-11-25 | 2020-03-31 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 230484.45 | 0 | 230484.45 | 0 | 0 | 0 | 230484.45 | 0 | 0 | 0 | 0 | 230484.45 | 38730.22 | [5 empty] | N | CS23W | 100%
502808 | NRSWA Construction Water A9 Dualling Luncarty to Birnam | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2017-07-26 | 2018-03-30 | 2018-03-30 | 2021-08-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 219766.03 | 593166.14 | 1169067.48 | 238627.01 | 2220626.66 | 209141 | 0 | 0 | 2429767.66 | 0 | 0 | 320232.34 | 320232.34 | 2750000 | 38730.22 | [5 empty] | N | CS23W | 100%
503146 | NRSWA Construction Water A90-A96 Haudagain Improvement Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-03-29 | 2018-07-23 | 2018-08-17 | 2021-01-29 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 84114.71 | 827288.26 | -205409.54 | 705993.43 | 0 | 0 | 0 | 705993.43 | 0 | 0 | 0 | 0 | 705993.43 | 38730.22 | [5 empty] | N | CS23W | 100%
502862 | NRSWA Construction Water B9090 Realignment Clephanton | Q&S4 | Supporting economic development | NRSWA |  |  | Water | SW | SWMD | NRSWA | MS7 | 2018-03-28 | 2018-06-28 | 2018-07-03 | 2019-02-26 | 2019-02-26 | Highland | 0 | 0 | 0 | 0 | 0 | 308101.04 | 799.01 | 0 | 308900.05 | 0 | 0 | 0 | 308900.05 | 0 | 0 | 0 | 0 | 308900.05 | 38730.22 | [5 empty] | N | CS23W | 100%
502831 | NRSWA Construction Water Baker Street - Drumfrochar Rd Greenock | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2018-01-30 | 2018-02-08 | 2019-03-11 | 2019-03-11 | Inverclyde | 0 | 0 | 0 | 0 | 34855.86 | 153944.14 | -5955.78 | 0 | 182844.22 | 0 | 0 | 0 | 182844.22 | 0 | 0 | 0 | 0 | 182844.22 | 38730.22 | [5 empty] | N | CS23W | 100%
503606 | NRSWA Construction Water Carman Road Rail Bridge Renton West Dunbartonshire | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-08-30 | 2019-09-24 | 2019-09-25 | 2020-03-31 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 17084.82 | 0 | 17084.82 | 0 | 0 | 0 | 17084.82 | 0 | 0 | 0 | 0 | 17084.82 | 38730.22 | [5 empty] | N | CS23W | 100%
503254 | NRSWA Construction Water Clyde Waterfron Renfrew | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-05-23 | 2019-03-25 | 2019-03-25 | 2022-09-30 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 62296.74 | 42784.68 | -16629.42 | 88452 | 354305.66 | 0 | 0 | 442757.66 | 0 | 0 | 0 | 0 | 442757.66 | 38730.22 | [5 empty] | N | CS23W | 100%
503265 | NRSWA Construction Water Clyde Waterfron Renfrew - TRIAL HOLE | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-05-29 | 2018-06-27 | 2018-06-27 | 2018-08-01 | 2018-08-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 19592.06 | 0 | 0 | 19592.06 | 0 | 0 | 0 | 19592.06 | 0 | 0 | 0 | 0 | 19592.06 | 38730.22 | [5 empty] | N | CS23W | 100%
402329 | NRSWA Construction Water Forth Crossing SWW11 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2012-08-29 | 2012-10-15 | 2015-04-01 |  | City of Edinburgh | 469402 | 0 | 30084.6 | 0 | 0 | 0 | 0 | 0 | 30084.6 | 0 | 0 | 0 | 499486.6 | 0 | 0 | 0 | 0 | 499486.6 | 0 | [5 empty] | N | CM_WSI | 100%
402330 | NRSWA Construction Water Forth Crossing SWW14 - 15 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2012-07-23 | 2012-09-24 | 2016-07-21 |  | City of Edinburgh | 246338 | 0 | 2346 | 62267.85 | 0 | 0 | 0 | 0 | 64613.85 | 0 | 0 | 0 | 310951.85 | 0 | 0 | 0 | 0 | 310951.85 | 0 | [5 empty] | N | CM_WSI | 100%
402331 | NRSWA Construction Water Forth Crossing SWW16 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2013-06-24 | 2013-11-18 | 2015-11-26 |  | Fife | 50172 | 0 | 28502.85 | 0 | 0 | 0 | 0 | 0 | 28502.85 | 0 | 0 | 0 | 78674.85 | 0 | 0 | 0 | 0 | 78674.85 | 0 | [5 empty] | N | CM_WSI | 100%
402332 | NRSWA Construction Water Forth Crossing SWW18 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2012-07-26 | 2012-09-17 | 2015-12-10 |  | Fife | 223077 | 0 | 166796 | 25732.56 | 1043.79 | 6414.86 | 0 | 0 | 199987.21 | 0 | 0 | 0 | 423064.21 | 0 | 0 | 0 | 0 | 423064.21 | 0 | [5 empty] | N | CM_WSI | 100%
402333 | NRSWA Construction Water Forth Crossing SWW25 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-08 | 2012-07-26 | 2013-05-13 | 2014-03-06 |  | City of Edinburgh | 45067.05 | 0 | 168.92 | 0 | 133.92 | 0 | 0 | 0 | 302.84 | 13859.77 | 0 | 0 | 59229.66 | 0 | 0 | 0 | 0 | 59229.66 | 0 | [5 empty] | N | CM_WSI | 100%
402326 | NRSWA Construction Water Forth Crossing SWW5 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-06 | 2012-07-20 | 2012-09-17 | 2015-11-26 |  | City of Edinburgh | 104893 | 0 | 42733.59 | 163.19 | 0 | 0 | 0 | 0 | 42896.78 | 0 | 0 | 0 | 147789.78 | 0 | 0 | 0 | 0 | 147789.78 | 0 | [5 empty] | N | CM_WSI | 100%
402327 | NRSWA Construction Water Forth Crossing SWW7 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-06 | 2012-07-26 | 2012-09-17 | 2015-11-26 |  | City of Edinburgh | 457227 | 0 | 290048 | 6160.58 | 273.45 | 0 | 0 | 0 | 296482.03 | 0 | 0 | 0 | 753709.03 | 0 | 0 | 0 | 0 | 753709.03 | 0 | [5 empty] | N | CM_WSI | 100%
503629 | NRSWA Construction Water Gibshill Rd Weir St Greenock | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2019-08-22 | 2019-09-24 | 2019-09-25 | 2020-03-31 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 40417.59 | 0 | 40417.59 | 0 | 0 | 0 | 40417.59 | 0 | 0 | 0 | 0 | 40417.59 | 38730.22 | [5 empty] | N | CS23W | 100%
502867 | NRSWA Construction Water Greenhills Road Widening East Kilbride | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-01-31 | 2018-04-11 | 2018-06-26 | 2021-10-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 44162.03 | 370888.04 | 1004892.94 | 50558.99 | 1470502 | 11451 | 0 | 0 | 1481953 | 0 | 0 | 18047 | 18047 | 1500000 | 38730.22 | [5 empty] | N | CS23W | 100%
502798 | NRSWA Construction Water Kirk Rd Widening Dunbeg Oban | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2018-03-26 | 2018-03-30 | 2018-10-19 | 2018-10-19 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 89717 | 420719.43 | 1335.63 | 0 | 511772.06 | 0 | 0 | 0 | 511772.06 | 0 | 0 | 0 | 0 | 511772.06 | 38730.22 | [5 empty] | N | CS23W | 100%
502737 | NRSWA Construction Water Muirhead Rd Overbridge Replacement Baillieston | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2017-11-29 | 2017-11-30 | 2019-02-04 | 2019-02-04 | Glasgow City | 0 | 0 | 0 | 0 | 172469.57 | 85750.07 | 1849.69 | 0 | 260069.32 | 0 | 0 | 0 | 260069.32 | 0 | 0 | 0 | 0 | 260069.32 | 38730.22 | [5 empty] | N | CS23W | 100%
502799 | NRSWA Construction Water Ravelrig Road Balerno | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2017-09-29 | 2017-09-29 | 2018-01-24 | 2018-03-22 | City of Edinburgh | 0 | 0 | 0 | 0 | 485000.23 | -399.96 | 0 | 0 | 484600.28 | 0 | 0 | 0 | 484600.28 | 0 | 0 | 0 | 0 | 484600.28 | 38730.22 | [5 empty] | N | CS23W | 100%
502345 | NRSWA Construction Water-11 Finlayson Drive Airdrie | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-10-07 | 2017-03-07 | 2017-03-10 | 2017-08-07 | 2017-08-07 | Perth and Kinross | 0 | 0 | 0 | 98646 | 424520.42 | 550 | 0 | 0 | 523716.42 | 0 | 0 | 0 | 523716.42 | 0 | 0 | 0 | 0 | 523716.42 | 38730.22 | [5 empty] | N | CS23W | 100%
502414 | NRSWA Construction Water-A737 Dalry Bypass | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-12-12 | 2017-09-29 | 2017-09-29 | 2020-01-30 |  | North Ayrshire | 0 | 0 | 0 | 2350 | 1032257.81 | 1472653.96 | 298320.82 | 52343.71 | 2857926.3 | 0 | 0 | 0 | 2857926.3 | 0 | 0 | 0 | 0 | 2857926.3 | 38730.22 | [5 empty] | N | CS23W | 100%
503038 | NRSWA Construction Water-A737 The Den Dalry | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-01-19 | 2018-06-29 | 2018-06-29 | 2020-03-27 |  | North Ayrshire | 0 | 0 | 0 | 0 | 2927.69 | 204424.4 | 237391.45 | 723.17 | 445466.7 | 0 | 0 | 0 | 445466.7 | 0 | 0 | 0 | 0 | 445466.7 | 38730.22 | [5 empty] | N | CS23W | 100%
503037 | NRSWA Construction Water-A77 Maybole Bypass | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS4 | 2018-01-23 | 2018-08-20 | 2018-08-31 | 2021-03-31 |  | South Ayrshire | 0 | 0 | 0 | 0 | 3469.61 | 56789.3 | 406122.27 | 641011.77 | 1107392.95 | 0 | 0 | 0 | 1107392.95 | 0 | 0 | 34607.05 | 34607.05 | 1142000 | 38730.22 | [5 empty] | N | CS23W | 100%
503138 | NRSWA Construction Water-A830 Shlatach Rail Bridge Glenfinnan | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-03-28 | 2018-11-26 | 2018-12-03 | 2021-01-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 66086 | 83414 | 40102.92 | 189602.92 | 0 | 0 | 0 | 189602.92 | 0 | 0 | 0 | 0 | 189602.92 | 38730.22 | [5 empty] | N | CS23W | 100%
503055 | NRSWA Construction Water-A9 Berriedale Braes Re-Alignment | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-01-30 | 2018-06-28 | 2018-07-02 | 2019-07-29 | 2019-07-29 | Highland | 0 | 0 | 0 | 0 | 3191.41 | 38248.61 | 31226.37 | 0 | 72666.38 | 0 | 0 | 0 | 72666.38 | 0 | 0 | 0 | 0 | 72666.38 | 38730.22 | [5 empty] | N | CS23W | 100%
503288 | NRSWA Construction Water-A9 Dualling Tay Crossing to Ballinluig | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2018-11-07 | 2021-06-21 | 2021-07-29 | 2022-04-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 15000.06 | 47999.94 | 16818.77 | 79818.77 | 1490978.49 | 0 | 0 | 1570797.26 | 0 | 0 | 0 | 0 | 1570797.26 | 38730.22 | [5 empty] | N | CS23W | 100%
502309 | NRSWA Construction Water-A95 Cromdale Footbridge Replacement Near Grantown-on-Spey | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-08-02 | 2017-01-06 | 2017-01-06 | 2017-01-26 | 2017-01-26 | Highland | 0 | 0 | 0 | 2071.79 | 546.9 | 0 | 0 | 0 | 2618.69 | 0 | 0 | 0 | 2618.69 | 0 | 0 | 0 | 0 | 2618.69 | 38730.22 | [5 empty] | N | CS23W | 100%
503081 | NRSWA Construction Water-B9006 Inshes Bridge Widening Inverness | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-03-28 | 2018-06-28 | 2018-06-28 | 2018-08-17 | 2018-08-17 | Highland | 0 | 0 | 0 | 0 | 0 | 75514.68 | 0 | 0 | 75514.68 | 0 | 0 | 0 | 75514.68 | 0 | 0 | 0 | 0 | 75514.68 | 38730.22 | [5 empty] | N | CS23W | 100%
503097 | NRSWA Construction Water-Bridgend Bridges near Stenhousemuir | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-04-11 | 2018-09-17 | 2018-10-08 | 2020-09-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 100084 | -5835.34 | 10578.27 | 104826.93 | 0 | 0 | 0 | 104826.93 | 0 | 0 | 0 | 0 | 104826.93 | 38730.22 | [5 empty] | N | CS23W | 100%
502321 | NRSWA Construction Water-Lornty Farmhouse Blairgowrie | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-10-07 | 2016-11-30 | 2017-02-10 | 2017-06-29 | 2017-07-03 | Perth and Kinross | 0 | 0 | 0 | 70604.97 | 111905.6 | 0 | 0 | 0 | 182510.57 | 0 | 0 | 0 | 182510.57 | 0 | 0 | 0 | 0 | 182510.57 | 38730.22 | [5 empty] | N | CS23W | 100%
503057 | NRSWA Construction Water-Retaining Wall on Galashiels Rd Walkerburn | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-01-23 | 2018-02-27 | 2018-03-15 | 2018-04-03 | 2018-04-03 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 8.81 | 0 | 0 | 8.81 | 0 | 0 | 0 | 8.81 | 0 | 0 | 0 | 0 | 8.81 | 38730.22 | [5 empty] | N | CS23W | 100%
502415 | NRSWA Construction Water-Slaughterhouse Park Dounby Orkney | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-12-09 | 2017-06-26 | 2017-06-30 | 2018-03-28 | 2018-03-28 | Orkney Islands | 0 | 0 | 0 | 309.57 | 58498.43 | -174.19 | 0 | 0 | 58633.81 | 0 | 0 | 0 | 58633.81 | 0 | 0 | 0 | 0 | 58633.81 | 38730.22 | [5 empty] | N | CS23W | 100%
503043 | NRSWA Construction Water-Springkell Avenue Rail Bridge Glasgow | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-01-30 | 2018-02-20 | 2018-02-21 | 2018-09-20 | 2018-09-20 | Glasgow City | 0 | 0 | 0 | 0 | 4738 | 37054.69 | 0 | 0 | 41792.69 | 0 | 0 | 0 | 41792.69 | 0 | 0 | 0 | 0 | 41792.69 | 38730.22 | [5 empty] | N | CS23W | 100%
503095 | NRSWA Construction Water-White Cart Flood Scheme Glasgow Area 36 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-04-11 | 2018-06-15 | 2018-06-26 | 2018-11-12 | 2018-11-12 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 5273.5 | 0 | 0 | 5273.5 | 0 | 0 | 0 | 5273.5 | 0 | 0 | 0 | 0 | 5273.5 | 38730.22 | [5 empty] | N | CS23W | 100%
509730 | NRSWA Edinburgh Trams (Finance) | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS3 | 2020-11-18 | 2020-12-07 | 2020-12-10 | 2023-05-15 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230095.31 | 230095.31 | 415243.75 | 0 | 0 | 645339.06 | 0 | 0 | 0 | 0 | 645339.06 | 0 | [5 empty] | N | CS23W | 100%
505384 | NRSWA Edinburgh Trams York Place to Newhaven | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2020-03-11 | 2020-05-29 | 2020-06-04 | 2024-01-19 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495239.31 | 495239.31 | 1182927.76 | 0 | 0 | 1678167.07 | 0 | 0 | 21832.93 | 21832.93 | 1700000 | 38730.22 | [5 empty] | N | CS23W | 100%
500779 | NRSWA HOLDING LINE SP Third Party - Sewer Diversions | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS7 | 2015-09-04 | 2019-09-09 | 2019-09-09 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 0 | 340509.42 | 443609.58 | 44094.33 | 0.01 | -131708.81 | 0 | 696504.53 | 0 | 0 | 0 | 696504.53 | 0 | 0 | 0 | 0 | 696504.53 | 2566127.23 | [5 empty] | N | CS23S | 100%
402624 | NRSWA HOLDING LINE SP Third Party - Sewer Diversions - 4026240000 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-03-22 | 2012-03-22 | 2012-07-10 | 2015-08-28 |  | Scottish Water Wide | 608000 | 0 | 103499.77 | 569.4 | 88.64 | 0 | 0 | 0 | 104157.81 | 0 | 0 | 0 | 712157.81 | 0 | 0 | 0 | 0 | 712157.81 | 0 | [5 empty] | N | CM_WWI | 100%
500778 | NRSWA HOLDING LINE SP Third Party - Water Diversions | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS7 | 2015-09-04 | 2019-09-30 | 2019-09-13 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 0 | 462256 | 697623 | 25553.95 | -25181.93 | -201300.56 | 0 | 958950.46 | 0 | 0 | 0 | 958950.46 | 0 | 0 | 0 | 0 | 958950.46 | 38730.22 | [5 empty] | N | CS23W | 100%
402623 | NRSWA HOLDING LINE SP Third Party - Water Diversions - 4026230000 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-03-22 | 2012-03-22 | 2012-07-03 | 2015-08-28 |  | Scottish Water Wide | 917216.93 | 0 | 410399.61 | 584.4 | 0 | 5.54 | 0 | 0 | 410989.55 | 0 | 0 | 0 | 1328206.48 | 0 | 0 | 0 | 0 | 1328206.48 | 0 | [5 empty] | N | CM_WSI | 100%
503301 | NRSWA HOLDING LINE SP Third Party-SR18 Sewer Diversions | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS0 | 2018-07-27 | 2021-05-31 | 2021-05-31 | 2021-05-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 382454 | -109392.09 | 246091.08 | 519152.99 | 227521.68 | 0 | 0 | 746674.67 | 0 | 0 | 0 | 0 | 746674.67 | 2566127.23 | [5 empty] | N | CS23S | 100%
503300 | NRSWA HOLDING LINE SP Third Party-SR18 Water Diversions | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2018-07-27 | 2021-06-07 | 2021-06-07 | 2021-06-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 96715.44 | 1593605.92 | 882983.57 | 2573304.93 | 76661.71 | 0 | 0 | 2649966.64 | 0 | 0 | 0 | 0 | 2649966.64 | 38730.22 | [5 empty] | N | CS23W | 100%
500781 | NRSWA Non Rechargeable C3 Sewer Estimates Scotland Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS7 | 2015-09-04 | 2019-09-25 | 2019-09-02 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 0 | 24229.99 | 74820.55 | 42974.83 | 0 | -77025 | 0 | 65000.37 | 0 | 0 | 0 | 65000.37 | 0 | 0 | 0 | 0 | 65000.37 | 2566127.23 | [5 empty] | N | CS23S | 100%
503297 | NRSWA Non Rechargeable C3 Sewer Estimates-SR18 Scotland Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-06-02 | 2021-06-02 | 2021-06-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 47909.01 | 49053.53 | -17178.56 | 79783.98 | 216 | 0 | 0 | 79999.98 | 0 | 0 | 0 | 0 | 79999.98 | 0 | [5 empty] | N | CS23S | 100%
500780 | NRSWA Non Rechargeable C3 Water Estimates Scotland Water Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS7 | 2015-09-04 | 2019-09-09 | 2019-09-09 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 0 | 182121.86 | 13898.26 | 115590 | 2619.42 | 8284.5 | 0 | 322514.04 | 0 | 0 | 0 | 322514.04 | 0 | 0 | 0 | 0 | 322514.04 | 38730.22 | [5 empty] | N | CS23W | 100%
503296 | NRSWA Non Rechargeable C3 Water Estimates-SR18 Scotland Wide | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-05-24 | 2021-05-24 | 2021-05-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 796620.51 | -592460.95 | 68808.11 | 272967.67 | 27032.33 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 38730.22 | [5 empty] | N | CS23W | 100%
502416 | NRSWA PIF Construction Sewer B936 Freuchie Bridge Deck | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-12-09 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | Fife | 0 | 0 | 0 | 1549 | -248.76 | 0 | 0 | 0 | 1300.24 | 0 | 0 | 0 | 1300.24 | 0 | 0 | 0 | 0 | 1300.24 | 2566127.23 | [5 empty] | N | CS23S | 100%
505608 | NRSWA Sewer Cross Tay Link Road | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS0 | 2020-03-30 | 2021-09-23 | 2021-11-15 | 2022-11-09 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84932.36 | 84932.36 | 35302.87 | 0 | 0 | 120235.23 | 0 | 0 | 0 | 0 | 120235.23 | 2566127.23 | [5 empty] | N | CS23S | 100%
402997 | NRSWA Wastewater Holding Line 2013-2014 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-09-27 |  |  | 2015-09-01 |  | Scottish Water Wide | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | [5 empty] | N | CM_WWI | 100%
505607 | NRSWA Water - Cross Tay Link Road | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2020-03-30 | 2021-09-27 | 2021-11-16 | 2022-11-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74820.48 | 74820.48 | 74804 | 0 | 0 | 149624.48 | 0 | 0 | 0 | 0 | 149624.48 | 38730.22 | [5 empty] | N | CS23W | 100%
508104 | NRSWA Water 18 Lake Avenue. Lanark | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2020-08-18 | 2020-10-19 | 2020-11-16 | 2021-08-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61553 | 61553 | 0 | 0 | 0 | 61553 | 0 | 0 | 0 | 0 | 61553 | 38730.22 | [5 empty] | N | CS23W | 100%
510131 | NRSWA Water A737 Beith Improvements | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2021-02-23 | 2021-11-22 | 2021-12-10 | 2022-11-18 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 12500 | 1024049.05 | 0 | 0 | 1036549.05 | 0 | 0 | 0 | 0 | 1036549.05 | 38730.22 | [5 empty] | N | CS23W | 100%
507412 | NRSWA Water A9 Dualling Lynebeg to Moy (Network Rail) | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2020-07-09 | 2020-11-24 | 2021-02-22 | 2021-02-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12830.31 | 12830.31 | 0 | 0 | 0 | 12830.31 | 0 | 0 | 0 | 0 | 12830.31 | 38730.22 | [5 empty] | N | CS23W | 100%
508022 | NRSWA Water A90 Glencarse Overbridge at St Madoes | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2020-08-11 | 2020-09-14 | 2020-09-14 | 2021-02-11 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51193.73 | 51193.73 | 0 | 0 | 0 | 51193.73 | 0 | 0 | 0 | 0 | 51193.73 | 38730.22 | [5 empty] | N | CS23W | 100%
508783 | NRSWA Water A96 Dualling Hardmuir to Fochabers | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2020-10-09 | 2020-12-22 | 2021-02-11 | 2021-02-11 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7423.3 | 7423.3 | 0 | 0 | 0 | 7423.3 | 0 | 0 | 0 | 0 | 7423.3 | 38730.22 | [5 empty] | N | CS23W | 100%
510130 | NRSWA Water B705 Shellies Bridge Reconstruction Catrine East Ayrshire | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2021-02-22 | 2021-07-19 | 2021-08-20 | 2022-07-19 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 19999.92 | 0 | 0 | 21999.92 | 0 | 0 | 0 | 0 | 21999.92 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510000 | NRSWA Water C29 Clyde Bridge Replacement Carstairs | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2021-02-12 | 2021-06-21 | 2021-07-12 | 2022-07-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 152000 | 0 | 0 | 156000 | 0 | 0 | 0 | 0 | 156000 | 38730.22 | [5 empty] | N | CS23W | 100%
402996 | NRSWA Water Holding Line 2013-2014 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-09-27 |  |  | 2015-10-09 |  | Scottish Water Wide | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | [5 empty] | N | CM_WSI | 100%
510132 | NRSWA Water M9 Winchburgh Junction Improvements | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2021-02-12 | 2021-07-19 | 2021-08-20 | 2022-07-29 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 146000 | 0 | 0 | 151000 | 0 | 0 | 0 | 0 | 151000 | 38730.22 | [5 empty] | N | CS23W | 100%
505752 | NRSWA Water Rail Bridge at Old Kilpatrick West Dunbartonshire. | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS2 | 2020-04-24 | 2020-07-23 | 2021-09-24 | 2022-04-28 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9178 | 9178 | 60884 | 0 | 0 | 70062 | 0 | 0 | 0 | 0 | 70062 | 38730.22 | [5 empty] | N | CS23W | 100%
507604 | NRSWA Water Reston Station near Eyemouth. | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2020-07-20 | 2020-12-21 | 2021-01-11 | 2021-06-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281727.95 | 281727.95 | 28023 | 0 | 0 | 309750.95 | 0 | 0 | 0 | 0 | 309750.95 | 38730.22 | [5 empty] | N | CS23W | 100%
510136 | NRSWA Water South College Street Improvements Aberdeen | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2021-03-03 | 2021-07-19 | 2021-08-20 | 2022-07-19 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 61284 | 0 | 0 | 62534 | 0 | 0 | 0 | 0 | 62534 | 0 | [5 empty] | N | CS23W | 100%
501013 | NW19 - Burn Road Inverness | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-02-21 | 2020-02-21 | 2019-09-26 | 2019-09-26 | 2019-09-26 | Highland | 0 | 0 | 27500 | 34114.62 | 36956 | -98569.62 | 0 | 0 | 1 | 3277.28 | 0 | 0 | 3278.28 | 0 | 0 | 0 | 0 | 3278.28 | 180449.74 | [5 empty] | N | FL_DD | 100%
504622 | N-W-20-130120 WI Co-ag Predictors St 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-26 | 2021-10-11 | 2023-04-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 14682.05 | 12417.95 | 27100 | 192900 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 220000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500744 | NW2-N1 SR15 Avoch Flooding Project | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-01-29 | 2019-06-11 | 2019-06-11 | 2019-06-06 | 2019-06-06 | Highland | 0 | 0 | 88100 | 237348.61 | 73169.7 | 89227.97 | -484270.94 | 0 | 3575.34 | 0 | 0 | 0 | 3575.34 | 0 | 0 | 0 | 0 | 3575.34 | 180449.74 | [5 empty] | N | FL_DD | 100%
500088 | NW303 - Harbour Road Inverness | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2019-07-18 | 2028-04-05 | 2028-04-05 | 2019-08-16 | 2028-04-05 | Highland | 0 | 0 | 23600 | 54205.05 | 37172.89 | 36022.06 | 84234.48 | 0 | 235234.48 | 0 | 0 | 0 | 235234.48 | 0 | 0 | 0 | 0 | 235234.48 | 388163.48 | [5 empty] | N | FL_NAMED | 100%
503787 | N-Water-NI-041119-Strathpeffer-Lower-DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504182 | N-W-I_051219_Tullich WOA-Raw and Final Interface | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2019-12-10 | 2021-01-18 | 2022-04-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2459.12 | 2023.36 | 4482.48 | 20999.1 | 0 | 0 | 25481.58 | 0 | 0 | 0 | 0 | 25481.58 | 311236.79 | [5 empty] | N | WSI | 100%
504975 | N-W-I-01022020-Inverness_WOA-Modeling | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 313.1 | 0 | 313.1 | 786.9 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 311236.79 | [5 empty] | N | CM_M&G | 100%
506930 | N-W-I-010620-Colonsay_WOA-Various | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10589.46 | 10589.46 | 0 | 0 | 0 | 10589.46 | 0 | 0 | 0 | 0 | 10589.46 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506927 | N-W-I-010620-West Lewis WOA-Linshader Water Supply Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-06-11 | 2021-02-22 | 2021-05-28 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5823 | 5823 | 4876.7 | 0 | 0 | 10699.7 | 0 | 0 | 0 | 0 | 10699.7 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505483 | N-W-I-020320-Storr Springs-Spring 11 Intake | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-05-11 | 2020-10-13 | 2021-02-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6279.07 | 12705.35 | 18984.42 | 0 | 0 | 0 | 18984.42 | 0 | 0 | 0 | 0 | 18984.42 | 311236.79 | [5 empty] | N | WSI | 100%
504096 | N-W-I-02122019-Port Ellen DMA - Imereval Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2019-12-05 | 2020-11-23 | 2021-04-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 19616.5 | 219877.86 | 239494.36 | 0 | 0 | 0 | 239494.36 | 0 | 0 | 0 | 0 | 239494.36 | 311236.79 | [5 empty] | N | WSI | 100%
504127 | N-W-I-031219-Daal_Terrace_WOA-Trial_Holes | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-12-04 |  | 2019-12-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | -103.19 | 2596.81 | 0 | 0 | 0 | 2596.81 | 0 | 0 | 0 | 0 | 2596.81 | 311236.79 | [5 empty] | N | CM_M&G | 100%
510115 | N-W-I-031220-Torra_WOA-Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6307.67 | 6307.67 | 0 | 0 | 0 | 6307.67 | 0 | 0 | 0 | 0 | 6307.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509641 | N-W-I-041120 - Backies To Knoxs Corner DMA - Golspie Tower Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-10 | 2021-06-14 | 2021-11-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2930 | 2930 | 27069.9 | 0 | 0 | 29999.9 | 0 | 0 | 0 | 0 | 29999.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505034 | N-W-I-050220-Conon_Bridge-WOA-TM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 215.89 | 0 | 215.89 | 3084.11 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505547 | N-W-I-05032020 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-03-06 |  | 2020-03-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 5326.84 | 688.96 | 6015.8 | 0 | 0 | 0 | 6015.8 | 0 | 0 | 0 | 0 | 6015.8 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506509 | N-W-I-060520-Stoneybridge WOA-Borrowdale Hotel mains replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-05-12 | 2021-02-15 | 2021-07-05 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23112 | 23112 | 1785.7 | 0 | 0 | 24897.7 | 0 | 0 | 0 | 0 | 24897.7 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509119 | N-W-I-061020-Stornoway_WOA-Handrailing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-06 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504545 | N-W-I-070120-Loch_Calder_WOA-Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-01-08 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2884.52 | 0 | 2884.52 | 0 | 0 | 0 | 2884.52 | 0 | 0 | 0 | 0 | 2884.52 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506120 | N-W-I-070420-Assynt_WOA-TM_Battery | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-04-08 |  | 2020-05-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1809.07 | 1809.07 | 0 | 0 | 0 | 1809.07 | 0 | 0 | 0 | 0 | 1809.07 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507562 | N-W-I-070720-Main extension towards 28 Back. | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-07-13 | 2021-01-18 | 2021-05-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55164.36 | 55164.36 | 1670.84 | 0 | 0 | 56835.2 | 0 | 0 | 0 | 0 | 56835.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508623 | N-W-I-070920-Grimshader Overland mains replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-09-18 | 2020-12-01 | 2021-02-05 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12070.17 | 12070.17 | 0 | 0 | 0 | 12070.17 | 0 | 0 | 0 | 0 | 12070.17 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510178 | N-W-I-071220-Torra _WOA-Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-12-07 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2783.81 | 2783.81 | 35.61 | 0 | 0 | 2819.42 | 0 | 0 | 0 | 0 | 2819.42 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510592 | N-W-I-08012021-Loch_Calder_WOA-1200m Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8131.7 | 8131.7 | 428.3 | 0 | 0 | 8560 | 0 | 0 | 0 | 0 | 8560 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510594 | N-W-I-08012021-Loch_Calder_WOA-360m Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490.65 | 490.65 | 7009.36 | 0 | 0 | 7500.01 | 0 | 0 | 0 | 0 | 7500.01 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509160 | N-W-I-081020-Portree Torvaig WOA Sconser Colliemore Embankment Slip Construction | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-10-12 | 2021-04-12 | 2021-08-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6115 | 6115 | 53884.76 | 0 | 0 | 59999.76 | 0 | 0 | 0 | 0 | 59999.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506180 | N-W-I-090420-West_Lewis_WTW-Amonia_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-14 |  | 2020-05-22 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2003.71 | 2003.71 | 0 | 0 | 0 | 2003.71 | 0 | 0 | 0 | 0 | 2003.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505623 | N-WI-100320 - Mallaig WTW Gate 50 Deliverables | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-05-20 | 2020-08-31 | 2021-02-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 8497.67 | 9971.85 | 18469.52 | 0 | 0 | 0 | 18469.52 | 0 | 0 | 0 | 0 | 18469.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505639 | N-W-I-10032020-Marybank DMA-DOMS container | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369 | 0 | 0 | 1369 | 0 | 0 | 0 | 0 | 1369 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508237 | N-W-I-100820-Stornoway Sand St. Goathill development-Removal of redundant AC water main. | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-08-19 | 2020-09-03 | 2021-01-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10423.64 | 10423.64 | 0 | 0 | 0 | 10423.64 | 0 | 0 | 0 | 0 | 10423.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509733 | N-W-I-101120-Assynt_Newmore_WOA-Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-11-11 |  | 2020-11-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2413.6 | 2413.6 | 0 | 0 | 0 | 2413.6 | 0 | 0 | 0 | 0 | 2413.6 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505149 | N-W-I-110220-Tullich_WOA-TFillPoint | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-02-12 |  | 2020-03-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 4858.78 | 0 | 4858.78 | 0 | 0 | 0 | 4858.78 | 0 | 0 | 0 | 0 | 4858.78 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506555 | N-W-I-110520-Bunessan_WOA-Meters | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-05-12 |  | 2020-02-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34112.41 | 34112.41 | 0 | 0 | 0 | 34112.41 | 0 | 0 | 0 | 0 | 34112.41 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507176 | N-W-I-120620-Staffin WOA-Staffin Sartle MR | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-06-18 | 2020-11-16 | 2021-04-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76513.99 | 76513.99 | -1246.99 | 0 | 0 | 75267 | 0 | 0 | 0 | 0 | 75267 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504326 | N-W-I-121219-Bogbain_TM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-12-15 |  | 2020-01-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 7117.03 | 0 | 7117.03 | 0 | 0 | 0 | 7117.03 | 0 | 0 | 0 | 0 | 7117.03 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506595 | N-W-I-130520-Tobermory_WOA-Meter& Kiosk | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-05-13 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389.75 | 389.75 | 6090.25 | 0 | 0 | 6480 | 0 | 0 | 0 | 0 | 6480 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509250 | N-W-I-131020-Torra_WOA-Swab Chambers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-10-13 |  | 2020-11-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2518.09 | 2518.09 | 0 | 0 | 0 | 2518.09 | 0 | 0 | 0 | 0 | 2518.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504637 | N-W-I-14012020- Geocrab WOA- Stockinish to Drinshader Iron /specials replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-28 |  | 2021-07-29 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 263.99 | 13398.26 | 13662.25 | 96621.72 | 0 | 0 | 110283.97 | 0 | 0 | 0 | 0 | 110283.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504648 | N-W-I-140120-Portree_Torvaig_WOA_Sconser_Colliemore_Embankment_Slip_Design | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-01-24 | 2020-08-13 | 2020-11-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1523.36 | 9491.88 | 11015.24 | 0 | 0 | 0 | 11015.24 | 0 | 0 | 0 | 0 | 11015.24 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505730 | N-W-I-140320-Torra_WOA_Valve_Replace | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 753.15 | 0 | 753.15 | 9442.88 | 0 | 0 | 10196.03 | 0 | 0 | 0 | 0 | 10196.03 | 119022.58 | [5 empty] | N | WSNI | 100%
507566 | N-W-I-140720-Coll_WOA-Comms Pipe | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415.42 | 415.42 | 5934.58 | 0 | 0 | 6350 | 0 | 0 | 0 | 0 | 6350 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511244 | N-W-I-15022021-Gigha_WOA-Loggers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2422.55 | 2422.55 | 77.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511785 | N-W-I-15032021-Tullich_WOA-Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.1 | 327.1 | 4285.74 | 0 | 0 | 4612.84 | 0 | 0 | 0 | 0 | 4612.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503841 | N-W-I-151119- Oykel Bridge- Black Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2019-11-19 |  | 2020-02-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 11533.1 | 0 | 11533.1 | 0 | 0 | 0 | 11533.1 | 0 | 0 | 0 | 0 | 11533.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504697 | N-W-I-16012020-UigWOA-Uig Glen MR | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-02-12 |  | 2020-12-16 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1189.32 | 48413.45 | 49602.77 | 0 | 0 | 0 | 49602.77 | 0 | 0 | 0 | 0 | 49602.77 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505731 | N-W-I-160320-Gigha_WOA-Meters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-18 |  | 2020-09-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 813.06 | 13620 | 14433.06 | 0 | 0 | 0 | 14433.06 | 0 | 0 | 0 | 0 | 14433.06 | 119022.58 | [5 empty] | N | WSNI | 100%
506243 | N-W-I-160420-Lochinver_WOA-Mains_Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-04-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37754.48 | 37754.48 | 5045.52 | 0 | 0 | 42800 | 0 | 0 | 0 | 0 | 42800 | 311236.79 | [5 empty] | N | CM_M&G | 100%
507742 | N-W-I-160720-Newmore_WOA-Valve Chamber | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-17 |  | 2020-11-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10005.84 | 10005.84 | 0 | 0 | 0 | 10005.84 | 0 | 0 | 0 | 0 | 10005.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509807 | N-W-I-161120-Clachan DMA Claddach Carnish | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-22 | 2021-07-12 | 2022-03-28 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2918.36 | 2918.36 | 38109.98 | 0 | 0 | 41028.34 | 0 | 0 | 0 | 0 | 41028.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509813 | N-W-I-161120-Gravir DMA- MR at chlorination house | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-22 | 2021-10-11 | 2022-05-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2169.36 | 2169.36 | 21392.14 | 0 | 0 | 23561.5 | 0 | 0 | 0 | 0 | 23561.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509815 | N-W-I-161120-Stoneybridge DMA MR next to Loch Vaccasary | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-22 | 2021-10-11 | 2022-05-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600.57 | 2600.57 | 13426.56 | 0 | 0 | 16027.13 | 0 | 0 | 0 | 0 | 16027.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511846 | N-W-I-17032021-Backies_WOA-Tanker Point | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.91 | 529.91 | 6942.84 | 0 | 0 | 7472.75 | 0 | 0 | 0 | 0 | 7472.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509825 | N-W-I-171120- Luskentyre PMA Beach Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-11-30 | 2020-12-10 | 2021-02-05 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13006.59 | 13006.59 | 0 | 0 | 0 | 13006.59 | 0 | 0 | 0 | 0 | 13006.59 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504370 | N-W-I-171219-Drumbeg Intake- Refurb Rose | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-17 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 119022.58 | [5 empty] | N | CM_WSI | 100%
511331 | N-W-I-180221-Benbecula WOA-Iron failures phase 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-03-03 | 2022-04-11 | 2022-11-22 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4280 | 4280 | 49719.99 | 0 | 0 | 53999.99 | 0 | 0 | 0 | 0 | 53999.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504414 | N-W-I-181219-Ullapool West DMA inlet meter- Cover | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | 0 | 0 | 2650 | 0 | 0 | 0 | 0 | 2650 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510781 | N-W-I-19012021-Torra_WOA- Meter Chamber | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2021-01-24 |  | 2021-03-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1715.76 | 1715.76 | 84.24 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503868 | N-W-I-191119-Inverness_WOA-Surface Drain | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-11-19 |  | 2019-12-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 10700 | -355.89 | 10344.11 | 0 | 0 | 0 | 10344.11 | 0 | 0 | 0 | 0 | 10344.11 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506278 | N-W-I-200420-W LewisWOA-Callanish Trosdam mains replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-04-23 | 2021-01-25 | 2021-03-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26589.36 | 26589.36 | 0 | 0 | 0 | 26589.36 | 0 | 0 | 0 | 0 | 26589.36 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507769 | N-W-I-200720-Aros_&_Salen_DMA-Aros_Dead_Leg | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-07-23 | 2020-11-03 | 2021-01-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8421.99 | 8421.99 | 0 | 0 | 0 | 8421.99 | 0 | 0 | 0 | 0 | 8421.99 | 119022.58 | [5 empty] | N | WSNI | 100%
503881 | N-W-I-201119-Bowmore_DMA-Gartmain | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2019-12-16 | 2021-01-19 | 2021-01-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 3144.29 | -645.85 | 2498.44 | 0 | 0 | 0 | 2498.44 | 0 | 0 | 0 | 0 | 2498.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504749 | N-W-I-210120-Inverness_WOA-Tanker_FP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-01-22 |  | 2020-06-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3210 | -722.89 | 2487.11 | 0 | 0 | 0 | 2487.11 | 0 | 0 | 0 | 0 | 2487.11 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504747 | N-W-I-210120-Tiree_WOA-FindFix | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-01-21 |  | 2020-02-21 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 22729.27 | 0 | 22729.27 | 0 | 0 | 0 | 22729.27 | 0 | 0 | 0 | 0 | 22729.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507811 | N-W-I-210720-Backies_WOA-Scour Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-22 |  | 2020-08-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3911.68 | 3911.68 | 0 | 0 | 0 | 3911.68 | 0 | 0 | 0 | 0 | 3911.68 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509368 | N-W-I-211020-Craighouse_WOA-Chambers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2020-10-22 |  | 2021-03-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4265.31 | 4265.31 | 34.69 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504772 | N-W-I-22012020-Barra WOA-Castlebay Square branch replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-02-12 |  | 2020-03-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 5973.55 | 764.76 | 6738.31 | 0 | 0 | 0 | 6738.31 | 0 | 0 | 0 | 0 | 6738.31 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505364 | N-W-I-220220-Inverness WOA-Trial_Holes | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-02-23 |  | 2020-11-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 9735 | 9905.09 | 0 | 0 | 0 | 9905.09 | 0 | 0 | 0 | 0 | 9905.09 | 311236.79 | [5 empty] | N | CM_M&G | 100%
508876 | N-W-I-220920-Loch_Calder_WOA-MR | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511965 | N-W-I-23032021-Tullich_WOA-Model | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 1885.74 | 0 | 0 | 2029.67 | 0 | 0 | 0 | 0 | 2029.67 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507848 | N-W-I-230720-Mallaig_WOA-WM Bursts | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-08-03 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948.6 | 948.6 | 13551.4 | 0 | 0 | 14500 | 0 | 0 | 0 | 0 | 14500 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507845 | N-W-I-230720-Torra_WOA-Valves | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-23 |  | 2020-11-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9948.83 | 9948.83 | 0 | 0 | 0 | 9948.83 | 0 | 0 | 0 | 0 | 9948.83 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509436 | N-W-I-231020-South Uist WOA-Strome inlet pipework | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-09 | 2021-09-20 | 2022-05-03 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2768.36 | 2768.36 | 29352.96 | 0 | 0 | 32121.32 | 0 | 0 | 0 | 0 | 32121.32 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509943 | N-W-I-231120-Inveraray_WOA-Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2695.33 | 2695.33 | 38504.66 | 0 | 0 | 41199.99 | 0 | 0 | 0 | 0 | 41199.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505905 | N-W-I-240320-Barcaldine_Village_DMA-Modelling | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-30 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765.46 | 1765.46 | 0 | 0 | 0 | 1765.46 | 0 | 0 | 0 | 0 | 1765.46 | 311236.79 | [5 empty] | N | CM_M&G | 100%
506342 | N-W-I-240420-Loch_Calder_WOA-MR | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-04-27 |  | 2020-04-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1763.36 | 1763.36 | 0 | 0 | 0 | 1763.36 | 0 | 0 | 0 | 0 | 1763.36 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507861 | N-W-I-240720-Tullich_WOA-WM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2020-08-03 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44072.54 | 44072.54 | 226.5 | 0 | 0 | 44299.04 | 0 | 0 | 0 | 0 | 44299.04 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506809 | N-W-I-250520-Torra_WOA-Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-05-25 |  | 2020-07-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1881.5 | 1881.5 | 0 | 0 | 0 | 1881.5 | 0 | 0 | 0 | 0 | 1881.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507363 | N-W-I-250620-Newmore_WOA-Compensation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-06-29 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6457.77 | 6457.77 | 0 | 0 | 0 | 6457.77 | 0 | 0 | 0 | 0 | 6457.77 | 311236.79 | [5 empty] | N | CM_M&G | 100%
510904 | N-W-I-260120- Inverness WOA Bunker Monitoring System | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-01-28 | 2021-09-06 | 2022-01-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2410.06 | 2410.06 | 18335.47 | 0 | 0 | 20745.53 | 0 | 0 | 0 | 0 | 20745.53 | 311236.79 | [5 empty] | N | WSI | 100%
506830 | N-W-I-260520-Tullich_WOA-MH_Covers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-05-26 |  | 2020-06-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3098.46 | 3098.46 | 0 | 0 | 0 | 3098.46 | 0 | 0 | 0 | 0 | 3098.46 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504878 | N-W-I-27012020-Adabrock SR-Leaking inlet pipe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-12 |  | 2020-09-08 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 6228.13 | 4533.71 | 10761.84 | 0 | 0 | 0 | 10761.84 | 0 | 0 | 0 | 0 | 10761.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504872 | N-W-I-27012020-Stornoway County DMA- Main replacement Laxdale Lane | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-02-12 | 2020-08-28 | 2021-05-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 43.06 | 35974.02 | 36017.08 | 17528.1 | 0 | 0 | 53545.18 | 0 | 0 | 0 | 0 | 53545.18 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504871 | N-W-I-27012020-Stornoway CountyDMA-Mains replacement Laxdale lane | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2022-05-19 | 2022-06-09 | 2022-09-15 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1779.93 | 1779.93 | 0 | 0 | 0 | 1779.93 | 0 | 0 | 0 | 0 | 1779.93 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506357 | N-W-I-270420-Tobermory _WOA-Service_Pipe | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-04-28 |  | 2020-06-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4815.23 | 4815.23 | 0 | 0 | 0 | 4815.23 | 0 | 0 | 0 | 0 | 4815.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506883 | N-W-I-280520-Tullich_WOA-Air_Valves | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-05-29 |  | 2020-08-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10486.92 | 10486.92 | 0 | 0 | 0 | 10486.92 | 0 | 0 | 0 | 0 | 10486.92 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509537 | N-W-I-281020-Benbecula_WOA-Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 2056.07 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509526 | N-W-I-281020-Tobermory_WOA-Cross Connection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-11-03 | 2020-11-03 | 2020-12-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8087.94 | 8087.94 | 0 | 0 | 0 | 8087.94 | 0 | 0 | 0 | 0 | 8087.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507941 | N-W-I-290720-Armadale PS DMA - Achnabat Skerray AC Main - RCI | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-27 | 2021-06-14 | 2021-12-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14507.72 | 14507.72 | 55669.54 | 0 | 0 | 70177.26 | 0 | 0 | 0 | 0 | 70177.26 | 311236.79 | [5 empty] | N | WSI | 100%
507448 | N-W-I-300620-Torra_WOA-Burst | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-01 |  | 2020-07-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1173.5 | 1173.5 | 0 | 0 | 0 | 1173.5 | 0 | 0 | 0 | 0 | 1173.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508474 | N-W-I-310820-Armadale PS DMA - Skelpick Bettyhill AC Main UITS & over lander | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-09-03 | 2020-11-09 | 2021-02-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75606.91 | 75606.91 | 0 | 0 | 0 | 75606.91 | 0 | 0 | 0 | 0 | 75606.91 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508490 | N-W-I-310820-Tobermory_WOA-X Connection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-09-01 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646.86 | 646.86 | 7203.14 | 0 | 0 | 7850 | 0 | 0 | 0 | 0 | 7850 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503992 | N-WI-NI-261119 - Backies WTW - Membrane Valve Transmitter & Switches Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-13 | 2021-05-02 | 2021-07-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5294.08 | 3144.92 | 8439 | 66561.16 | 0 | 0 | 75000.16 | 0 | 0 | 0 | 0 | 75000.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505779 | N-W-I-Tobermory_WOA-Gullen_Dhu_Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-20 |  | 2020-05-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 71.7 | 1024.35 | 1096.05 | 0 | 0 | 0 | 1096.05 | 0 | 0 | 0 | 0 | 1096.05 | 119022.58 | [5 empty] | N | WSNI | 100%
506030 | N-W-N-010420-Diabeg_WTW-Cl_Analyser | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-03 |  | 2020-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7164.78 | 7164.78 | 0 | 0 | 0 | 7164.78 | 0 | 0 | 0 | 0 | 7164.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506024 | N-W-N-010420-Lednagullin_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-03 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212.65 | 1212.65 | 87.35 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506027 | N-W-N-010420-Thusater_DSR-Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1544.33 | 1544.33 | 65.67 | 0 | 0 | 1610 | 0 | 0 | 0 | 0 | 1610 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506065 | N-W-N-020420-Seilabost_CWT-Level_Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-06 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.41 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506070 | N-W-N-020420-Tullich_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-03 |  | 2020-04-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675.12 | 1675.12 | 0 | 0 | 0 | 1675.12 | 0 | 0 | 0 | 0 | 1675.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510940 | N-W-N-28012021-Assynt_WOA-Pipework | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1495.32 | 0 | 0 | 1599.99 | 0 | 0 | 0 | 0 | 1599.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504617 | N-W-NI 130120-Croft_Hill_CWT-Panels | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-13 |  | 2020-06-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | -316.03 | 3183.97 | 0 | 0 | 0 | 3183.97 | 0 | 0 | 0 | 0 | 3183.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503903 | N-W-NI- 211119-Kinlochbervie_WTW-Membrane | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-21 |  | 2019-11-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | -4667.21 | 10332.79 | 0 | 0 | 0 | 10332.79 | 0 | 0 | 0 | 0 | 10332.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507424 | N-W-NI 290620 -Rhenigadale WTW- intake path and chamber access | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-07 | 2021-06-14 | 2021-11-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4809.36 | 4809.36 | 5912.39 | 0 | 0 | 10721.75 | 0 | 0 | 0 | 0 | 10721.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506541 | N-W-NI-0/0520-Torra_WTW-Floc_Tank_Corrosion | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-13 | 2020-08-21 | 2021-08-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55480.08 | 55480.08 | 47366.74 | 0 | 0 | 102846.82 | 0 | 0 | 0 | 0 | 102846.82 | 119022.58 | [5 empty] | N | WSNI | 100%
504976 | N-W-NI-01022020-Ardtoe_PS-Kiosk | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1298.13 | 0 | 1298.13 | 0 | 0 | 0 | 1298.13 | 0 | 0 | 0 | 0 | 1298.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504978 | N-W-NI-01022020-Kilmaluag_WTW-Compressors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-03 |  | 2020-09-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1121.96 | 14790.02 | 15911.98 | 0 | 0 | 0 | 15911.98 | 0 | 0 | 0 | 0 | 15911.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504980 | N-W-NI-01022020-Londornoch_WTW-Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-03 |  | 2020-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2063.67 | 3748.44 | 5812.11 | 0 | 0 | 0 | 5812.11 | 0 | 0 | 0 | 0 | 5812.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504979 | N-W-NI-01022020-Peddieston_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-03 |  | 2020-02-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4108.57 | 0 | 4108.57 | 0 | 0 | 0 | 4108.57 | 0 | 0 | 0 | 0 | 4108.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504977 | N-W-NI-01022020-Portree_Torvaig_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-03 |  | 2020-05-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 1691.1 | 1828.48 | 0 | 0 | 0 | 1828.48 | 0 | 0 | 0 | 0 | 1828.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504981 | N-W-NI-01022020-Sanna_WTW-Doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-03 |  | 2020-02-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2250.47 | 0 | 2250.47 | 0 | 0 | 0 | 2250.47 | 0 | 0 | 0 | 0 | 2250.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511551 | N-W-NI-01032021-Aviemore_WTW-Motor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1371.42 | 0 | 0 | 1476.09 | 0 | 0 | 0 | 0 | 1476.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511560 | N-W-NI-01032021-Geocrab_WTW-Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1779.3 | 1779.3 | 120.7 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511539 | N-W-NI-01032021-Glenconvinth_WTW-Motor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-01 |  | 2021-06-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1371.42 | 0 | 0 | 1476.09 | 0 | 0 | 0 | 0 | 1476.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511545 | N-W-NI-01032021-North_Lochs_WTW-Guttering | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-01 |  | 2021-06-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 2400 | 0 | 0 | 2583.18 | 0 | 0 | 0 | 0 | 2583.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511556 | N-W-NI-01032021-Scourie_WTW-Access Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212.62 | 3212.62 | 37.38 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 3250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511548 | N-W-NI-01032021-Teangue_WTW-Actuators | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2142.84 | 0 | 0 | 2306.39 | 0 | 0 | 0 | 0 | 2306.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511546 | N-W-NI-01032021-Tiree_WTW-Pall Rings | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2571.42 | 0 | 0 | 2767.68 | 0 | 0 | 0 | 0 | 2767.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511555 | N-W-NI-01032021-Tullich_WTW-Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2289.72 | 2289.72 | 110.28 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505769 | N-W-NI-010320-Bunessan_WTW-Diesel_Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-03-20 | 2020-11-16 | 2021-02-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 4278.4 | 9360.63 | 13639.03 | 0 | 0 | 0 | 13639.03 | 0 | 0 | 0 | 0 | 13639.03 | 119022.58 | [5 empty] | N | WSNI | 100%
505473 | N-W-NI-010320-Bunessan_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-02 |  | 2020-05-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2179.37 | 2028.9 | 4208.27 | 0 | 0 | 0 | 4208.27 | 0 | 0 | 0 | 0 | 4208.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505475 | N-W-NI-010320-Dunnet_Head_Brough_TWP-Bldng_Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-02 |  | 2020-07-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 71.96 | 991.42 | 1063.38 | 0 | 0 | 0 | 1063.38 | 0 | 0 | 0 | 0 | 1063.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505474 | N-W-NI-010320-Inverness_WTW-Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-02 |  | 2020-05-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 1117.8 | 1202.85 | 0 | 0 | 0 | 1202.85 | 0 | 0 | 0 | 0 | 1202.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506421 | N-W-NI-010520-North Area Drought Code 2020 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-06 | 2020-07-06 | 2021-05-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54220 | 54220 | 0 | 0 | 0 | 54220 | 0 | 0 | 0 | 0 | 54220 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506917 | N-W-NI-010620-Airport_DSR-Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-03 |  | 2020-08-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2286.09 | 2286.09 | 0 | 0 | 0 | 2286.09 | 0 | 0 | 0 | 0 | 2286.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506925 | N-W-NI-010620-Bruichladdich_DSR-Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1661.77 | 1661.77 | 0 | 0 | 0 | 1661.77 | 0 | 0 | 0 | 0 | 1661.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506929 | N-W-NI-010620-Loch_Calder_WTW-Pumps | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS7 |  | 2020-06-03 |  | 2020-09-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2587.38 | 2587.38 | 0 | 0 | 0 | 2587.38 | 0 | 0 | 0 | 0 | 2587.38 | 0 | [5 empty] | N | SR15_ENV_WFD | 100%
507479 | N-W-NI-010720-Reay TWP-Building_Condition | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-07-07 | 2021-02-15 | 2021-09-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10615.09 | 10615.09 | 14406.81 | 0 | 0 | 25021.9 | 0 | 0 | 0 | 0 | 25021.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508503 | N-W-NI-010920-Eoligarry_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-01 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1682.24 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508502 | N-W-NI-010920-Tarbert_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-01 |  | 2020-10-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3607.74 | 3607.74 | 0 | 0 | 0 | 3607.74 | 0 | 0 | 0 | 0 | 3607.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508506 | N-W-NI-010920-Tiree_WTW-Filtration_Gallery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-01 |  | 2020-09-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3974.95 | 3974.95 | 0 | 0 | 0 | 3974.95 | 0 | 0 | 0 | 0 | 3974.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509067 | N-W-NI-011020-Torra_WTW-Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-01 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1587.05 | 1587.05 | -287.05 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509065 | N-W-NI-011020-Tullich_WTW-Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-01 |  | 2020-11-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3020.15 | 3020.15 | 0 | 0 | 0 | 3020.15 | 0 | 0 | 0 | 0 | 3020.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509052 | N-W-NI-011020-Waternish_WOA-Legal Fees | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822.94 | 822.94 | 4827.06 | 0 | 0 | 5650 | 0 | 0 | 0 | 0 | 5650 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510064 | N-W-NI-011220-Achnashelloch_DSR-Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-01 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 353.27 | 5046.72 | 0 | 0 | 5399.99 | 0 | 0 | 0 | 0 | 5399.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510066 | N-W-NI-011220-Dunchraig_DSR-Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-01 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 353.27 | 5046.72 | 0 | 0 | 5399.99 | 0 | 0 | 0 | 0 | 5399.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510058 | N-W-NI-011220-Glenconvinth_WTW-Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 2616.81 | 0 | 0 | 2799.99 | 0 | 0 | 0 | 0 | 2799.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510072 | N-W-NI-011220-Newmore_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-02 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2242.98 | 0 | 0 | 2399.99 | 0 | 0 | 0 | 0 | 2399.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511010 | N-W-NI-02022021-Dalmally_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-02 |  | 2021-04-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1069.46 | 1069.46 | 30.55 | 0 | 0 | 1100.01 | 0 | 0 | 0 | 0 | 1100.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511021 | N-W-NI-02022021-Uig_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511566 | N-W-NI-02032021-Camisky_Wellfield_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.29 | 317.29 | 4157.16 | 0 | 0 | 4474.45 | 0 | 0 | 0 | 0 | 4474.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505478 | N-W-NI-020320-Applecross WTW-Membrane Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-03-18 | 2020-09-01 | 2020-12-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1960.13 | 22272.57 | 24232.7 | 0 | 0 | 0 | 24232.7 | 0 | 0 | 0 | 0 | 24232.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505484 | N-W-NI-020320-Bracadale_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-03 |  | 2020-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 2300.15 | 2391.74 | 0 | 0 | 0 | 2391.74 | 0 | 0 | 0 | 0 | 2391.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505477 | N-W-NI-020320-Campbeltown_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-02 |  | 2020-08-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 157.59 | 2408.93 | 2566.52 | 0 | 0 | 0 | 2566.52 | 0 | 0 | 0 | 0 | 2566.52 | 119022.58 | [5 empty] | N | WSNI | 100%
505487 | N-W-NI-020320-Kyle_of_Lochalsh_WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-03 |  | 2020-04-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 1375.77 | 1493.53 | 0 | 0 | 0 | 1493.53 | 0 | 0 | 0 | 0 | 1493.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505486 | N-W-NI-020320-Raasay_CWT-Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-03 |  | 2020-04-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4438.83 | 0 | 4438.83 | 0 | 0 | 0 | 4438.83 | 0 | 0 | 0 | 0 | 4438.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505479 | N-W-NI-020320-Stoneybridge_WTW-Power_Supply | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-03 |  | 2020-04-22 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1533.14 | 385.11 | 1918.25 | 0 | 0 | 0 | 1918.25 | 0 | 0 | 0 | 0 | 1918.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506079 | N-W-NI-020420-Bunessan_RWP-Pump_Spares | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-06 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3514.54 | 3514.54 | 35.46 | 0 | 0 | 3550 | 0 | 0 | 0 | 0 | 3550 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509083 | N-W-NI-021020-Stornoway_Point _WOA-LP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-02 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2071.62 | 2071.62 | 3278.38 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509071 | N-W-NI-021020-Tullich_WTW-Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-02 |  | 2021-02-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3373.16 | 3373.16 | 126.84 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509084 | N-W-NI-021020-Tullich_WTW-Ferric Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-02 |  | 2020-10-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17393.77 | 17393.77 | 0 | 0 | 0 | 17393.77 | 0 | 0 | 0 | 0 | 17393.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504098 | N-W-NI-021219-Campbeltown_WTW-Pump_Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-03 |  | 2019-12-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | -105.12 | 2594.88 | 0 | 0 | 0 | 2594.88 | 0 | 0 | 0 | 0 | 2594.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504093 | N-W-NI-021219-Carradale_WTW-Media_Maniofold | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-03 |  | 2020-03-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 12900 | -706.07 | 12193.93 | 0 | 0 | 0 | 12193.93 | 0 | 0 | 0 | 0 | 12193.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504086 | N-W-NI-021219-Inveraray-Furnace Generator Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2019-12-04 |  | 2020-04-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 341.42 | 64.59 | 406.01 | 0 | 0 | 0 | 406.01 | 0 | 0 | 0 | 0 | 406.01 | 119022.58 | [5 empty] | N | WSNI | 100%
504103 | N-W-NI-021219-Stoneybridge_WTW-Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-03 |  | 2020-05-25 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | -201.87 | 1298.13 | 0 | 0 | 0 | 1298.13 | 0 | 0 | 0 | 0 | 1298.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510097 | N-W-NI-021220-Bonar_Bridge_WTW-PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-03 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2589.14 | 2589.14 | 110.85 | 0 | 0 | 2699.99 | 0 | 0 | 0 | 0 | 2699.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510075 | N-W-NI-021220-Cladich_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-02 |  | 2021-02-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3633.95 | 3633.95 | 66.03 | 0 | 0 | 3699.98 | 0 | 0 | 0 | 0 | 3699.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510089 | N-W-NI-021220-Scourie_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.42 | 0 | 0 | 1400.01 | 0 | 0 | 0 | 0 | 1400.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510074 | N-W-NI-021220-Stornoway_WTW-Lights | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-02 |  | 2021-02-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1734.27 | 1734.27 | 165.72 | 0 | 0 | 1899.99 | 0 | 0 | 0 | 0 | 1899.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504987 | N-W-NI-03022020-Glenconvinth_WTW-GeneratorSwitch | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-05 |  | 2020-03-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5518.46 | 0 | 5518.46 | 0 | 0 | 0 | 5518.46 | 0 | 0 | 0 | 0 | 5518.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511044 | N-W-NI-03022021-Achuan_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 5073.35 | 0 | 0 | 5249.99 | 0 | 0 | 0 | 0 | 5249.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511040 | N-W-NI-03022021-Aviemore_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3274.58 | 3274.58 | 17125.42 | 0 | 0 | 20400 | 0 | 0 | 0 | 0 | 20400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505540 | N-W-NI-03032020-Uist Dynasand WTW-chlorine control | Q&S4 | Sustaining existing high service for customers | Water non infrastructure |  |  | Water |  | SWMD | Water non infrastructure | MS2 |  | 2020-03-09 | 2021-04-12 | 2021-09-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 1050.89 | 1400.89 | 3892.36 | 0 | 0 | 5293.25 | 0 | 0 | 0 | 0 | 5293.25 | 119022.58 | [5 empty] | N | SR15_CMA_WSNI | 100%
511597 | N-W-NI-03032021-Bedersaig_WTW-Flow Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-04 |  | 2021-06-03 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1200 | 0 | 0 | 1291.59 | 0 | 0 | 0 | 0 | 1291.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511598 | N-W-NI-03032021-Craighouse_WTW-Guttering | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-04 |  | 2021-06-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3257.16 | 0 | 0 | 3505.76 | 0 | 0 | 0 | 0 | 3505.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511599 | N-W-NI-03032021-Torra_WTW-Doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-04 |  | 2021-06-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2571.42 | 0 | 0 | 2767.68 | 0 | 0 | 0 | 0 | 2767.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505514 | N-W-NI-030320-Port_Charlotte_WTW_Clarifier_Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-04 |  | 2020-05-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 102.55 | 1281.4 | 1383.95 | 0 | 0 | 0 | 1383.95 | 0 | 0 | 0 | 0 | 1383.95 | 119022.58 | [5 empty] | N | WSNI | 100%
506087 | N-W-NI-030420-Inverness_WTW-Telemetry_CS_Pt1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-04-06 |  | 2021-03-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23085.65 | 23085.65 | 464.35 | 0 | 0 | 23550 | 0 | 0 | 0 | 0 | 23550 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506088 | N-W-NI-030420-Inverness_WW-Telemetry_CS_Pt2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-06 |  | 2020-10-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23085.65 | 23085.65 | 0 | 0 | 0 | 23085.65 | 0 | 0 | 0 | 0 | 23085.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507518 | N-W-NI-030720-Inverness_WTW-Switchgear | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.89 | 215.89 | 3084.11 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507521 | N-W-NI-030720-Laggan_Bridge_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-08 |  | 2020-08-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.6 | 1961.6 | 0 | 0 | 0 | 1961.6 | 0 | 0 | 0 | 0 | 1961.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507517 | N-W-NI-030720-Newmore_WTW-Building Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-07 |  | 2020-09-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663.49 | 1663.49 | 0 | 0 | 0 | 1663.49 | 0 | 0 | 0 | 0 | 1663.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507523 | N-W-NI-030720-Tullich_WOA-Valves | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-07 |  | 2020-09-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10690 | 10690 | 0 | 0 | 0 | 10690 | 0 | 0 | 0 | 0 | 10690 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508571 | N-W-NI-030920-Backies_WTW-PLC Card | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-07 |  | 2020-09-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5902.1 | 5902.1 | 0 | 0 | 0 | 5902.1 | 0 | 0 | 0 | 0 | 5902.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508562 | N-W-NI-030920-Torra WOA-Meter Chamber | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-09-03 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2336.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509605 | N-W-NI-031120- Ardrishaig_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-04 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2142.42 | 2142.42 | -492.42 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 1650 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509602 | N-W-NI-031120-Londornoch_WTW-HMI | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-04 |  | 2020-11-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3162.34 | 3162.34 | 0 | 0 | 0 | 3162.34 | 0 | 0 | 0 | 0 | 3162.34 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509589 | N-W-NI-031120-Uig_WTW-Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-03 |  | 2021-02-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1393.55 | 1393.55 | 356.44 | 0 | 0 | 1749.99 | 0 | 0 | 0 | 0 | 1749.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504117 | N-W-NI-031219-Staffin_WTW_Valve_Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-03 |  | 2020-09-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | -297.55 | 1902.45 | 0 | 0 | 0 | 1902.45 | 0 | 0 | 0 | 0 | 1902.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504119 | N-W-NI-031219-Stoneybridge_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-03 |  | 2020-01-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | -192.87 | 1307.13 | 0 | 0 | 0 | 1307.13 | 0 | 0 | 0 | 0 | 1307.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510121 | N-W-NI-031220-Ballygrant_WTW-Technocover | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-03 |  | 2021-04-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2007.93 | 2007.93 | 192.06 | 0 | 0 | 2199.99 | 0 | 0 | 0 | 0 | 2199.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510113 | N-W-NI-031220-Tarbert_WI_New_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-03 |  | 2021-03-27 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123.5 | 1123.5 | 76.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511066 | N-W-NI-04022021-Loch_Bruicheach_RWI-Access Track | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549.53 | 549.53 | 7850.45 | 0 | 0 | 8399.98 | 0 | 0 | 0 | 0 | 8399.98 | 119022.58 | [5 empty] | N | CM_WSI | 100%
511619 | N-W-NI-04032021-Backies_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.43 | 222.43 | 2914.26 | 0 | 0 | 3136.69 | 0 | 0 | 0 | 0 | 3136.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511600 | N-W-NI-04032021-Campbeltown_WTW-Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-04 |  | 2021-06-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1114.26 | 0 | 0 | 1199.31 | 0 | 0 | 0 | 0 | 1199.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506440 | N-W-NI-040520-Benbecula_WTW-Pump_CS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-12 |  | 2020-07-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2651.64 | 2651.64 | 0 | 0 | 0 | 2651.64 | 0 | 0 | 0 | 0 | 2651.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506464 | N-W-NI-040520-Geocrab_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-05 |  | 2020-06-08 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2749.38 | 2749.38 | 0 | 0 | 0 | 2749.38 | 0 | 0 | 0 | 0 | 2749.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506457 | N-W-NI-040520-Kessock_TWP-Pressure_Vessel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-05 |  | 2020-07-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115.7 | 1115.7 | 0 | 0 | 0 | 1115.7 | 0 | 0 | 0 | 0 | 1115.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506441 | N-W-NI-040520-Torra_WTW-Filter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-05 |  | 2020-08-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11399.56 | 11399.56 | 0 | 0 | 0 | 11399.56 | 0 | 0 | 0 | 0 | 11399.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507018 | N-W-NI-040620-Ardfern_WTW-pH_Probes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-04 |  | 2020-06-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1705.58 | 1705.58 | 0 | 0 | 0 | 1705.58 | 0 | 0 | 0 | 0 | 1705.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507013 | N-W-NI-040620-Barra_WTW-Gas Cage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-04 |  | 2020-09-16 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668.13 | 1668.13 | 0 | 0 | 0 | 1668.13 | 0 | 0 | 0 | 0 | 1668.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507016 | N-W-NI-040620-Bunessan_WTW-Fence | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-04 |  | 2020-06-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1725.07 | 1725.07 | 0 | 0 | 0 | 1725.07 | 0 | 0 | 0 | 0 | 1725.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507024 | N-W-NI-040620-Scourie_WTW-Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-04 |  | 2020-06-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3005.04 | 3005.04 | 0 | 0 | 0 | 3005.04 | 0 | 0 | 0 | 0 | 3005.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507012 | N-W-NI-040620-Stoneybridge_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-04 |  | 2021-02-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3671.33 | 3671.33 | 78.67 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 3750 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508019 | N-W-NI-040820-Campbeltown_WTW-Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-08-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5401.27 | 5401.27 | 0 | 0 | 0 | 5401.27 | 0 | 0 | 0 | 0 | 5401.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508018 | N-W-NI-040820-Kyle_of_Lochalsh_WTW-CP Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-09-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238.13 | 1238.13 | 0 | 0 | 0 | 1238.13 | 0 | 0 | 0 | 0 | 1238.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508025 | N-W-NI-040820-Loch_Ardrishaig_WTW-DCI Controllers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-09-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8847.18 | 8847.18 | 0 | 0 | 0 | 8847.18 | 0 | 0 | 0 | 0 | 8847.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508021 | N-W-NI-040820-Loch_Calder_RWI-Guarding | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-11-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179.93 | 5179.93 | 0 | 0 | 0 | 5179.93 | 0 | 0 | 0 | 0 | 5179.93 | 119022.58 | [5 empty] | N | CM_WSI | 100%
508587 | N-W-NI-040920-Fionnphort_DSR-Ladder Gates | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-07 |  | 2020-11-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5629.66 | 5629.66 | 0 | 0 | 0 | 5629.66 | 0 | 0 | 0 | 0 | 5629.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508585 | N-W-NI-040920-Inchlaggan_WTW-Access Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12062.91 | 12062.91 | 1937.09 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 14000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508591 | N-W-NI-040920-Scourie_WTW-Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-07 |  | 2020-09-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3280.13 | 3280.13 | 0 | 0 | 0 | 3280.13 | 0 | 0 | 0 | 0 | 3280.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509623 | N-W-NI-041120-Kinlochewe_WTW-Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-09 |  | 2020-10-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2071.36 | 2071.36 | 0 | 0 | 0 | 2071.36 | 0 | 0 | 0 | 0 | 2071.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509625 | N-W-NI-041120-Kinmylees_TWP-Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-09 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 2056.06 | 0 | 0 | 2199.99 | 0 | 0 | 0 | 0 | 2199.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509627 | N-W-NI-041120-Kyle_of_Lochalsh_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-09 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9831.26 | 9831.26 | -8431.26 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509615 | N-W-NI-041120-Teangue_WTW-Filtomat | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-09 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.97 | 2819.97 | 480.02 | 0 | 0 | 3299.99 | 0 | 0 | 0 | 0 | 3299.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510143 | N-W-NI-041220-Earlish_Uig_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-07 |  | 2021-03-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210.27 | 2210.27 | 289.71 | 0 | 0 | 2499.98 | 0 | 0 | 0 | 0 | 2499.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511069 | N-W-NI-05022021-Bracadale_WTW_CIP Heater | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228.97 | 228.97 | 3271.05 | 0 | 0 | 3500.02 | 0 | 0 | 0 | 0 | 3500.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511068 | N-W-NI-05022021-Carbost_WTW-VSD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-11 |  | 2021-04-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933.67 | 1933.67 | 366.35 | 0 | 0 | 2300.02 | 0 | 0 | 0 | 0 | 2300.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505027 | N-W-NI-050220-Inverness_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 392.52 | 0 | 392.52 | 5607.48 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 6000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505047 | N-W-NI-050220-Tobermory_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-06 |  | 2020-02-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 5117.66 | 0 | 5117.66 | 0 | 0 | 0 | 5117.66 | 0 | 0 | 0 | 0 | 5117.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505561 | N-W-NI-050320 - Londornoch WTW Thickened Sludge Pump No 2 Torque Limiter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-09 |  | 2020-03-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2489.42 | 0 | 2489.42 | 0 | 0 | 0 | 2489.42 | 0 | 0 | 0 | 0 | 2489.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505558 | N-W-NI-050320-Stoneybridge WOA-Garynamonie SR sample tap | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-20 | 2021-03-22 | 2021-06-25 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 17068.36 | 17768.36 | 9250.24 | 0 | 0 | 27018.6 | 0 | 0 | 0 | 0 | 27018.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506473 | N-W-NI-050520-Geocrab_WTW-Turbidity_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-06 |  | 2020-06-17 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3721.28 | 3721.28 | 0 | 0 | 0 | 3721.28 | 0 | 0 | 0 | 0 | 3721.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507041 | N-W-NI-050620-Embo_Mains_DSR-Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-08 |  | 2020-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5431.27 | 5431.27 | 0 | 0 | 0 | 5431.27 | 0 | 0 | 0 | 0 | 5431.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507042 | N-W-NI-050620-Kinlochewe_RWP-Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-08 |  | 2020-09-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2435.84 | 2435.84 | 0 | 0 | 0 | 2435.84 | 0 | 0 | 0 | 0 | 2435.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508057 | N-W-NI-050820-Campbeltown_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-05 |  | 2020-08-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1211.05 | 1211.05 | 0 | 0 | 0 | 1211.05 | 0 | 0 | 0 | 0 | 1211.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509098 | N-W-NI-051020-Gravir_DSR-Inlet | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-06 |  | 2021-02-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056.35 | 1056.35 | 243.65 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509656 | N-W-NI-051120-Ardrishaig_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-09 |  | 2021-02-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3652.38 | 3652.38 | -1452.4 | 0 | 0 | 2199.98 | 0 | 0 | 0 | 0 | 2199.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509654 | N-W-NI-051120-Lismore_Primary_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-09 |  | 2021-02-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.89 | 255.89 | 2144.1 | 0 | 0 | 2399.99 | 0 | 0 | 0 | 0 | 2399.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509635 | N-W-NI-051120-Ness_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-09 |  | 2021-03-22 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12559.19 | 12559.19 | 340.8 | 0 | 0 | 12899.99 | 0 | 0 | 0 | 0 | 12899.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509657 | N-W-NI-051120-Tarbert_WTW-Container | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-09 |  | 2020-07-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7938.79 | 7938.79 | 0 | 0 | 0 | 7938.79 | 0 | 0 | 0 | 0 | 7938.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504171 | N-W-NI-051219- Cladich WTW-Chemical Waste | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2019-12-10 | 2021-01-01 | 2021-02-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2121.76 | 15508.21 | 17629.97 | 0 | 0 | 0 | 17629.97 | 0 | 0 | 0 | 0 | 17629.97 | 119022.58 | [5 empty] | N | WSNI | 100%
504533 | N-W-NI-060120-Applercross_WTW-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-07 |  | 2020-05-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | -282.49 | 3517.51 | 0 | 0 | 0 | 3517.51 | 0 | 0 | 0 | 0 | 3517.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505061 | N-W-NI-060220-Ardrishaig_WTW-DAFValve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1593.18 | 0 | 1593.18 | 26.82 | 0 | 0 | 1620 | 0 | 0 | 0 | 0 | 1620 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505584 | N-W-NI-060320-Campbeltown_WTW_Storm_Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-09 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 172.14 | 0 | 172.14 | 2459.19 | 0 | 0 | 2631.33 | 0 | 0 | 0 | 0 | 2631.33 | 119022.58 | [5 empty] | N | WSNI | 100%
505578 | N-W-NI-060320-Cladish_WTW-Storm_Damage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-06 |  | 2020-03-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 2800 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505567 | N-W-NI-060320-Gigha_WTW-DOC_repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-06 |  | 2020-04-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 87.22 | 1246 | 1333.22 | 0 | 0 | 0 | 1333.22 | 0 | 0 | 0 | 0 | 1333.22 | 119022.58 | [5 empty] | N | WSNI | 100%
512198 | N-W-NI-06042021-Aird_Low_Lift_RWP-Fan | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8999.97 | 0 | 0 | 8999.97 | 0 | 0 | 0 | 0 | 8999.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512200 | N-W-NI-06042021-Ardrishaig_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200.01 | 0 | 0 | 1200.01 | 0 | 0 | 0 | 0 | 1200.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512193 | N-W-NI-06042021-Ardrishaig_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2299.99 | 0 | 0 | 2299.99 | 0 | 0 | 0 | 0 | 2299.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512190 | N-W-NI-06042021-Assynt_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 14000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512201 | N-W-NI-06042021-Carradale_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1299.97 | 0 | 0 | 1299.97 | 0 | 0 | 0 | 0 | 1299.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512212 | N-W-NI-06042021-Loch_Ashie_DIR-Dam Clips | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8099.98 | 0 | 0 | 8099.98 | 0 | 0 | 0 | 0 | 8099.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
512228 | N-W-NI-06042021-Poolewe_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200.03 | 0 | 0 | 2200.03 | 0 | 0 | 0 | 0 | 2200.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512225 | N-W-NI-06042021-Tiree_WTW-Cl Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3699.99 | 0 | 0 | 3699.99 | 0 | 0 | 0 | 0 | 3699.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506099 | N-W-NI-060420-Ballygrant_WTW-Turbidity_Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-07 |  | 2020-05-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3274.69 | 3274.69 | 0 | 0 | 0 | 3274.69 | 0 | 0 | 0 | 0 | 3274.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506102 | N-W-NI-060420-Colonsay_WTW-WQ_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-07 |  | 2020-05-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.81 | 3881.81 | 0 | 0 | 0 | 3881.81 | 0 | 0 | 0 | 0 | 3881.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506103 | N-W-NI-060420-Lochcarron_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-07 |  | 2020-07-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1187.96 | 1187.96 | 0 | 0 | 0 | 1187.96 | 0 | 0 | 0 | 0 | 1187.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506101 | N-W-NI-060420-Torra_WTW-Instrument | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-07 |  | 2020-05-14 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225.77 | 3225.77 | 0 | 0 | 0 | 3225.77 | 0 | 0 | 0 | 0 | 3225.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509122 | N-W-NI-061020-Ardhasaig_DSR-Inlet | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-07 |  | 2021-02-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1182.85 | 1182.85 | 117.15 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509133 | N-W-NI-061020-Portnahaven_DSR-Drain | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-07 |  | 2020-11-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042.42 | 1042.42 | 0 | 0 | 0 | 1042.42 | 0 | 0 | 0 | 0 | 1042.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509673 | N-W-NI-061120-Aviemore_WTW-Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-09 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 2056.06 | 0 | 0 | 2199.99 | 0 | 0 | 0 | 0 | 2199.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504225 | N-W-NI-061219-Broadford_WTW-LCT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-06 |  | 2019-12-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | -3923.61 | 11076.39 | 0 | 0 | 0 | 11076.39 | 0 | 0 | 0 | 0 | 11076.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504216 | N-W-NI-061219-Ullapool County SR- Land Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-06 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -1967.7 | 32.3 | 1967.7 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504199 | N-W-NI-061219-West Coast Sites-HMI Critical Spare | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-06 |  | 2020-01-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | -284.15 | 7215.85 | 0 | 0 | 0 | 7215.85 | 0 | 0 | 0 | 0 | 7215.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510574 | N-W-NI-07012021-Broadford_WTW-Power Supply | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2523.36 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510573 | N-W-NI-07012021-Kilmuir_DSR-Cl Moinitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-12 |  | 2021-02-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038.6 | 2038.6 | 261.4 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510566 | N-W-NI-07012021-Kinlochewe_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2649.29 | 2649.29 | 50.71 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510569 | N-W-NI-07012021-Stornoway_WTW-Purity Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-12 |  | 2021-03-13 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456.91 | 1456.91 | 243.12 | 0 | 0 | 1700.03 | 0 | 0 | 0 | 0 | 1700.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510570 | N-W-NI-07012021-Tobermory WTW-TTU Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1588.8 | 0 | 0 | 1700.01 | 0 | 0 | 0 | 0 | 1700.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510571 | N-W-NI-07012021-Tobermory_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1682.24 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504556 | N-W-NI-070120-Inveraray_WTW-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-02-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 3840.37 | 0 | 3840.37 | 0 | 0 | 0 | 3840.37 | 0 | 0 | 0 | 0 | 3840.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504554 | N-W-NI-070120-Portnahaven_DSR-Handrails | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-26 |  | 2020-08-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 2420 | 2596.64 | 0 | 0 | 0 | 2596.64 | 0 | 0 | 0 | 0 | 2596.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505071 | N-W-NI-070220-Ardrishaig_WTW-WQMonitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-07 |  | 2020-04-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 12601.51 | 121.51 | 12723.02 | 0 | 0 | 0 | 12723.02 | 0 | 0 | 0 | 0 | 12723.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505068 | N-W-NI-070220-Ardrishaig-WTW-RunToWaste | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-02-17 | 2020-07-07 | 2021-02-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1929.64 | 13154.42 | 15084.06 | 0 | 0 | 0 | 15084.06 | 0 | 0 | 0 | 0 | 15084.06 | 119022.58 | [5 empty] | N | WSNI | 100%
505085 | N-W-NI-070220-Ludaig_TWP-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-10 |  | 2020-03-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1379.61 | 344.48 | 1724.09 | 0 | 0 | 0 | 1724.09 | 0 | 0 | 0 | 0 | 1724.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505086 | N-W-NI-070220-Tiree WTW-filter change out | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-02-28 |  | 2021-01-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 144246.02 | 145246.02 | 0 | 0 | 0 | 145246.02 | 0 | 0 | 0 | 0 | 145246.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512242 | N-W-NI-07042021-Badcaul_WTW-Pressure Switches | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512253 | N-W-NI-07042021-West_Lewis_WTW-Cl Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-07 |  | 2021-07-07 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3699.99 | 0 | 0 | 3699.99 | 0 | 0 | 0 | 0 | 3699.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506111 | N-W-NI-070420-Kilberry_WTW-Pump_Motor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-08 |  | 2020-04-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1391.49 | 1391.49 | 0 | 0 | 0 | 1391.49 | 0 | 0 | 0 | 0 | 1391.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506542 | N-W-NI-070520-AirportDSR-Control_Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-05-13 | 2021-05-10 | 2021-07-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24771.44 | 24771.44 | 13246.81 | 0 | 0 | 38018.25 | 0 | 0 | 0 | 0 | 38018.25 | 119022.58 | [5 empty] | N | WSNI | 100%
506546 | N-W-NI-070520-Tobermory_WTW-DAF_Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-05-13 | 2021-05-10 | 2021-08-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23462 | 23462 | 2093.88 | 0 | 0 | 25555.88 | 0 | 0 | 0 | 0 | 25555.88 | 119022.58 | [5 empty] | N | WSNI | 100%
507481 | N-W-NI-070720-Bayhead(New)_TWS-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-02 |  | 2020-08-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1949.53 | 1949.53 | 0 | 0 | 0 | 1949.53 | 0 | 0 | 0 | 0 | 1949.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507563 | N-W-NI-070720-Herbusta_TWP-Wiring | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-07 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507482 | N-W-NI-070720-Inveraray_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-02 |  | 2020-08-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875.05 | 875.05 | 0 | 0 | 0 | 875.05 | 0 | 0 | 0 | 0 | 875.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507544 | N-W-NI-070720-Kyle_of_Lochalsh_WTW-PLC Cards | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-07 |  | 2020-08-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7343.77 | 7343.77 | 0 | 0 | 0 | 7343.77 | 0 | 0 | 0 | 0 | 7343.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507547 | N-W-NI-070720-Londornoch _WOA-Burst Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-07 |  | 2020-10-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4014.95 | 4014.95 | 0 | 0 | 0 | 4014.95 | 0 | 0 | 0 | 0 | 4014.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507476 | N-W-NI-070720-South_Lochboisdale_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-02 |  | 2020-08-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1339.59 | 1339.59 | 0 | 0 | 0 | 1339.59 | 0 | 0 | 0 | 0 | 1339.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508121 | N-W-NI-070820-Kinlochbervie_WTW-H&S Access Issues | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-08-14 | 2021-08-09 | 2022-01-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16918 | 16918 | 23081.99 | 0 | 0 | 39999.99 | 0 | 0 | 0 | 0 | 39999.99 | 119022.58 | [5 empty] | N | WSNI | 100%
508108 | N-W-NI-070820-Kyle_of_Lochalsh_WTW-Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-10 |  | 2020-09-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1092.05 | 1092.05 | 0 | 0 | 0 | 1092.05 | 0 | 0 | 0 | 0 | 1092.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508599 | N-W-NI-070920-Inverness_WTW-Loggers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-08 |  | 2020-11-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10078.32 | 10078.32 | 0 | 0 | 0 | 10078.32 | 0 | 0 | 0 | 0 | 10078.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510168 | N-W-NI-071220 - Backies WTW - Gas migration from the sewer to the effluent holding tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-16 | 2022-05-13 | 2022-12-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426.3 | 426.3 | 25000 | 0 | 0 | 25426.3 | 0 | 0 | 0 | 0 | 25426.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510169 | N-W-NI-071220-Balallan_East_DSR-Access Steps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-08 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294.39 | 294.39 | 4205.61 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510170 | N-W-NI-071220-Ballygrant_CWT-Fence | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-08 |  | 2021-03-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800.3 | 1800.3 | 99.69 | 0 | 0 | 1899.99 | 0 | 0 | 0 | 0 | 1899.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510175 | N-W-NI-071220-Inveraray_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-07 |  | 2021-03-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1784.73 | 1784.73 | -34.71 | 0 | 0 | 1750.02 | 0 | 0 | 0 | 0 | 1750.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510597 | N-W-NI-08012021-Inverness_WTW-Switchgear | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-12 |  | 2021-02-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899.84 | 1899.84 | 100.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510576 | N-W-NI-08012021-Various SRs-Access Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-12 |  | 2021-03-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4747.27 | 4747.27 | -147.24 | 0 | 0 | 4600.03 | 0 | 0 | 0 | 0 | 4600.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504560 | N-W-NI-080120-Ullapool_Tank_DSR-Technocovers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-08 |  | 2020-05-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 162.04 | 2862.04 | 0 | 0 | 0 | 2862.04 | 0 | 0 | 0 | 0 | 2862.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511116 | N-W-NI-08022021-Assynt_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2427.65 | 2427.65 | -1127.65 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511085 | N-W-NI-08022021-Glenconvinth_WTW-Dosing Skid | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-11 |  | 2021-04-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1265.65 | 1265.65 | 34.35 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511119 | N-W-NI-080221- Camisky WTW Clean CCT and replace valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-17 | 2022-04-01 | 2022-11-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3271.03 | 3271.03 | 46728.97 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511658 | N-W-NI-08032021-Newmore_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-09 |  | 2021-06-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5744.6 | 5744.6 | -894.6 | 0 | 0 | 4850 | 0 | 0 | 0 | 0 | 4850 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507074 | N-W-NI-080620-Portree_Torvaig_WTW-UV | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-09 |  | 2020-07-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2667.39 | 2667.39 | 0 | 0 | 0 | 2667.39 | 0 | 0 | 0 | 0 | 2667.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507572 | N-W-NI-080720-Newmore_WTW-Valve Chamber | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-09 |  | 2020-09-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2357.01 | 2357.01 | 0 | 0 | 0 | 2357.01 | 0 | 0 | 0 | 0 | 2357.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508632 | N-W-NI-080920-Badcaul_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-08 |  | 2020-11-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3383.97 | 3383.97 | 0 | 0 | 0 | 3383.97 | 0 | 0 | 0 | 0 | 3383.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508648 | N-W-NI-080920-Benbecula_WTW-Flooring | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-08 |  | 2021-03-07 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2590.72 | 2590.72 | 0 | 0 | 0 | 2590.72 | 0 | 0 | 0 | 0 | 2590.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508630 | N-W-NI-080920-Campbeltown_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-08 |  | 2021-03-08 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7309.85 | 7309.85 | 0 | 0 | 0 | 7309.85 | 0 | 0 | 0 | 0 | 7309.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508650 | N-W-NI-080920-Ness_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-08 |  | 2020-03-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1930.17 | 1930.17 | 0 | 0 | 0 | 1930.17 | 0 | 0 | 0 | 0 | 1930.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508652 | N-W-NI-080920-Ness_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-14 |  | 2020-09-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2506.19 | 2506.19 | 0 | 0 | 0 | 2506.19 | 0 | 0 | 0 | 0 | 2506.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508653 | N-W-NI-080920-Stornoway_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-14 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232.24 | 232.24 | 3317.76 | 0 | 0 | 3550 | 0 | 0 | 0 | 0 | 3550 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509165 | N-W-NI-081020-Lochcarron_Kilchoan WTWs-Turbidity Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-13 | 2021-12-06 | 2022-07-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6577 | 6577 | 28423.31 | 0 | 0 | 35000.31 | 0 | 0 | 0 | 0 | 35000.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510204 | N-W-NI-081220-Keils_DSR-Technocover | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-09 |  | 2021-04-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2007.93 | 2007.93 | 192.06 | 0 | 0 | 2199.99 | 0 | 0 | 0 | 0 | 2199.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510200 | N-W-NI-081220-Port_Charlotte_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-08 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257.27 | 257.27 | 2042.73 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510199 | N-W-NI-081220-Torra_WTW-H&S Bldng | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-08 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2242.98 | 0 | 0 | 2399.99 | 0 | 0 | 0 | 0 | 2399.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504590 | N-W-NI-090120-Ullapool WTW- Soda Dosing Loading Platform | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-15 | 2020-12-04 | 2021-07-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 513.77 | 45762.23 | 46276 | 3723.66 | 0 | 0 | 49999.66 | 0 | 0 | 0 | 0 | 49999.66 | 119022.58 | [5 empty] | N | CM_M&G | 100%
511138 | N-W-NI-09022021-Torra_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1682.64 | 1682.64 | 917.36 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505089 | N-W-NI-090220-Alligin_WTW-BldngCladding | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-10 |  | 2020-09-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 11882.05 | 0 | 11882.05 | 0 | 0 | 0 | 11882.05 | 0 | 0 | 0 | 0 | 11882.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505090 | N-W-NI-090220-Badcaul_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-10 |  | 2020-03-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1661.98 | 0 | 1661.98 | 0 | 0 | 0 | 1661.98 | 0 | 0 | 0 | 0 | 1661.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505088 | N-W-NI-090220-Meavaig_WTW-FlowMeter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-10 |  | 2020-03-09 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 865.05 | 0 | 865.05 | 0 | 0 | 0 | 865.05 | 0 | 0 | 0 | 0 | 865.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505087 | N-W-NI-090220-Ness_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-10 |  | 2020-06-04 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 877.17 | 11808.07 | 12685.24 | 0 | 0 | 0 | 12685.24 | 0 | 0 | 0 | 0 | 12685.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505602 | N-W-NI-090320 - Bonar Bridge WTW Replacement Raw Water Pump Motor No.1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-10 |  | 2020-09-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1153.86 | 4120.93 | 5274.79 | 0 | 0 | 0 | 5274.79 | 0 | 0 | 0 | 0 | 5274.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505605 | N-W-NI-09032020-Ness WTW-Dynasand filter door replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-10 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 115.79 | 0 | 115.79 | 1654.21 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 1770 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505611 | N-W-NI-09032020-Rhenigadale WTW-Faulty turb monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-10 |  | 2020-04-29 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 89.56 | 980.17 | 1069.73 | 0 | 0 | 0 | 1069.73 | 0 | 0 | 0 | 0 | 1069.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511676 | N-W-NI-090320211-Glenconvinth_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-09 |  | 2021-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212.62 | 212.62 | 2785.74 | 0 | 0 | 2998.36 | 0 | 0 | 0 | 0 | 2998.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511681 | N-W-NI-09032021-Camisky_Wellfield_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-09 |  | 2021-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3354.8 | 3354.8 | 445.2 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511690 | N-W-NI-09032021-Drimnin_WTW-Cl Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-09 |  | 2021-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2363.09 | 2363.09 | 236.91 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511686 | N-W-NI-09032021-Dunvegan_Oesdale_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-09 |  | 2021-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802.91 | 1802.91 | 297.09 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511678 | N-W-NI-09032021-Inverness_WTW-Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-09 |  | 2021-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.47 | 150.47 | 1971.42 | 0 | 0 | 2121.89 | 0 | 0 | 0 | 0 | 2121.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511682 | N-W-NI-09032021-Laggan_Bridge_WTW-Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-09 |  | 2021-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477.57 | 477.57 | 6257.16 | 0 | 0 | 6734.73 | 0 | 0 | 0 | 0 | 6734.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511689 | N-W-NI-09032021-Newmore_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-09 |  | 2021-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1283.21 | 1283.21 | 416.79 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505604 | N-W-NI-090320-Tarbert_WTW-BPT_covers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-10 |  | 2020-04-08 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 4082.05 | 0 | 4082.05 | 0 | 0 | 0 | 4082.05 | 0 | 0 | 0 | 0 | 4082.05 | 119022.58 | [5 empty] | N | WSNI | 100%
505597 | N-W-NI-090320-Ullapool WTW- Soda Storage Shed Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-03-09 |  | 2021-03-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8717.06 | 8717.06 | 0 | 0 | 0 | 8717.06 | 0 | 0 | 0 | 0 | 8717.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506179 | N-W-NI-090420-Geocrab_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-14 |  | 2020-07-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5278.27 | 5278.27 | 0 | 0 | 0 | 5278.27 | 0 | 0 | 0 | 0 | 5278.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506167 | N-W-NI-090420-Newmore_WTW-Cl_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-09 |  | 2020-05-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949.47 | 3949.47 | 0 | 0 | 0 | 3949.47 | 0 | 0 | 0 | 0 | 3949.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506174 | N-W-NI-090420-Stornoway_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-09 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698.44 | 698.44 | 1301.56 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506170 | N-W-NI-090420-West_Lewis_WTW-pH_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-09 |  | 2020-06-05 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2733.64 | 2733.64 | 0 | 0 | 0 | 2733.64 | 0 | 0 | 0 | 0 | 2733.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507098 | N-W-NI-090620-Campbeltown_WTW-Turb_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-18 |  | 2020-07-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3276.25 | 3276.25 | 0 | 0 | 0 | 3276.25 | 0 | 0 | 0 | 0 | 3276.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507606 | N-W-NI-090720-Gigha_WTW-LCT_Media_Change | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-07-13 | 2020-10-20 | 2020-11-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9907.48 | 9907.48 | 0 | 0 | 0 | 9907.48 | 0 | 0 | 0 | 0 | 9907.48 | 119022.58 | [5 empty] | N | WSNI | 100%
507603 | N-W-NI-090720-Port_Charlotte_WTW-Chloram_Alarms | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-07-13 | 2021-02-15 | 2021-02-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5807 | 5807 | 0 | 0 | 0 | 5807 | 0 | 0 | 0 | 0 | 5807 | 119022.58 | [5 empty] | N | WSNI | 100%
507611 | N-W-NI-090720-Tullich_WTW-Raw_Main_Fouling | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-14 | 2021-04-12 | 2021-11-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22272.72 | 22272.72 | 30765.62 | 0 | 0 | 53038.34 | 0 | 0 | 0 | 0 | 53038.34 | 119022.58 | [5 empty] | N | WSNI | 100%
508655 | N-W-NI-090920-Stornoway_WTW-Access | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-14 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508657 | N-W-NI-090920-Stornoway_WTW-Inlet Chamber | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-14 |  | 2020-10-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900.84 | 1900.84 | 0 | 0 | 0 | 1900.84 | 0 | 0 | 0 | 0 | 1900.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508659 | N-W-NI-090920-Ullapool_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-14 |  | 2020-11-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1158.5 | 1158.5 | 0 | 0 | 0 | 1158.5 | 0 | 0 | 0 | 0 | 1158.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509189 | N-W-NI-091020-Ardfern_WTW-Access Track | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-11 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14404.53 | 14404.53 | 295.47 | 0 | 0 | 14700 | 0 | 0 | 0 | 0 | 14700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509167 | N-W-NI-091020-Benbecula_WTW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-11 |  | 2020-11-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1158.7 | 1158.7 | 0 | 0 | 0 | 1158.7 | 0 | 0 | 0 | 0 | 1158.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509166 | N-W-NI-091020-Craighouse_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-11 |  | 2020-11-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004.36 | 2004.36 | 0 | 0 | 0 | 2004.36 | 0 | 0 | 0 | 0 | 2004.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509191 | N-W-NI-091020-Dalmally_WTW-Access Track | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-11 |  | 2021-02-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9636.44 | 9636.44 | -386.44 | 0 | 0 | 9250 | 0 | 0 | 0 | 0 | 9250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509188 | N-W-NI-091020-Ludaig_TWP-Radio Link | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-11 |  | 2021-03-28 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6115.01 | 6115.01 | 384.99 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509174 | N-W-NI-091020-North_Lochs_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-11 |  | 2020-11-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2906.69 | 2906.69 | 0 | 0 | 0 | 2906.69 | 0 | 0 | 0 | 0 | 2906.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509177 | N-W-NI-091020-Saddell_WTW-Inv_Disinfection_Autoshut | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-13 | 2021-05-03 | 2021-12-14 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1582.85 | 1582.85 | 11073.48 | 0 | 0 | 12656.33 | 0 | 0 | 0 | 0 | 12656.33 | 119022.58 | [5 empty] | N | WSNI | 100%
509178 | N-W-NI-091020-Stoneybridge_WTW-Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-11 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7070.66 | 7070.66 | -870.66 | 0 | 0 | 6200 | 0 | 0 | 0 | 0 | 6200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509179 | N-W-NI-091020-Tarbert_WTW-Aztec1000_Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-14 | 2021-08-16 | 2022-03-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2188.07 | 2188.07 | 22864.5 | 0 | 0 | 25052.57 | 0 | 0 | 0 | 0 | 25052.57 | 119022.58 | [5 empty] | N | WSNI | 100%
509176 | N-W-NI-091020-Ullapool WTW- Automate Caustic Dosing and Building Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-13 | 2021-10-11 | 2022-05-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10769 | 10769 | 79231.08 | 0 | 0 | 90000.08 | 0 | 0 | 0 | 0 | 90000.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509687 | N-W-NI-091120-Applecross_WTW-Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-10 |  | 2021-04-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9903.29 | 9903.29 | 296.7 | 0 | 0 | 10199.99 | 0 | 0 | 0 | 0 | 10199.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509694 | N-W-NI-091120-Glenconvinth_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-10 |  | 2020-03-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196.25 | 1196.25 | 0 | 0 | 0 | 1196.25 | 0 | 0 | 0 | 0 | 1196.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509686 | N-W-NI-091120-Kyle_of_Lochalsh_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-09 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2412.28 | 2412.28 | 0 | 0 | 0 | 2412.28 | 0 | 0 | 0 | 0 | 2412.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509691 | N-W-NI-091120-Tullich_WTW-Ferric Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-10 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2109.84 | 2109.84 | -24.4 | 0 | 0 | 2085.44 | 0 | 0 | 0 | 0 | 2085.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504241 | N-W-NI-091219-Carbost_WTW-Heater | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-09 |  | 2020-01-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | -182.14 | 1217.86 | 0 | 0 | 0 | 1217.86 | 0 | 0 | 0 | 0 | 1217.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504260 | N-W-NI-091219-Ft_Augustus_WTW-Sand_Filter_1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2019-12-10 |  | 2020-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 224135.25 | -7769.94 | 216365.31 | 0 | 0 | 0 | 216365.31 | 0 | 0 | 0 | 0 | 216365.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504255 | N-W-NI-091219-Loch_Calder_WTW-Motor_Gearbox | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-09 |  | 2020-02-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5906.59 | 0 | 5906.59 | 0 | 0 | 0 | 5906.59 | 0 | 0 | 0 | 0 | 5906.59 | 119022.58 | [5 empty] | N | CM_WSI | 100%
510220 | N-W-NI-091220-East_Langwell_DSR-Cut Cap | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-09 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.56 | 320.56 | 4579.44 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 4900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510228 | N-W-NI-091220-Stoneybridge_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-15 |  | 2021-02-19 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188.14 | 1188.14 | 211.86 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505113 | N-W-NI-100220- Londornoch WTW - DAF Gearbox Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-11 |  | 2020-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6019.44 | 26575.56 | 32595 | 63105.63 | 0 | 0 | 95700.63 | 0 | 0 | 0 | 0 | 95700.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511162 | N-W-NI-10022021-Campbeltown_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1300 | 0 | 0 | 1385.05 | 0 | 0 | 0 | 0 | 1385.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511157 | N-W-NI-10022021-Dalmally_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4841.31 | 4841.31 | -341.31 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505099 | N-W-NI-100220-Craighouse_WTW-Intake-repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-02-17 |  | 2020-07-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 24735.99 | 25735.99 | 0 | 0 | 0 | 25735.99 | 0 | 0 | 0 | 0 | 25735.99 | 119022.58 | [5 empty] | N | WSNI | 100%
505636 | N-W-NI-100320 Loch Duntelchaig RWI Cattle Grid replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-11 |  | 2020-11-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 7442.85 | 7967.85 | 0 | 0 | 0 | 7967.85 | 0 | 0 | 0 | 0 | 7967.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505644 | n-w-ni-10032020-Tiree WTW-Turbidity ICE PIC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 89.04 | 0 | 89.04 | 1271.96 | 0 | 0 | 1361 | 0 | 0 | 0 | 0 | 1361 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505618 | N-W-NI-100320-Luing_DSR-Chlorine_Instrument | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-10 |  | 2020-05-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 191.88 | 2741.2 | 2933.08 | 0 | 0 | 0 | 2933.08 | 0 | 0 | 0 | 0 | 2933.08 | 119022.58 | [5 empty] | N | WSNI | 100%
506191 | N-W-NI-100420-Tiree_WTW-Access_Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-16 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2523.36 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508149 | N-W-NI-100820-Borve_TWP-Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-11 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1588.79 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508129 | N-W-NI-100820-Kyle_of_Lochalsh-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-11 |  | 2020-08-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020.41 | 1020.41 | 0 | 0 | 0 | 1020.41 | 0 | 0 | 0 | 0 | 1020.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508692 | N-W-NI-100920-Arinagour WTW-Replacement monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-09-30 | 2021-07-05 | 2022-02-15 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2341.36 | 2341.36 | 23680.03 | 0 | 0 | 26021.39 | 0 | 0 | 0 | 0 | 26021.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508702 | N-W-NI-100920-Bunessan_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-14 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1214.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509707 | N-W-NI-101120-Craighouse_WTW-MH Covers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-10 |  | 2021-03-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4279.31 | 4279.31 | 20.68 | 0 | 0 | 4299.99 | 0 | 0 | 0 | 0 | 4299.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509721 | N-W-NI-101120-Savalbeg_WTW-Cl Analyser | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-10 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2242.98 | 0 | 0 | 2399.99 | 0 | 0 | 0 | 0 | 2399.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509737 | N-W-NI-101120-Torra_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-11 |  | 2021-03-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1265.05 | 1265.05 | 34.94 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509712 | N-W-NI-101120-Tullich_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-10 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296.52 | 296.52 | 2603.48 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504270 | N-W-NI-101219-Inveraray_WTW-pH_Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-10 |  | 2020-03-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1554.36 | 0 | 1554.36 | 0 | 0 | 0 | 1554.36 | 0 | 0 | 0 | 0 | 1554.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504287 | N-W-NI-101219-Ness_WTW-Monitor_Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-15 |  | 2020-02-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | -361.56 | 2338.44 | 0 | 0 | 0 | 2338.44 | 0 | 0 | 0 | 0 | 2338.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504272 | N-W-NI-101219-Port Charlotte WTW - Colour Instrument | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2019-12-18 | 2021-02-01 | 2020-11-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2401.27 | 11848.74 | 14250.01 | 0 | 0 | 0 | 14250.01 | 0 | 0 | 0 | 0 | 14250.01 | 119022.58 | [5 empty] | N | WSNI | 100%
510251 | N-W-NI-101220-Drumbeg WTW- Additional Membranes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-12-16 | 2021-03-22 | 2021-05-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7790 | 7790 | 12209.99 | 0 | 0 | 19999.99 | 0 | 0 | 0 | 0 | 19999.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510633 | N-W-NI-11012021-Gigha_WTW-Manifold | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-12 |  | 2021-03-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509.83 | 1509.83 | 90.16 | 0 | 0 | 1599.99 | 0 | 0 | 0 | 0 | 1599.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510623 | N-W-NI-11012021-Ullapool_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3846.3 | 3846.3 | 153.7 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511184 | N-W-NI-11022021-Aultbea_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273.74 | 273.74 | 1542.05 | 0 | 0 | 1815.79 | 0 | 0 | 0 | 0 | 1815.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511175 | N-W-NI-11022021-Boundary_Cottage_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1773.7 | 1773.7 | 126.3 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511196 | N-W-NI-11022021-Dinvegan_TWS-Access | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-12 |  | 2021-03-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3348.6 | 3348.6 | 451.4 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511195 | N-W-NI-11022021-Earlish_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460.49 | 1460.49 | 139.51 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511194 | N-W-NI-11022021-Elgol_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1495.35 | 0 | 0 | 1600.02 | 0 | 0 | 0 | 0 | 1600.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511185 | N-W-NI-11022021-Glenconvinth_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392.52 | 392.52 | 5607.5 | 0 | 0 | 6000.02 | 0 | 0 | 0 | 0 | 6000.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511199 | N-W-NI-11022021-Inverness_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2336.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511183 | N-W-NI-11022021-Newmore_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-11 |  | 2021-05-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5084.27 | 5084.27 | 1015.73 | 0 | 0 | 6100 | 0 | 0 | 0 | 0 | 6100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505152 | N-W-NI-110220-Ardrishaig_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-12 |  | 2020-03-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 6932.49 | 0 | 6932.49 | 0 | 0 | 0 | 6932.49 | 0 | 0 | 0 | 0 | 6932.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505151 | N-W-NI-110220-Gigha_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-12 |  | 2020-03-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2044.35 | 0 | 2044.35 | 0 | 0 | 0 | 2044.35 | 0 | 0 | 0 | 0 | 2044.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505150 | N-W-NI-110220-Meavaig_WTW- Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-12 |  | 2020-03-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 2428.94 | 0 | 2428.94 | 0 | 0 | 0 | 2428.94 | 0 | 0 | 0 | 0 | 2428.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511179 | N-W-NI-110221-Inveraray_WTW-Aztec_Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-16 | 2022-02-25 | 2022-10-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1757.15 | 1757.15 | 23164.48 | 0 | 0 | 24921.63 | 0 | 0 | 0 | 0 | 24921.63 | 119022.58 | [5 empty] | N | WSNI | 100%
511749 | N-W-NI-11032021-Aviemore_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1406.54 | 1406.54 | 20093.46 | 0 | 0 | 21500 | 0 | 0 | 0 | 0 | 21500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511750 | N-W-NI-11032021-Tarbert_WI_New_WTW-pH Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-11 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 124.3 | 1628.58 | 0 | 0 | 1752.88 | 0 | 0 | 0 | 0 | 1752.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506575 | N-W-NI-110520-Geocrab_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-12 |  | 2020-06-08 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374.69 | 1374.69 | 0 | 0 | 0 | 1374.69 | 0 | 0 | 0 | 0 | 1374.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506558 | N-W-NI-110520-Laggan_Bridge_WTW-RW_Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-12 |  | 2020-07-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12813.33 | 12813.33 | 0 | 0 | 0 | 12813.33 | 0 | 0 | 0 | 0 | 12813.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506554 | N-W-NI-110520-Loch_Nell_RWPS-Raw_Sample_Tap | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-13 | 2021-03-15 | 2021-04-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31058 | 31058 | 2515.32 | 0 | 0 | 33573.32 | 0 | 0 | 0 | 0 | 33573.32 | 119022.58 | [5 empty] | N | WSNI | 100%
506571 | N-W-NI-110520-N Lochs WTW-Investigate to replace filter flow control valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-20 | 2021-01-25 | 2021-05-03 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8217.36 | 8217.36 | 2503.74 | 0 | 0 | 10721.1 | 0 | 0 | 0 | 0 | 10721.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506561 | N-W-NI-110520-Ness WTW-Alum Saturation repair investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-05-20 | 2020-08-10 | 2020-11-11 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9515.33 | 9515.33 | 0 | 0 | 0 | 9515.33 | 0 | 0 | 0 | 0 | 9515.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506573 | N-W-NI-110520-Stoneybridge_Loch_Iarras-RTU | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-12 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3508.02 | 3508.02 | 8091.98 | 0 | 0 | 11600 | 0 | 0 | 0 | 0 | 11600 | 119022.58 | [5 empty] | N | CM_WSI | 100%
506569 | N-W-NI-110520-Tarbert_Ardhasaig_DSR-RTU | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-12 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905.22 | 2905.22 | 8694.78 | 0 | 0 | 11600 | 0 | 0 | 0 | 0 | 11600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506556 | N-W-NI-110520-Tiree WTW-CWBT Bypass Inspection and repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-20 | 2021-01-14 | 2021-09-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18999.36 | 18999.36 | 131022.48 | 0 | 0 | 150021.84 | 0 | 0 | 0 | 0 | 150021.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507150 | N-W-NI-110620-Lewis and Harris WTW - Monitors trial | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-07-07 | 2022-05-13 | 2021-01-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1105.84 | 1105.84 | 0 | 0 | 0 | 1105.84 | 0 | 0 | 0 | 0 | 1105.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507152 | N-W-NI-110620-Lochmaddy WTW-Bayhead and Sollas pumping outputs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-07 | 2021-07-12 | 2021-11-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8376 | 8376 | 45124.26 | 0 | 0 | 53500.26 | 0 | 0 | 0 | 0 | 53500.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508163 | N-W-NI-110820-Diabeg_WTW-Distribution Board | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-12 |  | 2020-03-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027.85 | 2027.85 | -136.4 | 0 | 0 | 1891.45 | 0 | 0 | 0 | 0 | 1891.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508150 | N-W-NI-110820-Newmore_WTW-Oil Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-11 |  | 2020-09-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5714.44 | 5714.44 | 0 | 0 | 0 | 5714.44 | 0 | 0 | 0 | 0 | 5714.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503793 | N-W-NI-111119-Allt Airdeasaidh(Badcaul WTW)-Access Track | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-11-27 | 2021-06-14 | 2022-04-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7155 | 55009.36 | 62164.36 | 251923.52 | 0 | 0 | 314087.88 | 0 | 0 | 0 | 0 | 314087.88 | 119022.58 | [5 empty] | N | CM_WSI | 100%
509749 | N-W-NI-111120-Croft_Hill_CWT-Panels | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-11 |  | 2020-11-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2834.72 | 2834.72 | 0 | 0 | 0 | 2834.72 | 0 | 0 | 0 | 0 | 2834.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509740 | N-W-NI-111120-Tullich_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-11 |  | 2020-11-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1211.68 | 1211.68 | 0 | 0 | 0 | 1211.68 | 0 | 0 | 0 | 0 | 1211.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504288 | N-W-NI-111219-Drumbeg Intake- Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 119022.58 | [5 empty] | N | CM_WSI | 100%
504295 | N-W-NI-111219-Inveraray_WTW-Access Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-15 |  | 2020-04-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 66.92 | 10566.92 | 0 | 0 | 0 | 10566.92 | 0 | 0 | 0 | 0 | 10566.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504293 | N-W-NI-111219-Kilchoan_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-15 |  | 2020-02-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | -223.05 | 2076.95 | 0 | 0 | 0 | 2076.95 | 0 | 0 | 0 | 0 | 2076.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504289 | N-W-NI-111219-Kilchrnnan_Taynuilt_WTW-Floor_Plates | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-15 |  | 2020-08-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 3844.17 | 0 | 3844.17 | 0 | 0 | 0 | 3844.17 | 0 | 0 | 0 | 0 | 3844.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504299 | N-W-NI-111219-Newmore_WTW-Sludge_Thickener | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-15 |  | 2020-02-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5636.49 | 0 | 5636.49 | 0 | 0 | 0 | 5636.49 | 0 | 0 | 0 | 0 | 5636.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503799 | N-W-NI-111219-Sheildaig WTW- HMI Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-13 |  | 2019-11-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7210.85 | 0 | 7210.85 | 0 | 0 | 0 | 7210.85 | 0 | 0 | 0 | 0 | 7210.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504305 | N-W-NI-111219-Stornoway_WTW-Guttering | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-15 |  | 2020-03-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1405.13 | 0 | 1405.13 | 0 | 0 | 0 | 1405.13 | 0 | 0 | 0 | 0 | 1405.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504304 | N-W-NI-111219-Stornoway_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-15 |  | 2020-08-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | -15.63 | 1384.37 | 0 | 0 | 0 | 1384.37 | 0 | 0 | 0 | 0 | 1384.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510286 | N-W-NI-111220-Bonar_Bridge_WTW-Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-15 |  | 2021-02-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1549.97 | 1549.97 | 100.02 | 0 | 0 | 1649.99 | 0 | 0 | 0 | 0 | 1649.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510283 | N-W-NI-111220-Colonsay_WTW-Step H&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-15 |  | 2021-02-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8113.53 | 8113.53 | -13.53 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 8100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510281 | N-W-NI-111220-Geocrab_WTW-Cl Bund | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-15 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 124.3 | 1775.7 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510259 | N-W-NI-111220-Kinlochbervie_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-15 |  | 2021-02-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2859.06 | 2859.06 | 40.95 | 0 | 0 | 2900.01 | 0 | 0 | 0 | 0 | 2900.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510275 | N-W-NI-111220-Loch_Airidh_Na_Lic_DSR-Hydrant | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-15 |  | 2021-02-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2659.85 | 2659.85 | 40.14 | 0 | 0 | 2699.99 | 0 | 0 | 0 | 0 | 2699.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510278 | N-W-NI-111220-Port_Charlotte_WTW-Manganese _Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-16 | 2021-10-11 | 2022-05-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4298.6 | 4298.6 | 33992.97 | 0 | 0 | 38291.56 | 0 | 0 | 0 | 0 | 38291.56 | 119022.58 | [5 empty] | N | WSNI | 100%
510260 | N-W-NI-111220-Port_Ellen_DSR-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-15 |  | 2021-03-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3049.95 | 3049.95 | 1250.04 | 0 | 0 | 4299.99 | 0 | 0 | 0 | 0 | 4299.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510266 | N-W-NI-111220-Tarbert_(WI)_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-15 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 425.23 | 6074.79 | 0 | 0 | 6500.02 | 0 | 0 | 0 | 0 | 6500.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510276 | N-W-NI-111220-Tarbert_(WI)_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-15 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.49 | 0 | 0 | 1199.99 | 0 | 0 | 0 | 0 | 1199.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510280 | N-W-NI-111220-Tiree_WTW-Fire Alarm | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-15 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6405.23 | 6405.23 | 94.77 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510267 | N-W-NI-111220-Ullapool WTW- Membranes Valves H&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-16 | 2021-10-11 | 2022-05-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8660 | 8660 | 1339.94 | 0 | 0 | 9999.94 | 0 | 0 | 0 | 0 | 9999.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510264 | N-W-NI-111220-Ullapool_WTW-Air Driers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-15 |  | 2021-03-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17867.86 | 17867.86 | -867.86 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 17000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504645 | N-W-NI-120120-Melvich_Strathy_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-01-15 |  | 2020-11-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4300 | -97.89 | 4202.11 | 97.89 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504614 | N-W-NI-120120-Tarbert_WTW-Sludge_Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-12 |  | 2020-02-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | -185.35 | 1714.65 | 0 | 0 | 0 | 1714.65 | 0 | 0 | 0 | 0 | 1714.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504615 | N-W-NI-120120-Tarbert_WTW-Soda_Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-13 |  | 2020-02-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1723.91 | 0 | 1723.91 | 0 | 0 | 0 | 1723.91 | 0 | 0 | 0 | 0 | 1723.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505216 | N-W-NI-12022020-Tarbert (WI) WOA-Miavaig river crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-03-06 | 2020-09-14 | 2020-12-16 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17702.69 | 17702.69 | 0 | 0 | 0 | 17702.69 | 0 | 0 | 0 | 0 | 17702.69 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505215 | N-W-NI-12022020-Tarbert (WI)WTW-CWT valve house flooring | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS3 |  | 2020-02-28 | 2021-03-15 | 2021-07-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1243.77 | 11401.59 | 12645.36 | 3744.12 | 0 | 0 | 16389.48 | 0 | 0 | 0 | 0 | 16389.48 | 306661.32 | [5 empty] | N | CM_M&G | 100%
505217 | N-W-NI-12022020-Tarbert WTW- Recirculation tank access | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-03-06 | 2021-01-14 | 2021-05-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10021.36 | 10021.36 | 0 | 0 | 0 | 10021.36 | 0 | 0 | 0 | 0 | 10021.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511203 | N-W-NI-12022021-Gigha_WTW-Membrane | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1543.93 | 1543.93 | 22056.05 | 0 | 0 | 23599.98 | 0 | 0 | 0 | 0 | 23599.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511207 | N-W-NI-12022021-Stornoway_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1987.55 | 1987.55 | 3912.45 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 5900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511208 | N-W-NI-12022021-Tarbert_WI_New_WTW-pH Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.03 | 121.03 | 1728.95 | 0 | 0 | 1849.98 | 0 | 0 | 0 | 0 | 1849.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511204 | N-W-NI-12022021-Teangue_WTW-VSD Spares | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 915.89 | 915.89 | 18884.1 | 0 | 0 | 19799.99 | 0 | 0 | 0 | 0 | 19799.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505162 | N-W-NI-120220-Inveraray_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-12 |  | 2020-03-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1492.25 | 0 | 1492.25 | 0 | 0 | 0 | 1492.25 | 0 | 0 | 0 | 0 | 1492.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505170 | N-W-NI-120220-Kyle_RWP-VSD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-13 |  | 2020-03-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1628.72 | 0 | 1628.72 | 0 | 0 | 0 | 1628.72 | 0 | 0 | 0 | 0 | 1628.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511197 | N-W-NI-120221-Assynt WTW- Run to Waste Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-16 | 2022-05-13 | 2022-12-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635.51 | 1635.51 | 23364.46 | 0 | 0 | 24999.97 | 0 | 0 | 0 | 0 | 24999.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511186 | N-W-NI-120221-Port_Charlotte_WTW-SCADA_Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-16 | 2022-02-25 | 2022-10-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3793.14 | 3793.14 | 46201.11 | 0 | 0 | 49994.25 | 0 | 0 | 0 | 0 | 49994.25 | 119022.58 | [5 empty] | N | WSNI | 100%
511202 | N-W-NI-120221-Tomich WTW Sand Filter refurbishment and Remin Vessel media | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-16 | 2022-05-13 | 2022-12-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635.51 | 1635.51 | 23364.46 | 0 | 0 | 24999.97 | 0 | 0 | 0 | 0 | 24999.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511774 | N-W-NI-12032021-Acharacle_WTW-COSHH Access | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562.62 | 562.62 | 7371.42 | 0 | 0 | 7934.04 | 0 | 0 | 0 | 0 | 7934.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511769 | N-W-NI-12032021-Carradale_WTW-MCT_Backwash_System | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-16 | 2022-04-11 | 2022-11-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3487.41 | 3487.41 | 46512.6 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 119022.58 | [5 empty] | N | WSNI | 100%
511753 | N-W-NI-12032021-Tarbert_WI_New_WTW-Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429.8 | 1429.8 | 570.2 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511755 | N-W-NI-12032021-Tobermory_WTW-Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1457.16 | 0 | 0 | 1568.37 | 0 | 0 | 0 | 0 | 1568.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511773 | N-W-NI-12032021-Torra_WTW-Clarifier_Condition | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-16 | 2022-04-11 | 2022-11-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 727.64 | 727.64 | 10000 | 0 | 0 | 10727.64 | 0 | 0 | 0 | 0 | 10727.64 | 119022.58 | [5 empty] | N | WSNI | 100%
511752 | N-W-NI-12032021-West_Lewis_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140.65 | 140.65 | 1842.84 | 0 | 0 | 1983.49 | 0 | 0 | 0 | 0 | 1983.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505686 | N-W-NI-120320-Campbeltown_WTW-Fire_Alarm | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-12 |  | 2020-08-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 244.3 | 3490 | 3734.3 | 0 | 0 | 0 | 3734.3 | 0 | 0 | 0 | 0 | 3734.3 | 119022.58 | [5 empty] | N | WSNI | 100%
506585 | N-W-NI-120520-Dunvegan_STW-Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-08-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6339.48 | 6339.48 | 0 | 0 | 0 | 6339.48 | 0 | 0 | 0 | 0 | 6339.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506582 | N-W-NI-120520-Port_Ellen_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-13 |  | 2020-07-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100.55 | 3100.55 | 0 | 0 | 0 | 3100.55 | 0 | 0 | 0 | 0 | 3100.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506583 | N-W-NI-120520-Tarbert_Arg_WTW-Level_Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-13 |  | 2020-07-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230.5 | 1230.5 | 0 | 0 | 0 | 1230.5 | 0 | 0 | 0 | 0 | 1230.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507167 | N-W-NI-120620-Aviemore_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-12 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 210 | 3000 | 0 | 0 | 3210 | 0 | 0 | 0 | 0 | 3210 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507172 | N-W-NI-120620-Kessock_TWP-Control_Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-16 |  | 2020-07-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.52 | 1658.52 | 0 | 0 | 0 | 1658.52 | 0 | 0 | 0 | 0 | 1658.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507174 | N-W-NI-120620-Loch_Bruicheach_RWI-Inlet_Screens | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-16 |  | 2020-09-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6394.39 | 6394.39 | 0 | 0 | 0 | 6394.39 | 0 | 0 | 0 | 0 | 6394.39 | 119022.58 | [5 empty] | N | CM_WSI | 100%
507175 | N-W-NI-120620-N_Coast Loch_Calder_WTW-Power | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-16 |  | 2020-10-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7575.46 | 7575.46 | 0 | 0 | 0 | 7575.46 | 0 | 0 | 0 | 0 | 7575.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507164 | N-W-NI-120620-Tullich_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-12 |  | 2020-08-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4018.93 | 4018.93 | 0 | 0 | 0 | 4018.93 | 0 | 0 | 0 | 0 | 4018.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507170 | N-W-NI-120620-Uig_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-12 |  | 2020-08-04 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3904.16 | 3904.16 | 0 | 0 | 0 | 3904.16 | 0 | 0 | 0 | 0 | 3904.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509210 | N-W-NI-121020_Torra_WTW-Aztec_monitor_replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-19 | 2021-08-16 | 2022-03-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2836 | 2836 | 22164.45 | 0 | 0 | 25000.45 | 0 | 0 | 0 | 0 | 25000.45 | 119022.58 | [5 empty] | N | WSNI | 100%
509216 | N-W-NI-121020-Bunessan_WOA-Iona_Subsea_Main_Insp | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-19 | 2022-05-13 | 2022-12-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954 | 954 | 9045.83 | 0 | 0 | 9999.83 | 0 | 0 | 0 | 0 | 9999.83 | 119022.58 | [5 empty] | N | WSNI | 100%
509231 | N-W-NI-121020-Dunnet_Head_Brough_TWP-VSD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-13 |  | 2020-10-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275.45 | 1275.45 | 0 | 0 | 0 | 1275.45 | 0 | 0 | 0 | 0 | 1275.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509232 | N-W-NI-121020-Loch_Glass_RWP-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-13 |  | 2021-02-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1981.08 | 1981.08 | 218.92 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509200 | N-W-NI-121020-Teangue_CWT-Kiosk Wiring | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-12 |  | 2020-11-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218.89 | 2218.89 | 0 | 0 | 0 | 2218.89 | 0 | 0 | 0 | 0 | 2218.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503909 | N-W-NI-121119-Tora_WTW-Sludge_Press | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-22 |  | 2020-10-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 10969.89 | 7983.55 | 18953.44 | 0 | 0 | 0 | 18953.44 | 0 | 0 | 0 | 0 | 18953.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503804 | N-W-NI-121119-Ullapool County DSR- Tank Handrails | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-02-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 8541.71 | 0 | 8541.71 | 458.29 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 9000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504335 | N-W-NI-121219-Earlish_Uig_WTW-Heater | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-15 |  | 2020-05-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | -235.59 | 1564.41 | 0 | 0 | 0 | 1564.41 | 0 | 0 | 0 | 0 | 1564.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504312 | N-W-NI-121219-Inverness_WOA-Replacement_Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-12-15 |  | 2020-01-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | -22962.93 | 14537.07 | 0 | 0 | 0 | 14537.07 | 0 | 0 | 0 | 0 | 14537.07 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504319 | N-W-NI-121219-Stornoway_WTW-Office | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-15 |  | 2020-10-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 114.69 | 2814.69 | 0 | 0 | 0 | 2814.69 | 0 | 0 | 0 | 0 | 2814.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504332 | N-W-NI-121219-Stornoway_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-15 |  | 2020-01-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 2489.81 | 0 | 2489.81 | 0 | 0 | 0 | 2489.81 | 0 | 0 | 0 | 0 | 2489.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504333 | N-W-NI-121219-Ullapool WTW- Soda Ash Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-01-09 | 2021-05-01 | 2021-07-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492.96 | 1492.96 | 11167.06 | 0 | 0 | 12660.02 | 0 | 0 | 0 | 0 | 12660.02 | 311236.79 | [5 empty] | N | CM_M&G | 100%
504623 | N-W-NI-13012020-Loch_Nell_RWPS-Bursting_Disks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-01-15 |  | 2020-06-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7973.82 | 5604.79 | 13578.61 | 0 | 0 | 0 | 13578.61 | 0 | 0 | 0 | 0 | 13578.61 | 119022.58 | [5 empty] | N | WSNI | 100%
504618 | N-W-NI-13012020-Torra_WTW-Intake_Raw_Main_Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-01-14 |  | 2020-09-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 16472.35 | 36371.64 | 52843.99 | 0 | 0 | 0 | 52843.99 | 0 | 0 | 0 | 0 | 52843.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510689 | N-W-NI-13012021-Ardrishaig_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-14 |  | 2021-03-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584.07 | 1584.07 | 15.92 | 0 | 0 | 1599.99 | 0 | 0 | 0 | 0 | 1599.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510670 | N-W-NI-13012021-Cowhill_DSR-Modelling | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.46 | 595.46 | 517.24 | 0 | 0 | 1112.7 | 0 | 0 | 0 | 0 | 1112.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510673 | N-W-NI-13012021-Kilchrennan-Taynuilt_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-14 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.4 | 0 | 0 | 1399.99 | 0 | 0 | 0 | 0 | 1399.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510672 | N-W-NI-13012021-Newmore_WTW-Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-14 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26491.63 | 26491.63 | 308.37 | 0 | 0 | 26800 | 0 | 0 | 0 | 0 | 26800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505175 | N-W-NI-130220-Garyvard_TWP-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-13 |  | 2020-04-17 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 4930.14 | 5283.41 | 0 | 0 | 0 | 5283.41 | 0 | 0 | 0 | 0 | 5283.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505181 | N-W-NI-130220-Londornoch_WTW-SiloBin | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 228.97 | 0 | 228.97 | 3271.03 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505186 | N-W-NI-130220-North_Lochs_WTW-Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-13 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1933.86 | 0 | 1933.86 | 0 | 0 | 0 | 1933.86 | 0 | 0 | 0 | 0 | 1933.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505174 | N-W-NI-130220-Strollamus_DSR-AccessRoad | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-13 |  | 2020-06-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 484.11 | 6900 | 7384.11 | 0 | 0 | 0 | 7384.11 | 0 | 0 | 0 | 0 | 7384.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505706 | N-W-NI-13032020-Aultbea Intake- Screen Chamber | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-03-30 | 2020-12-07 | 2021-05-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34685 | 34685 | 314.94 | 0 | 0 | 34999.94 | 0 | 0 | 0 | 0 | 34999.94 | 119022.58 | [5 empty] | N | CM_WSI | 100%
505725 | N-W-NI-13032020-Loch HatravatRWI-RTU replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-18 |  | 2020-01-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1015.81 | 14511.52 | 15527.33 | 0 | 0 | 0 | 15527.33 | 0 | 0 | 0 | 0 | 15527.33 | 119022.58 | [5 empty] | N | CM_WSI | 100%
505727 | N-W-NI-13032020-Loch Mor-A-Stairr-RTU replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-18 |  | 2020-01-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1015.79 | 14511.52 | 15527.31 | 0 | 0 | 0 | 15527.31 | 0 | 0 | 0 | 0 | 15527.31 | 119022.58 | [5 empty] | N | CM_WSI | 100%
505711 | N-W-NI-130320-Torra_WTW-RGF_Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-03-18 |  | 2020-09-08 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 3672.24 | 60060.28 | 63732.52 | 0 | 0 | 0 | 63732.52 | 0 | 0 | 0 | 0 | 63732.52 | 119022.58 | [5 empty] | N | WSNI | 100%
506598 | N-W-NI-130520-Urchany_DSR-Tanker_Point | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-05-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.56 | 320.56 | 4579.44 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 4900 | 311236.79 | [5 empty] | N | CM_M&G | 100%
507637 | N-W-NI-130720-Glendale_WTW-Kiosk | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-13 |  | 2020-09-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2090.65 | 2090.65 | 0 | 0 | 0 | 2090.65 | 0 | 0 | 0 | 0 | 2090.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507633 | N-W-NI-130720-Leurbost_TWP-Pump VSD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-13 |  | 2020-10-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7954.91 | 7954.91 | 0 | 0 | 0 | 7954.91 | 0 | 0 | 0 | 0 | 7954.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507652 | N-W-NI-130720-Stornoway_Container | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-13 |  | 2020-08-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3535.51 | 3535.51 | 0 | 0 | 0 | 3535.51 | 0 | 0 | 0 | 0 | 3535.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508174 | N-W-NI-130820-Boundary_DSR-Modem | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-20 |  | 2020-09-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1233.8 | 1233.8 | 0 | 0 | 0 | 1233.8 | 0 | 0 | 0 | 0 | 1233.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508183 | N-W-NI-130820-Tobermory_WTW-LCT_Air_Scour | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-08-19 | 2020-09-02 | 2020-11-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1179.51 | 1179.51 | 0 | 0 | 0 | 1179.51 | 0 | 0 | 0 | 0 | 1179.51 | 119022.58 | [5 empty] | N | WSNI | 100%
508188 | N-W-NI-130820-Tullich_WOA-Overland Pipe | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-08-14 |  | 2020-11-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21186.92 | 21186.92 | 0 | 0 | 0 | 21186.92 | 0 | 0 | 0 | 0 | 21186.92 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508181 | N-W-NI-130820-Tullich_WTW-CWT1_Outlet_Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-08-19 | 2021-01-05 | 2021-09-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35320 | 35320 | 78068.01 | 0 | 0 | 113388.01 | 0 | 0 | 0 | 0 | 113388.01 | 119022.58 | [5 empty] | N | WSNI | 100%
508182 | N-W-NI-130820-Tullich_WTW-SCADA_Inhibit_Warning | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-08-18 | 2021-01-18 | 2021-06-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6143 | 6143 | 3856.95 | 0 | 0 | 9999.95 | 0 | 0 | 0 | 0 | 9999.95 | 119022.58 | [5 empty] | N | WSNI | 100%
509235 | N-W-NI-131020-Dalwhinnie_WTW-Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-13 |  | 2020-08-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2725.89 | 2725.89 | 0 | 0 | 0 | 2725.89 | 0 | 0 | 0 | 0 | 2725.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509236 | N-W-NI-131020-Upper_Blairmore_DSR-Access Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5033.31 | 5033.31 | 0 | 0 | 0 | 5033.31 | 0 | 0 | 0 | 0 | 5033.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509751 | N-W-NI-131120-Assynt_WTW-Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-16 |  | 2021-03-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1407.17 | 1407.17 | 242.84 | 0 | 0 | 1650.01 | 0 | 0 | 0 | 0 | 1650.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509782 | N-W-NI-131120-Camisky_Wellfield_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.1 | 327.1 | 4672.9 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509787 | N-W-NI-131120-Durness_Keodale_WTW-Pipes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-16 |  | 2020-10-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1480.88 | 1480.88 | 0 | 0 | 0 | 1480.88 | 0 | 0 | 0 | 0 | 1480.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509786 | N-W-NI-131120-Iona_DSR-Investigation (H&S) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-16 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.66 | 90.66 | 1009.34 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509785 | N-W-NI-131120-Kinlochleven_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504341 | N-W-NI-131219-North_Lochs_WTW-Covers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-15 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1366.59 | 0 | 1366.59 | 33.41 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504346 | N-W-NI-131219-Stornoway_WTW-Filter_Checks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510696 | N-W-NI-14012021-Inverness_WTW-Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-14 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801.99 | 1801.99 | 448.01 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504647 | N-W-NI-140120-Loch_Calder_WTW-PLC _ Power | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-15 |  | 2020-04-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1310 | 10898.7 | 12208.7 | 0 | 0 | 0 | 12208.7 | 0 | 0 | 0 | 0 | 12208.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510706 | N-W-NI-140121- Melvich & Apigill DSR Tank Hatches | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-22 | 2021-09-24 | 2022-05-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2692 | 2692 | 29807.77 | 0 | 0 | 32499.77 | 0 | 0 | 0 | 0 | 32499.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505192 | N-W-NI-140220-Arnol_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-17 |  | 2020-03-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 2003.78 | 0 | 2003.78 | 0 | 0 | 0 | 2003.78 | 0 | 0 | 0 | 0 | 2003.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505195 | N-W-NI-140220-Diabeg_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-17 |  | 2020-06-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 2580 | 2763.18 | 0 | 0 | 0 | 2763.18 | 0 | 0 | 0 | 0 | 2763.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505729 | N-W-NI-140320-Campbeltown_WTW-Sludge_Bld_Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-18 |  | 2020-08-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 172.14 | 2523.78 | 2695.92 | 0 | 0 | 0 | 2695.92 | 0 | 0 | 0 | 0 | 2695.92 | 119022.58 | [5 empty] | N | WSNI | 100%
506240 | N-W-NI-14042020-Bunessan_WTW-Plasson_Valve_Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-20 | 2020-06-04 | 2021-07-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6857.3 | 6857.3 | 1452.05 | 0 | 0 | 8309.35 | 0 | 0 | 0 | 0 | 8309.35 | 119022.58 | [5 empty] | N | WSNI | 100%
506625 | N-W-NI-140520-Backies)WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-15 |  | 2020-07-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12270.71 | 12270.71 | 0 | 0 | 0 | 12270.71 | 0 | 0 | 0 | 0 | 12270.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506623 | N-W-NI-140520-Bonar_Bridge_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-15 |  | 2020-09-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3476.03 | 3476.03 | 0 | 0 | 0 | 3476.03 | 0 | 0 | 0 | 0 | 3476.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506624 | N-W-NI-140520-Carradale_WTW-Media | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-14 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785.05 | 785.05 | 11214.95 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 12000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506626 | N-W-NI-140520-Kinlochbervie_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-15 |  | 2020-10-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7243.5 | 7243.5 | 0 | 0 | 0 | 7243.5 | 0 | 0 | 0 | 0 | 7243.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507680 | N-W-NI-1407_Ardfern_WTW-pH Instrument | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-14 |  | 2020-07-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579.46 | 1579.46 | 0 | 0 | 0 | 1579.46 | 0 | 0 | 0 | 0 | 1579.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507675 | N-W-NI-140720-Acharacle_WTW-Moniktor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-14 |  | 2020-07-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3227.33 | 3227.33 | 0 | 0 | 0 | 3227.33 | 0 | 0 | 0 | 0 | 3227.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507682 | N-W-NI-140720-Rhenigadale_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-14 |  | 2020-08-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2342.82 | 2342.82 | 0 | 0 | 0 | 2342.82 | 0 | 0 | 0 | 0 | 2342.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507684 | N-W-NI-140720-Tarbert_WTW-Cl Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-14 |  | 2020-07-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1587.98 | 1587.98 | 0 | 0 | 0 | 1587.98 | 0 | 0 | 0 | 0 | 1587.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508197 | N-W-NI-140820-Aultbea WTW Foamball Catchers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-08-19 | 2021-04-12 | 2021-06-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15526 | 15526 | 10044.15 | 0 | 0 | 25570.15 | 0 | 0 | 0 | 0 | 25570.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508745 | N-W-NI-140920-Ardfern_WTW-Weed_Choking_Membranes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-09-16 | 2021-07-12 | 2022-02-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2090.59 | 2090.59 | 3294.14 | 0 | 0 | 5384.73 | 0 | 0 | 0 | 0 | 5384.73 | 119022.58 | [5 empty] | N | WSNI | 100%
509259 | N-W-NI-141020-Assynt_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-14 |  | 2021-03-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2147.72 | 2147.72 | 552.28 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509253 | N-W-NI-141020-Wester_Braes_TWP-Power | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-14 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.47 | 150.47 | 2149.53 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510299 | N-W-NI-141220-Hynish CWT-Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-12 | 2022-05-13 | 2022-12-26 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2136 | 2136 | 22864.43 | 0 | 0 | 25000.43 | 0 | 0 | 0 | 0 | 25000.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504654 | N-W-NI-15012020-Brnbecula Aird Low RWPS-Building ventilation for Generator | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 |  | 2020-02-03 |  | 2020-12-16 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1182.94 | 10823.32 | 12006.26 | 0 | 0 | 0 | 12006.26 | 0 | 0 | 0 | 0 | 12006.26 | 306661.32 | [5 empty] | N | CM_M&G | 100%
504670 | N-W-NI-15012020-Uig WTW-Leaking roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-05 |  | 2021-11-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 415.3 | 1887.5 | 2302.8 | 54175.86 | 0 | 0 | 56478.66 | 0 | 0 | 0 | 0 | 56478.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510730 | N-W-NI-15012021-Ardrishaig_WTW-DCI Controllers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-18 |  | 2021-03-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2419.55 | 2419.55 | 80.44 | 0 | 0 | 2499.99 | 0 | 0 | 0 | 0 | 2499.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510732 | N-W-NI-15012021-Kilmelford_WTW-pH Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-18 |  | 2021-03-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4054.76 | 4054.76 | 45.24 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510731 | N-W-NI-15012021-Newmore_WTW-Instrument | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-18 |  | 2021-03-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4808.32 | 4808.32 | 41.68 | 0 | 0 | 4850 | 0 | 0 | 0 | 0 | 4850 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510728 | N-W-NI-15012021-Tarbert_Arg_WTW-Filter pH Monitor A | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-18 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.84 | 1918.84 | 81.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510724 | N-W-NI-15012021-Tarbert_Arg_WTW-pH Monitor A | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-18 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.84 | 1918.84 | 81.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511227 | N-W-NI-15022021-Campbeltown_WTW-DAF | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2098.65 | 2098.65 | 51.35 | 0 | 0 | 2150 | 0 | 0 | 0 | 0 | 2150 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511237 | N-W-NI-15022021-North_Lochs_WTW-pH Controller | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1299.55 | 1299.55 | 0.45 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511233 | N-W-NI-15022021-Tobermory_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1214.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511230 | N-W-NI-15022021-Tullich_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3813.67 | 3813.67 | 86.33 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511780 | N-W-NI-15032021-Elgol_SDN-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1542.84 | 0 | 0 | 1660.6 | 0 | 0 | 0 | 0 | 1660.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511779 | N-W-NI-15032021-Lochcarron_WTW-Heating | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1262.62 | 1262.62 | 18037.38 | 0 | 0 | 19300 | 0 | 0 | 0 | 0 | 19300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511782 | N-W-NI-15032021-Spean_Bridge_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3257.16 | 0 | 0 | 3505.76 | 0 | 0 | 0 | 0 | 3505.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511781 | N-W-NI-15032021-Strollamus_SDN-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 1714.26 | 0 | 0 | 1845.1 | 0 | 0 | 0 | 0 | 1845.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507693 | N-W-NI-150720-3 Sites -Power Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2540.09 | 2540.09 | 59.91 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507688 | N-W-NI-150720-Kinlochewe_RWI-Screen | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-15 |  | 2020-10-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27069.86 | 27069.86 | 0 | 0 | 0 | 27069.86 | 0 | 0 | 0 | 0 | 27069.86 | 119022.58 | [5 empty] | N | CM_WSI | 100%
507696 | N-W-NI-150720-Ness_WTW-Cl Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-17 |  | 2020-08-25 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1253.1 | 1253.1 | 0 | 0 | 0 | 1253.1 | 0 | 0 | 0 | 0 | 1253.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508767 | N-W-NI-150920-Ardrishaig_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-16 |  | 2020-11-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1065 | 1065 | 0 | 0 | 0 | 1065 | 0 | 0 | 0 | 0 | 1065 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508761 | N-W-NI-150920-Benbecula_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-16 |  | 2020-09-25 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1112 | 1112 | 0 | 0 | 0 | 1112 | 0 | 0 | 0 | 0 | 1112 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508762 | N-W-NI-150920-North_Lochs_WTW-Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-16 |  | 2020-09-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1756.03 | 1756.03 | 0 | 0 | 0 | 1756.03 | 0 | 0 | 0 | 0 | 1756.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508770 | N-W-NI-150920-Tobermory_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-16 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2934.76 | 2934.76 | 0 | 0 | 0 | 2934.76 | 0 | 0 | 0 | 0 | 2934.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508769 | N-W-NI-150920-Tomich_WTW-Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-16 |  | 2020-10-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2597.29 | 2597.29 | 0 | 0 | 0 | 2597.29 | 0 | 0 | 0 | 0 | 2597.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508763 | N-W-NI-150920-Viewfield_DSR-Power | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-16 |  | 2020-10-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1857.03 | 1857.03 | 0 | 0 | 0 | 1857.03 | 0 | 0 | 0 | 0 | 1857.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509281 | N-W-NI-151020-Kyle_of_Lochalsh-PV Bladder | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-19 |  | 2021-02-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4093.3 | 4093.3 | 306.7 | 0 | 0 | 4400 | 0 | 0 | 0 | 0 | 4400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509274 | N-W-NI-151020-Loch_Calder_WTW-Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-19 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3279.63 | 3279.63 | 2970.37 | 0 | 0 | 6250 | 0 | 0 | 0 | 0 | 6250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509277 | N-W-NI-151020-Tarbert_WTW-Chem Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-19 |  | 2020-11-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2856.42 | 2856.42 | 0 | 0 | 0 | 2856.42 | 0 | 0 | 0 | 0 | 2856.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503839 | N-W-NI-151119-Ullapool WTW- Flow Switch Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-19 |  | 2019-12-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1520.7 | 0 | 1520.7 | 0 | 0 | 0 | 1520.7 | 0 | 0 | 0 | 0 | 1520.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510344 | N-W-NI-151220-Inshes_DSR-Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1269.16 | 1269.16 | 18130.86 | 0 | 0 | 19400.02 | 0 | 0 | 0 | 0 | 19400.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510339 | N-W-NI-151220-Kinlochbervie_WTW-Membrane | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294.39 | 294.39 | 4205.61 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510343 | N-W-NI-151220-Kinlochleven_WTW-RTU | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771.96 | 771.96 | 11028.03 | 0 | 0 | 11799.99 | 0 | 0 | 0 | 0 | 11799.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510346 | N-W-NI-151220-Newmore_WTW-Hatches | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641.12 | 641.12 | 9158.88 | 0 | 0 | 9800 | 0 | 0 | 0 | 0 | 9800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510338 | N-W-NI-151220-Newmore_WTW-Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-16 |  | 2021-03-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1827.84 | 1827.84 | 172.17 | 0 | 0 | 2000.01 | 0 | 0 | 0 | 0 | 2000.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504945 | N-W-NI-16012020-N Lochs WTW-Leaking roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-02-28 |  | 2020-10-13 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 731.79 | 4873.95 | 5605.74 | 0 | 0 | 0 | 5605.74 | 0 | 0 | 0 | 0 | 5605.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504685 | N-W-NI-160120-Ardfern_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-16 |  | 2020-02-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 3516.91 | 0 | 3516.91 | 0 | 0 | 0 | 3516.91 | 0 | 0 | 0 | 0 | 3516.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504679 | N-W-NI-160120-Balnain_DSR-Fuel_Cell | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-16 |  | 2020-02-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 9444.71 | 0 | 9444.71 | 0 | 0 | 0 | 9444.71 | 0 | 0 | 0 | 0 | 9444.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504695 | N-W-NI-160120-Glenconvinth_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-19 |  | 2020-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | -1003.82 | 1296.18 | 0 | 0 | 0 | 1296.18 | 0 | 0 | 0 | 0 | 1296.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504696 | N-W-NI-160120-Tarbert_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-19 |  | 2020-03-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1802.98 | 0 | 1802.98 | 0 | 0 | 0 | 1802.98 | 0 | 0 | 0 | 0 | 1802.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504694 | N-W-NI-160120-Teangue_WTW-Filtomat | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-19 |  | 2020-02-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | -485.59 | 7014.41 | 0 | 0 | 0 | 7014.41 | 0 | 0 | 0 | 0 | 7014.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504688 | N-W-NI-160120-Tobermory_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-19 |  | 2020-01-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1100.76 | 0 | 1100.76 | 0 | 0 | 0 | 1100.76 | 0 | 0 | 0 | 0 | 1100.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511257 | N-W-NI-16022021-Barra_WTW-Chamber Cover | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-16 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6057.43 | 6057.43 | 442.57 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511264 | N-W-NI-16022021-Culburnie_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 2616.8 | 0 | 0 | 2799.98 | 0 | 0 | 0 | 0 | 2799.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511263 | N-W-NI-16022021-Glenconvinth_WTW-UPS Unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-16 |  | 2021-05-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008.38 | 2008.38 | 91.62 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511823 | N-W-NI-16032021-Aultbea_WTW- Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 425.23 | 5571.42 | 0 | 0 | 5996.65 | 0 | 0 | 0 | 0 | 5996.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511821 | N-W-NI-16032021-Aultbea_WTW-Survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.29 | 317.29 | 4157.16 | 0 | 0 | 4474.45 | 0 | 0 | 0 | 0 | 4474.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511817 | N-W-NI-16032021-Torra_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 2400 | 0 | 0 | 2583.18 | 0 | 0 | 0 | 0 | 2583.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505742 | N-W-NI-160320-Ardrishaig_WTW-DOMS_Store | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-18 |  | 2020-03-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 11848.5 | 0 | 11848.5 | 0 | 0 | 0 | 11848.5 | 0 | 0 | 0 | 0 | 11848.5 | 119022.58 | [5 empty] | N | WSNI | 100%
505733 | N-W-NI-160320-Dalmally_WTW-Access_rd_repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-20 |  | 2020-06-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 773.5 | 11500 | 12273.5 | 0 | 0 | 0 | 12273.5 | 0 | 0 | 0 | 0 | 12273.5 | 119022.58 | [5 empty] | N | WSNI | 100%
511797 | N-W-NI-160321-Stoneybridge WTW Early Scope | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-19 | 2022-06-23 | 2023-02-03 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.86 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511830 | N-W-NI-160321-Tarbert CWT Right of access | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2022-06-23 | 2022-09-15 | 2023-04-28 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 0 | 0 | 22500 | 0 | 0 | 0 | 0 | 22500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506244 | N-W-NI-160420-Torra_WTW-Turbidity_Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-20 |  | 2020-05-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13199.14 | 13199.14 | 0 | 0 | 0 | 13199.14 | 0 | 0 | 0 | 0 | 13199.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506239 | N-W-NI-160420-Tullich_WOA-Main_Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-04-20 |  | 2020-06-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15517.29 | 15517.29 | 0 | 0 | 0 | 15517.29 | 0 | 0 | 0 | 0 | 15517.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507206 | N-W-NI-160620-Loch_Calder_WTW-Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-18 |  | 2020-11-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4168.46 | 4168.46 | 0 | 0 | 0 | 4168.46 | 0 | 0 | 0 | 0 | 4168.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507720 | N-W-NI-160720-Ardmnore_TWP-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-16 |  | 2020-08-26 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331.59 | 1331.59 | 0 | 0 | 0 | 1331.59 | 0 | 0 | 0 | 0 | 1331.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507723 | N-W-NI-160720-Badachro_WTW-Amiad Mods | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-07-16 |  | 2021-03-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16549.74 | 16549.74 | -449.74 | 0 | 0 | 16100 | 0 | 0 | 0 | 0 | 16100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507741 | N-W-NI-160720-Tullich_WTW-Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-17 |  | 2020-08-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6711.86 | 6711.86 | 0 | 0 | 0 | 6711.86 | 0 | 0 | 0 | 0 | 6711.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508808 | N-W-NI-160920-Arnisdale_WTW-UPS Batteries | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631.31 | 631.31 | 9018.69 | 0 | 0 | 9650 | 0 | 0 | 0 | 0 | 9650 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508775 | N-W-NI-160920-Port_Ellen_DSR-Diesel Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-16 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2242.99 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508806 | N-W-NI-160920-Staffin_WTW-Fan | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-18 |  | 2020-11-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1298.13 | 1298.13 | 0 | 0 | 0 | 1298.13 | 0 | 0 | 0 | 0 | 1298.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509302 | N-W-NI-161020-Invergarry_WTW-Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202.9 | 202.9 | 897.1 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509818 | N-W-NI-161120-Assynt_WTW-Lime System | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-18 |  | 2021-03-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030.66 | 2030.66 | 169.34 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509803 | N-W-NI-161120-Barra_WTW-Covers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-18 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 4018.68 | 0 | 0 | 4299.99 | 0 | 0 | 0 | 0 | 4299.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509816 | N-W-NI-161120-Loch_Lannsaidh_RWP-Survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536.45 | 536.45 | 7663.54 | 0 | 0 | 8199.99 | 0 | 0 | 0 | 0 | 8199.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504353 | N-W-NI-161219-Geocrab_WTW-Filter_Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-16 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -1869.16 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504364 | N-W-NI-161219-Kyle and Acharacle Chemical Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2019-12-17 | 2020-09-07 | 2020-11-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 56215.93 | 58215.93 | 0 | 0 | 0 | 58215.93 | 0 | 0 | 0 | 0 | 58215.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511828 | N-W-NI-16321Stornoway and Stoneybridge auto coag project Ph2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-22 | 2022-06-23 | 2023-02-03 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2355.14 | 2355.14 | 33644.86 | 0 | 0 | 36000 | 0 | 0 | 0 | 0 | 36000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504717 | N-W-NI-170120-Inverness_WTW-Circuit_Breaker | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-19 |  | 2020-02-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5350 | -195.95 | 5154.05 | 0 | 0 | 0 | 5154.05 | 0 | 0 | 0 | 0 | 5154.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505233 | N-W-NI-170220-Ardfern_WTW-PumpNr1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-17 |  | 2020-02-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1029.08 | 0 | 1029.08 | 0 | 0 | 0 | 1029.08 | 0 | 0 | 0 | 0 | 1029.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505234 | N-W-NI-170220-Campbeltown_WTW-Filter_Depth_Boards | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-17 |  | 2020-09-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 319.46 | 2220.17 | 2539.63 | 0 | 0 | 0 | 2539.63 | 0 | 0 | 0 | 0 | 2539.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505247 | N-W-NI-170220-Carbost_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-19 |  | 2020-03-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1534.49 | 0 | 1534.49 | 0 | 0 | 0 | 1534.49 | 0 | 0 | 0 | 0 | 1534.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505246 | N-W-NI-170220-Inveraray_WTW-Gem80_Spares | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-17 |  | 2020-06-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 2465 | 2641.64 | 0 | 0 | 0 | 2641.64 | 0 | 0 | 0 | 0 | 2641.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505249 | N-W-NI-170220-Port_Charlotte _WTW-RTU | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-19 |  | 2020-05-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 2665.86 | 2855.58 | 0 | 0 | 0 | 2855.58 | 0 | 0 | 0 | 0 | 2855.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511287 | N-W-NI-170221-Lochmaddy WTW-Install additional membranes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-03 | 2022-04-04 | 2022-11-15 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 3750 | 46249.95 | 0 | 0 | 49999.95 | 0 | 0 | 0 | 0 | 49999.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511882 | N-W-NI-17032021-Ardrishaig_WTW-pH Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1285.74 | 0 | 0 | 1383.87 | 0 | 0 | 0 | 0 | 1383.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511883 | N-W-NI-17032021-Campbeltown_WTW-Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 1885.74 | 0 | 0 | 2029.67 | 0 | 0 | 0 | 0 | 2029.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505774 | N-W-NI-170320-Ballygrant_WTW-Generator Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-20 | 2021-06-14 | 2021-10-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 4315.32 | 3103.05 | 7418.36 | 92342.85 | 0 | 0 | 99761.21 | 0 | 0 | 0 | 0 | 99761.21 | 119022.58 | [5 empty] | N | WSNI | 100%
505785 | N-W-NI-170320-Herbusta TWP- Wiring Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505766 | N-W-NI-170320-Taynuilt_WTW-H&S_Improv | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-03-20 | 2020-09-07 | 2020-12-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 8489.03 | 11281.23 | 19770.26 | 0 | 0 | 0 | 19770.26 | 0 | 0 | 0 | 0 | 19770.26 | 119022.58 | [5 empty] | N | WSNI | 100%
507231 | N-W-NI-170620-Bunessan_WTW-H&S_Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-06-23 | 2020-10-26 | 2021-09-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4417.72 | 4417.72 | 4564.11 | 0 | 0 | 8981.83 | 0 | 0 | 0 | 0 | 8981.83 | 119022.58 | [5 empty] | N | WSNI | 100%
507238 | N-W-NI-170620-Loch_Nell_RWPS-Condition_Report | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-06-23 | 2021-01-11 | 2021-06-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9956.36 | 9956.36 | 3825.76 | 0 | 0 | 13782.12 | 0 | 0 | 0 | 0 | 13782.12 | 119022.58 | [5 empty] | N | WSNI | 100%
507227 | N-W-NI-170620-Tobermory_WTW_Additional_Backwash_Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-06-23 | 2021-01-18 | 2021-03-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13239.67 | 13239.67 | 0 | 0 | 0 | 13239.67 | 0 | 0 | 0 | 0 | 13239.67 | 119022.58 | [5 empty] | N | WSNI | 100%
507225 | N-W-NI-170620-Tobermory_WTW-Intake_Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-06-23 | 2020-12-14 | 2020-12-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10750.26 | 10750.26 | 0 | 0 | 0 | 10750.26 | 0 | 0 | 0 | 0 | 10750.26 | 119022.58 | [5 empty] | N | WSNI | 100%
507235 | N-W-NI-170620-Tullich_WTW-Ferric_Tanks_Clean | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-06-23 | 2020-09-16 | 2020-10-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2397.87 | 2397.87 | 0 | 0 | 0 | 2397.87 | 0 | 0 | 0 | 0 | 2397.87 | 119022.58 | [5 empty] | N | WSNI | 100%
509831 | N-W-NI-171120-A-Kilmelford_WTW-Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-18 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383.02 | 383.02 | 1716.98 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509845 | N-W-NI-171120-Campbeltown_WTW-PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-18 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509850 | N-W-NI-171120-Carradale_WTW-PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-18 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504382 | N-W-NI-171219-Bonar_Bridge_WTW-Filtomats | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-17 |  | 2020-04-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | -85.11 | 8914.89 | 0 | 0 | 0 | 8914.89 | 0 | 0 | 0 | 0 | 8914.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504384 | N-W-NI-171219-Tongue_DSR-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-17 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -2290 | 210 | 2290 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504390 | N-W-NI-171219-Tongue_TWP-Flow_Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3210 | -3000 | 210 | 3000 | 0 | 0 | 3210 | 0 | 0 | 0 | 0 | 3210 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510750 | N-W-NI-18012021-Breanish_DSR-Handrails | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-19 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441.59 | 441.59 | 6308.4 | 0 | 0 | 6749.99 | 0 | 0 | 0 | 0 | 6749.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510752 | N-W-NI-18012021-Cameron_Tce_DRS--Handrails | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-19 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 686.92 | 686.92 | 9813.08 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 10500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511305 | N-W-NI-18022021-Tullich_WTW-Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1418.81 | 1418.81 | 81.19 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505266 | N-W-NI-180220-Achnahillin_DSR-Access_Track | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 2891.48 | 3061.57 | 0 | 0 | 0 | 3061.57 | 0 | 0 | 0 | 0 | 3061.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505261 | N-W-NI-180220-Altnaharra_WTW-Lights | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-19 |  | 2020-06-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 166.82 | 2591.41 | 2758.23 | 0 | 0 | 0 | 2758.23 | 0 | 0 | 0 | 0 | 2758.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505264 | N-W-NI-180220-Kinlochbervie_WTW-PLC-HMI_Alarm | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 0 | 157.01 | 2242.99 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505256 | N-W-NI-180220-Lochcarron_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-19 |  | 2020-05-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 150.47 | 1022.77 | 1173.24 | 0 | 0 | 0 | 1173.24 | 0 | 0 | 0 | 0 | 1173.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511918 | N-W-NI-18032021-Backies_WTW-Motors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1457.16 | 0 | 0 | 1568.37 | 0 | 0 | 0 | 0 | 1568.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511908 | N-W-NI-18032021-Kishorn_Sanachan_DSR-Access Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 4585.74 | 0 | 0 | 4935.74 | 0 | 0 | 0 | 0 | 4935.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511900 | N-W-NI-18032021-Tiree_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340.19 | 340.19 | 4457.16 | 0 | 0 | 4797.35 | 0 | 0 | 0 | 0 | 4797.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511906 | N-W-NI-18032021-Waternish_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 124.3 | 1628.58 | 0 | 0 | 1752.88 | 0 | 0 | 0 | 0 | 1752.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505797 | N-W-NI-180320-Campbeltown_WTW-RGF_C_Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-20 |  | 2020-05-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 523.36 | 6191.12 | 6714.48 | 0 | 0 | 0 | 6714.48 | 0 | 0 | 0 | 0 | 6714.48 | 119022.58 | [5 empty] | N | WSNI | 100%
511921 | N-W-NI-180321- S Lochboisdale SR Iron works replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-26 | 2022-06-23 | 2023-02-03 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1962.62 | 1962.62 | 28037.38 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506268 | N-W-NI-180420-Kyle WTW-Membrane Manifolds | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-27 | 2021-02-15 | 2021-05-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25625 | 25625 | 10729.02 | 0 | 0 | 36354.02 | 0 | 0 | 0 | 0 | 36354.02 | 119022.58 | [5 empty] | N | WSNI | 100%
507247 | N-W-NI-180620-Kyle of Lochalsh_WTW-Pump VSD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-18 |  | 2020-07-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3344.08 | 3344.08 | 0 | 0 | 0 | 3344.08 | 0 | 0 | 0 | 0 | 3344.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508812 | N-W-NI-180920-Gravir SR Increase access and repair. | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-09-28 | 2021-04-12 | 2021-11-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13446.36 | 13446.36 | 56575.06 | 0 | 0 | 70021.42 | 0 | 0 | 0 | 0 | 70021.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503844 | N-W-NI-181119-Torra_WTW-Poly_Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-19 |  | 2019-12-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1770.46 | 0 | 1770.46 | 0 | 0 | 0 | 1770.46 | 0 | 0 | 0 | 0 | 1770.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509875 | N-W-NI-181120-Craggie_TWP-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13551.07 | 13551.07 | 2548.92 | 0 | 0 | 16099.99 | 0 | 0 | 0 | 0 | 16099.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509862 | N-W-NI-181120-Earlish_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-19 |  | 2021-02-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210.27 | 2210.27 | 289.72 | 0 | 0 | 2499.99 | 0 | 0 | 0 | 0 | 2499.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509864 | N-W-NI-181120-Glendale_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-19 |  | 2021-03-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210.27 | 2210.27 | 289.72 | 0 | 0 | 2499.99 | 0 | 0 | 0 | 0 | 2499.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509865 | N-W-NI-181120-Glenelg_WTW-Drainage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5131.31 | 5131.31 | 118.69 | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 5250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509879 | N-W-NI-181120-Portree_Torvaig_WTW-UV | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-22 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2320.35 | 2320.35 | 179.64 | 0 | 0 | 2499.99 | 0 | 0 | 0 | 0 | 2499.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504419 | N-W-NI-181219-Loch_Calder_WTW-Covers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | -3738.32 | 261.68 | 3738.32 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504395 | N-W-NI-181219-Torra_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-18 |  | 2020-03-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 3933.33 | 0 | 3933.33 | 0 | 0 | 0 | 3933.33 | 0 | 0 | 0 | 0 | 3933.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510430 | N-W-NI-181220-N-Inveraray_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1365.1 | 1365.1 | 12990.63 | 0 | 0 | 14355.73 | 0 | 0 | 0 | 0 | 14355.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510426 | N-W-NI-181220-N-Inveraray_WTW-Sample Pot | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-21 |  | 2021-03-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028.3 | 2028.3 | 171.69 | 0 | 0 | 2199.99 | 0 | 0 | 0 | 0 | 2199.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510777 | N-W-NI-19012021-Craighouse_RWP-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-24 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1857.04 | 1857.04 | 142.96 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510766 | N-W-NI-19012021-Strontian_River_RWP-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-24 |  | 2021-03-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4898.18 | 4898.18 | 1001.8 | 0 | 0 | 5899.98 | 0 | 0 | 0 | 0 | 5899.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510768 | N-W-NI-19012021-Tiree_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-24 |  | 2021-03-27 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5483.64 | 5483.64 | 116.36 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 5600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510782 | N-W-NI-19012021-Tolsta_Gress_DSR-Handrails | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-20 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287.85 | 287.85 | 4112.16 | 0 | 0 | 4400.01 | 0 | 0 | 0 | 0 | 4400.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510787 | N-W-NI-190121-Lochmaddy WTW - Connect turbidity monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-11 | 2022-04-01 | 2022-11-11 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904 | 904 | 9095.74 | 0 | 0 | 9999.74 | 0 | 0 | 0 | 0 | 9999.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506238 | N-W-NI-190420-Eredine_WTW-Raw_Water_Quality | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-04-20 | 2020-07-13 | 2020-07-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030.94 | 1030.94 | 0 | 0 | 0 | 1030.94 | 0 | 0 | 0 | 0 | 1030.94 | 119022.58 | [5 empty] | N | WSNI | 100%
506697 | N-W-NI-190520-OUST DSR- &S Access Issues & Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-25 | 2021-01-18 | 2021-10-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19297 | 19297 | 30702.76 | 0 | 0 | 49999.76 | 0 | 0 | 0 | 0 | 49999.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509318 | N-W-NI-191020-Camisky_Wellfield_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-19 |  | 2020-11-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273.79 | 1273.79 | 0 | 0 | 0 | 1273.79 | 0 | 0 | 0 | 0 | 1273.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509316 | N-W-NI-191020-Glenfinnan_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-19 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5534.86 | 5534.86 | 0 | 0 | 0 | 5534.86 | 0 | 0 | 0 | 0 | 5534.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509312 | N-W-NI-191020-Loch_Calder_WTW-PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212.62 | 212.62 | 3037.38 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 3250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509320 | N-W-NI-191020-Strontian_WTW-Cl Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-19 |  | 2020-11-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2437.08 | 2437.08 | 0 | 0 | 0 | 2437.08 | 0 | 0 | 0 | 0 | 2437.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503876 | N-W-NI-191119-Drumbeg WTW- Recycle Pump replacement parts | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-21 |  | 2019-12-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1557.5 | 0 | 1557.5 | 0 | 0 | 0 | 1557.5 | 0 | 0 | 0 | 0 | 1557.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504424 | N-W-NI-191219-Stoneybridge_WTW-AlumMonitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-20 |  | 2020-03-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 13258.29 | 0 | 13258.29 | 0 | 0 | 0 | 13258.29 | 0 | 0 | 0 | 0 | 13258.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504422 | N-W-NI-191219-WI Co-ag Predictors St 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-28 | 2021-10-11 | 2023-04-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1009.16 | 26258.84 | 27268 | 192732.21 | 0 | 0 | 220000.21 | 0 | 0 | 0 | 0 | 220000.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510805 | N-W-NI-20012021-Torra_WTW-MCT Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-24 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2243 | 0 | 0 | 2400.01 | 0 | 0 | 0 | 0 | 2400.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510788 | N-W-NI-20012021-Tullich_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-24 |  | 2021-04-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3925 | 3925 | 75 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506272 | N-W-NI-200420-Loch_Fada_RWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-20 |  | 2020-07-27 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15934.83 | 15934.83 | 0 | 0 | 0 | 15934.83 | 0 | 0 | 0 | 0 | 15934.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506731 | N-W-NI-200520-Broadford_WTW-Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-21 |  | 2020-08-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2719.82 | 2719.82 | 0 | 0 | 0 | 2719.82 | 0 | 0 | 0 | 0 | 2719.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508308 | N-W-NI-200820-Camisky_Wellfield_WTW-Fire Alarm | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 425.23 | 6074.77 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508306 | N-W-NI-200820-Camisky_Wellfield_WTW-LR Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2336.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508309 | N-W-NI-200820-Invermoriston_WTW-Fence | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-25 |  | 2020-09-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2887.45 | 2887.45 | 0 | 0 | 0 | 2887.45 | 0 | 0 | 0 | 0 | 2887.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508290 | N-W-NI-200820-Ullapool_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.47 | 150.47 | 2149.53 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509341 | N-W-NI-201020-Glenconvinth_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-22 |  | 2020-10-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5548.31 | 5548.31 | 0 | 0 | 0 | 5548.31 | 0 | 0 | 0 | 0 | 5548.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509346 | N-W-NI-201020-Inverness_WTW-Survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-22 |  | 2020-11-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 821.96 | 821.96 | 0 | 0 | 0 | 821.96 | 0 | 0 | 0 | 0 | 821.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509337 | N-W-NI-201020-Kinlochleven_WTW-Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-22 |  | 2021-02-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1755.53 | 1755.53 | 94.47 | 0 | 0 | 1850 | 0 | 0 | 0 | 0 | 1850 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509331 | N-W-NI-201020-Stemster_DSR-Building Work | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399.07 | 399.07 | 5700.93 | 0 | 0 | 6100 | 0 | 0 | 0 | 0 | 6100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509343 | N-W-NI-201020-Tullich_WTW-Fence | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-22 |  | 2020-03-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4360.88 | 4360.88 | 0 | 0 | 0 | 4360.88 | 0 | 0 | 0 | 0 | 4360.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503879 | N-W-NI-201119-Acharacle_WTW-Level_Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-21 |  | 2020-01-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1627.91 | 0 | 1627.91 | 0 | 0 | 0 | 1627.91 | 0 | 0 | 0 | 0 | 1627.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509917 | N-W-NI-201120-Dunvegan_Oesdale_WTW-Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-22 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1712.61 | 1712.61 | 137.38 | 0 | 0 | 1849.99 | 0 | 0 | 0 | 0 | 1849.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510434 | N-W-NI-201220-N_Mallaig_WTW-Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 915.89 | 915.89 | 13084.11 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 14000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510436 | N-W-NI-201220-N-Poolewe_Regional_WTW-Chemicals | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-21 |  | 2021-03-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33648.01 | 33648.01 | 851.97 | 0 | 0 | 34499.98 | 0 | 0 | 0 | 0 | 34499.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510438 | N-W-NI-201220-N-Reay_TWP-Pumps CS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1334.58 | 1334.58 | 19065.42 | 0 | 0 | 20400 | 0 | 0 | 0 | 0 | 20400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510435 | N-W-NI-201220-N-Staffin_WTW-RWM Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-21 |  | 2021-02-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102.05 | 1102.05 | 197.94 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510437 | N-W-NI-201220-N-Tarbert_(WI)_New-WTW-Fuel Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1214.94 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510439 | N-W-NI-201220-N-Ullapool_WTW-Gate | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-21 |  | 2021-04-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1103.5 | 1103.5 | 96.48 | 0 | 0 | 1199.98 | 0 | 0 | 0 | 0 | 1199.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510811 | N-W-NI-21012021-Sadell_WTW-F Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-24 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977.96 | 977.96 | 1121.48 | 0 | 0 | 2099.44 | 0 | 0 | 0 | 0 | 2099.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510808 | N-W-NI-21012021-Ullapool_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-24 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232.24 | 232.24 | 3317.76 | 0 | 0 | 3550 | 0 | 0 | 0 | 0 | 3550 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504745 | N-W-NI-210120-Dalmally_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-21 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1383.09 | 0 | 1383.09 | 16.91 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504750 | N-W-NI-210120-Durness Keoldale WTW - Filter water holding chamber repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-01-22 |  | 2021-02-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 92921.87 | 95921.87 | 0 | 0 | 0 | 95921.87 | 0 | 0 | 0 | 0 | 95921.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504759 | N-W-NI-210120-Kinlochbervie; Bonar Bridge; Scourie WTW- Media replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-01-28 | 2020-02-02 | 2020-12-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 23204.74 | 37204.74 | 0 | 0 | 0 | 37204.74 | 0 | 0 | 0 | 0 | 37204.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504762 | N-W-NI-210120-Stornoway _WTW-FilterSurvey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-22 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | -3788.72 | 311.28 | 3788.72 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504753 | N-W-NI-210120-Stornoway_WTW- Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-22 |  | 2020-03-26 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1624.94 | 0 | 1624.94 | 0 | 0 | 0 | 1624.94 | 0 | 0 | 0 | 0 | 1624.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505362 | N-W-NI-210220-Londornoch_WTW-RCD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 0 | 91.59 | 1308.41 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505343 | N-W-NI-210220-Tiree WTW borehole 1 to 3 cleaning | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-03-03 | 2020-06-25 | 2020-06-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 106244.93 | 107244.93 | 0 | 0 | 0 | 107244.93 | 0 | 0 | 0 | 0 | 107244.93 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505357 | N-W-NI-210220-Tobermory-Turb_Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-23 |  | 2020-03-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1127.62 | 0 | 1127.62 | 0 | 0 | 0 | 1127.62 | 0 | 0 | 0 | 0 | 1127.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506288 | N-W-NI-210420-Kilberry_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-22 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448.13 | 448.13 | 6401.87 | 0 | 0 | 6850 | 0 | 0 | 0 | 0 | 6850 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506286 | N-W-NI-210420-Lochmaddy WTW-Re-membrane module in stream 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-05-06 | 2020-08-21 | 2020-12-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5628.02 | 5628.02 | 0 | 0 | 0 | 5628.02 | 0 | 0 | 0 | 0 | 5628.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506293 | N-W-NI-210420-Stoneybridge WTW-Treeated & final water sampling | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-06 | 2020-12-16 | 2022-02-04 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11053 | 11053 | 21646.98 | 0 | 0 | 32699.98 | 0 | 0 | 0 | 0 | 32699.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506290 | N-W-NI-210420-Tarbert (WI)WTW-Plant and Evoqua PLC comms | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-05-06 | 2021-04-19 | 2022-04-15 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3407.64 | 3407.64 | 7259.56 | 0 | 0 | 10667.2 | 0 | 0 | 0 | 0 | 10667.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506284 | N-W-NI-210420-Tarbert_WTW-Amonia_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-22 |  | 2020-06-22 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18200.51 | 18200.51 | 0 | 0 | 0 | 18200.51 | 0 | 0 | 0 | 0 | 18200.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506297 | N-W-NI-210420-Uig WTW-Supernatant & run to waste facility | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-06 | 2021-01-25 | 2021-06-07 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425.36 | 7425.36 | 3296.24 | 0 | 0 | 10721.6 | 0 | 0 | 0 | 0 | 10721.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507810 | N-W-NI-210720-Barra_WOA-Culvert | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-07-22 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275.05 | 1275.05 | 24.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507807 | N-W-NI-210720-Ullapool_County_DSR-Ball Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-22 |  | 2020-09-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5017.53 | 5017.53 | 0 | 0 | 0 | 5017.53 | 0 | 0 | 0 | 0 | 5017.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508326 | N-W-NI-210820-Assynt_WTW-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-25 |  | 2020-09-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3868.22 | 3868.22 | 0 | 0 | 0 | 3868.22 | 0 | 0 | 0 | 0 | 3868.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508321 | N-W-NI-210820-Bunessan_WTW-Membranes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508324 | N-W-NI-210820-Camisky_Wellfield_WTW-DW Ligting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1892.52 | 1892.52 | 4107.48 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 6000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508330 | N-W-NI-210820-Geograb_WTW-Window | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-25 |  | 2021-02-28 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5315 | 5315 | 35 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508338 | N-W-NI-210820-Stoneybridge_WTW-PACL Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-25 |  | 2020-09-04 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1112 | 1112 | 0 | 0 | 0 | 1112 | 0 | 0 | 0 | 0 | 1112 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509379 | N-W-NI-211020-Benbecula_WTW-Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-22 |  | 2021-03-19 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1931.63 | 1931.63 | 368.37 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509383 | N-W-NI-211020-Carradale_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-22 |  | 2020-11-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2567.16 | 2567.16 | 0 | 0 | 0 | 2567.16 | 0 | 0 | 0 | 0 | 2567.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503905 | N-W-NI-211119-Barcaldine_DSR-Land_Inv | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-21 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 5350 | -5009.97 | 340.03 | 5009.97 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503913 | N-W-NI-211119-Broadford_WTW-Amiad_Screens | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | -2654.93 | 12345.07 | 2654.93 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503899 | N-W-NI-211119-Inveraray_WTW-Heating | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-21 |  | 2020-08-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 61.47 | 2061.47 | 0 | 0 | 0 | 2061.47 | 0 | 0 | 0 | 0 | 2061.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503917 | N-W-NI-211119-Staffin_WTW-Compressors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-22 |  | 2019-12-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | -995.26 | 15004.74 | 0 | 0 | 0 | 15004.74 | 0 | 0 | 0 | 0 | 15004.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510456 | N-W-NI-211220-Bracadale_WTW-VSD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-21 |  | 2021-02-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385.27 | 1385.27 | 264.72 | 0 | 0 | 1649.99 | 0 | 0 | 0 | 0 | 1649.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510465 | N-W-NI-211220-Laggan_Bridge_WTW-Probes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-21 |  | 2021-03-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6670.91 | 6670.91 | 729.09 | 0 | 0 | 7400 | 0 | 0 | 0 | 0 | 7400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510440 | N-W-NI-211220-N-Broadford_Mid_Skye_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-21 |  | 2021-03-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2386.87 | 2386.87 | 213.12 | 0 | 0 | 2599.99 | 0 | 0 | 0 | 0 | 2599.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510843 | N-W-NI-22012021-Campbeltown_WTW-Scoping | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511362 | N-W-NI-22022021-Bayble_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-22 |  | 2021-05-22 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084.1 | 1084.1 | 115.9 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511363 | N-W-NI-22022021-Benbecula_WTW-Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-22 |  | 2021-04-05 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20769.76 | 20769.76 | 230.24 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 21000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511358 | N-W-NI-22022021-Borve_TWS-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.49 | 114.49 | 1635.5 | 0 | 0 | 1749.99 | 0 | 0 | 0 | 0 | 1749.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511365 | N-W-NI-22022021-Newmore_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-22 |  | 2021-05-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.4 | 0 | 0 | 1399.99 | 0 | 0 | 0 | 0 | 1399.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511383 | N-W-NI-22022021-Tarbert (Arg) WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-22 |  | 2021-05-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.4 | 0 | 0 | 1399.99 | 0 | 0 | 0 | 0 | 1399.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505367 | N-W-NI-220220-Appin_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-23 |  | 2020-03-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1556.87 | 0 | 1556.87 | 0 | 0 | 0 | 1556.87 | 0 | 0 | 0 | 0 | 1556.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505363 | N-W-NI-220220-Broadford_WTW-Transmitter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-23 |  | 2020-04-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2052.16 | 0 | 2052.16 | 0 | 0 | 0 | 2052.16 | 0 | 0 | 0 | 0 | 2052.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505369 | N-W-NI-220220-Dalmally_WTW-ValveActuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-23 |  | 2020-05-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 352.17 | 2780 | 3132.17 | 0 | 0 | 0 | 3132.17 | 0 | 0 | 0 | 0 | 3132.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505368 | N-W-NI-220220-Inveraray_WTW-DAF | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-23 |  | 2020-03-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1292.45 | 0 | 1292.45 | 0 | 0 | 0 | 1292.45 | 0 | 0 | 0 | 0 | 1292.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505365 | N-W-NI-220220-Loch_Calder_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-23 |  | 2020-04-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3341.73 | 0 | 3341.73 | 0 | 0 | 0 | 3341.73 | 0 | 0 | 0 | 0 | 3341.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505366 | N-W-NI-220220-Teangue_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-23 |  | 2020-04-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 1187.4 | 1272.45 | 0 | 0 | 0 | 1272.45 | 0 | 0 | 0 | 0 | 1272.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511950 | N-W-NI-22032021-Teangue_WTW-Fliter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.94 | 107.94 | 1414.26 | 0 | 0 | 1522.2 | 0 | 0 | 0 | 0 | 1522.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507286 | N-W-NI-220620-Dorrery_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-07-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1185.7 | 1185.7 | 0 | 0 | 0 | 1185.7 | 0 | 0 | 0 | 0 | 1185.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507282 | N-W-NI-220620-Kinlochbervie_WTW-Survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-07-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810.67 | 1810.67 | 0 | 0 | 0 | 1810.67 | 0 | 0 | 0 | 0 | 1810.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507281 | N-W-NI-220620-Loch_Calder_RWI-Survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-07-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1244.37 | 1244.37 | 0 | 0 | 0 | 1244.37 | 0 | 0 | 0 | 0 | 1244.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507284 | N-W-NI-220620-Londornoch_WTW-Pump | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS7 |  | 2020-06-23 |  | 2020-08-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3179.22 | 3179.22 | 0 | 0 | 0 | 3179.22 | 0 | 0 | 0 | 0 | 3179.22 | 0 | [5 empty] | N | SR15_ENV_WFD | 100%
507291 | N-W-NI-220620-Nerabus_DSR-Duct | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-08-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1484.13 | 1484.13 | 0 | 0 | 0 | 1484.13 | 0 | 0 | 0 | 0 | 1484.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507292 | N-W-NI-220620-Port_Charlotte_WTW-Clarifier_Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-06-24 | 2020-11-09 | 2021-01-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21879.74 | 21879.74 | 0 | 0 | 0 | 21879.74 | 0 | 0 | 0 | 0 | 21879.74 | 119022.58 | [5 empty] | N | WSNI | 100%
507283 | N-W-NI-220620-Thusater_TWP-Survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-07-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2387.72 | 2387.72 | 0 | 0 | 0 | 2387.72 | 0 | 0 | 0 | 0 | 2387.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507822 | N-W-NI-220720-Broadford_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-23 |  | 2020-08-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.91 | 3141.91 | 0 | 0 | 0 | 3141.91 | 0 | 0 | 0 | 0 | 3141.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507824 | N-W-NI-220720-Dunvegan_Osedale_WTW-Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-23 |  | 2020-08-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2625.48 | 2625.48 | 0 | 0 | 0 | 2625.48 | 0 | 0 | 0 | 0 | 2625.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507820 | N-W-NI-220720-Teangue_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-23 |  | 2020-08-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329.75 | 1329.75 | 0 | 0 | 0 | 1329.75 | 0 | 0 | 0 | 0 | 1329.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508868 | N-W-NI-220920-Assynt_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-22 |  | 2020-11-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12532.27 | 12532.27 | 0 | 0 | 0 | 12532.27 | 0 | 0 | 0 | 0 | 12532.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508852 | N-W-NI-220920-Assynt_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-22 |  | 2021-03-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1912.77 | 1912.77 | 0 | 0 | 0 | 1912.77 | 0 | 0 | 0 | 0 | 1912.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508859 | N-W-NI-220920-Camisky_Wellfield_WTW-PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-22 |  | 2020-10-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1186.25 | 1186.25 | 0 | 0 | 0 | 1186.25 | 0 | 0 | 0 | 0 | 1186.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508856 | N-W-NI-220920-Camisky_Wellfield_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2242.99 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508874 | N-W-NI-220920-Dunvegan_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-22 |  | 2020-10-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1773.46 | 1773.46 | 0 | 0 | 0 | 1773.46 | 0 | 0 | 0 | 0 | 1773.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508860 | N-W-NI-220920-Inverness_WTW-Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13811.77 | 13811.77 | 10188.23 | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 24000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508879 | N-W-NI-220920-Teangue_CWT-Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-22 |  | 2020-10-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3235.16 | 3235.16 | 0 | 0 | 0 | 3235.16 | 0 | 0 | 0 | 0 | 3235.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509413 | N-W-NI-221020-Bridge_of_Horn_DSR-Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5499.33 | 5499.33 | 2250.67 | 0 | 0 | 7750 | 0 | 0 | 0 | 0 | 7750 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509386 | N-W-NI-221020-Inchlaggan_WTW-Bldng Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2523.36 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509402 | N-W-NI-221020-Tobermory_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-23 |  | 2020-10-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49972.88 | 49972.88 | 2627.12 | 0 | 0 | 52600 | 0 | 0 | 0 | 0 | 52600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509405 | N-W-NI-221020-West_Lewis_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178.39 | 1178.39 | 0 | 0 | 0 | 1178.39 | 0 | 0 | 0 | 0 | 1178.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503940 | N-W-NI-221119-Bonar_Bridge_WTW-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-11-25 |  | 2021-02-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | -2281.17 | 4218.83 | 2281.17 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510507 | N-W-NI-221220-Newmore_WOA-Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-12-29 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.56 | 320.56 | 4579.44 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 4900 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504809 | N-W-NI-230120 Loch Calder WTW - Total Treated Water Chlorine Monitor Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-24 |  | 2021-09-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6204.19 | -4200.19 | 2004 | 5996.02 | 0 | 0 | 8000.02 | 0 | 0 | 0 | 0 | 8000.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511424 | N-W-NI-23022021-Earlish_WTW-Access Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2526.64 | 2526.64 | 173.36 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511426 | N-W-NI-23022021-Edinbane_SR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1761.03 | 1761.03 | 88.97 | 0 | 0 | 1850 | 0 | 0 | 0 | 0 | 1850 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511427 | N-W-NI-23022021-Stornoway_WTW-Cl Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260.55 | 1260.55 | 39.45 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511962 | N-W-NI-23032021-Badcaul_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 3685.74 | 0 | 0 | 3967.05 | 0 | 0 | 0 | 0 | 3967.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511973 | N-W-NI-23032021-Earlish Uig_WTW-Cl Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.49 | 114.49 | 1500 | 0 | 0 | 1614.49 | 0 | 0 | 0 | 0 | 1614.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511964 | N-W-NI-23032021-Newmore_WTW-Scraper | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304.21 | 304.21 | 3985.74 | 0 | 0 | 4289.95 | 0 | 0 | 0 | 0 | 4289.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511974 | N-W-NI-230321 - LOCH CALDER WTW - Sludge Blowers & Tanks Relocation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-30 | 2022-06-23 | 2023-02-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402.13 | 402.13 | 9999.99 | 0 | 0 | 10402.12 | 0 | 0 | 0 | 0 | 10402.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506332 | N-W-NI-230420-Lismore_Primary_WTW-Hypo_Dosing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-23 |  | 2020-05-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1639.29 | 1639.29 | 0 | 0 | 0 | 1639.29 | 0 | 0 | 0 | 0 | 1639.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507299 | N-W-NI-230620-North_Lochs_WTW-Motor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125.78 | 2125.78 | 0 | 0 | 0 | 2125.78 | 0 | 0 | 0 | 0 | 2125.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507850 | N-W-NI-230720-Backies_WTW-Guards | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421.96 | 421.96 | 6028.04 | 0 | 0 | 6450 | 0 | 0 | 0 | 0 | 6450 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507840 | N-W-NI-230720-Camisky_Wellfield_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-23 |  | 2020-09-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2727.04 | 2727.04 | 0 | 0 | 0 | 2727.04 | 0 | 0 | 0 | 0 | 2727.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507839 | N-W-NI-230720-Dunnet_Head_Brough_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-23 |  | 2020-10-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1247.33 | 1247.33 | 0 | 0 | 0 | 1247.33 | 0 | 0 | 0 | 0 | 1247.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507842 | N-W-NI-230720-Newmore_WTW-Air Compressor | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS7 |  | 2020-07-23 |  | 2020-08-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2730 | 2730 | 0 | 0 | 0 | 2730 | 0 | 0 | 0 | 0 | 2730 | 0 | [5 empty] | N | SR15_ENV_WFD | 100%
507843 | N-W-NI-230720-Tullich_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-23 |  | 2020-08-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2558.09 | 2558.09 | 0 | 0 | 0 | 2558.09 | 0 | 0 | 0 | 0 | 2558.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508923 | N-W-NI-230920-Durness_Keodale_WTW-Doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-09-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436.48 | 1436.48 | 0 | 0 | 0 | 1436.48 | 0 | 0 | 0 | 0 | 1436.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508924 | N-W-NI-230920-Gigha_ATE-Fire Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.8 | 106.8 | 1393.2 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509941 | N-W-NI-231120-Iona_DSR-Chamber_Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-11-25 | 2021-12-10 | 2022-07-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074.72 | 1074.72 | 3968.13 | 0 | 0 | 5042.85 | 0 | 0 | 0 | 0 | 5042.85 | 119022.58 | [5 empty] | N | WSNI | 100%
504472 | N-W-NI-231219- Ullapool WTW- H&S Loading Platform | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-07 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 13000 | 119022.58 | [5 empty] | N | CM_M&G | 100%
510508 | N-W-NI-231220-Edderton_Bogrow_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-29 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.47 | 150.47 | 2149.53 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504831 | N-W-NI-240120- Loch Calder - Stemster TWP Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-28 | 2021-08-16 | 2022-02-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6048.69 | 147257.31 | 153306 | 10694.42 | 0 | 0 | 164000.42 | 0 | 0 | 0 | 0 | 164000.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504827 | N-W-NI-24012020-Tarbert WTW-Membranes. Replace pipework with stainless steel. | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2021-06-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 11750.03 | -7803.03 | 3947 | 28053.43 | 0 | 0 | 32000.43 | 0 | 0 | 0 | 0 | 32000.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504833 | N-W-NI-240120-Backies_WTW-Access_Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-24 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | -6074.77 | 425.23 | 6074.77 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504822 | N-W-NI-240120-Benbecula_WOA-Marker _Posts | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-01-24 |  | 2020-02-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 4059.02 | 0 | 4059.02 | 0 | 0 | 0 | 4059.02 | 0 | 0 | 0 | 0 | 4059.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504820 | N-W-NI-240120-Stornoway _WTW-Cl_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-24 |  | 2020-05-15 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 190.24 | 2890.24 | 0 | 0 | 0 | 2890.24 | 0 | 0 | 0 | 0 | 2890.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504824 | N-W-NI-240120-Tarbert_Arg_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-24 |  | 2020-02-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1117.85 | 0 | 1117.85 | 0 | 0 | 0 | 1117.85 | 0 | 0 | 0 | 0 | 1117.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511445 | N-W-NI-24022021- Bowmore_DSR-Handrail | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2336.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511436 | N-W-NI-24022021-Geocrab_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.49 | 114.49 | 1635.5 | 0 | 0 | 1749.99 | 0 | 0 | 0 | 0 | 1749.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511456 | N-W-NI-240221 Loch Calder WTW - Sludge Tanks & Blower Relocation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2022-06-23 | 2022-09-15 | 2023-04-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512020 | N-W-NI-24032021-Ardrishaig_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2142.84 | 0 | 0 | 2306.39 | 0 | 0 | 0 | 0 | 2306.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512010 | N-W-NI-24032021-Arinagour_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1028.58 | 0 | 0 | 1107.08 | 0 | 0 | 0 | 0 | 1107.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512011 | N-W-NI-24032021-Lochmaddy_WTW-Roller Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1542.84 | 0 | 0 | 1660.6 | 0 | 0 | 0 | 0 | 1660.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505915 | N-W-NI-240320-Meavaig WTW-Overflow pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-14 | 2021-02-15 | 2021-05-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 8500 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 8500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506346 | N-W-NI-240420-Torra_WTW-Actuator_Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-27 |  | 2020-08-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1339.59 | 1339.59 | 0 | 0 | 0 | 1339.59 | 0 | 0 | 0 | 0 | 1339.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507333 | N-W-NI-240620-Embo_Mains_DSR-RTU | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-06-29 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1551.52 | 1551.52 | 168.48 | 0 | 0 | 1720 | 0 | 0 | 0 | 0 | 1720 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507336 | N-W-NI-240620-Kilchoan_WTW-Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3934.21 | 3934.21 | 0 | 0 | 0 | 3934.21 | 0 | 0 | 0 | 0 | 3934.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507876 | N-W-NI-240720-Inverness_WTW-Microstrainers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-03 |  | 2020-08-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2285.59 | 2285.59 | 0 | 0 | 0 | 2285.59 | 0 | 0 | 0 | 0 | 2285.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507859 | N-W-NI-240720-Loch_Calder_WTW-Blower | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-03 |  | 2020-08-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6216.96 | 6216.96 | 0 | 0 | 0 | 6216.96 | 0 | 0 | 0 | 0 | 6216.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507875 | N-W-NI-240720-Loch_Nell_RWP-Handrail | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-03 |  | 2020-09-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166.47 | 2166.47 | 0 | 0 | 0 | 2166.47 | 0 | 0 | 0 | 0 | 2166.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507866 | N-W-NI-240720-Torra_ WTW-Sensors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-03 |  | 2020-08-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5567.36 | 5567.36 | 0 | 0 | 0 | 5567.36 | 0 | 0 | 0 | 0 | 5567.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507865 | N-W-NI-240720-Ullapool_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-03 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4382.2 | 4382.2 | 0 | 0 | 0 | 4382.2 | 0 | 0 | 0 | 0 | 4382.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508341 | N-W-NI-240820-Carradale_WTW-Doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-25 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4387.85 | 4387.85 | 12.15 | 0 | 0 | 4400 | 0 | 0 | 0 | 0 | 4400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508345 | N-W-NI-240820-Edderton_DSR-Batteries | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-25 |  | 2020-09-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564.01 | 1564.01 | 0 | 0 | 0 | 1564.01 | 0 | 0 | 0 | 0 | 1564.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508327 | N-W-NI-240820-Geograb_WTW-Sludge Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5287.5 | 5287.5 | 62.5 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508342 | N-W-NI-240820-Inverness_WTW-Pump NRVs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-25 |  | 2020-09-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780.99 | 2780.99 | 0 | 0 | 0 | 2780.99 | 0 | 0 | 0 | 0 | 2780.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508347 | N-W-NI-240820-Port_Ellen_DSR-Handrail | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 3523.36 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 3700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508349 | N-W-NI-240820-Tullich_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-25 |  | 2020-10-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977.38 | 1977.38 | 0 | 0 | 0 | 1977.38 | 0 | 0 | 0 | 0 | 1977.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508935 | N-W-NI-240920-Inveraray_WTW--Fire Alarm | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-24 |  | 2020-10-14 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4054.31 | 4054.31 | 0 | 0 | 0 | 4054.31 | 0 | 0 | 0 | 0 | 4054.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508936 | N-W-NI-240920-Rhenigidale_WTW-Doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-24 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.43 | 222.43 | 3177.57 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508932 | N-W-NI-240920-Tarbert_WTW-Fire Alarm | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-24 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417.35 | 417.35 | 4982.65 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 5400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503944 | N-W-NI-241119-Durness_Sangomore_DSR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-11-25 |  | 2020-04-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 7250 | -3583.8 | 3666.2 | 3583.8 | 0 | 0 | 7250 | 0 | 0 | 0 | 0 | 7250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503943 | N-W-NI-241119-Londornoch_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-25 |  | 2020-01-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4281.04 | 0 | 4281.04 | 0 | 0 | 0 | 4281.04 | 0 | 0 | 0 | 0 | 4281.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509966 | N-W-NI-241120-Aviemore_WTW-Slurry Tanks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-24 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.05 | 1285.05 | 14.94 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509981 | N-W-NI-241120-Raasay WTW - Disinfection Dosing Point H&S | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2022-06-13 | 2022-06-14 | 2023-01-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000.04 | 0 | 0 | 5000.04 | 0 | 0 | 0 | 0 | 5000.04 | 311236.79 | [5 empty] | N | CM_M&G | 100%
509957 | N-W-NI-241120-Tullich_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1241.64 | 1241.64 | 58.36 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503942 | N-W-NI-24119-GighaWTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-25 |  | 2020-01-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 5185.56 | 0 | 5185.56 | 0 | 0 | 0 | 5185.56 | 0 | 0 | 0 | 0 | 5185.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510853 | N-W-NI-25012021-Alligin_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-26 |  | 2021-04-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1470.13 | 1470.13 | 29.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510876 | N-W-NI-25012021-Ullapool_WTW-Tank Emptying | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2907.85 | 2907.85 | 1492.16 | 0 | 0 | 4400.01 | 0 | 0 | 0 | 0 | 4400.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511461 | N-W-NI-25022021-Ardrishaig_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-26 |  | 2021-05-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2651.19 | 2651.19 | 48.81 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505413 | N-W-NI-250220-Assynt_CWT-Bldng_Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-26 |  | 2020-07-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 366.36 | 5456 | 5822.36 | 0 | 0 | 0 | 5822.36 | 0 | 0 | 0 | 0 | 5822.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505411 | N-W-NI-250220-Durness_Keodale_WTW-Fence | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-02-26 |  | 2022-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 425.89 | 7029.13 | 7455.02 | 154.98 | 0 | 0 | 7610 | 0 | 0 | 0 | 0 | 7610 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512021 | N-W-NI-25032021-N_Uist_Clachan_DSR-Radio Link | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-25 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 353.27 | 4628.58 | 0 | 0 | 4981.85 | 0 | 0 | 0 | 0 | 4981.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512022 | N-W-NI-25032021-Ness_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-25 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1200 | 0 | 0 | 1291.59 | 0 | 0 | 0 | 0 | 1291.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512044 | N-W-NI-25032021-Newmore_WTW-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1457.16 | 0 | 0 | 1568.37 | 0 | 0 | 0 | 0 | 1568.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512025 | N-W-NI-25032021-Uig_WTW-BPT Handrails | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-25 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1542.84 | 0 | 0 | 1660.6 | 0 | 0 | 0 | 0 | 1660.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505925 | N-W-NI-250320-Aird_Low_RWPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 490.65 | 0 | 490.65 | 7009.35 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505932 | N-W-NI-250320-Campbeltown_WTW-Chlorinator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-26 |  | 2020-04-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 435.05 | 6153.77 | 6588.82 | 0 | 0 | 0 | 6588.82 | 0 | 0 | 0 | 0 | 6588.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505937 | N-W-NI-250320-Stoneybridge_WTW-Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-26 |  | 2020-07-10 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 6137.81 | 11868.5 | 18006.31 | 0 | 0 | 0 | 18006.31 | 0 | 0 | 0 | 0 | 18006.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505924 | N-W-NI-250320-Tobermory_WTW-DAF_Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-26 |  | 2020-04-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 140.65 | 1947.72 | 2088.37 | 0 | 0 | 0 | 2088.37 | 0 | 0 | 0 | 0 | 2088.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505934 | N-W-NI-250320-Torra_WTW-Power_Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-26 |  | 2020-05-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 441.59 | 6213.87 | 6655.46 | 0 | 0 | 0 | 6655.46 | 0 | 0 | 0 | 0 | 6655.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505939 | N-W-NI-250320-Uig_WTW-Valves | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS2 |  | 2020-03-26 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1574.2 | 0 | 1574.2 | 0 | 0 | 0 | 1574.2 | 0 | 0 | 0 | 0 | 1574.2 | 0 | [5 empty] | N | SR15_ENV_WFD | 100%
506813 | N-W-NI-250520-Craighouse_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-25 |  | 2020-07-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4243.9 | 4243.9 | 0 | 0 | 0 | 4243.9 | 0 | 0 | 0 | 0 | 4243.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506807 | N-W-NI-250520-Port_Charlotte_WTW-Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-25 |  | 2020-07-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1151.46 | 1151.46 | 0 | 0 | 0 | 1151.46 | 0 | 0 | 0 | 0 | 1151.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506793 | N-W-NI-250520-Stoneybridge_WTW-Dosing Skid | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-25 |  | 2020-06-15 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3034.9 | 3034.9 | 0 | 0 | 0 | 3034.9 | 0 | 0 | 0 | 0 | 3034.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507392 | N-W-NI-250620-Inverness_WTW-Membrane | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS7 |  | 2020-06-29 |  | 2020-07-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1673.84 | 1673.84 | 0 | 0 | 0 | 1673.84 | 0 | 0 | 0 | 0 | 1673.84 | 0 | [5 empty] | N | SR15_ENV_WFD | 100%
507397 | N-W-NI-250620-Poolewe Regional WTW-Office Facility | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-29 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6101.7 | 6101.7 | 1198.3 | 0 | 0 | 7300 | 0 | 0 | 0 | 0 | 7300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507391 | N-W-NI-250620-Port_Charlotte_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1353.89 | 1353.89 | 0 | 0 | 0 | 1353.89 | 0 | 0 | 0 | 0 | 1353.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507360 | N-W-NI-250620-Stornoway_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-29 |  | 2020-08-25 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2096.5 | 2096.5 | 0 | 0 | 0 | 2096.5 | 0 | 0 | 0 | 0 | 2096.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508356 | N-W-NI-250820-Inveraray_WTW-Access Track | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-25 |  | 2021-02-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16149.53 | 16149.53 | -7749.53 | 0 | 0 | 8400 | 0 | 0 | 0 | 0 | 8400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508365 | N-W-NI-250820-Inverness_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.33 | 595.33 | 2654.67 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 3250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508364 | N-W-NI-250820-Loch_Ashie_WTW-Cladding | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9862.31 | 9862.31 | 5137.69 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508358 | N-W-NI-250820-Torra_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-25 |  | 2021-03-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3385.7 | 3385.7 | 64.3 | 0 | 0 | 3450 | 0 | 0 | 0 | 0 | 3450 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508352 | N-W-NI-250820-Ullapool_WTW-Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147.2 | 147.2 | 2102.8 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503974 | N-W-NI-251119-Benbecula_WTW-Radio_Link | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-26 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 999.82 | 0 | 999.82 | 0.18 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503953 | N-W-NI-251119-Tiree_WTW-Wellfare_Unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-26 |  | 2020-04-08 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 6107.37 | 2265 | 8372.37 | 0 | 0 | 0 | 8372.37 | 0 | 0 | 0 | 0 | 8372.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510891 | N-W-NI-26012021-Bonar_Bridge_WTW-Tank Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2604.7 | 2604.7 | 195.3 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510882 | N-W-NI-26012021-Lochgilphead_DSR-Access Track | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2021-03-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2120.65 | 2120.65 | 170 | 0 | 0 | 2290.65 | 0 | 0 | 0 | 0 | 2290.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510878 | N-W-NI-26012021-Polbain_DSR-Ball Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2021-04-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524.17 | 524.17 | 1073.96 | 0 | 0 | 1598.13 | 0 | 0 | 0 | 0 | 1598.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505423 | N-W-NI-260220-Inveraray_WTW-pH_Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-26 |  | 2020-06-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 232.24 | 3267.03 | 3499.27 | 0 | 0 | 0 | 3499.27 | 0 | 0 | 0 | 0 | 3499.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512050 | N-W-NI-26032021-North_Lochs_WOA-Valves | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-26 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2314.26 | 0 | 0 | 2490.9 | 0 | 0 | 0 | 0 | 2490.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
512051 | N-W-NI-26032021-West Coast_3nr WTW-Flooring | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 353.27 | 4628.58 | 0 | 0 | 4981.85 | 0 | 0 | 0 | 0 | 4981.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505959 | N-W-NI-260320-Assynt_WTW-Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 1863.7 | 2046.88 | 0 | 0 | 0 | 2046.88 | 0 | 0 | 0 | 0 | 2046.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505953 | N-W-NI-260320-Inverness_WTW-Microstrainer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 539.72 | 6348.9 | 6888.62 | 0 | 0 | 0 | 6888.62 | 0 | 0 | 0 | 0 | 6888.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505951 | N-W-NI-260320-Inverness_WTW-Security_Gate | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 0 | 91.59 | 1308.41 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508391 | N-W-NI-260820-N_Lochs_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-27 |  | 2020-09-14 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2246.05 | 2246.05 | 0 | 0 | 0 | 2246.05 | 0 | 0 | 0 | 0 | 2246.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508394 | N-W-NI-260820-Port_Charlotte_WTW-Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-27 |  | 2020-10-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3270.49 | 3270.49 | 0 | 0 | 0 | 3270.49 | 0 | 0 | 0 | 0 | 3270.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508415 | N-W-NI-260820-Stornoway_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-28 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2536.6 | 2536.6 | 63.4 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508416 | N-W-NI-260820-Stornoway_WTW-Gates | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-28 |  | 2020-11-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366.59 | 1366.59 | 0 | 0 | 0 | 1366.59 | 0 | 0 | 0 | 0 | 1366.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508392 | N-W-NI-260820-Tiree_WTW-Softener | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-27 |  | 2020-11-16 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2029.11 | 2029.11 | 0 | 0 | 0 | 2029.11 | 0 | 0 | 0 | 0 | 2029.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504064 | N-W-NI-261119-Loch_Duntelchaig_NRPH-Flooring | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-03 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5200 | -4859.81 | 340.19 | 4859.81 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 5200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504877 | N-W-NI-270120-Stornoway_WTW-Container | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-28 |  | 2020-10-07 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 5300 | 346.73 | 5646.73 | 0 | 0 | 0 | 5646.73 | 0 | 0 | 0 | 0 | 5646.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505449 | N-W-NI-270220-Inverness_WTW-Telemetry_Spares | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 22000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506364 | N-W-NI-270420-Stoneybridge_WTW-Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-28 |  | 2020-06-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2275.32 | 2275.32 | 0 | 0 | 0 | 2275.32 | 0 | 0 | 0 | 0 | 2275.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506847 | N-W-NI-270520-Backies_WTW-Compressor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-28 |  | 2020-07-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3239.16 | 3239.16 | 0 | 0 | 0 | 3239.16 | 0 | 0 | 0 | 0 | 3239.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506853 | N-W-NI-270520-Barra WTW RWI-Safe system for unblocking intake pipe. | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-06-04 | 2022-05-13 | 2022-12-26 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2405.36 | 2405.36 | 8315.97 | 0 | 0 | 10721.33 | 0 | 0 | 0 | 0 | 10721.33 | 119022.58 | [5 empty] | N | CM_WSI | 100%
506844 | N-W-NI-270520-Dalmally_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506868 | N-W-NI-270520-Lochinver_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-28 |  | 2020-07-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2957 | 2957 | 0 | 0 | 0 | 2957 | 0 | 0 | 0 | 0 | 2957 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506881 | N-W-NI-270520-Mealdarroch_DSR-Handrail | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1391.59 | 1391.59 | 8.41 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508422 | N-W-NI-270820-Allt_Gleann_Udalain_RWI-Gates | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-28 |  | 2020-09-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517.67 | 1517.67 | 0 | 0 | 0 | 1517.67 | 0 | 0 | 0 | 0 | 1517.67 | 119022.58 | [5 empty] | N | CM_WSI | 100%
508425 | N-W-NI-270820-Applecross_WTW-Chart Recorder | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-28 |  | 2020-09-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1877.86 | 1877.86 | 0 | 0 | 0 | 1877.86 | 0 | 0 | 0 | 0 | 1877.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508430 | N-W-NI-270820-Dunvegan_WTW-Doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-28 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7318 | 7318 | 282 | 0 | 0 | 7600 | 0 | 0 | 0 | 0 | 7600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508437 | N-W-NI-270820-Shulishader WPS-Install ball valve. | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-09-08 | 2021-07-19 | 2022-03-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4421.36 | 4421.36 | 8599.97 | 0 | 0 | 13021.33 | 0 | 0 | 0 | 0 | 13021.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508438 | N-W-NI-270820-Stornoway WTW- Clarifier H&S Lifting actions | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-09-08 | 2021-07-19 | 2022-03-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3651.32 | 3651.32 | 17949.38 | 0 | 0 | 21600.7 | 0 | 0 | 0 | 0 | 21600.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508421 | N-W-NI-270820-Stornoway_WTW-MH Cover | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-28 |  | 2020-11-13 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4109.92 | 4109.92 | 0 | 0 | 0 | 4109.92 | 0 | 0 | 0 | 0 | 4109.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508431 | N-W-NI-270820-Torvaig_WTW-Doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-28 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4736.92 | 4736.92 | -1836.92 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509494 | N-W-NI-271020-Ballygrant_WTW-pH Instrument | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-11-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1624.62 | 1624.62 | 0 | 0 | 0 | 1624.62 | 0 | 0 | 0 | 0 | 1624.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509490 | N-W-NI-271020-Craighouse_CWT-Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-11-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3457.71 | 3457.71 | 0 | 0 | 0 | 3457.71 | 0 | 0 | 0 | 0 | 3457.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509496 | N-W-NI-271020-Craighouse_WTW-Turb Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2020-11-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1624.62 | 1624.62 | 0 | 0 | 0 | 1624.62 | 0 | 0 | 0 | 0 | 1624.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510037 | N-W-NI-271120-Newmore_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-30 |  | 2021-02-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191.95 | 3191.95 | 608.06 | 0 | 0 | 3800.01 | 0 | 0 | 0 | 0 | 3800.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510032 | N-W-NI-271120-Strontian_WTW-Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-30 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3183.7 | 3183.7 | 316.3 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510959 | N-W-NI-28012021-Fort_Augustus_WTW-Fan Motor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-02 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1187.28 | 1187.28 | 112.72 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510949 | N-W-NI-28012021-Loch_Calder_WTW-Inlet | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-02 |  | 2021-03-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4444.29 | 4444.29 | 155.72 | 0 | 0 | 4600.01 | 0 | 0 | 0 | 0 | 4600.01 | 119022.58 | [5 empty] | N | CM_WSI | 100%
510935 | N-W-NI-28012021-Port_Charlotte_WTW-Analyser | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2318.75 | 2318.75 | -18.75 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510960 | N-W-NI-28012021-Tullich_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-02 |  | 2021-03-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3597.8 | 3597.8 | 702.2 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504893 | N-W-NI-280120-Garyvard_TWP-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-29 |  | 2020-03-27 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1219.47 | 0 | 1219.47 | 0 | 0 | 0 | 1219.47 | 0 | 0 | 0 | 0 | 1219.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504888 | N-W-NI-280120-Lemreway_SR-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-29 |  | 2020-03-13 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 5064.66 | 0 | 5064.66 | 0 | 0 | 0 | 5064.66 | 0 | 0 | 0 | 0 | 5064.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505462 | N-W-NI-28022020-Loch Airigh Na Lic- Chloramination | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-03-06 | 2020-12-07 | 2021-03-04 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 10090.34 | 10440.34 | 0 | 0 | 0 | 10440.34 | 0 | 0 | 0 | 0 | 10440.34 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507924 | N-W-NI-280720-Loch_Nell_RWP-Building Maint | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-03 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5067.14 | 5067.14 | -17.14 | 0 | 0 | 5050 | 0 | 0 | 0 | 0 | 5050 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507907 | N-W-NI-280720-Teangue_WTW-Heating Maint | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-03 |  | 2020-10-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2649.64 | 2649.64 | 0 | 0 | 0 | 2649.64 | 0 | 0 | 0 | 0 | 2649.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509548 | N-W-NI-281020-Barra_WTW-PACL Unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3555.51 | 3555.51 | 44.49 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509535 | N-W-NI-281020-Knoll_SR-Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-29 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129.87 | 2129.87 | 70.13 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509550 | N-W-NI-281020-Lochmaddy_WTW-CWT Work | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219.16 | 219.16 | 3130.84 | 0 | 0 | 3350 | 0 | 0 | 0 | 0 | 3350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504077 | N-W-NI-281119-Loch_Calder-RWI-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-03 |  | 2020-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5418.53 | 0 | 5418.53 | 0 | 0 | 0 | 5418.53 | 0 | 0 | 0 | 0 | 5418.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510511 | N-W-NI-281220-Badachro_WTW-Pressure Vessel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-29 |  | 2021-04-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2365.25 | 2365.25 | 134.73 | 0 | 0 | 2499.98 | 0 | 0 | 0 | 0 | 2499.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510514 | N-W-NI-281220-Campbeltown_WTW-DWW Tanks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-29 |  | 2021-03-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9634.58 | 9634.58 | 65.4 | 0 | 0 | 9699.98 | 0 | 0 | 0 | 0 | 9699.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510510 | N-W-NI-281220-Grantown_DSR-Power | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-29 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.49 | 0 | 0 | 1199.99 | 0 | 0 | 0 | 0 | 1199.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510973 | N-W-NI-29012021-Mealdarroch_TWP-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-02 |  | 2021-03-08 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136.38 | 1136.38 | 63.6 | 0 | 0 | 1199.98 | 0 | 0 | 0 | 0 | 1199.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504903 | N-W-NI-290120-North_Lochs_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-29 |  | 2020-04-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 4739.16 | 0 | 4739.16 | 0 | 0 | 0 | 4739.16 | 0 | 0 | 0 | 0 | 4739.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512068 | N-W-NI-29032021-Stornoway_WYW-Cl Sensor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-29 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.1 | 327.1 | 4285.74 | 0 | 0 | 4612.84 | 0 | 0 | 0 | 0 | 4612.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506384 | N-W-NI-290420-Campbeltown_WTW-Chloroguard | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-29 |  | 2020-05-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8973.85 | 8973.85 | 0 | 0 | 0 | 8973.85 | 0 | 0 | 0 | 0 | 8973.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507425 | N-W-NI-290620-Bayhead SR Access improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-08-11 | 2021-07-19 | 2022-03-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2094 | 2094 | 3255.7 | 0 | 0 | 5349.7 | 0 | 0 | 0 | 0 | 5349.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507419 | N-W-NI-290620-Port_Charlotte_WTW-Final_RTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-07-02 | 2020-11-09 | 2021-09-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30743.52 | 30743.52 | 293.04 | 0 | 0 | 31036.56 | 0 | 0 | 0 | 0 | 31036.56 | 119022.58 | [5 empty] | N | WSNI | 100%
507935 | N-W-NI-290720-Dalmally_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-03 |  | 2020-09-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1239.87 | 1239.87 | 0 | 0 | 0 | 1239.87 | 0 | 0 | 0 | 0 | 1239.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508997 | N-W-NI-290920-Altnaharra_WTW-CPU | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-30 |  | 2020-11-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4355.39 | 4355.39 | 0 | 0 | 0 | 4355.39 | 0 | 0 | 0 | 0 | 4355.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509002 | N-W-NI-290920-Benbecula_WTW-Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1511.27 | 1511.27 | 0 | 0 | 0 | 1511.27 | 0 | 0 | 0 | 0 | 1511.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508990 | N-W-NI-290920-Camisky_Wellfield_WTW-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-30 |  | 2020-11-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10075 | 10075 | 0 | 0 | 0 | 10075 | 0 | 0 | 0 | 0 | 10075 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508993 | N-W-NI-290920-Glenconvinth_WTW-DWW Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-30 |  | 2020-10-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2102.84 | 2102.84 | 0 | 0 | 0 | 2102.84 | 0 | 0 | 0 | 0 | 2102.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509005 | N-W-NI-290920-Glenuig_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-30 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1625.39 | 1625.39 | 0 | 0 | 0 | 1625.39 | 0 | 0 | 0 | 0 | 1625.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508999 | N-W-NI-290920-Scourie_WTW-Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219.16 | 219.16 | 3130.84 | 0 | 0 | 3350 | 0 | 0 | 0 | 0 | 3350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509003 | N-W-NI-290920-Tullich_WTW-DAF Cleans | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-30 |  | 2020-03-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3282.82 | 3282.82 | 0 | 0 | 0 | 3282.82 | 0 | 0 | 0 | 0 | 3282.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509004 | N-W-NI-290920-Tullich_WTW-DAF Turb Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-30 |  | 2020-10-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563.5 | 563.5 | 0 | 0 | 0 | 563.5 | 0 | 0 | 0 | 0 | 563.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504518 | N-W-NI-291219-Craggie_TWP-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-01-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1548.33 | 0 | 1548.33 | 0 | 0 | 0 | 1548.33 | 0 | 0 | 0 | 0 | 1548.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504515 | N-W-NI-291219-Glenelg_WTW-FM_Transmitter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-03-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | -263.82 | 2536.18 | 0 | 0 | 0 | 2536.18 | 0 | 0 | 0 | 0 | 2536.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504513 | N-W-NI-291219-Glenuig_WTW-Heater | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-05-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | -449.38 | 950.62 | 0 | 0 | 0 | 950.62 | 0 | 0 | 0 | 0 | 950.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504519 | N-W-NI-291219-Grantown_DSR-Power_Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-01-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | -101.5 | 1098.5 | 0 | 0 | 0 | 1098.5 | 0 | 0 | 0 | 0 | 1098.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504517 | N-W-NI-291219-Kyle_WTW-Pressure_Guages | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-01-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | -351.7 | 1548.3 | 0 | 0 | 0 | 1548.3 | 0 | 0 | 0 | 0 | 1548.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504514 | N-W-NI-291219-Raasay_WTW-Turb_Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-02-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | -253.77 | 3846.23 | 0 | 0 | 0 | 3846.23 | 0 | 0 | 0 | 0 | 3846.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504516 | N-W-NI-291219-Teangue_WTW-Access_Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-06 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | -3317.76 | 232.24 | 3317.76 | 0 | 0 | 3550 | 0 | 0 | 0 | 0 | 3550 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512091 | N-W-NI-30032021-Camisky_Wellfield_WTW-Membrane | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 1714.26 | 0 | 0 | 1845.1 | 0 | 0 | 0 | 0 | 1845.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512112 | N-W-NI-30032021-Dalmally_Strae_RWI-Steps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588.79 | 588.79 | 7714.26 | 0 | 0 | 8303.05 | 0 | 0 | 0 | 0 | 8303.05 | 119022.58 | [5 empty] | N | CM_WSI | 100%
512093 | N-W-NI-30032021-Tullich_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3257.16 | 0 | 0 | 3505.76 | 0 | 0 | 0 | 0 | 3505.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507428 | N-W-NI-300620-Kyle_of_Lochalsh_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-01 |  | 2020-08-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1985.33 | 1985.33 | 0 | 0 | 0 | 1985.33 | 0 | 0 | 0 | 0 | 1985.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507433 | N-W-NI-300620-Lochmaddy_WOA-Legal_Fees | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-07-01 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 5000 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 311236.79 | [5 empty] | N | CM_M&G | 100%
507436 | N-W-NI-300620-Port_Charlotte_WTW-H&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-01 |  | 2020-10-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6141.97 | 6141.97 | 0 | 0 | 0 | 6141.97 | 0 | 0 | 0 | 0 | 6141.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507975 | N-W-NI-300720-Appin_TWS-Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-03 |  | 2020-09-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3041.94 | 3041.94 | 0 | 0 | 0 | 3041.94 | 0 | 0 | 0 | 0 | 3041.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507973 | N-W-NI-300720-Cladich_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-03 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1497.58 | 1497.58 | 0 | 0 | 0 | 1497.58 | 0 | 0 | 0 | 0 | 1497.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509561 | N-W-NI-301020-Rhenigidale_WTW-pH Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2021-04-01 |  | 2020-11-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1286.24 | 1286.24 | 0 | 0 | 0 | 1286.24 | 0 | 0 | 0 | 0 | 1286.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510053 | N-W-NI-301120-Glenconvinth_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2336.43 | 0 | 0 | 2499.98 | 0 | 0 | 0 | 0 | 2499.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504520 | N-W-NI-301219-Dervaig_WTW-Relift_Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-01-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1145.3 | 0 | 1145.3 | 0 | 0 | 0 | 1145.3 | 0 | 0 | 0 | 0 | 1145.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504521 | N-W-NI-301219-Mulindry_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-01-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | -529.9 | 1570.1 | 0 | 0 | 0 | 1570.1 | 0 | 0 | 0 | 0 | 1570.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504959 | N-W-NI-31012020-Tarbert WTW-CWT Access | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-03-02 | 2020-08-27 | 2021-02-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476.62 | 476.62 | 0 | 0 | 0 | 476.62 | 0 | 0 | 0 | 0 | 476.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504974 | N-W-NI-310120-Balnain_DSR-SiteBatteries | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 75.23 | 0 | 75.23 | 1074.77 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | 1150 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504954 | N-W-NI-310120-Glenvconvinth_WTW-Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-03 |  | 2020-04-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | 196.6 | 3746.6 | 0 | 0 | 0 | 3746.6 | 0 | 0 | 0 | 0 | 3746.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504968 | N-W-NI-310120-Mallaig_WTW-Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-03 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | -297.82 | 2502.18 | 297.82 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504973 | N-W-NI-310120-Tiree_WTW-Door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-02-03 |  | 2020-10-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | -171.69 | 3048.31 | 171.69 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 3220 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512126 | N-W-NI-31032021-Londornoch_WTW-DAF Scraper | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-04-01 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5228.58 | 0 | 0 | 5228.58 | 0 | 0 | 0 | 0 | 5228.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508485 | N-W-NI-310820 - LOCH HORN RWI 1998 NC802056-WI-Debris entering intake | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-09-03 | 2020-11-09 | 2021-02-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23119 | 23119 | 0 | 0 | 0 | 23119 | 0 | 0 | 0 | 0 | 23119 | 119022.58 | [5 empty] | N | CM_WSI | 100%
508476 | N-W-NI-310820- THUSATER TWP 1964 ND052691-WNI- Loss of Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-09-03 | 2021-05-10 | 2021-12-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14914.09 | 14914.09 | 40108.09 | 0 | 0 | 55022.18 | 0 | 0 | 0 | 0 | 55022.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508488 | N-W-NI-310820-Torra_WTW-Sand_Filter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-01 |  | 2020-10-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2362 | 2362 | 0 | 0 | 0 | 2362 | 0 | 0 | 0 | 0 | 2362 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510159 | N-W-NI-431220-Back_Tolsta_WTW-Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-07 |  | 2021-03-07 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1394.31 | 1394.31 | 305.7 | 0 | 0 | 1700.01 | 0 | 0 | 0 | 0 | 1700.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510161 | N-W-NI-431220-Broadfdord_WTW-Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-07 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1588.8 | 0 | 0 | 1700.01 | 0 | 0 | 0 | 0 | 1700.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510147 | N-W-NI-431220-Loch_Calder_RWI-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-07 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226.26 | 1226.26 | 73.74 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 119022.58 | [5 empty] | N | CM_WSI | 100%
510160 | N-W-NI-431220-Valtos_SR-Steps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-07 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 353.27 | 5046.72 | 0 | 0 | 5399.99 | 0 | 0 | 0 | 0 | 5399.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503855 | N-W-NI-Bogbain_TWP- Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 9700 | -9111.21 | 588.79 | 9111.21 | 0 | 0 | 9700 | 0 | 0 | 0 | 0 | 9700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504222 | N-W-NI-Bogbain_TWP-Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-06 |  | 2019-12-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2108.4 | 0 | 2108.4 | 0 | 0 | 0 | 2108.4 | 0 | 0 | 0 | 0 | 2108.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505142 | N-W-NI-Campbeltown_WTW-Soda deposits | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-20 | 2020-08-31 | 2020-12-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 68162 | 69662 | 0 | 0 | 0 | 69662 | 0 | 0 | 0 | 0 | 69662 | 119022.58 | [5 empty] | N | WSNI | 100%
503849 | N-W-NI-Moineruadh-CWT-Cl_Analyser | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-19 |  | 2020-03-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 9700 | -220.21 | 9479.79 | 0 | 0 | 0 | 9479.79 | 0 | 0 | 0 | 0 | 9479.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503978 | N-W-NI-Shiledaig_WTW-HMI | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-27 |  | 2019-12-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4170 | 0 | 4170 | 0 | 0 | 0 | 4170 | 0 | 0 | 0 | 0 | 4170 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503861 | N-W-NI-Tobermory_WTW-Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-02-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1437.84 | 0 | 1437.84 | 62.16 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504378 | N-WW-171219-Kiltarlity_STW-MLSS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-19 |  | 2020-01-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | -404.82 | 2815.18 | 0 | 0 | 0 | 2815.18 | 0 | 0 | 0 | 0 | 2815.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510992 | N-WW-I-010221-South_Bragar_DOA_Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-02-01 |  | 2021-03-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460.6 | 3460.6 | 339.4 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511531 | N-WW-I-010321-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-01 |  | 2021-06-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2571.42 | 0 | 0 | 2767.68 | 0 | 0 | 0 | 0 | 2767.68 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506426 | N-WW-I-010420-Thurso_DOA-BT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-01 |  | 2020-08-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1893.24 | 1893.24 | 0 | 0 | 0 | 1893.24 | 0 | 0 | 0 | 0 | 1893.24 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512154 | N-WW-I-010421-Lerwick_Gremista_SPS-Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-07-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6199.97 | 0 | 0 | 6199.97 | 0 | 0 | 0 | 0 | 6199.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508516 | N-WW-I-010920-Kyleakin_DOA-Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-02 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7973.45 | 7973.45 | 626.55 | 0 | 0 | 8600 | 0 | 0 | 0 | 0 | 8600 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509060 | N-WW-I-011020-Dalsetter_Wynd_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-10-01 |  | 2020-11-20 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10174.67 | 10174.67 | 0 | 0 | 0 | 10174.67 | 0 | 0 | 0 | 0 | 10174.67 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506060 | N-WW-I-020420-Lerwick_DOA-Rising_Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9076.68 | 9076.68 | 18773.32 | 0 | 0 | 27850 | 0 | 0 | 0 | 0 | 27850 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506969 | N-WW-I-020620-Tobermory_DOA-CCTV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-06-03 |  | 2020-09-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2473.93 | 2473.93 | 0 | 0 | 0 | 2473.93 | 0 | 0 | 0 | 0 | 2473.93 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504109 | N-WW-I-021219-Wick_DOA-Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2019-12-04 |  | 2020-01-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2013.5 | 0 | 2013.5 | 0 | 0 | 0 | 2013.5 | 0 | 0 | 0 | 0 | 2013.5 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510083 | N-WW-I-021220-Oban_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-12-03 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213.39 | 1213.39 | 86.61 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506075 | N-WW-I-030420-Ardrishaig_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-04-06 |  | 2020-04-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1475.01 | 1475.01 | 0 | 0 | 0 | 1475.01 | 0 | 0 | 0 | 0 | 1475.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508565 | N-WW-I-030920-Dornoch_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-03 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435.05 | 435.05 | 6214.95 | 0 | 0 | 6650 | 0 | 0 | 0 | 0 | 6650 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505520 | N-WW-I-040320-North_Toogs_Burra_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-09 |  | 2020-11-11 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8986.39 | 8986.39 | 0 | 0 | 0 | 8986.39 | 0 | 0 | 0 | 0 | 8986.39 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506444 | N-WW-I-040520 - Salen Tigh Na Drochaid - Replace Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-05-29 | 2020-10-12 | 2021-04-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42529 | 42529 | 1171.3 | 0 | 0 | 43700.3 | 0 | 0 | 0 | 0 | 43700.3 | 209381.79 | [5 empty] | N | WWI | 100%
504135 | N-WW-I-041219-Muir_of_Ord-CCTV_Scoping | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2019-12-04 |  | 2020-01-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1840.37 | 0 | 1840.37 | 0 | 0 | 0 | 1840.37 | 0 | 0 | 0 | 0 | 1840.37 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504157 | N-WW-I-041219-Wick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2019-12-04 |  | 2020-01-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -114.76 | 1885.24 | 0 | 0 | 0 | 1885.24 | 0 | 0 | 0 | 0 | 1885.24 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510156 | N-WW-I-041220-Beachcroft_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-12-07 |  | 2021-03-20 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5837.78 | 5837.78 | -349.89 | 0 | 0 | 5487.89 | 0 | 0 | 0 | 0 | 5487.89 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510158 | N-WW-I-041220-Inver_Tce_DOA-B Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-12-07 |  | 2021-04-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1119.69 | 1119.69 | 80.31 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510536 | N-WW-I-050121-Oban_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-01-06 |  | 2021-02-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1911.82 | 1911.82 | 88.2 | 0 | 0 | 2000.02 | 0 | 0 | 0 | 0 | 2000.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510537 | N-WW-I-050121-Oban_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-01-06 |  | 2021-02-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669.74 | 1669.74 | 130.28 | 0 | 0 | 1800.02 | 0 | 0 | 0 | 0 | 1800.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505542 | N-WW-I-05032020-Campbeltown Kinloch Park - DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-06 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 160.38 | 0 | 160.38 | 1239.62 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507052 | N-WW-I-050620-Inverness_DOA-CCTV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-06-05 |  | 2020-07-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 920 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507055 | N-WW-I-050620-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-06-05 |  | 2021-03-13 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6046.35 | 6046.35 | 6803.65 | 0 | 0 | 12850 | 0 | 0 | 0 | 0 | 12850 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510539 | N-WW-I-060121-Thurso_DOA-BT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-01-06 |  | 2021-02-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3201.42 | 3201.42 | 48.56 | 0 | 0 | 3249.98 | 0 | 0 | 0 | 0 | 3249.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506105 | N-WW-I-060420-Shawbost_DOA_Manhole_Cover | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-04-07 |  | 2020-07-28 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3741.31 | 3741.31 | 0 | 0 | 0 | 3741.31 | 0 | 0 | 0 | 0 | 3741.31 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512207 | N-WW-I-060421-Brora_STW-Outfall Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600.01 | 0 | 0 | 2600.01 | 0 | 0 | 0 | 0 | 2600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512195 | N-WW-I-060421-Dornie_Lochside_SEP-Oufall Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900.01 | 0 | 0 | 1900.01 | 0 | 0 | 0 | 0 | 1900.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509670 | N-WW-I-061120-Portree_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-06 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.56 | 320.56 | 4579.44 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 4900 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504238 | N-WW-I-061219-Leverburgh-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2019-12-12 |  | 2020-02-14 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1344.56 | 0 | 1344.56 | 0 | 0 | 0 | 1344.56 | 0 | 0 | 0 | 0 | 1344.56 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504537 | N-WW-I-070120-Thurso_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-01-09 |  | 2020-03-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1757.07 | 0 | 1757.07 | 0 | 0 | 0 | 1757.07 | 0 | 0 | 0 | 0 | 1757.07 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508610 | N-WW-I-070920-Ft_William_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-09-07 |  | 2021-02-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14915.89 | 14915.89 | 0 | 0 | 0 | 14915.89 | 0 | 0 | 0 | 0 | 14915.89 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508602 | N-WW-I-070920-Isle_of_Mull_Salen_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1495.33 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508619 | N-WW-I-070920-Ullapool_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-09-07 |  | 2020-11-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4863.81 | 4863.81 | 0 | 0 | 0 | 4863.81 | 0 | 0 | 0 | 0 | 4863.81 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510581 | N-WW-I-080121-Inverness DOA- Lochardil Pl MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-01-08 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232.74 | 1232.74 | 67.26 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510583 | N-WW-I-080121-Inverness DOA- Victorai Tce MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-01-08 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 8.5 | 1291.48 | 0 | 0 | 1299.98 | 0 | 0 | 0 | 0 | 1299.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507588 | N-WW-I-080720-Yell_Burravoe_DOA- Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-07-10 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471.03 | 471.03 | 6728.97 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 7200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510205 | N-WW-I-081220-Balivanich_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-12-08 |  | 2021-02-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4436.16 | 4436.16 | -636.18 | 0 | 0 | 3799.98 | 0 | 0 | 0 | 0 | 3799.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510206 | N-WW-I-081220-North_Connel_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-12-10 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6403.45 | 6403.45 | 96.57 | 0 | 0 | 6500.02 | 0 | 0 | 0 | 0 | 6500.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510202 | N-WW-I-081220-Voe_DOA-Sewer MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-12-08 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5514.03 | 0 | 0 | 5900.01 | 0 | 0 | 0 | 0 | 5900.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507034 | N-WW-I-090620-Scalloway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-09 |  | 2020-08-12 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8699.78 | 8699.78 | 0 | 0 | 0 | 8699.78 | 0 | 0 | 0 | 0 | 8699.78 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509196 | N-WW-I-091020-Golspie_DOA-B Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-10-12 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2374.25 | 2374.25 | 825.75 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510212 | N-WW-I-091220-Wick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-12-10 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3193.99 | 3193.99 | 106.02 | 0 | 0 | 3300.01 | 0 | 0 | 0 | 0 | 3300.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504611 | N-WW-I-100120-Muir_of_Ord-Pipe_Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-01-14 |  | 2020-02-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 5350 | -263.68 | 5086.32 | 0 | 0 | 0 | 5086.32 | 0 | 0 | 0 | 0 | 5086.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504599 | N-WW-I-100120-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-16 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 8600 | -7994.32 | 605.68 | 7994.32 | 0 | 0 | 8600 | 0 | 0 | 0 | 0 | 8600 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505126 | N-WW-I-100220-Ardrishaig_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-11 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 643.57 | 0 | 643.57 | -33.57 | 0 | 0 | 610 | 0 | 0 | 0 | 0 | 610 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505118 | N-WW-I-100220-Broadstone_Av | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 562.62 | 0 | 562.62 | 8037.38 | 0 | 0 | 8600 | 0 | 0 | 0 | 0 | 8600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511146 | N-WW-I-100221-Inverness_DOA-Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-10 |  | 2021-05-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344.44 | 1344.44 | 55.56 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505625 | N-WW-I-100320-Inverness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-10 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 147.2 | 2112.18 | 2259.38 | -9.38 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2250 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507120 | N-WW-I-100620-Beauly_DOA-RisingMain | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-06-10 |  | 2020-06-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4868.89 | 4868.89 | 0 | 0 | 0 | 4868.89 | 0 | 0 | 0 | 0 | 4868.89 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507628 | N-WW-I-100720-Wick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-13 |  | 2020-09-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3167.35 | 3167.35 | 0 | 0 | 0 | 3167.35 | 0 | 0 | 0 | 0 | 3167.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508125 | N-WW-I-100820-Lerwick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-08-11 |  | 2020-11-19 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5591.55 | 5591.55 | 2968.45 | 0 | 0 | 8560 | 0 | 0 | 0 | 0 | 8560 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508694 | N-WW-I-100920-Evanton_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-10 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4590.63 | 4590.63 | 0 | 0 | 0 | 4590.63 | 0 | 0 | 0 | 0 | 4590.63 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509703 | N-WW-I-101120-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-11-11 |  | 2020-10-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1324.59 | 1324.59 | 0 | 0 | 0 | 1324.59 | 0 | 0 | 0 | 0 | 1324.59 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505128 | N-WW-I-110220-Lerwick_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-09-18 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1244.45 | 1244.45 | 0 | 0 | 0 | 1244.45 | 0 | 0 | 0 | 0 | 1244.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505130 | N-WW-I-110220-Oban_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-02-11 |  | 2020-02-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1338.93 | 0 | 1338.93 | 0 | 0 | 0 | 1338.93 | 0 | 0 | 0 | 0 | 1338.93 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508153 | N-WW-I-110820-Salen_DOA-Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-08-13 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1495.33 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508717 | N-WW-I-110920-Inverness_DOA_29_Clachnaharry_Rd_ Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-17 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507158 | N-WW-I-120620-Port of Ness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-06-12 |  | 2020-07-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2660.34 | 2660.34 | 0 | 0 | 0 | 2660.34 | 0 | 0 | 0 | 0 | 2660.34 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509222 | N-WW-I-121020-Crinan_DOA- Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-10-12 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.95 | 198.95 | 2401.05 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510688 | N-WW-I-130121-Inverness_DOA-BTrap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1130.35 | 1130.35 | 69.65 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510692 | N-WW-I-130121-Lerwick_DOA-B Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-01-13 |  | 2021-03-16 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5371.6 | 5371.6 | 428.4 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 5800 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506605 | N-WW-I-130520-Balvicar_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-14 |  | 2020-05-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2573.28 | 2573.28 | 0 | 0 | 0 | 2573.28 | 0 | 0 | 0 | 0 | 2573.28 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506589 | N-WW-I-130520-Kiltarlity_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-14 |  | 2020-08-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6110.03 | 6110.03 | 0 | 0 | 0 | 6110.03 | 0 | 0 | 0 | 0 | 6110.03 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507665 | N-WW-I-130720-Bowmore_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1214.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506615 | N-WW-I-140520-Inverness_DOA-Sewer & MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-14 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1728.31 | 1728.31 | 871.69 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508198 | N-WW-I-140820-Vatersay_DOA_Sea_Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-08-17 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 2056.07 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510303 | N-WW-I-141220-Latheronwheel_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2662.62 | 2662.62 | 38037.39 | 0 | 0 | 40700.01 | 0 | 0 | 0 | 0 | 40700.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506631 | N-WW-I-150520-Balintore_DOA_14_Bank_Street | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371.67 | 1371.67 | 0 | 0 | 0 | 1371.67 | 0 | 0 | 0 | 0 | 1371.67 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506632 | N-WW-I-150520-Balintore_DOA_Balintore_Inn | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329.43 | 1329.43 | 0 | 0 | 0 | 1329.43 | 0 | 0 | 0 | 0 | 1329.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508765 | N-WW-I-150920 - Latheronwheel DOA - Sewer Rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-10-27 | 2022-04-01 | 2022-11-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4539 | 4539 | 60471.36 | 0 | 0 | 65010.36 | 0 | 0 | 0 | 0 | 65010.36 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505221 | N-WW-I-160220-Thurso_DOA-BT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-02-18 |  | 2020-10-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 212.62 | 2979.8 | 3192.42 | 0 | 0 | 0 | 3192.42 | 0 | 0 | 0 | 0 | 3192.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507735 | N-WW-I-160720-Beauly_DOA-Buchan Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-07-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259.05 | 1259.05 | -59.05 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507728 | N-WW-I-160720-Kilmichael_DOA-Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-16 |  | 2020-07-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2094.62 | 2094.62 | 0 | 0 | 0 | 2094.62 | 0 | 0 | 0 | 0 | 2094.62 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507725 | N-WW-I-160720-Oban_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-16 |  | 2020-08-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2894.88 | 2894.88 | 0 | 0 | 0 | 2894.88 | 0 | 0 | 0 | 0 | 2894.88 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509309 | N-WW-I-161020-Invergordon_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-10-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27218.97 | 27218.97 | 20981.03 | 0 | 0 | 48200 | 0 | 0 | 0 | 0 | 48200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509297 | N-WW-I-161020-Lochgilphead_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-10-16 |  | 2020-10-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1567.43 | 1567.43 | 0 | 0 | 0 | 1567.43 | 0 | 0 | 0 | 0 | 1567.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511839 | N-WW-I-170321-Tobermory_DOA-Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4579.44 | 4579.44 | 65420.56 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507233 | N-WW-I-170620-Campbeltown_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-06-17 |  | 2020-06-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5682.08 | 5682.08 | 0 | 0 | 0 | 5682.08 | 0 | 0 | 0 | 0 | 5682.08 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510371 | N-WW-I-171220-Sandwick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.42 | 0 | 0 | 1400.01 | 0 | 0 | 0 | 0 | 1400.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505280 | N-WW-I-180220-Thurso_DOA-BT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-02-19 |  | 2020-06-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 1626.8 | 1751.1 | 0 | 0 | 0 | 1751.1 | 0 | 0 | 0 | 0 | 1751.1 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508258 | N-WW-I-180820-Ballachulish_DOA-Embankment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-08-19 |  | 2020-10-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22908.15 | 22908.15 | 0 | 0 | 0 | 22908.15 | 0 | 0 | 0 | 0 | 22908.15 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510420 | N-WW-I-181220-Mossbank_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5509.83 | 5509.83 | 190.17 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 5700 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505307 | N-WW-I-190220-Stornoway_DOA-Sewer | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS2 |  | 2020-02-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 369.69 | 1742 | 2111.69 | 38.31 | 38.31 | 53.1808 | 2150 | 14.8708 | 0 | 0 | 14.8708 | 2164.8708 | 346964.42 | [5 empty] | N | EC01A | 100%
506691 | N-WW-I-190520-Lochgilphead_DOA-Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-20 |  | 2020-07-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014.11 | 2014.11 | 0 | 0 | 0 | 2014.11 | 0 | 0 | 0 | 0 | 2014.11 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507271 | N-WW-I-190620-Inverness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-06-22 |  | 2020-08-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200.35 | 7200.35 | 0 | 0 | 0 | 7200.35 | 0 | 0 | 0 | 0 | 7200.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508282 | N-WW-I-190820-Dalmally_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-08-19 |  | 2020-08-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2374.48 | 2374.48 | 0 | 0 | 0 | 2374.48 | 0 | 0 | 0 | 0 | 2374.48 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509326 | N-WW-I-191020- Cromarty_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-10-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510.43 | 1510.43 | -10.43 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503871 | N-WW-I-191119-Wick_DOA_Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2019-11-21 |  | 2019-12-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1353.25 | 0 | 1353.25 | 0 | 0 | 0 | 1353.25 | 0 | 0 | 0 | 0 | 1353.25 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509890 | N-WW-I-191120-Glenachulish_SEP-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-19 |  | 2021-02-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3812.6 | 3812.6 | -12.6 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509899 | N-WW-I-191120-Strathpeffer_DOA- MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1169.61 | 1169.61 | 630.39 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505331 | N-WW-I-200220-Leurbost_East_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-02-24 |  | 2020-06-09 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 3462 | 3743.31 | 0 | 0 | 0 | 3743.31 | 0 | 0 | 0 | 0 | 3743.31 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505322 | N-WW-I-200220-Rosskeen_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4894.49 | 0 | 4894.49 | 0 | 0 | 0 | 4894.49 | 0 | 0 | 0 | 0 | 4894.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505319 | N-WW-I-200220-Strathpeffer_DOA - Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-24 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 771.96 | 8153.56 | 8925.52 | 2874.48 | 0 | 0 | 11800 | 0 | 0 | 0 | 0 | 11800 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505859 | N-WW-I-200320-Kingussie_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-23 |  | 2020-05-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 609.07 | 8658.74 | 9267.81 | 0 | 0 | 0 | 9267.81 | 0 | 0 | 0 | 0 | 9267.81 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506707 | N-WW-I-200520-Lochgilphead_DOA_28_Kilmory_Road | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-20 |  | 2020-05-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5968.62 | 5968.62 | 0 | 0 | 0 | 5968.62 | 0 | 0 | 0 | 0 | 5968.62 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509361 | N-WW-I-201020-Watten_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-10-21 |  | 2020-11-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2978.46 | 2978.46 | 0 | 0 | 0 | 2978.46 | 0 | 0 | 0 | 0 | 2978.46 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509911 | N-WW-I-201120-Stornoway_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6916.56 | 6916.56 | 3183.44 | 0 | 0 | 10100 | 0 | 0 | 0 | 0 | 10100 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504446 | N-WW-I-201219-Inverness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1111.75 | 0 | 1111.75 | 88.25 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504443 | N-WW-I-201219-Kingussie_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 7856 | -134.7 | 7721.3 | 134.7 | 0 | 0 | 7856 | 0 | 0 | 0 | 0 | 7856 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505866 | N-WW-I-210320-Keiss_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-23 |  | 2020-06-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 134.11 | 1868.6 | 2002.71 | 0 | 0 | 0 | 2002.71 | 0 | 0 | 0 | 0 | 2002.71 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505868 | N-WW-I-210320-N_Toogs_Burra_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-05-01 |  | 2020-10-10 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9465.18 | 9465.18 | 0 | 0 | 0 | 9465.18 | 0 | 0 | 0 | 0 | 9465.18 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506754 | N-WW-I-210520-Thurso_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2336.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507788 | N-WW-I-210720-Lerwick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-07-21 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1717.29 | 1717.29 | 24532.71 | 0 | 0 | 26250 | 0 | 0 | 0 | 0 | 26250 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507792 | N-WW-I-210720-Oban_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-21 |  | 2020-10-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13690.84 | 13690.84 | 0 | 0 | 0 | 13690.84 | 0 | 0 | 0 | 0 | 13690.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507796 | N-WW-I-210720-Thurso_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7724.66 | 7724.66 | 125.34 | 0 | 0 | 7850 | 0 | 0 | 0 | 0 | 7850 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511380 | N-WW-I-220221-Inverness_DOA-Trap IV1 1DW | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511377 | N-WW-I-220221-Inverness_DOA-Trap IV1 1EY | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511372 | N-WW-I-220221-Inverness_DOA-Trap IV3 5LR | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1214.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511382 | N-WW-I-220221-Inverness_DOA-Trap IV3 8HW | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1198.3 | 1198.3 | 1.7 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505873 | N-WW-I-220320-Eochar_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-23 |  | 2020-11-02 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 245.33 | 3220 | 3465.33 | 0 | 0 | 0 | 3465.33 | 0 | 0 | 0 | 0 | 3465.33 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505872 | N-WW-I-220320-Inverness_DOA-Dunabban_Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 147.2 | 2064.6 | 2211.8 | 38.2 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2250 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505870 | N-WW-I-220320-Inverness_DOA-KingDuncan-BTrap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 147.2 | 2064.6 | 2211.8 | 38.2 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2250 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507835 | N-WW-I-220720-Dingwall_DOA_2_George_Street | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-07-27 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5300 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 5300 | 209381.79 | [5 empty] | N | WWI | 100%
507814 | N-WW-I-220720-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-07-22 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212.62 | 212.62 | 3037.38 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 3250 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508885 | N-WW-I-22092020-Drumnadrochit_DOA | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27626.63 | 27626.63 | 0 | 0 | 0 | 27626.63 | 0 | 0 | 0 | 0 | 27626.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503925 | N-WW-I-221119-Cromarty_DOA-MH_Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-11-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -81.96 | 2418.04 | 81.96 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 209381.79 | [5 empty] | N | WWI | 100%
505375 | N-WW-I-230220-Ft Augustus_DOA- Canal_Centre NRV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25135.89 | 25135.89 | -25135.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWI | 100%
505370 | N-WW-I-230220-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-02-24 |  | 2020-04-14 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 1353 | 1451.13 | 0 | 0 | 0 | 1451.13 | 0 | 0 | 0 | 0 | 1451.13 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508913 | N-WW-I-23092020-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-09-23 |  | 2020-09-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4973.27 | 4973.27 | 0 | 0 | 0 | 4973.27 | 0 | 0 | 0 | 0 | 4973.27 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508905 | N-WW-I-23092020-Thurso_DOA-B Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1807.03 | 1807.03 | 0 | 0 | 0 | 1807.03 | 0 | 0 | 0 | 0 | 1807.03 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508920 | N-WW-I-23092020-Thurso_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7476.65 | 7476.65 | 0 | 0 | 0 | 7476.65 | 0 | 0 | 0 | 0 | 7476.65 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508908 | N-WW-I-23092020-Vatersay_DOA-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-09-23 |  | 2021-02-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6095.23 | 6095.23 | 0 | 0 | 0 | 6095.23 | 0 | 0 | 0 | 0 | 6095.23 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509925 | N-WW-I-231120-Yell_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261.68 | 261.68 | 3738.32 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505907 | N-WW-I-240320-Aviemore_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-25 |  | 2020-08-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 932.24 | 13908.69 | 14840.93 | 0 | 0 | 0 | 14840.93 | 0 | 0 | 0 | 0 | 14840.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505912 | N-WW-I-240320-Eriska;y_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-25 |  | 2020-08-13 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 2920 | 3130 | 0 | 0 | 0 | 3130 | 0 | 0 | 0 | 0 | 3130 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505918 | N-WW-I-240320-Oban_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-25 |  | 2020-04-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 4924 | 5274 | 0 | 0 | 0 | 5274 | 0 | 0 | 0 | 0 | 5274 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505917 | N-WW-I-240320-Wick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-25 |  | 2020-07-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 203.46 | 2832 | 3035.46 | 0 | 0 | 0 | 3035.46 | 0 | 0 | 0 | 0 | 3035.46 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503946 | N-WW-I-241119-Helmsdale_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2019-11-25 |  | 2020-01-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5536.05 | 0 | 5536.05 | 0 | 0 | 0 | 5536.05 | 0 | 0 | 0 | 0 | 5536.05 | 209381.79 | [5 empty] | N | WWI | 100%
511475 | N-WW-I-250221-Balivanich_DOA-X Connection | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338.91 | 338.91 | 4532.7 | 0 | 0 | 4871.61 | 0 | 0 | 0 | 0 | 4871.61 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512026 | N-WW-I-250321-Lochgilphead_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2672.44 | 2672.44 | 27.56 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506811 | N-WW-I-250520-Achmore_ST_DOA_Manholes | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-25 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1856 | 1856 | 0 | 0 | 0 | 1856 | 0 | 0 | 0 | 0 | 1856 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506815 | N-WW-I-250520-Doune-DOA_Rising_Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-26 |  | 2020-06-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573.3 | 1573.3 | 0 | 0 | 0 | 1573.3 | 0 | 0 | 0 | 0 | 1573.3 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508373 | N-WW-I-250820-Kingussie_DOA-Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2684.6 | 2684.6 | 115.4 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506826 | N-WW-I-260520-Inverness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-26 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724.77 | 1724.77 | 75.23 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506836 | N-WW-I-260520-Thurso_DOA- Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-26 |  | 2020-06-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036.28 | 2036.28 | 0 | 0 | 0 | 2036.28 | 0 | 0 | 0 | 0 | 2036.28 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507384 | N-WW-I-260620-Tarbert_DOA-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-06-29 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4293.6 | 4293.6 | -293.6 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510922 | N-WW-I-270121-Gairloch_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 3960 | 0 | 0 | 4045.05 | 0 | 0 | 0 | 0 | 4045.05 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505443 | N-WW-I-270220-Tolsta_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-05-01 |  | 2020-06-09 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3498 | 3498 | 0 | 0 | 0 | 3498 | 0 | 0 | 0 | 0 | 3498 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506841 | N-WW-I-270520-Thurso_DOA- Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-28 |  | 2020-10-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4353.48 | 4353.48 | 0 | 0 | 0 | 4353.48 | 0 | 0 | 0 | 0 | 4353.48 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509482 | N-WW-I-271020-Cromdale_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-10-27 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2665.68 | 2665.68 | 34.32 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509498 | N-WW-I-271020-Grantown DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-10-27 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2603.67 | 2603.67 | 96.33 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509481 | N-WW-I-271020-Inverness_DOA-Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-10-27 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149.05 | 1149.05 | 50.95 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504033 | N-WW-I-271119-Ft_William_Ashburn_Lane-Hatchbox | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2019-11-29 |  | 2020-04-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | -153.95 | 1546.05 | 0 | 0 | 0 | 1546.05 | 0 | 0 | 0 | 0 | 1546.05 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504508 | N-WW-I-271219-Bayble_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-01-06 |  | 2020-01-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | -554.79 | 1145.21 | 0 | 0 | 0 | 1145.21 | 0 | 0 | 0 | 0 | 1145.21 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504507 | N-WW-I-271219-Inverness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-06 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4482.68 | 0 | 4482.68 | 17.32 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510952 | N-WW-I-280121-Conon_Bridge_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530.37 | 1530.37 | 69.63 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510953 | N-WW-I-280121-Inverness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484.11 | 484.11 | 6915.88 | 0 | 0 | 7399.99 | 0 | 0 | 0 | 0 | 7399.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507916 | N-WW-I-280720 - Aviemore DOA - Burnside Road - Replace 18.5m of Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-09-17 | 2022-05-13 | 2022-12-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3765 | 3765 | 41234.74 | 0 | 0 | 44999.74 | 0 | 0 | 0 | 0 | 44999.74 | 209381.79 | [5 empty] | N | WWI | 100%
507911 | N-WW-I-280720 - Inverness DOA - Ardconnel Terrace - Resolve Sewer Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-08-20 | 2020-11-02 | 2021-07-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8538 | 8538 | 5748.7 | 0 | 0 | 14286.7 | 0 | 0 | 0 | 0 | 14286.7 | 209381.79 | [5 empty] | N | WWI | 100%
507913 | N-WW-I-280720 - Inverness DOA - Lochalsh Road - Replace 85m of Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-09-17 | 2022-05-13 | 2022-12-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5233.64 | 5233.64 | 74766.26 | 0 | 0 | 79999.9 | 0 | 0 | 0 | 0 | 79999.9 | 209381.79 | [5 empty] | N | WWI | 100%
507914 | N-WW-I-280720 - Kingussie DOA - Kingussie West SPS - Resolve Sewer Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-24 | 2022-05-09 | 2022-12-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6913.62 | 6913.62 | 63086.38 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000 | 90601.29 | [5 empty] | N | WWNI | 100%
508978 | N-WW-I-280920-Alness_Invergordon_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-29 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6032.55 | 6032.55 | 0 | 0 | 0 | 6032.55 | 0 | 0 | 0 | 0 | 6032.55 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508979 | N-WW-I-280920-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-09-29 |  | 2020-10-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1364.94 | 1364.94 | 0 | 0 | 0 | 1364.94 | 0 | 0 | 0 | 0 | 1364.94 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509511 | N-WW-I-281020-Drumnadrochit_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-10-28 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2623.29 | 2623.29 | 376.71 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504070 | N-WW-I-281119-Inverness-DOA-Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-11-29 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 7.04 | 1207.04 | -7.04 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504923 | N-WW-I-290120-North_Toogs_Burra_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-05-01 |  | 2020-04-03 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 7820 | -605 | 7215 | 605 | 0 | 0 | 7820 | 0 | 0 | 0 | 0 | 7820 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512077 | N-WW-I-290321-Aultbea_Cemetry_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1200 | 0 | 0 | 1291.59 | 0 | 0 | 0 | 0 | 1291.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512074 | N-WW-I-290321-Oban_Ganavan_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273.61 | 273.61 | 2828.58 | 0 | 0 | 3102.19 | 0 | 0 | 0 | 0 | 3102.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512071 | N-WW-I-290321-Portree_Cuillin_Hills_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.49 | 114.49 | 1500 | 0 | 0 | 1614.49 | 0 | 0 | 0 | 0 | 1614.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512072 | N-WW-I-290321-Portree_Main_SPS-Penstock | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212.62 | 212.62 | 2785.74 | 0 | 0 | 2998.36 | 0 | 0 | 0 | 0 | 2998.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512075 | N-WW-I-290321-Rosskeen_Transfer_SPS-Impellors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 4285.74 | 0 | 0 | 4468.92 | 0 | 0 | 0 | 0 | 4468.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509542 | N-WW-I-291020-Strathy_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-10-29 |  | 2020-11-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6412.53 | 6412.53 | 0 | 0 | 0 | 6412.53 | 0 | 0 | 0 | 0 | 6412.53 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505994 | N-WW-I-300320-Lerwick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-05-01 |  | 2020-09-22 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5880.45 | 5880.45 | 0 | 0 | 0 | 5880.45 | 0 | 0 | 0 | 0 | 5880.45 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505999 | N-WW-I-300320-Thurso_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-31 |  | 2020-06-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2422.8 | 2422.8 | 0 | 0 | 0 | 2422.8 | 0 | 0 | 0 | 0 | 2422.8 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505998 | N-WW-I-300320-Wick_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-31 |  | 2020-09-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3746.23 | 3746.23 | 0 | 0 | 0 | 3746.23 | 0 | 0 | 0 | 0 | 3746.23 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506000 | N-WW-I-300320-Wick_DOA-Sewer-MurchisonSt | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-31 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256.32 | 256.32 | 3150 | 0 | 0 | 3406.32 | 0 | 0 | 0 | 0 | 3406.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512097 | N-WW-I-300321-Dingwall_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392.52 | 392.52 | 5142.84 | 0 | 0 | 5535.36 | 0 | 0 | 0 | 0 | 5535.36 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512113 | N-WW-I-300321-Inver_Terrace_DOA-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1028.58 | 0 | 0 | 1107.08 | 0 | 0 | 0 | 0 | 1107.08 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506413 | N-WW-I-300420-Thurso_DOA_CCTV_Surveys | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-04-30 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113.5 | 9113.5 | 1586.5 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509027 | N-WW-I-300920-Balintore_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-09-30 |  | 2021-02-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1525.35 | 1525.35 | 0 | 0 | 0 | 1525.35 | 0 | 0 | 0 | 0 | 1525.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506018 | N-WW-I-310320-Lerwick_DOA-Rising_Main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-04-03 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 9866.29 | 0 | 9866.29 | 0 | 0 | 0 | 9866.29 | 0 | 0 | 0 | 0 | 9866.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512130 | N-WW-I-310321-Oban_DOA-Manholes | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-04-06 |  | 2021-06-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730.66 | 1730.66 | -30.66 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512143 | N-WW-I-310321-Roybridge_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1457.16 | 0 | 0 | 1457.16 | 0 | 0 | 0 | 0 | 1457.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512137 | N-WW-I-310321-Thurso_East_DOA-Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-04-01 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1971.42 | 0 | 0 | 1971.42 | 0 | 0 | 0 | 0 | 1971.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510988 | N-WW-NI-010221-Tarbert_Oakfield_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-01 |  | 2021-03-14 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4567.1 | 4567.1 | 32.9 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 4600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511008 | N-WW-NI-010221-Thurso_STC-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2733.26 | 2733.26 | 66.7 | 0 | 0 | 2799.96 | 0 | 0 | 0 | 0 | 2799.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511572 | N-WW-NI-010321-Cawdor_STW-UV Bulbs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-06-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1200 | 0 | 0 | 1291.59 | 0 | 0 | 0 | 0 | 1291.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511577 | N-WW-NI-010321-Croy_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-06-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 170.09 | 2228.58 | 0 | 0 | 2398.67 | 0 | 0 | 0 | 0 | 2398.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511534 | N-WW-NI-010321-Kirkwall_Ayre_Rd_SPS-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-01 |  | 2021-06-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2057.16 | 0 | 0 | 2214.17 | 0 | 0 | 0 | 0 | 2214.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511564 | N-WW-NI-010321-Nairn_STW-UV Lamps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-06-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857.01 | 857.01 | 12242.99 | 0 | 0 | 13100 | 0 | 0 | 0 | 0 | 13100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511575 | N-WW-NI-010321-Strathpeffer_STW-Heaters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-06-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.95 | 1684.95 | 515.05 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506437 | N-WW-NI-010420-Alness_Invergordon_STC-HMI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-04 |  | 2020-05-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1065 | 1065 | 0 | 0 | 0 | 1065 | 0 | 0 | 0 | 0 | 1065 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506046 | N-WW-NI-010420-Campbeltown_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-06-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23053.76 | 23053.76 | 0 | 0 | 0 | 23053.76 | 0 | 0 | 0 | 0 | 23053.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506045 | N-WW-NI-010420-Fortrose_STW-Biodisc_Filter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5596.53 | 5596.53 | 203.47 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 5800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506040 | N-WW-NI-010420-Kiltarlity_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-05-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8149.56 | 8149.56 | 0 | 0 | 0 | 8149.56 | 0 | 0 | 0 | 0 | 8149.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506033 | N-WW-NI-010420-Oban_Corran_Park_SPS-ST_Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-09-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1758.03 | 1758.03 | 0 | 0 | 0 | 1758.03 | 0 | 0 | 0 | 0 | 1758.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506043 | N-WW-NI-010420-Riverbank_Tce_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-06-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3507.43 | 3507.43 | 0 | 0 | 0 | 3507.43 | 0 | 0 | 0 | 0 | 3507.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506036 | N-WW-NI-010420-Tain_Golf_Course_SPS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-07 |  | 2020-09-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5082.84 | 5082.84 | 0 | 0 | 0 | 5082.84 | 0 | 0 | 0 | 0 | 5082.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512171 | N-WW-NI-010421-Arnol_STW-Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200.01 | 0 | 0 | 1200.01 | 0 | 0 | 0 | 0 | 1200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512147 | N-WW-NI-010421-Boat_of_Garten_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-07-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7599.97 | 0 | 0 | 7599.97 | 0 | 0 | 0 | 0 | 7599.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512149 | N-WW-NI-010421-Coll_Garyguirm_Sep-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-04-01 |  | 2021-07-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000.01 | 0 | 0 | 4000.01 | 0 | 0 | 0 | 0 | 4000.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512158 | N-WW-NI-010421-Halkirk_STW-Sprinkler System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-07-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1099.98 | 0 | 0 | 1099.98 | 0 | 0 | 0 | 0 | 1099.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512151 | N-WW-NI-010421-Kirkwall_HoW_STC-Conveyor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-07-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800.01 | 0 | 0 | 6800.01 | 0 | 0 | 0 | 0 | 6800.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512145 | N-WW-NI-010421-Oban_STW-PST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-07-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 35000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512156 | N-WW-NI-010421-Oban_STW-PST1 PST2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-07-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21399.98 | 0 | 0 | 21399.98 | 0 | 0 | 0 | 0 | 21399.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512168 | N-WW-NI-010421-Thurso_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-07-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3699.99 | 0 | 0 | 3699.99 | 0 | 0 | 0 | 0 | 3699.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507483 | N-WW-NI-010720-Broadford_STW-Dewaterer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-08-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4057.43 | 4057.43 | 0 | 0 | 0 | 4057.43 | 0 | 0 | 0 | 0 | 4057.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508531 | N-WW-NI-010920-Coastguard_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-02 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32923.6 | 32923.6 | 2076.4 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 35000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508515 | N-WW-NI-010920-Kilmory_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-02 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.07 | 119.07 | 1700.93 | 0 | 0 | 1820 | 0 | 0 | 0 | 0 | 1820 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508522 | N-WW-NI-010920-Kirkhill_STW-Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-02 |  | 2020-11-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13205.34 | 13205.34 | 0 | 0 | 0 | 13205.34 | 0 | 0 | 0 | 0 | 13205.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508529 | N-WW-NI-010920-Oban_Corran_Park_SPS-Macerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-02 |  | 2020-09-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565.93 | 1565.93 | 0 | 0 | 0 | 1565.93 | 0 | 0 | 0 | 0 | 1565.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508512 | N-WW-NI-010920-Oban_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-02 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.07 | 119.07 | 1700.93 | 0 | 0 | 1820 | 0 | 0 | 0 | 0 | 1820 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508509 | N-WW-NI-010920-Wellpark_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-02 |  | 2020-11-03 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1473.53 | 1473.53 | 0 | 0 | 0 | 1473.53 | 0 | 0 | 0 | 0 | 1473.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509059 | N-WW-NI-011020-Bridge_End_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-01 |  | 2020-03-12 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2749.74 | 2749.74 | 0 | 0 | 0 | 2749.74 | 0 | 0 | 0 | 0 | 2749.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509061 | N-WW-NI-011020-Clachan_Balvicar_STW-MBR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-01 |  | 2020-11-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37956.58 | 37956.58 | 0 | 0 | 0 | 37956.58 | 0 | 0 | 0 | 0 | 37956.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509063 | N-WW-NI-011020-Fortrose_STW-MH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-01 |  | 2020-11-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1393.35 | 1393.35 | 0 | 0 | 0 | 1393.35 | 0 | 0 | 0 | 0 | 1393.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509056 | N-WW-NI-011020-Walls_East_SEP-Access Roads | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-01 |  | 2020-11-16 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2805.72 | 2805.72 | 0 | 0 | 0 | 2805.72 | 0 | 0 | 0 | 0 | 2805.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509057 | N-WW-NI-011020-Wick_STW-Access Platform | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-01 |  | 2020-11-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3595.07 | 3595.07 | 0 | 0 | 0 | 3595.07 | 0 | 0 | 0 | 0 | 3595.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510055 | N-WW-NI-011220-Carrbridge_STW-Trailer Arm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-01 |  | 2021-03-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1962.63 | 0 | 0 | 2100.01 | 0 | 0 | 0 | 0 | 2100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511024 | N-WW-NI-020221-Lerwick_Gremista_SPS-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-02 |  | 2021-03-22 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810.63 | 1810.63 | 39.35 | 0 | 0 | 1849.98 | 0 | 0 | 0 | 0 | 1849.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511569 | N-WW-NI-020321-Fortrose_STW-UV Lamps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-06-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484.11 | 484.11 | 6342.84 | 0 | 0 | 6826.95 | 0 | 0 | 0 | 0 | 6826.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511574 | N-WW-NI-020321-Muir_of_Ord_STW-Heater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1028.58 | 0 | 0 | 1107.08 | 0 | 0 | 0 | 0 | 1107.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511579 | N-WW-NI-020321-Thurso_STW-FST Scrapers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-06-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4125.17 | 4125.17 | 74.83 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506061 | N-WW-NI-020420-Avoch_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-11-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800.48 | 4800.48 | 0 | 0 | 0 | 4800.48 | 0 | 0 | 0 | 0 | 4800.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506067 | N-WW-NI-020420-Dornoch_STW_Tanker_point_grating | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-03 |  | 2020-09-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3426.21 | 3426.21 | 0 | 0 | 0 | 3426.21 | 0 | 0 | 0 | 0 | 3426.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506053 | N-WW-NI-020420-Gairloch_STW-Site_Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.41 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506047 | N-WW-NI-020420-Kiknlochewe_Village_Sep-Access_Rd | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-10-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7050.73 | 7050.73 | 0 | 0 | 0 | 7050.73 | 0 | 0 | 0 | 0 | 7050.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512174 | N-WW-NI-020421-Kilmory_STW_Dewaterer Feed Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1599.99 | 0 | 0 | 1599.99 | 0 | 0 | 0 | 0 | 1599.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506967 | N-WW-NI-020620-Conon_Bridge_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2075.08 | 2075.08 | 0 | 0 | 0 | 2075.08 | 0 | 0 | 0 | 0 | 2075.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506963 | N-WW-NI-020620-Stornoway_Sand_St_SPS-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-16 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599.09 | 3599.09 | 0 | 0 | 0 | 3599.09 | 0 | 0 | 0 | 0 | 3599.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507505 | N-WW-NI-020720-Alness_Invergordon _STC_Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-09-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1526.67 | 1526.67 | 0 | 0 | 0 | 1526.67 | 0 | 0 | 0 | 0 | 1526.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507503 | N-WW-NI-020720-Conon_Bridge_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-07-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3165.69 | 3165.69 | 0 | 0 | 0 | 3165.69 | 0 | 0 | 0 | 0 | 3165.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507504 | N-WW-NI-020720-Ft_Augustus_STW-Actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-08-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1827.66 | 1827.66 | 0 | 0 | 0 | 1827.66 | 0 | 0 | 0 | 0 | 1827.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508543 | N-WW-NI-020920-Campbeltown-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-03 |  | 2020-11-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2089.32 | 2089.32 | 0 | 0 | 0 | 2089.32 | 0 | 0 | 0 | 0 | 2089.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508539 | N-WW-NI-020920-St_Margarets_Hope_SPS-Comms | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-03 |  | 2020-10-14 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3315.85 | 3315.85 | 0 | 0 | 0 | 3315.85 | 0 | 0 | 0 | 0 | 3315.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509075 | N-WW-NI-021020-Aviemore_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-02 |  | 2020-11-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1208.5 | 1208.5 | 0 | 0 | 0 | 1208.5 | 0 | 0 | 0 | 0 | 1208.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509073 | N-WW-NI-021020-Callart_SPS-Guide Rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-02 |  | 2020-10-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1544.14 | 1544.14 | 0 | 0 | 0 | 1544.14 | 0 | 0 | 0 | 0 | 1544.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509087 | N-WW-NI-021020-Dunbeg_Jane_Rd_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-05 |  | 2020-10-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038.7 | 2038.7 | 0 | 0 | 0 | 2038.7 | 0 | 0 | 0 | 0 | 2038.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509091 | N-WW-NI-021020-Ft_Augustus_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23641.26 | 23641.26 | 58.74 | 0 | 0 | 23700 | 0 | 0 | 0 | 0 | 23700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509072 | N-WW-NI-021020-Thurso_STC-Lime Silo | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-02 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190.84 | 190.84 | 1834.16 | 0 | 0 | 2025 | 0 | 0 | 0 | 0 | 2025 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509582 | N-WW-NI-021120-Aviemore_STW-Hydroranger | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-03 |  | 2020-11-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123.5 | 1123.5 | 0 | 0 | 0 | 1123.5 | 0 | 0 | 0 | 0 | 1123.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509578 | N-WW-NI-021120-Boat_of_Garten-Pump Kits | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-03 |  | 2020-11-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1292.29 | 1292.29 | 0 | 0 | 0 | 1292.29 | 0 | 0 | 0 | 0 | 1292.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509579 | N-WW-NI-021120-Hamnavoe_Burra_SEP-H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-03 |  | 2021-03-26 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6391.23 | 6391.23 | 108.76 | 0 | 0 | 6499.99 | 0 | 0 | 0 | 0 | 6499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509571 | N-WW-NI-021120-Kirkwall_HoW_STC-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-03 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274.77 | 274.77 | 3925.22 | 0 | 0 | 4199.99 | 0 | 0 | 0 | 0 | 4199.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509583 | N-WW-NI-021120-Stornoway_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-03 |  | 2021-03-13 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1751.23 | 1751.23 | 98.76 | 0 | 0 | 1849.99 | 0 | 0 | 0 | 0 | 1849.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504108 | N-WW-NI-021219-Carradale_Foreshore_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-02-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 3670.12 | 0 | 3670.12 | 0 | 0 | 0 | 3670.12 | 0 | 0 | 0 | 0 | 3670.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510076 | N-WW-NI-021220-Brora_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-03 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3234.95 | 3234.95 | 165.06 | 0 | 0 | 3400.01 | 0 | 0 | 0 | 0 | 3400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510086 | N-WW-NI-021220-Drimnin_SEP-Steps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2242.98 | 0 | 0 | 2399.99 | 0 | 0 | 0 | 0 | 2399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510103 | N-WW-NI-021220-Fassfern_SEP-Access-Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-02-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4030.72 | 4030.72 | 69.27 | 0 | 0 | 4099.99 | 0 | 0 | 0 | 0 | 4099.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510078 | N-WW-NI-021220-Golspie_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-03 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.92 | 1368.92 | 31.08 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505002 | N-WW-NI-030220-Dingwall_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-05-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 2626.05 | 2815.77 | 0 | 0 | 0 | 2815.77 | 0 | 0 | 0 | 0 | 2815.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504999 | N-WW-NI-030220-Kirkwall_HoW_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-07-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4138.62 | 4138.62 | 0 | 0 | 0 | 4138.62 | 0 | 0 | 0 | 0 | 4138.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511042 | N-WW-NI-030221-Flotta_Burnside_STW-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-03 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000.93 | 1000.93 | 14299.05 | 0 | 0 | 15299.98 | 0 | 0 | 0 | 0 | 15299.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511036 | N-WW-NI-030221-Inchree_STW-Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.45 | 120.45 | 1308.4 | 0 | 0 | 1428.85 | 0 | 0 | 0 | 0 | 1428.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505511 | N-WW-NI-030320-Alness_Invergordon_STW-SIS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-04 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 10176.56 | 0 | 10176.56 | 0 | 0 | 0 | 10176.56 | 0 | 0 | 0 | 0 | 10176.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505515 | N-WW-NI-030320-Barbaravuille_Sutor_SPS-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-04 |  | 2020-09-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 2105 | 2229.3 | 0 | 0 | 0 | 2229.3 | 0 | 0 | 0 | 0 | 2229.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505502 | N-WW-NI-030320-Clachan_STW-Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-04 |  | 2020-05-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 365.06 | 3585.96 | 3951.02 | 0 | 0 | 0 | 3951.02 | 0 | 0 | 0 | 0 | 3951.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505513 | N-WW-NI-030320-Dornoch_STW-SHT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-04 |  | 2020-09-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 435.05 | 6126.06 | 6561.11 | 0 | 0 | 0 | 6561.11 | 0 | 0 | 0 | 0 | 6561.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511596 | N-WW-NI-030321-Kincraig_STW-Guttering | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1285.74 | 0 | 0 | 1383.87 | 0 | 0 | 0 | 0 | 1383.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506080 | N-WW-NI-030420 - Carrbridge WwTW - Scum Removal System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-21 | 2022-06-17 | 2022-09-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 912 | 912 | 59087.89 | 0 | 0 | 59999.89 | 0 | 0 | 0 | 0 | 59999.89 | 90601.29 | [5 empty] | N | WWNI | 100%
506078 | N-WW-NI-030420 - Jura Woodside ST - Refurbishment of Outfall and ST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-01 | 2022-06-06 | 2022-09-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527.32 | 527.32 | 84372.68 | 0 | 0 | 84900 | 0 | 0 | 0 | 0 | 84900 | 90601.29 | [5 empty] | N | WWNI | 100%
506074 | N-WW-NI-030420-Broadford_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-06 |  | 2020-09-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5534.64 | 5534.64 | 0 | 0 | 0 | 5534.64 | 0 | 0 | 0 | 0 | 5534.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507006 | N-WW-NI-030620-Dornoch_STW-Poly Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1253.98 | 1253.98 | 0 | 0 | 0 | 1253.98 | 0 | 0 | 0 | 0 | 1253.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506990 | N-WW-NI-030620-Kincraig_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-09-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5661.08 | 5661.08 | 0 | 0 | 0 | 5661.08 | 0 | 0 | 0 | 0 | 5661.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507004 | N-WW-NI-030620-Meadows_SPS-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 0 | 0 | 0 | 163.55 | 0 | 0 | 0 | 0 | 163.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508555 | N-WW-NI-030920-Ft_Augustus_SPS-Guidrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-03 |  | 2020-10-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056.18 | 2056.18 | 0 | 0 | 0 | 2056.18 | 0 | 0 | 0 | 0 | 2056.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508567 | N-WW-NI-030920-Ft_Augustus_STW-Cover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-04 |  | 2020-10-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617.52 | 617.52 | 0 | 0 | 0 | 617.52 | 0 | 0 | 0 | 0 | 617.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509597 | N-WW-NI-031120-Aviemore_STW-PRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-03 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864.74 | 1864.74 | 135.26 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509588 | N-WW-NI-031120-Campbeltown_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-03 |  | 2020-11-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366.18 | 1366.18 | 0 | 0 | 0 | 1366.18 | 0 | 0 | 0 | 0 | 1366.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509606 | N-WW-NI-031120-Dulnain_Bridge_STW-Scum System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.91 | 529.91 | 7570.08 | 0 | 0 | 8099.99 | 0 | 0 | 0 | 0 | 8099.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504113 | N-WW-NI-031219-Wick_STW-CASS_Jack_Arm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-01-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -101 | 1899 | 0 | 0 | 0 | 1899 | 0 | 0 | 0 | 0 | 1899 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505013 | N-WW-NI-040220-Gairloch_East_Strath_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-07-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2686.85 | 2948.83 | 5635.68 | 0 | 0 | 0 | 5635.68 | 0 | 0 | 0 | 0 | 5635.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505010 | N-WW-NI-040220-Kildary_STW-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3236.25 | 0 | 3236.25 | 0 | 0 | 0 | 3236.25 | 0 | 0 | 0 | 0 | 3236.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505024 | N-WW-NI-040220-Kildary_STW-FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1066.36 | 0 | 1066.36 | 15233.64 | 0 | 0 | 16300 | 0 | 0 | 0 | 0 | 16300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505023 | N-WW-NI-040220-Stornoway_Coastguard_SPS-Deragger | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-03-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 4347.71 | 0 | 4347.71 | 0 | 0 | 0 | 4347.71 | 0 | 0 | 0 | 0 | 4347.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511052 | N-WW-NI-040221-Kilmory_STW-SHT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-04 |  | 2021-03-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.41 | 1296.41 | -96.4 | 0 | 0 | 1200.01 | 0 | 0 | 0 | 0 | 1200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511062 | N-WW-NI-040221-Strathpeffer_STW-FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-04 |  | 2021-03-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2604.78 | 2604.78 | 95.2 | 0 | 0 | 2699.98 | 0 | 0 | 0 | 0 | 2699.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505527 | N-WW-NI-040320-Croy_STW-Geared_Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 255.14 | 0 | 255.14 | 3644.86 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505523 | N-WW-NI-040320-St Margarets_Hope _STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-05-06 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2638 | 2638 | 0 | 0 | 0 | 2638 | 0 | 0 | 0 | 0 | 2638 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505539 | N-WW-NI-040320-Stornoway_STW-NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-05 |  | 2020-03-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1457.93 | 0 | 1457.93 | 0 | 0 | 0 | 1457.93 | 0 | 0 | 0 | 0 | 1457.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511617 | N-WW-NI-040321-Bu_Point_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-04 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 5442.84 | 0 | 0 | 5527.89 | 0 | 0 | 0 | 0 | 5527.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511607 | N-WW-NI-040321-Campbeltown_STW-SHT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862.64 | 862.64 | 1200 | 0 | 0 | 2062.64 | 0 | 0 | 0 | 0 | 2062.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511606 | N-WW-NI-040321-Evanton_STW-Huber Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3809.21 | 3809.21 | 90.79 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511618 | N-WW-NI-040321-Kilmory_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898.56 | 1898.56 | -248.56 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 1650 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511622 | N-WW-NI-040321-Kirkwall_HoW_STC-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-04 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.89 | 215.89 | 2828.58 | 0 | 0 | 3044.47 | 0 | 0 | 0 | 0 | 3044.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511613 | N-WW-NI-040321-Kirkwall_HoW_STC-SHT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-04 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 1714.26 | 0 | 0 | 1845.1 | 0 | 0 | 0 | 0 | 1845.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511620 | N-WW-NI-040321-Oban_STW-MLSS Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395.34 | 395.34 | 3857.16 | 0 | 0 | 4252.5 | 0 | 0 | 0 | 0 | 4252.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506448 | N-WW-NI-040520 - Stornoway Sand Street SPS CSO - Replace Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-21 | 2022-10-10 | 2023-01-16 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 88000 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 90000 | 90601.29 | [5 empty] | N | WWNI | 100%
506465 | N-WW-NI-040520-Campbeltown_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-06 |  | 2020-06-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300.09 | 2300.09 | 0 | 0 | 0 | 2300.09 | 0 | 0 | 0 | 0 | 2300.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506454 | N-WW-NI-040520-Kilmore_STW-Monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-04 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225.8 | 225.8 | 2174.2 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506452 | N-WW-NI-040520-Taynuilt_STW-Scraper_Blades | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-04 |  | 2020-05-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052.9 | 2052.9 | 0 | 0 | 0 | 2052.9 | 0 | 0 | 0 | 0 | 2052.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507035 | N-WW-NI-040620-Alness_Teaninich_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-05 |  | 2020-04-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19475.96 | 19475.96 | 0 | 0 | 0 | 19475.96 | 0 | 0 | 0 | 0 | 19475.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507032 | N-WW-NI-040620-HoW_Kirkwall_STC-SHT Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-07-06 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5167.4 | 5167.4 | 0 | 0 | 0 | 5167.4 | 0 | 0 | 0 | 0 | 5167.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507031 | N-WW-NI-040620-W_Mainland_Mart_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-10 |  | 2020-07-29 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369.99 | 1369.99 | 0 | 0 | 0 | 1369.99 | 0 | 0 | 0 | 0 | 1369.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508039 | N-WW-NI-040820-Alness_Invergordon_STW-Odour | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-08-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1154.44 | 1154.44 | 0 | 0 | 0 | 1154.44 | 0 | 0 | 0 | 0 | 1154.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508043 | N-WW-NI-040820-Carrbridge_STW-Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-06 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739.25 | 739.25 | 10560.75 | 0 | 0 | 11300 | 0 | 0 | 0 | 0 | 11300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508040 | N-WW-NI-040820-Stornoway_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-06 |  | 2020-09-11 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2965.05 | 2965.05 | 0 | 0 | 0 | 2965.05 | 0 | 0 | 0 | 0 | 2965.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508573 | N-WW-NI-040920-Dornoch_STW-Belt Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-04 |  | 2020-11-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2761.18 | 2761.18 | 0 | 0 | 0 | 2761.18 | 0 | 0 | 0 | 0 | 2761.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508575 | N-WW-NI-040920-Drumnadrochit_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-04 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2242.99 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508580 | N-WW-NI-040920-Kirkwall_HOW_STW-PST Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-04 |  | 2021-03-26 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1453.57 | 1453.57 | 0 | 0 | 0 | 1453.57 | 0 | 0 | 0 | 0 | 1453.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508577 | N-WW-NI-040920-Thurso_STW-DO Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-04 |  | 2020-09-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4842.07 | 4842.07 | 0 | 0 | 0 | 4842.07 | 0 | 0 | 0 | 0 | 4842.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509629 | N-WW-NI-041120-Inverness_SPS-APNRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-05 |  | 2020-08-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3480.59 | 3480.59 | 0 | 0 | 0 | 3480.59 | 0 | 0 | 0 | 0 | 3480.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509618 | N-WW-NI-041120-Kishorn_STW-Marker Post | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 353.27 | 5046.72 | 0 | 0 | 5399.99 | 0 | 0 | 0 | 0 | 5399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509621 | N-WW-NI-041120-Oban_Ganavan_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-05 |  | 2020-02-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2885.75 | 2885.75 | 0 | 0 | 0 | 2885.75 | 0 | 0 | 0 | 0 | 2885.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509611 | N-WW-NI-041120-Tore_STW-RBC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-05 |  | 2020-11-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2176.08 | 2176.08 | 0 | 0 | 0 | 2176.08 | 0 | 0 | 0 | 0 | 2176.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510166 | N-WW-NI-041220-Avoch_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-07 |  | 2021-03-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3434.62 | 3434.62 | 365.37 | 0 | 0 | 3799.99 | 0 | 0 | 0 | 0 | 3799.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510154 | N-WW-NI-041220-Campbeltown_STW-Monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-07 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1335.78 | 1335.78 | -35.79 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510149 | N-WW-NI-041220-Poolewe_SEP-Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-07 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2225.61 | 2225.61 | 74.39 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510152 | N-WW-NI-041220-Stornoway_STW-Lightning | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-07 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1214.94 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510151 | N-WW-NI-041220-Ullapool_STW-Keyclamp | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-07 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1401.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504526 | N-WW-NI-050120-Kirkwall_Glaitness_SPS-Scope | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-06-16 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3656.82 | 3656.82 | -6.82 | 0 | 0 | 3650 | 0 | 0 | 0 | 0 | 3650 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510529 | N-WW-NI-050121-Campbeltown_STW_H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-06 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7846.75 | 7846.75 | -546.75 | 0 | 0 | 7300 | 0 | 0 | 0 | 0 | 7300 | 90601.29 | [5 empty] | N | WWNI | 100%
510530 | N-WW-NI-050121-Dornoch_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-06 |  | 2021-02-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2532.93 | 2532.93 | 67.08 | 0 | 0 | 2600.01 | 0 | 0 | 0 | 0 | 2600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510533 | N-WW-NI-050121-Gairloch_Golf_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-06 |  | 2021-03-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1192.05 | 1192.05 | 107.96 | 0 | 0 | 1300.01 | 0 | 0 | 0 | 0 | 1300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510523 | N-WW-NI-050121-Oban_STW-Fire Sensors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-06 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142.77 | 142.77 | 1157.24 | 0 | 0 | 1300.01 | 0 | 0 | 0 | 0 | 1300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505044 | N-WW-NI-050220-Kirkwall_HoW_STC-Sludge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-02-19 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 3418 | 0 | 3418 | 0 | 0 | 0 | 3418 | 0 | 0 | 0 | 0 | 3418 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505041 | N-WW-NI-050220-Ullapool_STW-InletScreen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5756.32 | 0 | 5756.32 | 0 | 0 | 0 | 5756.32 | 0 | 0 | 0 | 0 | 5756.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505564 | N-WW-NI-050320-Kingussie_STW-RAS_Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 268.22 | 0 | 268.22 | 3831.78 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505565 | N-WW-NI-050320-Newtonmore_DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-06 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 3053.99 | 3250.25 | -250.25 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505555 | N-WW-NI-050320-Thurso_STC-Sludge_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-05 |  | 2020-09-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 1121.57 | 1206.62 | 0 | 0 | 0 | 1206.62 | 0 | 0 | 0 | 0 | 1206.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511626 | N-WW-NI-050321-Bu_Point_STW-Floor Inserts | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-05 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.94 | 107.94 | 1414.26 | 0 | 0 | 1522.2 | 0 | 0 | 0 | 0 | 1522.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511628 | N-WW-NI-050321-Embo_Links_SPS-Site Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 170.09 | 2228.58 | 0 | 0 | 2398.67 | 0 | 0 | 0 | 0 | 2398.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511631 | N-WW-NI-050321-Kishorn_STW-Humus Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129.68 | 129.68 | 1200 | 0 | 0 | 1329.68 | 0 | 0 | 0 | 0 | 1329.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511638 | N-WW-NI-050321-Mallaig_STW-Aerotor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286.69 | 286.69 | 3000 | 0 | 0 | 3286.69 | 0 | 0 | 0 | 0 | 3286.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511629 | N-WW-NI-050321-Oban_Corran_Park_SPS-Sensors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4839.5 | 4839.5 | 160.5 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511636 | N-WW-NI-050321-Strontian_Main_SEP-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-05 |  | 2021-06-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149.89 | 149.89 | 1585.74 | 0 | 0 | 1735.63 | 0 | 0 | 0 | 0 | 1735.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506479 | N-WW-NI-050520-Campbeltown_STW_PLC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-06 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233.31 | 233.31 | 3166.69 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506480 | N-WW-NI-050520-Kiltarlity_STW-Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-06 |  | 2020-06-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255.33 | 2255.33 | 0 | 0 | 0 | 2255.33 | 0 | 0 | 0 | 0 | 2255.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506472 | N-WW-NI-050520-Oban_STW_Sludge_Skips | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-06 |  | 2020-09-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3005.96 | 3005.96 | 0 | 0 | 0 | 3005.96 | 0 | 0 | 0 | 0 | 3005.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507049 | N-WW-NI-050620-Invergordon_Admiralty_Pier_SPS-Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-05 |  | 2020-08-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9893.34 | 9893.34 | 0 | 0 | 0 | 9893.34 | 0 | 0 | 0 | 0 | 9893.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507066 | N-WW-NI-050620-Invergordon_Foul_SPS-Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-08 |  | 2020-09-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9769.33 | 9769.33 | 0 | 0 | 0 | 9769.33 | 0 | 0 | 0 | 0 | 9769.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507064 | N-WW-NI-050620-Tain_STW-FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-05 |  | 2020-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10591.1 | 10591.1 | 0 | 0 | 0 | 10591.1 | 0 | 0 | 0 | 0 | 10591.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508078 | N-WW-NI-050820-Wick_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-06 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1401.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509106 | N-WW-NI-051020-Harbour_Rd_SPS-Building | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509658 | N-WW-NI-051120-Campbeltown_Kinloch_Park_SPS-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-06 |  | 2021-03-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7411.88 | 7411.88 | -11.9 | 0 | 0 | 7399.98 | 0 | 0 | 0 | 0 | 7399.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509645 | N-WW-NI-051120-Clachan_Balvicar_STW-Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220.7 | 220.7 | 1279.28 | 0 | 0 | 1499.98 | 0 | 0 | 0 | 0 | 1499.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509639 | N-WW-NI-051120-Kincraig_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-03-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17517.61 | 17517.61 | -17.6 | 0 | 0 | 17500.01 | 0 | 0 | 0 | 0 | 17500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509642 | N-WW-NI-051120-Nethy_Bridge_STW-Building | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-02-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1351.98 | 1351.98 | 48.02 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509643 | N-WW-NI-051120-Newtonmore_STW-Building | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-05 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1351.98 | 1351.98 | 48.02 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504530 | N-WW-NI-060120-Clachan_Seil_Brookside_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-06 |  | 2020-02-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1375.98 | 0 | 1375.98 | 0 | 0 | 0 | 1375.98 | 0 | 0 | 0 | 0 | 1375.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504532 | N-WW-NI-060120-Dulnain_Bridge-Brushes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-06 |  | 2020-04-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | -185.95 | 1214.05 | 0 | 0 | 0 | 1214.05 | 0 | 0 | 0 | 0 | 1214.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504531 | N-WW-NI-060120-Stornoway STW-Scaffolding | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-06 |  | 2020-02-07 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 5350 | -386.34 | 4963.66 | 0 | 0 | 0 | 4963.66 | 0 | 0 | 0 | 0 | 4963.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510556 | N-WW-NI-060121-Stornoway_STW-Blowers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-08 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 30000 | 0 | 0 | 32100 | 0 | 0 | 0 | 0 | 32100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505065 | N-WW-NI-060220-Lairg_War_Memorial_SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-04-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2150.12 | 0 | 2150.12 | 0 | 0 | 0 | 2150.12 | 0 | 0 | 0 | 0 | 2150.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505580 | N-WW-NI-060320-Campbeltown_Kinloch_Park_SPS-NRVs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-10 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2445.28 | 0 | 2445.28 | 154.72 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505576 | N-WW-NI-060320-Peninver_Outfall_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-06 |  | 2020-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2783.34 | 0 | 2783.34 | 0 | 0 | 0 | 2783.34 | 0 | 0 | 0 | 0 | 2783.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506112 | N-WW-NI-060420-Campbeltown_Kinloch_Park_SPS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-07 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12183.37 | 12183.37 | 0 | 0 | 0 | 12183.37 | 0 | 0 | 0 | 0 | 12183.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506090 | N-WW-NI-060420-Roybridge_SPS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-06 |  | 2020-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3007.53 | 3007.53 | 0 | 0 | 0 | 3007.53 | 0 | 0 | 0 | 0 | 3007.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506091 | N-WW-NI-060420-Stornoway_STW_KSB_Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-06 |  | 2020-06-11 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4705.03 | 4705.03 | 0 | 0 | 0 | 4705.03 | 0 | 0 | 0 | 0 | 4705.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512236 | N-WW-NI-060421-Ft_Augustus_STW-Kiosk Roof | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6699.98 | 0 | 0 | 6699.98 | 0 | 0 | 0 | 0 | 6699.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512192 | N-WW-NI-060421-Mallaig_STW_FST Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1599.99 | 0 | 0 | 1599.99 | 0 | 0 | 0 | 0 | 1599.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512219 | N-WW-NI-060421-Nairn_STW-Augers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54999.98 | 0 | 0 | 54999.98 | 0 | 0 | 0 | 0 | 54999.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506525 | N-WW-NI-060520_Newtonmore_STW_RASSAS_Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-07 |  | 2020-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3976.15 | 3976.15 | 0 | 0 | 0 | 3976.15 | 0 | 0 | 0 | 0 | 3976.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506499 | N-WW-NI-060520-Cawdor_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-06 |  | 2020-06-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4714.28 | 4714.28 | 0 | 0 | 0 | 4714.28 | 0 | 0 | 0 | 0 | 4714.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506526 | N-WW-NI-060520-Dornioch_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-07 |  | 2020-05-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100.07 | 4100.07 | 0 | 0 | 0 | 4100.07 | 0 | 0 | 0 | 0 | 4100.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506523 | N-WW-NI-060520-Fort_Augustus_STW_RAS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-07 |  | 2020-07-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3603.88 | 3603.88 | 0 | 0 | 0 | 3603.88 | 0 | 0 | 0 | 0 | 3603.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506524 | N-WW-NI-060520-Stromness-Bu-Point_STW-RASSAS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-07 |  | 2020-07-23 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7270.94 | 7270.94 | 729.06 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508105 | N-WW-NI-060820 - Halkirk WwTW - Refurbish SHT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-12-08 | 2022-05-13 | 2022-12-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3659 | 3659 | 46340.47 | 0 | 0 | 49999.47 | 0 | 0 | 0 | 0 | 49999.47 | 90601.29 | [5 empty] | N | WWNI | 100%
509131 | N-WW-NI-061020--Brora_STW-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-06 |  | 2020-11-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8626.61 | 8626.61 | 0 | 0 | 0 | 8626.61 | 0 | 0 | 0 | 0 | 8626.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509129 | N-WW-NI-061020--Harbour_St_Nairn_SPS-Building | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-06 |  | 2020-10-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7876.78 | 7876.78 | 0 | 0 | 0 | 7876.78 | 0 | 0 | 0 | 0 | 7876.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509124 | N-WW-NI-061020-Thurso_STW-Skips | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-06 |  | 2020-11-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4092.92 | 4092.92 | 0 | 0 | 0 | 4092.92 | 0 | 0 | 0 | 0 | 4092.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509667 | N-WW-NI-061120-Aultbea_Cemetry_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-06 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2617.68 | 2617.68 | 0 | 0 | 0 | 2617.68 | 0 | 0 | 0 | 0 | 2617.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509666 | N-WW-NI-061120-Golspie_STW-FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-06 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8338.31 | 8338.31 | 61.68 | 0 | 0 | 8399.99 | 0 | 0 | 0 | 0 | 8399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509672 | N-WW-NI-061120-Oban_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-09 |  | 2020-11-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3494.9 | 3494.9 | 0 | 0 | 0 | 3494.9 | 0 | 0 | 0 | 0 | 3494.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504232 | N-WW-NI-061219- Ballachulish_West_SPS-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2140 | -310 | 1830 | 310 | 0 | 0 | 2140 | 0 | 0 | 0 | 0 | 2140 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504237 | N-WW-NI-061219-Campbeltown_STW-Storm_Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-09 |  | 2020-03-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2400.21 | 0 | 2400.21 | 0 | 0 | 0 | 2400.21 | 0 | 0 | 0 | 0 | 2400.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504239 | N-WW-NI-061219-Ferness_STW-Odour | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-09 |  | 2020-01-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1343.47 | 0 | 1343.47 | 0 | 0 | 0 | 1343.47 | 0 | 0 | 0 | 0 | 1343.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504236 | N-WW-NI-061219-Furnace_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-09 |  | 2019-12-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1326.61 | 0 | 1326.61 | 0 | 0 | 0 | 1326.61 | 0 | 0 | 0 | 0 | 1326.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504235 | N-WW-NI-061219-Wick_Scalesburn_SPS-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-09 |  | 2020-11-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4280 | -1971.92 | 2308.08 | 0 | 0 | 0 | 2308.08 | 0 | 0 | 0 | 0 | 2308.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504228 | N-WW-NI-061219-Wick_STW-Grit_Plant | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-09 |  | 2020-03-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | -1008.07 | 2891.93 | 0 | 0 | 0 | 2891.93 | 0 | 0 | 0 | 0 | 2891.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504535 | N-WW-NI-070120-Portmahomack_Main_St_SPS-Guiderails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-09 |  | 2020-01-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1582.46 | 0 | 1582.46 | 0 | 0 | 0 | 1582.46 | 0 | 0 | 0 | 0 | 1582.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512237 | N-WW-NI-070421-Drumnadrochit_STW-Flow Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100.02 | 0 | 0 | 3100.02 | 0 | 0 | 0 | 0 | 3100.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512262 | N-WW-NI-070421-Kirkwall_HoW_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5099.99 | 0 | 0 | 5099.99 | 0 | 0 | 0 | 0 | 5099.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506550 | N-WW-NI-070520 - Northton SPS - Site Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-21 | 2022-08-22 | 2022-11-28 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 2551 | 52449.16 | 0 | 0 | 55000.16 | 0 | 0 | 0 | 0 | 55000.16 | 90601.29 | [5 empty] | N | WWNI | 100%
506533 | N-WW-NI-070520-Oban_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-07 |  | 2020-07-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2150.99 | 2150.99 | 0 | 0 | 0 | 2150.99 | 0 | 0 | 0 | 0 | 2150.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508122 | N-WW-NI-070820-Thurso_STC-Doors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-11 |  | 2020-10-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2284.21 | 2284.21 | 0 | 0 | 0 | 2284.21 | 0 | 0 | 0 | 0 | 2284.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508123 | N-WW-NI-070820-Wick_STW-Grit Classifier | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-11 |  | 2020-09-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086.22 | 2086.22 | 0 | 0 | 0 | 2086.22 | 0 | 0 | 0 | 0 | 2086.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508605 | N-WW-NI-070920-Dornoch_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-10-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7380.01 | 7380.01 | 0 | 0 | 0 | 7380.01 | 0 | 0 | 0 | 0 | 7380.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508604 | N-WW-NI-070920-Finstown_STW-Outfall Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2523.36 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508611 | N-WW-NI-070920-Newtonmore_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-11-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2915.03 | 2915.03 | 0 | 0 | 0 | 2915.03 | 0 | 0 | 0 | 0 | 2915.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508616 | N-WW-NI-070920-Oban_STW-Door Locks | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153.18 | 1153.18 | 0 | 0 | 0 | 1153.18 | 0 | 0 | 0 | 0 | 1153.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508614 | N-WW-NI-070920-Oban_STW-FST2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.03 | 214.03 | 2285.97 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510183 | N-WW-NI-071220-Kirkwall_HoW_STC-SHT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-07 |  | 2021-02-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550.45 | 2550.45 | 49.56 | 0 | 0 | 2600.01 | 0 | 0 | 0 | 0 | 2600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510187 | N-WW-NI-071220-Stornoway_STW-Sensor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-07 |  | 2021-02-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3738.6 | 3738.6 | 61.38 | 0 | 0 | 3799.98 | 0 | 0 | 0 | 0 | 3799.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510188 | N-WW-NI-071220-Ullapool_STW-Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-08 |  | 2021-03-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3849 | 3849 | -49.02 | 0 | 0 | 3799.98 | 0 | 0 | 0 | 0 | 3799.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504565 | N-WW-NI-080120-Bu_Point_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-01-18 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1585.33 | 0 | 1585.33 | 0 | 0 | 0 | 1585.33 | 0 | 0 | 0 | 0 | 1585.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504595 | N-WW-NI-080120-Conon_Bridge_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-04-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4280 | -129.99 | 4150.01 | 0 | 0 | 0 | 4150.01 | 0 | 0 | 0 | 0 | 4150.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504567 | N-WW-NI-080120-Grantown_STW-Sensors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-09 |  | 2020-01-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1117.3 | 0 | 1117.3 | 0 | 0 | 0 | 1117.3 | 0 | 0 | 0 | 0 | 1117.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504562 | N-WW-NI-080120-Jemimaville_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-09 |  | 2020-02-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1746.2 | 0 | 1746.2 | 0 | 0 | 0 | 1746.2 | 0 | 0 | 0 | 0 | 1746.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504572 | N-WW-NI-080120-Lerwick_Gremista_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-07 |  | 2020-02-13 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 2819.38 | -2636.2 | 183.18 | 2616.82 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510585 | N-WW-NI-080121-Tobermory_Glengorn_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-08 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212.62 | 212.62 | 3037.36 | 0 | 0 | 3249.98 | 0 | 0 | 0 | 0 | 3249.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511098 | N-WW-NI-080221-Balallan_West_STW-Tipping Tray | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 425.23 | 6500 | 0 | 0 | 6925.23 | 0 | 0 | 0 | 0 | 6925.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511092 | N-WW-NI-080221-Campbeltown_STW-Flow Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-08 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129.68 | 129.68 | 1042.3 | 0 | 0 | 1171.98 | 0 | 0 | 0 | 0 | 1171.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511083 | N-WW-NI-080221-Dingwall_STW_Aeration Ditch | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2021-04-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7347.16 | 7347.16 | 643.5 | 0 | 0 | 7990.66 | 0 | 0 | 0 | 0 | 7990.66 | 90601.29 | [5 empty] | N | WWNI | 100%
511089 | N-WW-NI-080221-Stornoway_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2021-03-29 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 984.68 | 984.68 | 1587.3 | 0 | 0 | 2571.98 | 0 | 0 | 0 | 0 | 2571.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511087 | N-WW-NI-080221-Ullapool_STW_Sludge Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.56 | 320.56 | 4900 | 0 | 0 | 5220.56 | 0 | 0 | 0 | 0 | 5220.56 | 90601.29 | [5 empty] | N | WWNI | 100%
511648 | N-WW-NI-080321-Lerwick_Rovahead_STW-Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-08 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4022.83 | 4022.83 | 77.17 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506139 | N-WW-NI-080420 - Conon Bridge WwTW - Refurbish SHTs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-14 | 2022-07-22 | 2022-10-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683 | 1683 | 123317.02 | 0 | 0 | 125000.02 | 0 | 0 | 0 | 0 | 125000.02 | 90601.29 | [5 empty] | N | WWNI | 100%
506143 | N-WW-NI-080420 - Dingwall WwTW - Refurbish FST 1 & 2 and PST 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-06-17 | 2020-10-05 | 2021-02-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115181.15 | 115181.15 | 0 | 0 | 0 | 115181.15 | 0 | 0 | 0 | 0 | 115181.15 | 90601.29 | [5 empty] | N | WWNI | 100%
506148 | N-WW-NI-080420 - Janetstown ST - Replace Reed Bed | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-09-01 | 2022-12-30 | 2023-04-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 107000 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 110000 | 90601.29 | [5 empty] | N | WWNI | 100%
506140 | N-WW-NI-080420 - Lochcarron Slumbay SPS - Refurbish SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-06-08 | 2020-10-19 | 2021-02-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59633.64 | 59633.64 | 0 | 0 | 0 | 59633.64 | 0 | 0 | 0 | 0 | 59633.64 | 90601.29 | [5 empty] | N | WWNI | 100%
506141 | N-WW-NI-080420_Strathpeffer_STW_Telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-11-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4281.31 | 4281.31 | 0 | 0 | 0 | 4281.31 | 0 | 0 | 0 | 0 | 4281.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506133 | N-WW-NI-080420-Kingussie SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-05-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.15 | 1778.15 | 0 | 0 | 0 | 1778.15 | 0 | 0 | 0 | 0 | 1778.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507088 | N-WW-NI-080620-Croy_STW-Technocover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10700 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507082 | N-WW-NI-080620-Fortrose_STW_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-08 |  | 2020-10-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5051.42 | 5051.42 | 0 | 0 | 0 | 5051.42 | 0 | 0 | 0 | 0 | 5051.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507083 | N-WW-NI-080620-Nethy_Bridge_STW-Filter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-08 |  | 2020-07-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3412.82 | 3412.82 | 0 | 0 | 0 | 3412.82 | 0 | 0 | 0 | 0 | 3412.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507081 | N-WW-NI-080620-Newtonmore_STW-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-08 |  | 2020-11-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9809.18 | 9809.18 | 0 | 0 | 0 | 9809.18 | 0 | 0 | 0 | 0 | 9809.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507086 | N-WW-NI-080620-Oban_Corran_Park_SPS-Macerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-08 |  | 2020-08-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12508.19 | 12508.19 | 0 | 0 | 0 | 12508.19 | 0 | 0 | 0 | 0 | 12508.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507591 | N-WW-NI-080720-Alness_Invergordon_STC-Centrifuge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-10 |  | 2020-10-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10688.97 | 10688.97 | 0 | 0 | 0 | 10688.97 | 0 | 0 | 0 | 0 | 10688.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507580 | N-WW-NI-080720-Dunvegan_Hotel_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-09-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3266.9 | 3266.9 | 0 | 0 | 0 | 3266.9 | 0 | 0 | 0 | 0 | 3266.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507592 | N-WW-NI-080720-Spean_Bridge_STW-Pump Connections | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-10 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4265.19 | 4265.19 | 34.81 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507582 | N-WW-NI-080720-Stornoway_STW-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-10-15 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5768.76 | 5768.76 | 0 | 0 | 0 | 5768.76 | 0 | 0 | 0 | 0 | 5768.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508646 | N-WW-NI-080920-Ullapool_STW-Centrifuge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-09 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6075.72 | 6075.72 | 0 | 0 | 0 | 6075.72 | 0 | 0 | 0 | 0 | 6075.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510203 | N-WW-NI-081220-Ft_Augustus_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-08 |  | 2021-03-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5428.76 | 5428.76 | 271.23 | 0 | 0 | 5699.99 | 0 | 0 | 0 | 0 | 5699.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511129 | N-WW-NI-090221-Ardersier_Jetty_SPS-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-09 |  | 2021-05-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1391.52 | 1391.52 | 8.48 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511130 | N-WW-NI-090221-Aviemore_STW-Access Platform | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-09 |  | 2021-05-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1371.5 | 0 | 0 | 1450 | 0 | 0 | 0 | 0 | 1450 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511133 | N-WW-NI-090221-Helmsdale_Shore_St_SPS-WW Cover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-09 |  | 2021-05-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399.07 | 399.07 | 5700.95 | 0 | 0 | 6100.02 | 0 | 0 | 0 | 0 | 6100.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511136 | N-WW-NI-090221-Kiltarlity_STW-Guiderails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-09 |  | 2021-05-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440.72 | 1440.72 | 59.28 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511128 | N-WW-NI-090221-Kingussie_STW-Flow Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-09 |  | 2021-03-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140.65 | 140.65 | 2009.35 | 0 | 0 | 2150 | 0 | 0 | 0 | 0 | 2150 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511132 | N-WW-NI-090221-Nairn_STW- Access Platform | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-09 |  | 2021-05-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1371.5 | 0 | 0 | 1450 | 0 | 0 | 0 | 0 | 1450 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511693 | N-WW-NI-090321-Bonar_Bridge_Ardgay_STW-Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372.9 | 372.9 | 4885.74 | 0 | 0 | 5258.64 | 0 | 0 | 0 | 0 | 5258.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511697 | N-WW-NI-090321--Dornoch_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 2400 | 0 | 0 | 2583.18 | 0 | 0 | 0 | 0 | 2583.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511696 | N-WW-NI-090321--Golspie_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3257.16 | 0 | 0 | 3505.76 | 0 | 0 | 0 | 0 | 3505.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511698 | N-WW-NI-090321-Port_Charlotte_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1200 | 0 | 0 | 1291.59 | 0 | 0 | 0 | 0 | 1291.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511703 | N-WW-NI-090321-Salen_Sep-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1114.26 | 0 | 0 | 1199.31 | 0 | 0 | 0 | 0 | 1199.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506176 | N-WW-NI-090420-Portree_Bayfield_Hospital_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-10 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 2056.07 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506182 | N-WW-NI-090420-Shetland_Walls_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-07-15 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11103.56 | 11103.56 | 0 | 0 | 0 | 11103.56 | 0 | 0 | 0 | 0 | 11103.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506158 | N-WW-NI-090420-Stornoway_STW_Inlet_Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-04-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2184.05 | 2184.05 | 0 | 0 | 0 | 2184.05 | 0 | 0 | 0 | 0 | 2184.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506160 | N-WW-NI-090420-Stornoway_STW_Sludge_Press_Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-07-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1964.13 | 1964.13 | 0 | 0 | 0 | 1964.13 | 0 | 0 | 0 | 0 | 1964.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507111 | N-WW-NI-090620 - Lochcarron WwTW - Odour Plant | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-06-15 | 2020-08-03 | 2020-10-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46363.86 | 46363.86 | 0 | 0 | 0 | 46363.86 | 0 | 0 | 0 | 0 | 46363.86 | 90601.29 | [5 empty] | N | WWNI | 100%
507093 | N-WW-NI-090620-Gairloch _STW-PWasher | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-10 |  | 2020-06-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2712.67 | 2712.67 | 0 | 0 | 0 | 2712.67 | 0 | 0 | 0 | 0 | 2712.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507092 | N-WW-NI-090620-Kirkhill_STW-MLSS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2772.1 | 2772.1 | 127.9 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508683 | N-WW-NI-090920-Alness&Invergordon_STW-Trap | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-09 |  | 2020-09-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3196.52 | 3196.52 | 0 | 0 | 0 | 3196.52 | 0 | 0 | 0 | 0 | 3196.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508662 | N-WW-NI-090920-Balintore_SPS-Guiderails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-09 |  | 2020-10-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1361.72 | 1361.72 | 0 | 0 | 0 | 1361.72 | 0 | 0 | 0 | 0 | 1361.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508664 | N-WW-NI-090920-Kishorn_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-09 |  | 2020-09-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053.28 | 2053.28 | 0 | 0 | 0 | 2053.28 | 0 | 0 | 0 | 0 | 2053.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509170 | N-WW-NI-091020-Balintore_Hilton_King_St_SPS-Telem | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-09 |  | 2021-03-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6327.88 | 6327.88 | -77.88 | 0 | 0 | 6250 | 0 | 0 | 0 | 0 | 6250 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509172 | N-WW-NI-091020-Balintore_Lady_St_SPS-Telem | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-09 |  | 2021-03-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6147.88 | 6147.88 | 102.12 | 0 | 0 | 6250 | 0 | 0 | 0 | 0 | 6250 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509185 | N-WW-NI-091020-Conon_Bridge_STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13205.8 | 13205.8 | 0 | 0 | 0 | 13205.8 | 0 | 0 | 0 | 0 | 13205.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509169 | N-WW-NI-091020--Kirkhill_STW-FST Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7315.59 | 7315.59 | 0 | 0 | 0 | 7315.59 | 0 | 0 | 0 | 0 | 7315.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509192 | N-WW-NI-091020-Kirkwall_Ayre_Rd-SPS-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-12 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509700 | N-WW-NI-091120-Dornoch_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-09 |  | 2021-03-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16036.28 | 16036.28 | 63.72 | 0 | 0 | 16100 | 0 | 0 | 0 | 0 | 16100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509696 | N-WW-NI-091120-Stornoway_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-09 |  | 2021-02-14 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382.61 | 2382.61 | 217.38 | 0 | 0 | 2599.99 | 0 | 0 | 0 | 0 | 2599.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509698 | N-WW-NI-091120-Ullapool_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-09 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4544.68 | 4544.68 | 455.32 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504249 | N-WW-NI-091219-Benderloch_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-12 |  | 2020-02-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 4144.26 | 0 | 4144.26 | 0 | 0 | 0 | 4144.26 | 0 | 0 | 0 | 0 | 4144.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504251 | N-WW-NI-091219-Watten_STW-Site_Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-09 |  | 2020-01-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3135.98 | 0 | 3135.98 | 0 | 0 | 0 | 3135.98 | 0 | 0 | 0 | 0 | 3135.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510215 | N-WW-NI-091220-Croy_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-10 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1330.18 | 1330.18 | 69.82 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510209 | N-WW-NI-091220-Distillery_Brae_SPS-NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-10 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2336.43 | 0 | 0 | 2499.98 | 0 | 0 | 0 | 0 | 2499.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510214 | N-WW-NI-091220-Stornoway_STW-FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-10 |  | 2021-02-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1844.8 | 1844.8 | 355.2 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510211 | N-WW-NI-091220-Tarbert_STW-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-10 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1613.93 | 1613.93 | -213.93 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504610 | N-WW-NI-100120-Alness_Invergordon_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-02-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2445.1 | 0 | 2445.1 | 0 | 0 | 0 | 2445.1 | 0 | 0 | 0 | 0 | 2445.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504612 | N-WW-NI-100120-Cawdor_STW-Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-03-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2150 | -895.35 | 1254.65 | 0 | 0 | 0 | 1254.65 | 0 | 0 | 0 | 0 | 1254.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504609 | N-WW-NI-100120-Inveraray_Barn_Brae_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-02-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 5522.86 | 0 | 5522.86 | 0 | 0 | 0 | 5522.86 | 0 | 0 | 0 | 0 | 5522.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504613 | N-WW-NI-100120-Inverness_Culduthel_Av_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-02-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1497.6 | 0 | 1497.6 | 0 | 0 | 0 | 1497.6 | 0 | 0 | 0 | 0 | 1497.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504602 | N-WW-NI-100120-Kyleakin_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-16 |  | 2020-10-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 8600 | -271.44 | 8328.56 | 271.44 | 0 | 0 | 8600 | 0 | 0 | 0 | 0 | 8600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504597 | N-WW-NI-100120-Lerwick_Rovahead_STC-Belt_Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-07 |  | 2020-01-30 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1249.49 | 0 | 1249.49 | 0 | 0 | 0 | 1249.49 | 0 | 0 | 0 | 0 | 1249.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504601 | N-WW-NI-100120-Salen_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-16 |  | 2020-02-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1367.55 | 0 | 1367.55 | 0 | 0 | 0 | 1367.55 | 0 | 0 | 0 | 0 | 1367.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505129 | N-WW-NI-100220-Alness_Teaninich_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-02-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1613.4 | 0 | 1613.4 | 0 | 0 | 0 | 1613.4 | 0 | 0 | 0 | 0 | 1613.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505121 | N-WW-NI-100220-Campbeltown_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-03-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2143.94 | 0 | 2143.94 | 0 | 0 | 0 | 2143.94 | 0 | 0 | 0 | 0 | 2143.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505098 | N-WW-NI-100220-Piperhill_SPS-Impellors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-03-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1749.31 | 0 | 1749.31 | 0 | 0 | 0 | 1749.31 | 0 | 0 | 0 | 0 | 1749.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511144 | N-WW-NI-100221-Dingwall_STW-Grit Plant | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-10 |  | 2021-03-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3159.42 | 3159.42 | 90.6 | 0 | 0 | 3250.02 | 0 | 0 | 0 | 0 | 3250.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511143 | N-WW-NI-100221-Dingwall_STW-Shaft Seals | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-10 |  | 2021-04-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4371.05 | 4371.05 | 228.95 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 4600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511154 | N-WW-NI-100221-Dornoch_STW-Logger | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-10 |  | 2021-05-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1046.18 | 1046.18 | 1028.05 | 0 | 0 | 2074.23 | 0 | 0 | 0 | 0 | 2074.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511147 | N-WW-NI-100221-Papigoe_Pilot_Row_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-10 |  | 2021-05-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1295.68 | 1295.68 | 54.32 | 0 | 0 | 1350 | 0 | 0 | 0 | 0 | 1350 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511149 | N-WW-NI-100221-Rosemarkie_New_SPS_EO-Storm Screen | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-10 |  | 2021-05-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22538 | 22538 | 14961.65 | 0 | 0 | 37499.65 | 0 | 0 | 0 | 0 | 37499.65 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505638 | N-WW-NI-100320- Eochar 1 SPS - Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-06-08 | 2021-01-14 | 2021-06-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10893.36 | 10893.36 | 3585.6 | 0 | 0 | 14478.96 | 0 | 0 | 0 | 0 | 14478.96 | 90601.29 | [5 empty] | N | WWNI | 100%
505654 | N-WW-NI-100320-Acharacle STW - Refurbish telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-04-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 71.96 | 1073.34 | 1145.3 | 0 | 0 | 0 | 1145.3 | 0 | 0 | 0 | 0 | 1145.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505653 | N-WW-NI-100320-Alness & Invergordon STW - Replace FE Pump A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-11-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 837.38 | 5278.5 | 6115.88 | 0 | 0 | 0 | 6115.88 | 0 | 0 | 0 | 0 | 6115.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505624 | N-WW-NI-100320-Campbeltown Bengullion Road SPS - Replace Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-09-23 | 2021-07-12 | 2021-11-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2093.02 | 3325.98 | 5419 | 67081.3 | 0 | 0 | 72500.3 | 0 | 0 | 0 | 0 | 72500.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505642 | N-WW-NI-100320-Connel TPS1 - Replace Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-06-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 523.36 | 7939.17 | 8462.53 | 0 | 0 | 0 | 8462.53 | 0 | 0 | 0 | 0 | 8462.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505648 | N-WW-NI-100320-Grantown STW - Electrical Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 503.74 | 0 | 503.74 | 7196.26 | 0 | 0 | 7700 | 0 | 0 | 0 | 0 | 7700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505655 | N-WW-NI-100320-Head of Work Kirkwall STC - Replace Return Liquor P2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-09-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1561.04 | 1561.04 | 0 | 0 | 0 | 1561.04 | 0 | 0 | 0 | 0 | 1561.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505657 | N-WW-NI-100320-Kilchoan Mingarry ST - Replace Cover & Refurbish Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-10-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 2600 | 2770.09 | 0 | 0 | 0 | 2770.09 | 0 | 0 | 0 | 0 | 2770.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505650 | N-WW-NI-100320-Nairn STW - CAS Basin Critical Spare | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-12 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 418.69 | 0 | 418.69 | 5981.31 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 6400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505629 | N-WW-NI-100320-Nairn_STW- Skimer_Arm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-10 |  | 2020-09-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4685.16 | 6300.35 | 10985.51 | 0 | 0 | 0 | 10985.51 | 0 | 0 | 0 | 0 | 10985.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505656 | N-WW-NI-100320-Rovahead STW - Critical Spare Belt for Belt Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11700 | 0 | 0 | 11700 | 0 | 0 | 0 | 0 | 11700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511717 | N-WW-NI-100321-Bu_Point_STW-Guide Rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-10 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.47 | 150.47 | 1971.42 | 0 | 0 | 2121.89 | 0 | 0 | 0 | 0 | 2121.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511716 | N-WW-NI-100321-Ferry_Inn_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2169.75 | 2169.75 | 130.25 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511723 | N-WW-NI-100321-Lochcarron_East_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 3685.74 | 0 | 0 | 3967.05 | 0 | 0 | 0 | 0 | 3967.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506195 | N-WW-NI-100420 - Thurso Harbour SPS CSO - Replace CSO Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-06-16 | 2022-09-12 | 2022-12-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3502.97 | 3502.97 | 171600 | 0 | 0 | 175102.97 | 0 | 0 | 0 | 0 | 175102.97 | 90601.29 | [5 empty] | N | WWNI | 100%
506198 | N-WW-NI-100420-Wick_Victoria_Pl_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-15 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.41 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507122 | N-WW-NI-100620 - Dunvegan WwTW - Demolish SHT 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-07-10 | 2021-03-29 | 2021-11-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12563 | 12563 | 24265.43 | 0 | 0 | 36828.43 | 0 | 0 | 0 | 0 | 36828.43 | 90601.29 | [5 empty] | N | WWNI | 100%
507126 | N-WW-NI-100620 - Stornoway MacKenzie Park - Demolish STs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-10-02 | 2022-05-13 | 2022-12-26 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2984.36 | 2984.36 | 27037.38 | 0 | 0 | 30021.74 | 0 | 0 | 0 | 0 | 30021.74 | 209381.79 | [5 empty] | N | WWI | 100%
507127 | N-WW-NI-100620-Fortrose_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-10 |  | 2020-07-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5628.99 | 5628.99 | 0 | 0 | 0 | 5628.99 | 0 | 0 | 0 | 0 | 5628.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507622 | N-WW-NI-100720-Forss_SEP-Outfall Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-13 |  | 2020-07-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1277.13 | 1277.13 | 0 | 0 | 0 | 1277.13 | 0 | 0 | 0 | 0 | 1277.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507613 | N-WW-NI-100720-Kildary_STW-Access Roads | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-10 |  | 2020-07-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2648.92 | 2648.92 | 0 | 0 | 0 | 2648.92 | 0 | 0 | 0 | 0 | 2648.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507619 | N-WW-NI-100720-Kildary_STW-Outfall Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1053.27 | 1053.27 | 15046.73 | 0 | 0 | 16100 | 0 | 0 | 0 | 0 | 16100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507612 | N-WW-NI-100720-Nairn_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-10 |  | 2020-10-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4696.4 | 4696.4 | 0 | 0 | 0 | 4696.4 | 0 | 0 | 0 | 0 | 4696.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507625 | N-WW-NI-100720-Oban_Gallanach_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-13 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483.02 | 483.02 | 4916.98 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 5400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507615 | N-WW-NI-100720-Thurso_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8920.25 | 8920.25 | 79.75 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 9000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508134 | N-WW-NI-100820-Campbeltown_STW- Odour | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-11 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193.93 | 1193.93 | -13.93 | 0 | 0 | 1180 | 0 | 0 | 0 | 0 | 1180 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508127 | N-WW-NI-100820-Campbeltown_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-11 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1972.68 | 1972.68 | -22.68 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 1950 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508703 | N-WW-NI-100920-Aviemore_STW- MLSS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-10-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12033.62 | 12033.62 | 0 | 0 | 0 | 12033.62 | 0 | 0 | 0 | 0 | 12033.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508699 | N-WW-NI-100920-Dounby_STW-Filters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-10 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 189.72 | 2710.28 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508690 | N-WW-NI-100920-Gremista_SPS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-10 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17420.9 | 17420.9 | -1020.9 | 0 | 0 | 16400 | 0 | 0 | 0 | 0 | 16400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508696 | N-WW-NI-100920-St_Marys_STW-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-10 |  | 2020-02-12 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349.09 | 1349.09 | 0 | 0 | 0 | 1349.09 | 0 | 0 | 0 | 0 | 1349.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509705 | N-WW-NI-101120-Dingwall_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-11 |  | 2021-04-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39814.45 | 39814.45 | 3085.54 | 0 | 0 | 42899.99 | 0 | 0 | 0 | 0 | 42899.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509717 | N-WW-NI-101120-Port_Ellen_SEP-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-11 |  | 2021-03-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1948.38 | 1948.38 | 151.62 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504267 | N-WW-NI-101219-Aviemore_STW-DO_Probes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-16 |  | 2020-01-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 8200 | -210.59 | 7989.41 | 0 | 0 | 0 | 7989.41 | 0 | 0 | 0 | 0 | 7989.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504264 | N-WW-NI-101219-Oban_STW-Belt_Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-12 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 16400.92 | -3933.79 | 12467.13 | 3933.79 | 0 | 0 | 16400.92 | 0 | 0 | 0 | 0 | 16400.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508691 | N-WW-NI-1090920-Wick_Victoria_Pl_SPS-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-10 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510614 | N-WW-NI-110121-Durness_Sango_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261.68 | 261.68 | 3738.32 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510613 | N-WW-NI-110121-Nairn_STW-Cetrifuge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399.07 | 399.07 | 5700.92 | 0 | 0 | 6099.99 | 0 | 0 | 0 | 0 | 6099.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510632 | N-WW-NI-110121-Ullapool_STW-Heaters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857.01 | 857.01 | 12243 | 0 | 0 | 13100.01 | 0 | 0 | 0 | 0 | 13100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511177 | N-WW-NI-110221-Aviemore_STW-MLSS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 425.23 | 6074.75 | 0 | 0 | 6499.98 | 0 | 0 | 0 | 0 | 6499.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511736 | N-WW-NI-110321-Applecross_Toilet_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140.65 | 140.65 | 1842.84 | 0 | 0 | 1983.49 | 0 | 0 | 0 | 0 | 1983.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511747 | N-WW-NI-110321-Broadford_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1862.74 | 1862.74 | 287.26 | 0 | 0 | 2150 | 0 | 0 | 0 | 0 | 2150 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511734 | N-WW-NI-110321-Jemimaville_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.94 | 107.94 | 1414.26 | 0 | 0 | 1522.2 | 0 | 0 | 0 | 0 | 1522.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506560 | N-WW-NI-1105020-Stornoway_STW_Pressure_Vessel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-12 |  | 2020-07-22 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934.85 | 934.85 | 0 | 0 | 0 | 934.85 | 0 | 0 | 0 | 0 | 934.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506566 | N-WW-NI-110520-Gairloch_STW_Calibration_Equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-12 |  | 2020-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1761 | 1761 | 0 | 0 | 0 | 1761 | 0 | 0 | 0 | 0 | 1761 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506576 | N-WW-NI-110520-Kingussie_STW-Compressor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-12 |  | 2020-07-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2165.09 | 2165.09 | 0 | 0 | 0 | 2165.09 | 0 | 0 | 0 | 0 | 2165.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506553 | N-WW-NI-110520-Thurso_Harbour_SPS_Surge_Vessel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-12 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10110.99 | 10110.99 | 5589.01 | 0 | 0 | 15700 | 0 | 0 | 0 | 0 | 15700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507144 | N-WW-NI-110620 - Furnace DOA - Leacann Burn - Replace River Crossing | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | GW0 |  | 2021-06-07 | 2021-09-13 | 2022-04-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10906 | 10906 | 32412.08 | 0 | 0 | 43318.08 | 0 | 0 | 0 | 0 | 43318.08 | 209381.79 | [5 empty] | N | WWI | 100%
508139 | N-WW-NI-110820-Campbeltown_STW-Actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-11 |  | 2020-11-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.01 | 3146.01 | 0 | 0 | 0 | 3146.01 | 0 | 0 | 0 | 0 | 3146.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508136 | N-WW-NI-110820-Oban_Gallanach_SPS-Macerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-11 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5668.88 | 5668.88 | 31.12 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 5700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508137 | N-WW-NI-110820-Oban_STW-Cake Breaker | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-11 |  | 2020-10-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8245.63 | 8245.63 | 0 | 0 | 0 | 8245.63 | 0 | 0 | 0 | 0 | 8245.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508158 | N-WW-NI-110820-Poolewe_ST-Gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-11-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1962.81 | 1962.81 | 0 | 0 | 0 | 1962.81 | 0 | 0 | 0 | 0 | 1962.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508712 | N-WW-NI-110920 - Balivanich WwTW - Access Track | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-01 | 2022-06-23 | 2023-02-03 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 976.92 | 976.92 | 9055.15 | 0 | 0 | 10032.07 | 0 | 0 | 0 | 0 | 10032.07 | 90601.29 | [5 empty] | N | WWNI | 100%
508708 | N-WW-NI-11092020-ROVAHEAD WWTW-INSTALLATION OF CHEMICAL DOSING UNIT (TTOX) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9859.35 | 9859.35 | 127635.66 | 0 | 0 | 137495 | 0 | 0 | 0 | 0 | 137495 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508714 | N-WW-NI-110920-Balmacara_STW_Blowers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-17 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11070.28 | 11070.28 | 2929.72 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 14000 | 90601.29 | [5 empty] | N | WWNI | 100%
508707 | N-WW-NI-110920-Roybridge_SPS_Air_Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-11 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508715 | N-WW-NI-110920-Stornoway_STW_Launder_Channel_FSTB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-17 |  | 2020-11-16 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30502.88 | 30502.88 | 0 | 0 | 0 | 30502.88 | 0 | 0 | 0 | 0 | 30502.88 | 90601.29 | [5 empty] | N | WWNI | 100%
509746 | N-WW-NI-111120-Aviemore_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-11 |  | 2020-11-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2140.86 | 2140.86 | 0 | 0 | 0 | 2140.86 | 0 | 0 | 0 | 0 | 2140.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509724 | N-WW-NI-111120-Nairn at Viaduct_SST-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-11-11 |  | 2021-02-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1216.04 | 1216.04 | 83.96 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509744 | N-WW-NI-111120-Nairn_Footpath_SPS-Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-11 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5514.02 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 5900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503802 | N-WW-NI-111219-Broadford_Ind_Est_SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-12 |  | 2020-07-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 9841.89 | 0 | 9841.89 | 0 | 0 | 0 | 9841.89 | 0 | 0 | 0 | 0 | 9841.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510271 | N-WW-NI-111220-Golspie_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-11 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4022.66 | 4022.66 | 77.34 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510291 | N-WW-NI-111220-Kilmory_STW-Filter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1789.12 | 1789.12 | 60.9 | 0 | 0 | 1850.02 | 0 | 0 | 0 | 0 | 1850.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510272 | N-WW-NI-111220-Thurso_Burnside_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-11 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 4018.68 | 0 | 0 | 4299.99 | 0 | 0 | 0 | 0 | 4299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510666 | N-WW-NI-120121-Evanton_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510660 | N-WW-NI-120121-Golspie_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29482.93 | 29482.93 | 117.07 | 0 | 0 | 29600 | 0 | 0 | 0 | 0 | 29600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510664 | N-WW-NI-120121-Lerwick_Gremista_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-13 |  | 2021-02-14 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2215.71 | 2215.71 | 84.28 | 0 | 0 | 2299.99 | 0 | 0 | 0 | 0 | 2299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511212 | N-WW-NI-120221-Conon_Bridge_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2228.51 | 2228.51 | 171.49 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511210 | N-WW-NI-120221-Dingwall_Bridgend_SPS-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020.12 | 1020.12 | 1028.05 | 0 | 0 | 2048.17 | 0 | 0 | 0 | 0 | 2048.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511188 | N-WW-NI-120221-Dulnain_Bridge_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.33 | 595.33 | 8504.65 | 0 | 0 | 9099.98 | 0 | 0 | 0 | 0 | 9099.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511190 | N-WW-NI-120221-Lochcarron_Slumbay_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5029.51 | 5029.51 | 370.49 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 5400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511191 | N-WW-NI-120221-N_Ballachulish_SEP-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8654.16 | 8654.16 | 45.84 | 0 | 0 | 8700 | 0 | 0 | 0 | 0 | 8700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511192 | N-WW-NI-120221-Portree_Cullin_Hills_SPS-NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1862.22 | 1862.22 | 137.78 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511216 | N-WW-NI-120221-Portree_STW-Bldng Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.88 | 183.88 | 2009.35 | 0 | 0 | 2193.23 | 0 | 0 | 0 | 0 | 2193.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511214 | N-WW-NI-120221-Stornoway_STW-DO Controller | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-12 |  | 2021-05-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.67 | 1778.67 | -178.65 | 0 | 0 | 1600.02 | 0 | 0 | 0 | 0 | 1600.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511761 | N-WW-NI-120321-Broadford_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191.13 | 191.13 | 1842.84 | 0 | 0 | 2033.97 | 0 | 0 | 0 | 0 | 2033.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511772 | N-WW-NI-120321-Ft_Augustus_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2057.16 | 0 | 0 | 2214.17 | 0 | 0 | 0 | 0 | 2214.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511771 | N-WW-NI-120321-Kirkhill_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2057.16 | 0 | 0 | 2214.17 | 0 | 0 | 0 | 0 | 2214.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506587 | N-WW-NI-120520 - Alness Teaninich SPS - Re-instate Storm Return Pumping | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-10-28 | 2022-05-27 | 2022-09-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12717 | 12717 | 177282.69 | 0 | 0 | 189999.69 | 0 | 0 | 0 | 0 | 189999.69 | 90601.29 | [5 empty] | N | WWNI | 100%
507161 | N-WW-NI-120620-Muir of Ord_STW-DAB_Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-12 |  | 2020-06-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3085.64 | 3085.64 | 0 | 0 | 0 | 3085.64 | 0 | 0 | 0 | 0 | 3085.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509218 | N-WW-NI-121020-Ardgour_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-12 |  | 2020-11-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9684.85 | 9684.85 | -5584.85 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509223 | N-WW-NI-121020-Broadford_STW-Fan | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-12 |  | 2021-03-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6406 | 6406 | 94 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509208 | N-WW-NI-121020-Crowlista_STW-Tipping Tray | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-12 |  | 2020-10-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2940.62 | 2940.62 | 0 | 0 | 0 | 2940.62 | 0 | 0 | 0 | 0 | 2940.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509229 | N-WW-NI-121020-Port_Ellen_SPS-Pump House | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-12 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2803.74 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509201 | N-WW-NI-121020-Portmahomack_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-12 |  | 2020-11-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1974.47 | 1974.47 | 0 | 0 | 0 | 1974.47 | 0 | 0 | 0 | 0 | 1974.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509211 | N-WW-NI-121020-Stornoway_STW-Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-12 |  | 2020-03-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4781.28 | 4781.28 | 0 | 0 | 0 | 4781.28 | 0 | 0 | 0 | 0 | 4781.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509203 | N-WW-NI-121020-Stornoway_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-12 |  | 2020-10-31 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2297.81 | 2297.81 | 0 | 0 | 0 | 2297.81 | 0 | 0 | 0 | 0 | 2297.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509220 | N-WW-NI-121020-Watten_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-12 |  | 2020-10-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1092.5 | 1092.5 | 0 | 0 | 0 | 1092.5 | 0 | 0 | 0 | 0 | 1092.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503810 | N-WW-NI-121119-Alness & Invergordon STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | -50.43 | 1349.57 | 50.43 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | WWNI | 100%
503807 | N-WW-NI-121119-Fort_Augustus_STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-12 |  | 2019-12-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1241.05 | 0 | 1241.05 | 0 | 0 | 0 | 1241.05 | 0 | 0 | 0 | 0 | 1241.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504635 | N-WW-NI-130120-Ft_Augustus_STW-Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-05-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | -41.84 | 2858.16 | 0 | 0 | 0 | 2858.16 | 0 | 0 | 0 | 0 | 2858.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510685 | N-WW-NI-130121-Conon_Bridge_STW-Platform | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510681 | N-WW-NI-130121-Kishorn_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-14 |  | 2021-04-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1483.72 | 1483.72 | 187.88 | 0 | 0 | 1671.6 | 0 | 0 | 0 | 0 | 1671.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510682 | N-WW-NI-130121-Leurbost_East_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-13 |  | 2021-03-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430.13 | 1430.13 | 69.88 | 0 | 0 | 1500.01 | 0 | 0 | 0 | 0 | 1500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510690 | N-WW-NI-130121-North_Ballachulish_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5529.72 | 5529.72 | 70.28 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 5600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510686 | N-WW-NI-130121-Shieldaig_Pier_SPS-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-13 |  | 2021-03-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15122.31 | 15122.31 | -922.31 | 0 | 0 | 14200 | 0 | 0 | 0 | 0 | 14200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510694 | N-WW-NI-130121-Thrunster_STW-Reed Beds | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4579.44 | 4579.44 | 65420.56 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505188 | N-WW-NI-130220-Alness_Invergordon_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-20 |  | 2020-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 1140.63 | 1225.68 | 0 | 0 | 0 | 1225.68 | 0 | 0 | 0 | 0 | 1225.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505190 | N-WW-NI-130220-Thurso _STW-Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-07-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 532.17 | 2903.85 | 3436.02 | 0 | 0 | 0 | 3436.02 | 0 | 0 | 0 | 0 | 3436.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506603 | N-WW-NI-130520 - Ullapool Ardmair ST - Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-07 | 2022-12-16 | 2023-03-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2308 | 2308 | 52691.61 | 0 | 0 | 54999.61 | 0 | 0 | 0 | 0 | 54999.61 | 90601.29 | [5 empty] | N | WWNI | 100%
506588 | N-WW-NI-130520-Dingwall_Jubilee_SPS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-06-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2213.7 | 2213.7 | 0 | 0 | 0 | 2213.7 | 0 | 0 | 0 | 0 | 2213.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506590 | N-WW-NI-130520-Inveraray_STW-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-07-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3694.35 | 3694.35 | 0 | 0 | 0 | 3694.35 | 0 | 0 | 0 | 0 | 3694.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507631 | N-WW-NI-130720-Alness_Invergordon_STC-Hot Box | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-13 |  | 2020-08-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357.76 | 1357.76 | 0 | 0 | 0 | 1357.76 | 0 | 0 | 0 | 0 | 1357.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507664 | N-WW-NI-130720-Carrbridge_STW-Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-08-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579.73 | 1579.73 | 0 | 0 | 0 | 1579.73 | 0 | 0 | 0 | 0 | 1579.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507630 | N-WW-NI-130720-Oban_STW-MH Cover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-13 |  | 2020-10-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2190.79 | 2190.79 | 0 | 0 | 0 | 2190.79 | 0 | 0 | 0 | 0 | 2190.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507662 | N-WW-NI-130720-Stornoway_STW-Doors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-13 |  | 2020-10-15 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3261.24 | 3261.24 | 0 | 0 | 0 | 3261.24 | 0 | 0 | 0 | 0 | 3261.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507659 | N-WW-NI-130720-Tain_STW-HUBER Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-13 |  | 2020-08-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2821.24 | 2821.24 | 0 | 0 | 0 | 2821.24 | 0 | 0 | 0 | 0 | 2821.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508191 | N-WW-NI-130820-Dingwall_STW-FST Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-09-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2501.81 | 2501.81 | 0 | 0 | 0 | 2501.81 | 0 | 0 | 0 | 0 | 2501.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508192 | N-WW-NI-130820-Lerwick_North_Taing_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-10-05 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5292.14 | 5292.14 | 0 | 0 | 0 | 5292.14 | 0 | 0 | 0 | 0 | 5292.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508189 | N-WW-NI-130820-Lochend_DOA-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-08-13 |  | 2020-09-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340.87 | 1340.87 | 0 | 0 | 0 | 1340.87 | 0 | 0 | 0 | 0 | 1340.87 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509239 | N-WW-NI-131020-Aviemore_STW-Autosampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-13 |  | 2020-11-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2886.52 | 2886.52 | 0 | 0 | 0 | 2886.52 | 0 | 0 | 0 | 0 | 2886.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509245 | N-WW-NI-131020-Beauly_Maple_Vale_SPS-Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-13 |  | 2021-04-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1602.67 | 1602.67 | 47.33 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 1650 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509248 | N-WW-NI-131020-Dingwall_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-13 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11505.09 | 11505.09 | 6694.91 | 0 | 0 | 18200 | 0 | 0 | 0 | 0 | 18200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509246 | N-WW-NI-131020-Golspie_STW-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-13 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085.01 | 1085.01 | 114.99 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509241 | N-WW-NI-131020-Woodside_STW-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-13 |  | 2020-11-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1863.84 | 1863.84 | 0 | 0 | 0 | 1863.84 | 0 | 0 | 0 | 0 | 1863.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503817 | N-WW-NI-131119-Bonawe_STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-04-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 10230.63 | 0 | 10230.63 | -8930.63 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWI | 100%
509774 | N-WW-NI-131120-Aviemore_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-13 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3502.98 | 3502.98 | 97.02 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509779 | N-WW-NI-131120-Drumnadrochit_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-13 |  | 2020-08-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2376.96 | 2376.96 | 0 | 0 | 0 | 2376.96 | 0 | 0 | 0 | 0 | 2376.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509778 | N-WW-NI-131120-Spean_Bridge_STW-Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-13 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4518.67 | 4518.67 | 131.32 | 0 | 0 | 4649.99 | 0 | 0 | 0 | 0 | 4649.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509788 | N-WW-NI-131120-Stornoway_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-16 |  | 2021-03-04 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2082.94 | 2082.94 | 117.06 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509789 | N-WW-NI-131120-Stornoway_STC-Compressor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-13 |  | 2020-11-26 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898.28 | 1898.28 | 0 | 0 | 0 | 1898.28 | 0 | 0 | 0 | 0 | 1898.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509777 | N-WW-NI-131120-Strontian_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-13 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1145.46 | 1145.46 | 54.54 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510700 | N-WW-NI-140121-Lairg_West_Ord_PL_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-15 |  | 2021-04-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3476.47 | 3476.47 | 73.52 | 0 | 0 | 3549.99 | 0 | 0 | 0 | 0 | 3549.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505198 | N-WW-NI-140220-Balintore_STW-RBC3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-05-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2695.33 | 38467.29 | 41162.62 | 0 | 0 | 0 | 41162.62 | 0 | 0 | 0 | 0 | 41162.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505200 | N-WW-NI-140220-Benderloch_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 4086.72 | 0 | 4086.72 | 113.28 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506614 | N-WW-NI-140520-Dornoch_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-07-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6834.57 | 6834.57 | 0 | 0 | 0 | 6834.57 | 0 | 0 | 0 | 0 | 6834.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506611 | N-WW-NI-140520-Grantown_STW-VSD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750.3 | 1750.3 | 0 | 0 | 0 | 1750.3 | 0 | 0 | 0 | 0 | 1750.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506613 | N-WW-NI-140520-Islay_Portnahaven_SPS_Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-18 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8954.87 | 8954.87 | 0 | 0 | 0 | 8954.87 | 0 | 0 | 0 | 0 | 8954.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506620 | N-WW-NI-140520-Lerwick_Rudda_Park_SPS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-06-04 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3288 | 3288 | 2912 | 0 | 0 | 6200 | 0 | 0 | 0 | 0 | 6200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506621 | N-WW-NI-140520-Tobremory_Pier_SPS-Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-05-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979.19 | 979.19 | 0 | 0 | 0 | 979.19 | 0 | 0 | 0 | 0 | 979.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507666 | N-WW-NI-140720-Oban_STW-Sludge Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-07-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7005.63 | 7005.63 | 0 | 0 | 0 | 7005.63 | 0 | 0 | 0 | 0 | 7005.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508721 | N-WW-NI-140920-Applecross_Toilet_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-17 |  | 2020-10-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669.51 | 1669.51 | 0 | 0 | 0 | 1669.51 | 0 | 0 | 0 | 0 | 1669.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508720 | N-WW-NI-140920-Kildary_STW-SHT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-17 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1563.96 | 1563.96 | 0 | 0 | 0 | 1563.96 | 0 | 0 | 0 | 0 | 1563.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508726 | N-WW-NI-140920-Kilmory_STW_Dewaterer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-17 |  | 2020-09-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1498.83 | 1498.83 | 0 | 0 | 0 | 1498.83 | 0 | 0 | 0 | 0 | 1498.83 | 90601.29 | [5 empty] | N | WWNI | 100%
508749 | N-WW-NI-140920-North_Ballachulish_STW_FST_Scrapers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-17 |  | 2020-10-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576.95 | 1576.95 | 0 | 0 | 0 | 1576.95 | 0 | 0 | 0 | 0 | 1576.95 | 90601.29 | [5 empty] | N | WWNI | 100%
508719 | N-WW-NI-140920-Rovahead_STW-Motor Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-17 |  | 2020-10-15 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2350.4 | 2350.4 | 0 | 0 | 0 | 2350.4 | 0 | 0 | 0 | 0 | 2350.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509266 | N-WW-NI-141020-Gremista_SPS-Gratings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-15 |  | 2020-11-23 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3153.34 | 3153.34 | 0 | 0 | 0 | 3153.34 | 0 | 0 | 0 | 0 | 3153.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509262 | N-WW-NI-141020-Rovahead_STC-Belt Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-14 |  | 2020-10-20 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1295.59 | 1295.59 | 0 | 0 | 0 | 1295.59 | 0 | 0 | 0 | 0 | 1295.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510307 | N-WW-NI-141220-Boat_of_Garten_STW_Critical_Spare_Pump_Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1977.79 | 0 | 0 | 2089 | 0 | 0 | 0 | 0 | 2089 | 90601.29 | [5 empty] | N | WWNI | 100%
510302 | N-WW-NI-141220-Boat_of_Garten_STW_RotacutLCP&PCU | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778.5 | 778.5 | 11121.5 | 0 | 0 | 11900 | 0 | 0 | 0 | 0 | 11900 | 90601.29 | [5 empty] | N | WWNI | 100%
510311 | N-WW-NI-141220-Stornoway_STC-Bldng | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-20 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031.31 | 4031.31 | 268.68 | 0 | 0 | 4299.99 | 0 | 0 | 0 | 0 | 4299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510310 | N-WW-NI-141220-Strathpeffer_STW-Guide Rail | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1214.94 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510298 | N-WW-NI-141220-Ullapool_Point_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6868.62 | 6868.62 | 131.37 | 0 | 0 | 6999.99 | 0 | 0 | 0 | 0 | 6999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510304 | N-WW-NI-141220-Wick_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4134.85 | 4134.85 | 65.16 | 0 | 0 | 4200.01 | 0 | 0 | 0 | 0 | 4200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510296 | N-WW-NI-14220-Boat_of_Garten_STW-Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-14 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038.82 | 2038.82 | 61.2 | 0 | 0 | 2100.02 | 0 | 0 | 0 | 0 | 2100.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504672 | N-WW-NI-150120-Cawdor_STW-Pump_CS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-16 |  | 2020-03-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3804.03 | 0 | 3804.03 | 0 | 0 | 0 | 3804.03 | 0 | 0 | 0 | 0 | 3804.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504666 | N-WW-NI-150120-Kinlochewe_Incheril_SEP-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-16 |  | 2020-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2670.96 | 0 | 2670.96 | 0 | 0 | 0 | 2670.96 | 0 | 0 | 0 | 0 | 2670.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504668 | N-WW-NI-150120-Lerwick_Gremista_SPS-Building | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-07-24 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6545 | 6545 | 555 | 0 | 0 | 7100 | 0 | 0 | 0 | 0 | 7100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504674 | N-WW-NI-150120-Lerwick_Gremista_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-03-12 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 2014.48 | 0 | 2014.48 | 235.52 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2250 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510713 | N-WW-NI-150121-Bridge_End_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2799.23 | 2799.23 | 450.77 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 3250 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510722 | N-WW-NI-150121-Campbeltown_STW-Tank Scoping | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2021-03-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1814.32 | 1814.32 | 35.68 | 0 | 0 | 1850 | 0 | 0 | 0 | 0 | 1850 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510720 | N-WW-NI-150121-Dingwall_DOA-Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1131.61 | 1131.61 | 68.39 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510712 | N-WW-NI-150121-Gremista_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197.2 | 1197.2 | 17102.8 | 0 | 0 | 18300 | 0 | 0 | 0 | 0 | 18300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511219 | N-WW-NI-150221-Dingwall_STW-Boiler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1481.4 | 1481.4 | 118.6 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511217 | N-WW-NI-150221-Lochcarron_STW-Tee Piece | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1364.82 | 1364.82 | 35.18 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511248 | N-WW-NI-150221-N_Ballachulish_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446.39 | 446.39 | 5140.2 | 0 | 0 | 5586.59 | 0 | 0 | 0 | 0 | 5586.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511786 | N-WW-NI-150321-Alness_Teaninich_SPS-Heater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1464.26 | 1464.26 | 185.74 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 1650 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511775 | N-WW-NI-150321-Boat_of_Garten_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1800 | 0 | 0 | 1937.38 | 0 | 0 | 0 | 0 | 1937.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511788 | N-WW-NI-150321-Lochcarron_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1200 | 0 | 0 | 1291.59 | 0 | 0 | 0 | 0 | 1291.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506220 | N-WW-NI-150420-Alness_Teaninich_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-15 |  | 2020-07-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11979.28 | 11979.28 | 0 | 0 | 0 | 11979.28 | 0 | 0 | 0 | 0 | 11979.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506222 | N-WW-NI-150420-Lerwick_Rovahead_STC-Belt_Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-09-29 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11695 | 11695 | 0 | 0 | 0 | 11695 | 0 | 0 | 0 | 0 | 11695 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506639 | N-WW-NI-150520-Boat_of_Garten_STW_Sludge_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-18 |  | 2020-09-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374.93 | 1374.93 | 0 | 0 | 0 | 1374.93 | 0 | 0 | 0 | 0 | 1374.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507194 | N-WW-NI-150620-Oban_STW-Actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-17 |  | 2020-09-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2963.39 | 2963.39 | 0 | 0 | 0 | 2963.39 | 0 | 0 | 0 | 0 | 2963.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507700 | N-WW-NI-150720-Bunessan_ST-H&S Imps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-10-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7806.3 | 7806.3 | 0 | 0 | 0 | 7806.3 | 0 | 0 | 0 | 0 | 7806.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507712 | N-WW-NI-150720-Cromdale_STW-Bearings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-11-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 0 | 0 | 0 | 157.01 | 0 | 0 | 0 | 0 | 157.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507701 | N-WW-NI-150720-Edderton_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-08-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193.44 | 4193.44 | 0 | 0 | 0 | 4193.44 | 0 | 0 | 0 | 0 | 4193.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507699 | N-WW-NI-150720-Halkirk_STW-Sprinkler System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-08-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1914.84 | 1914.84 | 0 | 0 | 0 | 1914.84 | 0 | 0 | 0 | 0 | 1914.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507714 | N-WW-NI-150720-Inchree_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-16 |  | 2021-03-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1711.44 | 1711.44 | 38.56 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 1750 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507715 | N-WW-NI-150720-Kingussie_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197.2 | 1197.2 | 26202.8 | 0 | 0 | 27400 | 0 | 0 | 0 | 0 | 27400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507708 | N-WW-NI-150720-Kirkwalll_HoW_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-08-03 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5812.68 | 5812.68 | 0 | 0 | 0 | 5812.68 | 0 | 0 | 0 | 0 | 5812.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508764 | N-WW-NI-150920 - Campbeltown Low Askomil West SPS - Replace Perimeter Wall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-10-05 | 2021-07-12 | 2022-02-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5824.4 | 5824.4 | 10229.17 | 0 | 0 | 16053.57 | 0 | 0 | 0 | 0 | 16053.57 | 90601.29 | [5 empty] | N | WWNI | 100%
508759 | N-WW-NI-150920-Kirkwall_HoW_STW-HMI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-17 |  | 2020-10-03 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1606.21 | 1606.21 | 0 | 0 | 0 | 1606.21 | 0 | 0 | 0 | 0 | 1606.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508756 | N-WW-NI-150920-Reay_East_SPS-Roof | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-17 |  | 2020-11-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620.35 | 1620.35 | 0 | 0 | 0 | 1620.35 | 0 | 0 | 0 | 0 | 1620.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509278 | N-WW-NI-151020-Drumnadrochit_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-15 |  | 2021-03-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13252.23 | 13252.23 | 147.77 | 0 | 0 | 13400 | 0 | 0 | 0 | 0 | 13400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509280 | N-WW-NI-151020-Muir_of_Ord_STW-Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-15 |  | 2020-11-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2818.06 | 2818.06 | 0 | 0 | 0 | 2818.06 | 0 | 0 | 0 | 0 | 2818.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503840 | N-WW-NI-151119-Thurso_STW-Auto_Sampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-19 |  | 2019-12-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | -126.39 | 8273.61 | 0 | 0 | 0 | 8273.61 | 0 | 0 | 0 | 0 | 8273.61 | 90601.29 | [5 empty] | N | WWNI | 100%
504347 | N-WW-NI-151219-Muir_of_Ord-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-16 |  | 2020-01-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3052.72 | 0 | 3052.72 | 0 | 0 | 0 | 3052.72 | 0 | 0 | 0 | 0 | 3052.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504348 | N-WW-NI-151219-St_Marys_Sep_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-16 |  | 2020-01-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | -161.51 | 1338.49 | 0 | 0 | 0 | 1338.49 | 0 | 0 | 0 | 0 | 1338.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510317 | N-WW-NI-151220-Grantown_STW-Scrapers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-16 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1914.83 | 1914.83 | 85.2 | 0 | 0 | 2000.03 | 0 | 0 | 0 | 0 | 2000.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510318 | N-WW-NI-151220-Kingussie_SPS-Impellors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2240.79 | 2240.79 | 59.19 | 0 | 0 | 2299.98 | 0 | 0 | 0 | 0 | 2299.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510335 | N-WW-NI-151220-Kingussie_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-16 |  | 2021-03-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545.9 | 1545.9 | 104.1 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 1650 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510316 | N-WW-NI-151220-Kingussie_STW-UPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-16 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436.13 | 1436.13 | 63.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510329 | N-WW-NI-151220-Lochcarron_STW-PFT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2085.54 | 2085.54 | 664.46 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 2750 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510332 | N-WW-NI-151220-Oban_STW-MCC Bldng | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-16 |  | 2021-03-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4029.18 | 4029.18 | 3429.48 | 0 | 0 | 7458.66 | 0 | 0 | 0 | 0 | 7458.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505218 | N-WW-NI-160220-Avoch_STW-RBC2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-08-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1470 | 20384.8 | 21854.8 | 0 | 0 | 0 | 21854.8 | 0 | 0 | 0 | 0 | 21854.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505224 | N-WW-NI-160220-Balivanich_STW-PolyTank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4139.91 | 0 | 4139.91 | 0 | 0 | 0 | 4139.91 | 0 | 0 | 0 | 0 | 4139.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505219 | N-WW-NI-160220-Boat_of_Garten_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-05-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1085.79 | 3425 | 4510.79 | 0 | 0 | 0 | 4510.79 | 0 | 0 | 0 | 0 | 4510.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505223 | N-WW-NI-160220-Dornoch_STW-PolyDosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1045.39 | 0 | 1045.39 | 0 | 0 | 0 | 1045.39 | 0 | 0 | 0 | 0 | 1045.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505220 | N-WW-NI-160220Henderson_Drive_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1577.97 | 0 | 1577.97 | 0 | 0 | 0 | 1577.97 | 0 | 0 | 0 | 0 | 1577.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505222 | N-WW-NI-160220-Kirkwall_HoW_STW-Lightning_Protection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1604.84 | 1604.84 | 0 | 0 | 0 | 1604.84 | 0 | 0 | 0 | 0 | 1604.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505225 | N-WW-NI-160220-Lochcarron_STW-PFT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-18 |  | 2020-09-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 595.33 | 9304.68 | 9900.01 | 0 | 0 | 0 | 9900.01 | 0 | 0 | 0 | 0 | 9900.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505743 | N-WW-NI-160320-Balivanich_STW-Isolater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1497.15 | 0 | 1497.15 | 1202.85 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505754 | N-WW-NI-160320-Caravan_Avie_SPS-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-16 |  | 2020-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 1234.11 | 1325.7 | 0 | 0 | 0 | 1325.7 | 0 | 0 | 0 | 0 | 1325.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505744 | N-WW-NI-160320-Cawdor_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-16 |  | 2020-05-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 336.92 | 4720.75 | 5057.67 | 0 | 0 | 0 | 5057.67 | 0 | 0 | 0 | 0 | 5057.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505756 | N-WW-NI-160320-Conon_Bridge_STW-Penstock | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-18 |  | 2020-10-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 9179.26 | 9879.26 | 0 | 0 | 0 | 9879.26 | 0 | 0 | 0 | 0 | 9879.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505749 | N-WW-NI-160320-Grantown_STW-Electrical_Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-16 |  | 2020-03-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 8236.21 | 0 | 8236.21 | 0 | 0 | 0 | 8236.21 | 0 | 0 | 0 | 0 | 8236.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511804 | N-WW-NI-160321-Alness_Invergordon_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206.07 | 206.07 | 2700 | 0 | 0 | 2906.07 | 0 | 0 | 0 | 0 | 2906.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511831 | N-WW-NI-160321-Avoch_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190.65 | 1190.65 | 17009.35 | 0 | 0 | 18200 | 0 | 0 | 0 | 0 | 18200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511834 | N-WW-NI-160321-Conon_Bridge_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.35 | 209.35 | 2742.84 | 0 | 0 | 2952.19 | 0 | 0 | 0 | 0 | 2952.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511801 | N-WW-NI-160321-Dingwall_STW-Fire Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140.65 | 140.65 | 1842.84 | 0 | 0 | 1983.49 | 0 | 0 | 0 | 0 | 1983.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511826 | N-WW-NI-160321-Fortrose_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3257.16 | 0 | 0 | 3505.76 | 0 | 0 | 0 | 0 | 3505.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507223 | N-WW-NI-160620-Arisaig_SEP-MH | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-22 |  | 2020-07-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2372.01 | 2372.01 | 0 | 0 | 0 | 2372.01 | 0 | 0 | 0 | 0 | 2372.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507221 | N-WW-NI-160620-Duror_STW-MH_Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-17 |  | 2020-07-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1673.49 | 1673.49 | 0 | 0 | 0 | 1673.49 | 0 | 0 | 0 | 0 | 1673.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507733 | N-WW-NI-160720-Grantown_STW-Access Roads | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-16 |  | 2020-08-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1962.81 | 1962.81 | 0 | 0 | 0 | 1962.81 | 0 | 0 | 0 | 0 | 1962.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507743 | N-WW-NI-160720-Invergordon_Cromlet_SPS-Wet Well | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-21 |  | 2020-08-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7954.82 | 7954.82 | 0 | 0 | 0 | 7954.82 | 0 | 0 | 0 | 0 | 7954.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507730 | N-WW-NI-160720-Kiltarlity_STW-Pump | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 |  | 2020-07-16 |  | 2020-08-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2428.55 | 2428.55 | 0 | 0 | 0 | 2428.55 | 0 | 0 | 0 | 0 | 2428.55 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
508772 | N-WW-NI-160920-Fortrose_Harbuor_SPS-VSD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-17 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 189.72 | 2710.28 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508777 | N-WW-NI-160920-Melness_STW-Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-17 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.41 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509306 | N-WW-NI-161020-Boat_of_Garden_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-19 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2098.14 | 2098.14 | 0 | 0 | 0 | 2098.14 | 0 | 0 | 0 | 0 | 2098.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509304 | N-WW-NI-161020-Campberltown_STW-Actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-16 |  | 2021-02-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2828.95 | 2828.95 | -28.95 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509308 | N-WW-NI-161020-Weyland_Bay_SPS-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-19 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5259.81 | 5259.81 | 75140.19 | 0 | 0 | 80400 | 0 | 0 | 0 | 0 | 80400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509809 | N-WW-NI-161120-Kildary_STW-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-16 |  | 2021-02-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1037.16 | 1037.16 | 62.84 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509797 | N-WW-NI-161120-Oban_STW-VSD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-16 |  | 2020-09-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3646.34 | 3646.34 | 0 | 0 | 0 | 3646.34 | 0 | 0 | 0 | 0 | 3646.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509812 | N-WW-NI-161120-Tornagrain_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-16 |  | 2021-03-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125.18 | 3125.18 | 174.82 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504355 | N-WW-NI-161219-Campbeltown_STW-Doors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-16 |  | 2019-12-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | -2056.07 | 143.93 | 0 | 0 | 0 | 143.93 | 0 | 0 | 0 | 0 | 143.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504360 | N-WW-NI-161219-Clachan_STW-Cabin | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2019-12-16 |  | 2020-07-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 5900 | -8.7 | 5891.3 | 8.7 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 5900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504358 | N-WW-NI-161219-Oban_STW-Doors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-16 |  | 2019-12-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 3670.18 | 0 | 3670.18 | 0 | 0 | 0 | 3670.18 | 0 | 0 | 0 | 0 | 3670.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504362 | N-WW-NI-161219-Wick_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-19 |  | 2020-02-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | -171.56 | 2828.44 | 0 | 0 | 0 | 2828.44 | 0 | 0 | 0 | 0 | 2828.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510369 | N-WW-NI-161220-Carrbridge_STW_Heating_&_Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 189.72 | 2710.28 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | WWNI | 100%
504722 | N-WW-NI-170120-Cawdor_STW-RASPump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | -3644.86 | 255.14 | 3644.86 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504720 | N-WW-NI-170120-Kirkhill_STW-Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-20 |  | 2020-01-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5511.54 | 0 | 5511.54 | 0 | 0 | 0 | 5511.54 | 0 | 0 | 0 | 0 | 5511.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504721 | N-WW-NI-170120-Stornoway_STC-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-20 |  | 2020-02-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1202.89 | 0 | 1202.89 | 0 | 0 | 0 | 1202.89 | 0 | 0 | 0 | 0 | 1202.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511288 | N-WW-NI-170221-Clachan_Balvicar_STW-Flow Meter | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-05-01 |  | 2021-05-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175.48 | 175.48 | 1742.3 | 0 | 0 | 1917.78 | 0 | 0 | 0 | 0 | 1917.78 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511285 | N-WW-NI-170221-Kirkwall_Ayre_Mills_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-17 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304.17 | 1304.17 | 95.83 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511291 | N-WW-NI-170221-Oban_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196.53 | 1196.53 | 3.47 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511880 | N-WW-NI-170321-Dornoch_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1285.74 | 0 | 0 | 1383.87 | 0 | 0 | 0 | 0 | 1383.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511876 | N-WW-NI-170321-Golspie_STW- Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.03 | 121.03 | 1585.74 | 0 | 0 | 1706.77 | 0 | 0 | 0 | 0 | 1706.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511872 | N-WW-NI-170321-Kildary_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1800 | 0 | 0 | 1937.38 | 0 | 0 | 0 | 0 | 1937.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511884 | N-WW-NI-170321-Melbost_SPS-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663.44 | 663.44 | 8314.26 | 0 | 0 | 8977.7 | 0 | 0 | 0 | 0 | 8977.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511867 | N-WW-NI-170321-Portmahomack_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1800 | 0 | 0 | 1937.38 | 0 | 0 | 0 | 0 | 1937.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506262 | N-WW-NI-170420-Campbeltown_STW-Actuators | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-05-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1479.36 | 1479.36 | 0 | 0 | 0 | 1479.36 | 0 | 0 | 0 | 0 | 1479.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507236 | N-WW-NI-170620-Oban_Gallanach_SPS-Muncher | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-17 |  | 2020-07-08 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4974.13 | 4974.13 | 0 | 0 | 0 | 4974.13 | 0 | 0 | 0 | 0 | 4974.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507752 | N-WW-NI-170720-Ardvasar_STW_Access_Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-21 |  | 2021-02-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2080 | 2080 | 420 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508214 | N-WW-NI-170820-Oban_STW_Scraper Wheels | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-17 |  | 2020-09-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373.55 | 1373.55 | 0 | 0 | 0 | 1373.55 | 0 | 0 | 0 | 0 | 1373.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508796 | N-WW-NI-170920-Invergordon_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1214.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508798 | N-WW-NI-170920-Kirkwall_HoW_STC-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-22 |  | 2021-02-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1627.27 | 1627.27 | 0 | 0 | 0 | 1627.27 | 0 | 0 | 0 | 0 | 1627.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508790 | N-WW-NI-170920-Lerwick_North_Ness_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-22 |  | 2020-11-05 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507.99 | 1507.99 | 0 | 0 | 0 | 1507.99 | 0 | 0 | 0 | 0 | 1507.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509823 | N-WW-NI-171120-Aviemore_STW-Electrics | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605.14 | 605.14 | 8644.86 | 0 | 0 | 9250 | 0 | 0 | 0 | 0 | 9250 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509859 | N-WW-NI-171120-Tain_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 955.14 | 955.14 | 13644.86 | 0 | 0 | 14600 | 0 | 0 | 0 | 0 | 14600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504374 | N-WW-NI-171219-Invergordon_63_Saltburn_ SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-19 |  | 2020-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3294.04 | 0 | 3294.04 | 0 | 0 | 0 | 3294.04 | 0 | 0 | 0 | 0 | 3294.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504388 | N-WW-NI-171219-Sletts_SPS-Pump_Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-06-26 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3144.75 | 3144.75 | 65.25 | 0 | 0 | 3210 | 0 | 0 | 0 | 0 | 3210 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510378 | N-WW-NI-171220-Aviemore_STW_Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2312.91 | 2312.91 | 12987.09 | 0 | 0 | 15300 | 0 | 0 | 0 | 0 | 15300 | 90601.29 | [5 empty] | N | WWNI | 100%
510393 | N-WW-NI-171220-Barbaraville_Sutor_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-17 |  | 2021-03-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4157.21 | 4157.21 | 42.78 | 0 | 0 | 4199.99 | 0 | 0 | 0 | 0 | 4199.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510391 | N-WW-NI-171220-North_Ballachulish_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-17 |  | 2021-03-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1301.2 | 1301.2 | 198.81 | 0 | 0 | 1500.01 | 0 | 0 | 0 | 0 | 1500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510394 | N-WW-NI-171220-Shieldaig_Pier_SPS-Gas Strutt | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-17 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4441.46 | 4441.46 | 458.54 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 4900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510399 | N-WW-NI-171220-Stornoway_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-18 |  | 2021-03-15 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3945.01 | 3945.01 | 354.99 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510397 | N-WW-NI-171220-Ullapool_STW-Gratings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128.28 | 128.28 | 1214.94 | 0 | 0 | 1343.22 | 0 | 0 | 0 | 0 | 1343.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510735 | N-WW-NI-180121-Tobermory_DOA-CCTV Scoping | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-01-18 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4889.69 | 4889.69 | 1360.31 | 0 | 0 | 6250 | 0 | 0 | 0 | 0 | 6250 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505279 | N-WW-NI-180220-Glenelg_STW-Access_Rd | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-09-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 1735.06 | 1865.9 | 0 | 0 | 0 | 1865.9 | 0 | 0 | 0 | 0 | 1865.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511326 | N-WW-NI-180221-Nairn_STW-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268.22 | 268.22 | 3831.8 | 0 | 0 | 4100.02 | 0 | 0 | 0 | 0 | 4100.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511318 | N-WW-NI-180221-Wick_Various_SPS-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516.82 | 516.82 | 7383.2 | 0 | 0 | 7900.02 | 0 | 0 | 0 | 0 | 7900.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505802 | N-WW-NI-180320-Balintore_STW-RBC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-05-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 12352.52 | 12496.45 | 0 | 0 | 0 | 12496.45 | 0 | 0 | 0 | 0 | 12496.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505803 | N-WW-NI-180320-Lerwick_Gremista_SPS-Grit_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-09-02 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5560 | 5560 | 0 | 0 | 0 | 5560 | 0 | 0 | 0 | 0 | 5560 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511896 | N-WW-NI-180321-Campbeltown_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454.22 | 454.22 | 4628.58 | 0 | 0 | 5082.8 | 0 | 0 | 0 | 0 | 5082.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511897 | N-WW-NI-180321-Cawdor_STW-UV Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 444.86 | 444.86 | 5828.58 | 0 | 0 | 6273.44 | 0 | 0 | 0 | 0 | 6273.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511914 | N-WW-NI-180321-Dingwall_STW-PST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421.96 | 421.96 | 5528.58 | 0 | 0 | 5950.54 | 0 | 0 | 0 | 0 | 5950.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511925 | N-WW-NI-180321-Dornoch_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392.52 | 392.52 | 5142.84 | 0 | 0 | 5535.36 | 0 | 0 | 0 | 0 | 5535.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511910 | N-WW-NI-180321-Nairn_STW-Skip Runners | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287.85 | 287.85 | 3771.42 | 0 | 0 | 4059.27 | 0 | 0 | 0 | 0 | 4059.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511890 | N-WW-NI-180321-Stornoway_STC-Sludge Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205.5 | 205.5 | 2314.26 | 0 | 0 | 2519.76 | 0 | 0 | 0 | 0 | 2519.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511888 | N-WW-NI-180321-Stornoway_STW-Flow Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1010.4 | 1010.4 | 1200 | 0 | 0 | 2210.4 | 0 | 0 | 0 | 0 | 2210.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511886 | N-WW-NI-180321-Stornoway_STW-MLSS Monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223.91 | 1223.91 | 76.09 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511924 | N-WW-NI-180321-Tain_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601.87 | 601.87 | 7885.74 | 0 | 0 | 8487.61 | 0 | 0 | 0 | 0 | 8487.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511891 | N-WW-NI-180321-Taynuilt_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-18 |  | 2021-06-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257.96 | 257.96 | 2057.16 | 0 | 0 | 2315.12 | 0 | 0 | 0 | 0 | 2315.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506649 | N-WW-NI-180520 - Portnahaven SPS - Replace guiderails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-06-01 | 2020-11-02 | 2021-01-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14440.16 | 14440.16 | 0 | 0 | 0 | 14440.16 | 0 | 0 | 0 | 0 | 14440.16 | 90601.29 | [5 empty] | N | WWNI | 100%
506667 | N-WW-NI-180520-Duror_STW_Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-19 |  | 2020-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4370.38 | 4370.38 | 0 | 0 | 0 | 4370.38 | 0 | 0 | 0 | 0 | 4370.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506669 | N-WW-NI-180520-Seaafield_Rd_SPS-Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-19 |  | 2020-11-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6154.07 | 6154.07 | 0 | 0 | 0 | 6154.07 | 0 | 0 | 0 | 0 | 6154.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507250 | N-WW-NI-180620-Nairn_STW-SAS Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-22 |  | 2020-07-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668.96 | 1668.96 | 0 | 0 | 0 | 1668.96 | 0 | 0 | 0 | 0 | 1668.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507268 | N-WW-NI-180620-Thurso_STW-Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-08-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1244 | 1244 | 0 | 0 | 0 | 1244 | 0 | 0 | 0 | 0 | 1244 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508248 | N-WW-NI-180820-Conon_Bridge_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3157.35 | 3157.35 | 8642.65 | 0 | 0 | 11800 | 0 | 0 | 0 | 0 | 11800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508250 | N-WW-NI-180820-Scrabster_BP_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-18 |  | 2020-11-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14523.92 | 14523.92 | 0 | 0 | 0 | 14523.92 | 0 | 0 | 0 | 0 | 14523.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509873 | N-WW-NI-181120-Bu_Point_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-18 |  | 2021-02-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1866.84 | 1866.84 | 133.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509877 | N-WW-NI-181120-Kirkhill_STW-Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-18 |  | 2021-02-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4812.4 | 4812.4 | 37.6 | 0 | 0 | 4850 | 0 | 0 | 0 | 0 | 4850 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509878 | N-WW-NI-181120-Oban_STW- Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-19 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2954.68 | 2954.68 | -54.68 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509870 | N-WW-NI-181120-Oban_STW-Sludge Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-18 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9430.59 | 9430.59 | 69.4 | 0 | 0 | 9499.99 | 0 | 0 | 0 | 0 | 9499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509876 | N-WW-NI-181120-Spean_Bridge_SPS-Meter Box | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2704 | 2704 | -303.64 | 0 | 0 | 2400.36 | 0 | 0 | 0 | 0 | 2400.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504416 | N-WW-NI-181219-Fortrose_STW-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2019-12-19 |  | 2020-04-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4700 | -790.94 | 3909.06 | 790.94 | 0 | 0 | 4700 | 0 | 0 | 0 | 0 | 4700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504411 | N-WW-NI-181219-Stornoway_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-19 |  | 2020-03-20 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 2045.2 | 0 | 2045.2 | 0 | 0 | 0 | 2045.2 | 0 | 0 | 0 | 0 | 2045.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510413 | N-WW-NI-181220-Alness_Invergordon_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-21 |  | 2021-03-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3585.76 | 3585.76 | 114.24 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 3700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510412 | N-WW-NI-181220-Evanton_STW_Sludge_Transfer_Pump_1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-18 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4509.93 | 4509.93 | 0 | 0 | 0 | 4509.93 | 0 | 0 | 0 | 0 | 4509.93 | 90601.29 | [5 empty] | N | WWNI | 100%
510415 | N-WW-NI-181220-Helmsdale_Shore_St_SPS-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 4018.68 | 0 | 0 | 4299.99 | 0 | 0 | 0 | 0 | 4299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510417 | N-WW-NI-181220-Thurso_Harbour_Storm_SPS_Gas_Detection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 2616.82 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 90601.29 | [5 empty] | N | WWNI | 100%
504727 | N-WW-NI-190120-Balintore_STW-RBC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-20 |  | 2020-02-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 22700 | -1568.71 | 21131.29 | 0 | 0 | 0 | 21131.29 | 0 | 0 | 0 | 0 | 21131.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504728 | N-WW-NI-190120-Duror_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | -6074.77 | 425.23 | 8074.77 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 8500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504729 | N-WW-NI-190120-FtAugustus_MarketHIll_SPS-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-20 |  | 2020-02-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1339.75 | 0 | 1339.75 | 0 | 0 | 0 | 1339.75 | 0 | 0 | 0 | 0 | 1339.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504723 | N-WW-NI-190120-Kilmory_STW-ValveScrew | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1283.29 | 0 | 1283.29 | 16.71 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504726 | N-WW-NI-190120-Kingussie_STW-ScopeReport | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | -82.56 | 2717.44 | 0 | 0 | 0 | 2717.44 | 0 | 0 | 0 | 0 | 2717.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504725 | N-WW-NI-190120-Oban_George_St_CSO-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-20 |  | 2020-01-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | -112.21 | 1187.79 | 0 | 0 | 0 | 1187.79 | 0 | 0 | 0 | 0 | 1187.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504724 | N-WW-NI-190120-Weyland_Bay_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | -2102.8 | 147.2 | 2102.8 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2250 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510765 | N-WW-NI-190121-Lerwick_Rovahead_STC-Belt Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-19 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6381.11 | 6381.11 | 7918.88 | 0 | 0 | 14299.99 | 0 | 0 | 0 | 0 | 14299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505302 | N-WW-NI-190220-Campbeltown_STW-Flooring_Clips | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-04-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 502.71 | 5772 | 6274.71 | 0 | 0 | 0 | 6274.71 | 0 | 0 | 0 | 0 | 6274.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505298 | N-WW-NI-190220-Clachan_Seil_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-05-14 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 119.25 | 1273.88 | 1393.13 | 0 | 0 | 0 | 1393.13 | 0 | 0 | 0 | 0 | 1393.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505305 | N-WW-NI-190220-Stornoway_STW-WashWater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-20 |  | 2020-03-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3296.39 | 0 | 3296.39 | 0 | 0 | 0 | 3296.39 | 0 | 0 | 0 | 0 | 3296.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511351 | N-WW-NI-190221-Aviemore_STW_Sludge Screen Level Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935.51 | 935.51 | 13364.5 | 0 | 0 | 14300.01 | 0 | 0 | 0 | 0 | 14300.01 | 90601.29 | [5 empty] | N | WWNI | 100%
505818 | N-WW-NI-190320-Lochinver_Inver_Tce_SPS-Converter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 5496.54 | 5921.77 | 0 | 0 | 0 | 5921.77 | 0 | 0 | 0 | 0 | 5921.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505828 | N-WW-NI-190320-Oban_STW-Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-20 |  | 2020-04-15 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 394.96 | 4887.82 | 5282.78 | 0 | 0 | 0 | 5282.78 | 0 | 0 | 0 | 0 | 5282.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507269 | N-WW-NI-190620-Edderton_STW-Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-22 |  | 2020-09-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5813.62 | 5813.62 | 0 | 0 | 0 | 5813.62 | 0 | 0 | 0 | 0 | 5813.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507277 | N-WW-NI-190620-Ft_Augustus_STW-PFT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-22 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9699.22 | 9699.22 | 0 | 0 | 0 | 9699.22 | 0 | 0 | 0 | 0 | 9699.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507279 | N-WW-NI-190620-Inverness_Culduthell_Av_SPS-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-22 |  | 2020-08-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270.4 | 1270.4 | 0 | 0 | 0 | 1270.4 | 0 | 0 | 0 | 0 | 1270.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507276 | N-WW-NI-190620-Kirkhill_STW-RAS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-09-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6718.63 | 6718.63 | 0 | 0 | 0 | 6718.63 | 0 | 0 | 0 | 0 | 6718.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507275 | N-WW-NI-190620-Tomatin_STW-Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-22 |  | 2020-09-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4101.49 | 4101.49 | 0 | 0 | 0 | 4101.49 | 0 | 0 | 0 | 0 | 4101.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508288 | N-WW-NI-190820-Ardersier_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-20 |  | 2020-10-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21524.57 | 21524.57 | 0 | 0 | 0 | 21524.57 | 0 | 0 | 0 | 0 | 21524.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508274 | N-WW-NI-190820-Clachan_Balvicar_SPS-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-19 |  | 2020-09-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052.48 | 2052.48 | 0 | 0 | 0 | 2052.48 | 0 | 0 | 0 | 0 | 2052.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508284 | N-WW-NI-190820-Ft Augustus_STW-MLSS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-19 |  | 2020-08-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4172.39 | 4172.39 | 0 | 0 | 0 | 4172.39 | 0 | 0 | 0 | 0 | 4172.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508262 | N-WW-NI-190820-Invergordon_Saltburn_SPS-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-19 |  | 2020-10-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3662.21 | 3662.21 | 0 | 0 | 0 | 3662.21 | 0 | 0 | 0 | 0 | 3662.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509325 | N-WW-NI-191020-Alness_Invergordon_STC-HMI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-19 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2626.64 | 2626.64 | 0 | 0 | 0 | 2626.64 | 0 | 0 | 0 | 0 | 2626.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509313 | N-WW-NI-191020-Dornoch_STW-Belt Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 811.16 | 811.16 | 7888.84 | 0 | 0 | 8700 | 0 | 0 | 0 | 0 | 8700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503875 | N-WW-NI-191119-Dulnain_Bridge_STW- SAS Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-21 |  | 2020-02-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | -133.75 | 3416.25 | 0 | 0 | 0 | 3416.25 | 0 | 0 | 0 | 0 | 3416.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503873 | N-WW-NI-191119-Kiltarlity_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-21 |  | 2020-02-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1317.34 | 0 | 1317.34 | 0 | 0 | 0 | 1317.34 | 0 | 0 | 0 | 0 | 1317.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509893 | N-WW-NI-191120-Cawdor_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-19 |  | 2021-03-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3342.55 | 3342.55 | 157.44 | 0 | 0 | 3499.99 | 0 | 0 | 0 | 0 | 3499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509900 | N-WW-NI-191120-Dingwall_DOA-Trap | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245.71 | 1245.71 | -45.71 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509892 | N-WW-NI-191120-Inverness_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-19 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1219.79 | 1219.79 | 80.21 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509883 | N-WW-NI-191120-Lairg_East_SPS-Guide Rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-19 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1176.12 | 1176.12 | 23.88 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509902 | N-WW-NI-191120-Melbost_SPS-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5889.16 | 5889.16 | 610.84 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509896 | N-WW-NI-191120-Oban_STW-Steps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-19 |  | 2021-02-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284.68 | 1284.68 | -184.68 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504430 | N-WW-NI-191219-Lerwick_Gremista_SPS-Refurb_NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-02-20 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 3389.6 | 0 | 3389.6 | 310.4 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 3700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504427 | N-WW-NI-191219-Sclloway_West_Shore_SPS - Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-03-27 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 20418.65 | 0 | 20418.65 | 1581.35 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 22000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504439 | N-WW-NI-191219-Thurso_STC-Lime_Bldng | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-20 |  | 2020-07-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 916.8 | 344.49 | 1261.29 | 0 | 0 | 0 | 1261.29 | 0 | 0 | 0 | 0 | 1261.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504433 | N-WW-NI-191219-Thurso_STW-Kiosk_Bldng | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-16 |  | 2020-07-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | -43.93 | 2856.07 | 0 | 0 | 0 | 2856.07 | 0 | 0 | 0 | 0 | 2856.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504742 | N-WW-NI-200120-Aviemore_STW-Pump_Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2862.38 | 0 | 2862.38 | -62.38 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504741 | N-WW-NI-200120-Dingwall_Jubilee_Park_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-21 |  | 2020-04-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6739.22 | 0 | 6739.22 | 0 | 0 | 0 | 6739.22 | 0 | 0 | 0 | 0 | 6739.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504739 | N-WW-NI-200120-Kiltarlity_STW-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1657.09 | 0 | 1657.09 | 92.91 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 1750 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504743 | N-WW-NI-200120-Portree_STW-InletScreen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-21 |  | 2020-08-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 2335.06 | 6835.06 | 0 | 0 | 0 | 6835.06 | 0 | 0 | 0 | 0 | 6835.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504737 | N-WW-NI-200120-Thurso_STW-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1428.64 | 0 | 1428.64 | 71.36 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510803 | N-WW-NI-200121-Dornoch_STW-WW Point | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304.21 | 304.21 | 4345.8 | 0 | 0 | 4650.01 | 0 | 0 | 0 | 0 | 4650.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510800 | N-WW-NI-200121-Lochcarron_Slumbay_SPS-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-20 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5513.1 | 5513.1 | 906.9 | 0 | 0 | 6420 | 0 | 0 | 0 | 0 | 6420 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505336 | N-WW-NI-200220-Halkirk_Braal_Rd_SPS-Building_Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-07-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 346.73 | 5113.26 | 5459.99 | 0 | 0 | 0 | 5459.99 | 0 | 0 | 0 | 0 | 5459.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505317 | N-WW-NI-200220-Portmahomack_STW-Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-20 |  | 2020-03-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1276.63 | 0 | 1276.63 | 0 | 0 | 0 | 1276.63 | 0 | 0 | 0 | 0 | 1276.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505334 | N-WW-NI-200220-Stornoway_STW-Screen_Brushes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-03-05 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 1737.03 | 0 | 1737.03 | 0 | 0 | 0 | 1737.03 | 0 | 0 | 0 | 0 | 1737.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505323 | N-WW-NI-200220-Tain_STW-UV_System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-05-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1694.39 | 20128 | 21822.39 | 0 | 0 | 0 | 21822.39 | 0 | 0 | 0 | 0 | 21822.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505839 | N-WW-NI-200320-Campbeltown_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-20 |  | 2020-05-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 106.16 | 1047.6 | 1153.76 | 0 | 0 | 0 | 1153.76 | 0 | 0 | 0 | 0 | 1153.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506710 | N-WW-NI-200520-Kirkwall_HOW_STW_PST2_Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-10-16 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3779.76 | 3779.76 | 0 | 0 | 0 | 3779.76 | 0 | 0 | 0 | 0 | 3779.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506713 | N-WW-NI-200520-Oban_Corran_Parks_SPS_Gas_Sensors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4375.32 | 4375.32 | 0 | 0 | 0 | 4375.32 | 0 | 0 | 0 | 0 | 4375.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506712 | N-WW-NI-200520-Tobermory_Pier_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-09-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7901.38 | 7901.38 | 0 | 0 | 0 | 7901.38 | 0 | 0 | 0 | 0 | 7901.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509333 | N-WW-NI-201020-Balivanich_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-21 |  | 2020-10-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1125.02 | 1125.02 | 0 | 0 | 0 | 1125.02 | 0 | 0 | 0 | 0 | 1125.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509355 | N-WW-NI-201020-Bu_Point_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-21 |  | 2021-02-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2553.89 | 2553.89 | 46.11 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509359 | N-WW-NI-201020-Dornoch_Shore_Rd_SPS-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274.62 | 2274.62 | 7525.38 | 0 | 0 | 9800 | 0 | 0 | 0 | 0 | 9800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509350 | N-WW-NI-201020-Glenmore_Campsite_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-21 |  | 2020-11-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2211.15 | 2211.15 | 0 | 0 | 0 | 2211.15 | 0 | 0 | 0 | 0 | 2211.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509335 | N-WW-NI-201020-Kilmelford_STW-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-21 |  | 2020-11-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371.63 | 1371.63 | 0 | 0 | 0 | 1371.63 | 0 | 0 | 0 | 0 | 1371.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503883 | N-WW-NI-201119-Brora_STW-Outfall_Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-21 |  | 2020-04-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6800 | 16975.31 | 23775.31 | 0 | 0 | 0 | 23775.31 | 0 | 0 | 0 | 0 | 23775.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503895 | N-WW-NI-201119-Henderson_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-21 |  | 2020-01-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1909.99 | 103.94 | 2013.93 | 0 | 0 | 0 | 2013.93 | 0 | 0 | 0 | 0 | 2013.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503890 | N-WW-NI-201119-Kingussie_STW-Air_Compressor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-21 |  | 2020-08-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | -3003.74 | 196.26 | 0 | 0 | 0 | 196.26 | 0 | 0 | 0 | 0 | 196.26 | 90601.29 | [5 empty] | N | CM_WWI | 100%
503886 | N-WW-NI-201119-Ullapool_STW-Centrifuge_HMI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-21 |  | 2019-12-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | -980.36 | 13419.64 | 0 | 0 | 0 | 13419.64 | 0 | 0 | 0 | 0 | 13419.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509919 | N-WW-NI-201120-Acharacle_SPS-Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3551.4 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509908 | N-WW-NI-201120-Campbeltown_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-23 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7973.7 | 7973.7 | 26.3 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509906 | N-WW-NI-201120-Jamestown_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477.57 | 477.57 | 6822.42 | 0 | 0 | 7299.99 | 0 | 0 | 0 | 0 | 7299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509914 | N-WW-NI-201120-Kilmory_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-23 |  | 2021-03-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2294.6 | 2294.6 | 5.4 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509920 | N-WW-NI-201120-Liveras_Park_CSO-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219.16 | 219.16 | 3130.84 | 0 | 0 | 3350 | 0 | 0 | 0 | 0 | 3350 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509912 | N-WW-NI-201120-Strathpeffer_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-23 |  | 2021-03-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20951.04 | 20951.04 | -551.04 | 0 | 0 | 20400 | 0 | 0 | 0 | 0 | 20400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504456 | N-WW-NI-201219-Bowmore_STW-Aerators | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-20 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | -2998.65 | 18701.35 | 8348.65 | 0 | 0 | 27050 | 0 | 0 | 0 | 0 | 27050 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504461 | N-WW-NI-201219-Stornoway_STW-Roller_Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2019-12-24 |  | 2021-02-27 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | -123.8 | 3176.2 | 123.8 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504449 | N-WW-NI-201219-Tain_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-20 |  | 2020-10-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 120.28 | 6120.28 | 0 | 0 | 0 | 6120.28 | 0 | 0 | 0 | 0 | 6120.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504458 | N-WW-NI-201219-Thurso_STC-Sludge_Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-24 |  | 2020-02-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | -123.13 | 5276.87 | 0 | 0 | 0 | 5276.87 | 0 | 0 | 0 | 0 | 5276.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510445 | N-WW-NI-201220-Portmahomack_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1469.8 | 1469.8 | 30.2 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510444 | N-WW-NI-201220-Thurso_Harbour_SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838.32 | 1838.32 | 26261.7 | 0 | 0 | 28100.02 | 0 | 0 | 0 | 0 | 28100.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504770 | N-WW-NI-210120-Brora_Salt_St_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-03-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3498.27 | 0 | 3498.27 | 0 | 0 | 0 | 3498.27 | 0 | 0 | 0 | 0 | 3498.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504769 | N-WW-NI-210120-Halkirk_STW-FallRestraint | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-07-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 654.89 | 2054.89 | 0 | 0 | 0 | 2054.89 | 0 | 0 | 0 | 0 | 2054.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510820 | N-WW-NI-210121-Lerwick_Gremista_SPS-Fire Doors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-21 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.49 | 114.49 | 1635.52 | 0 | 0 | 1750.01 | 0 | 0 | 0 | 0 | 1750.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510819 | N-WW-NI-210121-Thurso_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-01-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3089.1 | 3089.1 | 10.9 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510823 | N-WW-NI-210121-Thurso_STC-Trap | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-21 |  | 2021-02-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2077.69 | 2077.69 | 72.32 | 0 | 0 | 2150.01 | 0 | 0 | 0 | 0 | 2150.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510826 | N-WW-NI-210121-Thurso_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3020.97 | 3020.97 | 129.03 | 0 | 0 | 3150 | 0 | 0 | 0 | 0 | 3150 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505869 | N-WW-NI-210320-Alness_Invergordon_STC-Lime_HotBox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-06-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 955.14 | 13566.01 | 14521.15 | 0 | 0 | 0 | 14521.15 | 0 | 0 | 0 | 0 | 14521.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505867 | N-WW-NI-210320-Teaninich_SPS-Diaphram_CS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-05-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 1164.24 | 1249.29 | 0 | 0 | 0 | 1249.29 | 0 | 0 | 0 | 0 | 1249.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506289 | N-WW-NI-210420-Aviemore_STW-Radio_Link | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5153.8 | 5153.8 | 0 | 0 | 0 | 5153.8 | 0 | 0 | 0 | 0 | 5153.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506295 | N-WW-NI-210420-Conon_Bridge_STW_Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4005.85 | 4005.85 | 0 | 0 | 0 | 4005.85 | 0 | 0 | 0 | 0 | 4005.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506291 | N-WW-NI-210420-Fassfern_FE_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-06-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2443.13 | 2443.13 | 0 | 0 | 0 | 2443.13 | 0 | 0 | 0 | 0 | 2443.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506294 | N-WW-NI-210420-Rosemarkie_Caravan_Park-SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-05-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2448.13 | 2448.13 | 0 | 0 | 0 | 2448.13 | 0 | 0 | 0 | 0 | 2448.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506736 | N-WW-NI-210520 - Tobermory Glengorm SPS - Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-06-08 | 2020-11-09 | 2020-12-08 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14663.31 | 14663.31 | 0 | 0 | 0 | 14663.31 | 0 | 0 | 0 | 0 | 14663.31 | 90601.29 | [5 empty] | N | WWNI | 100%
506753 | N-WW-NI-210520-Edderton_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-21 |  | 2020-07-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346.83 | 6346.83 | 0 | 0 | 0 | 6346.83 | 0 | 0 | 0 | 0 | 6346.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506739 | N-WW-NI-210520-Tain_STW_UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-22 |  | 2020-07-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3724.2 | 3724.2 | 0 | 0 | 0 | 3724.2 | 0 | 0 | 0 | 0 | 3724.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508311 | N-WW-NI-210820-Croy_STW-UV Bulbs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1495.33 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508316 | N-WW-NI-210820-Kilmory_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-21 |  | 2020-09-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1524.6 | 1524.6 | 0 | 0 | 0 | 1524.6 | 0 | 0 | 0 | 0 | 1524.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508315 | N-WW-NI-210820-Kishorn_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1401.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508313 | N-WW-NI-210820-Nairn_STW-UV Sensor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-21 |  | 2020-10-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1856.87 | 1856.87 | 0 | 0 | 0 | 1856.87 | 0 | 0 | 0 | 0 | 1856.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508310 | N-WW-NI-210820-Newtonmore_STW-Aerator Flails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-21 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3519.87 | 3519.87 | 5980.13 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 9500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508830 | N-WW-NI-21092020-Thurso_STC-Trap | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-22 |  | 2020-10-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1049 | 1049 | 0 | 0 | 0 | 1049 | 0 | 0 | 0 | 0 | 1049 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509377 | N-WW-NI-211020-Kirkwall HoW STC-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-21 |  | 2020-11-30 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7007.39 | 7007.39 | 0 | 0 | 0 | 7007.39 | 0 | 0 | 0 | 0 | 7007.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509374 | N-WW-NI-211020-Tobermory_STW-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-21 |  | 2020-10-31 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1435.17 | 1435.17 | 0 | 0 | 0 | 1435.17 | 0 | 0 | 0 | 0 | 1435.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510464 | N-WW-NI-211220-Ardersier_STW_Scraper_Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3824.93 | 3824.93 | 0 | 0 | 0 | 3824.93 | 0 | 0 | 0 | 0 | 3824.93 | 90601.29 | [5 empty] | N | WWNI | 100%
504800 | N-WW-NI-220120-Halkirk_STW-ControlPanel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-24 |  | 2020-04-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3109.06 | 0 | 3109.06 | 0 | 0 | 0 | 3109.06 | 0 | 0 | 0 | 0 | 3109.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504780 | N-WW-NI-220120-Inveraray_Burn_Brae_DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-02-05 |  | 2020-07-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 346.59 | 6646.59 | 0 | 0 | 0 | 6646.59 | 0 | 0 | 0 | 0 | 6646.59 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504797 | N-WW-NI-220120-Nairn_STW-Centrifuge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-24 |  | 2020-07-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 17120 | 709.29 | 17829.29 | 0 | 0 | 0 | 17829.29 | 0 | 0 | 0 | 0 | 17829.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504781 | N-WW-NI-220120-Newtonmore_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | -141.4 | 1958.6 | 0 | 0 | 0 | 1958.6 | 0 | 0 | 0 | 0 | 1958.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510834 | N-WW-NI-220121-Bettyhill_Sep_Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25246.34 | 25246.34 | 53.66 | 0 | 0 | 25300 | 0 | 0 | 0 | 0 | 25300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511371 | N-WW-NI-220221-Minard_STW-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1962.6 | 0 | 0 | 2099.98 | 0 | 0 | 0 | 0 | 2099.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511360 | N-WW-NI-220221-Nairn_STW-MLSS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.4 | 2451.4 | -51.4 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511367 | N-WW-NI-220221-Taynuilt_STW-SHT Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.49 | 200.49 | 1099.5 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505874 | N-WW-NI-220320-Rovahead_STC-Pumps_Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-05-15 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1105.35 | 1105.35 | 0 | 0 | 0 | 1105.35 | 0 | 0 | 0 | 0 | 1105.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511944 | N-WW-NI-220321-Kilmory_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-22 |  | 2021-06-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2227.98 | 2227.98 | -27.98 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511961 | N-WW-NI-220321-Stornoway_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-22 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151.23 | 151.23 | 1414.26 | 0 | 0 | 1565.49 | 0 | 0 | 0 | 0 | 1565.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506303 | N-WW-NI-220420-Kildary_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492.63 | 1492.63 | 0 | 0 | 0 | 1492.63 | 0 | 0 | 0 | 0 | 1492.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506304 | N-WW-NI-220420-Nairn_STW-Telemetry_CS_Pt1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540.65 | 1540.65 | 22009.35 | 0 | 0 | 23550 | 0 | 0 | 0 | 0 | 23550 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506305 | N-WW-NI-220420-Nairn_STW-Telemetry_CS_Pt2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540.65 | 1540.65 | 22009.35 | 0 | 0 | 23550 | 0 | 0 | 0 | 0 | 23550 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506309 | N-WW-NI-220420-Wick_STW-Odour_Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-05-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22891.47 | 22891.47 | 0 | 0 | 0 | 22891.47 | 0 | 0 | 0 | 0 | 22891.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507836 | N-WW-NI-220720 - Nairn WwTW - Replace sludge augers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-08-26 | 2020-09-25 | 2020-11-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42200.38 | 42200.38 | 0 | 0 | 0 | 42200.38 | 0 | 0 | 0 | 0 | 42200.38 | 90601.29 | [5 empty] | N | WWNI | 100%
507815 | N-WW-NI-220720-Kirkwall_Ayre Rd_SPS-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-22 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8273.53 | 8273.53 | 126.47 | 0 | 0 | 8400 | 0 | 0 | 0 | 0 | 8400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507817 | N-WW-NI-220720-Kirkwall_Weyland_Bay_SPS-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-22 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6387.23 | 6387.23 | 112.77 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508890 | N-WW-NI-22092020-Daliburgh_North_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2022-06-11 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3935.76 | 3935.76 | 0 | 0 | 0 | 3935.76 | 0 | 0 | 0 | 0 | 3935.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508886 | N-WW-NI-22092020-Dounby_STW-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8078.97 | 8078.97 | 0 | 0 | 0 | 8078.97 | 0 | 0 | 0 | 0 | 8078.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508891 | N-WW-NI-22092020-Dounby_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-23 |  | 2021-03-08 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4040.74 | 4040.74 | 0 | 0 | 0 | 4040.74 | 0 | 0 | 0 | 0 | 4040.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508892 | N-WW-NI-22092020-Durness_Smoo_STW-Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-09-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10381.83 | 10381.83 | 0 | 0 | 0 | 10381.83 | 0 | 0 | 0 | 0 | 10381.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508882 | N-WW-NI-22092020-Lochcarron_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3023.01 | 3023.01 | 0 | 0 | 0 | 3023.01 | 0 | 0 | 0 | 0 | 3023.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509418 | N-WW-NI-221020-N Ballachulish_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2877.61 | 2877.61 | 0 | 0 | 0 | 2877.61 | 0 | 0 | 0 | 0 | 2877.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509385 | N-WW-NI-221020-Oban_Corran_Park_SPS-NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-23 |  | 2021-02-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2079.76 | 2079.76 | 20.24 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510491 | N-WW-NI-221220- Gremista_SPS_Gas_Detection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4226 | 4226 | 280.5 | 0 | 0 | 4506.5 | 0 | 0 | 0 | 0 | 4506.5 | 90601.29 | [5 empty] | N | WWNI | 100%
510493 | N-WW-NI-221220-Balintore_STW_Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 902.8 | 902.8 | 12897.21 | 0 | 0 | 13800.01 | 0 | 0 | 0 | 0 | 13800.01 | 90601.29 | [5 empty] | N | WWNI | 100%
510475 | N-WW-NI-221220-Oban_STW_Belt_Press_Nr1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161.69 | 161.69 | 1538.31 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | WWNI | 100%
510471 | N-WW-NI-221220-Spean_Bridge_STW_Scum_Pump_Nr1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2202.36 | 2202.36 | -2.36 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | WWNI | 100%
510496 | N-WW-NI-221220-Stenness_SPS_Foul_Pump_Nr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975 | 0 | 0 | 975 | 0 | 0 | 0 | 0 | 975 | 90601.29 | [5 empty] | N | WWNI | 100%
504807 | N-WW-NI-230120-Gairloch_DOA-Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-01-24 |  | 2020-03-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2388.7 | 0 | 2388.7 | 0 | 0 | 0 | 2388.7 | 0 | 0 | 0 | 0 | 2388.7 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504819 | N-WW-NI-230120-Gairloch_DOA-MH_Horisdale | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-01-24 |  | 2020-03-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3280.52 | 0 | 3280.52 | 0 | 0 | 0 | 3280.52 | 0 | 0 | 0 | 0 | 3280.52 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504804 | N-WW-NI-230120-Lochcarron_Slumbay_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-24 |  | 2020-03-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5466.31 | 10466.31 | 0 | 0 | 0 | 10466.31 | 0 | 0 | 0 | 0 | 10466.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504817 | N-WW-NI-230120-Nethy_Bridge-MH_Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1893.5 | 1893.5 | 106.5 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504818 | N-WW-NI-230120-Voe_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-03-23 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1169.86 | 0 | 1169.86 | 130.14 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505372 | N-WW-NI-230220-Ayre_Rd_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-06-25 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287.45 | 1287.45 | 0 | 0 | 0 | 1287.45 | 0 | 0 | 0 | 0 | 1287.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505378 | N-WW-NI-230220-Edderton_STW-SAF_Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-09-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 2100.58 | 2257.59 | 0 | 0 | 0 | 2257.59 | 0 | 0 | 0 | 0 | 2257.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505376 | N-WW-NI-230220-Evanton_STW_FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 0 | 137.38 | 1962.62 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505377 | N-WW-NI-230220-Halkirk_STW-Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-03-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2152.73 | 0 | 2152.73 | 0 | 0 | 0 | 2152.73 | 0 | 0 | 0 | 0 | 2152.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505373 | N-WW-NI-230220-Oban_STW-Crane | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-05-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 191.21 | 1796.79 | 1988 | 0 | 0 | 0 | 1988 | 0 | 0 | 0 | 0 | 1988 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505371 | N-WW-NI-230220-Swainbost_SEP-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-04-14 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 220.4 | 980 | 1200.4 | 0 | 0 | 0 | 1200.4 | 0 | 0 | 0 | 0 | 1200.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511413 | N-WW-NI-230221-Alness_Invergordon_STC-DSEAR H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-01 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5900 | 0 | 0 | 6285.98 | 0 | 0 | 0 | 0 | 6285.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511405 | N-WW-NI-230221-Aviemore_STW-Centrifuge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366.36 | 366.36 | 5233.65 | 0 | 0 | 5600.01 | 0 | 0 | 0 | 0 | 5600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511403 | N-WW-NI-230221-Boath_House_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340.14 | 1340.14 | 59.86 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511399 | N-WW-NI-230221-Craigton_SPS-Flooring | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101.72 | 1101.72 | 98.28 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511396 | N-WW-NI-230221-Ft_Augustus_STW-Heater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1401.85 | 0 | 0 | 1499.98 | 0 | 0 | 0 | 0 | 1499.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511391 | N-WW-NI-230221-Inverness_DOA-Sewer IV3 8RA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490.65 | 490.65 | 7009.35 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511414 | N-WW-NI-230221-Kirkwall_HOW_STC-DSEAR H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-26 |  | 2021-05-23 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | -10455.15 | 0 | 0 | 5899.99 | 0 | 0 | 0 | 0 | 5899.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511415 | N-WW-NI-230221-Lerwick_Rovahead_STC-DSEAR H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-01 |  | 2021-05-23 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5500 | 0 | 0 | 5885.98 | 0 | 0 | 0 | 0 | 5885.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511392 | N-WW-NI-230221-Mallaig_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 973.61 | 973.61 | 13084.1 | 0 | 0 | 14057.71 | 0 | 0 | 0 | 0 | 14057.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511395 | N-WW-NI-230221-Nairn_STW- Augur | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2087.34 | 2087.34 | 62.66 | 0 | 0 | 2150 | 0 | 0 | 0 | 0 | 2150 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511389 | N-WW-NI-230221-Newtonmore_STW_Pump Spare | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.99 | 542.99 | 7757 | 0 | 0 | 8299.99 | 0 | 0 | 0 | 0 | 8299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511394 | N-WW-NI-230221-Port_Charlotte_SPS_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379.44 | 379.44 | 5420.55 | 0 | 0 | 5799.99 | 0 | 0 | 0 | 0 | 5799.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511401 | N-WW-NI-230221-Rosemarkie_Caravan_SPS-Relays | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1192.05 | 1192.05 | 107.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511417 | N-WW-NI-230221-Stornoway_STC-DSEAR H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-01 |  | 2021-05-23 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5900 | 0 | 0 | 6285.98 | 0 | 0 | 0 | 0 | 6285.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511416 | N-WW-NI-230221-Thurso_STC-DSEAR H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-01 |  | 2021-05-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210.28 | 1210.28 | 17289.72 | 0 | 0 | 18500 | 0 | 0 | 0 | 0 | 18500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505884 | N-WW-NI-230320 - Eochar 2 SPS - Create Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-06-17 | 2021-01-14 | 2021-06-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9997.36 | 9997.36 | 3284.25 | 0 | 0 | 13281.61 | 0 | 0 | 0 | 0 | 13281.61 | 90601.29 | [5 empty] | N | WWNI | 100%
505904 | N-WW-NI-230320-Glenachulish_ST-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-25 |  | 2020-04-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 119.07 | 1765.9 | 1884.97 | 0 | 0 | 0 | 1884.97 | 0 | 0 | 0 | 0 | 1884.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505897 | N-WW-NI-230320-Tarbert_STW- Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-09-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 298.23 | 1453.7 | 1751.93 | 0 | 0 | 0 | 1751.93 | 0 | 0 | 0 | 0 | 1751.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505896 | N-WW-NI-230320-Teaninich_SPS-Transfer_Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 0 | 85.05 | 1214.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511981 | N-WW-NI-230321-Ballachulish_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149.89 | 149.89 | 1585.74 | 0 | 0 | 1735.63 | 0 | 0 | 0 | 0 | 1735.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511985 | N-WW-NI-230321-Dalwhinnie_STW-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392.52 | 392.52 | 5142.84 | 0 | 0 | 5535.36 | 0 | 0 | 0 | 0 | 5535.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511987 | N-WW-NI-230321-Fortrose_STW-Plinth | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140.65 | 140.65 | 1842.84 | 0 | 0 | 1983.49 | 0 | 0 | 0 | 0 | 1983.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511978 | N-WW-NI-230321-Kiltarlity_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5057.16 | 0 | 0 | 5443.14 | 0 | 0 | 0 | 0 | 5443.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511977 | N-WW-NI-230321-Muir_of_Ord_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1269.16 | 1269.16 | 18130.84 | 0 | 0 | 19400 | 0 | 0 | 0 | 0 | 19400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511991 | N-WW-NI-230321-North_Kessock_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.43 | 222.43 | 2914.26 | 0 | 0 | 3136.69 | 0 | 0 | 0 | 0 | 3136.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506336 | N-WW-NI-230420 - Laxay West SPS - Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-05-05 | 2022-08-11 | 2022-11-17 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1461 | 1461 | 48539.31 | 0 | 0 | 50000.31 | 0 | 0 | 0 | 0 | 50000.31 | 90601.29 | [5 empty] | N | WWNI | 100%
506339 | N-WW-NI-230420-Iochdar_STW-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-06-17 | 2021-01-14 | 2021-06-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35392.36 | 35392.36 | 14453.34 | 0 | 0 | 49845.7 | 0 | 0 | 0 | 0 | 49845.7 | 90601.29 | [5 empty] | N | WWNI | 100%
506333 | N-WW-NI-230420-Lerwick_Rovahead_STW-Gas_Detection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6551 | 6551 | 0 | 0 | 0 | 6551 | 0 | 0 | 0 | 0 | 6551 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506329 | N-WW-NI-230420-Port_Ellen_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-23 |  | 2020-07-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2637.36 | 2637.36 | 0 | 0 | 0 | 2637.36 | 0 | 0 | 0 | 0 | 2637.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507320 | N-WW-NI-230620-Marine_Tce_SPS-Lid | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-09-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4317.2 | 4317.2 | 0 | 0 | 0 | 4317.2 | 0 | 0 | 0 | 0 | 4317.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507313 | N-WW-NI-230620-Nairn_SWO_AT_Viaduct_CSO-Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-24 |  | 2021-02-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4629.65 | 4629.65 | 70.35 | 0 | 0 | 4700 | 0 | 0 | 0 | 0 | 4700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507309 | N-WW-NI-230620-Ship_Inn_SPS-Lid Braces | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-11-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1205.93 | 1205.93 | 0 | 0 | 0 | 1205.93 | 0 | 0 | 0 | 0 | 1205.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507851 | N-WW-NI-230720-Grantown_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-08-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12305.33 | 12305.33 | 0 | 0 | 0 | 12305.33 | 0 | 0 | 0 | 0 | 12305.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508918 | N-WW-NI-23092020-Broadford_STW-Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2442.66 | 2442.66 | 0 | 0 | 0 | 2442.66 | 0 | 0 | 0 | 0 | 2442.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508916 | N-WW-NI-23092020-Dounby_STW-Buliding | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-23 |  | 2021-03-22 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6528.5 | 6528.5 | 0 | 0 | 0 | 6528.5 | 0 | 0 | 0 | 0 | 6528.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508899 | N-WW-NI-23092020-Inveraray_Barn_Brae_SPS-Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1277.16 | 1277.16 | 0 | 0 | 0 | 1277.16 | 0 | 0 | 0 | 0 | 1277.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508897 | N-WW-NI-23092020-Kilmore_STW-Inlet | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.66 | 1258.66 | 0 | 0 | 0 | 1258.66 | 0 | 0 | 0 | 0 | 1258.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508901 | N-WW-NI-23092020-Mallaig_STW-Scrapers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.95 | 1377.95 | 0 | 0 | 0 | 1377.95 | 0 | 0 | 0 | 0 | 1377.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508900 | N-WW-NI-23092020-Tynribbie_STW-Sample Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1282.56 | 1282.56 | 0 | 0 | 0 | 1282.56 | 0 | 0 | 0 | 0 | 1282.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509921 | N-WW-NI-231120-Acharacle_SPS-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.94 | 107.94 | 1542.06 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 1650 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509922 | N-WW-NI-231120-Ft_William_Distillery_SPS-Doors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.94 | 1532.94 | 117.06 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 1650 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509934 | N-WW-NI-231120-Gairloch_An_Ard_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-23 |  | 2021-03-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3115.82 | 3115.82 | 134.18 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 3250 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509954 | N-WW-NI-231120-Kyle_Pladaig_Rd_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-26 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 4018.68 | 0 | 0 | 4299.99 | 0 | 0 | 0 | 0 | 4299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509952 | N-WW-NI-231120-Stornoway_STC-Belt Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-26 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3328.91 | 3328.91 | 271.09 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509940 | N-WW-NI-231120-Ullapool_STW-Guide Rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-23 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454.27 | 1454.27 | 45.72 | 0 | 0 | 1499.99 | 0 | 0 | 0 | 0 | 1499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504838 | N-WW-NI-240120-Nairn_3 Sites-Inlet_Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-06-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4400 | -109.95 | 4290.05 | 0 | 0 | 0 | 4290.05 | 0 | 0 | 0 | 0 | 4290.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504826 | N-WW-NI-240120-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-01-24 |  | 2020-06-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | -342.61 | 8657.39 | 0 | 0 | 0 | 8657.39 | 0 | 0 | 0 | 0 | 8657.39 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506343 | N-WWNI-240220 - Barvas Crossroads SPS - Site Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-05-19 | 2022-09-30 | 2023-01-06 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7145.24 | 7145.24 | 47854.76 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 55000 | 90601.29 | [5 empty] | N | WWNI | 100%
505393 | N-WW-NI-240220-Balivanich_STW-NRVs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-25 |  | 2020-08-24 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 180.95 | 2272.8 | 2453.75 | 0 | 0 | 0 | 2453.75 | 0 | 0 | 0 | 0 | 2453.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505392 | N-WW-NI-240220-Stornoway_DOA-Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-05-01 |  | 2020-04-14 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3279 | 3279 | 0 | 0 | 0 | 3279 | 0 | 0 | 0 | 0 | 3279 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505391 | N-WW-NI-240220-Strathpeffer_STW-Safety_Gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-25 |  | 2020-07-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 3019.02 | 3267.62 | 0 | 0 | 0 | 3267.62 | 0 | 0 | 0 | 0 | 3267.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511435 | N-WW-NI-240221-Oban_CorranPark_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619.18 | 619.18 | 7080.8 | 0 | 0 | 7699.98 | 0 | 0 | 0 | 0 | 7699.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511434 | N-WW-NI-240221-Oban_STW-Belt Pres | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 878.75 | 878.75 | 11671.25 | 0 | 0 | 12550 | 0 | 0 | 0 | 0 | 12550 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511441 | N-WW-NI-240221-Tobermory_STW-Access Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3155.51 | 3155.51 | 294.49 | 0 | 0 | 3450 | 0 | 0 | 0 | 0 | 3450 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505920 | N-WW-NI-240320-Oban_STW--Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-25 |  | 2020-10-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 768.3 | 10173.86 | 10942.16 | 0 | 0 | 0 | 10942.16 | 0 | 0 | 0 | 0 | 10942.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512004 | N-WW-NI-240321-Alness_Invergordon _STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2117.86 | 2117.86 | 82.14 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512009 | N-WW-NI-240321-Dingwall_STW-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.47 | 150.47 | 1971.42 | 0 | 0 | 2121.89 | 0 | 0 | 0 | 0 | 2121.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511999 | N-WW-NI-240321-Kirkwall_HoW-STC-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-24 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421.96 | 421.96 | 5528.58 | 0 | 0 | 5950.54 | 0 | 0 | 0 | 0 | 5950.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511994 | N-WW-NI-240321-Spey_Valley-STW-Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457.94 | 457.94 | 6000 | 0 | 0 | 6457.94 | 0 | 0 | 0 | 0 | 6457.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506344 | N-WW-NI-240420 - Glaitness SPS - Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-07-14 | 2022-08-04 | 2022-11-10 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 35000.04 | 0 | 0 | 50000.04 | 0 | 0 | 0 | 0 | 50000.04 | 90601.29 | [5 empty] | N | WWNI | 100%
506349 | N-WW-NI-240420-Kilmory_Inlet_SPS-Guiderails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507323 | N-WW-NI-240620-Broadford_Ind_Est_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-24 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20868.11 | 20868.11 | 5931.89 | 0 | 0 | 26800 | 0 | 0 | 0 | 0 | 26800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507325 | N-WW-NI-240620-Conon_Bridge_STW-Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-24 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210.95 | 2210.95 | -10.95 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507327 | N-WW-NI-240620-Gairloch_Lonemore_SPS_Fence & Gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-08-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1971.24 | 1971.24 | 0 | 0 | 0 | 1971.24 | 0 | 0 | 0 | 0 | 1971.24 | 90601.29 | [5 empty] | N | WWNI | 100%
507331 | N-WW-NI-240620-Oban_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-24 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899.25 | 899.25 | 12000.75 | 0 | 0 | 12900 | 0 | 0 | 0 | 0 | 12900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507874 | N-WW-NI-240720-Dingwall_Jubilee_Pk_SPS-Civils Hazards | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-02-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3107.06 | 3107.06 | 0 | 0 | 0 | 3107.06 | 0 | 0 | 0 | 0 | 3107.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507853 | N-WW-NI-240720-Grantown_STW-Sensors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-08-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5326.44 | 5326.44 | 0 | 0 | 0 | 5326.44 | 0 | 0 | 0 | 0 | 5326.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507870 | N-WW-NI-240720-Papigoe_SPS-Flow Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-08-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1244.96 | 1244.96 | 0 | 0 | 0 | 1244.96 | 0 | 0 | 0 | 0 | 1244.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507873 | N-WW-NI-240720-Stornoway_STW_DO_Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-08-14 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1015.23 | 1015.23 | 0 | 0 | 0 | 1015.23 | 0 | 0 | 0 | 0 | 1015.23 | 90601.29 | [5 empty] | N | WWNI | 100%
508939 | N-WW-NI-24092020-Inverbreakie_SPS-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-24 |  | 2020-10-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2531.88 | 2531.88 | 0 | 0 | 0 | 2531.88 | 0 | 0 | 0 | 0 | 2531.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508957 | N-WW-NI-24092020-Stornoway_STW-Auto Sampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-24 |  | 2020-10-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7114.1 | 7114.1 | 0 | 0 | 0 | 7114.1 | 0 | 0 | 0 | 0 | 7114.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508937 | N-WW-NI-24092020-Tain_STW-Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-24 |  | 2021-03-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759.3 | 1759.3 | 0 | 0 | 0 | 1759.3 | 0 | 0 | 0 | 0 | 1759.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508958 | N-WW-NI-240920-Helmsdale_STW_Splitter_Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-24 |  | 2020-11-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4942.35 | 4942.35 | 0 | 0 | 0 | 4942.35 | 0 | 0 | 0 | 0 | 4942.35 | 90601.29 | [5 empty] | N | WWNI | 100%
503945 | N-WW-NI-241119-Thurso_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1778.61 | 0 | 1778.61 | 0 | 0 | 0 | 1778.61 | 0 | 0 | 0 | 0 | 1778.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504499 | N-WW-NI-241219- Fort Augustus WWTW (North)Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | -92725.76 | 7274.24 | 93048.86 | 0 | 0 | 100323.1 | 0 | 0 | 0 | 0 | 100323.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504500 | N-WW-NI-241219-Cromarty Sutors WWTW (North) -Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-24 |  | 2021-05-01 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | -93230.4 | 6769.6 | 93230.41 | 0 | 0 | 100000.01 | 0 | 0 | 0 | 0 | 100000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510509 | N-WW-NI-241220-Leurbost_East_SPS_Pump_Nr1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-31 |  | 2021-02-20 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276.7 | 1276.7 | 23.31 | 0 | 0 | 1300.01 | 0 | 0 | 0 | 0 | 1300.01 | 90601.29 | [5 empty] | N | WWNI | 100%
504839 | N-WW-NI-250120-Nairn_3 Sites-Inlet_Screens Pt2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-02-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4540.37 | 0 | 4540.37 | 0 | 0 | 0 | 4540.37 | 0 | 0 | 0 | 0 | 4540.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510864 | N-WW-NI-250121-Bonawe_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339.03 | 339.03 | 3960.96 | 0 | 0 | 4299.99 | 0 | 0 | 0 | 0 | 4299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510859 | N-WW-NI-250121-Kiltarllity_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.4 | 0 | 0 | 1399.99 | 0 | 0 | 0 | 0 | 1399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510858 | N-WW-NI-250121-Kirkhill_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-25 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.4 | 0 | 0 | 1399.99 | 0 | 0 | 0 | 0 | 1399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510865 | N-WW-NI-250121-Lerwick_Rovahead_STW-Gratings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-27 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129.93 | 2129.93 | 70.08 | 0 | 0 | 2200.01 | 0 | 0 | 0 | 0 | 2200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510861 | N-WW-NI-250121-Taynuilt_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607.25 | 607.25 | 7792.76 | 0 | 0 | 8400.01 | 0 | 0 | 0 | 0 | 8400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510868 | N-WW-NI-250121-Watten_STW-Dosing System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139.5 | 1139.5 | 60.48 | 0 | 0 | 1199.98 | 0 | 0 | 0 | 0 | 1199.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505396 | N-WW-NI-250220-Eochar_SPS- Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-25 |  | 2020-08-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 105.33 | 1191.78 | 1297.11 | 0 | 0 | 0 | 1297.11 | 0 | 0 | 0 | 0 | 1297.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505394 | N-WW-NI-250220-Eochar_SPS-Wetwell | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-08-21 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 40.3 | 2666.45 | 2706.75 | 0 | 0 | 0 | 2706.75 | 0 | 0 | 0 | 0 | 2706.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511476 | N-WW-NI-250221-Tain_STW-Access Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3551.4 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512039 | N-WW-NI-250321-Boat_of_Garten_STW-WW System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.89 | 215.89 | 2828.58 | 0 | 0 | 3044.47 | 0 | 0 | 0 | 0 | 3044.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512036 | N-WW-NI-250321-Grantown_STW-Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.89 | 215.89 | 2828.58 | 0 | 0 | 3044.47 | 0 | 0 | 0 | 0 | 3044.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512041 | N-WW-NI-250321-Grantown_STW-Slip Ring | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392.52 | 392.52 | 5142.84 | 0 | 0 | 5535.36 | 0 | 0 | 0 | 0 | 5535.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512034 | N-WW-NI-250321-Kildary_STW-Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19302.19 | 19302.19 | 97.81 | 0 | 0 | 19400 | 0 | 0 | 0 | 0 | 19400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512037 | N-WW-NI-250321-Kirkhill_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2142.84 | 0 | 0 | 2306.39 | 0 | 0 | 0 | 0 | 2306.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512043 | N-WW-NI-250321-Laggan_Bridge_Lids | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1542.84 | 0 | 0 | 1660.6 | 0 | 0 | 0 | 0 | 1660.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512030 | N-WW-NI-250321-Lochcarron_STW-Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562.62 | 562.62 | 7371.42 | 0 | 0 | 7934.04 | 0 | 0 | 0 | 0 | 7934.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506806 | N-WW-NI-250520-Alness_Invergordon _STC-Conveyor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-25 |  | 2020-11-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5957.7 | 5957.7 | 0 | 0 | 0 | 5957.7 | 0 | 0 | 0 | 0 | 5957.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506814 | N-WW-NI-250520-Breasclete_STW_Cover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-25 |  | 2020-06-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1067.3 | 1067.3 | 0 | 0 | 0 | 1067.3 | 0 | 0 | 0 | 0 | 1067.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506789 | N-WW-NI-250520-Dornoch_STW_Poly_Unit_Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-25 |  | 2020-06-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126.51 | 1126.51 | 0 | 0 | 0 | 1126.51 | 0 | 0 | 0 | 0 | 1126.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506790 | N-WW-NI-250520-Nairn_STW-NRV_Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-25 |  | 2020-07-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2497.18 | 2497.18 | 0 | 0 | 0 | 2497.18 | 0 | 0 | 0 | 0 | 2497.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506801 | N-WW-NI-250520-Oban_STW-Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-25 |  | 2020-06-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1748.94 | 1748.94 | 0 | 0 | 0 | 1748.94 | 0 | 0 | 0 | 0 | 1748.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506800 | N-WW-NI-250520-Taynuilt_STW-Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-25 |  | 2020-07-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1437.72 | 1437.72 | 0 | 0 | 0 | 1437.72 | 0 | 0 | 0 | 0 | 1437.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507379 | N-WW-NI-250620-Gairloch_STW-UV Spares | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-26 |  | 2020-08-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8599.71 | 8599.71 | 0 | 0 | 0 | 8599.71 | 0 | 0 | 0 | 0 | 8599.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507358 | N-WW-NI-250620-Taynuilt_STW-Hopper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-26 |  | 2020-09-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3145.55 | 3145.55 | 0 | 0 | 0 | 3145.55 | 0 | 0 | 0 | 0 | 3145.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508371 | N-WW-NI-250820-Campbeltown_STW-Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1855.45 | 1855.45 | -55.45 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508372 | N-WW-NI-250820-Great_Glen_Waterparks_STW-RBC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-25 |  | 2020-10-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2576.92 | 2576.92 | 0 | 0 | 0 | 2576.92 | 0 | 0 | 0 | 0 | 2576.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508374 | N-WW-NI-250820-Oban_Gallanach-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-10-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1826.28 | 1826.28 | 0 | 0 | 0 | 1826.28 | 0 | 0 | 0 | 0 | 1826.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503963 | N-WW-NI-251119-Broadford_STW-Dewaterer_Vent | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-26 |  | 2020-09-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 965.76 | 7965.76 | 0 | 0 | 0 | 7965.76 | 0 | 0 | 0 | 0 | 7965.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503969 | N-WW-NI-251119-Tobermory_STW-Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-26 |  | 2020-03-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 4991.11 | 0 | 4991.11 | 0 | 0 | 0 | 4991.11 | 0 | 0 | 0 | 0 | 4991.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503973 | N-WW-NI251119-Wick_STW-Pump_Guiderails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-26 |  | 2020-03-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 4310.38 | 0 | 4310.38 | 0 | 0 | 0 | 4310.38 | 0 | 0 | 0 | 0 | 4310.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509982 | N-WW-NI-251120-Halkirk_Braal_Rd_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043.32 | 1043.32 | 56.68 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510005 | N-WW-NI-251120-Thurso_STC-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-26 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.94 | 107.94 | 1542.06 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 1650 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510006 | N-WW-NI-251120-Wick_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-26 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.96 | 71.96 | 1028.04 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504844 | N-WW-NI-260120-Alness_Invergordon_STW-Autosampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-03-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2334.11 | 0 | 2334.11 | 0 | 0 | 0 | 2334.11 | 0 | 0 | 0 | 0 | 2334.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504841 | N-WW-NI-260120-Campbeltown_Kinloch _Park_SPS-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-01-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1149.66 | 0 | 1149.66 | 0 | 0 | 0 | 1149.66 | 0 | 0 | 0 | 0 | 1149.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504843 | N-WW-NI-260120-Cawdor_STW-MeterCabling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-08-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -193.44 | 1806.56 | 0 | 0 | 0 | 1806.56 | 0 | 0 | 0 | 0 | 1806.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504840 | N-WW-NI-260120-Duror_STW-Cabling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-03-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2143.99 | 0 | 2143.99 | 0 | 0 | 0 | 2143.99 | 0 | 0 | 0 | 0 | 2143.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504847 | N-WW-NI-260120-Evanton_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-02-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | -114.69 | 3435.31 | 0 | 0 | 0 | 3435.31 | 0 | 0 | 0 | 0 | 3435.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504848 | N-WW-NI-260120-Kingussie_West_CSO-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-27 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -553.16 | 1446.84 | 553.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504842 | N-WW-NI-260120-Lerwick_Gremista_SPS-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-05-11 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | 2900 | 0 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504846 | N-WW-NI-260120-Stornoway_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-01-27 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | -3224.3 | 225.7 | 3224.3 | 0 | 0 | 3450 | 0 | 0 | 0 | 0 | 3450 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510903 | N-WW-NI-260121-Ardersier_Mid_Coul_SPS-NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2021-03-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1410.07 | 1410.07 | 188.08 | 0 | 0 | 1598.15 | 0 | 0 | 0 | 0 | 1598.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510897 | N-WW-NI-260121-Sletts_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3008.2 | 3008.2 | 91.8 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505432 | N-WW-NI-260220-Wick_STW-Inlet_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-03-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1160.62 | 0 | 1160.62 | 0 | 0 | 0 | 1160.62 | 0 | 0 | 0 | 0 | 1160.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511498 | N-WW-NI-260221_Kirkwall_Weyland_Bay_SPS_Emergency Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-26 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 5500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505944 | N-WW-NI-260320- Oban Corran Park SPS - Replace Inlet Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-11-23 | 2022-07-11 | 2022-10-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5820.26 | 5820.26 | 23232.94 | 0 | 0 | 29053.2 | 0 | 0 | 0 | 0 | 29053.2 | 90601.29 | [5 empty] | N | WWNI | 100%
512060 | N-WW-NI-260321-Bowmore_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418.69 | 418.69 | 5485.74 | 0 | 0 | 5904.43 | 0 | 0 | 0 | 0 | 5904.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512062 | N-WW-NI-260321-Clachan_Balvicar_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1447.94 | 1447.94 | -147.94 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512056 | N-WW-NI-260321-Kilmory_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277.59 | 277.59 | 2314.26 | 0 | 0 | 2591.85 | 0 | 0 | 0 | 0 | 2591.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506821 | N-WW-NI-260520-Kilmore_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-26 |  | 2020-06-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2186.57 | 2186.57 | 0 | 0 | 0 | 2186.57 | 0 | 0 | 0 | 0 | 2186.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507386 | N-WW-NI-260620-Grantown_STW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-09-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1944.78 | 1944.78 | 0 | 0 | 0 | 1944.78 | 0 | 0 | 0 | 0 | 1944.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507396 | N-WW-NI-260620-Oban_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-09-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12879.57 | 12879.57 | 0 | 0 | 0 | 12879.57 | 0 | 0 | 0 | 0 | 12879.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508399 | N-WW-NI-260820-Kirkhill_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-10-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2247.58 | 2247.58 | 0 | 0 | 0 | 2247.58 | 0 | 0 | 0 | 0 | 2247.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508396 | N-WW-NI-260820-Tobermory_Pier_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-08-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7862.12 | 7862.12 | 0 | 0 | 0 | 7862.12 | 0 | 0 | 0 | 0 | 7862.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508401 | N-WW-NI-260820-Victoria_Place_SPS-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-27 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510011 | N-WW-NI-261120-Kiltarlity_STW-Guiderails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-26 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359.81 | 359.81 | 5140.18 | 0 | 0 | 5499.99 | 0 | 0 | 0 | 0 | 5499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510025 | N-WW-NI-261120-Kinlochleven_STW-Lightning | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-27 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3458.79 | 3458.79 | -308.8 | 0 | 0 | 3149.99 | 0 | 0 | 0 | 0 | 3149.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510010 | N-WW-NI-261120-Wick_STW-Monitors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-26 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4584.65 | 4584.65 | 65.34 | 0 | 0 | 4649.99 | 0 | 0 | 0 | 0 | 4649.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504875 | N-WW-NI-270120-Appin_DOA -Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1421.76 | 0 | 1421.76 | 0 | 0 | 0 | 1421.76 | 0 | 0 | 0 | 0 | 1421.76 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504862 | N-WW-NI-270120-Aviemore_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 7400 | -2774.09 | 4625.91 | 0 | 0 | 0 | 4625.91 | 0 | 0 | 0 | 0 | 4625.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504863 | N-WW-NI-270120-Kingussie_DOA-MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -552.71 | 1447.29 | 552.71 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504864 | N-WW-NI-270120-Portmahomack_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1470.45 | 0 | 1470.45 | 0 | 0 | 0 | 1470.45 | 0 | 0 | 0 | 0 | 1470.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510916 | N-WW-NI-270121-Boat_of_Garten_STW-SAF Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 4300 | 0 | 0 | 4581.31 | 0 | 0 | 0 | 0 | 4581.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510913 | N-WW-NI-270121-Croy_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10700 | 0 | 0 | 11400 | 0 | 0 | 0 | 0 | 11400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510911 | N-WW-NI-270121-Duackside_SEP-Storm Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-05-01 |  | 2021-03-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2213.26 | 2213.26 | 237.2 | 0 | 0 | 2450.46 | 0 | 0 | 0 | 0 | 2450.46 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510917 | N-WW-NI-270121-Grantown_STW-Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3050.34 | 3050.34 | 49.66 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505435 | N-WW-NI-270220-Benderloch_STW-Gate_SafetyRepairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-06-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 270.66 | 4146.98 | 4417.64 | 0 | 0 | 0 | 4417.64 | 0 | 0 | 0 | 0 | 4417.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505450 | N-WW-NI-270220-Oban_STW-Alarm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-28 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 27.66 | 0 | 27.66 | 2122.34 | 0 | 0 | 2150 | 0 | 0 | 0 | 0 | 2150 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505438 | N-WW-NI-270220-Oban_STW-Pipework_Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-09-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6556.54 | 6556.54 | 0 | 0 | 0 | 6556.54 | 0 | 0 | 0 | 0 | 6556.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505451 | N-WW-NI-270220-Stornoway_Lower_Sandwick_SPS-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-28 |  | 2020-06-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 241.46 | 3751.54 | 3993 | 0 | 0 | 0 | 3993 | 0 | 0 | 0 | 0 | 3993 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505440 | N-WW-NI-270220-Stornoway_STW-Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-28 |  | 2021-02-10 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 241.46 | 3511.54 | 3753 | 547 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506006 | N-WW-NI-270320-Alness_Teaninich_SPS_Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-31 |  | 2020-04-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4926.25 | 4926.25 | 0 | 0 | 0 | 4926.25 | 0 | 0 | 0 | 0 | 4926.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505976 | N-WW-NI-270320-Kirkwall_Weyland_Bay_SPS_Gas_Detection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-04-10 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4283 | 4283 | 0 | 0 | 0 | 4283 | 0 | 0 | 0 | 0 | 4283 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506367 | N-WW-NI-270420-Finstown_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-07-21 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2828.4 | 2828.4 | 0 | 0 | 0 | 2828.4 | 0 | 0 | 0 | 0 | 2828.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506362 | N-WW-NI-270420-Grantown_STW-Scraper_Arm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-27 |  | 2020-07-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900.63 | 1900.63 | 0 | 0 | 0 | 1900.63 | 0 | 0 | 0 | 0 | 1900.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506354 | N-WW-NI-270420-HoW_Kirkwall_STC-Thermoblender | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-08-27 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27899 | 27899 | 9261 | 0 | 0 | 37160 | 0 | 0 | 0 | 0 | 37160 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506352 | N-WW-NI-270420-HoW_Kirkwall_STC-WW_Booster | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-05-25 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016.4 | 1016.4 | 0 | 0 | 0 | 1016.4 | 0 | 0 | 0 | 0 | 1016.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506862 | N-WW-NI-270520-Alness_Invergordon _STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-06-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2034.38 | 2034.38 | 0 | 0 | 0 | 2034.38 | 0 | 0 | 0 | 0 | 2034.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507899 | N-WW-NI-270720-Brora_STW-Outfall Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-08-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425.16 | 1425.16 | 0 | 0 | 0 | 1425.16 | 0 | 0 | 0 | 0 | 1425.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507905 | N-WW-NI-270720-Stornoway_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-08-27 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3035.55 | 3035.55 | 0 | 0 | 0 | 3035.55 | 0 | 0 | 0 | 0 | 3035.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508435 | N-WW-NI-270820-Aviemore_STW-HMI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-10-02 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5902.54 | 5902.54 | 0 | 0 | 0 | 5902.54 | 0 | 0 | 0 | 0 | 5902.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508436 | N-WW-NI-270820-Cawdor_STW-Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-28 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2201.19 | 2201.19 | 98.81 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508412 | N-WW-NI-270820-Newtonmore_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-11-11 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4591.32 | 4591.32 | 0 | 0 | 0 | 4591.32 | 0 | 0 | 0 | 0 | 4591.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508411 | N-WW-NI-270820-Tobermory_Pier_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-11-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37231.11 | 37231.11 | 0 | 0 | 0 | 37231.11 | 0 | 0 | 0 | 0 | 37231.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509499 | N-WW-NI-271020-Carrbridge_STW-Telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-27 |  | 2021-04-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8631.16 | 8631.16 | 68.84 | 0 | 0 | 8700 | 0 | 0 | 0 | 0 | 8700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509486 | N-WW-NI-271020-Dunvegan_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-27 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3123.26 | 3123.26 | 0 | 0 | 0 | 3123.26 | 0 | 0 | 0 | 0 | 3123.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509485 | N-WW-NI-271020-Nairn_STW-Bldng | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-27 |  | 2020-11-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4362.31 | 4362.31 | 0 | 0 | 0 | 4362.31 | 0 | 0 | 0 | 0 | 4362.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504004 | N-WW-NI-271119-Applecross_Toilet_SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | -1962.62 | 137.38 | 1962.62 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504027 | N-WW-NI-271119-Oban_Stevenson_St_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-01-20 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 4319.26 | 0 | 4319.26 | 0 | 0 | 0 | 4319.26 | 0 | 0 | 0 | 0 | 4319.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504020 | N-WW-NI-271119-Strathpeffer_Jamestown_ SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-09 |  | 2020-04-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | -113.4 | 5886.6 | 0 | 0 | 0 | 5886.6 | 0 | 0 | 0 | 0 | 5886.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504006 | N-WW-NI-271119-Wick_STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-03-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | -466.5 | 6533.5 | 0 | 0 | 0 | 6533.5 | 0 | 0 | 0 | 0 | 6533.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504040 | N-WW-NI-271119-Wick_STW _Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2019-12-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1533.83 | 0 | 1533.83 | 0 | 0 | 0 | 1533.83 | 0 | 0 | 0 | 0 | 1533.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504506 | N-WW-NI-271219-Crowlista_STW-Tipping_Tray | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-06 |  | 2020-06-29 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | -176.11 | 6323.89 | 0 | 0 | 0 | 6323.89 | 0 | 0 | 0 | 0 | 6323.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504505 | N-WW-NI-271219-Halkirk_STW-Sludge_HT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-06 |  | 2020-06-24 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1720 | 44.78 | 1764.78 | 0 | 0 | 0 | 1764.78 | 0 | 0 | 0 | 0 | 1764.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510955 | N-WW-NI-280121-Aultbea_Cemetry_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-01 |  | 2021-04-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4462.63 | 4462.63 | 387.4 | 0 | 0 | 4850.03 | 0 | 0 | 0 | 0 | 4850.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510957 | N-WW-NI-280121-Bonar_Bridge_Ardgay_STW-Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3668.93 | 3668.93 | 81.07 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 3750 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505463 | N-WW-NI-280220-Alness_Invergordon_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-02 |  | 2020-11-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 896.26 | 12793.39 | 13689.65 | 0 | 0 | 0 | 13689.65 | 0 | 0 | 0 | 0 | 13689.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505465 | N-WW-NI-280220-Bowmorre_STW-Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-02 |  | 2020-08-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 2348.8 | 2518.89 | 0 | 0 | 0 | 2518.89 | 0 | 0 | 0 | 0 | 2518.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505455 | N-WW-NI-280220-Kirkwall_Weyland_Bay_SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505464 | N-WW-NI-280220-Thurso_Harbour_Transfer_SPS-Telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-02 |  | 2020-04-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2973.26 | 0 | 2973.26 | 0 | 0 | 0 | 2973.26 | 0 | 0 | 0 | 0 | 2973.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506382 | N-WW-NI-280420-Conon_Bridge_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-29 |  | 2020-08-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11959.13 | 11959.13 | 0 | 0 | 0 | 11959.13 | 0 | 0 | 0 | 0 | 11959.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506895 | N-WW-NI-280520-Broadford_STW_PLC_Card | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-06-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997.5 | 997.5 | 0 | 0 | 0 | 997.5 | 0 | 0 | 0 | 0 | 997.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506885 | N-WW-NI-280520-Cumlodden_North_Sep-Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-06-12 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584.09 | 1584.09 | 0 | 0 | 0 | 1584.09 | 0 | 0 | 0 | 0 | 1584.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506876 | N-WW-NI-280520-Sordale_STW-Legal Fees | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684.5 | 684.5 | 1580.5 | 0 | 0 | 2265 | 0 | 0 | 0 | 0 | 2265 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506897 | N-WW-NI-280520-Tobermory_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-29 |  | 2020-06-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2182.8 | 2182.8 | 0 | 0 | 0 | 2182.8 | 0 | 0 | 0 | 0 | 2182.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507917 | N-WW-NI-280720 - Kincraig WwTW - Aeration | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-12-01 | 2021-04-12 | 2021-11-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11450.11 | 11450.11 | 94519.85 | 0 | 0 | 105969.96 | 0 | 0 | 0 | 0 | 105969.96 | 90601.29 | [5 empty] | N | WWNI | 100%
507928 | N-WW-NI-280720-Meadows_SPS-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-30 |  | 2021-03-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3193.35 | 3193.35 | 176.65 | 0 | 0 | 3370 | 0 | 0 | 0 | 0 | 3370 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508980 | N-WW-NI-280920-Kilmartin_STW-Filter Arm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-29 |  | 2020-10-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816.02 | 1816.02 | 0 | 0 | 0 | 1816.02 | 0 | 0 | 0 | 0 | 1816.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509515 | N-WW-NI-281020-Balintore_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601.84 | 2601.84 | 98.16 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509504 | N-WW-NI-281020-Boat_of_Garten-Upstands | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-28 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160.52 | 2160.52 | 39.49 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509512 | N-WW-NI-281020-Campbeltown_STW-Doors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-28 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284.71 | 284.71 | 2965.29 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 3250 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509529 | N-WW-NI-281020-Rovahead_STW-Generator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-28 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516.82 | 516.82 | 7383.18 | 0 | 0 | 7900 | 0 | 0 | 0 | 0 | 7900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504046 | N-WW-NI-281119-Alness_Invergordon_STW-PST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2019-12-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1909.92 | 0 | 1909.92 | 0 | 0 | 0 | 1909.92 | 0 | 0 | 0 | 0 | 1909.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504065 | N-WW-NI-281119-Baltasound_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-02-20 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 3686.26 | 0 | 3686.26 | 613.74 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504049 | N-WW-NI-281119-Campbeltown_STW-LIghtning | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | -2710.28 | 189.72 | 2710.28 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504512 | N-WW-NI-281219-Campbeltown_STW-Blowers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-06 |  | 2020-05-13 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | -132.91 | 4867.09 | 0 | 0 | 0 | 4867.09 | 0 | 0 | 0 | 0 | 4867.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504511 | N-WW-NI-281219-Lerwick_Rovahead_STW-Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-01-22 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1250.5 | 0 | 1250.5 | 1449.5 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504510 | N-WW-NI-281219-Lochcarron_STW-DO_Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-06 |  | 2020-01-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | -137.12 | 2562.88 | 0 | 0 | 0 | 2562.88 | 0 | 0 | 0 | 0 | 2562.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504509 | N-WW-NI-281219-Stornoway_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-06 |  | 2020-03-19 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 5350 | -331.68 | 5018.32 | 0 | 0 | 0 | 5018.32 | 0 | 0 | 0 | 0 | 5018.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504928 | N-WW-NI-290120-Aviemore_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-04-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 8800 | -80.82 | 8719.18 | 0 | 0 | 0 | 8719.18 | 0 | 0 | 0 | 0 | 8719.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504927 | N-WW-NI-290120-Fassfern_STW-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-10-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | -44.35 | 3175.65 | 0 | 0 | 0 | 3175.65 | 0 | 0 | 0 | 0 | 3175.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504930 | N-WW-NI-290120-Nairn_DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-05 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2150 | -2009.35 | 140.65 | 2009.35 | 0 | 0 | 2150 | 0 | 0 | 0 | 0 | 2150 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504906 | N-WW-NI-290120-Stornoway _STW-Container | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-08-18 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | -17.76 | 3532.24 | 0 | 0 | 0 | 3532.24 | 0 | 0 | 0 | 0 | 3532.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510974 | N-WW-NI-290121-Dornoch_STW-Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10083.29 | 10083.29 | 116.71 | 0 | 0 | 10200 | 0 | 0 | 0 | 0 | 10200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510968 | N-WW-NI-290121-Inveraray_Semples_Garage_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88.32 | 88.32 | 1261.68 | 0 | 0 | 1350 | 0 | 0 | 0 | 0 | 1350 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510981 | N-WW-NI-290121-Nairn_STW_Dry Well | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.35 | 209.35 | 2990.64 | 0 | 0 | 3199.99 | 0 | 0 | 0 | 0 | 3199.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505466 | N-WW-NI-290220-Broadford_STW-Kiosk_Power | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-02 |  | 2020-06-15 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 4161.84 | 4443.15 | 0 | 0 | 0 | 4443.15 | 0 | 0 | 0 | 0 | 4443.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505468 | N-WW-NI-290220-Dornoch_STW-Sludge_Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-02 |  | 2020-03-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3811.32 | 0 | 3811.32 | 0 | 0 | 0 | 3811.32 | 0 | 0 | 0 | 0 | 3811.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505472 | N-WW-NI-290220-Evanton_STW-FST_Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-02 |  | 2020-07-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 1823.69 | 1961.07 | 0 | 0 | 0 | 1961.07 | 0 | 0 | 0 | 0 | 1961.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505470 | N-WW-NI-290220-Garson_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-06-29 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6287.54 | 6287.54 | 0 | 0 | 0 | 6287.54 | 0 | 0 | 0 | 0 | 6287.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505471 | N-WW-NI-290220-Gremista_SPS-Site_Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 1098.19 | 0 | 1098.19 | 0 | 0 | 0 | 1098.19 | 0 | 0 | 0 | 0 | 1098.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505467 | N-WW-NI-290220-Thurso_STW-Shower_Area | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-02 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1841.84 | 0 | 1841.84 | 158.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505469 | N-WW-NI-290220-Thurso_STW-Sludge_Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-09-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4827.14 | 4827.14 | 0 | 0 | 0 | 4827.14 | 0 | 0 | 0 | 0 | 4827.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512087 | N-WW-NI-290321-Carrbridge_STW-Flume Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1800 | 0 | 0 | 1937.38 | 0 | 0 | 0 | 0 | 1937.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512082 | N-WW-NI-290321-Croy_STW-Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 3685.74 | 0 | 0 | 3967.05 | 0 | 0 | 0 | 0 | 3967.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512088 | N-WW-NI-290321-Kyleakin_Sep-FE Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2142.84 | 0 | 0 | 2306.39 | 0 | 0 | 0 | 0 | 2306.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512084 | N-WW-NI-290321-Oban_STW-Belt Press | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149.31 | 149.31 | 1200 | 0 | 0 | 1349.31 | 0 | 0 | 0 | 0 | 1349.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512085 | N-WW-NI-290321-Oban_STW-Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155.85 | 155.85 | 1285.74 | 0 | 0 | 1441.59 | 0 | 0 | 0 | 0 | 1441.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512089 | N-WW-NI-290321-Thurso_STC-Lime Silo Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2441.86 | 2441.86 | -141.86 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506389 | N-WW-NI-290420-Kincraig_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-29 |  | 2020-08-06 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1763.34 | 1763.34 | 0 | 0 | 0 | 1763.34 | 0 | 0 | 0 | 0 | 1763.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507408 | N-WW-NI-290620-Glenfinnan_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-11-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1191.38 | 1191.38 | 0 | 0 | 0 | 1191.38 | 0 | 0 | 0 | 0 | 1191.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507404 | N-WW-NI-290620-Kiltarlity_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-03-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24985.62 | 24985.62 | 0 | 0 | 0 | 24985.62 | 0 | 0 | 0 | 0 | 24985.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507422 | N-WW-NI-290620-Kirkwall_HoW_STC-Dewaterer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-08-13 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6565.08 | 6565.08 | 0 | 0 | 0 | 6565.08 | 0 | 0 | 0 | 0 | 6565.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507936 | N-WW-NI-290720 - Invergordon Admiralty Pier SPS - Replace CSO Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-01 | 2022-09-12 | 2023-04-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10242 | 10242 | 139758.26 | 0 | 0 | 150000.26 | 0 | 0 | 0 | 0 | 150000.26 | 90601.29 | [5 empty] | N | WWNI | 100%
507947 | N-WW-NI-290720-Ardersier_STW-Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2020-11-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13499.67 | 13499.67 | 0 | 0 | 0 | 13499.67 | 0 | 0 | 0 | 0 | 13499.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507954 | N-WW-NI-290720-Carsgate_South_SPS-Electrics | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2020-09-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224.05 | 1224.05 | 0 | 0 | 0 | 1224.05 | 0 | 0 | 0 | 0 | 1224.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507944 | N-WW-NI-290720-Glenmore_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-30 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 170.09 | 2429.91 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507943 | N-WW-NI-290720-Nairn_STW-Safety_Gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2020-11-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9185.18 | 9185.18 | 0 | 0 | 0 | 9185.18 | 0 | 0 | 0 | 0 | 9185.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507955 | N-WW-NI-290720-Wick_STW-Flooring | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7241.65 | 7241.65 | 278.35 | 0 | 0 | 7520 | 0 | 0 | 0 | 0 | 7520 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509008 | N-WW-NI-290920-Croy_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 189.72 | 2710.28 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509007 | N-WW-NI-290920-Nairn_STW-Auger | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-29 |  | 2020-10-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2834.77 | 2834.77 | 0 | 0 | 0 | 2834.77 | 0 | 0 | 0 | 0 | 2834.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509541 | N-WW-NI-291020-Stornoway_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-29 |  | 2020-04-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1109.7 | 1109.7 | 0 | 0 | 0 | 1109.7 | 0 | 0 | 0 | 0 | 1109.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509540 | N-WW-NI-291020-Ullapool_STW-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13359.21 | 13359.21 | 640.79 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 14000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509539 | N-WW-NI-291020-Wellpark_SPS-Controller | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-29 |  | 2020-11-12 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101.93 | 2101.93 | 0 | 0 | 0 | 2101.93 | 0 | 0 | 0 | 0 | 2101.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504075 | N-WW-NI-291119-Tore_STW-Outfall_Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2019-12-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3306.27 | 0 | 3306.27 | 0 | 0 | 0 | 3306.27 | 0 | 0 | 0 | 0 | 3306.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510512 | N-WW-NI-291220-Rovahead_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-31 |  | 2021-02-10 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1869.01 | 1869.01 | 131.01 | 0 | 0 | 2000.02 | 0 | 0 | 0 | 0 | 2000.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504946 | N-WW-NI-300120-Bowmore_STW-AlgaeSapper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-07-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | -33.05 | 1266.95 | 0 | 0 | 0 | 1266.95 | 0 | 0 | 0 | 0 | 1266.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504949 | N-WW-NI-300120-Campbeltown_STW-InletChannel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-03 |  | 2020-03-27 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 10999.97 | 771.96 | 11771.93 | 0 | 0 | 0 | 11771.93 | 0 | 0 | 0 | 0 | 11771.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504940 | N-WW-NI-300120-Campbeltown_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-05-14 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 10.97 | 1510.97 | 0 | 0 | 0 | 1510.97 | 0 | 0 | 0 | 0 | 1510.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504951 | N-WW-NI-300120-Tain_STW-Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-05 |  | 2020-02-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1243.07 | 0 | 1243.07 | 0 | 0 | 0 | 1243.07 | 0 | 0 | 0 | 0 | 1243.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505997 | N-WW-NI-300320-Dornoch_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-31 |  | 2020-05-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1334.44 | 1334.44 | 0 | 0 | 0 | 1334.44 | 0 | 0 | 0 | 0 | 1334.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506001 | N-WW-NI-300320-Grantfield_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-05-02 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5235.05 | 5235.05 | 0 | 0 | 0 | 5235.05 | 0 | 0 | 0 | 0 | 5235.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505992 | N-WW-NI-300320-Orphir_Village_STW-Telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1407 | 1407 | 0 | 0 | 0 | 1407 | 0 | 0 | 0 | 0 | 1407 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505989 | N-WW-NI-300320-Salen_Outlet_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-31 |  | 2020-05-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275.96 | 1275.96 | 0 | 0 | 0 | 1275.96 | 0 | 0 | 0 | 0 | 1275.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505983 | N-WW-NI-300320-Voe_STW-Access_Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088 | 1088 | 0 | 0 | 0 | 1088 | 0 | 0 | 0 | 0 | 1088 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505981 | N-WW-NI-300320-Walls_East_STW-Access_Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-09-11 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1672 | 1672 | 0 | 0 | 0 | 1672 | 0 | 0 | 0 | 0 | 1672 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512099 | N-WW-NI-300321-Edderton_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1542.84 | 0 | 0 | 1660.6 | 0 | 0 | 0 | 0 | 1660.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512096 | N-WW-NI-300321-Portree_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2571.42 | 0 | 0 | 2767.68 | 0 | 0 | 0 | 0 | 2767.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512094 | N-WW-NI-300321-Stornoway_STW-SHT Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392.52 | 392.52 | 5142.84 | 0 | 0 | 5535.36 | 0 | 0 | 0 | 0 | 5535.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506415 | N-WW-NI-300420-Newtonmore_STW-Telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-30 |  | 2020-07-23 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17834.05 | 17834.05 | 0 | 0 | 0 | 17834.05 | 0 | 0 | 0 | 0 | 17834.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507427 | N-WW-NI-300620-Dulnain_Bridge_STW-Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-30 |  | 2020-08-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1037.84 | 1037.84 | 0 | 0 | 0 | 1037.84 | 0 | 0 | 0 | 0 | 1037.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507969 | N-WW-NI-300720-Brora_STW-Fire Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2020-09-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1688.67 | 1688.67 | 0 | 0 | 0 | 1688.67 | 0 | 0 | 0 | 0 | 1688.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507982 | N-WW-NI-300720-Carnac_SPS-Gaskets | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-31 |  | 2020-09-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1325.05 | 1325.05 | 0 | 0 | 0 | 1325.05 | 0 | 0 | 0 | 0 | 1325.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507967 | N-WW-NI-300720-Embo_Links_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2020-10-27 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11529.36 | 11529.36 | 0 | 0 | 0 | 11529.36 | 0 | 0 | 0 | 0 | 11529.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507981 | N-WW-NI-300720-Rovahead_STW-Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2020-10-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6447.8 | 6447.8 | 0 | 0 | 0 | 6447.8 | 0 | 0 | 0 | 0 | 6447.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507979 | N-WW-NI-300720-Rovahead_STW-Pressure Monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2020-08-13 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1556.39 | 1556.39 | 0 | 0 | 0 | 1556.39 | 0 | 0 | 0 | 0 | 1556.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507963 | N-WW-NI-300720-South_Voxter_SEP-Handrail | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-30 |  | 2021-03-06 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6205.61 | 6205.61 | -5.61 | 0 | 0 | 6200 | 0 | 0 | 0 | 0 | 6200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507983 | N-WW-NI-300720-Strathpeffer_STW-FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-07-31 |  | 2021-03-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5749.72 | 5749.72 | 150.28 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 5900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507958 | N-WW-NI-300720-Wellpark_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-30 |  | 2020-09-28 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2401.47 | 2401.47 | 0 | 0 | 0 | 2401.47 | 0 | 0 | 0 | 0 | 2401.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509044 | N-WW-NI-300920-5Nr Sites Nethy_Bridge_STW-LOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9658.37 | 9658.37 | -1558.37 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 8100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509024 | N-WW-NI-300920-Barbaraville_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-30 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3344.21 | 3344.21 | 0 | 0 | 0 | 3344.21 | 0 | 0 | 0 | 0 | 3344.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509031 | N-WW-NI-300920-Boat_of_Garten_STW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-30 |  | 2020-10-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685.05 | 1685.05 | 0 | 0 | 0 | 1685.05 | 0 | 0 | 0 | 0 | 1685.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509023 | N-WW-NI-300920-Glenmore_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27037.46 | 27037.46 | -1337.46 | 0 | 0 | 25700 | 0 | 0 | 0 | 0 | 25700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509029 | N-WW-NI-300920-Rovahead_STW-SHT Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1246.76 | 1246.76 | 0 | 0 | 0 | 1246.76 | 0 | 0 | 0 | 0 | 1246.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509015 | N-WW-NI-300920-Sunnyside_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-30 |  | 2020-11-17 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2186.79 | 2186.79 | 0 | 0 | 0 | 2186.79 | 0 | 0 | 0 | 0 | 2186.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509030 | N-WW-NI-300920-Thurso_STC-Lime Silo | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.14 | 255.14 | 4444.86 | 0 | 0 | 4700 | 0 | 0 | 0 | 0 | 4700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509555 | N-WW-NI-301020-Alness_Invergordon_DOA | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-10-30 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379.44 | 379.44 | 5420.56 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 5800 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509559 | N-WW-NI-301020-Alness_Invergordon_STC-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-30 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3667.26 | 3667.26 | 132.74 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509554 | N-WW-NI-301020-Alness_Invergordon_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-30 |  | 2021-02-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2103.54 | 2103.54 | 96.46 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509565 | N-WW-NI-301020-Dingwall_STW-NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2021-04-01 |  | 2020-11-19 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231.8 | 1231.8 | 0 | 0 | 0 | 1231.8 | 0 | 0 | 0 | 0 | 1231.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509567 | N-WW-NI-301020-Dingwall_STW-Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2021-03-04 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3829.54 | 3829.54 | 470.46 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506002 | N-WW-NI-310320- Clachan_Seil_Brookside_SPS-Fencing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-31 |  | 2020-04-04 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203.4 | 1203.4 | 0 | 0 | 0 | 1203.4 | 0 | 0 | 0 | 0 | 1203.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506003 | N-WW-NI-310320-Campbeltowh_Kinloch_Park_SPS-VSD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-31 |  | 2020-04-21 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 27.66 | 1194.06 | 1221.72 | 0 | 0 | 0 | 1221.72 | 0 | 0 | 0 | 0 | 1221.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506007 | N-WW-NI-310320-Dornoch_STW-Roller CS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 2865 | 0 | 2865 | 245 | 0 | 0 | 3110 | 0 | 0 | 0 | 0 | 3110 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506010 | N-WW-NI-310320-Lerwick_DOA-Gremista_Rd_MH | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-14 |  | 2020-05-27 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 4884.42 | 346.73 | 5231.15 | 0 | 0 | 0 | 5231.15 | 0 | 0 | 0 | 0 | 5231.15 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506008 | N-WW-NI-310320-North_Ballachulish_STW-Lagging | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506013 | N-WW-NI-310320-Oban_Corran_Park_SPS-Macerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-31 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 1180 | 27.66 | 1207.66 | 92.34 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512142 | N-WW-NI-310321-Aviemore_STW-Hose Point | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 4800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512128 | N-WW-NI-310321-Kincraig_STW-Power | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-06-30 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2742.84 | 0 | 0 | 2742.84 | 0 | 0 | 0 | 0 | 2742.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512144 | N-WW-NI-310321-Kirkwall_HoW_STW-Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-06-30 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2657.16 | 0 | 0 | 2657.16 | 0 | 0 | 0 | 0 | 2657.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512134 | N-WW-NI-310321-Lochgair_Sep-Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-04-01 |  | 2021-06-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.18 | 144.18 | 3000 | 0 | 0 | 3144.18 | 0 | 0 | 0 | 0 | 3144.18 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508465 | N-WW-NI-310820-Bu_Point_STW-Wash_W System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-11-06 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908.92 | 2908.92 | 0 | 0 | 0 | 2908.92 | 0 | 0 | 0 | 0 | 2908.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508472 | N-WW-NI-310820-Cawdor_STW-pH Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-09-10 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320.69 | 1320.69 | 0 | 0 | 0 | 1320.69 | 0 | 0 | 0 | 0 | 1320.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508470 | N-WW-NI-310820-Fortrose_STW-UV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-10-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950.46 | 2950.46 | 0 | 0 | 0 | 2950.46 | 0 | 0 | 0 | 0 | 2950.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508473 | N-WW-NI-310820-Gairloch_East_Strath_SPS-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-10-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1829.19 | 1829.19 | 0 | 0 | 0 | 1829.19 | 0 | 0 | 0 | 0 | 1829.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508462 | N-WW-NI-310820-Munlochy_STW- Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-07-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11344.25 | 11344.25 | 0 | 0 | 0 | 11344.25 | 0 | 0 | 0 | 0 | 11344.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508493 | N-WW-NI-310820-Shieldaig_Pier_SPS-Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-01 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 7150 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506296 | N-WW-NII-210420-Fortrose_Harbour_SPS_Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-07-16 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4243.63 | 4243.63 | 0 | 0 | 0 | 4243.63 | 0 | 0 | 0 | 0 | 4243.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503950 | N-WW-NI-Taynuilt_STW-UV_Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 10300 | -9485.85 | 814.15 | 9485.85 | 0 | 0 | 10300 | 0 | 0 | 0 | 0 | 10300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504283 | N-WW-NI-Tobermory_SPS-Var | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-01-09 |  | 2021-03-30 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 3486.82 | 228325.36 | 231812.18 | 0 | 0 | 0 | 231812.18 | 0 | 0 | 0 | 0 | 231812.18 | 90601.29 |  |  |  |  | 13500 | N | CM_WWNI | 100%
504455 | N-WW-STW-201219-Oban_STW-Sludge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-20 |  | 2021-05-01 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 1402.16 | 20402.16 | 0 | 0 | 0 | 20402.16 | 0 | 0 | 0 | 0 | 20402.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500510 | O&D- Building Fabric Condition Surveys | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-11 |  | Scottish Water Wide | 0 | 0 | 17473 | 8371.65 | 20352.35 | 69487.24 | 30591.73 | 43423.03 | 189699 | 15301.17 | 0 | 0 | 205000.17 | 0 | 0 | 0 | 0 | 205000.17 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500511 | O&D- Building Fabric in Roof Renewals & Condition Surveys | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 |  | Scottish Water Wide | 0 | 0 | 282199 | 144609 | 228401 | 256587.9 | 92949.07 | 371669.2 | 1376415.17 | -18201.17 | 0 | 0 | 1358214 | 0 | 0 | 0 | 0 | 1358214 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500947 | O&D- Dumfries Office - Marchmount & Lincluden Depots | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-09-17 | 2019-09-06 | 2019-12-15 | 2021-06-16 |  | Dumfries and Galloway | 0 | 0 | 56607 | -5101.98 | 2200 | 97028.21 | 295279.12 | 1323329.65 | 1769342 | 312381 | 0 | 0 | 2081723 | 0 | 0 | 166537.84 | 166537.84 | 2248260.84 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500513 | O&D- EU Energy Directive | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 |  | Scottish Water Wide | 0 | 0 | 90241 | 72836.42 | 69669.96 | 105744.31 | 94854.31 | 191654 | 625000 | 0 | 0 | 0 | 625000 | 0 | 0 | 0 | 0 | 625000 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500520 | O&D- Facilities East Office Fairmilehead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-05-18 | 2016-10-24 | 2016-10-24 | 2019-03-07 |  | Scottish Water Wide | 0 | 0 | 301700 | 849674.93 | 1783224.55 | 1715213.35 | 39545.9 | 0 | 4689358.73 | -16652 | 0 | 0 | 4672706.73 | 0 | 0 | 0 | 0 | 4672706.73 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500514 | O&D- Fixed Wire Testing | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-11 |  | Scottish Water Wide | 0 | 0 | 108706.24 | 151257.76 | 75373 | 93638 | 63949.08 | 84646.92 | 577571 | 6428.76 | 0 | 0 | 583999.76 | 0 | 0 | 0 | 0 | 583999.76 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500515 | O&D- FRA inc Fire Alarms | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-11 |  | Scottish Water Wide | 0 | 0 | 88605 | 54097 | 62762.82 | 100947.52 | 102098.66 | 183646 | 592157 | 49842.72 | 0 | 0 | 641999.72 | 0 | 0 | 0 | 0 | 641999.72 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500516 | O&D- H&S Minor Works | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-11 |  | Scottish Water Wide | 0 | 0 | 188619 | 364067 | 412601 | 329583.49 | 366579.45 | 313060.06 | 1974510 | 8490.3 | 0 | 0 | 1983000.3 | 0 | 0 | 0 | 0 | 1983000.3 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500517 | O&D- Heating & Ventilation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-11 |  | Scottish Water Wide | 0 | 0 | 71001.35 | 61042.65 | 143646.3 | 141375.37 | 56855.34 | 44852 | 518773 | 80648.1 | 0 | 0 | 599421.1 | 0 | 0 | 0 | 0 | 599421.1 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500518 | O&D- Refurb & Capital Maintenance inc HVAC | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 |  | Scottish Water Wide | 0 | 0 | 143114 | 456482 | 329441.01 | 959030.99 | 595356.15 | 543714.72 | 3027138.87 | 271668.13 | 0 | 0 | 3298807 | 0 | 0 | 0 | 0 | 3298807 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500512 | O&D- Replacement Furniture (DSE) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-11 |  | Scottish Water Wide | 0 | 0 | 95097 | 49190.54 | 201343.46 | 142836.14 | 104015.8 | -2327.94 | 590155 | 189845.42 | 0 | 0 | 780000.42 | 0 | 0 | 0 | 0 | 780000.42 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500519 | O&D- Security Measures inc Intruder Alarms | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 |  | Scottish Water Wide | 0 | 0 | 106171.37 | 164061.63 | 265458.89 | 259111.2 | 51277.96 | 206101.96 | 1052183 | 79816.56 | 0 | 0 | 1131999.56 | 0 | 0 | 0 | 0 | 1131999.56 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500169 | Oban DOA (DOA001020) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-03-16 | 2016-05-23 | 2017-07-27 | 2018-03-01 | Na H-Eileanan an Iar | 0 | 0 | 9361.17 | 31552.83 | 22638.43 | 382.39 | 0 | 0 | 63934.82 | 0 | 0 | 0 | 63934.82 | 0 | 0 | 0 | 0 | 63934.82 | 9047.24 | [5 empty] | N | EC01D | 34.08% | CS16D | 65.92%
512220 | Oban Manor House SPS - Replacement Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-08-02 | 2021-10-22 | 2022-06-06 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14149.98 | 0 | 0 | 14149.98 | 0 | 0 | 0 | 0 | 14149.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46195 | Oban North- South TWS Refurb - TWS000580-TWS000581 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-03-27 | 2014-10-23 | 2014-10-23 | 2014-10-21 | 2014-10-23 | Argyll and Bute-North Argyll | 728722.47 | 0 | 1689.83 | 0 | 0 | 0 | 0 | 0 | 1689.83 | 0 | 0 | 0 | 730412.3 | 0 | 0 | 0 | 0 | 730412.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403830 | Oban North- South TWS Refurb - TWS000580-TWS000581 TR From 046195 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-06 | 2014-08-08 | 2014-08-08 | 2015-06-15 |  | Argyll and Bute-North Argyll | 162529.62 | 0 | 30105.21 | 0 | 0 | 0 | 0 | 0 | 30105.21 | 0 | 0 | 0 | 192634.83 | 0 | 0 | 0 | 0 | 192634.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
46222 | Oban STC Refurb - STC000032 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2011-03-07 | 2011-03-07 | 2011-03-07 | 2011-03-07 | Argyll and Bute-North Argyll | 185037.31 | 0 | -0.31 | 0 | 0 | 0 | 0 | 0 | -0.31 | 0 | 0 | 0 | 185037 | 0 | 0 | 0 | 0 | 185037 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504576 | Oban Stevenson Street SPS - Refurbish Screw Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-03-25 | 2020-08-31 | 2021-05-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 14719.63 | 100907.4 | 115627.03 | 0 | 0 | 0 | 115627.03 | 0 | 0 | 0 | 0 | 115627.03 | 90601.29 | [5 empty] | N | WWNI | 100%
510392 | Oban Stevenson Street SPS - Replace Screw Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2021-06-30 | 2023-04-14 | 2023-08-11 | 2024-06-14 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31512 | 31512 | 718488.33 | 0 | 0 | 750000.33 | 0 | 0 | 0 | 0 | 750000.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46201 | Oban STW Refurb - STW000559 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2011-02-28 | 2011-02-28 | 2011-02-28 | 2011-02-28 | Argyll and Bute-North Argyll | 125419.25 | 0 | -0.25 | 0 | 0 | 0 | 0 | 0 | -0.25 | 0 | 0 | 0 | 125419 | 0 | 0 | 0 | 0 | 125419 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511810 | Oban WwTW - Refurbish 2 No. SHTs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219999.96 | 0 | 0 | 219999.96 | 0 | 0 | 0 | 0 | 219999.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510244 | Oban WwTW - Washwater System Review | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-06-23 | 2022-09-15 | 2023-04-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3194 | 3194 | 216806.13 | 0 | 0 | 220000.13 | 0 | 0 | 0 | 0 | 220000.13 | 90601.29 | [5 empty] | N | WWNI | 100%
501168 | Ochiltree STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-04-12 | 2020-03-12 | 2020-03-23 | 2022-05-30 |  | East Ayrshire | 0 | 0 | 0 | 42142.34 | 74429.76 | -5483.99 | 248391.73 | 168225.8 | 527705.64 | 1200610 | 0 | 0 | 1728315.64 | 0 | 0 | 171684.36 | 171684.36 | 1900000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403798 | Old Broughty Ferry Castle Uns SO NO464304 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS7 | 2014-05-14 | 2015-12-10 | 2016-01-06 | 2016-03-31 | 2016-04-30 | Dundee City | 25562 | 25562 | 429532.94 | 73005.92 | 0 | -16758.31 | 0 | 0 | 485780.55 | 0 | 0 | 0 | 511342.55 | 0 | 0 | 0 | 0 | 511342.55 | 0 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
501381 | Old Cambus TWP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2018-04-30 | 2028-06-16 | 2028-10-20 | 2029-06-06 |  | Scottish Borders | 0 | 0 | 0 | 7779.77 | 245.79 | 424.6 | 284.15 | 0 | 8734.31 | 216971.72 | 0 | 0 | 225706.03 | 0 | 0 | 0 | 0 | 225706.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503417 | Old Craighall ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-01-21 | 2023-11-10 | 2024-02-13 | 2024-10-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 64441.86 | 11555.55 | 38192.18 | 114189.59 | 320383.41 | 0 | 0 | 434573 | 0 | 0 | 0 | 0 | 434573 | 122419.09 | [5 empty] | N | SG1 | 100%
501537 | Old Kilpatrick Large SR Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-09-21 | 2030-01-25 | 2030-09-11 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729210 | 0 | 0 | 729210 | 0 | 0 | 0 | 0 | 729210 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500772 | Old Mains Cottage Greenock Road Inchinnan Partial Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-08-10 | 2018-04-30 | 2018-05-22 | 2018-12-24 |  | Renfrewshire | 0 | 0 | 23500 | 50735 | 128377.14 | 930613.86 | 112774 | 18212 | 1264212 | 0 | 0 | 0 | 1264212 | 0 | 0 | 0 | 0 | 1264212 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503441 | Oldmeldrum STW - Surface Aerator Replacement & Interim Oxymem Install | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-01-16 | 2021-06-25 | 2021-08-16 | 2022-06-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 3655.68 | 398283.32 | 401939 | 1750703.05 | 0 | 0 | 2152642.05 | 0 | 0 | 0 | 0 | 2152642.05 | 122419.09 | [5 empty] | N | SG1 | 100%
502736 | Oldmeldrum WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2020-06-29 | 2022-08-31 | 2022-12-27 | 2023-12-15 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 68854.88 | 90485.37 | 65493.31 | 61715.8 | 286549.36 | 6474612.65 | 0 | 0 | 6761162.01 | 0 | 0 | 0 | 0 | 6761162.01 | 122419.09 | [5 empty] | N | SG1 | 100%
503630 | OMG06 Shortfall Project | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS3 | 2019-09-30 | 2020-03-31 | 2020-03-31 | 2021-09-30 | 2022-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 311335.99 | 1674285.31 | 1985621.3 | 425024.7 | 425024.7031 | 723182.358 | 2410646 | 298157.6549 | 0 | 0 | 298157.6549 | 2708803.6549 | 649651.11 | [5 empty] | N | DW5FS | 100%
50016 | OMG180 Risk Adjustment | Q&S4 | Programme Risk | OMG180 Risk |  |  | General |  | SWD | OMG180 Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61000000 | [5 empty] | N | SR15_RSK_OMG | 100%
502248 | On Site Productivity Improvements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | GW0 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-06-11 |  | Scottish Water Wide | 0 | 0 | 0 | 135242.6 | -242.6 | 61663.62 | 54444.4 | 4325.7 | 255433.72 | -4325.7 | 0 | 0 | 251108.02 | 0 | 0 | 0 | 0 | 251108.02 | 306661.32 | [5 empty] | N | CM_M&G | 100%
500850 | Onich RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-11-04 | 2016-03-25 | 2016-03-28 | 2017-01-31 | 2017-11-30 | Highland | 0 | 0 | 7050 | 22977.97 | 0 | 1000.03 | -8770.07 | 0 | 22257.93 | 0 | 0 | 0 | 22257.93 | 0 | 0 | 0 | 0 | 22257.93 | 61811.26 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 20 | [43 empty] | 0
402589 | OPA Focused Delivery CID WWI | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-20 | 2012-03-20 | 2012-04-02 | 2015-02-02 |  | All East Unitary Authorities | 269263.54 | 0 | 736.46 | 83.46 | 0 | 0 | 0 | 0 | 819.92 | 0 | 0 | 0 | 270083.46 | 0 | 0 | 0 | 0 | 270083.46 | 418763.58 | [5 empty] | N | CM_WWI | 100%
402590 | OPA Focused Delivery CID WWNI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-04-02 | 2017-02-16 |  | All East Unitary Authorities | 1360489 | 0 | 54625.98 | 844.67 | 0 | -1566.87 | 0 | 0 | 53903.78 | 0 | 0 | 0 | 1414392.78 | 0 | 0 | 0 | 0 | 1414392.78 | 181202.57 | [5 empty] | N | CM_WWNI | 100%
510963 | Operational Technology Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2028-04-28 | 2029-03-30 | 2029-08-01 | 2031-03-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618429.45 | 0 | 0 | 618429.45 | 0 | 0 | 0 | 0 | 618429.45 | 613322.63 | [5 empty] | N | CM_M&G | 100%
401680 | Opportunistic Lead Comms Pipe Replacement - East | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2011-06-23 | 2011-06-27 | 2014-03-31 | 2014-03-31 | All East Unitary Authorities | 106189 | 0 | 0 | -355.62 | 0 | 0 | 0 | 0 | -355.62 | 0 | 0 | 0 | 105833.38 | 0 | 0 | 0 | 0 | 105833.38 | 0 | [5 empty] | N | DW1B | 100%
401681 | Opportunistic Lead Comms Pipe Replacement - North | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2012-03-15 | 2012-03-26 | 2015-03-13 | 2015-03-31 | All North Unitary Authorities | 58575.56 | 0 | 23.18 | 0 | 0 | 0 | 0 | 0 | 23.18 | 0 | 0 | 0 | 58598.74 | 0 | 0 | 0 | 0 | 58598.74 | 0 | [5 empty] | N | DW1B | 100%
401679 | Opportunistic Lead Comms Pipe Replacement - South | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2012-02-10 | 2012-02-10 | 2015-03-25 | 2015-03-31 | All South Unitary Authorities | 74082 | 0 | 848 | -0.41 | -602.15 | 0 | 0 | 0 | 245.44 | 0 | 0 | 0 | 74327.44 | 0 | 0 | 0 | 0 | 74327.44 | 0 | [5 empty] | N | DW1B | 100%
401678 | Opportunistic Lead Comms Pipe Replacement - West (Forth and Clyde) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2011-10-27 | 2011-11-14 | 2014-12-15 | 2015-03-31 | All West Unitary Authorities | 125043 | 0 | 275 | -941.04 | 0 | 0 | 0 | 0 | -666.04 | 0 | 0 | 0 | 124376.96 | 0 | 0 | 0 | 0 | 124376.96 | 0 | [5 empty] | N | DW1B | 100%
500437 | OPS SVCW SR 15 Waste East Infra | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-11-27 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWI | 100%
400732 | OPTIMISE MAINTAIN - AUDIT PRVS - EAST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-22 | 2010-04-22 | 2010-05-03 | 2015-07-02 |  | Scottish Water Wide | 2739142 | 0 | 39075.76 | 6442.58 | 0 | 0 | 0 | 0 | 45518.34 | 0 | 0 | 0 | 2784660.34 | 0 | 0 | 0 | 0 | 2784660.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400733 | OPTIMISE MAINTAIN - AUDIT PRVS - WEST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-22 | 2010-04-22 | 2010-05-03 | 2015-07-02 |  | Scottish Water Wide | 3534103 | 0 | -20614 | -25906.68 | 0 | 0 | 0 | 0 | -46520.68 | 0 | 0 | 0 | 3487582.32 | 0 | 0 | 0 | 0 | 3487582.32 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507173 | Oracle ULA Exit | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2020-06-23 | 2020-11-25 | 2020-11-25 | 2021-08-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2322813 | 2322813 | 1017333.34 | 0 | 0 | 3340146.34 | 0 | 0 | 267211.7072 | 267211.7072 | 3607358.0472 | 613322.63 | [5 empty] | N | CM_M&G | 100%
404106 | Oran Contract- 44T Tractor Units and Trailers (HGV) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-23 | 2015-03-23 | 2015-03-23 | 2016-06-23 |  | Scottish Water Wide | 434759 | 0 | 198424.15 | -21989.66 | 0 | 0 | 0 | 0 | 176434.49 | 0 | 0 | 0 | 611193.49 | 0 | 0 | 0 | 0 | 611193.49 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502241 | Orbiston WWTW Legacy Sludge Removal | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater | SEPA | SWMD | Sludge | MS7 | 2016-06-30 | 2017-03-28 | 2017-05-11 | 2017-08-31 | 2017-11-30 | North Lanarkshire | 0 | 0 | 0 | 10327.1 | 41039.61 | 0 | 0 | 0 | 51366.71 | 0 | 0 | 0 | 51366.71 | 0 | 0 | 0 | 0 | 51366.71 | 0 | [5 empty] | Y | LA01_S | 100% | [41 empty] | 1 | [25 empty] | 0
501544 | Orkney Sludge Strategy Sanday Westray Kirbister and Boardhouse WTWs | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2027-04-12 | 2028-11-08 | 2029-03-13 | 2030-09-05 | 2030-12-06 | Orkney Islands | 0 | 0 | 23360.73 | 16088.43 | 18965.78 | 201636.68 | 87508.33 | 21137.05 | 368697 | 6568273.36 | 0 | 0 | 6936970.36 | 0 | 0 | 0 | 0 | 6936970.36 | 0 | [5 empty] | N | SR21_WA | 100%
502553 | Ormiston WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | East Lothian | 0 | 0 | 0 | 31033.94 | 28867.84 | 0 | 0 | 0 | 59901.78 | 0 | 0 | 0 | 59901.78 | 0 | 0 | 0 | 0 | 59901.78 | 122419.09 | [5 empty] | N | SG1 | 100%
500576 | Orphir Village WwTW - Enforcement Mitigations | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-02-22 | 2023-12-21 | 2024-03-13 | 2025-04-07 |  | Orkney Islands | 0 | 0 | 25559.02 | 8671.97 | 33315.61 | 32356.9 | 36664.66 | 53352.84 | 189921 | 1554019.78 | 0 | 0 | 1743940.78 | 0 | 0 | 0 | 0 | 1743940.78 | 122419.09 | [5 empty] | N | SG1 | 100%
403606 | Outcome of Failure Implementation Plans FPP Needs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-11-11 | 2013-11-21 | 2014-04-01 | 2016-12-19 |  | All East Unitary Authorities | 303821 | 0 | -54625 | -25540.49 | 256.8 | 0 | 0 | 0 | -79908.69 | 0 | 0 | 0 | 223912.31 | 0 | 0 | 0 | 0 | 223912.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508268 | Outerwards Reservoir Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-09-02 | 2021-04-06 | 2021-11-17 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6372 | 6372 | 58627.49 | 0 | 0 | 64999.49 | 0 | 0 | 0 | 0 | 64999.49 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403669 | Overton DSR Improvements to Inlet Arrangement | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2014-08-18 | 2015-06-30 | 2015-10-26 | 2017-08-28 | 2017-08-28 | Aberdeen City | 7020 | 0 | 162390 | 163864.24 | 141725.76 | -8572.72 | -4377.56 | 0 | 455029.72 | 0 | 0 | 0 | 462049.72 | 0 | 0 | 0 | 0 | 462049.72 | 119022.58 | [5 empty] | N | CM_WSNI | 7.336% | WG5 | 92.66%
502282 | Oykel Bridge - Radon | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS0 | 2019-06-28 | 2021-09-27 | 2022-01-03 |  |  | Highland | 0 | 0 | 0 | 24636.03 | 9100.5 | 13363.47 | 0 | 21461 | 68561 | 556438.83 | 0 | 0 | 624999.83 | 0 | 153480.2095 | 0 | 153480.2095 | 778480.0395 | 525664.36 | [5 empty] | Y | DW25P | 100% | [67 empty] | 0
504213 | Oykel Bridge WTW - Temporary TWS | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2019-06-28 | 2020-04-13 | 2020-07-20 | 2020-10-31 | 2020-07-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
45358 | Oykel Bridge WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-02-13 | 2012-05-14 | 2014-09-16 | 2014-11-21 | Highland | 334827.49 | 0 | -238.97 | 0 | 0 | 0 | 0 | 0 | -238.97 | 0 | 0 | 0 | 334588.52 | 0 | 0 | 0 | 0 | 334588.52 | 28761.13 | [5 empty] | N | DW13 | 100%
505448 | P3M Transition Costs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2020-04-17 | 2020-05-08 | 2020-05-08 | 2020-07-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1257929.51 | 1257929.51 | 0 | 0 | 0 | 1257929.51 | 0 | 0 | 0 | 0 | 1257929.51 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403271 | PACE Phase 2 Spend to Save | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-01-14 | 2013-06-14 | 2013-06-14 | 2016-05-31 |  | Scottish Water Wide | 2799601.53 | 0 | 68081.42 | -112.98 | 0 | 0 | 0 | 0 | 67968.44 | 0 | 0 | 0 | 2867569.97 | 0 | 0 | 0 | 0 | 2867569.97 | 271803.86 | [5 empty] | N | CM_WWNI | 100%
402687 | Package B - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-05-28 | 2012-09-26 | 2013-01-31 | 2014-12-18 | 2014-12-24 | Scottish Water Wide | 2806579.54 | 0 | -36028.04 | -15610.49 | 0 | 0 | 0 | 0 | -51638.53 | 0 | 0 | 0 | 2754941.01 | 0 | 0 | 0 | 0 | 2754941.01 | 0 | [5 empty] | N | DW9A | 100%
402888 | Package C - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 2055446.39 | 0 | 1942792.55 | 292518.37 | -4886.64 | 0 | 0 | 0 | 2230424.28 | 0 | 0 | 0 | 4285870.67 | 0 | 0 | 0 | 0 | 4285870.67 | 119022.58 | [5 empty] | N | CM_WSNI | 48% | DW9A | 52%
402889 | Package D - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2016-03-25 | 2016-03-25 | Scottish Water Wide | 4210597.59 | 0 | 4551823.44 | 1395787.56 | 473.15 | -220 | 0 | 0 | 5947864.15 | 0 | 0 | 0 | 10158461.74 | 0 | 0 | 0 | 0 | 10158461.74 | 119022.58 | [5 empty] | N | CM_WSNI | 45.1% | DW9A | 54.9%
402890 | Package E - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-16 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 3308494.47 | 0 | 3544477.05 | 1443347.04 | 1747.15 | 0 | 0 | 0 | 4989571.24 | 0 | 0 | 0 | 8298065.71 | 0 | 0 | 0 | 0 | 8298065.71 | 119022.58 | [5 empty] | N | DW9E | 0.1% | CM_WSNI | 48% | DW9A | 51.9%
402891 | Package F - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-10 | 2013-02-12 | 2013-02-13 | 2013-05-29 | 2013-06-24 | Scottish Water Wide | 197486.97 | 0 | -6975 | 0 | 0 | 0 | 0 | 0 | -6975 | 0 | 0 | 0 | 190511.97 | 0 | 0 | 0 | 0 | 190511.97 | 0 | [5 empty] | N | DW9A | 100%
402892 | Package G - Enhancement of WTW Security | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2016-03-30 | 2016-03-31 | Scottish Water Wide | 1740881.26 | 0 | 1731310.81 | 1010501.84 | 77188.59 | -45975.02 | 0 | 0 | 2773026.22 | 0 | 0 | 0 | 4513907.48 | 0 | 0 | 0 | 0 | 4513907.48 | 119022.58 | [5 empty] | N | DW9E | 2.9% | CM_WSNI | 48% | DW9A | 49.1%
501742 | Paisley Road Barrhead - Reline sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-06-19 | 2017-06-19 | 2017-06-19 | 2017-05-29 |  | Renfrewshire | 0 | 0 | 0 | 2347.55 | 3213.47 | 125.79 | 0 | 0 | 5686.81 | 0 | 0 | 0 | 5686.81 | 0 | 0 | 0 | 0 | 5686.81 | 209381.79 | [5 empty] | N | CM_WWI | 100%
46333 | Palnackie Septic Tank No.1 (Harbour) - STW000563 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-25 | 2010-07-26 | 2013-03-25 | 2014-09-09 | 2014-09-09 | Dumfries and Galloway | 1159027.88 | 0 | 14945.96 | -1006.43 | 4 | 0 | 0 | 0 | 13943.53 | 0 | 0 | 0 | 1172971.41 | 0 | 0 | 0 | 0 | 1172971.41 | 213020.38 | [5 empty] | N | SG1 | 24.98% | CM_WWNI | 75.02%
506392 | Pan Rocks EO Improvements | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-07-15 | 2021-09-09 | 2022-02-25 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3843 | 3843 | 23157 | 0 | 0 | 27000 | 0 | 0 | 0 | 0 | 27000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501155 | Pan Rocks SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-12-14 | 2017-03-28 | 2017-06-23 | 2019-01-31 |  | South Ayrshire | 0 | 0 | 8800.42 | 221686.58 | 744670 | 374928 | 26911 | -7364.03 | 1369631.97 | 9618.47 | 0 | 0 | 1379250.44 | 0 | 0 | 0 | 0 | 1379250.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508792 | Pan Scotland Amey Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-09-24 | 2020-12-16 | 2021-09-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79778 | 79778 | 70222.42 | 0 | 0 | 150000.42 | 0 | 0 | 0 | 0 | 150000.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504466 | Pan Scotland Chem Dosing Systems H&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-27 | 2021-04-15 | 2021-07-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256.32 | 256.32 | 0 | 0 | 0 | 256.32 | 0 | 0 | 0 | 0 | 256.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508563 | Pan Scotland CSD Minor Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-09-11 | 2021-03-29 | 2021-11-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19571 | 19571 | 80428.53 | 0 | 0 | 99999.53 | 0 | 0 | 0 | 0 | 99999.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509546 | Pan Scotland CSD Mission Timesheet | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-30 | 2021-06-23 | 2022-02-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73574 | 73574 | 176425.63 | 0 | 0 | 249999.63 | 0 | 0 | 0 | 0 | 249999.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509889 | Pan Scotland Emergency Works Final | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-11-27 | 2021-03-24 | 2021-11-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56629 | 56629 | 93371.48 | 0 | 0 | 150000.48 | 0 | 0 | 0 | 0 | 150000.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509985 | Pan Scotland Inspections and Maintenance Strategy for GCS Tanks (H&S) 75K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-04-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10412 | 10412 | 64588 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 75000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508794 | Pan Scotland Leslie Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-09-24 | 2020-12-15 | 2021-09-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84480 | 84480 | 165730.37 | 0 | 0 | 250210.37 | 0 | 0 | 0 | 0 | 250210.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509991 | Pan Scotland MacKenzie Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-03 | 2021-05-21 | 2021-09-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5167 | 5167 | 30999.67 | 0 | 0 | 36166.67 | 0 | 0 | 0 | 0 | 36166.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510171 | Pan Scotland SV Amey Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-12-17 | 2021-02-11 | 2021-08-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36779.38 | 36779.38 | 64168.76 | 0 | 0 | 100948.14 | 0 | 0 | 0 | 0 | 100948.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510172 | Pan Scotland SV Leslie Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-03-29 | 2021-06-21 | 2022-02-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47466.62 | 0 | 0 | 47466.62 | 0 | 0 | 0 | 0 | 47466.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510173 | Pan Scotland SV MacKenzie Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-12-17 | 2021-02-11 | 2021-08-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19182 | 19182 | 30818.16 | 0 | 0 | 50000.16 | 0 | 0 | 0 | 0 | 50000.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512092 | Pan Scotland Tanker and Tanker Fill Points | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3999999.96 | 0 | 0 | 3999999.96 | 0 | 0 | 0 | 0 | 3999999.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507626 | Pan Scotland-Inspection of Sea Outfalls | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 90000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508447 | Pan Scotland-Sea Outfall Inspections | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-28 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.31 | 981.31 | 14018.69 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508996 | Pan Scotland-WW-NI-290920-ESNET units to be purchased | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-29 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209773.11 | 209773.11 | -9773.11 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506891 | Pan-Scotland WQ Bench Instrumentation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 |  | 2020-07-20 | 2021-02-01 | 2021-07-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260635.99 | 260635.99 | 3929.44 | 0 | 0 | 264565.43 | 0 | 0 | 0 | 0 | 264565.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508820 | Panton McLeod Inspection & Temp Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-18 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65721.1 | 65721.1 | 134278.9 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509833 | Panton McLeod TWS Information Provision Support | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-20 | 2021-06-23 | 2022-02-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.96 | 71.96 | 1191.09 | 0 | 0 | 1263.05 | 0 | 0 | 0 | 0 | 1263.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509832 | Panton McLeod TWS Mission Consultancy Support | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-20 | 2021-06-23 | 2022-02-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283.93 | 283.93 | 4569.72 | 0 | 0 | 4853.65 | 0 | 0 | 0 | 0 | 4853.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502953 | Papa Stour Water supply | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWMD | DWQ Compliance | MS6 | 2016-09-28 | 2019-03-27 | 2019-06-28 | 2019-12-31 | 2022-05-20 | Shetland Islands | 0 | 0 | 0 | 0 | 20542.96 | 143986.01 | 253484.33 | 28172.7 | 446186 | 18814.5 | 18814.5 | 26117.7291 | 465000.5 | 7303.2291 | 0 | 0 | 7303.2291 | 472303.7291 | 1201459.13 | [5 empty] | Y | DW2 | 2.22% | DW23 | 48.89% | DW25P | 48.89% | [14 empty] | 1 | [48 empty] | 0
403567 | Park Crescent Torrance | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS7 | 2013-08-30 | 2014-12-11 | 2015-02-04 | 2015-07-16 | 2016-03-10 | East Dunbartonshire | 323184 | 323184 | 120116 | 5000 | 0 | 159424.79 | 0 | 0 | 284540.79 | 0 | 0 | 0 | 607724.79 | 0 | 0 | 0 | 0 | 607724.79 | 338633.31 | [5 empty] | N | FL_NAMED | 100%
504212 | Partick PS - Front Elevation remedial works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-06-05 |  | 2021-09-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 249.41 | 32006.6 | 32256 | 217743.67 | 0 | 0 | 249999.67 | 0 | 0 | 0 | 0 | 249999.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46194 | Partick SPS Refurb - SPS000366 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-17 | 2011-06-14 | 2011-08-22 | 2013-12-30 | 2014-02-25 | Glasgow City | 2957266.32 | 0 | 50697.84 | 0 | 0 | 0 | 0 | 0 | 50697.84 | 0 | 0 | 0 | 3007964.16 | 0 | 0 | 0 | 0 | 3007964.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501545 | Pateshill Raw Water Reservoir | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2016-01-27 | 2021-04-01 | 2022-03-10 | 2022-10-17 |  | West Lothian | 0 | 0 | 3689 | 18453.17 | 0 | 0 | 203.84 | -0.01 | 22346 | 327654.12 | 0 | 0 | 350000.12 | 0 | 0 | 0 | 0 | 350000.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501750 | Pateshill WTW - OMG4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-01-29 | 2016-03-07 | 2016-03-07 | 2016-03-31 | 2016-03-31 | West Lothian | 0 | 0 | 2462 | 7684.64 | 228.75 | 0 | 0 | 0 | 10375.39 | 0 | 0 | 0 | 10375.39 | 0 | 0 | 0 | 0 | 10375.39 | 1773.42 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
501389 | Pateshill WTW (Westwater Reservoir) Algae | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2020-11-23 | 2020-11-23 | 2021-07-02 | 2022-02-16 |  | West Lothian | 0 | 0 | 0 | 10046.51 | 0 | 638.7 | 0 | -10105.33 | 579.88 | 9875.4 | 0 | 0 | 10455.28 | 0 | 0 | 0 | 0 | 10455.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501397 | Pateshill WTW Raw Water Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2027-09-21 | 2028-07-17 | 2028-10-12 | 2029-11-09 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059117.01 | 0 | 0 | 1059117.01 | 0 | 0 | 0 | 0 | 1059117.01 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46822 | Pateshill WTW Refurb - WTW000626 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-05-07 | 2012-02-28 | 2012-08-20 | 2014-09-29 |  | West Lothian | 3031467.15 | 0 | -20087.4 | -3417.05 | 0 | 0 | 0 | 0 | -23504.45 | 0 | 0 | 0 | 3007962.7 | 0 | 0 | 0 | 0 | 3007962.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503440 | Pathhead WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-10-14 | 2024-07-15 | 2024-10-11 | 2025-07-29 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 59441.86 | 39733.04 | 21127.1 | 120302 | 629698.45 | 0 | 0 | 750000.45 | 0 | 0 | 0 | 0 | 750000.45 | 122419.09 | [5 empty] | N | SG1 | 100%
503544 | Patna WwTW Bathing Water Improvement | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MSU | 2022-08-08 | 2023-01-10 | 2023-04-12 | 2024-05-06 | 2024-08-06 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 27.55 | 74.82 | 102.37 | 4882689.94 | 0 | 0 | 4882792.31 | 0 | 1346772.0699 | 0 | 1346772.0699 | 6229564.3799 | 1035209.71 | [5 empty] | N | EC16B | 100%
501499 | PATNA WWTW NS414124 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-07-11 | 2020-08-07 | 2020-09-21 | 2022-02-11 |  | East Ayrshire | 0 | 0 | 0 | 43306.86 | 205553.08 | 24944.82 | 163347.24 | 1334675.4 | 1771827.4 | 1241141 | 0 | 0 | 3012968.4 | 0 | 0 | 82652.6 | 82652.6 | 3095621 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502865 | Payroll Oracle Cloud Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-09-29 | 2017-09-29 | 2017-09-29 | 2019-02-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 393561.79 | 513769.58 | -2039.38 | 0 | 905291.99 | 0 | 0 | 0 | 905291.99 | 0 | 0 | 0 | 0 | 905291.99 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403698 | PCCA Zone Rationalisation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-02-27 | 2016-07-29 | 2016-02-16 | 2015-10-30 |  | Scottish Water Wide | 74499 | 0 | 10759.1 | 175.36 | 0 | 0 | 0 | 0 | 10934.46 | 0 | 0 | 0 | 85433.46 | 0 | 0 | 0 | 0 | 85433.46 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502434 | Peat Inn & Denhead DMA - Cameron Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2020-10-01 | 2020-10-01 | 2028-07-24 | 2021-01-21 |  | Fife | 0 | 0 | 0 | 4764.74 | 365.02 | 21.29 | 2898.07 | -2579.43 | 5469.69 | 0 | 0 | 0 | 5469.69 | 0 | 0 | 0 | 0 | 5469.69 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509907 | Peddieston DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-10-20 | 2023-12-07 | 2024-03-18 | 2025-02-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 837.21 | 837.21 | 621938.77 | 0 | 0 | 622775.98 | 0 | 0 | 0 | 0 | 622775.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403973 | Peebles WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS4 | 2016-07-11 | 2018-11-05 | 2018-11-27 | 2020-11-09 |  | Scottish Borders | 2866.55 | 0 | 29088.45 | 75422.73 | 271147.21 | 1451750.32 | 1693906.75 | 65473.99 | 3586789.45 | 34666 | 0 | 0 | 3624322 | 0 | 0 | 0 | 0 | 3624322 | 0 | [5 empty] | N | SG1 | 100%
502613 | Pelstream Burn Crossing Stirling | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-08-28 | 2019-02-26 | 2019-06-10 | 2019-09-26 |  | Stirling | 0 | 0 | 0 | 1551.36 | 34662.64 | 73751 | 81992.31 | 0.69 | 191958 | 42 | 0 | 0 | 192000 | 0 | 0 | 0 | 0 | 192000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502554 | Pencaitland WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-04-15 | 2022-08-17 | 2022-12-20 | 2023-12-18 |  | East Lothian | 0 | 0 | 0 | 34581.06 | 9386.07 | 5741.56 | 3520.05 | 0.26 | 53229 | 81771.26 | 0 | 0 | 135000.26 | 0 | 0 | 0 | 0 | 135000.26 | 122419.09 | [5 empty] | N | SG1 | 100%
500171 | Penicuik DOA (DOA000526) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-04-29 | 2016-06-30 | 2017-06-29 | 2018-01-30 | Midlothian | 0 | 0 | 5000 | 33648 | 18769 | -3380.38 | 0 | 0 | 54036.62 | 0 | 0 | 0 | 54036.62 | 0 | 0 | 0 | 0 | 54036.62 | 93101.22 | [5 empty] | N | EC01D | 7.47% | CS16D | 18.51% | EC01G | 37.01% | EC10E | 37.01%
30573 | Penicuik STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-17 | 2010-09-20 | 2011-03-15 | 2012-01-27 | 2012-02-10 | Midlothian | 568855.38 | 0 | -13342.3 | 0 | 0 | 0 | 0 | 0 | -13342.3 | 0 | 0 | 0 | 555513.08 | 0 | 0 | 0 | 0 | 555513.08 | 119362.42 | [5 empty] | N | CM_WWNI | 20% | EC01A | 80%
502810 | Penicuik WWTW - Aeration Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-08-01 | 2017-08-01 | 2018-03-30 | 2019-11-28 |  | Midlothian | 0 | 0 | 0 | 0 | 43591.23 | 236038.7 | 267627.15 | -22027.08 | 525230 | 0 | 0 | 0 | 525230 | 0 | 0 | 0 | 0 | 525230 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503223 | Penicuik WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-05-25 | 2024-04-19 | 2024-07-19 | 2026-01-02 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 83888.74 | 36338.47 | 97082.79 | 217310 | 4584481.27 | 0 | 0 | 4801791.27 | 0 | 0 | 0 | 0 | 4801791.27 | 122419.09 | [5 empty] | N | SG1 | 100%
45570 | Peninver WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-19 | 2011-09-28 | 2012-07-18 | 2013-09-10 | 2014-01-27 | Argyll and Bute-North Argyll | 1105298.15 | 0 | -6287.87 | 0 | 0 | 0 | 0 | 0 | -6287.87 | 0 | 0 | 0 | 1099010.28 | 0 | 0 | 0 | 0 | 1099010.28 | 28761.13 | [5 empty] | N | DW23 | 100%
501501 | Pentland & Slaemuir Ave Port Glasgow - Replace sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-02-22 | 2017-12-18 | 2018-02-09 | 2019-08-30 |  | Inverclyde | 0 | 0 | 3342.34 | 7037.66 | 181877.63 | 608155.24 | 172688.13 | 1899 | 975000 | 0 | 0 | 0 | 975000 | 0 | 0 | 0 | 0 | 975000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403359 | Penwhapple Reservoir - Spillway Improvement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-04-29 | 2014-07-31 | 2014-07-31 | 2015-03-30 |  | South Ayrshire | 2427033.35 | 0 | 113007.6 | 3211.91 | 12834.76 | 0 | 0 | 0 | 129054.27 | 0 | 0 | 0 | 2556087.62 | 0 | 0 | 0 | 0 | 2556087.62 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501575 | Penwhapple WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-01-12 | 2017-03-06 | 2017-03-06 | 2017-08-31 | 2017-10-31 | South Ayrshire | 0 | 0 | 0.07 | 1073.31 | 676.04 | 0.01 | 0 | 0 | 1749.42 | 0 | 0 | 0 | 1749.42 | 0 | 0 | 0 | 0 | 1749.42 | 105615.47 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
505389 | Penwhapple WTW - Chemical Spill Tank Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-03-06 | 2020-12-17 | 2021-05-27 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12773 | 12773 | 3120.56 | 0 | 0 | 15893.56 | 0 | 0 | 0 | 0 | 15893.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503742 | Penwhapple WTW - Performance Improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-10-03 | 2021-10-11 | 2021-12-13 | 2022-07-20 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 4053.13 | 98098.42 | 102151.55 | 400300.86 | 0 | 0 | 502452.41 | 0 | 0 | 0 | 0 | 502452.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506261 | Penwhirn Reservoir Scour Restriction Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-08-20 | 2021-01-22 | 2021-02-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 14000 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 14000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507169 | Penwhirn WTW - Abandoned Washwater Tanks Demolition | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-06-22 | 2021-02-26 | 2021-05-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8222 | 8222 | 20744.8 | 0 | 0 | 28966.8 | 0 | 0 | 0 | 0 | 28966.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503356 | Penwhirn WTW - Additional Hypochlorite Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-03-12 | 2021-07-05 | 2021-10-04 | 2022-05-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 1962.62 | 31784.98 | 14080.4 | 47828 | 658159.81 | 0 | 0 | 705987.81 | 0 | 0 | 0 | 0 | 705987.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506183 | Penwhirn WTW - Ortho Bund Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-05 | 2020-11-09 | 2022-01-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7384 | 7384 | 59426.3 | 0 | 0 | 66810.3 | 0 | 0 | 0 | 0 | 66810.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502636 | Perkhill Road Lumphanan | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-17 | 2017-07-25 | 2017-07-28 | 2017-08-30 | 2017-08-30 | Aberdeenshire | 0 | 0 | 0 | 468.32 | 5753.75 | 0 | 0 | 0 | 6222.07 | 0 | 0 | 0 | 6222.07 | 0 | 0 | 0 | 0 | 6222.07 | 38730.22 | [5 empty] | N | CS23W | 100%
501099 | Perth & Kinross Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-01-22 | 2016-03-01 | 2016-03-04 | 2016-03-04 | Perth and Kinross | 0 | 0 | 2071.38 | 306.66 | 0 | 0 | 0 | 0 | 2378.04 | 0 | 0 | 0 | 2378.04 | 0 | 0 | 0 | 0 | 2378.04 | 0 | [5 empty] | N | EC10D | 100%
500168 | Perth City DOA (DOA000674) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS7 | 2015-03-26 | 2016-09-30 | 2016-09-30 | 2019-05-30 | 2020-01-08 | Perth and Kinross | 0 | 0 | 33270 | 284033 | 473530 | 193883.24 | 78221.76 | 5937.61 | 1068875.61 | 0 | 0 | 0 | 1068875.61 | 0 | 0 | 0 | 0 | 1068875.61 | 349451.88 | [5 empty] | N | CS11 | 19.85% | CS16D | 80.15%
45633 | Perth City STW Refurb - STW001712 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-06-28 | 2011-09-30 | 2013-03-28 |  | Perth and Kinross | 1974705.5 | 0 | -6148.15 | -1044.45 | 0 | 0 | 0 | 0 | -7192.6 | 0 | 0 | 0 | 1967512.9 | 0 | 0 | 0 | 0 | 1967512.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500635 | Perth City WwTW - Upgrade Access Road (Lower Friarton) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-20 | 2016-11-21 | 2016-11-21 | 2017-05-29 |  | Perth and Kinross | 0 | 0 | 101145 | 389458.35 | 151578.6 | 29848.55 | -936.13 | 0 | 671094.37 | 0 | 0 | 0 | 671094.37 | 0 | 0 | 0 | 0 | 671094.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502067 | Perth City WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2020-01-16 | 2021-03-30 | 2021-05-04 | 2022-03-10 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 9824 | 174753.98 | 184577.98 | 988624.02 | 0 | 0 | 1173202 | 0 | 0 | 93856.16 | 93856.16 | 1267058.16 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500210 | Perth- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS6 | 2015-03-20 | 2017-09-29 | 2017-09-29 | 2019-03-15 | 2019-09-30 | Perth and Kinross | 0 | 0 | 1000 | 29934 | 206004 | 403391.82 | 93913.44 | 10409.73 | 744652.99 | -6377.34 | -6377.34 | -8852.8336 | 738275.65 | -2475.4936 | 0 | 0 | -2475.4936 | 735800.1564 | 323388.43 | [5 empty] | N | DW5 | 100%
45801 | Perth Friarton SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-07-29 | 2011-08-09 | 2011-07-01 | 2011-07-01 | Perth and Kinross | 43397.64 | 0 | 4105.34 | 0 | 0 | 0 | 0 | 0 | 4105.34 | 0 | 0 | 0 | 47502.98 | 0 | 0 | 0 | 0 | 47502.98 | 119362.42 | [5 empty] | N | CM_WWNI | 8.488% | WQ01C | 91.51%
500868 | Perth RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-03-09 | 2018-09-18 | 2018-10-24 | 2019-09-30 | 2020-04-30 | Perth and Kinross | 0 | 0 | 19786.85 | 7325.15 | 24264.45 | 87513.77 | 81837.38 | 2321.4 | 223049 | 2000 | 2000 | 2776.3405 | 225049 | 776.3405 | 0 | 0 | 776.3405 | 225825.3405 | 582864.01 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 68.77 | [43 empty] | 0
503690 | Perth RWI - River Anti Pollution Measures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-12-27 | 2023-09-01 | 2024-01-04 | 2025-07-30 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 58718.36 | -22778.36 | 35940 | 414060.11 | 0 | 0 | 450000.11 | 0 | 0 | 0 | 0 | 450000.11 | 119022.58 | [5 empty] | N | CM_WSI | 100%
502933 | Perth STC - Enabling Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-10-31 | 2018-07-04 | 2018-11-26 | 2021-01-28 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 4549.71 | 285639.79 | 278114.79 | 13286.67 | 581590.96 | 1451.34 | 0 | 0 | 583042.3 | 0 | 0 | 0 | 0 | 583042.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
46745 | Perth STW - Enhancement of Sludge Treatment Facilities | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-16 | 2011-06-28 | 2011-09-30 | 2013-11-28 | 2014-01-27 | Perth and Kinross | 7874424.69 | 0 | -54121.36 | 20288.55 | 0 | 0 | 0 | 0 | -33832.81 | 0 | 0 | 0 | 7840591.88 | 0 | 0 | 0 | 0 | 7840591.88 | 28761.13 | [5 empty] | N | EC06 | 100%
402012 | Perth WWTW Inlet SPS | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-04-11 | 2014-07-02 | 2014-07-02 | 2015-03-18 | 2015-03-19 | Perth and Kinross | 2527497.73 | 0 | 113186.6 | 26203.18 | 0 | 0 | 0 | 0 | 139389.78 | 0 | 0 | 0 | 2666887.51 | 0 | 0 | 0 | 0 | 2666887.51 | 0 | [5 empty] | N | WQ01C | 100%
504736 | Peterhead Buchanhaven WWPS Penstock service/repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-11-24 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 20972 | 44380.37 | 65352.37 | 0 | 0 | 0 | 65352.37 | 0 | 0 | 0 | 0 | 65352.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500172 | Peterhead DOA (DOA000361) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-03-31 | 2016-08-08 | 2018-09-30 | 2018-11-30 | Aberdeenshire | 0 | 0 | 32752 | 18476.81 | 61423.19 | 56589 | 9825.37 | 0 | 179066.37 | 0 | 0 | 0 | 179066.37 | 0 | 0 | 0 | 0 | 179066.37 | 4617.88 | [5 empty] | Y | EC01G | 10.35% | CS16D | 89.65% | [37 empty] | 1 | [27 empty] | 0
506577 | Peterhead DOA Merchant St Sewer Relay | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-05-26 | 2021-10-11 | 2022-01-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22665 | 22665 | 20134.82 | 0 | 0 | 42799.82 | 0 | 0 | 0 | 0 | 42799.82 | 209381.79 | [5 empty] | N | CM_WWI | 100%
46258 | Peterhead Newfield WPS SR10 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-03-30 | 2009-02-17 | 2011-09-05 | 2012-03-29 |  | Aberdeenshire | 448551.62 | 0 | 620 | 0 | 0 | 0 | 0 | 0 | 620 | 0 | 0 | 0 | 449171.62 | 0 | 0 | 0 | 0 | 449171.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403277 | Ph 3 East Dunfermline WWTW Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-05-21 | 2015-03-26 | 2015-07-08 | 2015-12-04 |  | Fife | 283861.46 | 0 | 753282.18 | 2455.31 | 809.46 | 0 | 0 | 0 | 756546.95 | 0 | 0 | 0 | 1040408.41 | 0 | 0 | 0 | 0 | 1040408.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403278 | Ph 3 East Fochabers WWTW Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-08 | 2014-08-13 | 2014-08-13 | 2014-08-14 |  | Moray | 126036.93 | 0 | -33.92 | 0 | 0 | 0 | 0 | 0 | -33.92 | 0 | 0 | 0 | 126003.01 | 0 | 0 | 0 | 0 | 126003.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403280 | Ph 3 East Forres WWTW Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-01-10 | 2015-09-22 | 2015-09-16 | 2015-04-21 |  | Moray | 191256 | 0 | 5254.57 | 0 | 0 | 0 | 0 | 0 | 5254.57 | 0 | 0 | 0 | 196510.57 | 0 | 0 | 0 | 0 | 196510.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403279 | Ph 3 Head of Works STC Kirkwall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-01 | 2014-06-30 | 2014-04-16 | 2014-04-16 |  | Orkney Islands | 83247.73 | 0 | 3183.73 | 0 | 0 | 0 | 0 | 0 | 3183.73 | 0 | 0 | 0 | 86431.46 | 0 | 0 | 0 | 0 | 86431.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500170 | Philipshill DOA (DOA000616) & Allers DOA (DOA000617) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS7 | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-05-31 | 2020-01-08 | South Lanarkshire | 0 | 0 | 73937.35 | 308628.65 | 234930 | 117125 | 70300 | 20340.17 | 825261.17 | 0 | 0 | 0 | 825261.17 | 0 | 0 | 0 | 0 | 825261.17 | 349451.88 | [5 empty] | N | CS11 | 18.97% | CS16D | 81.03%
402987 | Philipshill Storm Return Pumping Station | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-30 | 2013-03-05 | 2013-03-18 | 2015-09-21 |  | South Lanarkshire | 258787 | 0 | 5450 | 0.31 | -3186.45 | 0 | 0 | 0 | 2263.86 | 0 | 0 | 0 | 261050.86 | 0 | 0 | 0 | 0 | 261050.86 | 209381.79 | [5 empty] | N | CM_WWI | 100%
46355 | Philipshill STW Refurb - STW000576 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-06-01 | 2011-09-21 | 2011-10-31 | 2016-02-16 |  | South Lanarkshire | 2838709.32 | 0 | 13753.03 | -16535.04 | 600.6 | 0 | 0 | 0 | -2181.41 | 0 | 0 | 0 | 2836527.91 | 0 | 0 | 0 | 0 | 2836527.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503224 | Philipshill WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-03-17 | 2025-01-08 | 2025-04-07 | 2026-05-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 65219.25 | 746.42 | 23734.33 | 89700 | 1910300.55 | 0 | 0 | 2000000.55 | 0 | 0 | 0 | 0 | 2000000.55 | 122419.09 | [5 empty] | N | SG1 | 100%
502691 | Philipshill WWTW - Phase B Aeration replacement - 5026910000 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2028-05-26 | 2028-09-18 | 2029-04-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250250.11 | 0 | 0 | 250250.11 | 0 | 0 | 0 | 0 | 250250.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501807 | Philipshill WWTW Grade 5 HC Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2020-01-16 | 2020-06-30 | 2020-08-31 | 2021-06-10 |  | South Lanarkshire | 0 | 0 | 0 | 6082.77 | 204.16 | 0 | 26362.07 | 370029 | 402678 | 0 | 0 | 0 | 402678 | 0 | 0 | 0 | 0 | 402678 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500211 | Picketlaw- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS4 | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-06-27 | 2021-06-15 | East Renfrewshire | 0 | 0 | 38753 | 47802.42 | 79902.25 | 81330.83 | 54709.26 | 27851.24 | 330349 | 5886.56 | 5886.56 | 34366.8627 | 336235.56 | 28480.3027 | 0 | -0.0027 | 28480.3 | 364715.86 | 2107629.1 | [5 empty] | N | DW5FS | 100%
506791 | Picketlaw Reservoir Responsive Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-05-26 |  | 2021-08-18 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4738.22 | 4738.22 | 8261.79 | 0 | 0 | 13000.01 | 0 | 0 | 0 | 0 | 13000.01 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500869 | Picketlaw RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-04-12 | 2017-03-30 | 2017-03-31 | 2018-08-31 | 2018-12-31 | East Renfrewshire | 0 | 0 | 2671.71 | 7621.29 | 98587 | 54146.78 | -9429.05 | 0 | 153597.73 | 3911.94 | 3911.9375 | 5430.4352 | 157509.67 | 1518.4977 | 0 | 0 | 1518.4977 | 159028.1677 | 242534.78 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 54.07 | [43 empty] | 0
501214 | Picketlaw WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-21 | 2016-09-06 | 2016-09-07 | 2016-09-30 | 2016-09-30 | South Lanarkshire | 0 | 0 | 761.13 | 1179.66 | 207.95 | 0 | 0 | 0 | 2148.74 | 0 | 0 | 0 | 2148.74 | 0 | 0 | 0 | 0 | 2148.74 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
505248 | Picketlaw WTW - Investigation on Chemical Spill Tank Ingress | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-27 |  | 2020-10-06 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 87.76 | 5704.57 | 5792.33 | 4207.8 | 0 | 0 | 10000.13 | 0 | 0 | 0 | 0 | 10000.13 | 119022.58 | [5 empty] | N | WSNI | 100%
404132 | Picketlaw WTW - Main Out | Q&S3B | Completion | OMG180 |  |  | Water | DWQR | WINF | OMG180 | MS3 | 2013-06-30 | 2016-01-31 | 2016-02-29 | 2023-03-20 | 2023-06-13 | East Renfrewshire | 0 | 0 | 0 | 11661.8 | 76869.1 | 243010.9 | -34218.01 | 853342.11 | 1150665.9 | 6728904.12 | 6728904.12 | 10753213.3288 | 7879570.02 | 4024309.2088 | 0 | 0 | 4024309.2088 | 11903879.2288 | 0 | [5 empty] | Y | DW25 | 100% | [20 empty] | 1 | [46 empty] | 0
503550 | Picketlaw WTW - Purchase Install & Commission Polymer Dosing Equipment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2020-03-26 | 2020-06-23 | 2021-08-06 | 2022-09-15 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9910 | 9910 | 10090.11 | 0 | 0 | 20000.11 | 0 | 0 | 0 | 0 | 20000.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505250 | Picketlaw WTW S14 & S15 Chambers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-27 |  | 2020-10-07 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 1351.62 | 11863.78 | 13215.4 | 0 | 0 | 0 | 13215.4 | 0 | 0 | 0 | 0 | 13215.4 | 119022.58 | [5 empty] | N | WSNI | 100%
500671 | Pier Road Balloch Sewer Replacment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-06-11 | 2017-01-30 | 2017-02-20 | 2017-10-27 |  | West Dunbartonshire | 0 | 0 | 22800 | 185033 | 51130 | -5687 | 1240.33 | 554.1 | 255070.43 | 0 | 0 | 0 | 255070.43 | 0 | 0 | 0 | 0 | 255070.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501658 | Pier Road-Cromlech Road Dunoon - Relay sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2020-08-31 | 2022-07-28 | 2022-10-25 | 2023-05-25 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 3834.94 | 526.76 | 12186.85 | 9.24 | 9944 | 26501.78 | 111025.22 | 0 | 0 | 137527 | 0 | 0 | 0 | 0 | 137527 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502209 | Pipebridge H&S Improvements East Region | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-05-09 | 2016-08-01 | 2016-09-30 | 2022-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 439137.02 | 938796.76 | 543444.37 | 277630.25 | 92691.05 | 2291699.45 | 28654.7 | 0 | 0 | 2320354.15 | 0 | 0 | 0 | 0 | 2320354.15 | 328404.37 | [5 empty] | N | CM_M&G | 100%
502201 | Pipebridge H&S Improvements North Region | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-04-18 | 2016-11-21 | 2017-07-04 | 2021-09-24 |  | Scottish Water Wide | 0 | 0 | 0 | 69618.94 | 74409.97 | 84999.06 | 362031.04 | 23477.99 | 614537 | -2.47 | 0 | 0 | 614534.53 | 0 | 0 | 0 | 0 | 614534.53 | 328404.37 | [5 empty] | N | CM_M&G | 100%
502202 | Pipebridge H&S Improvements South Region | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-05-04 | 2016-08-30 | 2016-10-25 | 2021-12-28 |  | Scottish Water Wide | 0 | 0 | 0 | 83884.46 | 568627.74 | 683256 | 315070.62 | 75187.68 | 1726026.5 | 412386 | 0 | 0 | 2138412.5 | 0 | 0 | 0 | 0 | 2138412.5 | 328404.37 | [5 empty] | N | CM_M&G | 100%
502203 | Pipebridge H&S Improvements West Region | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-04-18 | 2016-08-30 | 2016-11-28 | 2021-12-16 |  | Scottish Water Wide | 0 | 0 | 0 | 127858.7 | 544404.81 | 517974.26 | 444174.09 | 22916.14 | 1657328 | 611661.69 | 0 | 0 | 2268989.69 | 0 | 0 | 0 | 0 | 2268989.69 | 328404.37 | [5 empty] | N | CM_M&G | 100%
501611 | PITENWEEM WEST SHORE WWPS NO547024 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2028-02-21 | 2028-12-20 | 2029-04-25 | 2029-09-04 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141670.93 | 0 | 0 | 141670.93 | 0 | 0 | 0 | 0 | 141670.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500967 | Pitscottie WwPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-10-21 | 2018-03-14 | 2018-05-23 | 2020-02-14 |  | Fife | 0 | 0 | 7151.89 | 17447.11 | 184000 | 514970.76 | 69299.12 | 16289.12 | 809158 | 1336 | 0 | 0 | 810494 | 0 | 0 | 0 | 0 | 810494 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403625 | Pittenweem Model Build | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-12-17 | 2014-04-23 | 2014-04-29 | 2015-01-23 |  | Fife | 116099 | 0 | 6614.1 | 0 | 0 | 0 | 0 | 0 | 6614.1 | 0 | 0 | 0 | 122713.1 | 0 | 0 | 0 | 0 | 122713.1 | 418763.58 | [5 empty] | N | CM_WWI | 100%
30585 | Plains STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-15 | 2012-05-29 | 2012-08-20 | 2014-08-14 | 2014-09-29 | North Lanarkshire | 8537337.19 | 0 | 32812.02 | 55334.5 | 0 | 0 | 0 | 0 | 88146.52 | 0 | 0 | 0 | 8625483.71 | 0 | 0 | 0 | 0 | 8625483.71 | 270542.64 | [5 empty] | N | CM_WWNI | 5% | SG1 | 5% | EC10A | 40% | EC04A | 50%
502543 | Plains WwTW DOA - Moffat View Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-02-23 | 2017-02-23 | 2017-03-01 | 2017-03-31 |  | North Lanarkshire | 0 | 0 | 0 | 42523.36 | 820908.49 | -690.74 | 300.68 | 0 | 863041.79 | 0 | 0 | 0 | 863041.79 | 0 | 0 | 0 | 0 | 863041.79 | 209381.79 | [5 empty] | N | CM_WWI | 100%
404010 | Plan Attainment- Cost of Failure | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-03-29 | 2017-04-03 | 2017-04-03 | 2017-04-03 |  | Scottish Water Wide | 173465.68 | 0 | 56598.32 | -939.21 | 0 | 0 | 0 | 0 | 55659.11 | 0 | 0 | 0 | 229124.79 | 0 | 0 | 0 | 0 | 229124.79 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501223 | Planned Cleaning Programme - PCP | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2015-12-22 | 2016-05-18 | 2017-06-26 | 2021-06-09 |  | Scottish Water Wide | 0 | 0 | 33776.17 | 143894.46 | 18189.12 | 287613.25 | -140940.57 | 617174.57 | 959707 | 517142.64 | 0 | 0 | 1476849.64 | 0 | 0 | 0 | 0 | 1476849.64 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500708 | Planned Preventative Maintenance (Flushing & Swabbing) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2017-01-11 |  | Scottish Water Wide | 0 | 0 | 2662000 | 226225.11 | 17415.43 | 0 | 0 | 0 | 2905640.54 | 0 | 0 | 0 | 2905640.54 | 0 | 0 | 0 | 0 | 2905640.54 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502675 | Planned Preventative Maintenance (Year 3) 2017 to 2018 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-08-30 | 2017-09-26 | 2017-09-26 | 2021-06-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 2626405.26 | 2300251.78 | -1647730.68 | -576147.36 | 2702779 | 0 | 0 | 0 | 2702779 | 0 | 0 | 0 | 0 | 2702779 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503059 | Planned Preventative Maintenance (Year 4) 2018 to 2019 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-03-12 | 2019-03-28 | 2019-03-28 | 2021-06-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 3753.5 | 109964.69 | 1797653.63 | 799029.18 | 2710401 | 452599.34 | 0 | 0 | 3163000.34 | 0 | 0 | 0 | 0 | 3163000.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502261 | Planned Preventative Maintenance Year 2 (2016 - 2017) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-07-13 | 2016-07-13 | 2016-08-01 | 2021-06-30 |  | Scottish Water Wide | 0 | 0 | 0 | 1342187.81 | 922812.19 | 0 | 55.1 | -74941.99 | 2190113.11 | 0 | 0 | 0 | 2190113.11 | 0 | 0 | 0 | 0 | 2190113.11 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501718 | Plantation Avenue Patna - Relay sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-10-21 |  | East Ayrshire | 0 | 0 | 0 | 3313.17 | 0 | 0 | 0 | 0 | 3313.17 | 0 | 0 | 0 | 3313.17 | 0 | 0 | 0 | 0 | 3313.17 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506650 | Plean WwTW - FST scraper bridge refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-07-29 | 2021-03-03 | 2021-10-28 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21278.03 | 21278.03 | 148721.98 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 170000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502319 | PMAP - Pollution Management Action Plan - Year 2 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2016-08-23 | 2016-08-23 | 2016-10-26 | 2017-09-25 | 2017-09-25 | Scottish Water Wide | 0 | 0 | 0 | 886608.99 | 277965.1 | 391.69 | -307.91 | 0 | 1164657.87 | 0 | 0 | 0 | 1164657.87 | 0 | 0 | 0 | 0 | 1164657.87 | 1470767.03 | [5 empty] | N | SG5 | 100%
505612 | PMAP - Pollution Management Action Plan - Year 6 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2020-03-20 | 2020-03-30 | 2020-08-03 | 2021-09-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297311 | 297311 | 402689.14 | 0 | 0 | 700000.14 | 0 | 0 | 0 | 0 | 700000.14 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502715 | PMAP - Pollution Management Action Plan Yr3 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2017-05-04 | 2017-05-04 | 2017-06-01 | 2018-10-01 | 2018-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 887640.95 | 245976.99 | -22958.36 | 0 | 1110659.58 | 0 | 0 | 0 | 1110659.58 | 0 | 0 | 0 | 0 | 1110659.58 | 1470767.03 | [5 empty] | N | SG5 | 100%
503130 | PMAP - Pollution Management Action Plan Yr4 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2018-08-31 | 2018-08-31 | 2018-09-17 | 2019-07-15 | 2019-07-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 575695.62 | 19293.38 | -2482.55 | 592506.45 | 0 | 0 | 0 | 592506.45 | 0 | 0 | 0 | 0 | 592506.45 | 1470767.03 | [5 empty] | N | SG5 | 100%
503560 | PMAP - Pollution Management Action Plan Yr5 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS4 | 2019-03-26 | 2019-03-26 | 2019-06-03 | 2021-03-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 186000 | 736000 | 0 | 0 | 0 | 736000 | 0 | 0 | 0 | 0 | 736000 | 1470767.03 | [5 empty] | N | SG5 | 100%
501296 | PMAP Holding Line - SR15 Yr2-6 -Wastewater | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2021-04-15 | 2021-05-01 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 20.22 | 0 | 0 | -20.22 | 0 | -20.22 | 0 | 0 | -20.22 | 0 | 0 | 0 | 0 | -20.22 | 1470767.03 | [5 empty] | N | SG5 | 100%
46411 | Pollocktown PS Refurb - TWP000189 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-20 | 2011-12-29 | 2011-12-19 |  | East Renfrewshire | 40766.39 | 0 | 3291.78 | 0 | 0 | 0 | 0 | 0 | 3291.78 | 0 | 0 | 0 | 44058.17 | 0 | 0 | 0 | 0 | 44058.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500433 | Pollution Management Action Plan | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-11 | 2016-09-22 |  | Scottish Water Wide | 0 | 0 | 984391 | -25695.61 | 431.52 | 0 | 0 | 0 | 959126.91 | 0 | 0 | 0 | 959126.91 | 0 | 0 | 0 | 0 | 959126.91 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500908 | Poolewe WOA Melvaig South SR (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-06-30 | 2016-06-30 | Argyll and Bute-North Argyll | 0 | 0 | 3010 | -149.81 | 0 | 0 | 0 | 0 | 2860.19 | 0 | 0 | 0 | 2860.19 | 0 | 0 | 0 | 0 | 2860.19 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
502838 | Poolewe WTW Growth SR21 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2020-05-07 |  | Highland | 0 | 0 | 0 | 0 | 21346.13 | 1340.34 | 0 | -19644.38 | 3042.09 | 0 | 0 | 0 | 3042.09 | 0 | 0 | 0 | 0 | 3042.09 | 122419.09 | [5 empty] | N | WG1 | 100%
403415 | Port Appin Septic Tank and Outfall Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-12-05 | 2015-01-12 |  | Argyll and Bute-North Argyll | 286000 | 0 | 0 | -2765.58 | 0 | 0 | 0 | 0 | -2765.58 | 0 | 0 | 0 | 283234.42 | 0 | 0 | 0 | 0 | 283234.42 | 299983.07 | [5 empty] | N | CM_WWI | 40.15% | CM_WWNI | 59.85%
504012 | Port Charlotte Caustic Dosing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2019-12-04 | 2020-11-23 | 2021-05-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 22960.36 | 108202.64 | 131163 | 38837 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 170000 | 311236.79 | [5 empty] | N | WSI | 100%
502368 | Port Charlotte Clear Water Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2021-02-24 | 2021-02-24 | 2029-01-23 | 2030-08-19 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 35762.48 | 33128.44 | 1957.09 | 13437.92 | -13196.38 | 71089.55 | 1401167.54 | 0 | 0 | 1472257.09 | 0 | 0 | 0 | 0 | 1472257.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502131 | Port Charlotte STW Outfall Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 18464.01 | 0 | 0 | 0 | 0 | 18464.01 | 0 | 0 | 0 | 18464.01 | 0 | 0 | 0 | 0 | 18464.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500776 | Port Charlotte WOA Conisby SR Abandonment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-08-24 | 2020-03-02 | 2020-03-02 | 2019-06-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 28311 | 68658.02 | 10961.58 | -38615.8 | 30768.27 | 0 | 100083.07 | 0 | 0 | 0 | 100083.07 | 0 | 0 | 0 | 0 | 100083.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507368 | Port Charlotte WTW - Clarifier Tanks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-03-30 | 2023-11-24 | 2024-02-20 | 2025-04-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27261.65 | 27261.65 | 972738.35 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508574 | Port Charlotte WTW - PLC Replacement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-03-30 | 2023-10-18 | 2024-01-17 | 2024-10-25 | 2025-10-27 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269.09 | 5269.09 | 244730.91 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | [5 empty] | N | SR21_WA | 100%
403020 | Port Charlotte WTW Chemical Dosing Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-10-30 | 2012-10-30 | 2012-12-03 | 2013-11-22 |  | Argyll and Bute-Cowal & Bute | 414439 | 0 | 214.68 | 0 | 0 | 0 | 0 | 0 | 214.68 | 0 | 0 | 0 | 414653.68 | 0 | 0 | 0 | 0 | 414653.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502869 | Port Charlotte WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-26 | 2020-04-08 | 2020-04-08 | 2020-05-22 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 21238 | 3195.35 | 5533.21 | -14424.09 | 15542.46 | 0 | 0 | 0 | 15542.46 | 0 | 0 | 0 | 0 | 15542.46 | 122419.09 | [5 empty] | N | WG1 | 100%
501378 | Port Ellen TPS1 Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-04-12 | 2017-06-20 | 2017-06-26 | 2018-03-07 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 93085 | 721499 | -4316.51 | -18855.03 | 87.78 | 791500.24 | 0 | 0 | 0 | 791500.24 | 0 | 0 | 0 | 0 | 791500.24 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403431 | Port Glasgow Road Kilmacolm | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS4 | 2013-04-16 | 2019-03-26 | 2019-06-24 | 2020-07-10 |  | Renfrewshire | 44912.9 | 44912.9 | 47506.97 | 43854.13 | 67779 | 441132 | 1867472.4 | 184442.77 | 2652187.27 | 6736 | 0 | 0 | 2703836.17 | 0 | 0 | 0 | 0 | 2703836.17 | 180449.74 | [5 empty] | N | FL_DD | 100%
404095 | Portfolio Acceleration Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-12-24 | 2015-02-19 | 2015-02-19 | 2016-06-14 |  | Scottish Water Wide | 199676 | 0 | 877400.01 | -20923.38 | 0 | 0 | 0 | 0 | 856476.63 | 0 | 0 | 0 | 1056152.63 | 0 | 0 | 0 | 0 | 1056152.63 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501577 | Portfolio Programme and Project Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS4 | 2017-02-28 | 2018-04-30 | 2018-04-30 | 2020-03-13 |  | Scottish Water Wide | 0 | 0 | 92596 | 1068720.1 | 4018802.17 | 5267213.73 | 5442619.04 | -742866.04 | 15147085 | 0 | 0 | 0 | 15147085 | 0 | 0 | 0 | 0 | 15147085 | 306661.32 | [5 empty] | N | CM_M&G | 100%
510621 | Portmore DIR - Vegetation Removal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-01-28 | 2021-07-16 | 2022-02-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8419.03 | 8419.03 | 41580.98 | 0 | 0 | 50000.01 | 0 | 0 | 0 | 0 | 50000.01 | 311236.79 | [5 empty] | N | CM_WSI | 100%
300033 | Portobello Water Quality Study - Further Investigations | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-03-21 | 2012-06-15 | 2012-06-15 | 2015-01-09 | 2015-01-09 | City of Edinburgh | 83839 | 0 | -5842.4 | 0 | 0 | 0 | 0 | 0 | -5842.4 | 0 | 0 | 0 | 77996.6 | 0 | 0 | 0 | 0 | 77996.6 | 0 | [5 empty] | N | EC02B | 100%
300024 | Portobello Water Quality Study - Further Investigations | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2011-09-29 | 2019-01-23 | 2019-01-03 | 2019-01-16 | 2019-01-16 | City of Edinburgh | 243.9 | 0 | 46251.1 | -46251.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243.9 | 0 | 0 | 0 | 0 | 243.9 | 0 | [5 empty] | N | EC01C | 100%
403757 | Portobello West BW - Improvements to CSOs impacting Braid Burn and Bathing Water | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | SWMD | Ring Fenced Environmental | MS5 | 2014-03-31 | 2019-03-21 | 2019-03-21 | 2020-05-11 | 2020-10-31 | City of Edinburgh | 82211 | 0 | 1921 | 90735.57 | 334550.43 | 1566752 | 476362 | 6367 | 2476688 | 41100.66 | 41100.66 | 57054.7133 | 2599999.66 | 15954.0533 | 0 | 0 | 15954.0533 | 2615953.7133 | 0 | [5 empty] | Y | EC16 | 100% | [38 empty] | 1 | [28 empty] | 0
503732 | Portree - Braes DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2019-09-30 | 2021-11-22 | 2022-01-24 | 2022-10-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 12903.95 | 34664.05 | 47568 | 836838.04 | 0 | 0 | 884406.04 | 0 | 0 | 0 | 0 | 884406.04 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403677 | Portree Storr Forest WTW Emergency Temporary Crypto Barrier | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-12-20 | 2013-01-30 | 2014-04-09 | 2016-12-22 | 2017-06-30 | Highland | 1137229 | 0 | 1531475 | 448847.37 | 97927.88 | -81292.32 | 2997.49 | -2997.49 | 1996957.93 | 0 | 0 | 0 | 3134186.93 | 0 | 0 | 0 | 0 | 3134186.93 | 0 |  |  |  |  | 91884 | N | DW23 | 100%
502622 | Portree Torvaig WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-06 | 2020-04-06 | 2020-04-06 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 20930.23 | 415.9 | 2390.44 | 4231.17 | -22762.43 | 5205.31 | 0 | 0 | 0 | 5205.31 | 0 | 0 | 0 | 0 | 5205.31 | 122419.09 | [5 empty] | N | WG1 | 100%
509688 | Portskerra ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-10-13 | 2025-08-11 | 2025-11-03 | 2026-12-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63041 | 63041 | 1936959.27 | 0 | 0 | 2000000.27 | 0 | 0 | 0 | 0 | 2000000.27 | 122419.09 | [5 empty] | N | SG1 | 100%
402137 | Post Project Water Quality Sampling and Reporting- SWW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS4 | 2011-07-15 | 2011-09-26 | 2011-09-26 | 2020-10-13 |  | Scottish Water Wide | 580324.41 | 0 | 27902.59 | 48273 | 25000 | 0 | 9109.95 | 5890.05 | 116175.59 | 0 | 0 | 0 | 696500 | 0 | 0 | 0 | 0 | 696500 | 0 | [5 empty] | N | DW5A | 100%
400064 | Powburn PS Prestwick Refurb SPS000381 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2011-10-27 | 2011-10-31 | 2011-12-14 |  | South Ayrshire | 185587.15 | 0 | -251.23 | 0 | 0 | 0 | 0 | 0 | -251.23 | 0 | 0 | 0 | 185335.92 | 0 | 0 | 0 | 0 | 185335.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503324 | Powmill WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-08-05 | 2029-01-17 | 2029-05-09 | 2030-05-07 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 68716.44 | 4332.26 | 0.3 | 73049 | 0 | 0 | 0 | 73049 | 0 | 0 | 0 | 0 | 73049 | 122419.09 | [5 empty] | N | SG1 | 100%
401004 | Pre - QS II Capital Projects Land Cost run-offs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2012-05-16 | 2012-06-04 | 2015-11-03 |  | Scottish Water Wide | 2795547 | 0 | -70396.2 | 142 | 0 | 0 | 0 | 0 | -70254.2 | 0 | 0 | 0 | 2725292.8 | 0 | 0 | 0 | 0 | 2725292.8 | 730242.44 | [5 empty] | N | WSI | 25% | WSNI | 25% | WWI | 25% | WWNI | 25%
500080 | Pressure Management - New PMV and PMA Installs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-07-30 |  | Scottish Water Wide | 0 | 0 | 804674 | 917811 | 637273 | 482630 | 448157 | 155697.44 | 3446242.44 | 0 | 0 | 0 | 3446242.44 | 0 | 0 | 0 | 0 | 3446242.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511491 | Pressure Management - New PRV & PMA Installs RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-23 | 2023-02-16 | 2024-01-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26168.22 | 26168.22 | 373831.78 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511492 | Pressure Management - New PRV Controllers RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-23 | 2023-02-16 | 2024-01-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9813.08 | 9813.08 | 140186.92 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500081 | Pressure Management - PMV & PMA Optimisation Modulation Servicing and Replacement Controllers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-06-21 |  | Scottish Water Wide | 293.4 | 0 | 1861412.45 | -881760.44 | 2438280.17 | 2051476.42 | 2365933 | 2140912.88 | 9976254.48 | 0 | 0 | 0 | 9976547.88 | 0 | 0 | 0 | 0 | 9976547.88 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511489 | Pressure Management - Repair-Refurb and Optimise PRVs-PMAs RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-26 | 2023-02-16 | 2024-01-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91588.79 | 91588.79 | 1308411.21 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 1400000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511488 | Pressure Management - Repair-Refurb-Replace PRV Controllers RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-23 | 2023-02-16 | 2024-01-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26168.22 | 26168.22 | 373831.78 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511487 | Pressure Management - Replace Existing PRVs RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-23 | 2023-02-16 | 2024-01-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26168.22 | 26168.22 | 373831.78 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500082 | Pressure Management - Replacement of Existing PMVs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-27 | 2015-03-25 | 2015-03-25 | 2021-07-30 |  | Scottish Water Wide | 0 | 0 | 288095 | 265604 | 292195 | 352649 | 478653 | 274302.44 | 1951498.44 | 0 | 0 | 0 | 1951498.44 | 0 | 0 | 0 | 0 | 1951498.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500057 | Prestonpans Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-02-27 | 2016-05-18 | 2016-05-18 | 2017-04-21 |  | East Lothian | 102.09 | 0 | 77263.91 | 1299998 | 57077 | -20858.92 | 0 | 0 | 1413479.99 | 0 | 0 | 0 | 1413582.08 | 0 | 0 | 0 | 0 | 1413582.08 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403956 | Pre-Stress Concrete Pipe Proximity Risk | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 |  | Scottish Water Wide | 40000 | 0 | 102058 | -2057.89 | 0 | 0 | 0 | 0 | 100000.11 | 0 | 0 | 0 | 140000.11 | 0 | 0 | 0 | 0 | 140000.11 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503410 | Pre-stressed & post-tensioned concrete tanks capital maintenance (North) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2019-09-20 | 2022-01-17 | 2022-04-05 | 2022-12-02 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 24723.07 | 11636.93 | 36360 | 1169280.74 | 0 | 0 | 1205640.74 | 0 | 0 | 0 | 0 | 1205640.74 | 209623.87 | [5 empty] | N | CM_WSNI | 20% | CM_WWNI | 80%
503409 | Pre-stressed & post-tensioned concrete tanks capital maintenance (South) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2019-09-20 | 2021-05-24 | 2021-08-16 | 2022-05-17 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 17026.01 | 36516.99 | 53543 | 1275846.05 | 0 | 0 | 1329389.05 | 0 | 0 | 0 | 0 | 1329389.05 | 209623.87 | [5 empty] | N | CM_WSNI | 41.59% | CM_WWNI | 58.41%
503397 | Pre-stressed & post-tensioned concrete tanks capital maintenance (West) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2019-09-20 | 2021-07-19 | 2021-11-01 | 2022-06-27 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 36500 | 4542.72 | 41042.72 | 772525 | 0 | 0 | 813567.72 | 0 | 0 | 0 | 0 | 813567.72 | 209623.87 | [5 empty] | N | CM_WSNI | 16.59% | CM_WWNI | 83.41%
502713 | Pre-stressed concrete tanks capital maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-09-20 | 2021-08-30 | 2021-11-22 | 2024-03-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 83683.21 | 38138.45 | 23533.54 | 69450.8 | 214806 | 2898976.8 | 0 | 0 | 3113782.8 | 0 | 0 | 0 | 0 | 3113782.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400513 | Prestwick Airport Overflow Relief Sewer- Esplanade SPS Rising Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-04-07 | 2012-10-31 | 2012-11-26 | 2015-03-27 |  | South Ayrshire | 1450053 | 0 | 238767 | 121572.86 | -254.45 | 0 | 0 | 0 | 360085.41 | 0 | 0 | 0 | 1810138.41 | 0 | 0 | 0 | 0 | 1810138.41 | 299983.07 | [5 empty] | N | CM_WWI | 15.08% | CM_WWNI | 84.92%
500985 | Print Services | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-11-23 | 2017-10-09 | 2017-10-09 | 2018-06-13 |  | Scottish Water Wide | 0 | 0 | 72904 | 107252.98 | 229242.06 | 34261.6 | 0 | 0 | 443660.64 | 0 | 0 | 0 | 443660.64 | 0 | 0 | 0 | 0 | 443660.64 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503573 | Pro-Active Maintenance for Time Based Intervention | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2020-02-11 | 2020-02-11 | 2020-03-15 | 2021-12-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 214352.65 | 1221772.63 | 1436125.28 | 1064327.22 | 0 | 0 | 2500452.5 | 0 | 0 | 0 | 0 | 2500452.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503858 | Pro-active Maintenance for Time Based Intervention (North and East) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-12-05 | 2020-01-06 | 2020-06-22 | 2022-04-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 2118791 | 2188791 | 311208.7 | 0 | 0 | 2499999.7 | 0 | 0 | 0 | 0 | 2499999.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503062 | Proactive works to Gryfe VT Bridges | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 2019-12-17 |  | Inverclyde | 0 | 0 | 0 | 0 | 26399.63 | 31074.59 | 3462.83 | 0 | 60937.04 | 0 | 0 | 0 | 60937.04 | 0 | 0 | 0 | 0 | 60937.04 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501028 | Process Scientist Plan (IDP) Support - SR15 Yr1 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-09 | 2016-06-09 | 2016-06-09 | 2016-04-25 |  | Scottish Water Wide | 0 | 0 | 1182834.01 | 0 | 0 | 0 | 0 | 0 | 1182834.01 | 0 | 0 | 0 | 1182834.01 | 0 | 0 | 0 | 0 | 1182834.01 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502196 | Process Scientist Plan (IDP) Support (Waste) - SR15 Yr1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-09-29 | 2016-09-29 | 2016-09-14 | 2016-09-12 |  | Scottish Water Wide | 0 | 0 | 0 | 233973 | 0 | 0 | 0 | 0 | 233973 | 0 | 0 | 0 | 233973 | 0 | 0 | 0 | 0 | 233973 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403215 | Productisation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-12-10 | 2013-04-17 | 2013-04-17 | 2015-04-15 |  | Scottish Water Wide | 385060.48 | 0 | -36294.85 | 0 | 0 | 0 | 0 | 0 | -36294.85 | 0 | 0 | 0 | 348765.63 | 0 | 0 | 0 | 0 | 348765.63 | 509606.94 | [5 empty] | N | CM_WSNI | 25% | CM_WWI | 25% | CM_WWNI | 50%
502734 | Project ATOM - Lubrication Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-06-28 | 2017-06-28 | 2017-11-16 | 2021-04-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 81290.48 | 206419.52 | 48018.2 | -100372.92 | 235355.28 | 264644.72 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 357067.75 | [5 empty] | N | CM_WSNI | 100%
500758 | Project ATOM HL - Waste Water East | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 |  | All East Unitary Authorities | 0 | 0 | 382061 | 951443.95 | 622113.05 | -248455.06 | 343190.53 | 293285.84 | 2343639.31 | 170125.69 | 0 | 0 | 2513765 | 0 | 0 | 0 | 0 | 2513765 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500759 | Project ATOM HL - Waste Water North | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 |  | All North Unitary Authorities | 0 | 0 | 603435.72 | 620516.77 | 288612.51 | -340668.15 | 214687.15 | 175946.63 | 1562530.63 | 141512.37 | 0 | 0 | 1704043 | 0 | 0 | 0 | 0 | 1704043 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500760 | Project ATOM HL - Waste Water South | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 |  | All South Unitary Authorities | 0 | 0 | 385748 | 571222.62 | 429903.38 | -228125.82 | 217147.25 | 204539.67 | 1580435.1 | 138217.9 | 0 | 0 | 1718653 | 0 | 0 | 0 | 0 | 1718653 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500761 | Project ATOM HL - Waste Water West | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 |  | All West Unitary Authorities | 0 | 0 | 432958 | 584047 | 236119 | -255032.01 | 109277.01 | 94708.31 | 1202077.31 | 81692.69 | 0 | 0 | 1283770 | 0 | 0 | 0 | 0 | 1283770 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500762 | Project ATOM HL - Water East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-06-22 |  | All East Unitary Authorities | 0 | 0 | 328566 | 401738 | 68496 | -107950.39 | 149264.28 | 91358.66 | 931472.55 | 108991.45 | 0 | 0 | 1040464 | 0 | 0 | 0 | 0 | 1040464 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500763 | Project ATOM HL - Water North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-05-31 |  | All North Unitary Authorities | 0 | 0 | 530551.94 | 493016.06 | 785582 | -298407.9 | 157576.21 | 211502.75 | 1879821.06 | -15789.06 | 0 | 0 | 1864032 | 0 | 0 | 0 | 0 | 1864032 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500764 | Project ATOM HL - Water South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-05-31 |  | All South Unitary Authorities | 0 | 0 | 313597 | 163344 | 142547 | -29560.95 | 161348.89 | 99898.04 | 851173.98 | 53025.02 | 0 | 0 | 904199 | 0 | 0 | 0 | 0 | 904199 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500765 | Project ATOM HL - Water West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-05-31 |  | All West Unitary Authorities | 0 | 0 | 326421 | 405457 | 80643 | -104966.98 | 145188.06 | 98584 | 951326.08 | 85526.92 | 0 | 0 | 1036853 | 0 | 0 | 0 | 0 | 1036853 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500712 | Project ATOM Intervention | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWD | Wastewater non infrastructure | MS3 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2021-05-31 |  | Scottish Water Wide | 0 | 0 | 1110530.45 | 184219.51 | -104912.96 | -327113.28 | 59534.28 | -35232.25 | 887025.75 | 23009.25 | 0 | 0 | 910035 | 0 | 0 | 0 | 0 | 910035 | 401838.07 | [5 empty] | N | CM_WSI | 50% | CM_WWNI | 50%
512106 | Property - Asbestos Management & Fire Risk Assessments RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS1 | 2021-04-01 | 2021-04-26 | 2021-04-28 | 2022-06-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000.05 | 0 | 0 | 700000.05 | 0 | 0 | 0 | 0 | 700000.05 | 613322.63 | [5 empty] | N | CM_M&G | 100%
512079 | Property - Building Fabric RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS1 | 2021-04-01 | 2021-04-26 | 2021-04-28 | 2022-06-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334999.95 | 0 | 0 | 334999.95 | 0 | 0 | 0 | 0 | 334999.95 | 613322.63 | [5 empty] | N | CM_M&G | 100%
512217 | Property - External & Security Works RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000.02 | 0 | 0 | 540000.02 | 0 | 0 | 0 | 0 | 540000.02 | 613322.63 | [5 empty] | N | CM_M&G | 100%
512080 | Property - Legislative Testing RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS1 | 2021-04-01 | 2021-04-26 | 2021-04-29 | 2022-06-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 240000 | 613322.63 | [5 empty] | N | CM_M&G | 100%
512215 | Property - Minor Refurbishment & Capital Maintenance RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429999.97 | 0 | 0 | 1429999.97 | 0 | 0 | 0 | 0 | 1429999.97 | 613322.63 | [5 empty] | N | CM_M&G | 100%
512209 | Property - Non Catchment L&B RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 0 | 0 | 525000 | 0 | 0 | 0 | 0 | 525000 | 306661.32 | [5 empty] | N | CM_M&G | 100%
512213 | Property - RAP & LTRAP RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485000.02 | 0 | 0 | 1485000.02 | 0 | 0 | 0 | 0 | 1485000.02 | 613322.63 | [5 empty] | N | CM_M&G | 100%
512214 | Property - Replacement Furniture - RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134999.97 | 0 | 0 | 134999.97 | 0 | 0 | 0 | 0 | 134999.97 | 613322.63 | [5 empty] | N | CM_M&G | 100%
512216 | Property - Service Upgrades RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499999.99 | 0 | 0 | 499999.99 | 0 | 0 | 0 | 0 | 499999.99 | 613322.63 | [5 empty] | N | CM_M&G | 100%
512104 | Property - Statutory Compliance RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS1 | 2021-04-06 | 2021-04-26 | 2021-04-28 | 2022-06-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000.05 | 0 | 0 | 1000000.05 | 0 | 0 | 0 | 0 | 1000000.05 | 613322.63 | [5 empty] | N | CM_M&G | 100%
512208 | Property - Water Catchment L&B RP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235000.01 | 0 | 0 | 235000.01 | 0 | 0 | 0 | 0 | 235000.01 | 306661.32 | [5 empty] | N | CM_M&G | 100%
502393 | Property Estates - Loch Katrine Access Road Repair | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2017-01-16 | 2017-08-31 | 2017-08-31 | 2018-02-15 |  | All West Unitary Authorities | 0 | 0 | 0 | 14000 | 646525.92 | -28075.92 | -875.49 | 0 | 631574.51 | 0 | 0 | 0 | 631574.51 | 0 | 0 | 0 | 0 | 631574.51 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503087 | Property Facilities Statutory Building Compliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2018-07-13 | 2018-07-13 | 2018-07-16 | 2021-06-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1127831 | 1236538 | 908683.96 | 3273052.96 | 124417.86 | 0 | 0 | 3397470.82 | 0 | 0 | 0 | 0 | 3397470.82 | 613322.63 | [5 empty] | N | CM_M&G | 100%
400826 | Provision of Drought Plans Phase 2 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2011-05-13 | 2011-05-13 | 2015-03-06 |  | Scottish Water Wide | 383198.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383198.72 | 0 | 0 | 0 | 0 | 383198.72 | 0 | [6 empty] | CM_WSI | 100%
400798 | Provision of New DI Flowmetering SR10 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-01 | 2010-08-02 | 2015-09-16 |  | Scottish Water Wide | 1662000 | 0 | -161083.01 | 0 | 0 | 0 | 0 | 0 | -161083.01 | 0 | 0 | 0 | 1500916.99 | 0 | 0 | 0 | 0 | 1500916.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507847 | Provost Driver Court WWPS - Sewer Collapse | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2020-08-07 | 2021-10-25 | 2022-02-23 | 2022-08-24 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298500 | 298500 | 101500 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
404001 | PSCD Glenhove to Dalmacoulter Rising Main - Close Proximity Diversions | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | SW | WINF | Supply Resilience | MS6 | 2015-12-08 | 2016-03-30 | 2016-03-30 | 2019-03-31 | 2020-01-31 | North Lanarkshire | 586 | 0 | 3238759 | 5164682 | 2114871.63 | 278644.84 | 173513.82 | 82.88 | 10970554.17 | 0 | 0 | 0 | 10971140.17 | 0 | 0 | 0 | 0 | 10971140.17 | 1989709.51 | [5 empty] | Y | SR15_EXC_EXC | 7% | CS16WR | 93% | [22 empty] | 1 | [42 empty] | 0
511792 | PSTN Replacement Implementation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | GW0 | 2021-04-28 | 2022-04-22 | 2022-08-24 | 2024-04-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3684245 | 0 | 0 | 3684245 | 0 | 0 | 0 | 0 | 3684245 | 613322.63 | [5 empty] | N | CM_M&G | 100%
511791 | PSTN Replacement Technical Enablement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | GW0 | 2021-04-28 | 2022-04-22 | 2022-08-24 | 2024-04-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2978752 | 0 | 0 | 2978752 | 0 | 0 | 0 | 0 | 2978752 | 613322.63 | [5 empty] | N | CM_M&G | 100%
506396 | PS-WW-NI-290420-Pan Scotland-Replacement of Generator batteries | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-05-01 |  | 2020-10-29 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36362.04 | 36362.04 | 33637.96 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505669 | Public Network Katrine & Stronachlacher | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWMD | Exceptional Capital Maintenance | MS2 |  | 2020-03-12 |  | 2021-08-11 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 3271.03 | 14696.9 | 17967.93 | 36763.23 | 36763.225 | 51033.6151 | 54731.15 | 14270.3901 | 0 | 0 | 14270.3901 | 69001.5401 | 0 | [5 empty] | N | SR15_EXC_EXC | 100%
503582 | Pump Chain Maintenance - Phase 1 2 & 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2019-05-27 | 2019-05-27 | 2019-05-28 | 2021-10-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 361059.05 | 2216220.96 | 2577280 | 1022720.32 | 0 | 0 | 3600000.32 | 0 | 0 | 0 | 0 | 3600000.32 | 419247.74 | [5 empty] | N | CM_WSNI | 38.85% | CM_WWNI | 61.15%
510198 | Pumping Mains Inspections Phase 2 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWMD | SR21 Early Start | MS0 | 2020-12-22 | 2021-08-27 | 2021-12-29 | 2022-06-29 | 2022-09-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6526 | 6526 | 693473.89 | 0 | 0 | 699999.89 | 0 | 0 | 0 | 0 | 699999.89 | 0 | [5 empty] | N | SR21_WW | 100%
400991 | Pundeavon Reservoir Freeboard Related Remedial Work | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-06-07 | 2015-05-19 | 2015-06-15 | 2017-10-03 |  | North Ayrshire | 136802 | 0 | 800575.52 | 792545.33 | 138555.41 | 0 | 0 | -4963.98 | 1726712.28 | 0 | 0 | 0 | 1863514.28 | 0 | 0 | 0 | 0 | 1863514.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503699 | Purdomstone MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-08-09 | 2022-06-29 | 2022-09-12 | 2023-04-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 13687.06 | -7328.27 | 6358.79 | 1400673.88 | 0 | 0 | 1407032.67 | 0 | 0 | 0 | 0 | 1407032.67 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508299 | Purdomstone Reservoir Bywash veg and gravel clearance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-09-14 | 2020-12-07 | 2021-12-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46858 | 46858 | 103141.56 | 0 | 0 | 149999.56 | 0 | 0 | 0 | 0 | 149999.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503499 | PV Project Vesting - Pump Stations - East | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-05-13 | 2021-10-22 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 159546.09 | 238820.05 | 138791.86 | 537158 | 376241.96 | 0 | 0 | 913399.96 | 0 | 0 | 0 | 0 | 913399.96 | 808416.23 | [5 empty] | N | SG7 | 100%
503496 | PV Project Vesting - Pump Stations - North | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2022-05-13 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 177220.45 | 33933.47 | 5116.08 | 216270 | 77329.98 | 0 | 0 | 293599.98 | 0 | 0 | 0 | 0 | 293599.98 | 808416.23 | [5 empty] | N | SG7 | 100%
503492 | PV Project Vesting - Pump Stations - South | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-09-15 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 91876.25 | 116932.77 | 238419.98 | 447229 | 123671.43 | 0 | 0 | 570900.43 | 0 | 0 | 0 | 0 | 570900.43 | 808416.23 | [5 empty] | N | SG7 | 100%
503493 | PV Project Vesting - Pump Stations - West | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2022-04-28 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 338918.62 | 537688.25 | 615916.13 | 1492523 | 96911.11 | 0 | 0 | 1589434.11 | 0 | 0 | 0 | 0 | 1589434.11 | 808416.23 | [5 empty] | N | SG7 | 100%
502096 | PV Project Vesting - Spec upgrade - Barratt North | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS7 | 2016-03-07 | 2016-03-07 | 2016-07-22 | 2017-02-01 | 2017-02-03 | Scottish Water Wide | 0 | 0 | 15766.36 | -15766.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG7 | 100%
502095 | PV Project Vesting - Spec upgrade - Springfield | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS7 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2017-02-01 | 2017-02-03 | Scottish Water Wide | 0 | 0 | 15766.36 | -15766.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG7 | 100%
502097 | PV Project Vesting - Spec upgrade - Taylor Wimpey West | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS7 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2017-02-01 | 2017-02-03 | Scottish Water Wide | 0 | 0 | 15766.36 | -15766.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG7 | 100%
503498 | PV Project Vesting - SUDS - East | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-05-06 | 2021-10-22 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 92198.78 | 423773.57 | 424120.65 | 940093 | 326844.84 | 0 | 0 | 1266937.84 | 0 | 0 | 0 | 0 | 1266937.84 | 808416.23 | [5 empty] | N | SG7 | 100%
503497 | PV Project Vesting - SUDS - North | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-27 | 2019-02-27 | 2019-04-08 | 2022-05-13 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 21377.65 | 255437.51 | 98330.84 | 375146 | 168854.17 | 0 | 0 | 544000.17 | 0 | 0 | 0 | 0 | 544000.17 | 808416.23 | [5 empty] | N | SG7 | 100%
503495 | PV Project Vesting - SUDS - West | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2022-04-14 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 268250.39 | 244022.73 | 143802.88 | 656076 | 344824.06 | 0 | 0 | 1000900.06 | 0 | 0 | 0 | 0 | 1000900.06 | 808416.23 | [5 empty] | N | SG7 | 100%
503494 | PV Project Vesting - SUDS- South | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS3 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-09-01 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 69000.22 | 86731.77 | 182815.01 | 338547 | 71452.95 | 0 | 0 | 409999.95 | 0 | 0 | 0 | 0 | 409999.95 | 808416.23 | [5 empty] | N | SG7 | 100%
502099 | PV Project Vesting Pump Stations | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | General |  | SWD | Developer Asset Adoption | MS3 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 15766.36 | 224233.94 | 592013.7 | 1014722.81 | -284753.29 | 24299.12 | 1586282.64 | 381597.36 | 0 | 0 | 1967880 | 0 | 0 | 0 | 0 | 1967880 | 1209174.3 | [5 empty] | N | SG7 | 49.19% | WG7 | 50.81%
502100 | PV Project Vesting SUDS | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWD | Developer Asset Adoption | MS3 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2021-06-30 |  | Scottish Water Wide | 0 | 0 | 15766.36 | 9999 | 348366.01 | 332527.63 | -87789.72 | 633845.74 | 1252715.02 | -160733.89 | 0 | 0 | 1091981.13 | 0 | 0 | 0 | 0 | 1091981.13 | 1209174.3 | [5 empty] | N | SG7 | 8.423% | WG7 | 91.58%
502098 | PV Project Vesting Team and Small Works | Q&S4 | Supporting economic development | Infra Charge |  |  | General |  | SWD | Infra Charge | MS3 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2022-04-29 |  | Scottish Water Wide | 0 | 0 | 15766.36 | 2575110.63 | 3188186.01 | 2766522 | 2969640.91 | 2889340.29 | 14404566.2 | -4566.2 | 0 | 0 | 14400000 | 0 | 0 | 0 | 0 | 14400000 | 0 | [5 empty] | N | SG7 | 10% | WG7 | 10% | SG5 | 40% | WG5 | 40%
502226 | PVC Water Mains Study | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-16 | 2016-09-15 | 2016-10-21 | 2017-12-06 |  | Scottish Water Wide | 0 | 0 | 0 | 17390.82 | 18132.42 | -668.68 | 0 | 0 | 34854.56 | 0 | 0 | 0 | 34854.56 | 0 | 0 | 0 | 0 | 34854.56 | 311236.79 | [5 empty] | N | CM_M&G | 100%
404061 | Q Improvements Yr5 - Chloram Prog Line - Man Del | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-15 | 2014-12-15 | 2015-11-17 | 2017-10-26 |  | Scottish Water Wide | 45000 | 0 | 918973 | 1114535.87 | 369383.4 | 581.85 | 0 | 0 | 2403474.12 | 0 | 0 | 0 | 2448474.12 | 0 | 0 | 0 | 0 | 2448474.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502738 | QCE and Consultant Support Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2019-02-28 | 2019-02-28 | 2019-02-28 | 2019-02-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 1248066.07 | -22924.72 | 0 | 0 | 1225141.35 | 0 | 0 | 0 | 1225141.35 | 0 | 0 | 0 | 0 | 1225141.35 | 311236.79 | [5 empty] | N | CM_WSI | 100%
12059 | QS2 SWS Land and Compensation Liability | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS7 | 2008-04-01 | 2005-01-21 | 2005-02-21 | 2009-03-31 |  | Scottish Water Wide | 566461.56 | 0 | 0 | -566461.56 | 0 | 0 | 0 | 0 | -566461.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328404.37 | [5 empty] | N | Wa6 | 50% | Ww3 | 50%
403416 | QS3b AR - Ardersier WWTW - Outfall Extension | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-28 | 2015-03-06 | 2015-03-18 | 2015-03-18 | 2015-03-18 | Highland | 82209 | 0 | -48.77 | 0 | 0 | 0 | 0 | 0 | -48.77 | 0 | 0 | 0 | 82160.23 | 0 | 0 | 0 | 0 | 82160.23 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403879 | QS3b AR - Blairlinnans South WQ Improvements | Q&S3B | Completion | OMG180 |  |  | Water | DWQR | WINF | OMG180 | MS7 | 2014-07-31 | 2015-03-30 | 2015-03-30 | 2018-09-30 | 2019-08-31 | Glasgow City | 260097 | 0 | 1893215 | 145530.24 | 233049.4 | 224862.74 | 22418.45 | -41524.8 | 2477551.03 | 0 | 0 | 0 | 2737648.03 | 0 | 0 | 0 | 0 | 2737648.03 | 1951306 | [5 empty] | Y | DW5 | 100% | [20 empty] | 1 | [46 empty] | 0
403091 | QS3b AR - Burncrooks WTW | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-02-28 | 2014-10-02 | 2014-10-02 | 2014-10-21 | 2014-10-02 | East Renfrewshire | 212280.37 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 212451.37 | 0 | 0 | 0 | 0 | 212451.37 | 0 | [5 empty] | N | DW25 | 100%
402928 | QS3b AR - Cromwell Road CSO Removal of Raw Discharges | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2012-10-29 | 2015-09-22 | 2015-10-26 | 2016-03-31 | 2016-03-31 | Highland | 58578 | 0 | 910251 | 7935.72 | -1416.75 | 36.43 | 0 | 0 | 916806.4 | 0 | 0 | 0 | 975384.4 | 0 | 0 | 0 | 0 | 975384.4 | 633026 | [5 empty] | Y | EC10B | 100% | [65 empty] | 1 |  | 0
402950 | QS3b AR - Davidston Burn - Fish Pass Installation | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2012-09-17 | 2013-06-12 | 2013-08-23 | 2014-03-13 | 2014-03-25 | Aberdeenshire | 128320 | 0 | 728.29 | 0 | 0 | 0 | 0 | 0 | 728.29 | 0 | 0 | 0 | 129048.29 | 0 | 0 | 0 | 0 | 129048.29 | 0 | [5 empty] | N | WR2A | 100%
403504 | QS3b AR - Dumbarton WTW Abstraction Controls | Q&S3B | Completion | OMG180 |  |  | Water | SEPA | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-03-11 | 2015-07-20 | 2016-01-31 | 2016-03-31 | West Dunbartonshire | 22655.28 | 0 | 142541.09 | 24.85 | -157.78 | 1964.79 | 0 | 0 | 144372.95 | 0 | 0 | 0 | 167028.23 | 0 | 0 | 0 | 0 | 167028.23 | 62419 | [5 empty] | Y | WR1 | 100% | [65 empty] | 1 |  | 0
402986 | QS3b AR - Elmvale Row Flooding Glasgow | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS7 | 2012-09-28 | 2015-04-03 | 2015-04-07 | 2017-03-31 | 2017-06-30 | Glasgow City | 1958936 | 0 | 9030877 | 648905 | 830491.25 | -1026608.63 | 1 | 0 | 9483665.62 | 0 | 0 | 0 | 11442601.62 | 0 | 0 | 0 | 0 | 11442601.62 | 8344790 | [5 empty] | Y | CS11A | 30% | CS15 | 70% | [63 empty] | 1 |  | 0
403880 | QS3b AR - Forehill Distribution WQ Improvements | Q&S3B | Completion | OMG180 |  |  | Water | DWQR | WINF | OMG180 | MS7 | 2014-07-31 | 2015-06-15 | 2015-06-29 | 2019-03-31 | 2020-03-31 | Aberdeenshire | 124114 | 0 | 1230084 | 553928 | 638871 | 1880718 | 2079.39 | 17948.36 | 4323628.75 | 0 | 0 | 0 | 4447742.75 | 0 | 0 | 0 | 0 | 4447742.75 | 2690241 | [5 empty] | Y | DW5 | 100% | [20 empty] | 1 | [46 empty] | 0
403881 | QS3b AR - Glenfarg - Kinnesswood WQ Improvements | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS7 | 2014-07-31 | 2016-03-17 | 2016-03-17 | 2016-03-11 | 2016-03-17 | Fife | 57331.99 | 0 | -48197.19 | 896.71 | 0 | 0 | 0 | 0 | -47300.48 | 0 | 0 | 0 | 10031.51 | 0 | 0 | 0 | 0 | 10031.51 | 0 | [5 empty] | N | DW5 | 100%
402388 | QS3b AR - Internal Flooding Gables Bar Baillieston Road Glasgow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-03-31 | 2014-01-22 | 2014-01-22 | 2014-09-09 | 2014-09-09 | Glasgow City | 1843311 | 0 | 0 | 0 | 0 | -5200.16 | 0 | 0 | -5200.16 | 0 | 0 | 0 | 1838110.84 | 0 | 0 | 0 | 0 | 1838110.84 | 0 | [5 empty] | N | CS11A | 50% | CS15 | 50%
403090 | QS3b AR - Kaim WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | SEPA | WINF | DWQ Compliance | MS3 | 2013-01-17 | 2016-09-26 | 2016-09-27 | 2021-06-30 | 2021-09-23 | East Renfrewshire | 122472.97 | 122472.97 | 356178.93 | 5686690.1 | 4554416.43 | 2930634.67 | 906972.63 | 825718.44 | 15260611.19 | 106665.84 | 106665.8387 | 331244.0316 | 15489750 | 224578.1929 | 0 | 0 | 224578.1929 | 15714328.1929 | 5813947.47 | [5 empty] | N | DW25D | 10.45% | DW25P | 10.45% | DW2 | 39.55% | DW3C | 39.55%
403503 | QS3b AR - Killylour WTW Abstraction Controls | Q&S3B | Completion | OMG180 |  |  | Water | SEPA | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-03-11 | 2015-07-20 | 2016-01-31 | 2016-03-31 | Dumfries and Galloway | 19652.02 | 0 | 38798.8 | 469.46 | 1107.63 | 621.19 | 0 | 0 | 40997.08 | 0 | 0 | 0 | 60649.1 | 0 | 0 | 0 | 0 | 60649.1 | 63545 | [5 empty] | Y | WR1 | 100% | [65 empty] | 1 |  | 0
403502 | QS3b AR - Loch Eck WTW Abstraction Controls | Q&S3B | Completion | OMG180 |  |  | Water | SEPA | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-03-11 | 2015-10-30 | 2016-03-31 | 2016-03-31 | Argyll and Bute-Cowal & Bute | 18230.54 | 0 | 34967.09 | 322.03 | -299.95 | 1420.75 | 0 | 0 | 36409.92 | 0 | 0 | 0 | 54640.46 | 0 | 0 | 0 | 0 | 54640.46 | 71246 | [5 empty] | Y | WR1 | 100% | [65 empty] | 1 |  | 0
402738 | QS3b AR - Muirdykes WTW WQ Investigations and Solutions | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2012-11-05 | 2016-03-09 | 2016-01-06 | 2016-01-06 | 2016-01-06 | Renfrewshire | 1651786.2 | 0 | -17126.19 | 0 | 0 | 0 | 0 | 0 | -17126.19 | 0 | 0 | 0 | 1634660.01 | 0 | 0 | 0 | 0 | 1634660.01 | 0 |  |  |  |  | 115944 | N | DW3C | 0.16% | DW3H | 0.29% | DW23 | 99.55%
403087 | QS3b AR - North Harris Regional Scheme | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-01-17 | 2015-03-06 | 2014-12-12 | 2014-12-12 | 2014-12-12 | Na H-Eileanan an Iar | 226427.35 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 226426.35 | 0 | 0 | 0 | 0 | 226426.35 | 0 | [5 empty] | N | DW25 | 100%
403093 | QS3b AR - P001 UID In Park at South of Footbridge Kelvingrove Park | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | Glasgow City | 19000 | 0 | 0 | 0 | -104.02 | 0 | 0 | 0 | -104.02 | 0 | 0 | 0 | 18895.98 | 0 | 0 | 0 | 0 | 18895.98 | 0 | [5 empty] | N | EC01B | 100%
403094 | QS3b AR - P002 - UID - 439 Great Western Road CSO Kelvinbridge | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | Glasgow City | 274379.16 | 0 | 1228415.84 | 1012257 | 361968.07 | 76256.04 | -5774.46 | 0 | 2673122.49 | 0 | 0 | 0 | 2947501.65 | 0 | 0 | 0 | 0 | 2947501.65 | 0 | [5 empty] | N | EC01B | 100%
403095 | QS3b AR - P003 UID In Park North East of Prince of Wales Bridge Kelvingrove Park | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 20000 | 0 | 0 | 0 | -472.63 | 0 | 0 | 0 | -472.63 | 0 | 0 | 0 | 19527.37 | 0 | 0 | 0 | 0 | 19527.37 | 0 | [5 empty] | N | EC01B | 100%
403096 | QS3b AR - P004 UID Rear Of Kelvingrove Museum North 2 Argyle Street Glasgow | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 21191.36 | 0 | 284.64 | 286.64 | 3.57 | 0 | 0 | 0 | 574.85 | 0 | 0 | 0 | 21766.21 | 0 | 0 | 0 | 0 | 21766.21 | 0 | [5 empty] | N | EC01B | 100%
403097 | QS3b AR - P005 UID Off Garriochmill Road CSO North Kelvin | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS4 | 2012-11-22 | 2019-03-26 | 2019-03-25 | 2021-02-28 | 2021-06-03 | Glasgow City | 30800 | 0 | 2500 | 3100 | 1362 | 201766 | 1079177 | 273297 | 1561202 | 2500 | 2500 | 58333.8196 | 1594502 | 55833.8196 | 0 | 0 | 55833.8196 | 1650335.8196 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403098 | QS3b AR - P006 UID Near the Junction of Kelvindale Road and Balfour Street | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2019-12-13 | 2020-03-30 | 2021-11-16 | 2022-03-02 | Glasgow City | 64143 | 0 | 12608 | 2689 | 3000 | 146091 | 1456619 | 270155 | 1891162 | 1302500 | 1302500 | 1564425.0257 | 3257805 | 261925.0257 | 0 | 0 | 261925.0257 | 3519730.0257 | 0 |  |  |  |  | 30399.9996 | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403099 | QS3b AR - P007 UID Junction of Bellshaugh Gardens & Bellshaugh Road CSO | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS5 | 2012-11-22 | 2019-03-26 | 2019-08-19 | 2020-03-20 | 2021-02-28 | Glasgow City | 57230 | 0 | 11500 | 5660.49 | 6039.51 | 223967 | 896658 | 161554 | 1305379 | 2300 | 2300 | 3192.7916 | 1364909 | 892.7916 | 0 | 0 | 892.7916 | 1365801.7916 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403100 | QS3b AR - P008 UID At West Bank of Footbridge BGs Addison Road | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2019-03-13 | 2020-09-30 | 2021-07-19 | 2021-10-21 | Glasgow City | 24700 | 0 | 100 | 0 | 0 | 3677.97 | 12039.03 | 3000 | 18817 | 727 | 727 | 824.6563 | 44244 | 97.6563 | 0 | 0 | 97.6563 | 44341.6563 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403101 | QS3b AR - P009 UID North of Playground off Garriochmill Road | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS3 | 2012-11-21 | 2019-03-26 | 2019-08-01 | 2021-07-20 | 2021-10-22 | Glasgow City | 27110.26 | 0 | 3222.74 | 0 | 0 | 142492.91 | 1275420.09 | 355832.8 | 1776968.54 | 455815 | 455815 | 1257149.8493 | 2259893.8 | 801334.8493 | 0 | 4.6566e-10 | 801334.8493 | 3061228.6493 | 0 |  |  |  |  | 1950 | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403102 | QS3b AR - P010 UID Botanic Gardens Nr Junc of Garrioch Drive Garrioch Rd and Shakespeare St | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS3 | 2012-11-21 | 2019-09-11 | 2019-10-15 | 2021-07-09 | 2021-10-13 | Glasgow City | 31778 | 0 | 2550.56 | 1049.44 | 0 | 116369 | 952277 | 450267.8 | 1522513.8 | 253705 | 253705 | 308987.8474 | 1807996.8 | 55282.8474 | 0 | -2.3283e-10 | 55282.8474 | 1863279.6474 | 0 |  |  |  |  | 2949.9997 | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403103 | QS3b AR - P011 UID Queen Margaret Road Bridge CSO at Botanical Gardens | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS4 | 2012-11-22 | 2019-03-13 | 2020-03-09 | 2021-03-31 | 2021-06-28 | Glasgow City | 22825 | 0 | 417 | -417 | 0 | 9523.95 | 65665.05 | 30835 | 106024 | 2300 | 2300 | 21459.9541 | 131149 | 19159.9541 | 0 | 0 | 19159.9541 | 150308.9541 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403104 | QS3b AR - P012 UID 317 Northwoodside Road Glasgow | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2019-09-11 | 2020-01-24 | 2021-08-20 | 2021-11-23 | Glasgow City | 32865.7 | 0 | 49043.3 | 2587 | 769 | 95276 | 1159982 | 525466.08 | 1833123.38 | 145775 | 145775 | 182755.5625 | 2011764.08 | 36980.5625 | 0 | 0 | 36980.5625 | 2048744.6425 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403105 | QS3b AR - P013 UID At The Junction of Otago Street and Otago Lane North | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS6 | 2012-11-22 | 2018-03-28 | 2018-06-29 | 2019-12-31 | 2020-03-31 | Glasgow City | 48878 | 0 | 3622 | 63285.42 | 73581.58 | 126432.7 | 39950.3 | 1179 | 308051 | 1071 | 1071 | 1486.7303 | 358000 | 415.7303 | 0 | 0 | 415.7303 | 358415.7303 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403106 | QS3b AR - P014 UID Westbank Quadrant at Eldon Street Bridge CSO NS273667 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2018-06-07 | 2018-06-25 | 2022-10-31 | 2022-11-18 | Glasgow City | 45703 | 0 | 72797 | 151548 | 156613.12 | 525203.16 | 493033.72 | 67032 | 1466227 | 282311.92 | 282311.92 | 338533.3535 | 1794241.92 | 56221.4335 | 0 | 0 | 56221.4335 | 1850463.3535 | 0 |  |  |  |  | 4119.9996 | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403107 | QS3b AR - P015 UID Westbank Quadrant CSO at Depot Kelvingrove Park | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater | SEPA | WWINF | Ring Fenced Environmental | MS6 | 2012-11-22 | 2018-10-24 | 2019-01-14 | 2019-09-30 | 2022-11-18 | Glasgow City | 44967 | 0 | -3967 | 7802 | 79655.12 | 482488.88 | 170804 | 4656 | 741439 | 0 | 0 | 0 | 786406 | 0 | 0 | 0 | 0 | 786406 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403108 | QS3b AR - P016 UID At Rear of Kelvingrove Museum Kelvingrove Park | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 70143 | 0 | 5365 | 278635 | -4797.92 | 0 | 0.46 | 0 | 279202.54 | 0 | 0 | 0 | 349345.54 | 0 | 0 | 0 | 0 | 349345.54 | 0 | [5 empty] | N | EC10B | 100%
403109 | QS3b AR - P017 UID Junction Of Drymen Road and Thorn Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2012-11-22 | 2014-12-19 | 2015-04-13 | 2015-11-30 | 2016-01-31 | East Dunbartonshire | 248417 | 0 | 175195.06 | 450.55 | 469.39 | -82.37 | 0 | 0 | 176032.63 | 0 | 0 | 0 | 424449.63 | 0 | 0 | 0 | 0 | 424449.63 | 209743 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403110 | QS3b AR - P018 UID At the Junction of Hillfoot Drive and Hillside Avenue Bearsden | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2012-11-22 | 2018-11-06 | 2018-12-17 | 2018-11-05 | 2018-12-17 | East Dunbartonshire | 44206 | 0 | 6400 | 17800 | 6000 | -5109.76 | 0 | 0 | 25090.25 | 0 | 0 | 0 | 69296.25 | 0 | 0 | 0 | 0 | 69296.25 | 0 | [5 empty] | N | EC10B | 100%
403111 | QS3b AR - P019 UID In Garden of No 10 Leven Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2015-02-03 | 2015-02-03 | 2015-03-10 | 2015-03-10 | East Dunbartonshire | 90980 | 0 | -513.84 | 0 | 0 | 0 | 0 | 0 | -513.84 | 0 | 0 | 0 | 90466.16 | 0 | 0 | 0 | 0 | 90466.16 | 0 | [5 empty] | N | EC10B | 100%
403112 | QS3b AR - P020 UID Junction of Kessington Road and Inveroran Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2012-11-22 | 2014-11-24 | 2015-03-09 | 2015-09-30 | 2015-10-31 | East Dunbartonshire | 190902 | 0 | 46254 | 1199.98 | -789.05 | 0 | 0 | 0 | 46664.93 | 0 | 0 | 0 | 237566.93 | 0 | 0 | 0 | 0 | 237566.93 | 50233 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403113 | QS3b AR - P021 UID At Junction of Rannoch Drive and Maryhill Road | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2012-11-22 | 2016-03-22 | 2016-03-23 | 2016-03-31 | 2016-04-30 | East Dunbartonshire | 46255 | 0 | 253206 | 41648 | 1968 | -358.32 | 0 | 0 | 296463.68 | 0 | 0 | 0 | 342718.68 | 0 | 0 | 0 | 0 | 342718.68 | 160020 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
403115 | QS3b AR - P023 UID 250 Milngavie Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2012-11-22 | 2018-11-05 | 2018-12-17 | 2018-11-05 | 2018-12-17 | East Dunbartonshire | 51572 | 0 | -2156 | 3000.36 | 998.71 | -238.84 | 0 | 0 | 1604.23 | 0 | 0 | 0 | 53176.23 | 0 | 0 | 0 | 0 | 53176.23 | 0 | [5 empty] | N | EC10B | 100%
403116 | QS3b AR - P024 UID 22 Station Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2012-11-22 | 2019-05-20 | 2019-06-05 | 2019-05-20 | 2019-05-20 | East Dunbartonshire | 37826 | 0 | 6656 | -3020 | 6000 | 5000 | -6313.11 | 0 | 8322.89 | 0 | 0 | 0 | 46148.89 | 0 | 0 | 0 | 0 | 46148.89 | 0 | [5 empty] | N | EC10B | 100%
403117 | QS3b AR - P025 UID 11 Rubislaw Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2015-02-03 | 2015-02-03 | 2015-03-10 | 2015-03-10 | East Dunbartonshire | 40092 | 0 | -12626.27 | 0 | 0 | 0 | 0 | 0 | -12626.27 | 0 | 0 | 0 | 27465.73 | 0 | 0 | 0 | 0 | 27465.73 | 0 | [5 empty] | N | EC10B | 100%
403118 | QS3b AR - P026 UID Seafield Pumping Station Storage Need | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2012-12-07 | 2016-12-22 | 2017-01-23 | 2017-09-30 | 2018-01-31 | East Dunbartonshire | 56905.19 | 0 | 18182.01 | 449506.8 | 262219 | 4154.92 | -246705.03 | 0 | 487357.7 | 0 | 0 | 0 | 544262.89 | 0 | 0 | 0 | 0 | 544262.89 | 363071.29 | [5 empty] | Y | CM_WWNI | 45.26% | EC10B | 54.74% | [34 empty] | 1 | [30 empty] | 0
403119 | QS3b AR - P027 UID Duntocher CSO 3 Burnbrae Glasgow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2015-02-16 | 2015-03-18 | 2015-03-20 | 2015-03-25 | West Dunbartonshire | 59014 | 0 | -1153 | 520.94 | -620.4 | 0 | 0 | 0 | -1252.46 | 0 | 0 | 0 | 57761.54 | 0 | 0 | 0 | 0 | 57761.54 | 0 | [5 empty] | N | EC10B | 100%
403121 | QS3b AR - P029 UID Gavin Burn CSO Upstream of Old Kilpatrick Septic Tank | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2014-11-28 | 2015-01-24 | 2015-02-26 | 2015-03-11 | West Dunbartonshire | 56644.83 | 0 | 8890.17 | 545.87 | -1606.72 | 0 | 0 | 0 | 7829.32 | 0 | 0 | 0 | 64474.15 | 0 | 0 | 0 | 0 | 64474.15 | 0 |  |  |  |  | 12831.5346 | N | EC10B | 100%
403356 | QS3b AR - P030 UID Victoria Rd CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS7 | 2013-03-04 | 2017-06-27 | 2017-09-18 | 2018-12-31 | 2019-03-31 | South Lanarkshire | 29905 | 0 | -4444.91 | 88248.91 | 1765050 | 373019 | -8683 | -31973.4 | 2181216.6 | 0 | 0 | 0 | 2211121.6 | 0 | 0 | 0 | 0 | 2211121.6 | 112386 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
403086 | QS3b AR - Picketlaw WTW | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-02-20 | 2014-10-24 | 2014-10-24 | 2014-10-24 | 2014-10-24 | East Renfrewshire | 231779.18 | 0 | 20994.25 | -20108.3 | 0 | 0 | 0 | 0 | 885.95 | 0 | 0 | 0 | 232665.13 | 0 | 0 | 0 | 0 | 232665.13 | 0 | [5 empty] | N | DW25 | 100%
403957 | QS3b AR - Picketlaw WTW Main Out | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS7 | 2014-11-24 | 2016-05-30 | 2016-05-30 | 2016-06-02 | 2016-06-23 | East Renfrewshire | 53192.17 | 0 | -42599.93 | -1340.6 | 0 | 0 | 0 | 0 | -43940.53 | 0 | 0 | 0 | 9251.64 | 0 | 0 | 0 | 0 | 9251.64 | 0 | [5 empty] | N | DW23 | 50% | DW3C | 50%
402936 | QS3b AR - Stage 4 DOMS investigations in 4 zones | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2012-12-07 | 2013-05-31 | 2013-06-28 | 2014-03-14 | 2014-03-14 | Scottish Water Wide | 773631 | 0 | 0 | -176.56 | 0 | 0 | 0 | 0 | -176.56 | 0 | 0 | 0 | 773454.44 | 0 | 0 | 0 | 0 | 773454.44 | 0 | [5 empty] | N | DW5A | 100%
403501 | QS3b AR - Tighnabruaich WTW Abstraction Controls | Q&S3B | Completion | OMG180 |  |  | Water | SEPA | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-11-17 | 2015-11-17 | 2016-02-29 | 2016-02-29 | Argyll and Bute-North Argyll | 22215.7 | 0 | 97264.8 | 5158.7 | -1180.1 | -1348.92 | 0 | 0 | 99894.48 | 0 | 0 | 0 | 122110.18 | 0 | 0 | 0 | 0 | 122110.18 | 76986 | [5 empty] | Y | WR1 | 100% | [65 empty] | 1 |  | 0
402929 | QS3b AR - Toberonochy Isle of Luing - provision of appropriate WWT | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-09-18 | 2013-09-23 | 2013-11-06 | 2014-08-18 | 2014-11-14 | Argyll and Bute-North Argyll | 233415 | 0 | 585 | 484.7 | 0 | 0 | 0 | 0 | 1069.7 | 0 | 0 | 0 | 234484.7 | 0 | 0 | 0 | 0 | 234484.7 | 0 | [5 empty] | N | EC01A | 100%
403088 | QS3b AR - Tomatin WTW Upgrade | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-01-17 | 2015-03-06 | 2014-12-12 | 2014-12-12 | 2014-12-12 | Highland | 301686.7 | 0 | 0 | 94.9 | 0 | 0 | 0 | 0 | 94.9 | 0 | 0 | 0 | 301781.6 | 0 | 0 | 0 | 0 | 301781.6 | 0 | [5 empty] | N | DW25 | 100%
403222 | QS3b AR - Turriff WWTW Upgrade | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2013-01-14 | 2015-02-19 | 2015-03-09 | 2015-12-31 | 2016-03-31 | Aberdeenshire | 1171213.1 | 0 | 1741332.23 | -46950.64 | 562.67 | -69349.27 | 0 | 0 | 1625594.99 | 0 | 0 | 0 | 2796808.09 | 0 | 0 | 0 | 0 | 2796808.09 | 530269.82 | [5 empty] | Y | EC10A | 40.91% | CM_WWNI | 59.09% | [63 empty] | 1 |  | 0
501678 | Quality Management Systems Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2019-05-27 | 2020-09-11 | 2020-10-01 | 2020-09-14 |  | Scottish Water Wide | 0 | 0 | 0 | 22209.44 | 8568.8 | 6450 | 152520.12 | -157485.42 | 32262.95 | 0 | 0 | 0 | 32262.95 | 0 | 0 | 0 | 0 | 32262.95 | 306661.32 | [5 empty] | N | CM_M&G | 100%
45803 | Quarter SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-03-21 | 2011-07-29 | 2012-02-06 | 2012-02-13 | South Lanarkshire | 700959.78 | 0 | 7562.04 | -12097.51 | 0 | 0 | 0 | 0 | -4535.47 | 0 | 0 | 0 | 696424.31 | 0 | 0 | 0 | 0 | 696424.31 | 57522.26 | [5 empty] | N | WQ01B | 4.308% | WQ01C | 95.69%
403480 | Queen Margaret Drive Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-07-11 | 2014-07-30 | 2014-07-30 | 2014-09-03 | 2014-09-03 | Glasgow City | 63714.91 | 0 | 4774.57 | 0.01 | 0 | 0 | 0 | 0 | 4774.58 | 0 | 0 | 0 | 68489.49 | 0 | 0 | 0 | 0 | 68489.49 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
502937 | Quick Hits Critical Spares | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-11-30 | 2017-11-30 | 2017-12-20 | 2018-01-09 |  | Glasgow City | 0 | 0 | 0 | 0 | 522681.71 | 0 | 0 | 0 | 522681.71 | 0 | 0 | 0 | 522681.71 | 0 | 0 | 0 | 0 | 522681.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502285 | R&D - Innovation projects | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Wastewater |  | SWD | Research and Innovation | MS3 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2021-05-05 | 2021-05-06 | Scottish Water Wide | 0 | 0 | 0 | 11649.09 | 34439.64 | 209916.41 | 223001.58 | 285069.75 | 764076.47 | 0 | 0 | 0 | 764076.47 | 0 | 0 | 0 | 0 | 764076.47 | 1705308.55 | [5 empty] | N | I2S_WWNI | 100%
500638 | R&D SR15 Leakage Projects (ELL) | Q&S4 | Improving drinking water availability and resilience of service | Leakage |  |  | Water |  | SWD | Leakage | MS3 | 2015-05-18 | 2015-05-18 | 2015-06-01 | 2021-06-30 | 2021-06-30 | Scottish Water Wide | 0 | 0 | 49065.42 | 86310.56 | 88434 | 205451.91 | 83140.4 | 88393.93 | 600796.22 | 149203.78 | 149203.78 | 207120.2479 | 750000 | 57916.4679 | 0 | 0 | 57916.4679 | 807916.4679 | 0 | [5 empty] | N | CS14 | 100%
500640 | R&D SR15 Wastewater Treatment Pilots and Trials | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Wastewater | SW | SWD | Research and Innovation | MS3 | 2015-05-20 | 2015-05-20 | 2015-06-01 | 2021-05-07 | 2021-05-07 | Scottish Water Wide | 0 | 0 | 229898.78 | 381408.84 | 319675.69 | 359332.69 | 335397.31 | 300734.69 | 1926448 | 773551.75 | 773551.75 | 1073821.5228 | 2699999.75 | 300269.7728 | 0 | 0 | 300269.7728 | 3000269.5228 | 630290.41 | [5 empty] | N | I2S_WWNI | 100%
500641 | R&D SR15 Water PWNT Pilot | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Water |  | SWD | Research and Innovation | MS7 | 2015-05-20 | 2015-05-20 | 2015-10-01 | 2018-09-03 | 2018-09-03 | Scottish Water Wide | 0 | 0 | 93194 | 481705 | 195101 | 0 | 0 | 0 | 770000 | 0 | 0 | 0 | 770000 | 0 | 0 | 0 | 0 | 770000 | 1705308.55 | [5 empty] | N | I2S_WNI | 100%
500639 | R&D SR15 Water Treatment Pilots and Trials | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Water | SW | SWD | Research and Innovation | MS3 | 2015-05-20 | 2015-05-20 | 2015-06-01 | 2021-05-07 | 2021-05-07 | Scottish Water Wide | 0 | 0 | 543412 | 503258 | 238060 | -59730 | 90334.34 | 167695.69 | 1483030.03 | 746969.97 | 746969.9723 | 1036921.49 | 2230000 | 289951.5177 | 0 | 0 | 289951.5177 | 2519951.5177 | 1705308.55 |  |  |  |  | 110000 | N | I2S_WNI | 100%
512058 | R&I Define | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2021-03-31 | 2021-04-26 | 2021-04-29 | 2023-06-13 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000.06 | 0 | 0 | 750000.06 | 0 | 0 | 0 | 0 | 750000.06 | 311236.79 | [5 empty] | N | CM_M&G | 100%
512059 | R&I Develop | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2021-03-31 | 2021-04-26 | 2021-04-29 | 2023-06-13 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1999999.89 | 0 | 0 | 1999999.89 | 0 | 0 | 0 | 0 | 1999999.89 | 311236.79 | [5 empty] | N | CM_M&G | 100%
502623 | Raasay WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-04 | 2019-04-04 | Highland | 0 | 0 | 0 | 20930.23 | 374.31 | 915.54 | -20886.65 | 0 | 1333.43 | 0 | 0 | 0 | 1333.43 | 0 | 0 | 0 | 0 | 1333.43 | 122419.09 | [5 empty] | N | WG1 | 100%
46845 | Raasay WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-29 | 2011-09-08 | 2013-06-28 | 2013-09-30 | Highland | 2748896.12 | 0 | -24865.75 | 0 | 0 | 0 | 0 | 0 | -24865.75 | 0 | 0 | 0 | 2724030.37 | 0 | 0 | 0 | 0 | 2724030.37 | 28761.13 | [5 empty] | N | DW23 | 100%
402493 | Radon Mitigation Work At East Water Treatment Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-01-13 | 2012-08-18 | 2012-10-02 | 2016-03-22 |  | Aberdeenshire | 203810 | 0 | -8810 | 78.13 | 0 | 0 | 0 | 0 | -8731.87 | 0 | 0 | 0 | 195078.13 | 0 | 0 | 0 | 0 | 195078.13 | 119022.58 | [5 empty] | N | CM_M&G | 100%
506073 | RAINFALL DATA PROJECT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-04-06 |  | 2020-11-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23733.84 | 23733.84 | 0 | 0 | 0 | 23733.84 | 0 | 0 | 0 | 0 | 23733.84 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403408 | Ravelrigg PRV Hydro | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2013-03-01 | 2016-07-25 | 2016-07-25 | 2016-04-19 | 2016-07-25 | City of Edinburgh | 151966 | 151966 | 34348 | 3024.69 | 0 | 0 | 0 | 0 | 37372.69 | 0 | 0 | 0 | 189338.69 | 0 | 0 | 0 | 0 | 189338.69 | 0 | [5 empty] | N | CC1W | 100%
401532 | Raw Water Monitoring - WFD Article 7 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-02-03 | 2012-06-28 | 2012-07-24 | 2014-06-30 | 2014-08-29 | Scottish Water Wide | 810267 | 0 | 1571.09 | 3113.76 | 0 | 0 | 0 | 0 | 4684.85 | 0 | 0 | 0 | 814951.85 | 0 | 0 | 0 | 0 | 814951.85 | 0 | [5 empty] | N | DW24 | 100%
500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change |  |  | Water | SEPA | SWMD | Climate Change | MS7 | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-16 | 2016-12-22 | Scottish Water Wide | 0 | 0 | 16453.5 | 171883.5 | 85010.24 | 57019.46 | 0 | 0 | 330366.7 | 0 | 0 | 0 | 330366.7 | 0 | 0 | 0 | 0 | 330366.7 | 69200.64 | [5 empty] | N | CC4W | 100%
500036 | Raw Water Security Studies | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWD | SEMD | MS7 | 2015-02-17 | 2015-06-23 | 2015-06-23 | 2016-07-31 | 2016-07-31 | Scottish Water Wide | 0 | 0 | 302831.58 | 213427.42 | 0 | 3263.01 | 0 | 0 | 519522.01 | 0 | 0 | 0 | 519522.01 | 0 | 0 | 0 | 0 | 519522.01 | 737042.41 | [5 empty] | Y | DW9G | 100% | [64 empty] | 6 |  |  | 0
46378 | Raw Water Supplies - Gartmore to Killearn | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2014-03-10 | 2014-03-03 | 2014-03-06 | 2014-03-06 | Stirling | 64706.15 | 0 | 422 | 0 | 0 | 0 | 0 | 0 | 422 | 0 | 0 | 0 | 65128.15 | 0 | 0 | 0 | 0 | 65128.15 | 28761.13 | [5 empty] | N | DW10 | 100%
46377 | Raw Water Supplies - Kinlochard | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2014-02-24 | 2014-03-03 | 2014-03-06 | 2014-03-06 | Stirling | 49719.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49719.49 | 0 | 0 | 0 | 0 | 49719.49 | 0 | [6 empty] | DW10 | 100%
46376 | Raw Water Supplies - Loch Katrine-Trossachs Pier | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2011-06-22 | 2011-11-01 | 2013-03-22 | 2013-09-25 | Stirling | 2829666.4 | 0 | 6549.32 | 5545.52 | 0 | 0 | 0 | 0 | 12094.84 | 0 | 0 | 0 | 2841761.24 | 0 | 0 | 0 | 0 | 2841761.24 | 28761.13 | [5 empty] | N | DW10 | 100%
46379 | Raw Water Supplies - Newcastleton Activity Centre | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2011-03-31 | 2011-03-31 | 2012-02-24 | 2012-03-14 | Scottish Borders | 11672.67 | 0 | 0.57 | 0 | 0 | 0 | 0 | 0 | 0.57 | 0 | 0 | 0 | 11673.24 | 0 | 0 | 0 | 0 | 11673.24 | 0 | [5 empty] | N | DW10 | 100%
46380 | Raw Water Supplies - Stronachlacher - Loch Arklet | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2011-06-22 | 2011-12-19 | 2013-09-30 | 2013-12-10 | Stirling | 2791910.25 | 0 | 8317.31 | 19810.69 | 0 | 0 | 0 | 0 | 28128 | 0 | 0 | 0 | 2820038.25 | 0 | 0 | 0 | 0 | 2820038.25 | 28761.13 | [5 empty] | N | DW10 | 100%
511375 | Rawburn WTW - Inlet Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-10 | 2021-09-15 | 2022-04-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120.21 | 1120.21 | 29611.11 | 0 | 0 | 30731.32 | 0 | 0 | 0 | 0 | 30731.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507671 | Rawburn WTW - Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-30 | 2021-09-06 | 2022-04-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 31745.31 | 0 | 0 | 31908.86 | 0 | 0 | 0 | 0 | 31908.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501396 | Rawburn WTW Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 | 2020-12-07 | 2020-12-07 | 2021-02-26 | 2021-02-26 |  | Scottish Borders | 0 | 0 | 0 | 45032.93 | 10031.46 | 1158.06 | 0 | 0 | 56222.45 | 0 | 0 | 0 | 56222.45 | 0 | 0 | 0 | 0 | 56222.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502359 | Rawburn WTW Sludge Plant Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 | 2020-12-07 | 2020-12-07 | 2020-12-10 | 2021-02-26 |  | Scottish Borders | 0 | 0 | 0 | 42934.57 | 6152.19 | 6102.48 | 12568.39 | -44758.08 | 22999.55 | 32232.76 | 0 | 0 | 55232.31 | 0 | 0 | 0 | 0 | 55232.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511506 | RCC Dom Wastewater East SR21 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS2 |  | 2021-03-24 |  | 2027-02-27 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23921690.08 | 0 | 0 | 23921690.08 | 0 | 0 | 0 | 0 | 23921690.08 | 0 | [5 empty] | N | SG2 | 100%
511508 | RCC Dom Wastewater North SR21 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS2 |  | 2021-03-24 |  | 2027-02-27 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20341549.61 | 0 | 0 | 20341549.61 | 0 | 0 | 0 | 0 | 20341549.61 | 0 | [5 empty] | N | SG2 | 100%
511510 | RCC Dom Wastewater South SR21 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS2 |  | 2021-03-19 |  | 2027-02-27 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3406848.34 | 0 | 0 | 3406848.34 | 0 | 0 | 0 | 0 | 3406848.34 | 0 | [5 empty] | N | SG2 | 100%
511512 | RCC Dom Wastewater West SR21 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS2 |  | 2021-03-24 |  | 2027-02-27 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22986279.4 | 0 | 0 | 22986279.4 | 0 | 0 | 0 | 0 | 22986279.4 | 0 | [5 empty] | N | SG2 | 100%
511507 | RCC Dom Water East SR21 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS2 |  | 2021-03-24 |  | 2027-02-27 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16633331.11 | 0 | 0 | 16633331.11 | 0 | 0 | 0 | 0 | 16633331.11 | 0 | [5 empty] | N | WG2 | 100%
511509 | RCC Dom Water North SR21 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS2 |  | 2021-03-24 |  | 2027-02-27 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13178650.94 | 0 | 0 | 13178650.94 | 0 | 0 | 0 | 0 | 13178650.94 | 0 | [5 empty] | N | WG2 | 100%
511511 | RCC Dom Water South SR21 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS2 |  | 2021-03-19 |  | 2027-02-27 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333581.29 | 0 | 0 | 2333581.29 | 0 | 0 | 0 | 0 | 2333581.29 | 0 | [5 empty] | N | WG2 | 100%
511513 | RCC Dom Water West SR21 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS2 |  | 2021-03-24 |  | 2027-02-27 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12198069.24 | 0 | 0 | 12198069.24 | 0 | 0 | 0 | 0 | 12198069.24 | 0 | [5 empty] | N | WG2 | 100%
511514 | RCC Non Dom Wastewater East SR21 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 0 | [5 empty] | N | SG2 | 100%
511516 | RCC Non Dom Wastewater North SR21 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 0 | [5 empty] | N | SG2 | 100%
511518 | RCC Non Dom Wastewater South SR21 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 0 | [5 empty] | N | SG2 | 100%
511520 | RCC Non Dom Wastewater West SR21 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 0 | [5 empty] | N | SG2 | 100%
511515 | RCC Non Dom Water East SR21 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 0 | [5 empty] | N | WG2 | 100%
511517 | RCC Non Dom Water North SR21 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 0 | [5 empty] | N | WG2 | 100%
511519 | RCC Non Dom Water South SR21 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 0 | [5 empty] | N | WG2 | 100%
511521 | RCC Non Dom Water West SR21 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72 | 0 | 0 | 0.72 | 0 | 0 | 0 | 0 | 0.72 | 0 | [5 empty] | N | WG2 | 100%
500984 | RCC Programme Incheril Kinlochewe | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-12-09 | 2016-02-22 | 2016-03-29 | 2016-10-27 |  | Highland | 0 | 0 | 46323 | 123651.57 | 3825.93 | 7865.9 | 0 | 0 | 181666.4 | 0 | 0 | 0 | 181666.4 | 0 | 0 | 0 | 0 | 181666.4 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500982 | RCC Programme Wester Teaninch Farm | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-09-05 | 2018-02-21 | 2018-03-19 | 2019-03-22 |  | Highland | 0 | 0 | 0 | 6310.9 | 141719.6 | 540624.88 | -5950.2 | 177.39 | 682882.57 | 0 | 0 | 0 | 682882.57 | 0 | 0 | 0 | 0 | 682882.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506491 | RCI (Kelso North & Sprouston DMA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-11-22 | 2024-01-26 | 2024-04-25 | 2025-03-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2606.41 | 2606.41 | 357393.38 | 0 | 0 | 359999.79 | 0 | 0 | 0 | 0 | 359999.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506153 | RCI Achachork DMA (Toravaig) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-05-25 | 2021-01-15 | 2021-01-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8600.18 | 8600.18 | -4194.81 | 0 | 0 | 4405.37 | 0 | 0 | 0 | 0 | 4405.37 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505460 | RCI Arbuthnott DMA (Pitcarry Farm) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2020-03-27 | 2021-03-24 | 2021-03-29 | 2021-11-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 402.89 | 162718.84 | 163121.73 | 438392.27 | 0 | 0 | 601514 | 0 | 0 | 0 | 0 | 601514 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505902 | RCI Ardeonaig DMA (Ardenoaig) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-05-22 | 2021-01-18 | 2022-01-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34653 | 34653 | 125347.39 | 0 | 0 | 160000.39 | 0 | 0 | 0 | 0 | 160000.39 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506189 | RCI Armadale PS DMA (Shebster WSZ) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-21 | 2022-04-18 | 2022-05-23 | 2023-07-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19476.96 | 19476.96 | 1980671.68 | 0 | 0 | 2000148.64 | 0 | 0 | 0 | 0 | 2000148.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502791 | RCI Athelstaneford DMA (East Garleton Farm) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2027-04-02 | 2028-01-17 | 2028-04-13 | 2028-11-08 |  | East Lothian | 0 | 0 | 0 | 0 | 31400 | 31600 | 0 | -41344 | 21656 | 530983.43 | 0 | 0 | 552639.43 | 0 | 0 | 0 | 0 | 552639.43 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505885 | RCI Auchenbach Pumping Station DMA (Colinbar Circle) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-05-25 | 2021-04-14 | 2021-08-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38457.03 | 38457.03 | 247416.76 | 0 | 0 | 285873.79 | 0 | 0 | 0 | 0 | 285873.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511324 | RCI Auldearn DMA (Maviston Xmas Trees) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 |  | 2021-07-05 | 2021-10-01 | 2022-05-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000.02 | 0 | 0 | 155000.02 | 0 | 0 | 0 | 0 | 155000.02 | 0 | [5 empty] | N | SR21_WA | 100%
507418 | RCI Back DMA (Back Tolsta WOA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-11-08 | 2024-02-12 | 2024-05-13 | 2025-09-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9644.91 | 9644.91 | 1370355.56 | 0 | 0 | 1380000.47 | 0 | 0 | 0 | 0 | 1380000.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506233 | RCI Ballygrant DMA (Dunlossit Estate) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-07-07 | 2023-05-24 | 2023-11-01 | 2025-05-14 | 2025-08-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568.24 | 568.24 | 359934.51 | 0 | 0 | 360502.75 | 0 | 0 | 0 | 0 | 360502.75 | 0 | [5 empty] | N | SR21_WA | 100%
505447 | RCI Bigton DMA (Maywick Road) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2020-04-29 | 2021-05-10 | 2021-07-12 | 2022-10-28 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152802 | 152802 | 1439312.97 | 0 | 0 | 1592114.97 | 0 | 0 | 0 | 0 | 1592114.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506747 | RCI Bonhill DMA (Ladys Gate) (New) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-06-29 | 2020-10-01 | 2021-01-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50099 | 50099 | 0 | 0 | 0 | 50099 | 0 | 0 | 0 | 0 | 50099 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506228 | RCI Bowmore DMA (Torra Mains) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-07-29 | 2021-10-25 | 2021-12-06 | 2023-01-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26134.48 | 26134.48 | 1034301.77 | 0 | 0 | 1060436.25 | 0 | 0 | 0 | 0 | 1060436.25 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506619 | RCI Brabster DMA (Loch Calder WOA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2022-03-24 | 2024-02-08 | 2024-07-18 | 2026-01-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
505439 | RCI Brackenbrae Avenue DMA (Bishopbriggs) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-03-12 | 2020-09-14 | 2020-12-22 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 9900.84 | 106815.16 | 116716 | 0 | 0 | 0 | 116716 | 0 | 0 | 0 | 0 | 116716 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506271 | RCI Bragar DMA (West Lewis WOA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2022-04-20 | 2024-03-06 | 2024-08-14 | 2026-02-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4098.75 | 4098.75 | 575901.18 | 0 | 0 | 579999.93 | 0 | 0 | 0 | 0 | 579999.93 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506032 | RCI Broadford DMA & Breakish DMA (Broadford) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-29 | 2021-07-05 | 2021-08-30 | 2022-11-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88792.63 | 88792.63 | 2860320.66 | 0 | 0 | 2949113.29 | 0 | 0 | 0 | 0 | 2949113.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506402 | RCI Brue DMA (West Lewis WOA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2022-04-20 | 2024-06-11 | 2024-11-19 | 2026-06-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3023.46 | 3023.46 | 376976.53 | 0 | 0 | 379999.99 | 0 | 0 | 0 | 0 | 379999.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506748 | RCI Cairndow DMA (Cairndow WSZ) (New) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-06-29 | 2020-11-11 | 2021-11-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59500.13 | 59500.13 | 399340.48 | 0 | 0 | 458840.61 | 0 | 0 | 0 | 0 | 458840.61 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506187 | RCI Carnbee SR To Crail SR TM DMA (Balcaskie) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2021-03-12 | 2021-04-26 | 2021-05-13 | 2021-10-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55164 | 55164 | 123026.29 | 0 | 0 | 178190.29 | 0 | 0 | 0 | 0 | 178190.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507057 | RCI Catterthun DMA (Craigton of Monikie) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2021-03-30 | 2021-05-24 | 2021-06-14 | 2022-05-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69690 | 69690 | 725279.77 | 0 | 0 | 794969.77 | 0 | 0 | 0 | 0 | 794969.77 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511334 | RCI Clachan DMA (Longrigg) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-12-02 | 2023-06-12 | 2023-09-08 | 2024-08-15 | 2024-08-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35225.28 | 35225.28 | 604774.72 | 0 | 0 | 640000 | 0 | 0 | 0 | 0 | 640000 | 0 | [5 empty] | N | SR21_WA | 100%
506186 | RCI Clousta & Vementry DMA (Vementry) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-10-25 | 2024-01-01 | 2024-03-27 | 2025-05-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5722.08 | 5722.08 | 794277.79 | 0 | 0 | 799999.87 | 0 | 0 | 0 | 0 | 799999.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506025 | RCI Colintraive DMA (Dhu Loch WOA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-10-01 | 2024-01-24 | 2024-04-18 | 2025-07-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6298.96 | 6298.96 | 913700.94 | 0 | 0 | 919999.9 | 0 | 0 | 0 | 0 | 919999.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511704 | RCI Comrie & Bogside DMA (Righead Farm) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-07-13 | 2023-01-19 | 2023-04-19 | 2024-03-26 | 2024-03-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468.88 | 468.88 | 879999.96 | 0 | 0 | 880468.84 | 0 | 0 | 0 | 0 | 880468.84 | 0 | [5 empty] | N | SR21_WA | 100%
507186 | RCI Craigie DMA (Plewlands) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2021-03-30 | 2021-08-02 | 2021-09-28 | 2022-05-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37270.35 | 37270.35 | 1276628.4 | 0 | 0 | 1313898.75 | 0 | 0 | 0 | 0 | 1313898.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507061 | RCI Craigrothie & Dairsie DMA (Pitscottie TM Miltonfield) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2021-03-30 | 2021-05-10 | 2021-06-14 | 2021-09-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80733 | 80733 | 217576.43 | 0 | 0 | 298309.43 | 0 | 0 | 0 | 0 | 298309.43 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506188 | RCI Culbo DMA (Culbokie) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW2 | 2021-07-05 | 2021-12-06 | 2022-03-18 | 2023-09-29 | 2024-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2237.23 | 2237.23 | 557762.77 | 0 | 0 | 560000 | 0 | 0 | 0 | 0 | 560000 | 0 | [5 empty] | N | SR21_SS | 100%
506627 | RCI Duncanston DMA (Assynt WOA) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW2 | 2021-07-12 | 2022-05-09 | 2022-07-01 | 2024-01-12 | 2024-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2258.2 | 2258.2 | 1097741.8 | 0 | 0 | 1100000 | 0 | 0 | 0 | 0 | 1100000 | 0 | [5 empty] | N | SR21_WA | 100%
507060 | RCI Dunning & Aberuthven DMA (Dunning) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2021-03-30 | 2021-09-13 | 2021-10-04 | 2022-05-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66247 | 66247 | 1406089.05 | 0 | 0 | 1472336.05 | 0 | 0 | 0 | 0 | 1472336.05 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506231 | RCI Eathie DMA (Muirhead Farm and Eathie Mains) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-07-01 | 2021-10-25 | 2021-11-23 | 2023-06-06 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14060.07 | 14060.07 | 2065939.71 | 0 | 0 | 2079999.78 | 0 | 0 | 0 | 0 | 2079999.78 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509633 | RCI Evanton Swordale DMA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS1 | 2020-11-11 | 2021-05-10 | 2021-10-15 | 2023-04-28 | 2023-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617.82 | 617.82 | 350499.93 | 0 | 0 | 351117.75 | 0 | 0 | 0 | 0 | 351117.75 | 444766.03 | [5 empty] | N | SR21_WA | 50% | WG5 | 50%
504633 | RCI Evanton Swordale DMA (Swordale Road) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-15 | 2021-03-02 | 2021-10-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 9431.67 | 34239.33 | 43671 | 306328.99 | 0 | 0 | 349999.99 | 0 | 0 | 0 | 0 | 349999.99 | 119022.58 | [5 empty] | N | WSNI | 100%
511332 | RCI Ferntower DMA (Sauchie Place) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 |  | 2021-07-05 | 2021-10-01 | 2022-05-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000.02 | 0 | 0 | 200000.02 | 0 | 0 | 0 | 0 | 200000.02 | 0 | [5 empty] | N | SR21_WA | 100%
511339 | RCI Findhorn Bridge DMA (ARM) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 |  | 2021-07-05 | 2021-10-01 | 2022-05-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239999.94 | 0 | 0 | 239999.94 | 0 | 0 | 0 | 0 | 239999.94 | 0 | [5 empty] | N | SR21_WA | 100%
505442 | RCI Garve DMA (Little Garve) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-02 | 2021-07-05 | 2022-04-25 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58712 | 58712 | 190287.97 | 0 | 0 | 248999.97 | 0 | 0 | 0 | 0 | 248999.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506549 | RCI Gorbals SR to Barrhead DMA (Aurs Rd and Manse Court) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-06-22 | 2021-07-08 | 2022-02-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33009 | 33009 | 116991.16 | 0 | 0 | 150000.16 | 0 | 0 | 0 | 0 | 150000.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510538 | RCI Helensburgh North East DMA (Charlotte St - ARM) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS2 |  | 2021-01-18 | 2021-08-19 | 2022-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8564 | 8564 | 91436.26 | 0 | 0 | 100000.26 | 0 | 0 | 0 | 0 | 100000.26 | 0 | [5 empty] | N | SR21_WA | 100%
505504 | RCI High Dykes DMA (Auchincarroch Rd) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2020-03-31 | 2021-07-19 | 2021-08-10 | 2022-04-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112580 | 112580 | 1235444.9 | 0 | 0 | 1348024.9 | 0 | 0 | 0 | 0 | 1348024.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505927 | RCI Hilliclay DMA (Stainland) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-04-10 | 2022-07-15 | 2022-12-23 | 2024-07-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12270.18 | 12270.18 | 1027773.96 | 0 | 0 | 1040044.14 | 0 | 0 | 0 | 0 | 1040044.14 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506185 | RCI Houston DMA (Hagart Rd and South Mound) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-05-25 | 2020-09-10 | 2021-08-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120665 | 120665 | 125031.53 | 0 | 0 | 245696.53 | 0 | 0 | 0 | 0 | 245696.53 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505893 | RCI Houston DMA (Manse Crescent) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-05-25 | 2020-08-17 | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199832 | 199832 | 0 | 0 | 0 | 199832 | 0 | 0 | 0 | 0 | 199832 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506241 | RCI Kilmuir DMA (Kilmuir) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-07 | 2022-06-15 | 2022-10-10 | 2024-01-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171402 | 171402 | 3528597.58 | 0 | 0 | 3699999.58 | 0 | 0 | 0 | 0 | 3699999.58 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505499 | RCI Kilmun & Ardentinny DMA (Johnstone Avenue) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-03-17 | 2020-08-02 | 2021-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 86.12 | 71706.88 | 71793 | 0 | 0 | 0 | 71793 | 0 | 0 | 0 | 0 | 71793 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507991 | RCI Kilpatrick Drive DMA (Moorfoot) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWMD | SR21 Early Start | MS2 |  | 2020-09-15 | 2021-07-08 | 2021-10-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21596 | 21596 | 158404.07 | 0 | 0 | 180000.07 | 0 | 0 | 0 | 0 | 180000.07 | 0 | [5 empty] | N | SR21_SS | 100%
505497 | RCI Kingsmuir DMA (Golf Club Forfar) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2020-03-27 | 2021-05-10 | 2021-05-31 | 2022-01-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118672 | 118672 | 761327.9 | 0 | 0 | 879999.9 | 0 | 0 | 0 | 0 | 879999.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507779 | RCI Kinlochard DMA (Forest Hills) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWMD | SR21 Early Start | MS2 |  | 2020-09-15 | 2021-07-15 | 2022-02-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13817 | 13817 | 86183.49 | 0 | 0 | 100000.49 | 0 | 0 | 0 | 0 | 100000.49 | 0 | [5 empty] | N | SR21_SS | 100%
506618 | RCI Kinlochbervie DMA (Kinlochbervie WOA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-21 | 2021-06-21 | 2021-11-05 | 2022-08-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13370.18 | 13370.18 | 1026678.08 | 0 | 0 | 1040048.26 | 0 | 0 | 0 | 0 | 1040048.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506232 | RCI Kinlochleven DMA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-09-17 | 2021-10-25 | 2021-12-06 | 2022-11-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19540.08 | 19540.08 | 940609.18 | 0 | 0 | 960149.26 | 0 | 0 | 0 | 0 | 960149.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506234 | RCI Luing DMA (Cullipool) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-07-29 | 2021-10-25 | 2021-12-06 | 2023-03-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18138.18 | 18138.18 | 541994.64 | 0 | 0 | 560132.82 | 0 | 0 | 0 | 0 | 560132.82 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505445 | RCI Mains Hill DMA (Mains River) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-03-12 | 2020-08-10 | 2020-12-22 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 13282.92 | 111898.08 | 125181 | 1999.8 | 0 | 0 | 127180.8 | 0 | 0 | 0 | 0 | 127180.8 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511945 | RCI Mearns Road North DMA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-07-13 | 2023-01-19 | 2023-04-19 | 2024-03-26 | 2024-03-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443.51 | 443.51 | 330000 | 0 | 0 | 330443.51 | 0 | 0 | 0 | 0 | 330443.51 | 0 | [5 empty] | N | SR21_WA | 100%
506096 | RCI Nether Strathkinness SRMA DMA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2020-05-14 | 2020-08-31 | 2020-09-29 | 2021-03-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230781 | 230781 | 6365 | 0 | 0 | 237146 | 0 | 0 | 0 | 0 | 237146 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506130 | RCI Newfield PS to Broadmuir TM DMA (Peterhead Newfield 12&quot; TM) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-04-27 | 2024-03-13 | 2024-08-21 | 2026-03-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10881.32 | 10881.32 | 14989412.97 | 0 | 0 | 15000294.29 | 0 | 0 | 0 | 0 | 15000294.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507226 | RCI Newtonhill & Muchalls DMA (Newtonhill Rd) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2021-03-25 | 2021-05-24 | 2021-06-14 | 2021-11-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15186 | 15186 | 340505.44 | 0 | 0 | 355691.44 | 0 | 0 | 0 | 0 | 355691.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506545 | RCI Non - DMA (Bourtie Inverurie WSZ) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2022-03-23 | 2024-02-07 | 2024-07-17 | 2026-01-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7630 | 7630 | 952370.45 | 0 | 0 | 960000.45 | 0 | 0 | 0 | 0 | 960000.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509630 | RCI Nonakiln to Lamington TM DMA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS1 | 2020-11-11 | 2021-05-10 | 2021-10-15 | 2023-04-28 | 2023-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219.59 | 219.59 | 305500.12 | 0 | 0 | 305719.71 | 0 | 0 | 0 | 0 | 305719.71 | 0 | [5 empty] | N | SR21_WA | 100%
504301 | RCI Nonakiln to Lamington TM DMA (Scotsburn - New) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-03-30 | 2021-06-07 | 2022-01-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 645.24 | 26563.76 | 27209 | 277791.45 | 0 | 0 | 305000.45 | 0 | 0 | 0 | 0 | 305000.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506236 | RCI Non-DMA (Rosebery ERM WSZ - Cousland) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-06-22 | 2020-11-13 | 2021-07-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98800 | 98800 | 200 | 0 | 0 | 99000 | 0 | 0 | 0 | 0 | 99000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506400 | RCI North Lochs Main DMA (Grimshader) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2022-02-18 | 2024-06-11 | 2024-11-19 | 2026-06-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.82 | 5961.82 | 834047.64 | 0 | 0 | 840009.46 | 0 | 0 | 0 | 0 | 840009.46 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507498 | RCI Pan Scotland - Downsizing of Mains Assessment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2020-07-20 | 2020-07-29 | 2020-08-18 | 2022-04-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79566 | 79566 | 120433.67 | 0 | 0 | 199999.67 | 0 | 0 | 0 | 0 | 199999.67 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508760 | RCI Pan Scotland Deliver Project 2 (Pilot) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW2 | 2022-01-26 | 2023-09-11 | 2023-12-07 | 2026-02-03 | 2026-02-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.68 | 10.68 | 5544389.37 | 0 | 0 | 5544400.05 | 0 | 0 | 0 | 0 | 5544400.05 | 0 | [5 empty] | N | SR21_WA | 100%
508685 | RCI Pan Scotland Plan Project 1 (Pilot) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-26 | 2021-07-19 | 2021-07-19 | 2023-01-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32194.4 | 32194.4 | 87805.62 | 0 | 0 | 120000.02 | 0 | 0 | 0 | 0 | 120000.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506399 | RCI Peat Inn & Denhead DMA (Cameron) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2021-03-12 | 2021-05-10 | 2021-06-03 | 2022-07-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121358 | 121358 | 873925.74 | 0 | 0 | 995283.74 | 0 | 0 | 0 | 0 | 995283.74 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509293 | RCI Programme Installation of PRVs - East Region | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU |  | 2021-04-26 | 2021-07-16 | 2022-02-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246666.66 | 0 | 0 | 246666.66 | 0 | 0 | 0 | 0 | 246666.66 | 0 | [5 empty] | N | SR21_WA | 100%
510411 | RCI PRVs and Transients Pilot - East Region | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS2 |  | 2021-01-05 | 2021-06-21 | 2022-02-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2458 | 2458 | 122541.68 | 0 | 0 | 124999.68 | 0 | 0 | 0 | 0 | 124999.68 | 0 | [5 empty] | N | SR21_WA | 100%
506029 | RCI Roskhill DMA & Dunvegan DMA (Roag) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-29 | 2021-07-05 | 2021-10-11 | 2022-12-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101642.54 | 101642.54 | 2571549.45 | 0 | 0 | 2673191.99 | 0 | 0 | 0 | 0 | 2673191.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507189 | RCI Rossie DMA (Ethie PMA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2021-03-30 | 2021-09-13 | 2021-10-04 | 2022-12-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39146 | 39146 | 1045857.04 | 0 | 0 | 1085003.04 | 0 | 0 | 0 | 0 | 1085003.04 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511594 | RCI Rychraggan DMA (Balnain) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW2 | 2021-05-12 | 2022-11-18 | 2023-02-16 | 2024-01-24 | 2024-01-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2093.02 | 2093.02 | 597906.98 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | [5 empty] | N | SR21_WA | 100%
511304 | RCI Skernish DMA (DSR Comms Link) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS2 |  | 2021-03-05 | 2021-06-23 | 2022-02-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995.33 | 1995.33 | 28004.67 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | 0 | [5 empty] | N | SR21_WA | 100%
507493 | RCI SR21 ES Mains of Moyness - Non DMA Phase 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-07-29 | 2022-04-15 | 2022-08-15 | 2023-11-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60892.79 | 60892.79 | 1659075.77 | 0 | 0 | 1719968.56 | 0 | 0 | 0 | 0 | 1719968.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507594 | RCI St Marys DMA (Laird Street) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2021-03-12 | 2021-05-24 | 2021-07-05 | 2021-12-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38151 | 38151 | 322689.85 | 0 | 0 | 360840.85 | 0 | 0 | 0 | 0 | 360840.85 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506269 | RCI Starthy DMA Apigill (Loch Leacach) WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2022-03-25 | 2024-02-09 | 2024-07-19 | 2026-01-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
511337 | RCI Stirling TC North DMA (ARM) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS2 |  | 2021-03-05 | 2021-11-12 | 2022-06-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425.59 | 7425.59 | 103074.41 | 0 | 0 | 110500 | 0 | 0 | 0 | 0 | 110500 | 0 | [5 empty] | N | SR21_WA | 100%
505503 | RCI Strachur St Catherines DMA (Forest View and HighHall) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-03-11 | 2020-08-10 | 2021-01-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 15382.6 | 222293.03 | 237675.64 | 1000 | 0 | 0 | 238675.64 | 0 | 0 | 0 | 0 | 238675.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506616 | RCI Strachur St Catherines DMA (Phase 2) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-07-29 | 2022-07-15 | 2022-12-23 | 2024-07-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20649 | 20649 | 719350.86 | 0 | 0 | 739999.86 | 0 | 0 | 0 | 0 | 739999.86 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507569 | RCI Sumburgh DMA (Quendale) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2022-02-28 | 2024-06-10 | 2024-09-09 | 2026-03-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000.47 | 13000.47 | 1866999.69 | 0 | 0 | 1880000.16 | 0 | 0 | 0 | 0 | 1880000.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506149 | RCI Tankerness and Foubister DMA (Tankerness) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-28 | 2021-09-27 | 2021-11-08 | 2023-04-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122045.91 | 122045.91 | 2537954.09 | 0 | 0 | 2660000 | 0 | 0 | 0 | 0 | 2660000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507228 | RCI Tayvallich DMA (Ardrishaig WOA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-07-29 | 2021-10-25 | 2021-12-06 | 2023-03-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63749.81 | 63749.81 | 331078.42 | 0 | 0 | 394828.23 | 0 | 0 | 0 | 0 | 394828.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506275 | RCI Tore and Drumderfit DMA (Tore to Kessock) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW2 | 2021-07-05 | 2021-10-11 | 2021-11-26 | 2023-06-09 | 2023-09-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2284.93 | 2284.93 | 837715.07 | 0 | 0 | 840000 | 0 | 0 | 0 | 0 | 840000 | 0 | [5 empty] | N | SR21_WA | 100%
506889 | RCI Toward DMA (Toward Farm) New | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-02-28 | 2024-01-15 | 2024-06-24 | 2026-01-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418.6 | 418.6 | 0 | 0 | 0 | 418.6 | 0 | 0 | 0 | 0 | 418.6 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508926 | RCI University Avenue DMA (University Place) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWMD | SR21 Early Start | MS3 |  | 2020-09-30 | 2020-12-15 | 2021-08-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19824 | 19824 | 37105.61 | 0 | 0 | 56929.61 | 0 | 0 | 0 | 0 | 56929.61 | 0 | [5 empty] | N | SR21_WA | 100%
506190 | RCI Watten DMA (Loch Calder CWT WSZ) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2022-03-25 | 2024-02-09 | 2024-07-19 | 2026-01-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
505693 | RCI West Ballochy DMA (Hillside) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2020-03-27 | 2021-06-21 | 2021-07-12 | 2023-06-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117055 | 117055 | 2802944.72 | 0 | 0 | 2919999.72 | 0 | 0 | 0 | 0 | 2919999.72 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506151 | RCI West Line DMA (Oust WSZ) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-06-04 | 2022-12-19 | 2023-01-20 | 2024-03-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63432 | 63432 | 2336568.42 | 0 | 0 | 2400000.42 | 0 | 0 | 0 | 0 | 2400000.42 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505633 | RCI West Line DMA (Thusater) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-03-12 | 2021-03-15 | 2021-10-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 255.36 | 42014.63 | 42269.98 | 154060.22 | 0 | 0 | 196330.2 | 0 | 0 | 0 | 0 | 196330.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508398 | RCI Woodhill Road DMA (Ruskin Square) | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWMD | SR21 Early Start | MS3 |  | 2020-09-14 | 2020-10-05 | 2021-05-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252782 | 252782 | 42081.39 | 0 | 0 | 294863.39 | 0 | 0 | 0 | 0 | 294863.39 | 0 | [5 empty] | N | SR21_SS | 100%
500710 | Reactive Lead Communication Pipe Replacement Programme | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2021-05-28 | 2021-05-28 | Scottish Water Wide | 0 | 0 | 33890 | 137390.05 | 9313 | 401480.46 | 208668.04 | 207668.19 | 998409.74 | -17254.53 | -17254.534 | -23952.2307 | 981155.21 | -6697.6967 | 0 | 0 | -6697.6967 | 974457.5133 | 1617830.77 | [5 empty] | N | DW1A | 100%
505975 | Reallocation of Get To Site In Half The Time Phase 2 project costs | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-03-31 | 2020-06-08 | 2020-06-09 | 2020-06-09 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479439.25 | 479439.25 | -29439.25 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 450000 | 297505.85 | [5 empty] | N | FL_DD | 50% | SG1 | 50%
502975 | Red Burn Sewer Crossings | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS1 | 2020-01-24 | 2021-04-19 | 2021-06-25 | 2022-03-24 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 27146.7 | 51487.27 | 179169.84 | 412017.73 | 669821.53 | 2885218.16 | 0 | 0 | 3555039.69 | 0 | 0 | 0 | 0 | 3555039.69 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403433 | Redford Avenue Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-04-16 | 2014-09-15 | 2014-09-22 | 2015-03-30 | 2015-03-30 | City of Edinburgh | 655709 | 655709 | 32421 | 0 | -26131.25 | 0 | 0 | 0 | 6289.75 | 0 | 0 | 0 | 661998.75 | 0 | 0 | 0 | 0 | 661998.75 | 180449.74 |  |  |  |  | 5400 | N | FL_DD | 100%
402630 | Redundant Assets Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2012-04-17 | 2013-02-20 | 2013-02-20 | 2016-02-10 |  | Scottish Water Wide | 360247 | 0 | 31652.8 | 0 | 0 | 0 | 0 | 0 | 31652.8 | 0 | 0 | 0 | 391899.8 | 0 | 0 | 0 | 0 | 391899.8 | 613322.63 | [5 empty] | N | CM_M&G | 100%
510961 | Refresh Flooding Database | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS2 | 2021-02-23 | 2021-03-15 | 2021-05-10 | 2021-05-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284437.56 | 284437.56 | 0 | 0 | 0 | 284437.56 | 0 | 0 | 0 | 0 | 284437.56 | 613322.63 | [5 empty] | N | CM_M&G | 100%
510729 | Refresh Mobile Devices | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS0 | 2021-03-15 | 2021-06-21 | 2021-10-20 | 2023-02-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434825 | 434825 | 933479.71 | 0 | 0 | 1368304.71 | 0 | 0 | 0 | 0 | 1368304.71 | 613322.63 | [5 empty] | N | CM_M&G | 100%
511261 | Refurbishment Glenhove TWP No 1 Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-18 | 2021-11-11 | 2022-06-23 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2127.44 | 2127.44 | 118954.2 | 0 | 0 | 121081.64 | 0 | 0 | 0 | 0 | 121081.64 | 119022.58 | [5 empty] | N | WSNI | 100%
59 | REMOVAL OF RAW WATER SUPPLIES | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 |  | 2005-01-19 | 2001-10-01 | 2003-03-31 | 2009-02-28 | Scottish Water Wide | 782069.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782069.85 | 0 | 0 | 0 | 0 | 782069.85 | 0 | [6 empty] | DW3 | 33% | Wa13 | 33% | Wa1 | 34%
403885 | Renewables - Horizons Transfers Holding Line (Complete Projects) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-06-01 | 2014-06-01 | 2014-06-01 | 2014-06-01 | 2015-01-29 | Scottish Water Wide | 3501204.72 | 0 | -4.72 | -5505.38 | 0 | 0 | 0 | 0 | -5510.1 | 0 | 0 | 0 | 3495694.62 | 0 | 0 | 0 | 0 | 3495694.62 | 0 | [5 empty] | N | CC1W | 100%
403823 | Renewables - Hydro - Glen Ogil Hydro Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2014-12-18 | 2015-01-23 | Scottish Water Wide | 1048449 | 0 | -42384 | 276.34 | 0 | 0 | 0 | 0 | -42107.66 | 0 | 0 | 0 | 1006341.34 | 0 | 0 | 0 | 0 | 1006341.34 | 0 | [5 empty] | N | CC1W | 100%
403824 | Renewables - Hydro - Knockjarder SR Difgen Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-04 | 2014-08-04 | 2015-06-09 | 2015-06-10 | 2015-06-10 | Scottish Water Wide | 317483 | 0 | -20562.26 | 0 | 0 | 0 | 0 | 0 | -20562.26 | 0 | 0 | 0 | 296920.74 | 0 | 0 | 0 | 0 | 296920.74 | 0 | [5 empty] | N | CC1W | 100%
403825 | Renewables - Hydro - Loch Coulter Hydro Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-11-11 | 2015-03-31 | 2015-03-31 | Scottish Water Wide | 1013163 | 0 | 15133 | 4704 | 3778.49 | 5248.79 | 0 | 0 | 28864.28 | 0 | 0 | 0 | 1042027.28 | 0 | 0 | 0 | 0 | 1042027.28 | 0 | [5 empty] | N | CC1W | 100%
403826 | Renewables - Hydro - Loch Spallander Hydro Scheme | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water | SW | SWMD | Renewable power | MS7 | 2014-07-21 | 2014-07-21 | 2014-10-27 | 2015-03-31 | 2015-03-31 | Scottish Water Wide | 1458555 | 1458555 | -3683.63 | 107293.63 | 26898.92 | 0 | 0 | 0 | 130508.92 | 0 | 0 | 0 | 1589063.92 | 0 | 0 | 0 | 0 | 1589063.92 | 0 | [5 empty] | Y | CC1W | 100% | [60 empty] | 0.52 | [6 empty] | 0
403827 | Renewables - Hydro - Saline Difgen Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2014-08-08 | 2014-08-08 | 2014-11-28 | 2015-03-26 | 2015-03-26 | Scottish Water Wide | 927766 | 0 | 299321 | 78583 | 117262.53 | 180283.01 | 115740.89 | 9974.57 | 801165 | 2890.09 | 2890.09 | 4011.9369 | 1731821.09 | 1121.8469 | 0 | 0 | 1121.8469 | 1732942.9369 | 0 | [5 empty] | N | CC1W | 100%
403828 | Renewables - Hydro - Woodend Difgen Scheme | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2015-01-23 | 2015-01-29 | Scottish Water Wide | 1032758 | 0 | 74094 | 77012.04 | 3946.89 | 0 | 0 | 0 | 155052.93 | 0 | 0 | 0 | 1187810.93 | 0 | 0 | 0 | 0 | 1187810.93 | 0 | [5 empty] | N | CC1W | 100%
403877 | Renewables - PV - Balmore WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2014-11-07 | 2014-11-07 | Scottish Water Wide | 313666 | 0 | -5631 | -999.59 | 0 | 0 | 0 | 0 | -6630.59 | 0 | 0 | 0 | 307035.41 | 0 | 0 | 0 | 0 | 307035.41 | 0 | [5 empty] | N | CC1W | 100%
403876 | Renewables - PV - Blairlinnans WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2014-11-11 | 2014-11-11 | Scottish Water Wide | 292000 | 0 | -4906 | -813.67 | 0 | 0 | 0 | 0 | -5719.67 | 0 | 0 | 0 | 286280.33 | 0 | 0 | 0 | 0 | 286280.33 | 0 | [5 empty] | N | CC1W | 100%
403875 | Renewables - PV - Carron Valley WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-31 | 2014-07-31 | 2014-08-20 | 2014-11-11 | 2014-11-11 | Scottish Water Wide | 253767 | 0 | -3349 | -813.77 | 0 | 0 | 0 | 0 | -4162.77 | 0 | 0 | 0 | 249604.23 | 0 | 0 | 0 | 0 | 249604.23 | 0 | [5 empty] | N | CC1W | 100%
403874 | Renewables - PV - Forehill WTW & Depot | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-31 | 2014-07-31 | 2014-08-20 | 2014-11-06 | 2014-11-06 | Scottish Water Wide | 315910 | 0 | -5838 | -813.5 | 0 | 0 | 0 | 0 | -6651.5 | 0 | 0 | 0 | 309258.5 | 0 | 0 | 0 | 0 | 309258.5 | 0 | [5 empty] | N | CC1W | 100%
403873 | Renewables - PV - Mannofield WTW | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-31 | 2014-07-31 | 2014-08-20 | 2014-11-06 | 2014-11-06 | Scottish Water Wide | 313234 | 0 | -5592 | -813.38 | 0 | 0 | 0 | 0 | -6405.38 | 0 | 0 | 0 | 306828.62 | 0 | 0 | 0 | 0 | 306828.62 | 0 | [5 empty] | N | CC1W | 100%
403878 | Renewables - PV - Spey Scheme WTW (Badentinan) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-30 | 2014-07-30 | 2014-08-20 | 2014-11-06 | 2014-11-06 | Scottish Water Wide | 361340 | 0 | -6829 | -813.38 | 0 | 0 | 0 | 0 | -7642.38 | 0 | 0 | 0 | 353697.62 | 0 | 0 | 0 | 0 | 353697.62 | 0 | [5 empty] | N | CC1W | 100%
403577 | Renewables Programme SR15 Early Start | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-08-08 | 2015-11-09 | 2015-11-10 | 2015-11-10 |  | Scottish Water Wide | 851727 | 0 | -85397.54 | 3811.85 | -4701.2 | 0 | 0 | 0 | -86286.89 | 0 | 0 | 0 | 765440.11 | 0 | 0 | 0 | 0 | 765440.11 | 306661.32 | [5 empty] | N | CM_M&G | 100%
500929 | Renfrewshire & East Renfrewshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-11-20 | 2017-11-20 | 2017-10-19 | 2017-10-19 | East Renfrewshire | 0 | 0 | 5000 | 2000 | -4577.97 | 0 | 0 | 0 | 2422.03 | 0 | 0 | 0 | 2422.03 | 0 | 0 | 0 | 0 | 2422.03 | 106252.93 | [5 empty] | N | FL_DD | 100%
506680 | Repair at Dhu Loch CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-10-25 | 2023-12-12 | 2024-03-21 | 2025-02-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506684 | Repair at Glenhove DSR 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-09-15 | 2021-01-15 | 2021-03-23 | 2023-03-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105187.87 | 105187.87 | 1121265.28 | 0 | 0 | 1226453.15 | 0 | 0 | 323546.85 | 323546.85 | 1550000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506778 | Repair at Glenlatterach CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-09-28 | 2023-11-15 | 2024-02-23 | 2025-01-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638.16 | 638.16 | 749999.83 | 0 | 0 | 750637.99 | 0 | 0 | 0 | 0 | 750637.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503862 | Repair Ore Trunk sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2019-12-03 |  | 2020-03-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 21303.71 | 0 | 21303.71 | 0 | 0 | 0 | 21303.71 | 0 | 0 | 0 | 0 | 21303.71 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511496 | Repair-Refurb-Replace DMA Leak Detection Equipment RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-23 | 2021-04-01 | 2022-07-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15700.93 | 15700.93 | 224299.07 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 240000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511484 | Repair-Refurb-Replace SR Level Control Valves RP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2021-03-16 | 2021-03-23 | 2023-02-16 | 2024-01-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8177.57 | 8177.57 | 116822.43 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 125000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511483 | Repair-Refurb-Replace SR-TM Meters RP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2021-03-16 | 2021-03-23 | 2023-02-16 | 2024-01-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13607.48 | 13607.48 | 194392.52 | 0 | 0 | 208000 | 0 | 0 | 0 | 0 | 208000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507805 | Repairs to Loch Eck Tilting Weir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-07-21 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3118.23 | 3118.23 | -118.23 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500983 | Repeat Customer Contact Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-12-01 | 2015-12-01 | 2016-03-08 | 2017-03-06 |  | Scottish Water Wide | 0 | 0 | 41920 | 215595.71 | -30678.36 | 2145.46 | 0 | 0 | 228982.81 | 0 | 0 | 0 | 228982.81 | 0 | 0 | 0 | 0 | 228982.81 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503591 | Repeat Customer Contacts associated with ageing infrastructure Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-03-31 | 2022-11-10 | 2023-03-15 | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
403264 | Replace Huber screens at 20 sites | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-06 | 2015-12-16 | 2016-01-29 | 2017-06-30 |  | All East Unitary Authorities | 219801 | 0 | 1179233 | 1698270.39 | 317291.56 | 489 | -10147.63 | 0 | 3185136.32 | 0 | 0 | 0 | 3404937.32 | 0 | 0 | 0 | 0 | 3404937.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504605 | Replace media and structure in no2 lamella repair/renew damaged concrete | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-01-30 | 2020-08-14 | 2021-02-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 110.82 | 247165.18 | 247276 | 1000 | 0 | 0 | 248276 | 0 | 0 | 0 | 0 | 248276 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507951 | Replace PRVs A&B (Commissioners Rd Milngavie) -Needle Valves | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-10-20 | 2021-08-16 | 2021-12-10 | 2023-06-23 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282572.45 | 282572.45 | 717450.2 | 0 | 0 | 1000022.65 | 0 | 0 | 0 | 0 | 1000022.65 | 311236.79 | [5 empty] | N | WSI | 100%
509887 | Replacement Amlaird WTW DAF System | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-11-24 | 2021-03-11 | 2021-10-15 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34826 | 34826 | 168902.5 | 0 | 0 | 203728.5 | 0 | 0 | 0 | 0 | 203728.5 | 119022.58 | [5 empty] | N | WSNI | 100%
503478 | Replacement Main - Bogleshole Road Cambuslang | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2022-01-12 | 2022-10-18 | 2023-01-18 | 2023-08-15 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 1368.01 | 8901.99 | 10270 | 1486778.94 | 0 | 0 | 1497048.94 | 0 | 0 | 0 | 0 | 1497048.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400802 | Replacement Marker Buoys Scotland Wide | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-05-05 | 2010-05-05 | 2010-05-01 | 2016-09-20 |  | Scottish Water Wide | 111903.4 | 0 | 26010.6 | 2679.79 | 0 | 0 | 0 | 0 | 28690.39 | 0 | 0 | 0 | 140593.79 | 0 | 0 | 0 | 0 | 140593.79 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500945 | Replacement of obsolete portable gas monitoring equipment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS7 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 2016-09-01 |  | Scottish Water Wide | 0 | 0 | 155735.23 | 0 | 92.43 | 0 | 0 | 0 | 155827.66 | 0 | 0 | 0 | 155827.66 | 0 | 0 | 0 | 0 | 155827.66 | 328404.37 | [5 empty] | N | CM_M&G | 100%
510563 | Replacement of sectional damage on 600di CI Rising Main inclusive of temp works and re-instatement. | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2021-01-12 | 2021-03-19 | 2021-07-27 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10609.06 | 10609.06 | 89390.94 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
401976 | Replacement of the Monymusk Pumps and Pumping Main | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2011-03-24 | 2012-05-23 | 2012-07-02 | 2018-05-11 | 2018-05-11 | Aberdeenshire | 1193302.89 | 0 | 76197.11 | -73765.76 | 22.32 | 61.22 | 0 | 0 | 2514.89 | 0 | 0 | 0 | 1195817.78 | 0 | 0 | 0 | 0 | 1195817.78 | 0 | [5 empty] | N | WG5 | 100%
503267 | Replacement Sludge Tank and Mixer - Annan WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-07-28 | 2028-03-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513.32 | 513.32 | 299999.92 | 0 | 0 | 300513.24 | 0 | 0 | 0 | 0 | 300513.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500787 | Reservoir Capital Programme and QCE Support | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-08-13 | 2015-08-13 | 2018-03-22 | 2018-03-14 |  | Scottish Water Wide | 0 | 0 | 114436.17 | 596239.54 | 39974.53 | 0 | 0 | 0 | 750650.24 | 0 | 0 | 0 | 750650.24 | 0 | 0 | 0 | 0 | 750650.24 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402741 | Reservoir Maintenance - Baddinsgill Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-09-20 | 2012-11-12 | 2014-02-12 |  | Scottish Borders | 222737.32 | 0 | 155.83 | 0 | 0 | 0 | 0 | 0 | 155.83 | 0 | 0 | 0 | 222893.15 | 0 | 0 | 0 | 0 | 222893.15 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402663 | Reservoir Maintenance - Barcraigs Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-29 | 2013-02-11 | 2013-05-31 | 2014-08-27 |  | Renfrewshire | 298797.82 | 0 | 1156.05 | -5832.19 | 0 | 0 | 0 | 0 | -4676.14 | 0 | 0 | 0 | 294121.68 | 0 | 0 | 0 | 0 | 294121.68 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402720 | Reservoir Maintenance - Bradan Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-29 | 2013-02-07 | 2013-07-15 | 2014-03-06 |  | South Ayrshire | 20217.05 | 0 | 1044.63 | 0 | 0 | 0 | 0 | 0 | 1044.63 | 0 | 0 | 0 | 21261.68 | 0 | 0 | 0 | 0 | 21261.68 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402721 | Reservoir Maintenance - Camphill Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-15 | 2013-02-07 | 2013-05-31 | 2014-09-16 |  | North Ayrshire | 111225.75 | 0 | -5038.04 | -93.75 | 0 | 0 | 0 | 0 | -5131.79 | 0 | 0 | 0 | 106093.96 | 0 | 0 | 0 | 0 | 106093.96 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402664 | Reservoir Maintenance - Carron Valley | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-08-29 | 2013-02-25 | 2014-03-13 |  | Stirling | 231042.77 | 0 | 2910.78 | 0 | 0 | 0 | 0 | 0 | 2910.78 | 0 | 0 | 0 | 233953.55 | 0 | 0 | 0 | 0 | 233953.55 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402665 | Reservoir Maintenance - Daer Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-09-05 | 2012-11-12 | 2014-03-19 |  | Dumfries and Galloway | 316739.68 | 0 | 1134.23 | 0 | 0 | 0 | 0 | 0 | 1134.23 | 0 | 0 | 0 | 317873.91 | 0 | 0 | 0 | 0 | 317873.91 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402742 | Reservoir Maintenance - Fruid Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-15 | 2012-09-05 | 2012-11-19 | 2013-12-22 |  | Scottish Borders | 203750.67 | 0 | 362.12 | 0 | 0 | 0 | 0 | 0 | 362.12 | 0 | 0 | 0 | 204112.79 | 0 | 0 | 0 | 0 | 204112.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402666 | Reservoir Maintenance - Gladhouse Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-11-29 | 2013-02-25 | 2014-08-04 |  | Midlothian | 187330.67 | 0 | 890.97 | -871.01 | 0 | 0 | 0 | 0 | 19.96 | 0 | 0 | 0 | 187350.63 | 0 | 0 | 0 | 0 | 187350.63 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402743 | Reservoir Maintenance - Glenquey Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-08-23 | 2012-11-05 | 2014-01-15 |  | Perth and Kinross | 180562.13 | 0 | 171.21 | 0 | 0 | 0 | 0 | 0 | 171.21 | 0 | 0 | 0 | 180733.34 | 0 | 0 | 0 | 0 | 180733.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402722 | Reservoir Maintenance - Harelaw Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-20 | 2013-02-07 | 2013-06-03 | 2014-02-27 | 2014-02-27 | Inverclyde | 231365.74 | 0 | 151.55 | 0 | 0 | 0 | 0 | 0 | 151.55 | 0 | 0 | 0 | 231517.29 | 0 | 0 | 0 | 0 | 231517.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402723 | Reservoir Maintenance - Loch Thom Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-15 | 2012-11-14 | 2013-02-18 | 2014-03-31 | 2014-03-31 | Inverclyde | 534455.75 | 0 | 13036.82 | 341.9 | 0 | 0 | 0 | 0 | 13378.72 | 0 | 0 | 0 | 547834.47 | 0 | 0 | 0 | 0 | 547834.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402744 | Reservoir Maintenance - St Marys Loch | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-08-23 | 2012-11-05 | 2013-12-22 |  | Scottish Borders | 128042.11 | 0 | 764.17 | 0 | 0 | 0 | 0 | 0 | 764.17 | 0 | 0 | 0 | 128806.28 | 0 | 0 | 0 | 0 | 128806.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402667 | Reservoir Maintenance - Thorters | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-09-20 | 2012-11-19 | 2013-09-23 |  | East Lothian | 177924.25 | 0 | 893.45 | 0 | 0 | 0 | 0 | 0 | 893.45 | 0 | 0 | 0 | 178817.7 | 0 | 0 | 0 | 0 | 178817.7 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402745 | Reservoir Maintenance - Torduff Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-09-20 | 2013-02-26 | 2013-09-23 |  | Midlothian | 123819.4 | 0 | -876.74 | 0 | 0 | 0 | 0 | 0 | -876.74 | 0 | 0 | 0 | 122942.66 | 0 | 0 | 0 | 0 | 122942.66 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402719 | Reservoir Maintenance - Valve Repair Package | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-06 | 2013-05-03 | 2013-05-22 | 2013-05-22 |  | Scottish Water Wide | 7274.52 | 0 | -265.62 | 0 | 0 | 0 | 0 | 0 | -265.62 | 0 | 0 | 0 | 7008.9 | 0 | 0 | 0 | 0 | 7008.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46337 | Reservoir Maintenance Phase 1 South | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-04-01 | 2011-11-14 | 2011-12-01 | 2011-12-06 | 2011-12-06 | Scottish Water Wide | 115498.84 | 0 | -132.35 | 0 | 0 | 0 | 0 | 0 | -132.35 | 0 | 0 | 0 | 115366.49 | 0 | 0 | 0 | 0 | 115366.49 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403616 | Reservoir Programme Line for QCE Costs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-10-22 | 2013-10-22 | 2013-10-22 | 2015-06-10 |  | Scottish Water Wide | 27752.94 | 0 | 2578.89 | 0 | 0 | 0 | 0 | 0 | 2578.89 | 0 | 0 | 0 | 30331.83 | 0 | 0 | 0 | 0 | 30331.83 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507113 | Reservoir Safety Sign Check - North | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-06-22 | 2020-11-06 | 2021-06-25 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278 | 1278 | 921.58 | 0 | 0 | 2199.58 | 0 | 0 | 0 | 0 | 2199.58 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500741 | Reservoir Safety Signs to comply with RA2011 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | MS7 | 2019-12-20 | 2019-12-20 | 2019-12-20 | 2019-12-20 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 4186.05 | 21264.35 | -4329.42 | 13.4 | 140.26 | -21254.64 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 20 | 0 | [5 empty] | N | WR6 | 100%
500595 | Resilience - Mobile Water Treatment Works | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2019-06-14 | 2019-06-14 | 2019-06-14 | 2019-04-26 | 2019-04-26 | Scottish Water Wide | 0 | 0 | 26500.27 | 17550.62 | 105945.11 | 78280.75 | 113079.45 | 0 | 341356.2 | 0 | 0 | 0 | 341356.2 | 0 | 0 | 0 | 0 | 341356.2 | 638845.62 | [5 empty] | N | CS16WR | 100%
503111 | Resillience - Perth and Dundee Connectivity | IR18 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW0 | 2022-01-12 | 2022-08-11 | 2022-08-19 | 2022-08-19 | 2022-08-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 581085.65 | 131026.22 | 316946.59 | -142115.59 | 886942.85 | 2583057.15 | 0 | 0 | 3470000 | 0 | 712473.9159 | 0 | 712473.9159 | 4182473.9159 | 2696105.82 | [5 empty] | N | CS16WRID | 100%
503347 | Resource Scheduler | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2018-08-20 | 2019-09-24 | 2019-09-24 | 2021-04-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 49869.33 | 360211.56 | 95805.11 | 505886 | 0 | 0 | 0 | 505886 | 0 | 0 | 0 | 0 | 505886 | 306661.32 | [5 empty] | N | CM_M&G | 100%
509237 | Rhenigidale WTW - PLC | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW1 | 2022-01-03 | 2023-11-20 | 2024-04-29 | 2025-11-10 | 2026-02-10 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5254 | 5254 | 244745.39 | 0 | 0 | 249999.39 | 0 | 0 | 0 | 0 | 249999.39 | 0 | [5 empty] | N | SR21_SS | 100%
503363 | Rhenigidale WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-26 | 2020-03-31 | 2020-03-31 | 2020-05-07 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 20153.02 | -18054.62 | 0 | 2098.4 | 0 | 0 | 0 | 2098.4 | 0 | 0 | 0 | 0 | 2098.4 | 122419.09 | [5 empty] | N | WG1 | 100%
500810 | Rhynie RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-10-19 | 2017-08-10 | 2017-09-22 | 2018-06-30 | 2018-12-31 | Aberdeenshire | 0 | 0 | 569.73 | 510.66 | 7389.96 | 13900.97 | -2606.89 | 0 | 19764.43 | 0 | 0 | 0 | 19764.43 | 0 | 0 | 0 | 0 | 19764.43 | 2016.36 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 2.87 | [43 empty] | 0
502420 | Rhynie WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2027-04-01 | 2028-08-08 | 2028-11-28 | 2029-11-16 |  | Aberdeenshire | 0 | 0 | 0 | 20496.52 | 30.81 | 129.13 | 0 | 0 | 20656.46 | 12343.77 | 0 | 0 | 33000.23 | 0 | 0 | 0 | 0 | 33000.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403255 | Rhynie WWTW Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-01-18 | 2016-10-31 | 2016-10-31 | 2016-11-02 |  | Aberdeenshire | 21759.04 | 0 | 6219.99 | 4517.13 | 0 | 0 | 0 | 0 | 10737.12 | 0 | 0 | 0 | 32496.16 | 0 | 0 | 0 | 0 | 32496.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512153 | Rigside WwTW - Capital Maintenance (Recycled) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2022-04-04 | 2023-10-11 | 2024-01-09 | 2024-12-16 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601966 | 0 | 0 | 2601966 | 0 | 0 | 0 | 0 | 2601966 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503273 | Rigside WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-06-02 | 2020-06-02 | 2020-08-28 | 2020-08-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 74437.32 | 4125.37 | -2286.83 | 76275.86 | 0 | 0 | 0 | 76275.86 | 0 | 0 | 0 | 0 | 76275.86 | 122419.09 | [5 empty] | N | SG1 | 100%
501511 | RIGSIDE WWTW 1950 NS872356 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-04-14 | 2023-01-31 | 2023-05-01 | 2024-07-05 |  | South Lanarkshire | 0 | 0 | 0 | 140883.69 | 273681.96 | 39816.74 | 0 | 23285.61 | 477668 | 2124298.53 | 0 | 0 | 2601966.53 | 0 | 0 | 0 | 0 | 2601966.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500246 | Ringford WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS3 | 2017-07-28 | 2020-03-18 | 2020-09-07 | 2021-10-22 | 2022-01-24 | Dumfries and Galloway | 0 | 0 | 15732.21 | 64763 | 206670.72 | 58425.93 | 135225.04 | 704808.1 | 1185625 | 174416.34 | 174416.34 | 237803.9721 | 1360041.34 | 63387.6321 | 0 | -2.3283e-10 | 63387.6321 | 1423428.9721 | 1395918.04 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
400633 | Rising Mains - Pollution Hotspots Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2012-02-23 | 2012-03-14 | 2014-12-04 |  | Falkirk | 335876 | 0 | 151.93 | 0 | 0 | 0 | 0 | 0 | 151.93 | 0 | 0 | 0 | 336027.93 | 0 | 0 | 0 | 0 | 336027.93 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500214 | River Almond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-03-20 | 2016-09-14 | 2016-09-26 | 2019-07-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 11732 | 154334.13 | 154324.87 | 167774 | 55194.81 | 0 | 543359.81 | 0 | 0 | 0 | 543359.81 | 0 | 0 | 0 | 0 | 543359.81 | 4617.88 | [5 empty] | Y | EC01G | 10% | EC10H | 90% | [38 empty] | 1 | [26 empty] | 0
500090 | River Angus Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-03-20 | 2016-12-20 | 2017-01-26 | 2020-01-28 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 9185 | 81214.68 | 257316.32 | 292130 | 42032 | -15803.06 | 666074.94 | 0 | 0 | 0 | 666074.94 | 0 | 0 | 0 | 0 | 666074.94 | 200273.51 | [5 empty] | Y | EC10E | 50% | EC10H | 50% | [38 empty] | 1 | [26 empty] | 0
504469 | River Blaich burst main replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2019-12-24 |  | 2020-09-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 26870.12 | 31870.12 | 0 | 0 | 0 | 31870.12 | 0 | 0 | 0 | 0 | 31870.12 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500106 | River Carron Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2020-06-22 | 2020-11-11 | Scottish Water Wide | 0 | 0 | 22136 | 82403.66 | 339099.34 | 85335 | 50934.2 | 14034.03 | 593942.23 | 0 | 0 | 0 | 593942.23 | 0 | 0 | 0 | 0 | 593942.23 | 277289.62 | [5 empty] | N | EC01G | 0.3636% | CS16D | 1.455% | EC10E | 49.09% | EC10H | 49.09%
510009 | River Dee Water Crossing - Pipe Support Structural Assessment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-12-08 | 2021-05-21 | 2022-01-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.44 | 1285.44 | 11300 | 0 | 0 | 12585.44 | 0 | 0 | 0 | 0 | 12585.44 | 311236.79 | [5 empty] | N | WSI | 100%
500100 | River Don Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2020-04-29 | 2020-08-03 | Scottish Water Wide | 0 | 0 | 16694 | 110505.38 | 118997.62 | 666587.16 | 165961.81 | 67342.84 | 1146088.81 | 0 | 0 | 0 | 1146088.81 | 0 | 0 | 0 | 0 | 1146088.81 | 488073.14 | [5 empty] | N | CS16D | 12.56% | EC10E | 43.72% | EC10H | 43.72%
500101 | River Eden Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2020-02-14 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 12208 | 89258.13 | 219227.87 | 279335.91 | 145072.14 | -2919.93 | 742182.12 | 0 | 0 | 0 | 742182.12 | 0 | 0 | 0 | 0 | 742182.12 | 221694.31 | [5 empty] | N | CS16D | 21.28% | EC10E | 39.36% | EC10H | 39.36%
502199 | River Intake Monitoring - Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2016-06-01 | 2016-07-29 | 2016-08-11 | 2017-12-15 | 2017-12-15 | Scottish Water Wide | 0 | 0 | 0 | 19600 | 62200 | 1200 | 754.51 | 0 | 83754.51 | 0 | 0 | 0 | 83754.51 | 0 | 0 | 0 | 0 | 83754.51 | 640245.27 | [5 empty] | N | WR7 | 100%
506017 | River Kelvin and Dalmuir Aesthetic Surveys | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWMD | SR21 Early Start | MS3 | 2020-05-01 | 2020-07-31 | 2020-08-24 | 2021-07-30 | 2021-09-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 240.6 | 78229.4 | 78470 | 121791.38 | 0 | 0 | 200261.38 | 0 | 0 | 0 | 0 | 200261.38 | 0 | [5 empty] | N | SR21_WW | 100%
501715 | River Kelvin Sewer - Sewer cleaning along river bank | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-04-28 | 2018-05-25 | 2018-08-08 | 2019-02-19 |  | Glasgow City | 0 | 0 | 0 | 0 | 4773 | 244736.57 | -5148.01 | 0.44 | 244362 | 0 | 0 | 0 | 244362 | 0 | 0 | 0 | 0 | 244362 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504217 | River Larroch pipe crossing replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2019-12-11 | 2020-09-21 | 2021-01-21 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 3720.48 | 76154.99 | 79875.47 | 0 | 0 | 0 | 79875.47 | 0 | 0 | 0 | 0 | 79875.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501660 | River Leven Trunk Main Sewer - Inspect sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-07-19 | 2017-02-28 | 2017-03-17 | 2017-12-04 |  | Fife | 0 | 0 | 0 | 12000 | 35721.59 | 0 | -0.04 | 0 | 47721.55 | 0 | 0 | 0 | 47721.55 | 0 | 0 | 0 | 0 | 47721.55 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501193 | River Leven Trunk Sewer Reinstate River Bank | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-12-03 | 2016-08-02 | 2016-08-22 | 2016-11-02 |  | Fife | 0 | 0 | 7794.37 | 104574.72 | -369.14 | 25.01 | 0 | 0 | 112024.96 | 0 | 0 | 0 | 112024.96 | 0 | 0 | 0 | 0 | 112024.96 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507617 | River Lochy pipe crossing repair | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-07-17 | 2021-05-17 | 2021-11-26 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20630.36 | 20630.36 | 29391.39 | 0 | 0 | 50021.75 | 0 | 0 | 0 | 0 | 50021.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508805 | River Ore Sewer - Tullybreck Farm | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-06-22 | 2024-02-14 | 2024-05-22 | 2025-09-17 | 2025-09-18 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109439.84 | 109439.84 | 2690630.29 | 0 | 0 | 2800070.13 | 0 | 0 | 0 | 0 | 2800070.13 | 0 | [5 empty] | N | SR21_WW | 100%
402770 | River Ugie to St Fergus Water Main Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-03 | 2013-05-13 | 2013-08-30 | 2014-10-24 |  | Aberdeenshire | 742867 | 0 | 11599.49 | 43071.47 | 0 | 0 | 0 | 0 | 54670.96 | 0 | 0 | 0 | 797537.96 | 0 | 0 | 0 | 0 | 797537.96 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403544 | Rivers Ayr and Doon Strategic Study scoping of capex 3 costs | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2013-09-27 | 2015-01-29 | 2015-02-16 | 2017-03-31 | 2017-06-30 | South Ayrshire | 219562 | 0 | 709100 | 388924.1 | 100180.28 | 0 | 0 | 0 | 1198204.38 | 0 | 0 | 0 | 1417766.38 | 0 | 0 | 0 | 0 | 1417766.38 | 1186562 | [5 empty] | Y | EC10B | 0.7053% | EC16 | 99.29% | [63 empty] | 1 |  | 0
400593 | RM Customer Sewer Infra East | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 2504343.53 | 0 | 558810 | 987611.88 | 363029.35 | -357683.69 | 0 | 0 | 1551767.54 | 0 | 0 | 0 | 4056111.07 | 0 | 0 | 0 | 0 | 4056111.07 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400594 | RM Customer Sewer Infra North | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-01-21 |  | All North Unitary Authorities | 2047056.48 | 0 | 0 | 0 | 62155 | -62155 | 0 | 0 | 0 | 0 | 0 | 0 | 2047056.48 | 0 | 0 | 0 | 0 | 2047056.48 | 0 | [5 empty] | N | CM_WWI | 100%
400595 | RM Customer Sewer Infra Others East | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 6753275.32 | 0 | 1177798.4 | 1488342.97 | 8576.66 | 0 | 0 | 0 | 2674718.03 | 0 | 0 | 0 | 9427993.35 | 0 | 0 | 0 | 0 | 9427993.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400596 | RM Customer Sewer Infra Others North | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2553230.4 | 0 | 197238.53 | 236949.07 | 7460.32 | 0 | 0 | 0 | 441647.92 | 0 | 0 | 0 | 2994878.32 | 0 | 0 | 0 | 0 | 2994878.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400597 | RM Customer Sewer Infra Others South | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 2529132 | 0 | 497820 | 696780.57 | 5345.66 | 0 | 0 | 0 | 1199946.23 | 0 | 0 | 0 | 3729078.23 | 0 | 0 | 0 | 0 | 3729078.23 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400598 | RM Customer Sewer Infra Others West | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 2367230 | 0 | 472324.63 | 695013.76 | 5345.66 | 0 | 0 | 0 | 1172684.05 | 0 | 0 | 0 | 3539914.05 | 0 | 0 | 0 | 0 | 3539914.05 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400599 | RM Customer Sewer Infra South | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 6702907.8 | 0 | 1362416.37 | 1792668.06 | 594631 | -589285.34 | 0 | 0 | 3160430.09 | 0 | 0 | 0 | 9863337.89 | 0 | 0 | 0 | 0 | 9863337.89 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400600 | RM Customer Sewer Infra West | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 5204837.06 | 0 | 991533.12 | 1421440.91 | 680907.66 | -675562 | 0 | 0 | 2418319.69 | 0 | 0 | 0 | 7623156.75 | 0 | 0 | 0 | 0 | 7623156.75 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400581 | RM Customer Water Infra Bursts East | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 4136030.07 | 0 | 969008.39 | 92340.39 | 317672.82 | -308093.22 | 0 | 0 | 1070928.38 | 0 | 0 | 0 | 5206958.45 | 0 | 0 | 0 | 0 | 5206958.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400582 | RM Customer Water Infra Bursts North | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 4662501.65 | 0 | 989264.2 | 99915.4 | 396337.86 | -386757.26 | 0 | 0 | 1098760.2 | 0 | 0 | 0 | 5761261.85 | 0 | 0 | 0 | 0 | 5761261.85 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400583 | RM Customer Water Infra Bursts South | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 11130129.73 | 0 | 2709757.91 | 104167.76 | 1119543.79 | -1109964.19 | 0 | 0 | 2823505.27 | 0 | 0 | 0 | 13953635 | 0 | 0 | 0 | 0 | 13953635 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400584 | RM Customer Water Infra Bursts West | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 13756430.89 | 0 | 2862936.84 | 110887.6 | 1289452.91 | -1279873.31 | 0 | 0 | 2983404.04 | 0 | 0 | 0 | 16739834.93 | 0 | 0 | 0 | 0 | 16739834.93 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400585 | RM Customer Water Infra Others East | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 7037156.79 | 0 | 1423764.06 | -87945.51 | 589293.49 | -585334.89 | 0 | 0 | 1339777.15 | 0 | 0 | 0 | 8376933.94 | 0 | 0 | 0 | 0 | 8376933.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400586 | RM Customer Water Infra Others North | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2569930.24 | 0 | 635030.87 | -184208.71 | 97852.48 | -93893.88 | 0 | 0 | 454780.76 | 0 | 0 | 0 | 3024711 | 0 | 0 | 0 | 0 | 3024711 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400587 | RM Customer Water Infra Others South | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 5411099.17 | 0 | 1080390.56 | 51155.41 | 329204.76 | -325246.16 | 0 | 0 | 1135504.57 | 0 | 0 | 0 | 6546603.74 | 0 | 0 | 0 | 0 | 6546603.74 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400588 | RM Customer Water Infra Others West | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 2140824.78 | 0 | 439363.67 | 82164.95 | 174168.56 | -170209.96 | 0 | 0 | 525487.22 | 0 | 0 | 0 | 2666312 | 0 | 0 | 0 | 0 | 2666312 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400573 | RM Waste Non Infra EM East | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 9522415.05 | 0 | 1760182.49 | 791139.81 | 822002.85 | -820042.54 | 0 | 0 | 2553282.61 | 0 | 0 | 0 | 12075697.66 | 0 | 0 | 0 | 0 | 12075697.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400574 | RM Waste Non Infra EM North | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2015842 | 0 | 45081.6 | -97.43 | 173812.33 | -171852.02 | 0 | 0 | 46944.48 | 0 | 0 | 0 | 2062786.48 | 0 | 0 | 0 | 0 | 2062786.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400575 | RM Waste Non Infra EM South | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 9276281.51 | 0 | 1784705.14 | 844947.92 | 866542.94 | -893730.92 | 0 | 0 | 2602465.08 | 0 | 0 | 0 | 11878746.59 | 0 | 0 | 0 | 0 | 11878746.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400576 | RM Waste Non Infra EM West | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 9164354.26 | 0 | 1775417.29 | 827201.32 | 984293.43 | -982333.12 | 0 | 0 | 2604578.92 | 0 | 0 | 0 | 11768933.18 | 0 | 0 | 0 | 0 | 11768933.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500542 | RM Water East Infra | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 |  | All East Unitary Authorities | 0 | 0 | 56706 | 1599048.64 | 176.8 | 95.19 | 0 | 0 | 1656026.63 | 0 | 0 | 0 | 1656026.63 | 0 | 0 | 0 | 0 | 1656026.63 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500543 | RM Water East WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-27 | 2015-04-27 | 2015-04-27 | 2017-08-31 |  | All East Unitary Authorities | 0 | 0 | 4782 | 184250.13 | 0 | 0 | 0 | 0 | 189032.13 | 0 | 0 | 0 | 189032.13 | 0 | 0 | 0 | 0 | 189032.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500544 | RM Water East WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2017-08-31 |  | All East Unitary Authorities | 0 | 0 | 6832 | 292833.38 | 0 | 0 | 0 | 0 | 299665.38 | 0 | 0 | 0 | 299665.38 | 0 | 0 | 0 | 0 | 299665.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400577 | RM Water Non Infra East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 3100000 | 0 | 624922.86 | 2654.55 | 273108.73 | -271148.42 | 0 | 0 | 629537.72 | 0 | 0 | 0 | 3729537.72 | 0 | 0 | 0 | 0 | 3729537.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400578 | RM Water Non Infra North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2058992 | 0 | 441192.96 | 2988.75 | 253335.75 | -253335.75 | 0 | 0 | 444181.71 | -1116 | 0 | 0 | 2502057.71 | 0 | 0 | 0 | 0 | 2502057.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400579 | RM Water Non Infra South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 2575019.22 | 0 | 494071.61 | 42835.41 | 271789.27 | -269828.96 | 0 | 0 | 538867.33 | 0 | 0 | 0 | 3113886.55 | 0 | 0 | 0 | 0 | 3113886.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400580 | RM Water Non Infra West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 2601663.58 | 0 | 589048.86 | 102792.21 | 266511.44 | -264551.13 | 0 | 0 | 693801.38 | 0 | 0 | 0 | 3295464.96 | 0 | 0 | 0 | 0 | 3295464.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500545 | RM Water North Infra | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 |  | All North Unitary Authorities | 0 | 0 | 36454 | 2263653 | -69412.55 | 0 | 0 | 0 | 2230694.45 | 0 | 0 | 0 | 2230694.45 | 0 | 0 | 0 | 0 | 2230694.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500546 | RM Water North WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-27 | 2015-04-27 | 2015-04-27 | 2017-08-31 |  | All North Unitary Authorities | 0 | 0 | 3074 | 188582.44 | 0 | 0 | 0 | 0 | 191656.44 | 0 | 0 | 0 | 191656.44 | 0 | 0 | 0 | 0 | 191656.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500547 | RM Water North WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-27 | 2015-04-27 | 2015-04-27 | 2017-08-31 |  | All North Unitary Authorities | 0 | 0 | 4392 | 228086.31 | 0 | 0 | 0 | 0 | 232478.31 | 0 | 0 | 0 | 232478.31 | 0 | 0 | 0 | 0 | 232478.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500551 | RM Water South infra | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 |  | All South Unitary Authorities | 0 | 0 | 74932 | 3431713.64 | 0 | 0 | 0 | 0 | 3506645.64 | 0 | 0 | 0 | 3506645.64 | 0 | 0 | 0 | 0 | 3506645.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500552 | RM Water South WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 |  | All South Unitary Authorities | 0 | 0 | 6320 | 162624.29 | 0 | 0 | 0 | 0 | 168944.29 | 0 | 0 | 0 | 168944.29 | 0 | 0 | 0 | 0 | 168944.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500553 | RM Water South WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 |  | All South Unitary Authorities | 0 | 0 | 9028 | 621292.09 | 0 | 0 | 0 | 0 | 630320.09 | 0 | 0 | 0 | 630320.09 | 0 | 0 | 0 | 0 | 630320.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500548 | RM Water West infra | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 |  | All West Unitary Authorities | 0 | 0 | 76958 | 3274326.7 | 0 | 534446.72 | 0 | 0 | 3885731.42 | 0 | 0 | 0 | 3885731.42 | 0 | 0 | 0 | 0 | 3885731.42 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500549 | RM Water West WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 |  | All West Unitary Authorities | 0 | 0 | 6490 | 193273.2 | 0 | 0 | 0 | 0 | 199763.2 | 0 | 0 | 0 | 199763.2 | 0 | 0 | 0 | 0 | 199763.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500550 | RM Water West WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 |  | All West Unitary Authorities | 0 | 0 | 9272 | 301306.91 | 318.56 | 150944.09 | 0 | 0 | 461841.56 | 0 | 0 | 0 | 461841.56 | 0 | 0 | 0 | 0 | 461841.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501264 | Roanhead Terrace Kincardine Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-02-10 | 2017-01-19 | 2017-03-28 | 2017-06-30 |  | Fife | 0 | 0 | 3282 | 134327 | -3604 | -2475.47 | -2710.66 | 0 | 128818.87 | 0 | 0 | 0 | 128818.87 | 0 | 0 | 0 | 0 | 128818.87 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502935 | Roanheads SPS Rising Main Peterhead | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2018-03-29 | 2019-02-26 | 2019-05-23 | 2020-01-29 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 14300.7 | 73004.3 | 153490 | 2000 | 242795 | 250 | 0 | 0 | 243045 | 0 | 0 | 0 | 0 | 243045 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500047 | Roberton WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-06-23 | 2019-09-30 | 2020-02-28 | 2022-10-07 |  | Scottish Borders | 0 | 0 | 98749 | 316067.11 | 109039.73 | 218646.53 | 1225287.81 | 1084039.82 | 3051830 | 1625485 | 0 | 0 | 4677315 | 0 | 0 | 572685 | 572685 | 5250000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508124 | Roberton WTW - Coag Control Instrumentation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS3 |  | 2020-08-26 | 2021-01-11 | 2021-11-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40466 | 40466 | 59534.14 | 59534.14 | 82643.5218 | 100000.14 | 23109.3818 | 0 | 0 | 23109.3818 | 123109.5218 | 203486.13 | [5 empty] | N | DW25P | 100%
507782 | Roberton WTW - Fire Risk Assessment Work | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS2 |  | 2020-07-30 | 2021-06-07 | 2021-11-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9035 | 9035 | 10964.88 | 0 | 0 | 19999.88 | 0 | 0 | 0 | 0 | 19999.88 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503618 | Roberton WTW - pH correction for coagulation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS0 | 2020-09-25 | 2022-04-01 | 2022-08-03 |  | 2021-10-21 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 55210.61 | 107242.39 | 162453 | 2042937.15 | 2042937.15 | 2835944.5654 | 2205390.15 | 793007.4154 | 0 | 0 | 793007.4154 | 2998397.5654 | 203486.13 | [5 empty] | Y | DW25P | 100% | [18 empty] | 1 | [48 empty] | 0
501291 | Roberton WTW - Replacement Sludge Holding Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2015-12-04 | 2017-03-29 | 2017-05-19 | 2020-11-19 |  | Scottish Borders | 0 | 0 | 5481.61 | 92255.69 | 129863.49 | 376999.66 | 117127.5 | 13164.51 | 734892.46 | 500.16 | 0 | 0 | 735392.62 | 0 | 0 | 0 | 0 | 735392.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401311 | Rochomie Reservoir - Breaching embankment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2013-07-30 | 2013-08-13 | 2014-12-02 | 2014-07-01 | Moray | 567875 | 0 | 699.38 | -1673.8 | 0 | 0 | 0 | 0 | -974.42 | 0 | 0 | 0 | 566900.58 | 0 | 0 | 0 | 0 | 566900.58 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46853 | Rochomie WTW Upgrade (SWS2) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-09-11 | 2012-09-24 | 2013-03-28 | 2013-03-29 | Moray | 1254002.54 | 0 | -894.07 | 0 | 0 | 0 | 0 | 0 | -894.07 | 0 | 0 | 0 | 1253108.47 | 0 | 0 | 0 | 0 | 1253108.47 | 28761.13 | [5 empty] | N | DW23 | 100%
403951 | Rockcliffe BW - Improvement to Sufficient Status | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | NONINF | OMG180 | MS0 | 2014-11-19 | 2022-06-24 | 2022-09-13 | 2024-05-23 | 2024-11-01 | Dumfries and Galloway | 99678 | 0 | 1665 | 13107 | 168598 | 152297 | 318747.75 | 416486.7 | 1070901.45 | 7400014 | 7400014 | 10272479.2524 | 8570593.45 | 2872465.2524 | 0 | 0 | 2872465.2524 | 11443058.7024 | 2968532.67 | [5 empty] | Y | EC16 | 100% | [65 empty] | 1 |  | 0
402772 | Rockcliffe WwTW - Replacement of UV Sludge and Aeration Systems | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-09-10 | 2013-07-24 | 2013-08-30 | 2015-03-13 |  | Dumfries and Galloway | 743005 | 0 | 3538 | 2137 | 0 | 0 | 0 | 0 | 5675 | 0 | 0 | 0 | 748680 | 0 | 0 | 0 | 0 | 748680 | 90601.29 | [5 empty] | N | CM_WWI | 100%
501566 | Roer to Eela WTW - Raw Water Main Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-22 | 2027-10-28 | 2028-02-14 | 2029-01-25 |  | Shetland Islands | 0 | 0 | 84187.13 | 22577.06 | 999.81 | 66062 | -60860.02 | 0 | 112965.98 | 1785461 | 0 | 0 | 1898426.98 | 0 | 0 | 0 | 0 | 1898426.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46572 | Rolling Programme - Chlorine to Chloris Dosing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-07-14 | 2012-01-26 | 2012-02-20 | 2017-06-30 |  | Scottish Water Wide | 19392597.96 | 0 | 1598801.08 | 1770939.22 | 286927.27 | -314845.94 | 41.32 | 0 | 3341862.95 | 0 | 0 | 0 | 22734460.91 | 0 | 0 | 0 | 0 | 22734460.91 | 119022.58 |  |  |  |  | 1237230.2695 | N | CM_WSNI | 100%
46081 | Rolling Programme - GAC Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2010-03-11 | 2010-07-28 | 2015-05-29 |  | Scottish Water Wide | 5077805 | 0 | 21783.19 | 0 | 0 | 0 | 0 | 0 | 21783.19 | 0 | 0 | 0 | 5099588.19 | 0 | 0 | 0 | 0 | 5099588.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400085 | Rolling Programme - Membrane Replacement SR10 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-11-04 | 2010-11-05 | 2010-11-12 | 2015-03-31 |  | Scottish Water Wide | 8595523.47 | 0 | 195342.85 | -35396.21 | 0 | 0 | 0 | 0 | 159946.64 | 0 | 0 | 0 | 8755470.11 | 0 | 0 | 0 | 0 | 8755470.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500870 | Rosebery Hopes RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-08-17 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | East Lothian | 0 | 0 | 5298.78 | 4844.52 | 17739 | -17729.89 | 0 | 0 | 10152.41 | 0 | 0 | 0 | 10152.41 | 0 | 0 | 0 | 0 | 10152.41 | 325256.96 | [5 empty] | N | DW5FS | 100%
503949 | Rosebery T&O - Monitoring and Evaluation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-12 | 2021-07-05 | 2021-11-03 | 2022-05-04 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
503148 | Rosebery WTW - Filter media replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS7 | 2018-03-15 | 2018-03-30 | 2018-04-19 | 2018-11-30 |  | Midlothian | 0 | 0 | 0 | 0 | 56033.04 | 929858.84 | -73904.21 | -6303.14 | 905684.53 | 0 | 0 | 0 | 905684.53 | 0 | 0 | 0 | 0 | 905684.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502246 | Rosebery WTW Lime to Caustic | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-08-15 | 2019-10-01 | 2019-10-01 | 2021-07-12 |  | Midlothian | 0 | 0 | 0 | 13827.66 | 47520.37 | 805881.81 | 547061.42 | 708946.74 | 2123238 | 109653.22 | 0 | 0 | 2232891.22 | 0 | 0 | 17108.78 | 17108.78 | 2250000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403217 | Rosebery WTW- WOA Install Chloramination | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-07 | 2014-05-13 | 2014-04-16 | 2014-04-16 |  | East Lothian | 98709.96 | 0 | 835.7 | 0 | 0 | 0 | 0 | 0 | 835.7 | 0 | 0 | 0 | 99545.66 | 0 | 0 | 0 | 0 | 99545.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403220 | Rosebery WTW- WOA Roof Membrane | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-07 | 2014-05-15 | 2014-06-09 | 2015-02-27 |  | Midlothian | 1002055.18 | 0 | -48127.1 | 680.68 | 0 | 0 | 0 | 0 | -47446.42 | 0 | 0 | 0 | 954608.76 | 0 | 0 | 0 | 0 | 954608.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403970 | Rosewell WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2016-07-19 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | East Lothian | 904.37 | 0 | 16351.35 | 64164.65 | 109540.73 | 24383.68 | 2239.12 | 0 | 216679.53 | -1669.56 | 0 | 0 | 215914.34 | 0 | 0 | 0 | 0 | 215914.34 | 0 | [5 empty] | N | SG1 | 100%
503619 | Rosewell WwTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-02-28 | 2025-03-07 | 2025-06-09 | 2027-01-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 193129.61 | 214856.39 | 407986 | 5546985.59 | 0 | 0 | 5954971.59 | 0 | 0 | 0 | 0 | 5954971.59 | 122419.09 | [5 empty] | N | SG1 | 100%
46124 | Roslin STW Refurb - STW002150 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-16 | 2010-06-28 | 2010-08-09 | 2011-01-26 |  | Midlothian | 297647 | 0 | 199.93 | 0 | 0 | 0 | 0 | 0 | 199.93 | 0 | 0 | 0 | 297846.93 | 0 | 0 | 0 | 0 | 297846.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503260 | Roslin WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-02-28 | 2024-12-23 | 2025-03-24 | 2026-04-24 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 74866.55 | 6708.47 | 19730.98 | 101306 | 1898694.12 | 0 | 0 | 2000000.12 | 0 | 0 | 0 | 0 | 2000000.12 | 122419.09 | [5 empty] | N | SG1 | 100%
505984 | Rosneath Wwtw - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-09-14 | 2024-05-29 | 2024-08-28 | 2025-04-21 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29054 | 29054 | 370946.07 | 0 | 0 | 400000.07 | 0 | 0 | 0 | 0 | 400000.07 | 122419.09 | [5 empty] | N | SG1 | 100%
502951 | Ross Priory - Balmore Surge Vessel Lining | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-06-11 | 2022-04-01 | 2022-08-03 | 2023-03-15 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 6475.1 | 4282.73 | 9700.86 | 12224.32 | 32683.01 | 815820.94 | 0 | 0 | 848503.95 | 0 | 0 | 0 | 0 | 848503.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505139 | Ross Priory RWPS - Blairlinnans No.2 motor coupling replacment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-19 |  | 2020-05-28 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 625.68 | 8974.94 | 9600.62 | 0 | 0 | 0 | 9600.62 | 0 | 0 | 0 | 0 | 9600.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507087 | Ross Priory RWPS - LV system condition & compliance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-05-13 | 2024-03-29 | 2024-09-06 | 2026-03-20 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2733.54 | 2733.54 | -2733.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WSNI | 100%
502927 | Ross Priory to Blmore (Strathblane tunnel) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2021-04-01 | 2022-03-28 | 2022-06-27 | 2023-01-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 6024.67 | 4966.52 | 3320.03 | 13247.6 | 27558.81 | 132251.89 | 0 | 0 | 159810.7 | 0 | 0 | 0 | 0 | 159810.7 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505985 | Rothes RBC No1 Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-04-01 | 2020-04-16 | 2020-04-27 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8920.71 | 8920.71 | 0 | 0 | 0 | 8920.71 | 0 | 0 | 0 | 0 | 8920.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503276 | Rothes WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-05-04 | 2025-02-26 | 2025-05-14 | 2026-06-30 |  | Moray | 0 | 0 | 0 | 0 | 0 | 78497.03 | 11136.14 | 17540.83 | 107174 | 1892826.32 | 0 | 0 | 2000000.32 | 0 | 0 | 0 | 0 | 2000000.32 | 122419.09 | [5 empty] | N | SG1 | 100%
501638 | Rothesay Network Odour | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 | 2021-02-18 | 2021-02-18 | 2020-09-02 | 2020-09-02 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 166.36 | 19862.39 | 3468.89 | 9062.82 | 32560.46 | -1511.46 | 0 | 0 | 31049 | 0 | 0 | 0 | 0 | 31049 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501165 | Rothesay STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2015-12-03 | 2018-11-29 | 2018-12-17 | 2021-03-30 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 12056 | 255828.88 | 40930.71 | 352778.46 | 1313001.38 | 325638.21 | 2300233.64 | 130630.31 | 0 | 0 | 2430863.95 | 0 | 0 | 41382.05 | 41382.05 | 2472246 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506803 | Rothiemay DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-10 | 2021-08-06 | 2022-03-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502724 | Rothienorman Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2018-02-23 | 2018-08-28 | 2018-11-26 | 2019-02-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 11822.04 | 36108.49 | -1930.53 | -2535.79 | 43464.21 | 0 | 0 | 0 | 43464.21 | 0 | 0 | 0 | 0 | 43464.21 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400068 | Rothienorman STW Upgrade WQ01 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-10-06 | 2012-09-05 | 2013-01-07 | 2014-03-19 | 2014-03-26 | Aberdeenshire | 1109218.07 | 0 | 45081.75 | -1694.79 | 0 | 0 | 0 | 0 | 43386.96 | 0 | 0 | 0 | 1152605.03 | 0 | 0 | 0 | 0 | 1152605.03 | 151180.22 | [5 empty] | N | SG1 | 20% | WQ01 | 80%
503222 | Rothienorman WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-03-10 | 2024-01-11 | 2024-04-10 | 2025-06-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 89094.82 | 15514.39 | 29683.5 | 134292.71 | 2414585.61 | 0 | 0 | 2548878.32 | 0 | 0 | 0 | 0 | 2548878.32 | 122419.09 | [5 empty] | N | SG1 | 100%
504068 | Roughrigg Reservoir MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-03-27 | 2022-07-08 | 2022-11-09 | 2024-01-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 61603.07 | 40858.89 | 102461.96 | 1697553.47 | 0 | 0 | 1800015.43 | 0 | 0 | 0 | 0 | 1800015.43 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500940 | Roundknowe Road Calderbraes Golf Club Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-09-04 | 2018-09-18 | 2018-10-29 | 2019-06-11 |  | North Lanarkshire | 0 | 0 | 26881.08 | 26102.92 | 197586 | 1533546 | 287151 | 18623 | 2089890 | 0 | 0 | 0 | 2089890 | 0 | 0 | 0 | 0 | 2089890 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45362 | Rousay WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-12-07 | 2012-01-30 | 2012-09-27 | 2012-12-11 | Orkney Islands | 1140367.08 | 0 | 11889.84 | -16046.76 | 0 | 0 | 0 | 0 | -4156.92 | 0 | 0 | 0 | 1136210.16 | 0 | 0 | 0 | 0 | 1136210.16 | 57522.26 | [5 empty] | N | WG1 | 6.758% | DW13 | 7.984% | DW23 | 85.26%
402602 | Rova Head STC Lerwick | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-27 | 2014-05-23 | 2014-08-29 | 2014-09-01 |  | All East Unitary Authorities | 7460 | 0 | -1638.64 | 0 | 0 | 0 | 0 | 0 | -1638.64 | 0 | 0 | 0 | 5821.36 | 0 | 0 | 0 | 0 | 5821.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502200 | Rovahead STC - CM and Biothermic digester | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 |  | Shetland Islands | 0 | 0 | 0 | 15906.98 | 249.02 | 47.6 | 0 | 0 | 16203.6 | 0 | 0 | 0 | 16203.6 | 0 | 0 | 0 | 0 | 16203.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500491 | ROVAHEAD WwTW & STC CM - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-04-21 | 2016-11-30 | 2017-03-24 | 2018-12-17 |  | Shetland Islands | 0 | 0 | 73000 | 388298 | 773512 | 119183 | -1816 | -13080.71 | 1339096.29 | 0 | 0 | 0 | 1339096.29 | 0 | 0 | 0 | 0 | 1339096.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503041 | Rowallan Home Farm Kilmarnock - Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2018-08-15 | 2018-10-31 | 2019-01-14 | 2019-07-12 |  | East Ayrshire | 0 | 0 | 0 | 0 | 6395.2 | 365260.58 | 156211.22 | 57725.56 | 585592.56 | 0 | 0 | 0 | 585592.56 | 0 | 0 | 0 | 0 | 585592.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508159 | Rowbank and Barcriags Reservoir Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-09-02 | 2021-05-06 | 2021-12-17 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4437 | 4437 | 10563.33 | 0 | 0 | 15000.33 | 0 | 0 | 0 | 0 | 15000.33 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502911 | Rowett South Waste Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | WINF | Infra Charge | MS0 | 2020-01-16 | 2021-11-29 | 2022-02-07 | 2022-12-28 |  | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 31343.51 | 65855.96 | 2861.84 | 100061.31 | 1074686.29 | 0 | 0 | 1174747.6 | 0 | 0 | 0 | 0 | 1174747.6 | 0 | [5 empty] | N | SG5 | 100%
502692 | Royal Alexandria Hospital Temporary Treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2017-04-21 | 2018-02-21 | 2018-02-21 | 2018-09-28 |  | Renfrewshire | 0 | 0 | 0 | 0 | 697.56 | 66829.05 | 60043.03 | 94158.36 | 221728 | 13666.66 | 0 | 0 | 235394.66 | 0 | 0 | 0 | 0 | 235394.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501180 | RTU Replacement and Provision of Emergency Outstations | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2015-12-07 | 2015-12-07 | 2016-02-10 | 2021-05-26 |  | Scottish Water Wide | 0 | 0 | 82424 | -3233.77 | 977 | 0 | 0 | 51449.77 | 131617 | 9403.71 | 0 | 0 | 141020.71 | 0 | 0 | 0 | 0 | 141020.71 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
502876 | Ruthven Water Pipe Bridge Aberuthven | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS4 | 2018-08-15 | 2020-03-31 | 2020-09-21 | 2021-03-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 14679.7 | 49361.3 | 145134.99 | 495817.01 | 704993 | 23873 | 0 | 0 | 728866 | 0 | 0 | 0 | 0 | 728866 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501676 | RWI000447 - PETERHEAD BALMOOR RWI (Forehill WTW - Comp Flow) 1970 NK117474 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-06-02 |  | Aberdeenshire | 0 | 0 | 0 | 12994.67 | 0 | 0 | 0 | 0 | 12994.67 | 0 | 0 | 0 | 12994.67 | 0 | 0 | 0 | 0 | 12994.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402016 | RWI000743 Loch of Boardhouse RWI Screens | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-08-11 | 2013-10-31 | 2014-01-27 | 2015-03-26 |  | Orkney Islands | 158625 | 0 | 22309 | 0.34 | -57.15 | 0 | 0 | 0 | 22252.19 | 0 | 0 | 0 | 180877.19 | 0 | 0 | 0 | 0 | 180877.19 | 119022.58 | [5 empty] | N | CM_M&G | 100%
502782 | Ryat Linn and Waulkmill Glen MIOS and Maintenance Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-12-22 | 2017-12-22 | 2018-07-02 | 2018-08-27 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 69300 | 802553.49 | 374.22 | 0 | 872227.71 | 0 | 0 | 0 | 872227.71 | 0 | 0 | 0 | 0 | 872227.71 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504589 | S TWS & WTW sample tap investigations & resolution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2020-02-07 | 2021-03-29 | 2021-05-14 | 2023-02-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1148.09 | 22548.98 | 23697.07 | 192216.65 | 0 | 0 | 215913.72 | 0 | 0 | 0 | 0 | 215913.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401637 | S002 - UID - At junction of No 50 Walkinshaw Street - Queen Mary Street Glasgow Green | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-25 | 2013-03-18 | 2013-11-25 | 2014-02-26 | 2014-03-18 | Glasgow City | 147401 | 0 | 0 | 0 | 0 | -3697.4 | 0 | 0 | -3697.4 | 0 | 0 | 0 | 143703.6 | 0 | 0 | 0 | 0 | 143703.6 | 0 | [5 empty] | N | EC04B | 100%
401638 | S003 - UID - Glasgow Green | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-29 | 2013-05-13 | 2013-05-13 | 2014-03-26 | 2014-03-27 | Glasgow City | 858894 | 0 | 0 | 0 | 0 | -2118.51 | 0 | 0 | -2118.51 | 0 | 0 | 0 | 856775.49 | 0 | 0 | 0 | 0 | 856775.49 | 0 | [5 empty] | N | EC04B | 100%
401640 | S005 - UID - Outside No. 2 Orr Street Glasgow Green (GN no 17) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-25 | 2012-06-21 | 2012-06-25 | 2013-03-01 | 2013-05-30 | Glasgow City | 723704 | 0 | -5510.77 | 0 | 0 | 0 | 0 | 0 | -5510.77 | 0 | 0 | 0 | 718193.23 | 0 | 0 | 0 | 0 | 718193.23 | 0 | [5 empty] | N | EC04B | 100%
401642 | S009 - UID - Dalmarnock WwTP Inlet CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2010-12-15 | 2017-09-21 | 2017-09-25 | 2019-02-28 | 2019-03-31 | Glasgow City | 248427 | 0 | 346389 | 1280138.7 | 3700201.48 | 5954831.64 | 1307.21 | 8648.97 | 11291517 | 121089.78 | 46014.1164 | 63875.4273 | 11661033.78 | 17861.3109 | 0 | 0 | 17861.3109 | 11678895.0909 | 1692437.29 | [5 empty] | Y | EC04B | 38% | CM_WWNI | 62% | [34 empty] | 1 | [30 empty] | 0
401608 | S011 - UID - Crookston-Rosshall CSO 144 Cairnhill Circus Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-17 | 2012-11-30 | 2013-01-14 | 2013-06-06 | 2013-09-12 | Renfrewshire | 549863.1 | 0 | 14786.15 | 0 | 0 | 0 | 0 | 0 | 14786.15 | 0 | 0 | 0 | 564649.25 | 0 | 0 | 0 | 0 | 564649.25 | 0 | [5 empty] | N | EC04B | 100%
401643 | S014 - UID - Blackhall No.1 C.S.O. Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-01 | 2014-06-30 | 2015-05-25 | 2015-10-31 | 2018-03-31 | Renfrewshire | 201610 | 0 | 235520 | -49551.07 | 0 | -5880.25 | 0 | 0 | 180088.68 | 0 | 0 | 0 | 381698.68 | 0 | 0 | 0 | 0 | 381698.68 | 64855 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401610 | S015 - UID - Blackhall Syphon CSO 150yrd NW of Jennys Well Road Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-18 | 2013-09-18 | 2013-11-04 | 2014-05-26 | 2014-10-27 | Renfrewshire | 796012 | 0 | 91098 | 8049.2 | 0 | 0 | 0 | 0 | 99147.2 | 0 | 0 | 0 | 895159.2 | 0 | 0 | 0 | 0 | 895159.2 | 0 | [5 empty] | N | EC04B | 100%
401645 | S017 - UID - Adelphi Street Rear of Naut. College. | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-13 | 2013-09-23 | 2015-02-17 | 2015-03-24 | Renfrewshire | 37343.79 | 0 | 1244.21 | -62.03 | 0 | 0 | 0 | 0 | 1182.18 | 0 | 0 | 0 | 38525.97 | 0 | 0 | 0 | 0 | 38525.97 | 0 | [5 empty] | N | EC10B | 100%
401646 | S018 - UID - Adelphi Street 20m East of Commercial Road | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-08-12 | 2015-07-31 | 2015-09-30 | Glasgow City | 44582 | 0 | 0 | 0 | -646.33 | 0 | 0 | 0 | -646.33 | 0 | 0 | 0 | 43935.67 | 0 | 0 | 0 | 0 | 43935.67 | 329 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401647 | S019 - UID - Adelphi Street 20m West of Waddell Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-18 | 2014-08-12 | 2015-07-31 | 2015-09-30 | Glasgow City | 1276232 | 0 | 80691.87 | 4867.82 | 1131.22 | 0 | 0 | 0 | 86690.91 | 0 | 0 | 0 | 1362922.91 | 0 | 0 | 0 | 0 | 1362922.91 | 71978 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401649 | S021 - UID - Adelphi Street at (in Mosque) at Mosque Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-13 | 2013-09-23 | 2015-02-17 | 2015-03-24 | Glasgow City | 46859 | 0 | 141 | -250.78 | 0 | 0 | 0 | 0 | -109.78 | 0 | 0 | 0 | 46749.22 | 0 | 0 | 0 | 0 | 46749.22 | 0 | [5 empty] | N | EC10B | 100%
401611 | S022 - UID - Adelphi Street at (Sheriff Court) Gorbals Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-18 | 2013-12-30 | 2014-05-05 | 2014-10-14 | 2015-03-25 | Glasgow City | 866356 | 0 | 5571.14 | 0 | 0 | 0 | 0 | 0 | 5571.14 | 0 | 0 | 0 | 871927.14 | 0 | 0 | 0 | 0 | 871927.14 | 0 | [5 empty] | N | EC10B | 100%
401650 | S023 - UID - Adelphi Street at Commercial Road | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-08-12 | 2015-07-31 | 2015-09-30 | Glasgow City | 40667 | 0 | 283.06 | 1066.25 | -481.62 | 0 | 0 | 0 | 867.69 | 0 | 0 | 0 | 41534.69 | 0 | 0 | 0 | 0 | 41534.69 | 129 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401651 | S024 - UID - Adelphi Street at Crown Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-13 | 2013-09-23 | 2015-02-17 | 2015-03-24 | Glasgow City | 2693040 | 0 | 34089 | 1696.71 | 0 | 0 | 0 | 0 | 35785.71 | 0 | 0 | 0 | 2728825.71 | 0 | 0 | 0 | 0 | 2728825.71 | 0 | [5 empty] | N | EC10B | 100%
401653 | S026 - UID - Adelphi Street at McNeil Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-27 | 2014-05-05 | 2015-01-19 | 2015-03-24 | Glasgow City | 1358188.53 | 0 | 50458.47 | 2439.67 | 0 | 0 | 0 | 0 | 52898.14 | 0 | 0 | 0 | 1411086.67 | 0 | 0 | 0 | 0 | 1411086.67 | 0 | [5 empty] | N | EC04B | 100%
401613 | S028 - UID - Carlton Place at South Portland Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-18 | 2013-12-23 | 2014-05-05 | 2014-10-14 | 2015-03-25 | Renfrewshire | 47133 | 0 | 1113 | -2649.71 | 0 | 0 | 0 | 0 | -1536.71 | 0 | 0 | 0 | 45596.29 | 0 | 0 | 0 | 0 | 45596.29 | 0 | [5 empty] | N | EC10B | 100%
401654 | S029 - UID - Clyde Place at Commerce Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-01-06 | 2015-11-30 | 2016-03-31 | Glasgow City | 67927 | 0 | 1376.83 | 1861.1 | -114.5 | 0 | 0 | 0 | 3123.43 | 0 | 0 | 0 | 71050.43 | 0 | 0 | 0 | 0 | 71050.43 | 866 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401655 | S030 - UID - Clyde Place at Tradeston Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-18 | 2014-01-06 | 2015-11-30 | 2016-02-29 | Glasgow City | 3055520 | 0 | 379657 | 19944 | 30908.44 | 11451.63 | 0 | 0 | 441961.07 | 0 | 0 | 0 | 3497481.07 | 0 | 0 | 0 | 0 | 3497481.07 | 266968 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401656 | S031 - UID - Clyde Place at West Street from 32 St Andrews Road Pollokshields | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-06-30 | 2018-10-31 | Glasgow City | 100499 | 0 | 0 | 0 | 0 | 0 | -1472.74 | 0 | -1472.74 | 0 | 0 | 0 | 99026.26 | 0 | 0 | 0 | 0 | 99026.26 | 5799 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401657 | S032 - UID - Clyde Place at West Street from Paisley Road-West Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-01-06 | 2015-11-30 | 2016-03-31 | Glasgow City | 53746 | 0 | 1213.92 | 598.8 | -190.55 | 0 | 0 | 0 | 1622.17 | 0 | 0 | 0 | 55368.17 | 0 | 0 | 0 | 0 | 55368.17 | 232 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401658 | S033 - UID - Junction Of Gorbals Street- Norfolk Street (No.1) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-12-23 | 2014-05-05 | 2014-10-14 | 2015-03-25 | Glasgow City | 44865 | 0 | 0 | -1435.18 | 0 | 0 | 0 | 0 | -1435.18 | 0 | 0 | 0 | 43429.82 | 0 | 0 | 0 | 0 | 43429.82 | 0 | [5 empty] | N | EC10B | 100%
401659 | S034 - UID - Paisley Road At Junction With West Street (No.2) | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-01-06 | 2015-11-30 | 2016-03-31 | Glasgow City | 54752 | 0 | 0 | 457.62 | 0 | 0 | 0 | 0 | 457.62 | 0 | 0 | 0 | 55209.62 | 0 | 0 | 0 | 0 | 55209.62 | 228 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401660 | S035 - UID - Rutherglen Rd-Polmadie Rd (No. 1) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-30 | 2013-10-21 | 2014-11-13 | 2015-03-06 | South Lanarkshire | 764717 | 0 | 2455 | -2012.23 | 0 | 0 | 0 | 0 | 442.77 | 0 | 0 | 0 | 765159.77 | 0 | 0 | 0 | 0 | 765159.77 | 0 | [5 empty] | N | EC04B | 100%
401661 | S036 - UID - Rutherglen Rd-Polmadie Rd (No. 2) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-30 | 2013-10-21 | 2014-11-13 | 2015-03-06 | Glasgow City | 50131.61 | 0 | 79.39 | 0 | 0 | 0 | 0 | 0 | 79.39 | 0 | 0 | 0 | 50211 | 0 | 0 | 0 | 0 | 50211 | 0 | [5 empty] | N | EC04B | 100%
401662 | S037 - UID - Rutherglen Road at Fauldhouse St (Richmond Park) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2013-12-09 | 2014-07-30 | 2014-10-27 | Glasgow City | 62420 | 0 | 0 | 822.24 | 0 | 0 | 0 | 0 | 822.24 | 0 | 0 | 0 | 63242.24 | 0 | 0 | 0 | 0 | 63242.24 | 0 | [5 empty] | N | EC04B | 100%
401663 | S038 - UID - Rutherglen Road in Park (Richmond Park) | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS5 | 2010-12-15 | 2020-02-11 | 2020-01-13 | 2020-12-31 | 2021-03-31 | South Lanarkshire | 207195.17 | 0 | 13292.83 | 8559 | 68130.85 | 152992.15 | 908650.13 | 1179061.87 | 2330686.83 | 0 | 0 | 0 | 2537882 | 0 | 0 | 0 | 0 | 2537882 | 1916335 |  |  |  |  | 1876.5275 | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401664 | S039 - UID - Rutherglen Road Rear of No 473 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-12-15 | 2013-11-18 | 2013-12-09 | 2014-07-30 | 2014-10-27 | Glasgow City | 1004447.51 | 0 | 903.49 | -836.26 | 0 | 0 | 0 | 0 | 67.23 | 0 | 0 | 0 | 1004514.74 | 0 | 0 | 0 | 0 | 1004514.74 | 209381.79 | [5 empty] | N | CM_WWI | 2.331% | CS11A | 5.995% | EC04B | 91.67%
401665 | S040 - UID - Springfield Quay (No. 1) Seaward Street R-O Cinema Kingston | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-12-11 | 2014-09-01 | 2015-02-10 | 2015-03-20 | Glasgow City | 53736 | 0 | 447 | -285.66 | 0 | 0 | 0 | 0 | 161.34 | 0 | 0 | 0 | 53897.34 | 0 | 0 | 0 | 0 | 53897.34 | 3375 | [5 empty] | N | EC10B | 100%
401666 | S041 - UID - Springfield Quay No. 2 Car Park CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-12-10 | 2014-09-01 | 2015-02-10 | 2015-03-20 | Renfrewshire | 854401 | 0 | -21849 | 11405.16 | 0 | 0 | 0 | 0 | -10443.84 | 0 | 0 | 0 | 843957.16 | 0 | 0 | 0 | 0 | 843957.16 | 66106 | [5 empty] | N | EC10B | 100%
401667 | S042 - UID - 83 Borgie Crescent - Cambuslang | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-02 | 2011-12-07 | 2011-12-19 | 2012-01-25 | 2012-03-23 | South Lanarkshire | 20999.23 | 0 | 0 | 0 | 277.29 | 0 | 0 | 0 | 277.29 | 0 | 0 | 0 | 21276.52 | 0 | 0 | 0 | 0 | 21276.52 | 0 | [5 empty] | N | EC04B | 100%
401668 | S043 - UID - Cambuslang Road Richmond Laundry - South East of Railway Rutherglen | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS3 | 2010-12-02 | 2019-03-26 | 2019-05-21 | 2021-08-26 | 2021-11-29 | South Lanarkshire | 174698 | 0 | 36209 | 10953.38 | 76885.15 | 306790.47 | 1580192.97 | 210546.11 | 2221577.08 | 424821 | 424821 | 508161.2119 | 2821096.08 | 83340.2119 | 0 | 0 | 83340.2119 | 2904436.2919 | 2348796 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401669 | S044 - UID - Clinic Johnson Drive - Cambuslang | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-02 | 2013-05-27 | 2013-08-12 | 2014-02-17 | 2014-02-28 | South Lanarkshire | 498527 | 0 | 1623 | -1085.38 | 0 | 0 | 0 | 0 | 537.62 | 0 | 0 | 0 | 499064.62 | 0 | 0 | 0 | 0 | 499064.62 | 0 | [5 empty] | N | EC04B | 100%
401614 | S045 - UID - Clyde Industrial Estate Rutherglen | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS6 | 2010-11-17 | 2018-09-25 | 2019-01-11 | 2019-06-30 | 2019-08-31 | South Lanarkshire | 107706.31 | 0 | 15389.93 | 53873.78 | 98909.98 | 602339 | 29934 | 7515.02 | 807961.71 | 1491 | 1491 | 2069.7618 | 917159.02 | 578.7618 | 0 | 0 | 578.7618 | 917737.7818 | 410766 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401685 | S046 - UID - Downiebrae Road Farme Estate Shieldhall No 39 | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS3 | 2010-12-03 | 2020-03-19 | 2020-03-27 | 2021-09-10 | 2021-12-13 | South Lanarkshire | 90517 | 0 | 5290.44 | 13209.48 | 47328.08 | 181469 | 362182.05 | 1389476.95 | 1998956 | 1025546 | 1025546 | 1235712.3901 | 3115019 | 210166.3901 | 0 | 0 | 210166.3901 | 3325185.3901 | 397695 |  |  |  |  | 2990.0004 | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401686 | S047 - UID - Eastfield PS EO; Rutherglen | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2015-06-25 | 2015-08-03 | 2015-08-12 | 2015-08-12 | South Lanarkshire | 54503 | 0 | -991.23 | 0 | 0 | 0 | 0 | 0 | -991.23 | 0 | 0 | 0 | 53511.77 | 0 | 0 | 0 | 0 | 53511.77 | 0 | [5 empty] | N | EC04B | 100%
401687 | S048 - UID - Farme Estate PS EO; Downiebrae Road; Shieldhall No.40 | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS3 | 2010-12-03 | 2020-03-16 | 2020-03-27 | 2021-09-09 | 2021-12-10 | South Lanarkshire | 29320 | 0 | 7758 | 6878 | 39700 | 1442 | 5422 | 8437 | 69637 | 9863 | 9863 | 252367.8756 | 108820 | 242504.8756 | 0 | 2.9104e-11 | 242504.8756 | 351324.8756 | 455597 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401688 | S050 - UID - Morriston Street at Monkcastle Drive - Cambuslang | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-02-20 | 2013-03-28 | 2014-11-13 | 2015-03-06 | South Lanarkshire | 905260 | 0 | 60350 | -12975.08 | -108.76 | 0 | 0 | 0 | 47266.16 | 0 | 0 | 0 | 952526.16 | 0 | 0 | 0 | 0 | 952526.16 | 0 | [5 empty] | N | EC04B | 100%
401689 | S051 - UID - Standford Hall Allison Drive - Cambuslang | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-02-19 | 2013-03-28 | 2014-11-13 | 2015-03-06 | South Lanarkshire | 19930 | 0 | -1636.96 | 0 | 0 | 0 | 0 | 0 | -1636.96 | 0 | 0 | 0 | 18293.04 | 0 | 0 | 0 | 0 | 18293.04 | 0 | [5 empty] | N | EC04B | 100%
401616 | S053 - UID - Cressy Street off Govan Road in Ship Yards | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS6 | 2010-11-18 | 2018-03-22 | 2018-03-28 | 2020-03-10 | 2020-03-31 | Glasgow City | 172414 | 0 | 17738 | 46269.43 | 326611.77 | 950913 | 767720.86 | -3917.06 | 2105336 | 52250 | 52250 | 72531.8953 | 2330000 | 20281.8953 | 0 | 0 | 20281.8953 | 2350281.8953 | 728927 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401618 | S055 - UID - Govan Road - Ibrox | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-01 | 2014-12-23 | 2015-09-14 | 2017-02-28 | 2017-03-31 | Glasgow City | 502945 | 0 | 290095 | 352959.98 | 210444.43 | 45.02 | 25.78 | 0 | 853570.21 | 0 | 0 | 0 | 1356515.21 | 0 | 0 | 0 | 0 | 1356515.21 | 498170 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401619 | S056 - UID - Govan Road 40177 | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-11-26 | 2014-12-23 | 2015-09-14 | 2016-09-30 | 2017-02-28 | Glasgow City | 388377 | 0 | 795900 | 369661.84 | -8439.04 | 2146.59 | 20.59 | 0 | 1159289.98 | 0 | 0 | 0 | 1547666.98 | 0 | 0 | 0 | 0 | 1547666.98 | 707835 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401620 | S057 - UID - Govan Road 40178 | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-11-25 | 2014-12-22 | 2015-09-14 | 2016-11-30 | 2017-03-31 | Glasgow City | 361706 | 0 | 122769 | 695569.66 | 20455.7 | 2608.84 | 69.06 | 0 | 841472.26 | 0 | 0 | 0 | 1203178.26 | 0 | 0 | 0 | 0 | 1203178.26 | 593127.79 | [5 empty] | Y | CM_WWI | 13.64% | EC10B | 86.36% | [34 empty] | 1 | [30 empty] | 0
401622 | S059 - UID - Mavisbank Quay at Mavisbank Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-26 | 2013-02-20 | 2013-08-29 | 2014-03-24 | 2014-03-28 | Glasgow City | 597653.74 | 0 | 8442.09 | 0 | 0 | 0 | 0 | 0 | 8442.09 | 0 | 0 | 0 | 606095.83 | 0 | 0 | 0 | 0 | 606095.83 | 0 | [5 empty] | N | EC10B | 100%
401623 | S060 - UID - McKechnie Street off Govan Road CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-26 | 2013-09-16 | 2013-11-04 | 2014-03-24 | 2014-03-31 | Glasgow City | 324073 | 0 | 25308 | -325.99 | 0 | 0 | 0 | 0 | 24982.01 | 0 | 0 | 0 | 349055.01 | 0 | 0 | 0 | 0 | 349055.01 | 0 | [5 empty] | N | EC10B | 100%
401400 | S063 - UID - Stag Street at Highland Lane | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-09-10 | 2011-08-22 | 2013-08-19 | 2014-03-12 | 2014-03-28 | Glasgow City | 818243 | 0 | 0 | 0 | -39179.19 | 0 | 0 | 0 | -39179.19 | 0 | 0 | 0 | 779063.81 | 0 | 0 | 0 | 0 | 779063.81 | 0 | [5 empty] | N | EC10B | 100%
401690 | S065 - UID - 10 Holmbank Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-11-11 | 2014-09-22 | 2028-04-01 | 2028-04-01 | Glasgow City | 588476 | 0 | 59438 | -382.79 | 0 | 0 | 0 | 0 | 59055.21 | 0 | 0 | 0 | 647531.21 | 0 | 0 | 0 | 0 | 647531.21 | 65156 | [5 empty] | Y | EC04B | 100% | [67 empty] | 0
401692 | S068 - UID - Busby Bridge Downstream on West bank 12 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-15 | 2013-10-28 | 2015-01-19 | 2015-02-16 | East Renfrewshire | 351278.66 | 0 | 20784.34 | 2999.87 | -14974.14 | 0 | 0 | 0 | 8810.07 | 0 | 0 | 0 | 360088.73 | 0 | 0 | 0 | 0 | 360088.73 | 0 | [5 empty] | N | EC04B | 100%
401693 | S069 - UID - Busby Bridge Downstream on West Bank 4 inch | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-16 | 2013-10-28 | 2015-01-19 | 2015-02-16 | East Renfrewshire | 21597.1 | 0 | 129.16 | 0 | 0 | 0 | 0 | 0 | 129.16 | 0 | 0 | 0 | 21726.26 | 0 | 0 | 0 | 0 | 21726.26 | 0 | [5 empty] | N | EC04B | 100%
401694 | S070 - UID - Cartside Drive Opposite Public Park on East Bank | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-01-09 | 2013-03-21 | 2013-07-04 | 2013-09-12 | East Renfrewshire | 59980 | 0 | -656.74 | 0 | 0 | 0 | 0 | 0 | -656.74 | 0 | 0 | 0 | 59323.26 | 0 | 0 | 0 | 0 | 59323.26 | 0 | [5 empty] | N | EC04B | 100%
401626 | S072 - UID - Cartside Street at Sinclair Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 2015-10-30 | Glasgow City | 69769 | 0 | -3777.73 | 0 | 0 | 0 | 0 | 0 | -3777.73 | 0 | 0 | 0 | 65991.27 | 0 | 0 | 0 | 0 | 65991.27 | 0 | [5 empty] | N | EC04B | 100%
401696 | S073 - UID - East of New Bridge on South Bank Margaretta Buildings Clarkston Road | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-03 | 2015-02-12 | 2015-03-30 | 2015-10-31 | 2016-03-31 | Glasgow City | 437780 | 0 | 671621 | -21212.18 | -1642.62 | 2.12 | 0 | 0 | 648768.32 | 0 | 0 | 0 | 1086548.32 | 0 | 0 | 0 | 0 | 1086548.32 | 638439 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401697 | S075 - UID - Millbrae Bridge on North Bank Millbrae Road | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2010-12-03 | 2016-03-14 | 2016-03-22 | 2019-01-31 | 2019-09-30 | Glasgow City | 5560 | 0 | 1527.05 | 2294.06 | 271.28 | 0 | 18.47 | 0 | 4110.86 | 0 | 0 | 0 | 9670.86 | 0 | 0 | 0 | 0 | 9670.86 | 3283 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401698 | S076 - UID - Millbrae Bridge on South Bank Millbrae Road | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2010-12-03 | 2016-03-15 | 2016-03-22 | 2019-01-31 | 2019-03-31 | Glasgow City | 109367.15 | 0 | 502080.85 | 808540.82 | 55906.96 | 1361866.24 | 53134.32 | 5183.66 | 2786712.85 | 5073.6 | 5073.6 | 7043.0206 | 2901153.6 | 1969.4206 | 0 | 0 | 1969.4206 | 2903123.0206 | 3279862 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401699 | S077 - UID - Millholm Road Ejector Station | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-21 | 2013-08-12 | 2014-01-10 | 2014-02-03 | Glasgow City | 283653.19 | 0 | 1830.97 | 471.46 | 0 | 0 | 0 | 0 | 2302.43 | 0 | 0 | 0 | 285955.62 | 0 | 0 | 0 | 0 | 285955.62 | 0 | [5 empty] | N | EC04B | 100%
401700 | S079 - UID - Netherburn Avenue CSO (Williamwood Storm Tank) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-20 | 2014-01-27 | 2014-11-10 | 2015-02-06 | East Renfrewshire | 514292 | 0 | 29253 | 1750.57 | 0 | 0 | 0 | 0 | 31003.57 | 0 | 0 | 0 | 545295.57 | 0 | 0 | 0 | 0 | 545295.57 | 0 | [5 empty] | N | EC04B | 100%
401702 | S082 - UID - Old Castle Road Junction At Delvin Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2012-11-30 | 2013-02-04 | 2013-03-25 | 2013-05-21 | Glasgow City | 33021 | 0 | 849.16 | 0 | 0 | 0 | 0 | 0 | 849.16 | 0 | 0 | 0 | 33870.16 | 0 | 0 | 0 | 0 | 33870.16 | 0 | [5 empty] | N | EC04B | 100%
401703 | S083 - UID - Overflow adjacent to No 1A Moray Drive | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-07-30 | 2014-03-03 | 2014-11-09 | 2015-01-28 | East Renfrewshire | 705152 | 0 | -27124 | -8144.4 | 1.05 | 0 | 0 | 0 | -35267.35 | 0 | 0 | 0 | 669884.65 | 0 | 0 | 0 | 0 | 669884.65 | 0 | [5 empty] | N | EC04B | 100%
401856 | S086 - UID - Rear of No 88 Moray Gardens (Overlee Park) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-09-02 | 2013-07-19 | 2014-02-24 | 2014-11-09 | 2015-01-27 | East Renfrewshire | 357124 | 0 | 9911 | 1952.41 | 0 | 0 | 0 | 0 | 11863.41 | 0 | 0 | 0 | 368987.41 | 0 | 0 | 0 | 0 | 368987.41 | 0 | [5 empty] | N | EC04B | 100%
401705 | S087 - UID - Scotwood Overflow North East of Lay-by Busby Road | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS3 | 2010-12-03 | 2020-02-12 | 2020-01-10 | 2021-10-19 | 2022-02-02 | East Renfrewshire | 22780.69 | 0 | 26463.49 | 77503.31 | 227139.31 | 326614.2 | 2616647.44 | 3356711.01 | 6631078.76 | 1568603 | 1568603 | 2056847.6238 | 8222462.45 | 488244.6238 | 0 | -0.004 | 488244.6198 | 8710707.0698 | 3110294 |  |  |  |  | 63710.0004 | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401706 | S088 - UID - Williamwood Storm Tank Netherburn Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-20 | 2013-10-21 | 2014-10-09 | 2015-01-28 | East Renfrewshire | 251567 | 0 | 1993.79 | 1160.85 | 0 | 0 | 0 | 0 | 3154.64 | 0 | 0 | 0 | 254721.64 | 0 | 0 | 0 | 0 | 254721.64 | 0 | [5 empty] | N | EC04B | 100%
401707 | S089 - UID - Williamwood Storm Tank No1 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-20 | 2013-10-21 | 2014-10-09 | 2015-03-06 | East Renfrewshire | 338502 | 0 | -10367 | 39.62 | 0 | 0 | 0 | 0 | -10327.38 | 0 | 0 | 0 | 328174.62 | 0 | 0 | 0 | 0 | 328174.62 | 0 | [5 empty] | N | EC04B | 100%
401708 | S090 - UID - Williamwood Storm Tank East of No 76 First Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-16 | 2014-01-27 | 2014-11-10 | 2015-02-06 | East Renfrewshire | 16218.86 | 0 | 100.14 | -100.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16218.86 | 0 | 0 | 0 | 0 | 16218.86 | 0 | [5 empty] | N | EC04B | 100%
401630 | S092 - UID - 296 Linthaugh Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2013-01-22 | 2013-01-28 | 2013-06-06 | 2013-09-12 | Glasgow City | 740679.28 | 0 | 2526.3 | 0 | 0 | 0 | 0 | 0 | 2526.3 | 0 | 0 | 0 | 743205.58 | 0 | 0 | 0 | 0 | 743205.58 | 0 | [5 empty] | N | EC04B | 100%
401709 | S093 - UID - After Footbridge in Dovecothall Field | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS7 | 2010-12-15 | 2016-12-21 | 2017-01-23 | 2017-12-31 | 2018-02-28 | East Renfrewshire | 531925 | 0 | 88182 | 2127406 | 3715323 | -45114.52 | -56106.13 | 0 | 5829690.34 | 0 | 0 | 0 | 6361615.34 | 0 | 0 | 0 | 0 | 6361615.34 | 4793730 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401631 | S094 - UID - At rear of Leverndale Hospital Crookston Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2012-11-09 | 2012-11-19 | 2012-12-17 | 2013-01-17 | Glasgow City | 26803 | 0 | 3313.97 | 0 | 0 | 0 | 0 | 0 | 3313.97 | 0 | 0 | 0 | 30116.97 | 0 | 0 | 0 | 0 | 30116.97 | 0 | [5 empty] | N | EC04B | 100%
401710 | S096 - UID - Kings Inch Road at Ferry Road Renfrew | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-09 | 2016-07-21 | 2016-10-03 | 2017-10-31 | 2018-01-31 | Renfrewshire | 372283 | 0 | 153652 | 364372.88 | 1486484.24 | 0 | -2125.64 | 0 | 2002383.48 | 0 | 0 | 0 | 2374666.48 | 0 | 0 | 0 | 0 | 2374666.48 | 807733 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401633 | S097 - UID - New PS EO at Provost Drive Court Renfrew | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-11-27 | 2012-07-17 | 2012-11-14 | 2012-12-31 | 2016-10-31 | Glasgow City | 1201151 | 0 | 1468404 | 1751817.62 | 13210.68 | 12512.77 | 0 | 0 | 3245945.07 | 0 | 0 | 0 | 4447096.07 | 0 | 0 | 0 | 0 | 4447096.07 | 745277 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401718 | S098 - UID - Pollokshaws Road Pollok Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-07-24 | 2014-03-31 | 2015-01-19 | 2015-03-06 | Glasgow City | 894098 | 0 | 24073 | -10347.37 | 0 | 0 | 0 | 0 | 13725.63 | 0 | 0 | 0 | 907823.63 | 0 | 0 | 0 | 0 | 907823.63 | 0 | [5 empty] | N | EC04B | 100%
401719 | S099 - UID - Renfrew P.S.S. C.S.O. North Lodge Road Renfrew | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2014-04-28 | 2015-04-01 | 2015-04-17 | 2015-04-17 | Renfrewshire | 94561 | 0 | -120.52 | 0 | 0 | 0 | 0 | 0 | -120.52 | 0 | 0 | 0 | 94440.48 | 0 | 0 | 0 | 0 | 94440.48 | 0 | [5 empty] | N | EC10B | 100%
401721 | S102 - UID - Shawbridge Street North of Bridge | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-07-23 | 2014-03-31 | 2015-01-19 | 2015-03-06 | Glasgow City | 24500.59 | 0 | 1620.85 | 1272.03 | 0 | 0 | 0 | 0 | 2892.88 | 0 | 0 | 0 | 27393.47 | 0 | 0 | 0 | 0 | 27393.47 | 0 | [5 empty] | N | EC04B | 100%
401722 | S103 - UID - Shawbridge Street South of Bridge | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-07-23 | 2014-03-31 | 2015-01-19 | 2015-03-06 | Glasgow City | 34998 | 0 | 1094.67 | 1238.95 | 0 | 0 | 0 | 0 | 2333.62 | 0 | 0 | 0 | 37331.62 | 0 | 0 | 0 | 0 | 37331.62 | 0 | [5 empty] | N | EC04B | 100%
401635 | S104 - UID - Storm Sewage Overflow 63 Haining Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2012-07-17 | 2012-11-15 | 2012-12-07 | 2013-01-17 | Renfrewshire | 84062 | 0 | 73.41 | 1453.68 | -78.88 | 17.2 | 0 | 0 | 1465.41 | 0 | 0 | 0 | 85527.41 | 0 | 0 | 0 | 0 | 85527.41 | 0 | [5 empty] | N | EC10B | 100%
401723 | S105 - UID - Thornliebank Road Opposite Auldhouse Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-05-22 | 2013-10-21 | 2014-10-09 | 2014-12-19 | Glasgow City | 332879 | 0 | 383 | 429.7 | 0 | 0 | 0 | 0 | 812.7 | 0 | 0 | 0 | 333691.7 | 0 | 0 | 0 | 0 | 333691.7 | 0 | [5 empty] | N | EC04B | 100%
401744 | S106 - UID - Greenlaw Road No8 | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-10-15 | 2014-11-17 | 2015-05-31 | 2015-07-31 | Glasgow City | 788607 | 0 | 79830 | 1417.71 | -1073.35 | 0 | 0 | 0 | 80174.36 | 0 | 0 | 0 | 868781.36 | 0 | 0 | 0 | 0 | 868781.36 | 94950 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401745 | S107 - UID - Works Yard Dock Street Clydebank East | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-12-05 | 2015-02-18 | 2017-12-31 | 2018-02-28 | Glasgow City | 1319164 | 0 | -498084 | 416920 | 4577 | 1731 | 619 | 0 | -74237 | 0 | 0 | 0 | 1244927 | 0 | 0 | 0 | 0 | 1244927 | 570745 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401746 | S108 - UID - Millbrae Crescent Railway line CSO Yoker (GN no 45) | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2010-12-15 | 2014-12-05 | 2015-07-08 | 2020-03-31 | 2020-03-31 | Glasgow City | 786743 | 0 | 3995559.65 | 3438578.12 | 1220658.21 | 4431310.11 | 1548271.62 | 59891.05 | 14694268.76 | 49366.9 | 49366.9 | 68529.6617 | 15530378.66 | 19162.7617 | 0 | 0 | 19162.7617 | 15549541.4217 | 5121897.06 |  |  |  |  | 140.8333 | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401747 | S109 - UID - Greenlaw Road and 32 Lasswade Street (GN no.67) | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-10-14 | 2015-02-18 | 2015-05-31 | 2015-07-31 | Glasgow City | 46682.5 | 0 | 900.5 | 279.17 | -248.24 | 0 | 0 | 0 | 931.43 | 0 | 0 | 0 | 47613.93 | 0 | 0 | 0 | 0 | 47613.93 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401748 | S110 - UID - Napier St - Glasgow Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-11-28 | 2015-03-02 | 2015-03-19 | 2015-03-31 | Glasgow City | 95250.39 | 0 | 359.55 | 141.23 | 0 | 0 | 0 | 0 | 500.78 | 0 | 0 | 0 | 95751.17 | 0 | 0 | 0 | 0 | 95751.17 | 0 | [5 empty] | N | EC10B | 100%
401749 | S111 - UID - Junction of Dumbarton Road - Dyke Road - Culvert to Clyde | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-09 | 2014-12-05 | 2015-09-09 | 2016-03-31 | 2016-03-31 | Glasgow City | 281109 | 0 | 576163 | 7347.28 | 1405.01 | -383.52 | 0 | 0 | 584531.77 | 0 | 0 | 0 | 865640.77 | 0 | 0 | 0 | 0 | 865640.77 | 516437 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401750 | S112 - UID - Agamemnon Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-09 | 2016-03-15 | 2016-03-24 | 2017-01-31 | 2017-03-31 | Glasgow City | 144601 | 0 | 349619 | 2228968.03 | 18909.29 | -1267.89 | 0 | 0 | 2596228.43 | 0 | 0 | 0 | 2740829.43 | 0 | 0 | 0 | 0 | 2740829.43 | 469621 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401751 | S113 - UID - 49 Dumbarton Road (East) | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-14 | 2016-03-24 | 2017-01-31 | 2017-03-31 | Glasgow City | 104453 | 0 | 6789 | -0.21 | 0 | 1183.99 | 0 | 0 | 7972.78 | 0 | 0 | 0 | 112425.78 | 0 | 0 | 0 | 0 | 112425.78 | 590383 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401752 | S114 - UID - Opposite Lovatt Arms Public House No 2560 Dumbarton Road | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-11-28 | 2015-06-16 | 2016-03-31 | 2016-03-31 | Glasgow City | 17000 | 0 | 0 | 484 | -334.32 | 0 | 0 | 0 | 149.68 | 0 | 0 | 0 | 17149.68 | 0 | 0 | 0 | 0 | 17149.68 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401753 | S115 - UID - Junction of South Street - Edzell Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-29 | 2016-10-31 | 2017-11-30 | 2018-02-28 | Glasgow City | 45620 | 0 | 2783 | 4302.15 | 1572.04 | 517.9 | 365.78 | 0 | 9540.87 | 0 | 0 | 0 | 55160.87 | 0 | 0 | 0 | 0 | 55160.87 | 2498 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401754 | S116 - UID - Junction of South Street - Jordan Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-29 | 2016-10-31 | 2017-12-31 | 2018-03-31 | Glasgow City | 90215 | 0 | 178011 | 1500183.7 | 1821773.97 | 9711.33 | 8757.5 | 0 | 3518437.5 | 0 | 0 | 0 | 3608652.5 | 0 | 0 | 0 | 0 | 3608652.5 | 410689 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401755 | S117 - UID - Junction of South Street - Scotstoun Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-29 | 2016-05-16 | 2017-06-30 | 2017-08-31 | Glasgow City | 106896 | 0 | 117903 | 1829168.2 | 668603.98 | 440992.22 | -6884.11 | 0 | 3049783.29 | 0 | 0 | 0 | 3156679.29 | 0 | 0 | 0 | 0 | 3156679.29 | 610494 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401756 | S118 - UID - Junction of South Street and Ferryden Street (Glasgow N no 61) | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-22 | 2016-10-10 | 2017-06-30 | 2017-08-31 | Glasgow City | 19447.73 | 0 | 2972.27 | 4223 | -2848.07 | 1558.76 | 0 | 0 | 5905.96 | 0 | 0 | 0 | 25353.69 | 0 | 0 | 0 | 0 | 25353.69 | 4994 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401757 | S119 - UID - Junction of South Street - Sawmill Road | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-29 | 2016-06-29 | 2017-08-31 | 2017-10-31 | Glasgow City | 95717 | 0 | 28913 | 12776.02 | 290847.51 | 1438.96 | -630.04 | 0 | 333345.45 | 0 | 0 | 0 | 429062.45 | 0 | 0 | 0 | 0 | 429062.45 | 524390 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401759 | S121 - UID - Clydeway Expressway South of Sandyford Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | Glasgow City | 200227 | 0 | 18206 | 4337.77 | -4933.12 | 0 | 0 | 0 | 17610.65 | 0 | 0 | 0 | 217837.65 | 0 | 0 | 0 | 0 | 217837.65 | 0 | [5 empty] | N | EC10B | 100%
401762 | S124 - UID Outside No205 Finnieston Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2012-03-27 | 2015-01-05 | 2015-01-08 | 2015-01-08 | Glasgow City | 205924.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205924.99 | 0 | 0 | 0 | 0 | 205924.99 | 0 | [6 empty] | EC10B | 100%
401764 | S126 - UID Junction of Lancefield Quay - Lancefield Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2012-03-26 | 2015-01-05 | 2015-01-09 | 2015-01-09 | Glasgow City | 48327.85 | 0 | 50.63 | 0 | 0 | 0 | 0 | 0 | 50.63 | 0 | 0 | 0 | 48378.48 | 0 | 0 | 0 | 0 | 48378.48 | 0 | [5 empty] | N | EC10B | 100%
401773 | S135 - UID 237 South Street Whiteinch | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-22 | 2016-03-29 | 2017-05-31 | 2017-08-31 | Glasgow City | 170582 | 0 | 85200 | 1997602.51 | 424098.49 | 2637.69 | 0 | 0 | 2509538.69 | 0 | 0 | 0 | 2680120.69 | 0 | 0 | 0 | 0 | 2680120.69 | 743049 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401774 | S136 - UID South of Clydeside Expressway roundabout Ferry Road (GN no 40) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2011-09-30 | 2011-09-30 | 2015-05-13 | 2015-06-08 | Glasgow City | 1596.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596.22 | 0 | 0 | 0 | 0 | 1596.22 | 0 | [6 empty] | EC10B | 100%
401775 | S137 - UID Between Sawmill Road - Castlebank Crescent Castlebank Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-14 | 2016-03-24 | 2017-05-31 | 2017-08-31 | Glasgow City | 117002 | 0 | 376543 | 2489028.09 | 653666.86 | 11832.75 | -23421.03 | 0 | 3507649.67 | 0 | 0 | 0 | 3624651.67 | 0 | 0 | 0 | 0 | 3624651.67 | 947501 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401776 | S138 - UID East of Anderson Street at Castlebank Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-11 | 2016-03-16 | 2017-01-31 | 2017-03-31 | Glasgow City | 107379.23 | 0 | 766059.77 | 2117683.52 | -160315.69 | 38798.46 | 0 | 0 | 2762226.06 | 0 | 0 | 0 | 2869605.29 | 0 | 0 | 0 | 0 | 2869605.29 | 1002839 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401782 | S144 - UID - Corkerhill Road at Alness Crescent CSO Mosspark | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 696259 | 0 | -3962.11 | 1050.8 | 0 | 0 | 0 | 0 | -2911.31 | 0 | 0 | 0 | 693347.69 | 0 | 0 | 0 | 0 | 693347.69 | 0 | [5 empty] | N | EC04B | 100%
401783 | S145 - UID - Corkerhill Road at Arisaig Drive CSO Mosspark | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-16 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14953 | 0 | -1459 | -100.03 | 0 | 0 | 0 | 0 | -1559.03 | 0 | 0 | 0 | 13393.97 | 0 | 0 | 0 | 0 | 13393.97 | 0 | [5 empty] | N | EC04B | 100%
401784 | S146 - UID - 245 Corkerhill Road CSO Mosspark | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14436.08 | 0 | 99.92 | 29.67 | 0 | 0 | 0 | 0 | 129.59 | 0 | 0 | 0 | 14565.67 | 0 | 0 | 0 | 0 | 14565.67 | 0 | [5 empty] | N | EC04B | 100%
401785 | S147 - UID - Corkerhill Road at Mosspark Drive Mosspark | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14286 | 0 | -1666.93 | 0 | 0 | 0 | 0 | 0 | -1666.93 | 0 | 0 | 0 | 12619.07 | 0 | 0 | 0 | 0 | 12619.07 | 0 | [5 empty] | N | EC04B | 100%
401787 | S149 - UID - Rear Of No11 Kinnell Avenue Mosspark | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14991.74 | 0 | 100.26 | -100.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14991.74 | 0 | 0 | 0 | 0 | 14991.74 | 0 | [5 empty] | N | EC04B | 100%
401788 | S150 - UID - Burnfield Cottages Giffnock Overflow | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS7 | 2010-12-15 | 2016-09-14 | 2016-09-21 | 2017-05-31 | 2018-09-30 | East Renfrewshire | 204647 | 0 | 77586 | 800305 | 120942.32 | 27496.74 | 113.82 | 0 | 1026443.88 | 0 | 0 | 0 | 1231090.88 | 0 | 0 | 0 | 0 | 1231090.88 | 480445 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401789 | S151 - UID - 899 Aikenhead Road at Curtis Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-08-31 | 2018-10-31 | South Lanarkshire | 21093880 | 0 | 32624429.96 | 55445463.24 | 11542999.6 | 4587122.19 | 9234464.6 | 1091.96 | 113435571.55 | -1247.87 | -1247.87 | -1732.256 | 134528203.68 | -484.386 | 0 | 0 | -484.386 | 134527719.294 | 95337328 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401790 | S152 - UID - Curtis Avenue at Ardmay Crescent CSO Mount Florida | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-06-30 | 2018-10-31 | South Lanarkshire | 114680 | 0 | 0 | 0 | 0 | 0 | -1517.82 | 150.71 | -1367.11 | 0 | 0 | 0 | 113312.89 | 0 | 0 | 0 | 0 | 113312.89 | 3443 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401791 | S153 - UID - Prospecthill Road at Asda Store Entrance | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-06-30 | 2018-10-31 | South Lanarkshire | 99683 | 0 | 0 | 0 | 0 | 0 | -2026.12 | 0 | -2026.12 | 0 | 0 | 0 | 97656.88 | 0 | 0 | 0 | 0 | 97656.88 | 2474 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401792 | S154 - UID Causeyside St CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-02-29 | 2016-06-20 | 2017-11-30 | 2018-01-31 | Renfrewshire | 18662 | 0 | -3035 | 0 | 1074.82 | 15.31 | 1556.62 | 0.25 | -388 | 0 | 0 | 0 | 18274 | 0 | 0 | 0 | 0 | 18274 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401793 | S155 UID Town Centre No2 CSO South Corner of 20 Forbes Place Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-08-02 | 2016-08-03 | 2016-08-31 | 2016-10-31 | Renfrewshire | 19618 | 0 | -3963 | -3298.39 | 0 | 0 | 0 | 0 | -7261.39 | 0 | 0 | 0 | 12356.61 | 0 | 0 | 0 | 0 | 12356.61 | 0 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401794 | S156 UID Town Centre West No1 CSO Paisley Cart Walk West of Tannery Bridge Street Abbey Bridge | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-02-29 | 2016-06-20 | 2018-02-28 | 2019-08-31 | Renfrewshire | 352644.32 | 0 | 279429.93 | 1066187.75 | 1139373 | 49349 | 107347.6 | 795.4 | 2642482.68 | 0 | 0 | 0 | 2995127 | 0 | 0 | 0 | 0 | 2995127 | 3345359 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401795 | S157 UID Seedhill No1 CSO West of 6 Seedhill at Mill Street Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS3 | 2010-12-15 | 2016-09-29 | 2017-11-13 | 2021-07-06 | 2021-10-06 | Renfrewshire | 270046 | 0 | 58430 | 95533.85 | 117437.56 | 93799.15 | 522441.35 | 1888911.43 | 2776553.34 | 519586.38 | 519586.38 | 738523.5817 | 3566185.72 | 218937.2017 | 0 | -4.6566e-10 | 218937.2017 | 3785122.9217 | 1421093 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401798 | S160 UID Love Street CSO 98 New Sneddon Street Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-30 | 2014-09-09 | 2015-10-31 | 2016-01-31 | Renfrewshire | 991076 | 0 | 220182 | 2999.97 | -2271.98 | 0 | 0 | 0 | 220909.99 | 0 | 0 | 0 | 1211985.99 | 0 | 0 | 0 | 0 | 1211985.99 | 17030 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401799 | S161 UID New Sneddon St | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-30 | 2014-09-09 | 2015-10-31 | 2016-01-31 | Renfrewshire | 65129.71 | 0 | 17360.29 | 50.02 | -962.31 | 0 | 0 | 0 | 16448 | 0 | 0 | 0 | 81577.71 | 0 | 0 | 0 | 0 | 81577.71 | 4554 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401800 | S162 UID Old Sneddon Street Bridge Abercarn Bridge Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-30 | 2014-09-09 | 2015-10-31 | 2016-01-31 | Renfrewshire | 19980 | 0 | 1001 | -0.2 | -3385.85 | 0 | 0 | 0 | -2385.05 | 0 | 0 | 0 | 17594.95 | 0 | 0 | 0 | 0 | 17594.95 | 286 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401801 | S163 UID Rowan Street CSO 216 Rowan Street Paisley | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-28 | 2014-06-09 | 2015-10-31 | 2016-01-31 | Renfrewshire | 1001259 | 0 | 20674.94 | 685034.39 | -24037 | 0 | 0 | 0 | 681672.33 | 0 | 0 | 0 | 1682931.33 | 0 | 0 | 0 | 0 | 1682931.33 | 9017 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401803 | S165 UID Rear of No7 Falside Road Paisley Rear of Neilston Road CSO in DAS | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-08-26 | 2014-12-15 | 2015-07-31 | 2015-09-30 | Renfrewshire | 410628.39 | 0 | 104956.61 | 11290.12 | -2159.21 | 0 | 0 | 0 | 114087.52 | 0 | 0 | 0 | 524715.91 | 0 | 0 | 0 | 0 | 524715.91 | 28238 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401804 | S166 UID Park Road CSO Paisley No4 Park Ave | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-25 | 2014-11-28 | 2015-02-26 | 2015-03-25 | Renfrewshire | 121429 | 0 | 215 | 4619.03 | 2660.13 | 0 | 0 | 0 | 7494.16 | 0 | 0 | 0 | 128923.16 | 0 | 0 | 0 | 0 | 128923.16 | 0 | [5 empty] | N | EC04B | 100%
401817 | S179 - UID - Near River Clyde Walkway South East of Westhorn Playground | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-09 | 2014-02-12 | 2014-04-01 | 2016-03-31 | 2016-03-31 | Glasgow City | 1755444 | 0 | 786200 | 3632 | 0 | -463.56 | 0 | 0 | 789368.44 | 0 | 0 | 0 | 2544812.44 | 0 | 0 | 0 | 0 | 2544812.44 | 1054 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401819 | S181 - UID - Near junction of Kempock Street - Caimcraig Street GN No20 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-07-23 | 2013-09-02 | 2014-02-27 | 2014-03-25 | Glasgow City | 916410 | 0 | 1000 | -0.08 | 0 | -3002.06 | 0 | 0 | -2002.14 | 0 | 0 | 0 | 914407.86 | 0 | 0 | 0 | 0 | 914407.86 | 0 | [5 empty] | N | EC04B | 100%
401820 | S182 - UID - Potter Place at No9 Rattray Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-07-23 | 2013-11-29 | 2014-05-29 | 2014-10-28 | Renfrewshire | 491178 | 0 | 1537.4 | 252.56 | 0 | 0 | 0 | 0 | 1789.96 | 0 | 0 | 0 | 492967.96 | 0 | 0 | 0 | 0 | 492967.96 | 0 | [5 empty] | N | EC04B | 100%
401823 | S185 - UID - Tollcross Park at Tollcross Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-26 | 2013-03-27 | 2015-02-26 | 2015-03-31 | Glasgow City | 27630.14 | 0 | 243.82 | 0 | 0 | 0 | 0 | 0 | 243.82 | 0 | 0 | 0 | 27873.96 | 0 | 0 | 0 | 0 | 27873.96 | 0 | [5 empty] | N | EC04B | 100%
401824 | S186 - UID - Tollcross Park West of No 785 Tollcross Road GN No8 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-26 | 2013-03-27 | 2015-02-26 | 2015-03-31 | Glasgow City | 809798 | 0 | 15626.93 | 2309 | 0 | -285.5 | 0 | 0 | 17650.43 | 0 | 0 | 0 | 827448.43 | 0 | 0 | 0 | 0 | 827448.43 | 0 | [5 empty] | N | EC04B | 100%
401825 | S187 - UID - Tollcross Park at footbridge of GN No7 Leisure Centre | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-27 | 2014-03-31 | 2015-02-19 | 2015-03-27 | Glasgow City | 2052217 | 0 | 20598 | 0.28 | 0 | -191.92 | 0 | 0 | 20406.36 | 0 | 0 | 0 | 2072623.36 | 0 | 0 | 0 | 0 | 2072623.36 | 0 | [5 empty] | N | EC04B | 100%
401826 | S188 - UID - Wellshot Road at Fairburn Street | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-28 | 2013-03-28 | 2015-02-19 | 2015-03-27 | Glasgow City | 25936.31 | 0 | 13.69 | 1240.69 | 0 | -388.69 | 0 | 0 | 865.69 | 0 | 0 | 0 | 26802 | 0 | 0 | 0 | 0 | 26802 | 0 | [5 empty] | N | EC04B | 100%
401827 | S189 - UID - Opposite No4 Fairholm Street GN No6 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-28 | 2013-03-28 | 2015-02-19 | 2015-03-27 | Glasgow City | 27121 | 0 | 694 | 134.89 | 0 | -239.6 | 0 | 0 | 589.29 | 0 | 0 | 0 | 27710.29 | 0 | 0 | 0 | 0 | 27710.29 | 0 | [5 empty] | N | EC04B | 100%
401828 | S190 - UID - 186 Ardgay Street Rear of No182-186 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-12-13 | 2013-03-27 | 2013-03-27 | 2014-01-28 | 2014-03-25 | Glasgow City | 2880550 | 0 | 2087.82 | 1740.45 | 7591.22 | -7591.22 | 0 | 0 | 3828.27 | 0 | 0 | 0 | 2884378.27 | 0 | 0 | 0 | 0 | 2884378.27 | 0 | [5 empty] | N | EC04B | 33.42% | CS15 | 66.58%
401829 | S191 - UID - Storm Sewage Overflow GN No5 Culross Lane | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-07-08 | 2013-11-27 | 2014-03-12 | 2014-03-28 | Glasgow City | 369585 | 0 | 0 | 700 | 0 | -7519.52 | 0 | 0 | -6819.52 | 0 | 0 | 0 | 362765.48 | 0 | 0 | 0 | 0 | 362765.48 | 0 | [5 empty] | N | EC04B | 100%
401830 | S192 - UID - Carmyle Pumping Station River Road at Bowling Green | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-05-29 | 2014-01-06 | 2014-08-14 | 2015-03-19 | Glasgow City | 12882 | 0 | 0 | 0 | 0 | -679.5 | 0 | 0 | -679.5 | 0 | 0 | 0 | 12202.5 | 0 | 0 | 0 | 0 | 12202.5 | 0 | [5 empty] | N | EC04B | 100%
401831 | S193 - UID - Outside No19 River Road GN No83 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-05-13 | 2014-01-13 | 2014-08-14 | 2015-03-19 | Glasgow City | 897049 | 0 | 54620 | 0 | 0 | -7924.08 | 0 | 0 | 46695.92 | 0 | 0 | 0 | 943744.92 | 0 | 0 | 0 | 0 | 943744.92 | 0 | [5 empty] | N | EC04B | 100%
401832 | S194 - UID - At junction of River Road - Ardgargie Drive GN No16 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-05-15 | 2014-01-20 | 2014-08-14 | 2015-02-16 | Glasgow City | 876360 | 0 | 0 | 0 | 0 | -4073.78 | 0 | 0 | -4073.78 | 0 | 0 | 0 | 872286.22 | 0 | 0 | 0 | 0 | 872286.22 | 0 | [5 empty] | N | EC04B | 100%
401833 | S195 - UID - West of No149 Baillieston Road GN No4 | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-06-27 | 2013-06-28 | 2016-10-31 | 2016-12-31 | Glasgow City | 5747.47 | 0 | 194.82 | 70.98 | 0 | 0 | 0 | 0 | 265.8 | 0 | 0 | 0 | 6013.27 | 0 | 0 | 0 | 0 | 6013.27 | 0 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401834 | S196 - UID - Baillieston Road CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-06-26 | 2013-06-28 | 2016-10-31 | 2016-12-31 | Glasgow City | 1061129 | 0 | 5312.37 | 170340.69 | 25443.01 | 29448.98 | 0 | 0 | 230545.05 | 0 | 0 | 0 | 1291674.05 | 0 | 0 | 0 | 0 | 1291674.05 | 4525 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401835 | S197 - UID - Springhill Road Roundabout | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-09 | 2014-03-19 | 2014-03-24 | 2014-06-10 | 2015-02-04 | Glasgow City | 648671 | 0 | 27135 | 0.27 | 0 | 51000 | 0 | -0.27 | 78135 | 0 | 0 | 0 | 726806 | 0 | 0 | 0 | 0 | 726806 | 0 | [5 empty] | N | EC04B | 100%
401671 | S202 - UID - Cambuslang No.1 Pumping Station Cambuslang Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2015-04-10 | 2015-04-22 | 2015-04-29 | 2015-06-08 | Glasgow City | 150546.22 | 0 | 2025.77 | 0 | 0 | 0 | 0 | 0 | 2025.77 | 0 | 0 | 0 | 152571.99 | 0 | 0 | 0 | 0 | 152571.99 | 0 | [5 empty] | N | EC10B | 100%
401960 | S206 - UID - Corkerhill Road South of Railway Bridge CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-03-21 | 2013-05-24 | 2013-09-16 | 2014-08-11 | 2014-12-19 | Glasgow City | 418129 | 0 | -2286 | -284 | 0 | 0 | 0 | 0 | -2570 | 0 | 0 | 0 | 415559 | 0 | 0 | 0 | 0 | 415559 | 0 | [5 empty] | N | EC04B | 100%
401961 | S207 - UID - In Crossmill Avenue Opposite No. 54 CSO | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS7 | 2011-03-21 | 2016-12-20 | 2017-01-20 | 2017-08-31 | 2017-10-31 | Glasgow City | 18502 | 0 | 23413 | 85812 | 157793 | 2078.45 | -3954.3 | 0 | 265142.15 | 0 | 0 | 0 | 283644.15 | 0 | 0 | 0 | 0 | 283644.15 | 12883 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401962 | S208 - UID - Dalmarnock Bridge Overflow | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2011-03-21 | 2013-03-26 | 2017-03-29 | 2019-02-28 | 2019-03-31 | Glasgow City | 52000 | 0 | 0 | 29972 | 278718.57 | 28297 | 28188.37 | 374.06 | 365550 | 570.3 | 570.3 | 791.6735 | 418120.3 | 221.3735 | 0 | 0 | 221.3735 | 418341.6735 | 67739 | [5 empty] | Y | EC04B | 100% | [36 empty] | 1 | [30 empty] | 0
401967 | S209 - UID - Dalmarnock WWTW Storm Tank Overflow | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | MPT | OMG180 | MS5 | 2011-03-21 | 2017-12-21 | 2017-12-22 | 2019-02-28 | 2019-03-31 | Glasgow City | 60000 | 0 | 1621.48 | 616641.52 | 1944337 | 3406564 | 1894211.17 | 578624.83 | 8442000 | 103000 | 39140 | 54332.9834 | 8605000 | 15192.9834 | 0 | 0 | 15192.9834 | 8620192.9834 | 620244.29 |  |  |  |  | 5844.6758 | Y | EC04B | 38% | CM_WWNI | 62% | [34 empty] | 1 | [30 empty] | 0
401969 | S210 - UID - CSO UNKNOWN - New CSO Junction of South Street and Scotstoun Street | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2011-03-21 | 2016-03-29 | 2016-11-07 | 2017-06-30 | 2017-08-31 | Glasgow City | 43268.4 | 0 | 2070.6 | 6763.8 | -6064.8 | 1495 | -557.87 | 0 | 3706.73 | 0 | 0 | 0 | 46975.13 | 0 | 0 | 0 | 0 | 46975.13 | 6434 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
401970 | S211 - CSO new 13 Hall Street Clydebank | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2011-03-21 | 2016-03-14 | 2016-03-24 | 2017-01-31 | 2017-03-31 | Glasgow City | 31764 | 0 | -134 | -0.43 | 0 | 180.86 | 0 | 0 | 46.43 | 0 | 0 | 0 | 31810.43 | 0 | 0 | 0 | 0 | 31810.43 | 2968 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
402483 | S212 - UID - Parkhead - South West Corner of Hospital Grounds (GN No 21) Belvidere Hospital | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-11-16 | 2013-05-27 | 2013-08-19 | 2014-03-21 | 2014-03-31 | Glasgow City | 727845 | 0 | 0 | -0.1 | 0 | -5160.89 | 0 | 0 | -5160.99 | 0 | 0 | 0 | 722684.01 | 0 | 0 | 0 | 0 | 722684.01 | 0 | [5 empty] | N | EC04B | 100%
402491 | S213 - UID - Millholm Road Ejector Station | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-12-14 | 2013-05-16 | 2013-08-12 | 2014-01-10 | 2014-02-03 | Glasgow City | 2855 | 0 | 573.29 | -471.46 | 0 | 0 | 0 | 0 | 101.83 | 0 | 0 | 0 | 2956.83 | 0 | 0 | 0 | 0 | 2956.83 | 0 | [5 empty] | N | EC04B | 100%
402752 | S217 - Riverside Gardens PS EO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-06-28 | 2013-03-20 | 2013-05-20 | 2013-08-30 | 2013-11-28 | East Renfrewshire | 180757 | 0 | -141.27 | 0 | 0 | 0 | 0 | 0 | -141.27 | 0 | 0 | 0 | 180615.73 | 0 | 0 | 0 | 0 | 180615.73 | 0 | [5 empty] | N | EC04B | 100%
402753 | S218 - Polmadie Road (at Calder Street) | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS6 | 2012-06-28 | 2016-03-15 | 2016-03-22 | 2020-03-11 | 2020-03-31 | Glasgow City | 90623 | 0 | 225799 | 99356.3 | 9696.78 | 0 | 1160629.38 | 122036.54 | 1617518 | 833.3 | 833.3 | 1156.7623 | 1708974.3 | 323.4623 | 0 | 0 | 323.4623 | 1709297.7623 | 1636394 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
402830 | S220 UID Marshalls Lane PS | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2013-03-20 | 2013-03-28 | 2013-11-26 | 2014-01-30 | Renfrewshire | 96583 | 0 | 461.12 | 0 | 0 | 0 | 0 | 0 | 461.12 | 0 | 0 | 0 | 97044.12 | 0 | 0 | 0 | 0 | 97044.12 | 0 | [5 empty] | N | EC04B | 100%
402831 | S221 Piazza PS EO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2013-03-20 | 2013-03-28 | 2013-08-30 | 2013-11-25 | Renfrewshire | 93481 | 0 | -331.14 | 0 | 0 | 0 | 0 | 0 | -331.14 | 0 | 0 | 0 | 93149.86 | 0 | 0 | 0 | 0 | 93149.86 | 0 | [5 empty] | N | EC04B | 100%
402832 | S222 Park Road Storage Tank EO | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2015-03-25 | 2015-03-25 | 2015-03-25 | 2015-03-27 | Renfrewshire | 22980.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22980.29 | 0 | 0 | 0 | 0 | 22980.29 | 0 | [6 empty] | EC04B | 100%
402755 | S224 - 253 Byres Road CSO Glasgow | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | WWINF | OMG180 | MS6 | 2012-07-10 | 2017-12-20 | 2018-03-26 | 2019-03-31 | 2019-06-30 | Glasgow City | 88596.93 | 0 | 58103.29 | 23592.16 | 508965.62 | 901187 | 27555 | 1012.45 | 1520415.52 | 0 | 0 | 0 | 1609012.45 | 0 | 0 | 0 | 0 | 1609012.45 | 1127279 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
402756 | S225 - Balmoral Street Pumping Station | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2013-03-20 | 2013-03-28 | 2013-11-26 | 2014-01-21 | Glasgow City | 98331.76 | 0 | 675.03 | 0 | 0 | 0 | 0 | 0 | 675.03 | 0 | 0 | 0 | 99006.79 | 0 | 0 | 0 | 0 | 99006.79 | 0 | [5 empty] | N | EC10B | 100%
402757 | S226 - In grounds of Corpus Christi Primary School (No 44on Glasgow N List) Alderman Rd | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-27 | 2015-06-29 | 2015-10-31 | 2016-01-31 | Glasgow City | 161661 | 0 | 199818 | 1358.71 | -1506.28 | 0 | 0 | 0 | 199670.43 | 0 | 0 | 0 | 361331.43 | 0 | 0 | 0 | 0 | 361331.43 | 295069 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
402758 | S227 - At junction of Alderman Road and (GN no 52) Hermitage Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-27 | 2015-08-07 | 2015-12-31 | 2016-01-31 | Glasgow City | 219495 | 0 | 324824 | 908.73 | 147.24 | 0 | 0 | 0 | 325879.97 | 0 | 0 | 0 | 545374.97 | 0 | 0 | 0 | 0 | 545374.97 | 396268 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
402759 | S228 - Strauss Avenue CSO South of No.16 Clydebank | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-27 | 2015-06-18 | 2015-10-31 | 2016-01-31 | West Dunbartonshire | 154731 | 0 | 194867.75 | 6.59 | -69.25 | 0 | 0 | 0 | 194805.09 | 0 | 0 | 0 | 349536.09 | 0 | 0 | 0 | 0 | 349536.09 | 221953 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
402760 | S229 - 193 Durban Avenue CSO Mountblow | Q&S3B | Completion | OMG180 |  |  | Wastewater | SEPA | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-26 | 2015-05-18 | 2015-10-31 | 2016-01-31 | West Dunbartonshire | 144915 | 0 | 265170.34 | 1647.6 | -301.32 | 0 | 0 | 0 | 266516.62 | 0 | 0 | 0 | 411431.62 | 0 | 0 | 0 | 0 | 411431.62 | 326098 | [5 empty] | Y | EC10B | 100% | [36 empty] | 1 | [30 empty] | 0
402833 | S233 UID Glencorse St at the junction of Abbeyhill St Glasgow | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2014-12-22 | 2015-01-12 | 2015-03-30 | 2015-03-31 | Glasgow City | 818636.97 | 0 | 167645.96 | 2436.75 | -305.5 | 0 | 0 | 0 | 169777.21 | 0 | 0 | 0 | 988414.18 | 0 | 0 | 0 | 0 | 988414.18 | 0 | [5 empty] | N | EC04B | 100%
402834 | S234 UID Cranhill SO Cranhill Park Edinburgh Road | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2014-10-31 | 2014-11-06 | 2015-02-19 | 2015-03-23 | Glasgow City | 499757.51 | 0 | 131962.49 | -123.67 | 0 | 0 | 0 | 0 | 131838.82 | 0 | 0 | 0 | 631596.33 | 0 | 0 | 0 | 0 | 631596.33 | 0 | [5 empty] | N | EC04B | 100%
403140 | S236 - Dalmuir GSS Strategic Solution | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-12-18 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2015-04-30 | Glasgow City | 2239336.14 | 0 | 1650.48 | 0 | 0 | 0 | 0 | 0 | 1650.48 | 0 | 0 | 0 | 2240986.62 | 0 | 0 | 0 | 0 | 2240986.62 | 0 | [5 empty] | N | EC10B | 100%
403362 | S237 - UID - Monteith Drive WWPS Stamperland | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-03-18 | 2013-05-16 | 2013-10-21 | 2014-01-17 | 2014-03-20 | Glasgow City | 82514 | 0 | -3298.09 | 198.8 | 0 | 0 | 0 | 0 | -3099.29 | 0 | 0 | 0 | 79414.71 | 0 | 0 | 0 | 0 | 79414.71 | 0 | [5 empty] | N | EC04B | 100%
403474 | S238 - UID - Junction of South Street and Dilwara Avenue | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-05-13 | 2014-08-29 | 2014-09-01 | 2014-09-03 | 2014-10-27 | Glasgow City | 9904.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9904.75 | 0 | 0 | 0 | 0 | 9904.75 | 0 | [6 empty] | EC10B | 100%
403564 | S239 - UID - Kelvinside K15 Sth Bnk Hamilton Dr Lane | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-08-27 | 2014-11-28 | 2014-12-03 | 2015-01-12 | 2015-02-27 | Glasgow City | 17536 | 0 | 7714 | -4718.24 | 0 | 0 | 0 | 0 | 2995.76 | 0 | 0 | 0 | 20531.76 | 0 | 0 | 0 | 0 | 20531.76 | 0 | [5 empty] | N | EC10B | 100%
403689 | S240 - UID - City Centre Bell St East-sptmth Cso | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2014-01-30 | 2014-07-22 | 2014-08-11 | 2014-08-28 | 2014-10-27 | Glasgow City | 16261 | 0 | 1031.62 | 0 | 0 | 0 | 0 | 0 | 1031.62 | 0 | 0 | 0 | 17292.62 | 0 | 0 | 0 | 0 | 17292.62 | 0 | [5 empty] | N | EC04B | 100%
404009 | S241 - UID - Renfrew Haining Road CSO (Remedial works) | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2014-11-27 | 2015-02-27 | 2017-06-15 | 2017-05-18 | 2017-05-18 | Renfrewshire | 191106 | 0 | 618.08 | 6300 | -1381.27 | 0 | 0 | 0 | 5536.81 | 0 | 0 | 0 | 196642.81 | 0 | 0 | 0 | 0 | 196642.81 | 0 | [5 empty] | N | EC10B | 100%
502608 | Safety Review of Structural Plastic Media Filters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-10-31 | 2018-08-30 | 2018-10-26 | 2019-07-12 |  | Scottish Water Wide | 0 | 0 | 0 | 1555.14 | 90171.95 | 120274.29 | 27978.86 | 0 | 239980.24 | 0 | 0 | 0 | 239980.24 | 0 | 0 | 0 | 0 | 239980.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508757 | SAGIS Modelling Resource WW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS2 | 2020-10-13 | 2020-11-10 | 2021-08-02 | 2022-01-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88931 | 88931 | 111069.3 | 0 | 0 | 200000.3 | 0 | 0 | 0 | 0 | 200000.3 | 122419.09 | [5 empty] | N | SG1 | 100%
503371 | Saline WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-05-13 | 2028-03-21 | 2028-07-24 | 2029-01-12 |  | Fife | 0 | 0 | 0 | 0 | 0 | 77497.49 | 5050.47 | 0.04 | 82548 | 0 | 0 | 0 | 82548 | 0 | 0 | 0 | 0 | 82548 | 122419.09 | [5 empty] | N | SG1 | 100%
30737 | Salsburgh STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-08 | 2012-01-24 | 2012-06-11 | 2013-06-20 | 2013-07-12 | North Lanarkshire | 2346209.8 | 0 | -3846.6 | 0 | 0 | 0 | 0 | 0 | -3846.6 | 0 | 0 | 0 | 2342363.2 | 0 | 0 | 0 | 0 | 2342363.2 | 176884.68 | [5 empty] | N | CM_WWNI | 20% | EC04A | 20% | EC10B | 25% | EC10A | 35%
403547 | Saltcoats and Ardrossan BW Repair Sewerage System and Removal Cross Connections Scoping of Costs | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-23 | 2015-02-16 | 2015-04-22 | 2015-06-18 | 2015-06-18 | North Ayrshire | 134499 | 0 | 5450.97 | 0 | 0 | 0 | 0 | 0 | 5450.97 | 0 | 0 | 0 | 139949.97 | 0 | 0 | 0 | 0 | 139949.97 | 0 | [5 empty] | N | EC16A | 100%
501653 | SALTCOATS CANAL PL WWPS NS252413 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-07-19 | 2018-03-29 | 2018-08-27 | 2020-03-03 |  | North Ayrshire | 0 | 0 | 0 | 45064 | 402621 | 2392014 | 359763.56 | 48157.88 | 3247620.44 | 0 | 0 | 0 | 3247620.44 | 0 | 0 | 0 | 0 | 3247620.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402938 | Saltcoats SPS - Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-10-30 | 2015-02-13 | 2015-01-15 | 2015-01-16 |  | North Ayrshire | 46432 | 0 | -1200.52 | 0 | 0 | 0 | 0 | 0 | -1200.52 | 0 | 0 | 0 | 45231.48 | 0 | 0 | 0 | 0 | 45231.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511870 | Saltcoats WWPS - Capital Maintenance project. | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2024-03-04 | 2025-09-10 | 2025-12-09 | 2026-11-16 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000.04 | 0 | 0 | 2000000.04 | 0 | 0 | 0 | 0 | 2000000.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503445 | Sample Tap Replacement- Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2019-01-23 | 2019-01-23 | 2019-06-17 | 2020-04-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 26228.66 | 211200.51 | 218.02 | 237647.18 | 0 | 0 | 0 | 237647.18 | 0 | 0 | 0 | 0 | 237647.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500952 | SAN Decommissioning | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-12 | 2015-12-14 | 2015-12-14 | 2016-08-11 |  | Scottish Water Wide | 0 | 0 | 59841 | 46252.81 | 0 | 0 | 0 | 0 | 106093.81 | 0 | 0 | 0 | 106093.81 | 0 | 0 | 0 | 0 | 106093.81 | 306661.32 | [5 empty] | N | CM_M&G | 100%
45809 | Sand Street SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2012-07-09 | 2012-12-03 | 2013-03-25 | 2013-03-26 | Na H-Eileanan an Iar | 511272.82 | 0 | -1112.93 | 142.84 | 0 | 0 | 0 | 0 | -970.09 | 0 | 0 | 0 | 510302.73 | 0 | 0 | 0 | 0 | 510302.73 | 28761.13 | [5 empty] | N | WQ01C | 100%
500871 | Sanday Orkney RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-20 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Orkney Islands | 0 | 0 | 1866.84 | 3808.48 | 7110 | -7021.6 | 0 | 0 | 5763.72 | 0 | 0 | 0 | 5763.72 | 0 | 0 | 0 | 0 | 5763.72 | 131809.89 | [5 empty] | N | DW5FS | 100%
501258 | Sanday WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water | DWQR | NONINF | Water Non infrastructure | MS4 | 2016-07-29 | 2018-02-28 | 2018-04-26 |  |  | Orkney Islands | 0 | 0 | 2924.96 | 74994.65 | 192461.77 | 268030.77 | 829115.85 | 288058 | 1655586 | 0 | 0 | 0 | 1655586 | 0 | 0 | 169988 | 169988 | 1825574 | 119022.58 | [5 empty] | Y | CM_WSNI | 100% | [67 empty] | 0
501211 | Sanday WTW - QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS0 | 2019-09-30 | 2021-10-25 | 2022-08-16 | 2023-05-29 | 2023-08-22 | Orkney Islands | 0 | 0 | 5860.47 | 417.88 | 5605.82 | 108269.1 | 253669.66 | -18738.05 | 355084.88 | 3286085.63 | 3286085.63 | 4561646.2963 | 3641170.51 | 1275560.6663 | 0 | 0 | 1275560.6663 | 4916731.1763 | 98738.75 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
501539 | Sandbank SR Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2028-10-16 | 2029-08-24 | 2029-12-28 | 2030-08-14 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286838.03 | 0 | 0 | 286838.03 | 0 | 0 | 0 | 0 | 286838.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402989 | Sandend Caravan Park Seaview Road Sandend Banff | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2012-12-04 | 2013-02-25 | 2013-10-31 | 2013-10-31 | Aberdeenshire | 82983 | 0 | -955.58 | 0 | 0 | 0 | 0 | 0 | -955.58 | 0 | 0 | 0 | 82027.42 | 0 | 0 | 0 | 0 | 82027.42 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
503261 | Sandhead WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-14 | 2029-06-15 | 2030-06-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 87156.36 | 3340.85 | 26498.79 | 116996 | 0 | 0 | 0 | 116996 | 0 | 0 | 0 | 0 | 116996 | 122419.09 | [5 empty] | N | SG1 | 100%
503407 | Sandhead WwTW CSO | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2027-04-01 | 2027-04-29 | 2027-05-20 | 2028-01-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395999.97 | 0 | 0 | 395999.97 | 0 | 0 | 0 | 0 | 395999.97 | 2831984.65 | [5 empty] | N | CM_M&G | 18.75% | CM_WWNI | 37.5% | CM_WWI | 43.75%
502311 | Sandy Loch WOA Bressay WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-14 | 2028-03-02 | 2028-03-10 | 2029-01-22 |  | Shetland Islands | 0 | 0 | 0 | 7599 | 1761 | 439 | -1029.87 | 10908.99 | 19678.12 | 1099821.88 | 0 | 0 | 1119500 | 0 | 0 | 0 | 0 | 1119500 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500018 | Sandy Loch WOA Bressay WSZ - 5000180000 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-04 | 2016-06-17 | 2016-06-20 | 2016-06-23 |  | Shetland Islands | 0 | 0 | 28198 | -11247.84 | 6161.24 | 0 | 0 | 0 | 23111.4 | 0 | 0 | 0 | 23111.4 | 0 | 0 | 0 | 0 | 23111.4 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500087 | Sandy Loch WOA Quarff WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-03-13 | 2016-06-17 | 2016-07-27 | 2016-07-12 |  | Shetland Islands | 0 | 0 | 15268.37 | -9407.2 | 5115.33 | 0 | 0 | 0 | 10976.5 | 0 | 0 | 0 | 10976.5 | 0 | 0 | 0 | 0 | 10976.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500086 | Sandy Loch WOA Sandy Loch Lower CWT WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-03-13 | 2016-08-30 | 2016-10-13 | 2017-06-21 |  | Shetland Islands | 0 | 0 | 24797 | 107380.1 | 12320.08 | 4798.05 | -16001.08 | 0 | 133294.15 | 0 | 0 | 0 | 133294.15 | 0 | 0 | 0 | 0 | 133294.15 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501067 | Sandy Loch WOA Scalloway Re-Chlor WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2016-04-06 | 2024-05-31 | 2024-07-12 | 2026-06-11 |  | Shetland Islands | 0 | 0 | 94092 | -31736 | 50644 | 76644.9 | 4304.93 | 981.07 | 194930.9 | 0.01 | 0 | 0 | 194930.91 | 0 | 0 | 0 | 0 | 194930.91 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501066 | Sandy Loch WOA Sumburgh WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 |  | Shetland Islands | 0 | 0 | 26770.15 | -26770.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
500958 | Sandy Loch WTW Additional RGF - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-09-11 | 2018-05-31 | 2018-07-30 | 2021-07-08 |  | Shetland Islands | 0 | 0 | 31155 | 141879.91 | 170683.81 | 514217.51 | 920967.78 | 492502.14 | 2271406.14 | 60080 | 0 | 0 | 2331486.14 | 0 | 0 | 308792.86 | 308792.86 | 2640279 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500872 | Sanna RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-08-03 | 2018-08-29 | 2018-11-27 | 2019-03-31 | 2019-08-31 | Highland | 0 | 0 | 544.89 | 2224.49 | 2000 | 22298.49 | 7574.36 | -5367.57 | 29274.66 | 0 | 0 | 0 | 29274.66 | 0 | 0 | 0 | 0 | 29274.66 | 9822.09 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 3.73 | [43 empty] | 0
502624 | Sanna WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-08 | 2020-04-06 | 2020-04-06 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 20930.23 | 520.75 | 1385.35 | 8661.31 | -28219.15 | 3278.49 | 0 | 0 | 0 | 3278.49 | 0 | 0 | 0 | 0 | 3278.49 | 122419.09 | [5 empty] | N | WG1 | 100%
503219 | Sauchen WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-09-30 | 2022-08-24 | 2022-11-17 | 2023-11-14 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 83105.48 | 26547.58 | 58417.94 | 168071 | 1364263.17 | 0 | 0 | 1532334.17 | 0 | 0 | 0 | 0 | 1532334.17 | 122419.09 | [5 empty] | N | SG1 | 100%
500841 | Savalbeg RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2016-02-23 | 2016-03-28 | 2017-02-28 | 2018-04-30 | Highland | 0 | 0 | 14190 | 36371.91 | 18098.24 | 18743.05 | -17848.29 | 0 | 69554.91 | 0 | 0 | 0 | 69554.91 | 0 | 0 | 0 | 0 | 69554.91 | 147274.07 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 46.12 | [43 empty] | 0
502281 | Savalbeg WTW Sludge Lagoon Upgrade | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater | SEPA | SWMD | Sludge | MS3 | 2017-06-27 | 2019-02-28 | 2019-12-12 | 2021-11-19 | 2022-02-11 | Highland | 0 | 0 | 0 | 20223.16 | 12546.72 | 49851.04 | 68579.98 | 72492.1 | 223693 | 346126.49 | 346126.49 | 572801.4275 | 569819.49 | 226674.9375 | 0 | 0 | 226674.9375 | 796494.4275 | 290443.35 | [5 empty] | Y | LA01 | 100% | [41 empty] | 1 | [25 empty] | 0
45715 | Savalbeg WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-07-18 | 2012-03-01 | 2012-03-30 | Highland | 83209.32 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 83236.32 | 0 | 0 | 0 | 0 | 83236.32 | 28761.13 | [5 empty] | N | DW13 | 100%
402945 | Scalpay Street Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-10-01 | 2014-08-28 | 2014-09-18 | 2015-01-28 | 2015-01-28 | Glasgow City | 626693 | 626693 | 45583 | -1238.03 | -3965.49 | 0 | 0 | 0 | 40379.48 | 0 | 0 | 0 | 667072.48 | 0 | 0 | 0 | 0 | 667072.48 | 180449.74 | [5 empty] | N | FL_DD | 100%
502353 | Scientific - FOP - Additional Equipment for WW Regulatory Sampling | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-11-08 | 2016-11-08 | 2016-12-01 | 2020-08-27 |  | Scottish Water Wide | 0 | 0 | 0 | 252242.41 | 0 | 35863.2 | -426 | 0 | 287679.61 | 0 | 0 | 0 | 287679.61 | 0 | 0 | 0 | 0 | 287679.61 | 306661.32 | [5 empty] | N | CM_M&G | 100%
500489 | Scientific Instrument Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-05 | 2021-06-30 |  | Scottish Water Wide | 0 | 0 | 1110480 | 537819 | 422903 | 973286 | 280441.27 | 699661.73 | 4024591 | 0 | 0 | 0 | 4024591 | 0 | 0 | 0 | 0 | 4024591 | 613322.63 | [5 empty] | N | CM_M&G | 100%
511683 | Scientific Replacement Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS1 | 2021-03-24 | 2021-04-26 | 2021-04-27 | 2022-06-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197900 | 0 | 0 | 1197900 | 0 | 0 | 0 | 0 | 1197900 | 613322.63 | [5 empty] | N | CM_M&G | 100%
400606 | Scientific Services Capital Replacement Programme Chemistry | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-29 | 2011-01-13 | 2011-05-02 | 2015-11-10 |  | Scottish Water Wide | 956683 | 0 | -4390.95 | 871.25 | 0 | 0 | 0 | 0 | -3519.7 | 0 | 0 | 0 | 953163.3 | 0 | 0 | 0 | 0 | 953163.3 | 613322.63 | [5 empty] | N | CM_M&G | 100%
400607 | Scientific Services Capital Replacement Programme Micro Crypto - Sampling | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-31 | 2011-01-13 | 2011-05-02 | 2015-11-10 |  | Scottish Water Wide | 895136.6 | 0 | 38255.6 | 0 | 0 | 0 | 0 | 0 | 38255.6 | 0 | 0 | 0 | 933392.2 | 0 | 0 | 0 | 0 | 933392.2 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503380 | Scone WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-08-16 | 2025-06-13 | 2025-09-29 | 2026-10-14 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 79058.58 | 14999.37 | 0.05 | 94058 | 0 | 0 | 0 | 94058 | 0 | 0 | 0 | 0 | 94058 | 122419.09 | [5 empty] | N | SG1 | 100%
502868 | Scotland Terrace SPS Newburgh - SR15 CM | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS0 | 2020-02-28 | 2022-05-11 | 2022-08-15 | 2023-09-01 | 2023-12-04 | Fife | 0 | 0 | 0 | 0 | 34014.48 | 16801.35 | 8907.3 | 29596.88 | 89320 | 692763.39 | 0 | 0 | 782083.39 | 0 | 0 | 0 | 0 | 782083.39 | 0 | [5 empty] | N | SR21_WW | 100%
400061 | Scotland Wide Borehole Inspection Programme | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-12-07 | 2010-11-05 | 2011-01-26 | 2016-03-22 |  | Scottish Water Wide | 1014081.54 | 0 | 82778.69 | -31127.98 | 662.28 | 0 | 0 | 0 | 52312.99 | 0 | 0 | 0 | 1066394.53 | 0 | 0 | 0 | 0 | 1066394.53 | 119022.58 | [5 empty] | N | CM_WSI | 100%
500930 | Scottish Borders Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-01-31 | 2017-01-31 | 2016-12-16 | 2017-01-31 | Scottish Borders | 0 | 0 | 5927.7 | 1778.05 | 0 | 0 | 0 | 0 | 7705.75 | 0 | 0 | 0 | 7705.75 | 0 | 0 | 0 | 0 | 7705.75 | 106252.93 | [5 empty] | N | FL_DD | 100%
45413 | Scottish Water Bylaws | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-21 | 2010-06-28 | 2013-01-28 | 2016-04-01 | Scottish Water Wide | 3815887.15 | 0 | -506.11 | 0 | 0 | 0 | 0 | 0 | -506.11 | 0 | 0 | 0 | 3815381.04 | 0 | 0 | 0 | 0 | 3815381.04 | 28761.13 | [5 empty] | N | DW11 | 100%
9617 | SCOTTISH WATER PROPERTY RATIONALISATION (Receipt Funded) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 |  | 2004-03-24 | 2005-03-31 | 2006-03-31 |  | Scottish Water Wide | 3841386.28 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 3841525.28 | 0 | 0 | 0 | 0 | 3841525.28 | 306661.32 | [5 empty] | N | SM3 | 100%
509741 | Scotwood CSO Outlet Sewer Busby | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-05-23 | 2023-11-20 | 2024-03-04 | 2025-01-20 | 2025-01-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17024.04 | 17024.04 | 482660.66 | 0 | 0 | 499684.7 | 0 | 0 | 0 | 0 | 499684.7 | 0 | [5 empty] | N | SR21_WW | 100%
500873 | Scourie RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-08-29 | 2018-08-29 | 2018-11-27 | 2019-03-31 | 2019-08-31 | Highland | 0 | 0 | 564.92 | 1604.84 | 757.24 | 14833.16 | 7030.1 | -2941.54 | 21848.72 | 0 | 0 | 0 | 21848.72 | 0 | 0 | 0 | 0 | 21848.72 | 12673.9 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 4.26 | [43 empty] | 0
500629 | SCSP Business Improvement SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 698481.79 | 1609278.26 | 1594575.75 | 1448356.46 | 327790.89 | 339293.62 | 6017776.77 | 0 | 0 | 0 | 6017776.77 | 0 | 0 | 0 | 0 | 6017776.77 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500628 | SCSP Development Management SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 254433.96 | 747731.44 | 1683188.34 | 1934990.32 | -4620344.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_OVH | 100%
500627 | SCSP Director of SCSP SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 111843.89 | 154129.87 | 104825.89 | 483156.79 | 72913.01 | 0 | 926869.45 | 0 | 0 | 0 | 926869.45 | 0 | 0 | 0 | 0 | 926869.45 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500626 | SCSP Strategic & Economic Regulation SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 345933.08 | 380937.92 | 1156929.2 | 1272922.78 | 3076.64 | 3003.52 | 3162803.14 | 0 | 0 | 0 | 3162803.14 | 0 | 0 | 0 | 0 | 3162803.14 | 306661.32 | [5 empty] | N | CM_OVH | 100%
403016 | SCVW North Berwick WWTW - Scada replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2012-11-30 | 2013-09-30 | 2013-11-04 | 2018-03-02 |  | Scottish Borders | 375274 | 0 | 42500 | 79941.88 | 386399.12 | 8000 | 0 | 0 | 516841 | 0 | 0 | 0 | 892115 | 0 | 0 | 0 | 0 | 892115 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500668 | SE 543 John St Dalbeattie | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-02-21 | 2020-02-28 | 2020-03-04 | 2020-03-30 | 2021-04-01 | Dumfries and Galloway | 0 | 0 | 56912 | 27890.84 | 54138.04 | 31293.12 | -170233 | 31020.71 | 31021.71 | 0 | 0 | 0 | 31021.71 | 0 | 0 | 0 | 0 | 31021.71 | 180449.74 | [5 empty] | N | FL_DD | 100%
500011 | SE 843 - Easter Street Duns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2020-02-13 | 2020-02-13 | 2020-02-13 | 2019-12-19 | 2021-04-01 | Scottish Borders | 0 | 0 | 44707 | -40777.53 | 12070.53 | 129000 | 123433.21 | 0 | 268433.21 | 0 | 0 | 0 | 268433.21 | 0 | 0 | 0 | 0 | 268433.21 | 282366.25 | [5 empty] | N | FL_NAMED | 100%
403236 | SE15 ES - E014 Dukes Road CSO | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2013-01-23 | 2016-03-22 | 2016-05-13 | 2016-12-21 | 2017-03-14 | South Lanarkshire | 110784 | 110784 | 454700 | 2086522.01 | 32985.99 | 15884 | -33555.87 | 0 | 2556536.13 | 0 | 0 | 0 | 2667320.13 | 0 | 0 | 0 | 0 | 2667320.13 | 708517.15 | [5 empty] | N | EC01F | 45% | FL_DD | 55%
500654 | SE246 - Burnswark View Eaglesfield | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater | SW | WWINF | Flooding Demand Driven | MS2 | 2018-07-09 | 2020-03-23 | 2021-05-10 | 2022-01-13 | 2022-01-13 | Dumfries and Galloway | 0 | 0 | 80610 | 27390 | 23558.38 | 104352.62 | 248083.06 | 115569.94 | 599564 | 416294.45 | 442709 | 442709 | 1015858.45 | 0 | 0 | 26414.55 | 26414.55 | 1042273 | 180449.74 | [5 empty] | N | FL_DD | 100%
502582 | SE570 - High St & North Bridge St Hawick | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-03-31 | 2020-04-01 | 2020-04-01 | 2020-05-01 | 2021-04-01 | Scottish Borders | 0 | 0 | 0 | 44060.47 | 11939.53 | 31000 | -87000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | FL_DD | 100%
502581 | SE609 - George St Innerleithen | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-08-25 | 2022-01-03 | 2022-03-07 | 2023-01-20 | 2023-04-24 | Scottish Borders | 0 | 0 | 0 | 43060.47 | 4938.53 | 61481.34 | 43721.09 | 47210.57 | 200412 | 1339588 | 0 | 0 | 1540000 | 0 | 0 | 0 | 0 | 1540000 | 175086.76 | [5 empty] | N | FL_DD | 100%
502583 | SE842 - Sunnyside Duns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-07-18 | 2019-07-18 | 2019-07-18 | 2019-06-12 | 2019-06-12 | Scottish Borders | 0 | 0 | 0 | 43060.47 | 13939.53 | 36000 | -4931.87 | 0 | 88068.13 | 0 | 0 | 0 | 88068.13 | 0 | 0 | 0 | 0 | 88068.13 | 175086.76 | [5 empty] | N | FL_DD | 100%
500652 | SE847 Church Street Harbour Road Eyemouth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-03-14 | 2020-02-20 | 2020-03-23 | 2021-09-13 | 2021-09-13 | Scottish Borders | 0 | 0 | 77062 | 86857.1 | 102921.71 | 240277.19 | 1217130 | 1058402 | 2782650 | 649848.23 | 967350 | 967350 | 3432498.23 | 0 | 0 | 317501.77 | 317501.77 | 3750000 | 180449.74 |  |  |  |  | 4800 | N | FL_DD | 100%
507443 | Seafield PFI WwTW SR21 Sludge Treatment Assets/ Odour Improvement | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2021-11-08 | 2023-05-17 | 2023-08-15 | 2024-07-22 | 2024-07-23 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133883.3 | 133883.3 | 1866116.7 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | [5 empty] | N | SR21_WW | 100%
502229 | Seafield Pumping Station - New Build | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2019-08-26 | 2019-09-19 | 2019-09-19 | 2019-09-19 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 248748.39 | 0 | 248748.39 | 0 | 0 | 0 | 248748.39 | 0 | 0 | 0 | 0 | 248748.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403549 | Seamill BW UID Summerlea Road CSO and Removal of Flooding Manholes Adjacent to Kilbride Burn | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-23 | 2017-08-03 | 2017-07-19 | 2017-02-03 | 2017-07-31 | North Ayrshire | 53726 | 0 | 12272 | 25829.05 | -3151.75 | 0 | 0 | 0 | 34949.3 | 0 | 0 | 0 | 88675.3 | 0 | 0 | 0 | 0 | 88675.3 | 0 | [5 empty] | N | EC16A | 100%
500683 | SEATON WWPS WWPS 1988 NJ949085 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-06-03 | 2016-03-01 | 2016-05-31 | 2017-02-10 |  | Aberdeen City | 0 | 0 | 85178.25 | 153604.75 | 20995 | -7541 | 0 | 0 | 252237 | 0 | 0 | 0 | 252237 | 0 | 0 | 0 | 0 | 252237 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500594 | Security & End User Programme Governance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-03-14 | 2016-09-09 | 2016-09-09 | 2021-03-02 |  | Scottish Water Wide | 0 | 0 | 169798 | 190517.85 | 163053.01 | 78768.54 | -9671.12 | -3.03 | 592463.25 | 0 | 0 | 0 | 592463.25 | 0 | 0 | 0 | 0 | 592463.25 | 613322.63 | [5 empty] | N | CM_M&G | 100%
404035 | Security Enhancement at 3 WTWs | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2015-02-03 | 2015-09-08 | 2015-09-21 | 2016-03-23 | 2016-03-23 | Scottish Water Wide | 13813.01 | 0 | 2772140.99 | 376570 | 2229.48 | 78.75 | 0 | 0 | 3151019.22 | 0 | 0 | 0 | 3164832.23 | 0 | 0 | 0 | 0 | 3164832.23 | 119022.58 | [5 empty] | N | CM_WSNI | 48% | DW9A | 52%
500990 | Security Improvements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-11-17 | 2016-09-21 | 2016-09-21 | 2020-07-21 |  | Scottish Water Wide | 0 | 0 | 200064 | 2211188.52 | 599023.99 | 493120.83 | -298381.81 | -22093.88 | 3182921.66 | 0 | 0 | 0 | 3182921.66 | 0 | 0 | 0 | 0 | 3182921.66 | 306661.32 | [5 empty] | N | CM_M&G | 100%
404034 | Security improvements at Water Assets | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2015-02-27 | 2015-09-24 | 2015-11-09 | 2018-03-29 | 2018-03-29 | Scottish Water Wide | 9088 | 0 | 337398 | 1064498.59 | -251032.1 | 0 | 3027.13 | -19146.71 | 1134744.91 | 0 | 0 | 0 | 1143832.91 | 0 | 0 | 0 | 0 | 1143832.91 | 0 | [5 empty] | N | DW9A | 100%
501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWD | SEMD | MS7 | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 8000 | 3007.49 | 11168.13 | 0 | 0 | 0 | 22175.62 | 0 | 0 | 0 | 22175.62 | 0 | 0 | 0 | 0 | 22175.62 | 78123.85 | [5 empty] | N | DW9F | 100%
501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWMD | SEMD | MS6 | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-29 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 95883 | 179559.77 | 1111586.81 | 8418.51 | -262.41 | 332.32 | 1395518 | 68.2 | 68.2 | 94.6732 | 1395586.2 | 26.4732 | 0 | 0 | 26.4732 | 1395612.6732 | 78123.85 | [5 empty] | N | DW9F | 100%
501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWMD | SEMD | MS6 | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-17 | 2019-03-29 | Scottish Water Wide | 0 | 0 | 0 | 36386.12 | 261448.1 | 333655.96 | 3231.04 | 1158.78 | 635880 | 1346.04 | 1346.04 | 1868.5327 | 637226.04 | 522.4927 | 0 | 0 | 522.4927 | 637748.5327 | 78123.85 | [5 empty] | N | DW9F | 100%
501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWMD | SEMD | MS6 | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-08-16 | 2020-01-15 | Scottish Water Wide | 0 | 0 | 0 | 17790.14 | 298445.85 | 1506511.65 | 218023.79 | 3238.57 | 2044010 | 2649.8 | 2494.2868 | 3462.4948 | 2046659.8 | 968.208 | 0 | 0 | 968.208 | 2047628.008 | 389360.63 | [5 empty] | N | SR15_CMA_WSI | 5.869% | DW9F | 94.13%
501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWMD | SEMD | MS6 | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-09-24 | 2020-12-18 | Scottish Water Wide | 0 | 0 | 0 | 65391.05 | 65357.95 | 284295.52 | 1698991.29 | 130067.19 | 2244103 | 5365.45 | 5190.6911 | 7205.5629 | 2249468.45 | 2014.8718 | 0 | 0 | 2014.8718 | 2251483.3218 | 389360.63 | [5 empty] | N | SR15_CMA_WSI | 3.257% | DW9F | 96.74%
402766 | Security of Supply Resource | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2012-06-12 | 2012-06-12 | 2012-07-02 | 2017-06-26 |  | Scottish Water Wide | 31837 | 0 | 964 | 0.02 | -1882.99 | 0 | 0 | 0 | -918.97 | 0 | 0 | 0 | 30918.03 | 0 | 0 | 0 | 0 | 30918.03 | 0 | [5 empty] | N | DW9A | 100%
402626 | Security Review Risk Mitigation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-07-13 | 2012-10-25 | 2012-10-25 | 2015-03-23 |  | Scottish Water Wide | 372475.24 | 0 | 1462.5 | 0 | 0 | 0 | 0 | 0 | 1462.5 | 0 | 0 | 0 | 373937.74 | 0 | 0 | 0 | 0 | 373937.74 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500703 | SEPA Compliance Assessment Scheme - WW Networks | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater | SEPA | SWMD | Compliance Assessment Scheme | MS7 | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2016-08-22 | 2017-03-15 | Scottish Water Wide | 0 | 0 | 18717 | 8318.02 | 0 | 0 | 0 | 0 | 27035.02 | 0 | 0 | 0 | 27035.02 | 0 | 0 | 0 | 0 | 27035.02 | 172763.29 | [5 empty] | N | WQ01E | 100%
501622 | SEPA Compliance Assessment Scheme - WW Networks - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater | SEPA | SWMD | Compliance Assessment Scheme | MS7 | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-15 | Scottish Water Wide | 0 | 0 | 886 | 34841.12 | 10591.94 | -3701.53 | 0 | 214.45 | 42831.98 | 0 | 0 | 0 | 42831.98 | 0 | 0 | 0 | 0 | 42831.98 | 172763.29 | [5 empty] | N | WQ01E | 100%
500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater | SEPA | SWMD | Compliance Assessment Scheme | MS7 | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2016-12-06 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 20910 | 47724.9 | 410.1 | 0 | 0 | 0 | 69045 | 0 | 0 | 0 | 69045 | 0 | 0 | 0 | 0 | 69045 | 207623.13 | [5 empty] | N | WQ01D | 100%
501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater | SEPA | SWMD | Compliance Assessment Scheme | MS6 | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2020-03-30 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 3395.51 | 47007.8 | 528530.82 | 580214.06 | 670346.99 | 11538.82 | 1841034 | 965.53 | 965.53 | 1340.32 | 1841999.53 | 374.79 | 0 | 0 | 374.79 | 1842374.32 | 207623.13 | [5 empty] | N | WQ01D | 100%
509528 | SEPA Database Replacement project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2020-11-16 | 2020-12-07 | 2020-12-07 | 2021-04-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552829 | 552829 | 0 | 0 | 0 | 552829 | 0 | 0 | 0 | 0 | 552829 | 613322.63 | [5 empty] | N | CM_M&G | 100%
404116 | Service Contract for Maintenance of Water Resources CAR Licence Monitoring Equipment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-03-18 | 2015-03-18 | 2015-03-18 | 2017-04-06 |  | Scottish Water Wide | 49974 | 0 | -48389.36 | 124839.62 | -12526.25 | 0 | 0 | 0 | 63924.01 | 0 | 0 | 0 | 113898.01 | 0 | 0 | 0 | 0 | 113898.01 | 119022.58 | [5 empty] | N | WSNI | 100%
503293 | Service Risk Management Tool - SRMT | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-07-17 | 2019-09-30 | 2019-09-30 | 2019-09-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1096017.89 | 2108.09 | 0 | 1098125.98 | 0 | 0 | 0 | 1098125.98 | 0 | 0 | 0 | 0 | 1098125.98 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403623 | Service Transition Dev Services | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-12-24 | 2014-04-11 | 2014-04-11 | 2015-01-13 |  | Scottish Water Wide | 210531.99 | 0 | -1260.34 | 0 | 0 | 0 | 0 | 0 | -1260.34 | 0 | 0 | 0 | 209271.65 | 0 | 0 | 0 | 0 | 209271.65 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501937 | Severe Weather - Damaged Water Mains Shieldhill & Cample Mill | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-02-23 | 2017-08-29 | 2017-08-30 | 2018-06-28 |  | Dumfries and Galloway | 0 | 0 | 1185.3 | 14452.93 | 507088.35 | 310346.98 | 631.25 | 5789.19 | 839494 | 17367.42 | 0 | 0 | 856861.42 | 0 | 0 | 0 | 0 | 856861.42 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502397 | Sewage Related Debris Strategy & IDP Development | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MS3 | 2017-01-31 | 2017-01-31 | 2017-03-01 | 2021-05-21 | 2021-05-21 | Scottish Water Wide | 0 | 0 | 0 | 9158.88 | 1212 | 343.12 | 109665.56 | 2155.44 | 122535 | 17464.53 | 0 | 0 | 139999.53 | 0 | 4817.1687 | 0 | 4817.1687 | 144816.6987 | 0 | [5 empty] | N | EC16B | 100%
502604 | Sewage Related Debris Strategy & IDP Development_CAPEX element | IR18 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MS7 | 2020-10-15 | 2020-10-16 | 2020-11-17 | 2020-12-22 | 2028-04-01 | Scottish Water Wide | 0 | 0 | 0 | 176912.11 | 122631.91 | 39482.12 | 141816.36 | -22946.23 | 457896.27 | 0 | 0 | 0 | 457896.27 | 0 | 0 | 0 | 0 | 457896.27 | 0 | [5 empty] | N | EC16B | 100%
402536 | Sewer Flooding McGeoch Drive Dumfries | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-02-29 | 2013-11-18 | 2014-01-31 | 2014-06-18 | 2014-06-18 | Dumfries and Galloway | 585684 | 0 | -46812 | -1476.24 | 0 | 0 | 0 | 0 | -48288.24 | 0 | 0 | 0 | 537395.76 | 0 | 0 | 0 | 0 | 537395.76 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
402362 | Sewer Flooding at Elmgrove Scone | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-10-13 | 2013-10-17 | 2013-11-11 | 2014-02-10 | 2014-02-10 | Perth and Kinross | 390503 | 0 | -3508.64 | 72.06 | 0 | 0 | 0 | 0 | -3436.58 | 0 | 0 | 0 | 387066.42 | 0 | 0 | 0 | 0 | 387066.42 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
402197 | Sewer Flooding Burnbank Street Airdrie | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2011-06-10 | 2019-08-30 | 2019-10-04 | 2021-04-13 | 2021-04-13 | North Lanarkshire | 330000 | 330000 | 145015 | 174951 | 113180 | 152439 | 1771070.2 | 1481430.24 | 3838085.44 | 67062 | 74544.56 | 74544.56 | 4235147.44 | 0 | 0 | 7482.56 | 7482.56 | 4242630 | 180449.74 | [5 empty] | N | FL_DD | 100%
403498 | Sewer Flooding Campaign Programme Definition & Roadmap | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-10-04 | 2013-10-04 | 2013-10-07 | 2019-02-25 |  | Scottish Water Wide | 27439.02 | 0 | 17534.02 | 270016.37 | -111992.37 | 35941.53 | 0 | 0 | 211499.56 | 0 | 0 | 0 | 238938.58 | 0 | 0 | 0 | 0 | 238938.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504146 | Sewer Flooding Focus - EPI Focus Telemetry Improvements | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 |  | 2019-12-11 | 2020-03-06 | 2021-04-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1962.62 | 19944.38 | 21907 | 8092.8 | 0 | 0 | 29999.8 | 0 | 0 | 0 | 0 | 29999.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504158 | Sewer Flooding Focus - Flood Response Trailers - 15k per trailer. Further 4 would be required | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 |  | 2019-12-11 | 2020-03-10 | 2021-04-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 51493.23 | 5909.77 | 57403 | 2597.33 | 0 | 0 | 60000.33 | 0 | 0 | 0 | 0 | 60000.33 | 209381.79 | [5 empty] | N | Ww3 | 100%
504139 | Sewer flooding focus - Installation of Pressure Transducer Interface( PTIs) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-24 | 2021-05-01 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 12387.32 | 3500 | 15887.32 | 14112.68 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504167 | Sewer Flooding focus - Replace defective CCTV Equipment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 |  | 2019-12-13 | 2020-02-14 | 2021-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 88213.08 | 70500 | 158713.08 | 0 | 0 | 0 | 158713.08 | 0 | 0 | 0 | 0 | 158713.08 | 209381.79 | [5 empty] | N | Ww3 | 100%
402533 | Sewer Flooding Johnstone Drive Rutherglen | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-28 | 2012-05-25 | 2013-04-22 | 2013-08-01 |  | South Lanarkshire | 52542 | 0 | -528.67 | 0 | 0 | 0 | 0 | 0 | -528.67 | 0 | 0 | 0 | 52013.33 | 0 | 0 | 0 | 0 | 52013.33 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402236 | Sewer Flooding Steel Street at Cardwell Road Gourock | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-07-22 | 2014-04-02 | 2014-04-02 | 2014-12-16 | 2014-12-16 | Inverclyde | 1727977.31 | 0 | 112489.48 | 36.75 | 0 | 0 | 0 | 0 | 112526.23 | 0 | 0 | 0 | 1840503.54 | 0 | 0 | 0 | 0 | 1840503.54 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
503073 | Sewer Misconnection Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2018-04-06 | 2018-08-29 | 2018-09-24 | 2019-09-19 | 2019-09-19 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 557223.39 | 275390.61 | 4614.2 | 837228.2 | 0 | 0 | 0 | 837228.2 | 0 | 0 | 0 | 0 | 837228.2 | 0 | [5 empty] | N | EC16 | 100%
506215 | Sewer Network Demonstrator roll out into BAUATOS | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS2 | 2020-05-05 | 2020-05-20 | 2021-08-11 | 2022-02-09 | 2022-05-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776912 | 776912 | 613087.95 | 0 | 0 | 1389999.95 | 0 | 169105.5008 | 0 | 169105.5008 | 1559105.4508 | 413580.79 | [5 empty] | N | EC01M | 100%
45667 | Sewer Network Modelling - DAS Model Maintenance - Early Start Scoping | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2008-10-15 | 2010-03-24 | 2010-06-01 | 2014-12-08 |  | Scottish Water Wide | 2420315 | 0 | 19025.64 | 0 | 0 | 0 | 0 | 0 | 19025.64 | 0 | 0 | 0 | 2439340.64 | 0 | 0 | 0 | 0 | 2439340.64 | 418763.58 | [5 empty] | N | CM_WWI | 100%
46622 | Sewer Rehab - Albert Pier Rothesay (Saline Intrusion) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2009-03-19 | 2011-05-05 | 2011-05-16 | 2012-07-05 |  | Argyll and Bute-Cowal & Bute | 938353 | 0 | 64 | 0 | -48794.84 | 0 | 0 | 0 | -48730.84 | 0 | 0 | 0 | 889622.16 | 0 | 0 | 0 | 0 | 889622.16 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400510 | Sewer Rehab - Frith and Mossbank Shetland | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-03-24 | 2011-10-31 | 2011-12-12 | 2013-05-24 |  | Shetland Islands | 819365 | 0 | -1543.71 | 0 | 0 | 0 | 0 | 0 | -1543.71 | 0 | 0 | 0 | 817821.29 | 0 | 0 | 0 | 0 | 817821.29 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402526 | Sewer Rehab - PMAP Reactive Process Phase 3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-05 | 2012-04-24 | 2012-04-24 | 2013-08-12 |  | Scottish Water Wide | 1728836 | 0 | -4866.77 | 0 | 0 | 0 | 0 | 0 | -4866.77 | 0 | 0 | 0 | 1723969.23 | 0 | 0 | 0 | 0 | 1723969.23 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403349 | Sewer Rehab - PMAP Reactive Process Phase 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-18 | 2013-05-29 | 2013-05-29 | 2014-06-04 |  | Scottish Water Wide | 1639081 | 0 | 0 | -6060.88 | 0 | 0 | 0 | 0 | -6060.88 | 0 | 0 | 0 | 1633020.12 | 0 | 0 | 0 | 0 | 1633020.12 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403348 | Sewer Rehab - PMAP Reactive Process Phase 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-28 | 2014-03-25 | 2014-03-26 | 2015-09-21 |  | Scottish Water Wide | 1090001 | 0 | 71217 | 2550.06 | -796.19 | 0 | 0 | 0 | 72970.87 | 0 | 0 | 0 | 1162971.87 | 0 | 0 | 0 | 0 | 1162971.87 | 209381.79 | [5 empty] | N | CM_WWI | 100%
46148 | Sewer Rehab - Powburn Rising Main Scheme Phase 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2008-08-20 | 2012-03-08 | 2012-04-30 | 2014-06-06 |  | South Ayrshire | 4286075 | 0 | 0 | -1922.89 | 0 | 0 | 0 | 0 | -1922.89 | 0 | 0 | 0 | 4284152.11 | 0 | 0 | 0 | 0 | 4284152.11 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502286 | SFT Building Safety Inspections | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2017-04-03 | 2017-04-10 | 2017-04-10 | 2017-03-14 |  | Scottish Water Wide | 0 | 0 | 0 | 39957.34 | -7943.42 | 0 | 0 | 0 | 32013.92 | 0 | 0 | 0 | 32013.92 | 0 | 0 | 0 | 0 | 32013.92 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503452 | SGA- Blueprint for Sewers | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS3 | 2019-02-13 | 2019-07-18 | 2019-09-09 | 2021-06-23 | 2021-06-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1308.41 | 111530.36 | 139844.24 | 252683 | 1983.59 | 0 | 0 | 254666.59 | 0 | 547.1254 | 0 | 547.1254 | 255213.7154 | 295054.03 | [5 empty] | N | CS25 | 100%
403183 | Shafton Road Glasgow Phase1 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-12-17 | 2013-12-11 | 2013-12-12 | 2014-08-26 | 2014-10-01 | Glasgow City | 1953340 | 0 | 15173.45 | 6194.21 | 772.98 | 0 | 0 | 0 | 22140.64 | 0 | 0 | 0 | 1975480.64 | 0 | 0 | 0 | 0 | 1975480.64 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
503834 | Shalloch Park Sewer Collapse | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2019-11-29 |  | 2020-11-02 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 11513.08 | 118436.38 | 129949.46 | 20275.65 | 0 | 0 | 150225.11 | 0 | 0 | 0 | 0 | 150225.11 | 209381.79 | [5 empty] | N | SR15_CMA_WWI | 100%
403583 | Shandon Street Edinburgh | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-09-09 | 2013-12-23 | 2014-02-10 | 2014-06-30 | 2014-06-30 | City of Edinburgh | 395847 | 0 | 778 | -5213.62 | 0 | 0 | 0 | 0 | -4435.62 | 0 | 0 | 0 | 391411.38 | 0 | 0 | 0 | 0 | 391411.38 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
30875 | Shapinsay WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2012-01-31 | 2012-02-28 | 2013-03-01 | 2013-03-18 | Orkney Islands | 3353865.31 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 3353870.31 | 0 | 0 | 0 | 0 | 3353870.31 | 28761.13 | [5 empty] | N | DW23 | 100%
503239 | Sharphill Saltcoats | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2020-06-09 | 2020-06-09 | 2020-09-10 | 2022-03-18 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 20946.1 | 388667.11 | 1220541.2 | 1630154.41 | 1369955.79 | 0 | 0 | 3000110.2 | 0 | 0 | 240008.816 | 240008.816 | 3240119.016 | 444766.03 | [5 empty] | N | WG5 | 100%
502924 | Shawfair Danderhall Waste Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2021-06-25 |  | Midlothian | 0 | 0 | 0 | 0 | 41259.81 | 0 | 762550 | 11426.17 | 815235.98 | 0 | 0 | 0 | 815235.98 | 0 | 0 | 0 | 0 | 815235.98 | 0 | [5 empty] | N | SG5 | 100%
500740 | Shawfair-Zero Waste Water Main Upsize | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2015-07-27 | 2015-07-27 | 2015-07-27 | 2018-10-25 | 2018-10-25 | East Lothian | 0 | 0 | 175962 | 0 | -87999.99 | 0 | 0 | 0 | 87962.01 | 0 | 0 | 0 | 87962.01 | 0 | 0 | 0 | 0 | 87962.01 | 444766.03 | [5 empty] | N | WG5 | 100%
502942 | Shetland Water Strategy | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | SWD | SOSI | MS7 | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2020-01-31 | 2020-03-31 | Shetland Islands | 0 | 0 | 0 | 0 | 85259.9 | 229114.76 | 83084.07 | -1318.54 | 396140.19 | 0 | 0 | 0 | 396140.19 | 0 | 0 | 0 | 0 | 396140.19 | 3250279.58 | [5 empty] | Y | WG4 | 100% | [64 empty] | 1 |  |  | 0
404123 | Shieldaig WOA - Mary Street UITS Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-04-17 | 2015-04-17 | 2015-05-11 | 2016-01-21 |  | Highland | 0 | 0 | 315740.5 | -19.14 | 0 | 0 | 0 | 0 | 315721.36 | 0 | 0 | 0 | 315721.36 | 0 | 0 | 0 | 0 | 315721.36 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45414 | Shieldaig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-03-29 | 2011-09-01 | 2013-03-01 | 2013-03-27 | Highland | 3372234.89 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 3372279.89 | 0 | 0 | 0 | 0 | 3372279.89 | 57522.26 | [5 empty] | N | DW13 | 50% | DW23 | 50%
506108 | Shieldhall and Lower Clyde - SR21 Aesthetic Surveys | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWMD | SR21 Early Start | MS3 | 2020-05-04 | 2020-09-30 | 2020-10-15 | 2021-11-08 | 2021-10-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62945 | 62945 | 162055.33 | 0 | 0 | 225000.33 | 0 | 0 | 0 | 0 | 225000.33 | 0 | [5 empty] | N | SR21_WW | 100%
500717 | Shieldhall Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-07-23 | 2015-12-22 | 2016-01-19 | 2017-03-28 | 2017-05-15 | Glasgow City | 0 | 0 | 261208 | 56166.43 | 35.36 | 0 | 0 | 0 | 317409.79 | 0 | 0 | 0 | 317409.79 | 0 | 0 | 0 | 0 | 317409.79 | 106252.93 | [5 empty] | N | FL_DD | 100%
403772 | Shieldhall PST 4 6 8 Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-05-21 | 2014-05-26 | 2014-05-26 | 2016-08-16 |  | Glasgow City | 676556 | 0 | 448549.58 | 13544.76 | 5591.42 | -3962.51 | 0 | 0 | 463723.25 | 0 | 0 | 0 | 1140279.25 | 0 | 0 | 0 | 0 | 1140279.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501637 | Shieldhall Storm Return Automation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-03-16 | 2017-11-07 | 2018-01-30 | 2021-06-16 |  | Glasgow City | 0 | 0 | 0 | 179192 | -118989.87 | 514734.68 | 18123.76 | 1636.3 | 594696.87 | 4034.24 | 0 | 0 | 598731.11 | 0 | 0 | 0 | 0 | 598731.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501172 | Shieldhall STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS6 | 2016-03-02 | 2017-10-30 | 2017-11-06 | 2020-09-30 |  | Renfrewshire | 0 | 0 | 5161.68 | 1032338.15 | 942738.78 | 5167940.47 | 2250056.8 | -129916.88 | 9268319 | 211079.59 | 0 | 0 | 9479398.59 | 0 | 0 | 0 | 0 | 9479398.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
30878 | Shieldhall STW Refurb - STW000642 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-15 | 2011-09-23 | 2011-09-23 | 2013-11-27 |  | Glasgow City | 6343385.08 | 0 | -6149.5 | 0 | 0 | 0 | 0 | 0 | -6149.5 | 0 | 0 | 0 | 6337235.58 | 0 | 0 | 0 | 0 | 6337235.58 | 90601.29 |  |  |  |  | 41553 | N | CM_WWNI | 100%
401241 | Shieldhall UID Improvements Cluster 1 - Kinning Park SPS | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-07-19 | 2011-01-14 | 2011-01-27 | 2011-01-27 | 2011-03-14 | Glasgow City | 3021.99 | 0 | 0 | 0 | 1195.71 | 228.59 | 0 | 0 | 1424.3 | 0 | 0 | 0 | 4446.29 | 0 | 0 | 0 | 0 | 4446.29 | 0 | [5 empty] | N | EC10B | 100%
502938 | Shieldhall WWTW - Odour Control Unit Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-12-11 | 2017-12-11 | 2018-01-08 | 2018-01-09 |  | Glasgow City | 0 | 0 | 0 | 0 | 662951.51 | 0 | 0 | 0 | 662951.51 | 0 | 0 | 0 | 662951.51 | 0 | 0 | 0 | 0 | 662951.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511139 | Shieldhall WWTW - PSTs condition issue_refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2023-04-21 | 2024-10-29 | 2025-01-27 | 2026-01-02 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000.04 | 0 | 0 | 1000000.04 | 0 | 0 | 0 | 0 | 1000000.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507370 | Shieldhall WWTW - Refurb Fine Screens No.2 & No. 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-07-15 | 2020-07-22 | 2022-01-07 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193238 | 193238 | 11761.88 | 0 | 0 | 204999.88 | 0 | 0 | 0 | 0 | 204999.88 | 209381.79 | [5 empty] | N | CM_M&G | 100%
500757 | Shieldhall WWTW - Storm Tank Scraper Bridge Refurbishment | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWMD | Odour | MS7 | 2015-08-12 | 2015-10-26 | 2016-02-05 | 2017-04-10 | 2017-05-09 | Glasgow City | 0 | 0 | 47000 | 705043.97 | -150546.54 | 0 | -7768.64 | 298.54 | 594027.33 | 0 | 0 | 0 | 594027.33 | 0 | 0 | 0 | 0 | 594027.33 | 826685.67 | [5 empty] | N | CS2 | 100%
507307 | Shieldhall WWTW - Telemetry Outstation Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-06-25 | 2021-01-07 | 2021-08-20 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15216 | 15216 | 34784 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501683 | Shieldhall WWTW Grade 5 HC Sewer Ph1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-05-16 | 2017-02-13 | 2017-02-17 | 2021-09-01 |  | Glasgow City | 0 | 0 | 0 | 471779.17 | 539039.83 | 190500 | 1054633 | 134393.36 | 2390345.36 | 182240 | 0 | 0 | 2572585.36 | 0 | 0 | 11277.64 | 11277.64 | 2583863 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501747 | Shieldhall WwTW Grade 5 HC Sewer Phase2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-10-31 | 2019-05-31 | 2019-08-26 | 2021-05-20 |  | Glasgow City | 0 | 0 | 0 | 4795.67 | 48.62 | 73732.71 | 241149 | 14776 | 334502 | 2400 | 0 | 0 | 336902 | 0 | 0 | 0 | 0 | 336902 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501281 | SHIELDHALL WWTW NS533659 MCC Replacement (Phase 1- PreSed MCC) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS6 | 2016-01-20 | 2018-01-31 | 2018-01-31 | 2020-03-18 |  | Glasgow City | 0 | 0 | 14033 | 228154.86 | 269413.75 | 1090389.41 | 327858.51 | -34381.53 | 1895468 | 12110.25 | 0 | 0 | 1907578.25 | 0 | 0 | 0 | 0 | 1907578.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500197 | Shieldhall WWTW Odour Upgrade | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater | SEPA | NONINF | Odour | MS7 | 2015-07-21 | 2016-09-16 | 2017-02-27 | 2017-06-30 | 2017-11-30 | Glasgow City | 0 | 0 | 39577 | 283295.06 | 426634.32 | -57439.96 | -4218.42 | -5466.38 | 682381.62 | 0 | 0 | 0 | 682381.62 | 0 | 0 | 0 | 0 | 682381.62 | 826685.67 | [5 empty] | Y | CS2 | 100% | [46 empty] | 1 | [20 empty] | 0
403479 | Shotts (Glen Road) - Renew Overland pipeline | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2013-07-11 | 2016-04-08 | 2016-04-11 | 2017-01-25 |  | North Lanarkshire | 134441 | 0 | 589763 | 1236071.78 | 20475.22 | 5257.47 | 0 | 0 | 1851567.47 | 0 | 0 | 0 | 1986008.47 | 0 | 0 | 0 | 0 | 1986008.47 | 1465672.52 | [5 empty] | N | CM_M&G | 14.29% | CM_WWI | 85.71%
500177 | Shotts DOA (DOA000554) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-11-30 | 2016-01-18 | 2018-02-28 | 2018-03-31 | North Lanarkshire | 0 | 0 | 80361 | 65629.65 | 31230 | 30919.32 | 0 | 0 | 208139.97 | 0 | 0 | 0 | 208139.97 | 0 | 0 | 0 | 0 | 208139.97 | 72047.27 | [5 empty] | Y | CS11 | 43.84% | CS16D | 56.16% | [37 empty] | 1 | [27 empty] | 0
30880 | Shotts STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2012-01-24 | 2012-07-09 | 2013-01-07 | 2013-02-21 | North Lanarkshire | 1601398.3 | 0 | 801 | -18226.57 | 0 | 0 | 0 | 0 | -17425.57 | 0 | 0 | 0 | 1583972.73 | 0 | 0 | 0 | 0 | 1583972.73 | 176884.68 | [5 empty] | N | EC10A | 11.6% | EC01A | 11.7% | EC04A | 11.7% | CM_WWNI | 65%
503209 | Shotts WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-14 | 2029-06-15 | 2030-06-12 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 81775.66 | 5565.37 | 3109.97 | 90451 | 0 | 0 | 0 | 90451 | 0 | 0 | 0 | 0 | 90451 | 122419.09 | [5 empty] | N | SG1 | 100%
500698 | Sim Replacement and Mobile Device Upgrade Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-07-22 | 2015-07-22 | 2015-07-22 | 2016-05-11 |  | Scottish Water Wide | 0 | 0 | 1359603 | -53016.17 | 0 | 0 | 0 | 0 | 1306586.83 | 0 | 0 | 0 | 1306586.83 | 0 | 0 | 0 | 0 | 1306586.83 | 306661.32 | [5 empty] | N | CM_M&G | 100%
507813 | Simple Repair at Aberdeen Kirkhill DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-09-08 | 2020-09-29 | 2020-10-26 | 2022-04-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689379.26 | 689379.26 | 884173.86 | 0 | 0 | 1573553.12 | 0 | 0 | 156446.88 | 156446.88 | 1730000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505161 | Simple Repair at Achmore DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-17 | 2020-03-02 | 2020-12-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 20570 | 23650 | 36350 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 60000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506237 | Simple Repair at Airngarth DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-05-05 | 2020-07-14 | 2020-09-21 | 2021-07-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560556 | 560556 | 245694 | 0 | 0 | 806250 | 0 | 0 | 0 | 0 | 806250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509718 | Simple Repair at Airport DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-11-19 | 2021-02-08 | 2021-10-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137858 | 137858 | 103262.39 | 0 | 0 | 241120.39 | 0 | 0 | 0 | 0 | 241120.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508152 | Simple Repair at Ardfern CWT 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-08-25 | 2020-11-02 | 2021-03-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113296 | 113296 | 9254.19 | 0 | 0 | 122550.19 | 0 | 0 | 0 | 0 | 122550.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505212 | Simple Repair at Auchinstarry DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2020-03-19 | 2020-04-30 | 2020-06-15 | 2021-01-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2365.24 | 339394.94 | 341760.18 | 1499.98 | 0 | 0 | 343260.16 | 0 | 0 | 0 | 0 | 343260.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506245 | Simple Repair at Brackenhirst DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2020-05-04 | 2020-09-30 | 2021-05-13 | 2021-10-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65926.81 | 65926.81 | 541836.12 | 0 | 0 | 607762.93 | 0 | 0 | 0 | 0 | 607762.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509714 | Simple Repair at Bradan CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-11-11 | 2020-11-19 | 2020-12-07 | 2022-04-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175829 | 175829 | 181387.72 | 0 | 0 | 357216.72 | 0 | 0 | 0 | 0 | 357216.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504290 | Simple Repair at Burghill Old DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-01-15 | 2020-03-09 | 2020-12-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 16858.8 | 0 | 16858.8 | 5571.2 | 0 | 0 | 22430 | 0 | 0 | 0 | 0 | 22430 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504744 | Simple Repair at Carlochan DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-27 | 2020-02-03 | 2021-05-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7130.84 | 114102.16 | 121233 | 779.86 | 0 | 0 | 122012.86 | 0 | 0 | 0 | 0 | 122012.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508322 | Simple Repair at Carluke DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2020-09-21 | 2020-09-29 | 2021-05-10 | 2022-01-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202231 | 202231 | 163769.23 | 0 | 0 | 366000.23 | 0 | 0 | 0 | 0 | 366000.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508548 | Simple Repair at Chapelhill DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-09-22 | 2020-10-05 | 2021-05-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209208 | 209208 | 9791.8 | 0 | 0 | 218999.8 | 0 | 0 | 0 | 0 | 218999.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507812 | Simple Repair at Clachtoll DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-04-12 | 2021-08-16 | 2021-10-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6261 | 6261 | 45738.63 | 0 | 0 | 51999.63 | 0 | 0 | 0 | 0 | 51999.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507053 | Simple Repair at Clunyhill County DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-07-01 | 2020-08-10 | 2021-06-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133519 | 133519 | 1939.7 | 0 | 0 | 135458.7 | 0 | 0 | 0 | 0 | 135458.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503947 | Simple Repair at Cockburnspath DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2019-12-18 | 2020-01-20 | 2020-12-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 27691.82 | 108269.18 | 135961 | 39.09 | 0 | 0 | 136000.09 | 0 | 0 | 0 | 0 | 136000.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506884 | Simple Repair at Crawford DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-06-02 | 2020-08-03 | 2021-03-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248210.97 | 248210.97 | 0 | 0 | 0 | 248210.97 | 0 | 0 | 0 | 0 | 248210.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510100 | Simple Repair at Croft Hill CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-12-09 | 2020-12-17 | 2021-02-08 | 2021-08-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157101 | 157101 | 201729.37 | 0 | 0 | 358830.37 | 0 | 0 | 0 | 0 | 358830.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509798 | Simple Repair at Dodside DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-11-30 | 2020-12-16 | 2021-02-08 | 2022-09-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136000 | 136000 | 374404 | 0 | 0 | 510404 | 0 | 0 | 0 | 0 | 510404 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511410 | Simple Repair at Douglas Moor BPT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2021-03-22 | 2021-06-07 | 2021-05-03 | 2021-08-13 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611947.08 | 0 | 0 | 611947.08 | 0 | 0 | 0 | 0 | 611947.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507904 | Simple Repair at Dron DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-08-25 | 2020-11-02 | 2021-02-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108775 | 108775 | 20224.74 | 0 | 0 | 128999.74 | 0 | 0 | 0 | 0 | 128999.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507054 | Simple Repair at Drumbuie DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-06-17 | 2021-10-08 | 2022-06-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8734 | 8734 | 115965.72 | 0 | 0 | 124699.72 | 0 | 0 | 0 | 0 | 124699.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506319 | Simple Repair at Fionnphort DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-27 | 2020-09-21 | 2021-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172500 | 172500 | 0 | 0 | 0 | 172500 | 0 | 0 | 0 | 0 | 172500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509549 | Simple Repair at Flaughton South DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-11-27 | 2020-12-17 | 2021-03-29 | 2022-10-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34904 | 34904 | 300654.05 | 0 | 0 | 335558.05 | 0 | 0 | 0 | 0 | 335558.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505169 | Simple Repair at Four Winds Croft DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-17 | 2020-03-02 | 2020-12-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 22960 | 149361.18 | 172321.18 | 3978.82 | 0 | 0 | 176300 | 0 | 0 | 0 | 0 | 176300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507387 | Simple Repair at Gowanlea DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-08-14 | 2020-09-29 | 2021-03-08 | 2022-05-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206140 | 206140 | 93610 | 0 | 0 | 299750 | 0 | 0 | 0 | 0 | 299750 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509990 | Simple Repair at Gravir Marivig DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-03 | 2021-10-15 | 2022-03-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10503 | 10503 | 104756.66 | 0 | 0 | 115259.66 | 0 | 0 | 0 | 0 | 115259.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506199 | Simple Repair at Greenloaning DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-04-21 | 2020-08-31 | 2021-03-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87866 | 87866 | 3509.13 | 0 | 0 | 91375.13 | 0 | 0 | 0 | 0 | 91375.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511783 | Simple Repair at Hazeldene DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-06-14 | 2021-08-30 | 2021-09-13 | 2022-03-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799999.97 | 0 | 0 | 799999.97 | 0 | 0 | 0 | 0 | 799999.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507062 | Simple Repair at Highlees South DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2020-08-27 | 2020-09-15 | 2022-05-09 | 2022-12-06 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46026 | 46026 | 451973.79 | 0 | 0 | 497999.79 | 0 | 0 | 0 | 0 | 497999.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507353 | Simple Repair at Hillfarm DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-07-08 | 2020-08-03 | 2021-07-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78923 | 78923 | 5077.44 | 0 | 0 | 84000.44 | 0 | 0 | 0 | 0 | 84000.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509080 | Simple Repair at Kilphin CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-10-15 | 2021-02-01 | 2022-02-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33662 | 33662 | 8263.38 | 0 | 0 | 41925.38 | 0 | 0 | 0 | 0 | 41925.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505103 | Simple Repair at Kingston DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-02-11 | 2020-03-20 | 2021-05-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 27840 | 96860 | 124700 | 0 | 0 | 0 | 124700 | 0 | 0 | 0 | 0 | 124700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510863 | Simple Repair at Lagahorie DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2021-01-28 | 2021-03-01 | 2021-08-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20444 | 20444 | 198715.64 | 0 | 0 | 219159.64 | 0 | 0 | 0 | 0 | 219159.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509291 | Simple Repair at Lamlash DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-12-03 | 2021-02-15 | 2021-07-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52403 | 52403 | 162596.91 | 0 | 0 | 214999.91 | 0 | 0 | 0 | 0 | 214999.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507075 | Simple Repair at Landheads DSR 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2020-07-14 | 2020-07-17 | 2020-09-07 | 2021-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400355.4 | 400355.4 | 20000 | 0 | 0 | 420355.4 | 0 | 0 | 0 | 0 | 420355.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506317 | Simple Repair at Lanes DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-04-27 | 2021-09-13 | 2022-01-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4079 | 4079 | 38720.51 | 0 | 0 | 42799.51 | 0 | 0 | 0 | 0 | 42799.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507864 | Simple Repair at Langlee DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2020-12-11 | 2022-04-11 | 2022-05-02 | 2022-09-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1869 | 1869 | 345388.04 | 0 | 0 | 347257.04 | 0 | 0 | 0 | 0 | 347257.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504934 | Simple Repair at Loch Fergus DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-11 | 2020-06-22 | 2021-01-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129700 | 129700 | 0 | 0 | 0 | 129700 | 0 | 0 | 0 | 0 | 129700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512008 | Simple Repair at Mallaig CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-26 | 2021-04-12 | 2021-11-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209471.04 | 0 | 0 | 209471.04 | 0 | 0 | 0 | 0 | 209471.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508162 | Simple Repair at Midglen DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2020-08-26 | 2020-09-17 | 2020-10-01 | 2021-03-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357958 | 357958 | 39792 | 0 | 0 | 397750 | 0 | 0 | 0 | 0 | 397750 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505861 | Simple Repair at Neilston High DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-05-14 | 2020-07-14 | 2021-02-08 | 2022-01-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94269 | 94269 | 367981.5 | 0 | 0 | 462250.5 | 0 | 0 | 0 | 0 | 462250.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507918 | Simple Repair at Nereabols DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-08-13 | 2020-09-16 | 2021-02-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81835 | 81835 | 940.05 | 0 | 0 | 82775.05 | 0 | 0 | 0 | 0 | 82775.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511095 | Simple Repair at Northmavine SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-12 | 2021-06-21 | 2021-08-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3925.23 | 3925.23 | 57589.77 | 0 | 0 | 61515 | 0 | 0 | 0 | 0 | 61515 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507919 | Simple Repair at Peathill DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-08-13 | 2020-11-02 | 2021-08-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208327 | 208327 | 4523.25 | 0 | 0 | 212850.25 | 0 | 0 | 0 | 0 | 212850.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511406 | Simple Repair at Penwhapple CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2021-03-22 | 2021-08-02 | 2021-08-16 | 2021-11-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307566.16 | 0 | 0 | 307566.16 | 0 | 0 | 0 | 0 | 307566.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510044 | Simple Repair at Penwhirn CWT1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-04 | 2021-05-21 | 2022-01-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16450 | 16450 | 186835.64 | 0 | 0 | 203285.64 | 0 | 0 | 0 | 0 | 203285.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509283 | Simple Repair at Peterhead Newfield DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-11-23 | 2020-12-18 | 2021-02-15 | 2022-06-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216215 | 216215 | 1129727.22 | 0 | 0 | 1345942.22 | 0 | 0 | 4057.78 | 4057.78 | 1350000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505649 | Simple Repair at Port Ellen DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-03-19 | 2020-05-22 | 2021-02-11 | 2021-07-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70952 | 70952 | 160173.05 | 0 | 0 | 231125.05 | 0 | 0 | 0 | 0 | 231125.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504296 | Simple Repair at Raasay CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-01-27 | 2020-11-09 | 2021-03-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 104263 | 111263 | 0 | 0 | 0 | 111263 | 0 | 0 | 0 | 0 | 111263 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507860 | Simple Repair at Rochomie DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-09-08 | 2020-09-29 | 2020-11-02 | 2021-12-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541345.13 | 541345.13 | 463021.02 | 0 | 0 | 1004366.15 | 0 | 0 | 245633.85 | 245633.85 | 1250000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511135 | Simple Repair at Scalloway DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-19 | 2021-07-26 | 2021-10-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8799.07 | 8799.07 | 127850.93 | 0 | 0 | 136650 | 0 | 0 | 0 | 0 | 136650 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504168 | Simple Repair at Seilebost DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-24 | 2020-06-22 | 2021-05-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 6607.48 | 117517.52 | 124125 | -499.84 | 0 | 0 | 123625.16 | 0 | 0 | 0 | 0 | 123625.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506430 | Simple Repair at Shieldhill DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-07 | 2020-09-28 | 2021-08-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300730 | 300730 | 59269.91 | 0 | 0 | 359999.91 | 0 | 0 | 0 | 0 | 359999.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505844 | Simple Repair at Sourbank DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-04-14 | 2020-05-18 | 2020-12-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64987.92 | 64987.92 | 0 | 0 | 0 | 64987.92 | 0 | 0 | 0 | 0 | 64987.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506435 | Simple Repair at Stafflar DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-10-07 | 2020-10-29 | 2021-02-02 | 2021-10-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199855.28 | 199855.28 | 509148.67 | 0 | 0 | 709003.95 | 0 | 0 | 0 | 0 | 709003.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507912 | Simple Repair at Stonehaven Megray DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-08-17 | 2020-11-02 | 2021-06-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163134 | 163134 | 75515.61 | 0 | 0 | 238649.61 | 0 | 0 | 0 | 0 | 238649.61 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508464 | Simple Repair at Strutherhill DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2020-09-29 | 2020-10-21 | 2021-05-07 | 2021-12-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43730 | 43730 | 406695.23 | 0 | 0 | 450425.23 | 0 | 0 | 0 | 0 | 450425.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504294 | Simple Repair at Threaplands DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-01-27 | 2020-05-04 | 2021-03-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 21007.69 | 166042.31 | 187050 | 0 | 0 | 0 | 187050 | 0 | 0 | 0 | 0 | 187050 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509949 | Simple Repair at Ullapool CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-12-03 | 2021-01-11 | 2021-09-13 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118181 | 118181 | 65246.7 | 0 | 0 | 183427.7 | 0 | 0 | 0 | 0 | 183427.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506433 | Simple Repair at Upper Braes DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-05-07 | 2021-06-11 | 2021-09-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19986 | 19986 | 44513.71 | 0 | 0 | 64499.71 | 0 | 0 | 0 | 0 | 64499.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506248 | Simple Repair at Woodend Cell 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-05-13 | 2020-07-13 | 2020-08-10 | 2021-12-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 544341 | 544341 | 79384.03 | 0 | 0 | 623725.03 | 0 | 0 | 0 | 0 | 623725.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506221 | Simple Repairs T3 North B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-04-22 | 2021-02-22 | 2021-03-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181988 | 181988 | 86762.22 | 0 | 0 | 268750.22 | 0 | 0 | 0 | 0 | 268750.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501701 | Sinclair Drive Cowdenbeath - Reline Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-11-17 | 2017-05-23 | 2017-08-09 | 2019-02-14 |  | Fife | 0 | 0 | 0 | 11110 | 38449 | 17802 | 567 | -4860.89 | 63067.11 | 0 | 0 | 0 | 63067.11 | 0 | 0 | 0 | 0 | 63067.11 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511493 | Single Supplies Pilot | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-01 | 2021-12-06 | 2022-04-06 | 2022-10-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000.03 | 0 | 0 | 250000.03 | 0 | 0 | 0 | 0 | 250000.03 | 119022.58 | [5 empty] | N | CM_WSI | 100%
403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWMD | DWQ Compliance | MS7 | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-02-22 | 2017-05-16 | Scottish Water Wide | 73057 | 73057 | 268995 | 454948 | 15412.52 | 0 | 0 | 0 | 739355.52 | 0 | 0 | 0 | 812412.52 | 0 | 0 | 0 | 0 | 812412.52 | 112484.65 | [5 empty] | N | DW25PS | 10% | DW2_S | 90%
404099 | Skellyton (Larkhall) STW - Transfer project from 030881 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS6 | 2015-03-06 | 2016-09-02 | 2016-10-17 | 2017-05-05 | 2017-05-05 | South Lanarkshire | 9728.02 | 0 | 265470.38 | 1554463.33 | 796925.21 | -267464.6 | -102562.45 | -102441.89 | 2144389.98 | 6462.35 | 2778.8105 | 3857.4621 | 2160580.35 | 1078.6516 | 0 | 0 | 1078.6516 | 2161659.0016 | 90601.29 |  |  |  |  | 29740 | N | EC01A | 14.33% | EC04A | 14.33% | EC10A | 14.33% | CM_WWNI | 57%
30881 | Skellyton (Larkhall) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-27 | 2011-03-29 | 2012-12-11 | 2016-02-11 | 2016-10-31 | South Lanarkshire | 3362266.45 | 0 | 72347.5 | 12732.53 | 692.79 | 0 | 0 | 0 | 85772.82 | 0 | 0 | 0 | 3448039.27 | 0 | 0 | 0 | 0 | 3448039.27 | 148123.55 | [5 empty] | N | CM_WWNI | 19.97% | EC01A | 19.97% | EC04A | 60.05%
500178 | Skellyton DOA (DOA002580) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-11-30 | 2016-01-12 | 2018-11-26 | 2019-03-28 | South Lanarkshire | 0 | 0 | 108775 | 107165 | 44040 | 65020 | 4691.07 | 0 | 329691.07 | 0 | 0 | 0 | 329691.07 | 0 | 0 | 0 | 0 | 329691.07 | 76665.15 | [5 empty] | N | EC01G | 1.092% | CS11 | 45.28% | CS16D | 53.62%
503328 | Skellyton Pipebridge | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2027-07-20 | 2028-07-17 | 2028-09-11 | 2029-05-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_M&G | 100%
503212 | Skellyton WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-12-14 | 2024-09-12 | 2024-12-10 | 2025-09-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 76112.23 | 52991.4 | 14315.37 | 143419 | 1856581.33 | 0 | 0 | 2000000.33 | 0 | 0 | 0 | 0 | 2000000.33 | 122419.09 | [5 empty] | N | SG1 | 100%
505949 | Skellyton WwTW SR10 Outstanding CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2020-10-19 | 2023-01-27 | 2023-06-01 | 2024-08-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1172.64 | 1172.64 | 1330318 | 0 | 0 | 1331490.64 | 0 | 0 | 0 | 0 | 1331490.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501205 | Skerries WTW- QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS6 | 2017-03-28 | 2017-12-27 | 2018-09-21 | 2019-12-31 | 2020-03-31 | Shetland Islands | 0 | 0 | 1710.33 | 11767.64 | 44307.11 | 68078.73 | 156875.82 | -23451.68 | 259287.95 | 85.68 | 85.68 | 118.9384 | 259373.63 | 33.2584 | 0 | 0 | 33.2584 | 259406.8884 | 62107.87 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
403402 | Skye and Lochaber Area - Removal of Small Diameter AC Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-04-27 | 2013-04-27 | 2014-08-19 | 2015-10-07 |  | Highland | 182976.33 | 0 | 9713.72 | 85.2 | 0 | 0 | 0 | 0 | 9798.92 | 1074.69 | 0 | 0 | 193849.94 | 0 | 0 | 0 | 0 | 193849.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503658 | Sludge Management - Stabilisation of Monitoring Systems | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2019-09-18 | 2019-09-18 | 2019-09-18 | 2020-11-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 409032.54 | 80885.38 | 489917.92 | 0 | 0 | 0 | 489917.92 | 0 | 0 | 0 | 0 | 489917.92 | 306661.32 | [5 empty] | N | CM_M&G | 100%
501300 | Sludge Management Systems Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-02 | 2017-05-26 | 2017-05-26 | 2017-04-04 |  | Scottish Water Wide | 0 | 0 | 21300 | -299.13 | -58.24 | 0 | 0 | 0 | 20942.63 | 0 | 0 | 0 | 20942.63 | 0 | 0 | 0 | 0 | 20942.63 | 306661.32 | [5 empty] | N | CM_M&G | 100%
501283 | Small Value Holding Line - SR15 Yr2-6 -Wastewater - Managed Delivery | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-15 | 2021-02-01 |  | 2021-02-01 |  | Scottish Water Wide | 0 | 0 | 0 | 131.08 | 0 | 0 | 0 | -131.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWI | 34% | CM_WWNI | 66%
501284 | Small Value Holding Line - SR15 Yr2-6 -Wastewater - Scottish Water Delivery | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-15 | 2021-02-01 |  | 2021-02-01 |  | Scottish Water Wide | 0 | 0 | 92.23 | 0 | 0 | 140.88 | 0 | -233.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWI | 34% | CM_WWNI | 66%
502959 | Smith Place Dumfries - Sewer Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2027-04-01 | 2027-04-01 | 2027-06-11 | 2028-01-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000.03 | 0 | 0 | 350000.03 | 0 | 0 | 0 | 0 | 350000.03 | 209381.79 | [5 empty] | N | CM_WWI | 100%
401883 | SOA Foundation Environment Build and TGS | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-03-10 | 2011-04-04 | 2011-04-04 | 2014-06-06 |  | Scottish Water Wide | 2113143.51 | 0 | -4028 | 0 | 0 | 0 | 0 | 0 | -4028 | 0 | 0 | 0 | 2109115.51 | 0 | 0 | 0 | 0 | 2109115.51 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403868 | SOA Rebuild | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-08-20 | 2014-12-19 | 2014-12-19 | 2015-07-07 |  | Scottish Water Wide | 2165495 | 0 | -258737.66 | 0 | 0 | 0 | 0 | 0 | -258737.66 | 0 | 0 | 0 | 1906757.34 | 0 | 0 | 0 | 0 | 1906757.34 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403043 | Sollas AC Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-13 | 2012-12-17 | 2013-04-29 |  | Na H-Eileanan an Iar | 147648 | 0 | 155.03 | 0 | 0 | 0 | 0 | 0 | 155.03 | 0 | 0 | 0 | 147803.03 | 0 | 0 | 0 | 0 | 147803.03 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501317 | South SPS MCC Replacement Ph 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS4 | 2017-02-27 | 2018-06-05 | 2018-09-03 | 2020-12-14 |  | Scottish Water Wide | 0 | 0 | 0 | 55035.59 | 58430.41 | 451894 | 90200.32 | 68559.68 | 724120 | 0 | 0 | 0 | 724120 | 0 | 0 | 0 | 0 | 724120 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400818 | South Area Network Infiltration Investigations Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-05-18 | 2012-03-27 | 2012-03-27 | 2012-03-30 |  | North Lanarkshire | 61726.93 | 0 | 0 | 0 | 1421.47 | 0 | 0 | 0 | 1421.47 | 0 | 0 | 0 | 63148.4 | 0 | 0 | 0 | 0 | 63148.4 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507772 | South Building Conditions Interventions | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS2 |  | 2020-07-21 | 2021-04-02 | 2021-08-23 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 22000 | 58000 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 80000 | 306661.32 | [5 empty] | N | CM_M&G | 100%
511310 | South Calder Way Cascade Sewer. Newmains | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-03-04 | 2023-09-12 | 2023-12-11 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31830.47 | 31830.47 | 268169.53 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | [5 empty] | N | SR21_WW | 100%
500509 | South Edinburgh Service Resilience | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | WINF | Supply Resilience | MS3 | 2016-03-23 | 2018-02-26 | 2018-03-26 | 2021-08-24 | 2021-11-19 | All South Unitary Authorities | 0 | 0 | 131852.98 | 341784.02 | 1923969 | 9660635.41 | 9478374.14 | 2108102.19 | 23644717.74 | 113036.75 | 113036.75 | 2370466.2437 | 23757754.49 | 2257429.4937 | 0 | 0 | 2257429.4937 | 26015183.9837 | 5935596.51 | [5 empty] | Y | CS16WR | 100% | [24 empty] | 1 | [42 empty] | 0
511388 | South Harbour Street Ayr - Emergency works - 120K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2021-02-24 |  | 2021-03-24 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94485.86 | 94485.86 | 25514.14 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 120000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502567 | South Hoy WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS4 | 2021-01-05 | 2021-01-05 | 2021-01-18 | 2021-01-18 |  | Orkney Islands | 0 | 0 | 0 | 20930.23 | 3708.12 | 99061.71 | 24608.98 | 6688.32 | 154997.35 | 0 | 0 | 0 | 154997.35 | 0 | 0 | 0 | 0 | 154997.35 | 122419.09 | [5 empty] | N | WG1 | 100%
500931 | South Lanarkshire Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2016-11-04 | 2016-11-04 | 2016-10-25 | 2016-11-04 | South Lanarkshire | 0 | 0 | 8001.06 | 490.05 | 0 | 0 | 0 | 0 | 8491.11 | 0 | 0 | 0 | 8491.11 | 0 | 0 | 0 | 0 | 8491.11 | 106252.93 | [5 empty] | N | FL_DD | 100%
500700 | South Medwyn RW Pipeline - Landslides & Pipe Supports | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-08-03 | 2016-07-27 | 2016-08-17 | 2017-10-26 |  | Scottish Borders | 0 | 0 | 4080 | 60431.06 | 128235.66 | 9220.18 | 0 | -1382.84 | 200584.07 | 0 | 0 | 0 | 200584.07 | 0 | 0 | 0 | 0 | 200584.07 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500874 | South Moorhouse RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-09-20 | 2018-09-26 | 2018-12-03 | 2019-06-30 | 2020-03-31 | East Renfrewshire | 0 | 0 | 10252.59 | 12747.41 | 35476.14 | 135071.89 | 81760.84 | 537.13 | 275846 | 2000 | 2000 | 2776.3405 | 277846 | 776.3405 | 0 | 0 | 776.3405 | 278622.3405 | 451751.94 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 86.77 | [43 empty] | 0
503286 | South Queensferry WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-05-04 | 2025-02-25 | 2025-05-27 | 2026-06-30 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 75860.69 | 139.95 | 25203.82 | 101204.46 | 1898795.55 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 122419.09 | [5 empty] | N | SG1 | 100%
511480 | South Repair-Refurb-Replace DMA Meters and Loggers RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-29 | 2021-04-01 | 2022-07-01 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23551.4 | 23551.4 | 336448.6 | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 360000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403193 | South SVCM CID WWI Improvements Yr 3-4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-14 | 2013-04-25 | 2013-08-12 | 2015-01-26 |  | All South Unitary Authorities | 105295 | 0 | -3580.5 | 0 | 0 | 0 | 0 | 0 | -3580.5 | 0 | 0 | 0 | 101714.5 | 0 | 0 | 0 | 0 | 101714.5 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403044 | South Uist WOA - Bornish to Mingarraidh junction. AC Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-13 | 2012-12-03 | 2013-10-01 |  | Na H-Eileanan an Iar | 198401.69 | 0 | 19.77 | 0 | 0 | 0 | 0 | 0 | 19.77 | 0 | 0 | 0 | 198421.46 | 0 | 0 | 0 | 0 | 198421.46 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503082 | South Uist WTW New Source | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS1 | 2015-11-02 | 2022-12-15 | 2023-01-25 | 2024-07-18 | 2025-09-25 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 16149.58 | 38587.42 | 193062.82 | 79644.18 | 327444 | 10172556.5 | 10172556.5 | 14121240.2558 | 10500000.5 | 3948683.7558 | 0 | 0 | 3948683.7558 | 14448684.2558 | 7560411.92 | [5 empty] | N | DW3B | 7.484% | DW3C | 7.484% | WG4 | 24.95% | DW25P | 60.08%
403594 | South Wastewater Treatment - Health and Safety Interventions (Various) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-10-02 | 2013-10-02 | 2013-10-02 | 2015-09-01 |  | All South Unitary Authorities | 430299.85 | 0 | 48331.02 | 0 | 0 | 0 | 0 | 0 | 48331.02 | 0 | 0 | 0 | 478630.87 | 0 | 0 | 0 | 0 | 478630.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501550 | South West Telemetry Radio Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-01-21 | 2016-02-29 | 2016-02-29 | 2016-11-21 |  | Scottish Water Wide | 0 | 0 | 157730.98 | 471676.93 | 0 | 0 | 0 | 0 | 629407.91 | 0 | 0 | 0 | 629407.91 | 0 | 0 | 0 | 0 | 629407.91 | 306661.32 | [5 empty] | N | CM_M&G | 100%
403067 | South WWCM Inlet screen refurbishment programme | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-10-16 | 2012-10-16 | 2012-10-16 | 2015-06-11 |  | All South Unitary Authorities | 520000 | 0 | 7824.56 | 0 | 0 | 0 | 0 | 0 | 7824.56 | 0 | 0 | 0 | 527824.56 | 0 | 0 | 0 | 0 | 527824.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502231 | South WWTW MCC Replacements Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS4 | 2017-06-29 | 2018-12-19 | 2019-03-04 | 2021-03-22 |  | Scottish Water Wide | 0 | 0 | 0 | 26001.93 | 159111.07 | 1052348 | 2145455.91 | 372709.1 | 3755626 | 118728.8 | 0 | 0 | 3874354.8 | 0 | 0 | 325645.2 | 325645.2 | 4200000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
30891 | South Yell - Mid Yell and Cullivoe WTWs - Upgrade (incl 30524 - 30169) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2006-06-07 | 2007-09-26 | 2007-11-30 | 2012-03-26 | 2012-03-30 | Shetland Islands | 8603592.02 | 0 | 30559.38 | 0 | 0 | 0 | 0 | 0 | 30559.38 | 0 | 0 | 0 | 8634151.4 | 0 | 0 | 0 | 0 | 8634151.4 | 119022.58 | [5 empty] | N | DW13 | 19% | DW2 | 19% | DW3G | 19% | WSNI | 43%
45415 | Southdean Mill WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-12-20 | 2012-07-30 | 2013-05-29 | 2013-08-22 | Scottish Borders | 940494.06 | 0 | -24762.39 | 0 | 0 | 0 | 0 | 0 | -24762.39 | 0 | 0 | 0 | 915731.67 | 0 | 0 | 0 | 0 | 915731.67 | 28761.13 | [5 empty] | N | DW23 | 100%
501599 | Southpark Avenue Barrhead - Repair Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-01-19 | 2019-02-25 | 2019-03-25 | 2021-05-24 |  | Renfrewshire | 0 | 0 | 0 | 11388 | 197363.19 | 344702.81 | 1614005 | 554566 | 2722025 | 2248 | 0 | 0 | 2724273 | 0 | 0 | 275727 | 275727 | 3000000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507471 | Spean Bridge Developments - Water Infrastructure | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS2 |  | 2020-08-11 |  | 2021-05-01 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122999.93 | 0 | 0 | 122999.93 | 0 | 0 | 0 | 0 | 122999.93 | 0 | [5 empty] | N | WG5 | 100%
403529 | Spence Court East Kilbride | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-07-12 | 2014-12-16 | 2015-01-05 | 2016-03-22 | 2016-04-01 | South Lanarkshire | 318870 | 318870 | 54633 | 45497 | 0 | -4115.9 | 0 | 0 | 96014.1 | 0 | 0 | 0 | 414884.1 | 0 | 0 | 0 | 0 | 414884.1 | 180449.74 | [5 empty] | N | FL_DD | 100%
503340 | Spey Abstraction Scheme - Emergency Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2018-10-02 | 2018-10-02 | 2018-10-08 | 2019-06-26 |  | Moray | 0 | 0 | 0 | 0 | 0 | 1085031.12 | -94925.59 | 778.54 | 990884.07 | 0 | 0 | 0 | 990884.07 | 0 | 0 | 0 | 0 | 990884.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
45614 | Spey Scheme (Badentinan) WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-07-13 | 2014-01-08 | 2014-03-21 | Moray | 627236.87 | 0 | 2006.11 | 0 | 0 | 0 | 0 | 0 | 2006.11 | 0 | 0 | 0 | 629242.98 | 0 | 0 | 0 | 0 | 629242.98 | 28761.13 | [5 empty] | N | DW1A | 100%
402355 | Spiral Membrane Supply Incident | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2011-08-26 | 2011-08-26 | 2011-08-26 | 2015-09-30 |  | Scottish Water Wide | 1188218 | 0 | 44582.08 | 0 | 0 | 0 | 0 | 0 | 44582.08 | 0 | 0 | 0 | 1232800.08 | 0 | 0 | 0 | 0 | 1232800.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400927 | Sponsorship of MGSDP and GSS Project | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-04-21 | 2013-05-08 | 2013-05-09 | 2018-06-22 | 2011-03-14 | Glasgow City | 301676.37 | 0 | 6000.63 | 0.44 | 0 | -1125.03 | 0 | 0 | 4876.04 | 0 | 0 | 0 | 306552.41 | 0 | 0 | 0 | 0 | 306552.41 | 0 | [5 empty] | N | EC04C | 33.33% | EC10E | 33.33% | EC01D | 33.34%
502830 | Springbank Alyth Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2018-03-29 | 2018-11-21 | 2019-04-01 | 2019-08-29 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 13684.4 | 51221.6 | 130094 | 0 | 195000 | 0 | 0 | 0 | 195000 | 0 | 0 | 0 | 0 | 195000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500784 | Springfield WwTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-09-07 | 2019-02-01 | 2019-03-29 | 2021-04-23 |  | Fife | 0 | 0 | 108131 | 100990 | 204703.93 | 659425.76 | 1368640.31 | 962286 | 3404177 | 53232 | 0 | 0 | 3457409 | 0 | 0 | 345741 | 345741 | 3803150 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504671 | Springfield WWTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-09-15 | 2020-09-15 | 2020-09-15 | 2020-11-26 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18023.69 | 18023.69 | 0 | 0 | 0 | 18023.69 | 0 | 0 | 0 | 0 | 18023.69 | 122419.09 | [5 empty] | N | SG1 | 100%
504129 | Springhill Farm WWPS - Site Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2021-09-15 | 2023-04-07 | 2023-07-07 | 2024-05-13 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1904.64 | 29895.36 | 31799.99 | 568199.94 | 0 | 0 | 599999.93 | 0 | 0 | 0 | 0 | 599999.93 | 209381.79 | [5 empty] | N | WWI | 100%
503287 | Springholm WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-04-20 | 2023-09-01 | 2024-01-04 | 2025-01-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 65954.87 | 96.89 | 28754.25 | 94806 | 1905194.29 | 0 | 0 | 2000000.29 | 0 | 0 | 0 | 0 | 2000000.29 | 122419.09 | [5 empty] | N | SG1 | 100%
401739 | SPS - Critical Assets Data Quality Testing and Remedials - Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2011-01-10 | 2011-05-16 | 2011-06-15 | 2016-01-27 |  | Scottish Water Wide | 212157 | 0 | -2222.44 | 0 | 0 | 0 | 0 | 0 | -2222.44 | 0 | 0 | 0 | 209934.56 | 0 | 0 | 0 | 0 | 209934.56 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
501362 | SPS 1881 Prestonpans WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-07-19 | 2017-07-17 | 2018-01-08 | 2019-03-14 |  | East Lothian | 0 | 0 | 0 | 32194 | 516016 | 414115 | 29491 | -22904.16 | 968911.84 | 22904.16 | 0 | 0 | 991816 | 0 | 0 | 0 | 0 | 991816 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502406 | SPS Data Quality Priority and Remedials Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS0 | 2017-11-07 | 2022-04-18 | 2024-08-14 | 2025-09-12 |  | Scottish Water Wide | 0 | 0 | 0 | 2814.95 | 22170.17 | 40406.71 | 2135.57 | 62.94 | 67590.34 | 143970.54 | 0 | 0 | 211560.88 | 0 | 0 | 0 | 0 | 211560.88 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
501364 | SPS001544 East Mains WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-08-29 | 2020-03-18 | 2020-06-17 | 2019-07-12 |  | South Lanarkshire | 0 | 0 | 0 | 21521 | -8673 | 0 | -714.77 | 0 | 12133.23 | 0 | 0 | 0 | 12133.23 | 0 | 0 | 0 | 0 | 12133.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
404066 | SR 15 ES - Milngavie WOA M5 Mugdock WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-01-05 | 2015-07-30 | 2015-10-12 | 2020-03-31 |  | Glasgow City | 50457 | 0 | 1141083.7 | 1947685.3 | 2718082 | 829969.89 | -38443.14 | -26671.27 | 6571706.48 | 5000 | 0 | 0 | 6627163.48 | 0 | 0 | 0 | 0 | 6627163.48 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404005 | SR 15 ES - PSCD Newmore Raw Water Main - Close Proximity Diversions | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water | SW | SWD | Exceptional Capital Maintenance | MS5 | 2020-07-01 | 2020-09-14 | 2020-09-14 | 2020-09-16 | 2020-11-06 | Highland | 244 | 0 | 53159 | 42940 | 103126 | 3777.07 | 384.62 | -10085.14 | 193301.55 | 0 | 0 | 0 | 193545.55 | 0 | 0 | 0 | 0 | 193545.55 | 0 | [5 empty] | N | SR15_EXC_EXC | 100%
404081 | SR 15 ES - W298-SW325-SW326 Byres Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2015-07-27 | 2020-12-10 | 2021-02-12 | 2022-01-11 | 2022-02-28 | Glasgow City | 0 | 0 | 30000 | 0 | 3894 | 13106 | 10937.5 | 53682.67 | 111620.17 | 755157.83 | 0 | 0 | 866778 | 0 | 0 | 0 | 0 | 866778 | 175086.76 | [5 empty] | N | FL_DD | 100%
500438 | SR 15 SWD SVCW Waste East Infra | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-03-03 |  | All East Unitary Authorities | 0 | 0 | 865019.51 | 101287.61 | -72858.42 | 0 | 0 | 0 | 893448.7 | 0 | 0 | 0 | 893448.7 | 0 | 0 | 0 | 0 | 893448.7 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501951 | SR 15 Western Isles SR Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-02-15 | 2016-02-15 | 2016-04-26 | 2022-04-29 |  | All North Unitary Authorities | 0 | 0 | 435588.61 | 1029390.99 | 381953.9 | 178775.04 | 8858.25 | 73839.5 | 2108406.29 | 403276 | 0 | 0 | 2511682.29 | 0 | 0 | 0 | 0 | 2511682.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507952 | SR 21 Castle Moffat coagulant dosing H&S | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-06-24 | 2024-05-10 | 2024-10-18 | 2026-05-01 | 2026-08-03 | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58796.23 | 58796.23 | 1464460.16 | 0 | 0 | 1523256.39 | 0 | 0 | 0 | 0 | 1523256.39 | 0 | [5 empty] | N | SR21_WA | 100%
504210 | SR Bacti WQ Instruments | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-21 | 2021-04-02 | 2021-04-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 102647.17 | 79217.22 | 181864.39 | -2202.59 | 0 | 0 | 179661.8 | 0 | 0 | 0 | 0 | 179661.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400921 | SR Data Quality | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2010-06-02 | 2011-01-18 | 2011-01-18 | 2016-06-07 |  | Scottish Water Wide | 1057007 | 0 | 53761 | -54375.89 | 0 | -89697.58 | 0 | 0 | -90312.47 | 0 | 0 | 0 | 966694.53 | 0 | 0 | 0 | 0 | 966694.53 | 306661.32 | [5 empty] | N | CM_WWNI | 100%
500079 | SR Level Controls - New | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-02-27 | 2015-03-25 | 2015-03-25 | 2017-08-18 |  | Scottish Water Wide | 0 | 0 | 152689 | -94078 | -7556.63 | 0 | 0 | 0 | 51054.37 | 0 | 0 | 0 | 51054.37 | 0 | 0 | 0 | 0 | 51054.37 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500083 | SR Level Controls - Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-27 | 2015-03-25 | 2015-03-25 | 2021-07-30 |  | Scottish Water Wide | 0 | 0 | 119135 | 74295 | 34778 | 66734 | 52374 | 45890 | 393206 | 0 | 0 | 0 | 393206 | 0 | 0 | 0 | 0 | 393206 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503874 | SR Mission Simple Repairs T3 East C Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2019-12-02 | 2020-02-03 | 2021-05-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 629788 | 649788 | 27487.9 | 0 | 0 | 677275.9 | 0 | 0 | 0 | 0 | 677275.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503833 | SR Mission Simple Repairs T3 East D Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2019-11-28 | 2020-02-03 | 2021-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 35342.16 | 200520.84 | 235863 | 32887.3 | 0 | 0 | 268750.3 | 0 | 0 | 0 | 0 | 268750.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503836 | SR Mission Simple Repairs T3 East E Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2019-12-02 | 2020-02-03 | 2021-07-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 12735.95 | 212741.05 | 225477 | 43273.04 | 0 | 0 | 268750.04 | 0 | 0 | 0 | 0 | 268750.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504740 | SR Mission Simple Repairs T3 South B Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-27 | 2020-02-03 | 2022-04-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 34881 | 50881 | 199119.07 | 0 | 0 | 250000.07 | 0 | 0 | 0 | 0 | 250000.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504317 | SR Mission Simple Repairs T3 West B Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2019-12-20 | 2020-02-03 | 2021-05-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 97663.39 | 174441.61 | 272105 | 47400.86 | 0 | 0 | 319505.86 | 0 | 0 | 0 | 0 | 319505.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508872 | SR Mission Simple Repairs T3 West C | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-09-29 | 2020-10-05 | 2021-02-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88100 | 88100 | 142.86 | 0 | 0 | 88242.86 | 0 | 0 | 0 | 0 | 88242.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
37714 | SR06 Water Resource Strategic Studies - WFD Implementation Stage (SW Initiated CAR Licence) | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-02 | 2013-07-11 | 2008-12-02 | 2008-12-02 | 2011-01-01 | Scottish Water Wide | 327104 | 0 | 2586.48 | 440.93 | 0 | 0 | 0 | 0 | 3027.41 | 0 | 0 | 0 | 330131.41 | 0 | 0 | 0 | 0 | 330131.41 | 28761.13 | [5 empty] | N | WR1 | 100%
400609 | SR10 Access Land Reform | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2004-03-30 | 2010-06-07 | 2010-06-07 | 2015-10-01 |  | Scottish Water Wide | 41631 | 0 | -3537.58 | 0 | 0 | 0 | 0 | 0 | -3537.58 | 0 | 0 | 0 | 38093.42 | 0 | 0 | 0 | 0 | 38093.42 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403041 | SR10 Back Tolsta WOA - Stage 2 Additional Re-hab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-26 | 2013-03-25 | 2013-04-25 | 2014-11-03 |  | Na H-Eileanan an Iar | 206343 | 0 | 0 | -1718.41 | 0 | 0 | 0 | 0 | -1718.41 | 0 | 0 | 0 | 204624.59 | 0 | 0 | 0 | 0 | 204624.59 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402532 | SR10 EAST SR Inlet Control New Installations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-02-09 | 2012-02-09 | 2012-04-02 | 2015-06-15 |  | Scottish Water Wide | 238970 | 0 | -25768.73 | 0 | 0 | 0 | 0 | 0 | -25768.73 | 0 | 0 | 0 | 213201.27 | 0 | 0 | 0 | 0 | 213201.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400610 | SR10 Legacy Legal Liabilities | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-30 | 2014-06-23 | 2014-06-24 | 2015-12-08 |  | Scottish Water Wide | 750000 | 0 | -57291.57 | 0 | 42515 | 0 | 0 | 0 | -14776.57 | 0 | 0 | 0 | 735223.43 | 0 | 0 | 0 | 0 | 735223.43 | 613322.63 | [5 empty] | N | CM_M&G | 100%
402459 | SR10 Low Pressure Boundary Box Installations | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-02-22 | 2012-09-27 | 2012-09-28 | 2014-03-11 | 2014-03-27 | Scottish Water Wide | 28434.08 | 0 | 860 | 0 | 0 | 0 | 0 | 0 | 860 | 0 | 0 | 0 | 29294.08 | 0 | 0 | 0 | 0 | 29294.08 | 0 | [5 empty] | N | CS1 | 100%
400261 | SR10 Low Pressure Enhancement Cluster 1 Projects | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-02-09 | 2012-03-05 | 2014-03-28 | 2013-11-07 | All East Unitary Authorities | 142000 | 0 | 0 | -999.84 | 0 | 0 | 0 | 0 | -999.84 | 0 | 0 | 0 | 141000.16 | 0 | 0 | 0 | 0 | 141000.16 | 339997.92 | [5 empty] | N | CM_WSI | 29.08% | CS1 | 70.92%
400262 | SR10 Low Pressure Enhancement Cluster 2 Projects | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-01-30 | 2012-02-14 | 2016-11-15 | 2015-03-09 | Aberdeenshire | 353098.8 | 0 | 3747.2 | 21351.73 | 10130.77 | -93.4 | 0 | 0 | 35136.3 | 0 | 0 | 0 | 388235.1 | 0 | 0 | 0 | 0 | 388235.1 | 28761.13 | [5 empty] | N | CS1 | 100%
400263 | SR10 Low Pressure Enhancement Cluster 3 Projects | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2011-01-18 | 2011-02-07 | 2013-09-30 | 2013-03-31 | Highland | 357574 | 0 | -1793.51 | 0 | 0 | 0 | 0 | 0 | -1793.51 | 0 | 0 | 0 | 355780.49 | 0 | 0 | 0 | 0 | 355780.49 | 28761.13 | [5 empty] | N | CS1 | 100%
400264 | SR10 Low Pressure Enhancement Cluster 4 Projects | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2011-03-10 | 2011-03-14 | 2013-08-12 | 2013-08-20 | Perth and Kinross | 406748 | 0 | -4451.26 | 0 | 0 | 0 | 0 | 0 | -4451.26 | 0 | 0 | 0 | 402296.74 | 0 | 0 | 0 | 0 | 402296.74 | 28761.13 | [5 empty] | N | CS1 | 100%
400269 | SR10 Low Pressure Enhancement WSZ001013 Lochgilphead WSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-11-19 | 2013-03-12 | 2014-06-09 | 2014-03-19 | Argyll and Bute-North Argyll | 147536.55 | 0 | 147.65 | 0 | 0 | 0 | 0 | 0 | 147.65 | 0 | 0 | 0 | 147684.2 | 0 | 0 | 0 | 0 | 147684.2 | 28761.13 | [5 empty] | N | CS1 | 100%
400272 | SR10 Low Pressure Enhancement WSZ001467 Tobermory WSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2011-11-22 | 2012-03-05 | 2013-03-29 | 2013-03-29 | Argyll and Bute-North Argyll | 560049.77 | 0 | 181.4 | 0 | 0 | 0 | 0 | 0 | 181.4 | 0 | 0 | 0 | 560231.17 | 0 | 0 | 0 | 0 | 560231.17 | 28761.13 | [5 empty] | N | CS1 | 100%
400273 | SR10 Low Pressure Enhancement WSZ001495 Towerhill WSZ | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-06-29 | 2012-07-30 | 2013-01-15 | 2013-01-15 | Orkney Islands | 471168.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471168.67 | 0 | 0 | 0 | 0 | 471168.67 | 0 | [6 empty] | CS1 | 50% | DW5 | 50%
403999 | SR10 Membrane Replacement Purchase Code | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-11-21 | 2014-11-21 | 2014-11-24 | 2016-07-04 |  | Scottish Water Wide | 1479670 | 0 | 37191.44 | 0 | 0 | 0 | 0 | 0 | 37191.44 | 0 | 0 | 0 | 1516861.44 | 0 | 0 | 0 | 0 | 1516861.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400611 | SR10 Milngavie Reservoirs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-03-30 | 2013-03-05 | 2010-06-15 | 2015-10-01 |  | Scottish Water Wide | 204150 | 0 | -2511.5 | 0 | 0 | 0 | 0 | 0 | -2511.5 | 0 | 0 | 0 | 201638.5 | 0 | 0 | 0 | 0 | 201638.5 | 306661.32 | [5 empty] | N | CM_M&G | 100%
403042 | SR10 Ness WOA Swainbost Re-hab Stage 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-26 | 2013-08-22 | 2014-04-08 | 2015-03-03 |  | Na H-Eileanan an Iar | 295618 | 0 | 500 | -1676.36 | 0 | 0 | 0 | 0 | -1176.36 | 0 | 0 | 0 | 294441.64 | 0 | 0 | 0 | 0 | 294441.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46150 | SR10 New DAS Models | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2008-10-15 | 2010-03-24 | 2010-06-01 | 2015-03-11 |  | Scottish Water Wide | 452054 | 0 | 2544.13 | 0 | 0 | 0 | 0 | 0 | 2544.13 | 0 | 0 | 0 | 454598.13 | 0 | 0 | 0 | 0 | 454598.13 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400727 | SR10 NEW PRV Installs- Distribution Mains EAST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-22 | 2011-06-08 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 1318480.55 | 0 | 74517.32 | 13929.55 | 0 | 0 | 0 | 0 | 88446.87 | 0 | 0 | 0 | 1406927.42 | 0 | 0 | 0 | 0 | 1406927.42 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400728 | SR10 NEW PRV Installs- Distribution Mains WEST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-22 | 2011-06-06 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 1893371 | 0 | -57216.24 | 214.5 | 0 | 0 | 0 | 0 | -57001.74 | 0 | 0 | 0 | 1836369.26 | 0 | 0 | 0 | 0 | 1836369.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400729 | SR10 New PRV Installs- Trunk Mains EAST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-22 | 2011-06-09 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 204535 | 0 | -70.85 | 0 | 0 | 0 | 0 | 0 | -70.85 | -6553 | 0 | 0 | 197911.15 | 0 | 0 | 0 | 0 | 197911.15 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400726 | SR10 New PRV Installs- Trunk Mains WEST LEAKAGE DELIVERY AREA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-22 | 2011-06-06 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 257228 | 0 | -47486.49 | 0 | 0 | 0 | 0 | 0 | -47486.49 | 0 | 0 | 0 | 209741.51 | 0 | 0 | 0 | 0 | 209741.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400086 | SR10 New PVR Installs - Glasgow Trunk Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2009-12-17 | 2011-02-03 | 2011-04-04 | 2017-11-01 |  | Glasgow City | 538492 | 0 | 25363.01 | 66144.99 | -29590.36 | 0 | 0 | 0 | 61917.64 | 0 | 0 | 0 | 600409.64 | 0 | 0 | 0 | 0 | 600409.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400872 | SR10 Redundant Assets | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-21 | 2011-09-14 | 2011-09-14 | 2015-12-01 |  | Scottish Water Wide | 375022.09 | 0 | 73675 | 0 | 0 | 0 | 0 | 0 | 73675 | 0 | 0 | 0 | 448697.09 | 0 | 0 | 0 | 0 | 448697.09 | 613322.63 | [5 empty] | N | CM_M&G | 100%
400612 | SR10 Rural Landlord Liability | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-30 | 2010-06-15 | 2010-06-15 | 2015-10-01 |  | Scottish Water Wide | 448460 | 0 | -17155.07 | 0 | 0 | 0 | 0 | 0 | -17155.07 | 0 | 0 | 0 | 431304.93 | 0 | 0 | 0 | 0 | 431304.93 | 613322.63 | [5 empty] | N | CM_M&G | 100%
400752 | SR10 Service Reservoir Outlet Metering - New Installation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2011-06-30 | 2011-07-04 | 2015-07-02 |  | Scottish Water Wide | 272261 | 0 | -28507 | -6469 | -5307.29 | 0 | 0 | 0 | -40283.29 | 0 | 0 | 0 | 231977.71 | 0 | 0 | 0 | 0 | 231977.71 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400613 | SR10 Tenant Housing | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-30 | 2010-06-15 | 2010-06-15 | 2015-10-01 |  | Scottish Water Wide | 222390 | 0 | 4857.53 | 0 | 0 | 0 | 0 | 0 | 4857.53 | 0 | 0 | 0 | 227247.53 | 0 | 0 | 0 | 0 | 227247.53 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water | DWQR | SWD | SEMD | MS7 | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-09-01 | 2017-09-14 | Scottish Water Wide | 0 | 0 | 0 | 7194.94 | -2289.28 | 1723.76 | 0 | 0 | 6629.42 | 0 | 0 | 0 | 6629.42 | 0 | 0 | 0 | 0 | 6629.42 | 273508.41 | [5 empty] | N | DW9D | 100%
400750 | SR10 Trunk Main Metering - New Installation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2011-06-06 | 2011-06-20 | 2015-07-02 |  | Scottish Water Wide | 825774 | 0 | 12448.37 | 979.27 | 0 | 0 | 0 | 0 | 13427.64 | 0 | 0 | 0 | 839201.64 | 0 | 0 | 0 | 0 | 839201.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402531 | SR10 WEST SR Inlet Control New Installations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-02-07 | 2012-02-07 | 2012-04-02 | 2015-06-15 |  | Scottish Water Wide | 73297 | 0 | -4304.37 | 0 | 0 | 0 | 0 | 0 | -4304.37 | 0 | 0 | 0 | 68992.63 | 0 | 0 | 0 | 0 | 68992.63 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402505 | SR10 WWTW Odour Investigations | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2012-01-27 | 2012-05-16 | 2012-06-06 | 2013-05-23 |  | Scottish Water Wide | 53570.03 | 53570.03 | 0.97 | -974.87 | 0 | 0 | 0 | 0 | -973.9 | 0 | 0 | 0 | 52596.13 | 0 | 0 | 0 | 0 | 52596.13 | 0 | [5 empty] | N | QS4EQS | 100%
402740 | SR15 - Additional Support for Development of SR15 Capital Maintence Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2012-06-12 | 2012-12-10 | 2016-03-03 | 2016-03-03 |  | Scottish Water Wide | 621170.81 | 0 | -60854.82 | 0 | 0 | 0 | 0 | 0 | -60854.82 | 0 | 0 | 0 | 560315.99 | 0 | 0 | 0 | 0 | 560315.99 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502904 | SR15 - Blackwood WWTW CM Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2022-07-29 | 2024-06-05 | 2024-09-09 | 2025-11-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 36613.03 | 8653.26 | 1957.72 | 65853.71 | 113077.7 | 3389392.3 | 0 | 0 | 3502470 | 0 | 0 | 0 | 0 | 3502470 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500503 | SR15 Katrine | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-15 | 2021-06-04 |  | Scottish Water Wide | 0 | 0 | 102535.26 | 27164.74 | -28700 | 71568.58 | 78931.42 | 72124 | 323624 | 0 | 0 | 0 | 323624 | 0 | 0 | 0 | 0 | 323624 | 613322.63 | [5 empty] | N | CM_M&G | 100%
404067 | SR15 - Reactive & Opportunistic Lead Communication Pipe Replacement Programme | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS3 | 2015-06-15 | 2015-07-22 | 2015-07-22 | 2021-07-02 | 2021-05-07 | Scottish Water Wide | 0 | 0 | 36200 | 1252.6 | 0 | 154319.4 | 364321.4 | 29394.6 | 585488 | 390511.8 | 390511.8 | 542096.8613 | 975999.8 | 151585.0613 | 0 | 0 | 151585.0613 | 1127584.8613 | 0 | [5 empty] | N | DW1B | 100%
502302 | SR15 WW Temporary Chemical Dosing Systems Upgrade - Phase 4 (EAST) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2020-06-01 | 2022-01-14 | 2022-05-13 | 2023-08-01 |  | Scottish Water Wide | 0 | 0 | 0 | 38371.6 | 24145.73 | 2825.76 | 30184.33 | -2786.59 | 92740.82 | 2505009.96 | 0 | 0 | 2597750.78 | 0 | 0 | 0 | 0 | 2597750.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500962 | SR15 Aids to Navigation repair and replacement programme | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2015-12-09 | 2015-12-09 | 2016-01-05 | 2021-05-31 |  | Scottish Water Wide | 0 | 0 | 106216 | 5863 | 19156 | 2416 | 22081.23 | -17799.11 | 137933.12 | 0 | 0 | 0 | 137933.12 | 0 | 0 | 0 | 0 | 137933.12 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503581 | SR15 Asset Disposals (Finance) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS0 | 2019-05-20 | 2021-05-20 | 2022-02-21 | 2021-06-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4782.77 | -675.81 | 4106.97 | -3373.95 | 0 | 0 | 733.02 | 0 | 0 | 0 | 0 | 733.02 | 613322.63 | [5 empty] | N | CM_M&G | 100%
504207 | SR15 Balgray MIOS Phase 3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-01-22 | 2021-02-04 | 2021-06-10 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 2105.57 | 115959.43 | 118065 | 102935 | 0 | 0 | 221000 | 0 | 0 | 0 | 0 | 221000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511023 | SR15 BH Capital Maintenance - Provision of boxed spare pumps | Q&S4 | Sustaining existing high service for customers | Water non infrastructure |  |  | Water |  | SWD | Water non infrastructure | MS3 |  | 2021-02-25 | 2021-02-26 | 2021-05-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33243 | 33243 | 41757.42 | 0 | 0 | 75000.42 | 0 | 0 | 0 | 0 | 75000.42 | 119022.58 | [5 empty] | N | SR15_CMA_WSNI | 100%
500975 | SR15 Borehole Programme (Phase 1) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-11-26 | 2016-07-13 | 2016-09-07 | 2021-10-25 |  | Scottish Water Wide | 0 | 0 | 129944.09 | 936820.91 | 102512.78 | 395762.71 | 524873.39 | 168469.12 | 2258383 | 146811.15 | 0 | 0 | 2405194.15 | 0 | 0 | 0 | 0 | 2405194.15 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502274 | SR15 Borehole Programme (Phase 2B) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2020-06-18 | 2020-06-23 | 2020-06-26 | 2020-06-26 |  | Scottish Water Wide | 0 | 0 | 0 | 4500 | 24720.73 | 3721.76 | 12057.51 | -6487.97 | 38512.03 | 0 | 0 | 0 | 38512.03 | 0 | 0 | 0 | 0 | 38512.03 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500625 | SR15 Capital Overhead Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | -34702577.7 | -44115891.23 | -39541230.01 | -43137127.91 | -31292317.36 | -50962086.5 | -243751230.7 | 0 | 0 | 0 | -243751230.7 | 0 | 0 | 0 | 0 | -243751230.7 | 306661.32 | [5 empty] | N | CM_OVH | 100%
507450 | SR15 Clatto Cover Replacements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-14 | 2020-07-14 | 2020-11-23 |  | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1743.68 | 1743.68 | 0 | 0 | 0 | 1743.68 | 0 | 0 | 0 | 0 | 1743.68 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500936 | SR15 CMAP CSD Identified Sewer Rehabilitation Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-12-16 | 2015-12-16 | 2016-02-01 | 2016-06-29 |  | Scottish Water Wide | 0 | 0 | 933715.54 | 0 | 0 | 0 | 0 | 0 | 933715.54 | 0 | 0 | 0 | 933715.54 | 0 | 0 | 0 | 0 | 933715.54 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502283 | SR15 CMAP CSD Identified Sewer Rehabilitation Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-08-19 | 2016-08-19 | 2016-09-01 | 2017-04-06 |  | Scottish Water Wide | 0 | 0 | 0 | 900000.13 | 0 | 0 | 0 | 0 | 900000.13 | 0 | 0 | 0 | 900000.13 | 0 | 0 | 0 | 0 | 900000.13 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505763 | SR15 CMAP CSD Identified Sewer Rehabilitation Year 6 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2020-03-24 | 2020-03-31 | 2021-01-21 | 2021-05-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 836515 | 836515 | 63484.7 | 0 | 0 | 899999.7 | 0 | 0 | 0 | 0 | 899999.7 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502717 | SR15 CMAP CSD Identified Sewer Rehabilitation Year 3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-04-24 | 2017-04-24 | 2017-08-15 | 2018-08-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 829912.14 | 28758.87 | 0 | 0 | 858671.01 | 0 | 0 | 0 | 858671.01 | 0 | 0 | 0 | 0 | 858671.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503233 | SR15 CMAP CSD Identified Sewer Rehabilitation Year 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2019-08-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 860214.1 | 0 | 0 | 860214.1 | 0 | 0 | 0 | 860214.1 | 0 | 0 | 0 | 0 | 860214.1 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503561 | SR15 CMAP CSD Identified Sewer Rehabilitation Year 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2019-03-26 | 2019-03-26 | 2019-12-03 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 856726.32 | 0 | 856726.32 | 43273.68 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402734 | SR15 Cost Management Support | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-06-05 | 2012-08-07 | 2012-08-07 | 2015-11-02 |  | Scottish Water Wide | 346644.96 | 0 | 4293.72 | 0 | -1602.35 | 0 | 0 | 0 | 2691.37 | 0 | 0 | 0 | 349336.33 | 0 | 0 | 0 | 0 | 349336.33 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500582 | SR15 Energy Improvement Prog Accelerated Energy Consumption Reduction Prog (W & WW) | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater |  | SWD | Energy efficiency | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2017-04-13 | 2017-05-15 | Scottish Water Wide | 0 | 0 | 670608.82 | 434191.63 | -54695.79 | 0 | 0 | 0 | 1050104.66 | 0 | 0 | 0 | 1050104.66 | 0 | 0 | 0 | 0 | 1050104.66 | 1375666.49 | [5 empty] | N | I2S_WNI | 4.484% | I2S_WWNI | 95.52%
500488 | SR15 Enhanced Non Domestic Meter Replacement Programme | Q&S4 | Improving the customer experience | Meter Accuracy |  |  | Water |  | SWD | Meter Accuracy | MS3 | 2015-08-21 | 2017-02-16 | 2017-02-16 | 2021-05-21 | 2021-05-21 | Scottish Water Wide | 0 | 0 | 598398 | 3540587.47 | 2846271.62 | 3014742.91 | 2061519.36 | 1618709.64 | 13680229 | 787771.25 | 787771.25 | 1093560.6097 | 14468000.25 | 305789.3597 | 0 | 0 | 305789.3597 | 14773789.6097 | 6007068.75 | [5 empty] | N | CS4 | 100%
500648 | SR15 Environment Costs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS4 | 2015-09-02 | 2015-09-02 | 2015-09-02 | 2021-03-09 |  | Scottish Water Wide | 0 | 0 | 2254837 | 1460752.51 | 1795834.49 | 898486.43 | 290571.58 | 308620.99 | 7009103 | 0 | 0 | 0 | 7009103 | 0 | 0 | 0 | 0 | 7009103 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403962 | SR15 ES - 3 TWPs - West Area Cluster 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-05-08 | 2018-09-20 | 2018-09-24 | 2021-08-11 |  | All West Unitary Authorities | 416.92 | 0 | 56415.08 | 73026.3 | 168417.32 | 384498.78 | 108742.6 | 7299 | 798399.08 | 27215 | 0 | 0 | 826031 | 0 | 0 | 0 | 0 | 826031 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403961 | SR15 ES - 7 TWPs - West Area Cluster 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-07-06 | 2018-09-25 | 2018-10-02 | 2022-04-04 |  | All West Unitary Authorities | 1592 | 0 | 79112 | 90786.65 | 411886.8 | 750001.34 | 382583.11 | 288125.1 | 2002495 | 280421 | 0 | 0 | 2284508 | 0 | 0 | 0 | 0 | 2284508 | 119022.58 |  |  |  |  | 12828 | N | CM_WSNI | 100%
403124 | SR15 ES - Achmelvich WTW - Main out | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS7 | 2013-01-14 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Highland | 124761.87 | 124761.87 | 248383.46 | 745428.63 | 1239258.04 | 336579.23 | -20491.64 | 0 | 2549157.72 | 0 | 0 | 0 | 2673919.59 | 0 | 0 | 0 | 0 | 2673919.59 | 773016.66 | [5 empty] | Y | DW25P | 10% | DW2 | 90% | [16 empty] | 1 | [48 empty] | 0
403912 | SR15 ES - Ailsa Drive - Kirkintilloch | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2017-03-30 | 2020-02-17 | 2020-02-21 | 2020-10-30 | 2020-11-05 | East Dunbartonshire | 2862 | 2862 | 100419.25 | 198122.71 | 112857.57 | 96770.47 | 20067.72 | 13097.84 | 541335.56 | 0 | 0 | 0 | 544197.56 | 0 | 0 | 0 | 0 | 544197.56 | 1456386.61 | [5 empty] | N | EC01C | 100%
403332 | SR15 ES - Ailsa Road - Craig Street | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS2 | 2013-03-11 | 2019-08-27 | 2021-04-15 | 2021-11-25 | 2022-01-24 | North Lanarkshire | 153299.6 | 153299.6 | 151055.4 | 107149.83 | 41027.88 | -32532.71 | 58716.12 | 120609.88 | 446026.4 | -8791.55 | -8791.55 | -12204.1681 | 590534.45 | -3412.6181 | 0 | 0 | -3412.6181 | 587121.8319 | 1528054.73 | [5 empty] | N | FL_NAMED | 100%
403339 | SR15 ES - Airlie Street | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS7 | 2013-03-08 | 2015-10-01 | 2016-01-05 | 2021-01-25 | 2021-04-01 | Glasgow City | 48494.57 | 48494.57 | 322929.43 | 121396 | 2883 | -84190 | 90186 | -72929.31 | 380275.12 | 0 | 0 | 0 | 428769.69 | 0 | 0 | 0 | 0 | 428769.69 | 0 | [5 empty] | N | FL_NAMED | 100%
403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | SEPA | WINF | DWQ Compliance | MS4 | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2019-03-18 | 2022-12-16 | East Ayrshire | 184566.88 | 184566.88 | 11479642.12 | 31562741 | 10316182.69 | 990858.24 | 504557.21 | -1579788.56 | 53274192.71 | 16251 | 6987.93 | 40172.0521 | 53475010.59 | 33184.1221 | 0 | 42743.9615 | 75928.0836 | 53550938.6736 | 1644270.63 |  |  |  |  | 467820 | N | SR15_EXC_EXC | 4.3% | DW2 | 38.7% | CM_WSNI | 57%
403886 | SR15 ES - Assynt WTW - CWT Additional Storage | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | Highland | 5971.54 | 5971.54 | 10521.58 | -16374.67 | 72.56 | 0 | 0 | 0 | -5780.53 | 0 | 0 | 0 | 191.01 | 0 | 0 | 0 | 0 | 191.01 | 0 | [5 empty] | N | CS16W | 100%
403578 | SR15 ES - Assynt WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater | SEPA | SWMD | Sludge | MS7 | 2013-10-02 | 2015-03-26 | 2015-03-31 | 2015-11-30 | 2016-03-31 | Highland | 102089.25 | 102089.25 | 451535.75 | 289362.83 | 6160 | -4194.01 | 0 | 0 | 742864.57 | 0 | 0 | 0 | 844953.82 | 0 | 0 | 0 | 0 | 844953.82 | 0 | [5 empty] | Y | LA01 | 100% | [41 empty] | 1 | [25 empty] | 0
403132 | SR15 ES - Avonspark Street and Edgefauld Road Internal and External Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS7 | 2012-12-10 | 2015-06-25 | 2015-09-15 | 2017-03-16 | 2017-03-16 | Glasgow City | 272215 | 272215 | 2577916.96 | 613135.7 | 50348.75 | -4402.09 | 659.25 | 0 | 3237658.57 | 0 | 0 | 0 | 3509873.57 | 0 | 0 | 0 | 0 | 3509873.57 | 2185798.47 | [5 empty] | N | FL_NAMED | 100%
403989 | SR15 ES - Back Tolsta WTW - SR15 WQ Technical Expression Resolution | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-05-18 | 2018-01-23 | 2017-12-12 | 2017-12-12 | 2017-12-20 | Na H-Eileanan an Iar | 469.7 | 469.7 | 2055.3 | -2525 | 5691.23 | 70.44 | 593.33 | 0 | 5885.3 | 0 | 0 | 0 | 6355 | 0 | 0 | 0 | 0 | 6355 | 0 | [5 empty] | N | DW3B | 10% | DW25 | 90%
404037 | SR15 ES - Balmore South Region Nith WOA Brackenhirst WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-02-17 | 2017-06-30 | 2017-09-11 | 2019-09-16 |  | North Lanarkshire | 1240.88 | 0 | 9265.12 | 89805 | 740954 | 951091.8 | -100575.82 | 1583.02 | 1692123.12 | 0 | 0 | 0 | 1693364 | 0 | 0 | 0 | 0 | 1693364 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404036 | SR15 ES - Balmore South Region Nith WOA Dalmacoulter WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2027-05-10 | 2027-06-08 | 2029-03-01 |  | North Lanarkshire | 2572.61 | 0 | 9110.76 | 171397.63 | 64409 | -6074 | 3090.04 | -47004.63 | 194928.8 | 3318388.59 | 0 | 0 | 3515890 | 0 | 0 | 0 | 0 | 3515890 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403773 | SR15 ES - Balquhidder WTW manganese issues and Capital Maintenance work | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS7 | 2015-05-08 | 2016-03-30 | 2016-06-30 | 2017-06-30 | 2017-10-31 | Stirling | 464 | 315.52 | 87176 | 195777.05 | 114061.64 | -1638.08 | 12202.39 | -28373.69 | 379205.32 | 0 | 0 | 0 | 379669.32 | 0 | 0 | 0 | 0 | 379669.32 | 508423.93 | [5 empty] | Y | DW25P | 6.127% | CM_WSI | 19.61% | CM_WSNI | 74.27% | [17 empty] | 1 | [45 empty] | 0
403126 | SR15 ES - Bayhead WTW Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS5 | 2013-02-06 | 2016-07-22 | 2016-09-12 | 2019-09-30 | 2020-01-31 | Na H-Eileanan an Iar | 115146.46 | 115146.46 | 434026.54 | 1902777 | 179318 | 170104.64 | 105397.68 | 90044.68 | 2881668.54 | 0 | 0 | 0 | 2996815 | 0 | 0 | 0 | 0 | 2996815 | 0 | [5 empty] | Y | DW25 | 10% | DW3G | 20% | DW2 | 70% | [14 empty] | 1 | [48 empty] | 0
403699 | SR15 ES - Black Esk WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2014-03-31 | 2016-03-23 | 2016-03-28 | 2017-11-23 | 2021-10-08 | Dumfries and Galloway | 123564.93 | 88592.8201 | 334376.41 | 1263109.66 | 2469421.75 | 16588.2 | 1241.25 | 2153.92 | 4086891.19 | 14760.67 | 14760.67 | 20490.3229 | 4225216.79 | 5729.6529 | 0 | 0 | 5729.6529 | 4230946.4429 | 740960.62 |  |  |  |  | 8662 | N | DW3J | 9.313% | DW25P | 17.59% | DW3C | 73.1%
404052 | SR15 ES - Bradan WOA Bradan WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2028-06-06 | 2028-08-23 | 2029-01-02 |  | South Ayrshire | 960.29 | 0 | 1576.71 | 6608 | 0 | 54134 | -59060.53 | 0 | 3258.18 | 783221.66 | 0 | 0 | 787440.13 | 0 | 0 | 0 | 0 | 787440.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404051 | SR15 ES - Bradan WOA Stafflar WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2027-06-15 | 2027-07-07 | 2029-02-08 |  | South Ayrshire | 2137.71 | 0 | 170738.29 | 351711 | -313672.87 | 85515 | -32010.05 | 0.01 | 262281.38 | 1488491 | 0 | 0 | 1752910.09 | 0 | 0 | 0 | 0 | 1752910.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403821 | SR15 ES - Bradan WTW - Improving Drinking Water Quality Reliability | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS7 | 2015-07-16 | 2018-06-28 | 2018-06-22 | 2018-06-20 | 2018-06-28 | South Ayrshire | 133140.04 | 133140.04 | 177866.96 | -311007 | 471183.53 | -336267.16 | -387.78 | 0 | 1388.55 | -2443.74 | -2443.7425 | -3392.3306 | 132084.85 | -948.5881 | 0 | 0 | -948.5881 | 131136.2619 | 0 | [5 empty] | N | DW25 | 100%
403453 | SR15 ES - Bruichladdich Islay - provision of new septic tank and extend outfall | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2013-05-08 | 2015-02-27 | 2015-04-09 | 2015-07-31 | 2015-09-30 | Argyll and Bute-North Argyll | 128562 | 128562 | 99557.72 | 1185.91 | 12.36 | 0 | 0 | 0 | 100755.99 | 0 | 0 | 0 | 229317.99 | 0 | 0 | 0 | 0 | 229317.99 | 0 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
403333 | SR15 ES - Burnham Road | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2013-03-11 | 2017-04-07 | 2017-08-09 | 2016-10-11 | 2017-08-09 | Glasgow City | 54885 | 54885 | 7541 | 29116.75 | -8192.38 | 0 | 0 | 0 | 28465.37 | 0 | 0 | 0 | 83350.37 | 0 | 0 | 0 | 0 | 83350.37 | 1635990.1 | [5 empty] | N | FL_NAMED | 100%
403964 | SR15 ES - Camphill to Barcraigs Raw Water Transfer Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-07-23 | 2028-08-07 | 2028-09-07 | 2029-11-19 |  | North Ayrshire | 1369 | 0 | 52099 | -5027 | 740.47 | 5752.19 | 427.07 | 0 | 53991.73 | 2843732.27 | 0 | 0 | 2899093 | 0 | 0 | 0 | 0 | 2899093 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403703 | SR15 ES - Camps Road Carnock - Dunfermline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2014-03-17 | 2018-12-17 | 2019-02-28 | 2018-11-20 | 2018-11-20 | Fife | 90696 | 90696 | 25304 | 47801.81 | 32198.19 | 12726.65 | 0 | 0 | 118030.65 | 0 | 0 | 0 | 208726.65 | 0 | 0 | 0 | 0 | 208726.65 | 180449.74 | [5 empty] | N | FL_DD | 100%
403986 | SR15 ES - Carron Valley WTW Scada Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-07-06 | 2019-06-28 | 2019-09-02 | 2023-01-26 |  | Stirling | 4578 | 0 | 45522 | 61549.95 | 134763.29 | 270042.19 | 1253305.57 | 966122 | 2731305 | 1709194.26 | 0 | 0 | 4445077.26 | 0 | 0 | 554922.74 | 554922.74 | 5000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403340 | SR15 ES - Clarence Gardens | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS7 | 2013-03-08 | 2015-11-24 | 2016-04-04 | 2017-03-31 | 2017-03-31 | Glasgow City | 94114 | 94114 | 1388608 | 419184 | 9406.05 | 5933.65 | 1 | 0 | 1823132.7 | 0 | 0 | 0 | 1917246.7 | 0 | 0 | 0 | 0 | 1917246.7 | 904764.02 | [5 empty] | N | FL_NAMED | 100%
403985 | SR15 ES - Cochno Craigend Baljaffray SRs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-09-21 | 2020-09-21 | 2020-09-21 | 2019-05-07 |  | West Dunbartonshire | 457 | 0 | 154.96 | 6682.74 | 12781.92 | 0 | 0 | 0 | 19619.62 | 0 | 0 | 0 | 20076.62 | 0 | 0 | 0 | 0 | 20076.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404046 | SR15 ES - Craigendoran Helensburgh Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-02-03 | 2016-04-22 | 2016-04-08 | 2017-05-30 |  | Argyll and Bute-Cowal & Bute | 9046.26 | 0 | 1051930.74 | 1247733 | 1015124 | 26 | -16681.99 | 73.88 | 3298205.63 | 0 | 0 | 0 | 3307251.89 | 0 | 0 | 0 | 0 | 3307251.89 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403321 | SR15 ES - Craigneuk Avenue Airdrie Internal and External Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS3 | 2013-02-26 | 2020-09-24 | 2020-10-19 | 2022-05-24 | 2022-05-24 | North Lanarkshire | 219212 | 219212 | 108646 | 81632 | 12281 | 115328 | 828766.71 | 2995831.29 | 4142485 | 7084210.26 | 7084210.26 | 9589909.739 | 11445907.26 | 2505699.479 | 0 | 1.8626e-09 | 2505699.479 | 13951606.739 | 3900700.83 |  |  |  |  | 5180.0003 | N | FL_NAMED | 100%
403341 | SR15 ES - Crow Wood Terrace | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2013-03-11 | 2020-03-17 | 2020-01-06 | 2020-01-06 | 2021-04-01 | North Lanarkshire | 47744 | 47744 | 8110 | -608.41 | 60557.41 | 120197 | 82613.23 | -57792.75 | 213076.48 | 0 | 0 | 0 | 260820.48 | 0 | 0 | 0 | 0 | 260820.48 | 999635.37 | [5 empty] | N | FL_NAMED | 100%
404068 | SR15 ES - Customer Requested Lead Pipe Replacement | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS3 | 2015-03-19 | 2015-09-08 | 2015-10-01 | 2021-07-02 | 2021-03-29 | Scottish Water Wide | 0 | 0 | 500800 | 1118772.17 | 831609.17 | 607138.78 | 823410.55 | 805089.04 | 4686819.71 | 13180.29 | 13180.29 | 18296.4864 | 4700000 | 5116.1964 | 0 | 0 | 5116.1964 | 4705116.1964 | 2008341.65 | [5 empty] | N | DW1C | 100%
403822 | SR15 ES - Daer Network Disinfection Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2014-05-27 | 2015-12-04 | 2016-01-08 | 2017-03-31 | 2017-05-31 | South Lanarkshire | 268.29 | 268.29 | 63731.71 | 58000 | -694.21 | 652.6 | 0 | 0 | 121690.1 | 0 | 0 | 0 | 121958.39 | 0 | 0 | 0 | 0 | 121958.39 | 117323.06 | [5 empty] | Y | DW25TS | 100% | [64 empty] | 1 |  |  | 0
403517 | SR15 ES - Dalderse AAD - Recovering Value from Wastewater | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2013-08-20 | 2015-03-23 | 2015-03-23 | 2020-07-06 | 2020-07-06 | Falkirk | 187681 | 187681 | 8427.43 | 0 | 0 | 0 | 0 | 0 | 8427.43 | 0 | 0 | 0 | 196108.43 | 0 | 0 | 0 | 0 | 196108.43 | 0 | [5 empty] | N | EC06 | 100%
403696 | SR15 ES - Dealston Road Barrhead | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWMD | Flooding Named | MS7 | 2014-03-03 | 2014-12-05 | 2015-01-12 | 2015-09-28 | 2015-09-28 | East Renfrewshire | 731680 | 731680 | 160320 | 0 | 6568.36 | 0 | 0 | 0 | 166888.36 | 0 | 0 | 0 | 898568.36 | 0 | 0 | 0 | 0 | 898568.36 | 603995.95 | [5 empty] | N | FL_NAMED | 100%
404043 | SR15 ES - Deans 2 SPS Livingston Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-01-21 | 2016-01-11 | 2016-02-15 | 2016-04-22 |  | West Lothian | 762.62 | 0 | 143071.38 | 10671.53 | 358.8 | -2527.96 | 0 | 0 | 151573.75 | 0 | 0 | 0 | 152336.37 | 0 | 0 | 0 | 0 | 152336.37 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403074 | SR15 ES - DOMS level 2b (water quality) investigations in 13 zones | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2013-07-29 | 2013-12-20 | 2013-12-20 | 2015-04-08 | 2015-04-08 | Scottish Water Wide | 248517 | 248517 | -3112.38 | 0 | 0 | 0 | 0 | 0 | -3112.38 | 0 | 0 | 0 | 245404.62 | 0 | 0 | 0 | 0 | 245404.62 | 0 | [5 empty] | N | DW5A | 100%
403963 | SR15 ES - Dougliehill SR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS5 | 2015-07-06 | 2018-03-01 | 2018-03-16 | 2020-08-31 | 2021-03-31 | Renfrewshire | 903 | 0 | 119394 | 20772.71 | 320664.15 | 2240762.01 | 2136731.45 | -11531.32 | 4826793 | 126901 | 111964.7522 | 155426.1376 | 4954597 | 43461.3854 | 0 | 0 | 43461.3854 | 4998058.3854 | 544706.49 | [5 empty] | Y | CM_M&G | 3.7% | CM_WSNI | 8.07% | DW25 | 88.23% | [18 empty] | 1 | [44 empty] | 0
403695 | SR15 ES - Dumbarton Road (Clydebank Town Hall) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2014-04-09 | 2017-02-10 | 2016-06-28 | 2016-06-28 | 2017-02-10 | West Dunbartonshire | 8887 | 8887 | 113 | -6.49 | 0 | 0 | 0 | 0 | 106.51 | 0 | 0 | 0 | 8993.51 | 0 | 0 | 0 | 0 | 8993.51 | 145185.89 | [5 empty] | N | FL_NAMED | 100%
403223 | SR15 ES - E001 Glenmavis R-O 22 Glenwell ST CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2012-12-20 | 2015-12-18 | 2016-02-22 | 2016-07-31 | 2017-03-31 | North Lanarkshire | 69532.94 | 69532.94 | 168732.06 | 100767.23 | 1681.99 | -5603.92 | 0 | 0 | 265577.36 | 0 | 0 | 0 | 335110.3 | 0 | 0 | 0 | 0 | 335110.3 | 293378.6 | [5 empty] | Y | EC01F | 100% | [35 empty] | 4 | [31 empty] | 0
403224 | SR15 ES - E002 Glenmavis opp new Monkland Primary | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-05-21 | 2016-03-08 | 2016-06-23 | 2017-03-31 | North Lanarkshire | 20388.55 | 20388.55 | 45678.45 | 10898.6 | 0.02 | 1538.96 | 0 | 0 | 58116.03 | 0 | 0 | 0 | 78504.58 | 0 | 0 | 0 | 0 | 78504.58 | 293378.6 | [5 empty] | N | EC01F | 100%
403225 | SR15 ES - E003 Beechcroft WWPS NS685648 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2012-12-20 | 2015-07-23 | 2015-07-29 | 2015-08-11 | 2015-08-11 | Na H-Eileanan an Iar | 8010 | 8010 | -60.59 | -637.62 | 0 | 0 | -145.66 | 0 | -843.87 | 0 | 0 | 0 | 7166.13 | 0 | 0 | 0 | 0 | 7166.13 | 0 | [5 empty] | N | EC10B | 100%
403226 | SR15 ES - E004 DALDOWIE - Cluster 7 - Old Monkland 53-55 Woodside ST CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | SWMD | UWWTD - UID | MS6 | 2012-12-20 | 2018-11-21 | 2019-01-18 | 2019-02-28 | 2019-03-31 | North Lanarkshire | 8700.18 | 8700.18 | 3490.81 | 4084.86 | 53724.15 | 11816 | 669.33 | 36.65 | 73821.8 | 93.39 | 93.39 | 129.6412 | 82615.37 | 36.2512 | 0 | 0 | 36.2512 | 82651.6212 | 46023.48 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
403227 | SR15 ES - E005 Raebog Rd-Windsor Drive Dual Manhole | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2012-12-21 | 2019-07-22 | 2019-08-27 | 2020-03-17 | 2020-03-02 | North Lanarkshire | 10425.84 | 10425.84 | 61.56 | 2269.21 | 23243.39 | 22220 | 208229 | 1553 | 257576.16 | 1998 | 1998 | 2773.5642 | 270000 | 775.5642 | 0 | 0 | 775.5642 | 270775.5642 | 293378.6 | [5 empty] | N | EC01C | 100%
403228 | SR15 ES - E006 Raebog Rd Dual Manhole | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-05-20 | 2015-08-30 | 2016-06-23 | 2016-06-23 | North Lanarkshire | 80851 | 80851 | 800519 | 223218.25 | 8411.75 | -4571.44 | 0 | 0 | 1027577.56 | 0 | 0 | 0 | 1108428.56 | 0 | 0 | 0 | 0 | 1108428.56 | 293378.6 | [5 empty] | N | EC01C | 100%
403229 | SR15 ES - E007 190 Wraes View Gateside | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | SWMD | UWWTD - UID | MS7 | 2012-12-20 | 2015-10-09 | 2015-10-12 | 2015-10-31 | 2015-10-31 | East Renfrewshire | 4032 | 4032 | 111.61 | 0 | 0 | 0 | 0 | 0 | 111.61 | 0 | 0 | 0 | 4143.61 | 0 | 0 | 0 | 0 | 4143.61 | 0 | [5 empty] | Y | EC10B | 100% | [35 empty] | 2 | [31 empty] | 0
403230 | SR15 ES - E008 36 Vardar Avenue CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | SWMD | UWWTD - UID | MS7 | 2012-12-21 | 2015-08-27 | 2015-08-27 | 2015-08-31 | 2015-11-30 | East Renfrewshire | 32828 | 32828 | -635.43 | 0 | 0 | 0 | 0 | 0 | -635.43 | 0 | 0 | 0 | 32192.57 | 0 | 0 | 0 | 0 | 32192.57 | 0 | [5 empty] | Y | EC10B | 100% | [35 empty] | 1 | [31 empty] | 0
403231 | SR15 ES - E009 At rear of 9 Glasgow Road CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2012-12-20 | 2016-03-21 | 2016-03-29 | 2016-12-31 | 2017-03-31 | Renfrewshire | 24966.1 | 24966.1 | 137033.9 | 503705.12 | -762.61 | 3947.28 | 0 | 0 | 643923.69 | 0 | 0 | 0 | 668889.79 | 0 | 0 | 0 | 0 | 668889.79 | 430077.7 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
403232 | SR15 ES - E010 Bankholm Place SPS CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2012-12-21 | 2017-03-27 | 2017-03-27 | 2016-09-12 | 2017-03-27 | East Renfrewshire | 38936 | 38936 | 3607.64 | -40950.01 | 317.9 | 49.31 | 0.5 | 0 | -36974.66 | 0 | 0 | 0 | 1961.34 | 0 | 0 | 0 | 0 | 1961.34 | 20016.79 | [5 empty] | N | EC01F | 100%
403233 | SR15 ES - E011 Busby WwPS (Bankholm Place) | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2012-12-21 | 2018-01-31 | 2018-01-31 | 2016-02-23 | 2018-01-31 | East Renfrewshire | 3657.39 | 3657.39 | 77.97 | 62.88 | 61.56 | 0 | 0 | 0 | 202.41 | 0 | 0 | 0 | 3859.8 | 0 | 0 | 0 | 0 | 3859.8 | 0 | [5 empty] | N | EC01B | 100%
403234 | SR15 ES - E012 Cartside Rd Pumping Station EO at New Housing Dev Outside No 21 Newford Grove | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2012-12-20 | 2016-03-31 | 2016-03-31 | 2018-07-31 | 2018-10-31 | East Renfrewshire | 41666 | 41666 | 332748 | 300030 | 1206760.65 | 386457.05 | 3096.31 | -780.39 | 2228311.61 | 0 | 0 | 0 | 2269977.61 | 0 | 0 | 0 | 0 | 2269977.61 | 297558.71 | [5 empty] | Y | EC01F | 100% | [35 empty] | 2 | [31 empty] | 0
403235 | SR15 ES - E013 Cartside Rd Pumping Station at New Housing Dev Outside No 21 Newford Grove | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2012-12-20 | 2015-02-25 | 2015-02-25 | 2015-02-26 | 2015-02-26 | East Renfrewshire | 5437.62 | 5437.62 | 1027.19 | -3700.97 | 0 | 0 | -0.7 | 0 | -2674.48 | 0 | 0 | 0 | 2763.14 | 0 | 0 | 0 | 0 | 2763.14 | 0 | [5 empty] | N | EC10B | 100%
403237 | SR15 ES - E015 Fishescoates Avenue CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-07-24 | 2015-09-01 | 2016-12-31 | 2017-03-31 | South Lanarkshire | 77028.21 | 77028.21 | 322971.79 | 35277 | 0 | -17784.96 | 0 | 0 | 340463.83 | 0 | 0 | 0 | 417492.04 | 0 | 0 | 0 | 0 | 417492.04 | 528067.42 | [5 empty] | Y | EC01F | 100% | [35 empty] | 3 | [31 empty] | 0
403238 | SR15 ES - E016 Field off North Park Avenue CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS3 | 2012-12-21 | 2019-11-04 | 2020-03-02 | 2021-08-16 | 2021-11-16 | Renfrewshire | 71950 | 71950 | -6946 | 16017.85 | 83978.15 | 138362 | 747533 | 506866.72 | 1485811.72 | 145782 | 145782 | 178446.8627 | 1703543.72 | 32664.8627 | 0 | 0 | 32664.8627 | 1736208.5827 | 396528.45 |  |  |  |  | 2970 | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
403239 | SR15 ES - E017 Gateside SPS EO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-05-18 | 2015-08-03 | 2015-09-07 | 2016-01-28 | South Lanarkshire | 6249 | 6249 | 29129 | 1609 | 769 | -940.03 | 0 | 0 | 30566.97 | 0 | 0 | 0 | 36815.97 | 0 | 0 | 0 | 0 | 36815.97 | 82476.76 | [5 empty] | N | EC01F | 100%
403240 | SR15 ES - E018 Hugh Murray Grove | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-08-06 | 2015-11-09 | 2016-08-31 | 2017-03-31 | South Lanarkshire | 109784.3 | 109784.3 | 1086326.7 | 268191 | -14511.82 | 1569.1 | 0 | 0 | 1341574.98 | 0 | 0 | 0 | 1451359.28 | 0 | 0 | 0 | 0 | 1451359.28 | 399121.3 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
403241 | SR15 ES - E019 Junction Of Speirsbridge Road and Rouken Glen Road CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2016-02-24 | 2016-03-31 | 2016-09-30 | 2017-03-31 | East Renfrewshire | 145218.94 | 145218.94 | 351196.06 | 543503 | 0 | -20315.03 | 0 | 0 | 874384.03 | 0 | 0 | 0 | 1019602.97 | 0 | 0 | 0 | 0 | 1019602.97 | 171646.02 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
403242 | SR15 ES - E020 Just off Florence Drive in the grass area CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | SWMD | UWWTD - UID | MS7 | 2012-12-20 | 2015-03-30 | 2015-03-30 | 2015-07-31 | 2015-11-30 | East Renfrewshire | 65947 | 65947 | -823.51 | 142.35 | 0 | 0 | 0 | 0 | -681.16 | 0 | 0 | 0 | 65265.84 | 0 | 0 | 0 | 0 | 65265.84 | 0 | [5 empty] | Y | EC10B | 100% | [35 empty] | 1 | [31 empty] | 0
403243 | SR15 ES - E021 Mains avenue rear off (Timbers) CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS6 | 2013-02-11 | 2018-05-25 | 2018-07-06 | 2019-02-28 | 2019-03-31 | East Renfrewshire | 82052 | 82052 | 37660 | 40158 | 170133 | 363640 | -10903.68 | 34.07 | 600721.39 | 3972.61 | 3972.61 | 5514.659 | 686746 | 1542.049 | 0 | 0 | 1542.049 | 688288.049 | 261224.8 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
403244 | SR15 ES - E022 21 Robslee Road CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SW | WWINF | UWWTD - UID | MS5 | 2013-02-18 | 2018-06-27 | 2018-08-17 | 2020-08-31 | 2021-02-28 | East Renfrewshire | 36223 | 36223 | 14990 | 23121 | 145959 | 2094062 | 1351943.06 | 277469.94 | 3907545 | 2286 | 2286 | 3173.3572 | 3946054 | 887.3572 | 0 | 0 | 887.3572 | 3946941.3572 | 736772.65 |  |  |  |  | 5964 | Y | FL_NAMED | 49.19% | EC01F | 50.81% | [33 empty] | 4 | [31 empty] | 0
403245 | SR15 ES - E023 Rear of gardens at Moorburn Avenue No 41 CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-13 | 2018-06-27 | 2018-06-27 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 14875 | 14875 | -1968.8 | 293.8 | 707 | -221 | -246.96 | 0 | -1435.96 | 0 | 0 | 0 | 13439.04 | 0 | 0 | 0 | 0 | 13439.04 | 216640.81 | [5 empty] | N | EC01F | 100%
403246 | SR15 ES - E024 Rear of gardens at Moorburn Avenue No 51 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-13 | 2018-06-27 | 2018-06-27 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 14897 | 14897 | -1610 | -87 | 909 | -840.84 | -6.73 | 0 | -1635.57 | 0 | 0 | 0 | 13261.43 | 0 | 0 | 0 | 0 | 13261.43 | 216640.81 | [5 empty] | N | EC01F | 100%
403247 | SR15 ES - E025 On grass outside Our Lady of the Missions primary school off Wood Farm Road CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-18 | 2018-06-27 | 2018-06-27 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 5745 | 5745 | -698.56 | 153.56 | 601 | 1247.15 | 0 | 0 | 1303.15 | 0 | 0 | 0 | 7048.15 | 0 | 0 | 0 | 0 | 7048.15 | 216640.81 | [5 empty] | N | EC01F | 100%
403248 | SR15 ES - E026 10 Castlemilk Crescent Ashcroft | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2013-03-08 | 2015-07-30 | 2015-09-07 | 2016-02-29 | 2016-04-30 | Glasgow City | 51628.36 | 51628.36 | 294074.64 | 7888.5 | 809.5 | -4047.09 | 0 | 0 | 298725.55 | 0 | 0 | 0 | 350353.91 | 0 | 0 | 0 | 0 | 350353.91 | 165136.88 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
403249 | SR15 ES - E027 Eaglesham Road Busby | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2013-02-18 | 2016-12-13 | 2017-01-23 | 2018-03-31 | 2018-03-31 | East Renfrewshire | 71777 | 71777 | 14454 | 532981 | 268563.32 | -26961.61 | 8.29 | -8795.95 | 780249.05 | 0 | 0 | 0 | 852026.05 | 0 | 0 | 0 | 0 | 852026.05 | 633507.04 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
403250 | SR15 ES - E028 East Side of Airdrie Road South of Police Station 30 Arch Way Kilsyth | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2013-02-18 | 2015-08-11 | 2015-10-26 | 2016-02-29 | 2016-04-30 | North Lanarkshire | 51161.17 | 51161.17 | 186672.83 | -2155.91 | 658.22 | -1733.63 | 0 | 0 | 183441.51 | 0 | 0 | 0 | 234602.68 | 0 | 0 | 0 | 0 | 234602.68 | 351587.81 | [5 empty] | Y | EC01F | 3.036% | EC01B | 96.96% | [33 empty] | 1 | [31 empty] | 0
403251 | SR15 ES - E029 Glenside Drive CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-11 | 2015-10-27 | 2016-01-25 | 2016-09-20 | 2017-03-31 | South Lanarkshire | 79127.31 | 79127.31 | 425520.69 | 405314 | 5038 | -12783.97 | 0 | 0 | 823088.72 | 0 | 0 | 0 | 902216.03 | 0 | 0 | 0 | 0 | 902216.03 | 528067.42 | [5 empty] | N | EC01F | 100%
403640 | SR15 ES - E031 - Busby Cartside Lower SPS EO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2013-12-06 | 2016-12-14 | 2016-12-14 | 2016-12-15 | 2017-01-13 | East Renfrewshire | 5656.83 | 5656.83 | 2640.68 | -7465.53 | 0 | 0 | 0.3 | 0 | -4824.55 | 0 | 0 | 0 | 832.28 | 0 | 0 | 0 | 0 | 832.28 | 297558.71 | [5 empty] | N | EC01F | 100%
403639 | SR15 ES - E032 - South of Birchview Drive CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-12-17 | 2018-02-26 | 2018-03-13 | 2018-06-26 | 2018-10-16 | East Renfrewshire | 420.54 | 420.54 | 160.98 | 149.88 | 18698.6 | 3488 | 0 | -3544.61 | 18952.85 | 0 | 0 | 0 | 19373.39 | 0 | 0 | 0 | 0 | 19373.39 | 297558.71 | [5 empty] | N | EC01F | 100%
403747 | SR15 ES - E033 DALDOWIE - Cluster 7 - COATBRIDGE 30M W-O WOODSIDE ST CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | SWMD | UWWTD - UID | MS6 | 2014-03-17 | 2018-11-22 | 2019-01-18 | 2019-02-28 | 2019-03-31 | North Lanarkshire | 105900 | 105900 | 77125 | 75913.11 | 54061.89 | 79000 | 1129.17 | 250.83 | 287480 | 213.84 | 213.84 | 296.8463 | 393593.84 | 83.0063 | 0 | 0 | 83.0063 | 393676.8463 | 46023.48 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
403746 | SR15 ES - E035 - Deaconsbank WwPS | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-03-17 | 2015-02-25 | 2015-03-09 | 2015-02-26 | 2020-02-11 | East Renfrewshire | 16150.62 | 16150.62 | -0.01 | -427.05 | 0 | 0 | -0.35 | 0 | -427.41 | 0 | 0 | 0 | 15723.21 | 0 | 0 | 0 | 0 | 15723.21 | 0 | [5 empty] | N | EC01B | 100%
403913 | SR15 ES - E036 Rutherglen Stonelaw Rd-Buchanan Dr CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS7 | 2015-10-27 | 2017-06-30 | 2017-12-05 | 2019-01-31 | 2019-03-31 | South Lanarkshire | 2994.55 | 2994.55 | 28764.45 | 48579 | 494189 | 722792.32 | 6680.68 | -8543.62 | 1292461.83 | 0 | 0 | 0 | 1295456.38 | 0 | 0 | 0 | 0 | 1295456.38 | 373919.8 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
404031 | SR15 ES - E037 - In Field off Victoria Place behind No. 50 CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2018-05-10 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | East Renfrewshire | 1040 | 1040 | 7210 | 84923.72 | 38009.23 | 20210.99 | 59.93 | 0 | 150413.87 | 0 | 0 | 0 | 151453.87 | 0 | 0 | 0 | 0 | 151453.87 | 855170.77 | [5 empty] | N | EC01B | 100%
403922 | SR15 ES - E1052 - Dalkeith Road Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-03-31 | 2020-04-01 | 2020-04-10 | 2020-04-23 | 2021-04-01 | City of Edinburgh | 610 | 610 | 18500 | 39493.61 | 24896.39 | 37500 | -121000 | 0 | -610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180449.74 | [5 empty] | N | FL_DD | 100%
404039 | SR15 ES - E1134 - Kirknewton Mains Farm | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2018-06-07 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | West Lothian | 976 | 976 | 8000 | 43718.92 | 43207.08 | 3256.49 | 0 | 0 | 98182.49 | 0 | 0 | 0 | 99158.49 | 0 | 0 | 0 | 0 | 99158.49 | 587389.06 | [5 empty] | N | FL_NAMED | 100%
404027 | SR15 ES - E1254 - Waterside Haddington | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2019-06-14 | 2019-06-14 | 2019-05-28 | 2019-05-28 | 2019-05-28 | East Lothian | 610 | 610 | 12000 | 44545.69 | 17844.31 | 20000 | -94034.88 | 0 | 355.12 | 0 | 0 | 0 | 965.12 | 0 | 0 | 0 | 0 | 965.12 | 588103.68 | [5 empty] | N | FL_NAMED | 100%
403919 | SR15 ES - E1270 - Station Road Slamannan Falkirk | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2016-12-16 | 2016-12-16 | 2016-12-16 | 2016-06-28 | 2016-12-16 | Scottish Water Wide | 0 | 0 | 37221 | -37221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CS11 | 100%
404083 | SR15 ES - E1404 - Old Mill Road Craigrothie Fife | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2016-10-14 | 2016-10-14 | 2016-10-14 | 2016-09-06 | 2016-10-14 | Fife | 0 | 0 | 37062 | -17890.07 | 0 | 0 | 0 | 0 | 19171.93 | 0 | 0 | 0 | 19171.93 | 0 | 0 | 0 | 0 | 19171.93 | 66122.5 | [5 empty] | N | FL_NAMED | 100%
404023 | SR15 ES - E1446 - Main Street Limekilns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWMD | Flooding Named | MS2 | 2020-12-10 | 2020-12-16 | 2022-01-11 | 2022-06-27 | 2022-09-19 | Fife | 244 | 244 | 36256 | 33122.89 | 31801.5 | 8575.61 | 33312.4 | -8698.4 | 134370 | 32179.14 | 32179.14 | 44670.1247 | 166793.14 | 12490.9847 | 0 | 0 | 12490.9847 | 179284.1247 | 1351407.8 | [5 empty] | N | FL_NAMED | 100%
404028 | SR15 ES - E1452 - Townhill Road Dunfirmline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2017-10-17 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | Fife | 610 | 610 | 10000 | 28818.95 | -39428.95 | 0 | 0 | 0 | -610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33096.33 | [5 empty] | N | FL_NAMED | 100%
403923 | SR15 ES - E1618 - Rose Street Annan (14 33 and 35) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2018-02-28 | 2020-02-28 | 2021-04-06 | 2022-06-07 | 2022-06-07 | Dumfries and Galloway | 1053 | 1053 | 89584 | 19354.29 | 42161.29 | 249364.42 | 1058360 | -65363.08 | 1393460.92 | 4859242.37 | 6105486.0815 | 6105486.0815 | 6253756.29 | 0 | 0 | 1246243.71 | 1246243.71 | 7500000 | 180449.74 |  |  |  |  | 5070 | N | FL_DD | 100%
403924 | SR15 ES - E1619 - Hospital Road Annan | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-06-05 | 2018-06-05 | 2018-02-26 | 2018-06-05 | 2018-06-05 | Dumfries and Galloway | 702 | 702 | 35056 | 28244 | -63433.07 | 222.2 | -0.07 | 0 | 89.06 | 0 | 0 | 0 | 791.06 | 0 | 0 | 0 | 0 | 791.06 | 180449.74 | [5 empty] | N | FL_DD | 100%
403133 | SR15 ES - Eaglesham Road Clarkston Internal Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2012-11-30 | 2019-03-29 | 2019-06-07 | 2019-04-10 | 2019-04-10 | East Renfrewshire | 217087.56 | 217087.56 | 144912.44 | 29853 | -10860.82 | 37007.82 | -196130.17 | 0 | 4782.27 | 0 | 0 | 0 | 221869.83 | 0 | 0 | 0 | 0 | 221869.83 | 737559.72 | [5 empty] | N | FL_NAMED | 100%
402948 | SR15 ES - Easdale Isle of Seil - provision of appropriate Ww Treatment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS1 | 2012-09-17 | 2021-05-31 | 2021-08-16 | 2023-05-19 |  | Argyll and Bute-North Argyll | 76322 | 9016.1082 | 179928 | 378616 | 130911.78 | 805375.3 | 842109.16 | 179722.29 | 2516662.53 | 7539125.89 | 0 | 0 | 10132110.42 | 0 | 0 | 0 | 0 | 10132110.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402868 | SR15 ES - Estimating support | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-08-21 | 2012-08-21 | 2012-09-05 | 2016-06-28 |  | Scottish Water Wide | 439421.78 | 439421.78 | 0.22 | 0 | 0 | 0 | 0 | 0 | 0.22 | 0 | 0 | 0 | 439422 | 0 | 0 | 0 | 0 | 439422 | 613322.63 | [5 empty] | N | QS4EQS | 50% | QS4EQW | 50%
403641 | SR15 ES - Fair Isle WTW Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2014-01-13 | 2021-04-01 | 2020-12-21 | 2020-12-21 | 2021-04-01 | Shetland Islands | 66493.66 | 66493.66 | 807226.83 | 350121.99 | 32658.13 | 6091.48 | 2642.63 | 0.01 | 1198741.06 | 0 | 0 | 0 | 1265234.72 | 0 | 0 | 0 | 0 | 1265234.72 | 0 | [5 empty] | N | DW23 | 50% | DW25 | 50%
404019 | SR15 ES - Fettercairn WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2027-04-01 | 2028-01-19 | 2028-03-30 | 2028-10-11 |  | Aberdeen City | 1830 | 0 | 25289.01 | 26223.67 | 728.63 | 0 | 831.23 | -831.23 | 52241.31 | 63252.53 | 0 | 0 | 117323.84 | 0 | 0 | 0 | 0 | 117323.84 | 0 | [5 empty] | N | SG1 | 100%
403511 | SR15 ES - Flooding Model Maintenance Programme Batch 1 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2013-09-09 | 2014-05-30 | 2014-06-23 | 2018-11-26 | 2017-03-26 | Scottish Water Wide | 2081306 | 2081306 | 43366 | 333457 | 2500 | 193414.2 | 162.9 | 0 | 572900.1 | 0 | 0 | 0 | 2654206.1 | 0 | 0 | 0 | 0 | 2654206.1 | 558366.35 | [5 empty] | N | CS11 | 50% | CS15 | 50%
402747 | SR15 ES - Flow Gauging Strategy - Installation of Long Term Strategic Analogues | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2012-11-27 | 2013-08-20 | 2014-04-28 | 2018-12-12 | 2017-09-15 | Scottish Water Wide | 96082 | 96082 | 35531 | 38287 | 39700 | 50551.9 | 0 | 0 | 164069.9 | 0 | 0 | 0 | 260151.9 | 0 | 0 | 0 | 0 | 260151.9 | 0 | [5 empty] | N | WG4 | 100%
403714 | SR15 ES - Furnace WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2014-04-08 | 2014-09-30 | 2014-11-03 | 2015-02-28 | 2015-06-30 | Argyll and Bute-Cowal & Bute | 123559.37 | 123559.37 | -11670.37 | 0 | 0 | 0 | 0 | 0 | -11670.37 | 0 | 0 | 0 | 111889 | 0 | 0 | 0 | 0 | 111889 | 0 | [5 empty] | Y | EC06 | 100% | [41 empty] | 1 | [25 empty] | 0
404006 | SR15 ES - Geospatial SR15 Viewer | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2014-11-27 | 2015-07-22 | 2015-07-22 | 2015-07-22 |  | Scottish Water Wide | 365.85 | 365.85 | 949.71 | 0 | 0 | 0 | 0 | 0 | 949.71 | 0 | 0 | 0 | 1315.56 | 0 | 0 | 0 | 0 | 1315.56 | 0 | [5 empty] | N | DW5 | 100%
403304 | SR15 ES - Glasgow Strategic Study PEF Production | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2013-01-11 | 2013-07-08 | 2013-07-15 | 2016-09-27 |  | Scottish Water Wide | 69898 | 69898 | 0 | 0 | 0 | -733.84 | 0 | 0 | -733.84 | 0 | 0 | 0 | 69164.16 | 0 | 0 | 0 | 0 | 69164.16 | 306661.32 | [5 empty] | N | QS4EQS | 100%
403715 | SR15 ES - Glendyes WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2014-05-21 | 2014-11-21 | 2014-12-08 | 2015-03-31 | 2015-06-30 | Aberdeenshire | 77085.5 | 77085.5 | -22774.08 | 0 | 0 | 0 | 0 | 0 | -22774.08 | 0 | 0 | 0 | 54311.42 | 0 | 0 | 0 | 0 | 54311.42 | 0 | [5 empty] | Y | EC06 | 100% | [41 empty] | 1 | [25 empty] | 0
403987 | SR15 ES - Gowanbank WPS CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-05-08 | 2027-11-10 | 2028-02-08 | 2028-12-11 |  | Falkirk | 1037 | 0 | 115199 | 126148.87 | -43517.72 | 8889.91 | 15545.53 | -12889.04 | 209376.55 | 1449159.45 | 0 | 0 | 1659573 | 0 | 0 | 0 | 0 | 1659573 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403134 | SR15 ES - Greenlaw Road Newton Mearns Internal and External Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS4 | 2012-12-10 | 2020-05-27 | 2020-05-27 | 2020-01-31 | 2021-03-01 | East Renfrewshire | 157504.8 | 157504.8 | 89711.2 | 31098 | 39104.51 | 34581.49 | 13235.28 | -1667.26 | 206063.22 | 0 | 0 | 0 | 363568.02 | 0 | 0 | 0 | 0 | 363568.02 | 1797150 | [5 empty] | N | FL_NAMED | 100%
404093 | SR15 ES - Greenock WTW - SCADA Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-07-06 | 2020-08-07 | 2020-08-10 | 2023-08-23 |  | Inverclyde | 0 | 0 | 49622 | 35985.38 | 127284.67 | 57923.55 | 297159.7 | 826049.54 | 1394024.84 | 2749492 | 0 | 0 | 4143516.84 | 0 | 0 | 414199.16 | 414199.16 | 4557716 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404022 | SR15 ES - Hay Street Perth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2022-01-19 | 2022-05-27 | 2022-07-29 | 2023-07-11 | 2023-09-26 | Perth and Kinross | 610 | 610 | 9000 | 1699 | 3691 | 10000 | 38021.55 | 255751.44 | 318162.99 | -18772.99 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000 | 180449.74 | [5 empty] | N | FL_DD | 100%
403334 | SR15 ES - Hillhead Drive | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS4 | 2013-03-08 | 2020-07-03 | 2020-09-15 | 2020-09-15 | 2021-03-01 | North Lanarkshire | 103900 | 103900 | 369283 | -155711.77 | 44484.23 | 57044.54 | 20380 | -64887.75 | 270592.25 | 2842.18 | 2842.18 | 3945.4297 | 377334.43 | 1103.2497 | 0 | 0 | 1103.2497 | 378437.6797 | 0 | [5 empty] | N | FL_NAMED | 100%
403978 | SR15 ES - Innellan Ashburne Lodge UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-06-30 | 2018-08-31 | Argyll and Bute-Cowal & Bute | 294.85 | 294.85 | 75490.15 | 132349.34 | 623547.66 | 15230 | 10930.1 | -19488.55 | 838058.7 | 0 | 0 | 0 | 838353.55 | 0 | 0 | 0 | 0 | 838353.55 | 0 | [5 empty] | Y | EC01A | 100% | [34 empty] | 2 | [32 empty] | 0
403977 | SR15 ES - Innellan Dunadd UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-06-21 | 2018-06-21 | All West Unitary Authorities | 4055.75 | 4055.75 | 5727.25 | 1217 | 0 | -3508.16 | 0 | 0 | 3436.1 | 0 | 0 | 0 | 7491.85 | 0 | 0 | 0 | 0 | 7491.85 | 0 | [5 empty] | N | EC01A | 100%
404077 | SR15 ES - Invercannie & Mannofield WOA Mannofield WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-07-06 | 2016-07-06 | 2016-07-06 |  | Aberdeen City | 10.63 | 0 | 0 | 955.43 | 0 | 0 | 0 | 0 | 955.43 | 0 | 0 | 0 | 966.06 | 0 | 0 | 0 | 0 | 966.06 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404076 | SR15 ES - Invercannie & Mannofield WOA Pitfodels WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-23 | 2016-03-02 | 2016-03-02 | 2016-02-25 |  | Aberdeen City | 173.85 | 0 | 5707.27 | 955.44 | 0 | 0 | 0 | 0 | 6662.71 | 0 | 0 | 0 | 6836.56 | 0 | 0 | 0 | 0 | 6836.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404078 | SR15 ES - Invercannie & Mannofield WOA Rosehill Aberdeen WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-03-02 | 2016-03-02 | 2016-03-02 |  | Aberdeen City | 129.07 | 0 | 3621.82 | 955.45 | 0 | 0 | 0 | 0 | 4577.27 | 0 | 0 | 0 | 4706.34 | 0 | 0 | 0 | 0 | 4706.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404079 | SR15 ES - Invercannie WOA Megray WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-03-02 | 2016-03-02 | 2016-03-02 |  | Aberdeenshire | 54.27 | 0 | 4018.52 | 1715.52 | -45.97 | 0 | 0 | 0 | 5688.07 | 0 | 0 | 0 | 5742.34 | 0 | 0 | 0 | 0 | 5742.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403965 | SR15 ES - Katrine Aqueducts | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-11-02 | 2018-08-15 | 2018-10-08 | 2021-10-15 |  | Stirling | 4148 | 0 | 122014 | 325241.13 | 161719.87 | 2853686.95 | 8400203.57 | 7845256.2 | 19708121.72 | 1967942.81 | 0 | 0 | 21680212.53 | 0 | 0 | 819787.47 | 819787.47 | 22500000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403754 | SR15 ES - Killin WTW manganse Issues and Capital maintenance work | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS7 | 2014-04-04 | 2015-03-24 | 2016-03-29 | 2017-03-31 | 2018-03-31 | Stirling | 44420.33 | 703.8913 | 135629.67 | 186254.23 | 323509.7 | 65756.64 | 1011.31 | -29335.55 | 682826 | 0 | 0 | 0 | 727246.33 | 0 | 0 | 0 | 0 | 727246.33 | 606341.19 | [5 empty] | Y | DW3C | 3.33% | CM_WSNI | 96.67% | [16 empty] | 1 | [48 empty] | 0
403971 | SR15 ES - Kilmun Lagganbhuie UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2019-05-31 | 2019-08-31 | Argyll and Bute-Cowal & Bute | 8825.01 | 8825.01 | 26162.08 | 285814.91 | 254671 | -49000 | -40480 | 0 | 477167.99 | 0 | 0 | 0 | 485993 | 0 | 0 | 0 | 0 | 485993 | 0 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
403335 | SR15 ES - Kirkview Crescent | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2013-03-08 | 2019-04-30 | 2019-06-19 | 2019-05-03 | 2019-06-19 | East Renfrewshire | 135662 | 135662 | 201461 | 2251 | 3626 | 34498.95 | -241139.57 | 0 | 697.38 | 0 | 0 | 0 | 136359.38 | 0 | 0 | 0 | 0 | 136359.38 | 176952.24 | [5 empty] | N | FL_NAMED | 100%
403532 | SR15 ES - Kyle of Lochalsh WTW - Water Resource Strategic Study | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | SWMD | SOSI | MS3 | 2013-08-27 | 2016-10-31 | 2017-03-27 | 2021-10-01 | 2021-12-31 | Highland | 298171 | 298171 | 119457 | 131619.98 | 689711.18 | 54630.26 | 81855.86 | 84753.72 | 1162028 | 217794.72 | 217794.72 | 298050.8967 | 1677993.72 | 80256.1767 | 0 | 0 | 80256.1767 | 1758249.8967 | 1007001.41 |  |  |  |  | 15000 | Y | WG4A | 10% | WG4 | 90% | [23 empty] | 1 | [41 empty] | 0
404007 | SR15 ES - Laighpark Paisley WWTW NS485655 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-03-26 | 2019-03-13 | 2019-03-15 | 2021-10-29 |  | Renfrewshire | 2446.9 | 0 | 80574.1 | 145801.3 | -476.98 | 450339.82 | 2009023.85 | 1869284.01 | 4554546.1 | 1171263.49 | 0 | 0 | 5728256.49 | 0 | 0 | 1049807.51 | 1049807.51 | 6778064 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2019-02-27 | 2019-03-28 | Scottish Water Wide | 142211.46 | 142211.46 | 645864.54 | 272100.84 | 371172.33 | 273425.5 | 163994.22 | 0 | 1726557.43 | 0 | 0 | 0 | 1868768.89 | 0 | 0 | 0 | 0 | 1868768.89 | 0 | [5 empty] | N | EC06 | 100%
404092 | SR15 ES - Lindean SEP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-05-08 | 2016-12-21 | 2017-01-24 | 2017-10-25 |  | Scottish Water Wide | 0 | 0 | 65609 | 91570 | 214265 | 6868.91 | 2359.31 | 1696.42 | 382368.64 | 0 | 0 | 0 | 382368.64 | 0 | 0 | 0 | 0 | 382368.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
404054 | SR15 ES - Lintrathen WOA Lintrathen TM WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-05 | 2016-09-23 | 2016-10-17 | 2017-08-10 |  | Perth and Kinross | 26905 | 0 | 117253 | 736079 | 379687 | 148192.43 | 95104.91 | 2732.99 | 1479049.33 | 0 | 0 | 0 | 1505954.33 | 0 | 0 | 0 | 0 | 1505954.33 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403452 | SR15 ES - Lismore Oban - provision of septic tank and extended outfall | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2013-05-08 | 2015-03-10 | 2015-06-22 | 2015-12-31 | 2016-02-29 | Argyll and Bute-North Argyll | 45212.23 | 45212.23 | 122343.32 | 6983.74 | -3939.25 | 0 | 0 | 0 | 125387.81 | 0 | 0 | 0 | 170600.04 | 0 | 0 | 0 | 0 | 170600.04 | 0 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
404044 | SR15 ES - Loch Calder WOA Brabster WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2014-12-19 | 2022-07-13 | 2022-08-18 | 2022-12-07 |  | Highland | 4644 | 0 | 74372 | -35878 | 44477 | 14924.43 | 7725.48 | -2725.91 | 102895 | 834195.67 | 0 | 0 | 941734.67 | 0 | 0 | 0 | 0 | 941734.67 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404045 | SR15 ES - Loch Calder WOA Toftcarl WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-01-05 | 2027-05-04 | 2027-06-02 | 2028-04-07 |  | Highland | 1760.27 | 0 | 37997.73 | 15157 | 12962.46 | 38605.54 | -38605.54 | 38606 | 104723.19 | 641667.17 | 0 | 0 | 748150.63 | 0 | 0 | 0 | 0 | 748150.63 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403127 | SR15 ES - Loch Ness Regional WTW Scheme | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS3 | 2013-03-04 | 2018-02-28 | 2018-03-27 | 2022-01-31 | 2023-05-15 | Highland | 339720.5 | 254318.9067 | 331010.5 | 332847.72 | 1797860.93 | 8866701.47 | 9539077.87 | 4808900.96 | 25676399.45 | 1754892.77 | 1585452.4372 | 3812194.5242 | 27771012.71 | 2226742.087 | 0 | 215215.6215 | 2441957.7085 | 30212970.4185 | 5155024.65 | [5 empty] | Y | DW25P | 8.232% | DW3G | 8.232% | CM_WSI | 9.655% | DW2 | 73.88% | [12 empty] | 2 | [48 empty] | 0
403996 | SR15 ES - Lochaline WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS6 | 2016-04-25 | 2018-11-30 | 2019-01-07 | 2020-03-31 | 2020-03-02 | Highland | 3416 | 3416 | 61388.08 | 61046.45 | 299936.29 | 777663.69 | 440494.63 | 32412.93 | 1672942.07 | 11325.06 | 11325.061 | 15721.1127 | 1687683.13 | 4396.0517 | 0 | 0 | 4396.0517 | 1692079.1817 | 0 | [5 empty] | N | DW23 | 100%
403774 | SR15 ES - Lochearnhead WTW manganese Issues and Capital maintenance work | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS7 | 2015-05-08 | 2016-03-31 | 2016-08-02 | 2017-06-30 | 2018-03-31 | Stirling | 700 | 477.3823 | 98793 | 206717.76 | 153149.62 | -17264.03 | -16690.85 | 0 | 424705.5 | 0 | 0 | 0 | 425405.5 | 0 | 0 | 0 | 0 | 425405.5 | 655232.23 | [5 empty] | Y | DW3C | 5.723% | CM_WSNI | 94.28% | [16 empty] | 1 | [48 empty] | 0
403995 | SR15 ES - Londornoch WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS1 | 2016-04-01 | 2021-06-21 | 2021-07-20 | 2023-05-19 | 2023-06-26 | Highland | 0 | 0 | 644.54 | 3773.58 | 67044.82 | -17463.93 | 81603.43 | 577384.56 | 712987 | 1289677.29 | 1289677.29 | 1790291.6405 | 2002664.29 | 500614.3505 | 0 | 0 | 500614.3505 | 2503278.6405 | 0 | [5 empty] | Y | DW25 | 100% | [21 empty] | 1 | [45 empty] | 0
403604 | SR15 ES - Londornoch WTW Lagoons - Legacy Sludge LA01 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2014-05-21 | 2015-03-10 | 2015-03-23 | 2015-10-31 | 2016-03-31 | Highland | 97229.41 | 97229.41 | 103702.59 | -11534.14 | 0 | 0 | 0 | 0 | 92168.45 | 2603.09 | 2603.09 | 3613.5321 | 192000.95 | 1010.4421 | 0 | 0 | 1010.4421 | 193011.3921 | 0 | [5 empty] | Y | EC06 | 100% | [41 empty] | 1 | [25 empty] | 0
402949 | SR15 ES - LRC3 (Daldowie WWTW to Dalmarnock WWTW FE Transfer and Outfall) Development | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | MPT | UWWTD - Works | MS3 | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2022-10-21 | 2022-11-25 | Glasgow City | 1820434 | 1820434 | 1130117.6 | 2092680.58 | 6926138.82 | -2905717 | 3567273.69 | 6270853.31 | 17081347 | 12368251.98 | 12368251.98 | 15259619.7069 | 31270032.98 | 2891367.7269 | 0 | 0 | 2891367.7269 | 34161400.7069 | 1775291.26 |  |  |  |  | 712964 | N | EC10B | 6.4% | EC10A | 93.6%
404026 | SR15 ES - Main Street Newtonmore | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS1 | 2015-10-12 | 2021-04-01 | 2021-05-04 | 2022-03-03 | 2022-03-03 | Highland | 244 | 244 | 41126 | 187359 | 166004 | 56695.68 | 72883.32 | 416117.35 | 940185.35 | 1519172.04 | 1519172.04 | 1824184.7702 | 2459601.39 | 305012.7302 | 0 | 0 | 305012.7302 | 2764614.1202 | 117311.54 |  |  |  |  | 6000 | N | FL_NAMED | 100%
404048 | SR15 ES - Milngavie WOA C4 Craigmaddie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-01-05 | 2016-12-19 | 2017-01-30 | 2019-08-20 |  | Glasgow City | 12059 | 0 | 162196 | 293871 | 1842709 | -51126.53 | 1697.64 | 1784.89 | 2251132 | 0 | 0 | 0 | 2263191 | 0 | 0 | 0 | 0 | 2263191 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404049 | SR15 ES - Milngavie WOA M1 Mugdock WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2015-01-05 | 2024-08-07 | 2024-10-31 | 2026-02-04 |  | Glasgow City | 6780 | 0 | 260236 | -114904 | 169966 | -52858.42 | 31884.7 | -110616.28 | 183708 | 723499.53 | 0 | 0 | 913987.53 | 0 | 0 | 0 | 0 | 913987.53 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404050 | SR15 ES - Milngavie WOA M3 Mugdock WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS1 | 2015-01-05 | 2023-03-31 | 2023-05-22 | 2024-06-06 |  | Glasgow City | 6112 | 0 | 123117 | 66329 | 25847 | -78507.25 | 12804.52 | -27536.33 | 122053.95 | -0.04 | 0 | 0 | 128165.91 | 0 | 0 | 0 | 0 | 128165.91 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403694 | SR15 ES - Mingulay Crescent - Scaraway Street Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS7 | 2014-03-31 | 2016-08-02 | 2016-08-31 | 2017-10-31 | 2017-10-31 | Glasgow City | 84629 | 84629 | 166871 | 2343175 | 121304 | -5652 | 7673 | -18620.68 | 2614750.32 | 0 | 0 | 0 | 2699379.32 | 0 | 0 | 0 | 0 | 2699379.32 | 3226654.89 | [5 empty] | N | FL_NAMED | 100%
403693 | SR15 ES - Moraine Avenue (Lower) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS7 | 2014-04-28 | 2016-07-22 | 2016-09-05 | 2017-05-29 | 2017-05-29 | Glasgow City | 35139 | 35139 | 320861 | 1286538 | -49219.82 | 1788.82 | 1987.87 | 0 | 1561955.87 | 0 | 0 | 0 | 1597094.87 | 0 | 0 | 0 | 0 | 1597094.87 | 1064623.02 | [5 empty] | N | FL_NAMED | 100%
403692 | SR15 ES - Moraine Avenue (Upper) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2014-04-28 | 2019-03-20 | 2019-03-28 | 2019-01-28 | 2019-03-28 | Glasgow City | 91368 | 91368 | 265132 | -70491 | 111991 | -4073.92 | 1028.5 | 0 | 303586.58 | 0 | 0 | 0 | 394954.58 | 0 | 0 | 0 | 0 | 394954.58 | 1709599.7 | [5 empty] | N | FL_NAMED | 100%
403579 | SR15 ES - National Substance Strategy for Scotland - Priority Substances Directive | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2013-10-08 | 2013-12-13 | 2013-12-13 | 2016-09-29 | 2016-10-26 | Scottish Water Wide | 19064.8 | 19064.8 | 2435.2 | -260.2 | 0 | 0 | 0 | 0 | 2175 | 0 | 0 | 0 | 21239.8 | 0 | 0 | 0 | 0 | 21239.8 | 0 | [5 empty] | N | EC10A | 100%
404024 | SR15 ES - NE451 - Howard Place Dysart Kirkcaldy | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2018-04-11 | 2019-02-07 | 2019-02-25 | 2019-06-21 | 2019-06-21 | Fife | 366 | 366 | 1500 | 14986.31 | 17129.73 | 68494.96 | 233920 | 0 | 336031 | 603 | 0 | 0 | 337000 | 0 | 0 | 0 | 0 | 337000 | 180449.74 | [5 empty] | N | FL_DD | 100%
404038 | SR15 ES - NE53 - Queens Road Turriff | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-05-25 | 2017-05-25 | Aberdeenshire | 488 | 488 | 26000 | 4922.11 | 2654.09 | 0 | 0.11 | 0 | 33576.31 | 0 | 0 | 0 | 34064.31 | 0 | 0 | 0 | 0 | 34064.31 | 62492.89 | [5 empty] | N | FL_NAMED | 100%
403926 | SR15 ES - NE539 - Eilidh Fowlis Road Liff Dundee | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-07-18 | 2019-07-18 | Angus | 893 | 893 | 3700 | 36413.94 | 43993.06 | 56000 | -138859.14 | 0 | 1247.86 | -2139.86 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 180449.74 | [5 empty] | N | FL_DD | 100%
403925 | SR15 ES - NE59 - 4 Sutherland Crescent Buckie | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2015-11-11 | 2017-10-25 | 2018-01-29 | 2019-01-15 | 2019-01-15 | Moray | 610 | 610 | 34190.61 | 73980.39 | 289156.02 | 253056.98 | 26866.58 | -2815.86 | 674434.72 | 0 | 0 | 0 | 675044.72 | 0 | 0 | 0 | 0 | 675044.72 | 180449.74 | [5 empty] | N | FL_DD | 100%
403336 | SR15 ES - Nelson Street - South Scott Street Baillieston | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS6 | 2013-03-11 | 2016-03-02 | 2017-01-23 | 2018-03-21 | 2018-03-21 | Glasgow City | 139543.94 | 139543.94 | 520803.06 | 1101543 | 2342888.98 | 9595.03 | 204.99 | -125884.34 | 3849150.72 | 375884.34 | 375884.3416 | 521791.4588 | 4364579 | 145907.1172 | 0 | 0 | 145907.1172 | 4510486.1172 | 1549518.41 | [5 empty] | N | FL_NAMED | 100%
403990 | SR15 ES - Ness WTW - SR15 WQ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-04-28 | 2017-04-28 | 2017-04-28 | 2017-04-28 | 2017-04-28 | Na H-Eileanan an Iar | 0 | 0 | 0 | 396 | 211.29 | 311.19 | 0 | 0 | 918.48 | 0 | 0 | 0 | 918.48 | 0 | 0 | 0 | 0 | 918.48 | 0 | [5 empty] | N | DW25 | 100%
403944 | SR15 ES - Network Modelling (Creation of new all-mains models & strategic models) | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water | DWQR | SWMD | Interruptions to Supply | MS3 | 2014-10-13 | 2015-10-16 | 2015-10-19 | 2021-10-22 | 2022-01-21 | Scottish Water Wide | 106206 | 106206 | 710125 | 879993.95 | 559554.98 | 639866.14 | 243417.54 | 307996.57 | 3340954.18 | 53418.58 | 46836.2525 | 65016.6921 | 3500578.76 | 18180.4396 | 0 | 0 | 18180.4396 | 3518759.1996 | 311236.79 | [5 empty] | N | CM_WSI | 12.32% | CS12 | 43.84% | CS16W | 43.84%
403991 | SR15 ES - Newmore WTW - WQ & Essential Related CM Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2016-04-01 | 2018-08-29 | 2018-09-28 | 2023-01-02 | 2023-05-19 | Highland | 0 | 0 | 3639.03 | 309249.46 | 459203.43 | 852209.52 | 3468448.56 | 2805241 | 7897991 | 3042121 | 1064742.35 | 1928727.7016 | 10940112 | 863985.3516 | 0 | 1338927.2 | 2202912.5516 | 13143024.5516 | 1860855.31 |  |  |  |  | 85764 | Y | DW25P | 35% | CM_WSNI | 65% | [19 empty] | 1 | [45 empty] | 0
403992 | SR15 ES - North Lochs WTW - SR15 WQ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS5 | 2016-04-01 | 2018-02-28 | 2018-03-28 | 2020-08-31 | 2021-03-31 | Na H-Eileanan an Iar | 0 | 0 | 1219.51 | 42732.58 | 220633.8 | 1117098.61 | 192093.5 | 41106 | 1614884 | 15433.99 | 15433.99 | 21425.0057 | 1630317.99 | 5991.0157 | 0 | 0 | 5991.0157 | 1636309.0057 | 427866.62 |  |  |  |  | 5916.6665 | Y | DW25 | 100% | [21 empty] | 1 | [45 empty] | 0
403691 | SR15 ES - Number 6 Viewpark Drive | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS7 | 2014-04-25 | 2017-06-30 | 2017-09-18 | 2018-12-11 | 2018-12-11 | South Lanarkshire | 44470 | 44470 | 260905 | 104023 | 259728.68 | 43226.32 | -2353 | -9622.32 | 655907.68 | 0 | 0 | 0 | 700377.68 | 0 | 0 | 0 | 0 | 700377.68 | 145594.05 | [5 empty] | N | FL_NAMED | 100%
404020 | SR15 ES - NW95 - Princes Street Thurso | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-11-27 | 2020-04-30 | 2020-04-30 | 2020-05-12 | 2021-04-01 | Highland | 1220 | 1220 | 193590 | 846 | 54601.4 | 11459.94 | -261399.66 | -210.32 | -1112.64 | 0 | 0 | 0 | 107.36 | 0 | 0 | 0 | 0 | 107.36 | 180449.74 | [5 empty] | N | FL_DD | 100%
403630 | SR15 ES - Old Calder WTW Legacy Sludge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater | SEPA | SWMD | Wastewater non infrastructure | MS7 | 2014-02-11 | 2015-03-02 | 2015-03-30 | 2015-05-31 | 2015-05-31 | Highland | 39547.38 | 0 | 200730.54 | 0 | 30.88 | 0 | 0 | 0 | 200761.42 | 0 | 0 | 0 | 240308.8 | 0 | 0 | 0 | 0 | 240308.8 | 90601.29 | [5 empty] | Y | CM_WWNI | 100% | [41 empty] | 1 | [25 empty] | 0
403135 | SR15 ES - Old Street Clydebank Internal Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS7 | 2012-12-10 | 2015-08-06 | 2015-09-21 | 2016-07-29 | 2016-07-29 | Glasgow City | 137215.96 | 137215.96 | 1604972.04 | 64671 | 17907 | -35788.99 | 0 | 0 | 1651761.05 | 0 | 0 | 0 | 1788977.01 | 0 | 0 | 0 | 0 | 1788977.01 | 1691921.82 | [5 empty] | N | FL_NAMED | 100%
403337 | SR15 ES - Orbiston Street | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2013-03-08 | 2019-04-30 | 2019-05-23 | 2019-02-25 | 2019-05-23 | North Lanarkshire | 95524.22 | 95524.22 | 173523.78 | 35996.04 | 32947.13 | 9134.11 | 1932.23 | 0 | 253533.29 | 0 | 0 | 0 | 349057.51 | 0 | 0 | 0 | 0 | 349057.51 | 470562.95 | [5 empty] | N | FL_NAMED | 100%
403631 | SR15 ES - Papa Stour WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2016-09-28 | 2020-12-08 | 2020-12-10 | 2021-01-06 | 2021-04-01 | Shetland Islands | 34087.82 | 34087.82 | 8713.18 | 25968.59 | -17959.89 | 489.67 | 1773.63 | 1970.55 | 20955.73 | 0 | 0 | 0 | 55043.55 | 0 | 0 | 0 | 0 | 55043.55 | 0 | [5 empty] | N | DW25 | 10% | DW23 | 40% | DW2 | 50%
403958 | SR15 ES - Proactive Meter Maintenance (2015-17) | Q&S4 | Improving the customer experience | Meter Accuracy |  |  | Water |  | SWD | Meter Accuracy | MS7 | 2016-12-21 | 2017-01-18 | 2017-01-18 | 2016-10-26 |  | Scottish Water Wide | 185621.8 | 185621.8 | 196563.7 | -172732.48 | 0 | 0 | 0 | 0 | 23831.22 | 0 | 0 | 0 | 209453.02 | 0 | 0 | 0 | 0 | 209453.02 | 0 | [5 empty] | N | CS4 | 100%
403587 | SR15 ES - Programme Development - SWS2 Resource Support Costs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWMD | Wastewater non infrastructure | MS7 | 2013-09-17 | 2014-07-10 | 2016-08-23 | 2016-08-23 |  | Scottish Water Wide | 952475.44 | 238118.86 | -256552.7 | 40048.41 | 0 | 0 | 0 | 0 | -216504.29 | 0 | 0 | 0 | 735971.15 | 0 | 0 | 0 | 0 | 735971.15 | 516285.19 | [5 empty] | N | CM_WSNI | 25% | CM_WWNI | 25% | WG1 | 25% | WQ01 | 25%
404075 | SR15 ES - PSC Treated Water Storage Tanks Inspections Scotland Wide Program | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-01-26 | 2015-05-21 | 2015-06-15 | 2017-03-24 |  | Scottish Water Wide | 23000 | 0 | 1243563 | 614632.42 | 32049.7 | 0 | 0 | 0 | 1890245.12 | 0 | 0 | 0 | 1913245.12 | 0 | 0 | 0 | 0 | 1913245.12 | 209623.87 | [5 empty] | N | CM_WSNI | 46.88% | CM_WWI | 53.12%
404002 | SR15 ES - PSCD Blairlinnans to Old Kilpatrick Trunk Main - Close Proximity Diversions | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water | SW | SWD | Exceptional Capital Maintenance | MS7 | 2020-06-25 | 2020-08-11 | 2020-08-11 | 2020-08-17 | 2021-04-01 | West Dunbartonshire | 41.1 | 0 | 164111.9 | -63335 | 110610 | -6379 | 2469.35 | 1512.37 | 208989.62 | 0 | 0 | 0 | 209030.72 | 0 | 0 | 0 | 0 | 209030.72 | 0 | [5 empty] | N | SR15_EXC_EXC | 100%
404003 | SR15 ES - PSCD Bradan Trunk Main - Close Proximity Diversions | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water | SW | WINF | Exceptional Capital Maintenance | MS3 | 2016-01-29 | 2016-09-29 | 2016-09-29 | 2021-04-01 | 2021-04-01 | North Ayrshire | 1470.59 | 0 | 3427861.41 | 12866245 | 4900423 | 2360218.97 | 130328.5 | 703153.7 | 24388230.58 | 5000 | 5000 | 110970.4693 | 24394701.17 | 105970.4693 | 0 | 0 | 105970.4693 | 24500671.6393 | 0 | [5 empty] | N | SR15_EXC_EXC | 100%
404004 | SR15 ES - PSCD Glenhove to Gowanbank Rising Main - Close Proximity Diversions | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water | SW | WINF | Exceptional Capital Maintenance | MS7 | 2015-08-19 | 2015-10-16 | 2015-10-19 | 2017-03-31 | 2017-03-31 | North Lanarkshire | 1952 | 0 | 512225 | 201288 | 19931 | -23948 | -2294.1 | 0 | 707201.91 | 0 | 0 | 0 | 709153.91 | 0 | 0 | 0 | 0 | 709153.91 | 0 | [5 empty] | N | SR15_EXC_EXC | 100%
403982 | SR15 ES - Rhu Armadale Road UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2017-02-21 | 2018-03-27 | 2018-08-30 | 2018-08-30 | Argyll and Bute-Cowal & Bute | 3938 | 3938 | 3000 | 0 | 1129.6 | 2875.4 | 2671.59 | 129.02 | 9805.61 | 0 | 0 | 0 | 13743.61 | 0 | 0 | 0 | 0 | 13743.61 | 0 | [5 empty] | N | EC01A | 100%
403981 | SR15 ES - Rhu Artarman Road UNS SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2017-02-11 | 2018-03-27 | 2018-08-30 | 2018-08-30 | Argyll and Bute-Cowal & Bute | 3938 | 3938 | 31229 | 301811 | 179004.71 | 350017.29 | 0 | -33142.47 | 828919.53 | 0 | 0 | 0 | 832857.53 | 0 | 0 | 0 | 0 | 832857.53 | 0 | [5 empty] | N | EC01A | 100%
403983 | SR15 ES - Rhu Torwoodhill Road Uns SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-05-18 | 2018-11-01 | Argyll and Bute-Cowal & Bute | 3930 | 3930 | 61549 | 143268.49 | 884537.19 | -48104.68 | 0 | -15743.15 | 1025506.85 | 0 | 0 | 0 | 1029436.85 | 0 | 0 | 0 | 0 | 1029436.85 | 0 | [5 empty] | N | EC01A | 100%
403700 | SR15 ES - Roberton WTW - Manganese Polution Control & Automatic Coagulant Dosing | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWMD | DWQ Compliance | MS6 | 2014-02-17 | 2016-03-23 | 2016-03-28 | 2017-03-31 |  | Scottish Borders | 76358.91 | 76358.91 | 355686.09 | 701969.63 | 31569.95 | 7028.16 | 2975.88 | 5924.38 | 1105154.09 | 6803.2 | 6803.2 | 9443.9998 | 1188316.2 | 2640.7998 | 0 | 0 | 2640.7998 | 1190956.9998 | 406972.26 | [5 empty] | Y | DW25P | 21.36% | DW3C | 78.64% | [65 empty] | 0
403595 | SR15 ES - Robslee Drive - Burnfield Cottages | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2014-01-29 | 2018-06-29 | 2018-06-29 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 114677 | 114677 | 72063 | 63795 | 134382.34 | 76828.86 | 8026.54 | 0 | 355095.74 | 0 | 0 | 0 | 469772.74 | 0 | 0 | 0 | 0 | 469772.74 | 520131.84 | [5 empty] | N | FL_NAMED | 100%
401806 | SR15 ES - S168 UID East of 1 Espedair Street Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | SWMD | UWWTD - UID | MS6 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-31 | 2019-12-31 | Renfrewshire | 16089 | 16089 | -1532 | 7699.37 | -5116.37 | 800 | 764.77 | -564.74 | 2051.03 | 0 | 0 | 0 | 18140.03 | 0 | 0 | 0 | 0 | 18140.03 | 0 | [5 empty] | Y | EC04B | 100% | [35 empty] | 7 | [31 empty] | 0
401808 | SR15 ES - S170 UID Storm Water Overflow Rear of 27 Barterholm Road Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-03-31 | Renfrewshire | 6898 | 6898 | 0 | 642 | 83 | 4275 | 1752.7 | -211.71 | 6540.99 | 0 | 0 | 0 | 13438.99 | 0 | 0 | 0 | 0 | 13438.99 | 0 | [5 empty] | N | EC04B | 100%
401809 | SR15 ES - S171 UID Ardgowan Street South No1 CSO South end of Ardgowan Street Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-31 | 2020-03-31 | Renfrewshire | 14625 | 14625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14625 | 0 | 0 | 0 | 0 | 14625 | 0 | [6 empty] | EC04B | 100% | [35 empty] | 2 | [31 empty] | 0
401811 | SR15 ES - S173 UID Charleston No1 CSO Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-04-01 | Renfrewshire | 13025 | 13025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13025 | 0 | 0 | 0 | 0 | 13025 | 0 | [6 empty] | EC04B | 100%
401812 | SR15 ES - S174 UID Charleston No2 CSO Paisley Rowan St behind St Charles Primary School | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-03-31 | Renfrewshire | 10864 | 10864 | -1579 | 150 | 158 | 550 | 0 | 0 | -721 | 0 | 0 | 0 | 10143 | 0 | 0 | 0 | 0 | 10143 | 0 | [5 empty] | N | EC04B | 100%
401813 | SR15 ES - S175 UID 113 Neilston Road at end of Kilncroft Lane Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-03-31 | Renfrewshire | 10138 | 10138 | -5053 | 56.08 | 1643.92 | 1569 | 0 | 0 | -1784 | 0 | 0 | 0 | 8354 | 0 | 0 | 0 | 0 | 8354 | 0 | [5 empty] | N | EC04B | 100%
401814 | SR15 ES - S176 UID 129 Neilston Road Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-03-31 | Renfrewshire | 852148.01 | 852148.01 | 858162.99 | 1062885 | 7722678 | 3931849 | 276622.47 | -14187.47 | 13838009.99 | 0 | 0 | 0 | 14690158 | 0 | 0 | 0 | 0 | 14690158 | 0 | [5 empty] | N | EC04B | 100%
401815 | SR15 ES - S177 UID Charleston No3 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-03-31 | Renfrewshire | 4825 | 4825 | 0 | 2000 | 1017 | 4305 | 3000 | -1002 | 9320 | 0 | 0 | 0 | 14145 | 0 | 0 | 0 | 0 | 14145 | 0 | [5 empty] | N | EC04B | 100%
401816 | SR15 ES - S178 UID Rowan Street No2 Police Station Rowan Street Paisley | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-07-29 | 2020-03-31 | Renfrewshire | 6711 | 6711 | -711 | 712 | 488 | 2709 | 0 | 0 | 3198 | 0 | 0 | 0 | 9909 | 0 | 0 | 0 | 0 | 9909 | 0 | [5 empty] | N | EC04B | 100%
403716 | SR15 ES - Sanday Sludge Storage Area and Drying Beds | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS0 | 2014-04-08 | 2022-04-01 | 2022-06-06 | 2022-08-04 | 2022-10-27 | Orkney Islands | 26305.36 | 26305.36 | 45419.64 | 3003.16 | 29924.84 | 18591.54 | 25775.43 | 40759.11 | 163473.72 | 317461.47 | 317461.47 | 440690.5668 | 507240.55 | 123229.0968 | 0 | 0 | 123229.0968 | 630469.6468 | 0 | [5 empty] | Y | EC06 | 100% | [41 empty] | 1 | [25 empty] | 0
404086 | SR15 ES - Sandy Loch WOA Sandwick WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-09-20 | 2017-08-09 | 2018-05-23 |  | Shetland Islands | 3486 | 0 | 33255 | 50419 | 195036.71 | 77459.79 | -1938.65 | 5932.02 | 360163.87 | 0 | 0 | 0 | 363649.87 | 0 | 0 | 0 | 0 | 363649.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404085 | SR15 ES - Sandy Loch WOA South Burra WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-08-31 | 2016-11-21 | 2017-08-31 |  | Shetland Islands | 650 | 0 | 25426 | 291414 | 175367 | -35684.52 | -1214.08 | 0 | 455308.4 | 0 | 0 | 0 | 455958.4 | 0 | 0 | 0 | 0 | 455958.4 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403629 | SR15 ES - Savalbeg (Lairg) WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2014-02-11 | 2015-03-12 | 2015-03-23 | 2015-10-31 | 2016-03-31 | Highland | 119710.12 | 119710.12 | 88280.88 | -2316.97 | 0 | 0 | 0 | 0 | 85963.91 | 0 | 0 | 0 | 205674.03 | 0 | 0 | 0 | 0 | 205674.03 | 0 | [5 empty] | Y | EC06 | 100% | [41 empty] | 1 | [25 empty] | 0
403917 | SR15 ES - Savalbeg WTW - WQ & Essential CM Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS4 | 2016-03-29 | 2018-03-29 | 2018-03-29 | 2021-03-31 | 2022-06-24 | Highland | 0 | 0 | 39934.41 | 171557.33 | 688634.15 | 2636722.35 | 3548049.77 | 266327.99 | 7351226 | 58511 | 58511 | 906633.6569 | 7409737 | 848122.6569 | 0 | -9.3132e-10 | 848122.6569 | 8257859.6569 | 2744156.38 |  |  |  |  | 76084.2809 | Y | DW25 | 13% | DW2 | 87% | [16 empty] | 1 | [48 empty] | 0
404040 | SR15 ES - SE 390 - Main Street Newtongrange | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | GW2 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-08 | Midlothian | 2440 | 2440 | 6500 | 39544.07 | 22515.93 | 79556.77 | 59443.23 | -2018.77 | 205541.23 | 2018.76 | 2018.76 | 2802.3826 | 209999.99 | 783.6226 | 0 | 0 | 783.6226 | 210783.6126 | 0 | [5 empty] | N | FL_NAMED | 100%
404029 | SR15 ES - SE 663 - Marine Drive Edinburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2017-02-08 | 2017-11-08 | 2017-11-08 | 2017-05-23 | 2017-11-08 | City of Edinburgh | 976 | 976 | 17768 | 43112.66 | -61803.62 | 0 | 0 | 0 | -922.96 | 0 | 0 | 0 | 53.04 | 0 | 0 | 0 | 0 | 53.04 | 79433.4 | [5 empty] | N | FL_NAMED | 100%
404025 | SR15 ES - SE 730 - Harburn Road West Calder | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | West Lothian | 244 | 244 | 37000 | 6293 | 31544.32 | -75080.32 | 0.29 | 0 | -242.71 | 0 | 0 | 0 | 1.29 | 0 | 0 | 0 | 0 | 1.29 | 180449.74 | [5 empty] | N | FL_DD | 100%
402746 | SR15 ES - Security of Supply - Flow Gauging | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2012-08-08 | 2013-02-06 | 2013-02-07 | 2017-08-08 | 2017-09-15 | Scottish Water Wide | 121680 | 121680 | 40837.8 | 42982.2 | 7807.53 | 0 | 0 | 0 | 91627.53 | 0 | 0 | 0 | 213307.53 | 0 | 0 | 0 | 0 | 213307.53 | 0 | [5 empty] | N | WG4 | 100%
403993 | SR15 ES - South Uist WTW - SR15 WQ Improvements | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-11-02 | 2020-01-31 | 2020-01-07 | 2020-01-31 | 2021-04-01 | Na H-Eileanan an Iar | 101.77 | 101.77 | 8398.78 | -8500.55 | 8399.93 | 9.35 | 11558.51 | -628.87 | 19237.15 | 0 | 0 | 0 | 19338.92 | 0 | 0 | 0 | 0 | 19338.92 | 0 | [5 empty] | N | WG4 | 8.13% | DW25 | 10% | DW3B | 10% | DW3C | 71.87%
404053 | SR15 ES - Staffin WTW - CWT Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-11-22 | 2017-01-30 | 2017-01-30 | 2017-01-30 |  | Highland | 0 | 0 | 0 | 356.51 | 8.84 | 0 | 0 | 0 | 365.35 | 0 | 0 | 0 | 365.35 | 0 | 0 | 0 | 0 | 365.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402924 | SR15 ES - Stage 4 DOMS investigations in 31 zones | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2012-12-10 | 2013-10-24 | 2013-11-29 | 2017-03-27 | 2017-03-27 | Scottish Water Wide | 1907722 | 1907722 | 330992 | 142938.72 | 148437.28 | 0 | -10984.25 | 0 | 611383.75 | 0 | 0 | 0 | 2519105.75 | 0 | 0 | 0 | 0 | 2519105.75 | 0 | [5 empty] | N | DW5A | 100%
403125 | SR15 ES - Stoer WTW Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS6 | 2013-01-14 | 2016-03-31 | 2016-07-18 | 2017-12-31 | 2019-03-31 | Highland | 164265.76 | 164265.76 | 122286.34 | 2636754.28 | 1068327.48 | 63204.78 | 7098.41 | -68686.3 | 3828984.99 | 6295.25 | 6295.25 | 8738.8787 | 3999546 | 2443.6287 | 0 | 0 | 2443.6287 | 4001989.6287 | 2374619.47 | [5 empty] | Y | DW23 | 50% | DW25P | 50% | [16 empty] | 1 | [48 empty] | 0
403013 | SR15 ES - Strathpeffer Fish pass | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-11-19 | 2012-11-19 | 2013-11-19 | 2013-12-13 |  | Highland | 25239.04 | 0 | 1760.96 | -1487.51 | 0 | 0 | 0 | 0 | 273.45 | 0 | 0 | 0 | 25512.49 | 0 | 0 | 0 | 0 | 25512.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403753 | SR15 ES - Strathyre WTW manganse Issues and Capital maintenance work | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS7 | 2014-04-04 | 2015-03-24 | 2016-03-31 | 2018-01-31 | 2018-10-31 | Stirling | 40033.25 | 898.4337 | 95509.75 | 105723.06 | 376392.96 | 56183.55 | 1214.04 | -48769.89 | 586253.46 | 0 | 0 | 0 | 626286.71 | 0 | 0 | 0 | 0 | 626286.71 | 640684.93 | [5 empty] | Y | DW25P | 3.4% | CM_WSNI | 96.6% | [19 empty] | 1 | [45 empty] | 0
403980 | SR15 ES - Strone Dunselma Lodge WwTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS6 | 2015-03-17 | 2016-03-23 | 2016-03-29 | 2019-02-28 | 2019-03-31 | Argyll and Bute-Cowal & Bute | 4700.32 | 4700.32 | 83170.68 | 84606.08 | 684974.37 | 5854.55 | 38055 | -31093.37 | 865567.31 | 32153.37 | 32153.3665 | 44634.3467 | 902421 | 12480.9802 | 0 | 0 | 12480.9802 | 914901.9802 | 0 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
403702 | SR15 ES - Summerhill Road - Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2014-04-28 | 2015-06-25 | 2015-08-03 | 2016-03-11 | 2016-03-11 | Glasgow City | 42977 | 42977 | 1103672 | 69893 | 410 | -13697.38 | 0 | 0 | 1160277.62 | 0 | 0 | 0 | 1203254.62 | 0 | 0 | 0 | 0 | 1203254.62 | 180449.74 | [5 empty] | N | FL_DD | 100%
403930 | SR15 ES - SW1377 - 697 & 699 Clarkston Road | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-08-23 | 2020-01-29 | 2020-01-06 | 2021-04-01 | 2021-04-01 | Glasgow City | 732 | 732 | 28888 | 14112 | 55474.83 | 95681.17 | 323843.88 | 203613.56 | 721613.44 | 0 | 0 | 0 | 722345.44 | 0 | 0 | 0 | 0 | 722345.44 | 180449.74 |  |  |  |  | 1080 | N | FL_DD | 100%
404080 | SR15 ES - SW161 - Riverside Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS6 | 2015-05-11 | 2015-11-19 | 2016-03-22 | 2019-01-28 | 2019-01-28 | Glasgow City | 0 | 0 | 3000 | 10260.76 | 0 | 75688.41 | 0 | 0 | 88949.17 | 0 | 0 | 0 | 88949.17 | 0 | 0 | 0 | 0 | 88949.17 | 180449.74 | [5 empty] | N | FL_DD | 100%
403920 | SR15 ES - SW670 - Newfield Road Stonehouse | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-27 | 2018-02-23 | 2018-02-19 | 2018-02-19 | 2018-02-19 | South Lanarkshire | 488 | 488 | 32012 | 34512 | -67012 | 0 | 0.49 | 0 | -487.51 | 0 | 0 | 0 | 0.49 | 0 | 0 | 0 | 0 | 0.49 | 180449.74 | [5 empty] | N | FL_DD | 100%
403929 | SR15 ES - SW854 - 66 & 68 Burns Wynd Stonehouse | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2015-10-13 | 2018-03-20 | 2018-04-03 | 2018-08-21 | 2018-08-21 | South Lanarkshire | 488 | 488 | 44122 | 29960.38 | 463655.62 | 214597.19 | 32676.81 | 5884.61 | 790896.61 | 0 | 0 | 0 | 791384.61 | 0 | 0 | 0 | 0 | 791384.61 | 180449.74 | [5 empty] | N | FL_DD | 100%
403655 | SR15 ES - SWS2 Establishment Cost Capture for SR15 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2014-02-03 | 2016-09-21 | 2016-09-21 | 2016-08-23 | 2016-11-28 | Scottish Water Wide | 1271837.55 | 1271837.55 | 373397.45 | -161315.26 | 0 | 0 | 0 | 0 | 212082.19 | 0 | 0 | 0 | 1483919.74 | 0 | 0 | 0 | 0 | 1483919.74 | 0 | [5 empty] | N | DW23 | 100%
403895 | SR15 ES - Tighnabruaich WTW & CWT - WQ & Captial Maintenance | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS6 | 2015-04-27 | 2016-09-30 | 2017-03-20 | 2017-03-31 | 2019-12-31 | Argyll and Bute-Cowal & Bute | 15000 | 9464.2493 | 60178 | 155004.5 | 603987.98 | -43516.4 | 129446.29 | 16772.63 | 921873 | 18523.34 | 12410.6418 | 17228.0837 | 955396.34 | 4817.4419 | 0 | 0 | 4817.4419 | 960213.7819 | 1694511.02 | [5 empty] | Y | DW3C | 5% | DW25P | 13% | CM_WSNI | 33% | DW25T | 49% | [12 empty] | 1 | [48 empty] | 0
403713 | SR15 ES - Tiree WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2014-05-21 | 2015-03-26 | 2015-05-11 | 2015-07-31 | 2015-08-31 | Argyll and Bute-Cowal & Bute | 16907.4 | 16907.4 | 30250.21 | 0 | 0 | 0 | 0 | 0 | 30250.21 | 0 | 0 | 0 | 47157.61 | 0 | 0 | 0 | 0 | 47157.61 | 0 | [5 empty] | Y | EC06 | 100% | [41 empty] | 1 | [25 empty] | 0
403712 | SR15 ES - Torra WTW Legacy Sludge | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2014-05-22 | 2014-12-18 | 2015-01-26 | 2015-03-31 | 2016-03-31 | Argyll and Bute-North Argyll | 57358.58 | 57358.58 | 8917.42 | -5545.44 | 0 | 0 | 0 | 0 | 3371.98 | 0 | 0 | 0 | 60730.56 | 0 | 0 | 0 | 0 | 60730.56 | 0 | [5 empty] | Y | EC06 | 100% | [41 empty] | 1 | [25 empty] | 0
403979 | SR15 ES - Toward Old Pier House WwTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-22 | 2016-03-29 | 2017-03-31 | 2017-05-31 | Argyll and Bute-Cowal & Bute | 3938 | 3938 | 54576 | 202288.71 | -79487.71 | 205.11 | 0 | 0 | 177582.11 | 0 | 0 | 0 | 181520.11 | 0 | 0 | 0 | 0 | 181520.11 | 0 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
403816 | SR15 ES - Trunk Mains Strategy | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2014-06-20 | 2016-12-12 | 2016-12-12 | 2017-01-25 | 2017-01-25 | Scottish Water Wide | 5475.3 | 5475.3 | 28802.7 | -7100.46 | 0 | 0 | 0 | 0 | 21702.24 | 0 | 0 | 0 | 27177.54 | 0 | 0 | 0 | 0 | 27177.54 | 0 | [5 empty] | N | CS16W | 100%
404094 | SR15 ES - Turret WTW Scada Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-07-06 | 2021-03-10 | 2028-01-21 | 2021-03-10 |  | All West Unitary Authorities | 0 | 0 | 44370 | 4050.5 | -204.34 | 0 | -4691.75 | 2012.71 | 45537.12 | 0 | 0 | 0 | 45537.12 | 0 | 0 | 0 | 0 | 45537.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403994 | SR15 ES - Uig WTW - SR15 WQ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2016-02-29 | 2018-03-30 | 2018-06-27 | 2022-02-25 | 2022-05-20 | Na H-Eileanan an Iar | 0 | 0 | 2237.14 | 235534.58 | 516568.22 | 161408.22 | 1800704.28 | 957341.56 | 3673794 | 669361.07 | 669361.07 | 1287511.834 | 4343155.07 | 618150.764 | 0 | 0 | 618150.764 | 4961305.834 | 0 |  |  |  |  | 2180.0004 | Y | DW25 | 100% | [21 empty] | 1 | [45 empty] | 0
403338 | SR15 ES - Viewpark Road The Loaning | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2013-03-11 | 2018-12-06 | 2018-12-07 | 2018-12-07 | 2018-12-07 | North Lanarkshire | 150441.4 | 150441.4 | 190700.6 | 14775 | 16298 | 76214.19 | 3396.61 | 0 | 301384.4 | -1524.8 | -1524.8021 | -2116.6849 | 450301 | -591.8828 | 0 | 0 | -591.8828 | 449709.1172 | 1469853.01 | [5 empty] | N | FL_NAMED | 100%
403949 | SR15 ES - W125 - Trinley Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS0 | 2020-09-04 | 2021-11-08 | 2022-02-28 | 2023-03-10 | 2023-03-13 | Glasgow City | 1425 | 1425 | 25862.22 | 54137.78 | 37632.57 | 304452.65 | 169202.43 | 201458.35 | 792746 | 35828.96 | 0 | 0 | 829999.96 | 0 | 0 | 0 | 0 | 829999.96 | 175086.76 | [5 empty] | N | FL_DD | 100%
404041 | SR15 ES - W406 - Lilybank Street Hamilton | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS6 | 2018-02-26 | 2019-06-07 | 2019-07-12 | 2020-07-28 | 2020-08-18 | South Lanarkshire | 976 | 976 | 42524 | 12722.01 | 29606.35 | 119993.64 | 896056.99 | 153610.26 | 1254513.25 | 252 | 252 | 349.8189 | 1255741.25 | 97.8189 | 0 | 0 | 97.8189 | 1255839.0689 | 352094.6 | [5 empty] | N | FL_NAMED | 100%
403921 | SR15 ES - W441 - Machan Road Larkhall | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-30 | 2018-07-09 | 2018-07-09 | 2018-04-18 | 2018-04-18 | South Lanarkshire | 976 | 976 | 37000 | 34505.91 | 4397.65 | 1336.97 | -0.27 | 0 | 77240.26 | 0 | 0 | 0 | 78216.26 | 0 | 0 | 0 | 0 | 78216.26 | 180449.74 | [5 empty] | N | FL_DD | 100%
404042 | SR15 ES - W773 - The Cresent Lesmahagow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | WWINF | Flooding Named | MS3 | 2018-07-25 | 2020-03-17 | 2020-08-17 | 2021-05-07 | 2021-08-11 | South Lanarkshire | 488 | 488 | 3000 | 30512 | 21117.97 | 98746.03 | 339426 | 394181 | 886983 | 2250 | 2250 | 3123.3831 | 889721 | 873.3831 | 0 | 0 | 873.3831 | 890594.3831 | 443610.3 | [5 empty] | N | FL_NAMED | 100%
403948 | SR15 ES - Water of Leith | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-01-16 | 2019-04-29 | City of Edinburgh | 4500.97 | 4500.97 | 52617.03 | 418833.97 | -407652.99 | -61675.26 | 1602.94 | 0 | 3725.69 | 0 | 0 | 0 | 8226.66 | 0 | 0 | 0 | 0 | 8226.66 | 267377.18 | [5 empty] | N | EC01F | 50% | EC10B | 50%
403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | SWD | Supply Resilience | MS5 | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2016-07-01 | 2020-11-27 | Scottish Water Wide | 305681.28 | 305681.28 | 557605.72 | 1085514.81 | 277459.19 | 77470.25 | 94405.74 | 54727.63 | 2147183.33 | 0 | 0 | 0 | 2452864.61 | 0 | 0 | 0 | 0 | 2452864.61 | 0 | [5 empty] | N | CS16W | 100%
403690 | SR15 ES - Weavers Court - Paisley | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2014-04-28 | 2018-03-12 | 2019-04-17 | 2018-03-14 | 2019-04-17 | Renfrewshire | 108048 | 108048 | 110960.51 | -9695.51 | 3687 | 29255.29 | 100.71 | 0 | 134308 | 0 | 0 | 0 | 242356 | 0 | 0 | 0 | 0 | 242356 | 2468138.89 | [5 empty] | N | FL_NAMED | 100%
403697 | SR15 ES - Wellhouse Crescent | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater | SW | SWD | Flooding Named | MS7 | 2014-04-28 | 2020-02-12 | 2020-02-18 | 2020-02-18 | 2021-04-01 | Glasgow City | 89131 | 89131 | 44422 | 8612.03 | 35911.02 | 97923.95 | 142143.78 | -79091.69 | 249921.09 | 0 | 0 | 0 | 339052.09 | 0 | 0 | 0 | 0 | 339052.09 | 0 | [5 empty] | N | FL_NAMED | 100%
403988 | SR15 ES - West Lewis WTW - SR15 WQ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS6 | 2016-09-30 | 2018-02-28 | 2018-03-28 | 2020-03-31 | 2022-03-17 | Na H-Eileanan an Iar | 0 | 0 | 10691.12 | 42469.69 | 217914.57 | 864642.93 | 118066.69 | 20773 | 1274558 | 13456.44 | 13456.44 | 18679.8296 | 1288014.44 | 5223.3896 | 0 | 0 | 5223.3896 | 1293237.8296 | 2024560.16 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
403998 | SR15 ES - West Shore Pittenweem | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-04-05 | 2021-07-12 | 2021-09-06 | 2022-08-26 | 2022-10-07 | Fife | 1220 | 1220 | 29500 | 64668.97 | 50361.22 | 120249.82 | 46382.44 | -32805.44 | 278357 | 2592383.25 | 0 | 0 | 2871960.25 | 0 | 0 | 0 | 0 | 2871960.25 | 180449.74 | [5 empty] | N | FL_DD | 100%
403128 | SR15 ES - Yarrowfues WTW Main Out | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2013-03-18 | 2020-02-24 | 2020-02-24 | 2020-02-24 | 2021-04-01 | Scottish Borders | 127138.87 | 127138.87 | 17399.4 | 37572.39 | 159540.87 | -14789.85 | -17284.75 | -107.34 | 182330.72 | 0 | 0 | 0 | 309469.59 | 0 | 0 | 0 | 0 | 309469.59 | 0 | [5 empty] | N | DW25 | 100%
403605 | SR15 ES Clunas WTW and Treatment Trial - Legacy Sludge | IR18 | Protecting and enhancing the environment | Sludge |  |  | Wastewater | SEPA | SWMD | Sludge | MS4 | 2013-10-31 | 2018-03-20 | 2018-03-26 | 2021-02-25 | 2021-04-01 | Highland | 123835.35 | 123835.35 | 503725.65 | 150267 | 276438.09 | 967203.56 | 4007134.49 | 1873022.86 | 7777791.65 | 32338.34 | 20049.7708 | 63684.5026 | 7933965.34 | 43634.7318 | 88777.6734 | -63684.5026 | 68727.9026 | 8002693.2426 | 2644421.77 | [5 empty] | N | LA01 | 100%
500653 | SR15 ES Internal Sewer Flooding APNRV Programme Phase1 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2015-06-29 | 2015-06-29 | 2015-08-31 | 2017-09-12 | 2017-09-12 | Scottish Water Wide | 0 | 0 | 225769 | 259370.22 | 452492.36 | -103028.98 | 0 | 0 | 834602.6 | 0 | 0 | 0 | 834602.6 | 0 | 0 | 0 | 0 | 834602.6 | 692829.64 | [5 empty] | N | FL_NAMED | 19.24% | FL_DD | 80.76%
502020 | SR15 ESD Core Balancing Team Payment Line | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2022-04-01 | 2022-07-22 | Scottish Water Wide | 0 | 0 | 3248659 | 2290134.6 | 2221100.48 | -1048799.05 | -2494785.13 | -3811324.47 | 404985.43 | -2330210.43 | -1165105.217 | -1617364.3952 | -1925225 | -452259.1783 | 0 | 0 | -452259.1783 | -2377484.1783 | 4156900.56 | [5 empty] | N | CM_WSNI | 25% | CM_WWNI | 25% | DW2 | 50%
500584 | SR15 Heavy Goods Vehicles | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 2017-01-19 |  | Scottish Water Wide | 0 | 0 | 1556315 | -128066.18 | 0 | 0 | 0 | 0 | 1428248.82 | 0 | 0 | 0 | 1428248.82 | 0 | 0 | 0 | 0 | 1428248.82 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503580 | SR15 Internal Sewer Flooding Alternative Solutions Phase 10 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2019-06-26 | 2019-06-26 | 2019-08-19 | 2021-08-25 | 2021-08-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 581529.01 | 25642.99 | 607172 | 117828.15 | 25843.0487 | 35874.5512 | 725000.15 | 10031.5025 | 0 | 0 | 10031.5025 | 735031.6525 | 741832.2 | [5 empty] | N | FL_DD | 78.07% | FL_NAMED | 21.93%
502939 | SR15 Internal Sewer Flooding Alternative Solutions Phase 2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-10-11 | 2017-10-11 | 2017-11-01 | 2019-03-14 | 2019-03-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 569917.99 | 726547.23 | -43185.89 | 0 | 1253279.33 | 0 | 0 | 0 | 1253279.33 | 0 | 0 | 0 | 0 | 1253279.33 | 491137.98 | [5 empty] | N | FL_DD | 69.23% | FL_NAMED | 30.77%
502976 | SR15 Internal Sewer Flooding Alternative Solutions Phase 3 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater | SW | SWMD | Flooding Demand Driven | MS4 | 2017-12-12 | 2017-12-12 | 2018-02-08 | 2021-03-29 | 2021-04-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 296794.39 | 1177800.04 | -23056.94 | 14305.51 | 1465843 | 1000 | 0 | 0 | 1466843 | 0 | 0 | 0 | 0 | 1466843 | 355536.5 | [5 empty] | N | FL_DD | 100%
503080 | SR15 Internal Sewer Flooding Alternative Solutions Phase 4 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2018-02-26 | 2018-02-26 | 2018-04-02 | 2020-03-13 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 93859.49 | 771792.73 | 49971.87 | 126950.11 | 1042574.2 | 0 | 0 | 0 | 1042574.2 | 0 | 0 | 0 | 0 | 1042574.2 | 355536.5 | [5 empty] | N | FL_DD | 100%
503294 | SR15 Internal Sewer Flooding Alternative Solutions Phase 5 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2018-07-04 | 2018-07-04 | 2018-07-09 | 2019-03-05 | 2019-03-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 441794.39 | -39773.38 | 1899.12 | 403920.13 | 0 | 0 | 0 | 403920.13 | 0 | 0 | 0 | 0 | 403920.13 | 175086.76 | [5 empty] | N | FL_DD | 100%
503389 | SR15 Internal Sewer Flooding Alternative Solutions Phase 6 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2018-10-01 | 2018-10-01 | 2018-10-15 | 2020-06-04 | 2020-06-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 395511.17 | 67754.2 | 56.12 | 463321.48 | 0 | 0 | 0 | 463321.48 | 0 | 0 | 0 | 0 | 463321.48 | 175086.76 | [5 empty] | N | FL_DD | 100%
503390 | SR15 Internal Sewer Flooding Alternative Solutions Phase 7 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS4 | 2018-10-01 | 2018-10-01 | 2018-10-15 | 2021-03-19 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 158404.72 | 729005.69 | 96732.4 | 984142.81 | 0 | 0 | 0 | 984142.81 | 0 | 0 | 0 | 0 | 984142.81 | 175086.76 | [5 empty] | N | FL_DD | 100%
503489 | SR15 Internal Sewer Flooding Alternative Solutions Phase 8 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2019-02-28 | 2019-02-28 | 2019-05-16 | 2021-11-08 | 2021-10-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 106086.14 | 938707.46 | 71150.4 | 1115944 | 2042.81 | 759.5639 | 1054.404 | 1117986.81 | 294.8401 | 0 | 0 | 294.8401 | 1118281.6501 | 2214793.31 | [5 empty] | N | FL_DD | 62.82% | FL_NAMED | 37.18%
503579 | SR15 Internal Sewer Flooding Alternative Solutions Phase 9 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS4 | 2019-06-21 | 2019-06-21 | 2019-07-01 | 2021-01-27 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 690225.56 | 146377.44 | 836603 | 0 | 0 | 0 | 836603 | 0 | 0 | 0 | 0 | 836603 | 990873.57 | [5 empty] | N | FL_DD | 72.23% | FL_NAMED | 27.77%
500504 | SR15 Legacy Legal | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-04 |  | Scottish Water Wide | 0 | 0 | 70532 | 199468 | 0 | 47500 | 87625.08 | 98699.92 | 503825 | 0 | 0 | 0 | 503825 | 0 | 0 | 0 | 0 | 503825 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500583 | SR15 Light Commercial Vehicles | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 2017-01-19 |  | Scottish Water Wide | 0 | 0 | 3286121.99 | -153159.01 | 0 | 0 | 0 | 0 | 3132962.98 | 0 | 0 | 0 | 3132962.98 | 0 | 0 | 0 | 0 | 3132962.98 | 613322.63 | [5 empty] | N | CM_M&G | 100%
506203 | SR15 Logan Reservoir MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2020-05-11 | 2020-10-16 | 2020-10-20 | 2021-05-07 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 989902 | 989902 | 2897.65 | 0 | 0 | 992799.65 | 0 | 0 | 0 | 0 | 992799.65 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502801 | SR15 LRC3 - Daldowie WWTW Increase in Full Flow to Treatment | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2018-08-30 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | South Lanarkshire | 0 | 0 | 0 | 0 | 68250.6 | -68249.6 | 387.54 | 0 | 388.54 | 0 | 0 | 0 | 388.54 | 0 | 0 | 0 | 0 | 388.54 | 3550582.52 | [5 empty] | N | EC01B | 50% | EC10B | 50%
502400 | SR15 LRC3 - Short Term UWWTD Compliance at Dalmarnock & Daldowie WWTWs | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2017-01-26 | 2017-01-26 | 2017-06-13 | 2018-05-31 | 2018-11-30 | Glasgow City | 0 | 0 | 0 | 326367 | 357093.42 | 59347.12 | 0 | 0 | 742807.54 | 0 | 0 | 0 | 742807.54 | 0 | 0 | 0 | 0 | 742807.54 | 15547843.63 | [5 empty] | Y | EC01A | 100% | [40 empty] | 2 | [26 empty] | 0
500487 | SR15 Meter Maintenance and Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-05-21 |  | Scottish Water Wide | 0 | 0 | 3117885.42 | 386245.58 | 1417021.8 | 1491308 | 1073849.39 | 783014.81 | 8269325 | 2510675.35 | 0 | 0 | 10780000.35 | 0 | 0 | 0 | 0 | 10780000.35 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508601 | SR15 Milnbe Weir Eel Pass PPD | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS0 | 2021-03-03 | 2022-01-17 | 2022-03-18 | 2023-02-23 | 2023-02-24 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11429 | 11429 | 88571.56 | 88571.56 | 122952.4042 | 100000.56 | 34380.8442 | 0 | 0 | 34380.8442 | 134381.4042 | 0 | [5 empty] | N | WR1 | 100%
505407 | SR15 Milnby Weir | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | SEPA | SWD | SOSI | MS0 | 2021-03-03 | 2021-04-12 | 2021-05-18 | 2021-08-10 | 2021-11-08 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | WR1 | 100% | [37 empty] | 1 | [29 empty] | 0
500505 | SR15 Milngavie | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-15 | 2021-06-04 |  | Scottish Water Wide | 0 | 0 | 70745.59 | 26421.97 | 72932.44 | 85762.43 | 70314.68 | 43018.89 | 369196 | 0 | 0 | 0 | 369196 | 0 | 0 | 0 | 0 | 369196 | 613322.63 | [5 empty] | N | CM_M&G | 100%
504539 | SR15 Mugdock and Craigmaddie Strategic Approach | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS3 | 2020-01-30 | 2020-02-12 | 2020-02-17 | 2022-04-07 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 69631.78 | 172070.22 | 241702 | 9025.9 | 0 | 0 | 250727.9 | 0 | 0 | 0 | 0 | 250727.9 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500486 | SR15 Non Domestic Meters - New Installations | Q&S4 | Supporting economic development | First Time Meters |  |  | Water | SW | SWD | First Time Meters | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-05-21 |  | Scottish Water Wide | 0 | 0 | 842536 | 2163574.9 | 909392.2 | 1484611.9 | 1553234.3 | 1218840.7 | 8172190 | 1520809.54 | 0 | 0 | 9692999.54 | 0 | 0 | 0 | 0 | 9692999.54 | 10184396.32 | [5 empty] | N | WG6 | 100%
500506 | SR15 Outdoor Access | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-04 |  | Scottish Water Wide | 0 | 0 | 6892 | 2108 | 5900 | 4500 | 8348.46 | 1149.54 | 28898 | 0 | 0 | 0 | 28898 | 0 | 0 | 0 | 0 | 28898 | 613322.63 | [5 empty] | N | CM_M&G | 100%
505146 | SR15 Pendrich Farm Drainage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-03-11 | 2020-12-01 | 2021-08-05 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546.17 | 546.17 | 19357.86 | 0 | 0 | 19904.03 | 0 | 0 | 0 | 0 | 19904.03 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402243 | SR15 Planning - Activity Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2011-08-01 | 2012-10-22 | 2012-11-12 | 2016-06-14 |  | Scottish Water Wide | 831840.17 | 831840.17 | 213570.68 | 49699.57 | 2416.25 | 0 | 0 | 0 | 265686.5 | 0 | 0 | 0 | 1097526.67 | 0 | 0 | 0 | 0 | 1097526.67 | 306661.32 | [5 empty] | N | QS4EQS | 100%
500585 | SR15 Plant | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 2016-12-19 |  | Scottish Water Wide | 0 | 0 | 112694.23 | -26613.11 | 0 | 0 | 0 | 0 | 86081.12 | 0 | 0 | 0 | 86081.12 | 0 | 0 | 0 | 0 | 86081.12 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500507 | SR15 Redundant Assets | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-04 |  | Scottish Water Wide | 0 | 0 | 776 | 408499 | 396808.95 | 492585.96 | 427023.13 | 232901.51 | 1958594.54 | -21135.54 | 0 | 0 | 1937459 | 0 | 0 | 0 | 0 | 1937459 | 613322.63 | [5 empty] | N | CM_M&G | 100%
504344 | SR15 Rosebery WTW T&O - Contingency PAC Dosing Plant | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2020-04-29 | 2021-04-12 | 2021-04-12 | 2021-08-16 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 33463.08 | 933341.13 | 966804.21 | 533996.67 | 0 | 0 | 1500800.88 | 0 | 0 | 0 | 0 | 1500800.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500574 | SR15 Rural Estates | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-18 | 2015-05-18 | 2015-05-18 | 2021-06-11 |  | Scottish Water Wide | 0 | 0 | 94837.75 | 46162.25 | 91925.27 | 81074.73 | 88415.18 | 72473.82 | 474889 | 0 | 0 | 0 | 474889 | 0 | 0 | 0 | 0 | 474889 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502041 | SR15 Security Capital Maintenance Bundle 1 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-08-23 | 2017-03-23 | 2017-06-22 | 2017-12-19 |  | Scottish Water Wide | 0 | 0 | 0 | 13327.74 | 81707.36 | 0 | 0 | 0 | 95035.1 | 0 | 0 | 0 | 95035.1 | 0 | 0 | 0 | 0 | 95035.1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502042 | SR15 Security Capital Maintenance Bundle 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-08-23 | 2017-02-24 | 2017-04-20 | 2017-12-12 |  | Scottish Water Wide | 0 | 0 | 0 | 18306.39 | 166315.49 | 1659.74 | 0 | -552.23 | 185729.39 | 0 | 0 | 0 | 185729.39 | 0 | 0 | 0 | 0 | 185729.39 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502044 | SR15 Security Capital Maintenance Bundle 4 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-08-23 | 2017-08-16 | 2017-08-16 | 2017-08-03 |  | Scottish Water Wide | 0 | 0 | 0 | 6208.69 | -2726.15 | 0 | 0 | 0 | 3482.54 | 0 | 0 | 0 | 3482.54 | 0 | 0 | 0 | 0 | 3482.54 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502255 | SR15 Security Capital Maintenance Bundle 5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWD | Wastewater infrastructure | MS3 | 2017-11-08 | 2018-02-21 | 2018-03-15 | 2021-06-18 |  | Scottish Water Wide | 0 | 0 | 0 | 25805.39 | 98357.6 | 50680.55 | 242639.52 | 202020.94 | 619504 | 123572.38 | 0 | 0 | 743076.38 | 0 | 0 | 0 | 0 | 743076.38 | 209381.79 | [5 empty] | N | CM_WSNI | 100%
502596 | SR15 Security Capital Maintenance Bundle 6 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS6 | 2017-10-30 | 2019-05-14 | 2019-07-08 | 2020-07-02 |  | Scottish Water Wide | 0 | 0 | 0 | 2093.02 | 26067.44 | 72082.58 | 1340375.08 | 56436.88 | 1497055 | 3780.26 | 0 | 0 | 1500835.26 | 0 | 0 | 0 | 0 | 1500835.26 | 209381.79 | [5 empty] | N | CM_WSNI | 100%
502597 | SR15 Security Capital Maintenance Bundle 7 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS6 | 2017-10-24 | 2018-10-29 | 2019-04-22 | 2020-06-05 |  | Scottish Water Wide | 0 | 0 | 0 | 1046.51 | 4932.82 | 33722.03 | 196808.5 | 1973.14 | 238483 | 1839.69 | 0 | 0 | 240322.69 | 0 | 0 | 0 | 0 | 240322.69 | 209381.79 | [5 empty] | N | CM_WSNI | 100%
502594 | SR15 Security Capital Maintenance Bundle 8 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-10-24 | 2018-06-11 | 2018-07-10 | 2020-06-08 |  | Scottish Water Wide | 0 | 0 | 0 | 2093.02 | 2906.98 | 5932.64 | 30594 | 823.56 | 42350.2 | 0 | 0 | 0 | 42350.2 | 0 | 0 | 0 | 0 | 42350.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502595 | SR15 Security Capital Maintenance Bundle 9 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS4 | 2017-10-24 | 2019-05-21 | 2019-06-06 | 2020-12-21 |  | Scottish Water Wide | 0 | 0 | 0 | 2093.02 | 4779.5 | 8968.68 | 629312.89 | 82417.14 | 727571.23 | 3158.19 | 0 | 0 | 730729.42 | 0 | 0 | 0 | 0 | 730729.42 | 209381.79 | [5 empty] | N | CM_WSNI | 100%
502254 | SR15 Security Capital Maintenance IDP costs & emerging needs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWD | Wastewater infrastructure | MS3 | 2016-11-30 | 2017-03-28 | 2017-03-29 | 2021-05-03 |  | Scottish Water Wide | 0 | 0 | 0 | 98699.92 | 93300.08 | 22889.14 | 54838.82 | 97513.04 | 367241 | 227.89 | 0 | 0 | 367468.89 | 0 | 0 | 0 | 0 | 367468.89 | 209381.79 | [5 empty] | N | CM_WSNI | 100%
500980 | SR15 SPS Data Quality Testing & Priority Remedials Phase 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-05-31 | 2016-11-08 | 2016-11-30 | 2021-05-21 |  | Scottish Water Wide | 0 | 0 | 0 | 105487.75 | 149063.7 | 60067.54 | 36021.19 | -31786.18 | 318854 | 7955.28 | 0 | 0 | 326809.28 | 0 | 0 | 0 | 0 | 326809.28 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
507104 | SR15 SR Mission Year 6 Mission Hatch | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-07-21 | 2020-11-10 | 2020-11-06 | 2022-05-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271395.59 | 271395.59 | 678604.41 | 0 | 0 | 950000 | 0 | 0 | 0 | 0 | 950000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501192 | SR15 SR Repairs Additional Cells | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-23 | 2015-11-23 | 2016-01-14 | 2017-07-10 |  | All North Unitary Authorities | 0 | 0 | 351514 | 838956.23 | -158862.81 | 105.07 | -105.07 | 25546.61 | 1057154.03 | -25075.86 | 0 | 0 | 1032078.17 | 0 | 0 | 0 | 0 | 1032078.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403730 | SR15 Start Early Delivery Plan Development Wastewater Central - HL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2015-12-01 |  | Scottish Water Wide | 20000 | 0 | -159.27 | 389.43 | 42.55 | 0 | 0 | 0 | 272.71 | 0 | 0 | 0 | 20272.71 | 0 | 0 | 0 | 0 | 20272.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403732 | SR15 Start Early Delivery Plan Development Wastewater East - HL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-09-30 |  | All East Unitary Authorities | 432263.69 | 0 | 250862.31 | 1140.09 | 455.14 | 0 | 0 | 0 | 252457.54 | 0 | 0 | 0 | 684721.23 | 0 | 0 | 0 | 0 | 684721.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403734 | SR15 Start Early Delivery Plan Development Wastewater North - HL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-01-13 |  | All North Unitary Authorities | 4341 | 0 | -2833.53 | 0 | 0 | 0 | 0 | 0 | -2833.53 | 0 | 0 | 0 | 1507.47 | 0 | 0 | 0 | 0 | 1507.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403728 | SR15 Start Early Delivery Plan Development Wastewater South - HL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-15 |  | All South Unitary Authorities | 337395.87 | 0 | 383353.58 | -34579.15 | 2051.89 | 0 | 0 | 0 | 350826.32 | 0 | 0 | 0 | 688222.19 | 0 | 0 | 0 | 0 | 688222.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403731 | SR15 Start Early Delivery Plan Development Water Central - HL | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-07 |  | Scottish Water Wide | 361041.47 | 0 | 132065.53 | 8673.13 | 1362.71 | 0 | 0 | 74.82 | 142176.19 | 0 | 0 | 0 | 503217.66 | 0 | 0 | 0 | 0 | 503217.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403733 | SR15 Start Early Delivery Plan Development Water East - HL | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-06-07 |  | All East Unitary Authorities | 240906.27 | 0 | 182605.79 | 5545.02 | 0 | 0 | 0 | 0 | 188150.81 | 0 | 0 | 0 | 429057.08 | 0 | 0 | 0 | 0 | 429057.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403735 | SR15 Start Early Delivery Plan Development Water North - HL | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-08 |  | All North Unitary Authorities | 171670.62 | 0 | 426948.38 | -25211.45 | 1712.66 | 0 | 0 | 0 | 403449.59 | 0 | 0 | 0 | 575120.21 | 0 | 0 | 0 | 0 | 575120.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403729 | SR15 Start Early Delivery Plan Development Water South - HL | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-19 |  | All South Unitary Authorities | 156565.39 | 0 | -6565.39 | -17405.82 | 0 | 0 | 0 | 0 | -23971.21 | 0 | 0 | 0 | 132594.18 | 0 | 0 | 0 | 0 | 132594.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403736 | SR15 Start Early Delivery Plan Development Water West - HL | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-15 |  | All West Unitary Authorities | 194289.16 | 0 | 183500.17 | 15479.81 | -8604.1 | 0 | 0 | 0 | 190375.88 | 0 | 0 | 0 | 384665.04 | 0 | 0 | 0 | 0 | 384665.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403737 | SR15 Start Early Delivery Plan Development Water West - HL - 4037370000 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-05-10 |  | All West Unitary Authorities | 277227.52 | 0 | 34192.9 | 0 | 0 | 0 | 0 | 0 | 34192.9 | 0 | 0 | 0 | 311420.42 | 0 | 0 | 0 | 0 | 311420.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501001 | SR15 TE CM Staney Hill North (Q Sandy Loch WTW) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | NONINF | DWQ Compliance | MS3 | 2015-09-28 | 2018-09-21 | 2018-09-24 | 2023-02-16 | 2023-02-20 | Shetland Islands | 0 | 0 | 31287 | 141658.16 | 361096.4 | 1376955.69 | 783861.76 | 14090 | 2708949 | 3447261 | 3447261 | 5754114.1614 | 6156210 | 2306853.1614 | 0 | 0 | 2306853.1614 | 8463063.1614 | 0 |  |  |  |  | -5000.0003 | Y | DW25D | 100% | [22 empty] | 1 | [44 empty] | 0
403424 | SR15 Technology and Innovation strategy work | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2013-03-14 | 2013-03-14 | 2013-04-03 | 2018-03-12 |  | Scottish Water Wide | 174282.61 | 0 | 0.39 | 0 | 0 | 0 | 0 | 0 | 0.39 | 0 | 0 | 0 | 174283 | 0 | 0 | 0 | 0 | 174283 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501005 | SR15 Telemetry RTU Replacement - Phase 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS6 | 2016-02-25 | 2016-07-22 | 2016-08-31 | 2020-02-28 |  | Scottish Water Wide | 0 | 0 | 14482.71 | 588592.43 | 182330.85 | 37624.64 | 46869.08 | 17951.29 | 887851 | 24835.22 | 0 | 0 | 912686.22 | 0 | 0 | 0 | 0 | 912686.22 | 613322.63 | [5 empty] | N | CM_WWNI | 23.59% | CM_WSNI | 76.41%
501006 | SR15 Telemetry RTU Replacement - Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2016-01-25 | 2016-05-26 | 2016-06-10 | 2017-11-30 |  | Scottish Water Wide | 0 | 0 | 198402 | 146023.97 | -2525.15 | 12.46 | 255 | 0 | 342168.28 | 0 | 0 | 0 | 342168.28 | 0 | 0 | 0 | 0 | 342168.28 | 613322.63 | [5 empty] | N | CM_WSNI | 40.13% | CM_WWNI | 59.87%
501007 | SR15 Telemetry RTU Replacement - Phase 3 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS4 | 2016-09-22 | 2017-07-26 | 2017-08-31 | 2021-03-19 |  | Scottish Water Wide | 0 | 0 | 0 | 145119.88 | 657878.56 | 289095.84 | 298210.62 | 58262.1 | 1448567 | 10023.41 | 0 | 0 | 1458590.41 | 0 | 0 | 0 | 0 | 1458590.41 | 613322.63 | [5 empty] | N | CM_WWNI | 28.21% | CM_WSNI | 71.79%
501008 | SR15 Telemetry RTU Replacement - Phase 4 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS4 | 2016-09-22 | 2018-01-25 | 2018-02-28 | 2021-01-28 |  | Scottish Water Wide | 0 | 0 | 0 | 38882.64 | 228845.78 | 329270.5 | 452321.16 | 36106.92 | 1085427 | 5471.85 | 0 | 0 | 1090898.85 | 0 | 0 | 0 | 0 | 1090898.85 | 613322.63 | [5 empty] | N | CM_WWNI | 38.1% | CM_WSNI | 61.9%
501009 | SR15 Telemetry RTU Replacement - Phase 5 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-09-22 | 2017-12-15 | 2018-02-05 | 2021-07-19 |  | Scottish Water Wide | 0 | 0 | 0 | 42565.39 | 225201.29 | 696607.96 | 803030.4 | 151210.55 | 1918615.59 | 62632.7 | 0 | 0 | 1981248.29 | 0 | 0 | 0 | 0 | 1981248.29 | 613322.63 | [5 empty] | N | CM_WWNI | 36.89% | CM_WSNI | 63.11%
500948 | SR15 Telemetry RTU Upgrading - Phase 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS6 | 2016-05-13 | 2016-12-13 | 2016-12-14 | 2019-04-23 |  | Scottish Water Wide | 0 | 0 | 0 | 54909.96 | 117508.41 | 10424.25 | -4687.35 | 9659.73 | 187815 | 3629.2 | 0 | 0 | 191444.2 | 0 | 0 | 0 | 0 | 191444.2 | 306661.32 | [5 empty] | N | CM_WWNI | 100%
500949 | SR15 Telemetry RTU Upgrading - Phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS6 | 2016-08-18 | 2017-03-30 | 2017-06-01 | 2021-01-19 |  | Scottish Water Wide | 0 | 0 | 0 | 18917.56 | 303371 | 87504.25 | 201359.22 | 9084.97 | 620237 | 0 | 0 | 0 | 620237 | 0 | 0 | 0 | 0 | 620237 | 613322.63 | [5 empty] | N | CM_WWNI | 24.68% | CM_WSNI | 75.32%
500502 | SR15 Tenant Housing | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-08 |  | Scottish Water Wide | 0 | 0 | 37532.26 | 18047.74 | 29798.9 | 27969.89 | 24352.21 | 16850 | 154551 | 0 | 0 | 0 | 154551 | 0 | 0 | 0 | 0 | 154551 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500201 | SR15 Waste Water DOA Telemetry Schematics Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-03-23 | 2015-03-23 | 2015-03-23 | 2018-08-09 |  | Scottish Water Wide | 0 | 0 | 146264.15 | -14402.15 | 36408 | 10317.27 | 0 | 0 | 178587.27 | 0 | 0 | 0 | 178587.27 | 0 | 0 | 0 | 0 | 178587.27 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
504292 | SR15 White Loch MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-01-27 | 2020-02-28 | 2021-09-09 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 3461.42 | 24878.91 | 28340.32 | 21659.68 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502303 | SR15 WW Temporary Chemical Dosing Systems Upgrade -Phase 5 (NORTH) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2020-06-01 | 2022-01-17 | 2022-05-06 | 2023-07-31 |  | Scottish Water Wide | 0 | 0 | 0 | 21103.73 | 14401.03 | 542.61 | 18708.38 | 97213.3 | 151969.05 | 1288030.95 | 0 | 0 | 1440000 | 0 | 0 | 0 | 0 | 1440000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
49576 | SR15_CMA_MAG - Management and General - Adjustment | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2439683.58 | [5 empty] | N | SR15_CMA_MAG | 100%
49577 | SR15_CMA_UNP - Unpromoted Capital Maintenance - Adjustment | Q&S4 | Sustaining existing high service for customers | CM Risk Drawdown |  |  | General |  | SWD | CM Risk Drawdown | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SR15_CMA_UNP | 100%
49580 | SR15_CMA_WSI - Water infrastructure - Adjustment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3804722.5 | [5 empty] | N | SR15_CMA_WSI | 100%
49581 | SR15_CMA_WSNI - Water non infrastructure - Adjustment | Q&S4 | Sustaining existing high service for customers | Water non infrastructure |  |  | General |  | SWD | Water non infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119022.58 | [5 empty] | N | SR15_CMA_WSNI | 100%
49578 | SR15_CMA_WWI - Wastewater infrastructure - Adjustment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209381.79 | [5 empty] | N | SR15_CMA_WWI | 100%
49579 | SR15_CMA_WWNI - Wastewater non infrastructure - Adjustment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWD | Wastewater non infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90601.29 | [5 empty] | N | SR15_CMA_WWNI | 100%
49585 | SR15_CMP_LATE - Late - Adjustment | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23327986.29 | [5 empty] | N | SR15_CMP_LATE | 100%
49584 | SR15_CMP_PLAN - Planned - Adjustment | Q&S3B | Completion | OMG180 |  |  | General |  | SWD | OMG180 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64605651.09 | [5 empty] | N | SR15_CMP_PLAN | 100%
49544 | SR15_DWA_SEMD - SEMD - Adjustment | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | General |  | SWD | SEMD | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3783254.92 | [5 empty] | N | SR15_DWA_SEMD | 100%
49545 | SR15_DWA_SOSI - SOSI - Adjustment | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | General |  | SWD | SOSI | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SR15_DWA_SOSI | 100%
49547 | SR15_DWA_SRE - Supply Resilience - Adjustment | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | General |  | SWD | Supply Resilience | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3402929.81 | [5 empty] | N | SR15_DWA_SRE | 100%
49542 | SR15_DWQ_COM - DWQ Compliance - Adjustment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3671081.58 | [5 empty] | N | SR15_DWQ_COM | 100%
49543 | SR15_DWQ_REL - DWQ Reliability - Adjustment | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | General |  | SWD | DWQ Reliability | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8083206.57 | [5 empty] | N | SR15_DWQ_REL | 100%
49561 | SR15_ENV_ENVS - Environmental Studies - Adjustment | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | General |  | SWD | Environmental Studies | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4709311.8 | [5 empty] | N | SR15_ENV_ENVS | 100%
49554 | SR15_ENV_RBWD - Revised Bathing Waters Directive - Adjustment | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | General |  | SWD | Revised Bathing Waters Directive | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375046 | [5 empty] | N | SR15_ENV_RBWD | 100%
49556 | SR15_ENV_SHEL - Ringfenced Environmental Adjustment | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | General |  | SWD | Ring Fenced Environmental | MS0 | 2018-04-01 |  |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000986.04 | [5 empty] | N | SR15_ENV_SHEL | 100%
49555 | SR15_ENV_SLU - Sludge - Adjustment | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | General |  | SWD | Sludge | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4565666.17 | [5 empty] | N | SR15_ENV_SLU | 100%
49552 | SR15_ENV_UWWD - UWWTD - Adjustment | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | General |  | SWD | UWWTD - Works | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632725.6 | [5 empty] | N | SR15_ENV_UWWD | 100%
49612 | SR15_EXC - Exceptional - Adjustment | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWD | Exceptional Capital Maintenance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157385532.51 | [5 empty] | N | SR15_EXC_EXC | 100%
49538 | SR15_IR18_IR18 - IR18 - Adjustment | IR18 | IR18 Allowance | IR18 |  |  | Wastewater |  | SWD | IR18 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3426036.59 | [5 empty] | N | SR15_IR18_IR18 | 100%
49536 | SR15_RSK_CMR - Maintenance Risk - Adjustment | Q&S4 | Programme Risk | Maintenance Risk |  |  | General |  | SWD | Maintenance Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281321099.8 | [5 empty] | N | SR15_RSK_CMR | 100%
49535 | SR15_RSK_COMP - Completion Risk - Adjustment | Q&S4 | Programme Risk | Completion Risk |  |  | General |  | SWD | Completion Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000000 | [5 empty] | N | SR15_RSK_COMP | 100%
49537 | SR15_RSK_EHR - Enhanced Risk - Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | General |  | SWD | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139184927.82 | [5 empty] | N | SR15_RSK_EHR | 100%
50003 | SR15_RSK_EHR - Risk CEO- Adjustment | Q&S4 | Programme Risk | Enhanced Risk - Forecast Variance |  |  | General |  | SWD | Enhanced Risk - Forecast Variance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61195392.84 | [5 empty] | N | SR15_RSK_EHU | 100%
49586 | SR15_RSK_RINF - Ringfenced for Inflation - Adjustment | Q&S4 | Programme Risk | Ringfenced for Inflation |  |  | General |  | SWD | Ringfenced for Inflation | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38153821.58 | [5 empty] | N | SR15_RSK_RINF | 100%
49569 | SR15_SED_DAA - Developer Asset Adoption - Adjustment | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | General |  | SWD | Developer Asset Adoption | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2199945.14 | [5 empty] | N | SR15_SED_DAA | 100%
49570 | SR15_SED_FTM - First Time Meters - Adjustment | Q&S4 | Supporting economic development | First Time Meters |  |  | General |  | SWD | First Time Meters | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SR15_SED_FTM | 100%
49582 | SR15_SED_INFC - Infra Charge - Adjustment | Q&S4 | Supporting economic development | Infra Charge |  |  | General |  | SWD | Infra Charge | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG5 | 50% | WG5 | 50%
49571 | SR15_SED_NRSW - NRSWA - Adjustment | Q&S4 | Supporting economic development | NRSWA |  |  | General |  | SWD | NRSWA | MS2 |  | 2018-04-01 |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10652576.7 | [5 empty] | N | SR15_SED_NRSW | 100%
49567 | SR15_SED_RCC - RCC - Adjustment | Q&S4 | Supporting economic development | RCC |  |  | General |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64840488.47 | [5 empty] | N | SG2 | 50% | WG2 | 50%
49568 | SR15_SED_SCAP - Strategic Capacity - Adjustment | Q&S4 | Supporting economic development | Strategic Capacity |  |  | General |  | SWD | Strategic Capacity | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74218069.25 | [5 empty] | N | SR15_SED_SCAP | 100%
49565 | SR15_SEW_EFR - External Flooding - Adjustment | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SR15_SEW_EFR | 100%
49564 | SR15_SEW_IFR - Internal Flooding - Adjustment | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1452384.35 | [5 empty] | N | SR15_SEW_IFR | 100%
49613 | SR15_UID_UWWD - UWWTD - UIDs - Adjustment | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS2 | 2015-03-31 | 2015-03-31 |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12905115.34 | [5 empty] | N | SR15_UID_UWWD | 100%
503634 | SR21 Abergeldie Road Ballater | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2020-12-11 | 2021-09-07 | 2022-02-07 | 2022-07-22 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 8769.57 | 15257.02 | 24026.59 | 55684.98 | 0 | 0 | 79711.57 | 0 | 0 | 0 | 0 | 79711.57 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511097 | SR21 ASD - ARDRISHAIG WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 906441.02 | 0 | 0 | 906441.02 | 0 | 0 | 0 | 0 | 906441.02 | 0 | [5 empty] | N | SR21_WA | 100%
511099 | SR21 ASD - Auchneel WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191214.02 | 0 | 0 | 191214.02 | 0 | 0 | 0 | 0 | 191214.02 | 0 | [5 empty] | N | SR21_WA | 100%
511100 | SR21 ASD - Belmore WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273163.94 | 0 | 0 | 273163.94 | 0 | 0 | 0 | 0 | 273163.94 | 0 | [5 empty] | N | SR21_WA | 100%
511101 | SR21 ASD - Blairlinnans WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318690.98 | 0 | 0 | 318690.98 | 0 | 0 | 0 | 0 | 318690.98 | 0 | [5 empty] | N | SR21_WA | 100%
511103 | SR21 ASD - Glengap WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908349.98 | 0 | 0 | 908349.98 | 0 | 0 | 0 | 0 | 908349.98 | 0 | [5 empty] | N | SR21_WA | 100%
511120 | SR21 ASD - Hopes WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908349.98 | 0 | 0 | 908349.98 | 0 | 0 | 0 | 0 | 908349.98 | 0 | [5 empty] | N | SR21_WA | 100%
511121 | SR21 ASD - Inveraray WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 906066.98 | 0 | 0 | 906066.98 | 0 | 0 | 0 | 0 | 906066.98 | 0 | [5 empty] | N | SR21_WA | 100%
511122 | SR21 ASD - Mannofield WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455272.94 | 0 | 0 | 455272.94 | 0 | 0 | 0 | 0 | 455272.94 | 0 | [5 empty] | N | SR21_WA | 100%
511123 | SR21 ASD - Tarbert Arg WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2022-01-31 | 2023-08-09 | 2023-11-07 | 2024-10-14 | 2024-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 906066.98 | 0 | 0 | 906066.98 | 0 | 0 | 0 | 0 | 906066.98 | 0 | [5 empty] | N | SR21_WA | 100%
505652 | SR21 Badentinan Spey Wellfield upgrade | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-07-21 | 2024-02-15 | 2024-05-21 | 2026-07-21 |  | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58020 | 58020 | 7941979.64 | 0 | 0 | 7999999.64 | 0 | 0 | 0 | 0 | 7999999.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503635 | SR21 Beech Cottage Rothienorman Surface Water Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-05-12 | 2022-11-22 | 2023-02-15 | 2024-02-06 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 10595.54 | 43674.88 | 54270.42 | 545729.58 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 600000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503761 | SR21 Bonnycraig WTW Growth and Quality | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | MPT | SR21 Early Start | MS0 | 2019-09-30 | 2021-05-10 | 2021-05-25 | 2022-12-19 | 2023-03-16 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1825358.23 | 9159206.18 | 10984564.41 | 17346354.69 | 0 | 0 | 28330919.1 | 0 | 0 | 0 | 0 | 28330919.1 | 0 | [5 empty] | N | SR21_WA | 100%
511757 | SR21 Borehole Inspections (Phase 1) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MSU | 2021-04-01 | 2021-05-24 | 2021-05-31 | 2021-10-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1399999.98 | 0 | 0 | 1399999.98 | 0 | 0 | 0 | 0 | 1399999.98 | 306661.32 | [5 empty] | N | QS4EQS | 100%
505409 | SR21 Bradan_WTW Future Plan | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-08-04 | 2025-11-27 | 2026-02-20 | 2028-12-07 | 2028-12-08 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 125581.4 | 35359 | 160940.4 | 99839371.99 | 0 | 0 | 100000312.39 | 0 | 0 | 0 | 0 | 100000312.39 | 0 | [5 empty] | N | SR21_WA | 100%
505579 | SR21 Camphill WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2023-08-11 | 2025-10-03 | 2026-01-02 | 2028-06-06 | 2028-06-07 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51319.12 | 51319.12 | 25948918.32 | 0 | 0 | 26000237.44 | 0 | 0 | 0 | 0 | 26000237.44 | 0 | [5 empty] | N | SR21_WA | 100%
510139 | SR21 Carradale WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-05-30 | 2023-12-06 | 2024-03-05 | 2025-02-10 | 2025-02-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13183.98 | 13183.98 | 11987336.2 | 0 | 0 | 12000520.18 | 0 | 0 | 0 | 0 | 12000520.18 | 0 | [5 empty] | N | SR21_WA | 100%
503638 | SR21 Carstairs Junction Overland Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-08-04 | 2023-01-26 | 2023-04-24 | 2024-06-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 31905.02 | 62896 | 94801.02 | 2429977.03 | 0 | 0 | 2524778.04 | 0 | 0 | 0 | 0 | 2524778.04 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506578 | SR21 Castle Moffat | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-05-24 | 2024-05-31 | 2024-08-30 | 2027-01-14 | 2027-01-15 | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53217.74 | 53217.74 | 20947143.55 | 0 | 0 | 21000361.29 | 0 | 0 | 0 | 0 | 21000361.29 | 0 | [5 empty] | N | SR21_WA | 100%
510648 | SR21 CM Energy Team - CHP | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS3 | 2021-01-27 | 2021-02-25 | 2021-02-25 | 2027-03-11 | 2027-06-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654.21 | 654.21 | 799345.44 | 0 | 0 | 799999.65 | 0 | 0 | 0 | 0 | 799999.65 | 0 | [5 empty] | N | SR21_SS | 100%
510646 | SR21 CM Energy Team - Hydro | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS3 | 2021-01-29 | 2021-03-10 | 2021-03-15 | 2027-03-31 | 2027-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76897.24 | 76897.24 | 5166102.76 | 0 | 0 | 5243000 | 0 | 0 | 0 | 0 | 5243000 | 0 | [5 empty] | N | SR21_SS | 100%
510651 | SR21 CM Energy Team - Solar PV | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS3 | 2021-01-27 | 2021-02-23 | 2021-02-23 | 2027-03-31 | 2027-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10238.52 | 10238.52 | 489761.28 | 0 | 0 | 499999.8 | 0 | 0 | 0 | 0 | 499999.8 | 0 | [5 empty] | N | SR21_SS | 100%
510650 | SR21 CM Energy Team - Wind | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS3 | 2021-01-27 | 2021-02-23 | 2021-02-23 | 2027-03-31 | 2027-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848.23 | 1848.23 | 498151.44 | 0 | 0 | 499999.67 | 0 | 0 | 0 | 0 | 499999.67 | 0 | [5 empty] | N | SR21_SS | 100%
510603 | SR21 CMA Market Release | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2028-04-28 | 2029-03-30 | 2029-08-01 | 2031-03-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177000 | 0 | 0 | 1177000 | 0 | 0 | 0 | 0 | 1177000 | 613322.63 | [5 empty] | N | CM_M&G | 100%
511074 | SR21 CMAP - CSD Identified Sewer Rehabilitation - Year 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2021-02-22 | 2021-03-15 | 2021-07-14 | 2022-01-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000.01 | 0 | 0 | 900000.01 | 0 | 0 | 0 | 0 | 900000.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511835 | SR21 CMAP CSD identified sewer rehabilitation Mar 2021 - Mar 2027 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2021-03-26 | 2021-04-12 | 2021-04-13 | 2027-05-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5399999.78 | 0 | 0 | 5399999.78 | 0 | 0 | 0 | 0 | 5399999.78 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506835 | SR21 Colonsay WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2023-10-11 | 2026-02-04 | 2026-05-11 | 2028-05-16 | 2029-05-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000.05 | 0 | 0 | 4000000.05 | 0 | 0 | 0 | 0 | 4000000.05 | 0 | [5 empty] | N | SR21_WA | 100%
508989 | SR21 Control System Replacement Annan STW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2021-12-24 | 2023-08-08 | 2023-11-03 | 2024-10-25 | 2025-01-27 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36217.09 | 36217.09 | 1464074.54 | 0 | 0 | 1500291.63 | 0 | 0 | 0 | 0 | 1500291.63 | 0 | [5 empty] | N | SR21_WW | 100%
510546 | SR21 Control System Replacement - Ayr Shore Road SPS | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2021-09-30 | 2023-04-10 | 2023-07-07 | 2024-06-13 | 2024-06-14 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15565.36 | 15565.36 | 584455.72 | 0 | 0 | 600021.08 | 0 | 0 | 0 | 0 | 600021.08 | 0 | [5 empty] | N | SR21_WW | 100%
510521 | SR21 Control System Replacement - Bonnybridge STW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW1 | 2022-09-30 | 2024-04-09 | 2024-07-08 | 2025-06-13 | 2025-06-16 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15270.7 | 15270.7 | 744729.3 | 0 | 0 | 760000 | 0 | 0 | 0 | 0 | 760000 | 0 | [5 empty] | N | SR21_WW | 100%
510449 | SR21 Control System Replacement - Helensburgh STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2022-06-30 | 2024-01-08 | 2024-04-05 | 2025-03-13 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9052.52 | 9052.52 | 891399.66 | 0 | 0 | 900452.18 | 0 | 0 | 0 | 0 | 900452.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511495 | SR21 Core WTW pilots - Chlorine Dioxide | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-04-01 | 2021-11-08 | 2022-03-09 | 2022-09-07 | 2022-12-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499999.99 | 0 | 0 | 499999.99 | 0 | 0 | 0 | 0 | 499999.99 | 0 | [5 empty] | N | SR21_WA | 100%
511500 | SR21 Core WTW pilots - Ozone GAC | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-04-01 | 2021-11-08 | 2022-03-09 | 2022-09-07 | 2022-12-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499999.99 | 0 | 0 | 499999.99 | 0 | 0 | 0 | 0 | 499999.99 | 0 | [5 empty] | N | SR21_WA | 100%
503640 | SR21 Culroy Burn Crossing Minishant Maybole | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2021-08-26 | 2023-03-08 | 2023-05-25 | 2024-04-24 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 11058.44 | 25582.12 | 36640.56 | 363359.44 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509894 | SR21 CVT Vehicle Replacement Year 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2020-12-08 | 2021-01-07 | 2021-01-07 | 2022-07-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305012.85 | 305012.85 | 12427091.15 | 0 | 0 | 12732104 | 0 | 0 | 0 | 0 | 12732104 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503641 | SR21 Duntocher Burn Pipe Bridge Glasgow | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-03-02 | 2022-09-12 | 2022-12-06 | 2023-11-08 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 38005.93 | 13431.59 | 51437.52 | 434275.14 | 0 | 0 | 485712.66 | 0 | 0 | 0 | 0 | 485712.66 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507254 | SR21 Eela Water WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-01-19 | 2023-12-06 | 2024-05-15 | 2025-11-26 | 2026-02-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165691.57 | 165691.57 | 6334351.12 | 0 | 0 | 6500042.69 | 0 | 0 | 0 | 0 | 6500042.69 | 0 | [5 empty] | N | SR21_WA | 100%
511982 | SR21 Environments | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-04-28 | 2022-04-22 | 2022-08-24 | 2024-04-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502900 | 0 | 0 | 502900 | 0 | 0 | 0 | 0 | 502900 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503666 | SR21 ES - Afton Drought Resilience | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2021-11-15 | 2023-03-31 | 2023-07-25 | 2025-01-17 | 2025-04-18 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 46480.81 | 2536.57 | 49017.38 | 4950982.47 | 0 | 0 | 4999999.85 | 0 | 0 | 0 | 0 | 4999999.85 | 0 | [5 empty] | N | SR21_WA | 100%
503667 | SR21 ES - Turret Drought Resilience | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2021-12-17 | 2024-04-29 | 2024-09-02 | 2027-09-28 | 2027-09-29 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 118353.2 | -28934.42 | 89418.78 | 2910581.16 | 0 | 0 | 2999999.94 | 0 | 0 | 0 | 0 | 2999999.94 | 0 | [5 empty] | N | SR21_WA | 100%
503727 | SR21 ES Alyth Loyal - Cothelhill DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-10-03 | 2020-03-31 | 2021-03-31 | 2022-02-15 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 75696.73 | 81682.27 | 157379 | 892218.93 | 0 | 0 | 1049597.93 | 0 | 0 | 104960.07 | 104960.07 | 1154558 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507793 | SR21 ES Balgillie Reservoir Drawdown Improvement Project | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-05-26 | 2024-04-11 | 2024-09-19 | 2026-04-02 | 2026-07-03 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 2995 | 542459.09 | 0 | 0 | 545454.09 | 0 | 0 | 0 | 0 | 545454.09 | 0 | [5 empty] | N | SR21_WA | 100%
503681 | SR21 ES Balgray Reservoir MIOS -Top Water Lowering | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2021-03-30 | 2022-09-26 | 2022-12-21 | 2024-07-15 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 172344.28 | 59889.26 | 232233.54 | 1767766.46 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503725 | SR21 ES Barcraigs VT Bridge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2020-04-29 | 2021-03-11 | 2021-03-10 | 2021-11-04 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 101848.39 | 16686.61 | 118535 | 789865.61 | 0 | 0 | 908400.61 | 0 | 0 | 0 | 0 | 908400.61 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503653 | SR21 ES Bathgate STW Control Systems Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2021-03-31 | 2022-11-11 | 2023-02-13 | 2024-02-19 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 48895.88 | 28782.13 | 77678.01 | 791935.99 | 0 | 0 | 869614 | 0 | 0 | 0 | 0 | 869614 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504549 | SR21 ES Black Esk WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-01-26 | 2025-02-24 | 2025-06-30 | 2028-11-21 | 2028-11-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 23154.51 | 63916.97 | 87071.48 | 25913013.85 | 0 | 0 | 26000085.33 | 0 | 0 | 0 | 0 | 26000085.33 | 0 | [5 empty] | N | SR21_WA | 100%
503636 | SR21 ES Bonny Water Pipe Bridge Gateside Avenue Bonnybridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2020-07-30 | 2021-05-17 | 2021-08-09 | 2021-11-08 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 24044.41 | 47392.59 | 71437 | 387224.24 | 0 | 0 | 458661.24 | 0 | 0 | 0 | 0 | 458661.24 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503746 | SR21 ES Brechin STC - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2024-05-16 | 2026-03-18 | 2026-06-08 | 2027-07-16 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWNI | 100%
503687 | SR21 ES Caaf Spillway and Scour Control | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2020-06-29 | 2020-11-04 | 2020-11-04 | 2020-11-09 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 15642.37 | -6451.48 | 9190.89 | 0 | 0 | 0 | 9190.89 | 0 | 0 | 0 | 0 | 9190.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503715 | SR21 ES Cameron | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-08-12 | 2022-06-30 | 2022-09-13 | 2023-04-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 18290.38 | 8192.62 | 26483 | 373516.38 | 0 | 0 | 399999.38 | 0 | 0 | 0 | 0 | 399999.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503678 | SR21 ES Camps | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-03-26 | 2022-01-17 | 2022-03-21 | 2023-10-20 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 12843.87 | 324148.98 | 336992.85 | 1291558.7 | 0 | 0 | 1628551.55 | 0 | 0 | 0 | 0 | 1628551.55 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504849 | SR21 ES Carman Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-01-21 | 2023-08-28 | 2023-11-24 | 2024-11-11 | 2025-02-11 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3793 | 3793 | 541660.35 | 0 | 0 | 545453.35 | 0 | 0 | 0 | 0 | 545453.35 | 0 | [5 empty] | N | SR21_WA | 100%
503637 | SR21 ES Carmel Water Pipe Bridge Crosshouse | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2020-04-30 | 2021-07-26 | 2021-10-04 | 2022-04-04 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 22545.91 | 28608.09 | 51154 | 567612.45 | 0 | 0 | 618766.45 | 0 | 0 | 0 | 0 | 618766.45 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504391 | SR21 ES Carron Valley WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-10-12 | 2024-12-18 | 2025-03-11 | 2027-12-14 | 2027-12-15 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 28880.76 | 112194.9 | 141075.66 | 87849104.1 | 0 | 0 | 87990179.76 | 0 | 0 | 0 | 0 | 87990179.76 | 0 | [5 empty] | N | SR21_WA | 100%
503657 | SR21 ES CCTV Phase 5A Paisley & Glasgow | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2020-04-29 | 2021-05-31 | 2021-06-28 | 2022-05-13 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 45436.28 | 498062.72 | 543499 | 2926913.33 | 0 | 0 | 3470412.33 | 0 | 0 | 0 | 0 | 3470412.33 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503639 | SR21 ES CCTV Phase 5B Edinburgh | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2020-04-28 | 2021-05-03 | 2021-05-31 | 2022-04-22 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 39315.11 | 177153.89 | 216469 | 1827538.56 | 0 | 0 | 2044007.56 | 0 | 0 | 0 | 0 | 2044007.56 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503765 | SR21 ES Core WTW Pilots | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS0 | 2019-09-30 | 2021-05-24 | 2021-06-21 | 2021-10-18 | 2021-12-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8259.14 | 206238.02 | 214497.16 | 1285630.56 | 0 | 0 | 1500127.72 | 0 | 0 | 0 | 0 | 1500127.72 | 0 | [5 empty] | N | SR21_WA | 100%
504850 | SR21 ES Corsehouse Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS7 | 2020-12-22 | 2020-12-22 | 2021-02-08 | 2021-02-08 | 2021-04-12 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 10883.72 | 0 | 10883.72 | 0 | 0 | 0 | 10883.72 | 0 | 0 | 0 | 0 | 10883.72 | 0 | [5 empty] | N | SR21_WA | 100%
503682 | SR21 ES Corsehouse Reservoir -Spillway Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-10-14 | 2022-02-28 | 2022-05-23 | 2023-04-07 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 11731.77 | -5301.89 | 6429.88 | 853545.93 | 0 | 0 | 859975.81 | 0 | 0 | 0 | 0 | 859975.81 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504851 | SR21 ES Coulter Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-03-08 | 2023-10-11 | 2024-01-09 | 2024-12-25 | 2025-12-25 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 10883.72 | 0.28 | 10884 | 534570 | 0 | 0 | 545454 | 0 | 0 | 0 | 0 | 545454 | 0 | [5 empty] | N | SR21_WA | 100%
503679 | SR21 ES Cowgill Upper and Lower | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-01-05 | 2022-11-08 | 2023-01-20 | 2023-10-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 35708.18 | -11540.18 | 24168 | 975831.95 | 0 | 0 | 999999.95 | 0 | 0 | 0 | 0 | 999999.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503747 | SR21 ES Dalderse STC - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2023-06-01 | 2025-03-28 | 2025-06-30 | 2026-07-24 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854.4 | 854.4 | 1878852.18 | 0 | 0 | 1879706.58 | 0 | 0 | 0 | 0 | 1879706.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504852 | SR21 ES Drumbowie Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-07-08 | 2024-02-12 | 2024-05-10 | 2025-04-28 | 2026-04-27 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1608 | 1608 | 543846.07 | 0 | 0 | 545454.07 | 0 | 0 | 0 | 0 | 545454.07 | 0 | [5 empty] | N | SR21_WA | 100%
503757 | SR21 ES DSEAR Compliance (Desktop) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2020-01-23 | 2020-05-26 | 2021-02-16 | 2022-03-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 119182.98 | 207808.02 | 326991 | 707008.95 | 0 | 0 | 1033999.95 | 0 | 0 | 0 | 0 | 1033999.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503748 | SR21 ES Dunfermline STC - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2023-12-07 | 2025-07-02 | 2025-11-04 | 2026-09-21 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1640000 | 0 | 0 | 1640000 | 0 | 0 | 0 | 0 | 1640000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503680 | SR21 ES Dunside Upper and Lower | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-01-21 | 2022-11-10 | 2023-01-24 | 2023-10-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 39105.92 | -2246.88 | 36859.04 | 963564.81 | 0 | 0 | 1000423.85 | 0 | 0 | 0 | 0 | 1000423.85 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503728 | SR21 ES Edzell Rural DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-10-03 | 2020-01-31 | 2020-03-03 | 2021-06-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 440310.14 | 954285.86 | 1394596 | 134216.03 | 0 | 0 | 1528812.03 | 0 | 0 | 165799.97 | 165799.97 | 1694612 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503755 | SR21 ES Energy Efficiency Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS3 | 2020-07-03 | 2020-08-31 | 2021-02-18 | 2027-07-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264313 | 264313 | 1535687.13 | 0 | 0 | 1800000.13 | 0 | 0 | 0 | 0 | 1800000.13 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503656 | SR21 ES Forfar STW Control Systems Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-06-30 | 2023-03-07 | 2023-07-10 | 2025-01-31 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 51992.64 | 17256.02 | 69248.67 | 175751.33 | 0 | 0 | 245000 | 0 | 0 | 0 | 0 | 245000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503643 | SR21 ES Gills Burn Pipe Bridge Allanvale Dunlop | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2020-06-29 | 2021-07-19 | 2021-09-27 | 2022-04-08 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 17368.98 | 28736.02 | 46105 | 244472.21 | 0 | 0 | 290577.21 | 0 | 0 | 0 | 0 | 290577.21 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503750 | SR21 ES Girvan STC - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2024-01-26 | 2025-11-25 | 2026-02-23 | 2027-03-19 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830000 | 0 | 0 | 830000 | 0 | 0 | 0 | 0 | 830000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503646 | SR21 ES Glen Water Pipe Bridge Causeway Road Darvel | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2020-07-03 | 2021-07-26 | 2021-10-04 | 2022-04-04 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 16846.9 | 25175.1 | 42022 | 227991.26 | 0 | 0 | 270013.26 | 0 | 0 | 0 | 0 | 270013.26 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503672 | SR21 ES Glenfarg WTW upgrade | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW2 | 2021-04-12 | 2024-06-18 | 2024-09-09 | 2027-03-29 | 2027-03-30 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 288096.38 | 279219.22 | 567315.6 | 39604897.62 | 0 | 0 | 40172213.22 | 0 | 0 | 0 | 0 | 40172213.22 | 0 | [5 empty] | N | SR21_WA | 100%
503647 | SR21 ES Gremista SPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2022-01-19 | 2023-09-07 | 2023-12-06 | 2025-04-07 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 35757.67 | 7367.34 | 43125.01 | 2457015.91 | 0 | 0 | 2500140.92 | 0 | 0 | 0 | 0 | 2500140.92 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503676 | SR21 ES Gryfe 1 and 2 VT Bridge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-09-30 | 2020-09-14 | 2020-11-11 | 2021-10-20 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 10171.26 | 538064.74 | 548236 | 67560.54 | 0 | 0 | 615796.54 | 0 | 0 | 0 | 0 | 615796.54 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504854 | SR21 ES Hopes Reservoir Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-06-15 | 2024-01-18 | 2024-04-17 | 2025-04-03 | 2026-04-03 | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5782 | 5782 | 539672.14 | 0 | 0 | 545454.14 | 0 | 0 | 0 | 0 | 545454.14 | 0 | [5 empty] | N | SR21_WA | 100%
503758 | SR21 ES HV Dalgrain SPS Transformer & LV MCC Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-02-07 | 2023-10-13 | 2024-02-06 | 2025-05-06 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 73573.25 | -11747.92 | 61825.33 | 3938426.58 | 0 | 0 | 4000251.91 | 0 | 0 | 0 | 0 | 4000251.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503675 | SR21 ES HV Earthing surveys | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-10-01 | 2020-10-16 | 2020-11-19 | 2021-10-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 28361.93 | 339669.07 | 368031 | 523916.94 | 0 | 0 | 891947.94 | 0 | 0 | 0 | 0 | 891947.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503654 | SR21 ES Kinneil Kerse SCADA replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-08-20 | 2020-08-20 | 2020-08-20 | 2020-08-31 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 58677.67 | 3800.12 | 62477.78 | 0 | 0 | 0 | 62477.78 | 0 | 0 | 0 | 0 | 62477.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503752 | SR21 ES Kinneil Kerse STC - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2024-03-20 | 2026-01-19 | 2026-04-20 | 2027-05-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 970000 | 0 | 0 | 970000 | 0 | 0 | 0 | 0 | 970000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503754 | SR21 ES Kirkwall STC - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2024-05-16 | 2026-03-18 | 2026-06-15 | 2027-07-09 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969999.93 | 0 | 0 | 969999.93 | 0 | 0 | 0 | 0 | 969999.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503655 | SR21 ES Lanark STW Control Systems Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-06-30 | 2023-03-07 | 2023-07-10 | 2025-01-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 52240.48 | 13224.7 | 65465.18 | 154234.82 | 0 | 0 | 219700 | 0 | 0 | 0 | 0 | 219700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503759 | SR21 ES Liberton Trunk Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-08-03 | 2025-03-04 | 2025-07-09 | 2028-09-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 152332.08 | 22458 | 174790.08 | 14825209.92 | 0 | 0 | 15000000 | 0 | 0 | 0 | 0 | 15000000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504855 | SR21 ES Lintrathen Loch Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-06-06 | 2024-01-09 | 2024-04-08 | 2025-03-25 | 2026-03-25 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 10883.72 | 8489.97 | 19373.69 | 526080.32 | 0 | 0 | 545454 | 0 | 0 | 0 | 0 | 545454 | 0 | [5 empty] | N | SR21_WA | 100%
504856 | SR21 ES Loch Assapol Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS7 | 2020-12-22 | 2020-12-22 | 2021-02-08 | 2021-02-08 | 2021-04-02 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SR21_WA | 100%
504857 | SR21 ES Loch Glow Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS2 | 2021-04-01 | 2021-04-01 | 2024-04-08 | 2025-03-25 | 2026-03-25 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 10883.72 | 106.36 | 10990.08 | 0 | 0 | 0 | 10990.08 | 0 | 0 | 0 | 0 | 10990.08 | 0 | [5 empty] | N | SR21_WA | 100%
503685 | SR21 ES Loch Mhor an Stairr | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS1 | 2020-06-29 | 2021-10-11 | 2022-01-17 | 2022-08-19 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 20129.92 | 24864.16 | 44994.08 | 1365936.81 | 0 | 0 | 1410930.89 | 0 | 0 | 0 | 0 | 1410930.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503684 | SR21 ES Loch Riecawr Concrete Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-10-14 | 2022-01-17 | 2022-03-30 | 2022-10-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 11731.77 | -2956.04 | 8775.73 | 761273.38 | 0 | 0 | 770049.11 | 0 | 0 | 0 | 0 | 770049.11 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503683 | SR21 ES Loch Spallander Spillway Concrete Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-10-14 | 2022-01-17 | 2022-03-30 | 2022-10-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 11731.77 | -6940.78 | 4790.99 | 940798.11 | 0 | 0 | 945589.1 | 0 | 0 | 0 | 0 | 945589.1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503688 | SR21 ES Loch Venachar MIoS Upgrade | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-11-02 | 2022-05-06 | 2022-06-27 | 2023-02-28 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 17854.08 | -9472.08 | 8382 | 491617.58 | 0 | 0 | 499999.58 | 0 | 0 | 0 | 0 | 499999.58 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504858 | SR21 ES Loch Whinyeon Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-06-08 | 2024-01-15 | 2024-04-10 | 2025-03-27 | 2026-03-27 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 10883.72 | 7514.96 | 18398.68 | 527055.32 | 0 | 0 | 545454 | 0 | 0 | 0 | 0 | 545454 | 0 | [5 empty] | N | SR21_WA | 100%
503649 | SR21 ES Lochanbank Farm Pipe Bridge Kirkmuirhill | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2020-01-06 | 2019-12-12 | 2022-08-02 | 2020-05-29 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1287.35 | 0 | 1287.35 | 0 | 0 | 0 | 1287.35 | 0 | 0 | 0 | 0 | 1287.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504860 | SR21 ES Long Loch Drawdown Improvements | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-06-10 | 2024-01-12 | 2024-04-12 | 2025-03-31 | 2026-03-30 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 10883.72 | 0 | 10883.72 | 534570.28 | 0 | 0 | 545454 | 0 | 0 | 0 | 0 | 545454 | 0 | [5 empty] | N | SR21_WA | 100%
504971 | SR21 ES Lower Largo Bathing Water Study | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWMD | SR21 Early Start | MS4 | 2020-03-16 | 2021-02-23 | 2021-02-23 | 2021-03-17 | 2021-04-22 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 20185.95 | 25263.53 | 45449.48 | 462.4 | 0 | 0 | 45911.88 | 0 | 0 | 0 | 0 | 45911.88 | 0 | [5 empty] | N | SR21_WW | 100%
503674 | SR21 ES MCC Priority 1 Condition Surveys | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2020-06-19 | 2020-08-24 | 2020-11-30 | 2021-06-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 32611.9 | 152458.55 | 185070.45 | 525125.55 | 0 | 0 | 710196 | 0 | 0 | 0 | 0 | 710196 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503729 | SR21 ES Meikle Tullo WSZ Dykehead DMA - Memus Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-10-03 | 2020-02-28 | 2021-03-29 | 2021-10-08 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 136370.54 | 53432.46 | 189803 | 290527.26 | 0 | 0 | 480330.26 | 0 | 0 | 0 | 0 | 480330.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503716 | SR21 ES Mill Glen Breach | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 | 2020-04-02 | 2021-03-30 | 2021-06-11 | 2022-11-30 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 79776 | 177146 | 256922 | 1056331.84 | 0 | 0 | 1313253.84 | 0 | 0 | 105060.3072 | 105060.3072 | 1418314.1472 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503686 | SR21 ES Munnoch Breach | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2021-02-15 | 2021-10-11 | 2022-08-16 | 2023-03-15 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 63591.27 | 76811.45 | 140402.71 | 2238388.86 | 0 | 0 | 2378791.57 | 0 | 0 | 0 | 0 | 2378791.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503714 | SR21 ES North Third | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-08-28 | 2021-12-20 | 2022-05-19 | 2022-11-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 74000 | 93714 | 167714 | 946097.98 | 0 | 0 | 1113811.98 | 0 | 0 | 0 | 0 | 1113811.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503745 | SR21 ES P1 Pipe Bridge Repair-Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-05-18 | 2022-10-21 | 2023-01-20 | 2024-07-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 94202.48 | -43132.71 | 51069.77 | 1448930.21 | 0 | 0 | 1499999.98 | 0 | 0 | 0 | 0 | 1499999.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503463 | SR21 ES PMO Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 | 2021-02-23 | 2021-03-09 | 2021-04-01 | 2021-04-01 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1046811.03 | 2234221.33 | 3281032.36 | 218967.64 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 3500000 | 0 | [5 empty] | N | SR21_SS | 100%
504558 | SR21 ES Port Charlotte WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-06-27 | 2024-05-13 | 2024-10-21 | 2026-05-04 | 2026-08-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 23042.34 | 28212.81 | 51255.14 | 5948744.86 | 0 | 0 | 6000000 | 0 | 0 | 0 | 0 | 6000000 | 0 | [5 empty] | N | SR21_WA | 100%
503464 | SR21 ES Portfolio Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 | 2021-02-23 | 2021-03-10 | 2021-04-01 | 2021-04-01 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3909782.44 | 6632598.77 | 10542381.21 | -542381.21 | 0 | 0 | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | [5 empty] | N | SR21_SS | 100%
503664 | SR21 ES PSTN Investigation and Proposals | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS0 | 2019-09-12 | 2021-04-15 | 2021-04-15 | 2021-04-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 462164.93 | 347182.37 | 809347.3 | 63524.45 | 0 | 0 | 872871.75 | 0 | 0 | 0 | 0 | 872871.75 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503660 | SR21 ES Pumping Mains Inspections Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2020-12-22 | 2022-03-25 | 2022-06-27 | 2023-05-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5835.61 | 37367.39 | 43203 | 506796.96 | 0 | 0 | 549999.96 | 0 | 0 | 0 | 0 | 549999.96 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510403 | SR21 ES Reservoir Drawdown Improvements Finance Line | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS2 |  | 2021-02-11 |  | 2026-12-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080023.88 | 0 | 0 | 1080023.88 | 0 | 0 | 0 | 0 | 1080023.88 | 0 | [5 empty] | N | SR21_WA | 100%
505741 | SR21 ES Reservoir Safety Signs East | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-04-07 | 2021-03-15 | 2021-11-08 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12799.07 | 12799.07 | 127274.49 | 0 | 0 | 140073.56 | 0 | 0 | 0 | 0 | 140073.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505243 | SR21 ES Reservoir Safety Signs North | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-04-03 | 2020-10-26 | 2021-07-09 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90198 | 90198 | 20134.93 | 0 | 0 | 110332.93 | 0 | 0 | 0 | 0 | 110332.93 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505740 | SR21 ES Reservoir Safety Signs South | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-04-07 | 2020-08-10 | 2021-09-24 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37211.3 | 37211.3 | 32864.31 | 0 | 0 | 70075.61 | 0 | 0 | 0 | 0 | 70075.61 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503756 | SR21 ES Reservoir Safety Signs West | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2020-12-17 | 2020-03-31 | 2020-08-03 | 2021-01-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 22359.49 | -21807.99 | 551.5 | 0 | 0 | 0 | 551.5 | 0 | 0 | 0 | 0 | 551.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505747 | SR21 ES Reservoir Safety Signs West Region | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2020-07-21 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22359 | 22359 | 296659.5 | 0 | 0 | 319018.5 | 0 | 0 | 0 | 0 | 319018.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503677 | SR21 ES Rosebery | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-07-27 | 2022-06-17 | 2022-08-31 | 2023-04-03 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 19552.95 | -9204.44 | 10348.51 | 489651.5 | 0 | 0 | 500000.01 | 0 | 0 | 0 | 0 | 500000.01 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503744 | SR21 ES Rosebery WTW Taste & Odour Issues | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-07-27 | 2022-10-21 | 2023-02-10 | 2024-05-13 | 2024-07-04 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 125447.1 | 378570.14 | 504017.24 | 2995982.76 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 3500000 | 0 | [5 empty] | N | SR21_WA | 100%
503741 | SR21 ES SCADA Surveys | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 | 2019-10-01 | 2020-10-27 | 2021-04-15 | 2021-07-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 34113.63 | 28693.3 | 62806.93 | 107193.07 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 170000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504381 | SR21 ES- SR21 Compensation Valve Study | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS0 | 2021-03-16 | 2021-09-27 | 2022-01-26 | 2022-07-27 | 2022-10-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9436 | 9436 | 100563.99 | 0 | 0 | 109999.99 | 0 | 0 | 0 | 0 | 109999.99 | 0 | [5 empty] | N | SR21_WA | 100%
503749 | SR21 ES Stirling STC - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2023-12-07 | 2025-04-02 | 2025-08-05 | 2026-06-22 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687739.96 | 0 | 0 | 687739.96 | 0 | 0 | 0 | 0 | 687739.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503778 | SR21 ES Stoer WOA - Clashnessie DMA and Achnacarnin DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-10-04 | 2019-10-04 | 2019-11-11 | 2021-08-20 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 238984.71 | 175626.65 | 414611.36 | 165476.8 | 0 | 0 | 580088.16 | 0 | 0 | 0 | 0 | 580088.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503753 | SR21 ES Thurso STC - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2024-05-16 | 2026-03-18 | 2026-06-15 | 2027-07-09 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829999.91 | 0 | 0 | 829999.91 | 0 | 0 | 0 | 0 | 829999.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504393 | SR21 ES Tighnabruaich WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-07-12 | 2023-05-29 | 2023-11-06 | 2025-05-19 | 2025-08-19 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 14093.03 | 49037.97 | 63131 | 436868.61 | 0 | 0 | 499999.61 | 0 | 0 | 0 | 0 | 499999.61 | 0 | [5 empty] | N | SR21_WA | 100%
504557 | SR21 ES Torra WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2021-12-03 | 2024-07-31 | 2024-12-04 | 2028-02-18 | 2028-02-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 33636.64 | 41898.33 | 75534.96 | 14924999.74 | 0 | 0 | 15000534.7 | 0 | 0 | 0 | 0 | 15000534.7 | 0 | [5 empty] | N | SR21_WA | 100%
503751 | SR21 ES Underwood Cumnock STC - Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2024-01-26 | 2025-11-27 | 2026-02-23 | 2027-03-26 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690000 | 0 | 0 | 690000 | 0 | 0 | 0 | 0 | 690000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503462 | SR21 ES Waste Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 | 2021-02-23 | 2021-03-09 | 2021-04-01 | 2021-04-01 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1371139.94 | 1460250.81 | 2831390.74 | 368609.26 | 0 | 0 | 3200000 | 0 | 0 | 0 | 0 | 3200000 | 0 | [5 empty] | N | SR21_SS | 100%
504208 | SR21 ES Water MCC Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-07-08 | 2023-01-06 | 2023-05-01 | 2024-10-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8570.28 | 13944.72 | 22515 | 1699779.19 | 0 | 0 | 1722294.19 | 0 | 0 | 0 | 0 | 1722294.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503461 | SR21 ES Water Programme | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | MS2 | 2021-02-23 | 2021-03-10 | 2021-04-01 | 2021-04-01 | 2021-04-01 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 2277335.35 | 2638639.82 | 4915975.17 | 284024.83 | 0 | 0 | 5200000 | 0 | 0 | 0 | 0 | 5200000 | 0 | [5 empty] | N | SR21_SS | 100%
504996 | SR21 ES Water Supply Strategy Review Session | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-06-07 | 2021-10-11 | 2022-02-09 | 2023-10-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 42122.17 | 62122.17 | 37877.83 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503724 | SR21 ES Westmuir - Kingoldrum DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-10-03 | 2020-03-17 | 2020-03-30 | 2021-06-10 |  | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 147693.32 | 596002.68 | 743696 | 14650.03 | 0 | 0 | 758346.03 | 0 | 0 | 0 | 0 | 758346.03 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504553 | SR21 ES Winterhope WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-01-26 | 2024-06-04 | 2024-10-08 | 2027-10-22 | 2027-10-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 23456.22 | 48192.21 | 71648.42 | 8928516.88 | 0 | 0 | 9000165.3 | 0 | 0 | 0 | 0 | 9000165.3 | 0 | [5 empty] | N | SR21_WA | 100%
503610 | SR21 ES_Inverness WOA - Nairnside mains rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2019-07-30 | 2019-07-30 | 2019-09-30 | 2020-10-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 271345 | 56857.78 | 328202.78 | 4762 | 0 | 0 | 332964.78 | 0 | 0 | 0 | 0 | 332964.78 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503613 | SR21 ES_Loch Calder WOA - Roster Occumster Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2019-10-03 | 2021-05-10 | 2021-06-14 | 2022-04-13 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 74509.6 | 17645.4 | 92155 | 1395479.79 | 0 | 0 | 1487634.79 | 0 | 0 | 0 | 0 | 1487634.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503907 | SR21 Finlas WTW Mainout | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2023-04-06 | 2024-12-26 | 2025-03-24 | 2026-07-09 | 2027-07-09 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 20339 | 17986.15 | 38325.15 | 1561674.85 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 1600000 | 0 | [5 empty] | N | SR21_WA | 100%
511837 | SR21 FMAP Flooding Management Action Plan Mar 2021 - Mar 2027 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2021-03-25 | 2021-04-12 | 2021-04-13 | 2027-05-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5999999.92 | 0 | 0 | 5999999.92 | 0 | 0 | 0 | 0 | 5999999.92 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511558 | SR21 FMAP2 - Flooding Management Action Plan - Year 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-03-09 | 2021-03-15 | 2021-07-14 | 2022-01-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.98 | 0 | 0 | 999999.98 | 0 | 0 | 0 | 0 | 999999.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503642 | SR21 Garnock Water Pipe Bridge Dalry Road Kilwinning | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-03-29 | 2022-09-23 | 2022-12-19 | 2023-10-27 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 11307.99 | 13571.82 | 24879.81 | 293099.43 | 0 | 0 | 317979.24 | 0 | 0 | 0 | 0 | 317979.24 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503645 | SR21 Glen Ave Pipe Bridge Cumnock | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-04-02 | 2022-10-13 | 2023-01-13 | 2024-01-09 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 21458.05 | 8493.85 | 29951.9 | 537504.8 | 0 | 0 | 567456.7 | 0 | 0 | 0 | 0 | 567456.7 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511832 | SR21 Glendevon WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-12-29 | 2023-07-07 | 2023-10-05 | 2024-09-11 | 2024-09-12 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000000.04 | 0 | 0 | 50000000.04 | 0 | 0 | 0 | 0 | 50000000.04 | 0 | [5 empty] | N | SR21_WA | 100%
503648 | SR21 Kirkhouse Burn Killearn Pipe Bridges | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2020-09-18 | 2022-04-08 | 2022-07-25 | 2023-07-21 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 14417.77 | 46530.24 | 60948 | 799197.21 | 0 | 0 | 860145.21 | 0 | 0 | 0 | 0 | 860145.21 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503775 | SR21 Legacy Sludge - Loch Eck WTW Lagoons | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS7 | 2020-05-21 | 2020-05-21 | 2024-01-12 | 2020-06-04 | 2025-06-10 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 520 | 777.61 | 1297.61 | 0 | 0 | 0 | 1297.61 | 0 | 0 | 0 | 0 | 1297.61 | 0 | [5 empty] | N | SR21_WA | 100%
503773 | SR21 Legacy Sludge - Westray STC Lunnon Quarry and Drying Beds | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS7 | 2020-05-21 | 2020-05-21 | 2023-10-25 | 2020-06-04 | 2024-12-13 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.9 | 13.9 | 0 | 0 | 0 | 13.9 | 0 | 0 | 0 | 0 | 13.9 | 0 | [5 empty] | N | SR21_WA | 100%
510384 | SR21 Long Sea Outfall Inspections Phase 1 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWMD | SR21 Early Start | MS0 | 2020-12-22 | 2021-05-24 | 2021-06-25 | 2022-04-07 | 2022-07-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47907 | 47907 | 562093.46 | 0 | 0 | 610000.46 | 0 | 0 | 0 | 0 | 610000.46 | 0 | [5 empty] | N | SR21_WW | 100%
503767 | SR21 Mannofield WTW inlet improvements | IR18 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MSU | 2021-07-06 | 2022-10-21 | 2023-02-16 | 2024-02-12 | 2024-04-04 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 197.05 | 4609.8 | 4806.85 | 1295193.15 | 0 | 0 | 1300000 | 0 | 357247.742 | 0 | 357247.742 | 1657247.742 | 1295905.08 | [5 empty] | N | DW23 | 100%
509532 | SR21 Milngavie WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-12-27 | 2030-10-09 | 2031-01-10 | 2033-11-16 | 2033-11-17 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179007 | 179007 | 120820993 | 0 | 0 | 121000000 | 0 | 0 | 0 | 0 | 121000000 | 0 | [5 empty] | N | SR21_WA | 100%
511838 | SR21 Mitigations for internal flooding properties Mar 2021 - Mar 2027 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2021-03-25 | 2021-04-12 | 2021-04-13 | 2027-05-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000.18 | 0 | 0 | 5000000.18 | 0 | 0 | 0 | 0 | 5000000.18 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509762 | SR21 Multiple - GAC Replacement Programme Phase 1 Year 1&2 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW2 | 2021-12-07 | 2023-06-15 | 2023-09-13 | 2024-08-20 | 2024-08-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6765.69 | 6765.69 | 1609482.33 | 0 | 0 | 1616248.02 | 0 | 0 | 0 | 0 | 1616248.02 | 0 | [5 empty] | N | SR21_SS | 100%
509819 | SR21 Multiple - Membrane Programme Phase 1 Years 1 & 2 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW2 | 2021-12-07 | 2023-06-15 | 2023-09-13 | 2024-08-20 | 2024-08-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641 | 641 | 8482628.8 | 0 | 0 | 8483269.8 | 0 | 0 | 0 | 0 | 8483269.8 | 0 | [5 empty] | N | SR21_SS | 100%
511576 | SR21 Multi-Site Growth Investigations | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS1 | 2021-03-30 | 2022-01-17 | 2022-05-18 | 2022-11-16 | 2023-02-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43570.09 | 43570.09 | 622429.91 | 0 | 0 | 666000 | 0 | 0 | 0 | 0 | 666000 | 0 | [5 empty] | N | SR21_WW | 100%
511300 | SR21 Operational Technology WTW Audits | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2021-03-05 | 2021-04-12 | 2021-05-28 | 2024-11-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7324.42 | 7324.42 | 1422675.58 | 0 | 0 | 1430000 | 0 | 0 | 0 | 0 | 1430000 | 311236.79 | [5 empty] | N | CM_M&G | 100%
511527 | SR21 Overhead Allocation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 306661.32 | [5 empty] | N | CM_OVH | 100%
511524 | SR21 Overhead CSD | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 306661.32 | [5 empty] | N | CM_OVH | 100%
511525 | SR21 Overhead Digital | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 306661.32 | [5 empty] | N | CM_OVH | 100%
511523 | SR21 Overhead SCSP | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 306661.32 | [5 empty] | N | CM_OVH | 100%
511526 | SR21 Overhead Support | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS2 |  | 2021-03-15 |  | 2027-02-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0 | 0 | 0 | 0.71 | 306661.32 | [5 empty] | N | CM_OVH | 100%
511559 | SR21 PMAP2 - Pollution Management Action Plan - Year 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-03-09 | 2021-03-15 | 2021-07-14 | 2022-01-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 700000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505574 | SR21 Rawburn WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-11-04 | 2024-10-18 | 2025-01-10 | 2027-05-14 | 2027-05-17 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50305.16 | 50305.16 | 17949694.84 | 0 | 0 | 18000000 | 0 | 0 | 0 | 0 | 18000000 | 0 | [5 empty] | N | SR21_WA | 100%
510102 | SR21 RES - Watch Water Auxiliary Scour Design | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-01-21 | 2021-07-16 | 2022-02-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15333 | 15333 | 159666.62 | 0 | 0 | 174999.62 | 0 | 0 | 0 | 0 | 174999.62 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509438 | SR21 Roberton WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-02-21 | 2024-01-08 | 2024-06-17 | 2025-12-29 | 2026-03-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39587.61 | 39587.61 | 11960412.39 | 0 | 0 | 12000000 | 0 | 0 | 0 | 0 | 12000000 | 0 | [5 empty] | N | SR21_WA | 100%
512135 | SR21 Sale to Horizons | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU |  | 2021-05-01 |  | 2027-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72 | 0 | 0 | 0.72 | 0 | 0 | 0 | 0 | 0.72 | 306661.32 | [5 empty] | N | CM_OVH | 100%
503650 | SR21 South Calder Water Riverside Walk Motherwell | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-06-25 | 2023-01-05 | 2023-04-03 | 2024-03-29 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 24907.72 | 28188.28 | 53096 | 354644.89 | 0 | 0 | 407740.89 | 0 | 0 | 0 | 0 | 407740.89 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511984 | SR21 SPMO Services | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-04-28 | 2022-04-22 | 2022-08-24 | 2024-04-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 1600000 | 613322.63 | [5 empty] | N | CM_M&G | 100%
506510 | SR21 Stornoway WTW | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 | 2022-04-08 | 2024-02-23 | 2024-08-02 | 2026-02-13 | 2026-05-18 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106231.73 | 106231.73 | 12893768.27 | 0 | 0 | 13000000 | 0 | 0 | 0 | 0 | 13000000 | 0 | [5 empty] | N | SR21_WA | 100%
503652 | SR21 Toll Bridge Eyemouth Rising Main Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WINF | Wastewater infrastructure | MS0 | 2020-08-31 | 2022-02-10 | 2022-05-20 | 2023-04-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 12467.42 | 34095.58 | 46563 | 390281.48 | 0 | 0 | 436844.48 | 0 | 0 | 0 | 0 | 436844.48 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503644 | SR21 Tulloch Road Perth | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2020-12-11 | 2021-11-05 | 2022-03-04 | 2022-08-19 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 10924.13 | 13129.05 | 24053.18 | 106481.96 | 0 | 0 | 130535.14 | 0 | 0 | 0 | 0 | 130535.14 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512162 | SR21 TWP Level 3 Inspections | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-05-03 | 2022-01-17 | 2022-05-18 | 2022-11-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299999.98 | 0 | 0 | 299999.98 | 0 | 0 | 0 | 0 | 299999.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502925 | SR21 Wastewater Business Plan Development | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2029-04-02 | 2028-03-27 | 2028-03-27 | 2028-03-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511211 | SR21 Water SCADA CM OT Inspections | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MSU | 2021-04-01 | 2021-11-08 | 2022-03-09 | 2022-09-07 | 2022-12-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429999.97 | 0 | 0 | 1429999.97 | 0 | 0 | 0 | 0 | 1429999.97 | 0 | [5 empty] | N | SR21_WA | 100%
508795 | SR21 WW MCC Replacement Albert Road SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2022-01-31 | 2023-12-18 | 2024-02-26 | 2025-08-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12597.4 | 12597.4 | 1587402.6 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 1600000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503628 | SR21ES Herricks WTW upgrade | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | NONINF | SR21 Early Start | MS0 | 2021-02-26 | 2022-08-12 | 2022-10-10 | 2024-07-01 | 2024-10-02 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 149469.04 | 403452.94 | 552921.98 | 16747078.02 | 0 | 0 | 17300000 | 0 | 0 | 0 | 0 | 17300000 | 0 | [5 empty] | N | SR21_WA | 100%
506279 | SR21-Juniper House Refurbishment | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS0 | 2020-04-30 | 2021-09-27 | 2022-01-26 | 2025-07-25 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70946.49 | 70946.49 | 26429053.51 | 0 | 0 | 26500000 | 0 | 0 | 0 | 0 | 26500000 | 306661.32 | [5 empty] | N | CM_M&G | 100%
500084 | SR-TM Meters - New | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2021-07-30 |  | Scottish Water Wide | 0 | 0 | 385150 | 293876 | 169763.36 | 231610.64 | 319884 | 156195.44 | 1556479.44 | 0 | 0 | 0 | 1556479.44 | 0 | 0 | 0 | 0 | 1556479.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500085 | SR-TM Meters - Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-25 | 2015-03-25 | 2021-07-30 |  | Scottish Water Wide | 0 | 0 | 260879 | 101882 | 200992 | 196164 | 151444 | 136281.44 | 1047642.44 | 0 | 0 | 0 | 1047642.44 | 0 | 0 | 0 | 0 | 1047642.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503588 | SSD - SW support of Profibus remedial works | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2021-03-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 138642.42 | -80220.58 | 58421.84 | 0 | 0 | 0 | 58421.84 | 0 | 0 | 0 | 0 | 58421.84 | 613322.63 | [5 empty] | N | CM_WSNI | 30% | CM_WWNI | 70%
508855 | SSGE - Energy Efficiency - Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater |  | SWD | Energy efficiency | MS2 | 2020-10-14 | 2020-11-30 | 2021-04-09 | 2021-10-18 | 2022-01-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155450.89 | 155450.89 | 510549.11 | 510549.11 | 708729.0835 | 666000 | 198179.9735 | 0 | 0 | 198179.9735 | 864179.9735 | 1280912.62 | [5 empty] | N | I2S_WWNI | 100%
508854 | SSGE - Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS2 | 2020-10-14 | 2020-11-30 | 2021-04-02 | 2022-03-25 | 2022-06-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88172 | 88172 | 245827.6 | 245827.6 | 341250.5599 | 333999.6 | 95422.9599 | 0 | 0 | 95422.9599 | 429422.5599 | 94753.86 | [5 empty] | N | I2S_WNI | 100%
508853 | SSGE - Peatlands Restoration | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWMD | WFD | MS2 | 2020-11-06 | 2020-12-21 | 2021-10-18 | 2022-04-01 | 2022-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58186 | 58186 | 201755.37 | 201755.37 | 280070.8015 | 259941.37 | 78315.4315 | 0 | 0 | 78315.4315 | 338256.8015 | 0 | [5 empty] | N | SR15_ENV_WFD | 100%
509347 | SSGE Peatlands Restoration North Lochs and Sandy Lochs | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56479.62 | 56479.62 | 26020.38 | 26020.38 | 36120.7173 | 82500 | 10100.3373 | 0 | 0 | 10100.3373 | 92600.3373 | 0 | [5 empty] | N | SR15_ENV_WFD | 100%
503999 | S-S-NI-271119-Daer WTW - Redundant settlement tank fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-28 |  | 2020-03-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 11374.63 | 0 | 11374.63 | 0 | 0 | 0 | 11374.63 | 0 | 0 | 0 | 0 | 11374.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500173 | St Andrews DOA (DOA000247) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-04-29 | 2016-06-20 | 2019-03-27 | 2019-07-31 | Fife | 0 | 0 | 13937 | 153569.12 | 83863.88 | 71014 | 37043.39 | 0 | 359427.39 | 0 | 0 | 0 | 359427.39 | 0 | 0 | 0 | 0 | 359427.39 | 50334.66 | [5 empty] | N | EC01D | 12.3% | EC01G | 17.1% | CS16D | 33.63% | EC10E | 36.97%
511807 | St Andrews Network Strategic Study | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-06-01 | 2022-02-14 | 2022-06-15 | 2022-12-14 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141999.97 | 0 | 0 | 141999.97 | 0 | 0 | 0 | 0 | 141999.97 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502814 | St Andrews WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-04-09 | 2023-02-03 | 2023-05-08 | 2024-02-20 |  | Fife | 0 | 0 | 0 | 0 | 97236.65 | 36451.59 | 4862.53 | 30105.02 | 168655.79 | 595650.32 | 0 | 0 | 764306.11 | 0 | 0 | 0 | 0 | 764306.11 | 122419.09 | [5 empty] | N | SG1 | 100%
500695 | St Andrews WwTW & St Andrews STC SR15-CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS4 | 2015-06-30 | 2018-09-18 | 2019-03-29 | 2021-03-22 |  | Fife | 0 | 0 | 130610 | 46330.1 | 122609.4 | 398068.48 | 873025.02 | 207090 | 1777733 | 47585 | 0 | 0 | 1825318 | 0 | 0 | 180989 | 180989 | 2006307 | 181202.57 | [5 empty] | N | CM_WWNI | 100%
500174 | St Boswells DOA (DOA000039) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2017-02-27 | 2017-02-27 | 2017-03-31 | 2017-03-31 | Scottish Borders | 0 | 0 | 13526 | 7500 | -8014.76 | 0 | 0 | 0 | 13011.24 | 0 | 0 | 0 | 13011.24 | 0 | 0 | 0 | 0 | 13011.24 | 82349.38 | [5 empty] | Y | EC01D | 100% | [40 empty] | 1 | [26 empty] | 0
506122 | St Fergus DOA Rising main rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-05-26 | 2021-03-01 | 2021-12-17 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16785 | 16785 | 43215.09 | 0 | 0 | 60000.09 | 0 | 0 | 0 | 0 | 60000.09 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505049 | St Fergus Scotston WWPS rising main repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-03-31 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 108951.33 | 1098.03 | 110049.35 | 0 | 0 | 0 | 110049.35 | 0 | 0 | 0 | 0 | 110049.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502428 | St Fort Road Outfall | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | WWINF | UWWTD - Works | MS7 | 2016-11-21 | 2018-01-29 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Fife | 0 | 0 | 0 | 9239.06 | 93697.94 | 76740 | 0 | -2131.96 | 177545.04 | 0 | 0 | 0 | 177545.04 | 0 | 0 | 0 | 0 | 177545.04 | 41330.23 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
500577 | St Margarets Hope WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | Orkney Islands | 0 | 0 | 24641.68 | 6457.9 | 841.89 | 35.22 | 0 | 0 | 31976.69 | 0 | 0 | 0 | 31976.69 | 0 | 0 | 0 | 0 | 31976.69 | 122419.09 | [5 empty] | N | SG1 | 100%
500055 | St Marys Loch Fish Pass | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water | SEPA | SWD | WFD | MS7 | 2015-02-18 | 2015-03-09 | 2015-03-09 | 2015-11-30 | 2016-03-31 | Scottish Borders | 4670 | 4670 | 223830 | 153.53 | 0 | 0 | 0 | 0 | 223983.53 | 0 | 0 | 0 | 228653.53 | 0 | 0 | 0 | 0 | 228653.53 | 346337.12 | [5 empty] | Y | WR2A | 100% | [37 empty] | 1 | [29 empty] | 0
402748 | St Marys ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-07-20 | 2014-10-30 | 2014-11-24 | 2016-07-29 | 2016-07-29 | Orkney Islands | 175129 | 0 | 79634 | 65000 | 0 | -1821.48 | 0 | 0 | 142812.53 | 0 | 0 | 0 | 317941.53 | 0 | 0 | 0 | 0 | 317941.53 | 0 | [5 empty] | N | SG1 | 100%
500175 | St Monans DOA (DOA000252) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-09-28 | 2015-11-13 | 2017-05-30 | 2018-01-30 | Fife | 0 | 0 | 64064 | 54379 | 12620 | 123.85 | 0 | 0 | 131186.84 | 0 | 0 | 0 | 131186.84 | 0 | 0 | 0 | 0 | 131186.84 | 146942.16 | [5 empty] | N | EC01G | 4.722% | CS11 | 22.55% | CS16D | 27.6% | EC01D | 45.13%
501817 | St Monans WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-07-27 | Fife | 0 | 0 | 10465 | 0.12 | 0 | 0 | 0 | 0 | 10465.12 | 0 | 0 | 0 | 10465.12 | 0 | 0 | 0 | 0 | 10465.12 | 122419.09 | [5 empty] | N | SG1 | 100%
503476 | St Vigeans Avenue Newton Mearns | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2019-02-20 | 2019-02-20 | 2019-02-21 | 2019-03-14 | 2019-03-14 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 45732.77 | 3853.8 | 0 | 49586.57 | 0 | 0 | 0 | 49586.57 | 0 | 0 | 0 | 0 | 49586.57 | 5935596.51 | [5 empty] | N | CS16WR | 100%
500876 | Staffin Skye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-08-19 | 2018-11-21 | 2018-11-21 | 2018-11-30 | 2018-11-30 | Highland | 0 | 0 | 1267.34 | 2229.31 | 4197.8 | -4197.8 | 0 | 0 | 3496.65 | 0 | 0 | 0 | 3496.65 | 0 | 0 | 0 | 0 | 3496.65 | 77494.38 | [5 empty] | N | DW5FS | 100%
500752 | Staffin WTW CWT Capacity | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS7 | 2015-08-25 | 2017-05-12 | 2017-07-31 | 2018-08-30 |  | Highland | 0 | 0 | 93419 | 136262.78 | 681176.41 | 156789.76 | 69.05 | -122647.41 | 945069.59 | 0 | 0 | 0 | 945069.59 | 0 | 0 | 0 | 0 | 945069.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
45416 | Staffin WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-28 | 2011-11-14 | 2016-06-21 | 2016-06-29 | Highland | 2709580.83 | 0 | 531173.1 | 422069.57 | 0 | 45945.79 | 25985.99 | 0 | 1025174.45 | 0 | 0 | 0 | 3734755.28 | 0 | 0 | 0 | 0 | 3734755.28 | 28761.13 |  |  |  |  | 20540 | N | DW23 | 100%
507513 | Stafflar SR - Scour Pipe Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-25 | 2021-10-08 | 2022-04-11 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4564.08 | 4564.08 | 849.94 | 0 | 0 | 5414.02 | 0 | 0 | 0 | 0 | 5414.02 | 311236.79 | [5 empty] | N | CM_M&G | 100%
400928 | Stakeholder Management - Liasion of MGSDP and GSS Project | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-04-21 | 2013-05-08 | 2013-05-09 | 2018-06-22 | 2011-03-14 | Glasgow City | 266000 | 0 | 9001 | 0 | 0 | -6589.08 | 0 | 0 | 2411.92 | 0 | 0 | 0 | 268411.92 | 0 | 0 | 0 | 0 | 268411.92 | 0 | [5 empty] | N | EC01D | 33.33% | EC04C | 33.33% | EC10E | 33.33%
500104 | Standby Generators Phase 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-05-19 | 2016-03-29 | 2016-04-19 | 2022-01-12 |  | Scottish Water Wide | 0 | 0 | 540169 | 976312.31 | 1088756.86 | 367321.28 | 348309.14 | 12633.41 | 3333502 | 73718.9 | 0 | 0 | 3407220.9 | 0 | 0 | 0 | 0 | 3407220.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502337 | Standby Generators Phase 2A Multiple Sites East & North Mobile & Seasonal Hired | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-09-23 | 2018-10-25 | 2019-01-28 | 2021-06-18 |  | Scottish Water Wide | 0 | 0 | 0 | 8307.47 | 225073.04 | 353804.88 | 1045986.19 | 1004007.62 | 2637179.2 | 315602.8 | 0 | 0 | 2952782 | 0 | 0 | 0 | 0 | 2952782 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501687 | Standby Generators Phase 2B East & North Fixed Units | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2017-11-15 | 2027-09-15 | 2028-01-10 | 2029-03-28 |  | Scottish Water Wide | 0 | 0 | 0 | 12087.64 | 60587.36 | 364733.73 | 735.34 | 81100.93 | 519245 | 30754.8 | 0 | 0 | 549999.8 | 0 | 0 | 0 | 0 | 549999.8 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
510502 | Stanely Glennifer Braes TWP - H&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-25 | 2021-08-13 | 2022-03-28 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545.27 | 545.27 | 25000 | 0 | 0 | 25545.27 | 0 | 0 | 0 | 0 | 25545.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402867 | Stanely Reservoir -Installation of Drawdown Facility & Emergency Plan | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-21 | 2012-11-27 | 2013-02-25 | 2014-11-05 | 2014-11-05 | Renfrewshire | 237484 | 0 | 7170.37 | 0 | 0 | 0 | 0 | 0 | 7170.37 | 0 | 0 | 0 | 244654.37 | 0 | 0 | 0 | 0 | 244654.37 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501339 | STANELY SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-08 | 2028-07-25 | 2028-11-28 | 2030-02-25 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9300000.03 | 0 | 0 | 9300000.03 | 0 | 0 | 0 | 0 | 9300000.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508434 | Stanely WTW - Power Supply Relocation Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-11-25 | 2021-04-08 | 2021-11-19 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5009 | 5009 | 9990.64 | 0 | 0 | 14999.64 | 0 | 0 | 0 | 0 | 14999.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508142 | Stanley and Glen Dams Maintenance works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-08-19 | 2021-07-08 | 2022-01-21 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7896.33 | 7896.33 | 112149.57 | 0 | 0 | 120045.9 | 0 | 0 | 0 | 0 | 120045.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507445 | Stanley Reservoir Security Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-07-14 | 2020-10-07 | 2021-05-26 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21325.47 | 21325.47 | 0 | 0 | 0 | 21325.47 | 0 | 0 | 0 | 0 | 21325.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502763 | Stanley WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-08-08 | 2024-07-26 | 2024-10-24 | 2026-07-02 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 36725.76 | 31403.75 | 7998.13 | 52541.81 | 128669.45 | 7261756.02 | 0 | 0 | 7390425.47 | 0 | 0 | 0 | 0 | 7390425.47 | 122419.09 | [5 empty] | N | SG1 | 100%
501703 | Station Rd - Nairn Rd Ardersier - replace sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2018-08-27 | 2022-08-05 | 2022-11-11 | 2023-11-02 |  | Highland | 0 | 0 | 0 | 2418.28 | 7529.5 | 7923.92 | 0 | 80.45 | 17952.15 | 595854.18 | 0 | 0 | 613806.33 | 0 | 0 | 0 | 0 | 613806.33 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400926 | Station Road Plockton External Flooding - Sewer Rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-05-31 | 2011-10-31 | 2012-10-31 | 2013-06-20 |  | Highland | 386000 | 0 | -1048.5 | 0 | 0 | 0 | 0 | 0 | -1048.5 | 0 | 0 | 0 | 384951.5 | 0 | 0 | 0 | 0 | 384951.5 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510626 | STC Health Check Inspections (SW Wide) D.W.- 102K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7414.95 | 7414.95 | 95079.72 | 0 | 0 | 102494.67 | 0 | 0 | 0 | 0 | 102494.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508480 | Stellaire Ban Upper Proactive Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-09-03 | 2021-03-22 | 2021-06-18 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10585 | 10585 | 33595.28 | 0 | 0 | 44180.28 | 0 | 0 | 0 | 0 | 44180.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402168 | Stenness Village WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-06-13 | 2014-03-17 | 2014-05-28 | 2014-11-27 |  | Orkney Islands | 29749 | 0 | 694.46 | 0 | 0 | 0 | 0 | 0 | 694.46 | 0 | 0 | 0 | 30443.46 | 0 | 0 | 0 | 0 | 30443.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504387 | Stevenston DOA - Sewer Inspection | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2021-01-20 | 2021-03-08 | 2021-10-29 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 4566.1 | 18272.95 | 22839.05 | 47117.7 | 0 | 0 | 69956.75 | 0 | 0 | 0 | 0 | 69956.75 | 209381.79 | [5 empty] | N | WWI | 100%
500176 | Stevenston DOA (DOA000544) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS5 | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2020-03-09 | 2020-04-20 | North Ayrshire | 0 | 0 | 58109 | 284709 | 290872.61 | 273798.39 | 134491.93 | 113514.07 | 1155495 | 24505 | 24505 | 34017.1119 | 1180000 | 9512.1119 | 0 | 0 | 9512.1119 | 1189512.1119 | 404586.12 | [5 empty] | N | EC01G | 0.35% | EC01D | 1.33% | EC10E | 5.65% | CS11 | 20.23% | CS16D | 72.44%
403513 | Stevenston Point - Inlet Works Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2016-06-30 |  | North Ayrshire | 519494.81 | 0 | 25000.19 | -23678.78 | 0 | 0 | 0 | 0 | 1321.41 | 0 | 0 | 0 | 520816.22 | 0 | 0 | 0 | 0 | 520816.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502779 | Stevenston Point Headworks Coarse Screens CM | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS7 | 2017-06-20 | 2021-01-22 | 2021-03-02 | 2021-03-02 |  | North Ayrshire | 0 | 0 | 0 | 0 | 3207.75 | 135734.43 | 50723.94 | -46340.84 | 143325.28 | 0 | 0 | 0 | 143325.28 | 0 | 0 | 0 | 0 | 143325.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500932 | Stevenston Point Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | North Ayrshire | 0 | 0 | 6000 | 2000 | -4075.53 | 0 | 0 | 0 | 3924.47 | 0 | 0 | 0 | 3924.47 | 0 | 0 | 0 | 0 | 3924.47 | 106252.93 | [5 empty] | N | FL_DD | 100%
501518 | STEVENSTON POINT WWTW NS275404 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-09-05 | 2019-03-13 | 2019-03-28 | 2021-08-25 |  | North Ayrshire | 0 | 0 | 0 | 16616.29 | 334708.33 | 774930.14 | 2961157.88 | 1809172.04 | 5896584.68 | 772823.01 | 0 | 0 | 6669407.69 | 0 | 0 | 1080592.31 | 1080592.31 | 7750000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502249 | Stewart Drive Stornoway | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2017-06-29 | 2028-04-12 | 2028-06-09 | 2028-09-12 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 16665.34 | 3766.06 | 9462.41 | 4955.77 | 0.42 | 34850 | 329043.42 | 0 | 0 | 363893.42 | 0 | 0 | 0 | 0 | 363893.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502617 | Stewarton & Machrihanish DMA - Machrihanish Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2018-07-31 | 2019-09-18 | 2019-11-14 | 2020-03-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 18400 | 409.92 | 26024.95 | -43547.93 | -1222.87 | 64.08 | 0 | 0 | 0 | 64.08 | 0 | 0 | 0 | 0 | 64.08 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503737 | Stewarton & Machrihanish DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2019-10-04 | 2019-10-04 | 2020-02-18 | 2020-12-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 530041.76 | 425934.24 | 955976 | 999.95 | 0 | 0 | 956975.95 | 0 | 0 | 0 | 0 | 956975.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500179 | Stewarton DOA (DOA000159) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2019-01-31 | 2019-06-18 | East Ayrshire | 0 | 0 | 12315 | 39020 | 83759.78 | 66446.63 | 8368.57 | 0 | 209909.98 | 0 | 0 | 0 | 209909.98 | 0 | 0 | 0 | 0 | 209909.98 | 69265.59 | [5 empty] | N | EC01G | 0.9528% | EC10E | 21.91% | EC01D | 31.88% | CS16D | 45.26%
45019 | Stewarton STW Refurb - STW000671 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-13 | 2012-09-26 | 2013-01-14 | 2014-01-06 | 2014-04-17 | East Ayrshire | 1773514.9 | 0 | 1356.47 | 0 | 0 | 0 | 0 | 0 | 1356.47 | 0 | 0 | 0 | 1774871.37 | 0 | 0 | 0 | 0 | 1774871.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403939 | Stewarton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2018-06-13 | 2020-04-03 | 2020-03-30 | 2022-05-05 |  | East Ayrshire | 0 | 0 | 21902 | 20763.9 | 29496.67 | 27638.26 | 427392.7 | 487878.47 | 1015072 | 2343177 | 0 | 0 | 3358249 | 0 | 0 | 402910 | 402910 | 3761159 | 0 | [5 empty] | N | SG1 | 100%
502216 | Stichill ST Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-04-28 | 2019-02-12 | 2019-05-13 | 2020-03-19 |  | Scottish Borders | 0 | 0 | 0 | 20488.01 | 87105.99 | 207009 | 597856 | 9500 | 921959 | 1734 | 0 | 0 | 923693 | 0 | 0 | 0 | 0 | 923693 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510714 | Stichill WWTW - Septic Tank | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-03-06 | 2024-11-26 | 2025-02-27 | 2025-11-06 | 2026-02-06 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1613 | 1613 | 348387.32 | 0 | 0 | 350000.32 | 0 | 0 | 0 | 0 | 350000.32 | 0 | [5 empty] | N | SR21_WW | 100%
500180 | Stirling DOA (DOA000281) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater | SEPA | SWMD | Flood Risk Management Act | MS7 | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-08-29 | 2020-03-11 | Stirling | 0 | 0 | 36395 | 167369 | 89745 | 125000 | 78597 | 5275.97 | 502381.97 | 0 | 0 | 0 | 502381.97 | 0 | 0 | 0 | 0 | 502381.97 | 282022.48 | [5 empty] | N | EC01G | 16.49% | CS16D | 83.51%
402779 | Stirling Falkirk Yr 3 Promotion Health and Safety needs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-06-27 | 2012-06-27 | 2012-08-01 | 2016-05-19 |  | Stirling | 406809.05 | 0 | 26858.71 | 0 | 0 | 0 | 0 | 0 | 26858.71 | 0 | 0 | 0 | 433667.76 | 0 | 0 | 0 | 0 | 433667.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500933 | Stirling Hydraulic Verification - Gate 0-2 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2016-11-04 | 2016-11-04 | 2016-10-25 | 2016-11-04 | Stirling | 0 | 0 | 6000 | -918.81 | 0 | 0 | 0 | 0 | 5081.19 | 0 | 0 | 0 | 5081.19 | 0 | 0 | 0 | 0 | 5081.19 | 106252.93 | [5 empty] | N | FL_DD | 100%
511390 | Stirling Old Town Sewers | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-02-23 | 2023-08-30 | 2023-11-28 | 2024-11-04 | 2024-11-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13619 | 13619 | 440380.57 | 0 | 0 | 453999.57 | 0 | 0 | 0 | 0 | 453999.57 | 0 | [5 empty] | N | SR21_WW | 100%
403542 | Stirling Villages WwTWs - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2015-04-01 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2015-04-13 | Stirling | 57217.35 | 0 | 2276.45 | 0 | 0 | 0 | 0 | 0 | 2276.45 | 0 | 0 | 0 | 59493.8 | 0 | 0 | 0 | 0 | 59493.8 | 0 | [5 empty] | N | SG1 | 100%
403656 | Stobsmuir Dundee | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS7 | 2014-01-23 | 2014-01-23 | 2014-01-23 | 2015-02-05 |  | Dundee City | 40000 | 0 | -4807.02 | 0 | 0 | 0 | 0 | 0 | -4807.02 | 0 | 0 | 0 | 35192.98 | 0 | 0 | 0 | 0 | 35192.98 | 613322.63 | [5 empty] | N | CM_M&G | 100%
503730 | Stonebyres DMA Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2019-09-30 | 2021-06-07 | 2021-07-01 | 2022-06-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 36022.43 | 44717.57 | 80740 | 561260 | 0 | 0 | 642000 | 0 | 0 | 0 | 0 | 642000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
30909 | Stonehouse STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2010-09-20 | 2010-11-29 | 2015-03-25 | 2015-03-31 | South Lanarkshire | 3384163.86 | 0 | -1850.83 | -15828.93 | 10 | 0 | 0 | 0 | -17669.76 | 0 | 0 | 0 | 3366494.1 | 0 | 0 | 0 | 0 | 3366494.1 | 119362.42 | [5 empty] | N | CM_WWNI | 30.06% | EC04A | 69.94%
506557 | Stoneybridge Start Early works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-05-20 | 2020-12-04 | 2021-03-26 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68051.39 | 68051.39 | 264.16 | 0 | 0 | 68315.55 | 0 | 0 | 0 | 0 | 68315.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506779 | Stoneybridge WTW - Essential Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-06-23 | 2021-08-16 | 2021-08-23 | 2023-10-20 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299916.1 | 299916.1 | 5317213.75 | 0 | 0 | 5617129.85 | 0 | 0 | 0 | 0 | 5617129.85 | 119022.58 | [5 empty] | N | WSNI | 100%
501560 | Storm Tank Cleaning - Network Capacity Restoration Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-22 | 2017-03-28 | 2017-03-29 | 2019-01-30 |  | Scottish Water Wide | 0 | 0 | 3271.03 | -3271.03 | 585229.18 | 488936.63 | 13451.08 | 0 | 1087616.89 | 0 | 0 | 0 | 1087616.89 | 0 | 0 | 0 | 0 | 1087616.89 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501559 | Storm Tank Cleaning - Treatment Capacity Restoration Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-22 | 2016-04-18 | 2016-04-18 | 2018-01-24 |  | Scottish Water Wide | 0 | 0 | 47647.82 | 256245.64 | 6106.54 | 141.11 | 181345.58 | -181345.58 | 310141.11 | 0 | 0 | 0 | 310141.11 | 0 | 0 | 0 | 0 | 310141.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502230 | Stornoway DOA Saline Intrusion | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-05 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 29318.35 | 3748.32 | 0 | 0 | 0 | 33066.67 | 0 | 0 | 0 | 33066.67 | 0 | 0 | 0 | 0 | 33066.67 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403040 | Stornoway WOA - North Lochs Augmentation Line - Airiadh Na Lic tanks to Marybank PS - (Stage 2) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-26 | 2013-12-13 | 2014-02-11 | 2014-09-01 |  | Na H-Eileanan an Iar | 60675.52 | 0 | 1662.48 | -198.03 | 0 | 0 | 0 | 0 | 1464.45 | 0 | 0 | 0 | 62139.97 | 0 | 0 | 0 | 0 | 62139.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503421 | Stornoway WTW - Interim THM and Cryptosporidium measures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-10-31 | 2022-01-17 | 2022-04-18 | 2023-01-05 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 15992.7 | 98396.68 | 59782.42 | 174171.8 | 1534336.53 | 0 | 0 | 1708508.33 | 0 | 0 | 0 | 0 | 1708508.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
46842 | Storr Forest WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2013-01-30 | 2015-01-13 | 2015-01-13 | 2015-01-13 | Highland | 1195343.9 | 0 | 1096.16 | 0 | 0 | 0 | 0 | 0 | 1096.16 | 0 | 0 | 0 | 1196440.06 | 0 | 0 | 0 | 0 | 1196440.06 | 28761.13 | [5 empty] | N | DW23 | 100%
45556 | Stow STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-03-21 | 2011-07-29 | 2011-10-20 | 2011-11-28 | South Lanarkshire | 158832.66 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 159582.66 | 0 | 0 | 0 | 0 | 159582.66 | 28761.13 | [5 empty] | N | WQ01 | 100%
502829 | Strabathie ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2021-01-14 | 2021-01-14 | 2021-01-14 | 2021-02-01 |  | Aberdeen City | 0 | 0 | 0 | 0 | 64381.93 | 32910.79 | 22897.31 | -3413.81 | 116776.22 | 0 | 0 | 0 | 116776.22 | 0 | 0 | 0 | 0 | 116776.22 | 122419.09 | [5 empty] | N | SG1 | 100%
501488 | STRAN LARG ROAD WWPS(No 1) NX048623 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-07-19 | 2020-10-29 | 2021-01-18 | 2022-03-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 36764 | 127915 | 37261 | 182004 | 388520.45 | 772464.45 | 269065.74 | 0 | 0 | 1041530.19 | 0 | 0 | 24750.81 | 24750.81 | 1066281 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400097 | Stranraer Catchment UID Improvements | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-04 | 2011-10-13 | 2012-01-16 | 2013-03-12 | 2013-03-29 | Dumfries and Galloway | 240483 | 0 | -3079.97 | 0 | 0 | 0 | 0 | 0 | -3079.97 | 0 | 0 | 0 | 237403.03 | 0 | 0 | 0 | 0 | 237403.03 | 57522.26 | [5 empty] | N | EC01C | 35.24% | EC01B | 64.76%
402629 | Stranraer Catchment UID Improvements - Chevron Lochview Road Bishopburn Storm Overflow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-03-23 | 2012-08-24 | 2012-10-22 | 2013-03-28 | 2013-03-28 | Dumfries and Galloway | 1074575 | 0 | 18325 | 1362 | -2818.2 | 0 | 0 | 0 | 16868.8 | 0 | 0 | 0 | 1091443.8 | 0 | 0 | 0 | 0 | 1091443.8 | 418763.58 | [5 empty] | N | CS11A | 4.398% | CM_WWI | 26.13% | EC01B | 69.47%
402004 | Stranraer Catchment UID Improvements (Complex Solutions) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-21 | 2012-03-27 | 2012-05-21 | 2014-03-31 | 2014-02-14 | Dumfries and Galloway | 1530026 | 0 | 0 | 3244 | -574.62 | 0 | 0 | 0 | 2669.38 | 0 | 0 | 0 | 1532695.38 | 0 | 0 | 0 | 0 | 1532695.38 | 0 | [5 empty] | N | EC01B | 100%
402130 | Strategic Drainage Impact Assessment for Old Dalkeith Road Edinburgh | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2011-07-19 | 2011-08-18 | 2011-08-18 | 2011-12-09 |  | City of Edinburgh | 13656.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13656.78 | 0 | 0 | 0 | 0 | 13656.78 | 0 | [6 empty] | SG5 | 100%
500014 | Strategic Infrastructure - Bradan Pipe Inspection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2023-09-25 | 2024-11-15 | 2025-03-11 | 2026-06-03 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2447844.97 | 0 | 0 | 2447844.97 | 0 | 0 | 0 | 0 | 2447844.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503532 | Strategic Lead Sampling Programme | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2019-03-26 | 2019-03-26 | 2019-08-12 | 2021-12-17 | 2022-03-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 20934.58 | 78732.8 | 3632.69 | 103300.07 | 217261.52 | 0 | 0 | 320561.59 | 0 | 59926.342 | 0 | 59926.342 | 380487.932 | 19191.74 | [5 empty] | N | DW25TS | 100%
30913 | Strathaven STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2010-09-20 | 2010-11-29 | 2012-03-16 | 2012-03-21 | South Lanarkshire | 1421096.89 | 0 | 256.56 | 0 | 0 | 0 | 0 | 0 | 256.56 | 0 | 0 | 0 | 1421353.45 | 0 | 0 | 0 | 0 | 1421353.45 | 119362.42 | [5 empty] | N | CM_WWNI | 25% | EC10A | 75%
503274 | Strathaven WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-03-31 | 2020-03-31 | 2027-05-12 | 2020-06-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 78644.4 | 814.07 | 81.81 | 79540.28 | 0 | 0 | 0 | 79540.28 | 0 | 0 | 0 | 0 | 79540.28 | 122419.09 | [5 empty] | N | SG1 | 100%
501365 | STRATHBLANE WWTW NS547801 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-07-11 | 2021-01-05 | 2021-01-05 | 2021-01-15 |  | Stirling | 0 | 0 | 0 | 61666.51 | 157031.29 | -13994.03 | 0 | 7563.38 | 212267.15 | 0 | 0 | 0 | 212267.15 | 0 | 0 | 0 | 0 | 212267.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500110 | Strathclyde Loch Bathing Water Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 6834 | 60093.09 | 110167.91 | 246119 | 134844.37 | 0 | 558058.37 | 0 | 0 | 0 | 558058.37 | 0 | 0 | 0 | 0 | 558058.37 | 0 | [5 empty] | Y | EC16 | 100% | [38 empty] | 1 | [28 empty] | 0
45805 | Strathclyde Park SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2012-02-21 | 2012-07-31 | 2013-03-22 | 2013-03-22 | North Lanarkshire | 865314.3 | 0 | -1126.52 | 0 | 0 | 0 | 0 | 0 | -1126.52 | 0 | 0 | 0 | 864187.78 | 0 | 0 | 0 | 0 | 864187.78 | 119362.42 | [5 empty] | N | CM_WWNI | 10% | WQ01C | 90%
45557 | Strathmiglo STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2010-09-20 | 2011-07-07 | 2012-03-15 | 2012-03-26 | Fife | 880246.03 | 0 | 63492.33 | 0 | 0 | 0 | 0 | 0 | 63492.33 | 0 | 0 | 0 | 943738.36 | 0 | 0 | 0 | 0 | 943738.36 | 119362.42 | [5 empty] | N | CM_WWNI | 40% | WQ01 | 60%
501590 | Strathpeffer - Spa Pavillion Sewer Rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-06-29 | 2017-09-12 | 2018-01-22 | 2021-10-15 |  | Highland | 0 | 0 | 0 | 21107 | 403681 | 64765 | 10298 | 13600 | 513451 | 400 | 0 | 0 | 513851 | 0 | 0 | 0 | 0 | 513851 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506449 | STRATHYRE RISING MAIN REPLACEMENT | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-09-07 | 2021-03-02 | 2021-07-06 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25759 | 25759 | 24241 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45369 | Strathyre WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2012-07-29 | 2015-03-06 | Stirling | 211152.95 | 0 | 40.93 | 0 | 0 | 0 | 0 | 0 | 40.93 | 0 | 0 | 0 | 211193.88 | 0 | 0 | 0 | 0 | 211193.88 | 28761.13 | [5 empty] | N | DW13 | 100%
46846 | Strollamus WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-05-25 | 2012-06-25 | 2012-08-02 | 2012-09-05 | Highland | 163858.09 | 0 | 2506.89 | 0 | 0 | 0 | 0 | 0 | 2506.89 | 0 | 0 | 0 | 166364.98 | 0 | 0 | 0 | 0 | 166364.98 | 28761.13 | [5 empty] | N | DW23 | 100%
403938 | Stromness UWWTW (Transfer from 400089) | Q&S3B | Completion | Non OMG180 |  |  | Wastewater | SEPA | WWINF | Non OMG180 | MS6 | 2009-11-16 | 2015-10-29 | 2015-11-23 | 2018-02-23 | 2018-03-02 | Orkney Islands | 96078.05 | 0 | 3722788.95 | 4047033 | 537937 | 31163 | 0 | 51409.97 | 8390331.92 | 0 | 0 | 0 | 8486409.97 | 0 | 0 | 0 | 0 | 8486409.97 | 8966739.91 | [5 empty] | N | CM_WWI | 8% | EC01A | 92%
400089 | Stromness UWWTW Improvements Phase 3 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-11-16 | 2015-03-23 | 2014-12-01 | 2014-12-01 | 2015-02-03 | Orkney Islands | 1710547.5 | 0 | 1717.3 | -4686.13 | 20.8 | 0 | 0 | 0 | -2948.04 | 0 | 0 | 0 | 1707599.47 | 0 | 0 | 0 | 0 | 1707599.47 | 28761.13 | [5 empty] | N | EC01A | 100%
500877 | Stronsay RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-06 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Orkney Islands | 0 | 0 | 1392.07 | 2846.53 | 4955.33 | -4955.33 | 0 | 0 | 4238.6 | 0 | 0 | 0 | 4238.6 | 0 | 0 | 0 | 0 | 4238.6 | 89419.4 | [5 empty] | N | DW5FS | 100%
501092 | Stronsay WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS5 | 2016-10-28 | 2018-03-16 | 2018-03-27 | 2020-12-31 | 2021-03-31 | Orkney Islands | 0 | 0 | 27114.34 | 73480.8 | 514856.22 | 2447921.68 | 1041194.05 | 95790.57 | 4200357.66 | 80460.34 | 80460.34 | 479877.4045 | 4280818 | 399417.0645 | 0 | 0 | 399417.0645 | 4680235.0645 | 3614665.71 |  |  |  |  | 2428.9742 | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
500878 | Strontian RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-10-28 | 2018-09-27 | 2018-12-04 | 2019-03-31 | 2019-08-31 | Highland | 0 | 0 | 691.03 | 1308.97 | 3005.65 | 13696.33 | 6073.88 | -1999.79 | 22776.07 | 0 | 0 | 0 | 22776.07 | 0 | 0 | 0 | 0 | 22776.07 | 36779.09 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 7.49 | [43 empty] | 0
45370 | Strontian WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-18 | 2011-07-22 | 2012-02-09 | 2012-03-14 | Highland | 189878.28 | 0 | 670.2 | 0 | 0 | 0 | 0 | 0 | 670.2 | 0 | 0 | 0 | 190548.48 | 0 | 0 | 0 | 0 | 190548.48 | 28761.13 | [5 empty] | N | DW13 | 100%
505543 | Structural Condition of Drumboyhill DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-06 |  | 2021-08-17 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2616.82 | 11328.18 | 13945 | 20122.09 | 0 | 0 | 34067.09 | 0 | 0 | 0 | 0 | 34067.09 | 119022.58 | [5 empty] | N | WSNI | 100%
501553 | Structural-Strategic Mains- SWD interventions | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-02-23 | 2016-02-23 | 2016-04-01 | 2017-08-15 |  | Scottish Water Wide | 0 | 0 | 99367.08 | 187182.91 | 4996.8 | 0 | 0 | 0 | 291546.79 | 0 | 0 | 0 | 291546.79 | 0 | 0 | 0 | 0 | 291546.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500809 | Stuartfield WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS1 | 2018-04-16 | 2022-04-01 | 2022-08-22 | 2023-11-28 |  | Aberdeenshire | 0 | 0 | 21343.43 | 78503.63 | 31227.73 | 23929.21 | 98666.89 | 160660.11 | 414331 | 1640790.06 | 0 | 0 | 2055121.06 | 0 | 0 | 0 | 0 | 2055121.06 | 213020.38 | [5 empty] | N | CM_WWNI | 1% | SG1 | 99%
511051 | Study of transfer of HV assets to DNO | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2021-03-24 | 2021-12-06 | 2022-04-06 | 2022-10-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.72 | 42.72 | 27750.03 | 0 | 0 | 27792.75 | 0 | 0 | 0 | 0 | 27792.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500212 | Suainaval Western Isles- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-04-25 | 2016-06-20 | 2017-03-31 | 2018-06-30 | Na H-Eileanan an Iar | 0 | 0 | 422.12 | 32168.73 | -10634.73 | 1360 | -4845.4 | 0 | 18470.72 | 0 | 0 | 0 | 18470.72 | 0 | 0 | 0 | 0 | 18470.72 | 39674.04 | [5 empty] | Y | DW5FS | 100% | [19 empty] | 1 | [47 empty] | 0
500879 | Suainaval Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-31 | 2016-03-31 | 2016-07-18 | 2017-01-25 | 2017-11-13 | Na H-Eileanan an Iar | 0 | 0 | 2783.36 | 13967.64 | 21110.69 | 1137.95 | 487.61 | 0 | 39487.24 | 0 | 0 | 0 | 39487.24 | 0 | 0 | 0 | 0 | 39487.24 | 11740.11 | [5 empty] | N | DW5FS | 100%
501647 | Sub-sea Pipeline Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-04-20 | 2017-08-10 | 2017-09-08 | 2018-01-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 188568.53 | 102.9 | 0 | 0 | 188671.43 | 0 | 0 | 0 | 188671.43 | 0 | 0 | 0 | 0 | 188671.43 | 311236.79 | [5 empty] | N | CM_M&G | 100%
502795 | Suffolkhill Avenue Dumfries - Sewer Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-07-26 | 2017-07-26 | 2017-12-04 | 2018-05-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 383643 | 138894.41 | -185.99 | 0 | 522351.42 | 0 | 0 | 0 | 522351.42 | 0 | 0 | 0 | 0 | 522351.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
46231 | Sunnyside Fortrose and Rosemarkie CCTV and Pipe Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2008-10-01 | 2019-02-05 | 2019-02-01 | 2019-02-01 |  | Highland | 60708.56 | 0 | 0.44 | 0 | 0 | 0 | 0 | 0 | 0.44 | 0 | 0 | 0 | 60709 | 0 | 0 | 0 | 0 | 60709 | 209381.79 | [5 empty] | N | CM_WWI | 100%
50008 | Supplier Rebates Finance - SR15 - 2016-17 | Q&S3B | Completion | OMG180 |  |  | General |  | SWD | OMG180 | MS3 | 2017-03-31 | 2017-03-31 | 2017-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | -10383243 | 0 | 0 | 0 | 0 | -10383243 | 0 | 0 | 0 | -10383243 | 0 | 0 | 0 | 0 | -10383243 | 730242.44 | [5 empty] | N | SR15_DWA_PRE | 0.009352% | SR15_DWA_LEAK | 0.01525% | SR15_SEW_SWO | 0.02105% | SR15_ENV_RBWD | 0.03287% | SR15_DWA_EFA | 0.03337% | SR15_ENV_CAS | 0.04926% | SR15_ENV_WFD | 0.06577% | SR15_CCH_CC | 0.07481% | SR15_COS_REN | 0.08905% | SR15_ENV_SLU | 0.09835%
50013 | Supplier Rebates Finance - SR15 - 2017-18 | Q&S3B | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWD | Exceptional Capital Maintenance | MS3 | 2017-04-01 | 2017-04-01 | 2017-04-01 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | -7474506.12 | 0 | 0 | 0 | -7474506.12 | 0 | 0 | 0 | -7474506.12 | 0 | 0 | 0 | 0 | -7474506.12 | 730242.44 | [5 empty] | N | WG3 | 0.002112% | SR15_DWA_LEAK | 0.01541% | SR15_DWQ_FUT | 0.02207% | SR15_DWA_PRE | 0.0241% | SR15_DWA_EFA | 0.02432% | SR15_CEX_IT | 0.03023% | SR15_ENV_WFD | 0.04008% | SR15_ENV_RBWD | 0.04748% | SR15_SEW_SWO | 0.0565% | SR15_CCH_CC | 0.06171%
50024 | Supplier Rebates Finance - SR15 - 2018-19 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | -7809782.84 | 0 | 0 | -7809782.84 | 0 | 0 | 0 | -7809782.84 | 0 | 0 | 0 | 0 | -7809782.84 | 730242.44 | [5 empty] | N | SR15_ENV_HABD | -0.2677% | SR15_DWA_PRE | -0.0005855% | SR15_CCH_CC | 0.006823% | SR15_CMP_PFI | 0.01123% | SR15_ENV_ODO | 0.01572% | SR15_CEX_CMGT | 0.0187% | WG3 | 0.02241% | SR15_CEX_STU | 0.02635% | SR15_DWA_EFA | 0.02638% | SR15_DWA_LEAK | 0.03529%
50025 | Supplier Rebates Finance - SR15 - 2019-20 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MS7 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2020-03-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -7652612.27 | 0 | -7652612.27 | 0 | 0 | 0 | -7652612.27 | 0 | 0 | 0 | 0 | -7652612.27 | 730242.44 | [5 empty] | N | SR15_ENV_HABD | -0.007075% | SR15_CEX_CMGT | 0.003265% | SR15_SEW_SWO | 0.006715% | WG3 | 0.01354% | SR15_DWA_LEAK | 0.01391% | SR15_CEX_STU | 0.01568% | SR15_DWA_PRE | 0.01653% | SR15_DWA_EFA | 0.02038% | SR15_ENV_PSD | 0.02106% | SR15_COS_REN | 0.02111%
50026 | Supplier Rebates Finance - SR15 - 2020-21 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7682409.37 | -7682409.37 | 0 | 0 | 0 | -7682409.37 | 0 | 0 | 0 | 0 | -7682409.37 | 730242.44 | [5 empty] | N | SR15_DWQ_FUT | -0.1662% | SR15_CMP_LATE | -0.1354% | SR15_ENV_HABD | -0.007362% | SR15_DWA_PRE | -6.768e-05% | SR15_ENV_PSD | 0.005961% | SR15_CCH_CC | 0.01135% | SR15_ENV_ODO | 0.01157% | SR15_CEX_STU | 0.01384% | SR15_DWA_EFA | 0.01505% | SR15_COS_REN | 0.01613%
402078 | Supplier Rebates (Finance) | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS1 | 2011-03-23 | 2021-05-01 | 2021-03-02 | 2021-05-01 |  | Scottish Water Wide | -23954419.94 | 0 | -3689233.89 | 0 | 0 | 0 | 0 | 0 | -3689233.89 | 0 | 0 | 0 | -27643653.83 | 0 | 0 | 0 | 0 | -27643653.83 | 0 | [5 empty] | N | REB | 100%
509082 | Surface Water - Dalmuir Blue-Green Solutions | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS2 | 2020-10-15 | 2021-01-08 | 2022-04-19 | 2022-10-18 | 2023-01-18 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | 17500 | 182500 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 106252.93 | [5 empty] | N | FL_DD | 100%
508520 | Surface Water - Dundee Blue-Green Solutions | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2020-09-17 | 2021-01-08 | 2021-07-06 | 2021-12-06 | 2022-03-08 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114923 | 114923 | 9186.03 | 0 | 0 | 124109.03 | 0 | 0 | 0 | 0 | 124109.03 | 106252.93 | [5 empty] | N | FL_DD | 100%
508521 | Surface Water - Prestwick SWM Pilot | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2020-09-28 | 2021-01-08 | 2021-06-02 | 2021-12-01 | 2022-03-03 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21402 | 21402 | 150419.73 | 0 | 0 | 171821.73 | 0 | 0 | 0 | 0 | 171821.73 | 106252.93 | [5 empty] | N | FL_DD | 100%
508524 | Surface Water - Public Agency Disconnection Pilot | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2020-09-28 | 2021-01-08 | 2021-05-06 | 2021-11-04 | 2022-02-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153661 | 153661 | 7911.16 | 0 | 0 | 161572.16 | 0 | 0 | 0 | 0 | 161572.16 | 106252.93 | [5 empty] | N | FL_DD | 100%
502802 | Survey work to support Permanent Chemical Dosing at Daldowie WWTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2018-08-30 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | South Lanarkshire | 0 | 0 | 0 | 0 | 149563.71 | -149562.71 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 15547843.63 | [5 empty] | N | EC01A | 100%
502805 | Survey work to support Permanent Chemical Dosing at Dalmarnock WWTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2018-09-03 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | Glasgow City | 0 | 0 | 0 | 0 | 350093.38 | -350092.38 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 15547843.63 | [5 empty] | N | EC01A | 100%
502900 | Surveys and Rectification of Redundant Assets | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS3 | 2017-09-20 | 2017-09-20 | 2017-12-20 | 2021-10-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 237464 | 20390 | 102590.37 | 47177.71 | 407622.08 | 92377.93 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 328404.37 | [5 empty] | N | CM_M&G | 100%
503454 | Sustainable Catchment Decisions | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2019-01-30 | 2019-04-18 | 2019-04-22 | 2022-05-12 | 2022-05-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 37800 | 109611.4 | 8499.6 | 155911 | 149088.6 | 0 | 0 | 304999.6 | 0 | 41122.4888 | 0 | 41122.4888 | 346122.0888 | 295054.03 | [5 empty] | N | CS25 | 100%
503096 | Sustainable Regulation Projects- Value from Waste | IR18 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2019-01-04 | 2019-04-18 | 2019-04-22 | 2022-05-12 | 2022-05-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 56000 | 131866.62 | 4357.38 | 192224 | 62776.19 | 0 | 0 | 255000.19 | 0 | 17315.2955 | 0 | 17315.2955 | 272315.4855 | 295054.03 | [5 empty] | N | CS25 | 100%
402124 | Sustainable Solutions for Tackling Cryptosporidium | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-06-20 | 2012-09-26 | 2012-10-22 | 2014-12-22 | 2015-03-10 | Scottish Water Wide | 1669909 | 0 | -7521.29 | 0 | 0 | 0 | 0 | 0 | -7521.29 | 0 | 0 | 0 | 1662387.71 | 0 | 0 | 0 | 0 | 1662387.71 | 0 | [5 empty] | N | DW23A | 100%
401268 | Sustainable Treatment 1 Varying WwTW Performance In Relation To Environmental Conditions | Q&S3B | Completion | Non OMG180 |  |  | Wastewater | SEPA | SWMD | Non OMG180 | MS7 | 2010-09-15 | 2012-05-28 | 2012-09-24 | 2017-06-30 | 2017-09-30 | Scottish Water Wide | 989839.74 | 0 | 286982.51 | 120045.03 | 72219.37 | 0 | 0 | 0 | 479246.91 | 0 | 0 | 0 | 1469086.65 | 0 | 0 | 0 | 0 | 1469086.65 | 207999 | [5 empty] | Y | CC5S | 100% | [62 empty] | 1 |  |  |  |  | 0
401270 | Sustainable Treatment 3 Wetland Reed Bed Only Sustainability Trail | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-15 | 2011-02-18 | 2011-02-21 | 2014-12-24 | 2015-03-27 | Aberdeenshire | 364159 | 0 | 440.69 | 0 | 0 | 0 | 0 | 0 | 440.69 | 0 | 0 | 0 | 364599.69 | 0 | 0 | 0 | 0 | 364599.69 | 0 | [5 empty] | N | CC5S | 100%
503806 | SVCD App Development Phase 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-02-05 | 2020-02-28 | 2020-03-02 | 2020-05-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 321018.15 | 0 | 321018.15 | 0 | 0 | 0 | 321018.15 | 0 | 0 | 0 | 0 | 321018.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503022 | SVCD ATOM (LUBRICATION IMPROVEMENTS) PLANNED (SWD) - Yr4 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2018-03-16 | 2018-03-16 | 2018-04-02 | 2018-12-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 6214.95 | -6214.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
506670 | SVCD Central Water Non Infra - Geosmin and 2-MIB analysis | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS3 |  | 2020-08-27 | 2021-02-17 | 2021-11-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221877.01 | 221877.01 | 36370 | 0 | 0 | 258247.01 | 0 | 0 | 0 | 0 | 258247.01 | 0 | [5 empty] | N | SR21_WA | 100%
502087 | SVCD Reservoir Maintenance 16-17 East Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2018-12-14 |  | All East Unitary Authorities | 0 | 0 | 34383 | 298008 | 436585.64 | 181180.51 | -203223.82 | -588.21 | 746345.12 | 0 | 0 | 0 | 746345.12 | 0 | 0 | 0 | 0 | 746345.12 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502090 | SVCD Reservoir Maintenance 16-17 North Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-02-19 | 2016-02-19 | 2016-05-02 | 2021-07-23 |  | All North Unitary Authorities | 0 | 0 | 16355.14 | 390215.03 | 500605.17 | 24827.71 | 46628.27 | 14238.68 | 992870 | 28485.81 | 0 | 0 | 1021355.81 | 0 | 0 | 0 | 0 | 1021355.81 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502088 | SVCD Reservoir Maintenance 16-17 South Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-01 | 2016-03-01 | 2016-05-02 | 2021-07-23 |  | All South Unitary Authorities | 0 | 0 | 69905 | 337763.25 | 1416479.05 | 345608.35 | 263539.68 | -22456.46 | 2410838.87 | 1163.9 | 0 | 0 | 2412002.77 | 0 | 0 | 0 | 0 | 2412002.77 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502089 | SVCD Reservoir Maintenance 16-17 West Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-01 | 2016-03-01 | 2016-05-13 | 2022-04-14 |  | All West Unitary Authorities | 0 | 0 | 98130.84 | 956621.3 | 2088023.29 | 516442.95 | -169256.44 | -1493.38 | 3488468.56 | 0 | 0 | 0 | 3488468.56 | 0 | 0 | 0 | 0 | 3488468.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502590 | SVCD Reservoir Maintenance 17-18 East Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-05-30 | 2021-09-30 |  | All East Unitary Authorities | 0 | 0 | 0 | 49065.42 | 128742.28 | 256842.31 | 5000 | 13195.99 | 452846 | 33646.94 | 0 | 0 | 486492.94 | 0 | 0 | 0 | 0 | 486492.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502591 | SVCD Reservoir Maintenance 17-18 North Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-07-11 | 2021-07-15 |  | All North Unitary Authorities | 0 | 0 | 0 | 34653.45 | 95661.83 | 137348.48 | 151496.76 | -5863.42 | 413297.1 | 10096.37 | 0 | 0 | 423393.47 | 0 | 0 | 0 | 0 | 423393.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502592 | SVCD Reservoir Maintenance 17-18 South Area | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-14 | 2017-02-14 | 2017-05-01 | 2019-02-14 |  | All South Unitary Authorities | 0 | 0 | 0 | 65552.1 | 638097.6 | 309920.44 | -41443.98 | -3341.08 | 968785.08 | 0 | 0 | 0 | 968785.08 | 0 | 0 | 0 | 0 | 968785.08 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502593 | SVCD Reservoir Maintenance 17-18 SWD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-28 | 2017-02-28 | 2018-06-05 | 2020-02-28 |  | Scottish Water Wide | 0 | 0 | 0 | 51321.72 | 569457.62 | 152782.04 | -157129.32 | 0 | 616432.06 | 0 | 0 | 0 | 616432.06 | 0 | 0 | 0 | 0 | 616432.06 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502589 | SVCD Reservoir Maintenance 17-18 West Area | IR18 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water | DWQR | SWMD | Reservoirs | MS4 | 2017-02-17 | 2017-02-17 | 2017-04-17 | 2021-02-28 | 2021-03-31 | All West Unitary Authorities | 0 | 0 | 0 | 130841.12 | 1396243 | 1114617.28 | 260554.68 | -220768.81 | 2681487.27 | 0 | 0 | 0 | 2681487.27 | 0 | 0 | 0 | 0 | 2681487.27 | 668788.49 | [5 empty] | Y | WR6 | 17% | CM_WSI | 83% | [28 empty] | 1 | [36 empty] | 0
503157 | SVCD Reservoir Maintenance Yr4 to Yr6 SWD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-05-28 | 2018-05-28 | 2018-06-01 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 148090.8 | 444621.06 | 322947.46 | 915659.32 | -41903.25 | 0 | 0 | 873756.07 | 0 | 0 | 0 | 0 | 873756.07 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502291 | SVCD Responsive Wastewater East Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2016-10-25 | 2017-11-06 |  | All East Unitary Authorities | 0 | 0 | 0 | 147749.31 | 82951.19 | -37048.53 | 0 | 0 | 193651.97 | 0 | 0 | 0 | 193651.97 | 0 | 0 | 0 | 0 | 193651.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502292 | SVCD Responsive Wastewater North Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2017-01-23 | 2017-05-22 |  | All North Unitary Authorities | 0 | 0 | 0 | 891.04 | 0 | 0 | 0 | 0 | 891.04 | 0 | 0 | 0 | 891.04 | 0 | 0 | 0 | 0 | 891.04 | 599966.15 | [5 empty] | N | CM_WWI | 50% | CM_WWNI | 50%
502293 | SVCD Responsive Wastewater South Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2016-10-25 | 2017-04-21 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWI | 100%
502294 | SVCD Responsive Wastewater West Year 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2017-05-22 | 2017-05-22 |  | All West Unitary Authorities | 0 | 0 | 0 | 8618.63 | 0 | 0 | 0 | 0 | 8618.63 | 0 | 0 | 0 | 8618.63 | 0 | 0 | 0 | 0 | 8618.63 | 599966.15 | [5 empty] | N | CM_WWI | 50% | CM_WWNI | 50%
502295 | SVCD Responsive Water East Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-08-04 | 2016-08-04 | 2016-10-25 | 2018-02-06 |  | All East Unitary Authorities | 0 | 0 | 0 | 239987.32 | 397254.35 | 994.51 | 7802.59 | 728.56 | 646767.33 | 0 | 0 | 0 | 646767.33 | 0 | 0 | 0 | 0 | 646767.33 | 668304.54 | [5 empty] | N | CM_WSI | 25% | CM_WSNI | 75%
502296 | SVCD Responsive Water North Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-08-04 | 2016-08-04 | 2017-01-23 | 2017-05-22 |  | All North Unitary Authorities | 0 | 0 | 0 | 14833.02 | 631.08 | 0 | 0 | 0 | 15464.1 | 0 | 0 | 0 | 15464.1 | 0 | 0 | 0 | 0 | 15464.1 | 668304.54 | [5 empty] | N | CM_WSI | 25.34% | CM_WSNI | 74.66%
502297 | SVCD Responsive Water South Year 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-08-04 | 2016-08-04 | 2016-10-25 | 2017-04-21 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502298 | SVCD Responsive Water West Year 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-08-04 | 2016-08-04 | 2017-03-01 | 2017-05-22 |  | All West Unitary Authorities | 0 | 0 | 0 | 13711.75 | 84086.37 | 0 | 0 | 0.01 | 97798.12 | 0 | 0 | 0 | 97798.12 | 0 | 0 | 0 | 0 | 97798.12 | 668304.54 | [5 empty] | N | CM_WSI | 25% | CM_WSNI | 75%
503414 | SVCD SWD ATOM - Yr 4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-10-25 | 2018-10-25 | 2018-10-31 | 2021-02-03 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 130841.12 | 220.4 | -130825.69 | 235.83 | 0 | 0 | 0 | 235.83 | 0 | 0 | 0 | 0 | 235.83 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503477 | SVCD WASTE ALL AREAS Infra (SWD) Reactive -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2019-03-01 | 2019-03-01 | 2019-11-14 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 213271.03 | 8530631.15 | 193569.75 | 8937471.93 | 0 | 0 | 0 | 8937471.93 | 0 | 0 | 0 | 0 | 8937471.93 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503005 | SVCD WASTE EAST INFRA (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-29 | 2018-01-29 | 2018-04-02 | 2020-05-29 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 53644.86 | 1501977.04 | 47002.14 | 0 | 1602624.04 | 0 | 0 | 0 | 1602624.04 | 0 | 0 | 0 | 0 | 1602624.04 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503483 | SVCD WASTE EAST INFRA (SWD) - YR5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2019-03-26 | 2019-03-26 | 2019-07-01 | 2021-05-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 67496.64 | 480592.56 | 20141.26 | 568230.46 | 120771.84 | 0 | 0 | 689002.3 | 0 | 0 | 0 | 0 | 689002.3 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502979 | SVCD WASTE EAST INFRA PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2018-01-15 | 2018-01-15 | 2018-01-23 | 2020-11-24 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 39906.54 | 219508.07 | 500319.31 | 7650.72 | 767384.64 | 61341.93 | 0 | 0 | 828726.57 | 0 | 0 | 0 | 0 | 828726.57 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502980 | SVCD WASTE EAST INFRA RESPONSIVE (MD)-Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2019-07-08 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 18009 | 255441.9 | -6302.04 | 0 | 267148.86 | 0 | 0 | 0 | 267148.86 | 0 | 0 | 0 | 0 | 267148.86 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503482 | SVCD WASTE EAST NON INFRA (SWD) - YR5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2019-03-01 | 2019-03-01 | 2019-07-01 | 2021-05-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 410964.27 | 2076135.11 | 263387.49 | 2750486.86 | 111004.08 | 0 | 0 | 2861490.94 | 0 | 0 | 0 | 0 | 2861490.94 | 181202.57 | [5 empty] | N | CM_WWNI | 100%
503484 | SVCD WASTE EAST PLANNED (MD) - YR5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-02-28 | 2019-02-28 | 2019-05-20 | 2022-01-28 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 157009.35 | 768785.91 | 767586.74 | 1693382 | 314421.13 | 0 | 0 | 2007803.13 | 0 | 0 | 0 | 0 | 2007803.13 | 390584.36 | [5 empty] | N | CM_WWI | 33.33% | CM_WWNI | 66.67%
503485 | SVCD WASTE EAST RESPONSIVE (MD) - YR5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-02-28 | 2019-02-28 | 2019-05-01 | 2021-07-30 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 78700.31 | 1574550.85 | 42124.21 | 1695375.37 | 2253.59 | 0 | 0 | 1697628.96 | 0 | 0 | 0 | 0 | 1697628.96 | 390584.36 | [5 empty] | N | CM_WWNI | 43.33% | CM_WWI | 56.67%
503006 | SVCD WASTE EAST WWPS (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-01-29 | 2018-01-29 | 2018-04-02 | 2020-05-29 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 128644.86 | 827793.11 | 102899.59 | 0 | 1059337.56 | 0 | 0 | 0 | 1059337.56 | 0 | 0 | 0 | 0 | 1059337.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502981 | SVCD WASTE EAST WWPS PLANNED (MD)-Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-15 | 2018-01-15 | 2018-01-23 | 2020-09-22 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 40176.88 | 424985.61 | 120734.52 | 149.71 | 586046.71 | -0.26 | 0 | 0 | 586046.45 | 0 | 0 | 0 | 0 | 586046.45 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502982 | SVCD WASTE EAST WWPS RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2020-02-28 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 19009 | 325323.74 | 31325.59 | 180.45 | 375838.77 | 0 | 0 | 0 | 375838.77 | 0 | 0 | 0 | 0 | 375838.77 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503007 | SVCD WASTE EAST WWTW (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-04-02 | 2020-03-31 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 288694.35 | 1722125.91 | 8431.01 | 8285.29 | 2027536.56 | -2874.96 | 0 | 0 | 2024661.6 | 0 | 0 | 0 | 0 | 2024661.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502983 | SVCD WASTE EAST WWTW PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2018-01-31 | 2018-01-31 | 2018-02-08 | 2020-10-09 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 80696.04 | 118971.26 | 248652.52 | 392.08 | 448711.89 | -6220.85 | 0 | 0 | 442491.04 | 0 | 0 | 0 | 0 | 442491.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502984 | SVCD WASTE EAST WWTW RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2021-06-29 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 69257 | 1061028.79 | 1061387.9 | 93321.31 | 2284995 | 50000.02 | 0 | 0 | 2334995.02 | 0 | 0 | 0 | 0 | 2334995.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503003 | SVCD WASTE EMERGING NEEDS (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2021-05-01 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 436945.89 | 47441.87 | 205668.22 | 690055.98 | -124785.92 | 0 | 0 | 565270.06 | 0 | 0 | 0 | 0 | 565270.06 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503472 | SVCD WASTE NORTH (MD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-03-01 | 2019-03-01 | 2019-06-10 | 2021-09-17 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 153267.7 | 1366512.63 | 694862.32 | 2214642.65 | 153814.3 | 0 | 0 | 2368456.95 | 0 | 0 | 0 | 0 | 2368456.95 | 390584.36 | [5 empty] | N | CM_WWI | 13.48% | CM_WWNI | 86.52%
503442 | SVCD WASTE NORTH (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2019-03-26 | 2019-03-26 | 2019-06-03 | 2021-01-25 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 236.8 | 2216985.63 | 204898.78 | 2422121.21 | 0 | 0 | 0 | 2422121.21 | 0 | 0 | 0 | 0 | 2422121.21 | 390584.36 | [5 empty] | N | CM_WWI | 7.193% | CM_WWNI | 92.81%
503008 | SVCD WASTE NORTH INFRA (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-05 | 2019-09-10 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 70626.17 | 575220.51 | 76317.88 | 0 | 722164.56 | 0 | 0 | 0 | 722164.56 | 0 | 0 | 0 | 0 | 722164.56 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502985 | SVCD WASTE NORTH INFRA PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2019-05-13 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 22562.99 | -20231.77 | 124.73 | 32.95 | 2488.89 | 0 | 0 | 0 | 2488.89 | 0 | 0 | 0 | 0 | 2488.89 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502986 | SVCD WASTE NORTH INFRA RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2019-05-06 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 12524.81 | 53236.5 | -1737.93 | 0 | 64023.37 | 0 | 0 | 0 | 64023.37 | 0 | 0 | 0 | 0 | 64023.37 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503009 | SVCD WASTE NORTH WWPS (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-05 | 2019-09-02 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 98495.33 | 774630.13 | 61102.53 | 0 | 934227.99 | 0 | 0 | 0 | 934227.99 | 0 | 0 | 0 | 0 | 934227.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502987 | SVCD WASTE NORTH WWPS PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2021-09-17 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 22758.61 | 83179.65 | 136712.8 | -105019.73 | 137631.33 | 0 | 0 | 0 | 137631.33 | 0 | 0 | 0 | 0 | 137631.33 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502988 | SVCD WASTE NORTH WWPS RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2019-05-13 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 9478.88 | 19803.37 | -1239.56 | 0 | 28042.69 | 0 | 0 | 0 | 28042.69 | 0 | 0 | 0 | 0 | 28042.69 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503010 | SVCD WASTE NORTH WWTW (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-05 | 2019-09-10 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 272626.17 | 2165938.19 | 205486.85 | 93.53 | 2644144.73 | 0 | 0 | 0 | 2644144.73 | 0 | 0 | 0 | 0 | 2644144.73 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502989 | SVCD WASTE NORTH WWTW PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-21 | 2019-09-04 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 119553.64 | 537082.12 | 30863.6 | -20727.4 | 666771.96 | 0 | 0 | 0 | 666771.96 | 0 | 0 | 0 | 0 | 666771.96 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502990 | SVCD WASTE NORTH WWTW RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2018-01-30 | 2018-01-30 | 2018-02-21 | 2019-05-06 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 18637.76 | 48403.33 | -633.09 | 0 | 66408 | 0 | 0 | 0 | 66408 | 0 | 0 | 0 | 0 | 66408 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503465 | SVCD WASTE South (MD) Planned-Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-04-01 | 2021-07-31 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 170093.46 | 421668.24 | 124664.71 | 716426.41 | 78544.87 | 0 | 0 | 794971.28 | 0 | 0 | 0 | 0 | 794971.28 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503466 | SVCD WASTE SOUTH (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-03-26 | 2021-08-31 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 105673.38 | 1133446.97 | 439953.65 | 1679074 | 106765.06 | 0 | 0 | 1785839.06 | 0 | 0 | 0 | 0 | 1785839.06 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503011 | SVCD WASTE SOUTH INFRA (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-22 | 2018-01-22 | 2018-04-02 | 2020-02-18 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 179964.33 | 1651499.22 | 33153.85 | 300 | 1864917.4 | 0 | 0 | 0 | 1864917.4 | 0 | 0 | 0 | 0 | 1864917.4 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503460 | SVCD WASTE SOUTH Infra (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2019-02-28 | 2019-02-28 | 2019-12-30 | 2021-02-03 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 204161.74 | 195432.16 | 8473.63 | 408067.52 | -14330.98 | 0 | 0 | 393736.54 | 0 | 0 | 0 | 0 | 393736.54 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502991 | SVCD WASTE SOUTH INFRA PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2018-01-29 | 2018-01-29 | 2018-02-08 | 2021-02-03 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 58878.5 | 114151 | 83096.84 | -920.47 | 255205.87 | 0 | 0 | 0 | 255205.87 | 0 | 0 | 0 | 0 | 255205.87 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502992 | SVCD WASTE SOUTH INFRA RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2018-01-26 | 2018-01-26 | 2018-02-08 | 2021-02-03 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 90093.46 | 1020084.33 | 513655.63 | 212110.08 | 1835943.49 | 0.3 | 0 | 0 | 1835943.79 | 0 | 0 | 0 | 0 | 1835943.79 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503459 | SVCD WASTE SOUTH Non Infra (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 | 2019-03-20 | 2019-03-20 | 2019-04-01 | 2021-02-03 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 247242.71 | 2791957.86 | 175195.66 | 3214396.22 | -10209.87 | 0 | 0 | 3204186.35 | 0 | 0 | 0 | 0 | 3204186.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503012 | SVCD WASTE SOUTH WWPS (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-26 | 2020-03-24 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 87081.56 | 496275.28 | 31516.85 | 5899.43 | 620773.12 | 0 | 0 | 0 | 620773.12 | 0 | 0 | 0 | 0 | 620773.12 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502993 | SVCD WASTE SOUTH WWPS PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2018-01-15 | 2018-01-15 | 2018-01-30 | 2021-02-04 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 58920.09 | 124866.91 | 238237.42 | 5045.61 | 427070.03 | 500 | 0 | 0 | 427570.03 | 0 | 0 | 0 | 0 | 427570.03 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502994 | SVCD WASTE SOUTH WWPS RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2018-01-26 | 2018-01-26 | 2018-02-08 | 2020-09-08 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 24859.81 | 205646.57 | 129045.73 | 3134.11 | 362686.22 | 0 | 0 | 0 | 362686.22 | 0 | 0 | 0 | 0 | 362686.22 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503013 | SVCD WASTE SOUTH WWTW (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-01-31 | 2018-01-31 | 2018-02-26 | 2020-03-31 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 226700.96 | 3374770.66 | 865641.47 | 1191.77 | 4468304.86 | -1440.57 | 0 | 0 | 4466864.29 | 0 | 0 | 0 | 0 | 4466864.29 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502995 | SVCD WASTE SOUTH WWTW PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-17 | 2018-01-17 | 2018-01-30 | 2021-07-31 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 117102.8 | 731507.26 | 558913.06 | 286476.88 | 1694000 | 27627.74 | 0 | 0 | 1721627.74 | 0 | 0 | 0 | 0 | 1721627.74 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502996 | SVCD WASTE SOUTH WWTW RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2018-01-29 | 2018-01-29 | 2018-02-08 | 2021-02-03 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 50373.83 | 1248908.87 | 974126.25 | 5268.05 | 2278677 | 5906.69 | 0 | 0 | 2284583.69 | 0 | 0 | 0 | 0 | 2284583.69 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503004 | SVCD WASTE STC (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 | 2018-01-22 | 2018-01-22 | 2018-01-30 | 2020-10-13 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 98130.84 | 31000 | 346025.63 | 29518.28 | 504674.75 | -17463.55 | 0 | 0 | 487211.2 | 0 | 0 | 0 | 0 | 487211.2 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503471 | SVCD WASTE WEST (MD) Planned -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-04-01 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 137671.18 | 434917.51 | 560023.49 | 1132612.18 | 196480.03 | 0 | 0 | 1329092.21 | 0 | 0 | 0 | 0 | 1329092.21 | 390584.36 | [5 empty] | N | CM_WWI | 33.33% | CM_WWNI | 66.67%
503468 | SVCD WASTE WEST (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-04-01 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 78504.67 | 591163.73 | 93095.04 | 762763.44 | 143771.61 | 0 | 0 | 906535.05 | 0 | 0 | 0 | 0 | 906535.05 | 390584.36 | [5 empty] | N | CM_WWI | 16.67% | CM_WWNI | 83.33%
503014 | SVCD WASTE WEST INFRA (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-01 | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 230015.05 | 2828179.03 | -344650.71 | 37.41 | 2713580.79 | 15419.2 | 0 | 0 | 2728999.99 | 0 | 0 | 0 | 0 | 2728999.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503458 | SVCD WASTE WEST Infra (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2019-02-27 | 2019-02-27 | 2019-12-30 | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 280093.17 | 33534.61 | 41584.19 | 355211.97 | 0 | 0 | 0 | 355211.97 | 0 | 0 | 0 | 0 | 355211.97 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502997 | SVCD WASTE WEST INFRA PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-27 | 2018-02-27 | 2018-04-09 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 42523.36 | 24098.29 | 43120.37 | 5500.98 | 115243 | 59363.31 | 0 | 0 | 174606.31 | 0 | 0 | 0 | 0 | 174606.31 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502998 | SVCD WASTE WEST INFRA RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-26 | 2018-02-26 | 2018-06-08 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 22897.2 | 921874.19 | -327113.36 | 36269.56 | 653927.59 | -36866.49 | 0 | 0 | 617061.1 | 0 | 0 | 0 | 0 | 617061.1 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503457 | SVCD WASTE WEST Non Infra (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2019-03-13 | 2019-03-13 | 2019-04-01 | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 311070.09 | 2496094.34 | 160555.93 | 2967720.36 | 119956.2 | 0 | 0 | 3087676.56 | 0 | 0 | 0 | 0 | 3087676.56 | 181202.57 | [5 empty] | N | CM_WWNI | 100%
503015 | SVCD WASTE WEST WWPS (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 | 2018-01-31 | 2018-01-31 | 2018-02-01 | 2020-10-29 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 128794.68 | 1099398.57 | 320832.34 | 3649.3 | 1552674.89 | 15748.53 | 0 | 0 | 1568423.42 | 0 | 0 | 0 | 0 | 1568423.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502999 | SVCD WASTE WEST WWPS PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-28 | 2018-02-28 | 2018-04-09 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 34866.48 | 156015.08 | 34336.99 | 913.96 | 226132.51 | 121903.77 | 0 | 0 | 348036.28 | 0 | 0 | 0 | 0 | 348036.28 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503000 | SVCD WASTE WEST WWPS RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-28 | 2018-02-28 | 2018-06-08 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 21588.79 | 46941.93 | 421615.7 | 217697.87 | 707844.29 | -14032.81 | 0 | 0 | 693811.48 | 0 | 0 | 0 | 0 | 693811.48 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503016 | SVCD WASTE WEST WWTW (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-01 | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 243794.17 | 2902456.98 | 324957.72 | 4200 | 3475408.87 | -25409.05 | 0 | 0 | 3449999.82 | 0 | 0 | 0 | 0 | 3449999.82 | 209381.79 |  |  |  |  | 69282 | N | CM_WWI | 100%
503001 | SVCD WASTE WEST WWTW PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-27 | 2018-02-27 | 2018-04-09 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 65420.56 | 251819.79 | 111907.22 | -25152.44 | 403995.13 | 11013.19 | 0 | 0 | 415008.32 | 0 | 0 | 0 | 0 | 415008.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503002 | SVCD WASTE WEST WWTW RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-27 | 2018-02-27 | 2018-06-08 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 36064.49 | 466483.56 | -77974.71 | 76669.82 | 501243.16 | -34063.2 | 0 | 0 | 467179.96 | 0 | 0 | 0 | 0 | 467179.96 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502444 | SVCD Wastewater - Infra - East (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-19 | 2017-01-19 | 2017-04-03 | 2018-06-21 |  | All East Unitary Authorities | 0 | 0 | 0 | 40209.39 | 259372.15 | 20728 | -57794.19 | -145.97 | 262369.38 | 0 | 0 | 0 | 262369.38 | 0 | 0 | 0 | 0 | 262369.38 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502445 | SVCD Wastewater - Infra - East (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-04-12 | 2018-07-12 |  | All East Unitary Authorities | 0 | 0 | 0 | 17271.81 | 289275.37 | -26808.17 | 1175.07 | 311.12 | 281225.2 | 0 | 0 | 0 | 281225.2 | 0 | 0 | 0 | 0 | 281225.2 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502446 | SVCD Wastewater - Infra - East (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-19 | 2017-01-19 | 2017-04-03 | 2020-03-26 |  | All East Unitary Authorities | 0 | 0 | 0 | 54130.98 | 794080.88 | 1107052 | -24001.28 | 0 | 1931262.58 | 0 | 0 | 0 | 1931262.58 | 0 | 0 | 0 | 0 | 1931262.58 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502447 | SVCD Wastewater - Infra - North (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-05-09 | 2019-02-14 |  | All North Unitary Authorities | 0 | 0 | 0 | 23030.38 | 349732.23 | 108802.91 | -383.2 | 28.48 | 481210.8 | 0 | 0 | 0 | 481210.8 | 0 | 0 | 0 | 0 | 481210.8 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502448 | SVCD Wastewater - Infra - North (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-12 | 2017-01-12 | 2017-06-05 | 2018-03-01 |  | All North Unitary Authorities | 0 | 0 | 0 | 9158.88 | 21530.45 | 122.99 | 0 | 0 | 30812.31 | 0 | 0 | 0 | 30812.31 | 0 | 0 | 0 | 0 | 30812.31 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502449 | SVCD Wastewater - Infra - North (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-04-04 | 2019-05-30 |  | All North Unitary Authorities | 0 | 0 | 0 | 58048.82 | 511951.18 | -10000 | -2365.17 | 0 | 557634.83 | 0 | 0 | 0 | 557634.83 | 0 | 0 | 0 | 0 | 557634.83 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502450 | SVCD Wastewater - Infra - South (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-19 | 2017-01-19 | 2017-04-12 | 2020-09-08 |  | All South Unitary Authorities | 0 | 0 | 0 | 58878.5 | 159000 | 128071 | 0 | -5408.55 | 340540.95 | 0 | 0 | 0 | 340540.95 | 0 | 0 | 0 | 0 | 340540.95 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502451 | SVCD Wastewater - Infra - South (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-04-03 | 2019-06-04 |  | All South Unitary Authorities | 0 | 0 | 0 | 29859.81 | 1188240.72 | 131076.16 | 117605.03 | 0 | 1466781.72 | 0 | 0 | 0 | 1466781.72 | 0 | 0 | 0 | 0 | 1466781.72 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502452 | SVCD Wastewater - Infra - South (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-31 | 2017-01-31 | 2017-04-10 | 2019-03-13 |  | All South Unitary Authorities | 0 | 0 | 0 | 78504.67 | 951441.69 | 1144589.39 | 68335.91 | 79.78 | 2242951.43 | 0 | 0 | 0 | 2242951.43 | 0 | 0 | 0 | 0 | 2242951.43 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502453 | SVCD Wastewater - Infra - West (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-19 | 2017-01-19 | 2017-04-12 | 2021-02-26 |  | All West Unitary Authorities | 0 | 0 | 0 | 50373.83 | 287587.66 | 499933.33 | 89437.79 | -40784.87 | 886547.74 | 70273.08 | 0 | 0 | 956820.82 | 0 | 0 | 0 | 0 | 956820.82 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502454 | SVCD Wastewater - Infra - West (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-04-14 | 2019-02-04 |  | All West Unitary Authorities | 0 | 0 | 0 | 21588.79 | 431943.87 | -57922.51 | 510.73 | 0 | 396120.88 | 0 | 0 | 0 | 396120.88 | 0 | 0 | 0 | 0 | 396120.88 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502455 | SVCD Wastewater - Infra - West (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-31 | 2017-01-31 | 2017-11-17 | 2019-03-12 |  | All West Unitary Authorities | 0 | 0 | 0 | 118889.89 | 682155.96 | 1074403.71 | 60546.96 | 0 | 1935996.52 | 0 | 0 | 0 | 1935996.52 | 0 | 0 | 0 | 0 | 1935996.52 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502475 | SVCD Wastewater - Responsive WWTW - South (MD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-07 | 2017-02-07 | 2017-05-09 | 2020-03-26 |  | All South Unitary Authorities | 0 | 0 | 0 | 50373.83 | 731308.98 | 519465.24 | 109683.16 | 71367.4 | 1482198.61 | 0 | 0 | 0 | 1482198.61 | 0 | 0 | 0 | 0 | 1482198.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502456 | SVCD Wastewater - WWPS - East (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-19 | 2017-01-19 | 2017-04-03 | 2018-06-21 |  | All East Unitary Authorities | 0 | 0 | 0 | 40169.02 | 9921.77 | -43592.23 | -406.27 | 0 | 6092.29 | 0 | 0 | 0 | 6092.29 | 0 | 0 | 0 | 0 | 6092.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502457 | SVCD Wastewater - WWPS - East (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-05-18 | 2019-02-06 |  | All East Unitary Authorities | 0 | 0 | 0 | 17261.7 | 320845.65 | 373084.19 | 31033 | 0 | 742224.54 | 0 | 0 | 0 | 742224.54 | 0 | 0 | 0 | 0 | 742224.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502458 | SVCD Wastewater - WWPS - East (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-01-19 | 2017-01-19 | 2017-04-03 | 2020-03-31 |  | All East Unitary Authorities | 0 | 0 | 0 | 57984.24 | 899798.95 | 423490.27 | 34288.75 | 0 | 1415562.21 | 0 | 0 | 0 | 1415562.21 | 0 | 0 | 0 | 0 | 1415562.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502459 | SVCD Wastewater - WWPS - North (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-05-09 | 2018-03-01 |  | All North Unitary Authorities | 0 | 0 | 0 | 22529.71 | 2366.72 | 123.23 | 0 | 0 | 25019.65 | 0 | 0 | 0 | 25019.65 | 0 | 0 | 0 | 0 | 25019.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502460 | SVCD Wastewater - WWPS - North (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-12 | 2017-01-12 | 2017-06-05 | 2018-04-23 |  | All North Unitary Authorities | 0 | 0 | 0 | 9158.88 | 31153.46 | -38090.39 | 0 | 0 | 2221.95 | 0 | 0 | 0 | 2221.95 | 0 | 0 | 0 | 0 | 2221.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502461 | SVCD Wastewater - WWPS - North (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-05-09 | 2019-03-19 |  | All North Unitary Authorities | 0 | 0 | 0 | 37148.49 | 456010.3 | 271350.53 | 35538.12 | 0 | 800047.44 | 0 | 0 | 0 | 800047.44 | 0 | 0 | 0 | 0 | 800047.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502463 | SVCD Wastewater - WWPS - South (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-04-03 | 2020-06-19 |  | All South Unitary Authorities | 0 | 0 | 0 | 24859.81 | 431596 | 371520 | 86966 | -1971.25 | 912970.56 | 0 | 0 | 0 | 912970.56 | 0 | 0 | 0 | 0 | 912970.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502462 | SVCD Wastewater - WWPS - South (MD)Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-19 | 2017-01-19 | 2017-05-18 | 2020-09-08 |  | All South Unitary Authorities | 0 | 0 | 0 | 58878.5 | 237285 | 169121 | 0 | 4077.64 | 469362.14 | 0 | 0 | 0 | 469362.14 | 0 | 0 | 0 | 0 | 469362.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502464 | SVCD Wastewater - WWPS - South (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-01-31 | 2017-01-31 | 2017-11-17 | 2019-03-13 |  | All South Unitary Authorities | 0 | 0 | 0 | 100800.1 | 486923.44 | 221643.57 | -50.7 | 0.01 | 809316.41 | 0 | 0 | 0 | 809316.41 | 0 | 0 | 0 | 0 | 809316.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502465 | SVCD Wastewater - WWPS - West (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2017-01-19 | 2017-01-19 | 2017-04-24 | 2019-03-05 |  | All West Unitary Authorities | 0 | 0 | 0 | 50373.83 | 170024.68 | 292801.17 | 0 | -14853.24 | 498346.44 | 16806.19 | 0 | 0 | 515152.63 | 0 | 0 | 0 | 0 | 515152.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502466 | SVCD Wastewater - WWPS - West (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-06-05 | 2018-09-27 |  | All West Unitary Authorities | 0 | 0 | 0 | 21588.79 | 153500 | 98000 | -8971.17 | 0 | 264117.62 | 0 | 0 | 0 | 264117.62 | 0 | 0 | 0 | 0 | 264117.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502467 | SVCD Wastewater - WWPS - West (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-01-13 | 2017-01-13 | 2017-11-17 | 2019-03-12 |  | All West Unitary Authorities | 0 | 0 | 0 | 117589.11 | 970455.16 | 211791.45 | 19588.5 | 0 | 1319424.22 | 0 | 0 | 0 | 1319424.22 | 0 | 0 | 0 | 0 | 1319424.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502468 | SVCD Wastewater - WWTW - East (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-11 | 2017-02-11 | 2017-04-03 | 2019-05-29 |  | All East Unitary Authorities | 0 | 0 | 0 | 80810.37 | 545906.92 | 439971.76 | -23779.82 | 14.02 | 1042923.25 | 0 | 0 | 0 | 1042923.25 | 0 | 0 | 0 | 0 | 1042923.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502469 | SVCD Wastewater - WWTW - East (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-24 | 2017-02-24 | 2017-06-06 | 2021-06-30 |  | All East Unitary Authorities | 0 | 0 | 0 | 34915.11 | 1444276.71 | 1417660.79 | 184033.5 | 9426.17 | 3090312.28 | 17743.96 | 0 | 0 | 3108056.24 | 0 | 0 | 0 | 0 | 3108056.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502470 | SVCD Wastewater - WWTW - East (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-11 | 2017-02-11 | 2017-04-03 | 2019-12-31 |  | All East Unitary Authorities | 0 | 0 | 0 | 250598.84 | 1340246.56 | 813085.74 | -40565.2 | 0 | 2363365.94 | 0 | 0 | 0 | 2363365.94 | 0 | 0 | 0 | 0 | 2363365.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502471 | SVCD Wastewater - WWTW - North (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-07-18 | 2021-02-16 |  | All North Unitary Authorities | 0 | 0 | 0 | 44160.79 | 592584.24 | 300191.07 | 115471.75 | -339085.49 | 713322.36 | 0 | 0 | 0 | 713322.36 | 0 | 0 | 0 | 0 | 713322.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502472 | SVCD Wastewater - WWTW - North (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-06-05 | 2018-04-19 |  | All North Unitary Authorities | 0 | 0 | 0 | 18317.76 | 212592 | -2031.77 | 0 | 0 | 228877.99 | 0 | 0 | 0 | 228877.99 | 0 | 0 | 0 | 0 | 228877.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502473 | SVCD Wastewater - WWTW - North (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-05-09 | 2019-03-19 |  | All North Unitary Authorities | 0 | 0 | 0 | 61701.45 | 1493864.88 | 189210.8 | -69012.52 | 0 | 1675764.61 | 0 | 0 | 0 | 1675764.61 | 0 | 0 | 0 | 0 | 1675764.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502474 | SVCD Wastewater - WWTW - South (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-11 | 2017-02-11 | 2017-03-06 | 2020-09-08 |  | All South Unitary Authorities | 0 | 0 | 0 | 122102.8 | 633470.69 | 1044401.21 | 314212.29 | 5249.31 | 2119436.3 | 8333.99 | 0 | 0 | 2127770.29 | 0 | 0 | 0 | 0 | 2127770.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502476 | SVCD Wastewater - WWTW - South (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-21 | 2017-02-21 | 2017-11-17 | 2019-05-14 |  | All South Unitary Authorities | 0 | 0 | 0 | 267845.74 | 2324769.46 | 655911.42 | 9081 | 0 | 3257607.61 | -2314.95 | 0 | 0 | 3255292.66 | 0 | 0 | 0 | 0 | 3255292.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502477 | SVCD Wastewater - WWTW - West (MD) Planned - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-11 | 2017-02-11 | 2017-04-17 | 2022-04-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 100093.46 | 4171.78 | 141863.59 | 11654.21 | -75309.08 | 182473.95 | 89530.76 | 0 | 0 | 272004.71 | 0 | 0 | 0 | 0 | 272004.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502478 | SVCD Wastewater - WWTW - West (MD) Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-06-05 | 2019-01-18 |  | All West Unitary Authorities | 0 | 0 | 0 | 43177.57 | 253073.11 | 462100.99 | -21922.52 | 0 | 736429.15 | 0 | 0 | 0 | 736429.15 | 0 | 0 | 0 | 0 | 736429.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502479 | SVCD Wastewater - WWTW - West (SWD) - Yr3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-11 | 2017-02-11 | 2017-11-24 | 2019-03-12 |  | All West Unitary Authorities | 0 | 0 | 0 | 162750.5 | 2210274.09 | 624813.65 | 66348.68 | 0 | 3064186.92 | 0 | 0 | 0 | 3064186.92 | 0 | 0 | 0 | 0 | 3064186.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501946 | SVCD Wastewater East Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2018-08-22 |  | All East Unitary Authorities | 0 | 0 | 80284.31 | 93835.69 | 42115.26 | -45735.63 | 0 | 0 | 170499.63 | 0 | 0 | 0 | 170499.63 | 0 | 0 | 0 | 0 | 170499.63 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502107 | SVCD Wastewater East Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2018-04-11 |  | All East Unitary Authorities | 0 | 0 | 0 | 941016.01 | 44658.66 | 0 | 0 | 0 | 985674.67 | 0 | 0 | 0 | 985674.67 | 0 | 0 | 0 | 0 | 985674.67 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502110 | SVCD Wastewater East SPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2017-11-07 |  | All East Unitary Authorities | 0 | 0 | 69226 | 202912.72 | 93310.06 | 0 | 0 | 0 | 365448.78 | 0 | 0 | 0 | 365448.78 | 0 | 0 | 0 | 0 | 365448.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502115 | SVCD Wastewater East SPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2019-03-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 1160765.69 | 291718.1 | 49803.29 | 0 | 0.01 | 1502287.08 | 0 | 0 | 0 | 1502287.08 | 0 | 0 | 0 | 0 | 1502287.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502116 | SVCD Wastewater East WWTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2017-11-06 |  | All East Unitary Authorities | 0 | 0 | 138452 | 350558.18 | -12279.76 | 395.52 | 0 | 0 | 477125.94 | 0 | 0 | 0 | 477125.94 | 0 | 0 | 0 | 0 | 477125.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502117 | SVCD Wastewater East WWTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-03-22 | 2016-03-22 | 2016-03-31 | 2019-03-01 |  | All East Unitary Authorities | 0 | 0 | 69566.77 | 2689689.9 | 325123.9 | 33171.56 | -10124.86 | 0 | 3107427.27 | 0 | 0 | 0 | 3107427.27 | 0 | 0 | 0 | 0 | 3107427.27 | 90601.29 |  |  |  |  | 26166 | N | CM_WWNI | 100%
502118 | SVCD Wastewater North Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-03-21 | 2016-03-21 | 2016-04-08 | 2018-06-01 |  | All North Unitary Authorities | 0 | 0 | 0 | 165357.12 | 159245.06 | 1637.1 | 0 | 0 | 326239.28 | 0 | 0 | 0 | 326239.28 | 0 | 0 | 0 | 0 | 326239.28 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502119 | SVCD Wastewater North Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-03-21 | 2016-03-21 | 2016-04-08 | 2017-11-07 |  | All North Unitary Authorities | 0 | 0 | 21261.68 | 348851.63 | 14068.72 | 0 | 0 | 0 | 384182.03 | 0 | 0 | 0 | 384182.03 | 0 | 0 | 0 | 0 | 384182.03 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502120 | SVCD Wastewater North SPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-04-01 | 2016-04-01 | 2016-07-12 | 2018-02-12 |  | All North Unitary Authorities | 0 | 0 | 0 | 46596.44 | 66090.32 | 0 | 0 | 0 | 112686.76 | 0 | 0 | 0 | 112686.76 | 0 | 0 | 0 | 0 | 112686.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502121 | SVCD Wastewater North SPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-07-15 | 2017-11-07 |  | All North Unitary Authorities | 0 | 0 | 0 | 872058.84 | 26855.82 | 0 | 0 | 0 | 898914.66 | 0 | 0 | 0 | 898914.66 | 0 | 0 | 0 | 0 | 898914.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502122 | SVCD Wastewater North WWTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-03-31 | 2016-03-31 | 2016-04-08 | 2018-02-12 |  | All North Unitary Authorities | 0 | 0 | 99766 | 418520.19 | 184681.9 | 6335.47 | -3369.78 | -871.45 | 705062.32 | 0 | 0 | 0 | 705062.32 | 0 | 0 | 0 | 0 | 705062.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502123 | SVCD Wastewater North WWTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-07-05 | 2017-12-11 |  | All North Unitary Authorities | 0 | 0 | 789.82 | 1601184.3 | 485071.12 | -34756 | 0 | 0 | 2052289.24 | -4610.43 | 0 | 0 | 2047678.81 | 0 | 0 | 0 | 0 | 2047678.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502108 | SVCD Wastewater South Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-04-22 | 2016-04-22 | 2016-05-03 | 2017-11-02 |  | All South Unitary Authorities | 0 | 0 | 0 | 1382308.47 | -314033.12 | -15967.48 | 0 | 0 | 1052307.87 | 0 | 0 | 0 | 1052307.87 | 0 | 0 | 0 | 0 | 1052307.87 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502109 | SVCD Wastewater South Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-08-22 | 2018-03-07 |  | All South Unitary Authorities | 0 | 0 | 0 | 715123.96 | 152602.15 | 0 | 0 | 0 | 867726.11 | 0 | 0 | 0 | 867726.11 | 0 | 0 | 0 | 0 | 867726.11 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502111 | SVCD Wastewater South SPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-06-01 | 2017-09-18 |  | All South Unitary Authorities | 0 | 0 | 85049 | 240592.28 | 163393.66 | -29604.72 | 0 | 0 | 459430.22 | 0 | 0 | 0 | 459430.22 | 0 | 0 | 0 | 0 | 459430.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502112 | SVCD Wastewater South SPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-08-22 | 2018-03-07 |  | All South Unitary Authorities | 0 | 0 | 0 | 710417.27 | 56800.92 | 0 | 0 | 0 | 767218.19 | 0 | 0 | 0 | 767218.19 | 0 | 0 | 0 | 0 | 767218.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502113 | SVCD Wastewater South WWTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-04-22 | 2018-08-22 |  | All South Unitary Authorities | 0 | 0 | 174054 | 1485077.91 | 437811.62 | -183756.91 | -76839.16 | 0 | 1836347.46 | 0 | 0 | 0 | 1836347.46 | 0 | 0 | 0 | 0 | 1836347.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502114 | SVCD Wastewater South WWTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-06-22 | 2018-03-30 |  | All South Unitary Authorities | 0 | 0 | 0 | 3072628.91 | 399426.78 | 0 | 0 | 0 | 3472055.69 | 0 | 0 | 0 | 3472055.69 | 0 | 0 | 0 | 0 | 3472055.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502101 | SVCD Wastewater West Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2019-02-04 |  | All West Unitary Authorities | 0 | 0 | 0 | 898415.53 | 606132.34 | 150456.15 | -41261.84 | 0 | 1613742.18 | 0 | 0 | 0 | 1613742.18 | 0 | 0 | 0 | 0 | 1613742.18 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502102 | SVCD Wastewater West Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-04-22 | 2018-11-01 |  | All West Unitary Authorities | 0 | 0 | 100000 | 895393.46 | 11368.5 | -16603.94 | 0 | 0 | 990158.02 | 0 | 0 | 0 | 990158.02 | 0 | 0 | 0 | 0 | 990158.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502103 | SVCD Wastewater West SPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2019-01-08 |  | All West Unitary Authorities | 0 | 0 | 0 | 445790.08 | 295399.79 | 31726.99 | -40395.87 | 0 | 732520.99 | 0 | 0 | 0 | 732520.99 | 0 | 0 | 0 | 0 | 732520.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502104 | SVCD Wastewater West SPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2018-11-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 1150817.3 | 141092.28 | 62554.29 | 0 | 0 | 1354463.86 | 0 | 0 | 0 | 1354463.86 | 0 | 0 | 0 | 0 | 1354463.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502105 | SVCD Wastewater West WWTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-04-22 | 2018-08-24 |  | All West Unitary Authorities | 0 | 0 | 0 | 942656.67 | 292059.72 | -25524.26 | 0 | 0 | 1209192.13 | 0 | 0 | 0 | 1209192.13 | 0 | 0 | 0 | 0 | 1209192.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502106 | SVCD Wastewater West WWTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2018-11-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 2538780.7 | 458187.21 | 119331.16 | 0 | 0 | 3116299.07 | 0 | 0 | 0 | 3116299.07 | 0 | 0 | 0 | 0 | 3116299.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502482 | SVCD Water - Infra - Central - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-11-22 | 2019-04-15 |  | Scottish Water Wide | 0 | 0 | 0 | 17009.35 | 161645.82 | -5482.44 | -5640.3 | 354.69 | 167887.12 | 0 | 0 | 0 | 167887.12 | 0 | 0 | 0 | 0 | 167887.12 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502484 | SVCD Water - Infra - East - Managed Delivery - Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-14 | 2017-02-14 | 2017-05-08 | 2018-12-10 |  | All East Unitary Authorities | 0 | 0 | 0 | 33364.49 | 313277.09 | 239090.96 | 1596.38 | -1173.17 | 586155.75 | 0 | 0 | 0 | 586155.75 | 0 | 0 | 0 | 0 | 586155.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502485 | SVCD Water - Infra - East - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-04-03 | 2020-03-26 |  | All East Unitary Authorities | 0 | 0 | 0 | 147850.47 | 307366.77 | 2239581.09 | 110102.22 | 0 | 2804900.56 | 0 | 0 | 0 | 2804900.56 | 0 | 0 | 0 | 0 | 2804900.56 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502487 | SVCD Water - Infra - North - Managed Delivery - Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2019-01-17 |  | All North Unitary Authorities | 0 | 0 | 0 | 29439.25 | 86552.46 | 52894.17 | 103.94 | 86.37 | 169076.19 | 0 | 0 | 0 | 169076.19 | 0 | 0 | 0 | 0 | 169076.19 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502488 | SVCD Water - Infra - North - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-05-05 | 2018-11-29 |  | All North Unitary Authorities | 0 | 0 | 0 | 134724.68 | 467986.45 | 1462279.4 | -19515.66 | 0 | 2045474.87 | 0 | 0 | 0 | 2045474.87 | 0 | 0 | 0 | 0 | 2045474.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502490 | SVCD Water - Infra - South - Managed Delivery - Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-05-17 | 2018-06-07 |  | All South Unitary Authorities | 0 | 0 | 0 | 31401.87 | 181507 | 69097 | -5604.1 | 147.46 | 276549.23 | 0 | 0 | 0 | 276549.23 | 0 | 0 | 0 | 0 | 276549.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502491 | SVCD Water - Infra - South - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-11-10 | 2019-07-08 |  | All South Unitary Authorities | 0 | 0 | 0 | 152104.4 | 715323.03 | 3255613.81 | -19885.99 | 0 | 4103155.26 | 0 | 0 | 0 | 4103155.26 | 0 | 0 | 0 | 0 | 4103155.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502493 | SVCD Water - Infra - West - Managed Delivery - Responsive - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-06-05 | 2018-11-05 |  | All West Unitary Authorities | 0 | 0 | 0 | 35327.1 | 116871.76 | 102885.86 | 7960.47 | 0 | 263045.19 | 0 | 0 | 0 | 263045.19 | 0 | 0 | 0 | 0 | 263045.19 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502494 | SVCD Water - Infra - West - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-23 | 2017-02-23 | 2017-11-24 | 2019-06-18 |  | All West Unitary Authorities | 0 | 0 | 0 | 157009.35 | 289282.63 | 3921969.37 | -142418.54 | 0 | 4225842.81 | 0 | 0 | 0 | 4225842.81 | 0 | 0 | 0 | 0 | 4225842.81 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502481 | SVCD Water - Planned Infra - Central - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-10 | 2017-02-10 | 2017-04-28 | 2019-06-12 |  | Scottish Water Wide | 0 | 0 | 0 | 15046.73 | 8000 | 53274.25 | 13144.9 | 0 | 89465.88 | 0 | 0 | 0 | 89465.88 | 0 | 0 | 0 | 0 | 89465.88 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502483 | SVCD Water - Planned Infra - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-05-17 | 2021-09-30 |  | All East Unitary Authorities | 0 | 0 | 0 | 78504.67 | 122522 | 178973.33 | 49477.12 | 20974.88 | 450452 | 185077.63 | 0 | 0 | 635529.63 | 0 | 0 | 0 | 0 | 635529.63 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502486 | SVCD Water - Planned Infra - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2017-02-17 | 2017-02-17 | 2017-05-17 | 2019-07-05 |  | All North Unitary Authorities | 0 | 0 | 0 | 68217.38 | 708205.98 | 1060727.58 | 66594.7 | -3466.29 | 1900279.35 | 0 | 0 | 0 | 1900279.35 | 0 | 0 | 0 | 0 | 1900279.35 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502489 | SVCD Water - Planned Infra - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2017-02-17 | 2017-02-17 | 2017-05-17 | 2019-01-18 |  | All South Unitary Authorities | 0 | 0 | 0 | 72616.82 | 329027.71 | 78385.82 | -35727.92 | -107.65 | 444194.78 | 2577.56 | 0 | 0 | 446772.34 | 0 | 0 | 0 | 0 | 446772.34 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502492 | SVCD Water - Planned Infra - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-04-24 | 2022-04-13 |  | All West Unitary Authorities | 0 | 0 | 0 | 81775.7 | 563023 | 450110.57 | 207780.92 | 154241.2 | 1456931.39 | 38573.7 | 0 | 0 | 1495505.09 | 0 | 0 | 0 | 0 | 1495505.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502495 | SVCD Water - Planned TWS - Central - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-24 | 2018-09-06 |  | Scottish Water Wide | 0 | 0 | 0 | 28130.84 | 76905.27 | 557.79 | -23087.88 | 0 | 82506.02 | 0 | 0 | 0 | 82506.02 | 0 | 0 | 0 | 0 | 82506.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502496 | SVCD Water - Planned TWS - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-01-31 | 2017-01-31 | 2017-06-22 | 2021-09-30 |  | All East Unitary Authorities | 0 | 0 | 0 | 16355.14 | -367.02 | 4708.48 | 32723.89 | 31445.42 | 84865.91 | 5011.16 | 0 | 0 | 89877.07 | 0 | 0 | 0 | 0 | 89877.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502499 | SVCD Water - Planned TWS - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2017-02-01 | 2017-02-01 | 2017-06-05 | 2021-01-18 |  | All North Unitary Authorities | 0 | 0 | 0 | 13738.32 | 300564.4 | 218564.64 | 92795.77 | 13781.47 | 639444.6 | -3093.96 | 0 | 0 | 636350.64 | 0 | 0 | 0 | 0 | 636350.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502502 | SVCD Water - Planned TWS - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-01 | 2017-02-01 | 2017-06-05 | 2021-11-26 |  | All South Unitary Authorities | 0 | 0 | 0 | 15046.73 | 16335 | 37460 | 51293.38 | 79401.89 | 199537 | 88217.59 | 0 | 0 | 287754.59 | 0 | 0 | 0 | 0 | 287754.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502505 | SVCD Water - Planned TWS - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2017-01-31 | 2017-01-31 | 2017-04-17 | 2020-10-09 |  | All West Unitary Authorities | 0 | 0 | 0 | 16355.14 | 1161.54 | 20369.71 | 0 | -7906.86 | 29979.53 | 0 | 0 | 0 | 29979.53 | 0 | 0 | 0 | 0 | 29979.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502508 | SVCD Water - Planned WPS - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-11-29 |  | All East Unitary Authorities | 0 | 0 | 0 | 8504.67 | 73000 | 107902.44 | 150.11 | 0 | 189557.22 | 0 | 0 | 0 | 189557.22 | 0 | 0 | 0 | 0 | 189557.22 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502511 | SVCD Water - Planned WPS - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2021-01-29 |  | All North Unitary Authorities | 0 | 0 | 0 | 7196.26 | 33135.09 | 96370.82 | 186660.15 | 3878.92 | 327241.24 | 0 | 0 | 0 | 327241.24 | 0 | 0 | 0 | 0 | 327241.24 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502514 | SVCD Water - Planned WPS - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-02-09 | 2017-02-09 | 2017-05-05 | 2018-06-26 |  | All South Unitary Authorities | 0 | 0 | 0 | 7226.53 | 25269.73 | -6290.61 | 0 | 0 | 26205.66 | -0.01 | 0 | 0 | 26205.65 | 0 | 0 | 0 | 0 | 26205.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502517 | SVCD Water - Planned WPS - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-10 | 2017-02-10 | 2017-04-17 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 8504.67 | 28000 | 49037.57 | 23483.47 | 9191.65 | 118217.36 | 487.02 | 0 | 0 | 118704.38 | 0 | 0 | 0 | 0 | 118704.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502520 | SVCD Water - Planned WTW - Central - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-10 | 2017-02-10 | 2017-04-17 | 2018-09-26 |  | Scottish Water Wide | 0 | 0 | 0 | 15046.73 | 1354.33 | 162661.1 | 0 | 0 | 179062.16 | 0 | 0 | 0 | 179062.16 | 0 | 0 | 0 | 0 | 179062.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502522 | SVCD Water - Planned WTW - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-24 | 2017-02-24 | 2017-07-25 | 2021-10-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 54299.07 | 437948.09 | 47984.65 | 205222.26 | -233026.12 | 512427.95 | 20007.36 | 0 | 0 | 532435.31 | 0 | 0 | 0 | 0 | 532435.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502525 | SVCD Water - Planned WTW - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2017-02-14 | 2017-02-14 | 2017-05-25 | 2020-08-11 |  | All North Unitary Authorities | 0 | 0 | 0 | 47222.8 | 298041.76 | 898741.96 | 110707.65 | 33695.77 | 1388409.94 | 130642.27 | 0 | 0 | 1519052.21 | 0 | 0 | 0 | 0 | 1519052.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502528 | SVCD Water - Planned WTW - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-04-03 | 2021-09-24 |  | All South Unitary Authorities | 0 | 0 | 0 | 51155.71 | 390012.09 | 406816.33 | 62861.92 | -1839.56 | 909006.48 | 48105.94 | 0 | 0 | 957112.42 | 0 | 0 | 0 | 0 | 957112.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502531 | SVCD Water - Planned WTW - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-04-24 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 57570.09 | 18500 | 4581.97 | 494.81 | 1631.37 | 82778.24 | -220.76 | 0 | 0 | 82557.48 | 0 | 0 | 0 | 0 | 82557.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502497 | SVCD Water - Responsive TWS - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-01-31 | 2017-01-31 | 2017-05-15 | 2019-04-24 |  | All East Unitary Authorities | 0 | 0 | 0 | 7196.26 | 186881.82 | 368988.77 | 7667.38 | 37.41 | 570771.64 | 0 | 0 | 0 | 570771.64 | 0 | 0 | 0 | 0 | 570771.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502500 | SVCD Water - Responsive TWS - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-01 | 2017-02-01 | 2017-06-05 | 2019-09-06 |  | All North Unitary Authorities | 0 | 0 | 0 | 5887.85 | 67664.62 | 15030.37 | 20397.94 | 0 | 108980.78 | 0 | 0 | 0 | 108980.78 | 0 | 0 | 0 | 0 | 108980.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502503 | SVCD Water - Responsive TWS - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-05-01 | 2018-10-16 |  | All South Unitary Authorities | 0 | 0 | 0 | 6542.06 | 138266 | 132663.48 | 11741.12 | 0 | 289212.66 | 0 | 0 | 0 | 289212.66 | 0 | 0 | 0 | 0 | 289212.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502506 | SVCD Water - Responsive TWS - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2022-04-14 |  | All West Unitary Authorities | 0 | 0 | 0 | 7196.26 | 417547.21 | 3587.25 | 1426.89 | 277.05 | 430034.66 | 249.31 | 0 | 0 | 430283.97 | 0 | 0 | 0 | 0 | 430283.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502509 | SVCD Water - Responsive WPS - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-08-06 |  | All East Unitary Authorities | 0 | 0 | 0 | 3271.03 | 9739.25 | -13009.28 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502512 | SVCD Water - Responsive WPS - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2018-04-19 |  | All North Unitary Authorities | 0 | 0 | 0 | 3271.03 | 144435.23 | -5610.95 | 0 | 0 | 142095.31 | 0 | 0 | 0 | 142095.31 | 0 | 0 | 0 | 0 | 142095.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502515 | SVCD Water - Responsive WPS - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-11-05 |  | All South Unitary Authorities | 0 | 0 | 0 | 3271.03 | 4000 | 7082.19 | 0 | 0 | 14353.22 | 0 | 0 | 0 | 14353.22 | 0 | 0 | 0 | 0 | 14353.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502518 | SVCD Water - Responsive WPS - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-09-28 |  | All West Unitary Authorities | 0 | 0 | 0 | 3271.03 | 66085.96 | 11.47 | 4137.28 | 0 | 73505.73 | 0 | 0 | 0 | 73505.73 | 0 | 0 | 0 | 0 | 73505.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502523 | SVCD Water - Responsive WTW - East - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-06-22 | 2019-01-21 |  | All East Unitary Authorities | 0 | 0 | 0 | 23551.4 | 476577.86 | 30344.87 | -17346.99 | -26015.55 | 487111.59 | 20273.5 | 0 | 0 | 507385.09 | 0 | 0 | 0 | 0 | 507385.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502526 | SVCD Water - Responsive WTW - North - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2019-03-04 |  | All North Unitary Authorities | 0 | 0 | 0 | 20280.37 | 309836.02 | 180527.24 | -7462.75 | 0.08 | 503180.97 | 0 | 0 | 0 | 503180.97 | 0 | 0 | 0 | 0 | 503180.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502529 | SVCD Water - Responsive WTW - South - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-24 | 2020-08-31 |  | All South Unitary Authorities | 0 | 0 | 0 | 21588.79 | 91954 | 93663 | 1975.29 | -40588.15 | 168592.93 | 47748.23 | 0 | 0 | 216341.16 | 0 | 0 | 0 | 0 | 216341.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502532 | SVCD Water - Responsive WTW - West - Managed Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2022-04-14 |  | All West Unitary Authorities | 0 | 0 | 0 | 24859.81 | 251781.66 | 7582.52 | 3870.69 | 20231.24 | 308325.92 | 0 | 0 | 0 | 308325.92 | 0 | 0 | 0 | 0 | 308325.92 | 119022.58 |  |  |  |  | 379189.43 | N | CM_WSNI | 100%
502498 | SVCD Water - TWS - East - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-04-03 | 2020-03-13 |  | All East Unitary Authorities | 0 | 0 | 0 | 30093.46 | 476924.73 | 48640.61 | 4139.61 | 0 | 559798.41 | 0 | 0 | 0 | 559798.41 | 0 | 0 | 0 | 0 | 559798.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502501 | SVCD Water - TWS - North - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-15 | 2017-02-15 | 2017-05-09 | 2018-10-23 |  | All North Unitary Authorities | 0 | 0 | 0 | 25514.02 | 126581.97 | 25889.43 | 0 | 0.01 | 177985.42 | 0 | 0 | 0 | 177985.42 | 0 | 0 | 0 | 0 | 177985.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502504 | SVCD Water - TWS - South - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-11-03 | 2019-07-08 |  | All South Unitary Authorities | 0 | 0 | 0 | 36829.43 | 243343.72 | 125745.07 | 0 | 0 | 405918.22 | 0 | 0 | 0 | 405918.22 | 0 | 0 | 0 | 0 | 405918.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502507 | SVCD Water - TWS - West - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-11-24 | 2019-08-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 31601.87 | 252881.98 | 130734.12 | -74362.7 | 3024.55 | 343879.82 | 0 | 0 | 0 | 343879.82 | 0 | 0 | 0 | 0 | 343879.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502510 | SVCD Water - WPS - East - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-16 | 2017-02-16 | 2017-04-03 | 2020-03-23 |  | All East Unitary Authorities | 0 | 0 | 0 | 17224.93 | 178302.8 | 1938209.68 | 124519.11 | 0 | 2258256.52 | 0 | 0 | 0 | 2258256.52 | 0 | 0 | 0 | 0 | 2258256.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502513 | SVCD Water - WPS - North - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-05-05 | 2018-08-01 |  | All North Unitary Authorities | 0 | 0 | 0 | 21368.42 | 95116.91 | -10926.97 | 0 | 0 | 105558.36 | 0 | 0 | 0 | 105558.36 | 0 | 0 | 0 | 0 | 105558.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502516 | SVCD Water - WPS - South - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-11-17 | 2019-07-08 |  | All South Unitary Authorities | 0 | 0 | 0 | 14392.52 | 26318 | 1365314.36 | 4674.95 | 0 | 1410699.83 | 0 | 0 | 0 | 1410699.83 | 0 | 0 | 0 | 0 | 1410699.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502519 | SVCD Water - WPS - West - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-11-24 | 2020-04-28 |  | All West Unitary Authorities | 0 | 0 | 0 | 15046.73 | 74121.03 | 1260551.48 | -58282.84 | 0 | 1291436.4 | 0 | 0 | 0 | 1291436.4 | 0 | 0 | 0 | 0 | 1291436.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502521 | SVCD Water - WTW - Central - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-11-15 | 2018-08-09 |  | Scottish Water Wide | 0 | 0 | 0 | 17009.35 | 222365.37 | 27709.43 | 0 | 0 | 267084.16 | 0 | 0 | 0 | 267084.16 | 0 | 0 | 0 | 0 | 267084.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502524 | SVCD Water - WTW - East - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-23 | 2017-02-23 | 2017-04-03 | 2020-03-17 |  | All East Unitary Authorities | 0 | 0 | 0 | 126302.07 | 1583071.16 | 528832.93 | 6542.06 | 0 | 2244748.22 | 0 | 0 | 0 | 2244748.22 | 0 | 0 | 0 | 0 | 2244748.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502527 | SVCD Water - WTW - North - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-05-05 | 2019-05-03 |  | All North Unitary Authorities | 0 | 0 | 0 | 121398.58 | 1476037.16 | 564341.53 | 0 | 0 | 2161777.27 | 0 | 0 | 0 | 2161777.27 | 0 | 0 | 0 | 0 | 2161777.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502530 | SVCD Water - WTW - South - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-11-24 | 2020-06-05 |  | All South Unitary Authorities | 0 | 0 | 0 | 149801.52 | 1548484.61 | 768112.99 | 39587.45 | 9.24 | 2505995.8 | 0 | 0 | 0 | 2505995.8 | 0 | 0 | 0 | 0 | 2505995.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502533 | SVCD Water - WTW - West - Scottish Water Delivery - Yr3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-11-24 | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 108598.13 | 1437275.46 | 1632266.81 | -260915.43 | 9977.83 | 2927202.8 | 250937.6 | 0 | 0 | 3178140.4 | 0 | 0 | 0 | 0 | 3178140.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503515 | SVCD WATER CENTRAL (MD) - Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-21 | 2019-03-21 | 2019-04-02 | 2022-04-06 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 29439.25 | 0 | 650.93 | 30090.18 | 0 | 0 | 0 | 30090.18 | 0 | 0 | 0 | 0 | 30090.18 | 668304.54 | [5 empty] | N | CM_WSI | 37.5% | CM_WSNI | 62.5%
503516 | SVCD WATER CENTRAL (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-03-21 | 2019-03-21 | 2019-04-02 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 19626.17 | 188749.11 | 56262.59 | 264637.87 | -21500 | 0 | 0 | 243137.87 | 0 | 0 | 0 | 0 | 243137.87 | 668304.54 | [5 empty] | N | CM_WSI | 37.5% | CM_WSNI | 62.5%
502032 | SVCD Water Central Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-05-23 | 2017-11-22 |  | Scottish Water Wide | 0 | 0 | 0 | 45000 | 0 | -44999 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502033 | SVCD Water Central Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-02-29 | 2018-03-29 |  | Scottish Water Wide | 0 | 0 | 32710.28 | 502748.49 | -334919.11 | -13294.48 | 0 | 0 | 187245.18 | 0 | 0 | 0 | 187245.18 | 0 | 0 | 0 | 0 | 187245.18 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503031 | SVCD WATER CENTRAL PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 | 2022-04-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 98130.84 | 445611.51 | 119007.73 | 418.32 | 663168.4 | 48158.7 | 0 | 0 | 711327.1 | 0 | 0 | 0 | 0 | 711327.1 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
503021 | SVCD WATER CENTRAL RESPONSIVE (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 130841.12 | 894315.38 | 937644.2 | -1452033.21 | 510767.49 | -8137.56 | 0 | 0 | 502629.93 | 0 | 0 | 0 | 0 | 502629.93 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
502138 | SVCD Water Central TWS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2017-03-27 |  | Scottish Water Wide | 0 | 0 | 0 | 67316.24 | -67316.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
502139 | SVCD Water Central WTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-06 | 2016-04-06 | 2016-04-06 | 2018-03-19 |  | Scottish Water Wide | 0 | 0 | 0 | 121710.28 | 101500 | -7255.1 | 0 | 0 | 215955.18 | 0 | 0 | 0 | 215955.18 | 0 | 0 | 0 | 0 | 215955.18 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502140 | SVCD Water Central WTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2018-03-29 |  | Scottish Water Wide | 0 | 0 | 32710.28 | 202735.38 | 7542.04 | -16813.89 | 872.69 | 282.52 | 227329.02 | 0 | 0 | 0 | 227329.02 | 0 | 0 | 0 | 0 | 227329.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503520 | SVCD WATER EAST (MD) Planned -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2019-03-11 | 2019-03-11 | 2019-12-09 | 2021-10-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 23704.55 | 185784.11 | 149906.47 | 359395.13 | -2517.38 | 0 | 0 | 356877.75 | 0 | 0 | 0 | 0 | 356877.75 | 668304.54 | [5 empty] | N | CM_WSI | 25% | CM_WSNI | 75%
503521 | SVCD WATER EAST (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-05-01 | 2021-09-30 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 107512.98 | 1071459.68 | -303646.09 | 875326.57 | 140585.69 | 0 | 0 | 1015912.26 | 0 | 0 | 0 | 0 | 1015912.26 | 668304.54 | [5 empty] | N | CM_WSI | 29.53% | CM_WSNI | 70.47%
503519 | SVCD WATER EAST (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2019-03-13 | 2019-03-13 | 2019-09-02 | 2021-05-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 256947.94 | 4217590.22 | 221926.16 | 4696464.31 | -43182.51 | 0 | 0 | 4653281.8 | 0 | 0 | 0 | 0 | 4653281.8 | 668304.54 | [5 empty] | N | CM_WSI | 32.82% | CM_WSNI | 67.18%
502034 | SVCD Water East Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-22 | 2016-03-22 | 2016-03-31 | 2018-09-21 |  | All East Unitary Authorities | 0 | 0 | 145953.27 | 255999.73 | 32587 | -41812.62 | 0 | 0 | 392727.38 | 0 | 0 | 0 | 392727.38 | 0 | 0 | 0 | 0 | 392727.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502035 | SVCD Water East Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2020-12-01 |  | All East Unitary Authorities | 0 | 0 | 62542.06 | 204859 | 14148 | -47931.31 | 0 | 0 | 233617.75 | 0 | 0 | 0 | 233617.75 | 0 | 0 | 0 | 0 | 233617.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503027 | SVCD WATER EAST PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-01-25 | 2018-01-25 | 2018-01-30 | 2021-09-30 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 141075 | 183536.47 | 338369.81 | 55505.7 | 718486.98 | -24897.54 | 0 | 0 | 693589.44 | 0 | 0 | 0 | 0 | 693589.44 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
503028 | SVCD WATER EAST RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-01-30 | 2018-01-30 | 2018-02-20 | 2021-07-31 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 203521.96 | 203593.12 | 590630.36 | 79574.48 | 1077319.92 | 22648.96 | 0 | 0 | 1099968.88 | 0 | 0 | 0 | 0 | 1099968.88 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
503019 | SVCD WATER EAST RESPONSIVE (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-01-30 | 2018-01-30 | 2018-04-02 | 2021-05-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 337074.17 | 5862329.77 | 815554.69 | 2647.1 | 7017605.73 | 0 | 0 | 0 | 7017605.73 | 0 | 0 | 0 | 0 | 7017605.73 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
502141 | SVCD Water East TWS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-06 | 2016-04-06 | 2016-04-18 | 2017-08-29 |  | All East Unitary Authorities | 0 | 0 | 0 | 269177.57 | 37130.24 | 0 | 0 | 0 | 306307.81 | 0 | 0 | 0 | 306307.81 | 0 | 0 | 0 | 0 | 306307.81 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502142 | SVCD Water East TWS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-30 | 2016-03-30 | 2016-04-08 | 2020-12-01 |  | Scottish Water Wide | 0 | 0 | 0 | 388640.88 | 127289.64 | -34226.25 | 0 | 0 | 481704.27 | 0 | 0 | 0 | 481704.27 | 0 | 0 | 0 | 0 | 481704.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502143 | SVCD Water East WPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2021-09-30 |  | All East Unitary Authorities | 0 | 0 | 0 | 24588.79 | 80000 | 228.88 | 24281.81 | 8173.02 | 137272.49 | -355.72 | 0 | 0 | 136916.77 | 0 | 0 | 0 | 0 | 136916.77 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502144 | SVCD Water East WPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-01 | 2020-12-03 |  | All East Unitary Authorities | 0 | 0 | 0 | 271746.44 | 66372.56 | -32058.85 | 0 | 0 | 306060.15 | 0 | 0 | 0 | 306060.15 | 0 | 0 | 0 | 0 | 306060.15 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502145 | SVCD Water East WTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-04-22 | 2016-04-22 | 2016-04-27 | 2021-10-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 673737.69 | 951148.04 | -241284.5 | 26166.29 | 52929.6 | 1462697.12 | -0.12 | 0 | 0 | 1462697 | 0 | 0 | 0 | 0 | 1462697 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502146 | SVCD Water East WTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-01 | 2020-03-26 |  | All East Unitary Authorities | 0 | 0 | 43766.36 | 1637034.29 | 522640.5 | 61527.13 | 1038.97 | 0 | 2266007.24 | 0 | 0 | 0 | 2266007.24 | 0 | 0 | 0 | 0 | 2266007.24 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503509 | SVCD WATER NORTH (MD) Planned -Yr5 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2019-03-21 | 2019-03-21 | 2019-06-10 | 2022-01-21 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 106670.38 | 1011794.39 | 633011.35 | 1751476.12 | 273005.84 | 0 | 0 | 2024481.96 | 0 | 0 | 0 | 0 | 2024481.96 | 668304.54 | [5 empty] | N | CM_WSNI | 45% | CM_WSI | 55%
503510 | SVCD WATER NORTH (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-20 | 2019-03-20 | 2019-07-05 | 2021-05-01 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 23704.55 | 549663.54 | 56419.91 | 629788 | 518.39 | 0 | 0 | 630306.39 | 0 | 0 | 0 | 0 | 630306.39 | 668304.54 | [5 empty] | N | CM_WSI | 50% | CM_WSNI | 50%
503508 | SVCD WATER NORTH (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-03-26 | 2019-03-26 | 2020-02-06 | 2021-04-01 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 200.37 | 4158752.64 | -101624.48 | 4057328.53 | 0 | 0 | 0 | 4057328.53 | 0 | 0 | 0 | 0 | 4057328.53 | 668304.54 | [5 empty] | N | CM_WSI | 50% | CM_WSNI | 50%
502036 | SVCD Water North Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-22 | 2016-03-22 | 2016-04-08 | 2018-12-11 |  | All North Unitary Authorities | 0 | 0 | 110757.01 | 652461.22 | 1081310.1 | 116422.09 | 2701.79 | 0 | 1963652.21 | 0 | 0 | 0 | 1963652.21 | 0 | 0 | 0 | 0 | 1963652.21 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502037 | SVCD Water North Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-15 | 2017-11-02 |  | All North Unitary Authorities | 0 | 0 | 49720 | 348294.43 | -9814.17 | 0 | 0 | 0 | 388200.26 | 0 | 0 | 0 | 388200.26 | 0 | 0 | 0 | 0 | 388200.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503023 | SVCD WATER NORTH PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-07 | 2018-02-07 | 2018-02-21 | 2021-09-17 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 362716.97 | 3048347.65 | 864972.93 | 123593.54 | 4399631.09 | 53073.78 | 0 | 0 | 4452704.87 | 0 | 0 | 0 | 0 | 4452704.87 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
503024 | SVCD WATER NORTH RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-21 | 2021-06-17 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 70456.69 | 441765.39 | 127498.44 | 83732.48 | 723453 | 581.72 | 0 | 0 | 724034.72 | 0 | 0 | 0 | 0 | 724034.72 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
503017 | SVCD WATER NORTH RESPONSIVE (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2019-09-11 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 252897.2 | 4588934.28 | 344429.01 | 0 | 5186260.49 | 0 | 0 | 0 | 5186260.49 | 0 | 0 | 0 | 0 | 5186260.49 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
502147 | SVCD Water North TWS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-11 | 2016-04-11 | 2016-04-25 | 2018-09-03 |  | All North Unitary Authorities | 0 | 0 | 0 | 209475.38 | 230476.25 | -102975.12 | 0 | 995.32 | 337971.83 | 0 | 0 | 0 | 337971.83 | 0 | 0 | 0 | 0 | 337971.83 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502148 | SVCD Water North TWS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-30 | 2016-03-30 | 2016-04-08 | 2018-07-26 |  | All North Unitary Authorities | 0 | 0 | 15832 | 146168 | 26135.14 | 0 | 0 | 0 | 188135.14 | 0 | 0 | 0 | 188135.14 | 0 | 0 | 0 | 0 | 188135.14 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502149 | SVCD Water North WPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2018-04-19 |  | All North Unitary Authorities | 0 | 0 | 12300 | 1285.71 | 9841.53 | -32.79 | 0 | 0 | 23394.46 | 0 | 0 | 0 | 23394.46 | 0 | 0 | 0 | 0 | 23394.46 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502150 | SVCD Water North WPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-30 | 2016-03-30 | 2016-04-08 | 2017-11-01 |  | All North Unitary Authorities | 0 | 0 | 5299 | 125701 | -3882.42 | 0 | 0 | 41372.5 | 168490.08 | 0 | 0 | 0 | 168490.08 | 0 | 0 | 0 | 0 | 168490.08 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502151 | SVCD Water North WTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-22 | 2016-04-22 | 2016-04-25 | 2018-09-03 |  | All North Unitary Authorities | 0 | 0 | 0 | 218846.77 | 340785.59 | 17515.54 | 0 | -724.88 | 576423.02 | 0 | 0 | 0 | 576423.02 | 0 | 0 | 0 | 0 | 576423.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502152 | SVCD Water North WTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2018-07-26 |  | All North Unitary Authorities | 0 | 0 | 36897.2 | 1392363.33 | 325043.84 | 0 | 0 | 0 | 1754304.37 | 0 | 0 | 0 | 1754304.37 | 0 | 0 | 0 | 0 | 1754304.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503513 | SVCD WATER SOUTH (MD) Planned -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-26 | 2019-03-26 | 2019-06-24 | 2022-05-20 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 35556.79 | 389637.17 | 444915.69 | 870109.65 | 298883.19 | 0 | 0 | 1168992.84 | 0 | 0 | 0 | 0 | 1168992.84 | 668304.54 | [5 empty] | N | CM_WSI | 25% | CM_WSNI | 75%
503514 | SVCD WATER SOUTH (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-26 | 2019-03-26 | 2019-05-01 | 2021-08-31 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 47409.04 | 1135052.11 | 414129.85 | 1596591 | 92145.79 | 0 | 0 | 1688736.79 | 0 | 0 | 0 | 0 | 1688736.79 | 668304.54 | [5 empty] | N | CM_WSI | 40% | CM_WSNI | 60%
503512 | SVCD WATER SOUTH (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-27 | 2019-03-27 | 2020-02-06 | 2021-05-01 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 6596968.96 | -143414.33 | 6453554.63 | 37657.37 | 0 | 0 | 6491212 | 0 | 0 | 0 | 0 | 6491212 | 668304.54 | [5 empty] | N | CM_WSI | 50% | CM_WSNI | 50%
502038 | SVCD Water South Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-22 | 2016-03-22 | 2016-04-08 | 2018-06-26 |  | All South Unitary Authorities | 0 | 0 | 165579.44 | 253284.43 | 2138667.06 | 415059.18 | 12848.88 | 3913.12 | 2989352.11 | 0 | 0 | 0 | 2989352.11 | 0 | 0 | 0 | 0 | 2989352.11 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502039 | SVCD Water South Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-08-24 | 2018-02-01 |  | All South Unitary Authorities | 0 | 0 | 70981.31 | 482034.06 | 54779.44 | 0 | 0 | 0 | 607794.81 | 0 | 0 | 0 | 607794.81 | 0 | 0 | 0 | 0 | 607794.81 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503025 | SVCD WATER SOUTH PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-06 | 2018-02-06 | 2018-02-08 | 2022-05-21 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 140367.72 | 626293.31 | 383617.71 | 101711.26 | 1251990 | 330105.91 | 0 | 0 | 1582095.91 | 0 | 0 | 0 | 0 | 1582095.91 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
503026 | SVCD WATER SOUTH RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-06 | 2018-02-06 | 2018-02-08 | 2021-07-29 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 52336.45 | 834902.36 | 522152.24 | -93343.56 | 1316047.49 | 1058.34 | 0 | 0 | 1317105.83 | 0 | 0 | 0 | 0 | 1317105.83 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
503018 | SVCD WATER SOUTH RESPONSIVE (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 | 2018-02-21 | 2018-02-21 | 2018-02-21 | 2020-12-07 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 413617.36 | 6053747.66 | 554389.94 | 75979.16 | 7097734.12 | -8244.2 | 0 | 0 | 7089489.92 | 0 | 0 | 0 | 0 | 7089489.92 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
502153 | SVCD Water South TWS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2016-04-06 | 2016-04-06 | 2016-04-25 | 2018-09-27 |  | All South Unitary Authorities | 0 | 0 | 0 | 70949.7 | 381751.72 | 109276.17 | 8266.44 | 90238.44 | 660482.47 | 3705.12 | 0 | 0 | 664187.59 | 0 | 0 | 0 | 0 | 664187.59 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502154 | SVCD Water South TWS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-06-08 | 2017-09-08 |  | All South Unitary Authorities | 0 | 0 | 0 | 127167.83 | 56685.77 | 0 | 0 | 0 | 183853.6 | 0 | 0 | 0 | 183853.6 | 0 | 0 | 0 | 0 | 183853.6 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502155 | SVCD Water South WPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2017-11-21 |  | All South Unitary Authorities | 0 | 0 | 0 | 17595.14 | 79419.08 | -8664.8 | 0 | 0 | 88349.43 | 0 | 0 | 0 | 88349.43 | 0 | 0 | 0 | 0 | 88349.43 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502156 | SVCD Water South WPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2017-09-08 |  | All South Unitary Authorities | 0 | 0 | 0 | 53560.59 | 53286.22 | 0 | 0 | 0 | 106846.81 | 0 | 0 | 0 | 106846.81 | 0 | 0 | 0 | 0 | 106846.81 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502157 | SVCD Water South WTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2016-04-22 | 2016-04-22 | 2016-04-25 | 2019-08-08 |  | All South Unitary Authorities | 0 | 0 | 0 | 99583.18 | 107261.47 | 162301.46 | -61007.82 | -250.03 | 307888.26 | 9479.09 | 0 | 0 | 317367.35 | 0 | 0 | 0 | 0 | 317367.35 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502158 | SVCD Water South WTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-11 | 2016-04-11 | 2016-05-09 | 2018-02-01 |  | All South Unitary Authorities | 0 | 0 | 0 | 1077856.28 | 330233.7 | 0 | 0 | 0.01 | 1408089.98 | 0 | 0 | 0 | 1408089.98 | 0 | 0 | 0 | 0 | 1408089.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503535 | SVCD WATER WEST (MD) Planned -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-27 | 2019-03-27 | 2019-04-08 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 174203.92 | 17801.08 | 192005 | 70853.23 | 0 | 0 | 262858.23 | 0 | 0 | 0 | 0 | 262858.23 | 668304.54 | [5 empty] | N | CM_WSI | 30% | CM_WSNI | 70%
503536 | SVCD WATER WEST (MD) Responsive -Yr5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-28 | 2019-03-28 | 2019-05-02 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 1071008.72 | 54231.98 | 1125240.71 | 101182.68 | 0 | 0 | 1226423.39 | 0 | 0 | 0 | 0 | 1226423.39 | 668304.54 | [5 empty] | N | CM_WSI | 50% | CM_WSNI | 50%
503534 | SVCD WATER WEST (SWD) -Yr5 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2019-03-28 | 2019-03-28 | 2020-02-06 | 2021-05-01 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 8182025.18 | -28671.77 | 8153353.41 | 47161.02 | 0 | 0 | 8200514.43 | 0 | 0 | 0 | 0 | 8200514.43 | 668304.54 | [5 empty] | N | CM_WSNI | 40% | CM_WSI | 60%
502048 | SVCD Water West Infra (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-02 | 2016-03-02 | 2016-05-19 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 183439.25 | 281320.18 | 507766.29 | 16550.53 | 331616.99 | 51661.84 | 1372355.08 | 13488.19 | 0 | 0 | 1385843.27 | 0 | 0 | 0 | 0 | 1385843.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502047 | SVCD Water West Infra (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-05-13 | 2019-02-20 |  | All West Unitary Authorities | 0 | 0 | 78635.51 | 60045.48 | 32529.88 | -74136.95 | 0 | 0 | 97073.92 | 0 | 0 | 0 | 97073.92 | 0 | 0 | 0 | 0 | 97073.92 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503029 | SVCD WATER WEST PLANNED (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 213640.19 | 1051143.9 | 687377.74 | 512699.17 | 2464861 | 305183.85 | 0 | 0 | 2770044.85 | 0 | 0 | 0 | 0 | 2770044.85 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
503030 | SVCD WATER WEST RESPONSIVE (MD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 249845.79 | 1106561.68 | 810904.12 | -40528.06 | 2126783.53 | -6777.15 | 0 | 0 | 2120006.38 | 0 | 0 | 0 | 0 | 2120006.38 | 238045.17 |  |  |  |  | 88547 | N | CM_WSNI | 100%
503020 | SVCD WATER WEST RESPONSIVE (SWD) -Yr4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-02-26 | 2018-02-26 | 2018-03-01 | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 219485.98 | 6637546.25 | 602557.11 | 66619.83 | 7526209.17 | 267004.67 | 0 | 0 | 7793213.84 | 0 | 0 | 0 | 0 | 7793213.84 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
502160 | SVCD Water West TWS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-30 | 2016-03-30 | 2016-04-22 | 2022-05-12 |  | All West Unitary Authorities | 0 | 0 | 0 | 138020.41 | 186358.95 | -15285.33 | 37765.06 | -2386.73 | 344472.36 | 168.72 | 0 | 0 | 344641.08 | 0 | 0 | 0 | 0 | 344641.08 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502161 | SVCD Water West TWS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-03-30 | 2016-03-30 | 2016-05-23 | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 105365.81 | 41659.55 | 0 | -4564.24 | 830.97 | 143292.09 | 90389.36 | 0 | 0 | 233681.45 | 0 | 0 | 0 | 0 | 233681.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502162 | SVCD Water West WPS (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2022-04-14 |  | All West Unitary Authorities | 0 | 0 | 0 | 237004.65 | 146493.16 | 49794.97 | 53485.52 | -15302.08 | 471476.22 | 85216.56 | 0 | 0 | 556692.78 | 0 | 0 | 0 | 0 | 556692.78 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502163 | SVCD Water West WPS (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-06 | 2016-04-06 | 2016-06-13 | 2019-06-12 |  | All West Unitary Authorities | 0 | 0 | 0 | 165119.01 | 57968 | 40937.33 | -2353.55 | 0 | 261670.79 | 0 | 0 | 0 | 261670.79 | 0 | 0 | 0 | 0 | 261670.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502164 | SVCD Water West WTW (MD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2022-04-14 |  | All West Unitary Authorities | 0 | 0 | 0 | 319960.53 | 491106 | 20074.58 | -18497.8 | 228018.61 | 1040661.92 | 64303.32 | 0 | 0 | 1104965.24 | 0 | 0 | 0 | 0 | 1104965.24 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502165 | SVCD Water West WTW (SWD) - Yr2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-04-06 | 2016-04-06 | 2016-06-13 | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 624710.98 | 130681.07 | 51154.95 | -21746.03 | 97.44 | 784898.41 | 0.01 | 0 | 0 | 784898.42 | 0 | 0 | 0 | 0 | 784898.42 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402878 | SVCM Brachmont TWP Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-08-31 | 2013-02-11 | 2013-03-04 | 2013-07-23 |  | Aberdeenshire | 142224.8 | 0 | 7729.6 | 0 | 0 | 0 | 0 | 0 | 7729.6 | 0 | 0 | 0 | 149954.4 | 0 | 0 | 0 | 0 | 149954.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402291 | SVCM Domestic Night Use Allowance Study | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-08-29 | 2014-11-03 | 2014-11-03 | 2015-10-30 |  | Scottish Water Wide | 75444.39 | 0 | 12743.6 | 0 | 0 | 0 | 0 | 0 | 12743.6 | 0 | 0 | 0 | 88187.99 | 0 | 0 | 0 | 0 | 88187.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401355 | SVCM Lochmill Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-11-18 | 2011-12-05 | 2015-10-02 | 2012-06-20 | Fife | 32773 | 0 | -2504.75 | 0 | 0 | 0 | 0 | 0 | -2504.75 | 0 | 0 | 0 | 30268.25 | 0 | 0 | 0 | 0 | 30268.25 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400851 | SVCM South Trunk Main Restoration of Cathodic Protection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-05-10 | 2011-10-03 | 2012-01-13 | 2015-08-20 |  | Aberdeenshire | 48958 | 0 | 0 | 0.28 | -206.91 | 0 | 0 | 0 | -206.63 | 0 | 0 | 0 | 48751.37 | 0 | 0 | 0 | 0 | 48751.37 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402458 | SVCM Strategic Network Modelling of Central Belt | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-12-01 | 2012-01-16 | 2012-01-16 | 2017-06-12 |  | Scottish Water Wide | 141733 | 0 | 0 | 0 | -136295.02 | 0 | 0 | 0 | -136295.02 | 0 | 0 | 0 | 5437.98 | 0 | 0 | 0 | 0 | 5437.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500554 | SVCM Water East Infra (MD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-30 | 2015-06-30 | 2015-07-24 | 2018-02-12 |  | All East Unitary Authorities | 0 | 0 | 840292 | 515764.24 | 391710.38 | 0 | 0 | 0 | 1747766.62 | 0 | 0 | 0 | 1747766.62 | 0 | 0 | 0 | 0 | 1747766.62 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500522 | SVCM Water East Infra (SWD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2020-11-30 |  | All East Unitary Authorities | 0 | 0 | 562180 | -93179 | 180067 | -211699.91 | 0 | 0 | 437368.09 | 0 | 0 | 0 | 437368.09 | 0 | 0 | 0 | 0 | 437368.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402677 | SVCW - Chryston (Berryknowes) - Install new pumping station | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-06-07 | 2013-01-18 | 2013-04-23 | 2016-08-08 |  | North Lanarkshire | 70817 | 0 | 336926.18 | 47013.59 | 118.59 | 554.49 | 0 | 0 | 384612.85 | 0 | 0 | 0 | 455429.85 | 0 | 0 | 0 | 0 | 455429.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403258 | SVCW Montrose WwTW Inlet Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-01-14 | 2013-04-18 | 2013-09-10 | 2015-02-10 |  | Moray | 251584.98 | 0 | -584.98 | 0 | -776.74 | 0 | 0 | 0 | -1361.72 | 0 | 0 | 0 | 250223.26 | 0 | 0 | 0 | 0 | 250223.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402693 | SVCW Philip Murry Rd Bellshill - EMERGENCY Sewer repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-06-13 | 2012-09-14 | 2012-11-28 | 2014-01-13 |  | North Lanarkshire | 109228 | 0 | -155.99 | 0 | 0 | 0 | 0 | 0 | -155.99 | 0 | 0 | 0 | 109072.01 | 0 | 0 | 0 | 0 | 109072.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
401867 | SVCW Baddingsgill Reservoir Failed Bridges Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-22 | 2016-06-29 | 2016-07-01 | 2018-02-16 |  | Scottish Borders | 40851 | 0 | 23526 | 16363.87 | -113.38 | 0 | 0 | 0 | 39776.49 | 0 | 0 | 0 | 80627.49 | 0 | 0 | 0 | 0 | 80627.49 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401359 | SVCW Balgillie Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-10 | 2012-10-29 | 2013-02-11 | 2013-08-02 | 2013-08-02 | Fife | 211365 | 0 | -183.73 | 0 | 0 | 0 | 0 | 0 | -183.73 | 0 | 0 | 0 | 211181.27 | 0 | 0 | 0 | 0 | 211181.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401422 | SVCW Belmore WTW - provision of raw water colour - turbidity monitors | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-23 | 2011-06-21 | 2011-05-24 | 2011-07-30 |  | Argyll and Bute-Cowal & Bute | 25106.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25106.47 | 0 | 0 | 0 | 0 | 25106.47 | 0 | [6 empty] | CM_WSNI | 100%
403560 | SVCW Black Esk WTW - CWT Roof Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-08-26 | 2014-01-24 | 2014-02-20 | 2014-09-17 |  | Dumfries and Galloway | 182048 | 0 | 0 | -268.82 | 0 | 0 | 0 | 0 | -268.82 | 0 | 0 | 0 | 181779.18 | 0 | 0 | 0 | 0 | 181779.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402189 | SVCW Blackhills Collection System Final Decommissioning | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-15 | 2017-11-28 | 2017-11-28 | 2017-09-29 |  | Aberdeenshire | 3000 | 0 | 0 | 2962.5 | 3968.51 | 0 | 0 | 0 | 6931.01 | 0 | 0 | 0 | 9931.01 | 0 | 0 | 0 | 0 | 9931.01 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400875 | SVCW Boardhouse WTW Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-20 | 2012-01-12 | 2012-01-30 | 2012-07-16 |  | Orkney Islands | 65294 | 0 | 4255.47 | 0 | 0 | 0 | 0 | 0 | 4255.47 | 0 | 0 | 0 | 69549.47 | 0 | 0 | 0 | 0 | 69549.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402249 | SVCW Braeface Burst Control | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-18 | 2011-12-21 | 2012-01-30 | 2013-12-18 |  | Falkirk | 195235 | 0 | -176.88 | 0 | 0 | 0 | 0 | 0 | -176.88 | 0 | 0 | 0 | 195058.12 | 0 | 0 | 0 | 0 | 195058.12 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403194 | SVCW Broxburn Greendyke Rd External Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-18 | 2013-09-26 | 2013-12-05 | 2014-07-07 |  | West Lothian | 160073 | 0 | 904 | -475.73 | 0 | 0 | 0 | 0 | 428.27 | 0 | 0 | 0 | 160501.27 | 0 | 0 | 0 | 0 | 160501.27 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403783 | SVCW Business Change Stabilisation and Improvement Programme | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-05-07 | 2014-05-07 | 2014-11-17 | 2015-10-30 |  | Scottish Water Wide | 597788 | 0 | -53131.97 | 0 | 0 | 0 | 0 | 0 | -53131.97 | 0 | 0 | 0 | 544656.03 | 0 | 0 | 0 | 0 | 544656.03 | 613322.63 | [5 empty] | N | CM_M&G | 100%
402977 | SVCW Calliness Road SPS Drummore - Replacment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-19 | 2013-04-24 | 2013-12-13 | 2016-04-29 |  | Dumfries and Galloway | 180690 | 0 | 3000 | 108895.97 | 0 | -2394.77 | 0 | 0 | 109501.2 | 0 | 0 | 0 | 290191.2 | 0 | 0 | 0 | 0 | 290191.2 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400976 | SVCW Cameron Reservoir - Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-15 | 2011-06-28 | 2011-10-24 | 2012-12-18 | 2012-12-18 | Fife | 32244 | 0 | 261.71 | 0 | 0 | 0 | 0 | 0 | 261.71 | 0 | 0 | 0 | 32505.71 | 0 | 0 | 0 | 0 | 32505.71 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403049 | SVCW Carmunnock Road Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-05-17 | 2014-02-04 | 2014-02-17 | 2014-08-22 |  | Glasgow City | 257873 | 0 | 401 | -798.67 | 0 | 0 | 0 | 0 | -397.67 | 0 | 0 | 0 | 257475.33 | 0 | 0 | 0 | 0 | 257475.33 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500637 | SVCW Coastguard SPS - Replacement of 7nr Sets of Guide Rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-26 | 2015-06-17 | 2015-09-11 | 2015-10-02 |  | Na H-Eileanan an Iar | 0 | 0 | 195031.16 | 0 | 0 | 0 | 0 | 0 | 195031.16 | 0 | 0 | 0 | 195031.16 | 0 | 0 | 0 | 0 | 195031.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400897 | SVCW Coulter WTW Second Stage Filter Remedials | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-25 | 2012-10-31 | 2012-11-19 | 2015-06-25 |  | South Lanarkshire | 151320 | 0 | 37704.53 | 0 | 0 | 0 | 0 | 0 | 37704.53 | 0 | 0 | 0 | 189024.53 | 0 | 0 | 0 | 0 | 189024.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403892 | SVCW Cowdenbeath Perth Road Sewer Collapse | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-06-30 | 2014-10-23 | 2014-12-19 | 2015-05-04 |  | Fife | 222925 | 0 | -1330 | -0.3 | -237.35 | 0 | 0 | 0 | -1567.65 | 0 | 0 | 0 | 221357.35 | 0 | 0 | 0 | 0 | 221357.35 | 209381.79 | [5 empty] | N | CM_WWI | 100%
401966 | SVCW Craigluscar EW Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-04-01 | 2011-10-25 | 2011-11-21 | 2012-10-22 | 2012-10-22 | Fife | 26953 | 0 | -368.26 | 0 | 0 | 0 | 0 | 0 | -368.26 | 0 | 0 | 0 | 26584.74 | 0 | 0 | 0 | 0 | 26584.74 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403492 | SVCW Deanburn Park Linlithgow Sewer Collapse | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-05-15 | 2013-08-12 | 2013-08-26 | 2014-03-25 |  | West Lothian | 272203 | 0 | 619 | -1246.19 | 0 | 0 | 0 | 0 | -627.19 | 0 | 0 | 0 | 271575.81 | 0 | 0 | 0 | 0 | 271575.81 | 209381.79 | [5 empty] | N | CM_WWI | 100%