403632 | SVCW DI Metering Estate Investment SR15 - ES | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-01-24 | 2016-10-13 | 2016-10-13 | 2016-09-23 |  | Scottish Water Wide | 127094.78 | 0 | 1.22 | 0 | 0 | 0 | 0 | 0 | 1.22 | 0 | 0 | 0 | 127096 | 0 | 0 | 0 | 0 | 127096 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403719 | SVCW DMA Optimisation East | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-04-24 | 2014-05-12 | 2014-05-12 | 2015-10-26 |  | Scottish Water Wide | 100000 | 0 | -4099.41 | 0 | 0 | 0 | 0 | 0 | -4099.41 | 0 | 0 | 0 | 95900.59 | 0 | 0 | 0 | 0 | 95900.59 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403720 | SVCW DMA Optimisation West | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-04-24 | 2014-05-12 | 2014-05-12 | 2015-10-26 |  | Scottish Water Wide | 143000 | 0 | -40405.45 | 0 | 0 | 0 | 0 | 0 | -40405.45 | 0 | 0 | 0 | 102594.55 | 0 | 0 | 0 | 0 | 102594.55 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403083 | SVCW Don Area Emergency Generators | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-11-12 | 2012-11-12 | 2012-12-10 | 2020-03-23 |  | All East Unitary Authorities | 177164.84 | 0 | 0.16 | 0 | 0 | 0 | 65.87 | 0 | 66.03 | 0 | 0 | 0 | 177230.87 | 0 | 0 | 0 | 0 | 177230.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401214 | SVCW Don Cluster 1 Aldroughty Hotspot | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2013-07-28 | 2013-11-28 | 2016-05-20 |  | Aberdeenshire | 42093 | 0 | 142263 | 6182 | 831.14 | -221.88 | 0 | 0 | 149054.27 | 0 | 0 | 0 | 191147.27 | 0 | 0 | 0 | 0 | 191147.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403056 | SVCW Dreghorn Sewer Network EPI Resolution | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-04 | 2016-06-13 | 2016-06-13 | 2016-06-13 |  | North Ayrshire | 30390 | 0 | 9056 | -511.3 | 0 | 0 | 0 | 0 | 8544.7 | 0 | 0 | 0 | 38934.7 | 0 | 0 | 0 | 0 | 38934.7 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402570 | SVCW East Wastewater Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-21 | 2012-02-21 | 2012-04-23 | 2015-04-24 |  | All East Unitary Authorities | 175520 | 0 | -3520 | 0 | -1916.37 | 0 | 0 | 0 | -5436.37 | 0 | 0 | 0 | 170083.63 | 0 | 0 | 0 | 0 | 170083.63 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402569 | SVCW East Wastewater Non-Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-02-21 | 2012-02-21 | 2012-04-09 | 2015-07-14 |  | All East Unitary Authorities | 261995 | 0 | 5 | 0 | -2460.31 | 0 | 0 | 0 | -2455.31 | 0 | 0 | 0 | 259539.69 | 0 | 0 | 0 | 0 | 259539.69 | 90601.29 | [5 empty] | N | CM_WWI | 100%
402562 | SVCW East Water Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-22 | 2012-02-22 | 2012-04-23 | 2015-07-14 |  | All East Unitary Authorities | 345333 | 0 | 7483.79 | 7183.46 | -6875.05 | 0 | 0 | 0 | 7792.2 | 0 | 0 | 0 | 353125.2 | 0 | 0 | 0 | 0 | 353125.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402543 | SVCW East Water Non-Infra - 2012-2013 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-23 | 2016-05-30 |  | All East Unitary Authorities | 1214989 | 0 | -5250.47 | 0 | 0 | 0 | 0 | 0 | -5250.47 | 0 | 0 | 0 | 1209738.53 | 0 | 0 | 0 | 0 | 1209738.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402561 | SVCW East Water Non-Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-23 | 2016-09-26 |  | All East Unitary Authorities | 472428 | 0 | 47865.24 | 18536.06 | 1401.7 | 0 | 0 | 0 | 67803 | 0 | 0 | 0 | 540231 | 0 | 0 | 0 | 0 | 540231 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403508 | SVCW Facilities East Office Review | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-04-29 | 2015-06-22 | 2015-06-22 | 2015-06-18 |  | Scottish Water Wide | 65000 | 0 | -5797 | 0 | 0 | 0 | 0 | 0 | -5797 | 0 | 0 | 0 | 59203 | 0 | 0 | 0 | 0 | 59203 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403509 | SVCW Facilities North Office Inverness Review | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-04-29 | 2015-06-08 | 2015-06-08 | 2015-06-08 |  | Highland | 5000 | 0 | -3837.5 | 0 | 0 | 0 | 0 | 0 | -3837.5 | 0 | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 1162.5 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403173 | SVCW Fort William Ben Nevis Distillery WWPS - Access Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-11-21 | 2017-08-22 | 2017-10-24 | 2018-01-18 |  | Highland | 24971 | 0 | 60 | 12908.06 | 46880.38 | 280 | 0 | 0 | 60128.44 | 0 | 0 | 0 | 85099.44 | 0 | 0 | 0 | 0 | 85099.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402954 | SVCW Gatehouse STW - Surcharging Problem | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-10-19 | 2018-03-23 | 2018-03-23 | 2018-03-23 |  | Dumfries and Galloway | 44238 | 0 | 0 | 1732.15 | 5480.06 | 0 | 0 | 0 | 7212.21 | 0 | 0 | 0 | 51450.21 | 0 | 0 | 0 | 0 | 51450.21 | 90601.29 | [5 empty] | N | CM_WWI | 100%
402639 | SVCW Glasgow Sludge Pumping Mains monitoring equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-03-29 | 2012-03-29 | 2012-10-10 | 2019-08-06 |  | Glasgow City | 35000 | 0 | 0 | -3132.34 | -641.24 | 0 | 0 | 0 | -3773.58 | 0 | 0 | 0 | 31226.42 | 0 | 0 | 0 | 0 | 31226.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401358 | SVCW Glendevon Upper Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-10 | 2012-11-30 | 2013-01-09 | 2014-04-17 | 2014-04-07 | Perth and Kinross | 99055 | 0 | -1558 | 174.82 | 0 | 0 | 0 | 0 | -1383.18 | 0 | 0 | 0 | 97671.82 | 0 | 0 | 0 | 0 | 97671.82 | 119022.58 | [5 empty] | N | CM_WSI | 100%
402504 | SVCW Glenfarg (East) Reservoir - valve refurbishment and safety work | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-02 | 2013-12-17 | 2014-02-24 | 2014-08-15 | 2014-05-01 | Perth and Kinross | 28574 | 0 | -4127.67 | 0 | 0 | 0 | 0 | 0 | -4127.67 | 0 | 0 | 0 | 24446.33 | 0 | 0 | 0 | 0 | 24446.33 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401360 | SVCW Glenogil Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-10 | 2012-02-17 | 2012-08-27 | 2013-07-11 | 2013-07-11 | Angus | 65091.92 | 0 | 3392.39 | 0 | 0 | 0 | 0 | 0 | 3392.39 | 0 | 0 | 0 | 68484.31 | 0 | 0 | 0 | 0 | 68484.31 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401363 | SVCW Glensherup Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-10 | 2013-05-28 | 2013-08-08 | 2014-10-10 | 2014-12-10 | Perth and Kinross | 155192 | 0 | -913 | -259.51 | 0 | 0 | 0 | 0 | -1172.51 | 0 | 0 | 0 | 154019.49 | 0 | 0 | 0 | 0 | 154019.49 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402699 | SVCW Gonfirth WSZ Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-07-23 | 2014-05-16 | 2014-07-01 | 2014-12-17 |  | Shetland Islands | 28303 | 0 | -20043.02 | 0 | 0 | 0 | 0 | 0 | -20043.02 | 0 | 0 | 0 | 8259.98 | 0 | 0 | 0 | 0 | 8259.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401986 | SVCW Gowanbank SR Flowmeter Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-23 | 2012-02-23 | 2012-04-23 | 2015-01-12 |  | Falkirk | 65817 | 0 | -10228.77 | 0 | 0 | 0 | 0 | 0 | -10228.77 | 0 | 0 | 0 | 55588.23 | 0 | 0 | 0 | 0 | 55588.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403740 | SVCW Grantown WWTW - Temporary SAF Plant - ASP Selector zone | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-26 | 2014-03-11 | 2014-03-11 | 2015-01-13 |  | Highland | 82655.27 | 0 | 71.69 | 0 | 0 | 0 | 0 | 0 | 71.69 | 0 | 0 | 0 | 82726.96 | 0 | 0 | 0 | 0 | 82726.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402163 | SVCW Head of Works STC Lime Dust Extraction System | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-08-01 | 2012-07-31 | 2012-11-12 | 2015-03-25 |  | Orkney Islands | 143701 | 0 | -7018.14 | 0 | 0 | 0 | 0 | 0 | -7018.14 | 0 | 0 | 0 | 136682.86 | 0 | 0 | 0 | 0 | 136682.86 | 209381.79 | [5 empty] | N | CM_M&G | 100%
403073 | SVCW HL Central Water Infra SWD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-11-07 | 2012-11-07 | 2013-01-04 | 2017-03-17 |  | Scottish Water Wide | 532500 | 0 | 17500 | -100492.18 | -2451.02 | 0 | 0 | 0 | -85443.2 | 0 | 0 | 0 | 447056.8 | 0 | 0 | 0 | 0 | 447056.8 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403072 | SVCW HL Central Water Non-Infra SWD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-11-07 | 2012-11-07 | 2013-01-04 | 2016-12-07 |  | Scottish Water Wide | 581099 | 0 | 618901 | -144867.18 | -3263 | 0 | 0 | 0 | 470770.82 | 3263 | 0 | 0 | 1055132.82 | 0 | 0 | 0 | 0 | 1055132.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403364 | SVCW HL East Wastewater Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2016-06-17 |  | All East Unitary Authorities | 250000 | 0 | -10000 | -41888.96 | 0 | 0 | 0 | 0 | -51888.96 | 0 | 0 | 0 | 198111.04 | 0 | 0 | 0 | 0 | 198111.04 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403366 | SVCW HL East Wastewater Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-30 | 2016-02-01 |  | All East Unitary Authorities | 23510 | 0 | 51146.37 | 2398.26 | -1518.57 | 0 | 0 | 0 | 52026.06 | 0 | 0 | 0 | 75536.06 | 0 | 0 | 0 | 0 | 75536.06 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403365 | SVCW HL East Wastewater Non-Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2016-08-01 |  | All East Unitary Authorities | 6000000 | 0 | -436606 | -153872.78 | -3441 | 0 | 0 | 0 | -593919.78 | 0 | 0 | 0 | 5406080.22 | 0 | 0 | 0 | 0 | 5406080.22 | 90601.29 | [5 empty] | N | CM_WWI | 100%
403367 | SVCW HL East Wastewater Non-Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-30 | 2016-01-05 |  | All East Unitary Authorities | 151539 | 0 | 92090 | -17848 | -973.95 | 0 | 0 | 0 | 73268.05 | 0 | 0 | 0 | 224807.05 | 0 | 0 | 0 | 0 | 224807.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403384 | SVCW HL East Water Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-25 | 2013-02-25 | 2013-03-01 | 2016-06-29 |  | All East Unitary Authorities | 1047033 | 0 | 194319 | -103308.95 | 0 | 0 | 0 | 0 | 91010.05 | -8547.35 | 0 | 0 | 1129495.7 | 0 | 0 | 0 | 0 | 1129495.7 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403386 | SVCW HL East Water Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-08 | 2016-12-20 |  | All East Unitary Authorities | 628606 | 0 | 270671 | -142822.88 | -10514.7 | 0 | 0 | 0 | 117333.42 | -11611.5 | 0 | 0 | 734327.92 | 0 | 0 | 0 | 0 | 734327.92 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403385 | SVCW HL East Water Non-Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-02-25 | 2013-02-25 | 2013-03-01 | 2018-08-14 |  | All East Unitary Authorities | 2899130 | 0 | 231703.85 | 17163 | -5626.81 | 0 | 0 | 0 | 243240.04 | 0 | 0 | 0 | 3142370.04 | 0 | 0 | 0 | 0 | 3142370.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403387 | SVCW HL East Water Non-Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-30 | 2017-01-23 |  | All East Unitary Authorities | 1169471 | 0 | 217035 | -38245.73 | 354.86 | 140.3 | -8.22 | 0.01 | 179276.21 | 0 | 0 | 0 | 1348747.21 | 0 | 0 | 0 | 0 | 1348747.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403370 | SVCW HL North Wastewater Non-Infra (Treatment) 2013-2014 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-04-12 | 2015-01-06 |  | All North Unitary Authorities | 1436032.84 | 0 | -1151.65 | 0 | 0 | 0 | 0 | 0 | -1151.65 | 0 | 0 | 0 | 1434881.19 | 0 | 0 | 0 | 0 | 1434881.19 | 90601.29 | [5 empty] | N | CM_WWI | 100%
403388 | SVCW HL North Water Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-15 | 2013-02-15 | 2013-03-29 | 2015-08-19 |  | All North Unitary Authorities | 530000 | 0 | 121604.76 | 0 | 0 | 0 | 0 | 0 | 121604.76 | 0 | 0 | 0 | 651604.76 | 0 | 0 | 0 | 0 | 651604.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403390 | SVCW HL North Water Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-08 | 2015-12-15 |  | All North Unitary Authorities | 1054647 | 0 | 162833.39 | 1638.05 | -5140.5 | 0 | 0 | 0 | 159330.94 | 0 | 0 | 0 | 1213977.94 | 0 | 0 | 0 | 0 | 1213977.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403391 | SVCW HL North Water Non-Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-08 | 2015-12-15 |  | All North Unitary Authorities | 1239176 | 0 | 365485.68 | 0 | 0 | 0 | 0 | 0 | 365485.68 | 0 | 0 | 0 | 1604661.68 | 0 | 0 | 0 | 0 | 1604661.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403372 | SVCW HL South Wastewater Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2015-09-01 |  | All South Unitary Authorities | 300000 | 0 | 126662.21 | 0 | 0 | 0 | 0 | 0 | 126662.21 | 0 | 0 | 0 | 426662.21 | 0 | 0 | 0 | 0 | 426662.21 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403374 | SVCW HL South Wastewater Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2017-03-01 |  | All South Unitary Authorities | 238883 | 0 | 214057 | -85874.38 | 13231.27 | 0 | 0 | 0 | 141413.89 | 0 | 0 | 0 | 380296.89 | 0 | 0 | 0 | 0 | 380296.89 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403373 | SVCW HL South Wastewater Non-Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-01 | 2016-05-30 |  | All South Unitary Authorities | 4571700 | 0 | 481915.02 | 60 | 0 | 0 | 0 | 0 | 481975.02 | 0 | 0 | 0 | 5053675.02 | 0 | 0 | 0 | 0 | 5053675.02 | 90601.29 | [5 empty] | N | CM_WWI | 100%
403392 | SVCW HL South Water Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-15 | 2013-02-15 | 2013-03-29 | 2015-09-10 |  | All South Unitary Authorities | 1408805.24 | 0 | -36530.38 | 0 | 0 | 0 | 0 | 0 | -36530.38 | 0 | 0 | 0 | 1372274.86 | 0 | 0 | 0 | 0 | 1372274.86 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403394 | SVCW HL South Water Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-08 | 2015-11-27 |  | All South Unitary Authorities | 44268 | 0 | 532 | -1228.4 | 17.68 | 0 | 0 | 0 | -678.72 | 0 | 0 | 0 | 43589.28 | 0 | 0 | 0 | 0 | 43589.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403393 | SVCW HL South Water Non-Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-02-21 | 2013-02-21 | 2013-03-29 | 2015-10-08 |  | All South Unitary Authorities | 2800000 | 0 | -73845.04 | 0 | 0 | 0 | 0 | 0 | -73845.04 | 0 | 0 | 0 | 2726154.96 | 0 | 0 | 0 | 0 | 2726154.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403377 | SVCW HL West Wastewater Infra 2013-2015 CID | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-20 | 2013-02-20 | 2013-03-01 | 2016-06-30 |  | All West Unitary Authorities | 1088995.75 | 0 | 257342.25 | 871.4 | 0 | 0 | 0 | 0 | 258213.65 | 0 | 0 | 0 | 1347209.4 | 0 | 0 | 0 | 0 | 1347209.4 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403396 | SVCW HL West Water Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-29 | 2016-05-30 |  | All West Unitary Authorities | 275000 | 0 | 49000 | -74700.09 | 0 | 0 | 0 | 0 | -25700.09 | 0 | 0 | 0 | 249299.91 | 0 | 0 | 0 | 0 | 249299.91 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403398 | SVCW HL West Water Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2013-03-05 | 2013-03-05 | 2013-04-08 | 2022-06-08 |  | All West Unitary Authorities | 890559 | 0 | 72519 | 0.09 | -28901.37 | 0 | 41.33 | 0.01 | 43659.05 | 0 | 0 | 0 | 934218.05 | 0 | 0 | 0 | 0 | 934218.05 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403397 | SVCW HL West Water Non-Infra - 2013-2015 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-05-01 | 2016-05-31 |  | All West Unitary Authorities | 1320165.79 | 0 | 489483.22 | 110.85 | 0 | 0 | 0 | 0 | 489594.07 | 0 | 0 | 0 | 1809759.86 | 0 | 0 | 0 | 0 | 1809759.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403399 | SVCW HL West Water Non-Infra - 2013-2015 - CID | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-15 | 2020-09-30 |  | All West Unitary Authorities | 1096526 | 0 | 655561 | -183354.22 | 51430 | 500 | -341685.78 | -18926.34 | 163524.66 | 0 | 0 | 0 | 1260050.66 | 0 | 0 | 0 | 0 | 1260050.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403160 | SVCW Inverness WTW Acid Room Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-11-20 | 2015-01-29 | 2015-08-24 | 2017-06-21 |  | Highland | 151032 | 0 | 1041321 | 102666.21 | 14074.1 | 3754 | 0 | 0 | 1161815.31 | 0 | 0 | 0 | 1312847.31 | 0 | 0 | 0 | 0 | 1312847.31 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
403188 | SVCW Jerusalem Hotspot | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-14 | 2013-10-31 | 2014-02-17 | 2014-06-17 |  | Midlothian | 159355 | 0 | 1072 | -1826.11 | 0 | 0 | 0 | 0 | -754.11 | 0 | 0 | 0 | 158600.89 | 0 | 0 | 0 | 0 | 158600.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402169 | SVCW Kingoldrum Low Pressure Alleviation Scheme | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-09-26 | 2012-09-28 | 2012-11-26 | 2013-11-19 | 2013-11-28 | Angus | 127509 | 0 | -1774.82 | 0 | 0 | 0 | 0 | 0 | -1774.82 | 0 | 0 | 0 | 125734.18 | 0 | 0 | 0 | 0 | 125734.18 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403178 | SVCW Kingsknowe Crescent - External Sewer Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-10 | 2013-07-01 | 2013-07-01 | 2014-07-07 |  | City of Edinburgh | 529369 | 0 | 665 | -2226.34 | 0 | 0 | 0 | 0 | -1561.34 | 0 | 0 | 0 | 527807.66 | 0 | 0 | 0 | 0 | 527807.66 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403530 | SVCW Kishorn Sewer Diversion - SWS1 Legacy land issue | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-07-26 | 2016-07-20 | 2017-10-19 | 2018-02-05 |  | Highland | 7185.63 | 0 | 7174.37 | 7979.31 | 7215.46 | 175.44 | 0 | 0 | 22544.58 | 0 | 0 | 0 | 29730.21 | 0 | 0 | 0 | 0 | 29730.21 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402765 | SVCW Kyle WTW - Abstraction and Land Legacy Issues | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-07-05 | 2013-10-16 | 2013-11-29 | 2017-05-04 |  | Highland | 91999 | 0 | 0 | 23001 | -82340.3 | 0 | 0 | 0 | -59339.3 | 0 | 0 | 0 | 32659.7 | 0 | 0 | 0 | 0 | 32659.7 | 119022.58 | [5 empty] | N | CM_WSI | 100%
403123 | SVCW Kype Reservoir Spillway repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-11-06 | 2015-08-27 | 2015-09-18 | 2016-05-17 |  | South Lanarkshire | 107413.31 | 0 | 78968.69 | -0.42 | -254.11 | 0 | 0 | 0 | 78714.16 | 0 | 0 | 0 | 186127.47 | 0 | 0 | 0 | 0 | 186127.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402636 | SVCW Leggate SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2012-04-23 | 2018-03-27 | 2018-04-25 | 2019-07-22 |  | South Ayrshire | 98320.44 | 0 | 15179.56 | 96660 | 175889.77 | 655226.23 | 47147 | 4710 | 994812.56 | 0 | 0 | 0 | 1093133 | 0 | 0 | 0 | 0 | 1093133 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401474 | SVCW Levenwick Water Pumping Station Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-11-25 | 2011-12-09 | 2011-12-12 | 2015-07-23 |  | Shetland Islands | 148835 | 0 | -3828 | -3178.34 | -288.15 | 0 | 0 | 0 | -7294.49 | 0 | 0 | 0 | 141540.51 | 0 | 0 | 0 | 0 | 141540.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402344 | SVCW Lintrathen - Clatto 40inch Raw Water Main Rehabilitation works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-09-07 | 2014-10-20 | 2014-10-20 | 2014-10-20 |  | Angus | 25393.08 | 0 | 0 | 161.4 | 40.43 | 0 | 0 | 0 | 201.83 | 0 | 0 | 0 | 25594.91 | 0 | 0 | 0 | 0 | 25594.91 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401356 | SVCW Loch Glow Reservoir Interest of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-08-19 | 2011-11-29 | 2015-10-02 | 2012-09-21 | Fife | 34940.52 | 0 | -97.06 | 0 | 0 | 0 | 0 | 0 | -97.06 | 0 | 0 | 0 | 34843.46 | 0 | 0 | 0 | 0 | 34843.46 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400971 | SVCW Loch Romach - Pitching Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-15 | 2011-06-28 | 2011-09-26 | 2013-07-15 | 2013-07-15 | Aberdeenshire | 40653 | 0 | -493.88 | 0 | 0 | 0 | 0 | 0 | -493.88 | 0 | 0 | 0 | 40159.12 | 0 | 0 | 0 | 0 | 40159.12 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403551 | SVCW Loch Whinyeon MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-09-11 | 2014-07-09 | 2014-08-19 | 2015-02-27 | 2015-02-27 | Scottish Water Wide | 103149 | 0 | 0 | -637.99 | 0 | 0 | 0 | 0 | -637.99 | 0 | 0 | 0 | 102511.01 | 0 | 0 | 0 | 0 | 102511.01 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403599 | SVCW Lochgilphead A&BC Former Hospital Site Surface Water Removal | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-10-23 | 2013-11-22 | 2014-02-25 | 2015-08-07 |  | Argyll and Bute-North Argyll | 25372 | 0 | 174802.58 | 757.38 | 0 | 0 | 0 | 0 | 175559.96 | 0 | 0 | 0 | 200931.96 | 0 | 0 | 0 | 0 | 200931.96 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403608 | SVCW Lochmaddy - DOA Sewer Works | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-10-22 | 2013-11-22 | 2013-11-28 | 2015-02-02 |  | Na H-Eileanan an Iar | 83920.69 | 0 | 13517.31 | 0 | 0 | 0 | 0 | 0 | 13517.31 | 0 | 0 | 0 | 97438 | 0 | 0 | 0 | 0 | 97438 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402465 | SVCW Lochnaw Reservoir - Interests of Safety Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-11-23 | 2013-07-18 | 2013-08-12 | 2015-03-24 | 2015-03-24 | Dumfries and Galloway | 161203 | 0 | 51172.04 | 0 | 0 | 0 | 0 | 0 | 51172.04 | 0 | 0 | 0 | 212375.04 | 0 | 0 | 0 | 0 | 212375.04 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402729 | SVCW Lochwinnoch WwTW Inlet and Storm Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-06-07 | 2013-10-21 | 2014-03-28 | 2015-01-14 |  | Renfrewshire | 288005 | 0 | 8891.39 | 0 | 0 | 0 | 0 | 0 | 8891.39 | 0 | 0 | 0 | 296896.39 | 0 | 0 | 0 | 0 | 296896.39 | 90601.29 | [5 empty] | N | CM_WWI | 100%
401310 | SVCW Lower Glendevon Reservoir - Valve Tower | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-07-15 | 2012-01-13 | 2015-10-02 | 2013-03-15 | Perth and Kinross | 190986 | 0 | -466.83 | 0 | 0 | 0 | 0 | 0 | -466.83 | 0 | 0 | 0 | 190519.17 | 0 | 0 | 0 | 0 | 190519.17 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402953 | SVCW Lumphinans Farm - Sewer Rehabilitation-Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-13 | 2016-12-13 |  | Fife | 2337.89 | 0 | 18604.11 | 36613.29 | 0 | 0 | 0 | 0 | 55217.4 | 0 | 0 | 0 | 57555.29 | 0 | 0 | 0 | 0 | 57555.29 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402696 | SVCW Mains Hotspot - Carnock Fife | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-19 | 2012-11-30 | 2012-12-10 | 2013-09-01 |  | Fife | 86331.34 | 0 | 366.03 | 0 | 0 | 0 | 0 | 0 | 366.03 | 0 | 0 | 0 | 86697.37 | 0 | 0 | 0 | 0 | 86697.37 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46668 | SVCW Mains Rehab - WSZ000107 Badentinan CWT Findlay Road Birnie Place | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-30 | 2012-11-14 | 2012-12-03 | 2013-04-12 |  | Aberdeenshire | 110871 | 0 | -437.57 | 0 | 0 | 0 | 0 | 0 | -437.57 | 0 | 0 | 0 | 110433.43 | 0 | 0 | 0 | 0 | 110433.43 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46665 | SVCW Mains Rehab - WSZ000812 Huntershill Balmanno Cottages | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-06 | 2009-03-06 | 2012-09-26 | 2014-07-17 |  | Angus | 61984 | 0 | 73 | -272 | 0 | 0 | 0 | 0 | -199 | 0 | 0 | 0 | 61785 | 0 | 0 | 0 | 0 | 61785 | 311236.79 | [5 empty] | N | CM_WSI | 100%
46666 | SVCW Mains Rehab - WSZ000812 Huntershill North Lodge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-06 | 2009-03-06 | 2012-10-08 | 2013-05-13 |  | Angus | 156842 | 0 | -797.97 | 0 | 0 | 0 | 0 | 0 | -797.97 | 0 | 0 | 0 | 156044.03 | 0 | 0 | 0 | 0 | 156044.03 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402587 | SVCW Milngavie - Security Fence Removal | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-03-23 | 2012-09-25 | 2012-11-12 | 2013-03-05 |  | East Dunbartonshire | 233172.08 | 0 | -31.72 | 0 | 0 | 0 | 0 | 0 | -31.72 | 0 | 0 | 0 | 233140.36 | 0 | 0 | 0 | 0 | 233140.36 | 119022.58 | [5 empty] | N | CM_WSI | 100%
403282 | SVCW Neilston Low DMA Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-18 | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | East Renfrewshire | 35958 | 0 | -1908.81 | 0 | 0 | 0 | 0 | 0 | -1908.81 | 0 | 0 | 0 | 34049.19 | 0 | 0 | 0 | 0 | 34049.19 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402009 | SVCW Newmore Raw Water Main Embankment Failure | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-03-21 | 2013-11-18 | 2013-12-02 | 2014-07-07 |  | Highland | 113585.03 | 0 | -257.76 | 0 | 0 | 0 | 0 | 0 | -257.76 | 0 | 0 | 0 | 113327.27 | 0 | 0 | 0 | 0 | 113327.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403443 | SVCW North - Wastewater Non-Infra (Treatment) - 2014-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-05-16 | 2013-05-16 | 2014-04-04 | 2016-01-13 |  | All North Unitary Authorities | 1830750 | 0 | 224248.71 | 0 | 0 | 0 | 0 | 0 | 224248.71 | 0 | 0 | 0 | 2054998.71 | 0 | 0 | 0 | 0 | 2054998.71 | 90601.29 |  |  |  |  | 105104 | N | CM_WWI | 100%
403441 | SVCW North - Wastewater Infra - 2014-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2016-01-13 |  | All North Unitary Authorities | 527800 | 0 | 41660.88 | 0 | 0 | 0 | 0 | 0 | 41660.88 | 0 | 0 | 0 | 569460.88 | 0 | 0 | 0 | 0 | 569460.88 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403442 | SVCW North - Wastewater Non-Infra (SPS & Network Structures) - 2014-2015 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-05-13 | 2013-05-13 | 2013-05-13 | 2016-01-13 |  | All North Unitary Authorities | 1052185 | 0 | 176625.31 | 0 | 0 | 0 | 0 | 0 | 176625.31 | 0 | 0 | 0 | 1228810.31 | 0 | 0 | 0 | 0 | 1228810.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401299 | SVCW North Hoy WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-08-19 | 2012-08-03 | 2013-05-20 | 2015-03-02 |  | Orkney Islands | 52102 | 0 | -2815.54 | 0 | 0 | 0 | 0 | 0 | -2815.54 | 0 | 0 | 0 | 49286.46 | 0 | 0 | 0 | 0 | 49286.46 | 119022.58 |  |  |  |  | 50000 | N | CM_WSNI | 100%
402584 | SVCW North Water Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-03-09 | 2012-03-09 | 2012-04-23 | 2015-03-10 |  | All North Unitary Authorities | 814970 | 0 | 927.5 | 0 | 0 | 0 | 0 | 0 | 927.5 | 0 | 0 | 0 | 815897.5 | 0 | 0 | 0 | 0 | 815897.5 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403308 | SVCW NT SCADA Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-02-25 | 2014-11-14 | 2015-01-16 | 2017-10-27 |  | All East Unitary Authorities | 83558 | 0 | 80721 | 22504 | -19283 | 0 | -832.2 | 0 | 83109.8 | 0 | 0 | 0 | 166667.8 | 0 | 0 | 0 | 0 | 166667.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500581 | SVCW Reservoir Maintenance 15-16 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-10 | 2022-04-14 |  | Scottish Water Wide | 0 | 0 | 1514816 | 2059139.23 | 3051188.96 | -367633.44 | -531879.85 | 10957.92 | 5736588.82 | 0 | 0 | 0 | 5736588.82 | 0 | 0 | 0 | 0 | 5736588.82 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500646 | SVCW Reservoir Maintenance 15-16 SWD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-05-18 | 2015-05-18 | 2015-05-18 | 2018-05-30 |  | Scottish Water Wide | 0 | 0 | 359243.03 | 761822.98 | 251719.77 | 92152.18 | -1322.86 | 0 | 1463615.1 | 0 | 0 | 0 | 1463615.1 | 0 | 0 | 0 | 0 | 1463615.1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402555 | SVCW Reservoir Maintenance 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-23 | 2017-06-28 |  | Scottish Water Wide | 3200167 | 0 | 216805 | 251042.99 | 34654.78 | 0 | 0 | 0 | 502502.77 | 0 | 0 | 0 | 3702669.77 | 0 | 0 | 0 | 0 | 3702669.77 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402541 | SVCW Reservoir Maintenance 2012-2015 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-02-13 | 2012-02-13 | 2012-02-13 | 2018-07-19 |  | Scottish Water Wide | 1065234.29 | 0 | 208099.25 | 46881.4 | 10207.67 | 0 | 0 | 0 | 265188.32 | 0 | 0 | 0 | 1330422.61 | 0 | 0 | 0 | 0 | 1330422.61 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400977 | SVCW Roscobie Reservoir - Emergency Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-05-30 | 2011-08-08 | 2012-08-01 | 2012-08-01 | Fife | 58732.06 | 0 | -531.94 | 0 | 0 | 0 | 0 | 0 | -531.94 | 0 | 0 | 0 | 58200.12 | 0 | 0 | 0 | 0 | 58200.12 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403500 | SVCW Sewers & Water for Scotland 3rd Ed - WRc Support | Q&S4 | Supporting economic development | Strategic Capacity |  |  | General |  | SWD | Strategic Capacity | MS7 | 2013-07-03 | 2013-07-03 | 2013-08-01 | 2016-01-13 | 2016-02-11 | Scottish Water Wide | 118256.02 | 0 | 3050 | 0 | 0 | 0 | 0 | 0 | 3050 | 0 | 0 | 0 | 121306.02 | 0 | 0 | 0 | 0 | 121306.02 | 0 | [5 empty] | N | SG1 | 50% | WG1 | 50%
403053 | SVCW South Park Avenue Barrhead - Lift and Relay Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-15 | 2014-09-30 | 2014-10-06 | 2015-02-24 |  | Renfrewshire | 906306 | 0 | -38847.82 | 0 | 0 | 0 | 0 | 0 | -38847.82 | 0 | 0 | 0 | 867458.18 | 0 | 0 | 0 | 0 | 867458.18 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402560 | SVCW South Wastewater Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-21 | 2012-02-21 | 2012-03-01 | 2015-03-10 |  | All South Unitary Authorities | 1066868.46 | 0 | 84.38 | 0 | 0 | 0 | 0 | 0 | 84.38 | 0 | 0 | 0 | 1066952.84 | 0 | 0 | 0 | 0 | 1066952.84 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402553 | SVCW South Water Non-Infra - 2012-2013 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-02-15 | 2012-02-15 | 2012-04-02 | 2013-12-16 |  | All South Unitary Authorities | 1189244.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1189244.93 | 0 | 0 | 0 | 0 | 1189244.93 | 0 | [6 empty] | CM_WSNI | 100%
402558 | SVCW South Water Non-Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-22 | 2012-02-22 | 2012-04-23 | 2015-11-04 |  | All South Unitary Authorities | 157706.3 | 0 | 1529.42 | 0 | 0 | 0 | 0 | 0 | 1529.42 | 0 | 0 | 0 | 159235.72 | 0 | 0 | 0 | 0 | 159235.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402435 | SVCW SP East Water Infra 2011-12 - CID | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-10-31 | 2011-10-31 | 2011-11-07 | 2014-12-18 |  | All East Unitary Authorities | 257031 | 0 | 1500 | -1246.83 | 0 | 0 | 0 | 0 | 253.17 | 0 | 0 | 0 | 257284.17 | 0 | 0 | 0 | 0 | 257284.17 | 622473.57 | [5 empty] | N | CM_WSI | 50% | CM_WWI | 50%
402432 | SVCW SP East Water Non-Infra 2011-12 - CID | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-10-31 | 2011-10-31 | 2011-11-07 | 2015-04-02 |  | All East Unitary Authorities | 85089 | 0 | 4400.45 | 0 | 0 | 0 | 0 | 0 | 4400.45 | 0 | 0 | 0 | 89489.45 | 0 | 0 | 0 | 0 | 89489.45 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
402400 | SVCW SP South Water Non-Infra 2011-12 - CID | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-11-16 | 2011-11-16 | 2011-12-07 | 2015-12-11 |  | All South Unitary Authorities | 178187 | 0 | -9957.11 | 0 | 0 | 0 | 0 | 0 | -9957.11 | 0 | 0 | 0 | 168229.89 | 0 | 0 | 0 | 0 | 168229.89 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
401115 | SVCW SP West Water Non-Infra 2010-12 SWD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-07-01 | 2010-07-01 | 2011-04-29 | 2012-10-03 |  | All West Unitary Authorities | 446434.74 | 0 | 0 | 0 | 41.59 | 0 | 0 | 0 | 41.59 | 0 | 0 | 0 | 446476.33 | 0 | 0 | 0 | 0 | 446476.33 | 119022.58 | [5 empty] | N | CM_WSI | 100%
402268 | SVCW SPS000923 - Blaikies Quay WWPS Replacement Covers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-10-25 | 2012-02-23 | 2012-07-31 | 2012-11-29 |  | Aberdeen City | 125845 | 0 | -1549.47 | 0 | 0 | 0 | 0 | 0 | -1549.47 | 0 | 0 | 0 | 124295.53 | 0 | 0 | 0 | 0 | 124295.53 | 209381.79 | [5 empty] | N | CM_M&G | 100%
403153 | SVCW Stornoway WOA - Point WSZ Braighe AC Main Replacment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-15 | 2013-09-19 | 2014-04-04 | 2015-06-25 |  | Na H-Eileanan an Iar | 220541 | 0 | 31727.61 | 0 | 0 | 0 | 0 | 0 | 31727.61 | 0 | 0 | 0 | 252268.61 | 0 | 0 | 0 | 0 | 252268.61 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402106 | SVCW Stronsay WOA Water Mains Renewals | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-05-18 | 2013-01-26 | 2013-02-25 | 2014-11-24 |  | Orkney Islands | 63535 | 0 | -508.25 | 0 | 0 | 0 | 0 | 0 | -508.25 | 0 | 0 | 0 | 63026.75 | 0 | 0 | 0 | 0 | 63026.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403184 | SVCW Swinstie WwTW Elevated approach sewers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-02-04 | 2015-03-06 | 2018-12-03 | 2019-07-24 |  | North Lanarkshire | 140973.67 | 0 | 355844.33 | -7999.52 | 1243.9 | 1551.71 | 0 | 0 | 350640.42 | 0 | 0 | 0 | 491614.09 | 0 | 0 | 0 | 0 | 491614.09 | 209381.79 | [5 empty] | N | CM_WWI | 100%
401223 | SVCW Tay Cluster 1 Pitlessie Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2012-03-19 | 2012-05-04 | 2014-05-21 |  | Perth and Kinross | 468915 | 0 | -743.96 | -187.77 | 0 | 0 | 0 | 0 | -931.73 | 0 | 0 | 0 | 467983.27 | 0 | 0 | 0 | 0 | 467983.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401221 | SVCW Tay Cluster 3 WSZ001080 Gannochy SR TOWM | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2012-07-30 | 2012-08-29 | 2014-04-23 |  | Dundee City | 97438 | 0 | 8079.82 | 99.5 | 0 | 0 | 0 | 0 | 8179.32 | 0 | 0 | 0 | 105617.32 | 0 | 0 | 0 | 0 | 105617.32 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403137 | SVCW Telemetry - WMS Migration SR10 Ph1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS7 | 2013-03-06 | 2013-11-13 | 2013-12-02 | 2016-08-30 |  | Scottish Water Wide | 142804 | 0 | 66060.46 | 19480.21 | 5308.65 | 0 | 0 | 0 | 90849.32 | 0 | 0 | 0 | 233653.32 | 0 | 0 | 0 | 0 | 233653.32 | 613322.63 | [5 empty] | N | CM_WSNI | 50% | CM_WWNI | 50%
403138 | SVCW Telemetry RTU Replacement SR10 phase 2 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2013-01-17 | 2013-07-24 | 2013-09-09 | 2015-07-31 |  | Scottish Water Wide | 247968 | 0 | -1769 | -1157.62 | 0 | 0 | 0 | 0 | -2926.62 | 0 | 0 | 0 | 245041.38 | 0 | 0 | 0 | 0 | 245041.38 | 613322.63 | [5 empty] | N | CM_WWNI | 46.99% | CM_WSNI | 53.01%
403739 | SVCW Thankerton - Install new sewer pipe under West Coast Railway Line | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-08-25 | 2015-04-27 | 2015-04-27 | 2015-04-27 |  | South Lanarkshire | 18157.18 | 0 | -1272.93 | 0 | 0 | 0 | 0 | 0 | -1272.93 | 0 | 0 | 0 | 16884.25 | 0 | 0 | 0 | 0 | 16884.25 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403490 | SVCW Troqueer commissioning review | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-07-05 | 2013-07-05 | 2013-07-05 | 2016-10-10 |  | Dumfries and Galloway | 48713.41 | 0 | 11286.59 | -11561.88 | 0 | 0 | 0 | 0 | -275.29 | 0 | 0 | 0 | 48438.12 | 0 | 0 | 0 | 0 | 48438.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402365 | SVCW Troqueer WwTW Inlet Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2011-09-28 | 2011-10-07 | 2012-01-09 | 2016-10-10 |  | Dumfries and Galloway | 174168.61 | 0 | 7831.39 | -7728.2 | 0 | 0 | 0 | 0 | 103.19 | 0 | 0 | 0 | 174271.8 | 0 | 0 | 0 | 0 | 174271.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401494 | SVCW TWS001417 Turriff Prosptect Hill Internal Refurbishment of Service Reservoir | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-04-22 | 2012-07-24 | 2012-10-22 | 2013-04-26 |  | Aberdeenshire | 111363 | 0 | -1841.58 | 0 | 0 | 0 | 0 | 0 | -1841.58 | 0 | 0 | 0 | 109521.42 | 0 | 0 | 0 | 0 | 109521.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403167 | SVCW Ullapool WOA - Upper Braes WPS Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-16 | 2014-02-07 | 2014-06-30 | 2018-07-09 |  | Highland | 164354 | 0 | 29705 | -15311.51 | 126731.92 | -45843.47 | 10.77 | 6.12 | 95298.83 | 0 | 0 | 0 | 259652.83 | 0 | 0 | 0 | 0 | 259652.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403019 | SVCW Uphall WwPS Rising Main - Renewal | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-11-30 | 2016-03-29 | 2016-06-10 | 2016-11-17 |  | West Lothian | 33410 | 0 | 103470 | 282094 | 3207 | -1136.37 | 0 | 0 | 387634.63 | 0 | 0 | 0 | 421044.63 | 0 | 0 | 0 | 0 | 421044.63 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403312 | SVCW Upper Morton Small Reservoir Enhancement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-30 | 2015-07-13 | 2015-07-13 | 2014-04-22 | 2014-04-22 | West Lothian | 14962 | 0 | -1602.8 | 0 | 0 | 0 | 0 | 0 | -1602.8 | 0 | 0 | 0 | 13359.2 | 0 | 0 | 0 | 0 | 13359.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403701 | SVCW Water Balance Supply Pipe Leakage | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-02-12 | 2014-04-24 | 2014-04-24 | 2015-10-30 |  | Scottish Water Wide | 93797 | 0 | -283.65 | 0 | 0 | 0 | 0 | 0 | -283.65 | 0 | 0 | 0 | 93513.35 | 0 | 0 | 0 | 0 | 93513.35 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500570 | SVCW Water Central Infra (MD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2016-11-24 |  | Scottish Water Wide | 0 | 0 | 250300.53 | -200357.95 | 20.8 | 0 | 0 | 0.01 | 49963.38 | 0 | 0 | 0 | 49963.38 | 0 | 0 | 0 | 0 | 49963.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500539 | SVCW Water Central Infra (SWD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2016-12-21 |  | Scottish Water Wide | 0 | 0 | 249979.18 | -1228.46 | 17.8 | 0 | 0 | 0 | 248768.52 | 0 | 0 | 0 | 248768.52 | 0 | 0 | 0 | 0 | 248768.52 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500572 | SVCW Water Central Other (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-27 | 2017-04-28 |  | Scottish Water Wide | 0 | 0 | 78328.28 | 9841.64 | -1399.36 | 0 | 0 | 0 | 86770.56 | 0 | 0 | 0 | 86770.56 | 0 | 0 | 0 | 0 | 86770.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500541 | SVCW Water Central Other (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2016-12-21 |  | Scottish Water Wide | 0 | 0 | 16836 | -14264.54 | 0 | 0 | 0 | 0 | 2571.46 | 0 | 0 | 0 | 2571.46 | 0 | 0 | 0 | 0 | 2571.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500571 | SVCW Water Central WTW (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2016-08-23 |  | Scottish Water Wide | 0 | 0 | 177650.35 | -133356.32 | 3877.32 | 0 | 0 | 0 | 48171.35 | 0 | 0 | 0 | 48171.35 | 0 | 0 | 0 | 0 | 48171.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500540 | SVCW Water Central WTW (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2018-02-26 |  | Scottish Water Wide | 0 | 0 | 149499.68 | 316799.56 | 15709.28 | 98.63 | 0 | 89.98 | 482197.13 | 0 | 0 | 0 | 482197.13 | 0 | 0 | 0 | 0 | 482197.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500557 | SVCW Water East SR (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2015-05-22 | 2015-05-22 | 2015-05-29 | 2020-12-07 |  | All East Unitary Authorities | 0 | 0 | 197317 | 288945.53 | 306580.94 | 199228.29 | 15872.26 | -1289.82 | 1006654.2 | 14445.94 | 0 | 0 | 1021100.14 | 0 | 0 | 0 | 0 | 1021100.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500526 | SVCW Water East SR (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-28 | 2015-04-28 | 2015-04-28 | 2020-03-04 |  | All East Unitary Authorities | 0 | 0 | 206922 | 81201 | 15254 | -25006.8 | 0 | 0 | 278370.2 | 0 | 0 | 0 | 278370.2 | 0 | 0 | 0 | 0 | 278370.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500555 | SVCW Water East WPS (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-29 | 2016-09-28 |  | All East Unitary Authorities | 0 | 0 | 8792.52 | 0 | 0 | 0 | 0 | 0 | 8792.52 | 0 | 0 | 0 | 8792.52 | 0 | 0 | 0 | 0 | 8792.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500524 | SVCW Water East WPS (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-28 | 2015-04-28 | 2015-04-28 | 2020-11-27 |  | All East Unitary Authorities | 0 | 0 | 265988 | 187409.69 | 62692 | -64990.2 | 0 | 0 | 451099.49 | 0 | 0 | 0 | 451099.49 | 0 | 0 | 0 | 0 | 451099.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500556 | SVCW Water East WTW (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2018-02-08 |  | All East Unitary Authorities | 0 | 0 | 491516 | 694380.58 | 12552.78 | 0 | 0 | 0 | 1198449.36 | 0 | 0 | 0 | 1198449.36 | 0 | 0 | 0 | 0 | 1198449.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500525 | SVCW Water East WTW (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2020-11-27 |  | All East Unitary Authorities | 0 | 0 | 2306909.23 | 709531.32 | 249391.45 | -238806.23 | 0 | 0 | 3027025.77 | 0 | 0 | 0 | 3027025.77 | 0 | 0 | 0 | 0 | 3027025.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500558 | SVCW Water North Infra (MD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-25 | 2018-03-21 |  | All North Unitary Authorities | 0 | 0 | 669722 | 815300.91 | 597568.78 | 1849.51 | 0 | 262.62 | 2084703.82 | 0 | 0 | 0 | 2084703.82 | 0 | 0 | 0 | 0 | 2084703.82 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500527 | SVCW Water North Infra (SWD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2017-01-04 |  | All North Unitary Authorities | 0 | 0 | 380900 | 74723.83 | 728.89 | 0 | 0 | 0 | 456352.72 | 0 | 0 | 0 | 456352.72 | 0 | 0 | 0 | 0 | 456352.72 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500561 | SVCW Water North SR (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-05-25 | 2018-07-11 |  | All North Unitary Authorities | 0 | 0 | 306765 | 51933.99 | 68044.42 | -11716.12 | 55.41 | 0 | 415082.7 | 0 | 0 | 0 | 415082.7 | 0 | 0 | 0 | 0 | 415082.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500530 | SVCW Water North SR (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-12-15 |  | All North Unitary Authorities | 0 | 0 | 219313 | 41874.68 | 0 | 0 | 0 | 0 | 261187.68 | 0 | 0 | 0 | 261187.68 | 0 | 0 | 0 | 0 | 261187.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500559 | SVCW Water North WPS (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-05-25 | 2017-02-21 |  | All North Unitary Authorities | 0 | 0 | 11131 | 7874.01 | 53.04 | 0 | 0 | 0 | 19058.05 | 0 | 0 | 0 | 19058.05 | 0 | 0 | 0 | 0 | 19058.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500528 | SVCW Water North WPS (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-08-31 |  | All North Unitary Authorities | 0 | 0 | 65138.21 | 9165.42 | 0 | 0 | 0 | 0 | 74303.63 | 0 | 0 | 0 | 74303.63 | 0 | 0 | 0 | 0 | 74303.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500560 | SVCW Water North WTW (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-25 | 2018-06-22 |  | All North Unitary Authorities | 0 | 0 | 808598 | 120025.43 | 52462.62 | -28429.36 | 0 | 0 | 952656.69 | 0 | 0 | 0 | 952656.69 | 0 | 0 | 0 | 0 | 952656.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500529 | SVCW Water North WTW (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-01-04 |  | All North Unitary Authorities | 0 | 0 | 1694113.79 | 614611.46 | 1701.32 | 0 | 0 | 0 | 2310426.57 | 0 | 0 | 0 | 2310426.57 | 0 | 0 | 0 | 0 | 2310426.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500643 | SVCW Water Resources - Monitoring Equipment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2018-08-10 |  | Scottish Water Wide | 0 | 0 | 302440 | 98911.91 | 3129 | 3139.13 | 172.19 | 0 | 407792.23 | 0 | 0 | 0 | 407792.23 | 0 | 0 | 0 | 0 | 407792.23 | 119022.58 | [5 empty] | N | CM_WSI | 100%
500566 | SVCW Water South Infra (MD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2017-11-22 |  | All South Unitary Authorities | 0 | 0 | 116855 | 832361.93 | 170684.51 | -6424.13 | 0 | 144.77 | 1113622.07 | 0 | 0 | 0 | 1113622.07 | 0 | 0 | 0 | 0 | 1113622.07 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500535 | SVCW Water South Infra (SWD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-02-01 |  | All South Unitary Authorities | 0 | 0 | 859734 | 709.66 | 0 | 0 | 0 | 0 | 860443.66 | 0 | 0 | 0 | 860443.66 | 0 | 0 | 0 | 0 | 860443.66 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500569 | SVCW Water South SRs (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-25 | 2016-03-03 |  | All South Unitary Authorities | 0 | 0 | 3011.43 | 0 | 0 | 0 | 0 | 0 | 3011.43 | 0 | 0 | 0 | 3011.43 | 0 | 0 | 0 | 0 | 3011.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500538 | SVCW Water South SRs (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-08 |  | All South Unitary Authorities | 0 | 0 | 286276 | -25443.47 | 0 | 0 | 0 | 0 | 260832.53 | 0 | 0 | 0 | 260832.53 | 0 | 0 | 0 | 0 | 260832.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500567 | SVCW Water South WPS (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-25 | 2016-03-03 |  | All South Unitary Authorities | 0 | 0 | 6869.16 | 0 | 0 | 0 | 0 | 0 | 6869.16 | 0 | 0 | 0 | 6869.16 | 0 | 0 | 0 | 0 | 6869.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500536 | SVCW Water South WPS (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-08-02 |  | All South Unitary Authorities | 0 | 0 | 63788 | -1703.29 | 0 | 0 | 0 | 0 | 62084.71 | 0 | 0 | 0 | 62084.71 | 0 | 0 | 0 | 0 | 62084.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500568 | SVCW Water South WTW (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2018-05-30 |  | All South Unitary Authorities | 0 | 0 | 198027 | 320140.89 | 233840.24 | 36667.74 | 168.14 | 0 | 788844.01 | 0 | 0 | 0 | 788844.01 | 0 | 0 | 0 | 0 | 788844.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500537 | SVCW Water South WTW (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-06-01 |  | All South Unitary Authorities | 0 | 0 | 1971276 | 27327 | -69741.79 | 0 | 0 | 0 | 1928861.21 | 0 | 0 | 0 | 1928861.21 | 0 | 0 | 0 | 0 | 1928861.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500562 | SVCW Water West Infra (MD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-25 | 2022-04-06 |  | All West Unitary Authorities | 0 | 0 | 551946 | 2071586.31 | 962346.85 | 17136.41 | 25349.08 | -14196.13 | 3614168.52 | 0 | 0 | 0 | 3614168.52 | 0 | 0 | 0 | 0 | 3614168.52 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500531 | SVCW Water West Infra (SWD) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2019-02-08 |  | All West Unitary Authorities | 0 | 0 | 161402 | -42252.53 | 45850.53 | -66161.03 | 0 | 0 | 98838.97 | 0 | 0 | 0 | 98838.97 | 0 | 0 | 0 | 0 | 98838.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500565 | SVCW Water West SR (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-27 | 2017-06-09 |  | All West Unitary Authorities | 0 | 0 | 261073 | 71787.36 | 1044.68 | 0 | 0 | 0 | 333905.04 | 0 | 0 | 0 | 333905.04 | 0 | 0 | 0 | 0 | 333905.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500534 | SVCW Water West SR (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2019-02-08 |  | All West Unitary Authorities | 0 | 0 | 217820.42 | 98500.5 | 11060.02 | 24145.25 | 0 | 0 | 351526.19 | 0 | 0 | 0 | 351526.19 | 0 | 0 | 0 | 0 | 351526.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500563 | SVCW Water West WPS (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-27 | 2018-03-07 |  | All West Unitary Authorities | 0 | 0 | 417698 | 448826.6 | 94730.29 | -17225.21 | 0 | 0 | 944029.68 | 0 | 0 | 0 | 944029.68 | 0 | 0 | 0 | 0 | 944029.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500532 | SVCW Water West WPS (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2019-02-08 |  | All West Unitary Authorities | 0 | 0 | 46708 | 8395.79 | 14896.21 | -20374.27 | 0 | 0 | 49625.73 | 0 | 0 | 0 | 49625.73 | 0 | 0 | 0 | 0 | 49625.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500564 | SVCW Water West WTW (MD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-11-02 | 2015-06-05 | 2015-06-25 | 2017-08-24 |  | All West Unitary Authorities | 0 | 0 | 275953.49 | 299227.23 | 15731.05 | 0 | 0 | 0 | 590911.77 | 0 | 0 | 0 | 590911.77 | 0 | 0 | 0 | 0 | 590911.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500533 | SVCW Water West WTW (SWD) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2019-02-08 |  | All West Unitary Authorities | 0 | 0 | 674910.5 | 280780.26 | 0 | 9419.51 | 0 | 0 | 965110.27 | 0 | 0 | 0 | 965110.27 | 0 | 0 | 0 | 0 | 965110.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402556 | SVCW West Water Non-Infra - 2012-2013 - CID Delivery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-09 | 2016-01-14 |  | All West Unitary Authorities | 1002831 | 0 | -28267.36 | 0 | 0 | 0 | 0 | 0 | -28267.36 | 0 | 0 | 0 | 974563.64 | 0 | 0 | 0 | 0 | 974563.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402199 | SVCW Weyland Bay WWPS Replace Screen Covers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2011-09-12 | 2012-05-21 | 2012-06-25 | 2016-06-17 |  | Orkney Islands | 10000 | 0 | 0 | -2675.68 | 0 | 0 | 0 | 0 | -2675.68 | 0 | 0 | 0 | 7324.32 | 0 | 0 | 0 | 0 | 7324.32 | 209381.79 | [5 empty] | N | CM_M&G | 100%
402112 | SVCW Whalsay Old WSZ Low Pressure | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-05-18 | 2012-05-15 | 2012-05-30 | 2012-07-13 | 2012-07-13 | Shetland Islands | 30631.65 | 0 | 62.5 | 0 | 0 | 0 | 0 | 0 | 62.5 | 0 | 0 | 0 | 30694.15 | 0 | 0 | 0 | 0 | 30694.15 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403471 | SVCW WQ OPA North Hoy WTW Temporary Filtration | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-18 | 2014-05-12 | 2014-07-21 | 2016-03-09 |  | Orkney Islands | 233231 | 0 | 32979 | 11294.63 | 40.67 | -430.16 | 0 | 0 | 43884.14 | 0 | 0 | 0 | 277115.14 | 0 | 0 | 0 | 0 | 277115.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403448 | SVCW WQ OPA Savalbeg WTW Quality Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-05-13 | 2015-03-12 | 2015-03-02 | 2015-03-03 |  | Highland | 103000 | 0 | -27.1 | 0 | 0 | 0 | 0 | 0 | -27.1 | 0 | 0 | 0 | 102972.9 | 0 | 0 | 0 | 0 | 102972.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403449 | SVCW WQ OPA SR Sample Tap Replacement Programme Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-23 | 2013-07-29 | 2013-09-09 | 2015-03-30 |  | Scottish Water Wide | 590036 | 0 | -14947.82 | 88.75 | 0 | 0 | 0 | 0 | -14859.07 | 0 | 0 | 0 | 575176.93 | 0 | 0 | 0 | 0 | 575176.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401865 | SVCW WSZ 000663 Gallowhill WSZ Highfield Place Birkhill Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-23 | 2012-07-24 | 2012-09-28 | 2013-04-25 |  | Angus | 54674 | 0 | -2065.62 | 0 | 0 | 0 | 0 | 0 | -2065.62 | 0 | 0 | 0 | 52608.38 | 0 | 0 | 0 | 0 | 52608.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400797 | SVCW WSZ001402 Stobsmuir WSZand DMA004274 Perth Road - Thomson Street WMR | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-06-21 | 2011-06-23 | 2010-08-23 | 2012-03-29 |  | Dundee City | 100098 | 0 | -8492.87 | 0 | 0 | 0 | 0 | 0 | -8492.87 | 0 | 0 | 0 | 91605.13 | 0 | 0 | 0 | 0 | 91605.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402019 | SVCW WTW000606 Sandy Loch WTW Chemical Handling and Storage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-04-27 | 2014-12-17 | 2015-03-26 | 2017-06-21 |  | Shetland Islands | 194347 | 0 | 358958 | 65000 | 56453.09 | 0 | -3706 | 0 | 476705.09 | 0 | 0 | 0 | 671052.09 | 0 | 0 | 0 | 0 | 671052.09 | 119022.58 | [5 empty] | N | CM_M&G | 100%
401051 | SVCW WTW000616 Kirbister WTW Replace 8 Remaining High Lift Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-06 | 2014-06-30 | 2015-01-23 | 2016-03-29 |  | Orkney Islands | 352366 | 0 | 55145.9 | 91109.3 | 0 | -6595.29 | 0 | 0 | 139659.91 | 0 | 0 | 0 | 492025.91 | 0 | 0 | 0 | 0 | 492025.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
400978 | SVCW WW - Pre QH CAPEX CID Development Holding Line | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-05-31 | 2010-05-24 | 2013-02-08 | 2015-12-14 |  | Highland | 91772 | 0 | 197113.42 | 0 | 0 | 0 | 0 | 0 | 197113.42 | 0 | 0 | 0 | 288885.42 | 0 | 0 | 0 | 0 | 288885.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402077 | SW CMA Data Reconciliation Tables | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-09-20 | 2011-09-20 | 2011-09-20 | 2015-03-17 |  | Scottish Water Wide | 2231.71 | 0 | -677.27 | 0 | 0 | 0 | 0 | 0 | -677.27 | 0 | 0 | 0 | 1554.44 | 0 | 0 | 0 | 0 | 1554.44 | 0 | [5 empty] | N | CS20 | 100%
502639 | SW Managed Delivery - Post-Project Land Liabilities | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS4 | 2017-03-09 | 2017-03-09 | 2017-03-13 | 2021-03-24 |  | Scottish Water Wide | 0 | 0 | 0 | 18938.32 | 110072.03 | 265654.41 | 153335.24 | 121442.19 | 669442.19 | 365194.81 | 0 | 0 | 1034637 | 0 | 0 | 0 | 0 | 1034637 | 613322.63 | [5 empty] | N | CM_M&G | 100%
404118 | SW Scanning Radio Hardware Procurement (Telemetry) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-01-22 |  | Scottish Water Wide | 0 | 0 | 447836.14 | 0 | 0 | 0 | 0 | 0 | 447836.14 | 0 | 0 | 0 | 447836.14 | 0 | 0 | 0 | 0 | 447836.14 | 306661.32 | [5 empty] | N | CM_M&G | 100%
403580 | SW Wide Strategic Modelling - Phase 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-09-25 | 2018-12-19 | 2018-12-19 | 2020-06-29 |  | Scottish Water Wide | 124143.59 | 0 | 51328.41 | 91609.79 | 8000 | -15455.58 | 37957.54 | -12042.95 | 161397.21 | 0 | 0 | 0 | 285540.8 | 0 | 0 | 0 | 0 | 285540.8 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501017 | SW1015 - Shieldaig Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WINF | Flooding Demand Driven | MS1 | 2018-01-30 | 2021-07-15 | 2021-09-27 | 2022-08-26 | 2022-09-28 | Glasgow City | 0 | 0 | 21930 | 66070 | 87000 | 135431 | 378943 | -256759 | 432615 | 1860385.13 | 0 | 0 | 2293000.13 | 0 | 0 | 0 | 0 | 2293000.13 | 180449.74 | [5 empty] | N | FL_DD | 100%
500651 | SW1025 - 26 Afton Bridgend New Cumnock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-02-08 | 2018-03-27 | 2018-03-27 | 2017-10-17 | 2018-03-27 | East Ayrshire | 0 | 0 | 38389 | 46428 | -79879.75 | 968.97 | -0.02 | 0 | 5906.21 | 0 | 0 | 0 | 5906.21 | 0 | 0 | 0 | 0 | 5906.21 | 180449.74 | [5 empty] | N | FL_DD | 100%
502895 | SW1392 - Third Avenue Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WINF | Flooding Demand Driven | MS1 | 2020-03-24 | 2021-07-26 | 2021-09-27 | 2022-04-27 | 2022-07-28 | Glasgow City | 0 | 0 | 0 | 0 | 41860.47 | 97139.53 | 81635.5 | 188096.5 | 408732 | 488148.62 | 0 | 0 | 896880.62 | 0 | 0 | 0 | 0 | 896880.62 | 175086.76 |  |  |  |  | 34389.9996 | N | FL_DD | 100%
502228 | SW1616 - Gartcraig Rd - Fettes Street Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-06-03 | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-09-08 | Glasgow City | 0 | 0 | 0 | 37030.23 | 43969.77 | 85000 | 31197.34 | 2.25 | 197199.59 | 12800.41 | 0 | 0 | 210000 | 0 | 0 | 0 | 0 | 210000 | 175086.76 | [5 empty] | N | FL_DD | 100%
503318 | SW1617 - Newhills Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-10-11 | 2022-02-14 | 2022-04-18 | 2023-03-03 | 2023-06-05 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 44000 | 92200 | 38947.4 | 175147.4 | 424981.04 | 0 | 0 | 600128.44 | 0 | 0 | 0 | 0 | 600128.44 | 175086.76 | [5 empty] | N | FL_DD | 100%
500999 | SW163 - Broompark Drive Newton Mearns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2018-03-30 | 2019-05-16 | 2019-07-01 | 2019-09-30 | 2019-09-30 | East Renfrewshire | 0 | 0 | 22930 | 46633.66 | 57997.49 | 113889.85 | 216846 | -297 | 458000 | 2000 | 0 | 0 | 460000 | 0 | 0 | 0 | 0 | 460000 | 180449.74 | [5 empty] | N | FL_DD | 100%
500202 | SW167 - Aikenhead Road - Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-09-03 | 2019-09-24 | 2019-09-24 | 2019-09-04 | 2019-09-04 | Glasgow City | 0 | 0 | 66930 | 57070 | 15000 | 45000 | 89990.12 | 0 | 273990.12 | 0 | 0 | 0 | 273990.12 | 0 | 0 | 0 | 0 | 273990.12 | 520131.84 | [5 empty] | N | FL_NAMED | 100%
503172 | SW1670 - Borrowmeadow Road Stirling | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-05-10 | 2021-08-23 | 2021-11-01 | 2022-11-02 | 2023-02-02 | Stirling | 0 | 0 | 0 | 0 | 0 | 84000 | 58606.75 | 46389.25 | 188996 | 2771322.15 | 0 | 0 | 2960318.15 | 0 | 0 | 0 | 0 | 2960318.15 | 175086.76 | [5 empty] | N | FL_DD | 100%
503771 | SW1905 - Wellhouse Crescent Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW0 | 2022-02-23 | 2022-06-01 | 2022-08-12 | 2023-03-16 | 2023-05-09 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 265000 | 174118 | 439118 | 1060881.7 | 1060881.7 | 1472684.4101 | 1499999.7 | 411802.7101 | 0 | 0 | 411802.7101 | 1911802.4101 | 2690461.35 | [5 empty] | N | FL_NAMED | 100%
500743 | SW1907 - Sandy Road Carluke | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-02-25 | 2019-02-25 | South Lanarkshire | 0 | 0 | 15500 | 19500 | 12000 | -45905.09 | -1093.92 | 0 | 0.99 | 0 | 0 | 0 | 0.99 | 0 | 0 | 0 | 0 | 0.99 | 180449.74 | [5 empty] | N | FL_DD | 100%
500003 | SW195 - 2560-2562 Dumbarton Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2015-03-26 | 2015-06-25 | 2015-06-26 | 2017-12-20 | 2017-12-20 | West Dunbartonshire | 0 | 0 | 848820 | -19597.9 | 560701.79 | 1369.11 | 179.02 | 0 | 1391472.02 | 0 | 0 | 0 | 1391472.02 | 0 | 0 | 0 | 0 | 1391472.02 | 175086.76 | [5 empty] | N | FL_DD | 100%
504017 | S-W-271119-Steele Avenue Lochfoot - Water Quality | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-11-28 |  | 2019-12-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | -572.9 | 4427.1 | 0 | 0 | 0 | 4427.1 | 0 | 0 | 0 | 0 | 4427.1 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501016 | SW330 - Muirhead Way Bishopbriggs Glasgow | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | WWINF | Infra Charge | MS4 | 2018-02-22 | 2019-07-19 | 2019-09-30 | 2020-11-27 |  | East Dunbartonshire | 0 | 0 | 0 | 65306.81 | 120693.19 | 202200.64 | 511205.36 | 185489 | 1084895 | 1558 | 0 | 0 | 1086453 | 0 | 0 | 0 | 0 | 1086453 | 1470767.03 | [5 empty] | N | SG5 | 100%
502891 | SW343 - Peat Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-01-31 | 2020-03-05 | 2020-03-10 | 2020-03-10 | 2021-04-01 | Glasgow City | 0 | 0 | 0 | 0 | 43000 | 96000 | 47026.95 | 4873.75 | 190900.7 | 0 | 0 | 0 | 190900.7 | 0 | 0 | 0 | 0 | 190900.7 | 175086.76 | [5 empty] | N | FL_DD | 100%
502892 | SW344 Braidholm Road Giffnock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS1 | 2020-07-14 | 2021-04-01 | 2021-08-02 | 2022-03-24 | 2022-03-24 | East Renfrewshire | 0 | 0 | 0 | 0 | 42564.57 | 91935.43 | 76299.52 | 751625.17 | 962424.69 | 3305604.02 | 0 | 0 | 4268028.71 | 0 | 0 | 0 | 0 | 4268028.71 | 175086.76 |  |  |  |  | 32630.0004 | N | FL_DD | 100%
502893 | SW346 Beech Avenue Newton Mearns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2020-03-12 | 2021-02-09 | 2021-06-21 | 2022-02-07 | 2022-05-09 | East Renfrewshire | 0 | 0 | 0 | 0 | 43000 | 64000 | 83124.13 | 221709.69 | 411833.82 | 587908.18 | 0 | 0 | 999742 | 0 | 0 | 0 | 0 | 999742 | 175086.76 | [5 empty] | N | FL_DD | 100%
500748 | SW383 - Stanley Primary School Stanley Road Ardrossan - NR | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-05-06 | 2021-12-28 | 2021-12-29 | 2021-12-29 | 2021-12-29 | North Ayrshire | 0 | 0 | 23500 | 24530.23 | 55435.3 | 44534.47 | 82472.25 | 34733.75 | 265206 | 701917.62 | 0 | 0 | 967123.62 | 0 | 0 | 0 | 0 | 967123.62 | 180449.74 | [5 empty] | N | FL_DD | 100%
501011 | SW409 - Riddon Place Glasgow Flooding Project | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-03-19 | 2020-03-19 | 2020-03-19 | 2020-01-23 | 2021-04-01 | Glasgow City | 0 | 0 | 31056.93 | 34027.07 | 22916 | 6000 | 40775.14 | 0 | 134775.14 | 0 | 0 | 0 | 134775.14 | 0 | 0 | 0 | 0 | 134775.14 | 180449.74 | [5 empty] | N | FL_DD | 100%
500663 | SW522 - East Shaw Street Kilmarnock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS0 | 2020-11-26 | 2021-08-02 | 2021-08-09 | 2021-09-17 | 2021-09-20 | East Ayrshire | 0 | 0 | 23100 | 30930.23 | 16969.77 | 20000 | 73915.61 | 10484.39 | 175400 | 16600.35 | 16600.35 | 23044.1119 | 192000.35 | 6443.7619 | 0 | 0 | 6443.7619 | 198444.1119 | 368809.14 | [5 empty] | N | FL_NAMED | 100%
502425 | SW599 - Laighlands Road Bothwell | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-05-04 | 2021-09-13 | 2021-11-15 | 2022-09-30 | 2023-01-09 | South Lanarkshire | 0 | 0 | 0 | 41860.47 | 16139.53 | 34000 | 181367 | 423106 | 696473 | 5146827.08 | 0 | 0 | 5843300.08 | 0 | 0 | 0 | 0 | 5843300.08 | 175086.76 | [5 empty] | N | FL_DD | 100%
501000 | SW609 - Main Street Newmilns | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-12-19 | 2019-12-19 | 2019-12-19 | 2019-12-19 | 2020-07-01 | East Ayrshire | 0 | 0 | 26523 | 42109 | 12369 | 29581.77 | 43234.8 | -1219.05 | 152598.52 | 0 | 0 | 0 | 152598.52 | 0 | 0 | 0 | 0 | 152598.52 | 180449.74 | [5 empty] | N | FL_DD | 100%
502376 | SW615 - Baker Street Stirling | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2020-09-24 | 2020-09-30 | 2020-11-17 | 2022-03-21 | 2021-02-26 | Stirling | 0 | 0 | 0 | 42522.01 | 2477.99 | 29000 | 71331.41 | 24228.59 | 169560 | 440 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 170000 | 175086.76 | [5 empty] | N | FL_DD | 100%
502894 | SW666 - Bay Street Port Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS4 | 2020-09-21 | 2020-10-20 | 2020-11-09 | 2021-01-25 |  | Inverclyde | 0 | 0 | 0 | 0 | 41860.47 | 4139.53 | 33665.99 | 23159.03 | 102825.02 | 0 | 0 | 0 | 102825.02 | 0 | 0 | 0 | 0 | 102825.02 | 175086.76 | [5 empty] | N | FL_DD | 100%
501014 | SW741 - Kilbride Drive Helensburgh | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2019-02-08 | 2019-12-16 | 2020-01-27 | 2021-04-28 | 2021-04-28 | Argyll and Bute-Cowal & Bute | 0 | 0 | 22930 | 44566.68 | 51503.32 | 93383.97 | 396285.17 | 202879.08 | 811548.22 | 15385 | 0 | 0 | 826933.22 | 0 | 0 | 0 | 0 | 826933.22 | 180449.74 |  |  |  |  | 2949.9996 | N | FL_DD | 100%
502328 | SW759 - Woodlands Grove Kilmarnock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2021-08-17 | 2021-12-27 | 2022-02-28 | 2023-02-24 | 2023-05-25 | East Ayrshire | 0 | 0 | 0 | 43360.47 | 25639.53 | 77000 | 102878.6 | -22268.6 | 226610 | 1031390.11 | 0 | 0 | 1258000.11 | 0 | 0 | 0 | 0 | 1258000.11 | 175086.76 | [5 empty] | N | FL_DD | 100%
500681 | SW843 - Wellgate Lanark | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS1 | 2020-02-21 | 2021-04-19 | 2021-07-05 | 2022-05-16 | 2022-08-08 | South Lanarkshire | 0 | 0 | 62556 | 20783.9 | 24660.1 | 31000 | 131189.32 | 512430.68 | 782620 | 2493518.6 | 2493518.6 | 3461428.3276 | 3276138.6 | 967909.7276 | 0 | 0 | 967909.7276 | 4244048.3276 | 281012.82 |  |  |  |  | 31700.0004 | N | FL_NAMED | 100%
500682 | SW857 - Townhead Street Stonehouse | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WINF | Flooding Named | MS0 | 2019-04-29 | 2021-07-26 | 2021-09-20 | 2022-06-09 | 2022-06-09 | South Lanarkshire | 0 | 0 | 56500 | 20886.26 | 26210.11 | 37403.63 | 179971 | 108069 | 429040 | 936960 | 936960 | 1300659.9934 | 1366000 | 363699.9934 | 0 | 0 | 363699.9934 | 1729699.9934 | 466541.85 | [5 empty] | N | FL_NAMED | 100%
500732 | SW92 - Dukes Road Troon | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-03-14 | 2019-03-14 | 2019-03-14 | 2019-02-25 | 2019-02-25 | South Ayrshire | 0 | 0 | 22930 | 23500 | 20570 | -66999 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 60189.23 | [5 empty] | N | FL_NAMED | 100%
403300 | SWCW Thurso STW Access Remedial Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-01-17 | 2013-01-17 | 2013-03-21 | 2018-08-13 |  | Highland | 32987.1 | 0 | -0.1 | 120 | 0 | 0 | 0 | 0 | 119.9 | 0 | 0 | 0 | 33107 | 0 | 0 | 0 | 0 | 33107 | 90601.29 | [5 empty] | N | CM_WWI | 100%
49605 | SWD - Investment Profile Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | General |  | SWD | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | RISK | 100%
49702 | SWD - Unpromoted Capital Maintenance - Profile Adjustment | Q&S4 | Sustaining existing high service for customers | CM Risk Drawdown |  |  | General |  | SWD | CM Risk Drawdown | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SR15_CMA_UNP | 100%
403710 | SWD Non Infra 2014-15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-20 | 2014-02-20 | 2014-04-04 | 2015-11-18 |  | Highland | 2200000 | 0 | 727291.7 | -2033 | 0 | 0 | 0 | 0 | 725258.7 | 0 | 0 | 0 | 2925258.7 | 0 | 0 | 0 | 0 | 2925258.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500711 | Sweet Thorn Drive East Kilbride | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | WWINF | Infra Charge | MS6 | 2018-03-28 | 2019-09-19 | 2019-11-25 | 2020-03-31 |  | South Lanarkshire | 0 | 0 | 85125 | 50875 | 28855.88 | 117628.12 | 563513 | 113872 | 959869 | 0 | 0 | 0 | 959869 | 0 | 0 | 0 | 0 | 959869 | 1470767.03 | [5 empty] | N | SG5 | 100%
506031 | S-W-I-010420-Talla Aqueduct - Cleaves Well building and wall repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-04-01 |  | 2020-04-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5650.74 | 5650.74 | 0 | 0 | 0 | 5650.74 | 0 | 0 | 0 | 0 | 5650.74 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509055 | S-W-I-011020-Glencorse WOA-Norht Bridge 250mm main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-04-12 | 2021-06-14 | 2022-01-25 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5480 | 5480 | 64520.2 | 0 | 0 | 70000.2 | 0 | 0 | 0 | 0 | 70000.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506949 | S-W-I-020620-Limefield DSR - Waterston DSR Trunk Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-14 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28602.36 | 28602.36 | 0 | 0 | 0 | 28602.36 | 0 | 0 | 0 | 0 | 28602.36 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504151 | S-W-I-041219-Mosshall Street Transfers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-12-12 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 32100 | 15491.43 | 47591.43 | -15491.43 | 0 | 0 | 32100 | 0 | 0 | 0 | 0 | 32100 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504538 | S-W-I-070120-South Calder Bridge - Valve Installation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-03-27 | 2021-01-29 | 2021-11-26 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 3051.61 | 8171.4 | 11223 | 141497.77 | 0 | 0 | 152720.77 | 0 | 0 | 0 | 0 | 152720.77 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507548 | S-W-I-070720-Craigpark DSR Bypass PRV | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-10 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965.24 | 965.24 | 2334.76 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507576 | S-W-I-080720-Barbeth House New Abbey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2020-07-10 |  | 2021-02-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4667.48 | 4667.48 | 0 | 0 | 0 | 4667.48 | 0 | 0 | 0 | 0 | 4667.48 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505107 | S-W-I-100220-Elsrickle DMA Modelling Work | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | -566.68 | 533.32 | 566.68 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508698 | S-W-I-100920-Danderhall Inlet Flow Control | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-05-10 | 2021-08-13 | 2022-03-15 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3444 | 3444 | 11556.12 | 0 | 0 | 15000.12 | 0 | 0 | 0 | 0 | 15000.12 | 311236.79 | [5 empty] | N | WSI | 100%
508713 | S-W-I-110920-Firhill Old SR Bypass Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2021-01-08 | 2021-03-30 | 2021-11-09 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8499 | 8499 | 41500.77 | 0 | 0 | 49999.77 | 0 | 0 | 0 | 0 | 49999.77 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511762 | S-W-I-120321-Crossbankhead to Waterbeck - Mains Upgrade | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24550 | 24550 | 45000 | 0 | 0 | 69550 | 0 | 0 | 0 | 0 | 69550 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511767 | S-W-I-120321-Mortonhill Cottage Mid Calder EH53 0JT mains connection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1985.51 | 1985.51 | 28364.49 | 0 | 0 | 30350 | 0 | 0 | 0 | 0 | 30350 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504627 | S-W-I-130120-Camps WTW Private Supply Water Tank Access | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-01-15 |  | 2020-03-09 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 10991.63 | 0 | 10991.63 | 0 | 0 | 0 | 10991.63 | 0 | 0 | 0 | 0 | 10991.63 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505720 | S-W-I-13032020-Sunnyside monitoring | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-04-01 | 2021-01-11 | 2021-07-16 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6605 | 6605 | 3394.63 | 0 | 0 | 9999.63 | 0 | 0 | 0 | 0 | 9999.63 | 311236.79 | [5 empty] | N | CM_M&G | 100%
507650 | S-W-I-130720-Balgreen DSR Bypass PRV | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-07-14 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13094.85 | 13094.85 | -8794.85 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507645 | S-W-I-130720-Corra mill Road Crossford | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-07-15 | 2020-12-04 | 2021-03-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60192.29 | 60192.29 | 32.7 | 0 | 0 | 60224.99 | 0 | 0 | 0 | 0 | 60224.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507654 | S-W-I-130720-Newhouse TM Disconnection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-14 |  | 2020-08-12 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6630.64 | 6630.64 | 0 | 0 | 0 | 6630.64 | 0 | 0 | 0 | 0 | 6630.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507648 | S-W-I-130720-Torphichen Bypass PRV | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-07-15 | 2021-03-08 | 2021-05-17 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 13000 | 12000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 119022.58 | [5 empty] | N | WSNI | 100%
506610 | S-W-I-140520-Airdrie Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2020-05-15 |  | 2020-09-29 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87794.32 | 87794.32 | 5128.68 | 0 | 0 | 92923 | 0 | 0 | 0 | 0 | 92923 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507692 | S-W-I-150720-Barrasgate Cummertrees - Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-15 |  | 2020-07-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5513.08 | 5513.08 | 0 | 0 | 0 | 5513.08 | 0 | 0 | 0 | 0 | 5513.08 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507702 | S-W-I-150720-Pipe Crossing Station Road Kirkcowan - Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719.63 | 719.63 | 10280.37 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 11000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507698 | S-W-I-150720-Pipebridge Little Cairnbrock Stranraer - Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637.85 | 637.85 | 9112.15 | 0 | 0 | 9750 | 0 | 0 | 0 | 0 | 9750 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509284 | S-W-I-151020-Roberton WOA - Discolouration Network Modelling | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-15 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2585.73 | 2585.73 | 3864.27 | 0 | 0 | 6450 | 0 | 0 | 0 | 0 | 6450 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509288 | S-W-I-151020-The Grange Dolphinton | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-15 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1262.62 | 1262.62 | 18037.38 | 0 | 0 | 19300 | 0 | 0 | 0 | 0 | 19300 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509289 | S-W-I-151020-Woodhall Road Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-10-23 | 2021-06-14 | 2021-12-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15767.53 | 15767.53 | 34335.45 | 0 | 0 | 50102.98 | 0 | 0 | 0 | 0 | 50102.98 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510365 | S-W-I-161220-Fernieshaw Road Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-12-23 | 2021-07-05 | 2022-02-15 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5710.44 | 5710.44 | 44375 | 0 | 0 | 50085.44 | 0 | 0 | 0 | 0 | 50085.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511296 | S-W-I-170221-Alnwickhill PRV Heating | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245 | 245 | 3500 | 0 | 0 | 3745 | 0 | 0 | 0 | 0 | 3745 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511299 | S-W-I-170221-Cleghorn Bridge Structural Issues | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016.64 | 1016.64 | 14523.35 | 0 | 0 | 15539.99 | 0 | 0 | 0 | 0 | 15539.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504380 | S-W-I-171219-Burnbank Dunragit | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-12-18 |  | 2020-03-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 32101.94 | 0 | 32101.94 | 0 | 0 | 0 | 32101.94 | 0 | 0 | 0 | 0 | 32101.94 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504376 | S-W-I-171219-Meikleholm Langholm - Mains Upgrade | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-12-18 |  | 2020-02-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | -211.21 | 8788.79 | 0 | 0 | 0 | 8788.79 | 0 | 0 | 0 | 0 | 8788.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505270 | S-W-I-180220-Bridgebank Stranraer - Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-02-21 |  | 2020-03-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 15623.1 | 55.41 | 15678.51 | 0 | 0 | 0 | 15678.51 | 0 | 0 | 0 | 0 | 15678.51 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505277 | S-W-I-180220-Hightown Of Craigs Dumfries - Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-02-21 |  | 2020-06-22 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 5700 | 2785.37 | 8485.37 | 0 | 0 | 0 | 8485.37 | 0 | 0 | 0 | 0 | 8485.37 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511317 | S-W-I-180221-Boreland of Girthon Farm Sandgreen - Mains Upgrade | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26300 | 26300 | 5800 | 0 | 0 | 32100 | 0 | 0 | 0 | 0 | 32100 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511321 | S-W-I-180221-Greenfield WPS Stranraer - Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 30000 | 0 | 0 | 32100 | 0 | 0 | 0 | 0 | 32100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511320 | S-W-I-180221-Kettleton WOA - Network Modelling | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5245.97 | 5245.97 | 104.03 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506658 | S-W-I-180520-Pathfoot Smithy Bridge Survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-05-22 | 2020-12-07 | 2021-07-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7107 | 7107 | 2893.08 | 0 | 0 | 10000.08 | 0 | 0 | 0 | 0 | 10000.08 | 311236.79 | [5 empty] | N | CM_M&G | 100%
504408 | S-W-I-181219-Camps Private Water Supply Tank | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-12-18 |  | 2020-02-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2626.64 | 0 | 2626.64 | 0 | 0 | 0 | 2626.64 | 0 | 0 | 0 | 0 | 2626.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509885 | S-W-I-191120-Winterhope - Falford Waterbeck River Crossing TEES | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-11-19 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112639.79 | 112639.79 | -19639.79 | 0 | 0 | 93000 | 0 | 0 | 0 | 0 | 93000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504733 | S-W-I-20012020-South Calder Water Crossing - Optioneering | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 |  | 2020-03-27 | 2020-02-21 | 2020-05-29 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12538.81 | 12538.81 | 0 | 0 | 0 | 12538.81 | 0 | 0 | 0 | 0 | 12538.81 | 311236.79 | [5 empty] | N | CM_M&G | 100%
505851 | S-W-I-200320-Kelloholm SR - Cut & Cap Enabling Abandonment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-27 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | 1050 | 15000 | 0 | 0 | 16050 | 0 | 0 | 0 | 0 | 16050 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505855 | S-W-I-200320-Kirkconnel DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-27 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 883.18 | 21.36 | 904.54 | 12595.46 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 13500 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505836 | S-W-I-200320-Lanark Road West Link Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-03-27 |  | 2020-04-21 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 22244.82 | 23644.82 | 0 | 0 | 0 | 23644.82 | 0 | 0 | 0 | 0 | 23644.82 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508294 | S-W-I-200820-Arbigland - Tallowquhairn Kirkbean - Mains Upgrade | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-08-26 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52770.21 | 52770.21 | 6229.79 | 0 | 0 | 59000 | 0 | 0 | 0 | 0 | 59000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508293 | S-W-I-200820-Whitlawside Canonbie - Mains Upgrade | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9202.62 | 9202.62 | 0 | 0 | 0 | 9202.62 | 0 | 0 | 0 | 0 | 9202.62 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510707 | S-W-I-20210114-Fala TWP Pumping Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-01-25 | 2021-07-16 | 2022-02-28 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113.72 | 1113.72 | 98886.28 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510816 | S-W-I-21012021-Dumbryden Road | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-02-18 | 2021-08-13 | 2022-03-28 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623.71 | 623.71 | 30000 | 0 | 0 | 30623.71 | 0 | 0 | 0 | 0 | 30623.71 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505345 | S-W-I-210220-Chesser Pipebridge Safety Gate | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-02-21 |  | 2021-05-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | -239.33 | 2010.67 | 239.33 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2250 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506742 | S-W-I-210520-Drought Mitigation - Jockstown Link Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-05-22 |  | 2020-06-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13438.86 | 13438.86 | 0 | 0 | 0 | 13438.86 | 0 | 0 | 0 | 0 | 13438.86 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506745 | S-W-I-210520-Garwald Water Pumping - Drought Mitigation Measures | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-05-22 |  | 2020-07-20 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45847.39 | 45847.39 | 0 | 0 | 0 | 45847.39 | 0 | 0 | 0 | 0 | 45847.39 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508317 | S-W-I-210820 Nethan Bridge TM condition assessment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-09-01 | 2021-01-18 | 2021-05-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29211 | 29211 | 13388.58 | 0 | 0 | 42599.58 | 0 | 0 | 0 | 0 | 42599.58 | 311236.79 | [5 empty] | N | CM_M&G | 100%
508318 | S-W-I-210820-Townhead Street inch main abandonment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-09-01 | 2022-04-01 | 2022-11-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17857 | 17857 | 32142.88 | 0 | 0 | 49999.88 | 0 | 0 | 0 | 0 | 49999.88 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508836 | S-W-I-210920-Croftjane and Eccles Penpont Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12889.11 | 12889.11 | 0 | 0 | 0 | 12889.11 | 0 | 0 | 0 | 0 | 12889.11 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509373 | S-W-I-211020-Waterston DSR Bypass PRV | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2198.2 | 2198.2 | 0 | 0 | 0 | 2198.2 | 0 | 0 | 0 | 0 | 2198.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509391 | S-W-I-221020-Pateshill Trunk Main Valves Health and Safety Improvement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.31 | 981.31 | 14018.69 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509958 | S-W-I-241120 Airdrie Road mains replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-12-08 | 2021-07-05 | 2022-01-03 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17256.72 | 17256.72 | 32785.77 | 0 | 0 | 50042.49 | 0 | 0 | 0 | 0 | 50042.49 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509971 | S-W-I-241120-Chapleknowe Culvert Canonbie - Diversion | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2020-11-30 |  | 2021-02-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4904.57 | 4904.57 | 0 | 0 | 0 | 4904.57 | 0 | 0 | 0 | 0 | 4904.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509972 | S-W-I-241120-Ellenbank Cummertrees - Mains Upgrade | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-11-30 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3049.53 | 3049.53 | 0 | 0 | 0 | 3049.53 | 0 | 0 | 0 | 0 | 3049.53 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509967 | S-W-I-241120-Link Main at Gala Terrace Galashiels | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331.31 | 1331.31 | 19018.69 | 0 | 0 | 20350 | 0 | 0 | 0 | 0 | 20350 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503955 | S-W-I-251119-Millisle Street Dalbeattie - Mains Replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-11-28 |  | 2019-12-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 9364.95 | 0 | 9364.95 | 0 | 0 | 0 | 9364.95 | 0 | 0 | 0 | 0 | 9364.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503966 | S-W-I-251119-Pennersaughs Farm Eaglesfied - Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2019-11-28 |  | 2020-02-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 32696.15 | 0 | 32696.15 | -2696.15 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503976 | S-W-I-261119-Mill Road Lochmaben Link Main 90m | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2019-11-28 |  | 2020-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 17992.36 | 0 | 17992.36 | -492.36 | 0 | 0 | 17500 | 0 | 0 | 0 | 0 | 17500 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507883 | S-W-I-27072020-West Bretton - Link Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-27 |  | 2020-07-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7622.19 | 7622.19 | 0 | 0 | 0 | 7622.19 | 0 | 0 | 0 | 0 | 7622.19 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508432 | S-W-I-270820-Stonebyres Bridge Mains Diversion | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-08-28 |  | 2020-11-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21542.76 | 21542.76 | 0 | 0 | 0 | 21542.76 | 0 | 0 | 0 | 0 | 21542.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510944 | S-W-I-280121-Oakbank Meter Install | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2523.36 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508987 | S-W-I-280920- 56 Balmore-Glenhove TM scour survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-10-06 | 2021-01-15 | 2021-07-05 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7956 | 7956 | 2044.47 | 0 | 0 | 10000.47 | 0 | 0 | 0 | 0 | 10000.47 | 311236.79 | [5 empty] | N | CM_M&G | 100%
503984 | S-W-I-Cowgill Road Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-26 |  | 2019-12-20 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2696.64 | 0 | 2696.64 | 0 | 0 | 0 | 2696.64 | 0 | 0 | 0 | 0 | 2696.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503977 | S-W-I-Lovedale Road and Euchan St Sanquhar - Mains Abandonment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-11-28 |  | 2020-03-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 16567.77 | 0 | 16567.77 | 0 | 0 | 0 | 16567.77 | 0 | 0 | 0 | 0 | 16567.77 | 311236.79 | [5 empty] | N | CM_WSI | 100%
30934 | Swinstie (Cleland) STW Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-08 | 2010-11-16 | 2011-07-11 | 2012-03-16 | 2012-03-26 | North Lanarkshire | 966437.16 | 0 | 738.1 | 0 | 0 | 0 | 0 | 0 | 738.1 | 0 | 0 | 0 | 967175.26 | 0 | 0 | 0 | 0 | 967175.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500183 | Swinstie DOA (DOA000553) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-18 | 2018-01-31 | 2018-01-31 | North Lanarkshire | 0 | 0 | 90527 | 79975 | 30582.11 | 141.17 | 0 | 0 | 201225.28 | 0 | 0 | 0 | 201225.28 | 0 | 0 | 0 | 0 | 201225.28 | 0 | [5 empty] | Y | CS16D | 100% | [39 empty] | 1 | [27 empty] | 0
501314 | Swinstie Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-12-23 | 2018-01-23 | 2018-01-24 | 2019-02-13 |  | South Lanarkshire | 0 | 0 | 289255 | 174822 | 775529 | 2337639.6 | 754.4 | -47927.79 | 3530072.21 | 0 | 0 | 0 | 3530072.21 | 0 | 0 | 0 | 0 | 3530072.21 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501166 | Swinstie STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2015-11-25 | 2018-06-22 | 2018-06-28 | 2021-03-24 |  | South Lanarkshire | 0 | 0 | 17500 | 136005.61 | 72979.6 | 1052101.05 | 1020024.44 | 256233.43 | 2554844.13 | 4107.38 | 0 | 0 | 2558951.51 | 0 | 0 | 0 | 0 | 2558951.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
403191 | Swinstie WwTW Automatic Control | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-12-18 | 2013-03-25 | 2013-04-15 | 2015-09-25 |  | South Lanarkshire | 414909 | 0 | 0 | 177 | 7722.33 | 0 | 0 | 0 | 7899.33 | 0 | 0 | 0 | 422808.33 | 0 | 0 | 0 | 0 | 422808.33 | 90601.29 | [5 empty] | N | CM_WWI | 100%
45558 | Swinton STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-02-14 | 2011-08-26 | 2012-03-21 | 2012-03-30 | Scottish Borders | 866115.65 | 0 | 542.49 | 0 | 0 | 0 | 0 | 0 | 542.49 | 0 | 0 | 0 | 866658.14 | 0 | 0 | 0 | 0 | 866658.14 | 119362.42 | [5 empty] | N | CM_WWNI | 50% | WQ01 | 50%
500970 | SWM - Impact & Analysis - Stakeholder Engagement -Education and Communication | Q&S4 | Reducing flooding and pollution from sewers | Surface Water |  |  | Wastewater |  | SWD | Surface Water | MS3 | 2016-03-15 | 2016-03-15 | 2016-06-24 | 2021-06-25 | 2021-06-25 | Scottish Water Wide | 0 | 0 | 58977.37 | 101022.63 | 326694.3 | 376600.43 | 40151.39 | 0 | 903446.12 | 0 | 0 | 0 | 903446.12 | 0 | 0 | 0 | 0 | 903446.12 | 1335609.71 | [5 empty] | N | CS15C | 100%
49606 | SWMD - Investment Profile Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | General |  | SWMD | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | RISK | 100%
506035 | S-W-NI-010420- Fruid DIR Menzion intake replacement door | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-01 |  | 2020-06-11 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148.55 | 1148.55 | 0 | 0 | 0 | 1148.55 | 0 | 0 | 0 | 0 | 1148.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506022 | S-W-NI-010420-Castle Moffat WTW septic tank flooding | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-01 |  | 2020-04-15 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2032.4 | 2032.4 | 0 | 0 | 0 | 2032.4 | 0 | 0 | 0 | 0 | 2032.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506034 | S-W-NI-010420-Hopes WTW Outlet Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-01 |  | 2020-04-15 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8282.45 | 8282.45 | 0 | 0 | 0 | 8282.45 | 0 | 0 | 0 | 0 | 8282.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506038 | S-W-NI-010420-Rosebery WTW Chlorine changeover unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-01 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548.38 | 548.38 | 7551.62 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 8100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506039 | S-W-NI-010420-Strutherhill DSR Altitude Valve & Flow Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-01 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18400 | 0 | 0 | 18400 | 0 | 0 | 0 | 0 | 18400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506915 | S-W-NI-010620-Camps WTW Security CCTV | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5350.05 | 5350.05 | 0 | 0 | 0 | 5350.05 | 0 | 0 | 0 | 0 | 5350.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506918 | S-W-NI-010620-Megget Reservoir Barrier Security Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-03 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2854.15 | 2854.15 | 0 | 0 | 0 | 2854.15 | 0 | 0 | 0 | 0 | 2854.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507462 | S-W-NI-010720-Castle Moffat wtw - Chlorine policy compliance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-02 |  | 2020-10-05 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925.3 | 1925.3 | 0 | 0 | 0 | 1925.3 | 0 | 0 | 0 | 0 | 1925.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507478 | S-W-NI-010720-Fruid Reservoir Condensation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-02 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718.71 | 718.71 | 9981.3 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507474 | S-W-NI-010720-Fruid Reservoir Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-07-02 |  | 2021-03-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7484.35 | 7484.35 | -2284.35 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 5200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507468 | S-W-NI-010720-Sludge Press Performance Monitoring | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-02 |  | 2020-09-21 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2905.61 | 2905.61 | 0 | 0 | 0 | 2905.61 | 0 | 0 | 0 | 0 | 2905.61 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507465 | S-W-NI-010720-Talla Reservoir lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-02 |  | 2020-11-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1939.51 | 1939.51 | 0 | 0 | 0 | 1939.51 | 0 | 0 | 0 | 0 | 1939.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509051 | S-W-NI-011020-Marchbank WTW Hypo Dosing Points | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-08 | 2021-06-21 | 2022-02-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612 | 2612 | 27388.06 | 0 | 0 | 30000.06 | 0 | 0 | 0 | 0 | 30000.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509054 | S-W-NI-011020-Marchbank WTW-Front End Auto Shutdown | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-11-23 | 2020-12-14 | 2021-05-17 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6688 | 6688 | -1532.26 | 0 | 0 | 5155.74 | 0 | 0 | 0 | 0 | 5155.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506945 | S-W-NI-020620-Deans SR Drainage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-06-03 |  | 2021-03-30 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225.13 | 3225.13 | 0 | 0 | 0 | 3225.13 | 0 | 0 | 0 | 0 | 3225.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506952 | S-W-NI-020620-Megget Reservoir Fence Renewal | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-03 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4996.51 | 4996.51 | 0 | 0 | 0 | 4996.51 | 0 | 0 | 0 | 0 | 4996.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504993 | S-W-NI-030220-Castle Moffat WTW- Sludge Plant Pipework Tanker Mods | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | -1673.01 | 127 | 1673.01 | 0 | 0 | 1800.01 | 0 | 0 | 0 | 0 | 1800.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504982 | S-W-NI-030220-Crosswood Reservoir fence remedials | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-06 |  | 2020-05-28 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 929.06 | 12129.06 | 0 | 0 | 0 | 12129.06 | 0 | 0 | 0 | 0 | 12129.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506076 | S-W-NI-030420-Daer WTW filter gallery ingress | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-15 | 2020-11-10 | 2021-05-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9981 | 9981 | 2018.73 | 0 | 0 | 11999.73 | 0 | 0 | 0 | 0 | 11999.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506988 | S-W-NI-030620-Rosebery WTW Washwater bay No1 mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-31 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6426.76 | 6426.76 | 0 | 0 | 0 | 6426.76 | 0 | 0 | 0 | 0 | 6426.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506477 | S-W-NI-050520-Marchbank WTW DAF Compressors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-05 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.43 | 222.43 | 3177.57 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506476 | S-W-NI-050520-Pateshill WTW Sludge press wash water system | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-05 |  | 2020-06-03 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12170.46 | 12170.46 | 0 | 0 | 0 | 12170.46 | 0 | 0 | 0 | 0 | 12170.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507528 | S-W-NI-060720-Traprain Law TWS roof repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-06 |  | 2020-07-29 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1963.13 | 1963.13 | 0 | 0 | 0 | 1963.13 | 0 | 0 | 0 | 0 | 1963.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510558 | S-W-NI-07012021-Glencorse Hypo Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-22 | 2021-07-16 | 2022-02-28 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487.01 | 487.01 | 60000 | 0 | 0 | 60487.01 | 0 | 0 | 0 | 0 | 60487.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504540 | S-W-NI-070120-Rawburn wtw Poly Plant Fault Emergency Shutdown | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-15 | 2020-08-12 | 2021-07-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4340.54 | 46069.46 | 50410 | 13856.54 | 0 | 0 | 64266.54 | 0 | 0 | 0 | 0 | 64266.54 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505066 | S-W-NI-07022020-Glencorse Lime Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-02-27 |  | 2020-08-21 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 26500 | 53546.92 | 80046.92 | 0 | 0 | 0 | 80046.92 | 0 | 0 | 0 | 0 | 80046.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505078 | S-W-NI-070220-Drumpellier PBS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-03-27 | 2022-04-08 | 2022-09-28 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 230.71 | 8413.29 | 8644 | 91356.31 | 0 | 0 | 100000.31 | 0 | 0 | 0 | 0 | 100000.31 | 119022.58 | [5 empty] | N | WSNI | 100%
507555 | S-W-NI-070720-Daer WTW clarifier roof drainage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-15 | 2021-07-05 | 2021-11-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3642 | 3642 | 46358.08 | 0 | 0 | 50000.08 | 0 | 0 | 0 | 0 | 50000.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511115 | S-W-NI-08022021-Lanarkshire DSR flooring condition assessment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-18 | 2021-08-13 | 2022-03-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098.5 | 1098.5 | 8901.5 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511111 | S-W-NI-080221-Glassford DSR Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-18 | 2021-08-13 | 2022-03-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1173.51 | 1173.51 | 12826.49 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 14000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507570 | S-W-NI-080720-Burnswark WPS - Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-10 |  | 2020-10-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23148.17 | 23148.17 | 0 | 0 | 0 | 23148.17 | 0 | 0 | 0 | 0 | 23148.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504247 | S-W-NI-091219-Rosebery WTW Alba dosing pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-12 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | -3271.03 | 228.97 | 3271.03 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507137 | S-W-NI-100620-Edinburgh & Lothian DSR inlet control | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-06-11 |  | 2020-09-10 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42996.62 | 42996.62 | 3.38 | 0 | 0 | 43000 | 0 | 0 | 0 | 0 | 43000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505140 | S-W-NI-110220-Throughburn TWP MCC replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-03-27 | 2020-06-09 | 2021-02-25 | 2021-11-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106760 | 106760 | 233239.6 | 0 | 0 | 339999.6 | 0 | 0 | 0 | 0 | 339999.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511726 | S-W-NI-110321-Black Esk WTW - RGF No6 Media and Nozzle Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3286.47 | 3286.47 | 46663.54 | 0 | 0 | 49950 | 0 | 0 | 0 | 0 | 49950 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511727 | S-W-NI-110321-Black Esk WTW - Sludge Transfer pump No2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322.52 | 322.52 | 4225.74 | 0 | 0 | 4548.26 | 0 | 0 | 0 | 0 | 4548.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511731 | S-W-NI-110321-Crosswood WTW Power Kiosk | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-11 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1457.16 | 0 | 0 | 1568.37 | 0 | 0 | 0 | 0 | 1568.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511729 | S-W-NI-110321-Glengap WTW - Sludge thickener feed pumps x2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 926.36 | 926.36 | 13233.64 | 0 | 0 | 14160 | 0 | 0 | 0 | 0 | 14160 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511733 | S-W-NI-110321-Kingston DSR Sample Point | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-11 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389.25 | 389.25 | 5100 | 0 | 0 | 5489.25 | 0 | 0 | 0 | 0 | 5489.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511739 | S-W-NI-110321-Marchbank WTW - Auto Coag Control | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-11 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735.98 | 735.98 | 9642.84 | 0 | 0 | 10378.82 | 0 | 0 | 0 | 0 | 10378.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511735 | S-W-NI-110321-Marchbank WTW Ammonia Dosing Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-11 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3256.89 | 3256.89 | 3.11 | 0 | 0 | 3260 | 0 | 0 | 0 | 0 | 3260 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511730 | S-W-NI-110321-Penwhirn WTW - Thickened sludge mixing pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508.06 | 508.06 | 6411.42 | 0 | 0 | 6919.48 | 0 | 0 | 0 | 0 | 6919.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511743 | S-W-NI-110321-Penwhirn WTW & Ringford BH WTW - Portable Spectrophotometers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5550.77 | 5550.77 | -90.77 | 0 | 0 | 5460 | 0 | 0 | 0 | 0 | 5460 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511741 | S-W-NI-110321-Rosebery WTW Coagulation pH Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-11 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336.92 | 336.92 | 4414.26 | 0 | 0 | 4751.18 | 0 | 0 | 0 | 0 | 4751.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511742 | S-W-NI-110321-Rosebery WTW Filters 1 - 4 access improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-11 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142.94 | 142.94 | 1872.84 | 0 | 0 | 2015.78 | 0 | 0 | 0 | 0 | 2015.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511754 | S-W-NI-120321-Camps WTW Chlorine Change Over Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.91 | 529.91 | 6942.84 | 0 | 0 | 7472.75 | 0 | 0 | 0 | 0 | 7472.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511756 | S-W-NI-120321-Coulter WTW DAF Compressor Faults | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492.29 | 492.29 | 6450 | 0 | 0 | 6942.29 | 0 | 0 | 0 | 0 | 6942.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511760 | S-W-NI-120321-East Lodge Lilliesleaf - Replacement of 3 inch CI Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 1260 | 18000 | 0 | 0 | 19260 | 0 | 0 | 0 | 0 | 19260 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511758 | S-W-NI-120321-Fruid Farm UV WTW RW storage tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2433.64 | 2433.64 | 34766.36 | 0 | 0 | 37200 | 0 | 0 | 0 | 0 | 37200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511765 | S-W-NI-120321-Hillend Low Flow control valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323.83 | 323.83 | 4242.84 | 0 | 0 | 4566.67 | 0 | 0 | 0 | 0 | 4566.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511768 | S-W-NI-120321-Penwhirn WTW Wash water poly dosing pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 497.2 | 497.2 | 6514.26 | 0 | 0 | 7011.46 | 0 | 0 | 0 | 0 | 7011.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511759 | S-W-NI-120321-Roberton WTW - RGF Media Inspection | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-15 |  | 2021-06-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.73 | 276.73 | 3625.74 | 0 | 0 | 3902.47 | 0 | 0 | 0 | 0 | 3902.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504629 | S-W-NI-130120-Carrickstone Low path | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-15 |  | 2020-02-11 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2979.46 | 0 | 2979.46 | 0 | 0 | 0 | 2979.46 | 0 | 0 | 0 | 0 | 2979.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504632 | S-W-NI-130120-Rawburn WTW - Handrailing at Clarifier Steps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-15 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | -1401.87 | 98.13 | 1401.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504631 | S-W-NI-130220-Daer WTW Security Gate | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-15 |  | 2020-07-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | -71.07 | 2128.93 | 0 | 0 | 0 | 2128.93 | 0 | 0 | 0 | 0 | 2128.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505717 | S-W-NI-13032020 - Legbrannock Hammer Test | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-04-01 | 2020-10-19 | 2020-11-26 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11352.02 | 11352.02 | 0 | 0 | 0 | 11352.02 | 0 | 0 | 0 | 0 | 11352.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505724 | S-W-NI-13032020-Camps UV WTW Main out | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-03-31 | 2020-06-22 | 2021-05-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 311236.79 | [5 empty] | N | CM_M&G | 100%
507634 | S-W-NI-130720-Coulter WTW DAF (Supernatant) Turbidity Monitors (2) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-14 |  | 2020-08-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12832.14 | 12832.14 | 0 | 0 | 0 | 12832.14 | 0 | 0 | 0 | 0 | 12832.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507643 | S-W-NI-130720-Daer Clarifier concrete repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-07-15 | 2020-12-07 | 2022-01-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132607 | 132607 | 11393.33 | 0 | 0 | 144000.33 | 0 | 0 | 0 | 0 | 144000.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507641 | S-W-NI-130720-Daer WTW Platform Chemical Loading Bay | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-14 |  | 2020-09-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8078.26 | 8078.26 | 0 | 0 | 0 | 8078.26 | 0 | 0 | 0 | 0 | 8078.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507639 | S-W-NI-130720-East Craigs General Site Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-15 | 2021-06-07 | 2021-09-03 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4680 | 4680 | 5319.52 | 0 | 0 | 9999.52 | 0 | 0 | 0 | 0 | 9999.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507642 | S-W-NI-130720-Glencorse WTW General Site Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-07-15 | 2021-03-05 | 2022-01-10 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1639 | 1639 | 11361.35 | 0 | 0 | 13000.35 | 0 | 0 | 0 | 0 | 13000.35 | 119022.58 | [5 empty] | N | WSNI | 100%
507647 | S-W-NI-130720-Marchbank WTW General Site Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-15 | 2021-06-07 | 2021-09-03 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269.72 | 269.72 | 10758.42 | 0 | 0 | 11028.14 | 0 | 0 | 0 | 0 | 11028.14 | 119022.58 | [5 empty] | N | WSNI | 100%
507649 | S-W-NI-130720-Pateshill Lime Silo Access | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-15 | 2021-04-05 | 2021-09-20 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5602 | 5602 | 17398.14 | 0 | 0 | 23000.14 | 0 | 0 | 0 | 0 | 23000.14 | 119022.58 | [5 empty] | N | WSNI | 100%
507646 | S-W-NI-130720-Pateshill WTW General Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-15 | 2021-06-07 | 2021-09-03 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1586 | 1586 | 9414.36 | 0 | 0 | 11000.36 | 0 | 0 | 0 | 0 | 11000.36 | 119022.58 | [5 empty] | N | WSNI | 100%
507673 | S-W-NI-140720-Crosswood WTW UV pipework modification | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-14 |  | 2020-09-08 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5538.98 | 5538.98 | 0 | 0 | 0 | 5538.98 | 0 | 0 | 0 | 0 | 5538.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507668 | S-W-NI-140720-Pateshill wtw Chlorine Gas Inspection Window | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-07-14 |  | 2021-03-08 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043.46 | 2043.46 | 0 | 0 | 0 | 2043.46 | 0 | 0 | 0 | 0 | 2043.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507676 | S-W-NI-140720-Rosebery WTW - Raw and final pH monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-14 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4330.15 | 4330.15 | 2169.86 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507670 | S-W-NI-140720-Rosebery WTW Flooring | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-14 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422.81 | 422.81 | 5897.19 | 0 | 0 | 6320 | 0 | 0 | 0 | 0 | 6320 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508728 | S-W-NI-140920-Marchbank WTW - DAF Air Compressor control system | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-14 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.87 | 121.87 | 1598.13 | 0 | 0 | 1720 | 0 | 0 | 0 | 0 | 1720 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508730 | S-W-NI-140920-Pateshill WTW - Air Compressor control system | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-14 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.97 | 130.97 | 1585.04 | 0 | 0 | 1716 | 0 | 0 | 0 | 0 | 1716 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508733 | S-W-NI-140920-Rosebery WTW DAF Compressor control | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-14 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.97 | 130.97 | 1585.04 | 0 | 0 | 1716 | 0 | 0 | 0 | 0 | 1716 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508724 | S-W-NI-140920-Rosebery WTW new press cloths | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-14 |  | 2021-02-20 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9404.74 | 9404.74 | 0 | 0 | 0 | 9404.74 | 0 | 0 | 0 | 0 | 9404.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508723 | S-W-NI-140920-Rosebery WTW Press No1 Ram pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-14 |  | 2021-02-20 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4956.65 | 4956.65 | 2043.36 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 7000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508727 | S-W-NI-140920-Rosebery WTW Press No2 plate lifters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-14 |  | 2021-02-20 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3228.7 | 3228.7 | 0 | 0 | 0 | 3228.7 | 0 | 0 | 0 | 0 | 3228.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508737 | S-W-NI-140920-West water DIR compensation building ceiling | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-14 |  | 2020-11-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3685.9 | 3685.9 | 0 | 0 | 0 | 3685.9 | 0 | 0 | 0 | 0 | 3685.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510294 | S-W-NI-141220-Auchneel WTW - UPS modifications | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1549.71 | 1549.71 | 0 | 0 | 0 | 1549.71 | 0 | 0 | 0 | 0 | 1549.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510300 | S-W-NI-141220-Black Esk WTW - Alum Dosing Pump Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-16 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3204.98 | 3204.98 | 0 | 0 | 0 | 3204.98 | 0 | 0 | 0 | 0 | 3204.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510309 | S-W-NI-141220-Black Esk WTW - Sludge Thickener Pipework Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-16 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101.33 | 2101.33 | 0 | 0 | 0 | 2101.33 | 0 | 0 | 0 | 0 | 2101.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510312 | S-W-NI-141220-Glengap WTW - Poly Pumps Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-16 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5583.26 | 5583.26 | 0 | 0 | 0 | 5583.26 | 0 | 0 | 0 | 0 | 5583.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510314 | S-W-NI-141220-Glengap WTW - Pump Powerpack Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-16 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4823.38 | 4823.38 | 0 | 0 | 0 | 4823.38 | 0 | 0 | 0 | 0 | 4823.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511239 | S-W-NI-150221-Dechmont DSR - Daer inlet flow control | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-24 | 2022-09-15 | 2023-04-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5233.64 | 5233.64 | 74766.36 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 80000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511228 | S-W-NI-150221-Howden WTW - Membrane Discharge Pipe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883.18 | 883.18 | 12616.8 | 0 | 0 | 13499.98 | 0 | 0 | 0 | 0 | 13499.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511235 | S-W-NI-150221-Manse St WTW - Raw Water Inlet Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531.21 | 531.21 | 7588.8 | 0 | 0 | 8120.01 | 0 | 0 | 0 | 0 | 8120.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511223 | S-W-NI-150221-Rawburn WTW - Sludge Trailer Tow Bar | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.71 | 137.71 | 1967.3 | 0 | 0 | 2105.01 | 0 | 0 | 0 | 0 | 2105.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511245 | S-W-NI-150221-Roberton WTW - Clarifier Access Cover | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268.18 | 1268.18 | 18116.8 | 0 | 0 | 19384.98 | 0 | 0 | 0 | 0 | 19384.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511241 | S-W-NI-150221-Roberton WTW - Final Aluminium Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 818.41 | 818.41 | 11691.6 | 0 | 0 | 12510.01 | 0 | 0 | 0 | 0 | 12510.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511226 | S-W-NI-150221-Yarrowfeus WTW - DOC and Turbidity Instruments | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 5000 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511778 | S-W-NI-150321-Lothian Welfare Units | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000.04 | 0 | 0 | 50000.04 | 0 | 0 | 0 | 0 | 50000.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507704 | S-W-NI-150720-Hartwood WPS Lochmaben - Pump Renewal | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-15 |  | 2020-08-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2509.74 | 2509.74 | 0 | 0 | 0 | 2509.74 | 0 | 0 | 0 | 0 | 2509.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507695 | S-W-NI-150720-Relc DSR - Stockproof Perimeter Fence Upgrade | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-07-15 |  | 2020-08-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925.42 | 1925.42 | 0 | 0 | 0 | 1925.42 | 0 | 0 | 0 | 0 | 1925.42 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508766 | S-W-NI-150920-Glengap WTW - Various PLC software modifications | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-16 |  | 2021-02-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3841.54 | 3841.54 | 0 | 0 | 0 | 3841.54 | 0 | 0 | 0 | 0 | 3841.54 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508758 | S-W-NI-150920-Lochinvar WTW - DAF air control System Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-16 |  | 2021-03-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10165 | 10165 | 0 | 0 | 0 | 10165 | 0 | 0 | 0 | 0 | 10165 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508753 | S-W-NI-150920-Newcastleton WTW road repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-16 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610.83 | 610.83 | 8440.18 | 0 | 0 | 9051 | 0 | 0 | 0 | 0 | 9051 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509282 | S-W-NI-151020-Camps WTW Lime pipework re-route | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-15 |  | 2020-03-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6272.87 | 6272.87 | 0 | 0 | 0 | 6272.87 | 0 | 0 | 0 | 0 | 6272.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509285 | S-W-NI-151020-Coulter WTW DAF investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-23 | 2022-04-01 | 2022-11-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2308 | 2308 | 7692.32 | 0 | 0 | 10000.32 | 0 | 0 | 0 | 0 | 10000.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509286 | S-W-NI-151020-Elsrickle temporary booster pump power supply | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-23 | 2022-04-01 | 2022-11-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2904 | 2904 | 17096.44 | 0 | 0 | 20000.44 | 0 | 0 | 0 | 0 | 20000.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509279 | S-W-NI-151020-Fruid Reservoir Building Doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-15 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122.99 | 122.99 | 1757.01 | 0 | 0 | 1880 | 0 | 0 | 0 | 0 | 1880 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509276 | S-W-NI-151020-Rawburn WTW Poly Building Doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-15 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131.5 | 131.5 | 1878.5 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 2010 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509275 | S-W-NI-151020-Rosebery wtw Saturator inlet valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-15 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556.07 | 556.07 | 7943.93 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 8500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510341 | S-W-NI-151220-Black Esk WTW - Chlorinated Sample Pumps x2 Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-16 |  | 2021-03-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4127.38 | 4127.38 | 0 | 0 | 0 | 4127.38 | 0 | 0 | 0 | 0 | 4127.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510320 | S-W-NI-151220-Glengap WTW - Sludge Press Plate Shifter Blocks Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-16 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557.46 | 1557.46 | 0 | 0 | 0 | 1557.46 | 0 | 0 | 0 | 0 | 1557.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510340 | S-W-NI-151220-Penwhirn WTW - Poly Dosing Pipework Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-16 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1628.29 | 1628.29 | 0 | 0 | 0 | 1628.29 | 0 | 0 | 0 | 0 | 1628.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510323 | S-W-NI-151220-Penwhirn WTW - Boxed spare clothwash pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360.75 | 1360.75 | 19439.25 | 0 | 0 | 20800 | 0 | 0 | 0 | 0 | 20800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510327 | S-W-NI-151220-Penwhirn WTW - cloth wash pump repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-16 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4906.01 | 4906.01 | 0 | 0 | 0 | 4906.01 | 0 | 0 | 0 | 0 | 4906.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510336 | S-W-NI-151220-Penwhirn WTW - Repair Sludge Ram Pump C | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614.04 | 614.04 | 8485.97 | 0 | 0 | 9100 | 0 | 0 | 0 | 0 | 9100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510330 | S-W-NI-151220-Penwhirn WTW - Sludge Press Filter Cloth Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1711.14 | 1711.14 | 24158.87 | 0 | 0 | 25870 | 0 | 0 | 0 | 0 | 25870 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510345 | S-W-NI-151220-Winterhope WTW - Chlorinated Sample Pumps x3 Replacemen | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-16 |  | 2021-04-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4805.57 | 4805.57 | 0 | 0 | 0 | 4805.57 | 0 | 0 | 0 | 0 | 4805.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504680 | S-W-NI-160120-Carsphairn WTW - Generator Control Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-24 |  | 2020-02-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 5622.9 | 0 | 5622.9 | 0 | 0 | 0 | 5622.9 | 0 | 0 | 0 | 0 | 5622.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504693 | S-W-NI-160120-Glengap WTW - Sample waste pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-24 |  | 2020-04-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 8850 | -43.79 | 8806.21 | 0 | 0 | 0 | 8806.21 | 0 | 0 | 0 | 0 | 8806.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504686 | S-W-NI-160120-Lochfoot Store WTW - Access Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-24 |  | 2020-02-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 5073.64 | 0 | 5073.64 | 0 | 0 | 0 | 5073.64 | 0 | 0 | 0 | 0 | 5073.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511260 | S-W-NI-160221-Castle Moffat WTW Clarifiers H and S work | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-16 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7719.63 | 7719.63 | 110280.35 | 0 | 0 | 117999.98 | 0 | 0 | 0 | 0 | 117999.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511258 | S-W-NI-160221-Castle Moffat WTW Sludge Press Cloths | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-16 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650.28 | 650.28 | 9289.7 | 0 | 0 | 9939.98 | 0 | 0 | 0 | 0 | 9939.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511250 | S-W-NI-160221-Roberton WTW - Raw Water Inlet Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306.82 | 306.82 | 4383.2 | 0 | 0 | 4690.02 | 0 | 0 | 0 | 0 | 4690.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511253 | S-W-NI-160221-Roberton WTW - Thickener Feed Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832.8 | 832.8 | 11897.2 | 0 | 0 | 12730 | 0 | 0 | 0 | 0 | 12730 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511259 | S-W-NI-160221-Roberton WTW and Manse St WTW - Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-18 |  | 2021-04-04 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4294.35 | 4294.35 | 5.65 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511262 | S-W-NI-160221-West Netherton DSR - inlet outlet meter replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-16 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4696.27 | 4696.27 | 8203.73 | 0 | 0 | 12900 | 0 | 0 | 0 | 0 | 12900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507729 | S-W-NI-160720-Troqueer WWTW-Replace Access Platform | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-10-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3003.63 | 3003.63 | 0 | 0 | 0 | 3003.63 | 0 | 0 | 0 | 0 | 3003.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510358 | S-W-NI-161220-Carlops DSR Battery Pack | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1415.74 | 1415.74 | 5384.27 | 0 | 0 | 6800 | 0 | 0 | 0 | 0 | 6800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510353 | S-W-NI-161220-Castle Moffat WTW Improve Lighting and Heating | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600.44 | 1600.44 | 0 | 0 | 0 | 1600.44 | 0 | 0 | 0 | 0 | 1600.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510361 | S-W-NI-161220-Pateshill WTW Cl2 gas pressure Manifolds and pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801.42 | 1801.42 | 25448.59 | 0 | 0 | 27250 | 0 | 0 | 0 | 0 | 27250 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504703 | S-W-NI-170120-Glencorse WTW Ammonia Bund | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-04-21 | 2021-05-04 | 2021-10-19 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 230.82 | 18845.18 | 19076 | 156124.04 | 0 | 0 | 175200.04 | 0 | 0 | 0 | 0 | 175200.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505235 | S-W-NI-17022020-Glencorse DIR Road repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-03-13 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 18500 | -258.72 | 18241.28 | 0 | 0 | 0 | 18241.28 | 0 | 0 | 0 | 0 | 18241.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505230 | S-W-NI-170220-Castle Moffat WTW Alum Dosing Line | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-06-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | -854.07 | 2045.93 | 0 | 0 | 0 | 2045.93 | 0 | 0 | 0 | 0 | 2045.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505232 | S-W-NI-170220-Castle Moffat WTW Raw water colour monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | -19607.7 | 1392.3 | 19607.7 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 21000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511281 | S-W-NI-170221-Camps WTW Service Water Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 353.27 | 5046.75 | 0 | 0 | 5400.02 | 0 | 0 | 0 | 0 | 5400.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511283 | S-W-NI-170221-Daer WTW Lime Pump Heads replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213.27 | 213.27 | 3046.75 | 0 | 0 | 3260.02 | 0 | 0 | 0 | 0 | 3260.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511294 | S-W-NI-170221-Pateshill WTW press cloths | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698.36 | 698.36 | 9976.65 | 0 | 0 | 10675.01 | 0 | 0 | 0 | 0 | 10675.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511293 | S-W-NI-170221-Rosebery WTW Alba dosing Pump A | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-18 |  | 2021-04-04 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2282.81 | 2282.81 | 7.2 | 0 | 0 | 2290.01 | 0 | 0 | 0 | 0 | 2290.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511292 | S-W-NI-170221-Rosebery WTW Coag pH monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 2056.05 | 0 | 0 | 2199.98 | 0 | 0 | 0 | 0 | 2199.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508222 | S-W-NI-170820-Auchneel WTW - Raw water colour monitor replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-07-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15751.36 | 15751.36 | 0 | 0 | 0 | 15751.36 | 0 | 0 | 0 | 0 | 15751.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508231 | S-W-NI-170820-Cargen BH WTW - Water Softener Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-08-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1562.71 | 1562.71 | 0 | 0 | 0 | 1562.71 | 0 | 0 | 0 | 0 | 1562.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508209 | S-W-NI-170820-Lochinvar WTW - Contact Tank Cl2 sample pump Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375.02 | 2375.02 | 0 | 0 | 0 | 2375.02 | 0 | 0 | 0 | 0 | 2375.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508216 | S-W-NI-170820-Moffat WTW - Hypo dosing Plc watchdog Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-08-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2578.73 | 2578.73 | 0 | 0 | 0 | 2578.73 | 0 | 0 | 0 | 0 | 2578.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508217 | S-W-NI-170820-Penwhirn WTW - ALBA Dosing Pump Auto Stroke Positioners Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5070.44 | 5070.44 | 0 | 0 | 0 | 5070.44 | 0 | 0 | 0 | 0 | 5070.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508205 | S-W-NI-170820-Terregles BH WTW - Hypo Dosing System Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-08-20 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1990.89 | 1990.89 | 0 | 0 | 0 | 1990.89 | 0 | 0 | 0 | 0 | 1990.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508804 | S-W-NI-170920-Penwhirn WTW - Cloth wash pump system refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2498.55 | 2498.55 | 0 | 0 | 0 | 2498.55 | 0 | 0 | 0 | 0 | 2498.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508800 | S-W-NI-170920-Ringford BH WTW - Critical Spare CL2 Pump and UPS System | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5805.29 | 5805.29 | 0 | 0 | 0 | 5805.29 | 0 | 0 | 0 | 0 | 5805.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508787 | S-W-NI-170920-Winterhope WTW - Auma Actuators Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-24 |  | 2020-11-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6906.97 | 6906.97 | 0 | 0 | 0 | 6906.97 | 0 | 0 | 0 | 0 | 6906.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508785 | S-W-NI-170920-Winterhope WTW - Sludge Thickeners Access Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-24 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21382.19 | 21382.19 | 0 | 0 | 0 | 21382.19 | 0 | 0 | 0 | 0 | 21382.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508793 | S-W-NI-170920-Winterhope WTW - Standby Generator Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-24 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12700.19 | 12700.19 | 0 | 0 | 0 | 12700.19 | 0 | 0 | 0 | 0 | 12700.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504383 | S-W-NI-171219-Chalkieside DSR Sample Point | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-18 |  | 2020-03-10 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 6257.52 | 0 | 6257.52 | 0 | 0 | 0 | 6257.52 | 0 | 0 | 0 | 0 | 6257.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504386 | S-W-NI-171219-Fountainhall TWS Flow control valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-18 |  | 2020-10-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | -6542.06 | 457.94 | 0 | 0 | 0 | 457.94 | 0 | 0 | 0 | 0 | 457.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504367 | S-W-NI-171219-Glengap WTW - Hypo Dosing Kiosk and Tank Screens | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-18 |  | 2020-03-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 15474.02 | 0 | 15474.02 | 0 | 0 | 0 | 15474.02 | 0 | 0 | 0 | 0 | 15474.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504369 | S-W-NI-171219-Glengap WTW - Poly Dosing Tank Screens Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-18 |  | 2020-03-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | -131.71 | 8868.29 | 0 | 0 | 0 | 8868.29 | 0 | 0 | 0 | 0 | 8868.29 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504371 | S-W-NI-171219-GlengapWTW - Sludge Press Cloth Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-18 |  | 2020-04-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2465.55 | 0 | 2465.55 | 0 | 0 | 0 | 2465.55 | 0 | 0 | 0 | 0 | 2465.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504372 | S-W-NI-171219-Kettleton WTW - Access Path Handrail & Steps Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-18 |  | 2020-03-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2003.94 | 0 | 2003.94 | 0 | 0 | 0 | 2003.94 | 0 | 0 | 0 | 0 | 2003.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510737 | S-W-NI-180121-Bonnycraig WTW - Replacement Alum Dosing Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.89 | 425.89 | 6084.12 | 0 | 0 | 6510.01 | 0 | 0 | 0 | 0 | 6510.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510743 | S-W-NI-180121-Howden WTW - Membrane Plant Replacement Compressors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14250.47 | 14250.47 | 3.4 | 0 | 0 | 14253.87 | 0 | 0 | 0 | 0 | 14253.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510734 | S-W-NI-180121-Howden WTW - Replacement Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249.91 | 249.91 | 3570.08 | 0 | 0 | 3819.99 | 0 | 0 | 0 | 0 | 3819.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510742 | S-W-NI-180121-Hungry Snout RWP Generator Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26678.04 | 26678.04 | -1028.04 | 0 | 0 | 25650 | 0 | 0 | 0 | 0 | 25650 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510740 | S-W-NI-180121-Innerleithen WTW - Membrane Test Bath and Repair Kit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407.57 | 407.57 | 5822.44 | 0 | 0 | 6230.01 | 0 | 0 | 0 | 0 | 6230.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510736 | S-W-NI-180121-Roberton WTW - Replacement Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.12 | 221.12 | 3158.88 | 0 | 0 | 3380 | 0 | 0 | 0 | 0 | 3380 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510749 | S-W-NI-180121-Rosebery WTW - Sludge press transition | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.95 | 964.95 | 13785.04 | 0 | 0 | 14749.99 | 0 | 0 | 0 | 0 | 14749.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505274 | S-W-NI-180220-Gubhill WPS - Pumps Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-06-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 17300 | 58.13 | 17358.13 | 0 | 0 | 0 | 17358.13 | 0 | 0 | 0 | 0 | 17358.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505255 | S-W-NI-180220-Hungry Snout WPS Upgrading of Site Fire Alarm System | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.47 | 18.47 | 1881.53 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505257 | S-W-NI-180220-Megget DIR Dehumidifiers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14753.47 | 14753.47 | 4246.53 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 19000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505262 | S-W-NI-180220-Rosebery WTW Supernatant pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-18 |  | 2020-06-02 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | -62.76 | 3437.24 | 0 | 0 | 0 | 3437.24 | 0 | 0 | 0 | 0 | 3437.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511323 | S-W-NI-180221-Black Esk WTW - Auto De-sludge valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-18 |  | 2021-04-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2764.23 | 2764.23 | 0.75 | 0 | 0 | 2764.98 | 0 | 0 | 0 | 0 | 2764.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511328 | S-W-NI-180221-Lochinvar WTW - DAF Compressor Blower cooling fan | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620.31 | 1620.31 | 429.7 | 0 | 0 | 2050.01 | 0 | 0 | 0 | 0 | 2050.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511327 | S-W-NI-180221-Lochinvar WTW - Wash water valve Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-18 |  | 2021-04-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4145.08 | 4145.08 | -0.05 | 0 | 0 | 4145.03 | 0 | 0 | 0 | 0 | 4145.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511325 | S-W-NI-180221-Penwhirn WTW - Primary Filter C outlet Flow meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 5000 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511322 | S-W-NI-180221-Winterhope WTW - CL2 Gas change over system | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.91 | 529.91 | 7570.1 | 0 | 0 | 8100.01 | 0 | 0 | 0 | 0 | 8100.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505790 | S-W-NI-180320-Limefield DSR - Inlet Flow Controllers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-27 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 487.38 | 18.47 | 505.85 | 6944.15 | 0 | 0 | 7450 | 0 | 0 | 0 | 0 | 7450 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506651 | S-W-NI-180520-Black Esk wtw Hypo Dosing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-19 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2231.34 | 2231.34 | 0 | 0 | 0 | 2231.34 | 0 | 0 | 0 | 0 | 2231.34 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506657 | S-W-NI-180520-Glencorse wtw desludge valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-05-19 |  | 2021-04-04 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7798.9 | 7798.9 | -1298.9 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506654 | S-W-NI-180520-Rosebery WTW Supernatant | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-19 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.57 | 345.57 | 4654.43 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507258 | S-W-NI-180620-Castle Moffat WTW Clarifier No 1 refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-22 |  | 2020-09-10 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21206.46 | 21206.46 | 0 | 0 | 0 | 21206.46 | 0 | 0 | 0 | 0 | 21206.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507248 | S-W-NI-180620-Dunside TWP Standby Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-22 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1722.74 | 1722.74 | 0 | 0 | 0 | 1722.74 | 0 | 0 | 0 | 0 | 1722.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507251 | S-W-NI-180620-Dunslaw SR - Ball Valve Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526.17 | 526.17 | 7373.83 | 0 | 0 | 7900 | 0 | 0 | 0 | 0 | 7900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508251 | S-W-NI-180820-Black Esk - RGF Nr 2 Media and Nozzle investigation and Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-26 |  | 2020-10-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53521.98 | 53521.98 | 0 | 0 | 0 | 53521.98 | 0 | 0 | 0 | 0 | 53521.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508239 | S-W-NI-180820-Carsphairn WTW - Relift Pump Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1981.66 | 1981.66 | 0 | 0 | 0 | 1981.66 | 0 | 0 | 0 | 0 | 1981.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508259 | S-W-NI-180820-Killylour WTW - Recovered water sample pumps Provision | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-11-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5852.76 | 5852.76 | 0 | 0 | 0 | 5852.76 | 0 | 0 | 0 | 0 | 5852.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508256 | S-W-NI-180820-Killylour WTW - Sludge thickener gearbox replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8357.64 | 8357.64 | 0 | 0 | 0 | 8357.64 | 0 | 0 | 0 | 0 | 8357.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508249 | S-W-NI-180820-Penwhirn WTW - Cloth wash pump A refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-08-20 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5120 | 5120 | 0 | 0 | 0 | 5120 | 0 | 0 | 0 | 0 | 5120 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508244 | S-W-NI-180820-Terregles BH WTW - Water Softner Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-08-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.64 | 1658.64 | 0 | 0 | 0 | 1658.64 | 0 | 0 | 0 | 0 | 1658.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508241 | S-W-NI-180820-Winterhope WTW - pH monitors replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-26 |  | 2021-03-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25630.88 | 25630.88 | 0 | 0 | 0 | 25630.88 | 0 | 0 | 0 | 0 | 25630.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508811 | S-W-NI-180920-Auchentibber SR Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2419.32 | 2419.32 | 0 | 0 | 0 | 2419.32 | 0 | 0 | 0 | 0 | 2419.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508823 | S-W-NI-180920-Black Esk WTW RAM Sludge Pump Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7462.65 | 7462.65 | 0 | 0 | 0 | 7462.65 | 0 | 0 | 0 | 0 | 7462.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508818 | S-W-NI-180920-Durisdeer TWP Pumps Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5371.41 | 5371.41 | 0 | 0 | 0 | 5371.41 | 0 | 0 | 0 | 0 | 5371.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508819 | S-W-NI-180920-Kirkland to The Linn Tynron Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14752.26 | 14752.26 | 0 | 0 | 0 | 14752.26 | 0 | 0 | 0 | 0 | 14752.26 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508826 | S-W-NI-180920-Knockfell WPS Pump Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3807.1 | 3807.1 | 0 | 0 | 0 | 3807.1 | 0 | 0 | 0 | 0 | 3807.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508815 | S-W-NI-180920-Latch SR Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-11 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3019.27 | 3019.27 | 0 | 0 | 0 | 3019.27 | 0 | 0 | 0 | 0 | 3019.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508817 | S-W-NI-180920-Manse Street WTW Coag Pump Controller | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7608.85 | 7608.85 | 0 | 0 | 0 | 7608.85 | 0 | 0 | 0 | 0 | 7608.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508810 | S-W-NI-180920-Penwhirn WTW - Hydrovane 504 air end compressor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-09-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3662.57 | 3662.57 | 0 | 0 | 0 | 3662.57 | 0 | 0 | 0 | 0 | 3662.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508821 | S-W-NI-180920-Penwhirn WTW - Various Health and Safety Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6135.97 | 6135.97 | 0 | 0 | 0 | 6135.97 | 0 | 0 | 0 | 0 | 6135.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504412 | S-W-NI-181219-Camps Road Re-instatement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-18 |  | 2020-02-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | -1846.94 | 1853.06 | 0 | 0 | 0 | 1853.06 | 0 | 0 | 0 | 0 | 1853.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504404 | S-W-NI-181219-Marchbank WTW Filter 3A and 4B backwash valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2021-05-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | -1524.36 | 20475.64 | 1524.36 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 22000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504403 | S-W-NI-181219-Rawburn WTW Replacement generator fuel tank & fuel station | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4136.77 | 0 | 4136.77 | 63.23 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504397 | S-W-NI-181219-Rosebery WTW Compressor refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-18 |  | 2020-03-20 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 7457.39 | 0 | 7457.39 | 0 | 0 | 0 | 7457.39 | 0 | 0 | 0 | 0 | 7457.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504400 | S-W-NI-181219-Rosebery WTW Supernatant pump repacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-18 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 2057.66 | 0 | 2057.66 | 42.34 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510758 | S-W-NI-190121-Auchneel WTW - Carrier water booster pump x2 Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-22 |  | 2021-03-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076.4 | 7076.4 | 7.48 | 0 | 0 | 7083.88 | 0 | 0 | 0 | 0 | 7083.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510761 | S-W-NI-190121-Auchneel WTW - Clarifier Tank A Actuator Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-22 |  | 2021-03-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5055.64 | 5055.64 | 4.36 | 0 | 0 | 5060 | 0 | 0 | 0 | 0 | 5060 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510763 | S-W-NI-190121-Cargen WTW - Flowmeter & Transmitter Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236.31 | 236.31 | 3177.56 | 0 | 0 | 3413.87 | 0 | 0 | 0 | 0 | 3413.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510769 | S-W-NI-190121-Kettleton WTW - Chlorine sample pumps x2 Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232.06 | 232.06 | 3116.8 | 0 | 0 | 3348.86 | 0 | 0 | 0 | 0 | 3348.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510772 | S-W-NI-190121-Lochinvar WTW - Sludge Press Filter cloth | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-22 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279.35 | 279.35 | 3990.64 | 0 | 0 | 4269.99 | 0 | 0 | 0 | 0 | 4269.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510774 | S-W-NI-190121-Moffat WTW - Valve spindles extended fabricated x4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-22 |  | 2021-03-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2662.88 | 2662.88 | 1 | 0 | 0 | 2663.88 | 0 | 0 | 0 | 0 | 2663.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510780 | S-W-NI-190121-Penwhirn WTW - Supernatant Turbidity monitors x4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19807.07 | 19807.07 | 7717.93 | 0 | 0 | 27525 | 0 | 0 | 0 | 0 | 27525 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505293 | S-W-NI-190220-Kettleton WTW - New Handrail | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-05-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | -11.01 | 2639 | 0 | 0 | 0 | 2639 | 0 | 0 | 0 | 0 | 2639 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505299 | S-W-NI-190220-Kettleton WTW - Refurbish steps - stairways in Main Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-06-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 4300 | -9.74 | 4290.26 | 0 | 0 | 0 | 4290.26 | 0 | 0 | 0 | 0 | 4290.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505288 | S-W-NI-190220-Kettleton WTW - Caustic Tank Screens Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-05-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | -57.68 | 4142.32 | 0 | 0 | 0 | 4142.32 | 0 | 0 | 0 | 0 | 4142.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505289 | S-W-NI-190220-Kettleton wtw plc alarm changes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-05-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 4250 | 4.92 | 4254.92 | 0 | 0 | 0 | 4254.92 | 0 | 0 | 0 | 0 | 4254.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511350 | S-W-NI-190221-Kettleton WTW - Chlorine sample pumps replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306.82 | 306.82 | 4383.2 | 0 | 0 | 4690.02 | 0 | 0 | 0 | 0 | 4690.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511352 | S-W-NI-190221-Killylour WTW - Injection Cabinets Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165.19 | 165.19 | 2359.8 | 0 | 0 | 2524.99 | 0 | 0 | 0 | 0 | 2524.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511353 | S-W-NI-190221-Lawhead TWP Pump Overhaul | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-19 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 30000 | 0 | 0 | 32100 | 0 | 0 | 0 | 0 | 32100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511349 | S-W-NI-190221-Lochinvar WTW - CL2 Gas change over system | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.25 | 529.25 | 7560.75 | 0 | 0 | 8090 | 0 | 0 | 0 | 0 | 8090 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507274 | S-W-NI-190620-Rosebery WTW Sludge Press feed pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-22 |  | 2020-07-15 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4742.26 | 4742.26 | 0 | 0 | 0 | 4742.26 | 0 | 0 | 0 | 0 | 4742.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508266 | S-W-NI-190820-Camps WTW Service Water Tank Access | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-11-09 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14781.27 | 14781.27 | 0 | 0 | 0 | 14781.27 | 0 | 0 | 0 | 0 | 14781.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508281 | S-W-NI-190820-Coulter Access Road Re-instatment replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-10-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5923.04 | 5923.04 | 0 | 0 | 0 | 5923.04 | 0 | 0 | 0 | 0 | 5923.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508277 | S-W-NI-190820-Coulter WTW Security CCTV 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-21 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3973.02 | 3973.02 | 0 | 0 | 0 | 3973.02 | 0 | 0 | 0 | 0 | 3973.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508270 | S-W-NI-190820-Coulter WTW Sludge Holding and Densadeg access | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-26 |  | 2021-03-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37254.54 | 37254.54 | 0 | 0 | 0 | 37254.54 | 0 | 0 | 0 | 0 | 37254.54 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508275 | S-W-NI-190820-Daer WTW Lime Coag Pump Critical Spare | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-11-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11428.42 | 11428.42 | 0 | 0 | 0 | 11428.42 | 0 | 0 | 0 | 0 | 11428.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505330 | S-W-NI-200220-Eskdalemuir DSR - Telemetry Outstation Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-04-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 36 | 1436 | 0 | 0 | 0 | 1436 | 0 | 0 | 0 | 0 | 1436 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505318 | S-W-NI-200220-Killylour WTW - Recovered water turbidity meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-03-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3966.95 | 18.47 | 3985.42 | 0 | 0 | 0 | 3985.42 | 0 | 0 | 0 | 0 | 3985.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505326 | S-W-NI-200220-Langholm Whita DSR - Telemetry Building Access Door Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-03-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2463.55 | 9.24 | 2472.79 | 0 | 0 | 0 | 2472.79 | 0 | 0 | 0 | 0 | 2472.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505324 | S-W-NI-200220-Penwhirn WTW - UPS Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-03-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 6663.76 | 55.41 | 6719.17 | 0 | 0 | 0 | 6719.17 | 0 | 0 | 0 | 0 | 6719.17 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505321 | S-W-NI-200220-Terregles BH - Pump 2 Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | -17933 | 52067 | 17933 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510804 | S-W-NI-200221- Greenhill DSR floor replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-25 | 2021-07-16 | 2022-02-28 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 10000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 12000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505848 | S-W-NI-200320-Kettleton WTW - H&S Ground work Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-27 |  | 2020-07-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 206.07 | 7053.88 | 7259.95 | 0 | 0 | 0 | 7259.95 | 0 | 0 | 0 | 0 | 7259.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505843 | S-W-NI-200320-Legbrannock Sample Building Flat Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-27 |  | 2020-06-30 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 2218.47 | 2375.48 | 0 | 0 | 0 | 2375.48 | 0 | 0 | 0 | 0 | 2375.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505857 | S-W-NI-200320-Penwhirn WTW Old Sludge Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-27 |  | 2020-09-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 870.09 | 12422.41 | 13292.5 | 0 | 0 | 0 | 13292.5 | 0 | 0 | 0 | 0 | 13292.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505845 | S-W-NI-200320-Winterhope WTW - Caustic Tank Heater Repalcement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-27 |  | 2020-11-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 677.1 | 9676.31 | 10353.41 | 0 | 0 | 0 | 10353.41 | 0 | 0 | 0 | 0 | 10353.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507762 | S-W-NI-200720-Lochinvar WTW - pH sensors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-21 |  | 2020-08-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11778.66 | 11778.66 | 0 | 0 | 0 | 11778.66 | 0 | 0 | 0 | 0 | 11778.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507759 | S-W-NI-200720-Ringford BH - Refurbish Hypo Dosing Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-21 |  | 2020-09-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7945.8 | 7945.8 | 0 | 0 | 0 | 7945.8 | 0 | 0 | 0 | 0 | 7945.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508303 | S-W-NI-200820-Bonnycraig WTW - CWT Overflow Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753.27 | 1753.27 | 25046.73 | 0 | 0 | 26800 | 0 | 0 | 0 | 0 | 26800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508296 | S-W-NI-200820-Castle Moffat WTW Emergency Overflow tank Maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1611.7 | 1611.7 | 22738.31 | 0 | 0 | 24350 | 0 | 0 | 0 | 0 | 24350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508291 | S-W-NI-200820-Dunscore DSR - Stock Proof Fence Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268.48 | 1268.48 | 0 | 0 | 0 | 1268.48 | 0 | 0 | 0 | 0 | 1268.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508298 | S-W-NI-200820-Fruid Farm UV Kiosk | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718.71 | 718.71 | 9981.3 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508305 | S-W-NI-200820-Greenhill SR Path | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-11-23 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7171.03 | 7171.03 | 0 | 0 | 0 | 7171.03 | 0 | 0 | 0 | 0 | 7171.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508302 | S-W-NI-200820-Roberton WTW - Sedimentation Tank Flow Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-26 |  | 2021-04-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18954.88 | 18954.88 | 0 | 0 | 0 | 18954.88 | 0 | 0 | 0 | 0 | 18954.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509369 | S-W-NI-201020-Birset and Sheildhill DSR - Secondary Dosing Unit Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3155.48 | 3155.48 | 1044.53 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509371 | S-W-NI-201020-Campwood TWP Fence | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-23 |  | 2021-03-19 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3215.46 | 3215.46 | 0 | 0 | 0 | 3215.46 | 0 | 0 | 0 | 0 | 3215.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506178 | S-W-NI-20200409-Castle Moffat WTW Clarifier Auto shutdown | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-27 | 2021-02-08 | 2021-07-09 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20373 | 20373 | 21892.51 | 0 | 0 | 42265.51 | 0 | 0 | 0 | 0 | 42265.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506171 | S-W-NI-20200409-Hopes WTW Plc Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-27 | 2021-02-08 | 2021-06-25 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69718 | 69718 | 31125.2 | 0 | 0 | 100843.2 | 0 | 0 | 0 | 0 | 100843.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506175 | S-W-NI-20200409-Silverburn Pumps upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 |  | 2020-05-27 | 2020-08-21 | 2021-03-15 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105880.83 | 105880.83 | 0 | 0 | 0 | 105880.83 | 0 | 0 | 0 | 0 | 105880.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506330 | S-W-NI-20200423-Rosebery WTW Chlorine drum store doors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-27 | 2021-02-26 | 2021-07-27 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10945 | 10945 | 59733.26 | 0 | 0 | 70678.26 | 0 | 0 | 0 | 0 | 70678.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506507 | S-W-NI-20200506-Hungry Snout RW Turbidity Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-05-27 | 2020-11-06 | 2021-05-28 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19405 | 19405 | 2595.48 | 0 | 0 | 22000.48 | 0 | 0 | 0 | 0 | 22000.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507015 | S-W-NI-20200604-Castle Moffat WTW SCADA Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-06-05 | 2020-11-02 | 2021-04-27 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94763 | 94763 | 5236.8 | 0 | 0 | 99999.8 | 0 | 0 | 0 | 0 | 99999.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507771 | S-W-NI-20200720-Gladhouse Air Curtain Power | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-22 | 2021-04-12 | 2022-03-14 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113335.82 | 113335.82 | 16739.16 | 0 | 0 | 130074.98 | 0 | 0 | 0 | 0 | 130074.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509768 | S-W-NI-20201012-Hungry Snout RWP HV Room Study | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-12-08 | 2021-07-12 | 2022-01-03 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2861 | 2861 | 17139.19 | 0 | 0 | 20000.19 | 0 | 0 | 0 | 0 | 20000.19 | 311236.79 | [5 empty] | N | CM_M&G | 100%
509844 | S-W-NI-20201017-Castle Moffat Raw Water Colour Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-08 | 2021-07-12 | 2022-01-03 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7418 | 7418 | 17582.5 | 0 | 0 | 25000.5 | 0 | 0 | 0 | 0 | 25000.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509848 | S-W-NI-20201017-Fountainhall TWS Flow control Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-08 | 2021-05-21 | 2022-01-03 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4085.44 | 4085.44 | 8000 | 0 | 0 | 12085.44 | 0 | 0 | 0 | 0 | 12085.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509842 | S-W-NI-20201017-Rosebery WTW Turbidity Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-08 | 2021-07-05 | 2022-02-15 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6424 | 6424 | 73576.37 | 0 | 0 | 80000.37 | 0 | 0 | 0 | 0 | 80000.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510708 | S-W-NI-20210114-Morton Bore RWI main out investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-01-22 | 2022-06-23 | 2023-02-03 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9999.99 | 0 | 0 | 9999.99 | 0 | 0 | 0 | 0 | 9999.99 | 311236.79 | [5 empty] | N | CM_M&G | 100%
510710 | S-W-NI-20210114-Rosebery Washwater media traps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-22 | 2021-09-03 | 2022-04-18 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1972 | 1972 | 23027.64 | 0 | 0 | 24999.64 | 0 | 0 | 0 | 0 | 24999.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510709 | S-W-NI-20210114-Rosebery WTW Backwash Pump control | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-01-22 | 2021-09-17 | 2022-04-29 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1709 | 1709 | 18290.68 | 0 | 0 | 19999.68 | 0 | 0 | 0 | 0 | 19999.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510984 | S-W-Ni-20210129-Pateshill WTW Raw Water Study | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-26 | 2022-09-15 | 2023-04-28 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.67 | 345.67 | 25000 | 0 | 0 | 25345.67 | 0 | 0 | 0 | 0 | 25345.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511302 | S-W-NI-20210217- Silverburn TWP Power supply upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-26 | 2021-08-13 | 2022-03-28 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.13 | 248.13 | 50000 | 0 | 0 | 50248.13 | 0 | 0 | 0 | 0 | 50248.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511297 | S-W-NI-20210217-Rosebery WTW SCADA PC upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-26 | 2021-04-16 | 2021-06-21 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220.3 | 220.3 | 50000.01 | 0 | 0 | 50220.31 | 0 | 0 | 0 | 0 | 50220.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505358 | S-W-NI-210220-Bonnycraig WTW Temporary Pressure Filter Housing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-03-13 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3883.5 | 18.47 | 3901.97 | 298.03 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505351 | S-W-NI-210220-Marchbank wtw - WW settlement tank No4 inlet actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-05-13 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3400 | -10.26 | 3389.74 | 0 | 0 | 0 | 3389.74 | 0 | 0 | 0 | 0 | 3389.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505348 | S-W-NI-210220-Pateshill wtw - Pre-cip stop logs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-21 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3050 | -2832 | 218 | 2832 | 0 | 0 | 3050 | 0 | 0 | 0 | 0 | 3050 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505356 | S-W-NI-210220-Rawburn WTW Replacement Press Filter Cloth | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-21 |  | 2020-09-03 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 212.62 | 3015.47 | 3228.09 | 0 | 0 | 0 | 3228.09 | 0 | 0 | 0 | 0 | 3228.09 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505361 | S-W-NI-210220-Strutherhill DSR Altitude Valve & Flow Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-24 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 18500 | 1843.74 | 20343.74 | -1843.74 | 0 | 0 | 18500 | 0 | 0 | 0 | 0 | 18500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506299 | S-W-NI-2104120-Kype Reservoir Bridge | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-04-22 | 2021-06-16 | 2021-10-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14924.72 | 14924.72 | 118.29 | 0 | 0 | 15043.01 | 0 | 0 | 0 | 0 | 15043.01 | 311236.79 | [5 empty] | N | CM_M&G | 100%
506283 | S-W-NI-210420-Daer Clarifier Roof Ongoing Monitoring | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-04-29 | 2020-07-21 | 2022-06-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34371.52 | 34371.52 | 547.38 | 0 | 0 | 34918.9 | 0 | 0 | 0 | 0 | 34918.9 | 311236.79 | [5 empty] | N | CM_M&G | 100%
506285 | S-W-NI-210420-Rosebery WTW - Chlorine Cl2 system replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-21 |  | 2020-06-19 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11176.42 | 11176.42 | 0 | 0 | 0 | 11176.42 | 0 | 0 | 0 | 0 | 11176.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508312 | S-W-NI-210820-Blackburn Intake emergency maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-11-02 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1493.48 | 1493.48 | 0 | 0 | 0 | 1493.48 | 0 | 0 | 0 | 0 | 1493.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508314 | S-W-NI-210820-Glencorse wtw Lime dosing system pinch valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358.7 | 358.7 | 4981.3 | 0 | 0 | 5340 | 0 | 0 | 0 | 0 | 5340 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508842 | S-W-NI-210920-Glengap WTW Allen Bradley VSDs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8825.99 | 8825.99 | 0 | 0 | 0 | 8825.99 | 0 | 0 | 0 | 0 | 8825.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509381 | S-W-NI-211020-Glassford DSR Outlet Chlorine Analyser | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5221.31 | 5221.31 | 0 | 0 | 0 | 5221.31 | 0 | 0 | 0 | 0 | 5221.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509372 | S-W-NI-211020-Udston DSR Secondary Dosing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4214.18 | 4214.18 | 0 | 0 | 0 | 4214.18 | 0 | 0 | 0 | 0 | 4214.18 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506312 | S-W-NI-220220-Auchneel WTW - Sludge press cloths replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-22 |  | 2020-09-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3996.15 | 3996.15 | 0 | 0 | 0 | 3996.15 | 0 | 0 | 0 | 0 | 3996.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511366 | S-W-NI-220221-Gladhouse Air Curtain Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-22 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5377.94 | 5377.94 | 34077.06 | 0 | 0 | 39455 | 0 | 0 | 0 | 0 | 39455 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506318 | S-W-NI-220420-Black Esk WTW - Sludge Press Chainwheels Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-27 |  | 2020-06-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1845.64 | 1845.64 | 0 | 0 | 0 | 1845.64 | 0 | 0 | 0 | 0 | 1845.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506321 | S-W-NI-220420-Elsrickle Booster Standby Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-27 |  | 2020-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1697.22 | 1697.22 | 0 | 0 | 0 | 1697.22 | 0 | 0 | 0 | 0 | 1697.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506322 | S-W-NI-220420-Elsrickle Booster Supply Issues | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-27 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158220.95 | 158220.95 | -103220.95 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 55000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506320 | S-W-NI-220420-Penwhirn WTW - Coaq Lime Pump Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-27 |  | 2020-07-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7781.2 | 7781.2 | 0 | 0 | 0 | 7781.2 | 0 | 0 | 0 | 0 | 7781.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506315 | S-W-NI-220420-Penwhirn WTW - Sludge press distribution rings replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-27 |  | 2020-06-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.38 | 3524.38 | 0 | 0 | 0 | 3524.38 | 0 | 0 | 0 | 0 | 3524.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507816 | S-W-NI-220720-Rawburn WTW PH Control | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.01 | 143.01 | 1757 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509407 | S-W-NI-221020-Auchneel WTW - Hydrovane 504 air end compressor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3681.6 | 3681.6 | 0 | 0 | 0 | 3681.6 | 0 | 0 | 0 | 0 | 3681.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509409 | S-W-NI-221020-Auchneel WTW - Water Softener Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507.63 | 1507.63 | 0 | 0 | 0 | 1507.63 | 0 | 0 | 0 | 0 | 1507.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509414 | S-W-NI-221020-Black Esk WTW - Mecana Tertiary Filter Trial | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718.71 | 718.71 | 9981.3 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509420 | S-W-NI-221020-Carshairn WTW - Various Health and Safety Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-09-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2585.44 | 2585.44 | 0 | 0 | 0 | 2585.44 | 0 | 0 | 0 | 0 | 2585.44 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509400 | S-W-NI-221020-Elvanfoot TWP Standby Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-23 |  | 2021-02-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2076.78 | 2076.78 | 0 | 0 | 0 | 2076.78 | 0 | 0 | 0 | 0 | 2076.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509403 | S-W-NI-221020-Glassford DSR Welfare Unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000.02 | 1000.02 | 13999.99 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505881 | S-W-NI-230320-Bonnycraig WTW - Welfare Cabin Service Connections | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-27 |  | 2020-04-08 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 330.37 | 4712.06 | 5042.43 | 0 | 0 | 0 | 5042.43 | 0 | 0 | 0 | 0 | 5042.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505877 | S-W-NI-230320-Howden WTW CIP Warm Water Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-27 |  | 2020-06-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 153.74 | 2212.47 | 2366.21 | 0 | 0 | 0 | 2366.21 | 0 | 0 | 0 | 0 | 2366.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505875 | S-W-NI-230320-Watch Water - South Shore Replacement Fence | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-27 |  | 2020-09-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1373.83 | 22435.68 | 23809.51 | 0 | 0 | 0 | 23809.51 | 0 | 0 | 0 | 0 | 23809.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505882 | S-W-NI-230320-Yarrowfeus WTW - Redundant Sample Kiosk | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-27 |  | 2020-04-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 4003.47 | 4284.78 | 0 | 0 | 0 | 4284.78 | 0 | 0 | 0 | 0 | 4284.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511975 | S-W-NI-230321-Dronehill WPS Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206.07 | 206.07 | 2700 | 0 | 0 | 2906.07 | 0 | 0 | 0 | 0 | 2906.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507296 | S-W-NI-230620-Hopes WTW - Chemical Dosing Skid Curtains | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-07-20 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2671.72 | 2671.72 | 0 | 0 | 0 | 2671.72 | 0 | 0 | 0 | 0 | 2671.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509437 | S-W-NI-231020-Glengap WTW - Chlorination Control UPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-23 |  | 2021-02-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2517.26 | 2517.26 | 0 | 0 | 0 | 2517.26 | 0 | 0 | 0 | 0 | 2517.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509439 | S-W-NI-231020-Glengap WTW - Ortho Dosing Pumps Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5360.7 | 5360.7 | 0 | 0 | 0 | 5360.7 | 0 | 0 | 0 | 0 | 5360.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509441 | S-W-NI-231020-Glengap WTW - Ortho tank mixer replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6194.94 | 6194.94 | 0 | 0 | 0 | 6194.94 | 0 | 0 | 0 | 0 | 6194.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509443 | S-W-NI-231020-Lochinvar WTW - CCT Sample Pump No2 Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375.02 | 2375.02 | 0 | 0 | 0 | 2375.02 | 0 | 0 | 0 | 0 | 2375.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509447 | S-W-NI-231020-Lochinvar WTW - Various H&S Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-09-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081.42 | 2081.42 | 0 | 0 | 0 | 2081.42 | 0 | 0 | 0 | 0 | 2081.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509445 | S-W-NI-231020-Lochinvar WTW Filter press wash head | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4263.31 | 4263.31 | 0 | 0 | 0 | 4263.31 | 0 | 0 | 0 | 0 | 4263.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509446 | S-W-NI-231020-Lochinvar WTW pH system | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-23 |  | 2021-04-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11778.67 | 11778.67 | 0 | 0 | 0 | 11778.67 | 0 | 0 | 0 | 0 | 11778.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509433 | S-W-NI-231020-Winterhope WTW - Various H and S Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4038.68 | 4038.68 | 0 | 0 | 0 | 4038.68 | 0 | 0 | 0 | 0 | 4038.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511992 | S-W-NI-240321-Glencorse WTW - Leopold Underdrain Inspection | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-24 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771.96 | 771.96 | 10114.26 | 0 | 0 | 10886.22 | 0 | 0 | 0 | 0 | 10886.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507329 | S-W-NI-240620-Carnwath Sample Point H&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-06-29 | 2022-04-01 | 2022-11-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3860 | 3860 | 6140.2 | 0 | 0 | 10000.2 | 0 | 0 | 0 | 0 | 10000.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507330 | S-W-NI-240620-Legbrannock DSR Rotorks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-06-29 | 2021-07-12 | 2021-11-15 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9763.42 | 9763.42 | 20687.73 | 0 | 0 | 30451.15 | 0 | 0 | 0 | 0 | 30451.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509961 | S-W-NI-241120-Dingleton TWP - Replacement TWP and VSDs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1390.19 | 1390.19 | 23359.81 | 0 | 0 | 24750 | 0 | 0 | 0 | 0 | 24750 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509960 | S-W-NI-241120-Wanton Walls SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 4018.69 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503948 | S-W-NI-251119-AUCHNEEL WTW DRAINAGE WORKS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-28 |  | 2020-01-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | -322.9 | 4677.1 | 0 | 0 | 0 | 4677.1 | 0 | 0 | 0 | 0 | 4677.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510003 | S-W-NI-251120-Howden WTW Free Chlorine instrument | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.49 | 170.49 | 2149.52 | 0 | 0 | 2320 | 0 | 0 | 0 | 0 | 2320 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509995 | S-W-NI-251120-Landshead SCU - Building Refurbishement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-30 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20283.56 | 20283.56 | 0 | 0 | 0 | 20283.56 | 0 | 0 | 0 | 0 | 20283.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510007 | S-W-NI-251120-Rawburn WTW - Poly Building Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412.28 | 412.28 | 5889.72 | 0 | 0 | 6302 | 0 | 0 | 0 | 0 | 6302 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509998 | S-W-NI-251120-Rawburn wtw Site Area Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199.67 | 199.67 | 2640.33 | 0 | 0 | 2840 | 0 | 0 | 0 | 0 | 2840 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506827 | S-W-NI-260520-Carsphairn WTW ph analyser | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-27 |  | 2020-06-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6767.33 | 6767.33 | 0 | 0 | 0 | 6767.33 | 0 | 0 | 0 | 0 | 6767.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506832 | S-W-NI-260520-Penwhirn wtw Alba dosing pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-27 |  | 2020-10-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4684.95 | 4684.95 | 0 | 0 | 0 | 4684.95 | 0 | 0 | 0 | 0 | 4684.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506823 | S-W-NI-260620-Tynron SR Telemetry | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-27 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6880.47 | 6880.47 | 15119.53 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 22000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508390 | S-W-NI-260820-Manse Street WTW - CWT Emergency Overflow | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715.89 | 715.89 | 10084.11 | 0 | 0 | 10800 | 0 | 0 | 0 | 0 | 10800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509452 | S-W-NI-261020-Moffat WTW - Platform H and S Improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-27 |  | 2021-03-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14159.94 | 14159.94 | 0 | 0 | 0 | 14159.94 | 0 | 0 | 0 | 0 | 14159.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509456 | S-W-NI-261020-Penwhirn WTW - DAF Compressor Fan overload Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-27 |  | 2020-04-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1292.2 | 1292.2 | 0 | 0 | 0 | 1292.2 | 0 | 0 | 0 | 0 | 1292.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509462 | S-W-NI-261020-Penwhirn WTW - Filter cloth wash pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-27 |  | 2020-03-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12149.57 | 12149.57 | 0 | 0 | 0 | 12149.57 | 0 | 0 | 0 | 0 | 12149.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509466 | S-W-NI-261020-Penwhirn WTW - Poly Access H and S Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-27 |  | 2020-10-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6581.78 | 6581.78 | 0 | 0 | 0 | 6581.78 | 0 | 0 | 0 | 0 | 6581.78 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503979 | S-W-NI-261119-Carnduff WPS Sump pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | -2429.91 | 170.09 | 2429.91 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503981 | S-W-NI-261119-Coulter WTW Sodium Hypochlorite Dosing System Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-28 |  | 2020-03-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 15965.73 | 0 | 15965.73 | 0 | 0 | 0 | 15965.73 | 0 | 0 | 0 | 0 | 15965.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503990 | S-W-NI-261119-Daer WTW Aluminium Pump Additions | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-26 |  | 2020-05-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 8015.91 | 0 | 8015.91 | 0 | 0 | 0 | 8015.91 | 0 | 0 | 0 | 0 | 8015.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510016 | S-W-NI-261120-Black Esk WTW - Washdown hose in filter hall | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2706.59 | 2706.59 | 0 | 0 | 0 | 2706.59 | 0 | 0 | 0 | 0 | 2706.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510018 | S-W-NI-261120-Carsfad RWP - Hydrocarbon Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559.36 | 1559.36 | 21990.65 | 0 | 0 | 23550 | 0 | 0 | 0 | 0 | 23550 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510019 | S-W-NI-261120-Glengap wtw Allen Bradley Drive Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-30 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2946.99 | 2946.99 | 0 | 0 | 0 | 2946.99 | 0 | 0 | 0 | 0 | 2946.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510021 | S-W-NI-261120-Lochinvar WTW - Saturator Pressure vessel investigations and remedial works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-30 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6922.66 | 6922.66 | 0 | 0 | 0 | 6922.66 | 0 | 0 | 0 | 0 | 6922.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510020 | S-W-NI-261120-Lochinvar wtw Lime dosing pressure loading valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-30 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1726.65 | 1726.65 | 0 | 0 | 0 | 1726.65 | 0 | 0 | 0 | 0 | 1726.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510026 | S-W-NI-261120-Roughrigg DSR Inlet Actuators | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5305.38 | 5305.38 | 0 | 0 | 0 | 5305.38 | 0 | 0 | 0 | 0 | 5305.38 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510022 | S-W-NI-261120-Udston DSR Inlet Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-30 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2885.07 | 2885.07 | 0 | 0 | 0 | 2885.07 | 0 | 0 | 0 | 0 | 2885.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506368 | S-W-NI-270420-Castle Moffat WTW Scada Software Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-27 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6102.79 | 6102.79 | -6102.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
506365 | S-W-NI-270420-Daer WTW Sludge Press C Floating Floor Fault | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-27 |  | 2020-07-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12488.56 | 12488.56 | 0 | 0 | 0 | 12488.56 | 0 | 0 | 0 | 0 | 12488.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506360 | S-W-NI-270420-Innerleithen WTW Turbidity monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-27 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8570.09 | 8570.09 | 4529.91 | 0 | 0 | 13100 | 0 | 0 | 0 | 0 | 13100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506849 | S-W-NI-270520 - Glencorse WTW Sludge transfer pump B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-27 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7989.9 | 7989.9 | 0 | 0 | 0 | 7989.9 | 0 | 0 | 0 | 0 | 7989.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508419 | S-W-NI-270820-Halmyre WPS - Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-28 |  | 2020-11-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11256.96 | 11256.96 | 0 | 0 | 0 | 11256.96 | 0 | 0 | 0 | 0 | 11256.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504002 | S-W-NI-271119-Bonnycraig WTW Aluminium & Phosphate monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-28 |  | 2020-09-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 29000 | -709.96 | 28290.04 | 0 | 0 | 0 | 28290.04 | 0 | 0 | 0 | 0 | 28290.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504008 | S-W-NI-271119-Dingleton TWP Concrete Plinth | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-28 |  | 2019-12-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | -218.32 | 3781.68 | 0 | 0 | 0 | 3781.68 | 0 | 0 | 0 | 0 | 3781.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504011 | S-W-NI-271119-Manse Street WTW Storage Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-28 |  | 2020-03-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2045.63 | 0 | 2045.63 | 0 | 0 | 0 | 2045.63 | 0 | 0 | 0 | 0 | 2045.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504015 | S-W-NI-271119-Rawburn WTW Phosphate Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-28 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | -14018.69 | 981.31 | 14018.69 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504013 | S-W-NI-271119-Roberton WTW - Crane Hoist attachment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-28 |  | 2020-01-30 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | -174.93 | 1325.07 | 0 | 0 | 0 | 1325.07 | 0 | 0 | 0 | 0 | 1325.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508449 | S-W-NI-280820-Bairnkinnie WPS - Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-28 |  | 2020-09-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3740.33 | 3740.33 | 0 | 0 | 0 | 3740.33 | 0 | 0 | 0 | 0 | 3740.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508982 | S-W-NI-280920-Pateshill WTW Raw Water Study | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-01 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766.36 | 1766.36 | 25233.64 | 0 | 0 | 27000 | 0 | 0 | 0 | 0 | 27000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504023 | S-W-NI-281119-Castle Moffat WTW - Access Road improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-28 |  | 2020-03-02 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 7450.15 | 0 | 7450.15 | 0 | 0 | 0 | 7450.15 | 0 | 0 | 0 | 0 | 7450.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504039 | S-W-NI-281119-Castle Moffat WTW - DOC monitor refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-12 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 2183.96 | -1159.99 | 1023.97 | 2476.03 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504025 | S-W-NI-281119-Castle Moffat WTW Clarifier 2 Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-28 |  | 2020-05-04 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | -140.14 | 17359.86 | 0 | 0 | 0 | 17359.86 | 0 | 0 | 0 | 0 | 17359.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504042 | S-W-NI-281119-Castle Moffat WTW replacement lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-12 |  | 2020-02-24 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3061.75 | 0 | 3061.75 | 0 | 0 | 0 | 3061.75 | 0 | 0 | 0 | 0 | 3061.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504059 | S-W-NI-281119-Kettleton WTW Road Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-12 |  | 2020-01-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3548.97 | 0 | 3548.97 | 0 | 0 | 0 | 3548.97 | 0 | 0 | 0 | 0 | 3548.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504051 | S-W-NI-281119-Longplantings TWS - Wall repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-12 |  | 2020-10-28 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | -181.16 | 3318.84 | 0 | 0 | 0 | 3318.84 | 0 | 0 | 0 | 0 | 3318.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504045 | S-W-NI-281119-Rosbery WTW - Washwater bays cleaning | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-12 |  | 2019-12-05 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | -7998.24 | 4501.76 | 0 | 0 | 0 | 4501.76 | 0 | 0 | 0 | 0 | 4501.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504032 | S-W-NI-28112019-Castle Moffat WTW - Phosphate monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-28 |  | 2020-03-11 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 14598.14 | 0 | 14598.14 | 0 | 0 | 0 | 14598.14 | 0 | 0 | 0 | 0 | 14598.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510970 | S-W-NI-290121-Crosswood WTW UV pipework modification | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14693.77 | 14693.77 | 2506.23 | 0 | 0 | 17200 | 0 | 0 | 0 | 0 | 17200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507401 | S-W-NI-290620-Gladhouse Reservoir fence repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-29 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071.98 | 1071.98 | 15028.03 | 0 | 0 | 16100 | 0 | 0 | 0 | 0 | 16100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507442 | S-W-NI-300620-Hot Pressure Washers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-02 |  | 2020-11-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6131.79 | 6131.79 | 0 | 0 | 0 | 6131.79 | 0 | 0 | 0 | 0 | 6131.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507435 | S-W-NI-300620-Rawburn wtw Lime Dosing Injectors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-02 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205.61 | 205.61 | 2794.39 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507439 | S-W-NI-300620-Roberton WTW Filtered colour monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-07-02 |  | 2021-03-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34955.28 | 34955.28 | -13155.28 | 0 | 0 | 21800 | 0 | 0 | 0 | 0 | 21800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507432 | S-W-NI-300620-Watch Water and Dye Water - Access Road Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-02 |  | 2020-10-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3614.22 | 3614.22 | 0 | 0 | 0 | 3614.22 | 0 | 0 | 0 | 0 | 3614.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503988 | S-W-NI-Daer WTW Aluminium Analyser replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-11-26 |  | 2020-02-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 14010.5 | 1500 | 15510.5 | -1410.5 | 0 | 0 | 14100 | 0 | 0 | 0 | 0 | 14100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506924 | S-W-NI-Daer WTW Clarifier 9 A and B Cleaning | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50295.48 | 50295.48 | 0 | 0 | 0 | 50295.48 | 0 | 0 | 0 | 0 | 50295.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507554 | S-W-NI-Daer WTW Fire risk remedial work | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-07-15 | 2021-06-07 | 2021-11-16 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3070 | 3070 | 4130.06 | 0 | 0 | 7200.06 | 0 | 0 | 0 | 0 | 7200.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505721 | S-W-NI-Daer WTW translucent panel replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-04-07 | 2021-07-13 | 2021-12-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8246 | 8246 | 41753.67 | 0 | 0 | 49999.67 | 0 | 0 | 0 | 0 | 49999.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508261 | S-W-NI-Killylour WTW Pressure Switch on Sludge pump No1 Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-26 |  | 2020-08-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1555.61 | 1555.61 | 0 | 0 | 0 | 1555.61 | 0 | 0 | 0 | 0 | 1555.61 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505719 | S-W-NI-Tannochside roof refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-04-01 | 2021-05-04 | 2021-08-13 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16519 | 16519 | 27281.19 | 0 | 0 | 43800.19 | 0 | 0 | 0 | 0 | 43800.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
30947 | SWO - Deans Industrial Estate North SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-10-27 | 2012-01-16 | 2014-03-07 | 2014-03-24 | West Lothian | 191500 | 0 | 7.27 | 0 | 0 | 0 | 0 | 0 | 7.27 | 0 | 0 | 0 | 191507.27 | 0 | 0 | 0 | 0 | 191507.27 | 57522.26 | [5 empty] | N | EC09B | 50% | EC10D | 50%
45240 | SWO - Edgefield Industrial Estate SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-24 | 2012-02-06 | 2014-03-07 | 2014-03-24 | Midlothian | 157383 | 0 | -0.2 | 0 | 0 | 0 | 0 | 0 | -0.2 | 0 | 0 | 0 | 157382.8 | 0 | 0 | 0 | 0 | 157382.8 | 0 | [5 empty] | N | EC09B | 50% | EC10D | 50%
30948 | SWO - Greendykes Industrial Estate SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-10-27 | 2012-01-18 | 2013-07-24 | 2013-10-09 | West Lothian | 139722 | 0 | -125.19 | 0 | 0 | 0 | 0 | 0 | -125.19 | 0 | 0 | 0 | 139596.81 | 0 | 0 | 0 | 0 | 139596.81 | 57522.26 | [5 empty] | N | EC09B | 50% | EC10D | 50%
30952 | SWO - Pentland Industrial Estate SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-14 | 2012-02-07 | 2014-08-22 | 2014-08-29 | Midlothian | 178935 | 0 | 734 | 0 | 0 | 0 | 0 | 0 | 734 | 0 | 0 | 0 | 179669 | 0 | 0 | 0 | 0 | 179669 | 57522.26 | [5 empty] | N | EC09B | 50% | EC10D | 50%
30953 | SWO - Pentland Retail Park SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-14 | 2012-02-06 | 2014-08-28 | 2014-10-22 | Midlothian | 192617 | 0 | 271.57 | 0 | 0 | 0 | 0 | 0 | 271.57 | 0 | 0 | 0 | 192888.57 | 0 | 0 | 0 | 0 | 192888.57 | 57522.26 | [5 empty] | N | EC09B | 50% | EC10D | 50%
30943 | SWO - Righead Industrial Estate SWS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-24 | 2012-02-08 | 2014-08-22 | 2014-10-02 | North Lanarkshire | 237194 | 0 | 3003.4 | 0 | 0 | 0 | 0 | 0 | 3003.4 | 0 | 0 | 0 | 240197.4 | 0 | 0 | 0 | 0 | 240197.4 | 57522.26 | [5 empty] | N | EC09B | 50% | EC10D | 50%
300031 | SWS1 QS II Land Acquisition | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2015-11-03 |  | Scottish Water Wide | 652554 | 0 | -25204.52 | 0 | 0 | 0 | 0 | 0 | -25204.52 | 0 | 0 | 0 | 627349.48 | 0 | 0 | 0 | 0 | 627349.48 | 306661.32 | [5 empty] | N | CM_M&G | 100%
300030 | SWS1 QS II Land Compensation Liabilities | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2015-11-03 |  | Scottish Water Wide | 529090.85 | 0 | 7926.05 | 0 | 0 | 0 | 0 | 0 | 7926.05 | 0 | 0 | 0 | 537016.9 | 0 | 0 | 0 | 0 | 537016.9 | 306661.32 | [5 empty] | N | CM_M&G | 100%
300036 | SWS1 QS3a Land Acquisition | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2012-07-31 | 2012-07-31 | 2012-08-06 | 2015-11-03 |  | Scottish Water Wide | 421388.47 | 0 | 1575.16 | 0 | 0 | 0 | 0 | 0 | 1575.16 | 0 | 0 | 0 | 422963.63 | 0 | 0 | 0 | 0 | 422963.63 | 306661.32 | [5 empty] | N | CM_M&G | 100%
401033 | SWS1 Waste Water (Allocation) CX5-6 costs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWS1 | Management and General | MS0 | 2010-04-01 |  |  |  |  | Scottish Water Wide | 288394.24 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 0 | 0 | 288397 | 0 | 0 | 0 | 0 | 288397 | 306661.32 | [5 empty] | N | OHDW1 | 100%
401031 | SWS1 Water (Allocated) CX5-6 costs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWS1 | Management and General | MS0 | 2010-04-01 |  |  |  |  | Scottish Water Wide | 154448.05 | 0 | 1.95 | 0 | 0 | 0 | 0 | 0 | 1.95 | 0 | 0 | 0 | 154450 | 0 | 0 | 0 | 0 | 154450 | 306661.32 | [5 empty] | N | OHDS1 | 100%
401030 | SWS1 Water (Managed) CX5-6 costs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWS1 | Management and General | MS0 | 2010-04-01 |  |  |  |  | Scottish Water Wide | -18550.59 | 0 | 33.32 | 114.45 | 0 | 0 | 0 | 0 | 147.77 | 0 | 0 | 0 | -18402.82 | 0 | 0 | 0 | 0 | -18402.82 | 306661.32 | [5 empty] | N | OHDW1 | 100%
47196 | SWS2 Early Start Costs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS2 | 2001-02-25 | 2017-03-27 | 2022-05-30 | 2022-05-30 |  | Scottish Water Wide | 444841.06 | 0 | -57358.55 | -199844.5 | 313291.28 | -141782.53 | 168963.41 | -114384.3 | -31115.19 | -1361.18 | 0 | 0 | 412364.69 | 0 | 0 | 0 | 0 | 412364.69 | 306661.32 | [5 empty] | N | CM_M&G | 100%
402011 | SWS2 Fee reallocation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-02-24 | 2016-04-18 | 2016-03-08 | 2016-03-08 |  | Scottish Water Wide | -487440 | 0 | 487440 | 0 | 0 | 0 | 0 | 0 | 487440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119022.58 | [5 empty] | N | WSNI | 100%
402010 | SWS2 Overhead reallocation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS7 | 2011-02-24 | 2018-11-27 |  | 2019-01-15 |  | Scottish Water Wide | -800000 | 0 | 1330580 | 2484997 | 661852.97 | -942668.54 | -4994.72 | -62.48 | 3529704.24 | 0 | 0 | 0 | 2729704.24 | 0 | 0 | 0 | 0 | 2729704.24 | 613322.63 | [5 empty] | N | OHDS1 | 50% | OHDW1 | 50%
47197 | SWS2 Transition Costs | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWMD | Non OMG180 | MS4 | 2001-02-25 | 2012-01-04 | 2018-04-30 | 2019-02-13 |  | Scottish Water Wide | -2150000 | 0 | -20771288 | 0 | 0 | 0 | 0 | 0 | -20771288 | 0 | 0 | 0 | -22921288 | 0 | 0 | 0 | 0 | -22921288 | 0 | [5 empty] | N | RISK_SWS2 | 100%
402382 | SWW Sulphuric Acid Plant Interventions - Reputational | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-09-29 | 2012-06-05 | 2012-07-25 | 2014-09-01 |  | Scottish Water Wide | 4056919 | 0 | 3800 | -3629.15 | 0 | 0 | 0 | 0 | 170.85 | 0 | 0 | 0 | 4057089.85 | 0 | 0 | 0 | 0 | 4057089.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505968 | SWW Wastewater Reactive Capital | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-08 |  | 2021-05-01 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8668859.01 | 8668859.01 | 593878.58 | 0 | 0 | 9262737.59 | 0 | 0 | 0 | 0 | 9262737.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506334 | SWW Water Reactive Capital Y6 SR15 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-02 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18069237.67 | 18069237.67 | -569237.67 | 0 | 0 | 17500000 | 0 | 0 | 0 | 0 | 17500000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511931 | S-WW-190321-Port Rodie WWPS-Investigate the issues at the Pumping Station | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9999.99 | 0 | 0 | 9999.99 | 0 | 0 | 0 | 0 | 9999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511979 | S-WW-230321-135 Craigleith Road Sewer Investigations | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-03-25 | 2021-09-24 | 2022-05-09 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9999.99 | 0 | 0 | 9999.99 | 0 | 0 | 0 | 0 | 9999.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512064 | S-WW-260321- DALRY STW WWTW 1990 NX622804 - REPLACE BOTTOM BEARING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1800 | 0 | 0 | 1937.38 | 0 | 0 | 0 | 0 | 1937.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512063 | S-WW-260321-GARLIESTON WWTW 1994 NX480461 - REFURB SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1800 | 0 | 0 | 1937.38 | 0 | 0 | 0 | 0 | 1937.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512107 | S-WW-300321-CHEAPSIDE STREET EFOS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208999.98 | 0 | 0 | 208999.98 | 0 | 0 | 0 | 0 | 208999.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512109 | S-WW-300321-NETHERBURN WWTW REPLACE INLET SCREENS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-04-06 | 2021-09-24 | 2022-05-09 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199999.98 | 0 | 0 | 199999.98 | 0 | 0 | 0 | 0 | 199999.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512100 | S-WW-300321-UNION STREET.KIRKCUDBRIGHT-INVESTIGATION | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2021-03-31 | 2021-09-24 | 2022-05-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9999.99 | 0 | 0 | 9999.99 | 0 | 0 | 0 | 0 | 9999.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512133 | S-WW-310321-EAGLESHAM CLARIGESTER | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199999.98 | 0 | 0 | 199999.98 | 0 | 0 | 0 | 0 | 199999.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511003 | S-WW-I-010221-Barrbridge Rd CSO Coatbridge-Repair_Replace trough in screens at CSO | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-02-08 | 2021-05-07 | 2021-09-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 7250.02 | 0 | 0 | 8000.02 | 0 | 0 | 0 | 0 | 8000.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511046 | S-WW-I-030221-Craigentinny North Avenue sewer diversion-Scope options to disconnect combined sewer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2021-02-23 | 2021-03-04 | 2021-08-05 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3333 | 3333 | 6666.65 | 0 | 0 | 9999.65 | 0 | 0 | 0 | 0 | 9999.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507020 | S-WW-I-040620-38 Winton Terrace Edinburgh-Lift and relay 30 mtrs of damaged sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-06-11 |  | 2021-02-13 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53933.19 | 53933.19 | -20133.19 | 0 | 0 | 33800 | 0 | 0 | 0 | 0 | 33800 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507039 | S-WW-I-050620-15 Avon Road Cramond-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.24 | 9.24 | 34290.77 | 0 | 0 | 34300.01 | 0 | 0 | 0 | 0 | 34300.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508094 | S-WW-I-060820-John St Carluke-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-08-13 | 2020-10-19 | 2020-11-27 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26257.83 | 26257.83 | 0 | 0 | 0 | 26257.83 | 0 | 0 | 0 | 0 | 26257.83 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508675 | S-WW-I-080920-3 Leafield Rd Dumfries-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-09-22 | 2021-03-22 | 2021-08-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3148 | 3148 | 46852.11 | 0 | 0 | 50000.11 | 0 | 0 | 0 | 0 | 50000.11 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504278 | S-WW-I-101219-Blackwood -Sewer Collapse | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2019-12-11 |  | 2020-08-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 6069.59 | 191069.59 | 0 | 0 | 0 | 191069.59 | 0 | 0 | 0 | 0 | 191069.59 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504275 | S-WW-I-101219-Kircudbright-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2019-12-11 |  | 2020-06-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 17564.96 | -16256.55 | 1308.41 | 0 | 0 | 0 | 1308.41 | 0 | 0 | 0 | 0 | 1308.41 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505658 | S-WW-I-110320-26 Cultins Road Edinburgh-Engage jetting contractor to attempt retrieval of two jetting hoses | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-07-07 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 654.21 | 10327.05 | 10981.26 | 0 | 0 | 0 | 10981.26 | 0 | 0 | 0 | 0 | 10981.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511745 | S-WW-I-110321-DRUM FARM BEESWING-Feasibility study | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10700.01 | 0 | 0 | 10700.01 | 0 | 0 | 0 | 0 | 10700.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510703 | S-WW-I-140121-Dunbar Beach Sewer- Carry out Survey of beach sewers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2390.66 | 2390.66 | 1918.68 | 0 | 0 | 4309.34 | 0 | 0 | 0 | 0 | 4309.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511877 | S-WW-I-170321-108 Easter Rd-5 mtr dig to repair 150mm connection to main sewer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-24 | 2021-09-24 | 2022-05-09 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000.01 | 0 | 0 | 35000.01 | 0 | 0 | 0 | 0 | 35000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507263 | S-WW-I-180620-Burnside Gate-Project code to pay invoice | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-06-25 |  | 2020-09-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2765.42 | 2765.42 | 0 | 0 | 0 | 2765.42 | 0 | 0 | 0 | 0 | 2765.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505320 | S-WW-I-200220-Primrose Cottage Dalbeattie-Patching & Dig Up to Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-11-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 40065.65 | 45065.65 | 0 | 0 | 0 | 45065.65 | 0 | 0 | 0 | 0 | 45065.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506277 | S-WW-I-200420-24 Nairn Street Larkhall-Excavate in the carriageway to repair 4.5m deep sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-11 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19883.23 | 19883.23 | 5416.77 | 0 | 0 | 25300 | 0 | 0 | 0 | 0 | 25300 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504451 | S-WW-I-201219-Bellshill By-Pass-Repairs to brick chamber supporting the elevated sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2019-12-23 |  | 2020-07-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 21728.11 | 1177.35 | 22905.46 | 0 | 0 | 0 | 22905.46 | 0 | 0 | 0 | 0 | 22905.46 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504464 | S-WW-I-201219-Scotts St Annan-Sewer Relay | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2019-12-23 |  | 2020-11-27 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 49000 | 16990.13 | 65990.13 | 0 | 0 | 0 | 65990.13 | 0 | 0 | 0 | 0 | 65990.13 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504786 | S-WW-I-220120-Tuphole Braidwood Rd Carluke-Rebuild Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-11-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 16302.1 | 41302.1 | 0 | 0 | 0 | 41302.1 | 0 | 0 | 0 | 0 | 41302.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510840 | S-WW-I-220121-12 Glen Tanner Ek-Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-01-28 | 2021-08-13 | 2022-03-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799.07 | 799.07 | 10000 | 0 | 0 | 10799.07 | 0 | 0 | 0 | 0 | 10799.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510848 | S-WW-I-220121-43 Meikle Earnock Road Hamilton-Lift and relay approx 25mtrs of 150mm sewer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2021-01-26 | 2021-02-03 | 2021-05-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1333 | 1333 | 23666.65 | 0 | 0 | 24999.65 | 0 | 0 | 0 | 0 | 24999.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506300 | S-WW-I-220420-Mansefield Athelstaneford-Estimating Work | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-11 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.96 | 71.96 | 1028.04 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507828 | S-WW-I-220720-63 Deanburn Park-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-07-27 | 2020-10-19 | 2021-01-20 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16176.52 | 16176.52 | 0 | 0 | 0 | 16176.52 | 0 | 0 | 0 | 0 | 16176.52 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511490 | S-WW-I-260221-Seafield Recycling Centre scope options | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-10 | 2021-04-09 | 2021-09-27 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.25 | 1439.25 | 18560.75 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510024 | S-WW-I-261120-Loop Cottage Rd Castle Douglas-Pipework Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-12-03 | 2021-03-26 | 2021-11-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4735 | 4735 | 15264.6 | 0 | 0 | 19999.6 | 0 | 0 | 0 | 0 | 19999.6 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506898 | S-WW-I-280520-8 Wilder Place Galashiels-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-06-03 |  | 2021-07-30 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2895 | 2895 | 12104.94 | 0 | 0 | 14999.94 | 0 | 0 | 0 | 0 | 14999.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508681 | S-WW-I-Bothwellbank DOA-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 |  | 2021-04-12 | 2021-07-02 | 2022-02-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12455 | 12455 | 122545.5 | 0 | 0 | 135000.5 | 0 | 0 | 0 | 0 | 135000.5 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507927 | S-WW-I-Multiple Sites-CCTV Equipment Request | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-08-04 |  | 2020-08-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95487.85 | 95487.85 | 0 | 0 | 0 | 95487.85 | 0 | 0 | 0 | 0 | 95487.85 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504354 | S-WW-I-New Troys Road Lesmahagow-Excavate & repair pipe | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2019-12-16 |  | 2020-04-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 20100 | -2436.67 | 17663.33 | 0 | 0 | 0 | 17663.33 | 0 | 0 | 0 | 0 | 17663.33 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508177 | S-WW-I-PRESTON HOUSE ROAD LOCKERBIE-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-08-13 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3144.86 | 3144.86 | 21855.14 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505521 | S-WW-MD RESPONSIVE - Beatsons Builders - Penicuik - Repair Damaged Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-03-05 |  | 2020-08-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3972.61 | 320302.68 | 324275.29 | 125724.71 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 450000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505524 | S-WW-MD RESPONSIVE - Burst Rising Main - Backlowther SPS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-03-05 |  | 2020-06-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2616.82 | 16289.6 | 18906.42 | 0 | 0 | 0 | 18906.42 | 0 | 0 | 0 | 0 | 18906.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504788 | S-WW-NI=220120-Troqueer WWTW-Relpace RAS Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-05-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 16002.57 | 13309.77 | 29312.34 | 0 | 0 | 0 | 29312.34 | 0 | 0 | 0 | 0 | 29312.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511006 | S-WW-NI-010221-Dalscone WWTW-Replace Decant Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-04 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2132.8 | 2132.8 | -132.8 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510991 | S-WW-NI-010221-Skellyton WWTW-Replace DO probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-01 |  | 2021-03-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126.96 | 1126.96 | 91.75 | 0 | 0 | 1218.71 | 0 | 0 | 0 | 0 | 1218.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511533 | S-WW-NI-010321-Coalburn WWTW-Install a self-closing gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-01 |  | 2021-06-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1800 | 0 | 0 | 1937.38 | 0 | 0 | 0 | 0 | 1937.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511529 | S-WW-NI-010321-Lauder WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-01 |  | 2021-06-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1627.31 | 1627.31 | -27.31 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511553 | S-WW-NI-010321-Lesmahagow WWTW-Site Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1783.35 | 1783.35 | 416.65 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511562 | S-WW-NI-010321-Mauldslie WWTW-Install end caps for all biological filters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 124.3 | 1628.58 | 0 | 0 | 1752.88 | 0 | 0 | 0 | 0 | 1752.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506042 | S-WW-NI-01042020-Allers WWTW-Replacement Motor for Grit Plant | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-07-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5257.2 | 5257.2 | 0 | 0 | 0 | 5257.2 | 0 | 0 | 0 | 0 | 5257.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506019 | S-WW-NI-01042020-Bernard Steert Culvert-Flooding Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-04-01 |  | 2020-07-08 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47584.14 | 47584.14 | 0 | 0 | 0 | 47584.14 | 0 | 0 | 0 | 0 | 47584.14 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506021 | S-WW-NI-01042020-Lockerbie WWTW-New Critical Spare Humus Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-06-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2335.52 | 2335.52 | 0 | 0 | 0 | 2335.52 | 0 | 0 | 0 | 0 | 2335.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506023 | S-WW-NI-01042020-Oxton WWTW-Suply & Fit Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-02 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9910.5 | 9910.5 | -110.5 | 0 | 0 | 9800 | 0 | 0 | 0 | 0 | 9800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506037 | S-WW-NI-01042020-Troqueer Final WWPS-Replacement of approx 150m chainlink fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-05-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7960.23 | 7960.23 | 0 | 0 | 0 | 7960.23 | 0 | 0 | 0 | 0 | 7960.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512172 | S-WW-NI-010421- EARLSTON WWTW 1959 NT573382 - REPLACE BIO FILTER 3 PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15200.01 | 0 | 0 | 15200.01 | 0 | 0 | 0 | 0 | 15200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506425 | S-WW-NI-010520-Mauldslie WWTW-Replace gate valve at storm tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-05-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1185.84 | 1185.84 | 0 | 0 | 0 | 1185.84 | 0 | 0 | 0 | 0 | 1185.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506420 | S-WW-NI-010520-Rosewell WWTW-Investigating the final effluent outfall pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-05-01 |  | 2020-11-12 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5744.95 | 5744.95 | 393.07 | 0 | 0 | 6138.02 | 0 | 0 | 0 | 0 | 6138.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506931 | S-WW-NI-01062020-Bathgate WWTW-Construct access ramp | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-03 |  | 2021-03-13 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2478.77 | 2478.77 | -450.71 | 0 | 0 | 2028.06 | 0 | 0 | 0 | 0 | 2028.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506928 | S-WW-NI-010620-Blackwood WWTW-Investigate leaking from distribution Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-08-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2307.34 | 2307.34 | 0 | 0 | 0 | 2307.34 | 0 | 0 | 0 | 0 | 2307.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506933 | S-WW-NI-010620-Crossford WWTW-Refurbish the washwater system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-06-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2046.15 | 2046.15 | 0 | 0 | 0 | 2046.15 | 0 | 0 | 0 | 0 | 2046.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506921 | S-WW-NI-010620-Hawick WWTW-Removal of 4 x brick out houses | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-06-11 | 2020-08-07 | 2020-10-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85168.05 | 85168.05 | 0 | 0 | 0 | 85168.05 | 0 | 0 | 0 | 0 | 85168.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506926 | S-WW-NI-010620-Kelso WWTW-Fit new store door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1783.08 | 1783.08 | -83.08 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507459 | S-WW-NI-010720-Allers WWTW-Refurb 2 Screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-11-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42188.06 | 42188.06 | 0 | 0 | 0 | 42188.06 | 0 | 0 | 0 | 0 | 42188.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507458 | S-WW-NI-010720-Eaglesfield WWTW-Copasac area removal of hand railing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-11-25 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2695.34 | 2695.34 | 0 | 0 | 0 | 2695.34 | 0 | 0 | 0 | 0 | 2695.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507473 | S-WW-NI-010720-Lochmaben WWTW-Replace Washwater Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-08-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3693.43 | 3693.43 | 0 | 0 | 0 | 3693.43 | 0 | 0 | 0 | 0 | 3693.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507477 | S-WW-NI-010720-Shotts WWTW-Replace Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-10-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7341.5 | 7341.5 | 0 | 0 | 0 | 7341.5 | 0 | 0 | 0 | 0 | 7341.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507472 | S-WW-NI-010720-Troqueer WWTW-Replace Actuated Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-09-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3336.5 | 3336.5 | 0 | 0 | 0 | 3336.5 | 0 | 0 | 0 | 0 | 3336.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507464 | S-WW-NI-010720-Winchburgh WWTW-Supply & Install Compressor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-10-15 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6612.1 | 6612.1 | 0 | 0 | 0 | 6612.1 | 0 | 0 | 0 | 0 | 6612.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508511 | S-WW-NI-010920-Glen Noble WWPS-To investigate the reason for the progressive ground failure | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-09-03 | 2021-02-07 | 2021-10-18 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4643 | 4643 | 21841.01 | 0 | 0 | 26484.01 | 0 | 0 | 0 | 0 | 26484.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503784 | S-WW-NI-011119-Philipshill WWTW-Storm Mixer Removal | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-07-22 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2901.18 | 2901.18 | 0 | 0 | 0 | 2901.18 | 0 | 0 | 0 | 0 | 2901.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510065 | S-WW-NI-011220-Port Rodie WWPS-Replace Probe on Sump Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-02-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2449.89 | 2449.89 | -49.89 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511017 | S-WW-NI-020221-Hamilton WWTW-Replace a section of the RAS channel on FST3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-04 |  | 2021-03-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2769.9 | 2769.9 | 64.25 | 0 | 0 | 2834.15 | 0 | 0 | 0 | 0 | 2834.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511012 | S-WW-NI-020221-Troqueer STC-Replace Inlet Valve on Sludge holding tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-04 |  | 2021-03-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1779.72 | 1779.72 | -161 | 0 | 0 | 1618.72 | 0 | 0 | 0 | 0 | 1618.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511568 | S-WW-NI-020321-Collin WWTW-Replacement of Scum Boards on PST 1 and PST 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.83 | 345.83 | 1885.74 | 0 | 0 | 2231.57 | 0 | 0 | 0 | 0 | 2231.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506068 | S-WW-NI-02042020-Athelstaneford WWTW-Lifting Equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-06 |  | 2020-08-14 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7393.34 | 7393.34 | 0 | 0 | 0 | 7393.34 | 0 | 0 | 0 | 0 | 7393.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506048 | S-WW-NI-02042020-Daldowie WWTW-Critical Spares for NTF | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-09-04 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10466.32 | 10466.32 | 0 | 0 | 0 | 10466.32 | 0 | 0 | 0 | 0 | 10466.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506069 | S-WW-NI-02042020-Gullane WWTW-Lifting Equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-06 |  | 2020-07-08 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3118.58 | 3118.58 | 0 | 0 | 0 | 3118.58 | 0 | 0 | 0 | 0 | 3118.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506066 | S-WW-NI-02042020-Innerwick WWTW-Lifting Equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-07-13 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3757.84 | 3757.84 | 0 | 0 | 0 | 3757.84 | 0 | 0 | 0 | 0 | 3757.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506054 | S-WW-NI-02042020-Mennock SEP-Replacment of path and steps to sample point | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-07-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448.2 | 3448.2 | 0 | 0 | 0 | 3448.2 | 0 | 0 | 0 | 0 | 3448.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506058 | S-WW-NI-02042020-Olivers Tank SST-Install overland pipe | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-04-02 |  | 2020-04-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7389.64 | 7389.64 | 0 | 0 | 0 | 7389.64 | 0 | 0 | 0 | 0 | 7389.64 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506062 | S-WW-NI-02042020-Shotts WWTW-Replace compactor gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-07-30 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6253.82 | 6253.82 | 0 | 0 | 0 | 6253.82 | 0 | 0 | 0 | 0 | 6253.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506064 | S-WW-NI-02042020-Tyneholm WWPS-Replacement of 2No Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-04-02 |  | 2021-02-20 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16846.89 | 16846.89 | 164.11 | 0 | 0 | 17011 | 0 | 0 | 0 | 0 | 17011 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512177 | S-WW-NI-02042021-HARTHILL WWTW-REPLACEMENT HUMUS SLUDGE RETURN PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193.64 | 0 | 0 | 1193.64 | 0 | 0 | 0 | 0 | 1193.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512175 | S-WW-NI-02042021-PRESTONPANS WWPS-REPLACE 2XMAG TRANSMITTERS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754.69 | 0 | 0 | 1754.69 | 0 | 0 | 0 | 0 | 1754.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512179 | S-WW-NI-02042021-SALSBURGH WWTW-INSTALL HANDRAILING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-02 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5014.73 | 0 | 0 | 5014.73 | 0 | 0 | 0 | 0 | 5014.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506966 | S-WW-NI-020620-Albert Rd WWPS-Replace level sensors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-06-18 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559.39 | 2559.39 | 0 | 0 | 0 | 2559.39 | 0 | 0 | 0 | 0 | 2559.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506954 | S-WW-NI-020620-Daldowie WWTW-Replace Autosampler Compressor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1561.75 | 1561.75 | 0 | 0 | 0 | 1561.75 | 0 | 0 | 0 | 0 | 1561.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506958 | S-WW-NI-020620-Garlieston WWTW-Replace Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-06-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2494.2 | 2494.2 | 0 | 0 | 0 | 2494.2 | 0 | 0 | 0 | 0 | 2494.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506962 | S-WW-NI-020620-Mauldslie WWTW-Replacement batteries for MCC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381.02 | 1381.02 | 0 | 0 | 0 | 1381.02 | 0 | 0 | 0 | 0 | 1381.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507485 | S-WW-NI-020720-Allers WWTW-Purchase Washpactor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-07-07 | 2021-03-22 | 2021-06-07 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52854.16 | 52854.16 | 27273.72 | 0 | 0 | 80127.88 | 0 | 0 | 0 | 0 | 80127.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507501 | S-WW-NI-020720-Carbarns WWTW-Refurb Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-07-03 |  | 2021-07-30 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19154.32 | 19154.32 | 6080.65 | 0 | 0 | 25234.97 | 0 | 0 | 0 | 0 | 25234.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507491 | S-WW-NI-020720-Clarencefield WWTW-Install Toilet on Site | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-11-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9463.74 | 9463.74 | 0 | 0 | 0 | 9463.74 | 0 | 0 | 0 | 0 | 9463.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507499 | S-WW-NI-020720-Eaglesfield WWTW-H&S Civils | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-11-25 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8561.79 | 8561.79 | 0 | 0 | 0 | 8561.79 | 0 | 0 | 0 | 0 | 8561.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507487 | S-WW-NI-020720-Philipshill WWTW-Refurb Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-09-29 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8558.88 | 8558.88 | 0 | 0 | 0 | 8558.88 | 0 | 0 | 0 | 0 | 8558.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508537 | S-WW-NI-020920-Bothwellbank WWTW-Replace Scrapers FST3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-02 |  | 2020-09-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3651.85 | 3651.85 | 0 | 0 | 0 | 3651.85 | 0 | 0 | 0 | 0 | 3651.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508535 | S-WW-NI-020920-Bothwellbank WWTW-Replace Scrappers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-02 |  | 2020-09-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3651.85 | 3651.85 | 0 | 0 | 0 | 3651.85 | 0 | 0 | 0 | 0 | 3651.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508546 | S-WW-NI-020920-Langholm WWTW-Replace slip rings on all 4 tanks | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-02 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.55 | 1285.55 | 16314.46 | 0 | 0 | 17600.01 | 0 | 0 | 0 | 0 | 17600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508545 | S-WW-NI-020920-Linlithgow WWTW-Replace Support Beams | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-02 |  | 2020-10-29 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769.1 | 3769.1 | 0 | 0 | 0 | 3769.1 | 0 | 0 | 0 | 0 | 3769.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508540 | S-WW-NI-020920-Port Edgar WWPS-Replace Inlet Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-02 |  | 2021-03-18 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17668.9 | 17668.9 | 31.1 | 0 | 0 | 17700 | 0 | 0 | 0 | 0 | 17700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508541 | S-WW-NI-020920-S Queensferry WWTW-SAS Pump & Guide Rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-02 |  | 2020-10-23 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3261.19 | 3261.19 | 0 | 0 | 0 | 3261.19 | 0 | 0 | 0 | 0 | 3261.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508538 | S-WW-NI-020920-Stonehouse WWTW-Replace Sludge Dewatering Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-02 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630.85 | 630.85 | 8869.15 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 9500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509074 | S-WW-NI-021020-Dalry WWTW-Covers and Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-02 |  | 2021-02-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6647.8 | 6647.8 | -47.8 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 6600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509076 | S-WW-NI-021020-Garlieston North WWPS-Make the covers flush and supply fall protection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-02 |  | 2021-03-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14878.88 | 14878.88 | -278.88 | 0 | 0 | 14600 | 0 | 0 | 0 | 0 | 14600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509077 | S-WW-NI-021020-Garlieston South WWPS-Make the covers flush and supply fall protection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-02 |  | 2021-03-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15048.36 | 15048.36 | -248.36 | 0 | 0 | 14800 | 0 | 0 | 0 | 0 | 14800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509078 | S-WW-NI-021020-Moffat WWTW-Replace PST 2 motor & gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-02 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2377.12 | 2377.12 | 1622.88 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509085 | S-WW-NI-021020-Troqueer STW-Replace PLC on Faulty Filtrate Control | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-02 |  | 2020-10-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1830.14 | 1830.14 | 0 | 0 | 0 | 1830.14 | 0 | 0 | 0 | 0 | 1830.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504092 | S-WW-NI-021219-Bathgate WWTW-Repair to Boiler Room Roof | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-02-11 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 5705.96 | 0 | 5705.96 | 0 | 0 | 0 | 5705.96 | 0 | 0 | 0 | 0 | 5705.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504104 | S-WW-NI-021219-Dunbar WWTW-Replace Permeate Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-02-03 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1205.06 | 0 | 1205.06 | 0 | 0 | 0 | 1205.06 | 0 | 0 | 0 | 0 | 1205.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504089 | S-WW-NI-021219-Haddington WWTW-Replace Lower bearing on screw pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 36.94 | 467.09 | 504.03 | -300.93 | 0 | 0 | 203.1 | 0 | 0 | 0 | 0 | 203.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504097 | S-WW-NI-021219-North Berwick WWTW-Replacement Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-02-21 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 37473.98 | 0 | 37473.98 | 0 | 0 | 0 | 37473.98 | 0 | 0 | 0 | 0 | 37473.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504085 | S-WW-NI-021219-Ormiston WWTW-Critical Spare Basket | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-02-05 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 2824.32 | -0.01 | 2824.31 | 0 | 0 | 0 | 2824.31 | 0 | 0 | 0 | 0 | 2824.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504106 | S-WW-NI-021219-Troqueer WWTW-Replacement ball cock & float | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-02-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2491.3 | 0 | 2491.3 | 0 | 0 | 0 | 2491.3 | 0 | 0 | 0 | 0 | 2491.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510085 | S-WW-NI-021220-Avonbridge WWTW-Replace 2 No open chanNel flow monitors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6446.29 | 6446.29 | -146.29 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 6300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510096 | S-WW-NI-021220-Galashiels STC-Replace gas monitor panel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-02-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5779.34 | 5779.34 | -79.34 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 5700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510091 | S-WW-NI-021220-Galashiels STC-Thickened sludge tank mixer motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500.5 | 500.5 | 5099.5 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 5600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510101 | S-WW-NI-021220-Hamilton WWTW-Tanker Fill Building Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-12-14 | 2021-02-22 | 2021-05-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3721 | 3721 | 6279.44 | 0 | 0 | 10000.44 | 0 | 0 | 0 | 0 | 10000.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510080 | S-WW-NI-021220-Newbridge WWPS-Replace Pump No 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11984.34 | 11984.34 | -84.33 | 0 | 0 | 11900.01 | 0 | 0 | 0 | 0 | 11900.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510082 | S-WW-NI-021220-Newbridge WWPS-Replace Pump No 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 912.64 | 912.64 | 10987.36 | 0 | 0 | 11900 | 0 | 0 | 0 | 0 | 11900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510079 | S-WW-NI-021220-Philipshill WWTW-Refurb Storm tank mixer No.4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3943.94 | 3943.94 | 2556.07 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511043 | S-WW-NI-030221-Coldstream WWTW-Install permanent pipework to sludge return line | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-04 |  | 2021-05-03 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415.46 | 415.46 | 3903.25 | 0 | 0 | 4318.71 | 0 | 0 | 0 | 0 | 4318.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511037 | S-WW-NI-030221-Daldowie WWTW-Replacement bottom bearing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-08 |  | 2021-05-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6062.86 | 6062.86 | 5137.15 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 11200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511047 | S-WW-NI-030221-Galashiels STC-Thickened sludge tank mixer coupling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-04 |  | 2021-04-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3106.07 | 3106.07 | -106.05 | 0 | 0 | 3000.02 | 0 | 0 | 0 | 0 | 3000.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511045 | S-WW-NI-030221-Langholm WWTW-Refurbish filter drive 1 & 2 motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-04 |  | 2021-03-27 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2977.99 | 2977.99 | -178 | 0 | 0 | 2799.99 | 0 | 0 | 0 | 0 | 2799.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511034 | S-WW-NI-030221-Skellyton WWTW-Provide and install replacement washwater kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-04 |  | 2021-05-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457.02 | 457.02 | 18861.7 | 0 | 0 | 19318.72 | 0 | 0 | 0 | 0 | 19318.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511593 | S-WW-NI-030321-Allers WWTW-Replace RAS pump 2 for FST 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392.52 | 392.52 | 5142.84 | 0 | 0 | 5535.36 | 0 | 0 | 0 | 0 | 5535.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511584 | S-WW-NI-030321-Ancrum WWTW-Install bauer coupling to final tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-03 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298.62 | 298.62 | 2400 | 0 | 0 | 2698.62 | 0 | 0 | 0 | 0 | 2698.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511595 | S-WW-NI-030321-Ashgill WWTW-Refurbish the storm screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15715.67 | 15715.67 | 84.33 | 0 | 0 | 15800 | 0 | 0 | 0 | 0 | 15800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511583 | S-WW-NI-030321-Carbarns WWTW-Carry out an inspection and investigation for cabling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-03 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464.49 | 464.49 | 6085.74 | 0 | 0 | 6550.23 | 0 | 0 | 0 | 0 | 6550.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511588 | S-WW-NI-030321-Powfoot WWTW-Replace inlet valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-03 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344.41 | 344.41 | 3000 | 0 | 0 | 3344.41 | 0 | 0 | 0 | 0 | 3344.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511581 | S-WW-NI-030321-Shotts WWTW-Refurbish the gearbox from aerator No8 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-03 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.14 | 255.14 | 3342.84 | 0 | 0 | 3597.98 | 0 | 0 | 0 | 0 | 3597.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511589 | S-WW-NI-030321-Torthorwald WWTW-Replacement FE Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437.41 | 437.41 | 3085.74 | 0 | 0 | 3523.15 | 0 | 0 | 0 | 0 | 3523.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506082 | S-WW-NI-03042020-Coursington WWTW-Blower Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-06 |  | 2020-06-30 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4462.86 | 4462.86 | 0 | 0 | 0 | 4462.86 | 0 | 0 | 0 | 0 | 4462.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506084 | S-WW-NI-03042020-Eyemouth WWTW-Replace outlet pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-06 |  | 2020-04-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2045.72 | 2045.72 | 0 | 0 | 0 | 2045.72 | 0 | 0 | 0 | 0 | 2045.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506077 | S-WW-NI-03042020-West Linton WWPS-Replace inlet pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-06 |  | 2020-06-04 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1799.13 | 1799.13 | 0 | 0 | 0 | 1799.13 | 0 | 0 | 0 | 0 | 1799.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506978 | S-WW-NI-030620-Allers WWTW-Refurb Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-09-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5806 | 5806 | 0 | 0 | 0 | 5806 | 0 | 0 | 0 | 0 | 5806 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506987 | S-WW-NI-030620-Beeswing WWTW-Replacement Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-06-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17172.26 | 17172.26 | 0 | 0 | 0 | 17172.26 | 0 | 0 | 0 | 0 | 17172.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506979 | S-WW-NI-030620-Eaglesham WWTW-Replacement Bearing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-08 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5397.46 | 5397.46 | 0 | 0 | 0 | 5397.46 | 0 | 0 | 0 | 0 | 5397.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506991 | S-WW-NI-030620-Eastriggs WWTW-Replace the thickened sludge pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-08-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4083.2 | 4083.2 | 0 | 0 | 0 | 4083.2 | 0 | 0 | 0 | 0 | 4083.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506986 | S-WW-NI-030620-Glenluce WWTW-Refurb WashWater System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-06-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3538.42 | 3538.42 | 0 | 0 | 0 | 3538.42 | 0 | 0 | 0 | 0 | 3538.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506976 | S-WW-NI-030620-Jedburgh WWTW-Repair roof of aeration kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-03 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290.82 | 290.82 | 1609.18 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506977 | S-WW-NI-030620-Philipshill WWTW-Fit Chequer plates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-09-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27382.17 | 27382.17 | 0 | 0 | 0 | 27382.17 | 0 | 0 | 0 | 0 | 27382.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506981 | S-WW-NI-030620-Philipshill WWTW-Replacement Bearing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-06-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3399.18 | 3399.18 | 0 | 0 | 0 | 3399.18 | 0 | 0 | 0 | 0 | 3399.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506989 | S-WW-NI-030620-Roslin WWTW-New Pathways | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-03 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4723.26 | 4723.26 | 0 | 0 | 0 | 4723.26 | 0 | 0 | 0 | 0 | 4723.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506993 | S-WW-NI-030620-South Queensferry WWTW-Liquor Balancing Tank Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-08-19 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35327.4 | 35327.4 | 0 | 0 | 0 | 35327.4 | 0 | 0 | 0 | 0 | 35327.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506984 | S-WW-NI-030620-Torphichen WWTW-Pipework Mods | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-03 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1934.44 | 1934.44 | 23265.57 | 0 | 0 | 25200.01 | 0 | 0 | 0 | 0 | 25200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506985 | S-WW-NI-030620-Troqueer WWTW-Install Dosing Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-06-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2872.96 | 2872.96 | 0 | 0 | 0 | 2872.96 | 0 | 0 | 0 | 0 | 2872.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507516 | S-WW-NI-030720-Blackwood WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-08-20 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491.44 | 1491.44 | 0 | 0 | 0 | 1491.44 | 0 | 0 | 0 | 0 | 1491.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507512 | S-WW-NI-030720-Carfin WWPS-Replace impellors on pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-10-02 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2142.84 | 2142.84 | 0 | 0 | 0 | 2142.84 | 0 | 0 | 0 | 0 | 2142.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507524 | S-WW-NI-030720-Haddington WWTW-Replace Generator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-07-10 | 2021-06-04 | 2021-08-30 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26818 | 26818 | 73181.65 | 0 | 0 | 99999.65 | 0 | 0 | 0 | 0 | 99999.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507511 | S-WW-NI-030720-Ravenscraig Main WWPS-Replace Barrier | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-11-12 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1945.19 | 1945.19 | 0 | 0 | 0 | 1945.19 | 0 | 0 | 0 | 0 | 1945.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507510 | S-WW-NI-030720-Rosewell WWTW-Construct Access Paths | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2021-02-10 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10496.27 | 10496.27 | 3.73 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 10500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507522 | S-WW-NI-030720-Stonehouse WWTW-Inlet Screen refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-07-08 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1932.04 | 1932.04 | 0 | 0 | 0 | 1932.04 | 0 | 0 | 0 | 0 | 1932.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507515 | S-WW-NI-030720-Troqueer WWTW-Replace FST brushes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-03 |  | 2020-07-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1833.02 | 1833.02 | 0 | 0 | 0 | 1833.02 | 0 | 0 | 0 | 0 | 1833.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508002 | S-WW-NI-030820-Daldowie WWTW-Replacement Invertor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-08-21 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2232.44 | 2232.44 | 0 | 0 | 0 | 2232.44 | 0 | 0 | 0 | 0 | 2232.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508005 | S-WW-NI-030820-Gretna Services WWTW-Install fall arrest | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-11-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257.83 | 2257.83 | 0 | 0 | 0 | 2257.83 | 0 | 0 | 0 | 0 | 2257.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508000 | S-WW-NI-030820-Kings Drive WWPS-Replacement Level Sensor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-08-13 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1154.26 | 1154.26 | 0 | 0 | 0 | 1154.26 | 0 | 0 | 0 | 0 | 1154.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508559 | S-WW-NI-030920-Allers WWTW-Replace Scum Pumps with Submersible | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-09-07 | 2021-05-03 | 2021-07-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13367 | 13367 | 6722.76 | 0 | 0 | 20089.76 | 0 | 0 | 0 | 0 | 20089.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508557 | S-WW-NI-030920-Bothwellbank WWTW-Odour Survey Follow On | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-09-07 | 2020-10-22 | 2021-06-04 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9894 | 9894 | 105.56 | 0 | 0 | 9999.56 | 0 | 0 | 0 | 0 | 9999.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508554 | S-WW-NI-030920-Dalry WWTW-H&S Work | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-03 |  | 2020-11-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220.43 | 3220.43 | 0 | 0 | 0 | 3220.43 | 0 | 0 | 0 | 0 | 3220.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508553 | S-WW-NI-030920-Galashiels STC-Critical spare motor & gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-03 |  | 2020-10-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15620.21 | 15620.21 | 0 | 0 | 0 | 15620.21 | 0 | 0 | 0 | 0 | 15620.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508560 | S-WW-NI-030920-Glentrool WWTW-Road Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-09-07 | 2020-12-02 | 2021-02-23 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508561 | S-WW-NI-030920-Strathaven WWTW-Replace damaged drives | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-03 |  | 2020-10-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3243.24 | 3243.24 | 0 | 0 | 0 | 3243.24 | 0 | 0 | 0 | 0 | 3243.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508556 | S-WW-NI-030920-Troqueer STC-Replacement Impellors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-03 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2832.32 | 2832.32 | -32.32 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509590 | S-WW-NI-031120-Dalscone WWTW-Replace RAS Return Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1971.04 | 1971.04 | -52.33 | 0 | 0 | 1918.71 | 0 | 0 | 0 | 0 | 1918.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509592 | S-WW-NI-031120-Skellyton WWTW-Replace DO Sensor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-05 |  | 2020-11-18 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113.26 | 1113.26 | 0 | 0 | 0 | 1113.26 | 0 | 0 | 0 | 0 | 1113.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504125 | S-WW-NI-031219-Allers WWTW-Replacement Radio Link | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2019-12-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1938.89 | 0 | 1938.89 | 0 | 0 | 0 | 1938.89 | 0 | 0 | 0 | 0 | 1938.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504123 | S-WW-NI-031219-Port Rodie WWPS-Replacement Modems for SCADA | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-01-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1868.36 | 0 | 1868.36 | 0 | 0 | 0 | 1868.36 | 0 | 0 | 0 | 0 | 1868.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510122 | S-WW-NI-031220-Daldowie WWTW-Replace gearbox and motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-03 |  | 2021-02-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4952.9 | 4952.9 | 47.1 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510111 | S-WW-NI-031220-Galashiels WWTW-Refurbish drive & idler wheels | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-03 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5810.43 | 5810.43 | -210.43 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 5600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510118 | S-WW-NI-031220-Harthill WWTW-Critical Spares | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-03 |  | 2021-02-10 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4440.74 | 4440.74 | 59.26 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510114 | S-WW-NI-031220-Leet Green WWPS-Replace pump no.2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-03-08 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10534.34 | 10534.34 | -134.33 | 0 | 0 | 10400.01 | 0 | 0 | 0 | 0 | 10400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511058 | S-WW-NI-040221-Annan WWTW-Refurbish Thickener feed pump B | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-04 |  | 2021-03-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6176.92 | 6176.92 | -176.9 | 0 | 0 | 6000.02 | 0 | 0 | 0 | 0 | 6000.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511065 | S-WW-NI-040221-CALDERCRUIX THE MILL WWPS-Replace pump guide rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-04 |  | 2021-05-04 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.04 | 198.04 | 2149.55 | 0 | 0 | 2347.59 | 0 | 0 | 0 | 0 | 2347.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511063 | S-WW-NI-040221-East Mains WWPS-Replace NRVs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-04 |  | 2021-03-20 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2469.45 | 2469.45 | 30.55 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511054 | S-WW-NI-040221-Gretna WWTW-Refurbish sludge Mixer no.2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-04 |  | 2021-05-04 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5156.02 | 5156.02 | -156.02 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511061 | S-WW-NI-040221-Lockerbie WWTW-Refurbish Filter bed no5 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-04 |  | 2021-05-04 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2777.43 | 2777.43 | 22.57 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511049 | S-WW-NI-040221-Peebles WWTW-Refurbish inlet screen compactor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-04 |  | 2021-04-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8137.24 | 8137.24 | -118.5 | 0 | 0 | 8018.74 | 0 | 0 | 0 | 0 | 8018.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511605 | S-WW-NI-040321-Carbarns WWTW-Add durbar pating to the running surface of FST 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-04 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 837.38 | 837.38 | 10971.42 | 0 | 0 | 11808.8 | 0 | 0 | 0 | 0 | 11808.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511602 | S-WW-NI-040321-Carbarns WWTW-Carry out concrete repairs to the wallhead of FST 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-04 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 673.83 | 673.83 | 8828.58 | 0 | 0 | 9502.41 | 0 | 0 | 0 | 0 | 9502.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511614 | S-WW-NI-040321-Carbarns WWTW-DO Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-04 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374.42 | 1374.42 | 25.58 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511609 | S-WW-NI-040321-Dunnswood WWTW-Refurb Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-04 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.31 | 981.31 | 14018.69 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511615 | S-WW-NI-040321-Newtown St Boswells WWTW-Replace Humus return pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-04 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2393.21 | 2393.21 | 6.79 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511601 | S-WW-NI-040321-Skellyton WWTW-Replace the manual inlet bypass bar screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-04 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680.37 | 680.37 | 8914.26 | 0 | 0 | 9594.63 | 0 | 0 | 0 | 0 | 9594.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511612 | S-WW-NI-040321-Twynholm WWTW-Centre column Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2142.84 | 0 | 0 | 2306.39 | 0 | 0 | 0 | 0 | 2306.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506438 | S-WW-NI-040520-Various Sites-Analysis Kit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-05-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7278 | 7278 | 0 | 0 | 0 | 7278 | 0 | 0 | 0 | 0 | 7278 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507033 | S-WW-NI-040620-Bothwellbank WWTW-Odour Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-09-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2729.36 | 2729.36 | 0 | 0 | 0 | 2729.36 | 0 | 0 | 0 | 0 | 2729.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507030 | S-WW-NI-040620-Carbarns WWTW-Replace outdated internet provision | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-11-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4780.92 | 4780.92 | 0 | 0 | 0 | 4780.92 | 0 | 0 | 0 | 0 | 4780.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507023 | S-WW-NI-040620-Castlecary WWPS-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-20 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5836.79 | 5836.79 | 0 | 0 | 0 | 5836.79 | 0 | 0 | 0 | 0 | 5836.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507014 | S-WW-NI-040620-Galashiels WWTW-Replace centrifuge 2 gearbox motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3352.1 | 3352.1 | 0 | 0 | 0 | 3352.1 | 0 | 0 | 0 | 0 | 3352.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507011 | S-WW-NI-040620-Langholm WWTW-Replace scum board on PST1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-11 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528.75 | 528.75 | 7271.25 | 0 | 0 | 7800 | 0 | 0 | 0 | 0 | 7800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507009 | S-WW-NI-040620-Peebles WWTW-Refurb Filter Beds 3&4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-10-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594.14 | 7594.14 | 0 | 0 | 0 | 7594.14 | 0 | 0 | 0 | 0 | 7594.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507010 | S-WW-NI-040620-Peebles WWTW-Refurbishment filter beds 3 & 4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-06-25 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3202.29 | 3202.29 | 0 | 0 | 0 | 3202.29 | 0 | 0 | 0 | 0 | 3202.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507026 | S-WW-NI-040620-Salsburgh WWTW-Replacement of the dosing syphon | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-09-24 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6989.9 | 6989.9 | 0 | 0 | 0 | 6989.9 | 0 | 0 | 0 | 0 | 6989.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507028 | S-WW-NI-040620-Shotts WWTW-Refurb Amonia Monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-09-23 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6199.93 | 6199.93 | 0 | 0 | 0 | 6199.93 | 0 | 0 | 0 | 0 | 6199.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507008 | S-WW-NI-040620-Walkerburn WWTW-Refurbishment of all three filter beds | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-10-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6546.06 | 6546.06 | 0 | 0 | 0 | 6546.06 | 0 | 0 | 0 | 0 | 6546.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508020 | S-WW-NI-040820-Garlieston WWTW-Replace Pipework and fitting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-11-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1859.49 | 1859.49 | 0 | 0 | 0 | 1859.49 | 0 | 0 | 0 | 0 | 1859.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508017 | S-WW-NI-040820-Haddington WWTW-Replace cutter heads for the macerators | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-10-15 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1128.26 | 1128.26 | 71.74 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509626 | S-WW-NI-041120-Castle Douglas WWTW-Replace the MLSS System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12401.72 | 12401.72 | -160.08 | 0 | 0 | 12241.64 | 0 | 0 | 0 | 0 | 12241.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509614 | S-WW-NI-041120-Daldowie WWTW-Replace clutch and critical spare | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-02-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17982.12 | 17982.12 | 1917.88 | 0 | 0 | 19900 | 0 | 0 | 0 | 0 | 19900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509619 | S-WW-NI-041120-Glenluce WWTW-Replace faulty trace heating components | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-03-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2961.27 | 2961.27 | -161.27 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509610 | S-WW-NI-041120-Kelso WWTW-Install Inlet Auto Sampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1962.62 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509634 | S-WW-NI-041120-Kennedy WWTW-Replacement of the copings on circular percolating filters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392.42 | 392.42 | 2307.58 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509622 | S-WW-NI-041120-Loch Ryan WWTW-Replace bridge wheels on PST 1 and 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-05 |  | 2020-11-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4822.38 | 4822.38 | 0 | 0 | 0 | 4822.38 | 0 | 0 | 0 | 0 | 4822.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509628 | S-WW-NI-041120-Loch Ryan WWTW-Replace Grit Plant Automated Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-02-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2823.94 | 2823.94 | -23.94 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504156 | S-WW-NI-041219-Annan WWTW-Screen Motor & Bearings Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-02-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 6187.46 | 0 | 6187.46 | 0 | 0 | 0 | 6187.46 | 0 | 0 | 0 | 0 | 6187.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504137 | S-WW-NI-041219-Dunnswood WWTW-Refurb RAS Pump Set | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-03-06 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 9997.56 | 0 | 9997.56 | 0 | 0 | 0 | 9997.56 | 0 | 0 | 0 | 0 | 9997.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504141 | S-WW-NI-041219-Eaglesham WWTW-Scraper Assembly Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-02-07 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 3856.81 | 0 | 3856.81 | 0 | 0 | 0 | 3856.81 | 0 | 0 | 0 | 0 | 3856.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510144 | S-WW-NI-041220-Carbarns WWTW-Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8248.36 | 8248.36 | 7851.64 | 0 | 0 | 16100 | 0 | 0 | 0 | 0 | 16100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510146 | S-WW-NI-041220-Enterprise WWPS-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7214.7 | 7214.7 | -14.69 | 0 | 0 | 7200.01 | 0 | 0 | 0 | 0 | 7200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510150 | S-WW-NI-041220-Harbour Square WWPS-Modifications to allow easy over pumping | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-14 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559.37 | 1559.37 | 40.63 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510142 | S-WW-NI-041220-High Merryton East WWPS-Fitting Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 876.64 | 876.64 | 12523.36 | 0 | 0 | 13400 | 0 | 0 | 0 | 0 | 13400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510155 | S-WW-NI-041220-Lanark WWTW-Part Refurb of Screen 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-14 |  | 2020-10-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1932.74 | 1932.74 | 0 | 0 | 0 | 1932.74 | 0 | 0 | 0 | 0 | 1932.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510157 | S-WW-NI-041220-Town Yetholm WWTW-New penstock to PST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2225.42 | 2225.42 | -225.42 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510153 | S-WW-NI-041220-Troqueer WWTW-Replace the NRVs on the RAS return line | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448.55 | 1448.55 | 51.45 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505040 | S-WW-NI-050220-Dunnswood WWTW-Ferric Kiosk Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-06-02 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 8200 | 1122.88 | 9322.88 | 0 | 0 | 0 | 9322.88 | 0 | 0 | 0 | 0 | 9322.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505038 | S-WW-NI-050220-Eastfield WWPS-Refurb Pump 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-24 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 8200 | -7645.08 | 554.92 | 7645.08 | 0 | 0 | 8200 | 0 | 0 | 0 | 0 | 8200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505043 | S-WW-NI-050220-Ravenscraig Main WWPS-Generator Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-06-16 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 11.66 | 1311.66 | 0 | 0 | 0 | 1311.66 | 0 | 0 | 0 | 0 | 1311.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511632 | S-WW-NI-050321-S Queensferry WWTW-Replace the liquor return pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-05 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170.93 | 2170.93 | 29.07 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506474 | S-WW-NI-050520-KIRKCUD SELKIRK RD WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-06-23 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2347.71 | 2347.71 | 0 | 0 | 0 | 2347.71 | 0 | 0 | 0 | 0 | 2347.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506484 | S-WW-NI-050520-Port Edgar WWTW-Screen Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-05-14 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2889.72 | 2889.72 | 0 | 0 | 0 | 2889.72 | 0 | 0 | 0 | 0 | 2889.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507046 | S-WW-NI-050620-Carrington WWTW-Replace steps on site | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-10-28 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3005.5 | 3005.5 | 0 | 0 | 0 | 3005.5 | 0 | 0 | 0 | 0 | 3005.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507038 | S-WW-NI-050620-Eastfield WWPS-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-29 |  | 2020-11-04 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8340.25 | 8340.25 | 59.75 | 0 | 0 | 8400 | 0 | 0 | 0 | 0 | 8400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507059 | S-WW-NI-050620-Lockerbie WWTW-Resurface the area around the sludge bed | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-29 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675.94 | 675.94 | 7824.06 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 8500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507043 | S-WW-NI-050620-Penicuik WWTW--Replacement Steps H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5682.14 | 5682.14 | 0 | 0 | 0 | 5682.14 | 0 | 0 | 0 | 0 | 5682.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507048 | S-WW-NI-050620-Philipstoun WWTW-Dosing Syphon | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-08-24 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7846.6 | 7846.6 | 0 | 0 | 0 | 7846.6 | 0 | 0 | 0 | 0 | 7846.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507056 | S-WW-NI-050620-Troqueer WWTW-Resurface Area at inlet | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-10-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10747.32 | 10747.32 | 0 | 0 | 0 | 10747.32 | 0 | 0 | 0 | 0 | 10747.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507051 | S-WW-NI-050620-Troqueer WWTW-Resurface Car Park | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-08-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16471.82 | 16471.82 | 0 | 0 | 0 | 16471.82 | 0 | 0 | 0 | 0 | 16471.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508069 | S-WW-NI-050820-Ancrum WWTW-Handrails around inlet works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-05 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 878.54 | 878.54 | 9021.46 | 0 | 0 | 9900 | 0 | 0 | 0 | 0 | 9900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508063 | S-WW-NI-050820-Balmaclellan WwTW-Reed Bed | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-08-06 | 2021-02-23 | 2021-08-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41912.16 | 41912.16 | 61715.9 | 0 | 0 | 103628.06 | 0 | 0 | 0 | 0 | 103628.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508067 | S-WW-NI-050820-Beeswing WWTW-Refurbish Reed Beds | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-08-06 | 2021-02-08 | 2021-08-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21640.36 | 21640.36 | 64631.39 | 0 | 0 | 86271.75 | 0 | 0 | 0 | 0 | 86271.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508062 | S-WW-NI-050820-Bothwellbank WWTW-Refurbish Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-05 |  | 2020-10-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5238.04 | 5238.04 | 0 | 0 | 0 | 5238.04 | 0 | 0 | 0 | 0 | 5238.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508070 | S-WW-NI-050820-Castle Kennedy WWTW-Install CSO | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-08-06 | 2021-09-02 | 2021-12-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43102 | 43102 | 140898.2 | 0 | 0 | 184000.2 | 0 | 0 | 0 | 0 | 184000.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508066 | S-WW-NI-050820-Galashiels STC-Replace sludge tank mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-05 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9716.77 | 9716.77 | -279.36 | 0 | 0 | 9437.41 | 0 | 0 | 0 | 0 | 9437.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508077 | S-WW-NI-050820-Lauder WWTW-Replace Storm Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-06 |  | 2020-11-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3937.48 | 3937.48 | 0 | 0 | 0 | 3937.48 | 0 | 0 | 0 | 0 | 3937.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508071 | S-WW-NI-050820-Laurieston WWTW-Install CSO | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-08-06 | 2021-06-21 | 2021-08-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42975 | 42975 | 141025 | 0 | 0 | 184000 | 0 | 0 | 0 | 0 | 184000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508073 | S-WW-NI-050820-Lilliesleaf WWTW-Stair Case | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-05 |  | 2021-03-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9185.37 | 9185.37 | -185.37 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 9000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508061 | S-WW-NI-050820-Philipshill WWTW-Replace & Refurbish Storm tank Mixers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-05 |  | 2020-01-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18137.58 | 18137.58 | 0 | 0 | 0 | 18137.58 | 0 | 0 | 0 | 0 | 18137.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508055 | S-WW-NI-050820-West Mains WWPS-Replace Control Panel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-05 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16856.06 | 16856.06 | 43.95 | 0 | 0 | 16900 | 0 | 0 | 0 | 0 | 16900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509108 | S-WW-NI-051020-Clarencefield WWTW-Doors & Fall Protection on Storm Pump Wet Well | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-05 |  | 2020-11-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257.83 | 2257.83 | 0 | 0 | 0 | 2257.83 | 0 | 0 | 0 | 0 | 2257.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509100 | S-WW-NI-051020-Clarencefield WWTW-Replace doors on Primary tank Wet well | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-07 |  | 2020-11-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257.86 | 2257.86 | 0 | 0 | 0 | 2257.86 | 0 | 0 | 0 | 0 | 2257.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509093 | S-WW-NI-051020-Hamilton WWTW-Replace Garage Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-07 |  | 2020-07-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1494.87 | 1494.87 | 0 | 0 | 0 | 1494.87 | 0 | 0 | 0 | 0 | 1494.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509095 | S-WW-NI-051020-Hamilton WWTW-Replace Motor on Shutter Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-07 |  | 2020-04-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1109.8 | 1109.8 | 0 | 0 | 0 | 1109.8 | 0 | 0 | 0 | 0 | 1109.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509097 | S-WW-NI-051020-Penicuik WWTW-investigate options to install sound proofing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-10-09 | 2021-04-16 | 2021-08-20 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7278.42 | 7278.42 | 12787.62 | 0 | 0 | 20066.04 | 0 | 0 | 0 | 0 | 20066.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509109 | S-WW-NI-051020-Troqueer WWTW-replace the local isolation on 3 PSTs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-07 |  | 2020-11-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2699.49 | 2699.49 | 0 | 0 | 0 | 2699.49 | 0 | 0 | 0 | 0 | 2699.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509653 | S-WW-NI-051120-Collin WWTW-Fall protection on wet wells | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-06 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6208.51 | 6208.51 | -108.51 | 0 | 0 | 6100 | 0 | 0 | 0 | 0 | 6100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509640 | S-WW-NI-051120-Kirkcudbright WWTW-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2167.63 | 2167.63 | 29432.37 | 0 | 0 | 31600 | 0 | 0 | 0 | 0 | 31600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509651 | S-WW-NI-051120-Port Rodie WWPS-Hydraulic & control survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-06 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.96 | 214.96 | 2785.04 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509637 | S-WW-NI-051120-Thornhill WWTW-Install Sludge tank Stand pipes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-03-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6028.35 | 6028.35 | -328.35 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 5700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504186 | S-WW-NI-051219-Greengairs WWTW-Replace Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-01-20 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 5117.47 | 0 | 5117.47 | 0 | 0 | 0 | 5117.47 | 0 | 0 | 0 | 0 | 5117.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504177 | S-WW-NI-051219-Greengairs WWTW-Wallhead Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-08-28 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 66102.05 | 729.15 | 66831.2 | 0 | 0 | 0 | 66831.2 | 0 | 0 | 0 | 0 | 66831.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504184 | S-WW-NI-051219-Hamilton WWTW-Install External Lighting- | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-01-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2878.48 | 0 | 2878.48 | 0 | 0 | 0 | 2878.48 | 0 | 0 | 0 | 0 | 2878.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504165 | S-WW-NI-051219-Stonehouse WWTW-Critical Spare Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-06 |  | 2020-06-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 4043.59 | 2813.38 | 6856.97 | 0 | 0 | 0 | 6856.97 | 0 | 0 | 0 | 0 | 6856.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510540 | S-WW-NI-060120-Annan WWTW-Washwater pipework alterations | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-06 |  | 2021-03-27 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170.25 | 1170.25 | 29.72 | 0 | 0 | 1199.97 | 0 | 0 | 0 | 0 | 1199.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510545 | S-WW-NI-060121-Coulter Rd SPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-07 |  | 2021-04-05 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3128.94 | 3128.94 | 71.06 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510549 | S-WW-NI-060121-Dalbeattie WWTW-refurb 4No bridge brush mechanisms | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-07 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740.91 | 740.91 | 8159.08 | 0 | 0 | 8899.99 | 0 | 0 | 0 | 0 | 8899.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510555 | S-WW-NI-060121-Dalscone WWTW-Replace the outfall valve and rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-07 |  | 2021-03-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5383.46 | 5383.46 | 35.24 | 0 | 0 | 5418.7 | 0 | 0 | 0 | 0 | 5418.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510541 | S-WW-NI-060121-FOULDEN BASTLE ROAD SEP-Outfall Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-06 |  | 2021-02-19 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5492.23 | 5492.23 | -92.24 | 0 | 0 | 5399.99 | 0 | 0 | 0 | 0 | 5399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510543 | S-WW-NI-060121-Langholm WWTW-Refurbish Filter drives motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-07 |  | 2021-03-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2803.18 | 2803.18 | -3.2 | 0 | 0 | 2799.98 | 0 | 0 | 0 | 0 | 2799.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510542 | S-WW-NI-060121-Town Yetholm WWTW-Install handrails to PST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-06 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618.02 | 618.02 | 6181.96 | 0 | 0 | 6799.98 | 0 | 0 | 0 | 0 | 6799.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510548 | S-WW-NI-060121-Troqueer WWTW-RAS Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-07 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536.45 | 536.45 | 7663.56 | 0 | 0 | 8200.01 | 0 | 0 | 0 | 0 | 8200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505051 | S-WW-NI-060220-Blackridge WWTW-Parts for Storm Pump Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-02-19 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1565.01 | 0 | 1565.01 | 0 | 0 | 0 | 1565.01 | 0 | 0 | 0 | 0 | 1565.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505063 | S-WW-NI-060220-Dumfries Loganbarns WWPS-Removal and resealing of exisitng multi-pane metal gable windows | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-03-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1491.46 | 0 | 1491.46 | 0 | 0 | 0 | 1491.46 | 0 | 0 | 0 | 0 | 1491.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505058 | S-WW-NI-060220-Eyemouth WWTW-SBR2 Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-09-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 143.27 | 1543.27 | 0 | 0 | 0 | 1543.27 | 0 | 0 | 0 | 0 | 1543.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505050 | S-WW-NI-060220-Linhouse Burn Pipe Bridge-H&S Bollard | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-04-03 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1323.7 | 0 | 1323.7 | 0 | 0 | 0 | 1323.7 | 0 | 0 | 0 | 0 | 1323.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505060 | S-WW-NI-060220-Troqueer WWTW-Supply & Install Keypads for Access Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-05-22 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1284.64 | 428.22 | 1712.86 | 0 | 0 | 0 | 1712.86 | 0 | 0 | 0 | 0 | 1712.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505569 | S-WW-NI-060320-Bothwellbank WWTW-Building Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-06-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 663.44 | 7472.56 | 8136 | 1864.1 | 0 | 0 | 10000.1 | 0 | 0 | 0 | 0 | 10000.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505591 | S-WW-NI-060320-Eccles WWTW-Repair Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 293.82 | 2627.92 | 2921.74 | 0 | 0 | 0 | 2921.74 | 0 | 0 | 0 | 0 | 2921.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505577 | S-WW-NI-060320-Glentrool WWTW-Refurb Centre Column | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3382.64 | 18.47 | 3401.11 | 0 | 0 | 0 | 3401.11 | 0 | 0 | 0 | 0 | 3401.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505585 | S-WW-NI-060320-Kirkinner WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-04-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 192.9 | 3198.3 | 3391.2 | 0 | 0 | 0 | 3391.2 | 0 | 0 | 0 | 0 | 3391.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505586 | S-WW-NI-060320-Lauder WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3360.63 | 55.88 | 3416.51 | 0 | 0 | 0 | 3416.51 | 0 | 0 | 0 | 0 | 3416.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505588 | S-WW-NI-060320-Reston WWTW-Refurb Blower No2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 2860.88 | 3057.14 | 0 | 0 | 0 | 3057.14 | 0 | 0 | 0 | 0 | 3057.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505571 | S-WW-NI-060320-Rose Lane WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-05-18 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 799.96 | 7461.58 | 8261.54 | 0 | 0 | 0 | 8261.54 | 0 | 0 | 0 | 0 | 8261.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512234 | S-WW-NI-060421- BONCHESTER BRIDGE WWTW NT587124 - Refurbish Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-06 |  | 2021-07-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4900 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 4900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512235 | S-WW-NI-060421- DENHOLM WWTW 1972 NT571189 - REFURBISH INLET SCREEN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-06 |  | 2021-07-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600.03 | 0 | 0 | 3600.03 | 0 | 0 | 0 | 0 | 3600.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512222 | S-WW-NI-060421- EARLSTON WWTW 1959 NT573382 - REPLACE 2 HUMUS RETURN PUMPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-06 |  | 2021-07-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 11200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512230 | S-WW-NI-060421- MELROSE WWTW 1970 NT551346 - REFURBISH INLET SCREENS X2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-06 |  | 2021-07-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17399.97 | 0 | 0 | 17399.97 | 0 | 0 | 0 | 0 | 17399.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512188 | S-WW-NI-060421-Daldowie_STW_Bridge Scraper Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500.03 | 0 | 0 | 1500.03 | 0 | 0 | 0 | 0 | 1500.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512189 | S-WW-NI-060421-Lesmahagow_STW_Screening Motor & Critical Spare | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-06 |  | 2021-07-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2499.98 | 0 | 0 | 2499.98 | 0 | 0 | 0 | 0 | 2499.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506508 | S-WW-NI-060520-92 Wood Avenue Annan-Repair 150mm dia sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-11 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44756.9 | 44756.9 | -2756.89 | 0 | 0 | 42000.01 | 0 | 0 | 0 | 0 | 42000.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506493 | S-WW-NI-060520-Bathgate WWTW-Installation of sludge tanker discharge point | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-29 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5842.74 | 5842.74 | 0 | 0 | 0 | 5842.74 | 0 | 0 | 0 | 0 | 5842.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506494 | S-WW-NI-060520-Bathgate WWTW-Replace Centre Column Bearing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-06 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4095.15 | 4095.15 | 0 | 0 | 0 | 4095.15 | 0 | 0 | 0 | 0 | 4095.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506500 | S-WW-NI-060520-Eaglesfield WWTW-Replace lifting beam and flooring | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5449.62 | 5449.62 | 0 | 0 | 0 | 5449.62 | 0 | 0 | 0 | 0 | 5449.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506502 | S-WW-NI-060520-Eastriggs WWTW-Spare rotork for SBR decant valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-09-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3362.28 | 3362.28 | 0 | 0 | 0 | 3362.28 | 0 | 0 | 0 | 0 | 3362.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506505 | S-WW-NI-060520-Gordon WWTW- | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-06-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8206.43 | 8206.43 | 0 | 0 | 0 | 8206.43 | 0 | 0 | 0 | 0 | 8206.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506498 | S-WW-NI-060520-Hind Irving WWPS-Improve access to the pumping station | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-08-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4593.79 | 4593.79 | 0 | 0 | 0 | 4593.79 | 0 | 0 | 0 | 0 | 4593.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506519 | S-WW-NI-060520-MARINE PARADE WWPS-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-08-13 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9542.01 | 9542.01 | 0 | 0 | 0 | 9542.01 | 0 | 0 | 0 | 0 | 9542.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506514 | S-WW-NI-060520-Shotts WWTW-Replace an anoxic tank mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-06-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3391.26 | 3391.26 | 0 | 0 | 0 | 3391.26 | 0 | 0 | 0 | 0 | 3391.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507531 | S-WW-NI-060720-Galashiels WWTW-Repairs to centrifuge 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-06 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8458.61 | 8458.61 | -58.61 | 0 | 0 | 8400 | 0 | 0 | 0 | 0 | 8400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507530 | S-WW-NI-060720-Gatehouse WWTW-Install Handrails around PST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-09-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1757.26 | 1757.26 | 0 | 0 | 0 | 1757.26 | 0 | 0 | 0 | 0 | 1757.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507526 | S-WW-NI-060720-KIRKCUD MERSECROFT WWPS-Screen Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-09-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636.62 | 1636.62 | 0 | 0 | 0 | 1636.62 | 0 | 0 | 0 | 0 | 1636.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507536 | S-WW-NI-060720-Torthorwald WWTW-Replacement diaphragm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-08 |  | 2020-08-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1295.05 | 1295.05 | 0 | 0 | 0 | 1295.05 | 0 | 0 | 0 | 0 | 1295.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507534 | S-WW-NI-060720-Troqueer STC-Odour Control | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-06 |  | 2020-07-22 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2726.27 | 2726.27 | 0 | 0 | 0 | 2726.27 | 0 | 0 | 0 | 0 | 2726.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508096 | S-WW-NI-060820-Clarencefield WWTW-Replacement Doors on MCC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-06 |  | 2020-10-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212.22 | 3212.22 | 0 | 0 | 0 | 3212.22 | 0 | 0 | 0 | 0 | 3212.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508093 | S-WW-NI-060820-Gordon WWTW-Replacement Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-06 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283.2 | 283.2 | 3644.86 | 0 | 0 | 3928.06 | 0 | 0 | 0 | 0 | 3928.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508097 | S-WW-NI-060820-Kippford Merse Way WWPS-Replacement Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-06 |  | 2020-11-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6381.21 | 6381.21 | 0 | 0 | 0 | 6381.21 | 0 | 0 | 0 | 0 | 6381.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508102 | S-WW-NI-060820-Lesmahagow WWTW-Replace RAS Screw pump bearing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-06 |  | 2020-09-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25161.76 | 25161.76 | 0 | 0 | 0 | 25161.76 | 0 | 0 | 0 | 0 | 25161.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508095 | S-WW-NI-060820-Lincluden WWTW-H&S Platform | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-06 |  | 2020-10-20 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17383.03 | 17383.03 | 16.98 | 0 | 0 | 17400.01 | 0 | 0 | 0 | 0 | 17400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508107 | S-WW-NI-060820-Peebles WWTW-Reinstate Footpaths | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-06 |  | 2020-09-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2895.75 | 2895.75 | 0 | 0 | 0 | 2895.75 | 0 | 0 | 0 | 0 | 2895.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508099 | S-WW-NI-060820-Troqueer WWTW-Refurbish the washwater system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-06 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15622.72 | 15622.72 | 0 | 0 | 0 | 15622.72 | 0 | 0 | 0 | 0 | 15622.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508101 | S-WW-NI-060820-Troqueer WWTW-Replace FST 3 rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-06 |  | 2020-10-20 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7129.54 | 7129.54 | 0 | 0 | 0 | 7129.54 | 0 | 0 | 0 | 0 | 7129.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509121 | S-WW-NI-061020-Bilston WWPS-Replace discharge pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-07 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149.58 | 1149.58 | 1350.42 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509130 | S-WW-NI-061020-Denholm WWTW-Handrails & Kickplates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-07 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339.52 | 339.52 | 2060.48 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509134 | S-WW-NI-061020-Kirkliston WWPS-Replace main gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-07 |  | 2021-02-10 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2208.94 | 2208.94 | -108.94 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509123 | S-WW-NI-061020-Shotts WWTW-To replace the cover section of the screenings compactor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-07 |  | 2020-11-25 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168.03 | 1168.03 | 0 | 0 | 0 | 1168.03 | 0 | 0 | 0 | 0 | 1168.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509125 | S-WW-NI-061020-Swinstie WWTW-To repalce the chains of inlet screen no. 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-07 |  | 2021-02-10 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1891.6 | 1891.6 | -91.6 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509664 | S-WW-NI-061120-10 St Ninians-Replace the failed telemetry equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-09 |  | 2021-03-04 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273.97 | 1273.97 | 26.03 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509659 | S-WW-NI-061120-14 Clydebrae Drive Bothwell-Sewer Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 |  | 2021-05-10 | 2021-07-30 | 2022-03-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4788.36 | 4788.36 | -4788.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWI | 100%
509660 | S-WW-NI-061120-Marjoriebanks WWPS-Repair to road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-12 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4144.77 | 4144.77 | -844.77 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509665 | S-WW-NI-061120-Philipshill WWTW-Replace scrapers and arms | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-09 |  | 2020-11-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4292.43 | 4292.43 | 0 | 0 | 0 | 4292.43 | 0 | 0 | 0 | 0 | 4292.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509661 | S-WW-NI-061120-Troqueer STC-Replace faulty smoke beams sensors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-09 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 3080 | 220 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504229 | S-WW-NI-061219-Capability Studies | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-07-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 24902.4 | 107581.16 | 132483.56 | 367525.8 | 0 | 0 | 500009.36 | 0 | 0 | 0 | 0 | 500009.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504204 | S-WW-NI-061219-Coldstream WWTW-Replace Aerator No1 Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-06 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2610.66 | 0 | 2610.66 | -310.66 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504214 | S-WW-NI-061219-Coldstream WWTW-Replace Aerator No2 Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2291.04 | -0.01 | 2291.03 | -291.03 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504198 | S-WW-NI-061219-Hamilton Grammar School CSO-Level Sensor Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2019-12-06 |  | 2020-07-21 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 120.32 | 1720.32 | 0 | 0 | 0 | 1720.32 | 0 | 0 | 0 | 0 | 1720.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504552 | S-WW-NI-070120-Daldowie WWTW-Replace Pulley on NTF | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-02-08 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1568.34 | 0 | 1568.34 | 0 | 0 | 0 | 1568.34 | 0 | 0 | 0 | 0 | 1568.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504547 | S-WW-NI-070120-Dumfries Rasgill WWPS-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-03-05 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2708.16 | 0 | 2708.16 | 0 | 0 | 0 | 2708.16 | 0 | 0 | 0 | 0 | 2708.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504541 | S-WW-NI-070120-Kirkconnel WWTW-Replace 3 Solenoid Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-01-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1740.78 | 0 | 1740.78 | 0 | 0 | 0 | 1740.78 | 0 | 0 | 0 | 0 | 1740.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504536 | S-WW-NI-070120-Loch Ryan WWTW-Replacement Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-07 |  | 2020-02-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2334.68 | 0 | 2334.68 | 0 | 0 | 0 | 2334.68 | 0 | 0 | 0 | 0 | 2334.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510557 | S-WW-NI-070121-Dumfries College St SPS-Replacement Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-07 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614.04 | 614.04 | 8504.68 | 0 | 0 | 9118.72 | 0 | 0 | 0 | 0 | 9118.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510561 | S-WW-NI-070121-Gullane WWTW-Replace basket on inlet screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-11 |  | 2021-03-13 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2966.32 | 2966.32 | 52.36 | 0 | 0 | 3018.68 | 0 | 0 | 0 | 0 | 3018.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510560 | S-WW-NI-070121-Port Rodie WWPS-Refurbish Watertight Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-11 |  | 2021-03-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4606.75 | 4606.75 | -206.76 | 0 | 0 | 4399.99 | 0 | 0 | 0 | 0 | 4399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510565 | S-WW-NI-070121-Rosewell WWTW-Replace humus tank actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169.18 | 169.18 | 2149.52 | 0 | 0 | 2318.7 | 0 | 0 | 0 | 0 | 2318.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510568 | S-WW-NI-070121-Strathaven WWTW-Replace pump drive | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-11 |  | 2021-03-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3275.4 | 3275.4 | 43.32 | 0 | 0 | 3318.72 | 0 | 0 | 0 | 0 | 3318.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510559 | S-WW-NI-070121-Torthowald WWTW-Replace Pressure Washer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-07 |  | 2021-03-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2946.26 | 2946.26 | 53.72 | 0 | 0 | 2999.98 | 0 | 0 | 0 | 0 | 2999.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505067 | S-WW-NI-070220-Fauldhouse WWTW-Replace manual desludge valves with actuators | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 21100 | -10201.16 | 10898.84 | 10201.16 | 0 | 0 | 21100 | 0 | 0 | 0 | 0 | 21100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505072 | S-WW-NI-070220-Gifford WWTW-Replacement Railings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-06-15 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 10100 | -57.39 | 10042.62 | 0 | 0 | 0 | 10042.62 | 0 | 0 | 0 | 0 | 10042.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505076 | S-WW-NI-070220-Hamilton WWTW-Refurbish ASP Feed Pump No2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 17300 | -48.6 | 17251.4 | 48.6 | 0 | 0 | 17300 | 0 | 0 | 0 | 0 | 17300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505084 | S-WW-NI-070220-Hutton WWTW-Supply & Fit Sprinkler Arms | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-03-09 |  | 2020-08-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 213.62 | 6813.62 | -213.62 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 6600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505073 | S-WW-NI-070220-Priory Bridge WWPS-Replace Foul Pump No2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-05-29 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | -6.62 | 9893.38 | 0 | 0 | 0 | 9893.38 | 0 | 0 | 0 | 0 | 9893.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505082 | S-WW-NI-070220-Reston WWTW-Refurbush Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-02-25 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3070.91 | 0 | 3070.91 | 0 | 0 | 0 | 3070.91 | 0 | 0 | 0 | 0 | 3070.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505080 | S-WW-NI-070220-Troqueer STC-Supply & Fit 2no Valves onto decant pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-02-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3077.12 | 36.94 | 3114.06 | 0 | 0 | 0 | 3114.06 | 0 | 0 | 0 | 0 | 3114.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505077 | S-WW-NI-070220-Troqueer WWTW-Replacement Lighting at STC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-03-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 5942.88 | -0.01 | 5942.87 | 0 | 0 | 0 | 5942.87 | 0 | 0 | 0 | 0 | 5942.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506113 | S-WW-NI-07042020-Lincluden WWTW-refurbish the grit classifier No 1 Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-07 |  | 2020-04-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1227.9 | 1227.9 | 0 | 0 | 0 | 1227.9 | 0 | 0 | 0 | 0 | 1227.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506106 | S-WW-NI-07042020-Lincluden WWTW-refurbishment of both grit vortex motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-07 |  | 2020-04-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1477.83 | 1477.83 | 0 | 0 | 0 | 1477.83 | 0 | 0 | 0 | 0 | 1477.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506109 | S-WW-NI-07042020-Lincluden WWTW-replacement PST desludge valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-07 |  | 2020-04-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1828.48 | 1828.48 | 0 | 0 | 0 | 1828.48 | 0 | 0 | 0 | 0 | 1828.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506117 | S-WW-NI-07042020-Ormiston WWTW-Replace PST1 motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-07 |  | 2020-06-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2268.94 | 2268.94 | 0 | 0 | 0 | 2268.94 | 0 | 0 | 0 | 0 | 2268.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506121 | S-WW-NI-07042020-Penicuik WWTW-Replace passing valve at outlet of SBR C | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-05-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1191.97 | 1191.97 | 0 | 0 | 0 | 1191.97 | 0 | 0 | 0 | 0 | 1191.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506107 | S-WW-NI-07042020-Stonehouse WWTW- VSD and extension kit for the NTF feed pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-07 |  | 2020-05-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1712.18 | 1712.18 | 0 | 0 | 0 | 1712.18 | 0 | 0 | 0 | 0 | 1712.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512264 | S-WW-NI-070421- BATHGATE WWTW 1962 NS961703 - INSTALL LIFTING BEAM FOR HUMUS PUMP - 1.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | [5 empty] | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1099.98 | 0 | 0 | 1099.98 | 0 | 0 | 0 | 0 | 1099.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506536 | S-WW-NI-07052020-Dunnswood WWTW-Replace Lauder Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-11 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.52 | 103.52 | 1196.48 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506538 | S-WW-NI-07052020-Stonehouse WWTW-mods to the garage door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-18 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1863.36 | 1863.36 | 0 | 0 | 0 | 1863.36 | 0 | 0 | 0 | 0 | 1863.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506534 | S-WW-NI-070520-Shotts WWTW-Chemical Dosing Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-05-18 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2284.7 | 2284.7 | 0 | 0 | 0 | 2284.7 | 0 | 0 | 0 | 0 | 2284.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506543 | S-WW-NI-070520-Sorbie WWTW-Refurbishment of percolatiing filter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-05-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1351.93 | 1351.93 | 0 | 0 | 0 | 1351.93 | 0 | 0 | 0 | 0 | 1351.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506548 | S-WW-NI-070520-Troqueer WWTW-Replacement actuators on FST 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-10-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7124.51 | 7124.51 | 0 | 0 | 0 | 7124.51 | 0 | 0 | 0 | 0 | 7124.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508597 | S-WW-NI-070920-Biggar WWTW-Provide alternative lighting fixed to kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-09-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053.65 | 2053.65 | 0 | 0 | 0 | 2053.65 | 0 | 0 | 0 | 0 | 2053.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508595 | S-WW-NI-070920-Peebles WWTW-Ferric Dosing Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-09-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1859.75 | 1859.75 | 0 | 0 | 0 | 1859.75 | 0 | 0 | 0 | 0 | 1859.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509147 | S-WW-NI-071020-Bothwellbank WWTW-Replace Sludge tank mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-09-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7696.94 | 7696.94 | 0 | 0 | 0 | 7696.94 | 0 | 0 | 0 | 0 | 7696.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509143 | S-WW-NI-071020-Lesmahagow WWTW-Replace Inlet Screen No.1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20991.2 | 20991.2 | -391.19 | 0 | 0 | 20600.01 | 0 | 0 | 0 | 0 | 20600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509139 | S-WW-NI-071020-McDonald Road WWPS-Scope up repairs and quote for repair of the storm screw pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-10-09 | 2020-12-07 | 2021-08-13 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509140 | S-WW-NI-071020-Netherburn WWPS-Replace 2 pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-07 |  | 2020-11-07 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5196.06 | 5196.06 | 0 | 0 | 0 | 5196.06 | 0 | 0 | 0 | 0 | 5196.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509149 | S-WW-NI-071020-Whitehill WWPS-Replace Floor gratings indentified as a hazard | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-07 |  | 2021-03-13 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8547.8 | 8547.8 | -147.8 | 0 | 0 | 8400 | 0 | 0 | 0 | 0 | 8400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510165 | S-WW-NI-071220-Castle Douglas WWTW-Refurb self closing gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3528.43 | 3528.43 | 71.57 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510163 | S-WW-NI-071220-Coalburn WWTW-Refurbishment work on storm screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-04 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16110.64 | 16110.64 | 89.36 | 0 | 0 | 16200 | 0 | 0 | 0 | 0 | 16200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510181 | S-WW-NI-071220-Hamilton WWTW-Replace Inlet Screen 1 motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-02-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2284.87 | 2284.87 | 15.13 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510177 | S-WW-NI-071220-Kirkcudbright WWTW-Replace pump coupling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-14 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009.69 | 2009.69 | 90.31 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510162 | S-WW-NI-071220-Levenhall WWPS-Critical spare power supply unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-02-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331.59 | 1331.59 | 68.41 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510184 | S-WW-NI-071220-Sandhead WWTW-Replace Inlet number 1 pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-02-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1660.69 | 1660.69 | 39.31 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510167 | S-WW-NI-071220-Troqueer WWTW-Replace Drainage Pumps and Guide rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500.14 | 2500.14 | -0.14 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504571 | S-WW-NI-080120-Eyemoth WWTW-Inlet Screen Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-02-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 11034.64 | 0 | 11034.64 | 0 | 0 | 0 | 11034.64 | 0 | 0 | 0 | 0 | 11034.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504561 | S-WW-NI-080120-Hagmill WWPS-2 Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 7562.86 | 6213.87 | 13776.73 | 23.27 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 13800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510580 | S-WW-NI-080120-Mauldslie WWTW-Filter Bed Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1731.46 | 1731.46 | 68.54 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510595 | S-WW-NI-080121-Blackridge WWTW-Investigate blockage in PST feed pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2021-01-28 | 2021-02-04 | 2021-03-25 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10700 | 10700 | 0 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510593 | S-WW-NI-080121-Dunnswood WWTW-Replacement of exisiting ASP blowers payment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44045.12 | 44045.12 | 28.04 | 0 | 0 | 44073.16 | 0 | 0 | 0 | 0 | 44073.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510582 | S-WW-NI-080121-Earlston WWTW-Refurbish Primary desludge pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1991.12 | 1991.12 | 27.56 | 0 | 0 | 2018.68 | 0 | 0 | 0 | 0 | 2018.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510598 | S-WW-NI-080121-Gordon Braeheads WWPS-Refurb Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2245.44 | 2245.44 | -26.72 | 0 | 0 | 2218.72 | 0 | 0 | 0 | 0 | 2218.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511109 | S-WW-NI-080221-East Linton WWTW-Purchase a portable MLSS monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-08 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1495.35 | 0 | 0 | 1600.02 | 0 | 0 | 0 | 0 | 1600.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511094 | S-WW-NI-080221-Eastfield WWPS-Replacement fan kit for pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-08 |  | 2021-05-08 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1086.5 | 1086.5 | 113.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511105 | S-WW-NI-080221-Newton Stewart WWTW-Replace both baskets for screen 1 and 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5034 | 5034 | -2533.6 | 0 | 0 | 2500.4 | 0 | 0 | 0 | 0 | 2500.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511113 | S-WW-NI-080221-Slamannan WWTW-Refurbish air release valve pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-08 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2713.72 | 2713.72 | 1.7 | 0 | 0 | 2715.42 | 0 | 0 | 0 | 0 | 2715.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511090 | S-WW-NI-080221-Whitecrosss WWTW-Gratings and handrailing repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-08 |  | 2021-05-08 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332.86 | 332.86 | 20967.15 | 0 | 0 | 21300.01 | 0 | 0 | 0 | 0 | 21300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511644 | S-WW-NI-080321-New Abbey WWTW-Repair on burst pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1593.49 | 1593.49 | -193.49 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511645 | S-WW-NI-080321-Rockcliffe WWTW-Replace Storm Return Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.51 | 1307.51 | 15592.49 | 0 | 0 | 16900 | 0 | 0 | 0 | 0 | 16900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506136 | S-WW-NI-08042020-Gatehouse WWTW-H&S Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-07-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4400.86 | 4400.86 | 0 | 0 | 0 | 4400.86 | 0 | 0 | 0 | 0 | 4400.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506137 | S-WW-NI-08042020-Loch Ryan WWTW-Washpactor Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-07-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10970.41 | 10970.41 | 0 | 0 | 0 | 10970.41 | 0 | 0 | 0 | 0 | 10970.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506134 | S-WW-NI-08042020-Lochmaben WWTW-Refurb Geared Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-05-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4074.26 | 4074.26 | 0 | 0 | 0 | 4074.26 | 0 | 0 | 0 | 0 | 4074.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506129 | S-WW-NI-08042020-Newton Stewart WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-04-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1756.01 | 1756.01 | 0 | 0 | 0 | 1756.01 | 0 | 0 | 0 | 0 | 1756.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506147 | S-WW-NI-08042020-Springburn House EDI-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-05-20 |  | 2021-03-06 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33417.76 | 33417.76 | -4517.76 | 0 | 0 | 28900 | 0 | 0 | 0 | 0 | 28900 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507070 | S-WW-NI-080620-Back lowther WWPS-Wet well cover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-09-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6186.94 | 6186.94 | 0 | 0 | 0 | 6186.94 | 0 | 0 | 0 | 0 | 6186.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507068 | S-WW-NI-080620-Langholm WWTW-Resurface the area around the Filter bed | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-29 |  | 2021-03-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8626.71 | 8626.71 | -126.71 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 8500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507078 | S-WW-NI-080620-Lincluden WWTW-Concrete and masonry repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-07-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416.36 | 2416.36 | 0 | 0 | 0 | 2416.36 | 0 | 0 | 0 | 0 | 2416.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507072 | S-WW-NI-080620-Stran Larg Rd WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-06-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2121.36 | 2121.36 | 0 | 0 | 0 | 2121.36 | 0 | 0 | 0 | 0 | 2121.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507085 | S-WW-NI-080620-Swinstie WWTW-Replace rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-08-09 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1581.02 | 1581.02 | 0 | 0 | 0 | 1581.02 | 0 | 0 | 0 | 0 | 1581.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507080 | S-WW-NI-080620-Troqueer STC-Installation of Low Flow Pressure sensor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-06-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1443.78 | 1443.78 | 0 | 0 | 0 | 1443.78 | 0 | 0 | 0 | 0 | 1443.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507571 | S-WW-NI-080720-Galashiels STC-Gearbox Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-10 |  | 2020-07-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1477.55 | 1477.55 | 0 | 0 | 0 | 1477.55 | 0 | 0 | 0 | 0 | 1477.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507587 | S-WW-NI-080720-Lincluden WWTW-Refurb Compactor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-13 |  | 2020-08-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3668.36 | 3668.36 | -268.36 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507579 | S-WW-NI-080720-Salsburgh WWTW-Recast & Secure Gratings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-08 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590.43 | 590.43 | 7409.57 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507577 | S-WW-NI-080720-Troqueer WWTW-Install Access Hatches | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-13 |  | 2020-10-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11112.91 | 11112.91 | -112.91 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 11000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508639 | S-WW-NI-080920-Eaglesham WWTW-Survey condition of NTF tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-09 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.66 | 158.66 | 1241.34 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508631 | S-WW-NI-080920-Loch Ryan WWTW-Refurb FE Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-08 |  | 2020-09-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1833.98 | 1833.98 | 0 | 0 | 0 | 1833.98 | 0 | 0 | 0 | 0 | 1833.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508636 | S-WW-NI-080920-Troqueer STC-Refurb Poly transfer Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-08 |  | 2020-11-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1893.12 | 1893.12 | 0 | 0 | 0 | 1893.12 | 0 | 0 | 0 | 0 | 1893.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509162 | S-WW-NI-081020-Dalbeattie WWTW-Replace Jet Nozzles and Dash plates on Filter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-09 |  | 2021-02-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2670.56 | 2670.56 | 271.08 | 0 | 0 | 2941.64 | 0 | 0 | 0 | 0 | 2941.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509157 | S-WW-NI-081020-Duns WWTW-Health & Safety to sludge building | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-03 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688.26 | 4688.26 | 0 | 0 | 0 | 4688.26 | 0 | 0 | 0 | 0 | 4688.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509154 | S-WW-NI-081020-Galashiels STC-Replace rotor and stator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-08 |  | 2020-10-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7165.8 | 7165.8 | 0 | 0 | 0 | 7165.8 | 0 | 0 | 0 | 0 | 7165.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509152 | S-WW-NI-081020-Lockerbie WWTW-Refurbish filter no 7 centre column | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-08 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3938.68 | 3938.68 | -97.04 | 0 | 0 | 3841.64 | 0 | 0 | 0 | 0 | 3841.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509153 | S-WW-NI-081020-Moffat WWTW-Replace FST 1 motor & gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-08 |  | 2020-01-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4081.02 | 4081.02 | 0 | 0 | 0 | 4081.02 | 0 | 0 | 0 | 0 | 4081.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509164 | S-WW-NI-081020-Troqueer STC-Refurb Klampress Roller1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5672 | 5672 | 0 | 0 | 0 | 5672 | 0 | 0 | 0 | 0 | 5672 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510194 | S-WW-NI-081220-Bathgate WWTW-Carry out repairs to Huber R02 Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-02-28 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16308.38 | 16308.38 | 91.62 | 0 | 0 | 16400 | 0 | 0 | 0 | 0 | 16400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504587 | S-WW-NI-090120-Bothwellbank WWTW-Replace Combi Compaction | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-01-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1210.63 | 0 | 1210.63 | 0 | 0 | 0 | 1210.63 | 0 | 0 | 0 | 0 | 1210.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504575 | S-WW-NI-090120-Carbarns WWTW-Replace Sludge Main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-08-31 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 19400.38 | 55391.27 | 74791.65 | 0 | 0 | 0 | 74791.65 | 0 | 0 | 0 | 0 | 74791.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504578 | S-WW-NI-090120-Crossford WWTW-Refurb Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-02-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 6396.96 | 0 | 6396.96 | 0 | 0 | 0 | 6396.96 | 0 | 0 | 0 | 0 | 6396.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504582 | S-WW-NI-090120-Lochmaben WWTW-PST Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-02-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 4519.94 | 0 | 4519.94 | 0 | 0 | 0 | 4519.94 | 0 | 0 | 0 | 0 | 4519.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504580 | S-WW-NI-090120-Troqueer STC-2No. Replacement Motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-02-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 10631.65 | 0 | 10631.65 | 0 | 0 | 0 | 10631.65 | 0 | 0 | 0 | 0 | 10631.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505615 | S-WW-NI-090320-Granton WWPS-Installation and commissioning of storm rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-07-16 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 300.93 | 4214.47 | 4515.4 | 0 | 0 | 0 | 4515.4 | 0 | 0 | 0 | 0 | 4515.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505592 | S-WW-NI-090320-Motehill WWPS-Replacement Impellors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-08-05 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1125.23 | 16025.24 | 17150.47 | 0 | 0 | 0 | 17150.47 | 0 | 0 | 0 | 0 | 17150.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505600 | S-WW-NI-090320-North Middleton WWTW-Screen Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-10-14 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 719.63 | 10327.44 | 11047.07 | 0 | 0 | 0 | 11047.07 | 0 | 0 | 0 | 0 | 11047.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505593 | S-WW-NI-090320-Ormiston WWTW-Scraper Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-07-13 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 451.4 | 6431.52 | 6882.92 | 0 | 0 | 0 | 6882.92 | 0 | 0 | 0 | 0 | 6882.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511699 | S-WW-NI-090321-Ashgill WWTW-Carry out refurbishments of the blowers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-06-09 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 1371.42 | 0 | 0 | 1496.42 | 0 | 0 | 0 | 0 | 1496.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511700 | S-WW-NI-090321-Dunnswood WWTW-Replace damaged chamber cover at grit skip area | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-09 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1114.26 | 0 | 0 | 1199.31 | 0 | 0 | 0 | 0 | 1199.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506159 | S-WW-NI-09042020-Abercromby Rd WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2533.33 | 2533.33 | 0 | 0 | 0 | 2533.33 | 0 | 0 | 0 | 0 | 2533.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506164 | S-WW-NI-09042020-Earlston WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-05-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1986.92 | 1986.92 | 0 | 0 | 0 | 1986.92 | 0 | 0 | 0 | 0 | 1986.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506157 | S-WW-NI-09042020-Port Edgar WWTW-Repair Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-05-18 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6828.92 | 6828.92 | 0 | 0 | 0 | 6828.92 | 0 | 0 | 0 | 0 | 6828.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506156 | S-WW-NI-09042020-Roslin WWTW-Fit new pipe work to syphon for biofilters 1&2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-04-22 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1195.55 | 1195.55 | 0 | 0 | 0 | 1195.55 | 0 | 0 | 0 | 0 | 1195.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506181 | S-WW-NI-09042020-Troqueer Storm WWPS-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-08-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31853.29 | 31853.29 | 0 | 0 | 0 | 31853.29 | 0 | 0 | 0 | 0 | 31853.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507097 | S-WW-NI-090620-Dalscone WWTW-To supply and fit new Diaphragm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-06-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517.18 | 1517.18 | 0 | 0 | 0 | 1517.18 | 0 | 0 | 0 | 0 | 1517.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507091 | S-WW-NI-090620-Eastfield WWPS-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-07-27 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7673.98 | 7673.98 | 0 | 0 | 0 | 7673.98 | 0 | 0 | 0 | 0 | 7673.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507109 | S-WW-NI-090620-WELL SCHOOL SEP-Construct a footpath & repair access road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-11 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1949.54 | 1949.54 | 50.46 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507607 | S-WW-NI-090720- Back of Moss Farm Longridge-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-07-10 |  | 2021-07-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3277 | 3277 | 6722.83 | 0 | 0 | 9999.83 | 0 | 0 | 0 | 0 | 9999.83 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507596 | S-WW-NI-090720-Allers WWTW-Replace Concrete Steps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-07-09 |  | 2021-03-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12209.24 | 12209.24 | 0 | 0 | 0 | 12209.24 | 0 | 0 | 0 | 0 | 12209.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507610 | S-WW-NI-090720-Haddington WWTW-H&S Upgrades | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-09 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718.7 | 718.7 | 9981.3 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507597 | S-WW-NI-090720-Shotts WWTW-ASP Weir Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-07-09 |  | 2021-06-29 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3522 | 3522 | 7477.6 | 0 | 0 | 10999.6 | 0 | 0 | 0 | 0 | 10999.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507600 | S-WW-NI-090720-Shotts WWTW-Reinstate Slabs and renew steps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-07-09 |  | 2020-09-10 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12169.29 | 12169.29 | 0 | 0 | 0 | 12169.29 | 0 | 0 | 0 | 0 | 12169.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507595 | S-WW-NI-090720-Troqueer STC-Refurb Strainpress | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-09 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8466.88 | 8466.88 | 733.12 | 0 | 0 | 9200 | 0 | 0 | 0 | 0 | 9200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507593 | S-WW-NI-090720-Troqueer STC-Replace Top Link Belts | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-09 |  | 2020-10-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16643.48 | 16643.48 | 0 | 0 | 0 | 16643.48 | 0 | 0 | 0 | 0 | 16643.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507605 | S-WW-NI-090720-Twynholm WWTW-Health and Safety Work | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-09 |  | 2020-09-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3132.16 | 3132.16 | 0 | 0 | 0 | 3132.16 | 0 | 0 | 0 | 0 | 3132.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508678 | S-WW-NI-090920-Armadale WWTW-Replace Sand Filter Compressor No. 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-09 |  | 2021-02-26 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5137.34 | 5137.34 | -37.34 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 5100 | 90601.29 | [5 empty] | N | CM_WWI | 100%
508673 | S-WW-NI-090920-Bothwellbank WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-09 |  | 2020-10-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4204.15 | 4204.15 | 0 | 0 | 0 | 4204.15 | 0 | 0 | 0 | 0 | 4204.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508680 | S-WW-NI-090920-Dalmeny WWTW-Refurbish centre column bearing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-09 |  | 2020-10-16 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5538.52 | 5538.52 | 0 | 0 | 0 | 5538.52 | 0 | 0 | 0 | 0 | 5538.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508668 | S-WW-NI-090920-Moffat WWTW-Replacement Motor and gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-09 |  | 2020-09-19 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11314.09 | 11314.09 | 0 | 0 | 0 | 11314.09 | 0 | 0 | 0 | 0 | 11314.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508666 | S-WW-NI-090920-Newton Stewart WWTW-Refurb of the floating aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-09 |  | 2020-09-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16586.29 | 16586.29 | 0 | 0 | 0 | 16586.29 | 0 | 0 | 0 | 0 | 16586.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508663 | S-WW-NI-090920-Port Rodie WWPS-Refurb Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-09 |  | 2020-09-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6497 | 6497 | 0 | 0 | 0 | 6497 | 0 | 0 | 0 | 0 | 6497 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508660 | S-WW-NI-090920-Swinstie WWTW-Replace the failed and obsolete VSD drive | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-09 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4909.26 | 4909.26 | -9.26 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 4900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508656 | S-WW-NI-090920-Upper Burnmouth WWPS-Refurb 2 Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-09 |  | 2020-10-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5814.23 | 5814.23 | 0 | 0 | 0 | 5814.23 | 0 | 0 | 0 | 0 | 5814.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509171 | S-WW-NI-091020-Galashiels STC-Refurb Centrifuge No1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-01-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12473.94 | 12473.94 | 0 | 0 | 0 | 12473.94 | 0 | 0 | 0 | 0 | 12473.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509173 | S-WW-NI-091020-Glencaple SEP-Refurbish Brickwork and Replace Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3042.15 | 3042.15 | 0 | 0 | 0 | 3042.15 | 0 | 0 | 0 | 0 | 3042.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509190 | S-WW-NI-091020-Linlithgow WWTW-Replace actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2593.92 | 2593.92 | 6.08 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509184 | S-WW-NI-091020-Stepps WWPS-Replace Pump No 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5129.06 | 5129.06 | -2529.05 | 0 | 0 | 2600.01 | 0 | 0 | 0 | 0 | 2600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509186 | S-WW-NI-091020-Stepps WWPS-Replace Pump No 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299.41 | 299.41 | 2300.59 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509183 | S-WW-NI-091020-Trinity WWPS-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11279.98 | 11279.98 | 3320.03 | 0 | 0 | 14600 | 0 | 0 | 0 | 0 | 14600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509180 | S-WW-NI-091020-Troqueer STC-Replace Roller & belts on Klampress 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21772.92 | 21772.92 | -72.92 | 0 | 0 | 21700 | 0 | 0 | 0 | 0 | 21700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509175 | S-WW-NI-091020-Troqueer WWTW-Replace the PH Controller on the Sludge mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3347.58 | 3347.58 | -47.57 | 0 | 0 | 3300.01 | 0 | 0 | 0 | 0 | 3300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509680 | S-WW-NI-091120-Allers WWTW-Roof repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-09 |  | 2021-03-21 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552.85 | 1552.85 | -52.85 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509690 | S-WW-NI-091120-Annan WWTW-Screen gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-09 |  | 2020-11-19 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2437.76 | 2437.76 | 0 | 0 | 0 | 2437.76 | 0 | 0 | 0 | 0 | 2437.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509685 | S-WW-NI-091120-Chapelton WWTW-Replace MLSS Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-09 |  | 2020-11-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2494.29 | 2494.29 | 0 | 0 | 0 | 2494.29 | 0 | 0 | 0 | 0 | 2494.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509699 | S-WW-NI-091120-Eccles WWTW-Replace safety chains with gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.85 | 87.85 | 1112.15 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509682 | S-WW-NI-091120-Sandford WWPS-Replace telemetry outstation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-09 |  | 2021-02-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1367.3 | 1367.3 | 32.71 | 0 | 0 | 1400.01 | 0 | 0 | 0 | 0 | 1400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504252 | S-WW-NI-091219-Dalscone WWTW-Overhaul of Grit Seperator Extra Costs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-01-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 4116.44 | 74.82 | 4191.26 | 0 | 0 | 0 | 4191.26 | 0 | 0 | 0 | 0 | 4191.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504243 | S-WW-NI-091219-Dunnswood WWTW-Replace Grit Removal Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-02-02 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2009.2 | -0.01 | 2009.19 | 0 | 0 | 0 | 2009.19 | 0 | 0 | 0 | 0 | 2009.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504248 | S-WW-NI-091219-Woodbush WWPS-Safe Lifting Operation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2019-12-11 |  | 2021-02-23 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 9567.46 | -86.09 | 9481.37 | -2517 | 0 | 0 | 6964.37 | 0 | 0 | 0 | 0 | 6964.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510219 | S-WW-NI-091220-Coalburn WWTW-Refurb SAF Blower2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-02-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2138.93 | 2138.93 | 61.07 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510217 | S-WW-NI-091220-Coalburn WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3838.02 | 3838.02 | 61.99 | 0 | 0 | 3900.01 | 0 | 0 | 0 | 0 | 3900.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510213 | S-WW-NI-091220-Lockerbie WWTW-Increase width of bridge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637.39 | 637.39 | 8962.61 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 9600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510223 | S-WW-NI-091220-Shawhead WWPS-Replace pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-14 |  | 2021-02-10 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3351.64 | 3351.64 | 48.37 | 0 | 0 | 3400.01 | 0 | 0 | 0 | 0 | 3400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505095 | S-WW-NI-100220-Ayton WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4300 | -3889.58 | 410.42 | 3889.58 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505111 | S-WW-NI-100220-Broughton WWTW-Dismantle Drive & Fit New Chain | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-03-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2295.06 | 0 | 2295.06 | 0 | 0 | 0 | 2295.06 | 0 | 0 | 0 | 0 | 2295.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505100 | S-WW-NI-100220-Hawick WWTW-Replace Pressure Gauge on Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-03-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3224.13 | -0.01 | 3224.12 | 0 | 0 | 0 | 3224.12 | 0 | 0 | 0 | 0 | 3224.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505093 | S-WW-NI-100220-Hutton WWTW-Supply & Fit Scumboards & Brackets | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-09 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3400 | -3084.28 | 315.72 | 3084.28 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505097 | S-WW-NI-100220-Troqueer STC-Repair 3 sections of pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-02-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 9121.87 | 0 | 9121.87 | 0 | 0 | 0 | 9121.87 | 0 | 0 | 0 | 0 | 9121.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511150 | S-WW-NI-100221-Hamilton WWTW-Replace the cover for the desludge valve chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310.17 | 310.17 | 4018.7 | 0 | 0 | 4328.87 | 0 | 0 | 0 | 0 | 4328.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511142 | S-WW-NI-100221-Philipshill WWTW-replace the runs on the penstock | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310.17 | 310.17 | 4018.7 | 0 | 0 | 4328.87 | 0 | 0 | 0 | 0 | 4328.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511152 | S-WW-NI-100221-Strathaven WWTW-Install technocover for RAS well | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346.73 | 346.73 | 4953.25 | 0 | 0 | 5299.98 | 0 | 0 | 0 | 0 | 5299.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505637 | S-WW-NI-100320-Crossford WWTW-Parts to refurb the F.E turbidity meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-03-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2123.93 | 18.47 | 2142.4 | 0 | 0 | 0 | 2142.4 | 0 | 0 | 0 | 0 | 2142.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505645 | S-WW-NI-100320-Galashiels WWTW-Replacement PST 2 Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-04-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1514.31 | 55.88 | 1570.19 | 0 | 0 | 0 | 1570.19 | 0 | 0 | 0 | 0 | 1570.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505622 | S-WW-NI-100320-Haddington WWTW-Install Davit Arm for Safe Lifting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-08-14 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 490.65 | 6968.47 | 7459.12 | 0 | 0 | 0 | 7459.12 | 0 | 0 | 0 | 0 | 7459.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505634 | S-WW-NI-100320-Harthill WWTW-Replace the damaged rendering on the bothy | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-06-19 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 1348.47 | 1446.6 | 0 | 0 | 0 | 1446.6 | 0 | 0 | 0 | 0 | 1446.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505620 | S-WW-NI-100320-PENICUIK VALLEYFIELD ROAD NO1 CSO - Repair CSO Screen Ram | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-11 |  | 2020-03-30 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 4621.38 | 36.94 | 4658.32 | 0 | 0 | 0 | 4658.32 | 0 | 0 | 0 | 0 | 4658.32 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505631 | S-WW-NI-100320-Philipshill WWTW-Cover legal costs for removal of persons illegaly occupying SW land | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 4154.72 | 4239.77 | -2939.77 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505619 | S-WW-NI-100320-Woodbush WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-09-24 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 392.52 | 5561.33 | 5953.85 | 0 | 0 | 0 | 5953.85 | 0 | 0 | 0 | 0 | 5953.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511708 | S-WW-NI-100321-Bathgate WWTW-Relocate the provided actuators | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-10 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366.36 | 366.36 | 4800 | 0 | 0 | 5166.36 | 0 | 0 | 0 | 0 | 5166.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511709 | S-WW-NI-100321-Biggar WWTW-Metalwork repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726.17 | 726.17 | 9514.26 | 0 | 0 | 10240.43 | 0 | 0 | 0 | 0 | 10240.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511718 | S-WW-NI-100321-Biggar WWTW-Replace age deteriorated electrical and control equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1825.23 | 1825.23 | 26074.77 | 0 | 0 | 27900 | 0 | 0 | 0 | 0 | 27900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511705 | S-WW-NI-100321-Bothwellbank WWTW-To scope up a temporary odour masking system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2314.26 | 0 | 0 | 2490.9 | 0 | 0 | 0 | 0 | 2490.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511722 | S-WW-NI-100321-Dunnswood WWTW-Replace failed anoxic mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-10 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 425.23 | 5571.42 | 0 | 0 | 5996.65 | 0 | 0 | 0 | 0 | 5996.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511719 | S-WW-NI-100321-Duns WWTW-Replace outlet auto sampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.56 | 320.56 | 4200 | 0 | 0 | 4520.56 | 0 | 0 | 0 | 0 | 4520.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511715 | S-WW-NI-100321-Gair SEP-Replace septic tank covers and security | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 889.72 | 889.72 | 12710.28 | 0 | 0 | 13600 | 0 | 0 | 0 | 0 | 13600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511714 | S-WW-NI-100321-Linlithgow WWTW-Replace 2 x rotork valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-10 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292.08 | 292.08 | 2314.26 | 0 | 0 | 2606.34 | 0 | 0 | 0 | 0 | 2606.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511706 | S-WW-NI-100321-PORT WILLIAM NORTH WWPS-Replace both pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530.42 | 530.42 | 3171.42 | 0 | 0 | 3701.84 | 0 | 0 | 0 | 0 | 3701.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511713 | S-WW-NI-100321-STRATHCLYDE WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.1 | 327.1 | 4285.74 | 0 | 0 | 4612.84 | 0 | 0 | 0 | 0 | 4612.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507133 | S-WW-NI-100620-Coldstream WWTW-Refurb Surface Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-11 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4134.42 | 4134.42 | -234.42 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507131 | S-WW-NI-100620-Gretna WWPS-Replace both pumps at the WWPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-07-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3263.08 | 3263.08 | 0 | 0 | 0 | 3263.08 | 0 | 0 | 0 | 0 | 3263.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507125 | S-WW-NI-100620-Hamilton WWTW-Refurbish Wash Water Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-07-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3279.48 | 3279.48 | 0 | 0 | 0 | 3279.48 | 0 | 0 | 0 | 0 | 3279.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507123 | S-WW-NI-100620-Linthaugh WWPS-Replacement Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-11 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5226.9 | 5226.9 | -26.9 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 5200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507116 | S-WW-NI-100620-Prestonpans WWPS-Replacement flowmeter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-07-28 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5245.64 | 5245.64 | 0 | 0 | 0 | 5245.64 | 0 | 0 | 0 | 0 | 5245.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507128 | S-WW-NI-100620-Springholm WWTW-Various H&S works to remove risk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7498.96 | 7498.96 | 0 | 0 | 0 | 7498.96 | 0 | 0 | 0 | 0 | 7498.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507114 | S-WW-NI-100620-Strathaven WWTW-Repair RAS Sludge Line | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-06-18 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846.09 | 11846.09 | 0 | 0 | 0 | 11846.09 | 0 | 0 | 0 | 0 | 11846.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507130 | S-WW-NI-100620-Troqueer WWTW-Refurbishment of PST No2 Motor and Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-09-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9785.06 | 9785.06 | 0 | 0 | 0 | 9785.06 | 0 | 0 | 0 | 0 | 9785.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507623 | S-WW-NI-100720-Blackwood WWTW-Repair leaking from distribution Chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-10 |  | 2020-08-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2846.25 | 2846.25 | 0 | 0 | 0 | 2846.25 | 0 | 0 | 0 | 0 | 2846.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507616 | S-WW-NI-100720-East Linton WWTW-H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-10 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290.66 | 290.66 | 4009.34 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507621 | S-WW-NI-100720-South Queensferry WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-10 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157.64 | 2157.64 | 42.37 | 0 | 0 | 2200.01 | 0 | 0 | 0 | 0 | 2200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504265 | S-WW-NI-101219-Port William WWTW-Replace Tank Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-04-23 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 5783.04 | 318.64 | 6101.67 | 0 | 0 | 0 | 6101.67 | 0 | 0 | 0 | 0 | 6101.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510245 | S-WW-NI-101220-Ballochburn CSO-Replace the Grass Crete with Concrete | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586.47 | 586.47 | 6613.53 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 7200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510250 | S-WW-NI-101220-Bilston WWTW-Replacement Pump 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-26 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3193.83 | 3193.83 | 6.17 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510242 | S-WW-NI-101220-Newton Stewart WWTW-Replace RAS Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6281.18 | 6281.18 | -881.17 | 0 | 0 | 5400.01 | 0 | 0 | 0 | 0 | 5400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510238 | S-WW-NI-101220-St Abbs South SPS-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6884.1 | 6884.1 | -84.1 | 0 | 0 | 6800 | 0 | 0 | 0 | 0 | 6800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510618 | S-WW-NI-110121-Chapelcross WWTW-Reed Bed survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.15 | 491.15 | 5118.2 | 0 | 0 | 5609.35 | 0 | 0 | 0 | 0 | 5609.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510620 | S-WW-NI-110121-Eaglesfield WWTW-Reed Bed Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.15 | 491.15 | 5118.2 | 0 | 0 | 5609.35 | 0 | 0 | 0 | 0 | 5609.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510622 | S-WW-NI-110121-Ecclefechan WWTW-Reed Bed Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.15 | 491.15 | 5118.2 | 0 | 0 | 5609.35 | 0 | 0 | 0 | 0 | 5609.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510615 | S-WW-NI-110121-Moffat WWTW-Supply and install fall protection to wet wells | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2436.92 | 2436.92 | 63.08 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510627 | S-WW-NI-110121-Powfoot SEP-Reed Bed survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.15 | 491.15 | 5118.2 | 0 | 0 | 5609.35 | 0 | 0 | 0 | 0 | 5609.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510631 | S-WW-NI-110121-Strathaven WWTW-refurbish washwater system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-11 |  | 2021-02-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163.78 | 1163.78 | 845.56 | 0 | 0 | 2009.34 | 0 | 0 | 0 | 0 | 2009.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505135 | S-WW-NI-110220-Broughton WWTW-Replace Corroded Pipework to Holding Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -2269.49 | 230.52 | 2269.49 | 0 | 0 | 2500.01 | 0 | 0 | 0 | 0 | 2500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505143 | S-WW-NI-110220-Daldowie WWTW-Repair 2No Pot Holes in Access Rd | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 621 | -611.77 | 9.24 | 2290.77 | 0 | 0 | 2300.01 | 0 | 0 | 0 | 0 | 2300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505133 | S-WW-NI-110220-Newton Stewart WWTW-Emergency Light Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-03-20 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1369.88 | -0.01 | 1369.87 | 0 | 0 | 0 | 1369.87 | 0 | 0 | 0 | 0 | 1369.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511171 | S-WW-NI-110221-Ashgill WWTW-Seal dry well concrete wall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.43 | 222.43 | 3177.55 | 0 | 0 | 3399.98 | 0 | 0 | 0 | 0 | 3399.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511176 | S-WW-NI-110221-Daldowie WWTW-Refurb Motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18816.29 | 18816.29 | -1716.29 | 0 | 0 | 17100 | 0 | 0 | 0 | 0 | 17100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511182 | S-WW-NI-110221-Galashiels STC-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-11 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3722.95 | 3722.95 | 77.05 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511180 | S-WW-NI-110221-Kirkconnel WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594.42 | 594.42 | 5405.6 | 0 | 0 | 6000.02 | 0 | 0 | 0 | 0 | 6000.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511172 | S-WW-NI-110221-Philipshill WWTW-Refurbish the grit pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3975.54 | 3975.54 | 24.46 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505678 | S-WW-NI-110320-Castle Douglas WWTW-Supply & Fit Motor & Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-05-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 642.09 | 6847.41 | 7489.5 | 0 | 0 | 0 | 7489.5 | 0 | 0 | 0 | 0 | 7489.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505681 | S-WW-NI-110320-Dryffe Rd Lockerbie-Replacement Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-10-21 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 549.53 | 7832.31 | 8381.84 | 0 | 0 | 0 | 8381.84 | 0 | 0 | 0 | 0 | 8381.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505680 | S-WW-NI-110320-Eastriggs WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-06-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 346.73 | 4993.84 | 5340.57 | 0 | 0 | 0 | 5340.57 | 0 | 0 | 0 | 0 | 5340.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505666 | S-WW-NI-110320-HEATHHALL WHISKEY SPS CSO-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-03-11 |  | 2020-05-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 6083.8 | 6509.03 | 0 | 0 | 0 | 6509.03 | 0 | 0 | 0 | 0 | 6509.03 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505674 | S-WW-NI-110320-Loch Ryan WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-06-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1576.64 | 21569.19 | 23145.83 | 0 | 0 | 0 | 23145.83 | 0 | 0 | 0 | 0 | 23145.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505677 | S-WW-NI-110320-MINIGAFF HOLM PARK WWPS NX413652-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-06-22 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 703.18 | 7578.54 | 8281.72 | 0 | 0 | 0 | 8281.72 | 0 | 0 | 0 | 0 | 8281.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505660 | S-WW-NI-110320-Mosside WWPS-Replacement Grinder Critical Spare | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-06-16 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1036.05 | 12378.47 | 13414.52 | 0 | 0 | 0 | 13414.52 | 0 | 0 | 0 | 0 | 13414.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505664 | S-WW-NI-110320-S Queensferry WWTW-Repair Actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-03-24 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 4024.22 | 0 | 4024.22 | 0 | 0 | 0 | 4024.22 | 0 | 0 | 0 | 0 | 4024.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505673 | S-WW-NI-110320-Troqueer STC-Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-04-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 10501.56 | 55.88 | 10557.44 | 0 | 0 | 0 | 10557.44 | 0 | 0 | 0 | 0 | 10557.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505668 | S-WW-NI-110320-Troqueer STC-Supply and Replacement of 2No. Sludge Press Belts | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-04-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 14616.97 | 55.41 | 14672.38 | 0 | 0 | 0 | 14672.38 | 0 | 0 | 0 | 0 | 14672.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505671 | S-WW-NI-110320-Troqueer WWPS-H&S Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-07-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 9984.44 | 10684.44 | 0 | 0 | 0 | 10684.44 | 0 | 0 | 0 | 0 | 10684.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505662 | S-WW-NI-110320-Winchburgh WWTW-Upsize pump for the purpose of the tertiary SAF | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-11 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 506.15 | 18.47 | 524.62 | 4675.38 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 5200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511724 | S-WW-NI-110321-Biggar WWTW-Replace the roof of the sludge pumphouse building | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300.02 | 300.02 | 3685.74 | 0 | 0 | 3985.76 | 0 | 0 | 0 | 0 | 3985.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511725 | S-WW-NI-110321-Carstairs Junction WWTW-building refurbishments | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608.41 | 608.41 | 7971.42 | 0 | 0 | 8579.83 | 0 | 0 | 0 | 0 | 8579.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511732 | S-WW-NI-110321-Coalburn WWTW-Strip out SAF Unit No1 to survey condition | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314.02 | 314.02 | 4114.26 | 0 | 0 | 4428.28 | 0 | 0 | 0 | 0 | 4428.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511738 | S-WW-NI-110321-MCDIARMID WWPS-Replace old floats with new level controller and head | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430.87 | 430.87 | 3000 | 0 | 0 | 3430.87 | 0 | 0 | 0 | 0 | 3430.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511728 | S-WW-NI-110321-Philipshill WWTW-Replace Scraper Blades PST1&2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-11 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 816.84 | 816.84 | 10457.16 | 0 | 0 | 11274 | 0 | 0 | 0 | 0 | 11274 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511746 | S-WW-NI-110321-Selkirk WWTW-Replace drive wheel on FST bridge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-11 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 755.4 | 755.4 | 7628.58 | 0 | 0 | 8383.98 | 0 | 0 | 0 | 0 | 8383.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511737 | S-WW-NI-110321-Twynholm WWTW-Bring the Stand Pipes down to a proper tanker stand pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765.93 | 765.93 | 6257.16 | 0 | 0 | 7023.09 | 0 | 0 | 0 | 0 | 7023.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507143 | S-WW-NI-110620-Albert Rd WWPS-Replace actuator 4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-11 |  | 2021-03-29 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4390.5 | 4390.5 | 9.5 | 0 | 0 | 4400 | 0 | 0 | 0 | 0 | 4400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507157 | S-WW-NI-110620-Annan Riverside WWPS-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-06-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2181.33 | 2181.33 | 0 | 0 | 0 | 2181.33 | 0 | 0 | 0 | 0 | 2181.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507151 | S-WW-NI-110620-Bothwellbank WWTW-Investigation into ammonia failure | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-29 |  | 2021-01-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 769.65 | 769.65 | 9230.35 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507149 | S-WW-NI-110620-Carlops WWTW-Construct steps to reduce slip hazard | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-11 |  | 2021-04-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3005.61 | 3005.61 | -5.61 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507141 | S-WW-NI-110620-Dunnswood WWTW-Replace Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-06-22 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6420.46 | 6420.46 | 0 | 0 | 0 | 6420.46 | 0 | 0 | 0 | 0 | 6420.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507139 | S-WW-NI-110620-Galashiels WWTW-Refurbish filter media | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-10-09 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8485.32 | 8485.32 | 0 | 0 | 0 | 8485.32 | 0 | 0 | 0 | 0 | 8485.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507156 | S-WW-NI-110620-Greengairs WWTW-Replace the washwater pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-06-29 |  | 2021-03-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44172.85 | 44172.85 | 1265.91 | 0 | 0 | 45438.76 | 0 | 0 | 0 | 0 | 45438.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507145 | S-WW-NI-110620-Hawick WWTW-Removing & Building Wall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-08-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5388.49 | 5388.49 | 0 | 0 | 0 | 5388.49 | 0 | 0 | 0 | 0 | 5388.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507138 | S-WW-NI-110620-Lauder WWTW-Building Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-10-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5046.44 | 5046.44 | 0 | 0 | 0 | 5046.44 | 0 | 0 | 0 | 0 | 5046.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508155 | S-WW-NI-110820-Almondvale WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-11 |  | 2020-09-21 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3816.37 | 3816.37 | 0 | 0 | 0 | 3816.37 | 0 | 0 | 0 | 0 | 3816.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508143 | S-WW-NI-110820-Glassford WWTW-Replace DO Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-11 |  | 2020-08-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.47 | 1116.47 | 0 | 0 | 0 | 1116.47 | 0 | 0 | 0 | 0 | 1116.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508146 | S-WW-NI-110820-Harthill WWTW-Replace Wash Water Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-11 |  | 2020-10-05 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331.48 | 1331.48 | 0 | 0 | 0 | 1331.48 | 0 | 0 | 0 | 0 | 1331.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508140 | S-WW-NI-110820-Lanark WWTW-Repair Concrete Cracking | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-11 |  | 2020-10-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2198.38 | 2198.38 | 0 | 0 | 0 | 2198.38 | 0 | 0 | 0 | 0 | 2198.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508151 | S-WW-NI-110820-Port Rodie WWPS-Secure Floor fixing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-10-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2592.16 | 2592.16 | 0 | 0 | 0 | 2592.16 | 0 | 0 | 0 | 0 | 2592.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508160 | S-WW-NI-110820-Troqueer WWTW-Replace Scraper Bridge wheel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-11 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800.24 | 1800.24 | 0 | 0 | 0 | 1800.24 | 0 | 0 | 0 | 0 | 1800.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508710 | S-WW-NI-11092020-FORTH WWTW-INSTALLATION OF CHEMICAL DOSING UNIT (QP20) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-12 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9913.07 | 9913.07 | 127586.93 | 0 | 0 | 137500 | 0 | 0 | 0 | 0 | 137500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503794 | S-WW-NI-111119-SKELLYTON WWTW-REPLACEMENT VALVE | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-03-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7285.51 | 477.57 | 7763.08 | 0 | 0 | 0 | 7763.08 | 0 | 0 | 0 | 0 | 7763.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509729 | S-WW-NI-111120-Cairnryan WWTW-Replace KSB Pumps with Xylem | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-12 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859.22 | 859.22 | 10740.78 | 0 | 0 | 11600 | 0 | 0 | 0 | 0 | 11600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509723 | S-WW-NI-111120-Carbarns WWTW-Replace PST scraper bridge cable | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-12 |  | 2020-11-29 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652.56 | 1652.56 | 0 | 0 | 0 | 1652.56 | 0 | 0 | 0 | 0 | 1652.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509731 | S-WW-NI-111120-Dalscone WWTW-Refurb Grit ram pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-12 |  | 2021-02-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8808.28 | 8808.28 | 57.72 | 0 | 0 | 8866 | 0 | 0 | 0 | 0 | 8866 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509745 | S-WW-NI-111120-Hamilton WWTW-Lift and Refurbish ASP Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-12 |  | 2021-02-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.3 | 3881.3 | 18118.71 | 0 | 0 | 22000.01 | 0 | 0 | 0 | 0 | 22000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509732 | S-WW-NI-111120-Moffat WWTW-Supply and install fall protection to wet wells | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-12 |  | 2021-03-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6102.42 | 6102.42 | -2.42 | 0 | 0 | 6100 | 0 | 0 | 0 | 0 | 6100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509722 | S-WW-NI-111120-Nethanfoot WWPS-MD to Scope Repairs to Retaining Wall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-11-17 | 2021-06-04 | 2021-08-16 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643.48 | 643.48 | 9487.32 | 0 | 0 | 10130.8 | 0 | 0 | 0 | 0 | 10130.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509725 | S-WW-NI-111120-Newton Stewart WWTW-Replace the KSB tanker import pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-12 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15022.44 | 15022.44 | -322.44 | 0 | 0 | 14700 | 0 | 0 | 0 | 0 | 14700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509736 | S-WW-NI-111120-Strathaven WWTW-New NTF Drive | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-12 |  | 2021-02-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7684.86 | 7684.86 | 15.14 | 0 | 0 | 7700 | 0 | 0 | 0 | 0 | 7700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509743 | S-WW-NI-111120-Strathaven WWTW-Replace parts MLSS Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-12 |  | 2020-01-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3966.54 | 3966.54 | 0 | 0 | 0 | 3966.54 | 0 | 0 | 0 | 0 | 3966.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504297 | S-WW-NI-111219-Eastriggs WWTW-Sludge Pump Lagging | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-13 |  | 2019-12-27 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4567 | -0.01 | 4566.99 | 0 | 0 | 0 | 4566.99 | 0 | 0 | 0 | 0 | 4566.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504302 | S-WW-NI-111219-Plains WWTW-Replace Dry Bearing Shaft | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-13 |  | 2019-12-16 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 8830.46 | 0 | 8830.46 | 0 | 0 | 0 | 8830.46 | 0 | 0 | 0 | 0 | 8830.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510268 | S-WW-NI-111220-Bathgate WWTW-Supply and installation of 2 gearboxes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640.2 | 640.2 | 8859.8 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 9500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510274 | S-WW-NI-111220-Chapelcross WWTW-Repair acces road potholes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.43 | 177.43 | 2322.57 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510279 | S-WW-NI-111220-Coldstream WWTW-Replace office door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1239.09 | 1239.09 | -39.09 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510270 | S-WW-NI-111220-LAW NEAR WILDMAN RD CSO-telemetry equipment | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1292.68 | 1292.68 | 7.32 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510262 | S-WW-NI-111220-North Berwick WWTW-Evaluate and refurbish submersible pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-04-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3867.7 | 3867.7 | 32.3 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510282 | S-WW-NI-111220-Troqueer WWTW-Supply and fit ladder covers at sludge holding tanks | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-02-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600.48 | 1600.48 | -0.48 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510662 | S-WW-NI-120121-Cove WWTW-Supply hose reel for washdown | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.46 | 229.46 | 1379.88 | 0 | 0 | 1609.34 | 0 | 0 | 0 | 0 | 1609.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510641 | S-WW-NI-120121-Fillyside WWPS-Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-15 |  | 2021-03-04 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139.86 | 1139.86 | 60.12 | 0 | 0 | 1199.98 | 0 | 0 | 0 | 0 | 1199.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510659 | S-WW-NI-120121-Galashiels WWTW-Refurbish Recirc pump no1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219.2 | 219.2 | 1099.52 | 0 | 0 | 1318.72 | 0 | 0 | 0 | 0 | 1318.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510649 | S-WW-NI-120121-Loch Ryan WWTW-Replace the faulty wash water valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-15 |  | 2021-03-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925.71 | 1925.71 | -116.36 | 0 | 0 | 1809.35 | 0 | 0 | 0 | 0 | 1809.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510653 | S-WW-NI-120121-Troqueer WWTW-Site Drainage Pumping station Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185.99 | 185.99 | 2523.36 | 0 | 0 | 2709.35 | 0 | 0 | 0 | 0 | 2709.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510655 | S-WW-NI-120121-Tyninghame WWTW- Repair to blower number 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-15 |  | 2021-04-03 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2230.24 | 2230.24 | 488.48 | 0 | 0 | 2718.72 | 0 | 0 | 0 | 0 | 2718.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510642 | S-WW-NI-120121-West Linton WWPS-pump replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.46 | 136.46 | 1682.24 | 0 | 0 | 1818.7 | 0 | 0 | 0 | 0 | 1818.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505160 | S-WW-NI-120220-22 Lower Gilmore Place-Internal Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-02-12 |  | 2020-04-23 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | -20728.72 | 29271.29 | 0 | 0 | 0 | 29271.29 | 0 | 0 | 0 | 0 | 29271.29 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505158 | S-WW-NI-120220-Auchencrow WWTW-Filter Arms Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-09-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 138.11 | 1638.11 | 0 | 0 | 0 | 1638.11 | 0 | 0 | 0 | 0 | 1638.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505165 | S-WW-NI-120220-Gorebridge WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-03-07 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 1393.79 | 0 | 1393.79 | 0 | 0 | 0 | 1393.79 | 0 | 0 | 0 | 0 | 1393.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505157 | S-WW-NI-120220-Hawick WWTW-Remote Telemetry Units | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-02-27 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | -109.03 | 1490.97 | 0 | 0 | 0 | 1490.97 | 0 | 0 | 0 | 0 | 1490.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505167 | S-WW-NI-120220-Penicuik WWTW-Replacement Level Transmitter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-04-25 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 27.27 | 1527.27 | 0 | 0 | 0 | 1527.27 | 0 | 0 | 0 | 0 | 1527.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505155 | S-WW-NI-120220-Penpont Sep-Construction of Layby | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-05-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1771.86 | 35165.14 | 36937 | 0 | 0 | 0 | 36937 | 0 | 0 | 0 | 0 | 36937 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505163 | S-WW-NI-120220-Philipshill WWTW-Replace Motor on Fine Screen A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-04-09 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | -146.59 | 1353.41 | 0 | 0 | 0 | 1353.41 | 0 | 0 | 0 | 0 | 1353.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511187 | S-WW-NI-120221-Gilmerton WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-23 |  | 2021-03-10 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 0 | 0 | 0 | 196.26 | 0 | 0 | 0 | 0 | 196.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511189 | S-WW-NI-120221-Hamilton WWTW-Refurbish the outlet controller for the RTC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.22 | 136.22 | 1121.5 | 0 | 0 | 1257.72 | 0 | 0 | 0 | 0 | 1257.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511200 | S-WW-NI-120221-Newton Stewart WWTW-Replace MLSS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2589.37 | 2589.37 | -89.4 | 0 | 0 | 2499.97 | 0 | 0 | 0 | 0 | 2499.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505685 | S-WW-NI-120320-Ayton WWPS-Replacement Transfer Pump2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-05-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 463.91 | 5031.88 | 5495.79 | 0 | 0 | 0 | 5495.79 | 0 | 0 | 0 | 0 | 5495.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505701 | S-WW-NI-120320-Cairnryan WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-04-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 1903.24 | 2034.08 | 0 | 0 | 0 | 2034.08 | 0 | 0 | 0 | 0 | 2034.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505700 | S-WW-NI-120320-Dladowie WWTW-Replace Actuator Supports | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-05-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 256.63 | 3238.47 | 3495.1 | 0 | 0 | 0 | 3495.1 | 0 | 0 | 0 | 0 | 3495.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505689 | S-WW-NI-120320-Dunnswood WWTW-Replace Motor & Gearbox on Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-06-16 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 289.34 | 3681.47 | 3970.81 | 0 | 0 | 0 | 3970.81 | 0 | 0 | 0 | 0 | 3970.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505705 | S-WW-NI-120320-Eyemouth WWTW-installing spindles within the Hydro Brake chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 9.24 | 100.83 | 1299.18 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505702 | S-WW-NI-120320-Hawick stc-Replacement Motors x2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-04-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1225.25 | 18.47 | 1243.72 | 0 | 0 | 0 | 1243.72 | 0 | 0 | 0 | 0 | 1243.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505683 | S-WW-NI-120320-Leet Green WWPS-Refurb 2No Motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-03-24 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3851.87 | 0 | 3851.87 | 0 | 0 | 0 | 3851.87 | 0 | 0 | 0 | 0 | 3851.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505692 | S-WW-NI-120320-Leet Green WWPS-Replace Damaged Motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-03-24 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2712.31 | 55.88 | 2768.19 | 0 | 0 | 0 | 2768.19 | 0 | 0 | 0 | 0 | 2768.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505695 | S-WW-NI-120320-Leet Green WWPS-Replacement Motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-03-24 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2870.66 | 55.88 | 2926.54 | 0 | 0 | 0 | 2926.54 | 0 | 0 | 0 | 0 | 2926.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505682 | S-WW-NI-120320-Lockerbie WWTW-Refurbish Filter Bed Column 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-10-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 2631.66 | 2814.84 | 0 | 0 | 0 | 2814.84 | 0 | 0 | 0 | 0 | 2814.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505688 | S-WW-NI-120320-Powfoot WWPS-Replace 2x Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-04-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 261.68 | 3754.37 | 4016.05 | 0 | 0 | 0 | 4016.05 | 0 | 0 | 0 | 0 | 4016.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505704 | S-WW-NI-120320-Shotts Network Enforcement Notice EN | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-03-19 |  | 2021-02-23 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 5002.22 | 5355.49 | 0 | 0 | 0 | 5355.49 | 0 | 0 | 0 | 0 | 5355.49 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507160 | S-WW-NI-120620-Blackridge WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-10 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1305.6 | 1305.6 | 0 | 0 | 0 | 1305.6 | 0 | 0 | 0 | 0 | 1305.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507165 | S-WW-NI-120620-Dalscone WWTW-Refurb SAS Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1466.4 | 1466.4 | 0 | 0 | 0 | 1466.4 | 0 | 0 | 0 | 0 | 1466.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507159 | S-WW-NI-120620-DUMFRIES NITHSIDE WWPS-Cabling Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1476.2 | 1476.2 | 0 | 0 | 0 | 1476.2 | 0 | 0 | 0 | 0 | 1476.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507163 | S-WW-NI-120620-Duns WWTW-Replace gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1433.03 | 1433.03 | 0 | 0 | 0 | 1433.03 | 0 | 0 | 0 | 0 | 1433.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507168 | S-WW-NI-120620-Harvesters WWPS-H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-06-29 |  | 2020-10-19 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5582 | 5582 | 418.31 | 0 | 0 | 6000.31 | 0 | 0 | 0 | 0 | 6000.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507162 | S-WW-NI-120620-Langholm WWTW-PST Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1938.81 | 1938.81 | 0 | 0 | 0 | 1938.81 | 0 | 0 | 0 | 0 | 1938.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507166 | S-WW-NI-120620-Laurieston WWTW-Replace Filter Arms | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2281.53 | 2281.53 | 0 | 0 | 0 | 2281.53 | 0 | 0 | 0 | 0 | 2281.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508164 | S-WW-NI-120820-Burnside WWPS-Replacement Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-11-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4646.49 | 4646.49 | 0 | 0 | 0 | 4646.49 | 0 | 0 | 0 | 0 | 4646.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508168 | S-WW-NI-120820-Dunnswood WWTW-Replace broken panels on the disk filter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-12 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17801.94 | 17801.94 | -3501.93 | 0 | 0 | 14300.01 | 0 | 0 | 0 | 0 | 14300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508165 | S-WW-NI-120820-Edingham WWPS-Replacement Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-11-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6321.21 | 6321.21 | 0 | 0 | 0 | 6321.21 | 0 | 0 | 0 | 0 | 6321.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508167 | S-WW-NI-120820-Galashiels STC-Replace sludge recirculation pump 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-12 |  | 2020-09-25 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4381.56 | 4381.56 | 0 | 0 | 0 | 4381.56 | 0 | 0 | 0 | 0 | 4381.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508170 | S-WW-NI-120820-Harthill WWTW-Replace humus return pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-13 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253.06 | 253.06 | 2446.94 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508166 | S-WW-NI-120820-New Abbey WWPS-Replacement Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-11-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7332.54 | 7332.54 | 0 | 0 | 0 | 7332.54 | 0 | 0 | 0 | 0 | 7332.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508173 | S-WW-NI-120820-Olivers Tank-Install new holding tank & pipework & telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-08-17 | 2021-05-03 | 2021-11-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39768 | 39768 | 60232.16 | 0 | 0 | 100000.16 | 0 | 0 | 0 | 0 | 100000.16 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509217 | S-WW-NI-121020-Ashgill WWTW-Repairs to Lighning Protection System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-28 |  | 2021-03-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636.04 | 1636.04 | 63.96 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509225 | S-WW-NI-121020-Coldstream WWTW-Hand held turbidity meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-10-27 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1375.4 | 1375.4 | 24.61 | 0 | 0 | 1400.01 | 0 | 0 | 0 | 0 | 1400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509202 | S-WW-NI-121020-Newcastleton WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-10-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801.56 | 1801.56 | 0 | 0 | 0 | 1801.56 | 0 | 0 | 0 | 0 | 1801.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509207 | S-WW-NI-121020-Selkirk WWTW-Replace Grit Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-11-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2849.46 | 2849.46 | 0 | 0 | 0 | 2849.46 | 0 | 0 | 0 | 0 | 2849.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509215 | S-WW-NI-121020-Strathclyde WWTW-Replace scrapers flat bars and rubbers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-02-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5563.12 | 5563.12 | 0 | 0 | 0 | 5563.12 | 0 | 0 | 0 | 0 | 5563.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509755 | S-WW-NI-121120-Bothwellbank WWTW-Flow Control Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-11-24 | 2021-05-21 | 2022-01-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296.3 | 296.3 | 4700 | 0 | 0 | 4996.3 | 0 | 0 | 0 | 0 | 4996.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509759 | S-WW-NI-121120-Chirnside WWTW-Replace inlet screen motor & gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-17 |  | 2021-04-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5499.73 | 5499.73 | -99.73 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 5400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509753 | S-WW-NI-121120-Curhill Cres WWPS-Manhole Cover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-12 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522.7 | 522.7 | 4677.3 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 5200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509765 | S-WW-NI-121120-Eyemouth WWTW-Replace poly dosing system A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-17 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8411.65 | 8411.65 | -211.65 | 0 | 0 | 8200 | 0 | 0 | 0 | 0 | 8200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509763 | S-WW-NI-121120-Philipshill WWTW-WwPS Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-11-24 | 2021-03-15 | 2021-06-07 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1674 | 1674 | 3325.92 | 0 | 0 | 4999.92 | 0 | 0 | 0 | 0 | 4999.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509752 | S-WW-NI-121120-Stonehouse WWTW-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-12 |  | 2020-10-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3479.52 | 3479.52 | 0 | 0 | 0 | 3479.52 | 0 | 0 | 0 | 0 | 3479.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509758 | S-WW-NI-121120-Strathaven WWTW-Rising main burst repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-17 |  | 2020-11-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16165.23 | 16165.23 | 0 | 0 | 0 | 16165.23 | 0 | 0 | 0 | 0 | 16165.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509761 | S-WW-NI-121120-Walkerburn WWTW-Replace sludge tank mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-17 |  | 2021-03-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2953.76 | 2953.76 | -53.76 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504334 | S-WW-NI-121219-Hamilton WWTW-Install Sludge Blanket Detectors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2021-05-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 2662 | 17662 | 9337.7 | 0 | 0 | 26999.7 | 0 | 0 | 0 | 0 | 26999.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504325 | S-WW-NI-121219-Harleyholm SEP-Blocked Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2021-09-29 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 21715.9 | -18772.72 | 2943.19 | 22056.8 | 0 | 0 | 24999.99 | 0 | 0 | 0 | 0 | 24999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504311 | S-WW-NI-121219-Hawick WWTW-Structural Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-13 |  | 2020-02-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 7246.38 | 0 | 7246.38 | 0 | 0 | 0 | 7246.38 | 0 | 0 | 0 | 0 | 7246.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504307 | S-WW-NI-121219-Kelso WWTW-Blower Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-13 |  | 2020-01-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4229.78 | 37.41 | 4267.19 | 0 | 0 | 0 | 4267.19 | 0 | 0 | 0 | 0 | 4267.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504318 | S-WW-NI-121219-Loch Ryan WWTW-Site Inv & Condition Report | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-13 |  | 2019-12-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3105.04 | -0.01 | 3105.03 | 0 | 0 | 0 | 3105.03 | 0 | 0 | 0 | 0 | 3105.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504331 | S-WW-NI-121219-South Vennel Lanark-re lay approx 100m of sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2019-12-13 |  | 2020-04-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 21376.38 | 141376.38 | 0 | 0 | 0 | 141376.38 | 0 | 0 | 0 | 0 | 141376.38 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504322 | S-WW-NI-121219-Thornhill WWTW-Replace NRV & Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-13 |  | 2020-01-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1468.08 | -0.01 | 1468.07 | 0 | 0 | 0 | 1468.07 | 0 | 0 | 0 | 0 | 1468.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504315 | S-WW-NI-121219-Troqueer WWTW-PST 3 Scum Scrapers Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-13 |  | 2020-02-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 7805.25 | 37.41 | 7842.66 | 0 | 0 | 0 | 7842.66 | 0 | 0 | 0 | 0 | 7842.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504310 | S-WW-NI-121219-Tweed Bank WWPS-Rising Main Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-13 |  | 2020-10-09 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 24800 | 2183.86 | 26983.86 | 0 | 0 | 0 | 26983.86 | 0 | 0 | 0 | 0 | 26983.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504624 | S-WW-NI-130120-Foulden WWTW-Storm tank repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-01-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1612.32 | -0.01 | 1612.31 | 0 | 0 | 0 | 1612.31 | 0 | 0 | 0 | 0 | 1612.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504621 | S-WW-NI-130120-Walkerburn WWTW-Screen Hinges Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-08-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2010.7 | 4635.18 | 6645.87 | 0 | 0 | 0 | 6645.87 | 0 | 0 | 0 | 0 | 6645.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510684 | S-WW-NI-130121-Bathgate WWTW-Carry out repairs to screw pumphouse roof | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-15 |  | 2021-03-26 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7479.26 | 7479.26 | -60.56 | 0 | 0 | 7418.7 | 0 | 0 | 0 | 0 | 7418.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510674 | S-WW-NI-130121-Denholm WWTW-Investigate solution for Motor & Gearbox replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362.62 | 362.62 | 5046.72 | 0 | 0 | 5409.34 | 0 | 0 | 0 | 0 | 5409.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510675 | S-WW-NI-130121-Mauldslie WWTW-Removal of both storm screens for inspection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454.21 | 454.21 | 6355.12 | 0 | 0 | 6809.33 | 0 | 0 | 0 | 0 | 6809.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510677 | S-WW-NI-130121-Philipshill WWTW-Provide a PST bearing assembly | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417.65 | 417.65 | 5420.56 | 0 | 0 | 5838.21 | 0 | 0 | 0 | 0 | 5838.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510671 | S-WW-NI-130121-Ravenscraig WWPS-provide and fit a security kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15176.1 | 15176.1 | 23.91 | 0 | 0 | 15200 | 0 | 0 | 0 | 0 | 15200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510691 | S-WW-NI-130121-Swinstie WWTW-Replace PST2 scraper bridge gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3843.42 | 3843.42 | 1756.59 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 5600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505182 | S-WW-NI-130220-Burnhead SEP-Road Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-09-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 459 | 1343.5 | 1802.5 | 0 | 0 | 0 | 1802.5 | 0 | 0 | 0 | 0 | 1802.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505177 | S-WW-NI-130220-Dunragit WWTW-Demolition and make safe of old PS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-09-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 540 | 1512.14 | 2052.14 | 0 | 0 | 0 | 2052.14 | 0 | 0 | 0 | 0 | 2052.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505691 | S-WW-NI-130320-Dunbar WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-12 |  | 2020-05-21 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3175.23 | 2713.67 | 5888.9 | 0 | 0 | 0 | 5888.9 | 0 | 0 | 0 | 0 | 5888.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506596 | S-WW-NI-13052020-Troqueer STC-Replacement of drive roller and bearing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-09-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6860.31 | 6860.31 | 0 | 0 | 0 | 6860.31 | 0 | 0 | 0 | 0 | 6860.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506591 | S-WW-NI-13052020-Troqueer WWTW-To supply and install Rotork valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-10-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13496.99 | 13496.99 | 0 | 0 | 0 | 13496.99 | 0 | 0 | 0 | 0 | 13496.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506593 | S-WW-NI-130520-Bridgend WWTW-Repair fence and replace gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-07-24 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180.69 | 3180.69 | 0 | 0 | 0 | 3180.69 | 0 | 0 | 0 | 0 | 3180.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506601 | S-WW-NI-130520-Dalbeattie Port St CSO-Replacement of Brush shaft | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-14 |  | 2020-09-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8473.76 | 8473.76 | 0 | 0 | 0 | 8473.76 | 0 | 0 | 0 | 0 | 8473.76 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506592 | S-WW-NI-130520-Eastriggs WWTW-Purchase of air inlet rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-07-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997.94 | 2997.94 | 0 | 0 | 0 | 2997.94 | 0 | 0 | 0 | 0 | 2997.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506604 | S-WW-NI-130520-North Berwick WWTW-Replace a section of outfall pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-11-25 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3062.04 | 3062.04 | 0 | 0 | 0 | 3062.04 | 0 | 0 | 0 | 0 | 3062.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507658 | S-WW-NI-130720-Swinstie WWTW-Refurbish Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-14 |  | 2020-08-25 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2588.63 | 2588.63 | 0 | 0 | 0 | 2588.63 | 0 | 0 | 0 | 0 | 2588.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508187 | S-WW-NI-130820-Chapelton WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-10-02 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2113 | 2113 | 0 | 0 | 0 | 2113 | 0 | 0 | 0 | 0 | 2113 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508176 | S-WW-NI-130820-College St WWPS-Replace 2 pumps & controls | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-17 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16887.95 | 16887.95 | 112.05 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 17000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508178 | S-WW-NI-130820-Eastfield WWPS-Remove damaged gates and stone work | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-10-13 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4795.34 | 4795.34 | 0 | 0 | 0 | 4795.34 | 0 | 0 | 0 | 0 | 4795.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508175 | S-WW-NI-130820-Haddington WWTW-Refurb Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-09-01 | 2020-12-04 | 2021-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3966 | 3966 | 0 | 0 | 0 | 3966 | 0 | 0 | 0 | 0 | 3966 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508186 | S-WW-NI-130820-Kelso WWTW-Refurbish Blower no.2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-08-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1355.2 | 1355.2 | 0 | 0 | 0 | 1355.2 | 0 | 0 | 0 | 0 | 1355.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508180 | S-WW-NI-130820-Rowanburn WWTW-Generator earth rods | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2222.36 | 2222.36 | 0 | 0 | 0 | 2222.36 | 0 | 0 | 0 | 0 | 2222.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508184 | S-WW-NI-130820-Upper Burnmouth SPS-Replace Sensor Bracket | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2020-08-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278.94 | 1278.94 | 0 | 0 | 0 | 1278.94 | 0 | 0 | 0 | 0 | 1278.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508179 | S-WW-NI-130820-West Linton WWTW-Replace lifting sockets & davits | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-13 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5576.64 | 5576.64 | 223.36 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 5800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509240 | S-WW-NI-131020-Springholm WWTW-Replace the burst pressure vessel and burst pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-10-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380.12 | 1380.12 | 0 | 0 | 0 | 1380.12 | 0 | 0 | 0 | 0 | 1380.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503816 | S-WW-NI-131119-Coldstream WWTW-Outfall Pipe Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2019-12-04 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4152.4 | 273.84 | 4426.24 | 0 | 0 | 0 | 4426.24 | 0 | 0 | 0 | 0 | 4426.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503818 | S-WW-NI-131119-Dumfries St Marys WWPS-Civil Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2019-12-20 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1210.64 | 71.96 | 1282.6 | 0 | 0 | 0 | 1282.6 | 0 | 0 | 0 | 0 | 1282.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503811 | S-WW-NI-131119-Plains WWTW-Replacement Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-20 |  | 2020-03-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 9927.66 | 666.36 | 10594.02 | 0 | 0 | 0 | 10594.02 | 0 | 0 | 0 | 0 | 10594.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503814 | S-WW-NI-131119-Port Rodie SPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-03-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 28238.59 | 1674.77 | 29913.36 | 0 | 0 | 0 | 29913.36 | 0 | 0 | 0 | 0 | 29913.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503822 | S-WW-NI-131119-ST ABBS NORTH SPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-05-20 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2424.5 | 0 | 2424.5 | 0 | 0 | 0 | 2424.5 | 0 | 0 | 0 | 0 | 2424.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503815 | S-WW-NI-131119-Troqueer WWTW-Klampress Belt Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-20 |  | 2020-01-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 13151.27 | 693.46 | 13844.73 | 0 | 0 | 0 | 13844.73 | 0 | 0 | 0 | 0 | 13844.73 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503812 | S-WW-NI-13112019-Dalscone WWTW-Refurb Scraper Supports | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2019-12-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 4456.16 | 287.85 | 4744.01 | 0 | 0 | 0 | 4744.01 | 0 | 0 | 0 | 0 | 4744.01 | 90601.29 | [5 empty] | N | CM_WWI | 100%
509775 | S-WW-NI-131120-Kevock WWPS-Replace submersible pumps 1 & 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-17 |  | 2021-02-10 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6103.58 | 6103.58 | -3.57 | 0 | 0 | 6100.01 | 0 | 0 | 0 | 0 | 6100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509780 | S-WW-NI-131120-Lockerbie WWTW-Replace chains with gate on bridge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-17 |  | 2021-03-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1424.48 | 1424.48 | 75.52 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509776 | S-WW-NI-1311210-East Linton WWTW-Replacement parts for the RAS pump on site | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-17 |  | 2020-03-12 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3152.68 | 3152.68 | 0 | 0 | 0 | 3152.68 | 0 | 0 | 0 | 0 | 3152.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504641 | S-WW-NI-140120-Daldowie WWTW-FST Gearbox Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-02-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1712.62 | 0 | 1712.62 | 0 | 0 | 0 | 1712.62 | 0 | 0 | 0 | 0 | 1712.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504639 | S-WW-NI-140120-Shotts WWTW-Refurb Anoxic Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-02-04 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1306.91 | 0 | 1306.91 | 0 | 0 | 0 | 1306.91 | 0 | 0 | 0 | 0 | 1306.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510702 | S-WW-NI-140121-Innerwick WWTW- Vacuumpump replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241.14 | 241.14 | 3177.56 | 0 | 0 | 3418.7 | 0 | 0 | 0 | 0 | 3418.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510697 | S-WW-NI-140121-Newton Stewart WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-15 |  | 2021-03-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11806.47 | 11806.47 | -192.6 | 0 | 0 | 11613.87 | 0 | 0 | 0 | 0 | 11613.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510698 | S-WW-NI-140121-Port Rodie WWPS-Refurb Pump A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19791.66 | 19791.66 | -291.66 | 0 | 0 | 19500 | 0 | 0 | 0 | 0 | 19500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510701 | S-WW-NI-140121-S Queensferry WWTW-Repair Gas Detection System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-15 |  | 2021-04-04 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5341.14 | 5341.14 | 77.56 | 0 | 0 | 5418.7 | 0 | 0 | 0 | 0 | 5418.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505191 | S-WW-NI-140220-Auchencairn SEP-Reinstate Grasscrete | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-09-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | -17.01 | 1882.99 | 0 | 0 | 0 | 1882.99 | 0 | 0 | 0 | 0 | 1882.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505205 | S-WW-NI-140220-Eyemouth WWTW-Replace Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-19 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | -1532.91 | 167.09 | 1532.91 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505194 | S-WW-NI-140220-Lilliesleaf WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -184.69 | 2315.31 | 0 | 0 | 0 | 2315.31 | 0 | 0 | 0 | 0 | 2315.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505202 | S-WW-NI-140220-Lockerbie WWTW-Filter Bed Access Steps & Handrailing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-19 |  | 2020-11-25 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | -79.27 | 9420.74 | 79.27 | 0 | 0 | 9500.01 | 0 | 0 | 0 | 0 | 9500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505196 | S-WW-NI-140220-Newcastleton WWTW-Replacement Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4740.5 | 43259.5 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 48000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506209 | S-WW-NI-14042020-Hamilton WWTTW-Replacement Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-07-10 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1917.77 | 1917.77 | 0 | 0 | 0 | 1917.77 | 0 | 0 | 0 | 0 | 1917.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507674 | S-WW-NI-140720-Clarencefield WWTW-Replace rotten guide rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-14 |  | 2020-08-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259.84 | 1259.84 | 0 | 0 | 0 | 1259.84 | 0 | 0 | 0 | 0 | 1259.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507669 | S-WW-NI-140720-Coursington WWTW-Investigation on SAS lines | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-14 |  | 2020-08-13 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7296.58 | 7296.58 | 0 | 0 | 0 | 7296.58 | 0 | 0 | 0 | 0 | 7296.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507667 | S-WW-NI-140720-Eaglesham WWTW-Replace the wires on bio-filter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-14 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1805.52 | 1805.52 | 94.48 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507672 | S-WW-NI-140720-Larg Rd CSO-Replacement Valves | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-07-14 |  | 2020-08-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1204.57 | 1204.57 | 0 | 0 | 0 | 1204.57 | 0 | 0 | 0 | 0 | 1204.57 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507681 | S-WW-NI-140720-Newton Stewart WWPS-Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-10-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2143.28 | 2143.28 | 0 | 0 | 0 | 2143.28 | 0 | 0 | 0 | 0 | 2143.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507677 | S-WW-NI-140720-Troqueer WWTW-DO Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-14 |  | 2020-08-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1330.04 | 1330.04 | 0 | 0 | 0 | 1330.04 | 0 | 0 | 0 | 0 | 1330.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508196 | S-WW-NI-140820-Philipshill WWTW-Replace damaged cabling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-14 |  | 2020-09-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6246.16 | 6246.16 | 0 | 0 | 0 | 6246.16 | 0 | 0 | 0 | 0 | 6246.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509254 | S-WW-NI-141020-Coalburn WWTW-Survey of storm screen to assess repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-29 |  | 2020-11-05 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3229.77 | 3229.77 | 0 | 0 | 0 | 3229.77 | 0 | 0 | 0 | 0 | 3229.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509265 | S-WW-NI-141020-Dalscone WWTW-Refurb Aerator Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-11-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6154.95 | 6154.95 | 0 | 0 | 0 | 6154.95 | 0 | 0 | 0 | 0 | 6154.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509267 | S-WW-NI-141020-Esk WWPS-Remove and replace 2 x impellers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-28 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6517.47 | 6517.47 | 82.53 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 6600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509261 | S-WW-NI-141020-Langside Road WWPS-Replace pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-28 |  | 2021-02-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3958.5 | 3958.5 | -58.5 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509257 | S-WW-NI-141020-Strathaven WWTW-RAS pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-28 |  | 2021-02-18 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3706.48 | 3706.48 | 93.52 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509256 | S-WW-NI-141020-Strathaven WWTW-Survey Pista Grit to bring online | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.6 | 203.6 | 2696.4 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509263 | S-WW-NI-141020-Troqueer STC-Spare Klampress Belts | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-10-23 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14071.96 | 14071.96 | 0 | 0 | 0 | 14071.96 | 0 | 0 | 0 | 0 | 14071.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510719 | S-WW-NI-150121-DALBEATTIE PORT STREET WWPS-Replace Impellor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-15 |  | 2021-04-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2649.41 | 2649.41 | -16.8 | 0 | 0 | 2632.61 | 0 | 0 | 0 | 0 | 2632.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510717 | S-WW-NI-150121-Eddleston WWTW-Geared motor for compactor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-15 |  | 2021-04-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1581.79 | 1581.79 | -67.88 | 0 | 0 | 1513.91 | 0 | 0 | 0 | 0 | 1513.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510726 | S-WW-NI-150121-Gorebridge WWTW-MD to oversee the installation and set up of the SAF | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2021-01-26 | 2021-02-02 | 2021-09-06 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126047.63 | 126047.63 | 94952.37 | 0 | 0 | 221000 | 0 | 0 | 0 | 0 | 221000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510715 | S-WW-NI-150121-Kelso WWTW-Repair access road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-01-26 | 2021-07-16 | 2021-09-27 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 926 | 926 | 34773.69 | 0 | 0 | 35699.69 | 0 | 0 | 0 | 0 | 35699.69 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510716 | S-WW-NI-150121-Reston WWTW-Supply hose reel for washdown | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.46 | 229.46 | 1379.88 | 0 | 0 | 1609.34 | 0 | 0 | 0 | 0 | 1609.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511238 | S-WW-NI-150221-Charlesfield WWPS-Replace pump no 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-23 |  | 2021-04-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2458.73 | 2458.73 | -58.75 | 0 | 0 | 2399.98 | 0 | 0 | 0 | 0 | 2399.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511218 | S-WW-NI-150221-Coldstream WWTW-Replace Sludge Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226.65 | 226.65 | 1473.35 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511246 | S-WW-NI-150221-Galashiels STC-Poly dosing booster pump no 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1297.34 | 1297.34 | -97.34 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511224 | S-WW-NI-150221-Hawick WWTW-Replace turbidity monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-23 |  | 2021-04-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2552.99 | 2552.99 | -53 | 0 | 0 | 2499.99 | 0 | 0 | 0 | 0 | 2499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506217 | S-WW-NI-15042020-Armadale Rd WWPS-Carry out repairs to leaks on pump discharge pipe on No1 pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-04-28 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4584.03 | 4584.03 | 0 | 0 | 0 | 4584.03 | 0 | 0 | 0 | 0 | 4584.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506218 | S-WW-NI-15042020-Moffat WWTW-Replace inlet penstock spindle nut | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-05-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2236.06 | 2236.06 | 0 | 0 | 0 | 2236.06 | 0 | 0 | 0 | 0 | 2236.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506216 | S-WW-NI-15042020-Penicuik Valleyfield Road No1 CSO-Replace hydraulic hose | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-01 |  | 2020-04-27 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559.09 | 1559.09 | 0 | 0 | 0 | 1559.09 | 0 | 0 | 0 | 0 | 1559.09 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506219 | S-WW-NI-15042020-Salsburgh WWTW-Refurb both SAF Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-01 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 599.56 | 599.56 | 8000.44 | 0 | 0 | 8600 | 0 | 0 | 0 | 0 | 8600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506223 | S-WW-NI-15042020-Slamannan WWTW-2No Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-04-23 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248.77 | 1248.77 | 0 | 0 | 0 | 1248.77 | 0 | 0 | 0 | 0 | 1248.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506630 | S-WW-NI-15052020-Cove WWTW-Blower Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-19 |  | 2020-06-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2782.16 | 2782.16 | 0 | 0 | 0 | 2782.16 | 0 | 0 | 0 | 0 | 2782.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506638 | S-WW-NI-150520-Port Edgar WWTW-Screen Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-19 |  | 2020-06-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8404.71 | 8404.71 | 0 | 0 | 0 | 8404.71 | 0 | 0 | 0 | 0 | 8404.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506634 | S-WW-NI-150520-Richie Camps WWTW-Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-05-20 | 2020-11-10 | 2021-05-14 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 14000 | 0 | 0 | 23000 | 0 | 0 | 0 | 0 | 23000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506640 | S-WW-NI-150520-Rockliffe WWTW-Replacement of Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-05-20 | 2020-09-18 | 2021-02-23 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49589.53 | 49589.53 | 0 | 0 | 0 | 49589.53 | 0 | 0 | 0 | 0 | 49589.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506642 | S-WW-NI-150520-Troqueer WWTW-H&S Tree Felling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-05-19 |  | 2021-05-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43416.57 | 43416.57 | 173.1 | 0 | 0 | 43589.67 | 0 | 0 | 0 | 0 | 43589.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507190 | S-WW-NI-150620-Clarencefield WWTW-Replace Inlet Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2826.92 | 2826.92 | 0 | 0 | 0 | 2826.92 | 0 | 0 | 0 | 0 | 2826.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507196 | S-WW-NI-150620-North Burn WWPS-panel cooling fan | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-06-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1265.16 | 1265.16 | 0 | 0 | 0 | 1265.16 | 0 | 0 | 0 | 0 | 1265.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507192 | S-WW-NI-150620-Troqueer WWTW-Handrailing and Gratings replacements on PST2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-10-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26775.57 | 26775.57 | 0 | 0 | 0 | 26775.57 | 0 | 0 | 0 | 0 | 26775.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507697 | S-WW-NI-150720-Bridgend WWTW-Safety issues | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-10-14 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8408.68 | 8408.68 | 0 | 0 | 0 | 8408.68 | 0 | 0 | 0 | 0 | 8408.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507691 | S-WW-NI-150720-Fauldhouse WWTW-Refurb Sludge Holding Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-09-30 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8091.61 | 8091.61 | 0 | 0 | 0 | 8091.61 | 0 | 0 | 0 | 0 | 8091.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507703 | S-WW-NI-150720-Loch Ryan WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-08-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6735.15 | 6735.15 | 0 | 0 | 0 | 6735.15 | 0 | 0 | 0 | 0 | 6735.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507710 | S-WW-NI-150720-Mauldslie WWTW-Replacement Parts for Site telemetry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-07-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88219.08 | 88219.08 | -85319.07 | 0 | 0 | 2900.01 | 0 | 0 | 0 | 0 | 2900.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507707 | S-WW-NI-150720-Ormiston WWTW-Install lifting equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-16 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336.45 | 336.45 | 4663.55 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507705 | S-WW-NI-150720-Ormiston WWTW-Refurbishment of the gearbox and motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-11-06 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4742.02 | 4742.02 | 0 | 0 | 0 | 4742.02 | 0 | 0 | 0 | 0 | 4742.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507687 | S-WW-NI-150720-Stonehouse WWTW-Critical Spares for Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-09-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5453.92 | 5453.92 | 0 | 0 | 0 | 5453.92 | 0 | 0 | 0 | 0 | 5453.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507685 | S-WW-NI-150720-Stonehouse WWTW-Modify NTF No2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-03-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8711.86 | 8711.86 | 0 | 0 | 0 | 8711.86 | 0 | 0 | 0 | 0 | 8711.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510326 | S-WW-NI-151220-Coalburn WWTW-Replace Heating & Lighting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1643.04 | 1643.04 | 56.96 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510334 | S-WW-NI-151220-Hamilton WWTW-Replace Inlet Screen Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2303.58 | 2303.58 | -3.57 | 0 | 0 | 2300.01 | 0 | 0 | 0 | 0 | 2300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511252 | S-WW-NI-160221-Eaglesfield WWTW-Replace steps -H & S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300.03 | 300.03 | 1199.95 | 0 | 0 | 1499.98 | 0 | 0 | 0 | 0 | 1499.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511255 | S-WW-NI-160221-Moffat WWTW-CSO screen motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-23 |  | 2021-04-03 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1531.09 | 1531.09 | -131.1 | 0 | 0 | 1399.99 | 0 | 0 | 0 | 0 | 1399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511809 | S-WW-NI-160321-Broughton WWTW-Replace pump no2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149.31 | 149.31 | 1200 | 0 | 0 | 1349.31 | 0 | 0 | 0 | 0 | 1349.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511829 | S-WW-NI-160321-Dunbar WWTW-Refurb the washwater pump 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2142.84 | 0 | 0 | 2306.39 | 0 | 0 | 0 | 0 | 2306.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511800 | S-WW-NI-160321-Dunnswood WWTW-repalce existing safety chains | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2057.16 | 0 | 0 | 2214.17 | 0 | 0 | 0 | 0 | 2214.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511806 | S-WW-NI-160321-Gretna WWTW-Replace sludge tank no1 valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.51 | 171.51 | 1114.26 | 0 | 0 | 1285.77 | 0 | 0 | 0 | 0 | 1285.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511813 | S-WW-NI-160321-Haddington WWTW-Replace Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1371.42 | 0 | 0 | 1476.09 | 0 | 0 | 0 | 0 | 1476.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511827 | S-WW-NI-160321-NEWTON SEP-MD to investigate cause of overland flows | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2021-03-19 | 2021-03-22 | 2022-05-23 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1544.67 | 1544.67 | 9000.04 | 0 | 0 | 10544.71 | 0 | 0 | 0 | 0 | 10544.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511816 | S-WW-NI-160321-Newton St Boswells WWTW-Repair stairs at inlet | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492.63 | 1492.63 | -92.63 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511822 | S-WW-NI-160321-Roslin WWTW-Repair H&S hazards | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1646.47 | 1646.47 | 53.53 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511802 | S-WW-NI-160321-Troqueer STC-Replace Rotation Sensor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339.28 | 339.28 | 1800 | 0 | 0 | 2139.28 | 0 | 0 | 0 | 0 | 2139.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512232 | S-WW-NI-160421- GALASHIELS WWTW NT513351 - Refurbish inlet screen compactor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-06 |  | 2021-07-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5299.98 | 0 | 0 | 5299.98 | 0 | 0 | 0 | 0 | 5299.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507218 | S-WW-NI-160620-Earlston WWTW-PST Sludge Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2098.27 | 2098.27 | 0 | 0 | 0 | 2098.27 | 0 | 0 | 0 | 0 | 2098.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507213 | S-WW-NI-160620-Stenton WWTW-Repair tracks to the works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-06-29 |  | 2020-10-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20487 | 20487 | 329.82 | 0 | 0 | 20816.82 | 0 | 0 | 0 | 0 | 20816.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507216 | S-WW-NI-160620-Tyninghame WWTW-Repair Tracks | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-06-29 |  | 2020-10-05 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14127.95 | 14127.95 | 0 | 0 | 0 | 14127.95 | 0 | 0 | 0 | 0 | 14127.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507721 | S-WW-NI-160720-Carronbridge SEP-Refub Access Rd | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-16 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241.14 | 241.14 | 3158.87 | 0 | 0 | 3400.01 | 0 | 0 | 0 | 0 | 3400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507740 | S-WW-NI-160720-Daldowie WWTW-Refurbish Gearbox for FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6304.04 | 6304.04 | 0 | 0 | 0 | 6304.04 | 0 | 0 | 0 | 0 | 6304.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507727 | S-WW-NI-160720-Loch Ryan WWTW-Refurb Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-16 |  | 2020-08-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7274.73 | 7274.73 | 0 | 0 | 0 | 7274.73 | 0 | 0 | 0 | 0 | 7274.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507736 | S-WW-NI-160720-Loch Ryan WWTW-Replacement Fans | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-10-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13276.75 | 13276.75 | 0 | 0 | 0 | 13276.75 | 0 | 0 | 0 | 0 | 13276.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507732 | S-WW-NI-160720-Newton Stewart WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-07-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5716.6 | 5716.6 | 0 | 0 | 0 | 5716.6 | 0 | 0 | 0 | 0 | 5716.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507719 | S-WW-NI-160720-Strathaven WWTW-Replace Inlet Auto Sampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-16 |  | 2020-09-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7488.94 | 7488.94 | 0 | 0 | 0 | 7488.94 | 0 | 0 | 0 | 0 | 7488.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507739 | S-WW-NI-160720-Troqueer STC-Replace existing conveyor belt | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3577.72 | 3577.72 | 0 | 0 | 0 | 3577.72 | 0 | 0 | 0 | 0 | 3577.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508773 | S-WW-NI-160920- STRATHAVEN WWTW NS706443 - Replace drive motor - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-16 |  | 2020-10-07 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1449.84 | 1449.84 | 0 | 0 | 0 | 1449.84 | 0 | 0 | 0 | 0 | 1449.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509301 | S-WW-NI-161020-Dalscone WWTW-Replace a Sensor on the RAS return rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-11-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1310.83 | 1310.83 | 0 | 0 | 0 | 1310.83 | 0 | 0 | 0 | 0 | 1310.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509296 | S-WW-NI-161020-Haddington WWTW-replacing lower bearing on screw pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-10-29 | 2021-03-22 | 2021-07-12 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509300 | S-WW-NI-161020-St Boswells WWTW-Extend spindles on sludge tank desludge valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1731.03 | 1731.03 | -131.03 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509298 | S-WW-NI-161020-Stepps WWPS-Repair rising main pipework in wet well | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2021-02-10 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2587.05 | 2587.05 | 12.95 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509303 | S-WW-NI-161020-Troqueer WWTW-Refurb Mechanical Main Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.15 | 134.15 | 1965.86 | 0 | 0 | 2100.01 | 0 | 0 | 0 | 0 | 2100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509795 | S-WW-NI-161120-Biggar WWTW-Upgrade washwater facility | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-11-24 | 2021-05-07 | 2021-09-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3228.92 | 3228.92 | 56771.08 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 60000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509799 | S-WW-NI-161120-Hendersyde SPS-Replace security fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-17 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1881.81 | 1881.81 | -81.81 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509796 | S-WW-NI-161120-Mauldslie WWTW-Replacement Gates to Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-17 |  | 2021-02-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600.49 | 1600.49 | -100.49 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509794 | S-WW-NI-161120-Swinstie Elevated Sewer-Access Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-11-24 | 2021-05-03 | 2021-07-13 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431.52 | 431.52 | 14568.45 | 0 | 0 | 14999.97 | 0 | 0 | 0 | 0 | 14999.97 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504356 | S-WW-NI-161219-Haddington WWTW-Hydraullic Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-16 |  | 2021-05-30 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 8578.8 | 12718.64 | 21297.44 | -2297.44 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 19000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504361 | S-WW-NI-161219-Maxwell Park Dalbeattie-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2019-12-16 |  | 2020-11-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 35700 | -8174.16 | 27525.85 | 13000 | 0 | 0 | 40525.85 | 0 | 0 | 0 | 0 | 40525.85 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504357 | S-WW-NI-161219-North Berwick WWTW-6 month Outfall Bouy Repair Checks | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2019-12-16 |  | 2020-05-21 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 17376.16 | 0 | 17376.16 | 0 | 0 | 0 | 17376.16 | 0 | 0 | 0 | 0 | 17376.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504359 | S-WW-NI-161219-Wester Dunnes WWPS-Install chamber over rising main and install an isolation valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2019-12-16 |  | 2021-03-23 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 7186.27 | 22186.27 | -7186.27 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510348 | S-WW-NI-161220-Dunnswood WWTW-To refurbish the concrete steps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.72 | 144.72 | 1855.28 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510350 | S-WW-NI-161220-Ecclefechan WWTW-Install pump kiosk on top level | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-04-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3792.8 | 3792.8 | 7.2 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510364 | S-WW-NI-161220-GRETNA IND EST WWPS-Replace deragger | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273.84 | 273.84 | 3626.16 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510368 | S-WW-NI-161220-Penicuik WWTW-Replace SBR feed pumps 1 & provide critical spare | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-24 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6984.64 | 6984.64 | 15.36 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 7000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504700 | S-WW-NI-17012020-Eastfield WWPS-Replacement DWF Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-06-05 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 12440.36 | 10191.45 | 22631.81 | 0 | 0 | 0 | 22631.81 | 0 | 0 | 0 | 0 | 22631.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504702 | S-WW-NI-17012020-Pathhead WWTW-Filterbed Centre Column Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-04-10 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 9611.15 | 0 | 9611.15 | 0 | 0 | 0 | 9611.15 | 0 | 0 | 0 | 0 | 9611.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504705 | S-WW-NI-170120-Annan WWTW-Repairs to Grit plant & pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-02-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 5455.8 | 0 | 5455.8 | 0 | 0 | 0 | 5455.8 | 0 | 0 | 0 | 0 | 5455.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504706 | S-WW-NI-170120-Carfin WWPS-Refurb Submersible Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-03-05 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2815.38 | 0 | 2815.38 | 0 | 0 | 0 | 2815.38 | 0 | 0 | 0 | 0 | 2815.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504701 | S-WW-NI-170120-Eastfield WWPS-Refurbish Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-08-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 7836.88 | 9078.47 | 16915.35 | 0 | 0 | 0 | 16915.35 | 0 | 0 | 0 | 0 | 16915.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504716 | S-WW-NI-170120-Gullane WWTW-Replacement FE Pump 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-21 |  | 2021-02-28 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 5315.92 | 4389.24 | 9705.16 | -5.16 | 0 | 0 | 9700 | 0 | 0 | 0 | 0 | 9700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504708 | S-WW-NI-170120-Hamilton WWTW-Critical Spare Grinder | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-05-05 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 8713.73 | 7659.41 | 16373.14 | 0 | 0 | 0 | 16373.14 | 0 | 0 | 0 | 0 | 16373.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504714 | S-WW-NI-170120-Hawick WWTW-Refurb Compactor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-21 |  | 2020-01-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 10892.88 | 0 | 10892.88 | 0 | 0 | 0 | 10892.88 | 0 | 0 | 0 | 0 | 10892.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504712 | S-WW-NI-170120-Kirkconnel WWTW-Modify Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-21 |  | 2020-01-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 9654.46 | 0 | 9654.46 | 0 | 0 | 0 | 9654.46 | 0 | 0 | 0 | 0 | 9654.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504718 | S-WW-NI-170120-North Berwick WWTW-Screen Critical Spares | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-21 |  | 2020-04-03 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 10613.93 | 0 | 10613.93 | 0 | 0 | 0 | 10613.93 | 0 | 0 | 0 | 0 | 10613.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505228 | S-WW-NI-170220-Galashiels STC-Digester Mixer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-06-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 32100 | 2607.11 | 34707.11 | 0 | 0 | 0 | 34707.11 | 0 | 0 | 0 | 0 | 34707.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505240 | S-WW-NI-170220-Galashiels WWTW-Replacement PST2 Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-02-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2896.69 | 147.58 | 3044.27 | 0 | 0 | 0 | 3044.27 | 0 | 0 | 0 | 0 | 3044.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505238 | S-WW-NI-170220-Granton WWPS-Replace pumps with Flygt pumps with a new VSD panel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-04-30 |  | 2021-05-30 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 61417.17 | 66417.17 | -200.44 | 0 | 0 | 66216.73 | 0 | 0 | 0 | 0 | 66216.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511286 | S-WW-NI-170221-New Galloway WWPS-Replace two pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6433.05 | 6433.05 | -133.05 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 6300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511282 | S-WW-NI-170221-Newton Stewart WWTW-Replace basket for screen 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-23 |  | 2021-04-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2956.19 | 2956.19 | -56.2 | 0 | 0 | 2899.99 | 0 | 0 | 0 | 0 | 2899.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511279 | S-WW-NI-170221-Philipshill WWTW-Replace 6x DO probes on site | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6492.65 | 6492.65 | 7.35 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511298 | S-WW-NI-170221-Port William Middle Sq WWPS-Replace both pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561.71 | 561.71 | 4938.3 | 0 | 0 | 5500.01 | 0 | 0 | 0 | 0 | 5500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511284 | S-WW-NI-170221-Torthorwald WWTW-Replace mesh cover & supports & spec clips | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.35 | 209.35 | 2990.65 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505782 | S-WW-NI-170320-Dunnswood WWTW-Replacement Inlet Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-04-08 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 132.33 | 1461.33 | 1593.66 | 0 | 0 | 0 | 1593.66 | 0 | 0 | 0 | 0 | 1593.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505778 | S-WW-NI-170320-Galashiels WWTW-Replacement Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-09-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 208.77 | 1359.36 | 1568.13 | 0 | 0 | 0 | 1568.13 | 0 | 0 | 0 | 0 | 1568.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505783 | S-WW-NI-170320-Hamilton WWTW-H&S Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-05-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 171.59 | 2046.38 | 2217.97 | 0 | 0 | 0 | 2217.97 | 0 | 0 | 0 | 0 | 2217.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505770 | S-WW-NI-170320-Lanark WWTW-Replacement Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-05-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 1111 | 1189.5 | 0 | 0 | 0 | 1189.5 | 0 | 0 | 0 | 0 | 1189.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505780 | S-WW-NI-170320-Linthaugh WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-05-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 209.35 | 2511.94 | 2721.29 | 0 | 0 | 0 | 2721.29 | 0 | 0 | 0 | 0 | 2721.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505768 | S-WW-NI-170320-Lockerbie WWTW-Filter Bed Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-06-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 2087.09 | 2231.02 | 0 | 0 | 0 | 2231.02 | 0 | 0 | 0 | 0 | 2231.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505765 | S-WW-NI-170320-MILLDOWN WWPS-installing spindles within the Hydro Brake chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-06-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 228.4 | 1622.12 | 1850.52 | 0 | 0 | 0 | 1850.52 | 0 | 0 | 0 | 0 | 1850.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505772 | S-WW-NI-170320-Reston WWTW-move blowers and associated pipework away from the SAF unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-03-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2121.9 | 9.24 | 2131.14 | 0 | 0 | 0 | 2131.14 | 0 | 0 | 0 | 0 | 2131.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511869 | S-WW-NI-170321-Eastriggs WWTW-Refurbish inlet screen motor & gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9834.63 | 9834.63 | -134.63 | 0 | 0 | 9700 | 0 | 0 | 0 | 0 | 9700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511875 | S-WW-NI-170321-Joppa WWTW-MD scope and quote for control panel replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-24 | 2021-09-24 | 2022-05-09 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000.04 | 0 | 0 | 5000.04 | 0 | 0 | 0 | 0 | 5000.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511853 | S-WW-NI-170321-Lochmaben WWTW-Wall Head Plating | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-17 |  | 2021-06-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692.55 | 692.55 | 6428.58 | 0 | 0 | 7121.13 | 0 | 0 | 0 | 0 | 7121.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511863 | S-WW-NI-170321-Lockerbie WWTW-refurbish filter beb no1 column | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341.85 | 341.85 | 2400 | 0 | 0 | 2741.85 | 0 | 0 | 0 | 0 | 2741.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511866 | S-WW-NI-170321-Moffat WWTW-Replace filter arm end caps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302.35 | 302.35 | 2828.58 | 0 | 0 | 3130.93 | 0 | 0 | 0 | 0 | 3130.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511874 | S-WW-NI-170321-Ormiston WWTW-MD scope and quote for control panel replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-24 | 2021-09-24 | 2022-05-09 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000.04 | 0 | 0 | 5000.04 | 0 | 0 | 0 | 0 | 5000.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511879 | S-WW-NI-170321-Port Rodie WWPS-Investigate issues at Pumping Station | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-24 | 2021-09-24 | 2022-05-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230.88 | 230.88 | 9999.99 | 0 | 0 | 10230.87 | 0 | 0 | 0 | 0 | 10230.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511857 | S-WW-NI-170321-Port Rodie WWPS-Refurb Pump C | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-06-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288.36 | 288.36 | 14411.64 | 0 | 0 | 14700 | 0 | 0 | 0 | 0 | 14700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511871 | S-WW-NI-170321-Selkirk WWTW-Structural survey of storm tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-24 | 2021-09-24 | 2022-05-09 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115.44 | 115.44 | 5000.04 | 0 | 0 | 5115.48 | 0 | 0 | 0 | 0 | 5115.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511855 | S-WW-NI-170321-Troqueer STC-Refurb FE Booster pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.89 | 215.89 | 2828.58 | 0 | 0 | 3044.47 | 0 | 0 | 0 | 0 | 3044.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506264 | S-WW-NI-17042020-Newton St Boswells WWTW-scraper repairs and spindle & valve replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-05-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2645.95 | 2645.95 | 0 | 0 | 0 | 2645.95 | 0 | 0 | 0 | 0 | 2645.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506246 | S-WW-NI-17042020-Troqueer STC-supply and fit Stainless steel diverter plates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-12 |  | 2020-06-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2005.41 | 2005.41 | 0 | 0 | 0 | 2005.41 | 0 | 0 | 0 | 0 | 2005.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507245 | S-WW-NI-170620-Allers WWTW-Refurb NTF Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-31 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5136.72 | 5136.72 | 0 | 0 | 0 | 5136.72 | 0 | 0 | 0 | 0 | 5136.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507246 | S-WW-NI-170620-Hamilton WWTW-Refurb Storm Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-29 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22492.78 | 22492.78 | 7.22 | 0 | 0 | 22500 | 0 | 0 | 0 | 0 | 22500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507239 | S-WW-NI-170620-Kirkcudbright WWTW-Refurb Storm return pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19165.98 | 19165.98 | 0 | 0 | 0 | 19165.98 | 0 | 0 | 0 | 0 | 19165.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507241 | S-WW-NI-170620-Mosside WWPS-Supply of critical spare grinder | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-09-08 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14006.7 | 14006.7 | 0 | 0 | 0 | 14006.7 | 0 | 0 | 0 | 0 | 14006.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507243 | S-WW-NI-170620-Philipshill WWTW-Refurb Bearing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-08-05 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5457.78 | 5457.78 | 0 | 0 | 0 | 5457.78 | 0 | 0 | 0 | 0 | 5457.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507234 | S-WW-NI-170620-Swinton WWTW-Building Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-11-09 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4539.4 | 4539.4 | 0 | 0 | 0 | 4539.4 | 0 | 0 | 0 | 0 | 4539.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507237 | S-WW-NI-170620-Troqueer WWTW-Install Kicker Plates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3478.09 | 3478.09 | 0 | 0 | 0 | 3478.09 | 0 | 0 | 0 | 0 | 3478.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507230 | S-WW-NI-170620-Troqueer WWTW-Replacement actuator on FST 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-10-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7129.54 | 7129.54 | 0 | 0 | 0 | 7129.54 | 0 | 0 | 0 | 0 | 7129.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507756 | S-WW-NI-170720-9 Bothwellpark Road-Customer Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-07-20 |  | 2020-10-05 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43198.72 | 43198.72 | 0 | 0 | 0 | 43198.72 | 0 | 0 | 0 | 0 | 43198.72 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507744 | S-WW-NI-170720-Bothwellbank WWTW-Refurbish Sludge tank mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4098.76 | 4098.76 | 0 | 0 | 0 | 4098.76 | 0 | 0 | 0 | 0 | 4098.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507749 | S-WW-NI-170720-Dalmeny WWTW-install hinged grating | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-12 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160.85 | 2160.85 | 0 | 0 | 0 | 2160.85 | 0 | 0 | 0 | 0 | 2160.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507745 | S-WW-NI-170720-Dunbar WWTW-Investigate Sludge Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-07-20 |  | 2021-03-10 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 6000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507755 | S-WW-NI-170720-Dunbar WWTW-Repair Railings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-10 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1186.8 | 1186.8 | 0 | 0 | 0 | 1186.8 | 0 | 0 | 0 | 0 | 1186.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507751 | S-WW-NI-170720-Eddleston WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6911.27 | 6911.27 | -5211.27 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507753 | S-WW-NI-170720-Gorebridge WWTW-Replace Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-14 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1529.02 | 1529.02 | 0 | 0 | 0 | 1529.02 | 0 | 0 | 0 | 0 | 1529.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507750 | S-WW-NI-170720-North Berwick WWTW-Replace inlet pump 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-10-22 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14097.54 | 14097.54 | 0 | 0 | 0 | 14097.54 | 0 | 0 | 0 | 0 | 14097.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507748 | S-WW-NI-170720-Troqueer WWTW-Refit guards & fabricate dummy screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-17 |  | 2020-08-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2118.43 | 2118.43 | 0 | 0 | 0 | 2118.43 | 0 | 0 | 0 | 0 | 2118.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508210 | S-WW-NI-170820-POND HALL WWPS NT408760 - REPLACE 3X PUMPS REPLACE GUIDE RAILS - 7.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-17 |  | 2020-09-25 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7568.71 | 7568.71 | 0 | 0 | 0 | 7568.71 | 0 | 0 | 0 | 0 | 7568.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509840 | S-WW-NI-171120-Bothwellbank WWTW-Repair Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-17 |  | 2021-02-10 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2453.72 | 2453.72 | -53.72 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509830 | S-WW-NI-171120-Coldstream WWTW-Aerator Motor and Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-17 |  | 2021-02-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2178.3 | 2178.3 | 21.7 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509852 | S-WW-NI-171120-Crawford SEP-Replace Flooring | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-17 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748.6 | 748.6 | 10551.4 | 0 | 0 | 11300 | 0 | 0 | 0 | 0 | 11300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509851 | S-WW-NI-171120-Cuckoo Retail WWPS-Supply and fit fall protection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-17 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153.28 | 153.28 | 2046.72 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509828 | S-WW-NI-171120-Langholm WWTW-Refurbish outlet auto sampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-17 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1854.22 | 1854.22 | 45.78 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509835 | S-WW-NI-171120-Lauder WWTW-RAS Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-17 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1239.4 | 1239.4 | 60.6 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504385 | S-WW-NI-171219-Mauldslie WWTW-Replace Rotork Actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-18 |  | 2020-01-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1347.59 | 0 | 1347.59 | 0 | 0 | 0 | 1347.59 | 0 | 0 | 0 | 0 | 1347.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510402 | S-WW-NI-171220-Eastfield WWPS-Engineers to investigate the issues with the 2 ABB flow meters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.56 | 120.56 | 1579.44 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510406 | S-WW-NI-171220-Fauldhouse WWTW-Carry out patch repairs to access road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2704.24 | 2704.24 | -104.24 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510390 | S-WW-NI-171220-Galashiels STC-Digester feed pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5792.86 | 5792.86 | -392.85 | 0 | 0 | 5400.01 | 0 | 0 | 0 | 0 | 5400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510383 | S-WW-NI-171220-Harthill WWTW-Replacement Screen Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5286.41 | 5286.41 | 3671.59 | 0 | 0 | 8958 | 0 | 0 | 0 | 0 | 8958 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510386 | S-WW-NI-171220-Lockerbie WWTW-Refurbish Pump no2 and NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319.64 | 319.64 | 4280.37 | 0 | 0 | 4600.01 | 0 | 0 | 0 | 0 | 4600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510396 | S-WW-NI-171220-Ormiston WWTW-Install a concrete hardstanding storage | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-04-02 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1944.72 | 1944.72 | 55.28 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510404 | S-WW-NI-171220-Pencaitland WWTW-Replacememt Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-27 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500.94 | 3500.94 | -0.94 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510380 | S-WW-NI-171220-Town Yetholm WWTW-Repair Fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4481.82 | 4481.82 | -781.82 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 3700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510748 | S-WW-NI-180121-Caddonfoot WWTW-Refurb Washwater Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-28 |  | 2021-03-08 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1419.49 | 1419.49 | 80.52 | 0 | 0 | 1500.01 | 0 | 0 | 0 | 0 | 1500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510744 | S-WW-NI-180121-Dalscone WWTW-Refurbish the access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-28 |  | 2021-03-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2421.55 | 2421.55 | 78.44 | 0 | 0 | 2499.99 | 0 | 0 | 0 | 0 | 2499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510746 | S-WW-NI-180121-Eyemouth WWTW-Replace decant SBR decant valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-28 |  | 2021-03-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1313.59 | 1313.59 | 86.4 | 0 | 0 | 1399.99 | 0 | 0 | 0 | 0 | 1399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511312 | S-WW-NI-180221-Coldstream WWTW-Refurbish Old Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4027.12 | 4027.12 | -27.12 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511311 | S-WW-NI-180221-Galashiels WWTW-Repair concrete area surrounding septic tank screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5028.64 | 5028.64 | 71.36 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 5100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511314 | S-WW-NI-180221-Haddington WWTW-Supply and installation of replacement anti-flood pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340.19 | 340.19 | 4859.8 | 0 | 0 | 5199.99 | 0 | 0 | 0 | 0 | 5199.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511319 | S-WW-NI-180221-Troqueer WWTW-Replace the thermocouple for limits on FST3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280.4 | 280.4 | 919.6 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511898 | S-WW-NI-180321-Albert Rd WWPS-Inspect the screw gearboxes 3No to establish their condition | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614.95 | 614.95 | 8057.16 | 0 | 0 | 8672.11 | 0 | 0 | 0 | 0 | 8672.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511901 | S-WW-NI-180321-Albert Rd WWPS-Removal & refurb of storm screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1746.73 | 1746.73 | 24953.27 | 0 | 0 | 26700 | 0 | 0 | 0 | 0 | 26700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511920 | S-WW-NI-180321-Annan WWTW-Refurbish coarse screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2188.62 | 2188.62 | -88.62 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511894 | S-WW-NI-180321-Athelstaneford WWTW-Repairs to screening unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562.62 | 562.62 | 7371.42 | 0 | 0 | 7934.04 | 0 | 0 | 0 | 0 | 7934.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511915 | S-WW-NI-180321-Dalbeatie WWTW-Replace Washwater pipework after bursting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.22 | 136.22 | 1028.58 | 0 | 0 | 1164.8 | 0 | 0 | 0 | 0 | 1164.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511909 | S-WW-NI-180321-Eastriggs WWTW-New handrails and fencing to final tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875.73 | 875.73 | 8828.58 | 0 | 0 | 9704.31 | 0 | 0 | 0 | 0 | 9704.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511916 | S-WW-NI-180321-Forthill WWPS-Install 2 spare pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310.54 | 310.54 | 1800 | 0 | 0 | 2110.54 | 0 | 0 | 0 | 0 | 2110.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511893 | S-WW-NI-180321-Haddington WWTW-Repairs to screening unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5057.16 | 0 | 0 | 5443.14 | 0 | 0 | 0 | 0 | 5443.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511912 | S-WW-NI-180321-Kirkcudbright WWTW-Replace FE Pump B Coupling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205.62 | 205.62 | 1371.42 | 0 | 0 | 1577.04 | 0 | 0 | 0 | 0 | 1577.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511905 | S-WW-NI-180321-Prestonpans WWPS-Replace & install storm pump 4 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2105.63 | 2105.63 | 29794.38 | 0 | 0 | 31900 | 0 | 0 | 0 | 0 | 31900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511919 | S-WW-NI-180321-St Abbs South WWPS-install 2 spare pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271.29 | 271.29 | 1285.74 | 0 | 0 | 1557.03 | 0 | 0 | 0 | 0 | 1557.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506664 | S-WW-NI-18052020-Dalscone WWTW-refurbishment of outfall valve and Rotork actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-19 |  | 2020-05-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2141.35 | 2141.35 | 0 | 0 | 0 | 2141.35 | 0 | 0 | 0 | 0 | 2141.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507262 | S-WW-NI-180620-Airds Point STW-Structural Survey and Remedial Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-06-25 |  | 2021-06-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75336 | 75336 | 89664.31 | 0 | 0 | 165000.31 | 0 | 0 | 0 | 0 | 165000.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507249 | S-WW-NI-180620-Daldowie WWTW-Odour Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-09-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810.67 | 3810.67 | 0 | 0 | 0 | 3810.67 | 0 | 0 | 0 | 0 | 3810.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507266 | S-WW-NI-180620-North Berwick WWTW-scope up and cost the replacement of the three inlet screens | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-06-25 |  | 2021-07-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10478.92 | 10478.92 | 19521.09 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503853 | S-WW-NI-181119-Dalry WWTW-Rotork Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1743.73 | 0 | 1743.73 | 0 | 0 | 0 | 1743.73 | 0 | 0 | 0 | 0 | 1743.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503843 | S-WW-NI-181119-Rigside WWTW-Replacement Brackets | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-05-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2112.84 | 0 | 2112.84 | 0 | 0 | 0 | 2112.84 | 0 | 0 | 0 | 0 | 2112.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503845 | S-WW-NI-181119-Shotts WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2019-12-06 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1614.51 | 0 | 1614.51 | 0 | 0 | 0 | 1614.51 | 0 | 0 | 0 | 0 | 1614.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503852 | S-WW-NI-181119-Swinstie WWTW-Refurb Desludge Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-02 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 4244.68 | 0 | 4244.68 | 0 | 0 | 0 | 4244.68 | 0 | 0 | 0 | 0 | 4244.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503842 | S-WW-NI-181119-Swinstie WWTW-Replacement MCC Component | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-05-20 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1089.2 | 0 | 1089.2 | 0 | 0 | 0 | 1089.2 | 0 | 0 | 0 | 0 | 1089.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503850 | S-WW-NI-181119-Troqueer WWTW-Blower Diaphragm Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1392.14 | 18.7 | 1410.84 | 0 | 0 | 0 | 1410.84 | 0 | 0 | 0 | 0 | 1410.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503848 | S-WW-NI-181119-Troqueer WWTW-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2108.65 | 18.7 | 2127.35 | 0 | 0 | 0 | 2127.35 | 0 | 0 | 0 | 0 | 2127.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503847 | S-WW-NI-181119-Wanlockhead WWTW-Replacement Do Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-11-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1451.75 | 18.7 | 1470.45 | 0 | 0 | 0 | 1470.45 | 0 | 0 | 0 | 0 | 1470.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509871 | S-WW-NI-181120-Annan WWTW-Replace rusted handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-24 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101.26 | 2101.26 | -1.26 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509869 | S-WW-NI-181120-Broughton WWPS-Replace pump guide rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-24 |  | 2020-04-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331.01 | 1331.01 | 0 | 0 | 0 | 1331.01 | 0 | 0 | 0 | 0 | 1331.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509874 | S-WW-NI-181120-Mosside WWPS-Repairs to handrailing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-03-04 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1888.59 | 1888.59 | -88.59 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509863 | S-WW-NI-181120-Newton Stewart WWTW-Replacement geared motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-24 |  | 2020-10-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2749.5 | 2749.5 | 0 | 0 | 0 | 2749.5 | 0 | 0 | 0 | 0 | 2749.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504398 | S-WW-NI-181219-Bothwellbank WWTW-Refurbish Sludge Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-18 |  | 2020-02-08 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 3415.56 | 16 | 3431.56 | 0 | 0 | 0 | 3431.56 | 0 | 0 | 0 | 0 | 3431.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504402 | S-WW-NI-181219-Galashiels STC-Thickened Sludge Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | -5869.38 | 430.62 | 5869.38 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 6300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504405 | S-WW-NI-181219-Gretna WWTW-Refurb Sludge Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-02-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3952.37 | 0 | 3952.37 | 0 | 0 | 0 | 3952.37 | 0 | 0 | 0 | 0 | 3952.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504407 | S-WW-NI-181219-Gretna WWTW-Replacement Pump panels & VSD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-06-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | -34.8 | 8465.2 | 0 | 0 | 0 | 8465.2 | 0 | 0 | 0 | 0 | 8465.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504410 | S-WW-NI-181219-Hamilton WWTW-Internal lining of the sludge holding tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-06-29 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 22128.14 | 102128.14 | 0 | 0 | 0 | 102128.14 | 0 | 0 | 0 | 0 | 102128.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504396 | S-WW-NI-181219-Philipshill WWTW-Replacement Rotork for Storm Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-18 |  | 2020-02-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1262.31 | 0 | 1262.31 | 0 | 0 | 0 | 1262.31 | 0 | 0 | 0 | 0 | 1262.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504413 | S-WW-NI-181219-Shotts WWTW-Replacement Showers & Toilets | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-01-22 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 4022.9 | -0.01 | 4022.89 | 277.11 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504394 | S-WW-NI-181219-Skellyton WWTW-Refurbish Storm Screen Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-18 |  | 2020-01-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2140.6 | 0 | 2140.6 | 0 | 0 | 0 | 2140.6 | 0 | 0 | 0 | 0 | 2140.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504401 | S-WW-NI-181219-South Queensferry WWTW-Tank Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-07-06 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 10700 | -4298.64 | 6401.36 | 0 | 0 | 0 | 6401.36 | 0 | 0 | 0 | 0 | 6401.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510418 | S-WW-NI-181220-Annan WWTW-Repair sludge tank no2 holes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2381.73 | 2381.73 | 18.27 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510414 | S-WW-NI-181220-Armadale WWTW-Repairs to Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2592.87 | 2592.87 | -92.87 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510428 | S-WW-NI-181220-Galashiels STC-sludge tank pump pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110.3 | 110.3 | 1289.71 | 0 | 0 | 1400.01 | 0 | 0 | 0 | 0 | 1400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510431 | S-WW-NI-181220-High Street Kirkcudbright-Connect Surface water to Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-12-24 | 2021-05-10 | 2021-07-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 1450 | 28050 | 0 | 0 | 29500 | 0 | 0 | 0 | 0 | 29500 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510421 | S-WW-NI-181220-Loch Ryan WWTW-Replace Lights and Bollard | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-18 |  | 2021-02-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1958.32 | 1958.32 | 41.68 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510423 | S-WW-NI-181220-Moffat WWTW- FST 2 Replace bridge wheels | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-18 |  | 2021-02-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1926.12 | 1926.12 | 73.88 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510424 | S-WW-NI-181220-Moffat WWTW-Refurbish Wash water for inlet screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-04 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1660.51 | 1660.51 | 39.49 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510429 | S-WW-NI-181220-Troqueer WWTW-Engage M2 to carry out a Hydraulic Survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-12-24 | 2021-06-21 | 2022-02-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431 | 431 | 9569.2 | 0 | 0 | 10000.2 | 0 | 0 | 0 | 0 | 10000.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510773 | S-WW-NI-190121-Dalscone Old WWTW-Refurb pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-28 |  | 2021-04-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1522.35 | 1522.35 | 77.64 | 0 | 0 | 1599.99 | 0 | 0 | 0 | 0 | 1599.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510762 | S-WW-NI-190121-Galashiels STC-Temperature sensor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042.72 | 2042.72 | 57.24 | 0 | 0 | 2099.96 | 0 | 0 | 0 | 0 | 2099.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510759 | S-WW-NI-190121-Hamilton SPS Muir-Replace doors - Fire safety | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2124.8 | 2124.8 | 17.92 | 0 | 0 | 2142.72 | 0 | 0 | 0 | 0 | 2142.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505282 | S-WW-NI-190220-Bothwellbank WWTW-Repair Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-04-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 339.03 | 4509.19 | 4848.22 | 0 | 0 | 0 | 4848.22 | 0 | 0 | 0 | 0 | 4848.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505284 | S-WW-NI-190220-Galashiels STC-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-03-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 8093.41 | 0 | 8093.41 | 0 | 0 | 0 | 8093.41 | 0 | 0 | 0 | 0 | 8093.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505286 | S-WW-NI-190220-Galashiels STC-Sludge Pump Shelter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-08-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 440.44 | 4588 | 5028.43 | 0 | 0 | 0 | 5028.43 | 0 | 0 | 0 | 0 | 5028.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505300 | S-WW-NI-190220-Gretna WWTW-Replacement Monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-04-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 247.44 | 3306.8 | 3554.24 | 0 | 0 | 0 | 3554.24 | 0 | 0 | 0 | 0 | 3554.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505295 | S-WW-NI-190220-Shotts WWTW-Refurb Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-03-25 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 4030.3 | 316.13 | 4346.43 | 0 | 0 | 0 | 4346.43 | 0 | 0 | 0 | 0 | 4346.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505291 | S-WW-NI-190220-Swinstie WWTW-Screen Compactor Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-19 |  | 2020-04-14 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 7706.12 | 64.59 | 7770.71 | 0 | 0 | 0 | 7770.71 | 0 | 0 | 0 | 0 | 7770.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511357 | S-WW-NI-190221-Marine Parade WWPS-Replace pump no1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-23 |  | 2021-03-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636.87 | 1636.87 | -36.85 | 0 | 0 | 1600.02 | 0 | 0 | 0 | 0 | 1600.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505817 | S-WW-NI-190320-Blackridge WWTW-Refurb Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-04-30 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 464.49 | 6511.6 | 6976.09 | 0 | 0 | 0 | 6976.09 | 0 | 0 | 0 | 0 | 6976.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505810 | S-WW-NI-190320-Bothwellbank WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-05-04 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 132.33 | 1451.94 | 1584.27 | 0 | 0 | 0 | 1584.27 | 0 | 0 | 0 | 0 | 1584.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505811 | S-WW-NI-190320-Chapelton WWTW-Replace inlet penstock actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-08-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 2444.47 | 2529.52 | 0 | 0 | 0 | 2529.52 | 0 | 0 | 0 | 0 | 2529.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505823 | S-WW-NI-190320-Dunbar WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-04-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 2533.03 | 18.47 | 2551.5 | 0 | 0 | 0 | 2551.5 | 0 | 0 | 0 | 0 | 2551.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505824 | S-WW-NI-190320-Eaglesham WWTW-Installation of Handrailing around unprotected edge at FST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 217.38 | 9.24 | 226.62 | 2673.39 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505827 | S-WW-NI-190320-Ladywell SPS-2No Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-06-25 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 465.98 | 6267.45 | 6733.43 | 0 | 0 | 0 | 6733.43 | 0 | 0 | 0 | 0 | 6733.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505826 | S-WW-NI-190320-Lauder WWTW-H&S Handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-03-19 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 875.49 | 9630.5 | 10505.99 | 0 | 0 | 0 | 10505.99 | 0 | 0 | 0 | 0 | 10505.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505814 | S-WW-NI-190320-NEWTOWN ST BOSWELLS WWTW-Replacement of the spool valves on the sprinkler arm drives | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-05-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 202.23 | 1306.21 | 1508.44 | 0 | 0 | 0 | 1508.44 | 0 | 0 | 0 | 0 | 1508.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505815 | S-WW-NI-190320-Shotts WWTW-Supply and Fit Handrails H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-10-15 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 184.67 | 2253.88 | 2438.55 | 0 | 0 | 0 | 2438.55 | 0 | 0 | 0 | 0 | 2438.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505816 | S-WW-NI-190320-Stonehouse WWTW-Replace motor on NTF with better IP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-04-21 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 1727.31 | 1851.61 | 0 | 0 | 0 | 1851.61 | 0 | 0 | 0 | 0 | 1851.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505820 | S-WW-NI-190320-Strathaven WWTW-Refurb Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-04-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 2643.85 | 2833.57 | 0 | 0 | 0 | 2833.57 | 0 | 0 | 0 | 0 | 2833.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511930 | S-WW-NI-190321-Bathgate WWTW-Replace the site autosampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-19 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935.94 | 1935.94 | -35.94 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511926 | S-WW-NI-190321-Eccles WWTW-Valve Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-19 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193.94 | 193.94 | 1028.58 | 0 | 0 | 1222.52 | 0 | 0 | 0 | 0 | 1222.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511928 | S-WW-NI-190321-Lanark WWTW-Replace the actuators of the FST desludge valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2142.84 | 0 | 0 | 2306.39 | 0 | 0 | 0 | 0 | 2306.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511927 | S-WW-NI-190321-Newcastleton WWTW-Replace washwater pump no1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-19 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142.77 | 142.77 | 1114.26 | 0 | 0 | 1257.03 | 0 | 0 | 0 | 0 | 1257.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511934 | S-WW-NI-190321-Ormiston WWTW-To supply and install sections of railings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-19 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2314.26 | 0 | 0 | 2490.9 | 0 | 0 | 0 | 0 | 2490.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511929 | S-WW-NI-190321-Swinstie WWTW-Provide replacement DO probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-19 |  | 2021-06-19 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1114.26 | 0 | 0 | 1199.31 | 0 | 0 | 0 | 0 | 1199.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506700 | S-WW-NI-19052020-Carbarns WWTW-PST Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-07-26 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2531.81 | 2531.81 | 0 | 0 | 0 | 2531.81 | 0 | 0 | 0 | 0 | 2531.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506695 | S-WW-NI-19052020-Clyde Valley WWPS-Install NRV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-05-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190.12 | 1190.12 | 0 | 0 | 0 | 1190.12 | 0 | 0 | 0 | 0 | 1190.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506688 | S-WW-NI-19052020-Nethernburn WWPS-Lifitng Equipment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-09-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6868.32 | 6868.32 | 0 | 0 | 0 | 6868.32 | 0 | 0 | 0 | 0 | 6868.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506682 | S-WW-NI-190520-Strathaven WWTW-Replacement Guide Rails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7667.35 | 7667.35 | 0 | 0 | 0 | 7667.35 | 0 | 0 | 0 | 0 | 7667.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507278 | S-WW-NI-190620-CUMMERTREES SEP-Replace the septic tank lids | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-25 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140.19 | 140.19 | 1859.81 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507273 | S-WW-NI-190620-Kirkton WWTW-Install Stand Pipe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-07-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943.05 | 1943.05 | 0 | 0 | 0 | 1943.05 | 0 | 0 | 0 | 0 | 1943.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507272 | S-WW-NI-190620-Lochans WWTW-Replacement Path | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-25 |  | 2021-03-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2360.91 | 2360.91 | -260.91 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507270 | S-WW-NI-190620-West Linton WWPS-Replace raw sewage transfer pump B | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-08-03 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1874.38 | 1874.38 | 0 | 0 | 0 | 1874.38 | 0 | 0 | 0 | 0 | 1874.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503859 | S-WW-NI-191119-Bridgend WWTW-Fabrication Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-03-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 16315.4 | 18.7 | 16334.1 | 0 | 0 | 0 | 16334.1 | 0 | 0 | 0 | 0 | 16334.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503866 | S-WW-NI-191119-Cockenzie WWPS-Replacement Hydranger Monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2021-05-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | -1476.63 | 123.38 | 1476.63 | 0 | 0 | 1600.01 | 0 | 0 | 0 | 0 | 1600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503863 | S-WW-NI-191119-Eastfield WWPS-Replacement Fan | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-01-23 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 4081.66 | 0 | 4081.66 | 0 | 0 | 0 | 4081.66 | 0 | 0 | 0 | 0 | 4081.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503857 | S-WW-NI-191119-Gordon WWTW-H&S Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1845.95 | 230.88 | 2076.83 | 0 | 0 | 0 | 2076.83 | 0 | 0 | 0 | 0 | 2076.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503869 | S-WW-NI-191119-Kelso WWTW-Refurb Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-25 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | -1028.04 | 71.96 | 1028.04 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503870 | S-WW-NI-191119-Lochmaben WWTW-Refurb Faulty MLSS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-02-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1311.14 | 0 | 1311.14 | 0 | 0 | 0 | 1311.14 | 0 | 0 | 0 | 0 | 1311.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503867 | S-WW-NI-191119-Tyneholm WWPS-Replacement Impellor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-01-13 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1638.95 | 18.7 | 1657.65 | 0 | 0 | 0 | 1657.65 | 0 | 0 | 0 | 0 | 1657.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509881 | S-WW-NI-191120-Allers WWTW-Washwater Pump Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-02-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9569.04 | 9569.04 | 30.97 | 0 | 0 | 9600.01 | 0 | 0 | 0 | 0 | 9600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509895 | S-WW-NI-191120-Earlston WWTW-Replace sludge tank valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.8 | 345.8 | 4654.2 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509891 | S-WW-NI-191120-Galashiels WWTW-Cover for Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269.87 | 269.87 | 2830.13 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509886 | S-WW-NI-191120-Lockerbie WWTW-Refurbish filter no. 3 centre column | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-03-13 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2796.14 | 2796.14 | 3.87 | 0 | 0 | 2800.01 | 0 | 0 | 0 | 0 | 2800.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509884 | S-WW-NI-191120-Sandford WWTW-Replace Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-03-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7173.66 | 7173.66 | 26.35 | 0 | 0 | 7200.01 | 0 | 0 | 0 | 0 | 7200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504429 | S-WW-NI-191219-Eastfield WWPS-Replacement GRP Cover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-01-16 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 2291.71 | -0.01 | 2291.7 | 0 | 0 | 0 | 2291.7 | 0 | 0 | 0 | 0 | 2291.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504436 | S-WW-NI-191219-Eastfield WWPS-VSD Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-01-09 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3949.46 | 0 | 3949.46 | 0 | 0 | 0 | 3949.46 | 0 | 0 | 0 | 0 | 3949.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504431 | S-WW-NI-191219-Philipshill WWTW-Install Handrailing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2019-12-23 |  | 2020-07-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 105784.53 | 94944.08 | 200728.61 | 0 | 0 | 0 | 200728.61 | 0 | 0 | 0 | 0 | 200728.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504420 | S-WW-NI-191219-Troqueer STC-Cake Conveyor Lids | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-02-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3728.66 | -0.01 | 3728.65 | 0 | 0 | 0 | 3728.65 | 0 | 0 | 0 | 0 | 3728.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504418 | S-WW-NI-191219-Troqueer WWTW-Tanker Imports Transfer Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-03-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5652.42 | 0 | 5652.42 | 0 | 0 | 0 | 5652.42 | 0 | 0 | 0 | 0 | 5652.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504421 | S-WW-NI-191219-Whitecross WWTW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2021-06-10 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | -185255.12 | 14744.88 | 185340.54 | 0 | 0 | 200085.42 | 0 | 0 | 0 | 0 | 200085.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510792 | S-WW-NI-200121-Ashgill WWTW-Replace suspended solids meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-28 |  | 2021-03-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3980.42 | 3980.42 | 33.48 | 0 | 0 | 4013.9 | 0 | 0 | 0 | 0 | 4013.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510801 | S-WW-NI-200121-Bishops Burn WWPS-Replacement Pump and Refurb pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210.29 | 4210.29 | -110.29 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510799 | S-WW-NI-200121-Carbarns WWTW-Refurbish the roof of the electrical incomer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-19 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6296.03 | 6296.03 | 17.84 | 0 | 0 | 6313.87 | 0 | 0 | 0 | 0 | 6313.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510796 | S-WW-NI-200121-Lauder WWTW-Replace Inlet screen macerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-27 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3875.92 | 3875.92 | -62.04 | 0 | 0 | 3813.88 | 0 | 0 | 0 | 0 | 3813.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510797 | S-WW-NI-200121-Nethanfoot WWPS-Refurb Fence Due H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-01-28 | 2021-06-03 | 2021-10-08 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 18000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510802 | S-WW-NI-200121-Springholm WWTW-Replace the inlet screen basket & wear bar | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2931.47 | 2931.47 | 82.4 | 0 | 0 | 3013.87 | 0 | 0 | 0 | 0 | 3013.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510790 | S-WW-NI-200121-Stonehouse WWTW-Upgrade Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365.44 | 365.44 | 4953.28 | 0 | 0 | 5318.72 | 0 | 0 | 0 | 0 | 5318.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510794 | S-WW-NI-200121-Town Yetholm WWTW-Replace screen macerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4340.8 | 4340.8 | -222.12 | 0 | 0 | 4118.68 | 0 | 0 | 0 | 0 | 4118.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505328 | S-WW-NI-200220-Carronbridge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-02-27 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 182.99 | 12895.01 | 13078 | 0 | 0 | 0 | 13078 | 0 | 0 | 0 | 0 | 13078 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505329 | S-WW-NI-200220-Dalscone WWTW-Supply and fit gate valve on outfall pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2903.14 | 37.41 | 2940.55 | 0 | 0 | 0 | 2940.55 | 0 | 0 | 0 | 0 | 2940.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505325 | S-WW-NI-200220-Refurb Sludge Holding Tank Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-05-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2813.45 | 36.94 | 2850.39 | 0 | 0 | 0 | 2850.39 | 0 | 0 | 0 | 0 | 2850.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505837 | S-WW-NI-200320-Ashgill WWTW-Handrailing Installation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-03-23 |  | 2021-02-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 431.78 | 6143.15 | 6574.93 | 0 | 0 | 0 | 6574.93 | 0 | 0 | 0 | 0 | 6574.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505852 | S-WW-NI-200320-Athelstaneford WWTW-Repair Footpaths | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-06-09 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 471.03 | 6729.24 | 7200.27 | 0 | 0 | 0 | 7200.27 | 0 | 0 | 0 | 0 | 7200.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505835 | S-WW-NI-200320-Bothwellbank WWTW-Supply and Fit Handrails and Steps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-08-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 256.63 | 3222.9 | 3479.53 | 0 | 0 | 0 | 3479.53 | 0 | 0 | 0 | 0 | 3479.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505850 | S-WW-NI-200320-Coursington WWTW-Refurb Tanker Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-07-06 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2813.08 | 63486.13 | 66299.21 | 0 | 0 | 0 | 66299.21 | 0 | 0 | 0 | 0 | 66299.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505832 | S-WW-NI-200320-Daldowie WWTW-Supply and Fit Handrails and Kickplate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-09-07 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 217.38 | 2694.44 | 2911.82 | 0 | 0 | 0 | 2911.82 | 0 | 0 | 0 | 0 | 2911.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505831 | S-WW-NI-200320-Hamilton WWTW-Handrails & Gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 223.92 | 9.24 | 233.16 | 2766.85 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505849 | S-WW-NI-200320-Harthill WWTW-Replace the 2 slip rings on the PSTs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-04-02 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 3994.8 | 18.47 | 4013.27 | 0 | 0 | 0 | 4013.27 | 0 | 0 | 0 | 0 | 4013.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505847 | S-WW-NI-200320-Hawick STC-Wall Alteration Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-09-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3602.95 | 50386.42 | 53989.37 | 0 | 0 | 0 | 53989.37 | 0 | 0 | 0 | 0 | 53989.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505838 | S-WW-NI-200320-Lesmahagow WWTW-Install Handrailing around Site Office | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-10-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 366.36 | 5220.52 | 5586.88 | 0 | 0 | 0 | 5586.88 | 0 | 0 | 0 | 0 | 5586.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505853 | S-WW-NI-200320-Oxton WWTW-Replace existing perimeter fence | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-03-23 |  | 2020-09-21 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2289.72 | 31905.72 | 34195.44 | 0 | 0 | 0 | 34195.44 | 0 | 0 | 0 | 0 | 34195.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505846 | S-WW-NI-200320-Troqueer Final WWPS-Refurb Walkways around SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-07-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 556.07 | 7934.24 | 8490.31 | 0 | 0 | 0 | 8490.31 | 0 | 0 | 0 | 0 | 8490.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505841 | S-WW-NI-200320-Troqueer WWTW-Correct the safe turning point for the Artic | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-09-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1177.57 | 16864.68 | 18042.25 | 0 | 0 | 0 | 18042.25 | 0 | 0 | 0 | 0 | 18042.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506281 | S-WW-NI-200420-Dalscone WWTW-Installation of Turbidity probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-07-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5098.84 | 5098.84 | 0 | 0 | 0 | 5098.84 | 0 | 0 | 0 | 0 | 5098.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506280 | S-WW-NI-200420-SEAFIELD PROMENADE-Replace flap valve at the CSO outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-05-01 |  | 2020-09-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10338.66 | 10338.66 | 361.34 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506729 | S-WW-NI-20052020-Dalscone Old WWTW-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-21 |  | 2020-09-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6733.66 | 6733.66 | 0 | 0 | 0 | 6733.66 | 0 | 0 | 0 | 0 | 6733.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506715 | S-WW-NI-20052020-Port Edgar WWTW-Inlet Screen Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-15 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9218.27 | 9218.27 | 0 | 0 | 0 | 9218.27 | 0 | 0 | 0 | 0 | 9218.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506720 | S-WW-NI-20052020-Port Rodie WWPS-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6756.34 | 6756.34 | 0 | 0 | 0 | 6756.34 | 0 | 0 | 0 | 0 | 6756.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506725 | S-WW-NI-20052020-Troqueer WWTW-Replacement Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7504.7 | 7504.7 | 0 | 0 | 0 | 7504.7 | 0 | 0 | 0 | 0 | 7504.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506708 | S-WW-NI-200520-Ashgill WWTW-Refurb Screen 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12696.55 | 12696.55 | 0 | 0 | 0 | 12696.55 | 0 | 0 | 0 | 0 | 12696.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506711 | S-WW-NI-200520-Ashgill WWTW-Replace air compressor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3729.07 | 3729.07 | 0 | 0 | 0 | 3729.07 | 0 | 0 | 0 | 0 | 3729.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506714 | S-WW-NI-200520-Daldowie WWTW-Repair Mega Washer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-09-04 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28293.87 | 28293.87 | 0 | 0 | 0 | 28293.87 | 0 | 0 | 0 | 0 | 28293.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506705 | S-WW-NI-200520-Lauder WWTW-H&S Civils | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-20 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388.1 | 388.1 | 3711.91 | 0 | 0 | 4100.01 | 0 | 0 | 0 | 0 | 4100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507774 | S-WW-NI-200720-Douglas WWTW-Screen Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-10-09 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2015.78 | 2015.78 | 0 | 0 | 0 | 2015.78 | 0 | 0 | 0 | 0 | 2015.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507757 | S-WW-NI-200720-Lochmaben WWTW-H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264.14 | 2264.14 | 0 | 0 | 0 | 2264.14 | 0 | 0 | 0 | 0 | 2264.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507764 | S-WW-NI-200720-Troqueer WWTW-Reposition chute of compactor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1846.35 | 1846.35 | 0 | 0 | 0 | 1846.35 | 0 | 0 | 0 | 0 | 1846.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507766 | S-WW-NI-200720-Wanlockhead WWTW-Replace Supernatant pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-20 |  | 2020-09-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2176.08 | 2176.08 | 0 | 0 | 0 | 2176.08 | 0 | 0 | 0 | 0 | 2176.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503884 | S-WW-NI-201119-Biggar WWTW-Replacement Motor | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2019-11-25 |  | 2020-03-09 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 3558.64 | 18.7 | 3577.34 | 0 | 0 | 0 | 3577.34 | 0 | 0 | 0 | 0 | 3577.34 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503885 | S-WW-NI-201119-Carstairs Junc WWTW-Supply and fit GRP Walkway | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-01-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 4885.35 | 0 | 4885.35 | 0 | 0 | 0 | 4885.35 | 0 | 0 | 0 | 0 | 4885.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503878 | S-WW-NI-201119-Glassford WWTW-Repair Basket | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2019-11-25 |  | 2020-04-05 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 4002.55 | 18.7 | 4021.25 | 0 | 0 | 0 | 4021.25 | 0 | 0 | 0 | 0 | 4021.25 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503891 | S-WW-NI-201119-Newton Stewart WWTW-Lifting Equipment Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2842.02 | 0 | 2842.02 | 0 | 0 | 0 | 2842.02 | 0 | 0 | 0 | 0 | 2842.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503892 | S-WW-NI-201119-Newton Stewart WWTW-Refurb Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-23 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 8611.7 | 37.41 | 8649.11 | 0 | 0 | 0 | 8649.11 | 0 | 0 | 0 | 0 | 8649.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503889 | S-WW-NI-201119-Newton Stewart WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 11162.09 | 0 | 11162.09 | 0 | 0 | 0 | 11162.09 | 0 | 0 | 0 | 0 | 11162.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509918 | S-WW-NI-201120-Bathgate WWTW-3 No replacement motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 411.79 | 411.79 | 4788.21 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 5200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509915 | S-WW-NI-201120-Chapelton WWTW-Refurb Aerator 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-03-20 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4990.84 | 4990.84 | 9.16 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509905 | S-WW-NI-201120-Hornel Rd WWPS-Extend the concrete base | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-04-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9149.83 | 9149.83 | -49.83 | 0 | 0 | 9100 | 0 | 0 | 0 | 0 | 9100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509901 | S-WW-NI-201120-Lanark WWTW-replace safety chains with safety gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-02-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5103.11 | 5103.11 | -3.11 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 5100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509903 | S-WW-NI-201120-Thornhill WWTW-supply and replace the support steelwork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-03-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14354.47 | 14354.47 | -154.47 | 0 | 0 | 14200 | 0 | 0 | 0 | 0 | 14200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509909 | S-WW-NI-201120-Troqueer WWTW-Replace the motor and gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-24 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683.16 | 683.16 | 9051.54 | 0 | 0 | 9734.7 | 0 | 0 | 0 | 0 | 9734.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504460 | S-WW-NI-201219-Eastriggs WWTW-Sludge Thickener Stairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-08-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 17157.59 | 4750.77 | 21908.36 | 0 | 0 | 0 | 21908.36 | 0 | 0 | 0 | 0 | 21908.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504452 | S-WW-NI-201219-Windygoul Replacement Control Panel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2019-12-23 |  | 2020-09-02 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 55259 | 54741 | 110000 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 110000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504444 | S-WW-NI-202119-Kirkconnel WWTW-Replacement Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-10-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 54904.3 | -47606.24 | 7298.06 | 0 | 0 | 0 | 7298.06 | 0 | 0 | 0 | 0 | 7298.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504755 | S-WW-NI-210120 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-21 |  | 2020-02-13 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2779.98 | -0.01 | 2779.97 | 0 | 0 | 0 | 2779.97 | 0 | 0 | 0 | 0 | 2779.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504761 | S-WW-NI-210120-Troqueer WWTW-Replacement Grit Detritor Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-04-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1479.69 | 1314.31 | 2794 | 0 | 0 | 0 | 2794 | 0 | 0 | 0 | 0 | 2794 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510815 | S-WW-NI-210121-Bleachfield WWPS-Investigate solution for guiderail replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-01-28 | 2021-07-16 | 2022-02-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4380.5 | 4380.5 | 5619.51 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510807 | S-WW-NI-210121-Dalbeattie WWTW-Refurb Screens 1 & 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-04-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5704.74 | 5704.74 | 13.96 | 0 | 0 | 5718.7 | 0 | 0 | 0 | 0 | 5718.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510817 | S-WW-NI-210121-Daldowie WWTW-Refurb Conveyor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10578.56 | 10578.56 | 55.56 | 0 | 0 | 10634.12 | 0 | 0 | 0 | 0 | 10634.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510810 | S-WW-NI-210121-Newton Stewart WWTW-Refurb Screens 1 & 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-04-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5906.86 | 5906.86 | -88.16 | 0 | 0 | 5818.7 | 0 | 0 | 0 | 0 | 5818.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510818 | S-WW-NI-210121-Philipshill WWTW-Replace motor and gearbox of Phase B PST2 scraper bridge | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-08 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586.4 | 2586.4 | 63.2 | 0 | 0 | 2649.6 | 0 | 0 | 0 | 0 | 2649.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510813 | S-WW-NI-210121-Roslin WWTW-To get a quote and deliver the passive flow control solution | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-01-28 | 2021-06-23 | 2021-09-30 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 8750 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510827 | S-WW-NI-210121-Troqueer WWTW-Desludge Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-04-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12780.08 | 12780.08 | 38.6 | 0 | 0 | 12818.68 | 0 | 0 | 0 | 0 | 12818.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510812 | S-WW-NI-210121-Troqueer WWTW-New Foot Path | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3014.96 | 3014.96 | -14.96 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505344 | S-WW-NI-2102202-Newton Stewart WWTW-Aerator Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-04-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 541.26 | 5881.16 | 6422.42 | 0 | 0 | 0 | 6422.42 | 0 | 0 | 0 | 0 | 6422.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505352 | S-WW-NI-210220-North Berwick WWTW-Replacement Lights | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-03-23 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1400.82 | 0 | 1400.82 | 0 | 0 | 0 | 1400.82 | 0 | 0 | 0 | 0 | 1400.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505340 | S-WW-NI-210220-Selkirk WWTW-Aeration Gearbox Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-07-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2626.99 | 51740.5 | 54367.49 | -0.39 | 0 | 0 | 54367.1 | 0 | 0 | 0 | 0 | 54367.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505347 | S-WW-NI-210220-Skellyton WWTW-Pipework Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-04-14 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 709.24 | 10483.59 | 11192.82 | 0 | 0 | 0 | 11192.82 | 0 | 0 | 0 | 0 | 11192.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506292 | S-WW-NI-210420-Linthaugh WWPS-Repair rising main burst | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-05-11 |  | 2021-03-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647411 | 647411 | 1451.78 | 0 | 0 | 648862.78 | 0 | 0 | 0 | 0 | 648862.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506740 | S-WW-NI-210520-Coursington WWTW-FST Bridge Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-21 |  | 2020-10-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8028.38 | 8028.38 | 0 | 0 | 0 | 8028.38 | 0 | 0 | 0 | 0 | 8028.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506737 | S-WW-NI-210520-Kirkcudbright WWTW-Replacement Mixers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-21 |  | 2020-07-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8151.32 | 8151.32 | 0 | 0 | 0 | 8151.32 | 0 | 0 | 0 | 0 | 8151.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506752 | S-WW-NI-210520-North Berwick WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-21 |  | 2020-09-08 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3684.01 | 3684.01 | 0 | 0 | 0 | 3684.01 | 0 | 0 | 0 | 0 | 3684.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506733 | S-WW-NI-210520-Troqueer STC-Replacement bottom belt for Klampress | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-21 |  | 2020-06-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7119.23 | 7119.23 | 0 | 0 | 0 | 7119.23 | 0 | 0 | 0 | 0 | 7119.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507799 | S-WW-NI-210720-Annan WWTW-Repair the Vac Loader motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-21 |  | 2020-07-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2130.19 | 2130.19 | 0 | 0 | 0 | 2130.19 | 0 | 0 | 0 | 0 | 2130.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507872 | S-WW-NI-210720-Broughton WWTW-Drive Coupling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-17 |  | 2020-08-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2367.69 | 2367.69 | -467.69 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507795 | S-WW-NI-210720-Caddonfoot WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-08-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1703.71 | 1703.71 | 0 | 0 | 0 | 1703.71 | 0 | 0 | 0 | 0 | 1703.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507804 | S-WW-NI-210720-Coalburn WWTW-Sand Filter Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-21 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.76 | 103.76 | 1196.25 | 0 | 0 | 1300.01 | 0 | 0 | 0 | 0 | 1300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507803 | S-WW-NI-210720-Ednam WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-21 |  | 2020-09-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813.28 | 1813.28 | 0 | 0 | 0 | 1813.28 | 0 | 0 | 0 | 0 | 1813.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507776 | S-WW-NI-210720-Gretna Services WWTW-Access to Manhole | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-07-27 | 2020-09-28 | 2020-10-27 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9221.96 | 9221.96 | 0 | 0 | 0 | 9221.96 | 0 | 0 | 0 | 0 | 9221.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507823 | S-WW-NI-210720-Manse Rd CSO-Replace 2 wet well pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-09-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3082.04 | 3082.04 | 0 | 0 | 0 | 3082.04 | 0 | 0 | 0 | 0 | 3082.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508841 | S-WW-NI-210920-Blackwood The Lairs WWPS-Replace Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.76 | 103.76 | 1196.25 | 0 | 0 | 1300.01 | 0 | 0 | 0 | 0 | 1300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508843 | S-WW-NI-210920-Daldowie WWTW-Install rotation sensors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-22 |  | 2021-03-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3181.19 | 3181.19 | 518.81 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 3700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508831 | S-WW-NI-210920-Eastfield WWPS-hydraullic survey | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-09-30 | 2021-02-12 | 2021-06-21 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7932 | 7932 | 2068.17 | 0 | 0 | 10000.17 | 0 | 0 | 0 | 0 | 10000.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508839 | S-WW-NI-210920-Newton Stewart WWTW-refurbish the breakers on MCC1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-10-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1857.44 | 1857.44 | 0 | 0 | 0 | 1857.44 | 0 | 0 | 0 | 0 | 1857.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508832 | S-WW-NI-210920-North Berwick WWTW-Investigation Work | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-09-24 | 2021-03-23 | 2021-06-21 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5050 | 5050 | 4950 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508834 | S-WW-NI-210920-Philipshill WWTW-Replace Desludge Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-11-20 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369.48 | 1369.48 | 0 | 0 | 0 | 1369.48 | 0 | 0 | 0 | 0 | 1369.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508835 | S-WW-NI-210920-Sran Larg Rd WWPS-refurbish No 1 injector | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-09-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.77 | 1312.77 | 0 | 0 | 0 | 1312.77 | 0 | 0 | 0 | 0 | 1312.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503919 | S-WW-NI-211119-Annan Riverside WWPS-Install fall arrest protection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2501.89 | 0 | 2501.89 | 0 | 0 | 0 | 2501.89 | 0 | 0 | 0 | 0 | 2501.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503902 | S-WW-NI-211119-Gifford WWTW-Replace Handrailing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-06-15 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 6615.88 | 4000.5 | 10616.38 | 0 | 0 | 0 | 10616.38 | 0 | 0 | 0 | 0 | 10616.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503898 | S-WW-NI-211119-Kirkcudbright SPS-Replacement Pump & Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-10-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 30300 | 6934.93 | 37234.93 | 0 | 0 | 0 | 37234.93 | 0 | 0 | 0 | 0 | 37234.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503914 | S-WW-NI-211119-Moniaive WWTW-Provide H&S Hoist | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-04-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2663.74 | 17.88 | 2681.62 | 0 | 0 | 0 | 2681.62 | 0 | 0 | 0 | 0 | 2681.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503916 | S-WW-NI-211119-Newton St Boswells WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2020-01-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2605.69 | 10.56 | 2616.25 | 0 | 0 | 0 | 2616.25 | 0 | 0 | 0 | 0 | 2616.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503897 | S-WW-NI-211119-Strathaven WWTW-Replace Burst Sludge Main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-25 |  | 2019-12-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 10010.21 | 0 | 10010.21 | 0 | 0 | 0 | 10010.21 | 0 | 0 | 0 | 0 | 10010.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510451 | S-WW-NI-211220-Bothwellbank WWTW-Refurbish No2 sludge mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190.52 | 190.52 | 2509.48 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510455 | S-WW-NI-211220-Castle Douglas WWTW-Refurbish Inlet pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182.26 | 182.26 | 2317.75 | 0 | 0 | 2500.01 | 0 | 0 | 0 | 0 | 2500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510448 | S-WW-NI-211220-Chapelton WWTW-Replace FST 2 Scrapers and blades | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1441.84 | 1441.84 | 58.17 | 0 | 0 | 1500.01 | 0 | 0 | 0 | 0 | 1500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510447 | S-WW-NI-211220-Coursington WWTW-Fabricate and fit PST wheels | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2494.34 | 2494.34 | 5.67 | 0 | 0 | 2500.01 | 0 | 0 | 0 | 0 | 2500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510453 | S-WW-NI-211220-Wanlockhead WWTW-Replace Coupling on ditch rotor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278.78 | 1278.78 | 21.23 | 0 | 0 | 1300.01 | 0 | 0 | 0 | 0 | 1300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504777 | S-WW-NI-220120-Allers WWTW-Repair Roads | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-02-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 10336.18 | 0 | 10336.18 | 0 | 0 | 0 | 10336.18 | 0 | 0 | 0 | 0 | 10336.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504778 | S-WW-NI-220120-Daldowie WWTW-Replacement Gearbox for FST6 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-02-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 3940.98 | 0 | 3940.98 | 0 | 0 | 0 | 3940.98 | 0 | 0 | 0 | 0 | 3940.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504783 | S-WW-NI-220120-Hawick WWTW-Refurb Blower No3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-05-06 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4767.89 | 4226.66 | 8994.55 | 0 | 0 | 0 | 8994.55 | 0 | 0 | 0 | 0 | 8994.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504775 | S-WW-NI-220120-Lesmahagow WWTW- | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-03-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 9154.73 | 0 | 9154.73 | 0 | 0 | 0 | 9154.73 | 0 | 0 | 0 | 0 | 9154.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504773 | S-WW-NI-220120-Lesmahagow WWTW-Refurb Storm Screen No2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-05-05 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 5813.5 | 3089.91 | 8903.41 | 0 | 0 | 0 | 8903.41 | 0 | 0 | 0 | 0 | 8903.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510850 | S-WW-NI-220121-Denholm WWTW-Repair final tank scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1452.95 | 1452.95 | -96.8 | 0 | 0 | 1356.15 | 0 | 0 | 0 | 0 | 1356.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510844 | S-WW-NI-220121-Lauder WWTW-Replace MLSS monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264.98 | 264.98 | 1753.72 | 0 | 0 | 2018.7 | 0 | 0 | 0 | 0 | 2018.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511368 | S-WW-NI-220221-Hawick WWTW-DO calibration meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1214.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511361 | S-WW-NI-220221-Philipshill WWTW-Provide insulation to pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140.07 | 140.07 | 1588.8 | 0 | 0 | 1728.87 | 0 | 0 | 0 | 0 | 1728.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511946 | S-WW-NI-220321-Allers WWTW-PST head wall repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2142.84 | 0 | 0 | 2306.39 | 0 | 0 | 0 | 0 | 2306.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511952 | S-WW-NI-220321-Annan WWTW-Refurb Screen 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339.28 | 339.28 | 1800 | 0 | 0 | 2139.28 | 0 | 0 | 0 | 0 | 2139.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511956 | S-WW-NI-220321-Cardrona WWTW-Replace copasac brackets to inlet of septic tanks | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1371.42 | 0 | 0 | 1476.09 | 0 | 0 | 0 | 0 | 1476.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511955 | S-WW-NI-220321-Eddleston WWTW-Gearbox for pista grit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1285.74 | 0 | 0 | 1383.87 | 0 | 0 | 0 | 0 | 1383.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511947 | S-WW-NI-220321-Monaive WWTW-Screen Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-22 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293.49 | 293.49 | 1200 | 0 | 0 | 1493.49 | 0 | 0 | 0 | 0 | 1493.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511949 | S-WW-NI-220321-Thornhill WWTW-Screen Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-06-22 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115.44 | 115.44 | 1285.74 | 0 | 0 | 1401.18 | 0 | 0 | 0 | 0 | 1401.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506302 | S-WW-NI-220420-Eaglesfield WWTW- | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-05-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.89 | 1658.89 | 0 | 0 | 0 | 1658.89 | 0 | 0 | 0 | 0 | 1658.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506306 | S-WW-NI-220420-Newstead WWPS-Replacement Outlet Flow Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-05-05 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3602.57 | 3602.57 | 0 | 0 | 0 | 3602.57 | 0 | 0 | 0 | 0 | 3602.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506313 | S-WW-NI-220420-North Berwick WWTW- replace PST scraper arms and restore the PST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-04-22 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358252.37 | 358252.37 | 747.64 | 0 | 0 | 359000.01 | 0 | 0 | 0 | 0 | 359000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506311 | S-WW-NI-220420-Philipshill WWTW-Tank Draw Down Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-22 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365.2 | 365.2 | 4934.8 | 0 | 0 | 5300 | 0 | 0 | 0 | 0 | 5300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506783 | S-WW-NI-220520-Enterprise Park WWPS-Fall Protection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-08-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4245.88 | 4245.88 | 0 | 0 | 0 | 4245.88 | 0 | 0 | 0 | 0 | 4245.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506767 | S-WW-NI-220520-Enterprise Park WWPS-Replace Rotten Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-09-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7993.1 | 7993.1 | 0 | 0 | 0 | 7993.1 | 0 | 0 | 0 | 0 | 7993.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506784 | S-WW-NI-220520-Peebles WWTW-Replace Ferric Dosing Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-06-19 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107.36 | 2107.36 | 0 | 0 | 0 | 2107.36 | 0 | 0 | 0 | 0 | 2107.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507819 | S-WW-NI-220720-Annan WWTW-bridge control investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-09-21 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7130.07 | 7130.07 | 0 | 0 | 0 | 7130.07 | 0 | 0 | 0 | 0 | 7130.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507821 | S-WW-NI-220720-Annan WWTW-Critical spare geared motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-08-25 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3411.51 | 3411.51 | 0 | 0 | 0 | 3411.51 | 0 | 0 | 0 | 0 | 3411.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507826 | S-WW-NI-220720-Garlieston WWTW-Replacement Flow Monitor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-11-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3902.4 | 3902.4 | 0 | 0 | 0 | 3902.4 | 0 | 0 | 0 | 0 | 3902.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507834 | S-WW-NI-220720-Kippford Merse Way-Gratings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3142.52 | 3142.52 | 0 | 0 | 0 | 3142.52 | 0 | 0 | 0 | 0 | 3142.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507833 | S-WW-NI-220720-Lauder WWTW-Replace oxidation ditch aerator 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-07-27 | 2021-02-22 | 2021-06-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34678 | 34678 | 7321.65 | 0 | 0 | 41999.65 | 0 | 0 | 0 | 0 | 41999.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507832 | S-WW-NI-220720-Wanlockhead WWTW-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-09-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4880.12 | 4880.12 | 0 | 0 | 0 | 4880.12 | 0 | 0 | 0 | 0 | 4880.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508864 | S-WW-NI-220920-Glassford WWTW-Replacement DO Monitors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-09-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635.39 | 1635.39 | 0 | 0 | 0 | 1635.39 | 0 | 0 | 0 | 0 | 1635.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508877 | S-WW-NI-220920-Harbour Square SPS-Fencing to protect temporary pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-22 |  | 2020-10-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455.95 | 1455.95 | 0 | 0 | 0 | 1455.95 | 0 | 0 | 0 | 0 | 1455.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508861 | S-WW-NI-220920-Kirkcudbright WWTW-Replacement pressure vessel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-22 |  | 2020-10-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1939.5 | 1939.5 | 0 | 0 | 0 | 1939.5 | 0 | 0 | 0 | 0 | 1939.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508884 | S-WW-NI-220920-Linlithgow WWTW-Replace FFT penstock actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-01-12 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3709.87 | 3709.87 | -1609.87 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508866 | S-WW-NI-220920-Philipshill WWTW-Replacement Rotory parts | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-22 |  | 2020-09-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1875.78 | 1875.78 | 0 | 0 | 0 | 1875.78 | 0 | 0 | 0 | 0 | 1875.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508880 | S-WW-NI-220920-Port Rodie WWPS-Gas Monitoring Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-10-07 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1883.68 | 1883.68 | 0 | 0 | 0 | 1883.68 | 0 | 0 | 0 | 0 | 1883.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510487 | S-WW-NI-221220-Allers WWTW-Repair tank wall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-24 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5894.84 | 5894.84 | 5.16 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 5900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510494 | S-WW-NI-221220-Coldstream WWTW-Aerator Motor and Gearbox installation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-24 |  | 2021-02-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3613.12 | 3613.12 | -113.1 | 0 | 0 | 3500.02 | 0 | 0 | 0 | 0 | 3500.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510490 | S-WW-NI-221220-Kelso WWTW-Replace Blower No3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-24 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6475.9 | 6475.9 | -275.9 | 0 | 0 | 6200 | 0 | 0 | 0 | 0 | 6200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510485 | S-WW-NI-221220-Stonehouse WWTW-Refurb Storm Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-24 |  | 2021-03-20 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16735.58 | 16735.58 | 564.45 | 0 | 0 | 17300.03 | 0 | 0 | 0 | 0 | 17300.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504811 | S-WW-NI-230120-Castle Kennedy WWTW-Installation of Access Path | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1783.7 | -1431.1 | 352.6 | 1947.4 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504803 | S-WW-NI-230120-Eaglesfield WWTW-Replacement Geared Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-03-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3197.54 | 36.94 | 3234.48 | 0 | 0 | 0 | 3234.48 | 0 | 0 | 0 | 0 | 3234.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504806 | S-WW-NI-230120-Eastriggs WWPS-2No Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-02-20 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3064.49 | 0 | 3064.49 | 0 | 0 | 0 | 3064.49 | 0 | 0 | 0 | 0 | 3064.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504814 | S-WW-NI-230120-Philipshill WWTW-Tank Inspection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-03-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1648.1 | 0 | 1648.1 | 0 | 0 | 0 | 1648.1 | 0 | 0 | 0 | 0 | 1648.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504801 | S-WW-NI-230120-Troqueer Final WWPS-DO Probes & Controller | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-02-06 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 4755.79 | 0 | 4755.79 | 0 | 0 | 0 | 4755.79 | 0 | 0 | 0 | 0 | 4755.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511402 | S-WW-NI-230221-GALASHIELS STC-DSEAR H&S Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511411 | S-WW-NI-230221-Hawick STC-DSEAR H&S Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511422 | S-WW-NI-230221-Skellyton WWTW-Repairs to wet well | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2243 | 0 | 0 | 2400.01 | 0 | 0 | 0 | 0 | 2400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511418 | S-WW-NI-230221-TROQUEER STC-DSEAR H&S Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511442 | S-WW-NI-230221-Troqueer STC-Replace the Spare Belt to Klampress | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-25 |  | 2021-04-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7473.31 | 7473.31 | -173.3 | 0 | 0 | 7300.01 | 0 | 0 | 0 | 0 | 7300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505894 | S-WW-NI-23032020-Airds Point WWTW-Standby Generator Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-04-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1745.67 | 1745.67 | 0 | 0 | 0 | 1745.67 | 0 | 0 | 0 | 0 | 1745.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505892 | S-WW-NI-23032020-Troqueer STC-Refurbish Strainpress no2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-04-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 421.5 | 1715.84 | 2137.34 | 0 | 0 | 0 | 2137.34 | 0 | 0 | 0 | 0 | 2137.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505880 | S-WW-NI-23032020-Troqueer WWTW-investigate the Fire System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-07-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1787.62 | 1787.62 | 0 | 0 | 0 | 1787.62 | 0 | 0 | 0 | 0 | 1787.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505876 | S-WW-NI-230320-Gorebridge WWTW-Repair Access Road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-04-03 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 85.05 | 1285.05 | 0 | 0 | 0 | 1285.05 | 0 | 0 | 0 | 0 | 1285.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512067 | S-WW-NI-230321 - PORTPATRICK WWPS 1994 NW997542 - REPLACE RISER PIPEWORK & GUIDERAILS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510.28 | 510.28 | 6685.74 | 0 | 0 | 7196.02 | 0 | 0 | 0 | 0 | 7196.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512069 | S-WW-NI-230321- DUMFRIES CUCKOO RETAIL WWPS NX961769 - REPLACCE FOOTSTOOLS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.14 | 255.14 | 3342.84 | 0 | 0 | 3597.98 | 0 | 0 | 0 | 0 | 3597.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512066 | S-WW-NI-230321- PORT RODIE WWPS NX062610 - SPARE PARTS (PUMPS) | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.31 | 981.31 | 14018.69 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512090 | S-WW-NI-230321- TROQUEER STC - CALL OUT & LINK BELT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719.63 | 719.63 | 9428.58 | 0 | 0 | 10148.21 | 0 | 0 | 0 | 0 | 10148.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512116 | S-WW-NI-230321- TROQUEER WWTW 1950 NX971745 - REFURB SCREEN 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202.8 | 202.8 | 2657.16 | 0 | 0 | 2859.96 | 0 | 0 | 0 | 0 | 2859.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512115 | S-WW-NI-230321- TROQUEER WWTW 1950 NX971745 - REFURBISH SCREEN 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202.8 | 202.8 | 2657.16 | 0 | 0 | 2859.96 | 0 | 0 | 0 | 0 | 2859.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506328 | S-WW-NI-230420-Harelaw SEP-Health and safety access gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-09 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1674.54 | 1674.54 | 0 | 0 | 0 | 1674.54 | 0 | 0 | 0 | 0 | 1674.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507838 | S-WW-NI-230720-Bathgate WWTW-new access stairs on sludge holding tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-07-27 | 2021-01-06 | 2021-08-18 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34167 | 34167 | 30833.35 | 0 | 0 | 65000.35 | 0 | 0 | 0 | 0 | 65000.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507844 | S-WW-NI-230720-Cove WWTW-Replace Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-08-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3440.68 | 3440.68 | 0 | 0 | 0 | 3440.68 | 0 | 0 | 0 | 0 | 3440.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507852 | S-WW-NI-230720-Livingston WWPS-Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-11-02 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14084.26 | 14084.26 | 0 | 0 | 0 | 14084.26 | 0 | 0 | 0 | 0 | 14084.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507841 | S-WW-NI-230720-Plains WWTW-Repairs to Access Rd | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-24 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.82 | 384.82 | 4615.18 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507846 | S-WW-NI-230720-Stenton WWTW-Repair Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-09-30 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7839.13 | 7839.13 | 0 | 0 | 0 | 7839.13 | 0 | 0 | 0 | 0 | 7839.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508904 | S-WW-NI-230920-Almondvale WWPS-Replace dammaged pipe bend | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-23 |  | 2021-03-12 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3877.88 | 3877.88 | -77.87 | 0 | 0 | 3800.01 | 0 | 0 | 0 | 0 | 3800.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508917 | S-WW-NI-230920-Bonchester Bridge WWPS-Replace inlet pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-11-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2928.54 | 2928.54 | 0 | 0 | 0 | 2928.54 | 0 | 0 | 0 | 0 | 2928.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508906 | S-WW-NI-230920-Galashiels WWTW-Remove unsafe ladders etc | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-20 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3263.58 | 3263.58 | 0 | 0 | 0 | 3263.58 | 0 | 0 | 0 | 0 | 3263.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508914 | S-WW-NI-230920-Glencaple WWTW-2 Inlet Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-10-21 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3264.6 | 3264.6 | 0 | 0 | 0 | 3264.6 | 0 | 0 | 0 | 0 | 3264.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508911 | S-WW-NI-230920-Jedburgh WWTW-Refurbish inlet CSO screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-23 |  | 2020-11-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877.86 | 877.86 | 9340.85 | 0 | 0 | 10218.71 | 0 | 0 | 0 | 0 | 10218.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508912 | S-WW-NI-230920-Jedburgh WWTW-Replace 2 washwater pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8025.78 | 8025.78 | -25.78 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508902 | S-WW-NI-230920-Philipshill WWTW-Replace scrapers and arms | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4292.43 | 4292.43 | 0 | 0 | 0 | 4292.43 | 0 | 0 | 0 | 0 | 4292.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508898 | S-WW-NI-230920-Quarter WWPS-Replace Motor on Pump 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-23 |  | 2021-02-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5142.52 | 5142.52 | -42.52 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 5100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508919 | S-WW-NI-230920-Troqueer WWTW-Replace Klampress 2 Belt | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13762.28 | 13762.28 | 137.72 | 0 | 0 | 13900 | 0 | 0 | 0 | 0 | 13900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508922 | S-WW-NI-230920-Twynholm WWTW-Repairs to Access Rd | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-24 |  | 2020-10-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4103.6 | 4103.6 | 0 | 0 | 0 | 4103.6 | 0 | 0 | 0 | 0 | 4103.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509939 | S-WW-NI-231120-Joppa Mine Water-SW estimators to price up a new mine water outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805.56 | 805.56 | 264.44 | 0 | 0 | 1070 | 0 | 0 | 0 | 0 | 1070 | 209381.79 | [5 empty] | N | CM_WWI | 100%
509935 | S-WW-NI-231120-Lockerbie WWTW-Replace chains with gate in pump house | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-24 |  | 2021-03-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429.01 | 1429.01 | 70.99 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504479 | S-WW-NI-231219-Earlston WWTW-Distribution Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | -2062.33 | 637.67 | 2062.33 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504473 | S-WW-NI-231219-Hawick WWTW-Supply & fit GRP door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-05-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 455.63 | 2255.63 | 0 | 0 | 0 | 2255.63 | 0 | 0 | 0 | 0 | 2255.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504475 | S-WW-NI-231219-Jedburgh WWTW-Repair damaged roof to Aeration Kiosk | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-23 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | -1757.23 | 142.77 | 1757.23 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504468 | S-WW-NI-231219-New Abbey WWTW-Replace Telemetry Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-02-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2071.04 | 0 | 2071.04 | 0 | 0 | 0 | 2071.04 | 0 | 0 | 0 | 0 | 2071.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504471 | S-WW-NI-231219-Newton Stewart WWTW-Install Heating | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-01-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2217.96 | 0 | 2217.96 | 0 | 0 | 0 | 2217.96 | 0 | 0 | 0 | 0 | 2217.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504481 | S-WW-NI-231219-Newton Stewart WWTW-Replacement PumpA | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-03-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 8210.92 | 55.41 | 8266.33 | 0 | 0 | 0 | 8266.33 | 0 | 0 | 0 | 0 | 8266.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504484 | S-WW-NI-231219-Prestonpans WWPS-PLC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2019-12-23 |  | 2020-09-27 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 212815.82 | 59184.18 | 272000 | 43000.02 | 0 | 0 | 315000.02 | 0 | 0 | 0 | 0 | 315000.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504467 | S-WW-NI-231219-Troqueer WWTW-Fill Pot Holes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-23 |  | 2020-03-05 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2137.64 | -0.01 | 2137.63 | 0 | 0 | 0 | 2137.63 | 0 | 0 | 0 | 0 | 2137.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505889 | S-WW-NI-23-32020-Loganbarns WWPS-Investigate Fire System | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-01 |  | 2020-07-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456.6 | 1456.6 | 0 | 0 | 0 | 1456.6 | 0 | 0 | 0 | 0 | 1456.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504830 | S-WW-NI-240120-Bathgate WWTW-Replacement Safety Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-05-13 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1371.32 | -0.01 | 1371.31 | 0 | 0 | 0 | 1371.31 | 0 | 0 | 0 | 0 | 1371.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504832 | S-WW-NI-240120-Broughton WWTW-Washwater Kiosk Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-05-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1008.18 | 385.45 | 1393.63 | 0 | 0 | 0 | 1393.63 | 0 | 0 | 0 | 0 | 1393.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504836 | S-WW-NI-240120-Ormiston WWTW-Replacement Lighting & Heating | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-27 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 1395.94 | -1278.18 | 117.76 | 1682.24 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504825 | S-WW-NI-240120-Troqueer WWTW-2No Pressure Control Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-02-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2491.72 | 0 | 2491.72 | 0 | 0 | 0 | 2491.72 | 0 | 0 | 0 | 0 | 2491.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505385 | S-WW-NI-240220-Blackwood WWTW-Replace Wash Water Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-04-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1393.07 | 0 | 1393.07 | 0 | 0 | 0 | 1393.07 | 0 | 0 | 0 | 0 | 1393.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505383 | S-WW-NI-240220-Dumfries Loganbarns WWPS-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-06-22 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 110.06 | 1262.42 | 1372.48 | 0 | 0 | 0 | 1372.48 | 0 | 0 | 0 | 0 | 1372.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505387 | S-WW-NI-240220-Haddington WWTW-Replacement of 2No pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-04-24 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 342.54 | 5304.89 | 5647.43 | 0 | 0 | 0 | 5647.43 | 0 | 0 | 0 | 0 | 5647.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505381 | S-WW-NI-240220-Thornhill WWTW-H&S Mods | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 1648.06 | -0.01 | 1648.05 | 0 | 0 | 0 | 1648.05 | 0 | 0 | 0 | 0 | 1648.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511451 | S-WW-NI-240221-Forth WWTW-repair section of pipe & reinstate road | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202.8 | 202.8 | 2897.2 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511447 | S-WW-NI-240221-Langholm WWTW-Replace screw pump gearboxes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21577.26 | 21577.26 | -277.26 | 0 | 0 | 21300 | 0 | 0 | 0 | 0 | 21300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511438 | S-WW-NI-240221-Lesmahagow WWTW-install a new FFT flow meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2003.32 | 2003.32 | 4696.7 | 0 | 0 | 6700.02 | 0 | 0 | 0 | 0 | 6700.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511440 | S-WW-NI-240221-Port Rodie WWPS-Refurb Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287.88 | 1287.88 | 15312.1 | 0 | 0 | 16599.98 | 0 | 0 | 0 | 0 | 16599.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505900 | S-WW-NI-24032020-Roslin WWTW-Supply and fit panel heater | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-31 |  | 2020-07-24 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309.24 | 1309.24 | 0 | 0 | 0 | 1309.24 | 0 | 0 | 0 | 0 | 1309.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511995 | S-WW-NI-240321-Allers_STW_RAS_Pump_Building | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535.53 | 535.53 | 6771.42 | 0 | 0 | 7306.95 | 0 | 0 | 0 | 0 | 7306.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506350 | S-WW-NI-24042020-Lanark WWTW-Extend compactor chutes | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-05-05 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6296.72 | 6296.72 | 0 | 0 | 0 | 6296.72 | 0 | 0 | 0 | 0 | 6296.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506341 | S-WW-NI-240420-Eastriggs WWTW-New spare storm pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-05-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1717.5 | 1717.5 | 0 | 0 | 0 | 1717.5 | 0 | 0 | 0 | 0 | 1717.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507341 | S-WW-NI-240620-Gorebridge WWTW-Install Access Gates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-07-13 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675.56 | 1675.56 | 0 | 0 | 0 | 1675.56 | 0 | 0 | 0 | 0 | 1675.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507322 | S-WW-NI-240620-Harthill WWTW-Replacement Wash water pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-21 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107.6 | 2107.6 | 0 | 0 | 0 | 2107.6 | 0 | 0 | 0 | 0 | 2107.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507869 | S-WW-NI-240720-East Mains WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-09-18 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2294.98 | 2294.98 | 0 | 0 | 0 | 2294.98 | 0 | 0 | 0 | 0 | 2294.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507858 | S-WW-NI-240720-Gullane WWTW-H&S Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-24 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8145.8 | 8145.8 | 54.2 | 0 | 0 | 8200 | 0 | 0 | 0 | 0 | 8200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507868 | S-WW-NI-240720-Ladywell WWPS-Cable Ducting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-08-18 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2072.91 | 2072.91 | 0 | 0 | 0 | 2072.91 | 0 | 0 | 0 | 0 | 2072.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507856 | S-WW-NI-240720-Smithycroft WWPS-Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-24 |  | 2020-09-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4917.65 | 4917.65 | 0 | 0 | 0 | 4917.65 | 0 | 0 | 0 | 0 | 4917.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508332 | S-WW-NI-240820-Allers WWTW-Scraper Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1497.76 | 1497.76 | 0 | 0 | 0 | 1497.76 | 0 | 0 | 0 | 0 | 1497.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508343 | S-WW-NI-240820-Athelstaneford WWTW-Replace humus return pump 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-11 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1180 | 1180 | 0 | 0 | 0 | 1180 | 0 | 0 | 0 | 0 | 1180 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508328 | S-WW-NI-240820-Chainbridge WWPS-Replace Pump No2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302.4 | 302.4 | 1697.6 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508334 | S-WW-NI-240820-Gatehouse Fleet WWPS-Road Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-10-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1798 | 1798 | 0 | 0 | 0 | 1798 | 0 | 0 | 0 | 0 | 1798 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508329 | S-WW-NI-240820-Lincluden WWTW-Hand Rails & Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2231.8 | 2231.8 | 0 | 0 | 0 | 2231.8 | 0 | 0 | 0 | 0 | 2231.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508337 | S-WW-NI-240820-Park WWTW-Level off ground and add handrails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2679.78 | 2679.78 | 0 | 0 | 0 | 2679.78 | 0 | 0 | 0 | 0 | 2679.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508951 | S-WW-NI-240920-Annan WWTW-Belt press tracking unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-24 |  | 2020-10-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1872.65 | 1872.65 | 0 | 0 | 0 | 1872.65 | 0 | 0 | 0 | 0 | 1872.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508931 | S-WW-NI-240920-Harbour Squ WWPS-Radio Link | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-24 |  | 2020-09-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8748.08 | 8748.08 | 1670.63 | 0 | 0 | 10418.71 | 0 | 0 | 0 | 0 | 10418.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508943 | S-WW-NI-240920-Kirkcudbright WWTW-To refurbish the dry well FE pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-24 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7783.5 | 7783.5 | 2016.5 | 0 | 0 | 9800 | 0 | 0 | 0 | 0 | 9800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508954 | S-WW-NI-240920-Kirkton WWTW-Rotameter on recirculation pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-24 |  | 2020-10-13 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1315.92 | 1315.92 | 0 | 0 | 0 | 1315.92 | 0 | 0 | 0 | 0 | 1315.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508934 | S-WW-NI-240920-Lincluden WWTW-Welfare Building Upgrades | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-24 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692.54 | 692.54 | 9607.47 | 0 | 0 | 10300.01 | 0 | 0 | 0 | 0 | 10300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508933 | S-WW-NI-240920-Lochmaben WWTW-Sprial aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-24 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12344.46 | 12344.46 | -44.46 | 0 | 0 | 12300 | 0 | 0 | 0 | 0 | 12300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508946 | S-WW-NI-240920-Philipshill WWTW-Replace Inlet penstock | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-24 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339.03 | 339.03 | 3960.97 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508930 | S-WW-NI-240920-Strathaven WWTW-Replace PST 1 and 2 Rotorks | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-24 |  | 2020-11-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3863.02 | 3863.02 | 0 | 0 | 0 | 3863.02 | 0 | 0 | 0 | 0 | 3863.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508955 | S-WW-NI-240920-Torphichen WWTW-Power Supply | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-11-16 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1594.34 | 1594.34 | 0 | 0 | 0 | 1594.34 | 0 | 0 | 0 | 0 | 1594.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508945 | S-WW-NI-240920-Troqueer STC-Replace Klampress 1 Belt | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-25 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12736.59 | 12736.59 | -136.59 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 12600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508938 | S-WW-NI-240920-Troqueer WWTW-Refurbish Odour control pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-24 |  | 2020-10-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8878.55 | 8878.55 | 0 | 0 | 0 | 8878.55 | 0 | 0 | 0 | 0 | 8878.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509962 | S-WW-NI-241120-Annan WWTW-Replace inlet bypass actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-02-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1291 | 1291 | 9 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509965 | S-WW-NI-241120-East Linton WWTW-Replace dewatering pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.05 | 85.05 | 1214.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509969 | S-WW-NI-241120-Galashiels WWTW-Thickened sludge tank mixer coupling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142.77 | 142.77 | 1157.23 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509976 | S-WW-NI-241120-Melrose WWTW-Replace turbidity meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-03 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2467.64 | 2467.64 | 32.36 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504491 | S-WW-NI-241219-Maybole WWTW-Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-04 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | -92871.84 | 7128.16 | 92871.84 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510872 | S-WW-NI-250121-Stonehouse WWTW-Install necessary new handrailing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482.48 | 1482.48 | 17.52 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511467 | S-WW-NI-250221-Dunbar WWTW-Replace interstage pump A | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-26 |  | 2021-05-25 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5514 | 0 | 0 | 5899.98 | 0 | 0 | 0 | 0 | 5899.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511470 | S-WW-NI-250221-Fillyside WWPS-Installation of 4No vertical rail ladder safety systems | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-26 |  | 2021-05-25 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680.37 | 680.37 | 9719.65 | 0 | 0 | 10400.02 | 0 | 0 | 0 | 0 | 10400.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511477 | S-WW-NI-250221-Galashiels WWTW-Refurbish filter wall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-26 |  | 2021-05-25 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2563.99 | 2563.99 | -63.99 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511472 | S-WW-NI-250221-KIRKCUD HARBOUR SQU WWPS-Modify screen and adjust weir | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2021-03-01 | 2021-03-08 | 2021-07-05 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1706.57 | 1706.57 | 21293.43 | 0 | 0 | 23000 | 0 | 0 | 0 | 0 | 23000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511460 | S-WW-NI-250221-Lanark WWTW-Provide and install an adjustable splitter plate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-25 |  | 2021-05-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 2616.8 | 0 | 0 | 2799.98 | 0 | 0 | 0 | 0 | 2799.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511458 | S-WW-NI-250221-Rosewell WWTW-Follow On Work | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-01 | 2021-05-21 | 2021-07-19 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.31 | 981.31 | 15000 | 0 | 0 | 15981.31 | 0 | 0 | 0 | 0 | 15981.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511462 | S-WW-NI-250221-TRANENT WEST WINDYGOUL WWPS-Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-26 |  | 2021-05-25 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12331.27 | 12331.27 | 7068.73 | 0 | 0 | 19400 | 0 | 0 | 0 | 0 | 19400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512029 | S-WW-NI-25032021-DALMORE WWPS-RAILING REPLACMENT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2309.27 | 2309.27 | 0 | 0 | 0 | 2309.27 | 0 | 0 | 0 | 0 | 2309.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512035 | S-WW-NI-25032021-LANARK WWTW-REPLACEMENT SCAFFOLDING | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302.89 | 302.89 | 3968.46 | 0 | 0 | 4271.35 | 0 | 0 | 0 | 0 | 4271.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512024 | S-WW-NI-250321-EAGLESHAM WWTW 1965 NS579531 - REPLACE ARMS ON NFT | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1282.24 | 1282.24 | 18317.76 | 0 | 0 | 19600 | 0 | 0 | 0 | 0 | 19600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506810 | S-WW-NI-250520-Haddington WWTW-Repair walkway | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-07-06 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153.54 | 1153.54 | 0 | 0 | 0 | 1153.54 | 0 | 0 | 0 | 0 | 1153.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506802 | S-WW-NI-250520-Lochmaben WWTW-Install 2 drop kerbs and a bullnose for wheelbarrow | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-07-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1741.08 | 1741.08 | 0 | 0 | 0 | 1741.08 | 0 | 0 | 0 | 0 | 1741.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506798 | S-WW-NI-250520-Loonburn Pipe Bridge-Removal of Pipe Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-05-27 | 2020-09-07 | 2021-09-17 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56391.26 | 56391.26 | 194241.16 | 0 | 0 | 250632.42 | 0 | 0 | 0 | 0 | 250632.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506812 | S-WW-NI-250520-Salsburgh WWTW-Caustic Dosing Kit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-07-03 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2293.94 | 2293.94 | 0 | 0 | 0 | 2293.94 | 0 | 0 | 0 | 0 | 2293.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506787 | S-WW-NI-250520-Strathclyde WWPS-Replace Roller Shutter Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-09-04 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1976.54 | 1976.54 | 0 | 0 | 0 | 1976.54 | 0 | 0 | 0 | 0 | 1976.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507361 | S-WW-NI-25062020-Armadale WWTW-Replace Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-06-25 |  | 2021-07-30 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8729.65 | 8729.65 | 74367.78 | 0 | 0 | 83097.43 | 0 | 0 | 0 | 0 | 83097.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507371 | S-WW-NI-250620-Bothwellbank WWTW-Replace scrappers on FSTs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-07-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3670.56 | 3670.56 | 0 | 0 | 0 | 3670.56 | 0 | 0 | 0 | 0 | 3670.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507357 | S-WW-NI-250620-Daldowie WWTW-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-25 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10388.24 | 10388.24 | 111.76 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 10500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507367 | S-WW-NI-250620-East Beach Sewer-CCTV and repair damaged beach sewers | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-06-25 |  | 2020-10-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3940.39 | 3940.39 | 0 | 0 | 0 | 3940.39 | 0 | 0 | 0 | 0 | 3940.39 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507377 | S-WW-NI-250620-Gretna WWTW-Flooring and support steelwork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4396.1 | 4396.1 | 0 | 0 | 0 | 4396.1 | 0 | 0 | 0 | 0 | 4396.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507375 | S-WW-NI-250620-Troqueer STC-Klampress Belt | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-07-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14128.08 | 14128.08 | 0 | 0 | 0 | 14128.08 | 0 | 0 | 0 | 0 | 14128.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507364 | S-WW-NI-250620-Troqueer STC-Replace dewaterer 2 washwater recycle | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-08-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5556.83 | 5556.83 | 0 | 0 | 0 | 5556.83 | 0 | 0 | 0 | 0 | 5556.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508360 | S-WW-NI-250820-Eaglesfield WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-10-23 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1897.26 | 1897.26 | 0 | 0 | 0 | 1897.26 | 0 | 0 | 0 | 0 | 1897.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508367 | S-WW-NI-250820-Innerwick WWTW-Modify the grating H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-10-12 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1128.5 | 1128.5 | 0 | 0 | 0 | 1128.5 | 0 | 0 | 0 | 0 | 1128.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508363 | S-WW-NI-250820-Jedburgh WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-11-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753.37 | 1753.37 | 0 | 0 | 0 | 1753.37 | 0 | 0 | 0 | 0 | 1753.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508357 | S-WW-NI-250820-Nithsbridge WWPS-Pump Control | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1657.98 | 1657.98 | 0 | 0 | 0 | 1657.98 | 0 | 0 | 0 | 0 | 1657.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508355 | S-WW-NI-250820-Troqueer WWTW-Replacement Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1897.8 | 1897.8 | 0 | 0 | 0 | 1897.8 | 0 | 0 | 0 | 0 | 1897.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508968 | S-WW-NI-250920-Armadale WWTW-Final Effluent Auto Sampler Installation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-10-28 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579.46 | 1579.46 | -179.45 | 0 | 0 | 1400.01 | 0 | 0 | 0 | 0 | 1400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508969 | S-WW-NI-250920-Armadale WWTW-Install lifting eye bolt to sludge tank cover | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-11-11 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679.88 | 1679.88 | 0 | 0 | 0 | 1679.88 | 0 | 0 | 0 | 0 | 1679.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508964 | S-WW-NI-250920-Coldstream WWTW-Refurbish RAS pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-10-13 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2530.45 | 2530.45 | 0 | 0 | 0 | 2530.45 | 0 | 0 | 0 | 0 | 2530.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508971 | S-WW-NI-250920-Dalscone WWTW-Replace SC200 Controller for Turbidity Probe | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-10-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1222.55 | 1222.55 | 0 | 0 | 0 | 1222.55 | 0 | 0 | 0 | 0 | 1222.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508970 | S-WW-NI-250920-East Saltoun-Fabricate 2 x fittings for copasacs on the inlet of the works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-10-13 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2268.62 | 2268.62 | 0 | 0 | 0 | 2268.62 | 0 | 0 | 0 | 0 | 2268.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508972 | S-WW-NI-250920-Forth WWTW-Repair to Welfare Heating | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-11-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1770.99 | 1770.99 | 0 | 0 | 0 | 1770.99 | 0 | 0 | 0 | 0 | 1770.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508966 | S-WW-NI-250920-Galashiels WWTW-Strainpress pressure sensor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-10-30 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1424.19 | 1424.19 | 0 | 0 | 0 | 1424.19 | 0 | 0 | 0 | 0 | 1424.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508967 | S-WW-NI-250920-Palnure SEP-Negotations with Landowner Regarding Access | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-25 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300.88 | 300.88 | 769.12 | 0 | 0 | 1070 | 0 | 0 | 0 | 0 | 1070 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508974 | S-WW-NI-250920-Strathaven WWTW-H&S Replace ST handrailing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-25 |  | 2021-02-10 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1225.28 | 1225.28 | 74.72 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508965 | S-WW-NI-250920-Troqueer WWPS-Anti run back device | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-25 |  | 2020-10-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2613.39 | 2613.39 | 0 | 0 | 0 | 2613.39 | 0 | 0 | 0 | 0 | 2613.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503962 | S-WW-NI-251119-Lauder WWPS-H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-27 |  | 2019-12-03 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1464.1 | 0 | 1464.1 | 0 | 0 | 0 | 1464.1 | 0 | 0 | 0 | 0 | 1464.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509988 | S-WW-NI-251120-Annan WWTW-Sludge Tank Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 425.23 | 6074.77 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509992 | S-WW-NI-251120-Cardrona WWPS-Replace 2 pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-03-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3177.02 | 3177.02 | 22.99 | 0 | 0 | 3200.01 | 0 | 0 | 0 | 0 | 3200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509999 | S-WW-NI-251120-Dalry WWTW-Replace RAS Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-03-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3743.61 | 3743.61 | -143.61 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509984 | S-WW-NI-251120-Galashiels WWTW-Various H&S Items | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 509.12 | 509.12 | 6390.88 | 0 | 0 | 6900 | 0 | 0 | 0 | 0 | 6900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510002 | S-WW-NI-251120-Monktonhall WWPS-Repalce Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-02-27 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5510.57 | 5510.57 | -10.57 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 5500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509996 | S-WW-NI-251120-Newton Stewart WWTW-Replacement of the Stone trap | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-03-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4897.76 | 4897.76 | -197.76 | 0 | 0 | 4700 | 0 | 0 | 0 | 0 | 4700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510885 | S-WW-NI-260121-ATHELSTANEFORD WWTW-Install hose and couplings for de-watering pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-11 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1173.35 | 1173.35 | 36 | 0 | 0 | 1209.35 | 0 | 0 | 0 | 0 | 1209.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510887 | S-WW-NI-260121-PENCAITLAND WWTW-Install a chute to the screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-04-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1707.88 | 1707.88 | 1.48 | 0 | 0 | 1709.36 | 0 | 0 | 0 | 0 | 1709.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510883 | S-WW-NI-260121-Stonehouse WWTW-Replace the disc filter backwash pump 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-26 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385.3 | 1385.3 | 14.71 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510894 | S-WW-NI-260121-Whitsome WWTW-Replace pressure relief valves on ferric dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-27 |  | 2021-03-08 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1089.57 | 1089.57 | 19.8 | 0 | 0 | 1109.37 | 0 | 0 | 0 | 0 | 1109.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505421 | S-WW-NI-260220-Allers WWTW-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-04-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 129.15 | 1672.84 | 1801.99 | 0 | 0 | 0 | 1801.99 | 0 | 0 | 0 | 0 | 1801.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505429 | S-WW-NI-260220-Douglas WWTW-Replacement Gearbox & bearings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-03-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1566.4 | 18.47 | 1584.87 | 0 | 0 | 0 | 1584.87 | 0 | 0 | 0 | 0 | 1584.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505418 | S-WW-NI-260220-Eyemouth WWTW-Replace Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-04-09 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 110.64 | 1619.96 | 1730.6 | 0 | 0 | 0 | 1730.6 | 0 | 0 | 0 | 0 | 1730.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505424 | S-WW-NI-260220-Foreland Place WWPS-Emergency Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-02-27 |  | 2020-03-31 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 23280.72 | 701.58 | 23982.3 | 0 | 0 | 0 | 23982.3 | 0 | 0 | 0 | 0 | 23982.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511497 | S-WW-NI-260221-Duns WWTW-Install spare autosampler | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-01 |  | 2021-05-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220.11 | 220.11 | 1600 | 0 | 0 | 1820.11 | 0 | 0 | 0 | 0 | 1820.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511485 | S-WW-NI-260221-Glassford WWTW-Upgrade the GE Fanuc 90-30 PLC to a Siemens S7-1500 PLC | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-03-10 | 2021-08-13 | 2022-03-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753.27 | 1753.27 | 23046.73 | 0 | 0 | 24800 | 0 | 0 | 0 | 0 | 24800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511501 | S-WW-NI-260221-Jedburgh WWTW-Replace RAS pump no3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-01 |  | 2021-05-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1375.1 | 1375.1 | 724.9 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505941 | S-WW-NI-26032020-BURNHEAD WWPS-Pump Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-05-06 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1093.41 | 1093.41 | 0 | 0 | 0 | 1093.41 | 0 | 0 | 0 | 0 | 1093.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505943 | S-WW-NI-26032020-Dunbar WWTW-Replacement DO Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-04-18 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100.31 | 1100.31 | 0 | 0 | 0 | 1100.31 | 0 | 0 | 0 | 0 | 1100.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505952 | S-WW-NI-26032020-Fauldhouse WWTW-Refurbishment of the inlet screen basket | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-04-06 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 4082.61 | 18.47 | 4101.08 | 0 | 0 | 0 | 4101.08 | 0 | 0 | 0 | 0 | 4101.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505945 | S-WW-NI-26032020-Loch Ryan WWTW-Generator Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-04-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 5121.84 | 18.47 | 5140.31 | 0 | 0 | 0 | 5140.31 | 0 | 0 | 0 | 0 | 5140.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505947 | S-WW-NI-26032020-Philipshill WWTW-For fitting a telemetry signal to the ICC for the fire alarm | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-04-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 27.66 | 3171.24 | 3198.9 | 0 | 0 | 0 | 3198.9 | 0 | 0 | 0 | 0 | 3198.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505950 | S-WW-NI-26032020-Whitecross WWTW-Replacement of badly rusted gratings hatches and support brackets | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-08-14 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 165.96 | 3907.66 | 4073.62 | 0 | 0 | 0 | 4073.62 | 0 | 0 | 0 | 0 | 4073.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512061 | S-WW-NI-260321- ANNAN WWTW 1970 NY193651 - REFURBISH COMPACTOR | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1200 | 0 | 0 | 1291.59 | 0 | 0 | 0 | 0 | 1291.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512057 | S-WW-NI-260321- ROCKCLIFFE WWTW NX853532 - REFURBISH STORM PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510.28 | 510.28 | 6685.74 | 0 | 0 | 7196.02 | 0 | 0 | 0 | 0 | 7196.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512053 | S-WW-NI-260321-GAVINTON WWPS NT772524 - REPLACE PUMP 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 124.3 | 1628.58 | 0 | 0 | 1752.88 | 0 | 0 | 0 | 0 | 1752.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512055 | S-WW-NI-260321-Hamilton_STW_FST2 Bearing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1371.42 | 0 | 0 | 1476.09 | 0 | 0 | 0 | 0 | 1476.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512054 | S-WW-NI-260321-Philipshill_STW_Desludge Pump 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242.06 | 242.06 | 3171.42 | 0 | 0 | 3413.48 | 0 | 0 | 0 | 0 | 3413.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512052 | S-WW-NI-260321-Philipshill_STW_Pressure & Air flow transducers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-26 |  | 2021-06-26 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.89 | 215.89 | 2828.58 | 0 | 0 | 3044.47 | 0 | 0 | 0 | 0 | 3044.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507389 | S-WW-NI-260620-Carfin WWPS-Pump Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-30 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3208.8 | 3208.8 | 0 | 0 | 0 | 3208.8 | 0 | 0 | 0 | 0 | 3208.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507393 | S-WW-NI-260620-Galashiels STC-Gearbox Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2942.87 | 2942.87 | 0 | 0 | 0 | 2942.87 | 0 | 0 | 0 | 0 | 2942.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507383 | S-WW-NI-260620-Galashiels-Replacement Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200.52 | 4200.52 | 0 | 0 | 0 | 4200.52 | 0 | 0 | 0 | 0 | 4200.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507385 | S-WW-NI-260620-Harthill WWTW-Install autowasting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-08-25 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5774.72 | 5774.72 | 0 | 0 | 0 | 5774.72 | 0 | 0 | 0 | 0 | 5774.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507395 | S-WW-NI-260620-Harthill WWTW-Install Drive onto the Filter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-06-29 |  | 2021-08-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15580.16 | 15580.16 | 169419.85 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 185000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507390 | S-WW-NI-260620-North Berwick WWTW-Carry out an inspection of all three inlet pump guiderails | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-06-29 |  | 2020-10-07 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11567.19 | 11567.19 | 18500 | 0 | 0 | 30067.19 | 0 | 0 | 0 | 0 | 30067.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507394 | S-WW-NI-260620-Pencaitland WWTW-Install Gratings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-13 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1497.48 | 1497.48 | 0 | 0 | 0 | 1497.48 | 0 | 0 | 0 | 0 | 1497.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507388 | S-WW-NI-260620-Penicuik WWTW-Reroofing the facilities building | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-10-29 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500.92 | 10500.92 | 0 | 0 | 0 | 10500.92 | 0 | 0 | 0 | 0 | 10500.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507381 | S-WW-NI-260620-Reston WWTW-Replacement Gratings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-29 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417.37 | 417.37 | 3282.63 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 3700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507380 | S-WW-NI-260620-Tweed Bank WWPS-Screen Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-08-03 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10610.55 | 10610.55 | 0 | 0 | 0 | 10610.55 | 0 | 0 | 0 | 0 | 10610.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508377 | S-WW-NI-260820-Almondvale WWPS-Replace Pump No1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-10-19 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4370.9 | 4370.9 | 0 | 0 | 0 | 4370.9 | 0 | 0 | 0 | 0 | 4370.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508380 | S-WW-NI-260820-Annan WWTW-Replace faulty valve and rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5318.36 | 5318.36 | 0 | 0 | 0 | 5318.36 | 0 | 0 | 0 | 0 | 5318.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508389 | S-WW-NI-260820-Dunnswood WWTW-Replace Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-10-16 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6690.75 | 6690.75 | 0 | 0 | 0 | 6690.75 | 0 | 0 | 0 | 0 | 6690.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508387 | S-WW-NI-260820-Glespin WWTW-Distribution Tank Investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-09-01 | 2020-11-23 | 2021-03-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30371 | 30371 | 0 | 0 | 0 | 30371 | 0 | 0 | 0 | 0 | 30371 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508383 | S-WW-NI-260820-Hawick WWTW-Replace Storm Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5689.21 | 5689.21 | 0 | 0 | 0 | 5689.21 | 0 | 0 | 0 | 0 | 5689.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508385 | S-WW-NI-260820-Newton St Boswells WWTW-Compressor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-09-03 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3342.34 | 3342.34 | 0 | 0 | 0 | 3342.34 | 0 | 0 | 0 | 0 | 3342.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508376 | S-WW-NI-260820-Philipshill WWTW-Flooding Remedial Work | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-26 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528.75 | 528.75 | 6671.25 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 7200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508402 | S-WW-NI-260820-Stonehouse WWTW-Refurb Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-26 |  | 2020-10-21 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3628.84 | 3628.84 | 0 | 0 | 0 | 3628.84 | 0 | 0 | 0 | 0 | 3628.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509453 | S-WW-NI-261020-Daldowie WWTW-Provide and install two replacement NTF pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-28 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.72 | 57.72 | 81142.28 | 0 | 0 | 81200 | 0 | 0 | 0 | 0 | 81200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509460 | S-WW-NI-261020-Ormiston WWTW-Upgrade the tertiary compressor 2 air comp control system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-28 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1682.24 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509457 | S-WW-NI-261020-Patthead WWTW-Critical spare humus return pump and impellor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-10-12 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513.19 | 1513.19 | 0 | 0 | 0 | 1513.19 | 0 | 0 | 0 | 0 | 1513.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509464 | S-WW-NI-261020-Winchburgh WWTW-Replace the Lower Inlet Gate Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-28 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.43 | 222.43 | 3177.57 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503993 | S-WW-NI-261119-Kelso WWTW-Refurb Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-27 |  | 2020-04-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1257.02 | 811.92 | 2068.94 | 0 | 0 | 0 | 2068.94 | 0 | 0 | 0 | 0 | 2068.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503975 | S-WW-NI-261119-Kirkconnel WWTW-FE Pumping Station Steelwork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-27 |  | 2020-02-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 4990.68 | 18.7 | 5009.38 | 0 | 0 | 0 | 5009.38 | 0 | 0 | 0 | 0 | 5009.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510015 | S-WW-NI-261120-Allers WWTW-Replace NRV on pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-03 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933.01 | 1933.01 | 66.99 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510017 | S-WW-NI-261120-Annan WWTW-Replace chain for self closing gate at dry well entrance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-03-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1496.48 | 1496.48 | 3.52 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510014 | S-WW-NI-261120-Coldstream WWTW-Refurb H&S Steps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-03 |  | 2020-06-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1504.01 | 1504.01 | -4.01 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510012 | S-WW-NI-261120-Ormiston WWTW-Replace gear box and motor for PST | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634.03 | 634.03 | 7865.97 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 8500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504869 | S-WW-NI-270120-Allers WWTW-Replace Brush Assembly | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-07-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1783.7 | 504.9 | 2288.6 | 0 | 0 | 0 | 2288.6 | 0 | 0 | 0 | 0 | 2288.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504859 | S-WW-NI-270120-Dunnswood WWTW-Replacement Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-03-23 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 6335.28 | 0 | 6335.28 | 0 | 0 | 0 | 6335.28 | 0 | 0 | 0 | 0 | 6335.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504876 | S-WW-NI-270120-Philipshill WWTW-Replacement Parts for HMI | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-02-19 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1177.01 | 0 | 1177.01 | 0 | 0 | 0 | 1177.01 | 0 | 0 | 0 | 0 | 1177.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504853 | S-WW-NI-270120-Rosewell WWTW-Refurb Submersible Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-27 |  | 2020-04-17 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 1783.7 | 507.42 | 2291.12 | 0 | 0 | 0 | 2291.12 | 0 | 0 | 0 | 0 | 2291.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510923 | S-WW-NI-270121-Galashiels STC-Replace basket & rake on screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1776.2 | 1776.2 | 23342.48 | 0 | 0 | 25118.68 | 0 | 0 | 0 | 0 | 25118.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510912 | S-WW-NI-270121-Galashiels STC-Replace digester pressure relief valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539.76 | 539.76 | 5678.96 | 0 | 0 | 6218.72 | 0 | 0 | 0 | 0 | 6218.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510915 | S-WW-NI-270121-Hawick STC-Refurbish digester pressure relief valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474.34 | 474.34 | 4744.36 | 0 | 0 | 5218.7 | 0 | 0 | 0 | 0 | 5218.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510909 | S-WW-NI-270121-Hawick WWTW-Replace Final tank no2 gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140.7 | 1140.7 | 13996.72 | 0 | 0 | 15137.42 | 0 | 0 | 0 | 0 | 15137.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510920 | S-WW-NI-270121-UPPER BURNMOUTH WWPS-Replace 2 pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6391.4 | 6391.4 | 8.61 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 6400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505965 | S-WW-NI-27032020-Galashiels WWTW-Replace Recirculation Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-05-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3674.62 | 3674.62 | 0 | 0 | 0 | 3674.62 | 0 | 0 | 0 | 0 | 3674.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505966 | S-WW-NI-27032020-Hawick WWTW-Replacement RAS Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-08-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8955.06 | 8955.06 | 0 | 0 | 0 | 8955.06 | 0 | 0 | 0 | 0 | 8955.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505964 | S-WW-NI-27032020-Loch Ryan WWTW-Replacement PST2 Scrapers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-06-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3563.24 | 3563.24 | 0 | 0 | 0 | 3563.24 | 0 | 0 | 0 | 0 | 3563.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505972 | S-WW-NI-27032020-North Berwick WWTW-Replacememt Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-05-06 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880.47 | 2880.47 | 0 | 0 | 0 | 2880.47 | 0 | 0 | 0 | 0 | 2880.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505973 | S-WW-NI-27032020-Pond Hall WWPS-Replace UPS Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-06-22 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3360.35 | 3360.35 | 0 | 0 | 0 | 3360.35 | 0 | 0 | 0 | 0 | 3360.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505974 | S-WW-NI-27032020-Trinity WWPS-Investigation and refurbishment of the long sea outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-09-15 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4817.91 | 4817.91 | 0 | 0 | 0 | 4817.91 | 0 | 0 | 0 | 0 | 4817.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505963 | S-WW-NI-27032020-Troqueer WWTW-Folomatic control works on inlet actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-04-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2955.71 | 2955.71 | 0 | 0 | 0 | 2955.71 | 0 | 0 | 0 | 0 | 2955.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505967 | S-WW-NI-27032020-Walkerburn WWTW-Pump Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-05-27 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3463.43 | 166.52 | 3629.95 | 0 | 0 | 0 | 3629.95 | 0 | 0 | 0 | 0 | 3629.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506859 | S-WW-NI-270520-Earlston WWTW-Refurbishment of sprinkler columns | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-06-11 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2858.16 | 2858.16 | 0 | 0 | 0 | 2858.16 | 0 | 0 | 0 | 0 | 2858.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506866 | S-WW-NI-270520-Eastriggs WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-08-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5309.3 | 5309.3 | 0 | 0 | 0 | 5309.3 | 0 | 0 | 0 | 0 | 5309.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506855 | S-WW-NI-270520-Gatehouse WWTW-Inlet Screen Investigation & Scope | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2021-03-19 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892.9 | 892.9 | 0 | 0 | 0 | 892.9 | 0 | 0 | 0 | 0 | 892.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506843 | S-WW-NI-270520-Hamilton WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-06-16 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4428.34 | 4428.34 | 0 | 0 | 0 | 4428.34 | 0 | 0 | 0 | 0 | 4428.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506850 | S-WW-NI-270520-Hutton North SEP-Purchase of Land | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-27 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6380.01 | 6380.01 | 33276.11 | 0 | 0 | 39656.12 | 0 | 0 | 0 | 0 | 39656.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506863 | S-WW-NI-270520-Loch Ryan WWTW-Repair to perculating filter column | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-08-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7739.32 | 7739.32 | 0 | 0 | 0 | 7739.32 | 0 | 0 | 0 | 0 | 7739.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506848 | S-WW-NI-270520-Troqueer STC-Supply & Fit Load Monitors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-09-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8563.94 | 8563.94 | 0 | 0 | 0 | 8563.94 | 0 | 0 | 0 | 0 | 8563.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506846 | S-WW-NI-270520-Troqueer WWTW-Install Sump Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-27 |  | 2020-07-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4651.11 | 4651.11 | 0 | 0 | 0 | 4651.11 | 0 | 0 | 0 | 0 | 4651.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507887 | S-WW-NI-270720-Biggar WWTW-Refurb inlet flow meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-08-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2293.5 | 2293.5 | 0 | 0 | 0 | 2293.5 | 0 | 0 | 0 | 0 | 2293.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507900 | S-WW-NI-270720-Dalscone WWTW-Repair Filter Distribution Arms | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-08-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768.74 | 1768.74 | 0 | 0 | 0 | 1768.74 | 0 | 0 | 0 | 0 | 1768.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507898 | S-WW-NI-270720-Galashiels STC-Temp Sensor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-27 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290.23 | 290.23 | 1828.48 | 0 | 0 | 2118.71 | 0 | 0 | 0 | 0 | 2118.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507885 | S-WW-NI-270720-Harthill WWTW-Replace MLSS for autowasting | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-27 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802.9 | 1802.9 | 297.1 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507882 | S-WW-NI-270720-Mauldslie WWTW-Replace Inlet Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-09-13 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1164.5 | 1164.5 | 0 | 0 | 0 | 1164.5 | 0 | 0 | 0 | 0 | 1164.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507891 | S-WW-NI-270720-Patthead WWTW-Various H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-09-03 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675.56 | 1675.56 | 0 | 0 | 0 | 1675.56 | 0 | 0 | 0 | 0 | 1675.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508409 | S-WW-NI-270820-Coldstream WWTW-Replace washdown hose system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-09-14 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3239.14 | 3239.14 | 0 | 0 | 0 | 3239.14 | 0 | 0 | 0 | 0 | 3239.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508433 | S-WW-NI-270820-Cummertrees SEP-Replace Manhole covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-11-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2096.28 | 2096.28 | 0 | 0 | 0 | 2096.28 | 0 | 0 | 0 | 0 | 2096.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508417 | S-WW-NI-270820-Dalscone Old WWTW-Supply and fit connection pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-10-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4284.73 | 4284.73 | 0 | 0 | 0 | 4284.73 | 0 | 0 | 0 | 0 | 4284.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508429 | S-WW-NI-270820-Enterprise Park WWPS-Install fall protect system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2276.54 | 2276.54 | -76.53 | 0 | 0 | 2200.01 | 0 | 0 | 0 | 0 | 2200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508424 | S-WW-NI-270820-Gorebridge WWTW-Install a fixed swing jib & a tralif | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-27 |  | 2021-02-20 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3178.06 | 3178.06 | 21.95 | 0 | 0 | 3200.01 | 0 | 0 | 0 | 0 | 3200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508410 | S-WW-NI-270820-Lanark WWTW-Remove tanker loading gantry | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-11-04 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6930.29 | 6930.29 | 0 | 0 | 0 | 6930.29 | 0 | 0 | 0 | 0 | 6930.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508420 | S-WW-NI-270820-Troqueer WWTW- PH probes and a PH controller | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-27 |  | 2020-11-05 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3375.63 | 3375.63 | 0 | 0 | 0 | 3375.63 | 0 | 0 | 0 | 0 | 3375.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508427 | S-WW-NI-270820-Victoria Harb WWPS-Repair Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-27 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172.9 | 172.9 | 2327.1 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508426 | S-WW-NI-270820-Westmains WWPS-Replace Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-09-08 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1503 | 1503 | 0 | 0 | 0 | 1503 | 0 | 0 | 0 | 0 | 1503 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509493 | S-WW-NI-271020-Kelso WWTW-Refurbish scum box & Scraper | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-11-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679.01 | 1679.01 | 0 | 0 | 0 | 1679.01 | 0 | 0 | 0 | 0 | 1679.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509488 | S-WW-NI-271020-Spott Sep-Replacement Work | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-29 |  | 2020-11-10 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1589.67 | 1589.67 | 0 | 0 | 0 | 1589.67 | 0 | 0 | 0 | 0 | 1589.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504005 | S-WW-NI-271119-Ancrum WWTW-Microstrainer Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3519.92 | 18.7 | 3538.62 | -338.62 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504000 | S-WW-NI-271119-Ashgill WWTW-Remedial Works on Sand Filters | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-27 |  | 2020-05-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 10391.52 | 25883.94 | 36275.46 | 0 | 0 | 0 | 36275.46 | 0 | 0 | 0 | 0 | 36275.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504003 | S-WW-NI-271119-Bathgate WWTW-Install Decant Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-27 |  | 2020-03-31 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 7082.28 | 0 | 7082.28 | 0 | 0 | 0 | 7082.28 | 0 | 0 | 0 | 0 | 7082.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504010 | S-WW-NI-271119-Galashiels STC-Refurb Pump 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-27 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | -3028 | 272.01 | 3027.99 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503997 | S-WW-NI-271119-Glassford WWTW-Replace Inlet Actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-27 |  | 2020-02-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 2794.98 | 0 | 2794.98 | 0 | 0 | 0 | 2794.98 | 0 | 0 | 0 | 0 | 2794.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503996 | S-WW-NI-271119-Lesmahagow WWTW-Grit Rake Overhaul | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-27 |  | 2020-02-27 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 14741.35 | 46.76 | 14788.11 | 0 | 0 | 0 | 14788.11 | 0 | 0 | 0 | 0 | 14788.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510034 | S-WW-NI-271120-Lockerbie WWPS-Install fall arrest to dry well | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-04-03 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2142.39 | 2142.39 | 57.61 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510030 | S-WW-NI-271120-Strathaven WWTW-PST 1 desludge actuator Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-03 |  | 2021-02-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1162.45 | 1162.45 | 37.55 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504890 | S-WW-NI-280120-Langholm WWTW-Replacement Access Stairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-03-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4435.44 | 0 | 4435.44 | 0 | 0 | 0 | 4435.44 | 0 | 0 | 0 | 0 | 4435.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510929 | S-WW-NI-280121-Annan WWTW-Motor & Gearbox for grit classifier | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448.16 | 448.16 | 4370.52 | 0 | 0 | 4818.68 | 0 | 0 | 0 | 0 | 4818.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510930 | S-WW-NI-280121-Armadale WWTW-Replace sand filter washwater pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454.7 | 454.7 | 4464 | 0 | 0 | 4918.7 | 0 | 0 | 0 | 0 | 4918.7 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510932 | S-WW-NI-280121-Dunbar WWTW-Purchase a Hach DR3900 & HachDR1900 spectrophotometer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-28 |  | 2021-04-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5803.05 | 5803.05 | -3.04 | 0 | 0 | 5800.01 | 0 | 0 | 0 | 0 | 5800.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510934 | S-WW-NI-280121-Eastfield WWPS-Installation of a replacement clamp | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-28 |  | 2021-03-19 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2981.52 | 2981.52 | 18.48 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510943 | S-WW-NI-280121-Greengairs WWTW-To provide and install a replacement actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1282.62 | 1282.62 | 17.39 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510939 | S-WW-NI-280121-Hamilton WWTW-Replace centre bearing of FST 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-28 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14163.76 | 14163.76 | -163.76 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 14000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512065 | S-WW-NI-280321- PORT RODIE WWPS NX062610 - SPARE PUMP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-28 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1871.03 | 1871.03 | 26728.97 | 0 | 0 | 28600 | 0 | 0 | 0 | 0 | 28600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506376 | S-WW-NI-280420-Loch Ryan WWTW-refurb of the grit classifier | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-05-11 | 2020-06-29 | 2020-10-27 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14402.79 | 14402.79 | 0 | 0 | 0 | 14402.79 | 0 | 0 | 0 | 0 | 14402.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506378 | S-WW-NI-280420-Mavor Roundabout EK-Excavate in the carriageway to repair 4.6m deep sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-05-11 |  | 2021-07-30 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68457 | 68457 | 11542.74 | 0 | 0 | 79999.74 | 0 | 0 | 0 | 0 | 79999.74 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506381 | S-WW-NI-280420-TERREGLES PUMP STN -Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-06-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.22 | 2504.22 | 0 | 0 | 0 | 2504.22 | 0 | 0 | 0 | 0 | 2504.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506877 | S-WW-NI-280520-Newton St Boswells WWTW-Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-06-11 |  | 2021-05-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165568.16 | 165568.16 | 60032.8 | 0 | 0 | 225600.96 | 0 | 0 | 0 | 0 | 225600.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506875 | S-WW-NI-280520-Philipshill WWTW-Replace SCADA | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-11 |  | 2021-02-21 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13980.96 | 13980.96 | 19.04 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 14000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506882 | S-WW-NI-280520-Port Edgar WWTW-Install Conveyor Gear Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-06-15 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2646.56 | 2646.56 | 0 | 0 | 0 | 2646.56 | 0 | 0 | 0 | 0 | 2646.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506887 | S-WW-NI-280520-Unit 8 South Avenue Blantyre-Sewer Repair | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-06-29 | 2020-09-14 | 2021-08-16 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100389.62 | 100389.62 | 99610.38 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506878 | S-WW-NI-280520-Walkerburn WWTW-Replace Screw Pump Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-11 |  | 2020-06-25 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2132.3 | 2132.3 | 0 | 0 | 0 | 2132.3 | 0 | 0 | 0 | 0 | 2132.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507915 | S-WW-NI-280720-BALMACLELLAN WWTW- Repair T-bar & mesh panel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-28 |  | 2020-10-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040.89 | 2040.89 | 0 | 0 | 0 | 2040.89 | 0 | 0 | 0 | 0 | 2040.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507910 | S-WW-NI-280720-Chapelton WWTW-Replace RAS screw | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-08-05 | 2021-04-02 | 2021-11-15 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38217 | 38217 | 85282.88 | 0 | 0 | 123499.88 | 0 | 0 | 0 | 0 | 123499.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507908 | S-WW-NI-280720-Coursington WWTW-Replace the Anoxic Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-28 |  | 2020-09-19 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1881.61 | 1881.61 | 0 | 0 | 0 | 1881.61 | 0 | 0 | 0 | 0 | 1881.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507921 | S-WW-NI-280720-Dunbar WWTW-Replace Wash Water Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-28 |  | 2020-08-21 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2477.55 | 2477.55 | 0 | 0 | 0 | 2477.55 | 0 | 0 | 0 | 0 | 2477.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508454 | S-WW-NI-280820-Armadale WWTW-Supply of critical spare storm pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-10-23 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2694.38 | 2694.38 | 0 | 0 | 0 | 2694.38 | 0 | 0 | 0 | 0 | 2694.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508452 | S-WW-NI-280820-Beauchburn WWTW- H&S anchor point | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-11-04 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1742.83 | 1742.83 | 0 | 0 | 0 | 1742.83 | 0 | 0 | 0 | 0 | 1742.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508448 | S-WW-NI-280820-Coldstream WWTW-Replace sludge return pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-09-30 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1173.5 | 1173.5 | 0 | 0 | 0 | 1173.5 | 0 | 0 | 0 | 0 | 1173.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508445 | S-WW-NI-280820-Enterprise Park WWPS1-Fall Protection | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | 9.35 | 2190.65 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508450 | S-WW-NI-280820-Kelso WWTW-Refurb Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-09-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1173.5 | 1173.5 | 0 | 0 | 0 | 1173.5 | 0 | 0 | 0 | 0 | 1173.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508451 | S-WW-NI-280820-Lauder WWTW-Replace Sludge return pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-10-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1286.17 | 1286.17 | 0 | 0 | 0 | 1286.17 | 0 | 0 | 0 | 0 | 1286.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508441 | S-WW-NI-280820-Linlithgow WWTW-Replace dosing Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-28 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1872.66 | 1872.66 | 27.35 | 0 | 0 | 1900.01 | 0 | 0 | 0 | 0 | 1900.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508440 | S-WW-NI-280820-Mauldslie WWTW-Tanker loading couplings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-10-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139.85 | 1139.85 | 0 | 0 | 0 | 1139.85 | 0 | 0 | 0 | 0 | 1139.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508442 | S-WW-NI-280820-Newton Stewart WWTW-Investigation of Grit Storage Bay | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-09-01 | 2021-03-15 | 2021-05-13 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6348 | 6348 | 3651.74 | 0 | 0 | 9999.74 | 0 | 0 | 0 | 0 | 9999.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508443 | S-WW-NI-280820-Newtown Mill WWPS-Investigate private road repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-09-01 | 2020-11-02 | 2021-01-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22964 | 22964 | 569.19 | 0 | 0 | 23533.19 | 0 | 0 | 0 | 0 | 23533.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509509 | S-WW-NI-281020-Bathgate WWTW-Replace Motor and Gearbox on Sand Filter No 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-10-12 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6093.52 | 6093.52 | 0 | 0 | 0 | 6093.52 | 0 | 0 | 0 | 0 | 6093.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509506 | S-WW-NI-281020-Cuthill Cres WWPS-Replace Grinder Unit | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13012.82 | 13012.82 | -212.82 | 0 | 0 | 12800 | 0 | 0 | 0 | 0 | 12800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509517 | S-WW-NI-281020-Denholm WWTW-Install aeration tank valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-28 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3184.18 | 3184.18 | -284.18 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509523 | S-WW-NI-281020-Galashiels STC-Refurbish screens sludge tank mixer no.1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-28 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13400.22 | 13400.22 | -81.51 | 0 | 0 | 13318.71 | 0 | 0 | 0 | 0 | 13318.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509521 | S-WW-NI-281020-Hawick WWTW-Replace no.3 Mixers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5431.15 | 5431.15 | -31.15 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 5400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509514 | S-WW-NI-281020-Langholm WWTW-Refurbish Filter drives motors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-11-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3495.22 | 3495.22 | 0 | 0 | 0 | 3495.22 | 0 | 0 | 0 | 0 | 3495.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509502 | S-WW-NI-281020-Old Graitney WWPS-Fall protection on wetwell | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2021-02-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4308.22 | 4308.22 | -108.22 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509527 | S-WW-NI-281020-Quarter WWPS-Provide and install replacement pump for #2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-28 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410.07 | 410.07 | 4689.94 | 0 | 0 | 5100.01 | 0 | 0 | 0 | 0 | 5100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504024 | S-WW-NI-281119- | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-28 |  | 2020-06-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4367.91 | 3190.67 | 7558.58 | 0 | 0 | 0 | 7558.58 | 0 | 0 | 0 | 0 | 7558.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504050 | S-WW-NI-281119-Amisfield WWTW-Provide Sound Booth | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-01-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 3833.61 | 0 | 3833.61 | 0 | 0 | 0 | 3833.61 | 0 | 0 | 0 | 0 | 3833.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504028 | S-WW-NI-281119-Annan WWTW - Repalce Slip Ring on FST1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-28 |  | 2020-02-13 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4382.93 | 0 | 4382.93 | 0 | 0 | 0 | 4382.93 | 0 | 0 | 0 | 0 | 4382.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504041 | S-WW-NI-281119-Dunnswood WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-01-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 3677.06 | 0 | 3677.06 | 0 | 0 | 0 | 3677.06 | 0 | 0 | 0 | 0 | 3677.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504021 | S-WW-NI-281119-Galashiels WWTW-Replace Recirc Pump3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-28 |  | 2020-01-04 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 6881.59 | 0 | 6881.59 | 0 | 0 | 0 | 6881.59 | 0 | 0 | 0 | 0 | 6881.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504035 | S-WW-NI-281119-Hamilton WWTW-Survey & Repair Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-13 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 8798.22 | -7848.13 | 950.09 | 13149.91 | 0 | 0 | 14100 | 0 | 0 | 0 | 0 | 14100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504022 | S-WW-NI-281119-Leet Green WWPS-Install VSD on 2pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-28 |  | 2019-12-19 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4384.96 | 0 | 4384.96 | 0 | 0 | 0 | 4384.96 | 0 | 0 | 0 | 0 | 4384.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504060 | S-WW-NI-281119-Loch Ryan WWTW-Refurb Launder Trough | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-02-11 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 8923.67 | 0 | 8923.67 | 0 | 0 | 0 | 8923.67 | 0 | 0 | 0 | 0 | 8923.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504030 | S-WW-NI-281119-Moffat WWTW-Replacement FST Wheel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-01-08 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 3227.94 | 0 | 3227.94 | 0 | 0 | 0 | 3227.94 | 0 | 0 | 0 | 0 | 3227.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504031 | S-WW-NI-281119-Newton St Boswells WWTW-Refurb Inlet Screen | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-04-29 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 6901.97 | 37.41 | 6939.38 | 0 | 0 | 0 | 6939.38 | 0 | 0 | 0 | 0 | 6939.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504044 | S-WW-NI-281119-Port Rodie WWPS- Replacement of UPS batteries & panel | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-04-30 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 2508.54 | 1601.6 | 4110.14 | 0 | 0 | 0 | 4110.14 | 0 | 0 | 0 | 0 | 4110.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504048 | S-WW-NI-281119-Troqueer WWTW-Replace Sludge Tank Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2019-12-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 7023.14 | 0 | 7023.14 | 0 | 0 | 0 | 7023.14 | 0 | 0 | 0 | 0 | 7023.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504902 | S-WW-NI-290120-Bathgate WWTW-Various H&S Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-31 |  | 2021-02-28 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 29700 | -75.16 | 29624.84 | 75.16 | 0 | 0 | 29700 | 0 | 0 | 0 | 0 | 29700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504920 | S-WW-NI-290120-Coldstream WWTW-Gantry for lifting Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 5300 | -4875.25 | 424.76 | 4944.04 | 0 | 0 | 5368.8 | 0 | 0 | 0 | 0 | 5368.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504917 | S-WW-NI-290120-Coldstream WWTW-Refurb Sludge Tank Stairs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-31 |  | 2021-02-28 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 9800 | 118.88 | 9918.88 | -118.88 | 0 | 0 | 9800 | 0 | 0 | 0 | 0 | 9800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504914 | S-WW-NI-290120-Cove WWTW-H&S around final sample chamber | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-31 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 8900 | 43.8 | 8943.8 | -43.8 | 0 | 0 | 8900 | 0 | 0 | 0 | 0 | 8900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504898 | S-WW-NI-290120-Daldowie WWTW-Replacement Screen Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-04-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | -21.58 | 5078.42 | 0 | 0 | 0 | 5078.42 | 0 | 0 | 0 | 0 | 5078.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504922 | S-WW-NI-290120-Doonside Towers WWPS-Repalcement Duckfoot | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-06-26 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | -18.79 | 9981.22 | 0 | 0 | 0 | 9981.22 | 0 | 0 | 0 | 0 | 9981.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504915 | S-WW-NI-290120-Galashiels STC-Repalcement Sludge Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-02-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 5872.02 | 0 | 5872.02 | 0 | 0 | 0 | 5872.02 | 0 | 0 | 0 | 0 | 5872.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504905 | S-WW-NI-290120-Loch Ryan WWTW-Refurb Launder Trough | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-03-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 8983.41 | 0 | 8983.41 | 0 | 0 | 0 | 8983.41 | 0 | 0 | 0 | 0 | 8983.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504908 | S-WW-NI-290120-Newbridge WWPS-2No Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-03-24 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 5055.17 | 0 | 5055.17 | 0 | 0 | 0 | 5055.17 | 0 | 0 | 0 | 0 | 5055.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504924 | S-WW-NI-290120-Ormiston WWTW-Supply & Fit Air Vents | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-02-11 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3438.21 | -0.01 | 3438.2 | 0 | 0 | 0 | 3438.2 | 0 | 0 | 0 | 0 | 3438.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504901 | S-WW-NI-290120-Philipshill WWTW-Replace Site Drainage | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-04-20 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | -3.03 | 11196.97 | 0 | 0 | 0 | 11196.97 | 0 | 0 | 0 | 0 | 11196.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504911 | S-WW-NI-290120-Troqueer STC-Installation of Perpex & Heaters at Poly Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-03-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 6074.24 | -0.01 | 6074.23 | 0 | 0 | 0 | 6074.23 | 0 | 0 | 0 | 0 | 6074.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510978 | S-WW-NI-290121-19 Townhead Crescent Castle Douglas-feasability study | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2021-02-04 | 2021-05-21 | 2022-01-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.89 | 215.89 | 3084.08 | 0 | 0 | 3299.97 | 0 | 0 | 0 | 0 | 3299.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510972 | S-WW-NI-290121-Annan WWTW-New Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-29 |  | 2021-03-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2521.08 | 2521.08 | -202.4 | 0 | 0 | 2318.68 | 0 | 0 | 0 | 0 | 2318.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510965 | S-WW-NI-290121-Carbarns WWTW-replacement actuator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 2056.08 | 0 | 0 | 2200.01 | 0 | 0 | 0 | 0 | 2200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510980 | S-WW-NI-290121-Chapelton WWTW-Replace the solenoid valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-01 |  | 2021-03-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1159.7 | 1159.7 | 40.28 | 0 | 0 | 1199.98 | 0 | 0 | 0 | 0 | 1199.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510985 | S-WW-NI-290121-Hamilton WWTW-RAS channel refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224.2 | 224.2 | -176.64 | 0 | 0 | 47.56 | 0 | 0 | 0 | 0 | 47.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510969 | S-WW-NI-290121-Philipshill WWTW-Purchase a critical spare motor and gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-29 |  | 2021-03-17 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2394.53 | 2394.53 | 63.2 | 0 | 0 | 2457.73 | 0 | 0 | 0 | 0 | 2457.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510983 | S-WW-NI-290121-Philipshill WWTW-Replace power cabling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165.32 | 165.32 | 3752.24 | 0 | 0 | 3917.56 | 0 | 0 | 0 | 0 | 3917.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510979 | S-WW-NI-290121-Rigside WWTW-New Rotork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235.05 | 1235.05 | 64.95 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510975 | S-WW-NI-290121-Whitsome WWTW-Replace Ferric Dosing Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-29 |  | 2021-03-15 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1092.5 | 1092.5 | 107.48 | 0 | 0 | 1199.98 | 0 | 0 | 0 | 0 | 1199.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506388 | S-WW-NI-290420-Cairnryan WWPS-Replace Stena Flow Meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-09-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3059.52 | 3059.52 | 0 | 0 | 0 | 3059.52 | 0 | 0 | 0 | 0 | 3059.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506394 | S-WW-NI-290420-Eastriggs WWTW-Mixer Refurb | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-05-22 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4080.18 | 4080.18 | 0 | 0 | 0 | 4080.18 | 0 | 0 | 0 | 0 | 4080.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506390 | S-WW-NI-290420-Rockcliffe WWTW-Various H&S Work | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-06-29 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2784.74 | 2784.74 | 0 | 0 | 0 | 2784.74 | 0 | 0 | 0 | 0 | 2784.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507406 | S-WW-NI-290620-Athelstaneford WWTW-H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-08-03 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2244.82 | 2244.82 | 0 | 0 | 0 | 2244.82 | 0 | 0 | 0 | 0 | 2244.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507402 | S-WW-NI-290620-Carrington WWTW-Install hand rails & kick plates | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-23 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2148.28 | 2148.28 | 0 | 0 | 0 | 2148.28 | 0 | 0 | 0 | 0 | 2148.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507400 | S-WW-NI-290620-Dalscone WWTW-Repair Bridge & Access Rd | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-06-29 |  | 2020-09-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10362.92 | 10362.92 | 0 | 0 | 0 | 10362.92 | 0 | 0 | 0 | 0 | 10362.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507413 | S-WW-NI-290620-Eastfield WWPS-Fitting H&S Gate | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-08-24 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903.65 | 1903.65 | 0 | 0 | 0 | 1903.65 | 0 | 0 | 0 | 0 | 1903.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507416 | S-WW-NI-290620-Killburn WWPS-Install Gate & Railings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-20 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1645.56 | 1645.56 | 0 | 0 | 0 | 1645.56 | 0 | 0 | 0 | 0 | 1645.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507417 | S-WW-NI-290620-Lanark WWTW-replace sensor for MLSS meter | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-16 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2352.17 | 2352.17 | 0 | 0 | 0 | 2352.17 | 0 | 0 | 0 | 0 | 2352.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507403 | S-WW-NI-290620-Milton Bridge WWPS-H&S | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-29 |  | 2020-07-14 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1640.56 | 1640.56 | 0 | 0 | 0 | 1640.56 | 0 | 0 | 0 | 0 | 1640.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507950 | S-WW-NI-290720-Dalbeattie Port St WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-10-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9252.83 | 9252.83 | 0 | 0 | 0 | 9252.83 | 0 | 0 | 0 | 0 | 9252.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507937 | S-WW-NI-290720-Eddleston WWTW-Install stairway | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4919.32 | 4919.32 | -219.32 | 0 | 0 | 4700 | 0 | 0 | 0 | 0 | 4700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507942 | S-WW-NI-290720-Gretna WWTW-Flooring and support steelwork | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-09-18 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4386.75 | 4386.75 | 0 | 0 | 0 | 4386.75 | 0 | 0 | 0 | 0 | 4386.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507939 | S-WW-NI-290720-Hawick WWTW-Replace storm pump no.1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-08-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5632.17 | 5632.17 | 0 | 0 | 0 | 5632.17 | 0 | 0 | 0 | 0 | 5632.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507934 | S-WW-NI-290720-Lanark WWTW-Replace RAS Screw Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-05 | 2021-04-13 | 2021-11-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75070 | 75070 | 114930.24 | 0 | 0 | 190000.24 | 0 | 0 | 0 | 0 | 190000.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507946 | S-WW-NI-290720-Longriggend WWTW-Bring Wash Water into Bylaws Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-04 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1705.4 | 1705.4 | -1705.39 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507948 | S-WW-NI-290720-Newton Stewart WWTW-Replace Sludge Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-10-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10407.39 | 10407.39 | 0 | 0 | 0 | 10407.39 | 0 | 0 | 0 | 0 | 10407.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507940 | S-WW-NI-290720-North Berwick WWTW-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-11-05 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21287.46 | 21287.46 | 0 | 0 | 0 | 21287.46 | 0 | 0 | 0 | 0 | 21287.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507938 | S-WW-NI-290720-Peebles WWTW-Replace PST Ladders | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-04 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197.95 | 1197.95 | 12702.05 | 0 | 0 | 13900 | 0 | 0 | 0 | 0 | 13900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508994 | S-WW-NI-290920-Carbarns WWTW-Replace two winches and stainless steel cables for anoxic zone mixers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-29 |  | 2020-10-27 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1611.21 | 1611.21 | 0 | 0 | 0 | 1611.21 | 0 | 0 | 0 | 0 | 1611.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509001 | S-WW-NI-290920-Troqueer WWTW-Repair Storm pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-29 |  | 2020-10-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1359.07 | 1359.07 | 0 | 0 | 0 | 1359.07 | 0 | 0 | 0 | 0 | 1359.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509547 | S-WW-NI-291020-Lasswade WWPS-Replacement of open mesh flooring | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418.69 | 418.69 | 5981.31 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 6400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509538 | S-WW-NI-291020-Port Rodie WWPS-replace water tight door seal and refurbish door locking mechanism | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-29 |  | 2020-11-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3088.1 | 3088.1 | 0 | 0 | 0 | 3088.1 | 0 | 0 | 0 | 0 | 3088.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509534 | S-WW-NI-291020-Troqueer STC-Replace Poly pump and Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-29 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862.25 | 862.25 | 5949.98 | 0 | 0 | 6812.23 | 0 | 0 | 0 | 0 | 6812.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509536 | S-WW-NI-291020-Troqueer WWTW- Filtrate Return Pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-29 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9741.52 | 9741.52 | -41.52 | 0 | 0 | 9700 | 0 | 0 | 0 | 0 | 9700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504082 | S-WW-NI-291119-Ormiston WWTW-Replacement Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-04 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 3350.11 | -3042.63 | 307.48 | 4392.52 | 0 | 0 | 4700 | 0 | 0 | 0 | 0 | 4700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504933 | S-WW-NI-300120-Lauder WWTW-Removal of Aerator for investigation and repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-03-02 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 4759.59 | 0 | 4759.59 | 0 | 0 | 0 | 4759.59 | 0 | 0 | 0 | 0 | 4759.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504941 | S-WW-NI-300120-Strathaven WWTW-Replace the DB | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-03-02 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 4836.25 | -0.01 | 4836.24 | 0 | 0 | 0 | 4836.24 | 0 | 0 | 0 | 0 | 4836.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504936 | S-WW-NI-300130-Fillyside WWPS-Crane Issue - Investigation and Repair hoist | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-31 |  | 2020-05-19 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 11800 | 6.43 | 11806.43 | 0 | 0 | 0 | 11806.43 | 0 | 0 | 0 | 0 | 11806.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505979 | S-WW-NI-30032020-Haddington WWTW-Replacement tank bridge motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-05-05 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575.32 | 2575.32 | 0 | 0 | 0 | 2575.32 | 0 | 0 | 0 | 0 | 2575.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505986 | S-WW-NI-30032020-Haddington WWTW-To get existing aerator removed and evaluated | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-05-14 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6291.22 | 6291.22 | 0 | 0 | 0 | 6291.22 | 0 | 0 | 0 | 0 | 6291.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505988 | S-WW-NI-30032020-Harvesters WWPS-supply and installation of new pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-31 |  | 2020-04-29 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5802.26 | 5802.26 | 0 | 0 | 0 | 5802.26 | 0 | 0 | 0 | 0 | 5802.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512114 | S-WW-NI-300321- BLACKRIDGE WWTW 1950 NS910677 - REFURBISH FILTER BED CENTRE COLUMN | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-31 |  | 2021-06-30 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647.66 | 647.66 | 8485.74 | 0 | 0 | 9133.4 | 0 | 0 | 0 | 0 | 9133.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506407 | S-WW-NI-300420-47 Eskbank Road Dalkeith-Excavate to Repair Defect found | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-01 |  | 2021-05-01 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27228.5 | 27228.5 | 571.5 | 0 | 0 | 27800 | 0 | 0 | 0 | 0 | 27800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506404 | S-WW-NI-300420-Clyde Valley WWPS-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-08-06 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5342.24 | 5342.24 | 0 | 0 | 0 | 5342.24 | 0 | 0 | 0 | 0 | 5342.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506411 | S-WW-NI-300420-Coalburn WWTW-Flooding prevention investigation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 |  | 2020-05-11 | 2020-07-17 | 2021-02-03 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14704.27 | 14704.27 | 0 | 0 | 0 | 14704.27 | 0 | 0 | 0 | 0 | 14704.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506408 | S-WW-NI-300420-Hawick WWTW-Replacement Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-01 |  | 2020-05-20 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3539.41 | 3539.41 | 0 | 0 | 0 | 3539.41 | 0 | 0 | 0 | 0 | 3539.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506414 | S-WW-NI-300420-Lesmahagow DOA- investigation to establish the sources of infiltration | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2020-05-11 | 2020-08-12 | 2020-11-24 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16749.57 | 16749.57 | 0 | 0 | 0 | 16749.57 | 0 | 0 | 0 | 0 | 16749.57 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506405 | S-WW-NI-300420-Shotts Station Rd CSO-compensation and servitude claim | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-01 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5491.48 | 5491.48 | 1008.52 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507976 | S-WW-NI-300720-Dalscone Old WWTW-Removal for Trees onsite | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.35 | 9.35 | 12590.65 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 12600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507974 | S-WW-NI-300720-Dumfries Cuckoo WWPS-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-11-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15425.59 | 15425.59 | 0 | 0 | 0 | 15425.59 | 0 | 0 | 0 | 0 | 15425.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507970 | S-WW-NI-300720-Lincluden WWTW-New gate and bomb doors | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-11-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5333.58 | 5333.58 | 0 | 0 | 0 | 5333.58 | 0 | 0 | 0 | 0 | 5333.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507977 | S-WW-NI-300720-Lincluden WWTW-Replace 2 actuators and 1 spindle | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-04 |  | 2021-03-14 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10069.38 | 10069.38 | -269.38 | 0 | 0 | 9800 | 0 | 0 | 0 | 0 | 9800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507960 | S-WW-NI-300720-Lincluden WWTW-Various Works | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-09-18 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4449.48 | 4449.48 | 0 | 0 | 0 | 4449.48 | 0 | 0 | 0 | 0 | 4449.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507978 | S-WW-NI-300720-Ormiston WWTW-Replacing covers and railings | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-08-24 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3082.8 | 3082.8 | 0 | 0 | 0 | 3082.8 | 0 | 0 | 0 | 0 | 3082.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507980 | S-WW-NI-300720-Pencaitland WWTW-Replace Recirc Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-04 |  | 2021-03-27 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7005 | 7005 | -5 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 7000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507959 | S-WW-NI-300720-Troqueer STC-Replacement Thickener Geared Motor | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-08-08 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3295.14 | 3295.14 | 0 | 0 | 0 | 3295.14 | 0 | 0 | 0 | 0 | 3295.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507971 | S-WW-NI-300720-Troqueer WWTW-Replacement of the obsolete gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-04 |  | 2020-09-21 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6977.26 | 6977.26 | 0 | 0 | 0 | 6977.26 | 0 | 0 | 0 | 0 | 6977.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509011 | S-WW-NI-300920-Blackridge WWTW-Repair Vertical Wash Water Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426.03 | 426.03 | 5873.97 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 6300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509026 | S-WW-NI-300920-Cargenbridge WWPS-Replace Roller Shutter Door | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364.83 | 364.83 | 3235.17 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509017 | S-WW-NI-300920-Eastriggs WWTW-Replace screw pump back stop | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-30 |  | 2020-11-26 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9401.05 | 9401.05 | 0 | 0 | 0 | 9401.05 | 0 | 0 | 0 | 0 | 9401.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509009 | S-WW-NI-300920-Lesmahagow WWTW-Replace Humus Return Pump No.1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-30 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2622.07 | 2622.07 | 2377.93 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509042 | S-WW-NI-300920-Lincluden WWTW-Repair to Sludge Mixer | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-02 |  | 2020-10-20 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4551.44 | 4551.44 | 0 | 0 | 0 | 4551.44 | 0 | 0 | 0 | 0 | 4551.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509033 | S-WW-NI-300920-Lincluden WWTW-Replace Grating and Flooring | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-30 |  | 2021-02-10 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17375.38 | 17375.38 | -175.38 | 0 | 0 | 17200 | 0 | 0 | 0 | 0 | 17200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509012 | S-WW-NI-300920-Moffat WWTW- PST 1 Replace bridge wheels | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-30 |  | 2020-10-19 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3135.18 | 3135.18 | 0 | 0 | 0 | 3135.18 | 0 | 0 | 0 | 0 | 3135.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509021 | S-WW-NI-300920-Newton Stewart WWTW-Refurb the drum thickener | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-30 |  | 2021-04-03 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15332.9 | 15332.9 | -1114.19 | 0 | 0 | 14218.71 | 0 | 0 | 0 | 0 | 14218.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509028 | S-WW-NI-300920-Troqueer STC-Replace 2 Poly Plant Blowers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-30 |  | 2020-10-17 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10568.25 | 10568.25 | 0 | 0 | 0 | 10568.25 | 0 | 0 | 0 | 0 | 10568.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509562 | S-WW-NI-301020-Eastfield WWPS-Replace fans for the panel & VSD | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-30 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.35 | 209.35 | 2990.65 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509564 | S-WW-NI-301020-Kelso WWTW-Install dosing pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-30 |  | 2020-11-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2671.29 | 2671.29 | 47.42 | 0 | 0 | 2718.71 | 0 | 0 | 0 | 0 | 2718.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509560 | S-WW-NI-301020-Ormiston WWTW-Repair storm tank 1s scraper chain | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-30 |  | 2021-03-22 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12477.62 | 12477.62 | -777.62 | 0 | 0 | 11700 | 0 | 0 | 0 | 0 | 11700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509566 | S-WW-NI-301020-Pencaitland WWTW-Valve Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-30 |  | 2020-11-12 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1244.62 | 1244.62 | 0 | 0 | 0 | 1244.62 | 0 | 0 | 0 | 0 | 1244.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509556 | S-WW-NI-301020-Penicuik WWTW-Critical spare inlet valve for the SBRs | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-30 |  | 2020-03-12 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5077.64 | 5077.64 | 0 | 0 | 0 | 5077.64 | 0 | 0 | 0 | 0 | 5077.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510039 | S-WW-NI-301120-Coalburn WWTW-Actuator Valves | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-03 |  | 2020-09-12 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385 | 1385 | 15.01 | 0 | 0 | 1400.01 | 0 | 0 | 0 | 0 | 1400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510038 | S-WW-NI-301120-Various Sites-High Voltage Maintenance Overdue | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-03 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4579.44 | 4579.44 | 65420.56 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 70000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510679 | S-WW-NI-30121-Birkenshaw WWPS-Carry out refurbishement of pumps 2 and 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14817.58 | 14817.58 | -17.58 | 0 | 0 | 14800 | 0 | 0 | 0 | 0 | 14800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510287 | S-WW-NI-31 Silverwells Crescent-Arboriculture survey | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-12-24 | 2021-02-08 | 2021-06-21 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573 | 1573 | 3426.84 | 0 | 0 | 4999.84 | 0 | 0 | 0 | 0 | 4999.84 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506012 | S-WW-NI-31032020-Kirkconnel WWTW-Replacment of path and steps to sample point on site | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-04-01 |  | 2021-02-15 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2743.52 | 2743.52 | 0 | 0 | 0 | 2743.52 | 0 | 0 | 0 | 0 | 2743.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507984 | S-WW-NI-310720-Cardrona WWTW-Reed Bed Performance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-08-05 | 2021-02-12 | 2021-08-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21596.16 | 21596.16 | 193531.5 | 0 | 0 | 215127.66 | 0 | 0 | 0 | 0 | 215127.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507986 | S-WW-NI-310720-Gordon WWTW-Final Tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-08-05 | 2021-02-22 | 2021-03-10 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11232.38 | 11232.38 | 0 | 0 | 0 | 11232.38 | 0 | 0 | 0 | 0 | 11232.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507989 | S-WW-NI-310720-St Boswells WWTW-Install Handrail | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-04 |  | 2021-05-01 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220.11 | 220.11 | 1379.89 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508471 | S-WW-NI-310820-Hamilton WWTW-Installation of critical parts for muncher | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-09-25 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342.77 | 1342.77 | 0 | 0 | 0 | 1342.77 | 0 | 0 | 0 | 0 | 1342.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508463 | S-WW-NI-310820-Joppa WWPS-Replace Check Valve | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-11-03 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344.87 | 1344.87 | 0 | 0 | 0 | 1344.87 | 0 | 0 | 0 | 0 | 1344.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508466 | S-WW-NI-310820-Loch Ryan WWTW-Replace Booster Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-09-04 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2078.73 | 2078.73 | 0 | 0 | 0 | 2078.73 | 0 | 0 | 0 | 0 | 2078.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508461 | S-WW-NI-310820-North Berwick WWTW-Pipework Repair | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-31 |  | 2021-05-01 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1401.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508469 | S-WW-NI-310820-Strathclyde WWPS1-Replace Damaged Guards | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-31 |  | 2020-10-05 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2013.56 | 2013.56 | 0 | 0 | 0 | 2013.56 | 0 | 0 | 0 | 0 | 2013.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509662 | S-WW-NI-Dunnswood WWTW-replace the failed sludge pump suction pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2020-11-12 | 2021-02-08 | 2021-10-11 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3731.16 | 3731.16 | 16396.88 | 0 | 0 | 20128.04 | 0 | 0 | 0 | 0 | 20128.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505036 | S-WW-NI-Eastriggs WWTW-Mechanical Seal on Sludge Feed Pump | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-09 |  | 2020-03-23 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 1631.74 | 0 | 1631.74 | 0 | 0 | 0 | 1631.74 | 0 | 0 | 0 | 0 | 1631.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510849 | S-WW-NI-Galashiels STC-Alter thickened feed pump pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-26 |  | 2021-03-07 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1396.6 | 1396.6 | 12.76 | 0 | 0 | 1409.36 | 0 | 0 | 0 | 0 | 1409.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509913 | S-WW-NI-Joppa Mine Water-Engage with Intertek to carry out dispersion modelling | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-12-03 | 2021-07-09 | 2022-02-21 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2415 | 2415 | 5084.97 | 0 | 0 | 7499.97 | 0 | 0 | 0 | 0 | 7499.97 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504219 | S-WW-NI-Kirkubright Harbour WWPS-Screen Adjustments & Weir Plate | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 |  | 2019-12-11 |  | 2020-08-26 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | -17213.58 | 7786.42 | 0 | 0 | 0 | 7786.42 | 0 | 0 | 0 | 0 | 7786.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508172 | S-WW-NI-Longriggend WWTW-Bring Wash Water into Bylaws Compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-08-14 | 2021-05-04 | 2021-08-04 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15331 | 15331 | 16669.1 | 0 | 0 | 32000.1 | 0 | 0 | 0 | 0 | 32000.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506547 | S-WW-NI-Mansefield Athelstaneford-Investigations | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS4 |  | 2020-05-12 | 2020-07-20 | 2021-03-31 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 26000 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 0 | 26000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504584 | S-WW-NI-North Kirkliston WWPS-Replace 2No Pumps | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-05-14 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 6495.2 | 5876.09 | 12371.29 | 0 | 0 | 0 | 12371.29 | 0 | 0 | 0 | 0 | 12371.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509148 | S-WW-NI-S Quuensferry WWTW-Replace SBR Blower | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-07 |  | 2020-03-12 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4207.98 | 4207.98 | 0 | 0 | 0 | 4207.98 | 0 | 0 | 0 | 0 | 4207.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507112 | S-WW-NI-Slamannan WWTW-Refurbishmen of final settlement tank | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-06-11 |  | 2021-06-29 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55534 | 55534 | 194465.55 | 0 | 0 | 249999.55 | 0 | 0 | 0 | 0 | 249999.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503958 | S-WW-NI-SWINSTON WWTW-Gearbox for Aerator | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-27 |  | 2020-01-04 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 1899.17 | 60.34 | 1959.51 | 0 | 0 | 0 | 1959.51 | 0 | 0 | 0 | 0 | 1959.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
45540 | Symington A STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-05 | 2011-02-07 | 2011-07-04 | 2012-03-16 | 2012-03-22 | South Lanarkshire | 1003868.54 | 0 | 311.36 | 0 | 0 | 0 | 0 | 0 | 311.36 | 0 | 0 | 0 | 1004179.9 | 0 | 0 | 0 | 0 | 1004179.9 | 238142.92 | [5 empty] | N | CM_WWI | 2.471% | CS11A | 6.355% | WQ01 | 91.17%
45541 | Symington B STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-05 | 2011-02-07 | 2011-10-24 | 2012-06-24 | 2012-06-28 | South Lanarkshire | 1066244.65 | 0 | 812.77 | 0 | 0 | 0 | 0 | 0 | 812.77 | 0 | 0 | 0 | 1067057.42 | 0 | 0 | 0 | 0 | 1067057.42 | 28761.13 | [5 empty] | N | WQ01 | 100%
501154 | Syskeside SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-02-17 | 2018-11-05 | 2019-02-04 | 2020-02-18 |  | North Lanarkshire | 0 | 0 | 909.35 | 70857.33 | 34689.32 | 544359.36 | 377835.66 | 5848.98 | 1034500 | 2500 | 0 | 0 | 1037000 | 0 | 0 | 0 | 0 | 1037000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502182 | T&I - Telemetry Service Improvements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-06-29 | 2016-10-28 | 2016-10-28 | 2021-05-17 |  | Scottish Water Wide | 0 | 0 | 0 | 389447.89 | 561273.96 | 127091.1 | 125945.22 | 175929.83 | 1379688 | 0 | 0 | 0 | 1379688 | 0 | 0 | 0 | 0 | 1379688 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501253 | Tain additional FST (Growth funded) plus various CM ( inlet screen PFT if required MCC refurbishm | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS6 | 2016-03-02 | 2018-09-28 | 2018-10-30 | 2020-06-29 |  | Highland | 0 | 0 | 5728.8 | 215606.6 | 136996.21 | 646956.48 | 1666254.82 | -27788.91 | 2643754 | 51421.56 | 0 | 0 | 2695175.56 | 0 | 0 | 0 | 0 | 2695175.56 | 213020.38 | [5 empty] | N | CM_WWNI | 35% | SG1 | 65%
501420 | Talla Aqueduct - 2019 Walk through Inspection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2028-01-28 | 2029-01-08 | 2029-03-22 | 2030-04-23 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.51 | 44.51 | 4499999.86 | 0 | 0 | 4500044.37 | 0 | 0 | 0 | 0 | 4500044.37 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501617 | Talla Aqueduct - Broughton Siphons | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-07-23 | 2028-05-30 | 2028-08-16 | 2029-09-17 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4971751 | 0 | 0 | 4971751 | 0 | 0 | 0 | 0 | 4971751 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504961 | Talla Aqueduct - Full Inspection ASV2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2020-03-02 | 2021-03-19 | 2021-06-02 | 2022-03-18 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 27987.45 | 271469.8 | 299457.25 | 714895.57 | 0 | 0 | 1014352.82 | 0 | 0 | 0 | 0 | 1014352.82 | 119022.58 | [5 empty] | N | CM_WSI | 100%
503366 | Talla Aqueduct - Inspection Planning | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-09-28 | 2018-09-28 | 2019-09-16 | 2021-04-14 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 28976.48 | 193072.36 | 28068.98 | 250117.83 | 0 | 0 | 0 | 250117.83 | 0 | 0 | 0 | 0 | 250117.83 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45651 | Talla Aqueduct Refurb | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2012-08-30 | 2012-09-17 | 2015-07-30 |  | Scottish Borders | 7179571 | 0 | 121113 | 199945.35 | -5520.81 | 0 | -0.01 | 0 | 315537.54 | 0 | 0 | 0 | 7495108.54 | 0 | 0 | 0 | 0 | 7495108.54 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510105 | Talla Reservoir Bottom Draw Off Valve Repair | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-04-01 | 2021-04-19 | 2021-07-12 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2213 | 2213 | 152787 | 0 | 0 | 155000 | 0 | 0 | 0 | 0 | 155000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401972 | Talla Reservoir Safe Operation of Scour Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-04-01 | 2014-03-31 | 2014-04-21 | 2015-01-12 | 2015-01-12 | Scottish Borders | 641437 | 0 | -7222 | -249.73 | 0 | 0 | 0 | 0 | -7471.73 | 0 | 0 | 0 | 633965.27 | 0 | 0 | 0 | 0 | 633965.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45280 | Tanker Fill Point Balmore WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-06-14 | 2011-03-30 | 2011-06-23 | East Dunbartonshire | 547741.6 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 0 | 547742.9 | 0 | 0 | 0 | 0 | 547742.9 | 28761.13 | [5 empty] | N | DW8 | 100%
45282 | Tanker Fill Point Blairlinnans WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2012-01-16 | 2012-02-23 | 2012-03-14 | West Dunbartonshire | 263100.22 | 0 | 108.68 | 0 | 0 | 0 | 0 | 0 | 108.68 | 0 | 0 | 0 | 263208.9 | 0 | 0 | 0 | 0 | 263208.9 | 28761.13 | [5 empty] | N | DW8 | 100%
45284 | Tanker Fill Point Carron Valley WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-10-11 | 2011-01-28 | 2011-06-23 | Falkirk | 190609.51 | 0 | -22.51 | 0 | 0 | 0 | 0 | 0 | -22.51 | 0 | 0 | 0 | 190587 | 0 | 0 | 0 | 0 | 190587 | 28761.13 | [5 empty] | N | DW8 | 100%
45285 | Tanker Fill Point Fairmilehead WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-09-24 | 2010-11-08 | 2011-05-24 | 2012-03-30 | City of Edinburgh | 339120.29 | 0 | 498.71 | 0 | -22.02 | 0 | 0 | 0 | 476.69 | 0 | 0 | 0 | 339596.98 | 0 | 0 | 0 | 0 | 339596.98 | 28761.13 | [5 empty] | N | DW8 | 100%
45286 | Tanker Fill Point Finmont WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-02 | 2011-07-29 | 2011-10-05 | Fife | 436124.05 | 0 | 6019.55 | -6019.58 | 0 | 0 | 0 | 0 | -0.03 | 0 | 0 | 0 | 436124.02 | 0 | 0 | 0 | 0 | 436124.02 | 0 | [5 empty] | N | DW8 | 100%
45287 | Tanker Fill Point Forehill WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-09 | 2011-03-29 | 2011-06-23 | Aberdeenshire | 351447.31 | 0 | 242.99 | 0 | 0 | 0 | 0 | 0 | 242.99 | 0 | 0 | 0 | 351690.3 | 0 | 0 | 0 | 0 | 351690.3 | 28761.13 | [5 empty] | N | DW8 | 100%
45288 | Tanker Fill Point Mannofield WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-23 | 2012-02-23 | 2012-03-14 | Aberdeen City | 483724.01 | 0 | 286 | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 0 | 0 | 484010.01 | 0 | 0 | 0 | 0 | 484010.01 | 28761.13 | [5 empty] | N | DW8 | 100%
45289 | Tanker Fill Point Overton Greenock WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2011-01-17 | 2012-02-19 | 2012-03-14 | Inverclyde | 471461.33 | 0 | 6.89 | 0 | 0 | 0 | 0 | 0 | 6.89 | 0 | 0 | 0 | 471468.22 | 0 | 0 | 0 | 0 | 471468.22 | 28761.13 | [5 empty] | N | DW8 | 100%
45291 | Tanker Fill Point Perth WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-02 | 2011-03-03 | 2011-06-23 | Perth and Kinross | 367773.39 | 0 | 214.72 | 0 | 0 | 0 | 0 | 0 | 214.72 | 0 | 0 | 0 | 367988.11 | 0 | 0 | 0 | 0 | 367988.11 | 28761.13 | [5 empty] | N | DW8 | 100%
45292 | Tanker Fill Point Whitehillocks WOA | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-11-08 | 2011-03-02 | 2011-06-23 | Angus | 272223.68 | 0 | 158.16 | 0 | 0 | 0 | 0 | 0 | 158.16 | 0 | 0 | 0 | 272381.84 | 0 | 0 | 0 | 0 | 272381.84 | 28761.13 | [5 empty] | N | DW8 | 100%
509070 | Tarbert (WI) WTW - SCADA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-01-03 | 2023-11-20 | 2024-04-29 | 2025-11-10 | 2026-02-10 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14069.11 | 14069.11 | 235958.31 | 0 | 0 | 250027.42 | 0 | 0 | 0 | 0 | 250027.42 | 0 | [5 empty] | N | SR21_WA | 100%
502872 | Tarbert (WI) WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW2 | 2022-02-16 | 2022-03-14 | 2022-03-14 | 2022-03-14 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 21238 | 1489.88 | 9066.04 | -4813 | 26980.92 | 0 | 0 | 0 | 26980.92 | 0 | 0 | 0 | 0 | 26980.92 | 122419.09 | [5 empty] | N | WG1 | 100%
500184 | Tarbert DOA (DOA002408) Environmental Study | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater | SEPA | SWMD | Flood Assessments | MS7 | 2015-03-20 | 2015-11-30 | 2016-01-11 | 2017-02-28 | 2017-05-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 42286 | 40471 | 15399.18 | 41.28 | 0 | 0 | 98197.46 | 0 | 0 | 0 | 98197.46 | 0 | 0 | 0 | 0 | 98197.46 | 72047.27 | [5 empty] | Y | CS16D | 40.17% | CS11 | 59.83% | [37 empty] | 1 | [27 empty] | 0
500880 | Tarbert Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-09-20 | 2018-09-18 | 2018-12-13 | 2019-03-27 | 2019-09-30 | Na H-Eileanan an Iar | 0 | 0 | 1581.68 | 3568.21 | 6367 | 73562.87 | 17237.92 | 329.73 | 102647.41 | 0 | 0 | 0 | 102647.41 | 0 | 0 | 0 | 0 | 102647.41 | 97085.51 | [5 empty] | N | DW5FS | 100%
502835 | Tarbert WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-07-18 | 2018-07-17 | 2018-07-17 | 2018-07-17 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 57254.81 | 23277.41 | 0 | 0 | 80532.22 | 0 | 0 | 0 | 80532.22 | 0 | 0 | 0 | 0 | 80532.22 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504203 | Tarbert WTW - CWT | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-09-01 | 2023-08-02 | 2023-11-06 | 2025-06-16 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 176556.28 | 3896.92 | 180453.2 | 3319602.39 | 0 | 0 | 3500055.59 | 0 | 0 | 0 | 0 | 3500055.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511582 | Tarbet DSR - low CL2 residuals maining out modelling scenarios | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-11 | 2022-01-28 | 2022-09-12 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 745.93 | 745.93 | 9999.99 | 0 | 0 | 10745.92 | 0 | 0 | 0 | 0 | 10745.92 | 119022.58 | [5 empty] | N | WSNI | 100%
500686 | Tarbolton Rising Main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-06-11 | 2016-05-18 | 2016-06-13 | 2016-09-30 |  | South Ayrshire | 0 | 0 | 66557 | 738874 | 26386.76 | 20214.18 | 11722.64 | -5730.52 | 858024.07 | 0 | 0 | 0 | 858024.07 | 0 | 0 | 0 | 0 | 858024.07 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501270 | Tarbolton SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2016-07-19 | 2017-11-07 | 2018-03-26 | 2018-10-30 |  | South Ayrshire | 0 | 0 | 0 | 30180 | 318820 | 424542.92 | 9733.29 | 9961.23 | 793237.43 | -1238.28 | 0 | 0 | 791999.15 | 0 | 0 | 0 | 0 | 791999.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500881 | Tarskavaig Skye RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-20 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 0 | 490.79 | 1083.55 | 0 | 0 | 0 | 0 | 1574.34 | 0 | 0 | 0 | 1574.34 | 0 | 0 | 0 | 0 | 1574.34 | 10180.72 | [5 empty] | N | DW5FS | 100%
46847 | Tarskavaig WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-01 | 2011-03-14 | 2014-12-01 | 2015-03-27 | Na H-Eileanan an Iar | 1053408.29 | 0 | 44948.52 | -10506.85 | 24820.97 | -11082.13 | 0 | 0 | 48180.51 | 0 | 0 | 0 | 1101588.8 | 0 | 0 | 0 | 0 | 1101588.8 | 28761.13 | [5 empty] | N | DW23 | 100%
502827 | Tarves WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS2 | 2020-01-23 | 2021-03-31 | 2021-05-18 | 2022-01-13 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 64604.45 | 17150.63 | 5266.13 | 108965.79 | 195987 | 879403.16 | 0 | 0 | 1075390.16 | 0 | 0 | 86031.2128 | 86031.2128 | 1161421.3728 | 122419.09 | [5 empty] | N | SG1 | 100%
400279 | Tay Cluster 2 Capital Maintenance Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-30 | 2012-07-31 | 2012-09-03 | 2013-08-02 |  | Perth and Kinross | 886307 | 0 | 2696.48 | 0 | 0 | 0 | 0 | 0 | 2696.48 | 0 | 0 | 0 | 889003.48 | 0 | 0 | 0 | 0 | 889003.48 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401222 | Tay Cluster 2 Lintrathen (5 WSZs) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2012-12-11 | 2013-01-30 | 2014-05-09 |  | Perth and Kinross | 1175950 | 0 | 25185 | -5181.03 | 0 | 0 | 0 | 0 | 20003.97 | 0 | 0 | 0 | 1195953.97 | 0 | 0 | 0 | 0 | 1195953.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500108 | Tay Coastal Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-12-14 | 2016-12-19 | 2019-04-04 | 2020-01-08 | Scottish Water Wide | 0 | 0 | 21309 | 41063.07 | 29834.93 | 60313 | 7009.51 | 0 | 159529.51 | 0 | 0 | 0 | 159529.51 | 0 | 0 | 0 | 0 | 159529.51 | 211553.37 | [5 empty] | N | EC01G | 0.5128% | EC10E | 49.74% | EC10H | 49.74%
501048 | Tay Large Middle Ground Scheme | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2015-10-09 | 2018-06-26 | 2018-08-06 | 2021-03-30 |  | Fife | 0 | 0 | 30750 | 55000 | 30950.11 | 478929.88 | 75536.7 | 136656.35 | 807823.04 | 3084.48 | 0 | 0 | 810907.52 | 0 | 0 | 0 | 0 | 810907.52 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401491 | Tay Leakage Region New and Replacement Leakage Assets | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-08 | 2012-03-15 | 2012-03-15 | 2015-07-31 |  | All East Unitary Authorities | 1188388 | 0 | 73871 | 0 | -1383.22 | 0 | 0 | 0 | 72487.78 | 0 | 0 | 0 | 1260875.78 | 0 | 0 | 0 | 0 | 1260875.78 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501105 | Tay PFI Hatton Aesthetic and Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-12-19 | 2017-01-20 | 2018-06-30 | 2018-12-31 | Dundee City | 0 | 0 | 608 | 14339.25 | 22299.75 | 13647.85 | 25 | 0 | 50919.85 | 0 | 0 | 0 | 50919.85 | 0 | 0 | 0 | 0 | 50919.85 | 79083.98 | [5 empty] | Y | EC01G | 3.809% | EC10E | 96.19% | [38 empty] | 1 | [26 empty] | 0
501831 | Tay PFI Hatton PFI Grade 5 HC Sewer | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS7 | 2020-04-28 | 2020-05-07 | 2020-06-05 | 2020-06-05 | 2021-04-01 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SR21_WW | 100%
403899 | TCM - Non Infra Alliance | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-30 | 2014-10-08 | 2014-10-08 | 2017-01-26 |  | Scottish Water Wide | 1813801 | 906900.5 | 374097 | 40578.37 | 1123.2 | 0 | 0 | 0 | 415798.57 | 0 | 0 | 0 | 2229599.57 | 0 | 0 | 0 | 0 | 2229599.57 | 613322.63 | [5 empty] | N | CM_M&G | 100%
511193 | Teangue WTW - PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-06-01 | 2023-12-08 | 2024-03-07 | 2025-02-12 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000.01 | 0 | 0 | 500000.01 | 0 | 0 | 0 | 0 | 500000.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402679 | Teangue WTW - Raw Water Main Upsize | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-21 | 2012-09-21 | 2012-10-22 | 2013-09-23 |  | Highland | 650602 | 0 | 29593 | 3425.08 | -44789.92 | -644.4 | 0 | 0 | -12416.24 | 0 | 0 | 0 | 638185.76 | 0 | 0 | 0 | 0 | 638185.76 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402952 | Teangue WTW - Standby Filtomat Installation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-09 | 2014-06-20 | 2014-06-23 | 2015-07-17 |  | Highland | 1280423 | 0 | 229577 | 0 | 160.05 | 0 | 0 | 0 | 229737.05 | 0 | 0 | 0 | 1510160.05 | 0 | 0 | 0 | 0 | 1510160.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503365 | Teangue WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2021-01-29 |  | Highland | 0 | 0 | 0 | 0 | 0 | 20233.02 | -13949.42 | 0 | 6283.6 | 0 | 0 | 0 | 6283.6 | 0 | 0 | 0 | 0 | 6283.6 | 122419.09 | [5 empty] | N | WG1 | 100%
400486 | Teangue WTW Supply Zone Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS5 | 2001-02-25 | 2005-01-21 | 2005-02-21 | 2018-10-08 | 2018-10-08 | Highland | 1195.74 | 0 | 75.23 | 0 | 0 | 0 | -1270.97 | 0 | -1195.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | WG1 | 100%
404108 | Technology for Water and Waste Water Operatives | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-04 | 2016-03-03 | 2016-03-03 | 2016-03-03 |  | Scottish Water Wide | 50000 | 0 | 1219.51 | 0 | 0 | 0 | 0 | 0 | 1219.51 | 0 | 0 | 0 | 51219.51 | 0 | 0 | 0 | 0 | 51219.51 | 306661.32 | [5 empty] | N | CM_M&G | 100%
500624 | Technology Information & Business Change SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 5728557.08 | 5006873.51 | 10092169.84 | 10310257.53 | 13530071.84 | 9866154.95 | 54534084.74 | 0 | 0 | 0 | 54534084.74 | 0 | 0 | 0 | 0 | 54534084.74 | 306661.32 | [5 empty] | N | CM_OVH | 100%
502288 | TEL - Private Wire comms. replacement phase1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2016-09-15 | 2016-12-20 | 2017-01-16 | 2018-01-18 |  | Scottish Water Wide | 0 | 0 | 0 | 21380.91 | 16985.92 | 905.95 | 138.5 | 0 | 39411.28 | 0 | 0 | 0 | 39411.28 | 0 | 0 | 0 | 0 | 39411.28 | 613322.63 | [5 empty] | N | CM_WSNI | 17.17% | CM_WWNI | 82.83%
502234 | TEL - SR15 Telemetry RTU Replacement - Phase 6 Datacall | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-09-22 | 2018-05-31 | 2018-07-30 | 2021-11-10 |  | Scottish Water Wide | 0 | 0 | 0 | 38317.97 | 75109.82 | 172048.43 | 427353.65 | 586743.72 | 1299573.59 | 370707.69 | 0 | 0 | 1670281.28 | 0 | 0 | 0 | 0 | 1670281.28 | 613322.63 | [5 empty] | N | CM_WWNI | 41.29% | CM_WSNI | 58.71%
502237 | TEL - SR15 Telemetry RTU Upgrading - Phase 3 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS6 | 2016-08-18 | 2017-03-23 | 2017-05-15 | 2020-05-27 |  | Scottish Water Wide | 0 | 0 | 0 | 30207.82 | 179639.03 | 30883.71 | 13884.25 | 338.19 | 254953 | 0 | 0 | 0 | 254953 | 0 | 0 | 0 | 0 | 254953 | 613322.63 | [5 empty] | N | CM_WWNI | 31.93% | CM_WSNI | 68.07%
502238 | TEL - SR15 Telemetry RTU Upgrading - Phase 4 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS4 | 2016-08-18 | 2017-03-30 | 2017-06-26 | 2021-03-23 |  | Scottish Water Wide | 0 | 0 | 0 | 33520.74 | 118436.78 | 142538.21 | 50236.09 | 13627.18 | 358359 | 3242.98 | 0 | 0 | 361601.98 | 0 | 0 | 0 | 0 | 361601.98 | 613322.63 | [5 empty] | N | CM_WWNI | 29.7% | CM_WSNI | 70.3%
502239 | TEL - SR15 Telemetry RTU Upgrading - Phase 5 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS4 | 2016-08-18 | 2017-03-28 | 2017-06-05 | 2021-03-05 |  | Scottish Water Wide | 0 | 0 | 0 | 26143.22 | 136793.19 | 108175.33 | 112820.33 | -5602.07 | 378330 | 7544.92 | 0 | 0 | 385874.92 | 0 | 0 | 0 | 0 | 385874.92 | 613322.63 | [5 empty] | N | CM_WWNI | 13.3% | CM_WSNI | 86.7%
35821 | Telemetry - Data Quality End to End Testing Ph 2 Ness Area | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2007-05-09 | 2007-06-26 | 2007-07-16 | 2015-12-21 | 2015-10-13 | Scottish Water Wide | 4687190 | 0 | -200.12 | 0 | 0 | 0 | 0 | 0 | -200.12 | 0 | 0 | 0 | 4686989.88 | 0 | 0 | 0 | 0 | 4686989.88 | 28761.13 | [5 empty] | N | DW14 | 100%
404017 | Telemetry - Exo RDI and Ellipse Synch improvement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-01-06 | 2015-01-06 | 2015-01-06 | 2017-11-08 |  | Scottish Water Wide | 15000 | 0 | 10000 | -3024.24 | 0 | 0 | 0 | 0 | 6975.76 | 0 | 0 | 0 | 21975.76 | 0 | 0 | 0 | 0 | 21975.76 | 613322.63 | [5 empty] | N | CM_WSNI | 50% | CM_WWNI | 50%
401200 | Telemetry - First Time provision of Telemetry at 25 WWTWs | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2010-08-19 | 2012-12-10 | 2013-01-22 | 2014-12-01 |  | Scottish Water Wide | 250819.49 | 0 | 98.85 | 0 | 0 | 0 | 0 | 0 | 98.85 | 0 | 0 | 0 | 250918.34 | 0 | 0 | 0 | 0 | 250918.34 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
401199 | Telemetry - First Time provision of Telemetry at SPSs Phase 1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2010-08-19 | 2011-03-01 | 2011-04-25 | 2015-11-20 |  | Scottish Water Wide | 1149804 | 0 | 12077.72 | 120 | 0 | 0 | 0 | 0 | 12197.72 | 0 | 0 | 0 | 1162001.72 | 0 | 0 | 0 | 0 | 1162001.72 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
401201 | Telemetry - SPS Data Quality Phase 1 Testing | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2010-08-19 | 2011-02-28 | 2011-04-01 | 2016-02-25 |  | Scottish Water Wide | 658829.62 | 0 | 1493.55 | 0 | 0 | 0 | 0 | 0 | 1493.55 | 0 | 0 | 0 | 660323.17 | 0 | 0 | 0 | 0 | 660323.17 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
500490 | Telemetry - SR Data Quality Phase1 (SR15) | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-25 | 2021-05-28 |  | Scottish Water Wide | 0 | 0 | 309469 | 220032.46 | 229508.85 | 203791.53 | 95638.98 | -73379.82 | 985061 | 119857.3 | 0 | 0 | 1104918.3 | 0 | 0 | 0 | 0 | 1104918.3 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
402695 | Telemetry - TSAT - Replacement of Unsupported equipment | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2012-06-22 | 2013-01-30 | 2013-02-18 | 2015-02-19 |  | Scottish Water Wide | 698495 | 0 | 15431.84 | 218.96 | 0 | 0 | 0 | 0 | 15650.8 | 0 | 0 | 0 | 714145.8 | 0 | 0 | 0 | 0 | 714145.8 | 613322.63 | [5 empty] | N | CM_WSNI | 18.17% | CM_WWNI | 81.83%
500736 | Telemetry - Water DMA logger Alarming Phase1 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2018-07-12 |  | Scottish Water Wide | 0 | 0 | 29174 | 38482 | 68418 | 6953.36 | 0 | 0 | 143027.36 | 0 | 0 | 0 | 143027.36 | 0 | 0 | 0 | 0 | 143027.36 | 306661.32 | [5 empty] | N | CM_WWNI | 100%
500944 | Telemetry - Water Time of Travel Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2015-09-07 | 2015-09-07 | 2015-11-02 | 2016-10-20 |  | Scottish Water Wide | 0 | 0 | 5290 | 21658.54 | 0 | 0 | 0 | 0 | 26948.54 | 0 | 0 | 0 | 26948.54 | 0 | 0 | 0 | 0 | 26948.54 | 306661.32 | [5 empty] | N | CM_WWNI | 100%
501639 | Telemetry Application Consolidation | Q&S4 | Improving the customer experience | Meter Accuracy |  |  | General |  | SWD | Meter Accuracy | MS3 | 2016-02-15 | 2016-08-29 | 2016-08-29 | 2021-06-15 |  | Scottish Water Wide | 0 | 0 | 173356 | 855060.64 | 487281.96 | 788910.87 | 1200598.53 | 375558 | 3880766 | 0 | 0 | 62092.256 | 3880766 | 62092.256 | 0 | 248369.024 | 310461.28 | 4191227.28 | 6313730.07 |  |  |  |  | 7914.3298 | N | CS4 | 20.25% | CM_M&G | 79.75%
403947 | Telemetry Communication - Clatto (Fife) Scanner Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-10-29 | 2015-05-05 | 2015-05-05 | 2015-09-14 |  | Fife | 96952 | 0 | 170635.88 | 0 | 0 | 0 | 0 | 0 | 170635.88 | 0 | 0 | 0 | 267587.88 | 0 | 0 | 0 | 0 | 267587.88 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502721 | Telemetry ICC Water Initiatives | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-05-12 | 2017-05-12 | 2017-06-15 | 2021-01-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 91469.43 | 115461.23 | 85216.34 | 5171.11 | 297318.11 | 0 | 0 | 0 | 297318.11 | 0 | 0 | 0 | 0 | 297318.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402582 | Telemetry Improvements | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-03-15 | 2017-01-23 | 2017-01-23 | 2016-07-01 |  | Scottish Water Wide | 1533818 | 0 | 612688 | 53108.1 | 0 | 0 | 0 | 0 | 665796.1 | 0 | 0 | 0 | 2199614.1 | 0 | 0 | 0 | 0 | 2199614.1 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403603 | Telemetry Logger Alarming | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2016-08-15 |  | Scottish Water Wide | 90870 | 0 | 1650.61 | 79.88 | 0 | 0 | 0 | 0 | 1730.49 | 0 | 0 | 0 | 92600.49 | 0 | 0 | 0 | 0 | 92600.49 | 306661.32 | [5 empty] | N | CM_WWNI | 100%
400341 | Telemetry Low Voltage Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2008-11-25 | 2009-07-28 | 2010-07-29 | 2015-02-19 |  | Scottish Water Wide | 8206 | 0 | -149.84 | 0 | 0 | 0 | 0 | 0 | -149.84 | 0 | 0 | 0 | 8056.16 | 0 | 0 | 0 | 0 | 8056.16 | 306661.32 | [5 empty] | N | CM_WWNI | 100%
501679 | Telemetry Networks Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-11-28 | 2017-03-22 | 2017-03-22 | 2018-03-28 |  | Scottish Water Wide | 0 | 0 | 0 | 1014968.9 | 92217.05 | -33.21 | 0 | 0 | 1107152.74 | 0 | 0 | 0 | 1107152.74 | 0 | 0 | 0 | 0 | 1107152.74 | 306661.32 | [5 empty] | N | CM_M&G | 100%
403593 | Telemetry Scanning Radio - Risk Mitigation | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-12-03 | 2014-06-17 | 2014-06-17 | 2015-07-24 |  | Fife | 358938.66 | 0 | 117815.56 | 0 | 0 | 0 | 0 | 0 | 117815.56 | 0 | 0 | 0 | 476754.22 | 0 | 0 | 0 | 0 | 476754.22 | 613322.63 | [5 empty] | N | CM_M&G | 100%
511794 | Telemetry Top End Rationalisation - Migration | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MSU | 2021-04-28 | 2022-04-22 | 2022-08-24 | 2024-04-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 306661.32 | [5 empty] | N | CM_M&G | 100%
511793 | Telemetry Top End Rationalisation - Technical Enablement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MSU | 2021-04-28 | 2022-04-22 | 2022-08-24 | 2024-04-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 306661.32 | [5 empty] | N | CM_M&G | 100%
402690 | Telemetry WWTW Critical Data Quality | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2012-06-13 | 2013-02-20 | 2013-03-04 | 2017-04-25 |  | Scottish Water Wide | 299353 | 0 | 151221 | 35770.21 | -6265.13 | 0 | 0 | 0 | 180726.08 | 0 | 0 | 0 | 480079.08 | 0 | 0 | 0 | 0 | 480079.08 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
402689 | Telemetry WWTW Data Quality | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2012-06-21 | 2013-02-20 | 2013-03-06 | 2017-03-28 |  | Scottish Water Wide | 2574126 | 0 | 328317 | -2790.63 | 100.56 | 0 | 0 | 0 | 325626.93 | 0 | 0 | 0 | 2899752.93 | 0 | 0 | 0 | 0 | 2899752.93 | 306661.32 | [5 empty] | N | CM_WSNI | 100%
502774 | Temporary Phosphorus Treatment at Peebles WwTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWD | UWWTD - Works | MS7 | 2017-08-01 | 2017-08-01 | 2017-12-05 | 2017-12-31 | 2018-01-31 | Scottish Borders | 0 | 0 | 0 | 0 | 15151.06 | -15151.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | EC01A | 100% | [34 empty] | 1 | [32 empty] | 0
403033 | Terregles BH Water Supply Augmentation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-02-04 | 2014-07-31 | 2014-07-31 | 2015-09-21 |  | Dumfries and Galloway | 1140346 | 0 | 320930 | 2799.26 | 7058.45 | 0 | 0 | 0 | 330787.71 | 0 | 0 | 0 | 1471133.71 | 0 | 0 | 0 | 0 | 1471133.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500477 | Terregles WTW - Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2017-07-21 | 2018-11-27 | 2019-06-26 | 2019-09-30 | 2019-09-30 | Dumfries and Galloway | 0 | 0 | 13294.54 | 33699.51 | 23994.85 | 12209.83 | 738.25 | 0 | 83936.98 | 0 | 0 | 0 | 83936.98 | 0 | 0 | 0 | 0 | 83936.98 | 463259.66 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
45572 | Terregles WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-01-13 | 2011-09-22 | 2011-05-03 | 2011-12-01 | 2011-03-14 | Dumfries and Galloway | 73079.17 | 0 | 314.53 | 0 | 0 | 0 | 0 | 0 | 314.53 | 0 | 0 | 0 | 73393.7 | 0 | 0 | 0 | 0 | 73393.7 | 28761.13 | [5 empty] | N | DW1A | 100%
501299 | Test Service Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-02 | 2017-04-25 | 2017-04-25 | 2018-04-18 |  | Scottish Water Wide | 0 | 0 | 93569 | 169065.48 | 45688.39 | 0 | 0 | 0 | 308322.87 | 0 | 0 | 0 | 308322.87 | 0 | 0 | 0 | 0 | 308322.87 | 306661.32 | [5 empty] | N | CM_M&G | 100%
501685 | Thankerton Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-07-19 | 2021-04-30 | 2021-07-20 | 2021-11-25 |  | South Lanarkshire | 0 | 0 | 0 | 5700 | 2000 | 0 | 3032 | 0 | 10732 | 58768 | 0 | 0 | 69500 | 0 | 0 | 0 | 0 | 69500 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402961 | The Grove Ewanfield Crieff | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-28 | 2014-12-15 | 2015-09-01 | 2016-01-11 | 2016-01-11 | Perth and Kinross | 235559 | 235559 | 395012 | -3542.22 | 1016.72 | 0 | 0 | 0 | 392486.5 | 0 | 0 | 0 | 628045.5 | 0 | 0 | 0 | 0 | 628045.5 | 180449.74 | [5 empty] | N | FL_DD | 100%
403273 | The Ness - Dollar | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-02-01 | 2014-12-05 | 2015-04-13 | 2015-09-29 | 2015-10-01 | Clackmannanshire | 578381 | 578381 | 685403 | 0.42 | -39152.78 | 0 | 0 | 0 | 646250.64 | 0 | 0 | 0 | 1224631.64 | 0 | 0 | 0 | 0 | 1224631.64 | 180449.74 | [5 empty] | N | FL_DD | 100%
403001 | Theatre Lane at Regent Quay Aberdeen - Odour-Flooding | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-04 | 2017-05-08 | 2017-06-30 | 2018-01-17 |  | Aberdeen City | 1000 | 0 | 14585.88 | 16263.12 | 56627 | 3903.93 | -2251.1 | 0.19 | 89129.02 | 0 | 0 | 0 | 90129.02 | 0 | 0 | 0 | 0 | 90129.02 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502767 | THM Study 1 - West | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water | DWQR | SWD | DWQ - Preparing for Future Investment | MS7 | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-07-27 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 21508.78 | 23672.39 | 157866.86 | -128357.39 | 74690.63 | 0 | 0 | 0 | 74690.63 | 0 | 0 | 0 | 0 | 74690.63 | 337621.75 | [5 empty] | N | DW25PS | 100%
502768 | THM Study 2 - North A | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water | DWQR | SWD | DWQ - Preparing for Future Investment | MS7 | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-07-27 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 33370.8 | 28521.24 | 236988.8 | -234990.29 | 63890.55 | 0 | 0 | 0 | 63890.55 | 0 | 0 | 0 | 0 | 63890.55 | 337621.75 | [5 empty] | N | DW25PS | 100%
502769 | THM Study 3 - South | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water | DWQR | SWD | DWQ - Preparing for Future Investment | MS7 | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-07-27 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 31187.42 | 61469.41 | 219698.11 | -211199.31 | 101155.64 | 0 | 0 | 0 | 101155.64 | 0 | 0 | 0 | 0 | 101155.64 | 506432.62 | [5 empty] | N | DW25PS | 100%
502770 | THM Study 4 - East | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water | DWQR | SWD | DWQ - Preparing for Future Investment | MS7 | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-02-26 | 2020-07-27 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 30984.25 | 39677.79 | 213850.61 | -209126 | 75386.65 | 0 | 0 | 0 | 75386.65 | 0 | 0 | 0 | 0 | 75386.65 | 673842.56 | [5 empty] | N | DW25PS | 100%
502771 | THM Study 5 - North B | IR18 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water | DWQR | SWD | DWQ - Preparing for Future Investment | MS7 | 2017-06-21 | 2019-04-18 | 2019-04-18 |  |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 3662.62 | -39.85 | 0 | 0 | 3622.77 | 0 | 0 | 0 | 3622.77 | 0 | 0 | 0 | 0 | 3622.77 | 168810.87 | [5 empty] | Y | DW25PS | 100% | [67 empty] | 0
503302 | Thorn Drive Bearsden Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-04-22 | 2022-01-19 | 2022-04-07 | 2022-08-23 | 2022-11-23 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 51000 | 41413.02 | 21872.98 | 114286 | 155713.92 | 0 | 0 | 269999.92 | 0 | 0 | 0 | 0 | 269999.92 | 175086.76 | [5 empty] | N | FL_DD | 100%
503386 | Thornhill WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-04-16 | 2028-02-23 | 2028-06-27 | 2028-12-18 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 80052.86 | 3286.1 | 0.04 | 83339 | 0 | 0 | 0 | 83339 | 0 | 0 | 0 | 0 | 83339 | 122419.09 | [5 empty] | N | SG1 | 100%
46412 | Thornliebank TWP Refurb - TWP000223 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-20 | 2011-12-29 | 2011-12-19 |  | Glasgow City | 46611.64 | 0 | 1343.85 | 0 | 0 | 0 | 0 | 0 | 1343.85 | 0 | 0 | 0 | 47955.49 | 0 | 0 | 0 | 0 | 47955.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500434 | Thornton Main SPS Replace Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-06-11 | 2017-02-17 | 2017-03-27 | 2017-08-28 |  | Fife | 0 | 0 | 9631 | -379.02 | 33108.93 | 0.01 | 0 | 74.82 | 42435.73 | 0 | 0 | 0 | 42435.73 | 0 | 0 | 0 | 0 | 42435.73 | 209381.79 | [5 empty] | N | CM_WWI | 100%
45808 | Thorntonhall SPS Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-02-24 | 2011-04-11 | 2014-03-31 | 2014-03-31 | South Lanarkshire | 1668302.47 | 0 | 5850.63 | -7830.11 | 0 | 0 | 0 | 0 | -1979.48 | 0 | 0 | 0 | 1666322.99 | 0 | 0 | 0 | 0 | 1666322.99 | 119362.42 | [5 empty] | N | CM_WWNI | 10% | WQ01C | 90%
508481 | Thorters Reservoir Maintenance and spillway survey | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-09-15 | 2021-09-10 | 2022-04-25 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25424.08 | 25424.08 | 174639.71 | 0 | 0 | 200063.79 | 0 | 0 | 0 | 0 | 200063.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500185 | Thurso DOA (DOA001050) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-12-02 | 2016-01-11 | 2017-05-31 | 2017-07-31 | Highland | 0 | 0 | 55719 | 164000.19 | 18344.09 | 0 | 0 | 0 | 238063.28 | 0 | 0 | 0 | 238063.28 | 0 | 0 | 0 | 0 | 238063.28 | 72047.27 | [5 empty] | Y | CS11 | 47.31% | CS16D | 52.69% | [37 empty] | 1 | [27 empty] | 0
509739 | Thurso STC - Imported Sludge Cake Handling | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-08-05 | 2023-02-03 | 2023-09-18 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 139700.07 | 0 | 0 | 140000.07 | 0 | 0 | 0 | 0 | 140000.07 | 90601.29 | [5 empty] | N | WWNI | 100%
502284 | TI&BC - Browser Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-07-13 | 2017-02-24 | 2017-02-24 | 2017-07-03 |  | Scottish Water Wide | 0 | 0 | 0 | 449768.03 | 74721.03 | 0 | 0 | 0 | 524489.06 | 0 | 0 | 0 | 524489.06 | 0 | 0 | 0 | 0 | 524489.06 | 306661.32 | [5 empty] | N | CM_M&G | 100%
502124 | TI&BC - Technology for Water & Waste Water Operatives | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-03-25 | 2017-04-04 | 2017-04-04 | 2020-01-20 |  | Scottish Water Wide | 0 | 0 | 36200.61 | 699080.87 | 675812 | 555790.83 | 28729.71 | -4586.45 | 1991027.57 | 0 | 0 | 0 | 1991027.57 | 0 | 0 | 0 | 0 | 1991027.57 | 306661.32 | [5 empty] | N | CM_M&G | 100%
502219 | TI&BC Dual Communications for Telemetry | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-04-29 | 2017-03-30 | 2017-03-30 | 2017-03-03 |  | Scottish Water Wide | 0 | 0 | 0 | 91554.02 | 0 | 0 | 0 | 0 | 91554.02 | 0 | 0 | 0 | 91554.02 | 0 | 0 | 0 | 0 | 91554.02 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501308 | TI&BC SR15 Portfolio Delivery Resources | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2021-03-02 |  | Scottish Water Wide | 0 | 0 | 341940 | 956278.05 | 785286.34 | 307441.51 | 77722.64 | 42568.08 | 2511236.62 | 0 | 0 | 0 | 2511236.62 | 0 | 0 | 0 | 0 | 2511236.62 | 306661.32 | [5 empty] | N | CM_M&G | 100%
502351 | TIBC SAN @ Stepps Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2017-02-02 |  | Scottish Water Wide | 0 | 0 | 0 | 457663.94 | 0 | 0 | 0 | 0 | 457663.94 | 0 | 0 | 0 | 457663.94 | 0 | 0 | 0 | 0 | 457663.94 | 306661.32 | [5 empty] | N | CM_M&G | 100%
501540 | Tighnabruaich SR Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-08 | 2027-11-18 | 2028-03-23 | 2028-08-02 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126077.01 | 0 | 0 | 126077.01 | 0 | 0 | 0 | 0 | 126077.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502432 | Tighnabruaich WTW - Ardlamont SR and SDN | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-03-21 | 2019-08-28 | 2019-08-28 | 2019-05-28 | 2019-05-28 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 166.63 | 340.64 | -117.91 | 0 | 389.36 | 0 | 0 | 0 | 389.36 | 0 | 0 | 0 | 0 | 389.36 | 0 | [5 empty] | N | DW25T | 100%
502310 | Tighnabruaich WTW - Portavadie DSR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS7 | 2015-04-27 | 2016-09-30 | 2018-02-21 | 2018-07-31 | 2018-10-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 8967.13 | 44642.05 | 60990.03 | 204.24 | -478.29 | 114325.16 | 0 | 0 | 0 | 114325.16 | 0 | 0 | 0 | 0 | 114325.16 | 0 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
502431 | Tighnabruaich WTW - Portavadie SR and SDN | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-04-06 | 2019-06-21 | 2019-06-05 | 2019-05-28 | 2019-05-28 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0.02 | 0 | 85.16 | 0 | 0 | 85.18 | 0 | 0 | 0 | 85.18 | 0 | 0 | 0 | 0 | 85.18 | 0 | [5 empty] | N | DW25T | 100%
502575 | Tighnabruaich WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-22 | 2020-04-22 | 2020-04-22 | 2020-04-22 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 20930.23 | 276.28 | 6167.27 | 8909.76 | -2847.01 | 33436.53 | -130.96 | 0 | 0 | 33305.57 | 0 | 0 | 0 | 0 | 33305.57 | 122419.09 | [5 empty] | N | WG1 | 100%
500181 | Tillicoultry DOA (DOA000310) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-12-19 | 2016-12-20 | 2017-01-31 | 2017-02-28 | Clackmannanshire | 0 | 0 | 13425 | 5203 | -5389.94 | 0 | 0 | 0 | 13238.06 | 0 | 0 | 0 | 13238.06 | 0 | 0 | 0 | 0 | 13238.06 | 85931.02 | [5 empty] | Y | EC01D | 100% | [40 empty] | 1 | [26 empty] | 0
501156 | Tillicoultry STW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-07-11 | 2018-12-20 | 2019-02-04 | 2021-10-11 |  | Clackmannanshire | 0 | 0 | 0 | 148181.94 | 252197.65 | 461532.27 | 1212128.93 | 1218823.21 | 3292864 | 727659 | 0 | 0 | 4020523 | 0 | 0 | 495758 | 495758 | 4516281 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503305 | Tillicoultry WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-04-15 | 2019-04-15 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 24921.03 | 0 | 0 | 24921.03 | 0 | 0 | 0 | 24921.03 | 0 | 0 | 0 | 0 | 24921.03 | 122419.09 | [5 empty] | N | SG1 | 100%
505070 | Tillicoultry WwTW Replacement Air compressor Units | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 |  | 2020-02-20 | 2021-03-18 | 2021-07-16 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 1962.62 | 1774.78 | 3737.4 | 26262.6 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | 209381.79 | [5 empty] | N | Ww3 | 100%
403131 | Tiree Crossapol Replacement Septic Tank and New Outfall | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater | SEPA | SWMD | Wastewater non infrastructure | MS7 | 2012-11-30 | 2013-09-17 | 2014-01-21 | 2014-11-30 | 2015-03-31 | Argyll and Bute-North Argyll | 310492 | 0 | 2000 | 5259.41 | 0 | 0 | 0 | 0 | 7259.41 | 0 | 0 | 0 | 317751.41 | 0 | 0 | 0 | 0 | 317751.41 | 90601.29 | [5 empty] | Y | CM_WWNI | 100% | [34 empty] | 1 | [32 empty] | 0
500900 | Tiree WOA Caolas SR (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-11-18 | 2017-02-27 | 2017-02-27 | 2019-07-23 | 2019-07-23 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 186.92 | -186.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | DW25D | 100%
500910 | Tiree WOA Ruaig SDN (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2017-03-15 | 2017-03-23 | 2017-03-23 |  |  | Argyll and Bute-North Argyll | 0 | 0 | 16704 | 7033.02 | 574.14 | 2382 | 1502.35 | 0 | 28195.51 | 0 | 0 | 0 | 28195.51 | 0 | 0 | 0 | 0 | 28195.51 | 466277.79 | [5 empty] | Y | DW25T | 100% | [67 empty] | 0
500902 | Tiree WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2018-03-31 | 2018-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 83.72 | -83.72 | 123.03 | 0 | -123.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
501199 | Tiree WTW Boreholes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-07-13 | 2017-08-23 | 2017-09-25 | 2023-04-03 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 42762.22 | 95686.73 | 32236.48 | -23648.78 | 661.45 | 147698.1 | 390806.06 | 0 | 0 | 538504.16 | 0 | 0 | 0 | 0 | 538504.16 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
404033 | Tobermory (Craignure WQ) - Man Del Completion Project TR 045029 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2009-03-12 | 2012-11-01 | 2013-11-20 | 2020-04-28 | 2020-12-01 | Argyll and Bute-North Argyll | 26875 | 0 | 289842.67 | 3007982.5 | 1834478.49 | 1087259 | 48950.8 | 47948.54 | 6316462 | 17183.42 | 5240.9431 | 7275.3213 | 6360520.42 | 2034.3782 | 0 | 0 | 2034.3782 | 6362554.7982 | 0 |  |  |  |  | 44674.4718 | N | DW23 | 30.5% | WG1 | 69.5%
509742 | Tobermory DOA - Argyll Terrace & West Street - Sewer Rehabilitation | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-12-14 | 2022-05-13 | 2022-12-26 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4625 | 4625 | 60374.74 | 0 | 0 | 64999.74 | 0 | 0 | 0 | 0 | 64999.74 | 209381.79 | [5 empty] | N | WWI | 100%
403165 | Tobermory Reservoir | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-07 | 2014-07-28 | 2014-07-23 | 2014-05-16 | 2014-05-16 | Argyll and Bute-North Argyll | 63442.19 | 0 | 1452 | 0 | 0 | 0 | 0 | 0 | 1452 | 0 | 0 | 0 | 64894.19 | 0 | 0 | 0 | 0 | 64894.19 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500912 | Tobermory WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-09-30 | 2016-09-30 | Argyll and Bute-North Argyll | 0 | 0 | 6480 | -3258.38 | 231.9 | 0 | 0 | 0 | 3453.52 | 0 | 0 | 0 | 3453.52 | 0 | 0 | 0 | 0 | 3453.52 | 0 | [5 empty] | Y | DW25D | 100% | [22 empty] | 1 | [44 empty] | 0
504709 | Toberonochy STW restore outfall | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 |  | 2020-12-08 | 2022-08-26 | 2022-12-02 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4056.36 | 4056.36 | 23464.59 | 0 | 0 | 27520.95 | 0 | 0 | 0 | 0 | 27520.95 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500882 | Tolsta Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-11-02 | 2018-09-21 | 2018-11-20 | 2019-06-25 | 2020-03-19 | Na H-Eileanan an Iar | 0 | 0 | 5113.05 | 7883.52 | 18934.79 | 109738.09 | 62707.8 | 395.6 | 204772.85 | -2817.47 | -2817.47 | -3911.128 | 201955.38 | -1093.658 | 0 | 0 | -1093.658 | 200861.722 | 432810.51 | [5 empty] | N | DW5FS | 100%
506609 | Tomatin river crossing replacement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-05-19 | 2020-11-30 | 2021-07-05 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87740.48 | 87740.48 | 2345.8 | 0 | 0 | 90086.28 | 0 | 0 | 0 | 0 | 90086.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511814 | Tomatin WOA- Additional mains rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-03-17 | 2022-06-23 | 2023-02-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2616.82 | 2616.82 | 37383.18 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000 | 311236.79 | [5 empty] | N | WSI | 100%
404134 | Tomatin WTW - Cartridge Filters + UV | Q&S3B | Completion | OMG180 |  |  | Water | DWQR | NONINF | OMG180 | MS3 | 2016-03-31 | 2018-12-20 | 2018-12-21 | 2021-06-17 | 2021-09-16 | Highland | 0 | 0 | 0 | 0 | 500250.07 | 1803305.64 | 1897574.56 | 519152.11 | 4720282.38 | 70982.62 | 70982.6151 | 501112.5572 | 4791265 | 430129.9421 | 0 | 0 | 430129.9421 | 5221394.9421 | 3033534 |  |  |  |  | 219279.9996 | Y | DW25 | 100% | [20 empty] | 1 | [46 empty] | 0
404103 | Tomatin WTW Upgrade | Q&S3B | Completion | OMG180 |  |  | Water |  | SWD | OMG180 | MS7 | 2016-03-31 | 2018-01-23 | 2017-12-12 | 2017-12-12 | 2017-12-20 | Highland | 0 | 0 | 22912.75 | -22912.75 | 6776.65 | 0 | 18.47 | 32.61 | 6827.73 | 0 | 0 | 0 | 6827.73 | 0 | 0 | 0 | 0 | 6827.73 | 0 | [5 empty] | N | DW25 | 100%
503527 | Tomatin WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2024-07-23 | 2026-06-09 | 2026-09-14 | 2027-10-08 |  | Highland | 0 | 0 | 0 | 0 | 0 | 59441.86 | 14565.38 | -7889.24 | 66118 | 1933882.42 | 0 | 0 | 2000000.42 | 0 | 0 | 0 | 0 | 2000000.42 | 122419.09 | [5 empty] | N | SG1 | 100%
502576 | Tomich WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 20930.23 | 671.68 | 2160.9 | 25078.91 | -43969.68 | 4872.04 | 0 | 0 | 0 | 4872.04 | 0 | 0 | 0 | 0 | 4872.04 | 122419.09 | [5 empty] | N | WG1 | 100%
403588 | Tomnavoulin Catchment - Intake and treatment Improvements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-09-17 | 2013-10-14 | 2013-11-08 | 2015-02-12 |  | Moray | 264315 | 0 | 20484.38 | 151.33 | 64.22 | 0 | 0 | 0 | 20699.93 | 0 | 0 | 0 | 285014.93 | 0 | 0 | 0 | 0 | 285014.93 | 119022.58 | [5 empty] | N | CM_WSI | 100%
501201 | Tomnavoulin WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2027-04-01 | 2028-10-25 | 2029-02-27 | 2021-01-15 |  | Aberdeenshire | 0 | 0 | 14830.71 | 0 | 0 | 0 | 0 | -14651.16 | 179.55 | 0 | 0 | 0 | 179.55 | 0 | 0 | 0 | 0 | 179.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508579 | Tongue WwTW - SR21 Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2023-10-13 | 2025-08-08 | 2026-01-05 | 2026-12-07 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19078 | 19078 | 1980921.97 | 0 | 0 | 1999999.97 | 0 | 0 | 0 | 0 | 1999999.97 | 122419.09 | [5 empty] | N | SG1 | 100%
501736 | Torcross DSR Mainout | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2028-07-24 | 2029-05-09 | 2029-09-12 | 2030-01-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99999.97 | 0 | 0 | 99999.97 | 0 | 0 | 0 | 0 | 99999.97 | 4989107.96 | [5 empty] | N | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 28.57% | CM_WSI | 47.62%
505092 | Torduff and Clubbiedean road repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-03-04 | 2020-04-10 | 2020-08-12 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 49029.9 | 0 | 49029.9 | 0 | 0 | 0 | 49029.9 | 0 | 0 | 0 | 0 | 49029.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502387 | Tornagrain Development Water Infrastructure | IR18 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2018-12-18 | 2018-12-18 | 2019-02-04 | 2019-02-21 | 2019-02-21 | Highland | 0 | 0 | 0 | 0 | 0 | 856598.13 | 0 | 0 | 856598.13 | 0 | 0 | 0 | 856598.13 | 0 | 0 | 0 | 0 | 856598.13 | 444766.03 |  |  |  |  | 17705 | N | WG5 | 100%
31091 | Torphichen STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-29 | 2010-11-01 | 2011-02-01 | 2014-01-07 | 2014-01-24 | West Lothian | 3119049.89 | 0 | 154475.41 | 11385.81 | 0 | 0 | 0 | 0 | 165861.22 | 0 | 0 | 0 | 3284911.11 | 0 | 0 | 0 | 0 | 3284911.11 | 57522.26 | [5 empty] | N | EC10A | 10% | EC04A | 90%
403427 | Torphichen WMR | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-04-03 | 2013-09-24 | 2013-09-30 | 2015-01-07 |  | West Lothian | 793801 | 0 | 14217 | -3705.55 | 0 | 0 | 0 | 0 | 10511.45 | 0 | 0 | 0 | 804312.45 | 0 | 0 | 0 | 0 | 804312.45 | 311236.79 | [5 empty] | N | CM_WSI | 100%
45543 | Torphins STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2012-03-27 | 2012-11-12 | 2014-02-21 | 2014-02-25 | Aberdeenshire | 1096857.19 | 0 | 22714.05 | 0 | 0 | 0 | 0 | 0 | 22714.05 | 0 | 0 | 0 | 1119571.24 | 0 | 0 | 0 | 0 | 1119571.24 | 119362.42 | [5 empty] | N | CM_WWNI | 20% | WQ01 | 80%
500883 | Torra Islay RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-10-06 | 2018-09-18 | 2018-11-19 | 2019-03-31 | 2020-02-29 | Argyll and Bute-North Argyll | 0 | 0 | 1899.35 | 8208.97 | 11362.09 | 42833.48 | 11547.79 | -2552.72 | 73298.96 | 0 | 0 | 0 | 73298.96 | 0 | 0 | 0 | 0 | 73298.96 | 126571.05 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 16.8 | [43 empty] | 0
502371 | Torra WOA Airport SR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-04-23 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 10046.51 | 410.1 | 1489.68 | -9446.56 | 0 | 2499.73 | 0 | 0 | 0 | 2499.73 | 0 | 0 | 0 | 0 | 2499.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500901 | Torra WOA Airport SR (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2016-12-22 | 2017-03-01 | 2017-03-01 | 2017-12-31 | 2017-12-31 | Argyll and Bute-North Argyll | 0 | 0 | 3139.53 | 0 | 451.11 | 0 | 0 | 0 | 3590.64 | 0 | 0 | 0 | 3590.64 | 0 | 0 | 0 | 0 | 3590.64 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
508576 | Torra WTW - PLC & SCADA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW1 | 2022-03-30 | 2024-01-17 | 2024-06-26 | 2025-10-27 | 2026-01-27 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5225.03 | 5225.03 | 244775.17 | 0 | 0 | 250000.2 | 0 | 0 | 0 | 0 | 250000.2 | 0 | [5 empty] | N | SR21_WA | 100%
502374 | Torra WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-08-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 8583.6 | 1212.88 | 13318.8 | 86414.4 | -28534.61 | 80995.07 | 0 | 0 | 0 | 80995.07 | 0 | 0 | 0 | 0 | 80995.07 | 122419.09 | [5 empty] | N | WG1 | 100%
503551 | Torra WTW Growth - Emergency Tankering | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-05-01 | 2019-05-01 | 2019-06-17 | 2020-08-25 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 67151.61 | 6293.7 | 73445.31 | 0 | 0 | 0 | 73445.31 | 0 | 0 | 0 | 0 | 73445.31 | 122419.09 | [5 empty] | N | SG1 | 100%
503562 | Torra WTW Growth - TTU Installation | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2019-04-30 | 2020-03-17 | 2020-03-31 | 2021-09-10 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 718160.6 | 1742792.81 | 2460953.41 | 448693.93 | 0 | 0 | 2909647.34 | 0 | 0 | 190352.66 | 190352.66 | 3100000 | 122419.09 | [5 empty] | N | SG1 | 100%
502279 | Torra WTW Sludge Lagoon Upgrade | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater | SEPA | SWMD | Sludge | MS7 | 2017-06-16 | 2018-03-21 | 2018-05-28 | 2018-11-30 | 2019-01-31 | Highland | 0 | 0 | 0 | 21819.82 | 72449.6 | 69587.68 | 275.83 | -1303.69 | 162829.24 | 0 | 0 | 0 | 162829.24 | 0 | 0 | 0 | 0 | 162829.24 | 207663.58 | [5 empty] | Y | LA01 | 100% | [41 empty] | 1 | [25 empty] | 0
500842 | Torridon RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-10-28 | 2017-03-23 | 2017-04-25 | 2017-06-30 | 2018-03-31 | Highland | 0 | 0 | 3000 | 10403.97 | 11972.43 | 12450.16 | 1706.7 | 85.44 | 39618.7 | 0 | 0 | 0 | 39618.7 | 0 | 0 | 0 | 0 | 39618.7 | 13518.27 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 4.15 | [43 empty] | 0
500903 | Torridon WTW (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2017-02-27 | 2017-03-16 | 2017-03-16 | 2017-07-31 | 2017-07-31 | Highland | 0 | 0 | 2160 | 2171.48 | -792.99 | 0 | 0 | 0 | 3538.49 | 0 | 0 | 0 | 3538.49 | 0 | 0 | 0 | 0 | 3538.49 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
46826 | Torrin WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-19 | 2012-06-20 | 2012-11-19 | 2015-03-31 | 2015-03-31 | Highland | 7865477.59 | 0 | 387478.79 | 10084.71 | -15946.3 | 0 | 0 | 0 | 381617.2 | 0 | 0 | 0 | 8247094.79 | 0 | 0 | 0 | 0 | 8247094.79 | 28761.13 | [5 empty] | N | WG4 | 20.04% | DW23 | 79.96%
402676 | Torwood WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS1 | 2012-06-19 | 2021-08-09 | 2021-11-03 | 2023-08-07 |  | Falkirk | 236252 | 0 | 112617 | 7437.6 | 14127.4 | 71434.5 | 479737.4 | 420402.1 | 1105756 | 1637406.12 | 0 | 0 | 2979414.12 | 0 | 0 | 0 | 0 | 2979414.12 | 0 | [5 empty] | N | SG1 | 100%
507966 | Touch No.3 - MIoS_Outlet Pipework and Valve Tower Modifications | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-08-30 | 2023-04-04 | 2023-06-26 | 2024-05-13 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5374.77 | 5374.77 | 394933.28 | 0 | 0 | 400308.05 | 0 | 0 | 0 | 0 | 400308.05 | 311236.79 | [5 empty] | N | CM_WSI | 100%
511359 | Touch Reservoirs Tower Surveys | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | GW0 |  | 2021-05-24 | 2021-08-13 | 2022-03-28 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | [5 empty] | N | SR21_WA | 100%
403613 | Toughbook Replacement Project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2015-03-12 |  | Scottish Water Wide | 4546746 | 0 | -55361.66 | 0 | 0 | 0 | 0 | 0 | -55361.66 | 0 | 0 | 0 | 4491384.34 | 0 | 0 | 0 | 0 | 4491384.34 | 613322.63 | [5 empty] | N | CM_M&G | 100%
502973 | Townholm Pipe Bridge Kilmarnock | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2018-06-18 | 2021-02-24 | 2021-05-05 | 2021-12-07 |  | East Ayrshire | 0 | 0 | 0 | 0 | 13214.19 | 6301.35 | 1223.37 | 112733.28 | 133472.19 | 561918.81 | 0 | 0 | 695391 | 0 | 0 | 0 | 0 | 695391 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403411 | TR61 Version 12 Software (WRc CP500) | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-03-04 | 2013-03-04 | 2013-04-01 | 2016-02-02 |  | Scottish Water Wide | 27297.44 | 0 | 5940 | 0 | 0 | 0 | 0 | 0 | 5940 | 0 | 0 | 0 | 33237.44 | 0 | 0 | 0 | 0 | 33237.44 | 730242.44 | [5 empty] | N | WSI | 0.25% | WSNI | 0.25% | WWNI | 0.25% | WWI | 99.25%
501327 | Trade Effluent Systems Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2019-03-04 |  | Scottish Water Wide | 0 | 0 | 0 | 90592.02 | 409407.98 | 365980.55 | 0 | 0 | 865980.55 | 0 | 0 | 0 | 865980.55 | 0 | 0 | 0 | 0 | 865980.55 | 306661.32 | [5 empty] | N | CM_M&G | 100%
503593 | Transformational Change Project | Q&S4 | Sustaining existing high service for customers | Transformation Demonstrators |  |  | General |  | SWD | Transformation Demonstrators | GW2 | 2021-06-16 | 2023-01-24 | 2023-05-29 | 2024-12-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3468562.99 | 4354400.18 | 7822963.17 | 664782.84 | 0 | 0 | 8487746.01 | 0 | 0 | 0 | 0 | 8487746.01 | 0 | [5 empty] | N | SR15_CMA_TD | 100%
402152 | Treated Water Sample tap replacement Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-06-13 | 2011-08-08 | 2011-09-12 | 2013-10-08 |  | Scottish Water Wide | 1843533.56 | 0 | 3.59 | 0 | 0 | 0 | 0 | 0 | 3.59 | 0 | 0 | 0 | 1843537.15 | 0 | 0 | 0 | 0 | 1843537.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401431 | Treated Water Sample Tap Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-24 | 2011-11-04 | 2012-02-01 | 2015-11-20 |  | Scottish Water Wide | 279973 | 0 | -2103.28 | 0 | 0 | 0 | 0 | 0 | -2103.28 | 0 | 0 | 0 | 277869.72 | 0 | 0 | 0 | 0 | 277869.72 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503253 | Treated Water Storage Water Quality Improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1496070.64 | 2383590.29 | 867868.03 | 4747528.96 | 51997.49 | 0 | 0 | 4799526.45 | 0 | 0 | 0 | 0 | 4799526.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503065 | Treated Water Storage Water Quality Improvements - Phase 1 East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2018-04-19 | 2018-06-21 | 2018-06-21 | 2020-05-29 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 53891.2 | 2011256.74 | 717270.95 | 748859.53 | 3531278.41 | 0 | 0 | 0 | 3531278.41 | 0 | 0 | 0 | 0 | 3531278.41 | 430259.37 | [5 empty] | N | CM_WSI | 20% | CM_WSNI | 80%
503066 | Treated Water Storage Water Quality Improvements - Phase 1 North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2018-04-19 | 2018-06-21 | 2018-06-21 | 2020-05-26 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 18837.21 | 306326.12 | 68642.88 | 76628.79 | 470435 | 0 | 0 | 0 | 470435 | 0 | 0 | 0 | 0 | 470435 | 430259.37 | [5 empty] | N | CM_WSI | 20% | CM_WSNI | 80%
503067 | Treated Water Storage Water Quality Improvements - Phase 1 South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2018-04-17 | 2018-06-18 | 2018-06-18 | 2020-05-29 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 12558.14 | 741048.22 | -19257.25 | 269382.89 | 1003732 | 0 | 0 | 0 | 1003732 | 0 | 0 | 0 | 0 | 1003732 | 430259.37 | [5 empty] | N | CM_WSI | 20% | CM_WSNI | 80%
503068 | Treated Water Storage Water Quality Improvements - Phase 1 West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2018-04-17 | 2018-06-18 | 2018-06-18 | 2020-03-23 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 12558.14 | 1495718.6 | 15614.09 | 407678.17 | 1931569 | 0 | 0 | 0 | 1931569 | 0 | 0 | 0 | 0 | 1931569 | 430259.37 | [5 empty] | N | CM_WSI | 20% | CM_WSNI | 80%
503553 | Treated Water Storage Water Quality Improvements - Phase 2 East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-25 | 2019-03-28 | 2019-04-01 | 2022-02-16 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 2560996 | 2926697.94 | 5487693.94 | 38681.63 | 0 | 0 | 5526375.57 | 0 | 0 | 0 | 0 | 5526375.57 | 430259.37 | [5 empty] | N | CM_WSI | 10% | CM_WSNI | 90%
503554 | Treated Water Storage Water Quality Improvements - Phase 2 North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2019-03-25 | 2019-03-28 | 2019-04-01 | 2021-03-26 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 1090004.12 | 905569.02 | 1995573.14 | 165922.18 | 0 | 0 | 2161495.32 | 0 | 0 | 0 | 0 | 2161495.32 | 430259.37 | [5 empty] | N | CM_WSI | 10% | CM_WSNI | 90%
503555 | Treated Water Storage Water Quality Improvements - Phase 2 South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2019-03-25 | 2019-03-28 | 2019-04-01 | 2021-03-31 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 1349014.29 | 1488309.12 | 2837323.41 | 168812.25 | 0 | 0 | 3006135.66 | 0 | 0 | 0 | 0 | 3006135.66 | 430259.37 | [5 empty] | N | CM_WSI | 10% | CM_WSNI | 90%
503556 | Treated Water Storage Water Quality Improvements - Phase 2 West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2019-03-25 | 2019-03-28 | 2019-04-01 | 2022-02-02 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 2086737.07 | 2480790.34 | 4567527.41 | 117196.33 | 0 | 0 | 4684723.74 | 0 | 0 | 0 | 0 | 4684723.74 | 430259.37 | [5 empty] | N | CM_WSI | 10% | CM_WSNI | 90%
509118 | Trial Inspections of Reservoir Bridges | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2020-10-08 | 2021-04-26 | 2021-04-29 | 2021-07-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46775 | 46775 | 23225.44 | 0 | 0 | 70000.44 | 0 | 0 | 0 | 0 | 70000.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500238 | Trinity SPS Rising Main - Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-05-07 | 2016-12-14 | 2017-02-28 | 2017-10-23 |  | City of Edinburgh | 0 | 0 | 86983 | 325249 | 422267.63 | 0.37 | -6637.24 | 0 | 827862.76 | 0 | 0 | 0 | 827862.76 | 0 | 0 | 0 | 0 | 827862.76 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402824 | Trinity SPS Rising main Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-14 | 2014-01-30 | 2014-02-24 | 2015-03-25 |  | City of Edinburgh | 209763 | 0 | 929 | 925.72 | -4288.08 | 0 | 0 | 0 | -2433.36 | 0 | 0 | 0 | 207329.64 | 0 | 0 | 0 | 0 | 207329.64 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500851 | Trislaig RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2015-11-04 | 2016-03-25 | 2016-05-24 | 2018-03-31 | 2018-06-30 | Highland | 0 | 0 | 1736.99 | 6788.87 | 456.88 | 45638.47 | 2653.4 | 0 | 57274.61 | 0 | 0 | 0 | 57274.61 | 0 | 0 | 0 | 0 | 57274.61 | 5909.44 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 33.34 | [43 empty] | 0
402263 | Tronafirth ST - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-08-17 | 2013-09-30 | 2013-12-02 | 2014-03-28 | 2014-03-28 | Shetland Islands | 349978.5 | 0 | 1181.5 | -214.63 | 0 | 0 | 0 | 0 | 966.87 | 0 | 0 | 0 | 350945.37 | 0 | 0 | 0 | 0 | 350945.37 | 0 | [5 empty] | N | SG1 | 100%
402520 | Troon Pan Rocks SPS EO Outfall Extension | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-06 | 2016-02-15 | 2016-02-01 | 2016-02-19 |  | South Ayrshire | 49398.28 | 0 | 3152.8 | 0 | 0 | 0 | 0 | 0 | 3152.8 | 0 | 0 | 0 | 52551.08 | 0 | 0 | 0 | 0 | 52551.08 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403550 | Troqueer WWTW - Critical items for compliance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-08-02 | 2014-01-15 | 2014-01-15 | 2015-11-05 |  | Dumfries and Galloway | 530000 | 0 | 81884.68 | 4940 | 0 | 0 | 0 | 0 | 86824.68 | 0 | 0 | 0 | 616824.68 | 0 | 0 | 0 | 0 | 616824.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500182 | Troqueer DOA (DOA000121) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2020-01-07 | 2020-03-03 | Dumfries and Galloway | 0 | 0 | 15707 | 39892.66 | 73449.34 | 37250 | 33701 | -9574.58 | 190425.42 | 0 | 0 | 0 | 190425.42 | 0 | 0 | 0 | 0 | 190425.42 | 111423.32 | [5 empty] | N | EC01G | 6.06% | EC01D | 44.79% | CS16D | 49.15%
402881 | Troqueer Sewage Pump Station | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2012-08-27 | 2017-06-20 | 2017-06-20 | 2017-06-20 |  | Dumfries and Galloway | 235896 | 0 | 185439 | 232493.57 | 4132.23 | 419.39 | 732.69 | 0 | 423216.89 | 0 | 0 | 0 | 659112.89 | 0 | 0 | 0 | 0 | 659112.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511125 | Troqueer STC-Replacement of Klampress | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2023-04-04 | 2024-10-10 | 2025-01-08 | 2025-12-16 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.96 | 0 | 0 | 999999.96 | 0 | 0 | 0 | 0 | 999999.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402628 | Troqueer WwTW DO Plant Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-04-16 | 2012-08-08 | 2012-09-28 | 2013-09-16 |  | Dumfries and Galloway | 336759.98 | 0 | 466.27 | 0 | 0 | 0 | 0 | 0 | 466.27 | 0 | 0 | 0 | 337226.25 | 0 | 0 | 0 | 0 | 337226.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
400605 | TS 3rd Party Services | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 |  | Scottish Water Wide | -1577562.8 | 0 | 26893.83 | 28990.15 | -113146.26 | 146799.59 | 10672.33 | 9186.7 | 109396.34 | 0 | 0 | 0 | -1468166.46 | 0 | 0 | 0 | 0 | -1468166.46 | 306661.32 | [5 empty] | N | OHDS1 | 100%
400474 | TS AIM indirect overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 |  | Scottish Water Wide | 19124680.68 | 0 | 12228.52 | -13293.38 | -4185.27 | 170.32 | 0 | 0 | -5079.81 | 0 | 0 | 0 | 19119600.87 | 0 | 0 | 0 | 0 | 19119600.87 | 306661.32 | [5 empty] | N | OHDS1 | 100%
403896 | TS Alliance Management | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-29 | 2019-03-28 | 2018-10-08 | 2018-10-08 |  | Scottish Water Wide | 625772.54 | 0 | 9696.46 | 0 | 0 | 0 | 0 | 0 | 9696.46 | 0 | 0 | 0 | 635469 | 0 | 0 | 0 | 0 | 635469 | 613322.63 | [5 empty] | N | OHDS1 | 50% | OHDW1 | 50%
400479 | TS AS indirect overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 |  | Scottish Water Wide | 9050647.78 | 0 | 14880.53 | -2872.23 | 499.08 | 0 | 0 | 0 | 12507.38 | 0 | 0 | 0 | 9063155.16 | 0 | 0 | 0 | 0 | 9063155.16 | 306661.32 | [5 empty] | N | OHDS1 | 100%
403897 | TS Business Improvement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-29 | 2019-03-27 | 2018-10-08 | 2018-10-08 |  | Scottish Water Wide | 202665.79 | 0 | 185.64 | 0 | 368.78 | 0 | 0 | 0 | 554.42 | 0 | 0 | 0 | 203220.21 | 0 | 0 | 0 | 0 | 203220.21 | 613322.63 | [5 empty] | N | OHDS1 | 50% | OHDW1 | 50%
400541 | TS Corporate Comms indirect overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 |  | Scottish Water Wide | 3623275.23 | 0 | 7037.13 | 0 | 2651.96 | 0 | 0 | 0 | 9689.09 | 0 | 0 | 0 | 3632964.32 | 0 | 0 | 0 | 0 | 3632964.32 | 306661.32 | [5 empty] | N | OHDS1 | 100%
400537 | TS Financial Control indirect overhead | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 1771807.55 | 0 | 96120 | 0 | 3306.49 | 0 | 2144.55 | 0 | 101571.04 | 0 | 0 | 0 | 1873378.59 | 0 | 0 | 0 | 0 | 1873378.59 | 0 | [5 empty] | N | EC01A | 100%
400477 | TS GIV indirect overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 |  | Scottish Water Wide | 5361088.34 | 0 | 0 | 0 | 5182.33 | 0 | 0 | 0 | 5182.33 | 0 | 0 | 0 | 5366270.67 | 0 | 0 | 0 | 0 | 5366270.67 | 306661.32 | [5 empty] | N | OHDS1 | 100%
400539 | TS I.T. indirect overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 |  | Scottish Water Wide | 23134684.93 | 0 | -70104.94 | 611.64 | 0 | 0 | 0 | 0 | -69493.3 | 0 | 0 | 0 | 23065191.63 | 0 | 0 | 0 | 0 | 23065191.63 | 613322.63 | [5 empty] | N | OHDS1 | 50% | OHDW1 | 50%
400542 | TS Regulation indirect overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 |  | Scottish Water Wide | 3163070.15 | 0 | 2136.94 | 0 | 0 | 0 | 0 | 0 | 2136.94 | 0 | 0 | 0 | 3165207.09 | 0 | 0 | 0 | 0 | 3165207.09 | 306661.32 | [5 empty] | N | OHDS1 | 100%
400543 | TS SW Overhead reallocation project | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 |  | Scottish Water Wide | -63886696.7 | 0 | -922004.76 | 0 | 0 | 0 | 0 | 0 | -922004.76 | 0 | 0 | 0 | -64808701.46 | 0 | 0 | 0 | 0 | -64808701.46 | 306661.32 | [5 empty] | N | OHDS1 | 100%
403499 | Tullibardine WSZ - Orchil Road Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-06-12 | 2014-03-20 | 2014-03-27 | 2014-11-13 |  | Perth and Kinross | 503061 | 0 | 673.32 | 393.91 | 0 | 0 | 0 | 0 | 1067.23 | 0 | 0 | 0 | 504128.23 | 0 | 0 | 0 | 0 | 504128.23 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503661 | Tullich PAC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2019-08-13 | 2020-02-24 | 2020-02-24 | 2021-02-05 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 446325.27 | 348778.09 | 795103.36 | 1944.32 | 0 | 0 | 797047.68 | 0 | 0 | 0 | 0 | 797047.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500852 | Tullich RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS7 | 2015-12-10 | 2016-03-30 | 2016-08-08 | 2017-07-03 | 2018-03-08 | Argyll and Bute-North Argyll | 0 | 0 | 6651.26 | 23530.25 | 38979.6 | 4076.69 | -393.93 | 0 | 72843.87 | 0 | 0 | 0 | 72843.87 | 0 | 0 | 0 | 0 | 72843.87 | 65608.63 | [5 empty] | N | DW5FS | 100%
500573 | Tullich WOA - Oban North & South TWS Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-06-08 | 2020-03-27 | 2020-03-29 | 2021-12-01 |  | Highland | 0 | 0 | 103505 | 155182.55 | 195899.59 | 302107 | 901362.17 | 1933160.69 | 3591217 | 4754055 | 0 | 0 | 8345272 | 0 | 0 | -345272 | -345272 | 8000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503617 | Tullich WOA Oban 12 Main Refurbishment (CWA) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2019-07-05 | 2020-11-18 | 2020-11-09 | 2022-03-17 |  | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 469003.46 | 1154076.25 | 1623079.71 | 1134943.55 | 0 | 0 | 2758023.26 | 0 | 0 | 354931.74 | 354931.74 | 3112955 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501111 | Tullich WOA Oban 12inch Da Main Refurbishment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-03-21 | 2020-04-02 | 2020-04-02 | 2020-02-28 |  | Argyll and Bute-North Argyll | 0 | 0 | 36000 | 9752.93 | 96614.05 | 74192.43 | -178370.28 | -30319.65 | 7869.48 | 0 | 0 | 0 | 7869.48 | 0 | 0 | 0 | 0 | 7869.48 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500054 | Tullich WOA Oban South WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-18 | 2016-11-18 | 2017-06-26 | 2018-09-11 |  | Argyll and Bute-North Argyll | 0 | 0 | 8235 | 40129 | 145882.98 | -30676.99 | -10108.21 | 197.53 | 153659.31 | 0 | 0 | 0 | 153659.31 | 0 | 0 | 0 | 0 | 153659.31 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502233 | Tullich WTW Temporary UV treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2017-01-25 |  | Highland | 0 | 0 | 0 | 1418228.74 | -20597.01 | 572.75 | 0 | 0 | 1398204.48 | 0 | 0 | 0 | 1398204.48 | 0 | 0 | 0 | 0 | 1398204.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
46838 | Tullich WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2015-03-27 | 2016-04-01 | 2014-10-24 | 2016-04-01 | Argyll and Bute-North Argyll | 1956538.93 | 0 | 776.76 | 142.35 | 0 | 0 | 0 | 0 | 919.11 | 0 | 0 | 0 | 1957458.04 | 0 | 0 | 0 | 0 | 1957458.04 | 147783.71 | [5 empty] | N | CM_WSNI | 40% | DW23 | 60%
403862 | Tullich WTW Upgrade TR from 046838 | Q&S3B | Completion | Non OMG180 |  |  | Water | DWQR | NONINF | Non OMG180 | MS6 | 2014-06-24 | 2015-10-29 | 2016-01-18 | 2019-03-31 | 2019-03-31 | Argyll and Bute-North Argyll | 273058 | 0 | 2137845 | 13785345.59 | 11311547.68 | 4309739.19 | 2351399.2 | -1853997.66 | 32041879 | 25063.31 | 10025.324 | 13916.8565 | 32340000.31 | 3891.5325 | 0 | 0 | 3891.5325 | 32343891.8425 | 8066542.18 |  |  |  |  | 133847 | Y | DW23 | 40% | CM_WSNI | 60% | [18 empty] | 1 | [46 empty] | 0
501633 | Turbidity Scanning Compliance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2027-10-07 | 2028-12-13 | 2029-04-17 | 2030-03-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529999.98 | 0 | 0 | 529999.98 | 0 | 0 | 0 | 0 | 529999.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
46181 | Turnberry SPS Refurb - SPS001936 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-21 | 2012-02-20 | 2012-04-24 | 2013-03-15 |  | South Ayrshire | 744283.11 | 0 | -187.14 | 0 | 0 | 0 | 0 | 0 | -187.14 | 0 | 0 | 0 | 744095.97 | 0 | 0 | 0 | 0 | 744095.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502409 | Turnberry SPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-07-25 | 2018-12-20 | 2019-03-08 | 2019-08-13 |  | South Ayrshire | 0 | 0 | 0 | 4083.9 | 61710.57 | 282400.53 | 226898 | 2334.67 | 577427.67 | 0 | 0 | 0 | 577427.67 | 0 | 0 | 0 | 0 | 577427.67 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500889 | Turret - Balmoe - Carron Valley RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-11-21 | 2018-09-26 | 2018-11-29 | 2019-09-30 | 2020-07-31 | Falkirk | 0 | 0 | 7916.89 | 7696.89 | 11925.39 | 36955.5 | 66415.56 | 4241.77 | 135152 | 2000 | 2000 | 2776.3405 | 137152 | 776.3405 | 0 | 0 | 776.3405 | 137928.3405 | 403640.09 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 38.72 | [43 empty] | 0
500888 | Turret A RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-10-06 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Stirling | 0 | 0 | 2431.21 | 1345.28 | 1427.16 | -1427.16 | 0 | 0 | 3776.49 | 0 | 0 | 0 | 3776.49 | 0 | 0 | 0 | 0 | 3776.49 | 69065.41 | [5 empty] | N | DW5FS | 100%
402737 | Turret Cathodic Protection | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-07-23 | 2020-03-25 | 2020-04-02 | 2020-05-20 |  | Stirling | 23500 | 0 | 69914.83 | 10224.17 | 93286 | 103890.2 | -58644 | -2142.79 | 216528.41 | 0 | 0 | 0 | 240028.41 | 0 | 0 | 0 | 0 | 240028.41 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503525 | Turret Lower Powerhouse HV Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2019-04-08 | 2022-01-17 | 2022-03-03 | 2022-12-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 110659.9 | 113804.1 | 224464 | 1687081.51 | 0 | 0 | 1911545.51 | 0 | 0 | 0 | 0 | 1911545.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505933 | Turret No auto shutdown on low Chlorine | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-03 | 2020-08-20 | 2021-09-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 119022.58 | [5 empty] | N | WSNI | 100%
511702 | Turret WTW - SCADA & PLC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-12-14 | 2023-06-22 | 2023-09-20 | 2024-08-27 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000.1 | 0 | 0 | 2000000.1 | 0 | 0 | 0 | 0 | 2000000.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502586 | Turret WTW Legacy Sludge Sludge Removal & Lagoon Modifications | IR18 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS0 | 2017-12-29 | 2021-12-06 | 2022-04-08 | 2023-11-23 | 2024-02-23 | Perth and Kinross | 0 | 0 | 0 | 35216.4 | 42964.42 | 169993.29 | 103052.6 | 67958.29 | 419185 | 4130509.52 | 0 | 0 | 4549694.52 | 0 | 1139301.2713 | 0 | 1139301.2713 | 5688995.7913 | 1024271.42 | [5 empty] | N | LA01 | 100%
500213 | Turriff - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-03-30 | 2016-05-30 | 2017-03-31 | 2018-06-30 | Aberdeenshire | 0 | 0 | 15457 | 15932.34 | 12093.36 | 1400 | -9319.52 | 0 | 35563.18 | 0 | 0 | 0 | 35563.18 | 0 | 0 | 0 | 0 | 35563.18 | 127087.8 | [5 empty] | Y | DW5FS | 100% | [19 empty] | 1 | [47 empty] | 0
506515 | Turriff Brackans DSR Bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-08-09 | 2022-05-23 | 2022-08-30 | 2023-12-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10620.65 | 10620.65 | 889379.35 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500890 | Turriff RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-10-13 | 2018-09-26 | 2018-11-30 | 2019-06-27 | 2020-02-28 | Aberdeenshire | 0 | 0 | 26600 | 18676.6 | 37000 | 112827.28 | 81449.83 | 5463.29 | 282017 | 0 | 0 | 0 | 282017 | 0 | 0 | 0 | 0 | 282017 | 1297898.84 | [5 empty] | N | DW5FS | 100%
501195 | Turriff TWP - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-05-06 | 2027-05-06 | 2027-05-06 | 2027-05-06 |  | Aberdeenshire | 0 | 0 | 12679.79 | 1278.36 | 641.93 | 0 | 0 | 0 | 14600.08 | 0 | 0 | 0 | 14600.08 | 0 | 0 | 0 | 0 | 14600.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503537 | Turriff WTW - Ceramac Pilot Plant - Design Installation and Operation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2019-03-19 | 2021-04-07 | 2021-04-07 | 2021-04-08 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 7001.41 | 707804.45 | 5194.14 | 720000 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 0 | 720000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501002 | Turriff WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2027-04-01 | 2029-02-14 | 2029-04-19 | 2032-04-29 |  | Aberdeenshire | 0 | 0 | 107967.82 | 12302.74 | 106357.55 | 877424.94 | -490987.17 | 7135.59 | 620201.48 | -7419.41 | 0 | 0 | 612782.07 | 0 | 0 | 0 | 0 | 612782.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503072 | Turriff WTW - Essential CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-02-11 | 2021-01-27 | 2021-01-27 | 2022-09-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 58430.17 | 6012.61 | 678860.08 | 4418388.66 | 5161691.52 | 5687778.48 | 0 | 0 | 10849470 | 0 | 0 | 1150530 | 1150530 | 12000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503054 | Turriff WTW - installation of UV treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2018-01-24 | 2018-01-24 | 2018-02-12 | 2018-12-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 1454419.03 | 905667.32 | 255.74 | 600.91 | 2360943 | 643.17 | 0 | 0 | 2361586.17 | 0 | 0 | 0 | 0 | 2361586.17 | 119022.58 |  |  |  |  | 39196 | N | CM_WSNI | 100%
502781 | Turriff WTW - RGF Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2017-08-29 | 2017-08-29 | 2017-09-25 | 2020-11-23 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 215793.35 | 101408.15 | 1782960.57 | 430137.93 | 2530300 | 4807.3 | 0 | 0 | 2535107.3 | 0 | 0 | 0 | 0 | 2535107.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501027 | Turriff WTW QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWMD | DWQ Reliability | MS6 | 2016-03-25 | 2017-10-27 | 2018-02-28 | 2018-10-31 | 2020-03-31 | Aberdeenshire | 0 | 0 | 18483 | 24190.54 | 166279.82 | 57089.98 | -8397.58 | 2198.24 | 259844 | 1082 | 1082 | 1502.0002 | 260926 | 420.0002 | 0 | 0 | 420.0002 | 261346.0002 | 471905.77 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
403307 | Turriff WTW RGFs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-29 | 2015-08-10 | 2015-07-29 | 2015-07-29 |  | Aberdeenshire | 665889.26 | 0 | -4538.14 | 0 | 0 | 0 | 0 | 0 | -4538.14 | 0 | 0 | 0 | 661351.12 | 0 | 0 | 0 | 0 | 661351.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
45615 | Turriff WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-07-08 | 2013-10-03 | 2014-03-21 | Aberdeenshire | 638026.03 | 0 | -2852.39 | 23.73 | 0 | 0 | 0 | 0 | -2828.66 | 0 | 0 | 0 | 635197.37 | 0 | 0 | 0 | 0 | 635197.37 | 28761.13 | [5 empty] | N | DW1A | 100%
503277 | Turriff WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-04-27 | 2024-02-09 | 2024-05-15 | 2025-04-25 |  | Moray | 0 | 0 | 0 | 0 | 0 | 82034.53 | 15615.27 | 367043.8 | 464693.6 | 1887758.27 | 0 | 0 | 2352451.87 | 0 | 0 | 0 | 0 | 2352451.87 | 122419.09 | [5 empty] | N | SG1 | 100%
503565 | Turriff WWTW- Flocor tower replacement | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS0 | 2020-01-24 | 2021-09-07 | 2021-11-15 | 2023-05-26 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 150540.91 | 51249.09 | 201790 | 3460273.93 | 0 | 0 | 3662063.93 | 0 | 0 | 0 | 0 | 3662063.93 | 122419.09 | [5 empty] | N | SG1 | 100%
401377 | Turriff WwTW Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-02-07 | 2014-10-31 | 2015-07-06 | 2015-07-06 |  | Aberdeenshire | 1239884.83 | 0 | -5432.72 | 0 | 0 | 0 | 0 | 0 | -5432.72 | 0 | 0 | 0 | 1234452.11 | 0 | 0 | 0 | 0 | 1234452.11 | 90601.29 | [5 empty] | N | SG1 | 30% | CM_WWNI | 70%
45376 | Tweedsmuir WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-28 | 2012-02-20 | 2015-02-13 | 2015-09-18 | Scottish Borders | 2959028.28 | 0 | 240268.92 | 31454.31 | -4235.02 | -1642.92 | 0 | 0 | 265845.29 | 0 | 0 | 0 | 3224873.57 | 0 | 0 | 0 | 0 | 3224873.57 | 28761.13 | [5 empty] | N | DW23 | 100%
402206 | TWP 0000488 - Shenval Water Pumping Station Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-08-19 | 2011-10-10 | 2012-01-23 | 2012-09-06 |  | Perth and Kinross | 151129 | 0 | 472.01 | 0 | 0 | 0 | 0 | 0 | 472.01 | 0 | 0 | 0 | 151601.01 | 0 | 0 | 0 | 0 | 151601.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402385 | TWP000444 - Mannofield MPS2 - Feasibility Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-09-27 | 2012-12-07 | 2013-02-18 | 2013-08-30 |  | Aberdeen City | 388655.95 | 0 | 122929.4 | 0 | 0 | 0 | 0 | 0 | 122929.4 | 0 | 0 | 0 | 511585.35 | 0 | 0 | 0 | 0 | 511585.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501950 | TWPs - West Area Cluster 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-03-31 | 2019-03-01 | 2019-03-01 | 2022-01-26 |  | All West Unitary Authorities | 0 | 0 | 1942 | 139658.24 | 420963.08 | 329702.78 | 707751.9 | 759949 | 2359967 | 585848 | 0 | 0 | 2945815 | 0 | 0 | 0 | 0 | 2945815 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505405 | TWS Asset Repair Mission m2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2020-03-05 | 2020-04-07 | 2020-11-19 | 2021-09-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1127.08 | 2931717.93 | 2932845 | 267154.81 | 0 | 0 | 3199999.81 | 0 | 0 | 0 | 0 | 3199999.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507338 | TWS Complex Bypasses Batch 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-10-24 | 2024-09-09 | 2025-02-17 | 2026-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2260.51 | 2260.51 | -2260.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
508960 | TWS Complex Bypasses Batch 10 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-10-24 | 2024-09-09 | 2025-02-17 | 2026-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803139.46 | 0 | 0 | 803139.46 | 0 | 0 | 0 | 0 | 803139.46 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507339 | TWS Complex Bypasses Batch 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-10-24 | 2024-09-09 | 2025-02-17 | 2026-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2878 | 2878 | 149122.04 | 0 | 0 | 152000.04 | 0 | 0 | 0 | 0 | 152000.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507340 | TWS Complex Bypasses Batch 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-10-24 | 2024-09-09 | 2025-02-17 | 2026-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2080.41 | 2080.41 | -1243.2 | 0 | 0 | 837.21 | 0 | 0 | 0 | 0 | 837.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507342 | TWS Complex Bypasses Batch 4 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-10-24 | 2024-09-09 | 2025-02-17 | 2026-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2203.59 | 2203.59 | 708633.62 | 0 | 0 | 710837.21 | 0 | 0 | 0 | 0 | 710837.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508734 | TWS Complex Bypasses Batch 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-10-24 | 2024-09-09 | 2025-02-17 | 2026-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -379.4 | 0 | 0 | -379.4 | 0 | 0 | 0 | 0 | -379.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508738 | TWS Complex Bypasses Batch 6 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-10-24 | 2024-09-09 | 2025-02-17 | 2026-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502095.62 | 0 | 0 | 502095.62 | 0 | 0 | 0 | 0 | 502095.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508741 | TWS Complex Bypasses Batch 7 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-11-24 | 2024-10-10 | 2025-03-20 | 2026-10-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384944.92 | 0 | 0 | 384944.92 | 0 | 0 | 0 | 0 | 384944.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508801 | TWS Complex Bypasses Batch 8 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-10-24 | 2024-09-09 | 2025-02-17 | 2026-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630265.58 | 0 | 0 | 630265.58 | 0 | 0 | 0 | 0 | 630265.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508959 | TWS Complex Bypasses Batch 9 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-11-24 | 2024-10-10 | 2025-03-20 | 2026-10-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551994.59 | 0 | 0 | 551994.59 | 0 | 0 | 0 | 0 | 551994.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510127 | TWS Emerging Risks Sample Taps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 |  | 2020-12-16 | 2020-12-16 | 2021-09-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83030 | 83030 | 143274.68 | 0 | 0 | 226304.68 | 0 | 0 | 0 | 0 | 226304.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507103 | TWS Mission Secondment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2020-06-19 | 2020-10-27 | 2020-10-27 | 2021-07-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24678 | 24678 | 15321.79 | 0 | 0 | 39999.79 | 0 | 0 | 0 | 0 | 39999.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512016 | TWS SPMA Compliant 2 Step Bypasses East Yr1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512017 | TWS SPMA Compliant 2 Step Bypasses North Yr1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512018 | TWS SPMA Compliant 2 Step Bypasses South Yr1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512019 | TWS SPMA Compliant 2 Step Bypasses West Yr1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-03-03 | 2023-09-11 | 2023-12-08 | 2024-11-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512012 | TWS SPMA Compliant Simple Repairs East | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-16 | 2021-04-26 | 2021-05-03 | 2022-04-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7420500.02 | 0 | 0 | 7420500.02 | 0 | 0 | 0 | 0 | 7420500.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512013 | TWS SPMA Compliant Simple Repairs North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-16 | 2021-04-26 | 2021-05-03 | 2022-04-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512014 | TWS SPMA Compliant Simple Repairs South | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-16 | 2021-04-26 | 2021-05-03 | 2022-04-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512015 | TWS SPMA Compliant Simple Repairs West | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-16 | 2021-04-26 | 2021-05-03 | 2022-04-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511710 | TWSM Franklaw Civils Amey 211 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-04-02 | 2021-07-19 | 2022-03-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311.79 | 311.79 | 165000 | 0 | 0 | 165311.79 | 0 | 0 | 0 | 0 | 165311.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511711 | TWSM Franklaw Civils Amey 212 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-04-02 | 2021-07-19 | 2022-03-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 165000 | 0 | 0 | 165130.84 | 0 | 0 | 0 | 0 | 165130.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511712 | TWSM Franklaw Civils Amey 213 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-04-02 | 2021-08-16 | 2022-03-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.96 | 186.96 | 165000 | 0 | 0 | 165186.96 | 0 | 0 | 0 | 0 | 165186.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511878 | TWSM Franklaw Civils GLL 211 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-07-05 | 2021-07-05 | 2022-03-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 0 | 0 | 165000 | 0 | 0 | 0 | 0 | 165000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511744 | TWSM Franklaw UV Connection Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-24 | 2021-05-03 | 2021-08-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511014 | TWSM Simple Repair at Ullapool DSR | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2021-02-09 | 2021-03-02 | 2021-06-10 | 2021-09-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20299.83 | 20299.83 | 281598.17 | 0 | 0 | 301898 | 0 | 0 | 0 | 0 | 301898 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500853 | Tyndrum RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS7 | 2016-04-07 | 2017-03-23 | 2017-05-23 | 2018-11-30 | 2019-08-31 | Stirling | 0 | 0 | 1409.4 | 1982.6 | 9674.87 | 3270.82 | 1317.04 | 0 | 17654.73 | 0 | 0 | 0 | 17654.73 | 0 | 0 | 0 | 0 | 17654.73 | 12415.64 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 1.99 | [43 empty] | 0
500724 | Udny Green WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2020-02-03 | 2022-05-12 | 2022-09-05 | 2024-04-12 |  | Aberdeenshire | 0 | 0 | 27767.26 | 58914.31 | 81297.33 | 10654.69 | 35058.78 | 138073.63 | 351766 | 2630971.57 | 0 | 0 | 2982737.57 | 0 | 0 | 0 | 0 | 2982737.57 | 122419.09 | [5 empty] | N | SG1 | 100%
500725 | Udny Station WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS1 | 2018-03-27 | 2022-04-01 | 2022-09-02 | 2023-12-26 |  | Aberdeenshire | 0 | 0 | 28907.67 | 51671.7 | 81673.28 | 11458.99 | 96973.77 | 142726.59 | 413412 | 1638112.29 | 0 | 0 | 2051524.29 | 0 | 0 | 0 | 0 | 2051524.29 | 122419.09 | [5 empty] | N | SG1 | 100%
508220 | UID - MILL PARK WWPS NO480324 EO DUNDEE | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-07-07 | 2025-05-23 | 2025-10-31 | 2027-05-14 | 2027-08-16 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000.17 | 0 | 0 | 500000.17 | 0 | 0 | 0 | 0 | 500000.17 | 0 | [5 empty] | N | SR21_WW | 100%
508289 | UID - 103-105 High Street Stewarton | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-03-06 | 2023-07-11 | 2023-09-11 | 2025-03-24 | 2025-06-24 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 496999.96 | 0 | 0 | 499999.96 | 0 | 0 | 0 | 0 | 499999.96 | 0 | [5 empty] | N | SR21_WW | 100%
509020 | UID - 12 Sarkside SWO Gretna | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-01-04 | 2023-05-11 | 2023-07-12 | 2025-01-22 | 2025-04-24 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 33000 | 467999.97 | 0 | 0 | 500999.97 | 0 | 0 | 0 | 0 | 500999.97 | 0 | [5 empty] | N | SR21_WW | 100%
508279 | UID - 2 Kirkford Kirkford Bridge Stewarton | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-03-06 | 2023-07-11 | 2023-08-14 | 2025-02-24 | 2025-05-27 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34500 | 34500 | 465500.04 | 0 | 0 | 500000.04 | 0 | 0 | 0 | 0 | 500000.04 | 0 | [5 empty] | N | SR21_WW | 100%
508285 | UID - 78 High Street Stewarton | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-03-06 | 2023-07-11 | 2023-09-11 | 2025-03-24 | 2025-06-24 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 495000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WW | 100%
508100 | UID - BLACKNESS WWPS | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-05-08 | 2023-09-12 | 2023-11-13 | 2025-05-26 | 2025-08-26 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 498500 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WW | 100%
509025 | UID - Burnhead_Stapleton Road CSO Annan | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-07-07 | 2023-11-13 | 2024-01-12 | 2025-07-25 | 2025-10-27 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 32000 | 468604.65 | 0 | 0 | 500604.65 | 0 | 0 | 0 | 0 | 500604.65 | 0 | [5 empty] | N | SR21_WW | 100%
509062 | UID - Caerketton Avenue CSO Bilston | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-11-21 | 2023-03-28 | 2023-05-29 | 2024-12-09 | 2025-03-11 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 462500 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WW | 100%
31251 | UID - Cowdenbeath WWPS- Storm Tank | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-06 | 2010-08-23 | 2010-09-06 | 2014-03-21 | 2014-03-24 | Fife | 8791421 | 0 | 4000 | -60245.46 | 0 | 0 | 0 | 0 | -56245.46 | 0 | 0 | 0 | 8735175.54 | 0 | 0 | 0 | 0 | 8735175.54 | 57522.26 |  |  |  |  | 10506 | N | EC01 | 50% | EC10 | 50%
37781 | UID - Cumbernauld uSWO | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-11 | 2011-02-24 | 2011-03-07 | 2013-02-07 | 2013-02-26 | North Lanarkshire | 3551162 | 0 | -3483.02 | 0 | 0 | 0 | 0 | 0 | -3483.02 | 0 | 0 | 0 | 3547678.98 | 0 | 0 | 0 | 0 | 3547678.98 | 57522.26 | [5 empty] | N | EC09 | 50% | EC10 | 50%
508267 | UID - David Dale CSO Stewarton | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-03-08 | 2023-07-13 | 2023-09-13 | 2024-03-13 | 2024-06-13 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 496500.03 | 0 | 0 | 500000.03 | 0 | 0 | 0 | 0 | 500000.03 | 0 | [5 empty] | N | SR21_WW | 100%
507497 | UID - Dunfermline Storm Tanks Assessment | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS2 | 2020-08-05 | 2021-04-01 | 2021-12-15 | 2022-06-15 | 2022-09-15 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 99000.02 | 0 | 0 | 100000.02 | 0 | 0 | 0 | 0 | 100000.02 | 0 | [5 empty] | N | SR21_WW | 100%
31284 | UID - Elderslie-Old Patrick Water No2 CSO 242 Main Road at Elderslie Bridge | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-08-13 | 2009-10-06 | 2009-09-14 | 2010-03-22 | 2010-06-07 | Renfrewshire | 2610022.19 | 0 | 374.85 | 0 | 0 | 0 | 0 | 0 | 374.85 | 0 | 0 | 0 | 2610397.04 | 0 | 0 | 0 | 0 | 2610397.04 | 86283.39 | [5 empty] | N | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
509045 | UID - Gifford STW Inlet CSO Gifford | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-06-30 | 2023-11-06 | 2024-01-05 | 2025-07-18 | 2025-10-20 | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 32000 | 468604.65 | 0 | 0 | 500604.65 | 0 | 0 | 0 | 0 | 500604.65 | 0 | [5 empty] | N | SR21_WW | 100%
509064 | UID - Glebe Road CSO Cramond | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-01-13 | 2023-05-22 | 2023-07-21 | 2024-02-20 | 2024-02-21 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 33000 | 467000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WW | 100%
508590 | UID - Glensburgh SPS CSO Grangemouth Dalderse DOA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-12-12 | 2023-04-18 | 2023-06-19 | 2024-12-30 | 2025-04-01 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 496000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WW | 100%
508112 | UID - Inchcolm Drive CSO North Queensferry | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-09-19 | 2024-01-24 | 2024-03-26 | 2025-10-07 | 2026-01-07 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499999.9 | 0 | 0 | 499999.9 | 0 | 0 | 0 | 0 | 499999.9 | 0 | [5 empty] | N | SR21_WW | 100%
509041 | UID - Kirkhill CSO Penicuik | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-10-27 | 2023-03-31 | 2023-06-01 | 2024-12-12 | 2025-03-14 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38500 | 38500 | 461500 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WW | 100%
31388 | UID - Laighstonehall Road at 193 Chantinghall Road | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-21 | 2010-08-23 | 2010-09-20 | 2011-03-24 | 2011-03-25 | South Lanarkshire | 571183.12 | 0 | 104.21 | 0 | 0 | 0 | 0 | 0 | 104.21 | 0 | 0 | 0 | 571287.33 | 0 | 0 | 0 | 0 | 571287.33 | 86283.39 | [5 empty] | N | EC04 | 33.21% | EC10 | 33.21% | EC01 | 33.58%
300014 | UID - Lamont Drive - Rubie Crescent | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-01-31 | 2011-10-14 | 2011-10-31 | 2012-03-16 | 2012-03-30 | North Ayrshire | 342236 | 0 | -1509.63 | 0 | 0 | 0 | 0 | 0 | -1509.63 | 0 | 0 | 0 | 340726.37 | 0 | 0 | 0 | 0 | 340726.37 | 86283.39 | [5 empty] | N | EC02 | 33% | EC10 | 33% | EC01 | 34%
507747 | UID - Laurence Croft Road Stirling | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-07-07 | 2023-11-13 | 2024-01-12 | 2025-07-25 | 2025-10-27 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499999.98 | 0 | 0 | 499999.98 | 0 | 0 | 0 | 0 | 499999.98 | 0 | [5 empty] | N | SR21_WW | 100%
508110 | UID - Little Carron SPS St Andrews | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-02-10 | 2023-06-19 | 2023-08-18 | 2025-02-28 | 2025-06-02 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499999.82 | 0 | 0 | 499999.82 | 0 | 0 | 0 | 0 | 499999.82 | 0 | [5 empty] | N | SR21_WW | 100%
508080 | UID - Lochloy Road CSO Nairn | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-09-29 | 2023-02-03 | 2023-04-06 | 2024-10-17 | 2025-01-17 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 13500 | 486500 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WW | 100%
506586 | UID - Lord Ancrums Wood Easthouses | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-10-31 | 2023-03-07 | 2023-05-08 | 2024-11-18 | 2025-02-18 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45500 | 45500 | 454999.99 | 0 | 0 | 500499.99 | 0 | 0 | 0 | 0 | 500499.99 | 0 | [5 empty] | N | SR21_WW | 100%
508116 | UID - Main Street CSO Limekilns | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-04-28 | 2023-09-04 | 2023-11-03 | 2025-05-16 | 2025-08-18 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.33 | 1919.33 | 497999.99 | 0 | 0 | 499919.32 | 0 | 0 | 0 | 0 | 499919.32 | 0 | [5 empty] | N | SR21_WW | 100%
508369 | UID - Mallaig WWPS 4 CSO | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-03-31 | 2023-08-07 | 2023-10-06 | 2025-04-18 | 2025-07-21 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 487999.93 | 0 | 0 | 499999.93 | 0 | 0 | 0 | 0 | 499999.93 | 0 | [5 empty] | N | SR21_WW | 100%
31412 | UID - Meikle Earnock Road at Irvine Terrace | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-13 | 2011-03-07 | 2011-07-05 | 2011-11-17 | 2011-12-15 | South Lanarkshire | 665235.75 | 0 | 87.58 | 0 | 0 | 0 | 0 | 0 | 87.58 | 0 | 0 | 0 | 665323.33 | 0 | 0 | 0 | 0 | 665323.33 | 86283.39 | [5 empty] | N | EC04 | 33.02% | EC10 | 33.02% | EC01 | 33.96%
31417 | UID - Millerpark Wellhall Road Bridge | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-13 | 2011-03-07 | 2011-05-20 | 2011-12-15 | 2011-12-15 | South Lanarkshire | 555406 | 0 | -772 | 0 | 0 | 0 | 0 | 0 | -772 | 0 | 0 | 0 | 554634 | 0 | 0 | 0 | 0 | 554634 | 86283.39 | [5 empty] | N | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
31426 | UID - Mote Hill Palace Grounds Road Hamilton | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-13 | 2011-01-25 | 2011-02-21 | 2012-03-22 | 2012-03-23 | South Lanarkshire | 5037430 | 0 | -896.37 | 0 | 0 | 0 | 0 | 0 | -896.37 | 0 | 0 | 0 | 5036533.63 | 0 | 0 | 0 | 0 | 5036533.63 | 86283.39 | [5 empty] | N | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
31429 | UID - Neilsland Road at Burnhouse Road | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-21 | 2010-03-25 | 2010-04-06 | 2011-03-24 | 2011-03-25 | South Lanarkshire | 843318.96 | 0 | 87.59 | 0 | 0 | 0 | 0 | 0 | 87.59 | 0 | 0 | 0 | 843406.55 | 0 | 0 | 0 | 0 | 843406.55 | 86283.39 | [5 empty] | N | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
31439 | UID - Off Path 72 Westwood Crescent | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-21 | 2010-03-25 | 2010-03-05 | 2010-12-15 | 2010-12-21 | South Lanarkshire | 693080.99 | 0 | 104.21 | 0 | 0 | 0 | 0 | 0 | 104.21 | 0 | 0 | 0 | 693185.2 | 0 | 0 | 0 | 0 | 693185.2 | 86283.39 | [5 empty] | N | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
509038 | UID - Picnic Site SPS CSO Fochabers | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-02-10 | 2023-06-19 | 2023-08-18 | 2025-02-28 | 2025-06-02 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31395.35 | 31395.35 | 468604.65 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WW | 100%
508592 | UID - Polmont N & S side of M9 CSO Polmonthill SPS CSO & Kinneil Kerse WWTW Kinneil Kerse DOA | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-10-31 | 2023-03-07 | 2023-05-08 | 2024-11-18 | 2025-02-18 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 23000 | 477000.15 | 0 | 0 | 500000.15 | 0 | 0 | 0 | 0 | 500000.15 | 0 | [5 empty] | N | SR21_WW | 100%
507050 | UID - Preston Crescent and Spittalfield Road Inverkeithing | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-06-05 | 2023-10-10 | 2023-12-11 | 2025-06-23 | 2025-09-23 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 499999.96 | 0 | 0 | 500999.96 | 0 | 0 | 0 | 0 | 500999.96 | 0 | [5 empty] | N | SR21_WW | 100%
508106 | UID - Snab Lane SPS CSO and Furnace Lane CSO | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2022-12-16 | 2023-04-24 | 2023-06-23 | 2025-01-03 | 2025-04-07 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 498500.11 | 0 | 0 | 500000.11 | 0 | 0 | 0 | 0 | 500000.11 | 0 | [5 empty] | N | SR21_WW | 100%
507545 | UID - St Bridgets Brae CSO Dalgety Bay | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-03-31 | 2023-08-07 | 2023-10-06 | 2025-04-18 | 2025-07-21 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35500 | 35500 | 464500 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | [5 empty] | N | SR21_WW | 100%
508292 | UID - Torryburn SPS CSO Valleyfield | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-08-08 | 2023-12-13 | 2024-02-13 | 2025-08-26 | 2025-11-26 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000.08 | 0 | 0 | 500000.08 | 0 | 0 | 0 | 0 | 500000.08 | 0 | [5 empty] | N | SR21_WW | 100%
507500 | UID - Valleyfield CSO Assessment | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | MS2 | 2020-08-05 | 2021-04-01 | 2022-01-12 | 2022-09-15 | 2022-12-16 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | [5 empty] | N | SR21_WW | 100%
508148 | UID - Valleyfield STW Inlet CSO | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-07-28 | 2023-12-04 | 2024-02-02 | 2025-08-15 | 2025-11-17 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000.14 | 0 | 0 | 500000.14 | 0 | 0 | 0 | 0 | 500000.14 | 0 | [5 empty] | N | SR21_WW | 100%
507738 | UID - Woodside Road Stirling | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | SWD | SR21 Early Start | GW0 | 2023-07-07 | 2023-11-13 | 2024-01-12 | 2025-07-25 | 2025-10-27 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499999.99 | 0 | 0 | 499999.99 | 0 | 0 | 0 | 0 | 499999.99 | 0 | [5 empty] | N | SR21_WW | 100%
403807 | UID Output Support - Sewer Cleaning | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2014-06-23 | 2015-02-12 | 2015-02-19 | 2018-02-23 | 2018-02-26 | Glasgow City | 262022 | 0 | 1248840 | 129327.93 | 171199.43 | 5743.12 | 256.88 | -256.88 | 1555110.48 | 0 | 0 | 0 | 1817132.48 | 0 | 0 | 0 | 0 | 1817132.48 | 0 | [5 empty] | N | EC10B | 100%
31434 | UID WP6.1 Kilmarnock Gravity Transfer Scheme | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-02-20 | 2010-01-14 | 2011-11-08 | 2013-10-23 | 2013-12-23 | East Ayrshire | 25070886.8 | 0 | 153702.21 | 56789.08 | 1241.24 | 2293.2 | 24.44 | 0 | 214050.16 | 0 | 0 | 0 | 25284936.96 | 0 | 0 | 0 | 0 | 25284936.96 | 86283.39 | [5 empty] | N | EC01A | 33.33% | EC02A | 33.33% | EC10A | 33.33%
36868 | UID WP6.2 Gatehead Tank to Meadowhead Inlet Works Transfer Scheme | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-02-20 | 2010-01-14 | 2010-12-08 | 2012-03-16 | 2012-03-30 | East Ayrshire | 15410452.69 | 0 | 54051.19 | 30946.28 | 11109.28 | 764.4 | 10423.68 | 0 | 107294.83 | 0 | 0 | 0 | 15517747.52 | 0 | 0 | 0 | 0 | 15517747.52 | 86283.39 | [5 empty] | N | EC02 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
36860 | UID WP6.3 Irvine Transfer Scheme | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-02-21 | 2010-01-14 | 2010-12-08 | 2013-01-31 | 2013-02-26 | North Ayrshire | 24666791 | 0 | 23582.35 | 95.13 | 7.41 | 0 | 0 | 0 | 23684.89 | 0 | 0 | 0 | 24690475.89 | 0 | 0 | 0 | 0 | 24690475.89 | 86283.39 |  |  |  |  | 18747 | N | EC02 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
403468 | UIDs Legacy Issues | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-07-12 | 2014-06-30 | 2014-08-01 | 2015-12-07 | 2016-01-08 | All West Unitary Authorities | 215071.05 | 0 | 99547.95 | 0 | -3911.63 | 0 | 0 | 0 | 95636.32 | 0 | 0 | 0 | 310707.37 | 0 | 0 | 0 | 0 | 310707.37 | 0 | [5 empty] | N | EC01D | 100%
509638 | UIG WTW - RWI | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2022-01-28 | 2023-12-15 | 2024-05-24 | 2025-12-05 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16284.57 | 16284.57 | 333715.43 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000 | 311236.79 | [5 empty] | N | WSI | 100%
402611 | UITS Recurring Bursts Remedial Actions | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-04-24 | 2012-04-24 | 2012-05-29 | 2015-11-20 |  | Scottish Water Wide | 3677107 | 0 | 180946 | 123187.85 | 2756.28 | 0 | 0 | 0 | 306890.13 | 0 | 0 | 0 | 3983997.13 | 0 | 0 | 0 | 0 | 3983997.13 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505518 | Ullapool DSR - H&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2020-09-24 | 2020-09-24 | 2020-10-14 | 2020-10-14 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1133.42 | 2415.79 | 3549.21 | 0 | 0 | 0 | 3549.21 | 0 | 0 | 0 | 0 | 3549.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500907 | Ullapool WOA SRs (Improving WQ Reliability in Network) | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS6 | 2016-01-12 | 2016-03-30 | 2016-03-30 | 2021-07-05 | 2021-10-04 | Highland | 0 | 0 | 0.35 | 0 | 8.84 | 407.07 | 220 | 0 | 636.26 | 0 | 0 | 0 | 636.26 | 0 | 0 | 0 | 0 | 636.26 | 466277.79 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
50030 | Unallocated Programme Overheads | Q&S3B | Completion | OMG180 |  |  | General |  | SWD | OMG180 | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12600000 | 12600000 | 0 | 0 | 0 | 12600000 | 0 | 0 | 0 | 0 | 12600000 | 1036903.76 | [5 empty] | N | SR15_ENV_SGR | 0.001226% | SR15_DWA_PRE | 0.008198% | SR15_CEX_STU | 0.009052% | WG3 | 0.01321% | SR15_DWA_LEAK | 0.01726% | SR15_ENV_HABD | 0.02172% | SR15_DWA_EFA | 0.02258% | SR15_SEW_SWO | 0.02636% | SR15_CCH_CC | 0.03815% | SR15_DWQ_FUT | 0.04738%
500966 | Underwood (Cumnock) STC CHP replacement | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-11-16 | 2016-03-30 | 2016-09-26 | 2017-03-30 |  | East Ayrshire | 0 | 0 | 1087.98 | 218352.27 | 2438.36 | -1209.04 | 0 | 0 | 220669.57 | 0 | 0 | 0 | 220669.57 | 0 | 0 | 0 | 0 | 220669.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
31596 | Underwood (Cumnock) STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2010-12-23 | 2011-02-14 | 2014-03-27 | 2014-05-12 | East Ayrshire | 5374135.85 | 0 | 295403.3 | 680174.44 | 372.47 | 0 | 0 | 0 | 975950.21 | 0 | 0 | 0 | 6350086.06 | 0 | 0 | 0 | 0 | 6350086.06 | 176884.68 |  |  |  |  | 32779 | N | EC04A | 3.025% | EC10A | 9.188% | CM_WWNI | 32.83% | EC01A | 54.95%
500186 | Underwood Cumnock DOA (DOA000144) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-04-29 | 2016-06-29 | 2018-02-27 | 2018-06-25 | East Ayrshire | 0 | 0 | 2000 | 21798.7 | 14298.31 | -865.45 | 0 | 0 | 37231.56 | 0 | 0 | 0 | 37231.56 | 0 | 0 | 0 | 0 | 37231.56 | 4617.88 | [5 empty] | N | EC01G | 46.22% | CS16D | 53.78%
503420 | Unst WTW - Interim THM and Cryptosporidium measures | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-10-31 | 2020-03-31 | 2020-09-14 | 2021-05-21 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 16736.04 | 41074.19 | 724428.76 | 782238.99 | 83243.83 | 0 | 0 | 865482.82 | 0 | 0 | 0 | 0 | 865482.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502568 | Unst WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2021-04-01 | 2021-04-01 | 2020-10-08 | 2020-09-18 |  | Shetland Islands | 0 | 0 | 0 | 20930.23 | 0 | -20695.43 | 0 | 289.19 | 523.99 | 0 | 0 | 0 | 523.99 | 0 | 0 | 0 | 0 | 523.99 | 122419.09 | [5 empty] | N | SG1 | 100%
46856 | Unst WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-29 | 2011-09-15 | 2013-02-08 | 2013-02-21 | Shetland Islands | 3933525.59 | 0 | -38444.27 | 166.09 | 0 | 0 | 0 | 0 | -38278.18 | 0 | 0 | 0 | 3895247.41 | 0 | 0 | 0 | 0 | 3895247.41 | 28761.13 | [5 empty] | N | DW23 | 100%
500672 | Update the National Sludge Strategy | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-09-07 | 2016-03-21 | 2016-03-30 | 2018-06-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 120000 | 608983.33 | 742453.71 | 200115.96 | 1679.69 | 0 | 1673232.69 | 0 | 0 | 0 | 1673232.69 | 0 | 0 | 0 | 0 | 1673232.69 | 0 | [5 empty] | Y | EC06C | 100% | [40 empty] | 1 | [26 empty] | 0
503211 | Upgrade - Investigation and Scope Definition for potential Growth Project post 2021 at Silver Sand | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-02-04 | 2019-02-04 | Fife | 0 | 0 | 0 | 0 | 0 | 25841.58 | 0 | 0 | 25841.58 | 0 | 0 | 0 | 25841.58 | 0 | 0 | 0 | 0 | 25841.58 | 122419.09 | [5 empty] | N | SG1 | 100%
31598 | Uplawmoor STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-04-29 | 2011-06-10 | 2011-09-30 | 2012-03-26 | 2012-04-26 | East Renfrewshire | 268383.52 | 0 | 816.3 | 0 | 0 | 0 | 0 | 0 | 816.3 | 0 | 0 | 0 | 269199.82 | 0 | 0 | 0 | 0 | 269199.82 | 270542.64 | [5 empty] | N | SG1 | 3.019% | EC10A | 8.388% | EC04A | 12.58% | CM_WWNI | 76.01%
503304 | Uplawmoor WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2027-04-15 | 2028-10-04 | 2029-02-06 | 2029-10-01 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 28480.15 | 6687.96 | -0.11 | 35168 | 0 | 0 | 0 | 35168 | 0 | 0 | 0 | 0 | 35168 | 122419.09 | [5 empty] | N | SG1 | 100%
501514 | UPLAWMOOR WWTW 1972 NS431552 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS6 | 2016-08-19 | 2018-12-20 | 2019-03-15 | 2020-09-25 |  | East Renfrewshire | 0 | 0 | 0 | 69116.28 | 173603.27 | 428299.17 | 820356.37 | 85031.91 | 1576407 | 15081 | 0 | 0 | 1591488 | 0 | 0 | 0 | 0 | 1591488 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500109 | Upper Clyde Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS5 | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-08-31 | 2021-01-28 | Scottish Water Wide | 0 | 0 | 14176 | 83616.52 | 235096.48 | 504047 | 728380.78 | 221173.23 | 1786490 | 13509.93 | 13509.93 | 18754.0828 | 1799999.93 | 5244.1528 | 0 | 0 | 5244.1528 | 1805244.0828 | 694779.36 | [5 empty] | N | EC01G | 0.1114% | CS16D | 9.192% | EC10H | 45.35% | EC10E | 45.35%
509769 | Upper Drumbuie DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-06-01 | 2024-02-28 | 2024-06-03 | 2025-05-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163.16 | 1163.16 | 414607.26 | 0 | 0 | 415770.42 | 0 | 0 | 0 | 0 | 415770.42 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510108 | Upper Glendevon Pressure Relief Pipes and access covers | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-12-17 | 2021-07-22 | 2022-04-04 |  | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2567.35 | 2567.35 | 17445.6 | 0 | 0 | 20012.95 | 0 | 0 | 0 | 0 | 20012.95 | 311236.79 | [5 empty] | N | CM_WSI | 100%
400506 | Upper Muir Street SPS Refurb - SPS000452 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-04-28 | 2011-06-15 | 2011-07-25 | 2012-01-16 |  | South Lanarkshire | 137308.01 | 0 | 0 | 0 | 124.77 | 0 | 0 | 0 | 124.77 | 0 | 0 | 0 | 137432.78 | 0 | 0 | 0 | 0 | 137432.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508218 | Upper Torwoodhill Road Rhu - pressure improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-12-15 | 2021-03-10 | 2021-06-08 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2246.06 | 0 | 0 | 5000.06 | 0 | 0 | 0 | 0 | 5000.06 | 311236.79 | [5 empty] | N | WSI | 100%
511110 | URGENT - ST Nicholas SPS Rising Main | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 |  | 2021-02-09 | 2021-03-05 | 2021-09-17 |  | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100735.5 | 100735.5 | -35179.9 | 0 | 0 | 65555.6 | 0 | 0 | 0 | 0 | 65555.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502419 | Uryside Drainage Mitigation Works Design & Build Proposal | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS3 | 2017-03-30 | 2017-03-30 | 2018-06-01 | 2021-07-30 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 5578.53 | -3090 | 0 | -2488.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | SG1 | 100%
402731 | VACANT - GAP SITE METERING PHASE 2 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-06-13 | 2012-06-13 | 2012-07-02 | 2015-10-26 |  | Scottish Water Wide | 5168000 | 0 | 29924.22 | 0 | 0 | 0 | 0 | 0 | 29924.22 | 0 | 0 | 0 | 5197924.22 | 0 | 0 | 0 | 0 | 5197924.22 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500727 | Validation of External Flooding due to Overloading Sewers (EFOS) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS3 | 2016-01-08 | 2016-03-21 | 2016-03-22 | 2021-04-01 | 2021-04-02 | Scottish Water Wide | 0 | 0 | 213282.25 | 99529.75 | -85812 | 43479.38 | 74520.62 | 0 | 345000 | 5000 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000 | 106252.93 | [5 empty] | N | FL_DD | 100%
500187 | Valleyfield DOA (DOA000204) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-12-21 | 2016-02-15 | 2018-04-30 | 2018-07-31 | Fife | 0 | 0 | 85850 | 101081.21 | 33947 | 35631.81 | 0 | 0 | 256510.02 | 0 | 0 | 0 | 256510.02 | 0 | 0 | 0 | 0 | 256510.02 | 72047.27 | [5 empty] | Y | CS11 | 45.89% | CS16D | 54.11% | [37 empty] | 1 | [27 empty] | 0
401339 | Various Low Pressure Enhancement Investigations | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-10-31 | 2012-11-29 | 2015-10-15 | 2015-10-15 | Scottish Water Wide | 119774 | 0 | -9759.31 | 0 | 0 | 0 | 0 | 0 | -9759.31 | 0 | 0 | 0 | 110014.69 | 0 | 0 | 0 | 0 | 110014.69 | 0 | [5 empty] | N | CS1 | 100%
3495 | VARIOUS WWTWS - SUPPLY AND INSTALLATION OF FLOW MONITORS | Q&S2 | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2003-05-19 | 2004-02-13 | 2004-05-24 | 2007-12-21 | 2011-03-15 | Scottish Water Wide | 2367792.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2367792.7 | 0 | 0 | 0 | 0 | 2367792.7 | 0 | [6 empty] | EC1/2 | 50% | WQ1/1 | 50%
500096 | Varying Treatment Studies | Q&S4 | Climate Change | Climate Change |  |  | Wastewater | SEPA | SWD | Climate Change | MS7 | 2015-03-31 | 2017-09-25 | 2017-10-25 | 2018-03-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 163.55 | 0 | 66297.48 | 5066.53 | 0 | 0 | 71527.56 | 0 | 0 | 0 | 71527.56 | 0 | 0 | 0 | 0 | 71527.56 | 34072.29 | [5 empty] | Y | CC3S | 100% | [62 empty] | 2 |  |  |  |  | 0
402846 | Vere Terrace Kirkmuirhill Blackwood | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-08-15 | 2014-09-04 | 2014-10-20 | 2015-02-11 | 2015-02-11 | South Lanarkshire | 366946 | 366946 | 87276 | -3771.83 | 0 | 0 | 0 | 0 | 83504.17 | 0 | 0 | 0 | 450450.17 | 0 | 0 | 0 | 0 | 450450.17 | 180449.74 | [5 empty] | N | FL_DD | 100%
500678 | Victoria Parade & Milverton Dunoon | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2022-01-06 | 2022-05-16 | 2022-06-27 | 2023-05-31 | 2023-08-29 | Argyll and Bute-Cowal & Bute | 0 | 0 | 23500 | 1339.12 | 4460.88 | 16700 | 104820.01 | 32960.99 | 183781 | 439675.87 | 0 | 0 | 623456.87 | 0 | 0 | 0 | 0 | 623456.87 | 180449.74 | [5 empty] | N | FL_DD | 100%
500769 | Victoria St Craigellachie Sewer Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-27 | 2016-07-20 | 2016-10-24 | 2017-08-24 |  | Moray | 0 | 0 | 30000 | 148446 | 74979 | 258.33 | -843.82 | 0 | 252839.51 | 0 | 0 | 0 | 252839.51 | 0 | 0 | 0 | 0 | 252839.51 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502633 | Victory Avenue sewer replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-03-15 | 2018-01-29 | 2018-02-13 | 2018-09-25 |  | Dumfries and Galloway | 0 | 0 | 0 | 2355.14 | 48069.86 | 299033.09 | 20158.39 | 419.53 | 370036 | 484.55 | 0 | 0 | 370520.55 | 0 | 0 | 0 | 0 | 370520.55 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403360 | Viewpark Drive Rutherglen Internal Flooding | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-03-04 | 2015-10-15 | 2015-10-15 | 2015-10-15 | 2015-11-02 | South Lanarkshire | 248868 | 248868 | -248489.1 | 207.4 | 116.69 | 0 | 0 | 0 | -248165.01 | 0 | 0 | 0 | 702.99 | 0 | 0 | 0 | 0 | 702.99 | 180449.74 | [5 empty] | N | FL_DD | 100%
404112 | Vodafone to EE SIM Replacement | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-04 | 2015-03-31 | 2015-03-31 | 2016-03-03 |  | Scottish Water Wide | 1174445 | 0 | 271.67 | 0 | 0 | 0 | 0 | 0 | 271.67 | 0 | 0 | 0 | 1174716.67 | 0 | 0 | 0 | 0 | 1174716.67 | 306661.32 | [5 empty] | N | CM_M&G | 100%
501646 | Voice Networks Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-08-29 | 2017-09-27 | 2017-09-27 | 2020-05-14 |  | Scottish Water Wide | 0 | 0 | 0 | 326336.5 | 1417280.21 | 1716223.4 | 83107.28 | 112246.01 | 3655193.4 | 0 | 0 | 0 | 3655193.4 | 0 | 0 | 0 | 0 | 3655193.4 | 613322.63 | [5 empty] | N | CM_M&G | 100%
504591 | W TWS & WTW sample tap investigations & resolution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2020-02-07 | 2021-11-22 | 2022-04-29 | 2023-11-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1432.61 | 9580.39 | 11013 | 323847.12 | 0 | 0 | 334860.12 | 0 | 0 | 0 | 0 | 334860.12 | 238045.17 | [5 empty] | N | CM_WSNI | 100%
502207 | W101 - Oak Mall Hamilton Way Greenock | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2017-03-31 | 2017-09-26 | 2018-01-08 | 2018-11-30 | 2018-11-30 | Inverclyde | 0 | 0 | 0 | 386909.09 | 1405261.71 | 1102047.2 | 0 | -32042.79 | 2862175.21 | 0 | 0 | 0 | 2862175.21 | 0 | 0 | 0 | 0 | 2862175.21 | 175086.76 | [5 empty] | N | FL_DD | 100%
503074 | W101 - Oak Mall Hamilton Way Greenock (1B) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS1 | 2019-05-20 | 2021-05-03 | 2021-07-14 | 2022-02-02 | 2022-05-10 | Inverclyde | 0 | 0 | 0 | 0 | 20930.23 | 25069.77 | 181440 | 84486 | 311926 | 835127.95 | 0 | 0 | 1147053.95 | 0 | 0 | 0 | 0 | 1147053.95 | 175086.76 | [5 empty] | N | FL_DD | 100%
500664 | W172 - Annbank Road Mossblown | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS0 | 2019-02-08 | 2022-05-19 | 2022-12-07 | 2023-12-13 | 2023-12-14 | South Ayrshire | 0 | 0 | 30430 | 49600 | 74891.1 | 135923.9 | 45498.13 | 44915.87 | 381259 | 340901.07 | 340901.07 | 473228.7221 | 722160.07 | 132327.6521 | 0 | 0 | 132327.6521 | 854487.7221 | 1351407.8 | [5 empty] | N | FL_NAMED | 100%
500301 | W20 - 7 Nether Walk Mauchline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-06-11 | 2019-06-11 | 2019-06-11 | 2019-06-07 | 2019-06-07 | East Ayrshire | 0 | 0 | 23813 | 70425.89 | 31649.57 | 26111.54 | -149793.87 | 0 | 2206.13 | 0 | 0 | 0 | 2206.13 | 0 | 0 | 0 | 0 | 2206.13 | 180449.74 | [5 empty] | N | FL_DD | 50% | FL_NAMED | 50%
501543 | W250 - Milngavie Road Bearsden Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-03-30 | 2020-03-30 | 2020-02-14 | 2020-03-30 | 2021-04-01 | East Dunbartonshire | 0 | 0 | 22930 | 25661.23 | 111223.27 | 190518.14 | 84014.82 | 0 | 434347.46 | 0 | 0 | 0 | 434347.46 | 0 | 0 | 0 | 0 | 434347.46 | 180449.74 | [5 empty] | N | FL_DD | 100%
503538 | W335 Viewpark Road Motherwell (SR15) | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2022-01-06 | 2022-05-12 | 2022-07-14 | 2023-05-31 | 2023-08-31 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 55161.12 | 11710.02 | 66871.14 | 2296128.82 | 2296128.82 | 3187417.7082 | 2362999.96 | 891288.8882 | 0 | 0 | 891288.8882 | 3254288.8482 | 1469853.01 | [5 empty] | N | FL_NAMED | 100%
500302 | W462 - Coalburn Road Coalburn | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-10-08 | 2020-03-18 | 2020-03-30 | 2022-06-29 | 2022-06-29 | South Lanarkshire | 0 | 0 | 58000 | 74971.65 | 44021.64 | 92898.71 | 346847 | 428300 | 1045039 | 775061.02 | 823748 | 823748 | 1820100.02 | 0 | 0 | 48686.98 | 48686.98 | 1868787 | 180449.74 |  |  |  |  | 12150 | N | FL_DD | 100%
500017 | W473 - Conon Avenue | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater | SW | WWINF | Flooding Demand Driven | MS3 | 2018-12-07 | 2019-07-15 | 2019-09-23 | 2022-01-10 | 2022-04-08 | East Dunbartonshire | 0 | 0 | 35685.64 | 81314.36 | 100000 | 547559 | 4142952 | 1542750 | 6450261 | 771593 | 192898.1804 | 413346.2082 | 7221854 | 220448.0278 | 0 | 583609.5702 | 804057.598 | 8025911.598 | 1890049.44 |  |  |  |  | 1980 | N | FL_DD | 75% | FL_NAMED | 25%
501020 | W481 - Moncrieff Avenue Lenzie Kirkintilloch Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-05-09 | 2019-05-09 | East Dunbartonshire | 0 | 0 | 21930 | 46086 | 73251.05 | 6870.1 | -148085.95 | 0 | 51.2 | 0 | 0 | 0 | 51.2 | 0 | 0 | 0 | 0 | 51.2 | 180449.74 | [5 empty] | N | FL_DD | 100%
502327 | W571 - Dolphin Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-11-05 | 2022-03-21 | 2022-05-23 | 2023-05-19 | 2023-08-17 | Glasgow City | 0 | 0 | 0 | 44060.47 | 27939.53 | 80004.91 | 58441.51 | 70850.03 | 281296.44 | 2058703.56 | 0 | 0 | 2340000 | 0 | 0 | 0 | 0 | 2340000 | 175086.76 | [5 empty] | N | FL_DD | 100%
502375 | W574 1-21 Clarkston Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS0 | 2019-07-02 | 2021-09-20 | 2022-01-10 | 2022-07-07 | 2022-10-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 57000 | 58000 | 163965 | -6886 | 272079 | 499920.61 | 0 | 0 | 771999.61 | 0 | 0 | 0 | 0 | 771999.61 | 175086.76 | [5 empty] | N | FL_DD | 100%
502907 | W574 Clarkston Road Flooding - Short Term Solution | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | Glasgow City | 0 | 0 | 0 | 0 | 12000 | -756.6 | 0 | 0 | 11243.4 | 0 | 0 | 0 | 11243.4 | 0 | 0 | 0 | 0 | 11243.4 | 175086.76 | [5 empty] | N | FL_DD | 100%
500913 | W6 - Fisher Avenue Kilsyth | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS4 | 2018-11-22 | 2019-08-27 | 2019-09-24 | 2020-10-26 |  | Glasgow City | 0 | 0 | 341602 | 52835.14 | 33478.9 | 124988.96 | 356849.98 | 61031.28 | 970786.26 | 2250 | 0 | 0 | 973036.26 | 0 | 0 | 0 | 0 | 973036.26 | 180449.74 | [5 empty] | N | FL_DD | 100%
502887 | W630 - High Street Mauchline | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-01-14 | 2021-04-01 | East Ayrshire | 0 | 0 | 0 | 0 | 42398.14 | 54601.86 | 16367.02 | 0 | 113367.02 | 0 | 0 | 0 | 113367.02 | 0 | 0 | 0 | 0 | 113367.02 | 175086.76 | [5 empty] | N | FL_DD | 100%
500662 | W646 - Brandon Gardens Prestwick | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS3 | 2020-02-19 | 2020-10-13 | 2020-11-23 | 2021-10-08 | 2021-10-08 | South Ayrshire | 0 | 0 | 23500 | 17530.23 | 28343.4 | 73626.37 | 677844.89 | 1235371.11 | 2056216 | 372865.04 | 372865.04 | 458405.1595 | 2429081.04 | 85540.1195 | 0 | 0 | 85540.1195 | 2514621.1595 | 304107.44 |  |  |  |  | 31700.0003 | N | FL_NAMED | 100%
502689 | W691 - Geilston Park Cardross | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2021-10-15 | 2022-02-21 | 2022-04-25 | 2023-03-10 | 2023-06-12 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 58628.26 | 21598.74 | 32845.09 | 89738.36 | 202810.45 | 777189.55 | 0 | 0 | 980000 | 0 | 0 | 0 | 0 | 980000 | 175086.76 | [5 empty] | N | FL_DD | 100%
501191 | W701 3 Glen Road Shotts | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-13 | 2019-03-13 | 2019-03-13 | 2019-02-25 | 2019-02-25 | North Lanarkshire | 0 | 0 | 23611 | 13419.23 | 32525.91 | 13266.8 | 0.23 | 0 | 82823.17 | 0 | 0 | 0 | 82823.17 | 0 | 0 | 0 | 0 | 82823.17 | 180449.74 | [5 empty] | N | FL_DD | 100%
502410 | W775 - Dumbarton Road Glasgow | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-02-25 | 2019-02-25 | West Dunbartonshire | 0 | 0 | 0 | 12465.12 | 13534.88 | -24650.14 | 1924.47 | 0 | 3274.33 | 0 | 0 | 0 | 3274.33 | 0 | 0 | 0 | 0 | 3274.33 | 175086.76 | [5 empty] | N | FL_DD | 100%
501542 | W92 - Buchlyvie Road Paisley | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2018-12-17 | 2019-08-29 | 2019-10-07 | 2020-08-26 | 2020-09-01 | Renfrewshire | 0 | 0 | 29855 | 48219.66 | 31925.34 | 159371 | 574158 | -66891 | 776638 | 0 | 0 | 0 | 776638 | 0 | 0 | 0 | 0 | 776638 | 355536.5 | [5 empty] | N | FL_DD | 100%
500941 | Walker Street Paisley Survey & Reline Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-09-02 | 2017-10-27 | 2017-12-01 | 2018-03-22 |  | Renfrewshire | 0 | 0 | 6000 | 4544 | 102040.47 | 23631.92 | -0.39 | -3429.75 | 132786.25 | 0 | 0 | 0 | 132786.25 | 0 | 0 | 0 | 0 | 132786.25 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502602 | Wallyford - WIA Network Reinforcements | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS2 | 2019-09-18 | 2019-09-18 | 2021-06-01 | 2022-09-08 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 39775.7 | 151.53 | 39927.23 | 568072.77 | 0 | 0 | 608000 | 0 | 0 | 0 | 0 | 608000 | 444766.03 | [5 empty] | N | WG5 | 100%
501689 | WAN Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2020-06-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 375217.61 | 372240.01 | -139883.34 | 607574.28 | 0 | 0 | 0 | 607574.28 | 0 | 0 | 0 | 0 | 607574.28 | 306661.32 | [5 empty] | N | CM_M&G | 100%
500439 | Waste East SPS MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 2019-07-05 |  | All East Unitary Authorities | 0 | 0 | 101933 | 804842.88 | 533492.38 | 281392.88 | 121853.3 | 0 | 1843514.44 | 0 | 0 | 0 | 1843514.44 | 0 | 0 | 0 | 0 | 1843514.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500440 | Waste East SPS OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2015-11-25 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWNI | 100%
500441 | Waste East SPS SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2016-11-23 |  | All East Unitary Authorities | 0 | 0 | 1095069 | 215104.32 | 126.21 | 0 | 0 | 0 | 1310299.53 | 0 | 0 | 0 | 1310299.53 | 0 | 0 | 0 | 0 | 1310299.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500442 | Waste East WWTW MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-18 | 2015-05-18 | 2015-05-18 | 2018-12-19 |  | All East Unitary Authorities | 0 | 0 | 711824 | 1420372.47 | 1486222.83 | -600528.43 | 4385.24 | 0 | 3022276.11 | 0 | 0 | 0 | 3022276.11 | 0 | 0 | 0 | 0 | 3022276.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500443 | Waste East WWTW OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-11-26 |  | All East Unitary Authorities | 0 | 0 | 59.06 | 0 | 0 | 0 | 0 | 0 | 59.06 | 0 | 0 | 0 | 59.06 | 0 | 0 | 0 | 0 | 59.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500444 | Waste East WWTW SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-05-17 |  | All East Unitary Authorities | 0 | 0 | 3175049.85 | 703786.15 | 53107.6 | 0 | 0 | 0 | 3931943.6 | 0 | 0 | 0 | 3931943.6 | 0 | 0 | 0 | 0 | 3931943.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512167 | WASTE INFRA_SWD Responsive Repair_refurb_FMAP | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-04-01 |  | 2021-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 0 | 0 | 999999.99 | 0 | 0 | 0 | 0 | 999999.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512166 | WASTE INFRA_SWD Responsive Repair_Refurb_IRONWORKS | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MSU |  | 2021-04-01 |  | 2021-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 0 | 0 | 999999.99 | 0 | 0 | 0 | 0 | 999999.99 | 209381.79 | [5 empty] | N | CM_WSI | 100%
512165 | WASTE INFRA_SWD responsive Repair_Refurb_Sewers_Laterals_Pipebridges_Syphons_CSO | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU |  | 2021-04-01 |  | 2021-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 0 | 0 | 999999.99 | 0 | 0 | 0 | 0 | 999999.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
512161 | WASTE NON INFRA_SWD Responsive Repair_Refurb_SPS | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-01 |  | 2021-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 0 | 0 | 999999.99 | 0 | 0 | 0 | 0 | 999999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512160 | WASTE NON INFRA_SWD Responsive Repair_Refurb_WWTW | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-01 |  | 2021-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 0 | 0 | 999999.99 | 0 | 0 | 0 | 0 | 999999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500445 | Waste North Infra MD SVCW SR 15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2017-02-21 |  | All North Unitary Authorities | 0 | 0 | 108943 | 111609.62 | 3626.3 | 0 | 0 | 0 | 224178.92 | 0 | 0 | 0 | 224178.92 | 0 | 0 | 0 | 0 | 224178.92 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500446 | Waste North Infra OPS SVCW SR 15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2015-08-03 |  | All North Unitary Authorities | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500447 | Waste North Infra SWD SVCW SR 15 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-19 |  | All North Unitary Authorities | 0 | 0 | 547194 | 93210.28 | 0 | 0 | 0 | 0 | 640404.28 | 0 | 0 | 0 | 640404.28 | 0 | 0 | 0 | 0 | 640404.28 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500448 | Waste North SPS MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-13 | 2015-05-13 | 2015-05-13 | 2017-02-01 |  | All North Unitary Authorities | 0 | 0 | 8420 | 291866.13 | 352.25 | 0 | 0 | 0 | 300638.38 | 0 | 0 | 0 | 300638.38 | 0 | 0 | 0 | 0 | 300638.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500449 | Waste North SPS OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2015-08-03 |  | All North Unitary Authorities | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500450 | Waste North SPS SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2017-01-19 |  | All North Unitary Authorities | 0 | 0 | 694036.16 | 139180.94 | 2332 | 0 | 0 | 0 | 835549.1 | 0 | 0 | 0 | 835549.1 | 0 | 0 | 0 | 0 | 835549.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500451 | Waste North WWTW MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-08 | 2017-08-10 |  | All North Unitary Authorities | 0 | 0 | 578912 | 466341.71 | 55571.52 | 0 | 0 | 0 | 1100825.23 | 0 | 0 | 0 | 1100825.23 | 0 | 0 | 0 | 0 | 1100825.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500452 | Waste North WWTW OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2015-08-03 |  | All North Unitary Authorities | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500453 | Waste North WWTW SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-19 |  | All North Unitary Authorities | 0 | 0 | 2532790 | 310809.16 | 23984.78 | 0 | 0 | 0 | 2867583.94 | 0 | 0 | 0 | 2867583.94 | 0 | 0 | 0 | 0 | 2867583.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500454 | Waste South Infra MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2017-02-20 |  | All South Unitary Authorities | 0 | 0 | 1162069 | 772870.46 | -215007.27 | 0 | 0 | 0 | 1719932.19 | 0 | 0 | 0 | 1719932.19 | 0 | 0 | 0 | 0 | 1719932.19 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500455 | Waste South Infra OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-07 |  | All South Unitary Authorities | 0 | 0 | 1335925 | -82223.9 | 18645.28 | 0 | 0 | 0 | 1272346.38 | 0 | 0 | 0 | 1272346.38 | 0 | 0 | 0 | 0 | 1272346.38 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500456 | Waste South Infra SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-07 |  | All South Unitary Authorities | 0 | 0 | 538257 | -538257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWI | 100%
500457 | Waste South SPS MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2017-02-20 |  | All South Unitary Authorities | 0 | 0 | 768013 | 1402632.3 | 70694.47 | 4310.56 | 0 | 0 | 2245650.33 | 0 | 0 | 0 | 2245650.33 | 0 | 0 | 0 | 0 | 2245650.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500458 | Waste South SPS OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-02-07 |  | All South Unitary Authorities | 0 | 0 | 565459.64 | 218822.43 | 10099.74 | 0 | 43.06 | 0 | 794424.87 | 0 | 0 | 0 | 794424.87 | 0 | 0 | 0 | 0 | 794424.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500459 | Waste South SPS SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-02-07 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WWNI | 100%
500460 | Waste South WWTW MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-29 | 2017-03-21 |  | All South Unitary Authorities | 0 | 0 | 2085118 | 1850463.43 | -9132.43 | 0 | 0 | 0 | 3926449 | 0 | 0 | 0 | 3926449 | 0 | 0 | 0 | 0 | 3926449 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500461 | Waste South WWTW OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-07 |  | All South Unitary Authorities | 0 | 0 | 2596838.58 | 927113.79 | 20053.27 | 18.22 | 0 | 0 | 3544023.86 | 0 | 0 | 0 | 3544023.86 | 0 | 0 | 0 | 0 | 3544023.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500462 | Waste South WWTW SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2018-09-19 |  | All South Unitary Authorities | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401136 | Waste Water CAR License Variation - North | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-07-01 | 2010-07-01 | 2011-05-02 | 2016-01-13 |  | All North Unitary Authorities | 45998.58 | 0 | -6120 | 4602.75 | 0 | 0 | 0 | 0 | -1517.25 | 0 | 0 | 0 | 44481.33 | 0 | 0 | 0 | 0 | 44481.33 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403306 | Waste Water DOA Telemetry Schematics Upgrade | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-14 | 2013-11-05 | 2013-11-06 | 2016-01-28 |  | Scottish Water Wide | 637205 | 0 | -17916.95 | 16.14 | 0 | 0 | 0 | 0 | -17900.81 | 0 | 0 | 0 | 619304.19 | 0 | 0 | 0 | 0 | 619304.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503150 | Waste Water Energy Improvement Programme FOP | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2018-03-29 | 2018-03-29 | 2018-09-03 | 2021-10-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1056012.95 | 1530172.42 | 81814.63 | 2668000 | 0 | 0 | 0 | 2668000 | 0 | 0 | 0 | 0 | 2668000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501786 | Waste Water Lifting Chains | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-02 | 2028-08-08 | 2028-12-12 | 2030-03-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241943.09 | 0 | 0 | 241943.09 | 0 | 0 | 0 | 0 | 241943.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
402530 | Waste Water Pipe Bridges - HS Assessment - Remedials Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-09 | 2013-10-29 | 2013-11-08 | 2014-11-28 |  | Scottish Water Wide | 597701 | 0 | 20591 | -1379.64 | 0 | 0 | 0 | 0 | 19211.36 | 0 | 0 | 0 | 616912.36 | 0 | 0 | 0 | 0 | 616912.36 | 209381.79 | [5 empty] | N | CM_M&G | 100%
500463 | Waste West Infra MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2018-07-10 |  | All West Unitary Authorities | 0 | 0 | 122076 | 359263.45 | 206931.01 | 7628.77 | 0 | 0 | 695899.23 | 0 | 0 | 0 | 695899.23 | 0 | 0 | 0 | 0 | 695899.23 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500464 | Waste West Infra OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-02 |  | All West Unitary Authorities | 0 | 0 | 1131944.59 | 68297.16 | -77608.44 | 0 | 0 | 0 | 1122633.31 | 0 | 0 | 0 | 1122633.31 | 0 | 0 | 0 | 0 | 1122633.31 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500465 | Waste West Infra SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-16 |  | All West Unitary Authorities | 0 | 0 | 82196 | -60900.49 | 0 | 0 | 0 | 0 | 21295.51 | 0 | 0 | 0 | 21295.51 | 0 | 0 | 0 | 0 | 21295.51 | 209381.79 | [5 empty] | N | CM_WWI | 100%
500466 | Waste West SPS MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2019-06-12 |  | All West Unitary Authorities | 0 | 0 | 106735 | 427628.57 | 285937.5 | -7590.92 | 1226.47 | 120 | 814056.62 | 0 | 0 | 0 | 814056.62 | 0 | 0 | 0 | 0 | 814056.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500467 | Waste West SPS OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-01-17 |  | All West Unitary Authorities | 0 | 0 | 1438300 | 541198.46 | -277.96 | 0 | 0 | 0 | 1979220.51 | 0 | 0 | 0 | 1979220.51 | 0 | 0 | 0 | 0 | 1979220.51 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403376 | Waste West SPS OPS SVCW QSIV - 4033760000 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2017-03-03 |  | All West Unitary Authorities | 6215000 | 0 | 675425 | 20377.03 | -41861.48 | 0 | 0 | 0.01 | 653940.56 | 0 | 0 | 0 | 6868940.56 | 0 | 0 | 0 | 0 | 6868940.56 | 90601.29 | [5 empty] | N | CM_WWI | 100%
500468 | Waste West SPS SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-15 | 2015-04-15 | 2015-04-15 | 2017-01-02 |  | All West Unitary Authorities | 0 | 0 | 46252 | -16108.07 | -2439.93 | 0 | 0 | 0 | 27704 | 0 | 0 | 0 | 27704 | 0 | 0 | 0 | 0 | 27704 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500469 | Waste West WWTW MD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2019-05-08 |  | All West Unitary Authorities | 0 | 0 | 649389 | 1105633.37 | 635561.76 | -33020.57 | -13873.92 | 1078.18 | 2344767.82 | 0 | 0 | 0 | 2344767.82 | 0 | 0 | 0 | 0 | 2344767.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500470 | Waste West WWTW OPS SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-17 |  | All West Unitary Authorities | 0 | 0 | 3903196.55 | 1089666.73 | -1072781.69 | 0 | 0 | 0 | 3920081.59 | 0 | 0 | 0 | 3920081.59 | 0 | 0 | 0 | 0 | 3920081.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500471 | Waste West WWTW SWD SVCW QSIV | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-17 |  | All West Unitary Authorities | 0 | 0 | 305166.13 | 67274.19 | 9826.12 | 0 | 0 | 0 | 382266.44 | 0 | 0 | 0 | 382266.44 | 0 | 0 | 0 | 0 | 382266.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502722 | Wastewater Asset Capability | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-05-14 | 2021-06-02 | 2021-06-02 | 2021-06-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 259404.71 | 280625.1 | 112971.6 | 13863.07 | 666864.48 | 0 | 0 | 0 | 666864.48 | 0 | 0 | 0 | 0 | 666864.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500065 | Wastewater Security - Site Risk Assessments and Survey and Scoping Studies | Q&S4 | Protecting and enhancing the environment | Scottish Government Requirements |  |  | Wastewater |  | SWD | Scottish Government Requirements | MS7 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | Scottish Water Wide | 0 | 0 | 21986.16 | 0 | 0 | 0 | 0 | 0 | 21986.16 | 0 | 0 | 0 | 21986.16 | 0 | 0 | 0 | 0 | 21986.16 | 0 | [5 empty] | N | EC21D | 100%
508126 | Watch Water Reservoir - Aeration Curtain | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-08-26 | 2021-01-11 | 2021-07-19 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 48000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403771 | Water & Waste Water Chemical Dosing Systems - Improvements at High Priority Sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2014-04-25 | 2014-10-15 | 2014-10-08 | 2021-07-19 |  | Scottish Water Wide | 3034266 | 0 | 6061547 | 3222277.44 | 1525021.1 | 325443.89 | 225924.75 | 48493.82 | 11408708 | 33381.25 | 0 | 0 | 14476355.25 | 0 | 0 | 0 | 0 | 14476355.25 | 328404.37 | [5 empty] | N | CM_M&G | 100%
402052 | Water Balance Field Trough Studies | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2014-04-16 | 2014-04-16 | 2015-10-30 |  | Scottish Water Wide | 122490 | 0 | 3108.57 | 0 | 0 | 0 | 0 | 0 | 3108.57 | 0 | 0 | 0 | 125598.57 | 0 | 0 | 0 | 0 | 125598.57 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402055 | Water Balance Model Improvements | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2014-11-03 | 2014-11-03 | 2015-10-30 |  | Scottish Water Wide | 33640 | 0 | 8787.44 | 0 | 0 | 0 | 0 | 0 | 8787.44 | 0 | 0 | 0 | 42427.44 | 0 | 0 | 0 | 0 | 42427.44 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402057 | Water Balance Property Count | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2015-11-13 | 2016-02-29 | 2015-10-30 |  | Scottish Water Wide | 5690.39 | 0 | -592.93 | 0 | 0 | 0 | 0 | 0 | -592.93 | 0 | 0 | 0 | 5097.46 | 0 | 0 | 0 | 0 | 5097.46 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402049 | Water Balance Service Reservoir Leakage Estimation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-20 | 2015-01-23 | 2015-01-23 | 2015-10-30 |  | Scottish Water Wide | 13453 | 0 | -241.04 | 0 | 0 | 0 | 0 | 0 | -241.04 | 0 | 0 | 0 | 13211.96 | 0 | 0 | 0 | 0 | 13211.96 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402050 | Water Balance Trunk Mains Leakage Estimation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2015-11-13 | 2016-02-01 | 2015-10-30 |  | Scottish Water Wide | 39034.83 | 0 | -334.65 | 0 | 0 | 0 | 0 | 0 | -334.65 | 0 | 0 | 0 | 38700.18 | 0 | 0 | 0 | 0 | 38700.18 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401974 | Water Balance WwTW Potable Water Consumption | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-02-15 | 2011-08-02 | 2011-08-02 | 2015-10-30 |  | Scottish Water Wide | 114252.1 | 0 | -79.92 | 0 | 0 | 0 | 0 | 0 | -79.92 | 0 | 0 | 0 | 114172.18 | 0 | 0 | 0 | 0 | 114172.18 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503572 | Water Byelaw Compliance at SW Assets - Phase 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-09-17 | 2020-02-21 | 2020-07-07 | 2021-11-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 293201.52 | 1248617.28 | 1541818.79 | 1459001.82 | 0 | 0 | 3000820.61 | 0 | 0 | 0 | 0 | 3000820.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502188 | Water bylaws Compliance at SW Assets- Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-04 | 2017-04-27 | 2017-05-15 | 2018-02-14 |  | Scottish Water Wide | 0 | 0 | 0 | 72419.76 | 651751.14 | -10067.21 | 0 | 0 | 714103.69 | 0 | 0 | 0 | 714103.69 | 0 | 0 | 0 | 0 | 714103.69 | 209623.87 | [5 empty] | N | CM_WSNI | 9.911% | CM_WWNI | 90.09%
502325 | Water bylaws Compliance at SW Assets- Phase 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-02-27 | 2017-05-23 | 2017-07-19 | 2018-12-18 |  | Scottish Water Wide | 0 | 0 | 0 | 9438.82 | 270716.72 | 221358.01 | 14262.57 | 3675.88 | 519452 | 0 | 0 | 0 | 519452 | 0 | 0 | 0 | 0 | 519452 | 300225.16 | [5 empty] | N | CM_WWNI | 48% | CM_WSNI | 52%
503053 | Water Central- DWQR Chloramination & Chemical Dosing Flow Switches Inspections | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-02-26 | 2018-02-26 | 2018-03-05 | 2018-03-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 291484.71 | 0 | 0 | 0 | 291484.71 | 0 | 0 | 0 | 291484.71 | 0 | 0 | 0 | 0 | 291484.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511740 | Water Demand Management Improvement Data Studies | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2021-03-29 | 2021-04-29 | 2021-04-29 | 2022-07-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500431 | Water Efficiency Advice and Water Saving Packs and Trials | Q&S4 | Improving drinking water availability and resilience of service | Efficency Advice |  |  | Water | DWQR | SWD | Efficency Advice | MS5 | 2015-04-02 | 2015-04-02 | 2015-04-02 | 2020-12-16 | 2021-01-18 | Scottish Water Wide | 0 | 0 | 118343 | 188916.58 | 139547.49 | 153589.93 | 121828.67 | 77524.33 | 799750 | 11250 | 11250 | 15616.9153 | 811000 | 4366.9153 | 0 | 0 | 4366.9153 | 815366.9153 | 673425.52 | [5 empty] | N | CS18W | 100%
402771 | Water Efficiency Trial | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2012-07-09 | 2014-04-29 | 2014-04-29 | 2016-05-06 | 2016-06-09 | Scottish Water Wide | 1400000 | 0 | -48721.45 | 142.35 | 871.72 | 0 | 0 | 0 | -47707.38 | 0 | 0 | 0 | 1352292.62 | 0 | 0 | 0 | 0 | 1352292.62 | 0 | [5 empty] | N | CS19 | 100%
512170 | WATER INFRA_SWD Responsive Repair_Refurb_Dist Mains_Aquaducts_Pipe crossings_Strategic Valves | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2021-04-01 |  | 2021-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 0 | 0 | 999999.99 | 0 | 0 | 0 | 0 | 999999.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
512164 | WATER INFRA_SWD Responsive Repair_Refurb_IRONWORKS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2021-04-01 |  | 2021-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 0 | 0 | 999999.99 | 0 | 0 | 0 | 0 | 999999.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
512163 | WATER INFRA_SWD Responsive Repair_Refurb_Raw Water Mains and Trunk Mains | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU |  | 2021-04-01 |  | 2021-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 0 | 0 | 999999.99 | 0 | 0 | 0 | 0 | 999999.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503202 | Water Mains Flooding Risk Assessment | IR18 | Improving the customer experience | Customer Experience Studies |  |  | Wastewater |  | SWD | Customer Experience Studies | MS3 | 2019-09-09 | 2020-06-23 | 2020-08-27 | 2021-04-14 | 2021-06-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 19302.22 | 52068.51 | 71304.61 | 142675.34 | 101764.1 | 0 | 0 | 244439.44 | 0 | 28069.1687 | 0 | 28069.1687 | 272508.6087 | 1106452.62 | [5 empty] | N | CS17_S | 100%
500636 | Water Network Model Maintenance | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 | 2015-11-02 | 2015-11-02 | 2015-12-01 | 2021-02-12 |  | Scottish Water Wide | 0 | 0 | 247489 | 928755.72 | 465090.96 | 317056.61 | 158645.67 | 119095.93 | 2236133.89 | 4632.95 | 0 | 0 | 2240766.84 | 0 | 0 | 0 | 0 | 2240766.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
512157 | WATER NON INFRA_SWD Responsive Repair_Refurb_WPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-01 |  | 2021-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 0 | 0 | 999999.99 | 0 | 0 | 0 | 0 | 999999.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512155 | WATER NON INFRA_SWD Responsive Repair_Refurb_WTW | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-01 |  | 2021-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 0 | 0 | 999999.99 | 0 | 0 | 0 | 0 | 999999.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500473 | Water of Leith Strategic Solution Development | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2015-03-31 | 2016-03-01 | 2016-03-14 | 2018-11-30 | 2019-08-31 | City of Edinburgh | 0 | 0 | 121378 | 273843.73 | 435256.27 | 550968 | 49242.04 | 0 | 1430688.04 | 0 | 0 | 0 | 1430688.04 | 0 | 0 | 0 | 0 | 1430688.04 | 203233.4 | [5 empty] | Y | EC01D | 50% | EC10E | 50% | [38 empty] | 1 | [26 empty] | 0
400113 | Water of Leith Strategic Study | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-02-23 | 2011-01-17 | 2011-01-17 | 2013-03-13 | 2013-05-14 | City of Edinburgh | 338663.04 | 0 | 0 | 0 | 1081.74 | 1541.97 | 0 | 0 | 2623.71 | 0 | 0 | 0 | 341286.75 | 0 | 0 | 0 | 0 | 341286.75 | 28761.13 | [5 empty] | N | EC04C | 100%
502764 | WATER OF LEITH UIDs - BATCH 6.2 - Colinton Rd @ St Cuthberts Court CSO. | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS0 | 2017-06-02 | 2021-04-19 | 2021-09-27 | 2022-02-17 | 2022-02-17 | City of Edinburgh | 0 | 0 | 0 | 0 | 82811 | 50783 | 32702 | 100845 | 267141 | 174329.02 | 0 | 0 | 441470.02 | 0 | 0 | 0 | 0 | 441470.02 | 0 | [5 empty] | N | SR21_WW | 100%
502751 | WATER OF LEITH UIDs - BATCH 0 - 2 x STUDY OUTPUTS | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | SWD | UWWTD - UID | MS7 | 2017-05-16 | 2017-07-14 | 2017-07-14 | 2017-05-31 | 2017-10-30 | City of Edinburgh | 0 | 0 | 0 | 0 | 48304.64 | 0 | 0 | 0 | 48304.64 | 0 | 0 | 0 | 48304.64 | 0 | 0 | 0 | 0 | 48304.64 | 133688.59 | [5 empty] | N | EC01F | 100%
502740 | WATER OF LEITH UIDs - BATCH 1 - South Gyle Gogarloch SPS EO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS3 | 2017-05-31 | 2019-03-27 | 2020-02-24 | 2021-05-06 | 2021-08-09 | City of Edinburgh | 0 | 0 | 0 | 0 | 54066 | 2638 | 58426 | 13537 | 128667 | 2202 | 2202 | 21628.7899 | 130869 | 19426.7899 | 0 | 0 | 19426.7899 | 150295.7899 | 133688.59 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
502749 | WATER OF LEITH UIDs - BATCH 10 - Gyle Public Park No1 and No2 CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS3 | 2017-10-31 | 2020-03-31 | 2020-03-31 | 2022-03-31 | 2022-07-07 | City of Edinburgh | 0 | 0 | 0 | 0 | 125823 | 17418 | 168480.53 | 851422.47 | 1163144 | 501792.84 | 501792.84 | 610445.7538 | 1664936.84 | 108652.9138 | 0 | 0 | 108652.9138 | 1773589.7538 | 133688.59 |  |  |  |  | 2990.0004 | N | EC01F | 100%
502750 | WATER OF LEITH UIDs - BATCH 11 - Curriehill Storm Tank CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | SWD | UWWTD - UID | MS7 | 2017-10-24 | 2017-12-19 | 2018-01-17 | 2018-01-31 | 2018-05-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 42645.34 | 108592.01 | 0 | 0 | 151237.35 | 0 | 0 | 0 | 151237.35 | 0 | 0 | 0 | 0 | 151237.35 | 267377.18 | [5 empty] | Y | EC10B | 50% | EC01F | 50% | [33 empty] | 1 | [31 empty] | 0
502741 | WATER OF LEITH UIDs - BATCH 2 - Currie Old Mill Off Lanark Road CSO and Juniper Green | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS3 | 2017-06-01 | 2020-01-29 | 2020-03-23 | 2021-05-28 | 2021-09-02 | City of Edinburgh | 0 | 0 | 0 | 0 | 113342 | 23332 | 155261 | 551332 | 843267 | 2250 | 2250 | 157035.2377 | 845517 | 154785.2377 | 0 | 2.3283e-10 | 154785.2377 | 1000302.2377 | 133688.59 | [5 empty] | N | EC01F | 100%
502742 | WATER OF LEITH UIDs - BATCH 3 - Juniper Green Off Lanark Road CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS3 | 2017-06-01 | 2020-01-21 | 2020-02-24 | 2021-08-06 | 2021-11-09 | City of Edinburgh | 0 | 0 | 0 | 0 | 93222 | 29088 | 175051.92 | 422355.08 | 719717 | 114849 | 114849 | 145710.4193 | 834566 | 30861.4193 | 0 | 0 | 30861.4193 | 865427.4193 | 133688.59 | [5 empty] | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
502743 | WATER OF LEITH UIDs - BATCH 4 - Balerno Bridge Road CSOs | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater | SEPA | WWINF | SR21 Early Start | MS3 | 2017-06-02 | 2020-03-31 | 2020-03-31 | 2022-06-13 | 2022-09-15 | City of Edinburgh | 0 | 0 | 0 | 0 | 118843 | 64688 | 144280 | 210430 | 538241 | 719928 | 767385 | 767385 | 1258169 | 0 | 0 | 47457 | 47457 | 1305626 | 0 | [5 empty] | Y | SR21_WW | 100% | [35 empty] | 1 | [31 empty] | 0
502744 | WATER OF LEITH UIDs - BATCH 5 - Currie Kinauld Farm CSO | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Wastewater |  | WWINF | SR21 Early Start | MS2 | 2017-06-02 | 2020-07-30 | 2021-05-17 | 2022-04-25 | 2022-04-25 | City of Edinburgh | 0 | 0 | 0 | 0 | 101315 | 21298 | 90482 | 185029 | 398124 | 294341.02 | 0 | 0 | 692465.02 | 0 | 0 | 0 | 0 | 692465.02 | 0 | [5 empty] | N | SR21_WW | 100%
502745 | WATER OF LEITH UIDs - BATCH 6.1 - Colinton Redford Drive CSO No. 2 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2017-06-02 | 2019-08-21 | 2019-09-02 | 2019-09-19 | 2019-09-19 | City of Edinburgh | 0 | 0 | 0 | 0 | 120424 | 39702 | 17416.14 | 0 | 177542.14 | 0 | 0 | 0 | 177542.14 | 0 | 0 | 0 | 0 | 177542.14 | 133688.59 | [5 empty] | N | EC01F | 100%
502746 | WATER OF LEITH UIDs - BATCH 7 - Longstone CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WINF | UWWTD - UID | MS0 | 2017-10-30 | 2021-10-04 | 2022-01-05 | 2022-10-10 | 2023-01-24 | City of Edinburgh | 0 | 0 | 0 | 0 | 206894 | 109276 | 56477 | 68434 | 441081 | 1587843.59 | 1587843.59 | 2204197.2264 | 2028924.59 | 616353.6364 | 0 | 0 | 616353.6364 | 2645278.2264 | 133688.59 | [5 empty] | N | EC01F | 100%
502747 | WATER OF LEITH UIDs - BATCH 8 - Kingsknowe R-O 29 Dovecot Grove CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS3 | 2017-10-31 | 2020-02-17 | 2020-03-23 | 2021-08-16 | 2021-11-17 | City of Edinburgh | 0 | 0 | 0 | 0 | 107885 | 44340 | 278608 | 467664 | 898497 | 146092 | 146092 | 180292.2244 | 1044589 | 34200.2244 | 0 | 0 | 34200.2244 | 1078789.2244 | 133688.59 |  |  |  |  | 2949.9996 | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
502748 | WATER OF LEITH UIDs - BATCH 9.1 - Currie Kinleith Ind Est CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS3 | 2017-10-30 | 2020-03-31 | 2020-03-31 | 2022-03-25 | 2022-07-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 88031 | 28114 | 84699 | 73336 | 274180 | 154600 | 154600 | 186511.0857 | 428780 | 31911.0857 | 0 | 0 | 31911.0857 | 460691.0857 | 133688.59 |  |  |  |  | 2270.0004 | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
502765 | WATER OF LEITH UIDs - BATCH 9.2 - Currie GDN 2A Lanark Road West CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater | SEPA | WWINF | UWWTD - UID | MS3 | 2017-10-31 | 2020-03-31 | 2020-11-30 | 2021-09-06 | 2021-12-07 | City of Edinburgh | 0 | 0 | 0 | 0 | 130610 | 89354 | 70649 | 351590 | 642203 | 23896 | 23896 | 61006.8983 | 666099 | 37110.8983 | 0 | 0 | 37110.8983 | 703209.8983 | 133688.59 |  |  |  |  | 2990.0003 | Y | EC01F | 100% | [35 empty] | 1 | [31 empty] | 0
503256 | Water Quality Improvement - Greenock Phase 2 - Conditioning | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS3 | 2018-06-28 | 2019-06-28 | 2019-09-03 | 2021-06-29 | 2022-03-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 326478 | 180663.11 | 165686.89 | 672828 | 5000 | 38891 | 38891 | 677828 | 0 | 33891 | 0 | 33891 | 711719 | 701384.22 | [5 empty] | Y | DW5MC | 100% | [23 empty] | 65.78 | [43 empty] | 0
503257 | Water Quality Improvement - Greenock Phase 2 - Flushing | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS4 | 2018-06-28 | 2019-05-29 | 2019-09-06 | 2021-03-31 | 2022-07-26 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 275220 | 387708.86 | 420698.14 | 1083627 | 0 | 166373 | 166373 | 1083627 | 0 | 166373 | 0 | 166373 | 1250000 | 254657.2 | [5 empty] | N | DW5FS | 100%
503355 | Water Quality Improvement- Afton RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2020-03-20 | 2020-03-20 | 2020-03-20 | 2020-03-23 | 2021-04-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 45627.91 | 63372.09 | -61272.38 | 47727.62 | 0 | 0 | 0 | 47727.62 | 0 | 0 | 0 | 0 | 47727.62 | 0 | [5 empty] | N | DW5FS | 100%
503193 | Water Quality Improvement- Amlaird Flushing RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS4 | 2018-06-28 | 2018-12-21 | 2019-03-28 | 2020-07-07 | 2021-10-29 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 227645.55 | 174789.5 | 83413.85 | 485848.9 | 1702.66 | 1702.6617 | 41164.2163 | 487551.56 | 39461.5546 | 0 | -0.0046 | 39461.55 | 527013.11 | 0 | [5 empty] | N | DW5FS | 100%
503336 | Water Quality Improvement-Wick East DMA | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | WINF | DWQ Compliance | MS2 | 2018-06-28 | 2021-03-31 | 2021-08-02 | 2021-07-02 | 2022-07-25 | Highland | 0 | 0 | 0 | 0 | 0 | 40498.94 | 361218.39 | -228206.33 | 173511 | 3939674.72 | 3939674.72 | 5327145.6538 | 4113185.72 | 1387470.9338 | 0 | -0.0038 | 1387470.93 | 5500656.65 | 1805010.12 | [5 empty] | Y | DW5MR | 100% | [19 empty] | 1 | [47 empty] | 0
501184 | Water Quality Investigation into Deteriorating Cast Iron Mains | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-11-04 | 2016-04-12 | 2016-04-18 | 2017-01-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 3262 | 82693.21 | 8520.78 | 7116.56 | 0 | 0 | 101592.55 | 0 | 0 | 0 | 101592.55 | 0 | 0 | 0 | 0 | 101592.55 | 0 | [5 empty] | Y | DW5A | 100% | [64 empty] | 1 |  |  | 0
511701 | Water Quality Network Investigations | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | Water |  | SWD | SR21 Early Start | MS0 | 2021-04-07 | 2023-06-12 | 2023-09-08 | 2024-08-15 | 2024-08-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7552.15 | 7552.15 | 3446447.85 | 0 | 0 | 3454000 | 0 | 0 | 0 | 0 | 3454000 | 0 | [5 empty] | N | SR21_WA | 100%
402613 | Water Quality OPA Action Plan - Central | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-05-01 | 2014-08-04 |  | Scottish Water Wide | 9898107.1 | 0 | -238 | 0 | 0 | 0 | 0 | 0 | -238 | 0 | 0 | 0 | 9897869.1 | 0 | 0 | 0 | 0 | 9897869.1 | 119022.58 |  |  |  |  | 156863 | N | CM_WSNI | 100%
403794 | Water Quality OPA Action Plan - Central Year 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-05-19 | 2014-06-25 | 2014-06-25 | 2015-09-11 |  | Scottish Water Wide | 2005500 | 0 | 149372.52 | 0 | 0 | 0 | 0 | 0 | 149372.52 | 0 | 0 | 0 | 2154872.52 | 0 | 0 | 0 | 0 | 2154872.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402612 | Water Quality OPA Action Plan - North | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-02-22 | 2012-03-22 | 2012-04-02 | 2015-01-23 |  | All North Unitary Authorities | 269091.86 | 0 | 281.81 | 0 | 0 | 0 | 0 | 0 | 281.81 | 0 | 0 | 0 | 269373.67 | 0 | 0 | 0 | 0 | 269373.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500623 | Water Service Strategy GM SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 243588.37 | 549819.68 | 931123.56 | 1140392.35 | 425620.08 | 417141.21 | 3707685.24 | 0 | 0 | 0 | 3707685.24 | 0 | 0 | 0 | 0 | 3707685.24 | 306661.32 | [5 empty] | N | CM_OVH | 100%
506432 | Water SVCD Responsive Y6 Time | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-05 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105964.59 | 105964.59 | 394035.41 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502673 | Waternish WOA - Geary DMA - Mains Renewal - WQ pH Issue | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2020-05-22 |  | Highland | 0 | 0 | 0 | 0 | 13509.54 | 1394.34 | 6833.84 | -6833.84 | 14903.88 | 0 | 0 | 0 | 14903.88 | 0 | 0 | 0 | 0 | 14903.88 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502625 | Waternish WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2020-04-06 | 2020-04-06 | 2020-04-06 | 2020-04-28 |  | Highland | 0 | 0 | 0 | 20930.23 | 207.95 | 2310.72 | 23177.29 | -40195.68 | 6430.51 | 0 | 0 | 0 | 6430.51 | 0 | 0 | 0 | 0 | 6430.51 | 122419.09 | [5 empty] | N | WG1 | 100%
45573 | Waternish WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-11 | 2011-07-22 | 2012-01-16 | 2012-03-14 | Highland | 183693.07 | 0 | 76.2 | 0 | 0 | 0 | 0 | 0 | 76.2 | 0 | 0 | 0 | 183769.27 | 0 | 0 | 0 | 0 | 183769.27 | 28761.13 | [5 empty] | N | DW13 | 100%
502433 | Waulkmill Glen & Ryat Linn MIOS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2018-01-31 | 2018-01-31 | 2018-03-01 | 2019-01-11 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 63084.25 | 373377.58 | -17759.25 | 74.82 | 418777.4 | 0 | 0 | 0 | 418777.4 | 0 | 0 | 0 | 0 | 418777.4 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404104 | Waulkmillglen Reservoir - Various IoS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-03-06 | 2015-12-11 | 2015-12-14 | 2016-01-05 |  | East Renfrewshire | 19.98 | 0 | 340555.88 | 0 | 0 | 0 | 0 | 0 | 340555.88 | 0 | 0 | 0 | 340575.86 | 0 | 0 | 0 | 0 | 340575.86 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403080 | Wellbank WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-12-10 | 2014-09-18 | 2014-11-28 | 2015-08-27 | 2015-08-28 | Angus | 829865 | 0 | 321825 | 19998.62 | 16318.66 | 0 | 0 | 0 | 358142.28 | 0 | 0 | 0 | 1188007.28 | 0 | 0 | 0 | 0 | 1188007.28 | 0 | [5 empty] | N | SG1 | 100%
503611 | Wellington WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2022-08-23 | 2024-07-12 | 2024-10-10 | 2025-12-03 |  | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 62675.58 | 59187.43 | 121863.01 | 1906930.76 | 0 | 0 | 2028793.77 | 0 | 0 | 0 | 0 | 2028793.77 | 122419.09 | [5 empty] | N | SG1 | 100%
504254 | W-E-NI-09122019-BADENTINAN RWI-Investigation into installing standby generator (5591) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-05-01 |  | 2020-01-07 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 2836.11 | 0 | 2836.11 | 198.53 | 0 | 0 | 3034.64 | 0 | 0 | 0 | 0 | 3034.64 | 119022.58 | [5 empty] | N | CM_WSI | 100%
403636 | West Area CMC Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-12-30 | 2013-12-30 | 2014-07-02 | 2017-03-06 |  | All West Unitary Authorities | 368488 | 0 | 32630 | -3266.53 | -16.72 | 0 | 0 | 0 | 29346.75 | 0 | 0 | 0 | 397834.75 | 0 | 0 | 0 | 0 | 397834.75 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507784 | West Building Condition Interventions | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 |  | 2020-07-29 | 2021-01-21 | 2021-12-03 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28072 | 28072 | 51928.38 | 0 | 0 | 80000.38 | 0 | 0 | 0 | 0 | 80000.38 | 306661.32 | [5 empty] | N | CM_M&G | 100%
404032 | West Coast Weather Incident - Burn & River crossing & intake reinstatement | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-12-05 | 2014-12-05 | 2015-01-19 | 2015-11-06 |  | Highland | 153993 | 0 | 142499 | -0.05 | -2158.28 | 0 | 0 | 0 | 140340.67 | 0 | 0 | 0 | 294333.67 | 0 | 0 | 0 | 0 | 294333.67 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503624 | West drought 2019 & 2020 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2020-05-29 | 2020-05-29 | 2020-06-01 | 2021-05-20 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967413.21 | 967413.21 | 32586.79 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500766 | West John Street Arbroath Replace Gravity Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-24 | 2016-06-16 | 2016-08-23 | 2017-03-23 |  | Angus | 0 | 0 | 37000 | 336649 | 9353 | 1422.58 | 0 | 0 | 384424.58 | 0 | 0 | 0 | 384424.58 | 0 | 0 | 0 | 0 | 384424.58 | 209381.79 | [5 empty] | N | CM_WWI | 100%
400761 | West Leak Detection Equipment | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 266000 | 0 | -35171.29 | 0 | 0 | 0 | 0 | 0 | -35171.29 | 0 | 0 | 0 | 230828.71 | 0 | 0 | 0 | 0 | 230828.71 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503425 | West Lewis - WG4 - Improvement to Supply-Demand Balance | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water | DWQR | WINF | SOSI | MS0 | 2016-03-29 | 2022-03-14 | 2022-04-06 | 2023-01-30 | 2023-05-02 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 62500 | 81161.46 | 278830.18 | 422491.64 | 1161151.21 | 1161151.21 | 1611875.5605 | 1583642.85 | 450724.3505 | 0 | 0 | 450724.3505 | 2034367.2005 | 258568.71 | [5 empty] | Y | WG4 | 100% | [25 empty] | 1 | [41 empty] | 0
401404 | West Lewis Water Rehab Cluster Project Isle of Lewis | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-13 | 2014-03-27 | 2014-05-07 | 2015-12-01 |  | Na H-Eileanan an Iar | 353440 | 0 | 44151.24 | 2287.23 | 0 | 0 | 0 | 0 | 46438.47 | 0 | 0 | 0 | 399878.47 | 0 | 0 | 0 | 0 | 399878.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500884 | West Lewis Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-04-07 | 2018-09-26 | 2018-12-11 | 2019-06-11 | 2020-02-28 | Na H-Eileanan an Iar | 0 | 0 | 4355.08 | 10309.92 | 9115.35 | 40172.78 | 37288.87 | 2629 | 103871 | 0 | 0 | 0 | 103871 | 0 | 0 | 0 | 0 | 103871 | 194558.84 | [5 empty] | N | DW5FS | 100%
500216 | West Lewis WI - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWD | DWQ Compliance | MS7 | 2015-03-20 | 2016-03-30 | 2016-06-20 | 2017-03-15 | 2018-12-21 | Na H-Eileanan an Iar | 0 | 0 | 527.16 | 31842.97 | 28932.81 | 2913.03 | 3183.53 | 0 | 67399.5 | 0 | 0 | 0 | 67399.5 | 0 | 0 | 0 | 0 | 67399.5 | 266208.2 | [5 empty] | N | DW5FS | 100%
502752 | West Lewis WOA- Linshader and bernera Undersea Pipe Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2027-04-27 | 2028-02-11 | 2028-05-02 | 2029-02-13 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 42478.98 | 11674.31 | 1215.22 | -581.66 | 54786.85 | 1055213.12 | 0 | 0 | 1109999.97 | 0 | 0 | 0 | 0 | 1109999.97 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502619 | West Lewis WOA- Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2020-04-30 | 2021-09-27 | 2021-10-25 | 2022-09-05 |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 20128.53 | 3205.53 | 2009.49 | 474.63 | 46593.82 | 72412 | 500008.84 | 0 | 0 | 572420.84 | 0 | 0 | 0 | 0 | 572420.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402212 | West Lewis WTW and WSZ Western Isles Additional Storage Provision | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-03-20 | 2013-02-11 | 2013-03-18 | 2014-06-10 |  | Na H-Eileanan an Iar | 595500 | 0 | 0 | 956.26 | 0 | 0 | 0 | 0 | 956.26 | 0 | 0 | 0 | 596456.26 | 0 | 0 | 0 | 0 | 596456.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502133 | West Lewis WTW CWT | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water | DWQR | SWD | Supply Resilience | MS7 | 2016-03-24 | 2016-03-29 | 2016-03-29 | 2016-03-31 | 2016-03-31 | Na H-Eileanan an Iar | 0 | 0 | 65.42 | 0 | 0 | 0 | 0 | 0 | 65.42 | 0 | 0 | 0 | 65.42 | 0 | 0 | 0 | 0 | 65.42 | 1989709.51 | [5 empty] | Y | CS16WR | 100% | [24 empty] | 1 | [42 empty] | 0
402207 | West Line Heathfield SR WSZ000776 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-13 | 2012-09-13 | 2012-10-31 | 2013-05-20 |  | Highland | 279431 | 0 | -1713.3 | 0 | 0 | 0 | 0 | 0 | -1713.3 | 0 | 0 | 0 | 277717.7 | 0 | 0 | 0 | 0 | 277717.7 | 311236.79 | [5 empty] | N | CM_WSI | 100%
31772 | West Linton STW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-08 | 2010-09-20 | 2010-11-29 | 2013-03-29 | 2013-05-14 | Scottish Borders | 1225231.7 | 0 | 12387.27 | 0 | 0 | 0 | 0 | 0 | 12387.27 | 0 | 0 | 0 | 1237618.97 | 0 | 0 | 0 | 0 | 1237618.97 | 241781.51 | [5 empty] | N | SG1 | 5% | CM_WWNI | 25% | EC10A | 70%
403972 | West Linton WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS0 | 2016-10-04 | 2023-09-29 | 2023-12-28 | 2025-01-31 |  | Scottish Borders | 9516.54 | 0 | 12552.46 | 20498.13 | 1954.36 | 18109.88 | 29011.5 | 38729.13 | 120855.46 | 1846217.07 | 0 | 0 | 1976589.07 | 0 | 0 | 0 | 0 | 1976589.07 | 90601.29 | [5 empty] | N | CM_WWNI | 41.25% | SG1 | 58.75%
501100 | West Lothian Surface Water Action Plan | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater | SEPA | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-09-27 | 2016-09-29 | 2020-02-19 | 2019-11-30 | West Lothian | 0 | 0 | 10169 | 132650.84 | 60055.5 | 58124.66 | 10073.07 | 19646.47 | 290719.54 | 0 | 0 | 0 | 290719.54 | 0 | 0 | 0 | 0 | 290719.54 | 0 | [5 empty] | Y | EC10D | 100% | [40 empty] | 6 | [26 empty] | 0
403275 | West Mill Road - Lasswade | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-01-23 | 2014-10-02 | 2014-10-15 | 2015-03-30 | 2015-03-30 | Midlothian | 421690 | 421690 | 25992 | 8679.56 | -3204.03 | 0 | 0 | 0 | 31467.53 | 0 | 0 | 0 | 453157.53 | 0 | 0 | 0 | 0 | 453157.53 | 180449.74 | [5 empty] | N | FL_DD | 100%
400634 | West Pollution Hotspots Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2013-02-13 | 2013-05-20 | 2014-05-27 |  | All West Unitary Authorities | 123734 | 0 | 0 | -1737.84 | 0 | 0 | 0 | 0 | -1737.84 | 0 | 0 | 0 | 121996.16 | 0 | 0 | 0 | 0 | 121996.16 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511482 | West Repair-Refurb-Replace DMA Meters and Loggers RP | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2021-03-16 | 2021-03-24 | 2021-04-01 | 2022-07-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37943.93 | 37943.93 | 542056.07 | 0 | 0 | 580000 | 0 | 0 | 0 | 0 | 580000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502257 | West SPS MCC Replacements Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-09-22 | 2018-06-07 | 2018-11-12 | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 52083 | 143590 | 808664 | 58397 | 54244 | 1116978 | 3521 | 0 | 0 | 1120499 | 0 | 0 | 0 | 0 | 1120499 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502247 | West SPS MCC Replacements Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2020-05-19 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 23926.39 | 43.72 | 2592.85 | -26374.38 | 188.57 | 0 | 0 | 0 | 188.57 | 0 | 0 | 0 | 0 | 188.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509880 | West Water Dam - Spillway Inspection and Repairs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-01-03 | 2023-07-12 | 2023-10-10 | 2024-09-16 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1255.81 | 1255.81 | 298968.84 | 0 | 0 | 300224.65 | 0 | 0 | 0 | 0 | 300224.65 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510806 | West Water Reservoir - Site Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-03-11 | 2021-06-18 | 2022-01-31 |  | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3527.35 | 3527.35 | 46472.65 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501315 | West WWTW MCC Replacement Ph 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS2 | 2016-10-04 | 2021-03-09 | 2022-08-18 | 2025-08-29 |  | Scottish Water Wide | 0 | 0 | 0 | 4043.08 | 52875.44 | 0.01 | -0.01 | -14449.52 | 42469 | 0 | 0 | 0 | 42469 | 0 | 0 | 0 | 0 | 42469 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501310 | Westburn Cambuslang PS RM | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-12-01 | 2018-01-29 | 2018-02-19 | 2018-05-25 |  | South Lanarkshire | 0 | 0 | 6101 | 129172 | 287073 | 258654 | 0 | 1296.65 | 682296.65 | 0 | 0 | 0 | 682296.65 | 0 | 0 | 0 | 0 | 682296.65 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503033 | Wester Balbeggie River Ore Sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2021-08-24 | 2023-02-27 | 2023-05-19 | 2024-02-27 |  | Fife | 0 | 0 | 0 | 0 | 6768.75 | 16565.97 | 4624.42 | 21150.86 | 49110 | 180690.16 | 0 | 0 | 229800.16 | 0 | 0 | 0 | 0 | 229800.16 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506805 | Westfield DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-08-08 | 2023-09-25 | 2024-11-21 | 2025-02-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2094.52 | 2094.52 | 347905.48 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 350000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500492 | Westfield WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-25 | 2016-07-31 | West Lothian | 0 | 0 | 60228 | 1874.57 | 360 | 0 | 0 | 0 | 62462.57 | 0 | 0 | 0 | 62462.57 | 0 | 0 | 0 | 0 | 62462.57 | 122419.09 | [5 empty] | N | SG1 | 100%
503228 | WestfieldWwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-09-02 | 2029-02-21 | 2029-06-15 | 2030-06-12 |  | West Lothian | 0 | 0 | 0 | 0 | 0 | 78171.44 | 20941.58 | -0.02 | 99113 | 0 | 0 | 0 | 99113 | 0 | 0 | 0 | 0 | 99113 | 122419.09 | [5 empty] | N | SG1 | 100%
500771 | Westhill Service Reservoir | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | NONINF | Infra Charge | MS3 | 2016-08-31 | 2018-09-12 | 2019-01-08 | 2021-06-14 |  | Aberdeenshire | 0 | 0 | 11045.68 | 92934.07 | 436972.33 | 500389.27 | 1095185.64 | 936082.01 | 3072609 | 345285.37 | 0 | 0 | 3417894.37 | 0 | 0 | 36230.63 | 36230.63 | 3454125 | 444766.03 | [5 empty] | N | WG5 | 100%
402769 | Westhills WSZ - Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-09 | 2014-03-26 | 2014-03-27 | 2014-10-14 |  | Angus | 57695 | 0 | 909.09 | 0 | 0 | 0 | 0 | 0 | 909.09 | 0 | 0 | 0 | 58604.09 | 0 | 0 | 0 | 0 | 58604.09 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402716 | Westhills WSZ Low Pressure Enhancement WSZ001563 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-03 | 2014-12-05 | 2014-12-16 | 2015-06-25 | 2015-03-27 | Angus | 67572.41 | 0 | 3318.57 | 0 | 0 | 0 | 0 | 0 | 3318.57 | 0 | 0 | 0 | 70890.98 | 0 | 0 | 0 | 0 | 70890.98 | 0 | [5 empty] | N | CS1 | 100%
501704 | Westmill Farm Glenrothes - Reline sewer | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-11-17 | 2017-05-23 | 2017-07-24 | 2017-09-26 |  | Fife | 0 | 0 | 0 | 11235 | 45926 | 1456.01 | 0 | 0 | 58617.01 | 0 | 0 | 0 | 58617.01 | 0 | 0 | 0 | 0 | 58617.01 | 209381.79 | [5 empty] | N | CM_WWI | 100%
501255 | Westray WTW - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS1 | 2016-07-29 | 2027-07-07 | 2027-08-06 | 2028-02-01 |  | Orkney Islands | 0 | 0 | 2338 | 89382.98 | 0 | -5994.74 | 0 | -0.24 | 85726 | 0 | 0 | 0 | 85726 | 0 | 0 | 0 | 0 | 85726 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500720 | Weyland Bay WWPS 1997 HY458121 - SR15 Capital Maintenance | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2015-07-07 | 2018-03-28 | 2018-03-29 | 2021-04-20 |  | Orkney Islands | 0 | 0 | 75025 | 33565 | 214114 | 546554 | 102761.08 | 6065.92 | 978085 | 558 | 0 | 0 | 978643 | 0 | 0 | 0 | 0 | 978643 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
500194 | WFD Abstraction Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Water | SEPA | SWD | Environmental Studies | MS7 | 2015-03-26 | 2016-09-30 | 2016-10-03 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 5535 | 31508 | 61181.81 | 2889.64 | -9781.79 | 0 | 91332.66 | 0 | 0 | 0 | 91332.66 | 0 | 0 | 0 | 0 | 91332.66 | 664921.77 | [5 empty] | Y | WR1A | 100% | [40 empty] | 8 | [26 empty] | 0
402618 | WFD CAR licence Monitoring Equipment Refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-03-26 | 2012-10-09 | 2012-10-22 | 2014-12-02 |  | Scottish Water Wide | 632000 | 0 | -8000 | -1409.92 | 0 | 0 | 0 | 0 | -9409.92 | 0 | 0 | 0 | 622590.08 | 0 | 0 | 0 | 0 | 622590.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Water | SEPA | SWD | Environmental Studies | MS7 | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-29 | 2018-03-29 | Scottish Water Wide | 0 | 0 | 8693 | 23241 | 126232.68 | 26517.52 | 1274.58 | 0 | 185958.78 | 0 | 0 | 0 | 185958.78 | 0 | 0 | 0 | 0 | 185958.78 | 100684.66 | [5 empty] | N | WR2B | 100%
500891 | Whalsay Shetland RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS6 | 2016-10-19 | 2018-09-21 | 2019-03-18 | 2019-05-31 | 2020-02-29 | Shetland Islands | 0 | 0 | 857.04 | 8543.79 | 4347.36 | 30780.99 | 9723.86 | 13366.96 | 67620 | 0 | 0 | 0 | 67620 | 0 | 0 | 0 | 0 | 67620 | 43188.25 | [5 empty] | Y | DW5FS | 100% | [23 empty] | 15.77 | [43 empty] | 0
403670 | Whalsay WTW Upgrade | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water | DWQR | SWMD | DWQ Compliance | MS7 | 2014-02-17 | 2016-01-29 | 2016-03-23 | 2018-01-31 | 2018-12-31 | Shetland Islands | 57282.47 | 57282.47 | 1497383.53 | 3113151.78 | 495600.34 | 135167.17 | -29763.84 | 0 | 5211538.98 | 0 | 0 | 0 | 5268821.45 | 0 | 0 | 0 | 0 | 5268821.45 | 3644365.96 |  |  |  |  | 262196 | Y | DW25P | 10% | DW2 | 45% | DW23 | 45% | [14 empty] | 1 | [48 empty] | 0
508128 | Whinnyfold SEP Ecological Treatment Plant | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-01 | 2022-06-23 | 2023-02-03 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6362.24 | 6362.24 | 243637.77 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503245 | Whinnyfold ST ecological treatment system | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2027-04-01 | 2028-02-16 | 2028-06-14 | 2028-10-19 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294433.81 | 0 | 0 | 294433.81 | 0 | 0 | 0 | 0 | 294433.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508287 | Whiteadder Reservoir Actuator Repair | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-09-08 | 2020-12-07 | 2021-06-14 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6348 | 6348 | 3651.72 | 0 | 0 | 9999.72 | 0 | 0 | 0 | 0 | 9999.72 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500687 | Whitecraigs Court Giffnock | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2015-06-11 | 2020-02-18 | 2020-03-16 | 2021-06-28 |  | East Renfrewshire | 0 | 0 | 6750 | 12029 | 70243 | 79577 | 297671 | 836923.69 | 1303193.69 | -31385.69 | 0 | 0 | 1271808 | 0 | 0 | 178192 | 178192 | 1450000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502823 | Whitecross WwTW - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2020-01-30 | 2020-01-30 | 2020-01-30 | 2020-03-27 |  | West Lothian | 0 | 0 | 0 | 0 | 74965.67 | 37811.65 | 8822.93 | 0 | 121600.25 | 0 | 0 | 0 | 121600.25 | 0 | 0 | 0 | 0 | 121600.25 | 122419.09 | [5 empty] | N | SG1 | 100%
503384 | Whiteford ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2027-05-13 | 2028-03-21 | 2028-07-24 | 2029-01-12 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 66450.7 | 6450.59 | 6755.71 | 79657 | 2343.02 | 0 | 0 | 82000.02 | 0 | 0 | 0 | 0 | 82000.02 | 122419.09 | [5 empty] | N | SG1 | 100%
501200 | Whitehall DSR CM | IR18 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2018-12-21 | 2020-12-21 | 2020-12-21 | 2022-04-25 | 2022-07-20 | Orkney Islands | 0 | 0 | 18092.93 | 30822.63 | 25151.73 | 21899.66 | 309743.4 | 353438.65 | 759149 | 1266851 | 1550718 | 1550718 | 2026000 | 0 | 283867 | 0 | 283867 | 2309867 | 1277702.09 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
508414 | Whitehill Interceptor | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2021-04-23 | 2021-05-24 | 2021-10-29 | 2023-05-12 | 2023-08-14 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 48500 | 48500 | 67326.2569 | 50000 | 18826.2569 | 0 | 0 | 18826.2569 | 68826.2569 | 4617.88 | [5 empty] | N | EC01G | 100%
401293 | Whitehillocks East - DW5 Iron and Manganese Distribution WQ Improvements | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-10-05 | 2010-10-05 | 2011-02-01 | 2014-02-21 | 2014-03-28 | Angus | 9573350 | 0 | 77571 | 35856.42 | 0 | 0 | 0 | 0 | 113427.42 | 0 | 0 | 0 | 9686777.42 | 0 | 0 | 0 | 0 | 9686777.42 | 311236.79 | [5 empty] | N | CM_WSI | 1% | DW5 | 99%
401294 | Whitehillocks West - DW5 Iron and Manganese Distribution WQ Improvements | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-22 | 2010-09-22 | 2011-02-01 | 2014-11-24 | 2015-03-17 | Angus | 7308600.95 | 0 | 156462.05 | 13190.64 | 0 | 0 | 0 | 0 | 169652.69 | 0 | 0 | 0 | 7478253.64 | 0 | 0 | 0 | 0 | 7478253.64 | 311236.79 | [5 empty] | N | CM_WSI | 13% | DW5 | 87%
500023 | Whitehillocks WOA Morphie WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-13 | 2016-09-12 | 2016-10-31 | 2018-01-26 |  | Aberdeenshire | 0 | 0 | 44644 | 439358 | -93806.51 | 75586.42 | -13723.53 | 0 | 452058.38 | 0 | 0 | 0 | 452058.38 | 0 | 0 | 0 | 0 | 452058.38 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500022 | Whitehillocks WOA Westhills WSZ | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-09 | 2016-09-12 | 2017-06-26 | 2018-03-29 |  | Aberdeenshire | 0 | 0 | 54300 | 68457 | 244187 | 30983.4 | -21426.31 | 12022.69 | 388523.79 | 0 | 0 | 0 | 388523.79 | 0 | 0 | 0 | 0 | 388523.79 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502204 | Whitehillocks WTW - Causeywell SR | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS5 | 2016-03-24 | 2016-07-06 | 2016-07-06 | 2019-09-30 | 2019-09-30 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 275.41 | 0 | 275.41 | 0 | 0 | 0 | 275.41 | 0 | 0 | 0 | 0 | 275.41 | 1207597.94 | [5 empty] | Y | DW25T | 100% | [22 empty] | 1 | [44 empty] | 0
501232 | Whitehillocks WTW - Quality and CM | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | NONINF | DWQ Reliability | MS3 | 2016-03-31 | 2018-08-29 | 2018-09-07 |  | 2022-07-19 | Angus | 0 | 0 | 41788.23 | 395068.88 | 366498.44 | 3637769.78 | 4180968.47 | 1661103.2 | 10283197 | 961216 | 842601.945 | 2056434.4167 | 11244413 | 1213832.4717 | 0 | 154939.4367 | 1368771.9084 | 12613184.9084 | 2534218.47 | [5 empty] | Y | CM_WSNI | 12.34% | DW25P | 43.83% | DW25T | 43.83% | [17 empty] | 1 | [45 empty] | 0
502194 | Whitehillocks WTW - Water Quality Instruments | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | SWD | DWQ Reliability | MS4 | 2016-03-22 | 2016-03-30 | 2016-03-30 | 2016-03-31 |  | Angus | 0 | 0 | 0 | 0 | 162.6 | 0 | 1496 | 0 | 1658.6 | -1496 | -1496 | -2076.7027 | 162.6 | -580.7027 | 0 | 0 | -580.7027 | -418.1027 | 1207597.94 | [5 empty] | Y | DW25P | 100% | [67 empty] | 0
45613 | Whitehillocks WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2011-05-23 | 2011-05-23 | 2013-05-01 | 2013-12-30 | Angus | 584561.51 | 0 | 508.39 | 0 | 0 | 0 | 0 | 0 | 508.39 | 0 | 0 | 0 | 585069.9 | 0 | 0 | 0 | 0 | 585069.9 | 28761.13 | [5 empty] | N | DW1A | 100%
501220 | Whitehills 1 & 2 TWP | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2016-07-13 | 2018-08-01 | 2018-08-21 | 2020-09-28 |  | Fife | 0 | 0 | 14503.9 | 99600.94 | 236358.28 | 689280.42 | 1006258.49 | 265397.97 | 2311400 | 15400 | 0 | 0 | 2326800 | 0 | 0 | 0 | 0 | 2326800 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509128 | Whitehouse DSR Rationalisation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-06-21 | 2023-08-07 | 2023-11-08 | 2024-10-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2542.33 | 2542.33 | 258120.68 | 0 | 0 | 260663 | 0 | 0 | 0 | 0 | 260663 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
502899 | Whitelaw Drive Bathgate_Sewer rehab | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-09-13 | 2017-09-13 | 2017-11-13 | 2018-06-20 |  | West Lothian | 0 | 0 | 0 | 0 | 493590.4 | -44372.64 | 249.45 | 134.42 | 449601.63 | 0 | 0 | 0 | 449601.63 | 0 | 0 | 0 | 0 | 449601.63 | 209381.79 | [5 empty] | N | CM_WWI | 100%
403601 | Whiteside Cottages Bathgate | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2013-10-23 | 2019-09-06 | 2020-02-21 | 2019-09-12 | 2019-09-12 | West Lothian | 56898.06 | 56898.06 | 65132.94 | 10973 | 47226.03 | 41769.97 | -159235.69 | 0 | 5866.25 | 0 | 0 | 0 | 62764.31 | 0 | 0 | 0 | 0 | 62764.31 | 180449.74 | [5 empty] | N | FL_DD | 100%
402697 | Wholesale Data Improvement - Assurance Framework | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2012-06-12 | 2015-05-12 | 2015-05-12 | 2015-03-31 |  | Scottish Water Wide | 283342.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283342.07 | 0 | 0 | 0 | 0 | 283342.07 | 0 | [6 empty] | CS20 | 100%
503262 | Wigtown ST - Investigation and Scope Definition for Potential Growth Project post 2021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2027-09-02 | 2029-02-21 | 2029-06-15 | 2030-06-12 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 77306.64 | 5698.35 | 0.01 | 83005 | 0 | 0 | 0 | 83005 | 0 | 0 | 0 | 0 | 83005 | 122419.09 | [5 empty] | N | SG1 | 100%
500222 | Willowgate RM Perth Railway Bridge | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-03-24 | 2016-08-04 | 2016-09-26 | 2018-04-30 |  | Perth and Kinross | 0 | 0 | 89000 | 1291473 | 514159 | 68886 | 0 | -16969.39 | 1946548.61 | 0 | 0 | 0 | 1946548.61 | 0 | 0 | 0 | 0 | 1946548.61 | 209381.79 | [5 empty] | N | CM_WWI | 100%
402991 | Wilson Street Candleriggs Glasgow | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2013-03-15 | 2013-06-05 | 2013-10-25 | 2013-10-25 | Glasgow City | 47367 | 0 | -264.19 | 0 | 0 | 0 | 0 | 0 | -264.19 | 0 | 0 | 0 | 47102.81 | 0 | 0 | 0 | 0 | 47102.81 | 209381.79 | [5 empty] | N | CM_WWI | 40% | CS11A | 60%
506423 | WIN10 Discovery | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS2 | 2020-10-13 | 2020-10-13 | 2022-03-14 | 2023-11-06 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_M&G | 100%
403967 | Winchburgh WwTW - Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS1 | 2018-11-07 | 2021-07-26 | 2021-09-21 | 2024-04-29 |  | West Lothian | 13556.56 | 0 | 21856.44 | 16739.8 | 46917.59 | 134030.92 | 1329543.5 | 1956802.51 | 3505890.76 | 30774552.68 | 0 | 0 | 34294000 | 0 | 0 | 0 | 0 | 34294000 | 0 | [5 empty] | N | SG1 | 100%
503045 | Winchburgh WwTW - Growth Intermediate Solution Support | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2020-01-24 | 2020-03-31 | 2020-02-25 | 2021-07-02 |  | West Lothian | 0 | 0 | 0 | 0 | 41883.58 | 12804.58 | 1958265.4 | 1874511.61 | 3887465.17 | 501472.78 | 0 | 0 | 4388937.95 | 0 | 0 | -42.95 | -42.95 | 4388895 | 122419.09 | [5 empty] | N | SG1 | 100%
503125 | Winchburgh WwTW - Growth Support for SAF Package Plant | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-03-30 | 2018-03-30 | 2018-05-09 | 2020-06-24 |  | West Lothian | 0 | 0 | 0 | 0 | 40000 | 408131.83 | 0 | 0 | 448131.83 | 0 | 0 | 0 | 448131.83 | 0 | 0 | 0 | 0 | 448131.83 | 122419.09 | [5 empty] | N | SG1 | 100%
506896 | Windows 10 Upgrade | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2020-06-02 | 2020-08-31 | 2020-09-01 | 2021-09-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8716513 | 8716513 | 1200737.41 | 0 | 0 | 9917250.41 | 0 | 0 | 793380.0328 | 793380.0328 | 10710630.4428 | 613322.63 | [5 empty] | N | CM_M&G | 100%
403866 | Windows Server Decommission | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-09-05 | 2014-09-05 | 2014-10-01 | 2014-12-18 |  | Scottish Water Wide | 152356 | 0 | 5942.82 | 0 | 0 | 0 | 0 | 0 | 5942.82 | 0 | 0 | 0 | 158298.82 | 0 | 0 | 0 | 0 | 158298.82 | 613322.63 | [5 empty] | N | CM_M&G | 100%
501756 | Windyfield Rhynie DSR Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2027-11-08 | 2029-01-19 | 2029-05-24 | 2030-01-02 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699999.94 | 0 | 0 | 699999.94 | 0 | 0 | 0 | 0 | 699999.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
45027 | Windyfield Rhynie WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-03-29 | 2011-08-29 | 2013-02-28 | 2013-03-18 | Aberdeenshire | 1636912.53 | 0 | -93.97 | 0 | 0 | 0 | 0 | 0 | -93.97 | 0 | 0 | 0 | 1636818.56 | 0 | 0 | 0 | 0 | 1636818.56 | 28761.13 | [5 empty] | N | DW23 | 100%
49609 | WINF - Investment Profile Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | Water |  | SWD | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | RISK | 100%
506338 | Winterhope DIR Spillway Drainage Improvements | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS2 |  | 2020-09-24 | 2021-06-16 | 2022-01-26 | 2022-01-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39330.08 | 39330.08 | 40733.59 | 40733.59 | 56545.1576 | 80063.67 | 15811.5676 | 0 | 0 | 15811.5676 | 95875.2376 | 2601944.88 | [5 empty] | N | CS22 | 100%
510145 | Winterhope WOA - Falford River Emergency Bridge Crossing | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-12-11 | 2021-07-12 | 2022-02-02 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23154 | 23154 | 46845.9 | 0 | 0 | 69999.9 | 0 | 0 | 0 | 0 | 69999.9 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503050 | Wishaw TM Water Quality | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2020-08-31 | 2021-09-13 | 2021-11-24 | 2022-12-19 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 27397.67 | 11643.16 | 26409.17 | 165828.42 | 231278.42 | 968721.58 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501204 | WISTON TWP NS957319 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-11-06 | 2016-09-30 | 2016-11-21 | 2019-03-15 |  | South Lanarkshire | 0 | 0 | 1415.44 | 87098.37 | 130707.33 | 126394 | 11100 | 3395.86 | 360111 | 603.75 | 0 | 0 | 360714.75 | 0 | 0 | 0 | 0 | 360714.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501004 | WMS Data Inclusion on Schematics | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-09-25 | 2015-11-18 | 2016-02-18 | 2018-04-18 |  | Scottish Water Wide | 0 | 0 | 26721 | 49408 | 43204.03 | 0 | 0 | 0 | 119333.03 | 0 | 0 | 0 | 119333.03 | 0 | 0 | 0 | 0 | 119333.03 | 613322.63 | [5 empty] | N | CM_WWNI | 20% | CM_WSNI | 80%
505804 | W-N-NI-180320-Stornoway WOA- DOMS Store | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-03-24 |  | 2020-07-31 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 3300 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504965 | W-N-NI-310120-Drumbeg WTW- PLC Spare | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-05 |  | 2020-03-28 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 1195 | 0 | 1195 | 0 | 0 | 0 | 1195 | 0 | 0 | 0 | 0 | 1195 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
401091 | WOA000168 Glenconvinth Mains Rehab 2 WSZs Balnain Buntait and Kirkhill | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2012-03-27 | 2012-06-14 | 2013-10-09 |  | Highland | 416635 | 0 | -172.18 | 0 | 0 | 0 | 0 | 0 | -172.18 | 0 | 0 | 0 | 416462.82 | 0 | 0 | 0 | 0 | 416462.82 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401309 | WOA000257 Marchbank 3 schemes within 3 DMAs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2013-01-11 | 2013-02-12 | 2015-04-03 |  | City of Edinburgh | 1204188 | 0 | 84008 | 703.93 | -892.04 | 0 | 0 | 0 | 83819.89 | 0 | 0 | 0 | 1288007.89 | 0 | 0 | 0 | 0 | 1288007.89 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401144 | WOA000332 South Uist WSZ001378 Isle of South Uist UITS | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-10-17 | 2012-11-22 | 2012-12-17 | 2013-10-01 |  | Na H-Eileanan an Iar | 689000 | 0 | -9347.8 | 0 | 0 | 0 | 0 | 0 | -9347.8 | 0 | 0 | 0 | 679652.2 | 0 | 0 | 0 | 0 | 679652.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401099 | WOA000341 Storr Forest Achachork DMA Torvaig Mains Rehab | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-06-28 | 2012-02-22 | 2012-03-26 | 2013-08-20 |  | Highland | 300712.66 | 0 | 109.39 | 0 | 0 | 0 | 0 | 0 | 109.39 | 0 | 0 | 0 | 300822.05 | 0 | 0 | 0 | 0 | 300822.05 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401145 | WOA000360 Tiree 2 Schemes Within Tiree DMA | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2012-04-24 | 2012-07-23 | 2013-03-20 |  | Argyll and Bute-North Argyll | 872842 | 0 | 74.54 | 0 | 0 | 0 | 0 | 0 | 74.54 | 0 | 0 | 0 | 872916.54 | 0 | 0 | 0 | 0 | 872916.54 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401100 | WOA000372 Tullich 8 schemes in 7 DMAs within Oban North and Oban South WSZs | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2012-04-23 | 2012-08-27 | 2013-01-25 |  | Argyll and Bute-North Argyll | 457000 | 0 | -1470.72 | 0 | 0 | 0 | 0 | 0 | -1470.72 | 0 | 0 | 0 | 455529.28 | 0 | 0 | 0 | 0 | 455529.28 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401142 | WOA000396 Assynt and Newmore WOA 2 Schemes At Nigg and Shandwick | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2013-12-16 | 2014-01-31 | 2015-09-21 |  | Highland | 662164 | 0 | 184623 | 3976.26 | 9908.94 | 0 | 0 | 0 | 198508.2 | 0 | 0 | 0 | 860672.2 | 0 | 0 | 0 | 0 | 860672.2 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504211 | Woodbush SPS - Screen Refurb + pump lift operation | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 |  | 2020-06-29 |  | 2021-03-10 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 8000.01 | 0 | 0 | 10000.01 | 0 | 0 | 0 | 0 | 10000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509727 | Woodbush SPS site refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 | 2020-11-20 | 2020-11-20 | 2021-11-03 | 2023-06-28 |  | East Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84271 | 84271 | 565879.91 | 0 | 0 | 650150.91 | 0 | 0 | 0 | 0 | 650150.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
501734 | Woodhead DSR Mainout | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2028-07-24 | 2029-05-09 | 2029-09-12 | 2030-01-22 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000.03 | 0 | 0 | 100000.03 | 0 | 0 | 0 | 0 | 100000.03 | 4989107.96 | [5 empty] | N | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 28.57% | CM_WSI | 47.62%
501076 | Woodside Drive Calderbank | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-11-18 | 2018-04-30 | 2018-06-18 | 2020-02-19 |  | North Lanarkshire | 0 | 0 | 11437.38 | 69577.74 | 204005.88 | 1604185.1 | 748590.9 | 4953 | 2642750 | 2250 | 0 | 0 | 2645000 | 0 | 0 | 0 | 0 | 2645000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511537 | Woodside Turriff - IoS Drainage Works | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 |  | 2021-07-05 | 2021-09-24 | 2022-05-09 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000.04 | 0 | 0 | 50000.04 | 0 | 0 | 0 | 0 | 50000.04 | 311236.79 | [5 empty] | N | CM_WSI | 100%
500943 | Work Scheduling and Field Services Refresh | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-03-30 | 2016-09-23 | 2016-09-23 | 2018-07-25 |  | Scottish Water Wide | 0 | 0 | 514927 | 1576193.02 | 710046.44 | 321985.2 | 0 | 0 | 3123151.66 | 0 | 0 | 0 | 3123151.66 | 0 | 0 | 0 | 0 | 3123151.66 | 613322.63 | [5 empty] | N | CM_M&G | 100%
500622 | Workplace & Property Management SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 2526708 | 3693138.99 | 2362727.21 | 2082201.71 | 2319851.16 | 1916261.64 | 14900888.71 | 0 | 0 | 0 | 14900888.71 | 0 | 0 | 0 | 0 | 14900888.71 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500977 | Wormit Outfall Repairs | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-11-21 | 2017-06-27 | 2017-06-27 | 2017-06-28 |  | Fife | 0 | 0 | 0 | 2106 | 190.63 | 140.65 | -139.32 | 0 | 2297.96 | 0 | 0 | 0 | 2297.96 | 0 | 0 | 0 | 0 | 2297.96 | 209381.79 | [5 empty] | N | CM_WWI | 100%
502611 | Wormit- Removal of Raw Discharges Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater | SEPA | SWMD | Environmental Studies | MS7 | 2017-02-28 | 2017-10-26 | 2017-12-12 | 2018-08-31 | 2018-11-30 | Fife | 0 | 0 | 0 | 657.01 | 15242.99 | 18986.97 | 0 | 0 | 34886.97 | 0 | 0 | 0 | 34886.97 | 0 | 0 | 0 | 0 | 34886.97 | 203233.4 | [5 empty] | Y | EC01D | 100% | [40 empty] | 1 | [26 empty] | 0
404063 | WQ Improvement Yr5 - Fetler RO | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-01-15 | 2015-10-21 | 2015-11-27 | 2016-03-29 |  | Scottish Water Wide | 10099 | 0 | 664525 | 25629.24 | 0 | 0 | 0 | 0 | 690154.24 | 0 | 0 | 0 | 700253.24 | 0 | 0 | 0 | 0 | 700253.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404062 | WQ Improvement Yr5 - Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2015-10-27 |  | Scottish Water Wide | 110165 | 0 | 888.73 | 0 | 0 | 0 | 0 | 0 | 888.73 | 0 | 0 | 0 | 111053.73 | 0 | 0 | 0 | 0 | 111053.73 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404055 | WQ Improvement Yr5 - Tomnavoulin WTW - UV Treatment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-01-15 | 2015-08-27 | 2015-10-05 | 2015-10-20 |  | Scottish Water Wide | 4377 | 0 | 19685.84 | 0 | 0 | 0 | 0 | 0 | 19685.84 | 0 | 0 | 0 | 24062.84 | 0 | 0 | 0 | 0 | 24062.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404058 | WQ Improvements 14-15 - Non Inf SV - Man Del | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-12 | 2014-12-12 | 2015-04-14 | 2016-02-08 |  | Scottish Water Wide | 18395.68 | 0 | 318597.82 | 1656.13 | 301.35 | 0 | 0 | 0 | 320555.3 | 0 | 0 | 0 | 338950.98 | 0 | 0 | 0 | 0 | 338950.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404101 | WQ Improvements 14-15 Man Del Membrane Installation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-02-19 | 2015-02-19 | 2015-04-14 | 2015-10-01 |  | Scottish Water Wide | 1624583 | 0 | 298217 | -429.35 | 0 | 0 | 0 | 0 | 297787.65 | 0 | 0 | 0 | 1922370.65 | 0 | 0 | 0 | 0 | 1922370.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404064 | WQ Improvements Yr5 - Inf Flushing SWD | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2015-11-09 |  | Scottish Water Wide | 26712 | 0 | 564996.65 | 0 | 0 | 0 | 0 | 0 | 564996.65 | 0 | 0 | 0 | 591708.65 | 0 | 0 | 0 | 0 | 591708.65 | 311236.79 | [5 empty] | N | CM_WSI | 100%
404060 | WQ Improvements Yr5 - Membrane GAC Polishing Filters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2015-04-13 | 2016-01-11 |  | Scottish Water Wide | 440824.14 | 0 | 541936.76 | 0 | 0 | 0 | 0 | 0 | 541936.76 | 0 | 0 | 0 | 982760.9 | 0 | 0 | 0 | 0 | 982760.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404057 | WQ Improvements Yr5 - Non Inf Quick Hits - SWD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2018-04-25 |  | Scottish Water Wide | 3761294.75 | 0 | 1535056.25 | 452538.1 | 72321.63 | 0 | 0 | 0 | 2059915.98 | 0 | 0 | 0 | 5821210.73 | 0 | 0 | 0 | 0 | 5821210.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404084 | WQ Improvements Yr5 - South Area SRs - SWD | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2015-11-12 |  | Scottish Water Wide | 46750.25 | 0 | 168197.1 | 0 | 0 | 0 | 0 | 0 | 168197.1 | 0 | 0 | 0 | 214947.35 | 0 | 0 | 0 | 0 | 214947.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404059 | WQ Improvements Yr5 - SR Repair Programme - Man Del | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2015-02-02 | 2017-02-23 |  | Scottish Water Wide | 743945 | 0 | 2312328 | 297662.03 | 155792.09 | 3792.07 | 0 | 0 | 2769574.19 | 0 | 0 | 0 | 3513519.19 | 0 | 0 | 0 | 0 | 3513519.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
404065 | WQ Improvements Yr5 - Tullich WTW - Chloramination | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-01-21 | 2015-09-07 | 2016-01-12 | 2016-02-15 |  | Scottish Water Wide | 19710 | 0 | 47808.21 | 17.75 | 335.81 | 0 | 0 | 0 | 48161.77 | 0 | 0 | 0 | 67871.77 | 0 | 0 | 0 | 0 | 67871.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506728 | WQ Mains Rehabilitation Ph 1 (MA2b) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-05-31 | 2021-06-07 | 2021-10-06 | 2022-04-06 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12988.85 | 12988.85 | 22317.81 | 0 | 0 | 35306.66 | 0 | 0 | 0 | 0 | 35306.66 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507475 | WQ Mains Rehabilitation Ph 1 MA2b - PLAN | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW2 | 2022-05-06 | 2024-03-22 | 2024-08-30 | 2026-03-13 | 2026-06-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91245.5 | 91245.5 | 148754.5 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | [5 empty] | N | SR21_SS | 100%
507488 | WQ Mains Rehabilitation Ph 1 MA2b DELIVERY | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | WINF | SR21 Early Start | MS3 | 2020-11-26 | 2020-12-21 | 2021-01-05 | 2023-12-21 | 2024-03-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765138 | 765138 | 3114861.64 | 0 | 0 | 3879999.64 | 0 | 0 | 0 | 0 | 3879999.64 | 0 | [5 empty] | N | SR21_SS | 100%
403792 | WQ OPA - Automatic Coagulation Control - Delivery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-05-09 | 2014-08-25 | 2014-10-31 | 2015-10-16 |  | Scottish Water Wide | 225271 | 0 | 42409.77 | 0 | 0 | 0 | 0 | 0 | 42409.77 | 0 | 0 | 0 | 267680.77 | 0 | 0 | 0 | 0 | 267680.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403906 | WQ OPA Ardrishaig Raw Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-08-15 | 2014-10-01 | 2014-10-20 | 2015-04-10 |  | Argyll and Bute-Cowal & Bute | 165023 | 0 | 55395 | -0.1 | -9182.26 | 0 | 0 | 0 | 46212.64 | 0 | 0 | 0 | 211235.64 | 0 | 0 | 0 | 0 | 211235.64 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403793 | WQ OPA GAC Polishing Filters Year 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-05-09 | 2014-07-30 | 2014-08-01 | 2015-03-27 |  | Scottish Water Wide | 286638 | 0 | 1819.36 | 0 | 0 | 0 | 0 | 0 | 1819.36 | 0 | 0 | 0 | 288457.36 | 0 | 0 | 0 | 0 | 288457.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403789 | WQ OPA Network Flushing Teams Year 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-05-19 | 2014-06-25 | 2014-06-25 | 2015-09-10 |  | Scottish Water Wide | 1692101.66 | 0 | 6839.77 | 0 | 0 | 0 | 0 | 0 | 6839.77 | 0 | 0 | 0 | 1698941.43 | 0 | 0 | 0 | 0 | 1698941.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403472 | WQ OPA Network Interventions | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-05-20 | 2013-08-20 | 2013-10-01 | 2015-02-27 |  | Scottish Water Wide | 1133759.34 | 0 | 717.5 | 0 | 0 | 0 | 0 | 0 | 717.5 | 0 | 0 | 0 | 1134476.84 | 0 | 0 | 0 | 0 | 1134476.84 | 311236.79 | [5 empty] | N | CM_WSI | 100%
403790 | WQ OPA Process Science Teams Year 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-02 | 2014-06-23 | 2014-06-23 | 2015-10-30 |  | Scottish Water Wide | 654159.4 | 0 | 3903.23 | 0 | 0 | 0 | 0 | 0 | 3903.23 | 0 | 0 | 0 | 658062.63 | 0 | 0 | 0 | 0 | 658062.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403469 | WQ OPA SR Repair Programme Phase 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-05-13 | 2013-08-20 | 2013-10-17 | 2016-03-30 |  | Argyll and Bute-North Argyll | 4155573 | 0 | 104400 | 15379.12 | 18308.86 | 32164.82 | 0 | 0 | 170252.8 | 0 | 0 | 0 | 4325825.8 | 0 | 0 | 0 | 0 | 4325825.8 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
403317 | WQ OPA THM issues - Chloramination at Western Isles Sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-02 | 2013-04-02 | 2013-05-15 | 2014-11-03 |  | Na H-Eileanan an Iar | 1713029.62 | 0 | -25240.62 | -962.34 | 0 | 0 | 0 | 0 | -26202.96 | 0 | 0 | 0 | 1686826.66 | 0 | 0 | 0 | 0 | 1686826.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507574 | WQ Responsive Mains Cleaning Ph 1 MA2b_Delivery | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW2 | 2021-09-14 | 2024-01-25 | 2024-04-19 | 2026-09-11 | 2028-01-13 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.68 | 10.68 | 6363188.86 | 0 | 0 | 6363199.54 | 0 | 0 | 0 | 0 | 6363199.54 | 0 | [5 empty] | N | SR21_SS | 100%
507575 | WQ Responsive Mains Cleaning Ph 1 MA2b_Plan | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | SR21 Early Start | GW2 | 2023-03-09 | 2025-01-22 | 2025-07-02 | 2027-01-13 | 2027-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37458.72 | 37458.72 | 159341.18 | 0 | 0 | 196799.9 | 0 | 0 | 0 | 0 | 196799.9 | 0 | [5 empty] | N | SR21_SS | 100%
500606 | WSS Cost Intelligence SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 2789761.75 | 2292183.51 | 1719779.24 | 1766143.51 | 1147930.79 | 487968.32 | 10203767.13 | 0 | 0 | 0 | 10203767.13 | 0 | 0 | 0 | 0 | 10203767.13 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500619 | WSS Investment Planning SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 138481.55 | 1311142.71 | 1277003.27 | 1284591.45 | 518467.77 | 87164.28 | 4616851.03 | 0 | 0 | 0 | 4616851.03 | 0 | 0 | 0 | 0 | 4616851.03 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500618 | WSS Public Health & Water Quality SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 44992.24 | 37689.53 | 169574.08 | 355933.1 | 54250.19 | 17352.74 | 679791.88 | 0 | 0 | 0 | 679791.88 | 0 | 0 | 0 | 0 | 679791.88 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500617 | WSS Reservoir Planning SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 21249.19 | 38170.9 | 143819.14 | 196159.95 | 169986.1 | 196979.8 | 766365.08 | 0 | 0 | 0 | 766365.08 | 0 | 0 | 0 | 0 | 766365.08 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500616 | WSS Supply Demand Balance SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 48698.95 | 95837.94 | 305394.7 | 312064.75 | 121274.65 | 225417.93 | 1108688.92 | 0 | 0 | 0 | 1108688.92 | 0 | 0 | 0 | 0 | 1108688.92 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500615 | WSS Water Risk Lifecycle Planning SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 524767.27 | 1208106.89 | 1959818.44 | 1646061.85 | 1725477 | 1073851.61 | 8138083.06 | 0 | 0 | 0 | 8138083.06 | 0 | 0 | 0 | 0 | 8138083.06 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500614 | WSS Water Service Strategy SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 355193.26 | 1265242.67 | 1613363.54 | 1280316.44 | 162218.53 | 378954.19 | 5055288.63 | 0 | 0 | 0 | 5055288.63 | 0 | 0 | 0 | 0 | 5055288.63 | 306661.32 | [5 empty] | N | CM_OVH | 100%
401433 | WSZ000107 Badentinan WSZ Mains Rehabilitation Iron Failures | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-01-11 | 2012-10-30 | 2012-12-17 | 2013-06-24 |  | Moray | 343845 | 0 | -2850.22 | 0 | 0 | 0 | 0 | 0 | -2850.22 | 0 | 0 | 0 | 340994.78 | 0 | 0 | 0 | 0 | 340994.78 | 311236.79 | [5 empty] | N | CM_WSI | 100%
34916 | WSZ000337-Carnbee WSZ-Crail to St Andrews AC Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2006-11-23 | 2008-07-31 | 2008-09-18 | 2009-04-24 |  | Fife | 1561034 | 0 | 8129 | 100696.99 | -31822.33 | 0 | 0 | 0 | 77003.66 | 0 | 0 | 0 | 1638037.66 | 0 | 0 | 0 | 0 | 1638037.66 | 311236.79 | [5 empty] | N | WSI | 100%
402356 | WSZ000346 - Carse of Gowrie WSZ - Re-hab of 9inch A.C. Water Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-11-21 | 2012-12-19 | 2012-12-10 | 2014-09-01 |  | Perth and Kinross | 474225.93 | 0 | 3472.34 | 0 | 0 | 0 | 0 | 0 | 3472.34 | 0 | 0 | 0 | 477698.27 | 0 | 0 | 0 | 0 | 477698.27 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402495 | WSZ000356 - Catterthun WSZ Hot Spot - Mains Re-habilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-01-30 | 2013-07-29 | 2013-10-21 | 2014-08-01 |  | Angus | 293796 | 0 | 0 | -3000.98 | 0 | 0 | 0 | 0 | -3000.98 | 0 | 0 | 0 | 290795.02 | 0 | 0 | 0 | 0 | 290795.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
402045 | WSZ000447 Crombie WSZ Mains Rehabilitation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-29 | 2013-06-13 | 2013-06-18 | 2014-08-01 |  | Angus | 149226 | 0 | 55 | -17.01 | 0 | 0 | 0 | 0 | 37.99 | 0 | 0 | 0 | 149263.99 | 0 | 0 | 0 | 0 | 149263.99 | 311236.79 | [5 empty] | N | CM_WSI | 100%
401557 | WSZ001578 Whiteness and Weisdale Mains Renewal | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-11-30 | 2013-09-25 | 2013-10-28 | 2014-12-11 |  | Shetland Islands | 633239.56 | 0 | 3642.44 | 1997.49 | 0 | 0 | 0 | 0 | 5639.93 | 0 | 0 | 0 | 638879.49 | 0 | 0 | 0 | 0 | 638879.49 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503104 | WTW Performance enhancement plans (WTW PEP) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-04-27 | 2018-04-27 | 2018-05-01 | 2021-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 147232.03 | 106358.25 | 246409.72 | 500000 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501338 | WTW000067 - COULTER WTW 2001 NT035276 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-01-26 | 2020-09-16 | 2021-01-29 | 2021-01-29 |  | South Lanarkshire | 0 | 0 | 0 | 4796.35 | 0 | 1206.2 | 31.41 | -5472.69 | 561.27 | 0 | 0 | 0 | 561.27 | 0 | 0 | 0 | 0 | 561.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
500981 | WTW000078 - DAER WTW 1956 NS978092 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 | 2015-10-23 | 2020-09-04 | 2020-12-11 | 2020-12-11 |  | South Lanarkshire | 0 | 0 | 24168 | 140955.64 | 20239.45 | -4796.09 | 0 | -10412 | 170155 | 0 | 0 | 0 | 170155 | 0 | 0 | 0 | 0 | 170155 | 311236.79 | [5 empty] | N | CM_WSI | 100%
501332 | WTW000233 - SOUTH MOORHOUSE WTW 1995 NS526511 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2027-11-12 | 2028-08-10 | 2028-12-14 | 2029-04-25 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000.02 | 0 | 0 | 100000.02 | 0 | 0 | 0 | 0 | 100000.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501403 | WTW000476 - SPEY BADENTINAN WTW 1994 NJ282568 - CM | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2027-12-09 | 2028-12-20 | 2029-04-25 | 2029-12-10 |  | Moray | 0 | 0 | 5023.26 | 0 | 0 | 0 | 830.16 | -830.16 | 5023.26 | 405814.58 | 0 | 0 | 410837.84 | 0 | 0 | 0 | 0 | 410837.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402093 | WTW000515 Forehill WTW Pesticide Removal Stage | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2011-05-23 | 2012-03-27 | 2013-01-14 | 2014-11-13 | 2014-12-03 | Aberdeenshire | 7799342.91 | 0 | 194928.19 | 119.66 | 0 | 0 | 0 | 0 | 195047.85 | 0 | 0 | 0 | 7994390.76 | 0 | 0 | 0 | 0 | 7994390.76 | 0 |  |  |  |  | 48825.5237 | N | DW3H | 100%
501388 | WTW000626 - PATESHILL WTW NS983595 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2017-08-28 | 2020-09-30 | 2020-09-28 | 2022-01-31 |  | West Lothian | 0 | 0 | 0 | 92411.23 | 149801.73 | 342302.04 | 431739.79 | 1867654.65 | 2883909.44 | 1736053 | 0 | 0 | 4619962.44 | 0 | 0 | 380037.56 | 380037.56 | 5000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501390 | WTW000627 - ROSEBERY WTW 1940 NT305570 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-11-17 | 2019-07-31 | 2019-08-30 | 2022-11-10 |  | Midlothian | 0 | 0 | 0 | 101941.76 | 802311.59 | 792354.21 | 2474013.46 | 1725982.98 | 5896604 | 9449720.1 | 0 | 0 | 15346324.1 | 0 | 0 | 2153675.9 | 2153675.9 | 17500000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501382 | WTW000628 - CASTLE MOFFAT WTW 1974 NT600697 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2020-09-04 | 2020-09-04 | 2021-07-02 | 2022-09-29 |  | East Lothian | 0 | 0 | 0 | 50145.3 | 46429.81 | 135995.99 | 11883.32 | 2766.6 | 247221.01 | 24779.46 | 0 | 0 | 272000.47 | 0 | 0 | 0 | 0 | 272000.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501379 | WTW000640 - MARCHBANK WTW NT165645 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2017-03-31 | 2021-03-23 | 2021-03-22 | 2022-09-29 |  | City of Edinburgh | 0 | 0 | 0 | 48016.79 | 221595.61 | 71804 | 375136.6 | 1462300.36 | 2178853.36 | 2011440 | 0 | 0 | 4190293.36 | 0 | 0 | 335223.4688 | 335223.4688 | 4525516.8288 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
501393 | WTW000712 - HOWDEN WTW NT456275 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2017-08-29 | 2020-02-28 | 2020-02-28 | 2022-05-30 |  | Scottish Borders | 0 | 0 | 0 | 66797.3 | 470262.27 | 345056.17 | 1496678.58 | 2058231.4 | 4437025.72 | 3975461 | 0 | 0 | 8412486.72 | 0 | 0 | 1587513.28 | 1587513.28 | 10000000 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
402692 | WTW500064331 Craighead WTW - Rebuild | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-20 | 2014-10-01 | 2014-10-01 | 2014-10-21 | 2014-10-01 | Aberdeenshire | 255864.54 | 0 | -5230.71 | 0 | 0 | 0 | 0 | 0 | -5230.71 | 0 | 0 | 0 | 250633.83 | 0 | 0 | 0 | 0 | 250633.83 | 119022.58 | [5 empty] | N | DW3C | 30% | CM_WSNI | 70%
34885 | WW Infra Cap Maint Hotspots - Tranche 10 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2006-12-14 | 2008-05-28 | 2008-06-23 | 2015-03-04 |  | Scottish Water Wide | 393500 | 0 | -797.71 | 0 | 0 | 0 | 0 | 0 | -797.71 | 0 | 0 | 0 | 392702.29 | 0 | 0 | 0 | 0 | 392702.29 | 209381.79 | [5 empty] | N | WWI | 100%
500611 | WW Service Strategy GM SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 80775.91 | 739686.47 | 1090212.41 | 1349659.41 | 1160672.68 | 979252.79 | 5400259.67 | 0 | 0 | 0 | 5400259.67 | 0 | 0 | 0 | 0 | 5400259.67 | 306661.32 | [5 empty] | N | CM_OVH | 100%
502256 | WW SR15 Temporary Chemical Dosing Upgrade Programme- Phase 1 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2016-07-29 | 2019-03-29 | 2019-03-29 | 2024-09-16 |  | Scottish Water Wide | 0 | 0 | 0 | 67229.35 | 93820.65 | 549394.14 | 314791.74 | 1192303.96 | 2217539.84 | 1759281.88 | 0 | 0 | 3976821.72 | 0 | 0 | 0 | 0 | 3976821.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502300 | WW SR15 Temporary Chemical Dosing Upgrade Programme- Phase 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2017-08-16 | 2020-06-06 | 2020-03-24 | 2022-05-04 |  | Scottish Water Wide | 0 | 0 | 0 | 32283.07 | 29669.36 | 240555.93 | 140499.94 | 102234.7 | 545243 | 1125340.32 | 0 | 0 | 1670583.32 | 0 | 0 | 0 | 0 | 1670583.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
502301 | WW SR15 Temporary Chemical Dosing Upgrade Programme- Phase 3 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2017-11-27 | 2020-03-28 | 2020-03-26 | 2021-06-24 |  | Scottish Water Wide | 0 | 0 | 0 | 26294.46 | 10476.84 | 32935.08 | 128187.92 | 43681.71 | 241576 | 551638.1 | 0 | 0 | 793214.1 | 0 | 0 | 0 | 0 | 793214.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506434 | WW SVCD Responsive Y6 Time | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-01 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483139.2 | 483139.2 | 16860.8 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504178 | W-W-051219 Amlaird DAF | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2019-12-09 |  | 2021-07-13 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 66.18 | 11559.19 | 11625.37 | 9396.06 | 0 | 0 | 21021.43 | 0 | 0 | 0 | 0 | 21021.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504183 | W-W-051219 Neilston WTW-H&S Measures Wash Water Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2019-12-09 |  | 2020-08-12 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 24600 | 3195.28 | 27795.28 | 0 | 0 | 0 | 27795.28 | 0 | 0 | 0 | 0 | 27795.28 | 119022.58 | [5 empty] | N | WSNI | 100%
503983 | W-W-261119 Balmore WTW-HV Breaker | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2021-05-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 21699.55 | -19850.93 | 1848.62 | 25914.38 | 0 | 0 | 27763 | 0 | 0 | 0 | 0 | 27763 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506937 | W-W-I-010620 CV WOA Bonny Water | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-06-12 | 2021-05-13 | 2021-11-19 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34316 | 34316 | 83061.69 | 0 | 0 | 117377.69 | 0 | 0 | 0 | 0 | 117377.69 | 311236.79 | [5 empty] | N | CM_M&G | 100%
508060 | W-W-I-050820-RCI Pentland Drive DMA (Bishopbriggs Hotspots) NEW | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-10-22 | 2020-12-08 | 2021-10-22 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22578 | 22578 | 3000 | 0 | 0 | 25578 | 0 | 0 | 0 | 0 | 25578 | 311236.79 | [5 empty] | N | WSI | 100%
511158 | W-W-I-100221-Avondale valve installation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-02-18 | 2021-11-05 | 2022-06-20 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16071.74 | 16071.74 | 254954.22 | 0 | 0 | 271025.96 | 0 | 0 | 0 | 0 | 271025.96 | 311236.79 | [5 empty] | N | CM_WSI | 100%
509221 | W-W-I-121020-Katrine Aqueduct-Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-14 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2642.28 | 2642.28 | 8057.72 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 311236.79 | [5 empty] | N | WSI | 100%
505171 | W-W-I-130220-Milngavie Commissioners Rd PRVs - Peak 42 Modifications | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-02-13 |  | 2020-08-26 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 2665.68 | 8459.42 | 11125.1 | 0 | 0 | 0 | 11125.1 | 0 | 0 | 0 | 0 | 11125.1 | 311236.79 | [5 empty] | N | SR15_CMA_WSI | 100%
505285 | W-W-I-190220-Balmore WestLow Moss Prison - Control Valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2020-02-19 |  | 2020-05-25 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 1295.04 | 4995 | 6290.04 | 0 | 0 | 0 | 6290.04 | 0 | 0 | 0 | 0 | 6290.04 | 311236.79 | [5 empty] | N | WSI | 100%
511356 | W-W-I-190221-Downieston Farm Patna - Mains Diversion | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2021-03-08 | 2021-03-03 | 2021-08-06 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 33000 | 67000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
506724 | W-W-I-200520-Bradan-PRGF 1-8 Filter Nozzle Clean (6th of 8) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-21 |  | 2020-08-11 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30219.08 | 30219.08 | 0 | 0 | 0 | 30219.08 | 0 | 0 | 0 | 0 | 30219.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511387 | WW-I-220221-Grantown_DOA-Sewer PH26 3JU | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-22 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1202.32 | 1202.32 | 1097.68 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510874 | W-W-I-250121-Bardowie Pipebridge - Replacement Grating | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2021-01-25 |  | 2021-05-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152.83 | 152.83 | 1985.04 | 0 | 0 | 2137.87 | 0 | 0 | 0 | 0 | 2137.87 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510902 | W-WI-260121 - Minnoch Crescent 6 Inch Garden Main | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-02-05 | 2022-01-06 | 2022-09-15 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8542 | 8542 | 91458.02 | 0 | 0 | 100000.02 | 0 | 0 | 0 | 0 | 100000.02 | 311236.79 | [5 empty] | N | CM_WSI | 100%
507345 | W-W-I-260620-M5 Restriction Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-06-26 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260.91 | 260.91 | 3515.09 | 0 | 0 | 3776 | 0 | 0 | 0 | 0 | 3776 | 311236.79 | [5 empty] | N | WSI | 100%
505434 | W-W-I-270220-Corrie - Outlet Flow Meter Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7 | 27.7 | 1154.3 | 0 | 0 | 1182 | 0 | 0 | 0 | 0 | 1182 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509655 | W-WI-Harbour Road Contamination Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-12-23 | 2021-10-14 | 2022-05-27 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1105.42 | 1105.42 | 4181.34 | 0 | 0 | 5286.76 | 0 | 0 | 0 | 0 | 5286.76 | 311236.79 | [5 empty] | N | CM_M&G | 100%
49610 | WWINF - Investment Profile Adjustment | Q&S4 | Programme Risk | Enhanced Risk |  |  | Wastewater |  | WWINF | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | RISK | 100%
504320 | W-W-INFRA-121219 - Byrehill VC - H&S Issues | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-12-16 |  | 2020-02-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3504 | -814.41 | 2689.59 | 0 | 0 | 0 | 2689.59 | 0 | 0 | 0 | 0 | 2689.59 | 311236.79 | [5 empty] | N | CM_WSI | 100%
508009 | W-W-NI-0030820-Carron Valley-Emergency lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-10-15 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9924.67 | 9924.67 | 0 | 0 | 0 | 9924.67 | 0 | 0 | 0 | 0 | 9924.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511554 | W-W-NI-010321-Afton-Clarifier Flow Meter Trial | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-03-01 |  | 2021-06-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5411.16 | 0 | 0 | 5411.16 | 0 | 0 | 0 | 0 | 5411.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511535 | W-W-NI-010321-Muirdykes-SRGF Software Modifications | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.38 | 221.38 | 2900.58 | 0 | 0 | 3121.96 | 0 | 0 | 0 | 0 | 3121.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506028 | W-W-NI-010420-Castlemilk - Install VSDs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-03 |  | 2020-06-11 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83170.24 | 83170.24 | 0 | 0 | 0 | 83170.24 | 0 | 0 | 0 | 0 | 83170.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506934 | W-W-NI-010620 Gartcarron CWT 1 Cut and Cap | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-06-12 | 2021-07-01 | 2021-12-03 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6080.53 | 6080.53 | 954.38 | 0 | 0 | 7034.91 | 0 | 0 | 0 | 0 | 7034.91 | 311236.79 | [5 empty] | N | CM_M&G | 100%
507452 | W-W-NI-010720-Picketlaw-Post Contact Static Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-03 |  | 2021-02-10 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16805.65 | 16805.65 | 0 | 0 | 0 | 16805.65 | 0 | 0 | 0 | 0 | 16805.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508526 | W-W-NI-010920-Turret CWT CFD Modelling | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-02 |  | 2020-06-12 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18075.36 | 18075.36 | 10830.65 | 0 | 0 | 28906 | 0 | 0 | 0 | 0 | 28906 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510054 | W-W-NI-011220-Glenhove-Distribution Board | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-04 |  | 2021-03-15 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200.26 | 4200.26 | 0 | 0 | 0 | 4200.26 | 0 | 0 | 0 | 0 | 4200.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510062 | W-W-NI-011220-Strachur-Sample tap and access path improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-04 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052.92 | 1052.92 | 16355.08 | 0 | 0 | 17408 | 0 | 0 | 0 | 0 | 17408 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505482 | W-W-NI-020320-Penwhapple- DAF Recycle Pump C Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-03 |  | 2020-07-23 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2667.9 | -2667.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
511565 | W-W-NI-020321-Bradan-Sludge Thickener Sensing Probe | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-02 |  | 2021-06-02 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.37 | 141.37 | 1852.26 | 0 | 0 | 1993.63 | 0 | 0 | 0 | 0 | 1993.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506063 | W-W-NI-020420-Amlaird - Refurb of Chloram Plant pipework/pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-04-03 |  | 2020-08-26 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 296.43 | 4296.43 | 22.57 | 0 | 0 | 4319 | 0 | 0 | 0 | 0 | 4319 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510093 | W-W-NI-021220-Penwhapple-Cl2 Detector | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-04 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960.75 | 960.75 | 0 | 0 | 0 | 960.75 | 0 | 0 | 0 | 0 | 960.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504522 | W-W-NI-030120 - Bradan WTW - Sludge Press 3 Hydraulic Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-03-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2943 | 0 | 2943 | 0 | 0 | 0 | 2943 | 0 | 0 | 0 | 0 | 2943 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504523 | W-W-NI-030120 - Colmonell TWP Ceiling Collapse | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-02-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3185.83 | 0 | 3185.83 | 0 | 0 | 0 | 3185.83 | 0 | 0 | 0 | 0 | 3185.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504525 | W-W-NI-030120 - Loch Turret Lagoons Monitoring | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-06-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1498 | 0 | 1498 | 0 | 0 | 0 | 1498 | 0 | 0 | 0 | 0 | 1498 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504524 | W-W-NI-030120 - Muirdykes WTW DAF no. 1 - Gearbox and Motor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-06 |  | 2020-09-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 443.81 | 6332.59 | 6776.4 | 0 | 0 | 0 | 6776.4 | 0 | 0 | 0 | 0 | 6776.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505500 | W-W-NI-030320-Afton- Chlorine Injector Cabinets | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-03 |  | 2020-08-26 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 378 | 5402.47 | 5780.47 | 0 | 0 | 0 | 5780.47 | 0 | 0 | 0 | 0 | 5780.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505490 | W-W-NI-030320-Bradan- Davit For Coag Sample Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-03 |  | 2020-08-26 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 131.04 | 1885.88 | 2016.92 | 0 | 0 | 0 | 2016.92 | 0 | 0 | 0 | 0 | 2016.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505492 | W-W-NI-030320-Megray WSZ - Replace Valves at Dunnotter Av & Lowwood Rd (5917) | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-03-10 |  | 2021-05-01 |  | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 6140.46 | 0 | 6140.46 | 0 | 0 | 0 | 6140.46 | 0 | 0 | 0 | 0 | 6140.46 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505495 | W-W-NI-030320-Penwhapple- Door Replacements | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-03 |  | 2020-08-26 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 655.91 | 9858.19 | 10514.1 | 0 | 0 | 0 | 10514.1 | 0 | 0 | 0 | 0 | 10514.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511586 | W-W-NI-030321-Afton-SCADA Shutdown Modifications | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-03 |  | 2021-06-03 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402.53 | 402.53 | 5274 | 0 | 0 | 5676.53 | 0 | 0 | 0 | 0 | 5676.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511585 | W-W-NI-030321-Blairlinnans-Sludge System RAM Pump Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-08 |  | 2021-06-03 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899.53 | 899.53 | 19163.47 | 0 | 0 | 20063 | 0 | 0 | 0 | 0 | 20063 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511587 | W-W-NI-030321-Turret-Sludge press feed RAM pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-03 |  | 2021-06-03 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 30000 | 0 | 0 | 32100 | 0 | 0 | 0 | 0 | 32100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506071 | W-W-NI-030420- Milngavie - PLC 4 Processor Card | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2021-05-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206.41 | 206.41 | 2736.59 | 0 | 0 | 2943 | 0 | 0 | 0 | 0 | 2943 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506982 | W-W-NI-030620-Balmore-Alum Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-06-03 |  | 2021-03-08 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14432.96 | 14432.96 | 0 | 0 | 0 | 14432.96 | 0 | 0 | 0 | 0 | 14432.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506980 | W-W-NI-030620-Old Kilpatrick-inlet HMI replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-03 |  | 2020-08-12 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13261.57 | 13261.57 | 0 | 0 | 0 | 13261.57 | 0 | 0 | 0 | 0 | 13261.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507992 | W-W-NI-030820-Amlaird-Replacement Rotork | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-11-05 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2773.79 | 2773.79 | 0 | 0 | 0 | 2773.79 | 0 | 0 | 0 | 0 | 2773.79 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507994 | W-W-NI-030820-Balmore-CCT Outlet Particle Counter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-01-12 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7379.66 | 7379.66 | 0 | 0 | 0 | 7379.66 | 0 | 0 | 0 | 0 | 7379.66 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507993 | W-W-NI-030820-Picketlaw-Install Sludge Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-11-05 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4163.74 | 4163.74 | 0 | 0 | 0 | 4163.74 | 0 | 0 | 0 | 0 | 4163.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508010 | W-W-NI-030820-Turret-Road repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-09-24 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18797.87 | 18797.87 | 0 | 0 | 0 | 18797.87 | 0 | 0 | 0 | 0 | 18797.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509604 | W-W-NI-031120-Gorbals Drumboyhill-Investigation on Drive failure | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-12 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26321.55 | 26321.55 | -22362.55 | 0 | 0 | 3959 | 0 | 0 | 0 | 0 | 3959 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510129 | W-W-NI-031220- Gorbals-Drumboyhill-Replacement Drives | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-04 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1842.25 | 1842.25 | 26105.75 | 0 | 0 | 27948 | 0 | 0 | 0 | 0 | 27948 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505517 | W-W-NI-040320-Afton-Treated Water Turbidity Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-04 |  | 2020-08-26 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 4237.46 | 13.88 | 4251.34 | 0 | 0 | 0 | 4251.34 | 0 | 0 | 0 | 0 | 4251.34 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505516 | W-W-NI-040320-Bradan-Sludge Building Lighting Rods | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-04 |  | 2020-08-26 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 2418.47 | 2586.47 | 0 | 0 | 0 | 2586.47 | 0 | 0 | 0 | 0 | 2586.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506439 | W-W-NI-040520-Bradan - Thickened Sludge Transfer Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-06 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7400.65 | 7400.65 | -2660.65 | 0 | 0 | 4740 | 0 | 0 | 0 | 0 | 4740 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506459 | W-W-NI-040520-Leanach - Telemetry outstation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-06 |  | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.07 | 109.07 | 1345.93 | 0 | 0 | 1455 | 0 | 0 | 0 | 0 | 1455 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506451 | W-W-NI-040520-Limerigg - Pump replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-06 |  | 2020-10-02 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2463.73 | 2463.73 | 0 | 0 | 0 | 2463.73 | 0 | 0 | 0 | 0 | 2463.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506446 | W-W-NI-040520-Stafflar - Meter Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-06 |  | 2020-09-08 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21171.93 | 21171.93 | 0 | 0 | 0 | 21171.93 | 0 | 0 | 0 | 0 | 21171.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506996 | W-W-NI-040620-Afton-Chlorguard install | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-05 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995.8 | 1995.8 | 28299.2 | 0 | 0 | 30295 | 0 | 0 | 0 | 0 | 30295 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506997 | W-W-NI-040620-Amliard-Chlorguard install | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-05 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25655.96 | 25655.96 | 0 | 0 | 0 | 25655.96 | 0 | 0 | 0 | 0 | 25655.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506995 | W-W-NI-040620-Dunblane -Chlorguard install | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-05 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1764.53 | 1764.53 | 24995.47 | 0 | 0 | 26760 | 0 | 0 | 0 | 0 | 26760 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506998 | W-W-NI-040620-Gorblas-Chlorguard install | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-05 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3518.26 | 3518.26 | 50048.74 | 0 | 0 | 53567 | 0 | 0 | 0 | 0 | 53567 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506999 | W-W-NI-040620-Penwhapple-Chlorguard install | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-05 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223.96 | 1223.96 | 17273.04 | 0 | 0 | 18497 | 0 | 0 | 0 | 0 | 18497 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508011 | W-W-NI-040820-Braeval-H&S issues | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-11-24 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568.88 | 1568.88 | 0 | 0 | 0 | 1568.88 | 0 | 0 | 0 | 0 | 1568.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508024 | W-W-NI-040820-Camphill-Clarifier Stoplogs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2020-10-15 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11424 | 11424 | 0 | 0 | 0 | 11424 | 0 | 0 | 0 | 0 | 11424 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508012 | W-W-NI-040820-Carron Valley-Balance tank and thickener feed pump A | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-04 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8523.32 | 8523.32 | 7740.68 | 0 | 0 | 16264 | 0 | 0 | 0 | 0 | 16264 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508014 | W-W-NI-040820-Carron Valley-Coag lime pump A | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-10-02 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9384.88 | 9384.88 | 0 | 0 | 0 | 9384.88 | 0 | 0 | 0 | 0 | 9384.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508015 | W-W-NI-040820-Killin-New reject flow meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-04 |  | 2020-10-02 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4258.15 | 4258.15 | 0 | 0 | 0 | 4258.15 | 0 | 0 | 0 | 0 | 4258.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508023 | W-W-NI-040820-Stanely Hollowhouse- Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2020-09-20 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5749.93 | 5749.93 | 0 | 0 | 0 | 5749.93 | 0 | 0 | 0 | 0 | 5749.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508013 | W-W-NI-040820-Turret-Actiflow no 1 scrapper replace | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-06 |  | 2021-03-15 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29919.91 | 29919.91 | 0 | 0 | 0 | 29919.91 | 0 | 0 | 0 | 0 | 29919.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509612 | W-W-NI-041120-Milngavie-Lamella Floc Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-12 |  | 2021-03-20 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16414.25 | 16414.25 | 0 | 0 | 0 | 16414.25 | 0 | 0 | 0 | 0 | 16414.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504163 | W-W-NI-041219 - Burncrooks WTW - UPS Rep. Sludge system | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-12-05 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2273.31 | 0 | 2273.31 | 0 | 0 | 0 | 2273.31 | 0 | 0 | 0 | 0 | 2273.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504162 | W-W-NI-041219 - Picketlaw WTW - Rep. Headloss Meter Filter 3 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-12-05 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 814.32 | 494.25 | 1308.57 | 0 | 0 | 0 | 1308.57 | 0 | 0 | 0 | 0 | 1308.57 | 119022.58 | [5 empty] | N | WSNI | 100%
504144 | W-W-NI-041219 - Picketlaw WTW - Replacement Recirc Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-05 |  | 2020-01-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2933.94 | 0 | 2933.94 | 0 | 0 | 0 | 2933.94 | 0 | 0 | 0 | 0 | 2933.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504155 | W-W-NI-041219- Picketlaw WTW - Rep. Pressure Flow Meter Switch | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-05 |  | 2020-02-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3175.63 | -1222.93 | 1952.7 | 0 | 0 | 0 | 1952.7 | 0 | 0 | 0 | 0 | 1952.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504145 | WW-NI-041219-Esnet Implementation Plan | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-09 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 11974.11 | 147220.2 | 159194.31 | -9194.31 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504150 | WW-NI-041219-Hamilton WWTW-Replace Top Level Scrappers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-04 |  | 2020-01-28 |  | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 4673.98 | 0 | 4673.98 | 0 | 0 | 0 | 4673.98 | 0 | 0 | 0 | 0 | 4673.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510141 | W-W-NI-041220-Balmichael-Hypo Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-04 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5034.03 | 5034.03 | 0 | 0 | 0 | 5034.03 | 0 | 0 | 0 | 0 | 5034.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506482 | W-W-NI-05050-Bradan - Alum Transfer Pump Mitigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-06 |  | 2020-07-07 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19737.88 | 19737.88 | 0 | 0 | 0 | 19737.88 | 0 | 0 | 0 | 0 | 19737.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506461 | W-W-NI-050520-Blairlinnans - RGF4 stream 2 inlet actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-06 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258.88 | 258.88 | 3486.12 | 0 | 0 | 3745 | 0 | 0 | 0 | 0 | 3745 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506463 | W-W-NI-050520-Dhu Loch - Hypo pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-06 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140.08 | 140.08 | 1788.92 | 0 | 0 | 1929 | 0 | 0 | 0 | 0 | 1929 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506462 | W-W-NI-050520-Loch Eck WTW - sludge thickener feed pump2 refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-06 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321.88 | 321.88 | 4386.12 | 0 | 0 | 4708 | 0 | 0 | 0 | 0 | 4708 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507037 | W-W-NI-050620 Blairvockie DSR Cut and Cap investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-06-26 | 2021-07-08 | 2022-02-18 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13285 | 13285 | 0 | 0 | 0 | 13285 | 0 | 0 | 0 | 0 | 13285 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507040 | W-W-NI-050620 Port of Menteith DSR investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-06-25 | 2021-07-08 | 2022-02-18 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9321 | 9321 | 2505.36 | 0 | 0 | 11826.36 | 0 | 0 | 0 | 0 | 11826.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508030 | W-W-NI-050820-Afton-Lime Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-06 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3757.37 | 3757.37 | 8558.63 | 0 | 0 | 12316 | 0 | 0 | 0 | 0 | 12316 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508029 | W-W-NI-050820-Balmichael-Sulphuric Acid Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2021-03-23 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3835.94 | 3835.94 | 0 | 0 | 0 | 3835.94 | 0 | 0 | 0 | 0 | 3835.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508031 | W-W-NI-050820-Biglees-Ball Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-06 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11320.64 | 11320.64 | 0 | 0 | 0 | 11320.64 | 0 | 0 | 0 | 0 | 11320.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508033 | W-W-NI-050820-Bradan-Filter Headloss Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2020-10-28 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5843.85 | 5843.85 | 0 | 0 | 0 | 5843.85 | 0 | 0 | 0 | 0 | 5843.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508034 | W-W-NI-050820-Bradan-Sludge Chemical Waste Tank | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2020-09-14 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3035.88 | 3035.88 | 0 | 0 | 0 | 3035.88 | 0 | 0 | 0 | 0 | 3035.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508027 | W-W-NI-050820-Camphill-Building Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2020-08-14 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1811.16 | 1811.16 | 0 | 0 | 0 | 1811.16 | 0 | 0 | 0 | 0 | 1811.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508026 | W-W-NI-050820-Camphill-Scada upgrade low cl2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2020-11-10 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2415.71 | 2415.71 | 0 | 0 | 0 | 2415.71 | 0 | 0 | 0 | 0 | 2415.71 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508032 | W-W-NI-050820-Fauldribbon-Flow Meters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2020-08-27 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4712.08 | 4712.08 | 0 | 0 | 0 | 4712.08 | 0 | 0 | 0 | 0 | 4712.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508028 | W-W-NI-050820-Greenock-Replace Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2021-03-23 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2854.82 | 2854.82 | 0 | 0 | 0 | 2854.82 | 0 | 0 | 0 | 0 | 2854.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508035 | W-W-NI-050820-Penwhapple-Sludge Conveyor Removal | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2020-09-29 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5112.88 | 5112.88 | 0 | 0 | 0 | 5112.88 | 0 | 0 | 0 | 0 | 5112.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509092 | W-W-NI-051020-Amlaird-Replacement Cl2 UPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-06 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1855.58 | 1855.58 | 0 | 0 | 0 | 1855.58 | 0 | 0 | 0 | 0 | 1855.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509079 | W-W-NI-051020-Loch Eck-Hypo Dosing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-05 |  | 2021-03-27 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7636.58 | 7636.58 | 0 | 0 | 0 | 7636.58 | 0 | 0 | 0 | 0 | 7636.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509650 | W-WNI-051120-Gateside TWP - Pipework Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-11-27 | 2021-11-01 | 2022-04-05 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6521.36 | 6521.36 | 79100 | 0 | 0 | 85621.36 | 0 | 0 | 0 | 0 | 85621.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504189 | W-W-NI-051219 - Bradan WTW - PRGF 1-8 Filter Nozzle Clean (4th of 8) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-05 |  | 2020-02-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 32663.81 | 0 | 32663.81 | 0 | 0 | 0 | 32663.81 | 0 | 0 | 0 | 0 | 32663.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504166 | W-W-NI-051219 - Carron Valley Filter F rotork wash out valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-05 |  | 2020-03-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2990.67 | 0 | 2990.67 | 0 | 0 | 0 | 2990.67 | 0 | 0 | 0 | 0 | 2990.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504164 | W-W-NI-051219 - Helensburgh DSR - HMI replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-12-05 |  | 2021-03-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3242.34 | -3242.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
504187 | W-W-NI-051219 - Turret PACL dosing pump B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-12-05 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2517.73 | 0 | 2517.73 | 0 | 0 | 0 | 2517.73 | 0 | 0 | 0 | 0 | 2517.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504172 | W-W-NI-051219- Turret poly pump A actiflow Stream no1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-05 |  | 2019-12-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4396.32 | 0 | 4396.32 | 0 | 0 | 0 | 4396.32 | 0 | 0 | 0 | 0 | 4396.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510551 | W-W-NI-060121-Camphill-Generator Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-07 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9947.07 | 9947.07 | -124.07 | 0 | 0 | 9823 | 0 | 0 | 0 | 0 | 9823 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510484 | W-W-NI-060121-Carrick Castle-Provision of module sample taps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-07 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945 | 945 | 13500 | 0 | 0 | 14445 | 0 | 0 | 0 | 0 | 14445 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505566 | W-W-NI-060320-Camphill- PRGF no. 2-Media and Nozzle Repl. | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-06 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 18.7 | 3518.7 | 49981.3 | 0 | 0 | 53500 | 0 | 0 | 0 | 0 | 53500 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506093 | W-W-NI-060420-Picketlaw - Stop Log Storage Unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-10 |  | 2020-08-26 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448.76 | 1448.76 | 0 | 0 | 0 | 1448.76 | 0 | 0 | 0 | 0 | 1448.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508654 | W-WNI-060620 - Afton DIR Intake Road Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2020-11-27 | 2021-09-01 | 2021-11-04 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5128.16 | 5128.16 | 350 | 0 | 0 | 5478.16 | 0 | 0 | 0 | 0 | 5478.16 | 311236.79 | [5 empty] | N | CM_M&G | 100%
508098 | W-W-NI-060820-Amlaird WTW- CAT 1 & 2 Building & Site repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2021-07-05 | 2021-07-06 | 2022-02-15 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2651.15 | 2651.15 | 11483.55 | 0 | 0 | 14134.7 | 0 | 0 | 0 | 0 | 14134.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508086 | W-W-NI-060820-Arrochar-Tighness Burn pipe bridge | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-07 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 5000 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 5350 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508037 | W-W-NI-060820-Bradan-LCC Controller Phased | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-07 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21831.88 | 21831.88 | 0 | 0 | 0 | 21831.88 | 0 | 0 | 0 | 0 | 21831.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508036 | W-W-NI-060820-Darvel-Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-06 |  | 2020-09-22 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10712.32 | 10712.32 | 0 | 0 | 0 | 10712.32 | 0 | 0 | 0 | 0 | 10712.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508085 | W-W-NI-060820-Dhu Loch-Sample Tap Concrete Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-07 |  | 2020-11-19 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008.1 | 2008.1 | 0 | 0 | 0 | 2008.1 | 0 | 0 | 0 | 0 | 2008.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508083 | W-W-NI-060820-Dhu Loch-Washwaster Recovery Pump 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-08-07 |  | 2020-10-09 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6144.37 | 6144.37 | 0 | 0 | 0 | 6144.37 | 0 | 0 | 0 | 0 | 6144.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508038 | W-W-NI-060820-Greenock-Final Lime Pump B Gearbox | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-07 |  | 2020-08-22 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3223.96 | 3223.96 | 0 | 0 | 0 | 3223.96 | 0 | 0 | 0 | 0 | 3223.96 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508084 | W-W-NI-060820-Lochend-Sample tap path handrail provision | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-07 |  | 2020-10-21 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309.47 | 1309.47 | 0 | 0 | 0 | 1309.47 | 0 | 0 | 0 | 0 | 1309.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508087 | W-W-NI-060820-Lochgoilhead-Inlet Strainer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-07 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.52 | 239.52 | 3209.48 | 0 | 0 | 3449 | 0 | 0 | 0 | 0 | 3449 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508103 | W-W-NI-060820-Picketlaw WTW-CAT 1 & 2 Building & Site Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-10-09 | 2021-06-07 | 2022-01-18 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045.41 | 1045.41 | -1045.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
508082 | W-W-NI-060820-Slafarquar to Loch Coulter-Leaking aqueduct | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-07 |  | 2020-10-02 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61202.76 | 61202.76 | 0 | 0 | 0 | 61202.76 | 0 | 0 | 0 | 0 | 61202.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509117 | W-W-NI-061020-Amlaird-PLC Inlet Poly | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-06 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1198.12 | 1198.12 | 16903.88 | 0 | 0 | 18102 | 0 | 0 | 0 | 0 | 18102 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509116 | W-W-NI-061020-Bradan-Hypo Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-06 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9723.25 | 9723.25 | 2067.75 | 0 | 0 | 11791 | 0 | 0 | 0 | 0 | 11791 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503788 | W-W-NI-061119-Blairlinnans WTW- sludge withdrawal pump refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-12-09 |  | 2021-02-26 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 5055.73 | 0 | 5055.73 | 0 | 0 | 0 | 5055.73 | 0 | 0 | 0 | 0 | 5055.73 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504542 | W-W-NI-070120 - Castlemilk Low PS - Refurb of Welfare Facilities | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-07 |  | 2020-03-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4849.25 | 0 | 4849.25 | 0 | 0 | 0 | 4849.25 | 0 | 0 | 0 | 0 | 4849.25 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510554 | W-W-NI-070121-Balquhidder-Replacement recycle pump A | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-07 |  | 2021-03-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4154.9 | 4154.9 | -12.88 | 0 | 0 | 4142.02 | 0 | 0 | 0 | 0 | 4142.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510552 | W-W-NI-070121-Bradan-Telemetry Controller | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-07 |  | 2021-04-04 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22366.88 | 22366.88 | 103.12 | 0 | 0 | 22470 | 0 | 0 | 0 | 0 | 22470 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510553 | W-W-NI-070121-Turret-Ortho monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-07 |  | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14716.13 | 14716.13 | -13.13 | 0 | 0 | 14703 | 0 | 0 | 0 | 0 | 14703 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512248 | W-W-NI-070421-Afton-Clarifier Cones | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15899.03 | 0 | 0 | 15899.03 | 0 | 0 | 0 | 0 | 15899.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512245 | W-W-NI-070421-Muirdykes-Hypo Dosing Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4965.03 | 0 | 0 | 4965.03 | 0 | 0 | 0 | 0 | 4965.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506537 | W-W-NI-070520-Burncrooks - Guttering & Waterproofing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-12 |  | 2020-09-25 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5124.18 | 5124.18 | 0 | 0 | 0 | 5124.18 | 0 | 0 | 0 | 0 | 5124.18 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506540 | W-W-NI-070520-Finlas- RGF Tb monitors link to telemetry with alarms | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-12 |  | 2020-09-04 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1870.3 | 1870.3 | 0 | 0 | 0 | 1870.3 | 0 | 0 | 0 | 0 | 1870.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508113 | W-W-NI-070820 Lipney DSR flow control/Bypass investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-08-25 | 2021-09-10 | 2022-04-25 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4794.08 | 4794.08 | 10270.07 | 0 | 0 | 15064.15 | 0 | 0 | 0 | 0 | 15064.15 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508111 | W-W-NI-070820 Quarter BPT outlet pipe investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-08-25 | 2021-09-10 | 2022-02-21 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7864.08 | 7864.08 | 7200 | 0 | 0 | 15064.08 | 0 | 0 | 0 | 0 | 15064.08 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508089 | W-W-NI-070820-Blairlinnans-Shutter door motor and barrel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-07 |  | 2020-10-30 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4798.35 | 4798.35 | 0 | 0 | 0 | 4798.35 | 0 | 0 | 0 | 0 | 4798.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508088 | W-W-NI-070820-Loch Eck-Final Hypo dosing pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-07 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.46 | 221.46 | 2951.54 | 0 | 0 | 3173 | 0 | 0 | 0 | 0 | 3173 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508608 | W-W-NI-070920-Carron Valley WTW CCT Limeberg Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-09-23 | 2021-07-01 | 2021-12-17 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11442.85 | 11442.85 | 9999.99 | 0 | 0 | 21442.84 | 0 | 0 | 0 | 0 | 21442.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508615 | W-W-NI-070920-Carron Valley WTW Lime H&S and dosing pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 |  | 2022-04-01 | 2022-06-24 | 2023-02-06 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.86 | 45.86 | 0 | 0 | 0 | 45.86 | 0 | 0 | 0 | 0 | 45.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508612 | W-W-NI-070920-Castlemilk-PLC Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-08 |  | 2020-10-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4034.5 | 4034.5 | 0 | 0 | 0 | 4034.5 | 0 | 0 | 0 | 0 | 4034.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503791 | W-W-NI-071119-Finlas WTW-Replace recovered water pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-05 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 751.28 | -672.51 | 78.77 | 1125.23 | 0 | 0 | 1204 | 0 | 0 | 0 | 0 | 1204 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510185 | W-W-NI-071220-Carron Valley WTW raw Inlet chamber roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-12-21 | 2021-07-16 | 2022-02-28 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750 | 4750 | 5250.01 | 0 | 0 | 10000.01 | 0 | 0 | 0 | 0 | 10000.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510180 | W-W-NI-071220-Loch Ascog-Roofing Repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-08 |  | 2021-03-25 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2058.5 | 2058.5 | 0 | 0 | 0 | 2058.5 | 0 | 0 | 0 | 0 | 2058.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510164 | W-W-NI-071220-Turret-Final sample floor fixings for H&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-08 |  | 2021-03-12 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17264.92 | 17264.92 | 0 | 0 | 0 | 17264.92 | 0 | 0 | 0 | 0 | 17264.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511082 | W-W-NI-080221-Balmore-Retrofit AH Breaker No 5 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-09 |  | 2021-05-08 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943.38 | 1943.38 | 27762.6 | 0 | 0 | 29705.98 | 0 | 0 | 0 | 0 | 29705.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511642 | W-W-NI-080321-Glenhove-Garbethill No 2 Pump Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-08 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 793.68 | 793.68 | 10398.84 | 0 | 0 | 11192.52 | 0 | 0 | 0 | 0 | 11192.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511643 | W-W-NI-080321-Lugton-Roof Tile replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-08 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.14 | 255.14 | 3342.84 | 0 | 0 | 3597.98 | 0 | 0 | 0 | 0 | 3597.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506132 | W-W-NI-080420-Glenhove - Replacement Butterfly Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-10 |  | 2020-08-26 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4777.4 | 4777.4 | 0 | 0 | 0 | 4777.4 | 0 | 0 | 0 | 0 | 4777.4 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504585 | W-W-NI-090120 - Bradan WTW - Bird Mesh Guards | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-10 |  | 2020-03-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2616.94 | 0 | 2616.94 | 0 | 0 | 0 | 2616.94 | 0 | 0 | 0 | 0 | 2616.94 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505603 | W-W-NI-090320-Amlaird - Generator refurbishment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-09 |  | 2021-03-23 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2138.3 | 27.76 | 2166.06 | 0 | 0 | 0 | 2166.06 | 0 | 0 | 0 | 0 | 2166.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505594 | W-W-NI-090320-Bradan - PRGF 1-8 Filter Nozzle Clean (5th of 8) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-09 |  | 2020-07-22 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2358.36 | 38739.98 | 41098.34 | 0 | 0 | 0 | 41098.34 | 0 | 0 | 0 | 0 | 41098.34 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511679 | WW-NI-090321-Dalbeattie WWTW-Replacement basket for screen 2 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-10 |  | 2021-06-09 |  | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2853.1 | 2853.1 | -153.1 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507599 | W-W-NI-090720-Afton-Treated Water pH Meters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-09 |  | 2020-10-19 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9593.59 | 9593.59 | 0 | 0 | 0 | 9593.59 | 0 | 0 | 0 | 0 | 9593.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507601 | W-W-NI-090720-Castlemilk High-Rendering Works | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-09 |  | 2020-08-24 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12924.21 | 12924.21 | 0 | 0 | 0 | 12924.21 | 0 | 0 | 0 | 0 | 12924.21 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508671 | W-WNI-090920 Greenock WTW - Service Water Supply Investigations | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 |  | 2020-11-27 | 2021-03-18 | 2021-09-03 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5382.04 | 5382.04 | 0 | 0 | 0 | 5382.04 | 0 | 0 | 0 | 0 | 5382.04 | 311236.79 | [5 empty] | N | CM_M&G | 100%
509181 | W-W-NI-091020-No welfare facilities at a number of west water sites | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-10-14 | 2021-03-23 | 2021-12-03 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7570.36 | 7570.36 | 12451.15 | 0 | 0 | 20021.51 | 0 | 0 | 0 | 0 | 20021.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509681 | W-W-NI-091120-Loch Eck-Sludge Press Cloth | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-12 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 473.94 | 473.94 | 6134.06 | 0 | 0 | 6608 | 0 | 0 | 0 | 0 | 6608 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504253 | W-W-NI-091219 - Bradan WTW - 2RGF No. 1 Outlet Flow Meter Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-12-09 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2258.27 | 0 | 2258.27 | 0 | 0 | 0 | 2258.27 | 0 | 0 | 0 | 0 | 2258.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504256 | W-W-NI-091219 - Bradan WTW - Inlet Poly Pump and SCADA | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-09 |  | 2020-05-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7787.94 | 5459.06 | 13247 | 0 | 0 | 0 | 13247 | 0 | 0 | 0 | 0 | 13247 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504250 | W-W-NI-091219- Bradan WTW - Site Road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-09 |  | 2020-08-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8214.56 | 0 | 8214.56 | 0 | 0 | 0 | 8214.56 | 0 | 0 | 0 | 0 | 8214.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505617 | W-W-NI-100320 - Bradan - PRGF 7 Trough Leaks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-12 |  | 2020-08-26 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 664.07 | 5166.7 | 5830.77 | 0 | 0 | 0 | 5830.77 | 0 | 0 | 0 | 0 | 5830.77 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505630 | W-W-NI-100320 - Bradan - Turbine House SCADA Link | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-12 |  | 2020-08-26 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 7171.14 | 813.7 | 7984.84 | 0 | 0 | 0 | 7984.84 | 0 | 0 | 0 | 0 | 7984.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507134 | W-W-NI-100620 Turret WTW Investigate feasibility of phase protection relays on MCC panels | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS4 |  | 2020-06-12 | 2020-08-17 | 2021-03-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553.23 | 553.23 | 0 | 0 | 0 | 553.23 | 0 | 0 | 0 | 0 | 553.23 | 311236.79 | [5 empty] | N | CM_M&G | 100%
507614 | W-W-NI-100720-Burns Road-Roof Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-10 |  | 2020-08-27 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9995.91 | 9995.91 | 0 | 0 | 0 | 9995.91 | 0 | 0 | 0 | 0 | 9995.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507620 | W-W-NI-100720-Picketlaw-Fence installation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188.88 | 188.88 | 2486.12 | 0 | 0 | 2675 | 0 | 0 | 0 | 0 | 2675 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504276 | W-W-NI-101219 - Afton WTW - Sludge Conveyor Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-10 |  | 2020-01-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7005 | 0 | 7005 | 0 | 0 | 0 | 7005 | 0 | 0 | 0 | 0 | 7005 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504280 | W-W-NI-101219 - Penwhapple WTW - Poly Mixer Spool Piece | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-10 |  | 2020-07-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2990 | -2990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
510231 | W-W-NI-101220-Garthamlock-Crash Barrier Scaffolding | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-15 |  | 2021-03-23 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.88 | 13.88 | 0 | 0 | 0 | 13.88 | 0 | 0 | 0 | 0 | 13.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511178 | W-W-NI-110221-Gorbals-Drumboyhill-Replacement UPS | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-02-12 |  | 2021-04-05 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3852 | 3852 | 0 | 0 | 0 | 3852 | 0 | 0 | 0 | 0 | 3852 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506563 | W-W-NI-11050-Finlas-CL2 room egress hands improvement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-13 |  | 2020-11-19 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1286.69 | 1286.69 | 0 | 0 | 0 | 1286.69 | 0 | 0 | 0 | 0 | 1286.69 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506568 | W-W-NI-110520-Flatt Farm-Secondary Disinfection | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-13 |  | 2020-10-19 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4066.36 | 4066.36 | 0 | 0 | 0 | 4066.36 | 0 | 0 | 0 | 0 | 4066.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506567 | W-W-NI-110520-Gateside-Secondary Disinfection | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-12 |  | 2020-10-21 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101.48 | 2101.48 | 0 | 0 | 0 | 2101.48 | 0 | 0 | 0 | 0 | 2101.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506565 | W-W-NI-110520-Holehouse-Secondary Disinfection | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-12 |  | 2020-10-19 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4052.48 | 4052.48 | 0 | 0 | 0 | 4052.48 | 0 | 0 | 0 | 0 | 4052.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506564 | W-W-NI-110520-Turret-Treated lime dosing scour pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-13 |  | 2020-09-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3541.68 | 3541.68 | 0 | 0 | 0 | 3541.68 | 0 | 0 | 0 | 0 | 3541.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507146 | W-W-NI-110620 Turret WTW Install and commission auto duty-stby lime dosing system | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-06-17 | 2020-10-14 | 2021-06-18 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12183.6 | 12183.6 | -106.36 | 0 | 0 | 12077.24 | 0 | 0 | 0 | 0 | 12077.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508705 | W-W-NI-110920-Glenhove-Replacement Butterfly Valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-16 |  | 2021-02-13 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11113.88 | 11113.88 | 0 | 0 | 0 | 11113.88 | 0 | 0 | 0 | 0 | 11113.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504300 | W-W-NI-111219 - Bradan WTW - Alum Pump Power Supply | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-11 |  | 2020-05-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3645.05 | 2341.95 | 5987 | 0 | 0 | 0 | 5987 | 0 | 0 | 0 | 0 | 5987 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504303 | W-W-NI-111219 - Lochranza WTW - Treated Water Colour Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-11 |  | 2020-02-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3777 | 0 | 3777 | 0 | 0 | 0 | 3777 | 0 | 0 | 0 | 0 | 3777 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510263 | W-W-NI-111220-Turret Houses-Roof slates | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-15 |  | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4486.03 | 4486.03 | 63873.97 | 0 | 0 | 68360 | 0 | 0 | 0 | 0 | 68360 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510644 | W-W-NI-120121-Camphill-Sludge Press Cloth | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188.77 | 1188.77 | 16784.12 | 0 | 0 | 17972.89 | 0 | 0 | 0 | 0 | 17972.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510645 | W-W-NI-120121-Greenock-Treated Water Flow Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285.31 | 285.31 | 3877.56 | 0 | 0 | 4162.87 | 0 | 0 | 0 | 0 | 4162.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510643 | W-W-NI-120121-Ross Priory-Pump condition & performance survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14821.88 | 14821.88 | 158.12 | 0 | 0 | 14980 | 0 | 0 | 0 | 0 | 14980 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511770 | W-WNI-120321-Bradan WTW-Climate Control Conditioning for Hypo Room | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-03-23 | 2021-12-03 | 2022-07-18 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.14 | 157.14 | 50000 | 0 | 0 | 50157.14 | 0 | 0 | 0 | 0 | 50157.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511763 | W-W-NI-120321-Muirdykes-Sodium Hydroxide Tank Surrounds | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-12 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270.91 | 270.91 | 3549.42 | 0 | 0 | 3820.33 | 0 | 0 | 0 | 0 | 3820.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511764 | W-W-NI-120321-Muirdykes-Sodium Hypochlorite Tank Surrounds | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-12 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270.91 | 270.91 | 3549.42 | 0 | 0 | 3820.33 | 0 | 0 | 0 | 0 | 3820.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508171 | W-W-NI-120820-Bradan-Filter Air Vent Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-14 |  | 2020-11-10 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34438.16 | 34438.16 | 0 | 0 | 0 | 34438.16 | 0 | 0 | 0 | 0 | 34438.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509212 | W-W-NI-121020-Amlaird-Backwash inlet valve & Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-14 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1585.54 | 1585.54 | 7461.46 | 0 | 0 | 9047 | 0 | 0 | 0 | 0 | 9047 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509214 | W-W-NI-121020-Glaisnock-Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-14 |  | 2021-02-20 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1404.88 | 1404.88 | 0 | 0 | 0 | 1404.88 | 0 | 0 | 0 | 0 | 1404.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509213 | W-W-NI-121020-Penwhapple-PC replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-14 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18822.36 | 18822.36 | 13277.64 | 0 | 0 | 32100 | 0 | 0 | 0 | 0 | 32100 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503803 | W-W-NI-121119-Canada Hill DSR-Replace telemetry outstation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-11-18 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1539.75 | 13.88 | 1553.63 | 0 | 0 | 0 | 1553.63 | 0 | 0 | 0 | 0 | 1553.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503800 | W-W-NI-121119-Finlas WTW- Replace pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-11-18 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 1268.57 | -1121.69 | 146.88 | 1886.12 | 0 | 0 | 2033 | 0 | 0 | 0 | 0 | 2033 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504309 | W-W-NI-121219 - Balmichael WTW - BH No 5 Generator Reurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-16 |  | 2020-03-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2650.99 | 0 | 2650.99 | 0 | 0 | 0 | 2650.99 | 0 | 0 | 0 | 0 | 2650.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504328 | W-W-NI-121219 - Balmore WTW - Rep. Main Drives | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-16 |  | 2020-03-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 63761.89 | 0 | 63761.89 | 0 | 0 | 0 | 63761.89 | 0 | 0 | 0 | 0 | 63761.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504314 | W-W-NI-121219 - Lochranza WTW - Generator Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-16 |  | 2020-03-11 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1303.85 | 0 | 1303.85 | 0 | 0 | 0 | 1303.85 | 0 | 0 | 0 | 0 | 1303.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504306 | W-W-NI-121219 - Penwhapple WTW - DAF 2&3 Nozzle Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-16 |  | 2020-07-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4811 | -4811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
507635 | W-W-NI-130720-Crosbie-Roof Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-15 |  | 2020-08-22 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9458.01 | 9458.01 | 0 | 0 | 0 | 9458.01 | 0 | 0 | 0 | 0 | 9458.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507661 | W-W-NI-130720-Picketlaw-Refurbishment of Generator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.05 | 222.05 | 2959.95 | 0 | 0 | 3182 | 0 | 0 | 0 | 0 | 3182 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507656 | W-W-NI-130720-Woodhill-Replacement Ball Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650.62 | 650.62 | 9082.38 | 0 | 0 | 9733 | 0 | 0 | 0 | 0 | 9733 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504340 | W-W-NI-131219 - Amlaird WTW - Refurb of Soda Ash Unit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-16 |  | 2020-02-25 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3971.85 | 0 | 3971.85 | 0 | 0 | 0 | 3971.85 | 0 | 0 | 0 | 0 | 3971.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504342 | W-W-NI-131219 - Amlaird WTW - Replacement Coag Lime Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2019-12-16 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 13163 | -9635.87 | 3527.13 | 0 | 0 | 0 | 3527.13 | 0 | 0 | 0 | 0 | 3527.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504345 | W-W-NI-131219 - Finlas WTW - MCC room roof condition survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-28 | 2021-06-16 | 2021-08-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1284 | 9143.08 | 10427.08 | -85.09 | 0 | 0 | 10341.99 | 0 | 0 | 0 | 0 | 10341.99 | 119022.58 | [5 empty] | N | WSNI | 100%
504343 | W-W-NI-131219 - Loch Eck WTW Landslide risk assessment | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 |  | 2020-01-29 | 2020-02-13 | 2020-11-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1068.4 | 4239.11 | 5307.51 | 0 | 0 | 0 | 5307.51 | 0 | 0 | 0 | 0 | 5307.51 | 119022.58 | [5 empty] | N | WSNI | 100%
504636 | W-W-NI-140120 - Ross Priory RWPS - HC compound vegetation clearance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-17 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666.64 | 666.64 | 9523.36 | 0 | 0 | 10190 | 0 | 0 | 0 | 0 | 10190 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504651 | W-W-NI-150120-Cameron raw BPT - install livestock proof fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-28 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6249 | 6249 | 437 | 0 | 0 | 6686 | 0 | 0 | 0 | 0 | 6686 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504650 | W-W-NI-150120-Finlas WTW - main MCC relays replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-13 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8419 | -7868.22 | 550.78 | 7868.22 | 0 | 0 | 8419 | 0 | 0 | 0 | 0 | 8419 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507711 | W-W-NI-150720-Belmore-Final sample tap upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493.81 | 493.81 | 6842.19 | 0 | 0 | 7336 | 0 | 0 | 0 | 0 | 7336 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507690 | W-W-NI-150720-Gorbals-Fence gate installation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-15 |  | 2020-09-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1592.11 | 1592.11 | 0 | 0 | 0 | 1592.11 | 0 | 0 | 0 | 0 | 1592.11 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507689 | W-W-NI-150720-Milngavie-Lamella Sludge Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-15 |  | 2020-09-30 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13083.61 | 13083.61 | 0 | 0 | 0 | 13083.61 | 0 | 0 | 0 | 0 | 13083.61 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510322 | W-W-NI-151220- Glenhove-New Power connection | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-15 |  | 2021-03-23 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2203.98 | 2203.98 | 0 | 0 | 0 | 2203.98 | 0 | 0 | 0 | 0 | 2203.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505738 | W-W-NI-160320 Bradan WTW - Inlet Channel Cover Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-04-03 | 2020-10-07 | 2021-05-03 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4910 | 4910 | 439.62 | 0 | 0 | 5349.62 | 0 | 0 | 0 | 0 | 5349.62 | 119022.58 | [5 empty] | N | WSNI | 100%
511825 | W-W-NI-160321-Giffordland-Ball Valve Repl | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9282.66 | 9282.66 | -320.66 | 0 | 0 | 8962 | 0 | 0 | 0 | 0 | 8962 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511818 | W-W-NI-160321-Picketlaw-Fixed Loading Point for Sludge Tanker | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371.92 | 371.92 | 4872.84 | 0 | 0 | 5244.76 | 0 | 0 | 0 | 0 | 5244.76 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511819 | W-W-NI-160321-Stronachlacher-Replacement Heaters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-16 |  | 2021-06-16 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.15 | 174.15 | 2281.74 | 0 | 0 | 2455.89 | 0 | 0 | 0 | 0 | 2455.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507214 | W-W-NI160620-Amlaird-Refurb Thickening Sludge Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-07-08 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267.91 | 1267.91 | 0 | 0 | 0 | 1267.91 | 0 | 0 | 0 | 0 | 1267.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507215 | W-W-NI-160620-Turret Lagoon Survey -Maptek | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-10-02 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1609.88 | 1609.88 | 0 | 0 | 0 | 1609.88 | 0 | 0 | 0 | 0 | 1609.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507718 | W-W-NI-160720-Alexandria-Sludge press cloths | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-16 |  | 2021-02-10 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6990.56 | 6990.56 | 0 | 0 | 0 | 6990.56 | 0 | 0 | 0 | 0 | 6990.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507717 | W-W-NI-160720-Belmore-Filter Cloth Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-16 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638.32 | 638.32 | 8906.68 | 0 | 0 | 9545 | 0 | 0 | 0 | 0 | 9545 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507716 | W-W-NI-160720-Belmore-Sludge press maintenance | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-07-16 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10163.22 | 10163.22 | 11083.78 | 0 | 0 | 21247 | 0 | 0 | 0 | 0 | 21247 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507724 | W-W-NI-160720-Bradan-PRGF 1-8 Filter Nozzle Clean (No. 2) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-16 |  | 2020-09-17 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29700.06 | 29700.06 | 0 | 0 | 0 | 29700.06 | 0 | 0 | 0 | 0 | 29700.06 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508782 | W-W-NI-160920-Balmichael-Shiskine Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-17 |  | 2021-02-12 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7479.24 | 7479.24 | 0 | 0 | 0 | 7479.24 | 0 | 0 | 0 | 0 | 7479.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508781 | W-W-NI-160920-Balmore-Rotork & Gearboxes | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-09-17 |  | 2021-03-15 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18667.33 | 18667.33 | 0 | 0 | 0 | 18667.33 | 0 | 0 | 0 | 0 | 18667.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508771 | W-W-NI-160920-Muirdykes-Hot Flushing Dosing Lines | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-16 |  | 2020-06-12 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34128.64 | 34128.64 | 0 | 0 | 0 | 34128.64 | 0 | 0 | 0 | 0 | 34128.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504352 | W-W-NI-161219 - Belmore WTW - Tank mixer B replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-01-22 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1049.14 | -886.14 | 163 | 2323.36 | 0 | 0 | 2486.36 | 0 | 0 | 0 | 0 | 2486.36 | 119022.58 | [5 empty] | N | WSNI | 100%
505226 | W-W-NI-170220-Amlaird WTW - Replacement Roof | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-19 |  | 2020-08-26 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 1540.8 | 4906.5 | 6447.3 | 0 | 0 | 0 | 6447.3 | 0 | 0 | 0 | 0 | 6447.3 | 119022.58 | [5 empty] | N | WSNI | 100%
505239 | W-W-NI-170220-Loch Eck WTW - Aztec 1000 alum monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-19 |  | 2020-04-21 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 3653.76 | 11597.98 | 15251.74 | 0 | 0 | 0 | 15251.74 | 0 | 0 | 0 | 0 | 15251.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511290 | W-W-NI-170221-Afton-Coag pH | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3277.82 | 3277.82 | 10504.15 | 0 | 0 | 13781.97 | 0 | 0 | 0 | 0 | 13781.97 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511289 | W-W-NI-170221-Bradan-Sludge Building Stairwell | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245 | 245 | 3500 | 0 | 0 | 3745 | 0 | 0 | 0 | 0 | 3745 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505767 | W-W-NI-17030- Castlemilk - Reinstate Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-19 |  | 2020-07-21 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 2717.58 | 2906.58 | 0 | 0 | 0 | 2906.58 | 0 | 0 | 0 | 0 | 2906.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505773 | W-W-NI-170320- Amlaird - Replacement Alum Pump A | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-19 |  | 2020-04-24 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 81.84 | -81.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
505777 | W-W-NI-170320- Picketlaw - Supernatant Return Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-19 |  | 2020-08-26 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 327.3 | 4690.58 | 5017.88 | 0 | 0 | 0 | 5017.88 | 0 | 0 | 0 | 0 | 5017.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511860 | W-W-NI-170321-Alexandria-Secondary Filter Valve Actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-17 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.33 | 154.33 | 2022 | 0 | 0 | 2176.33 | 0 | 0 | 0 | 0 | 2176.33 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511850 | W-W-NI-170321-Amlaird-High Pressure Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-17 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 816.26 | 816.26 | 8049.42 | 0 | 0 | 8865.68 | 0 | 0 | 0 | 0 | 8865.68 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511851 | W-W-NI-170321-Amlaird-Upgrade Fire Alarm System | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-17 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190.05 | 190.05 | 2490 | 0 | 0 | 2680.05 | 0 | 0 | 0 | 0 | 2680.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511849 | W-W-NI-170321-Balmore-Retrofit 3 x AK Breaker | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-17 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159.53 | 2159.53 | 30850.47 | 0 | 0 | 33010 | 0 | 0 | 0 | 0 | 33010 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511864 | W-W-NI-170321-Brig o Turk-H&S access platform | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-17 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378 | 378 | 4952.58 | 0 | 0 | 5330.58 | 0 | 0 | 0 | 0 | 5330.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511862 | W-W-NI-170321-Gartcarron-Pump capacity investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-17 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 140 | 1834.26 | 0 | 0 | 1974.26 | 0 | 0 | 0 | 0 | 1974.26 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509827 | W-W-NI-171120-Amlaird-Install Puddle Pump & level switch | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-20 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277.92 | 277.92 | 3758.08 | 0 | 0 | 4036 | 0 | 0 | 0 | 0 | 4036 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509826 | W-W-NI-171120-Balmore-LLPs Particle Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-17 |  | 2021-02-25 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7376.19 | 7376.19 | 0 | 0 | 0 | 7376.19 | 0 | 0 | 0 | 0 | 7376.19 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509837 | W-W-NI-171120-Carron Valley-SCADA PC | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-20 |  | 2021-02-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2467.63 | 2467.63 | 0 | 0 | 0 | 2467.63 | 0 | 0 | 0 | 0 | 2467.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509838 | W-W-NI-171120-Carron Valley-Sludge press filter cloths | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-20 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1707.88 | 1707.88 | 24186.12 | 0 | 0 | 25894 | 0 | 0 | 0 | 0 | 25894 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511306 | W-W-NI-180221-Balmore-Poly dosing Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1124.58 | 1124.58 | 16065.4 | 0 | 0 | 17189.98 | 0 | 0 | 0 | 0 | 17189.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511307 | W-W-NI-180221-Kilbowie-Replacement Inlet Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11955.84 | 11955.84 | 1954.16 | 0 | 0 | 13910 | 0 | 0 | 0 | 0 | 13910 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511309 | W-W-NI-180221-Picketlaw-Bauer Connections for Sludge removal | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523.23 | 523.23 | 7474.75 | 0 | 0 | 7997.98 | 0 | 0 | 0 | 0 | 7997.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511308 | W-W-NI-180221-Picketlaw-Redirect Sample tap waste | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3199.28 | 3199.28 | -0.28 | 0 | 0 | 3199 | 0 | 0 | 0 | 0 | 3199 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505801 | W-W-NI-180320- Muirdykes - Sludge Holding Tank Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 1344 | 13.88 | 1357.88 | 19186.12 | 0 | 0 | 20544 | 0 | 0 | 0 | 0 | 20544 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505812 | W-W-NI-180320-Blairlinnans WTW - Alum monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-19 |  | 2021-02-10 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 1653.18 | 26730.01 | 28383.19 | 203.81 | 0 | 0 | 28587 | 0 | 0 | 0 | 0 | 28587 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505793 | W-W-NI-180320-Greenbank - Replacement Sample Tap | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2021-05-01 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 1285.58 | 18378.21 | 19663.79 | -12.79 | 0 | 0 | 19651 | 0 | 0 | 0 | 0 | 19651 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505800 | W-W-NI-180320-Greenock - Final Water Sample Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-25 |  | 2020-08-26 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 3407.48 | 3645.48 | 0 | 0 | 0 | 3645.48 | 0 | 0 | 0 | 0 | 3645.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505787 | W-W-NI-180320-Greenock - IBC Replacement for Lime Batch Tanks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-19 |  | 2020-08-26 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 13.88 | 1613.88 | 0 | 0 | 0 | 1613.88 | 0 | 0 | 0 | 0 | 1613.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511889 | W-W-NI-180321-Afton-Sludge Trace Heating | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-22 |  | 2021-06-18 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 409.53 | 409.53 | 5365.74 | 0 | 0 | 5775.27 | 0 | 0 | 0 | 0 | 5775.27 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511902 | W-W-NI-180321-Balmichael-Lighting Upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-18 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 224 | 2934.84 | 0 | 0 | 3158.84 | 0 | 0 | 0 | 0 | 3158.84 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511903 | W-W-NI-180321-Bradan-Relift Pump 9-13 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-18 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283.53 | 283.53 | 3714.84 | 0 | 0 | 3998.37 | 0 | 0 | 0 | 0 | 3998.37 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511887 | W-W-NI-180321-Greenock-Sludge Poly Step Over | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-18 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.72 | 595.72 | 7805.16 | 0 | 0 | 8400.88 | 0 | 0 | 0 | 0 | 8400.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506648 | W-W-NI-180520-Picketlaw-PLC Scada Modifications | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-20 |  | 2021-05-01 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900.17 | 900.17 | 3200.83 | 0 | 0 | 4101 | 0 | 0 | 0 | 0 | 4101 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507256 | W-W-NI-180620-Bradan - 14 no. Power Control Units | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-07-24 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10251.12 | 10251.12 | 0 | 0 | 0 | 10251.12 | 0 | 0 | 0 | 0 | 10251.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507259 | W-WNI-180620-Bradan-Chlorine Building Roller Shutter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-10-09 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3179.14 | 3179.14 | 0 | 0 | 0 | 3179.14 | 0 | 0 | 0 | 0 | 3179.14 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507257 | W-W-NI-180620-Ladykirk-H&S Issues | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2020-09-07 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2353.16 | 2353.16 | 0 | 0 | 0 | 2353.16 | 0 | 0 | 0 | 0 | 2353.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508223 | W-W-NI-180820-Camphill-Ortho Building Drainage | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-20 |  | 2020-10-19 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1942.3 | 1942.3 | 0 | 0 | 0 | 1942.3 | 0 | 0 | 0 | 0 | 1942.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508224 | W-W-NI-180820-Camphill-Poly Sparge Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577.41 | 577.41 | 10317.59 | 0 | 0 | 10895 | 0 | 0 | 0 | 0 | 10895 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508228 | W-W-NI-180820-Finlas-Door Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-20 |  | 2020-10-21 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1624.01 | 1624.01 | 0 | 0 | 0 | 1624.01 | 0 | 0 | 0 | 0 | 1624.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508230 | W-W-NI-180820-Killin-Poly pump A | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-20 |  | 2020-09-25 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2381.23 | 2381.23 | 0 | 0 | 0 | 2381.23 | 0 | 0 | 0 | 0 | 2381.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508229 | W-W-NI-180820-Milngavie-Alum Pump A | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-20 |  | 2020-10-18 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7250.74 | 7250.74 | 0 | 0 | 0 | 7250.74 | 0 | 0 | 0 | 0 | 7250.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508226 | W-W-NI-180820-Turret-Filter 6 outlet valve repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-08-20 |  | 2020-10-12 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3944.16 | 3944.16 | 0 | 0 | 0 | 3944.16 | 0 | 0 | 0 | 0 | 3944.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508814 | W-W-NI180920-Muirdykes-Sodium Hydroxide Tank B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-18 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1874.81 | 1874.81 | 5990.19 | 0 | 0 | 7865 | 0 | 0 | 0 | 0 | 7865 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503854 | W-W-NI-181119-Belmore WTW-Mn Sampling | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2019-11-18 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4384.35 | -3950.35 | 434 | 6193.46 | 0 | 0 | 6627.46 | 0 | 0 | 0 | 0 | 6627.46 | 311236.79 | [5 empty] | N | CM_M&G | 100%
509866 | W-W-NI-181120-Carron Valley-Filter A air scour actuator valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-20 |  | 2021-03-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2530.54 | 2530.54 | 0 | 0 | 0 | 2530.54 | 0 | 0 | 0 | 0 | 2530.54 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509867 | W-W-NI-181120-Carron Valley-Sludge pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-20 |  | 2020-03-12 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6985.5 | 6985.5 | 0 | 0 | 0 | 6985.5 | 0 | 0 | 0 | 0 | 6985.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511347 | W-W-NI-190221-Alexandria-Filter Press Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-19 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337.77 | 337.77 | 4825.25 | 0 | 0 | 5163.02 | 0 | 0 | 0 | 0 | 5163.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511346 | W-W-NI-190221-Dhu Loch-Door Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-19 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208.04 | 208.04 | 2971.95 | 0 | 0 | 3179.99 | 0 | 0 | 0 | 0 | 3179.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505809 | W-W-NI-190320 - Loch Ascog - Inlet valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-19 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 340.91 | 62.46 | 403.37 | 4807.63 | 0 | 0 | 5211 | 0 | 0 | 0 | 0 | 5211 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505822 | W-W-NI-190320-Turret - Filter 3 washout rotork | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-19 |  | 2020-08-26 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 225.11 | 3229.28 | 3454.39 | 0 | 0 | 0 | 3454.39 | 0 | 0 | 0 | 0 | 3454.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506679 | W-W-NI-190520-Alexandria-lime room flooding investigation TE driver | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-20 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153.88 | 153.88 | 1986.12 | 0 | 0 | 2140 | 0 | 0 | 0 | 0 | 2140 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506678 | W-W-NI-190520-Alexandria-RGF 2 and 4 replacement-TE driver | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-20 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223.88 | 223.88 | 2986.12 | 0 | 0 | 3210 | 0 | 0 | 0 | 0 | 3210 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506694 | W-W-NI-190520-Blairlinnans-Press cloth | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-20 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17369.12 | 17369.12 | 0 | 0 | 0 | 17369.12 | 0 | 0 | 0 | 0 | 17369.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506672 | W-W-NI-190520-Burncrooks-Filter Investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-20 |  | 2020-08-31 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2940.41 | 2940.41 | 0 | 0 | 0 | 2940.41 | 0 | 0 | 0 | 0 | 2940.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507260 | W-W-NI-190620-Balmichael-Cl2 Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-23 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377.88 | 377.88 | 5186.12 | 0 | 0 | 5564 | 0 | 0 | 0 | 0 | 5564 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507261 | W-W-NI-190620-Midglen-Dosing Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-23 |  | 2021-03-23 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1167.63 | 1167.63 | 0 | 0 | 0 | 1167.63 | 0 | 0 | 0 | 0 | 1167.63 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508255 | W-W-NI-190820-Camphill-pH Instruments | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17897 | 17897 | 6820 | 0 | 0 | 24717 | 0 | 0 | 0 | 0 | 24717 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508254 | W-W-NI-190820-Camphill-Turbidity Meters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57143.4 | 57143.4 | 22036.6 | 0 | 0 | 79180 | 0 | 0 | 0 | 0 | 79180 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508253 | W-W-NI-190820-Muirdykes-Turbidity Meters | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23880.68 | 23880.68 | 70279.32 | 0 | 0 | 94160 | 0 | 0 | 0 | 0 | 94160 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504437 | W-W-NI-191219 - Amlaird WTW - LED Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-23 |  | 2020-03-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4114.95 | 0 | 4114.95 | 0 | 0 | 0 | 4114.95 | 0 | 0 | 0 | 0 | 4114.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504428 | W-W-NI-191219- Amlaird WTW - Replacement Washwater Actuator | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-12-23 |  | 2020-08-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4229 | 0.16 | 4229.16 | 0 | 0 | 0 | 4229.16 | 0 | 0 | 0 | 0 | 4229.16 | 311236.79 | [5 empty] | N | CM_WSI | 100%
505833 | W-W-NI-200320-Muirdykes - DAF No. 1 Gearbox | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-03-26 |  | 2020-08-26 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 3200.63 | 13.88 | 3214.51 | -4.51 | 0 | 0 | 3210 | 0 | 0 | 0 | 0 | 3210 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506719 | W-W-NI-200520-Afton-Cl2 Changeover Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-21 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11216.41 | 11216.41 | 5208.59 | 0 | 0 | 16425 | 0 | 0 | 0 | 0 | 16425 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506726 | W-W-NI-200520-Balmichael-Door Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-05-21 |  | 2021-02-25 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16283.62 | 16283.62 | 0 | 0 | 0 | 16283.62 | 0 | 0 | 0 | 0 | 16283.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506718 | W-W-NI-200520-Penwhapple-Cl2 Changeover Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-05-21 |  | 2021-02-25 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11693.88 | 11693.88 | 2858.12 | 0 | 0 | 14552 | 0 | 0 | 0 | 0 | 14552 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508407 | W-W-NI-200820- CARTSIDE ROAD WWPS NS577562 - REPLACE PUMP GUIDE BRACKET - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-28 |  | 2020-11-04 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7709.84 | 7709.84 | -3709.84 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509330 | W-W-NI-201020-Bradan-LCC Monitore | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-22 |  | 2020-11-25 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1511.88 | 1511.88 | 0 | 0 | 0 | 1511.88 | 0 | 0 | 0 | 0 | 1511.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509328 | W-W-NI-201020-Bradan-Louvre Windows | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-22 |  | 2020-11-21 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3475.35 | 3475.35 | 0 | 0 | 0 | 3475.35 | 0 | 0 | 0 | 0 | 3475.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509329 | W-W-NI-201020-Corrie-Treated Water Colour Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-22 |  | 2020-11-06 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3798.5 | 3798.5 | 0 | 0 | 0 | 3798.5 | 0 | 0 | 0 | 0 | 3798.5 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509327 | W-W-NI-201020-Picketlaw-Alum Monitors | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-22 |  | 2021-04-01 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14071.95 | 14071.95 | 0 | 0 | 0 | 14071.95 | 0 | 0 | 0 | 0 | 14071.95 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509904 | W-W-NI-201120-Amlaird-Additional Analogue-Digital Panel and Cards | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-20 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29535.26 | 29535.26 | 55839.74 | 0 | 0 | 85375 | 0 | 0 | 0 | 0 | 85375 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504442 | W-W-NI-201219 - Balmore WTW - Water Colour Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-23 |  | 2020-03-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 14007.93 | 0 | 14007.93 | 0 | 0 | 0 | 14007.93 | 0 | 0 | 0 | 0 | 14007.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504450 | W-W-NI-201219 - Carron Valley Replace poly dosing pumps | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS4 |  | 2019-12-23 |  | 2020-10-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 24709 | 0.08 | 24709.08 | -0.08 | 0 | 0 | 24709 | 0 | 0 | 0 | 0 | 24709 | 311236.79 | [5 empty] | N | CM_WSI | 100%
504447 | W-W-NI-201219- Carron Valley WTW Rotork valve | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 |  | 2019-12-23 |  | 2020-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2767.35 | 34.7 | 2802.05 | 0 | 0 | 0 | 2802.05 | 0 | 0 | 0 | 0 | 2802.05 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510809 | W-W-NI-210120-Turret-Pumpstandalone controller PLCHMI | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-22 |  | 2021-03-12 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10281.88 | 10281.88 | 432 | 0 | 0 | 10713.88 | 0 | 0 | 0 | 0 | 10713.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505346 | W-W-NI-210220-Burncrooks WTW - Sludge Press cloths | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-28 |  | 2020-08-19 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15325.7 | 15325.7 | 0 | 0 | 0 | 15325.7 | 0 | 0 | 0 | 0 | 15325.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505341 | W-W-NI-210220-Camphill - Sludge Plate Overhaul | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-02-25 |  | 2020-04-12 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2814.48 | 8985.65 | 11800.13 | -73.13 | 0 | 0 | 11727 | 0 | 0 | 0 | 0 | 11727 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506750 | W-W-NI-210320-Lochranza-Door Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-05-22 |  | 2021-02-25 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17430.88 | 17430.88 | 0 | 0 | 0 | 17430.88 | 0 | 0 | 0 | 0 | 17430.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506751 | W-W-NI-210520-Corrie-Door Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-05-22 |  | 2021-02-28 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18297.6 | 18297.6 | 0 | 0 | 0 | 18297.6 | 0 | 0 | 0 | 0 | 18297.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506732 | W-W-NI-210520-Kildonan-Door Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-05-21 |  | 2021-02-28 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12811.45 | 12811.45 | 0 | 0 | 0 | 12811.45 | 0 | 0 | 0 | 0 | 12811.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506734 | W-W-NI-210520-Kilmory Upper-Door Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-05-21 |  | 2021-03-05 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12505.41 | 12505.41 | 0 | 0 | 0 | 12505.41 | 0 | 0 | 0 | 0 | 12505.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506735 | W-W-NI-210520-Whiting Bay-Door Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-05-22 |  | 2021-02-25 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12505.41 | 12505.41 | 0 | 0 | 0 | 12505.41 | 0 | 0 | 0 | 0 | 12505.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507791 | W-W-NI-210720-Busbiemuir-Secondary Disinfection | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-22 |  | 2020-08-18 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7447.1 | 7447.1 | 0 | 0 | 0 | 7447.1 | 0 | 0 | 0 | 0 | 7447.1 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509349 | W-W-NI-211020-Afton-Washwater Tank 3 Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-22 |  | 2021-03-28 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13097.61 | 13097.61 | 0 | 0 | 0 | 13097.61 | 0 | 0 | 0 | 0 | 13097.61 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509352 | W-W-NI-211020-Alexandria-Ladders DAF Tank Cleaning | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-22 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594.21 | 594.21 | 8590.79 | 0 | 0 | 9185 | 0 | 0 | 0 | 0 | 9185 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509351 | W-W-NI-211020-Belmore-Lime dosing system deep clean | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-22 |  | 2021-02-10 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8568.59 | 8568.59 | 1637.41 | 0 | 0 | 10206 | 0 | 0 | 0 | 0 | 10206 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509348 | W-W-NI-211020-Greenock-DCI Face plates | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-22 |  | 2021-05-01 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.15 | 353.15 | 4832.85 | 0 | 0 | 5186 | 0 | 0 | 0 | 0 | 5186 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503912 | W-W-NI-211119-Bradan WTW - Sludge Press C Filter Cloth Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-11-22 |  | 2020-08-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 11999.23 | 221.3 | 12220.53 | 5916.47 | 0 | 0 | 18137 | 0 | 0 | 0 | 0 | 18137 | 119022.58 | [5 empty] | N | Wa6 | 100%
510459 | W-W-NI-211220-Finlas-UPS Battery Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-21 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.69 | 114.69 | 1426.31 | 0 | 0 | 1541 | 0 | 0 | 0 | 0 | 1541 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510468 | W-W-NI-211220-Greenock-Alum Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4440.73 | 4440.73 | 10361.26 | 0 | 0 | 14801.99 | 0 | 0 | 0 | 0 | 14801.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510461 | W-W-NI-211220-Milngavie-RFG Chemical clean | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3478.88 | 3478.88 | 49486.12 | 0 | 0 | 52965 | 0 | 0 | 0 | 0 | 52965 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510469 | W-W-NI-211220-Muirdykes-2RGF Actuated Valves Checks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.43 | 177.43 | 2322.56 | 0 | 0 | 2499.99 | 0 | 0 | 0 | 0 | 2499.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510470 | W-W-NI-211220-Penwhapple-Inlet Poly Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-28 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2109.73 | 2109.73 | 30.29 | 0 | 0 | 2140.02 | 0 | 0 | 0 | 0 | 2140.02 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510460 | W-W-NI-211220-Picketlaw-Path to bypass valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.5 | 177.5 | 2323.5 | 0 | 0 | 2501 | 0 | 0 | 0 | 0 | 2501 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506770 | W-W-NI-220520-Alexandria-Press wash pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-22 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685.88 | 685.88 | 9586.12 | 0 | 0 | 10272 | 0 | 0 | 0 | 0 | 10272 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506771 | W-W-NI-220520-Blairlinnans-RGF 304 outlet valve actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-22 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3439.81 | 3439.81 | 0 | 0 | 0 | 3439.81 | 0 | 0 | 0 | 0 | 3439.81 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506769 | W-W-NI-220520-Carron Valley-Female changing room | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-22 |  | 2020-07-07 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3553.47 | 3553.47 | 0 | 0 | 0 | 3553.47 | 0 | 0 | 0 | 0 | 3553.47 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506768 | W-W-NI-220520-Strathyre-final sample hut roof leak | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-22 |  | 2020-09-08 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3554.13 | 3554.13 | 0 | 0 | 0 | 3554.13 | 0 | 0 | 0 | 0 | 3554.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508873 | W-W-NI-220920-Balmore-Alum Monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14391.32 | 14391.32 | 0 | 0 | 0 | 14391.32 | 0 | 0 | 0 | 0 | 14391.32 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508883 | W-W-NI-220920-Belmore-Cl2 Changeover Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-25 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8104.13 | 8104.13 | 0 | 0 | 0 | 8104.13 | 0 | 0 | 0 | 0 | 8104.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508875 | W-W-NI-220920-Milngavie-Overview Scada Screen | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450.89 | 450.89 | 6229.11 | 0 | 0 | 6680 | 0 | 0 | 0 | 0 | 6680 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508857 | W-W-NI-220920-Muirdykes-Secondary Filter Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199.41 | 199.41 | 2636.59 | 0 | 0 | 2836 | 0 | 0 | 0 | 0 | 2836 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509390 | W-W-NI-221020-Carron Valley-CMAC UPS bypass | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-23 |  | 2020-11-13 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1266.64 | 1266.64 | 0 | 0 | 0 | 1266.64 | 0 | 0 | 0 | 0 | 1266.64 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509389 | W-W-NI-221020-Carron Valley-PAC dosing point | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-23 |  | 2021-02-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7165.88 | 7165.88 | 0 | 0 | 0 | 7165.88 | 0 | 0 | 0 | 0 | 7165.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509392 | W-W-NI-221020-Crianlarich-Final turbidity meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3902.51 | 3902.51 | 0 | 0 | 0 | 3902.51 | 0 | 0 | 0 | 0 | 3902.51 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509393 | W-W-NI-221020-Faughlin resi-Boundary fence | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 210 | 3000 | 0 | 0 | 3210 | 0 | 0 | 0 | 0 | 3210 | 311236.79 | [5 empty] | N | CM_WSI | 100%
510476 | W-W-NI-221220-Carron Valley-Sludge press A and B wash carriage upgrade | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668.93 | 668.93 | 9556.05 | 0 | 0 | 10224.98 | 0 | 0 | 0 | 0 | 10224.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510482 | W-W-NI-221220-Kirkhill-Roof replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4870.63 | 4870.63 | -13.63 | 0 | 0 | 4857 | 0 | 0 | 0 | 0 | 4857 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510481 | W-W-NI-221220-Limerigg-Pumping station-replacement Manifold | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242.07 | 242.07 | 3245.94 | 0 | 0 | 3488.01 | 0 | 0 | 0 | 0 | 3488.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510483 | W-W-NI-221220-Strathyre-HS access platform | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-12-22 |  | 2021-04-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5622.55 | 5622.55 | 0.45 | 0 | 0 | 5623 | 0 | 0 | 0 | 0 | 5623 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510473 | W-W-NI-221220-Turret-Big sludge press cloth | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759.86 | 759.86 | 10855.14 | 0 | 0 | 11615 | 0 | 0 | 0 | 0 | 11615 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510472 | W-W-NI-221220-Turret-Entry gate cattle grid broken | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3330.88 | 3330.88 | -13.88 | 0 | 0 | 3317 | 0 | 0 | 0 | 0 | 3317 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510474 | W-W-NI-221220-Turret-Lime plant replacement kit | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-12-22 |  | 2021-03-23 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4539.31 | 4539.31 | 0 | 0 | 0 | 4539.31 | 0 | 0 | 0 | 0 | 4539.31 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
511400 | W-W-NI-230221-Amlaird-Replacement Inlet Poly Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551.3 | 551.3 | 7875.7 | 0 | 0 | 8427 | 0 | 0 | 0 | 0 | 8427 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505891 | W-W-NI-230320-Gorbals Drumboyhill - Outlet Valve No 2 Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-03-26 |  | 2020-05-13 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 8690.89 | 12108.14 | 20799.03 | 0 | 0 | 0 | 20799.03 | 0 | 0 | 0 | 0 | 20799.03 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505895 | W-W-NI-230320-Turret - Lime system investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 114.16 | 13.88 | 128.04 | 1616.96 | 0 | 0 | 1745 | 0 | 0 | 0 | 0 | 1745 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506331 | W-W-NI-230420-Hillfarm - Telemetry Building | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-24 |  | 2020-08-26 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5593.53 | 5593.53 | 0 | 0 | 0 | 5593.53 | 0 | 0 | 0 | 0 | 5593.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507304 | W-W-NI-230620-Belmore-Welfare facilities repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-25 |  | 2020-08-25 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6617.23 | 6617.23 | 0 | 0 | 0 | 6617.23 | 0 | 0 | 0 | 0 | 6617.23 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508896 | W-W-NI-230920-Afton-Roof Leaks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.88 | 118.88 | 1486.12 | 0 | 0 | 1605 | 0 | 0 | 0 | 0 | 1605 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508894 | W-W-NI-230920-Bradan-Power Factor Correction | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46019.61 | 46019.61 | -19964.61 | 0 | 0 | 26055 | 0 | 0 | 0 | 0 | 26055 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508889 | W-W-NI-230920-Katrine Membrane Plant-Replacement Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2021-02-10 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6040.61 | 6040.61 | 0 | 0 | 0 | 6040.61 | 0 | 0 | 0 | 0 | 6040.61 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508893 | W-W-NI-230920-Muirdykes-SRGF Backwash Flow Controls | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.11 | 187.11 | 2460.89 | 0 | 0 | 2648 | 0 | 0 | 0 | 0 | 2648 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508895 | W-W-NI-230920-Penwhapple-DAF Davits | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-23 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468.88 | 468.88 | 6486.12 | 0 | 0 | 6955 | 0 | 0 | 0 | 0 | 6955 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508888 | W-W-NI-230920-Picketlaw- DAF Flushing Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-23 |  | 2020-11-19 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9 | 117.9 | 0 | 0 | 0 | 117.9 | 0 | 0 | 0 | 0 | 117.9 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509435 | W-W-NI-231020-Afton-pH Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-10-23 |  | 2021-03-08 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5915.99 | 5915.99 | 0 | 0 | 0 | 5915.99 | 0 | 0 | 0 | 0 | 5915.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509434 | W-W-NI-231020-Bairdsknowe -pH Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4222.83 | 4222.83 | 1626.17 | 0 | 0 | 5849 | 0 | 0 | 0 | 0 | 5849 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509431 | W-W-NI-231020-Bearyards Tower-Flow meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653.76 | 653.76 | 9127.24 | 0 | 0 | 9781 | 0 | 0 | 0 | 0 | 9781 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509432 | W-W-NI-231020-High Borland-pH Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-10-23 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4222.38 | 4222.38 | 1626.62 | 0 | 0 | 5849 | 0 | 0 | 0 | 0 | 5849 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505379 | W-W-NI-240220-Carrick Castle - CL2 dosing pump replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-28 |  | 2020-08-26 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 1223.28 | 18.47 | 1241.75 | 0 | 0 | 0 | 1241.75 | 0 | 0 | 0 | 0 | 1241.75 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505380 | W-W-NI-240220-Carrick Castle- Raw inlet valve actuator replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-28 |  | 2020-04-14 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1383.05 | 1383.05 | 0 | 0 | 0 | 1383.05 | 0 | 0 | 0 | 0 | 1383.05 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505382 | W-W-NI-240220-Picketlaw - Thickening sludge Pipework replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-02-28 |  | 2020-08-26 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 1389.1 | 27.7 | 1416.8 | 70.2 | 0 | 0 | 1487 | 0 | 0 | 0 | 0 | 1487 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505910 | W-W-NI-240320-Carron Valley- Roof replace bullnoses | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-03-26 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 416.01 | 13.88 | 429.89 | 5929.11 | 0 | 0 | 6359 | 0 | 0 | 0 | 0 | 6359 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512007 | W-W-NI-240321-Turret-Filter 6 media and Nozzle | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-25 |  | 2021-06-24 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5411 | 5411 | 77300 | 0 | 0 | 82711 | 0 | 0 | 0 | 0 | 82711 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507303 | W-W-NI-240620-Belmore-Final lime pump B stroke controller replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-25 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258.09 | 258.09 | 3474.91 | 0 | 0 | 3733 | 0 | 0 | 0 | 0 | 3733 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507301 | W-W-NI-240620-Dhu Loch-MSP pump 1 replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-02 |  | 2020-07-21 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2088.12 | 2088.12 | 0 | 0 | 0 | 2088.12 | 0 | 0 | 0 | 0 | 2088.12 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507302 | W-W-NI-240620-Finlas-Service water pump A replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-25 |  | 2020-09-25 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1628.6 | 1628.6 | 0 | 0 | 0 | 1628.6 | 0 | 0 | 0 | 0 | 1628.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507855 | W-W-NI-240720-Corsehouse Reservoir-Contribution for Fencing | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-24 |  | 2021-03-23 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3801.49 | 3801.49 | 0 | 0 | 0 | 3801.49 | 0 | 0 | 0 | 0 | 3801.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508942 | W-W-NI-240920-Alexandria-Cl2 Changeover Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-25 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543.13 | 543.13 | 7546.87 | 0 | 0 | 8090 | 0 | 0 | 0 | 0 | 8090 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508909 | W-W-NI-240920-Carron Valley-Filter G turbidity meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-25 |  | 2020-10-22 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8613.48 | 8613.48 | 0 | 0 | 0 | 8613.48 | 0 | 0 | 0 | 0 | 8613.48 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508941 | W-W-NI-240920-Finlas-Cl2 Changeover Panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-09-25 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.25 | 529.25 | 7560.75 | 0 | 0 | 8090 | 0 | 0 | 0 | 0 | 8090 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508910 | W-W-NI-240920-Gartcarron-Hypo dosing system | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-25 |  | 2020-10-12 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4176.88 | 4176.88 | 0 | 0 | 0 | 4176.88 | 0 | 0 | 0 | 0 | 4176.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508907 | W-W-NI-240920-Turret-Sludge press cloths | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-09-25 |  | 2020-11-06 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5906.3 | 5906.3 | 0 | 0 | 0 | 5906.3 | 0 | 0 | 0 | 0 | 5906.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510875 | W-W-NI-250121-Amlaird-Sludge Conveyor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10328.69 | 10328.69 | -13.69 | 0 | 0 | 10315 | 0 | 0 | 0 | 0 | 10315 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510854 | W-W-NI-250121-Turret-Caustic pumps flow paced control | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-29 |  | 2021-03-04 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7276.76 | 7276.76 | -93.88 | 0 | 0 | 7182.88 | 0 | 0 | 0 | 0 | 7182.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506797 | W-W-NI-250520-Amlaird-Sludge Lagoon Pipework | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-29 |  | 2020-07-30 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90495.93 | 90495.93 | 0 | 0 | 0 | 90495.93 | 0 | 0 | 0 | 0 | 90495.93 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506795 | W-W-NI-250520-Bankell-Sump Pumps Install | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-29 |  | 2021-02-10 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2410.24 | 2410.24 | 0 | 0 | 0 | 2410.24 | 0 | 0 | 0 | 0 | 2410.24 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506796 | W-W-NI-250520-Dalwhatswood-Drive Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-29 |  | 2021-03-23 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3466.28 | 3466.28 | 0 | 0 | 0 | 3466.28 | 0 | 0 | 0 | 0 | 3466.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506808 | W-W-NI-250520-Picketlaw-Repairs to access road | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-29 |  | 2020-09-21 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8885.49 | 8885.49 | 0 | 0 | 0 | 8885.49 | 0 | 0 | 0 | 0 | 8885.49 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507318 | W-W-NI-250620-Alexandria-Supernatent pump 1 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-25 |  | 2021-03-23 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5494.28 | 5494.28 | 0 | 0 | 0 | 5494.28 | 0 | 0 | 0 | 0 | 5494.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507316 | W-W-NI-250620-Belmore-Alum monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-26 |  | 2020-10-02 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27803.13 | 27803.13 | 0 | 0 | 0 | 27803.13 | 0 | 0 | 0 | 0 | 27803.13 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507319 | W-W-NI-250620-Blairlinnans-Lagoon sampling | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-26 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511.99 | 511.99 | 7102.01 | 0 | 0 | 7614 | 0 | 0 | 0 | 0 | 7614 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507317 | W-W-NI-250620-Cairndow-Inlet valve actuator | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-25 |  | 2020-09-26 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3275.3 | 3275.3 | 0 | 0 | 0 | 3275.3 | 0 | 0 | 0 | 0 | 3275.3 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503952 | W-W-NI-251119-Bradan WTW - Carrier Water Relocation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-11-26 |  | 2020-10-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 27360.65 | 18441.96 | 45802.61 | 0 | 0 | 0 | 45802.61 | 0 | 0 | 0 | 0 | 45802.61 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510890 | W-W-NI-260121-Afton-CCT Actuated Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1099 | 1099 | 15700 | 0 | 0 | 16799 | 0 | 0 | 0 | 0 | 16799 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510879 | W-W-NI-260121-Afton-Final Turbidity Monitor Installation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7937.95 | 7937.95 | 5314.04 | 0 | 0 | 13251.99 | 0 | 0 | 0 | 0 | 13251.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510880 | W-W-NI-260121-Afton-Sludge Poly Bund Repair | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391.09 | 391.09 | 5388.8 | 0 | 0 | 5779.89 | 0 | 0 | 0 | 0 | 5779.89 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510889 | W-W-NI-260121-Camphill-Air Scour Flow Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-29 |  | 2021-03-12 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210 | 2210 | 37 | 0 | 0 | 2247 | 0 | 0 | 0 | 0 | 2247 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510881 | W-W-NI-260121-Muirdykes-Temporary 2RGF Turbidity Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573.88 | 573.88 | 8000 | 0 | 0 | 8573.88 | 0 | 0 | 0 | 0 | 8573.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510888 | W-W-NI-260121-Penwhapple-Sludge Pipework Trace Heating | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-29 |  | 2021-04-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025.36 | 2025.36 | 7.64 | 0 | 0 | 2033 | 0 | 0 | 0 | 0 | 2033 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505416 | W-W-NI-260220-Balmore WTW - Replacement Thermometers | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2021-05-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.7 | 18.7 | 1854.3 | 0 | 0 | 1873 | 0 | 0 | 0 | 0 | 1873 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505427 | W-W-NI-260220-Glenhove DSR - Retrofit AK Breaker Dal No 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-02-27 |  | 2020-09-07 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10505.88 | 10505.88 | 0 | 0 | 0 | 10505.88 | 0 | 0 | 0 | 0 | 10505.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506819 | W-W-NI-260520-Amlaird-Road repairs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-29 |  | 2020-09-29 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4815.85 | 4815.85 | 0 | 0 | 0 | 4815.85 | 0 | 0 | 0 | 0 | 4815.85 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506822 | W-W-NI-260520-Broadside-Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-05-29 |  | 2021-03-12 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11110.83 | 11110.83 | 2799.17 | 0 | 0 | 13910 | 0 | 0 | 0 | 0 | 13910 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506824 | W-W-NI-260520-Hill of Row-Radio link | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-29 |  | 2020-06-16 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2961.6 | 2961.6 | 0 | 0 | 0 | 2961.6 | 0 | 0 | 0 | 0 | 2961.6 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507344 | W-W-NI-260620-Carron Valley-Lime plant new actuated valves | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-06-26 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27542.51 | 27542.51 | 36657.49 | 0 | 0 | 64200 | 0 | 0 | 0 | 0 | 64200 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507346 | W-W-NI-260620-Carron Valley-New Hypo pump B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-26 |  | 2020-08-11 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5054.58 | 5054.58 | 0 | 0 | 0 | 5054.58 | 0 | 0 | 0 | 0 | 5054.58 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503986 | W-W-NI-261119-Carron Valley WTW - Interlock Valve | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-11-26 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1938.16 | 0 | 1938.16 | 0 | 0 | 0 | 1938.16 | 0 | 0 | 0 | 0 | 1938.16 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504873 | W-W-NI-270120-Afton WTW - Lamella Feed Pumps Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-27 |  | 2020-05-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3705.46 | 1085.4 | 4790.86 | 0 | 0 | 0 | 4790.86 | 0 | 0 | 0 | 0 | 4790.86 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504870 | W-W-NI-270120-Afton WTW - Sludge Tanker Turning Area | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-27 |  | 2020-06-30 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2904.33 | 817.29 | 3721.62 | 0 | 0 | 0 | 3721.62 | 0 | 0 | 0 | 0 | 3721.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504868 | W-W-NI-270120-Bradan WTW - Sludge Buffer Tank Mixer | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-27 |  | 2020-02-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2235.36 | 0 | 2235.36 | 0 | 0 | 0 | 2235.36 | 0 | 0 | 0 | 0 | 2235.36 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504874 | W-W-NI-270120-Penwhapple WTW - GAC Air Scour Flow Meter | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-27 |  | 2020-07-23 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2502.41 | -2502.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
510901 | W-W-NI-270121-Alexandria-Lime Dosing System Jetting and CCTV Survey | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168.39 | 168.39 | 2405.6 | 0 | 0 | 2573.99 | 0 | 0 | 0 | 0 | 2573.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510899 | W-W-NI-270121-Belmore WTW - UPS Battery | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2021-01-29 |  | 2021-03-27 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177 | 1177 | 0 | 0 | 0 | 1177 | 0 | 0 | 0 | 0 | 1177 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510900 | W-W-NI-270121-Blairlinnans Chlorine Catchpot | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404.82 | 404.82 | 5783.16 | 0 | 0 | 6187.98 | 0 | 0 | 0 | 0 | 6187.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510918 | W-W-NI-270121-Camphill-Hypo Dosing Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406.79 | 406.79 | 5811.2 | 0 | 0 | 6217.99 | 0 | 0 | 0 | 0 | 6217.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510919 | W-W-NI-270121-Thornliebank-Pump No 2 Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12709.36 | 12709.36 | -0.36 | 0 | 0 | 12709 | 0 | 0 | 0 | 0 | 12709 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505437 | W-W-NI-270220-Crianlarich new road investigation | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2022-02-10 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 1284 | 13542 | 14826 | 73520.82 | 0 | 0 | 88346.82 | 0 | 0 | 0 | 0 | 88346.82 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505433 | W-W-NI-270220-Drumchapel WT - 2 VSDs | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-02-27 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.88 | 13.88 | 2297.12 | 0 | 0 | 2311 | 0 | 0 | 0 | 0 | 2311 | 119022.58 | [5 empty] | N | WSNI | 100%
505957 | W-W-NI-270320-Carron Valley - Heaters replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190.25 | 190.25 | 2505.75 | 0 | 0 | 2696 | 0 | 0 | 0 | 0 | 2696 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505954 | W-W-NI-270320-Dhu Loch - post soda pump B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-03 |  | 2020-05-20 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3097.57 | 3097.57 | 0 | 0 | 0 | 3097.57 | 0 | 0 | 0 | 0 | 3097.57 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505955 | W-W-NI-270320-Ross Priory-Blairlinnans No2 motor cable | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-03 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11466.41 | 11466.41 | 3513.59 | 0 | 0 | 14980 | 0 | 0 | 0 | 0 | 14980 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
505958 | W-W-NI-270320-Tyndrum Heater replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-03 |  | 2020-07-03 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2677.55 | 2677.55 | 0 | 0 | 0 | 2677.55 | 0 | 0 | 0 | 0 | 2677.55 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506842 | W-W-NI-270520-TURRET WTW - SCADA SYSTEM Telemetry Proposal | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-06-05 | 2020-12-07 | 2021-07-26 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52711 | 52711 | 18784.52 | 0 | 0 | 71495.52 | 0 | 0 | 0 | 0 | 71495.52 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507877 | W-W-NI-270720-Picketlaw-Replacement pH Holders | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-27 |  | 2020-11-19 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3237.2 | 3237.2 | 0 | 0 | 0 | 3237.2 | 0 | 0 | 0 | 0 | 3237.2 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
508530 | W-W-NI-270820- COLLIER ST SPS - REPLACE NRV - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1588.79 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504014 | W-W-NI-271119-Belmore WTW - TE item Mn stage recommissioning scope | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 |  | 2020-01-29 | 2021-05-13 | 2021-09-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 10700 | -4400 | 6300 | 16400.83 | 0 | 0 | 22700.83 | 0 | 0 | 0 | 0 | 22700.83 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
503998 | W-W-NI-271119-Penwhapple WTW - Ortho Bund Investigations | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 |  | 2020-01-29 | 2020-09-10 | 2021-08-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1382.09 | 1404.91 | 2787 | 2562.92 | 0 | 0 | 5349.92 | 0 | 0 | 0 | 0 | 5349.92 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510028 | W-W-NI-271120-Burncrooks-UPS Replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-11-27 |  | 2020-10-12 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2779.87 | 2779.87 | 0 | 0 | 0 | 2779.87 | 0 | 0 | 0 | 0 | 2779.87 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504885 | W-W-NI-280120-Bradan WTW - Coag Lime Pump B | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-29 |  | 2020-04-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 12626.63 | 20.82 | 12647.45 | 0 | 0 | 0 | 12647.45 | 0 | 0 | 0 | 0 | 12647.45 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504879 | W-W-NI-280120-Camphill WTW - Thickened Sludge Transfer Pump 2 R&S | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-29 |  | 2020-02-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2772.74 | 13.88 | 2786.62 | 0 | 0 | 0 | 2786.62 | 0 | 0 | 0 | 0 | 2786.62 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504880 | W-W-NI-280120-Castlehill TWP - Pump 2 Motor Refurb | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-01-29 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8319.44 | 36.94 | 8356.38 | 0 | 0 | 0 | 8356.38 | 0 | 0 | 0 | 0 | 8356.38 | 119022.58 | [5 empty] | N | WSNI | 100%
504881 | W-W-NI-280120-Muirdykes WTW - DAF Scraper No. 2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-29 |  | 2020-02-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3644.19 | 13.88 | 3658.07 | 0 | 0 | 0 | 3658.07 | 0 | 0 | 0 | 0 | 3658.07 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510948 | W-W-NI-280121-Killin-Alum monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3827.05 | 3827.05 | 10902.95 | 0 | 0 | 14730 | 0 | 0 | 0 | 0 | 14730 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510946 | W-W-NI-280121-Turret-Alum monitor | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3827.05 | 3827.05 | 10902.95 | 0 | 0 | 14730 | 0 | 0 | 0 | 0 | 14730 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506886 | W-W-NI-280520-Amlaird-Gas detection panel | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-29 |  | 2020-06-19 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3333.01 | 3333.01 | 0 | 0 | 0 | 3333.01 | 0 | 0 | 0 | 0 | 3333.01 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506911 | W-W-NI-280520-Pirnmill-Road Repair Contribution | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-06-01 |  | 2020-11-25 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.88 | 120.88 | 0 | 0 | 0 | 120.88 | 0 | 0 | 0 | 0 | 120.88 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509524 | W-W-NI-281020-Auchenback-Mould Removal | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-10-28 |  | 2020-01-12 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSNI | 100%
504897 | W-W-NI-290120-Amlaird WTW-Chlorine Injectors replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-29 |  | 2020-08-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3492.11 | 13.88 | 3505.99 | 0 | 0 | 0 | 3505.99 | 0 | 0 | 0 | 0 | 3505.99 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504895 | W-W-NI-290120-Amlaird WTW-DAF 3 Turbidity Meter replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-29 |  | 2020-03-12 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5551.71 | 13.88 | 5565.59 | 0 | 0 | 0 | 5565.59 | 0 | 0 | 0 | 0 | 5565.59 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504899 | W-W-NI-290120-Bradan WTW - PRGF 1-8 Filter Nozzle Clean (4th of 8) | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-29 |  | 2020-04-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 29630.51 | 13.88 | 29644.39 | 0 | 0 | 0 | 29644.39 | 0 | 0 | 0 | 0 | 29644.39 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
510967 | W-W-NI-290121-Bankell-Refurbishment of Stone Wall | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-01-29 |  | 2021-05-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153.3 | 1153.3 | 16475.68 | 0 | 0 | 17628.98 | 0 | 0 | 0 | 0 | 17628.98 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506386 | W-W-NI-290420-Amlaird - Replacement DAF Shaft | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-04-30 |  | 2020-08-26 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3007.35 | 3007.35 | 0 | 0 | 0 | 3007.35 | 0 | 0 | 0 | 0 | 3007.35 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506383 | W-W-NI-290420-Amlaird - Supernatant Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-04-30 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14493.7 | 14493.7 | 0 | 0 | 0 | 14493.7 | 0 | 0 | 0 | 0 | 14493.7 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506905 | W-W-NI-290520-Carron Valley-Filters top up and skim | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-05-29 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138005.94 | 138005.94 | 7107.07 | 0 | 0 | 145113 | 0 | 0 | 0 | 0 | 145113 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507399 | W-W-NI-290620-Carron Valley-Rotork replacement | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-07-02 |  | 2020-08-12 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5188.43 | 5188.43 | 0 | 0 | 0 | 5188.43 | 0 | 0 | 0 | 0 | 5188.43 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504084 | W-W-NI-291119 - Bradan WTW - Backwash Chamber Cover Plates | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-02 |  | 2020-02-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 13212.53 | 0 | 13212.53 | 0 | 0 | 0 | 13212.53 | 0 | 0 | 0 | 0 | 13212.53 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504074 | W-W-NI-291119 - Brig o Turk Comms link | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2019-12-02 |  | 2019-12-18 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1915.28 | 0 | 1915.28 | 0 | 0 | 0 | 1915.28 | 0 | 0 | 0 | 0 | 1915.28 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504194 | W-W-NI-291119- Alloa WWTW NS887918 - SR15 Support survey (MCC) - 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -1869.16 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504067 | W-W-NI-291119-Turret WTW Poly Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2019-11-29 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2284.74 | 0 | 2284.74 | 0 | 0 | 0 | 2284.74 | 0 | 0 | 0 | 0 | 2284.74 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504931 | W-W-NI-300120-Bradan WTW - PRGF 5 Trough Leaks | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-01-30 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4224.53 | 13.88 | 4238.41 | 0 | 0 | 0 | 4238.41 | 0 | 0 | 0 | 0 | 4238.41 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504932 | W-W-NI-300120-Penwhapple WTW - Sludge Thickener Feed Pumps | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-01-30 |  | 2020-09-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 6006.72 | 2542.93 | 8549.65 | 0 | 0 | 0 | 8549.65 | 0 | 0 | 0 | 0 | 8549.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504947 | W-W-NI-300120-Turret WTW PACL pump no2 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-01-30 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2517.73 | 13.88 | 2531.61 | 0 | 0 | 0 | 2531.61 | 0 | 0 | 0 | 0 | 2531.61 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
512110 | W-W-NI-300321-Amlaird WTW-Press Platform Investigation | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 |  | 2021-04-01 | 2021-12-24 | 2022-08-08 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000.04 | 0 | 0 | 5000.04 | 0 | 0 | 0 | 0 | 5000.04 | 311236.79 | [5 empty] | N | CM_M&G | 100%
512108 | W-W-NI-300321-Loch Eck-Sludge Thickener Feed Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2021-03-30 |  | 2021-06-30 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 817.3 | 817.3 | 10708.26 | 0 | 0 | 11525.56 | 0 | 0 | 0 | 0 | 11525.56 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506406 | W-W-NI-300420-Afton - Roof Lashings | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-01 |  | 2020-08-26 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1429.65 | 1429.65 | 0 | 0 | 0 | 1429.65 | 0 | 0 | 0 | 0 | 1429.65 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
506497 | W-W-NI-300420-ARDOCH WWTW 2002 NS374758- REPLACE PANELS ON FINE SCREEN A - 5.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-06-03 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5279.04 | 5279.04 | 0 | 0 | 0 | 5279.04 | 0 | 0 | 0 | 0 | 5279.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506418 | W-W-NI-300420-Bradan - Sludge Thickener Feed Pump C | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 |  | 2020-05-01 |  | 2020-11-09 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2269.91 | 2269.91 | 0 | 0 | 0 | 2269.91 | 0 | 0 | 0 | 0 | 2269.91 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507964 | W-W-NI-300720-Amlaird- Washwater pumps repl. | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-08-04 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1191.78 | 1191.78 | 16813.22 | 0 | 0 | 18005 | 0 | 0 | 0 | 0 | 18005 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509557 | W-W-NI-301020-Muirdykes-Hypo Pump | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 |  | 2020-11-04 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406 | 406 | 5800 | 0 | 0 | 6206 | 0 | 0 | 0 | 0 | 6206 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
509558 | W-W-NI-301020-Muirdykes-Sodium Hydroxide Line Flush | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-11-05 |  | 2021-02-15 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5093.04 | 5093.04 | 0 | 0 | 0 | 5093.04 | 0 | 0 | 0 | 0 | 5093.04 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
504955 | W-W-NI-310120-Highlees SR - Lighting | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 |  | 2020-02-03 |  | 2021-02-26 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4352.2 | 18.47 | 4370.67 | 0 | 0 | 0 | 4370.67 | 0 | 0 | 0 | 0 | 4370.67 | 119022.58 | [5 empty] | N | CM_WSNI | 100%
507624 | WW-NI-N-100720 - Dingwall Jubilee SPS - Replace Covers | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 |  | 2022-04-01 | 2022-07-21 | 2023-03-03 |  | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308.41 | 1308.41 | 78691.56 | 0 | 0 | 79999.97 | 0 | 0 | 0 | 0 | 79999.97 | 90601.29 | [5 empty] | N | WWNI | 100%
503781 | WW-NI-WEST-Stevenston Point WwTW- MH Cover Replacement | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-10-31 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 4650 | -4345.79 | 304.21 | 4345.79 | 0 | 0 | 4650 | 0 | 0 | 0 | 0 | 4650 | 209381.79 | [5 empty] | N | CM_M&G | 100%
500613 | WWSS Asset Intelligence SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 1412797.66 | 431128.43 | 377446.24 | 269158.7 | 120916.11 | 98411.74 | 2709858.88 | 0 | 0 | 0 | 2709858.88 | 0 | 0 | 0 | 0 | 2709858.88 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500612 | WWSS Env Reg and Climate Change SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 36843.55 | 63168.35 | 97971.08 | 88426.83 | 81261.32 | 7617.99 | 375289.12 | 0 | 0 | 0 | 375289.12 | 0 | 0 | 0 | 0 | 375289.12 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500608 | WWSS Flooding SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 285093.28 | 938008.92 | 900162.54 | 1165573.37 | 1366556.6 | 1659386.02 | 6314780.73 | 0 | 0 | 0 | 6314780.73 | 0 | 0 | 0 | 0 | 6314780.73 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500610 | WWSS Risk & Lifecycle Planning SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 470815.56 | 1269075.28 | 1787261.27 | 2097023.03 | 1127310.28 | 1037418.96 | 7788904.38 | 0 | 0 | 0 | 7788904.38 | 0 | 0 | 0 | 0 | 7788904.38 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500609 | WWSS Technical Support and Assurance SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 104390.26 | 1091334.98 | 1677472.51 | 1614271.27 | 1458930.93 | 1430510.87 | 7376910.82 | 0 | 0 | 0 | 7376910.82 | 0 | 0 | 0 | 0 | 7376910.82 | 306661.32 | [5 empty] | N | CM_OVH | 100%
500607 | WWSS WW Service Strategy SR15 Overhead | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 |  | Scottish Water Wide | 0 | 0 | 211082.55 | 337016.64 | 499915.9 | 644814.71 | 185556.72 | 257134.98 | 2135521.5 | 0 | 0 | 0 | 2135521.5 | 0 | 0 | 0 | 0 | 2135521.5 | 306661.32 | [5 empty] | N | CM_OVH | 100%
401326 | WWTW - Scraper Bridge Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-02-08 | 2010-08-23 | 2010-08-23 | 2015-06-02 |  | Scottish Water Wide | 309428.15 | 0 | -309428.15 | 0 | 0 | 0 | 0 | 0 | -309428.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504034 | W-WW - NI - 211119 - Lochgoilhead WWTW - Replace Chlorine Pump - 1.6K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2019-11-29 |  | 2020-07-20 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | -1600 | 0 | 1600 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509872 | W-WW-011020- STEWARTON WWTW NS408449 - REPLACE 9 WINDOWS ON THE ADMIN BUILDING - 6.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-19 |  | 2021-03-12 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6395.35 | 6395.35 | 4.64 | 0 | 0 | 6399.99 | 0 | 0 | 0 | 0 | 6399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509305 | W-WW-011020-GAILES WWPS NS323359 - REPLACE CRITICAL SPARE DIFFUSER - 11.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-20 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 745.79 | 745.79 | 10654.21 | 0 | 0 | 11400 | 0 | 0 | 0 | 0 | 11400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511268 | W-WW-040221- GIRVAN WWTW NX190999 - REPLACE DUCKFOOT ON SBR FEED PUMP 3 - 7.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490.65 | 490.65 | 7009.35 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507790 | W-WW-090720- BONESS WWTW NT022813 - HEALTH & SAFETY: REPLACE GRID FLOORING SUPPORTS CABLE TRAYS & HANDRAIL - 10.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-22 |  | 2020-10-07 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10155.29 | 10155.29 | 0 | 0 | 0 | 10155.29 | 0 | 0 | 0 | 0 | 10155.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508742 | W-WW-100920-GARNIELAND ERSKINE WWPS NS483699 - REPLACE RTU - 5.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-17 |  | 2021-02-28 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5134.17 | 5134.17 | 0 | 0 | 0 | 5134.17 | 0 | 0 | 0 | 0 | 5134.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505798 | W-WW-120320- ARDROSSAN WWPS 2 NS226419 - H&S- SURVEY MCC PANEL - 9.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-09-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 595.33 | 8441.65 | 9036.98 | 0 | 0 | 0 | 9036.98 | 0 | 0 | 0 | 0 | 9036.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509822 | W-WW-121120- KILLEARN WWTW 1971 NS517844 - REPLACE GRATINGS AT SAS RETURN VALVE (H&S) - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-19 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509295 | W-WW-151020- PENZANCE WAY WWPS NS694710 - REPLACE NRV - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-20 |  | 2020-11-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455.23 | 1455.23 | 0 | 0 | 0 | 1455.23 | 0 | 0 | 0 | 0 | 1455.23 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511378 | W-WW-180221- DALMOAK WWPS NS387771 - REPLACE SITE LIGHTING - 1.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-22 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.4 | 0 | 0 | 1399.99 | 0 | 0 | 0 | 0 | 1399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511330 | W-WW-180221- MAYBOLE WWTW NS310088 - Replace Rotork Actuator - 1.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-18 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 124.3 | 1775.7 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505808 | W-WW-180320- FAST TRACK - BISHOPTON WWPS NS444700 - Refurb Submersible Pump - 7.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-07-20 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 484.11 | 8679.3 | 9163.41 | 0 | 0 | 0 | 9163.41 | 0 | 0 | 0 | 0 | 9163.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506870 | W-WW-210520-GLENOCHIL WWPS NS874762- REPLACE FOUL PUMP NO1 - 2.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-08-03 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2347.29 | 2347.29 | 0 | 0 | 0 | 2347.29 | 0 | 0 | 0 | 0 | 2347.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508492 | W-WW-270820- NEILSTON KIRKTONFIELD CRES WWPS NS488573 - REFURBISH KIOSK (H&S) - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-11-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5969.83 | 5969.83 | 0 | 0 | 0 | 5969.83 | 0 | 0 | 0 | 0 | 5969.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507760 | W-WW-FAST TRACK 140720 - LUGAR WWPS NS585207 - REFURB FOUL PUMP 2 - 4.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-22 |  | 2020-08-18 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4019.38 | 4019.38 | 0 | 0 | 0 | 4019.38 | 0 | 0 | 0 | 0 | 4019.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509339 | W-WW-INFRA- 151020- DALDERSE WWTW 1966 NS903822 - REPLACE BURST PIPEWORK - 8.9K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-10-26 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582.24 | 582.24 | 8317.76 | 0 | 0 | 8900 | 0 | 0 | 0 | 0 | 8900 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504704 | W-WW-INFRA- 16012020- RHU LARGARIE LODGE SEP 2017 NS277835 - ABANDON SEPTIC TANK INSTALL PIPEWORK BYPASS & MANHOLES - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-01-22 |  | 2020-05-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | -299.87 | 4200.13 | 0 | 0 | 0 | 4200.13 | 0 | 0 | 0 | 0 | 4200.13 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510870 | W-WW-INFRA- 210121- ALBERT DRIVE CSO 2014 NS559713 - 76 & 78 Inveroran Drive Bearsden - PNRV Repairs - 5.2K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS4 |  | 2021-01-27 |  | 2021-04-02 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5154.71 | 5154.71 | 45.28 | 0 | 0 | 5199.99 | 0 | 0 | 0 | 0 | 5199.99 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510830 | W-WW-INFRA- 210121- CARTSIDE ROAD WWPS NS577562 - REFURBISH RISING MAIN REPLACE MH COVER - 23.2K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-01-27 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517.76 | 1517.76 | 21682.24 | 0 | 0 | 23200 | 0 | 0 | 0 | 0 | 23200 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504115 | W-WW-INFRA- 291119 - Kilbirnie CSO - Sewer Repair Milton St Kilbirnie - 27K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-05 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 28389.36 | 0 | 28389.36 | -1389.36 | 0 | 0 | 27000 | 0 | 0 | 0 | 0 | 27000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504132 | W-WW-INFRA- 291119- Charles Rodger Place Bridge of Allan - 8.5K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2019-12-05 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 8972.8 | 0 | 8972.8 | -472.8 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 8500 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504989 | W-WW-INFRA- MAJOR SEWER MANHOLE REPAIR BRANSHILL SAUCHIE ALLOA - 10.5K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-02-03 |  | 2020-07-27 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | -109.58 | 10390.42 | 0 | 0 | 0 | 10390.42 | 0 | 0 | 0 | 0 | 10390.42 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510609 | W-WW-INFRA-070121- IRVINE BEACH PARK WWPS NS312374 - Marine Drive Combined Sewer Repair - 34.4K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28987.55 | 28987.55 | 5412.45 | 0 | 0 | 34400 | 0 | 0 | 0 | 0 | 34400 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510579 | W-WW-INFRA-070121- LARGS WWTW NS194624 - REPAIR LEAKING 160MM PIPE & REINSTATE - 5.4K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5323.27 | 5323.27 | 76.73 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 5400 | 209381.79 | [5 empty] | N | CM_WWI | 100%
505263 | W-WW-INFRA-130220- ERSKINE WWTW NS494691 - SEWER REHAB - 43.5K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-02-20 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | -1072.21 | 42427.79 | 1072.21 | 0 | 0 | 43500 | 0 | 0 | 0 | 0 | 43500 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511503 | W-WW-INFRA-180221- GLASGOW MOLENDINAR ST CSO 2009 NS598648 - Replacement trap - 274 High Street Glasgow - 50K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-03-02 |  | 2021-05-26 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3271.03 | 3271.03 | 46728.97 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
507359 | W-WW-INFRA-180620-JORDAN STREET CSO 2017 NS537668- REPLACE DAMAGED COVERS REINSTATE DAMAGED ROADWAY - 11.7K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-06-25 |  | 2020-09-07 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16521.74 | 16521.74 | 0 | 0 | 0 | 16521.74 | 0 | 0 | 0 | 0 | 16521.74 | 209381.79 | [5 empty] | N | CM_WWI | 100%
511011 | W-WW-INFRA-210121- CATRINEHOLM WWTW NS522258 - REPLACE SAF VALVES - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-02 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4448.53 | 4448.53 | 51.45 | 0 | 0 | 4499.98 | 0 | 0 | 0 | 0 | 4499.98 | 209381.79 | [5 empty] | N | CM_WWI | 100%
504921 | W-WW-INFRA-22 Michael Drive Helensburgh - Sewer Relining Works- 36K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-01-30 |  | 2020-09-02 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 3898.12 | 39898.12 | 0 | 0 | 0 | 39898.12 | 0 | 0 | 0 | 0 | 39898.12 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506403 | W-WW-INFRA-230420-GARNIELAND ERSKINE WWPS NS483699- PENSTOCK SURVEY- 7.5K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-05-04 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46303.31 | 46303.31 | -21303.31 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
506483 | W-WW-INFRA-300420-W-WW-INFRA-300420- PRINTERS ROW WWPS NS546883- Replace Power Cables - 20.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-06-17 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20683.9 | 20683.9 | 0 | 0 | 0 | 20683.9 | 0 | 0 | 0 | 0 | 20683.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505735 | W-WW-INFRA-BALMAHA WWTW NS420907- Replace gully connection to sewer network - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2020-03-17 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 8533.62 | 8697.17 | -2297.17 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 6400 | 209381.79 | [5 empty] | N | CM_WWI | 100%
508915 | W-WW-N170920- HELENSBURGH WWTW 2001 NS321800 - REPLACE INLET SAMPLER FRIDGE - 7.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-28 |  | 2021-02-19 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7523.2 | 7523.2 | 0 | 0 | 0 | 7523.2 | 0 | 0 | 0 | 0 | 7523.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504197 | W-WW-N291119- GIRVAN WWTW - Replace Pipe Manifold - 3.5K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3641.81 | 0 | 3641.81 | 0 | 0 | 0 | 3641.81 | 0 | 0 | 0 | 0 | 3641.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510352 | W-WW-NI- 101220- DUNBLANE WWTW NN782006 - REPLACE DRIVE KEY - 2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-21 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037.47 | 2037.47 | 262.53 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504029 | W-WW-NI- 211119 - Stirling STC - Replace Pump Motor - 2k - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2019-11-29 |  | 2020-06-15 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -1869.16 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510499 | W-WW-NI- 241220- DENNY WWTW NS820830 - REFURBISH INLET SCREEN - 38.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-23 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2528.04 | 2528.04 | 35971.95 | 0 | 0 | 38499.99 | 0 | 0 | 0 | 0 | 38499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503965 | W-WW-NI- 251119- Bonnybridge WwTW NS836811 - Replace Drive & Trailing Wheels on FST 2 - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-27 |  | 2020-07-27 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 8469.3 | 0 | 8469.3 | 0 | 0 | 0 | 8469.3 | 0 | 0 | 0 | 0 | 8469.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504136 | W-WW-NI- 291119 - Girvan WWTW NX190999 - Modify Lifting Crane - 1.9K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2007.91 | 0 | 2007.91 | 0 | 0 | 0 | 2007.91 | 0 | 0 | 0 | 0 | 2007.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504195 | W-WW-NI- Callander Park WWPS 1994 NS904792 - FAST TRACK-Replace Foul Pump Guiderails & Pump Stool - 5K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2019-12-11 |  | 2020-06-15 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | -4672.9 | 327.1 | 0 | 0 | 0 | 327.1 | 0 | 0 | 0 | 0 | 327.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505481 | W-WW-NI- FAST TRACK - MANSFIELD HEIGHTS WWPS 2007 NS623142 - Replace Foul Transfer Pump 1 - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-06 |  | 2020-07-27 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 1829.3 | 1960.14 | 0 | 0 | 0 | 1960.14 | 0 | 0 | 0 | 0 | 1960.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511018 | W-WW-NI- FAST TRACK 020221 - DALDERSE STC - REPLACE FILTRATE SUMP PUMP A - 3.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-02 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.89 | 215.89 | 3084.1 | 0 | 0 | 3299.99 | 0 | 0 | 0 | 0 | 3299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511032 | W-WW-NI- FAST TRACK 020221 - UNDERWOOD (CUMNOCK) STC - REPLACE CLEAN WASHWATER PUMP - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-02 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2082.88 | 2082.88 | 17.1 | 0 | 0 | 2099.98 | 0 | 0 | 0 | 0 | 2099.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506155 | W-WW-NI- FAST TRACK 080420 - CUSTOM HOUSE WWPS NS282762 - REFURBISH FOUL PUMP - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-14 |  | 2020-07-27 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4976.49 | 4976.49 | 0 | 0 | 0 | 4976.49 | 0 | 0 | 0 | 0 | 4976.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505476 | W-WW-NI- FAST TRACK 20FEB20 - BISHOPTON WWPS NS444700 - REFURBISH SUBMERSIBLE PUMP - 10.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-03 |  | 2020-05-14 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 10534.29 | 1765.9 | 12300.19 | 0 | 0 | 0 | 12300.19 | 0 | 0 | 0 | 0 | 12300.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506468 | W-WW-NI- HOPEBANK WWPS NR980700 - Replace Submersible pump 2 - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-05 |  | 2020-05-13 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 0 | 0 | 0 | 163.55 | 0 | 0 | 0 | 0 | 163.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504121 | W-WW-NI- IRVINE SPORTS CLUB SPS 2012 NS314392 - New VSD in Control Panel - 8K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2019-12-05 |  | 2020-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8255.56 | 0 | 8255.56 | 0 | 0 | 0 | 8255.56 | 0 | 0 | 0 | 0 | 8255.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504392 | W-WW-NI- LUGGIEBANK WWPS NS763728 - Replace Submersible Pump - FAST TRACK - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2021-05-01 |  | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | -3738.32 | 261.68 | 3738.32 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512265 | W-WW-NI-010421- FALLIN WWTW 1960 NS835923 - INSTALL HANDRAILING & PIPEWORK (H&S) - 8.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | [5 empty] | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8099.98 | 0 | 0 | 8099.98 | 0 | 0 | 0 | 0 | 8099.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512249 | W-WW-NI-010421- LAMLASH WWPS 3 2006 NS026309 - REPLACE SUBMERSIBLE PUMPS X 2 - 14.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14800.03 | 0 | 0 | 14800.03 | 0 | 0 | 0 | 0 | 14800.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512250 | W-WW-NI-010421- PARTICK WWPS NS565664 - REPLACE LEVEL SENSORS X4 - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5099.99 | 0 | 0 | 5099.99 | 0 | 0 | 0 | 0 | 5099.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512257 | W-WW-NI-010421- STRATHBLANE WWTW NS547801 - REPLACE ACCESS LADDER (H&S) - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2699.97 | 0 | 0 | 2699.97 | 0 | 0 | 0 | 0 | 2699.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509043 | W-WW-NI-011020- AIRTH WWTW NS903881 - REFURBISH INLET SCREEN - 8.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8022.82 | 8022.82 | 0 | 0 | 0 | 8022.82 | 0 | 0 | 0 | 0 | 8022.82 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509048 | W-WW-NI-011020- BANKEND WWPS NS398758 - REPLACE SHAFT DRIVEN PUMP - 9.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.33 | 595.33 | 8504.67 | 0 | 0 | 9100 | 0 | 0 | 0 | 0 | 9100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509258 | W-WW-NI-011020- BOGANY POINT WWPS NS107653 - REPLACE VSD - 6.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-20 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6139.61 | 6139.61 | 60.39 | 0 | 0 | 6200 | 0 | 0 | 0 | 0 | 6200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509039 | W-WW-NI-011020- CALLANDER WWTW NN638072 - REFURBISH INLET SCREEN - 8.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-09 |  | 2021-02-18 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8662.76 | 8662.76 | 0 | 0 | 0 | 8662.76 | 0 | 0 | 0 | 0 | 8662.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509307 | W-WW-NI-011020- CROSSHILL WWTW NS322068 - REFURBISH SAF UNIT LIDS - 7.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-20 |  | 2021-02-10 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7838.65 | 7838.65 | -338.65 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509251 | W-WW-NI-011020- CROSSHILL WWTW NS322068 - Replace Storm Return Pump 1 - 2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-20 |  | 2021-02-10 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2280.69 | 2280.69 | 19.31 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509252 | W-WW-NI-011020- CUMNOCK UNDERWOOD WWTW NS558204 - Refurbish Inlet Screens x2 - 16.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-20 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079.44 | 1079.44 | 15420.56 | 0 | 0 | 16500 | 0 | 0 | 0 | 0 | 16500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509270 | W-WW-NI-011020- DALDERSE STC - FAST TRACK - REPLACE SCREENED SLUDGE PUMP B - 8.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-20 |  | 2020-10-12 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8568.41 | 8568.41 | 0 | 0 | 0 | 8568.41 | 0 | 0 | 0 | 0 | 8568.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509040 | W-WW-NI-011020- DEANSTON WWTW NN713018 - REFURBISH INLET SCREEN - 1.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-09 |  | 2021-03-04 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344.38 | 1344.38 | 0 | 0 | 0 | 1344.38 | 0 | 0 | 0 | 0 | 1344.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509362 | W-WW-NI-011020- DENNY WWTW NS820830 - REPLACE TANKER DRAW OFF POINTS (H&S) - 3.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-26 |  | 2021-02-26 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3058.8 | 3058.8 | 41.2 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509037 | W-WW-NI-011020- DOLLAR WWTW NS953978 - REFURBISH INLET SCREEN - 6.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-07-12 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6694.89 | 6694.89 | 0 | 0 | 0 | 6694.89 | 0 | 0 | 0 | 0 | 6694.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509032 | W-WW-NI-011020- DOUNE WWTW NN729008 - REPLACE RECIRCULATION PUMP & SOLAR PANELS - 8.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-11-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8757.95 | 8757.95 | 0 | 0 | 0 | 8757.95 | 0 | 0 | 0 | 0 | 8757.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509310 | W-WW-NI-011020- DRONGAN WWTW NS429187 - Replace Multi-turn Actuator - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-20 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3649.06 | 3649.06 | 50.94 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 3700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509047 | W-WW-NI-011020- ELLISTON WWPS 1996 NS395603 - REPLACE PUMP NO1 - 7.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7577.2 | 7577.2 | 0 | 0 | 0 | 7577.2 | 0 | 0 | 0 | 0 | 7577.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509050 | W-WW-NI-011020- ERSKINE WWTW NS494691 - REFURBISH FINE SCREEN C - 7.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2020-10-12 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7036 | 7036 | 0 | 0 | 0 | 7036 | 0 | 0 | 0 | 0 | 7036 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509049 | W-WW-NI-011020- GAILES WWPS NS323359 - REPLACEMENT FANS ON VSD - 4.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-09 |  | 2021-03-12 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3744.93 | 3744.93 | 0 | 0 | 0 | 3744.93 | 0 | 0 | 0 | 0 | 3744.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509311 | W-WW-NI-011020- MAUCHLINE WWTW NS492254 - Refurbish Mixer - 2.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-26 |  | 2021-03-21 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2317.3 | 2317.3 | 82.7 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509046 | W-WW-NI-011020- Stevenston Point DOA - Glengarnock Beith 1 Kersland Rd KA14 3BA - Replacement APNRV - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-09 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2523.36 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509036 | W-WW-NI-011020-CASTLE TERRACE WWPS NS400752- REPLACE SUBMERSIBLE PUMP - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-09 |  | 2021-02-10 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2315.49 | 2315.49 | 0 | 0 | 0 | 2315.49 | 0 | 0 | 0 | 0 | 2315.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509255 | W-WW-NI-011020-LOCHGOILHEAD WWTW 2004 NN202019 - PHASE 1 REMOVE DISLODGED CONCRETE SURROUND SECTIONS - 7.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-20 |  | 2021-02-10 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7087.67 | 7087.67 | 12.33 | 0 | 0 | 7100 | 0 | 0 | 0 | 0 | 7100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503783 | W-WW-NI-011119-Laighpark WwTW-Sludge Pump Refurbishment | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 5425.53 | -4777.87 | 647.66 | 9252.34 | 0 | 0 | 9900 | 0 | 0 | 0 | 0 | 9900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511578 | W-WW-NI-020321- (GIRVAN STC) - GAS MONITORS STC HEALTH CHECK SURVEYS - 6.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-04 |  | 2021-06-02 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 425.23 | 5571.42 | 0 | 0 | 5996.65 | 0 | 0 | 0 | 0 | 5996.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506168 | W-WW-NI-020420- ARDENCRAIG WWPS 2006 NR976709 - REPLACE SUBMERSIBLE PUMP 1 - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-16 |  | 2020-04-21 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333.64 | 333.64 | 0 | 0 | 0 | 333.64 | 0 | 0 | 0 | 0 | 333.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506135 | W-WW-NI-020420- CATRINEHOLM WWTW NS522258- H&S- Install Safety rails and grid flooring on 2x Percolating filters - 5.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5856.27 | 5856.27 | 43.73 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 5900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506097 | W-WW-NI-020420- DUNBLANE WWTW NN782006 - REPLACE AIR BLOWER - 10.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-07-20 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10530.02 | 10530.02 | 0 | 0 | 0 | 10530.02 | 0 | 0 | 0 | 0 | 10530.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506051 | W-WW-NI-020420- FINTRY WWTW NS614873 - Replace PST3 Desludge Pump 1 - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-16 |  | 2020-07-10 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4024.77 | 4024.77 | 0 | 0 | 0 | 4024.77 | 0 | 0 | 0 | 0 | 4024.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506049 | W-WW-NI-020420- LOMOND IND EST WWPS 1999 NS395808 - Replace Sewage Pumps 1&2 and associated Guide Rails - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-03 |  | 2020-07-20 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5908.26 | 5908.26 | 0 | 0 | 0 | 5908.26 | 0 | 0 | 0 | 0 | 5908.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506166 | W-WW-NI-020420- MAUCHLINE WWTW NS492254- HEALTH & SAFETY- INSTALL HANDRAILS & WALKWAY TO PERCOLATING FILTERS - 6.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-14 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6844.4 | 6844.4 | 55.6 | 0 | 0 | 6900 | 0 | 0 | 0 | 0 | 6900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506116 | W-WW-NI-020420- NEILSTON WWTW NS479578 - REPLACE DAMAGED BRUSHES - 2.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-07-27 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2158.93 | 2158.93 | 0 | 0 | 0 | 2158.93 | 0 | 0 | 0 | 0 | 2158.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506128 | W-WW-NI-020420- NEILSTON WWTW NS479578- Replace Actuator - 2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-07-25 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255.47 | 2255.47 | 0 | 0 | 0 | 2255.47 | 0 | 0 | 0 | 0 | 2255.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506104 | W-WW-NI-02042020- DOLLAR WWTW NS953978 - REPLACE FLOOD LIGHTS - 6.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-04-09 |  | 2020-07-20 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7216.78 | 7216.78 | -4685 | 0 | 0 | 2531.78 | 0 | 0 | 0 | 0 | 2531.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506100 | W-WW-NI-02042020- GIRVAN WWTW NX190999 - HEALTH & SAFETY - REPLACE PURLINS ON ABANDONED EQUIPMENT - 14.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-07-20 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14178.97 | 14178.97 | 0 | 0 | 0 | 14178.97 | 0 | 0 | 0 | 0 | 14178.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506098 | W-WW-NI-02042020- HOLY LOCH WWPS NS180799- Replace Submersible Pump A - 4.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-04-21 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300.93 | 300.93 | 0 | 0 | 0 | 300.93 | 0 | 0 | 0 | 0 | 300.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506095 | W-WW-NI-020420-BATH STREET LARGS WWPS NS201591- GOGO STREET FAST TRACK PUMP REPLACEMENT - 6.4k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-07-20 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6321.62 | 6321.62 | 0 | 0 | 0 | 6321.62 | 0 | 0 | 0 | 0 | 6321.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506092 | W-WW-NI-020420-LOACH AVENUE WWPS NS328384- Refurbish Pump Storm Pump 3 - 5.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-09 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5111.76 | 5111.76 | 88.24 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 5200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506114 | W-WW-NI-020420-NEILSTON WWTW NS479578- Replacement Motor for Screw Pump 2 - 5.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-07-20 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5230.89 | 5230.89 | 0 | 0 | 0 | 5230.89 | 0 | 0 | 0 | 0 | 5230.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507507 | W-WW-NI-020720- AYR SHORE ROAD WWPS NS338232 - REPLACE DOUBLE DOORS TO HV BUILDING - 7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-04-12 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6997.94 | 6997.94 | 0 | 0 | 0 | 6997.94 | 0 | 0 | 0 | 0 | 6997.94 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507539 | W-WW-NI-020720- BONNYBRIDGE WWTW NS836811 - REPLACE 2 X RAS PUMPS - 6.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-10-29 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6264.71 | 6264.71 | 0 | 0 | 0 | 6264.71 | 0 | 0 | 0 | 0 | 6264.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507509 | W-WW-NI-020720- DALDERSE STC - REPLACE BIO GAS FLOW METER - 9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-10-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8938.79 | 8938.79 | 0 | 0 | 0 | 8938.79 | 0 | 0 | 0 | 0 | 8938.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507565 | W-WW-NI-020720- TILLICOULTRY WWTW NS917965 - Replace connection flange & reinstall aerator - 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-10-23 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250.05 | 1250.05 | 0 | 0 | 0 | 1250.05 | 0 | 0 | 0 | 0 | 1250.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507527 | W-WW-NI-020720-COLLIER ST SPS - REPLACE SUBMERSIBLE PUMPS 1&2 - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-08-31 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4930.15 | 4930.15 | 0 | 0 | 0 | 4930.15 | 0 | 0 | 0 | 0 | 4930.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507508 | W-WW-NI-020720-DEANSTON WWTW NN713018 - HEALTH & SAFETY MEASURES FOR FILTER BEDS - 10.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-10-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10575 | 10575 | 0 | 0 | 0 | 10575 | 0 | 0 | 0 | 0 | 10575 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507543 | W-WW-NI-020720-SALTCOATS CANAL PL WWPS NS252413- H&S: REPLACE LIGHTING & FITTINGS - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663.21 | 1663.21 | 36.79 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504133 | W-WW-NI-021119- Erskine WWTW NS494691 - Fast Track Replace Storm Pump - 8K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-01-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | -2762.21 | 5237.79 | 0 | 0 | 0 | 5237.79 | 0 | 0 | 0 | 0 | 5237.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504134 | W-WW-NI-021119- ERSKINE WWTW NS494691 - REPLACE DRAIN DOWN PUMP - FAST TRACK - 4.2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4460.19 | 0 | 4460.19 | 0 | 0 | 0 | 4460.19 | 0 | 0 | 0 | 0 | 4460.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504110 | W-WW-NI-021219- COWIE WWTW 1972 NS849899 - REPLACE SCRAPERS SCUMBOARDS & CENTRE COLUMN - 7K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | -6542.06 | 457.94 | 6542.06 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 7000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504105 | W-WW-NI-021219- DALDERSE WWTW 1966 NS903822 - REPACE PULSATION DAMPNER 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-06-15 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 2034.84 | 0 | 2034.84 | 0 | 0 | 0 | 2034.84 | 0 | 0 | 0 | 0 | 2034.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504095 | W-WW-NI-021219- Dumbarton Distillery WWPS NS397751 - Replace Roof 7.6k - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-09-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7600 | -7102.8 | 497.2 | 0 | 0 | 0 | 497.2 | 0 | 0 | 0 | 0 | 497.2 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504604 | W-WW-NI-030120-LUGGIEBANK WWPS NS763728- Replace Pump - FAST TRACK - 8.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | -7943.93 | 556.07 | 11443.93 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 12000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508645 | W-WW-NI-030920- ALVA WWTW NS874966 - REPLACE AERATORS x4 - 9.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-11 |  | 2021-05-31 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 928.97 | 928.97 | 13271.02 | 0 | 0 | 14199.99 | 0 | 0 | 0 | 0 | 14199.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508634 | W-WW-NI-030920- AYR SHORE ROAD WWPS NS338232 - REPLACE LIGHTING IN SCREENS BUILDING (H&S) - 2.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-11 |  | 2021-03-28 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2839.72 | 2839.72 | 60.28 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508582 | W-WW-NI-030920- BISHOPTON WWPS NS444700 - Replace Light & Heat at the Pumping Station (H&S) - 4.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 4018.69 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508658 | W-WW-NI-030920- BONNYBRIDGE WWTW NS83681 - REFURB SPIRAC UNIT - 22.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-11 |  | 2021-02-27 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22865.03 | 22865.03 | 0 | 0 | 0 | 22865.03 | 0 | 0 | 0 | 0 | 22865.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508627 | W-WW-NI-030920- CARRIDEN WWPS 1985 NT019814 - REPLACE 2x NRVs - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-11 |  | 2021-02-27 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2735.4 | 2735.4 | 1064.6 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508584 | W-WW-NI-030920- COACH CLOSE WWPS NS731777 - REPLACE KIOSK(H&S) - 7.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503.74 | 503.74 | 7196.26 | 0 | 0 | 7700 | 0 | 0 | 0 | 0 | 7700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508670 | W-WW-NI-030920- DAILLY WWPS NS268015 - INSTALL MANHOLE - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-11 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242.06 | 242.06 | 3457.94 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 3700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508672 | W-WW-NI-030920- DAILLY WWTW NS265012 - RE-LAY WATER MAIN - 2.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-10-15 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3619.72 | 3619.72 | 0 | 0 | 0 | 3619.72 | 0 | 0 | 0 | 0 | 3619.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508677 | W-WW-NI-030920- DALDERSE STC - REFURB FLOW METER - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-10-26 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559.67 | 1559.67 | 0 | 0 | 0 | 1559.67 | 0 | 0 | 0 | 0 | 1559.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508598 | W-WW-NI-030920- DUMBARTON DISTILLERY WWPS NS397751 - REPLACE PUMP & PIPEWORK - 10.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654.21 | 654.21 | 9945.79 | 0 | 0 | 10600 | 0 | 0 | 0 | 0 | 10600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508622 | W-WW-NI-030920- ERSKINE WWTW NS494691 - REPLACE GEARBOX (INLET FINE SCREEN A) - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-09-18 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 0 | 0 | 0 | 137.38 | 0 | 0 | 0 | 0 | 137.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508667 | W-WW-NI-030920- GAILES WWPS NS323359 - REFURBISH AIR HANDLING UNITS - 9.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-11 |  | 2021-02-15 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9571.54 | 9571.54 | 0 | 0 | 0 | 9571.54 | 0 | 0 | 0 | 0 | 9571.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508679 | W-WW-NI-030920- GIRVAN HARBOUR WWPS NX818982 - REPLACE BATTERY TRIPPING UNIT - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-08-12 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4130.29 | 4130.29 | 0 | 0 | 0 | 4130.29 | 0 | 0 | 0 | 0 | 4130.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508628 | W-WW-NI-030920- GIRVAN STC - FAST TRACK -REPLACE CENTRIFUGAL MIXER PUMP - 10.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-10-13 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10646.9 | 10646.9 | 0 | 0 | 0 | 10646.9 | 0 | 0 | 0 | 0 | 10646.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508593 | W-WW-NI-030920- HOLMBANK AVENUE CSO NS570615 - REPLACE SCREEN COVER - 20K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308.41 | 1308.41 | 18691.59 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508607 | W-WW-NI-030920- KINLOCHARD WWTW 1999 NN464023 - REFURB RAISED HATCH (HEALTH & SAFETY) - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-11 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1588.79 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508625 | W-WW-NI-030920- MEADOWHEAD WWTW NS339361 - REFURBISH Centrifugal Grit Detritor Pump 1 - 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-11 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5637.75 | 5637.75 | 62.25 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 5700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508626 | W-WW-NI-030920- MEADOWHEAD WWTW NS339361 - REPLACE GRIT DETRITOR 2 PUMP 1 - 10.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-08-12 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10208.03 | 10208.03 | 0 | 0 | 0 | 10208.03 | 0 | 0 | 0 | 0 | 10208.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508617 | W-WW-NI-030920- MILLPORT WWTW 2003 NS153540 - REPLACE INLET SCREEN BASKET - 11.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-11-27 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11049.34 | 11049.34 | 0 | 0 | 0 | 11049.34 | 0 | 0 | 0 | 0 | 11049.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508638 | W-WW-NI-030920- TIGHNABRUAICH WWTW NR980700 - REPLACE GUIDE RAILS - 1.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-10-02 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309.88 | 1309.88 | 0 | 0 | 0 | 1309.88 | 0 | 0 | 0 | 0 | 1309.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508596 | W-WW-NI-030920-CARTSIDE ROAD WWPS NS577562- REFURBISH PIPEWORK - 7.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 497.2 | 497.2 | 7102.8 | 0 | 0 | 7600 | 0 | 0 | 0 | 0 | 7600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509603 | W-WW-NI-031120- LINWOOD WWPS NS447648 - URGENT RECONNECT DUCKFOOT & INSTALL GUIDERAILS - 12.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12680.84 | 12680.84 | 19.16 | 0 | 0 | 12700 | 0 | 0 | 0 | 0 | 12700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511266 | W-WW-NI-04021- DALMOAK WWPS NS387771 - REPLACE FOLDING DOOR WITH ROLLER DOOR (H&S) - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261.68 | 261.68 | 3738.3 | 0 | 0 | 3999.98 | 0 | 0 | 0 | 0 | 3999.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511272 | W-WW-NI-040221- ALLOA WWTW NS887918 - REPLACE SLUDGE PIPELINE MANIFOLD - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2655.22 | 2655.22 | 44.75 | 0 | 0 | 2699.97 | 0 | 0 | 0 | 0 | 2699.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511295 | W-WW-NI-040221- ALVA WWTW NS874966 - REFURBISH AERATOR 1 - 9.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621.5 | 621.5 | 8878.5 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 9500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511277 | W-WW-NI-040221- ASHTON WWPS 1993 NS234772 - REPLACE CHANGEOVER BOX (H&S) - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2523.35 | 0 | 0 | 2699.99 | 0 | 0 | 0 | 0 | 2699.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511169 | W-WW-NI-040221- BENLEDI AVENUE WWPS 1981 NS508626 - REPLACE FAULTY PUMP - 5.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-10 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5514 | 0 | 0 | 5899.98 | 0 | 0 | 0 | 0 | 5899.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511165 | W-WW-NI-040221- BISHOPTON WWPS NS444700 - REPLACE EXTERNAL LIGHTING & BUILDING HEATING (H&S) - 4.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-10 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 4018.7 | 0 | 0 | 4300.01 | 0 | 0 | 0 | 0 | 4300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511301 | W-WW-NI-040221- CALLANDER WWTW NN638072 - REPLACE INLET SCREEN RAKE ARM - 3.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.43 | 222.43 | 3177.55 | 0 | 0 | 3399.98 | 0 | 0 | 0 | 0 | 3399.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511173 | W-WW-NI-040221- DALDERSE WWTW 1966 NS903822 - REPLACE DOORS ON CONTROL CABINET - 1.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-11 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 124.3 | 1775.7 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511271 | W-WW-NI-040221- DALMARNOCK SLUDGE WWPS 2000 NS610624 - REFURBISH SLUDGE MUNCHER - 11.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11573.88 | 11573.88 | 26.12 | 0 | 0 | 11600 | 0 | 0 | 0 | 0 | 11600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511081 | W-WW-NI-040221- DEANSTON WWTW NN713018 - WELFARE FACILITIES REFURB (H&S) - 7.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-05 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7502.88 | 7502.88 | 197.12 | 0 | 0 | 7700 | 0 | 0 | 0 | 0 | 7700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511303 | W-WW-NI-040221- DUNBLANE WWTW NN782006 - Refurbish Huber Inlet Screen 1 - 50.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-17 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3290.65 | 3290.65 | 47009.35 | 0 | 0 | 50300 | 0 | 0 | 0 | 0 | 50300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511106 | W-WW-NI-040221- DUNBLANE WWTW NN782006 - REPLACE SUBMERSIBLE PUMP & SOCKETS - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-08 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 170.09 | 2429.9 | 0 | 0 | 2599.99 | 0 | 0 | 0 | 0 | 2599.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511168 | W-WW-NI-040221- DUNOON WWTW NS165745 - REPLACE OUTSIDE LIGHTING (H&S) - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-10 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1495.35 | 0 | 0 | 1600.02 | 0 | 0 | 0 | 0 | 1600.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511167 | W-WW-NI-040221- GAILES WWPS NS323359 - REPLACE PUMP BEARINGS (IMPERIAL SIZES) - 6.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6877.84 | 6877.84 | 22.16 | 0 | 0 | 6900 | 0 | 0 | 0 | 0 | 6900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511206 | W-WW-NI-040221- GARTMORE WWTW NS525967 - REFURBISH AERATOR - 13.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-12 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13434.28 | 13434.28 | 65.72 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 13500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511164 | W-WW-NI-040221- GIRVAN STC - REFURBISH SLUDGE TANK PUMP MIXER - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3787.6 | 3787.6 | 12.4 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511161 | W-WW-NI-040221- KINNING PARK WWPS NS575644 - REFURBISH PACKING GLANDS - 6.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-18 |  | 2021-03-29 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6894.92 | 6894.92 | 5.1 | 0 | 0 | 6900.02 | 0 | 0 | 0 | 0 | 6900.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511205 | W-WW-NI-040221- KIPPEN WWTW NS653952 - MANHOLES GULLIES & DRAINAGE SYSTEM AT TANKER POINT (H&S) - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-12 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3551.4 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511276 | W-WW-NI-040221- LAIGHPARK PAISLEY WWTW NS485655 - REPLACE FLOW MONITOR PROBE - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1495.35 | 0 | 0 | 1600.02 | 0 | 0 | 0 | 0 | 1600.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511166 | W-WW-NI-040221- LARGS WWTW NS194624 - REPLACEMENT VALVES ON BIOFILTER PIPEWORK (H&S) - 2.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-10 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279.98 | 279.98 | 2520 | 0 | 0 | 2799.98 | 0 | 0 | 0 | 0 | 2799.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511163 | W-WW-NI-040221- MAYBOLE WWTW NS310088 - REPLACE BLOWER (GRIT CLASSIFIER) - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1682.25 | 0 | 0 | 1800.01 | 0 | 0 | 0 | 0 | 1800.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511170 | W-WW-NI-040221- MAYBOLE WWTW NS310088 - REPLACE DOSING CONTROLLER - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-15 |  | 2021-03-28 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1554.67 | 1554.67 | 45.35 | 0 | 0 | 1600.02 | 0 | 0 | 0 | 0 | 1600.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511269 | W-WW-NI-040221- NEW CUMNOCK WWTW NS622140 - REPLACE MIXER - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153.96 | 4153.96 | 46.04 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511078 | W-WW-NI-040221- PLEAN WWTW NS841870 - REFURBISH AERATOR 1 - 12.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-15 |  | 2021-03-22 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8048.88 | 8048.88 | 4051.1 | 0 | 0 | 12099.98 | 0 | 0 | 0 | 0 | 12099.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511274 | W-WW-NI-040221- PLEAN WWTW NS841870 - REPLACE CABLE & SLIP RING MODULE - 10.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511275 | W-WW-NI-040221- PLEAN WWTW NS841870 - REPLACE MIXER - 4.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268.22 | 268.22 | 3831.8 | 0 | 0 | 4100.02 | 0 | 0 | 0 | 0 | 4100.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511086 | W-WW-NI-040221- STIRLING WWTW 1968 NS808935 - REPLACE SAS PUMP B - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-08 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3551.4 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511273 | W-WW-NI-040221-LOCHEARNHEAD WWPS NN593238 - REPLACE OUTLET FLOW METER - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392.52 | 392.52 | 5607.5 | 0 | 0 | 6000.02 | 0 | 0 | 0 | 0 | 6000.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511280 | W-WW-NI-040221-STIRLING WWTW 1968 NS808935 - REPLACE PST 2 SCRAPER MECHANISM - 18.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-17 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190.65 | 1190.65 | 17009.35 | 0 | 0 | 18200 | 0 | 0 | 0 | 0 | 18200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511278 | W-WW-NI-040221-UNDERCLIFF RD WWPS 1993 NS190698 - REPLACE PUSH BUTTON STATION ON BAND SCREEN 1 - 2.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-16 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 2616.8 | 0 | 0 | 2799.98 | 0 | 0 | 0 | 0 | 2799.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511675 | W-WW-NI-040321- DALDERSE STC - REPLACE CENTRIFUGE LINERS - 9.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-09 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608.41 | 608.41 | 7971.42 | 0 | 0 | 8579.83 | 0 | 0 | 0 | 0 | 8579.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511666 | W-WW-NI-040321- DALMOAK WWPS NS387771 - REPLACE GEARBOX-MOTOR COMBO - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-08 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333.64 | 333.64 | 4371.42 | 0 | 0 | 4705.06 | 0 | 0 | 0 | 0 | 4705.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511671 | W-WW-NI-040321- DRONGAN WWTW NS429187 - REPLACE PST POWER CABLE RETRACTOR DRUM (H&S) - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-08 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 1714.26 | 0 | 0 | 1845.1 | 0 | 0 | 0 | 0 | 1845.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511667 | W-WW-NI-040321- ERSKINE WWTW NS494691 - REPLACE MLSS MONITOR (AERTATION LANE 2) - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-08 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2452.94 | 2452.94 | 47.06 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511673 | W-WW-NI-040321- FINTRY WWTW NS614873 - PNRV Replacement - 40 Main St Fintry - 10.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-09 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 686.92 | 686.92 | 9000 | 0 | 0 | 9686.92 | 0 | 0 | 0 | 0 | 9686.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511646 | W-WW-NI-040321- GARNIELAND ERSKINE WWPS NS483699 - REFURBISH PENSTOCK - 13.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-08 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883.18 | 883.18 | 12616.82 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 13500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511625 | W-WW-NI-040321- GIRVAN WWTW NX190999 - REPLACE UPS SYSTEM - 3.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-04 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235.51 | 235.51 | 3085.74 | 0 | 0 | 3321.25 | 0 | 0 | 0 | 0 | 3321.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511674 | W-WW-NI-040321- KILLIN WWTW 1985 NN575331 - Replace Humus Pump - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-09 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1371.42 | 0 | 0 | 1476.09 | 0 | 0 | 0 | 0 | 1476.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511672 | W-WW-NI-040321- MAYBOLE WWTW NS310088 - REPLACE WASH-WATER PUMP 2 - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-08 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 1714.26 | 0 | 0 | 1845.1 | 0 | 0 | 0 | 0 | 1845.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511669 | W-WW-NI-040321- PAISLEY LAIGHPARK SLDG TFR WWPS NS485655 - REPLACE ISOLATOR (H&S) - 2.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-08 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2487.01 | 2487.01 | -87.01 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511668 | W-WW-NI-040321- SHIELDHALL WWTW NS533659 - REPLACE ROTORK ACTUATOR ON PST 7 - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-08 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1457.16 | 0 | 0 | 1568.37 | 0 | 0 | 0 | 0 | 1568.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511624 | W-WW-NI-040321- SHIELDHALL WWTW NS533659 - Replacement portable suspended solids meter -2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-04 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.47 | 150.47 | 1971.42 | 0 | 0 | 2121.89 | 0 | 0 | 0 | 0 | 2121.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511680 | W-WW-NI-040321- STIRLING WWTW 1968 NS808935 - H&S NEEDS WITHIN THE ST. NINIANS BUILDING -10.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-09 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 9171.42 | 0 | 0 | 9871.42 | 0 | 0 | 0 | 0 | 9871.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511677 | W-WW-NI-040321- STIRLING WWTW 1968 NS808935 - REPLACE WALKWAY & HANDRAILS ON SCRAPER BRIDGE (H&S) - 9.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-09 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641.12 | 641.12 | 8400 | 0 | 0 | 9041.12 | 0 | 0 | 0 | 0 | 9041.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511670 | W-WW-NI-040321- UNDERWOOD (CUMNOCK) STC - REPLACE MIXER - 4.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-08 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307.48 | 307.48 | 4028.58 | 0 | 0 | 4336.06 | 0 | 0 | 0 | 0 | 4336.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511623 | W-WW-NI-040321- UNDERWOOD (CUMNOCK) STC - REPLACE SHAKER PLATES - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-04 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.64 | 176.64 | 2314.26 | 0 | 0 | 2490.9 | 0 | 0 | 0 | 0 | 2490.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507071 | W-WW-NI-040620-ALVA WWTW NS874966-FIT PUMP - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-12 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1962.62 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507067 | W-WW-NI-040620-CENTRAL DOCK RD WWPS NS562652- REPLACE GUIDE POLES - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-12 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 170.09 | 2429.91 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507047 | W-WW-NI-040620-DALGRAIN WWPS 1976 NS915823- REPLACE LAUNDER WASHWATER PUMPS 1 & 2 - 7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-12 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457.94 | 457.94 | 6542.06 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 7000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507076 | W-WW-NI-040620-SKELMORLIE SHORE ROAD WWPS NS193667 - H&S: FIT HANDRAIL GATE & COVER STRAPS - 2.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-12 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2242.99 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509620 | W-WW-NI-041120- HOSPITALITY INN WWPS NS331384 - REPLACE SUBMERSIBLE PUMP 1 - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-05 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672.74 | 3672.74 | 27.26 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 3700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511635 | W-WW-NI-050221- LAIGHPARK PAISLEY WWTW NS485655 - REFURBISH PST 4 (SPECIALIST INSTALL) - 21.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-05 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1406.54 | 1406.54 | 20093.46 | 0 | 0 | 21500 | 0 | 0 | 0 | 0 | 21500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505582 | W-WW-NI-050320- BUCHLYVIE WWTW 1996 NS574942 - EMERGENCY REFURB OF SCRAPER BRIDGE DRIVE WHEEL & GEARBOX - 7.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-04-03 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 7687.74 | 0 | 7687.74 | 0 | 0 | 0 | 7687.74 | 0 | 0 | 0 | 0 | 7687.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505716 | W-WW-NI-050320- CUMNOCK UNDERWOOD WWTW NS558204 -REFURB INLET SCREENS 1 & 2 - 21.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-09-17 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 19924.24 | 21324.24 | 0 | 0 | 0 | 21324.24 | 0 | 0 | 0 | 0 | 21324.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505640 | W-WW-NI-050320- SHIELDHALL WWTW NS533659- Replacement VSD for aerator 2/4 - 2.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 2178.8 | 0 | 2178.8 | 0 | 0 | 0 | 2178.8 | 0 | 0 | 0 | 0 | 2178.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505562 | W-WW-NI-05032020-HEALTH & SAFETY - IRVINE BEACH PARK WWPS NS312374 - Replace wet well covers - 7.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-06 |  | 2020-09-29 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 484.11 | 6890.23 | 7374.34 | 0 | 0 | 0 | 7374.34 | 0 | 0 | 0 | 0 | 7374.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505632 | W-WW-NI-050320-AYR SHORE ROAD WWPS NS338232- Refurb Storm Stripping Pump - 29.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-06-02 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 1949.53 | 27831.12 | 29780.65 | 0 | 0 | 0 | 29780.65 | 0 | 0 | 0 | 0 | 29780.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505718 | W-WW-NI-050320-DALDERSE WWTW 1966 NS903822- Remove trailing wheel assemble supply new wheel bearing refurb and install - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-03-17 |  | 2020-05-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 0 | 163.55 | 2336.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505560 | W-WW-NI-050320-HEALTH & SAFETY- STEWARTON WWTW NS408449 - Replace mesh flooring & install Handrails - 10.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-06 |  | 2020-08-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 693.46 | 9185.51 | 9878.97 | 0 | 0 | 0 | 9878.97 | 0 | 0 | 0 | 0 | 9878.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505726 | W-WW-NI-050320-LAIGHPARK PAISLEY WWTW NS485655- REPLACE FST CABLE -4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-27 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 261.68 | 3696.53 | 3958.21 | 0 | 0 | 0 | 3958.21 | 0 | 0 | 0 | 0 | 3958.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505745 | W-WW-NI-050320-NEWFORD GROVE WWPS NS577562 - Replace Submersible Pump - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 287.85 | 4091.88 | 4379.73 | 0 | 0 | 0 | 4379.73 | 0 | 0 | 0 | 0 | 4379.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505646 | W-WW-NI-050320-STEWARTON WWTW NS408449- REPLACE TWO FAULTY MOTORS ON PISTA GRIT PLANT- 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-05-14 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 1676.73 | 0 | 1676.73 | 0 | 0 | 0 | 1676.73 | 0 | 0 | 0 | 0 | 1676.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505712 | W-WW-NI-050320-STIRLING WWTW 1968 NS808935- REPLACE SBR BLOWER SENTINEL CONTROL UNIT - 5.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-27 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 359.81 | 5063.76 | 5423.57 | 0 | 0 | 0 | 5423.57 | 0 | 0 | 0 | 0 | 5423.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505728 | W-WW-NI-050320-UNDERWOOD (CUMNOCK) STC- CHANNEL DRAIN - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 2310 | 2473.55 | 26.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505715 | W-WW-NI-050320-UNDERWOOD (CUMNOCK) STC- REPLACE ROTORK VALVE - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-24 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 333.64 | 4740.8 | 5074.44 | 0 | 0 | 0 | 5074.44 | 0 | 0 | 0 | 0 | 5074.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511637 | W-WW-NI-050321- LAIGHPARK PAISLEY WWTW NS485655 - REFURBISH SCRAPER BLADES FOR FST 4 - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-05 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4978.1 | 4978.1 | 21.9 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509273 | W-WW-NI-051020- DUNOON WWTW NS165745 - FAST TRACK - REPLACE SAS BUFFER TANK MIXER - 3.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-20 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.14 | 255.14 | 3644.86 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509636 | W-WW-NI-051120- ARDOCH WWTW 2002 NS374758 - INSTALL BLOWER - 17.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7493.59 | 7493.59 | 14506.4 | 0 | 0 | 21999.99 | 0 | 0 | 0 | 0 | 21999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505122 | W-WW-NI-060220- BRAEHEAD SHOPPING CENT WWPS NS523670 - Replace Guide Rails - 11K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-07-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 4594.63 | 15594.63 | 0 | 0 | 0 | 15594.63 | 0 | 0 | 0 | 0 | 15594.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505074 | W-WW-NI-060220- COYLTON WWTW NS401200 - Replace Inlet Screen Basket - 8.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | -196.24 | 7903.76 | 0 | 0 | 0 | 7903.76 | 0 | 0 | 0 | 0 | 7903.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505127 | W-WW-NI-060220- DALMARNOCK SLUDGE WWPS 2000 NS610624 - Replace PLC CPU - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-13 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -1869.16 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505069 | W-WW-NI-060220- DUNLOP ALLANVALE WWPS 2009 NS407497 - REPLACE 2X FOUL PUMPS - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 17.14 | 2517.14 | 0 | 0 | 0 | 2517.14 | 0 | 0 | 0 | 0 | 2517.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505120 | W-WW-NI-060220- LARGS WWTW NS194624 - Replace HMI on MCC2 - 5.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-02-26 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | -135.19 | 5364.81 | 0 | 0 | 0 | 5364.81 | 0 | 0 | 0 | 0 | 5364.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505104 | W-WW-NI-060220- LOCHWINNOCH WWTW 1971 NS356589 - Replace RAS return pump - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-07-27 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | -200.94 | 5799.06 | 0 | 0 | 0 | 5799.06 | 0 | 0 | 0 | 0 | 5799.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505101 | W-WW-NI-060220- POLMONTHILL WWPS 2000 NS953795 - Replace Foul Pump - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-07-20 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -31.28 | 1968.72 | 0 | 0 | 0 | 1968.72 | 0 | 0 | 0 | 0 | 1968.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505102 | W-WW-NI-060220- POWBURN WWPS NS352266- Replace Gear box on isolation valve - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-11 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -2336.45 | 163.55 | 2336.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505081 | W-WW-NI-060220- STEWARTON WWTW NS408449 - Fit sludge draw-off pipe - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-05-11 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -194.45 | 2305.55 | 0 | 0 | 0 | 2305.55 | 0 | 0 | 0 | 0 | 2305.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505079 | W-WW-NI-06022020- GIRVAN HARBOUR WWPS NX818982 - REPLACE ACTUATOR - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-07-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | -562.03 | 2937.97 | 0 | 0 | 0 | 2937.97 | 0 | 0 | 0 | 0 | 2937.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506094 | W-WW-NI-060420-DALGRAIN WWPS 1976 NS915823 - Replace Drive system for Storm Screw Pump 4 - 23.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-07-20 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23652.47 | 23652.47 | 0 | 0 | 0 | 23652.47 | 0 | 0 | 0 | 0 | 23652.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508114 | W-WW-NI-060820- BATTERY PARK WWPS NS254779 - HEALTH & SAFETY: REPLACE HANDRAIL & FLOOR GRATING AT INLET - 3.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-05-01 |  | 2020-09-16 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3110 | 3110 | 290 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508118 | W-WW-NI-060820- DALGRAIN WWPS 1976 NS915823 - REPLACEMENT CONTACTS FOR HV CONTACTORS - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-10 |  | 2020-10-26 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2599.59 | 2599.59 | 0 | 0 | 0 | 2599.59 | 0 | 0 | 0 | 0 | 2599.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508120 | W-WW-NI-060820- HOLMSTON WWPS 2 NS358214 - REFURBISH SUBMERSIBLE PUMP 1 - 3.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-10 |  | 2020-09-25 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3094.11 | 3094.11 | 0 | 0 | 0 | 3094.11 | 0 | 0 | 0 | 0 | 3094.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508117 | W-WW-NI-060820-STIRLING STC - REPLACE CONVEYOR DRIVE DRUM - 4.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-10 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244.31 | 4244.31 | 0 | 0 | 0 | 4244.31 | 0 | 0 | 0 | 0 | 4244.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510591 | W-WW-NI-070120- BOWHOUSE WWPS NS934805 - PLC REMEDIAL WORK - 11.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732.71 | 732.71 | 10467.28 | 0 | 0 | 11199.99 | 0 | 0 | 0 | 0 | 11199.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510611 | W-WW-NI-070121- BONNYBRIDGE WWTW NS836811 - REPLACE SCREEN DRIVE MOTOR - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-11 |  | 2021-03-20 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1445.52 | 1445.52 | 54.48 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510605 | W-WW-NI-070121- CATRINEHOLM WWTW NS522258 - REFURBISH INLET FINE SCREEN BASKET - 4.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-11 |  | 2021-03-05 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4011 | 4011 | 89 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510607 | W-WW-NI-070121- CUNNINGHAM ROAD WWPS NS811931 - REPLACE PUMP 1 - 2.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2232.46 | 2232.46 | 567.54 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 2800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510612 | W-WW-NI-070121- DALDERSE STC - Replace sludge digester pressure relief valves - 10.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660.75 | 660.75 | 9439.24 | 0 | 0 | 10099.99 | 0 | 0 | 0 | 0 | 10099.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510590 | W-WW-NI-070121- DALDERSE WWTW 1966 NS903822 - REPLACE FAILED BRUSH MOTOR - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1446.08 | 1446.08 | 53.92 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510577 | W-WW-NI-070121- DALMELLINGTON WWTW NS476050 - REFURBISH BELLSBANK INLET PUMP 3 - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274.77 | 274.77 | 3925.24 | 0 | 0 | 4200.01 | 0 | 0 | 0 | 0 | 4200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510586 | W-WW-NI-070121- EAST BAY WWPS NS175767 - REPLACE FLOW METER - 6.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1982.78 | 1982.78 | 4717.2 | 0 | 0 | 6699.98 | 0 | 0 | 0 | 0 | 6699.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510606 | W-WW-NI-070121- GIRVAN WWTW NX190999 - CRITICAL SPARES FOR DE-CANT ARMS - 8.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604.69 | 604.69 | 8317.76 | 0 | 0 | 8922.45 | 0 | 0 | 0 | 0 | 8922.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510596 | W-WW-NI-070121- HELENSBURGH WWTW 2001 NS321800 - REFURBISH HIGH TIDE LIFT PUMP 2 - 7.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-11 |  | 2021-03-04 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7111.47 | 7111.47 | 88.52 | 0 | 0 | 7199.99 | 0 | 0 | 0 | 0 | 7199.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510589 | W-WW-NI-070121- KINNING PARK WWPS NS575644 - REPLACE INLET PENSTOCK GEARBOX - 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372.9 | 372.9 | 5327.08 | 0 | 0 | 5699.98 | 0 | 0 | 0 | 0 | 5699.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510588 | W-WW-NI-070121- MILLPORT WWTW 2003 NS153540 - Refurbish Grit Auger - 13K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12936.61 | 12936.61 | 63.39 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 13000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510608 | W-WW-NI-070121- PARTICK WWPS NS565664 - INSTALL VSDs (ENERGY EFFICIENCY) - 28K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18371.78 | 18371.78 | 9628.2 | 0 | 0 | 27999.98 | 0 | 0 | 0 | 0 | 27999.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510604 | W-WW-NI-070121- PARTICK WWPS NS565664 - REFURBISH NEW FOUL PUMP 4 - 10.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680.37 | 680.37 | 9719.64 | 0 | 0 | 10400.01 | 0 | 0 | 0 | 0 | 10400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510578 | W-WW-NI-070121- SKELMORLIE SHORE ROAD WWPS NS193667 - INSTALL HANDRAIL BARRIER & 17 COVERS - 2.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2363.01 | 2363.01 | 36.99 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 2400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510610 | W-WW-NI-070121- UNDERWOOD (CUMNOCK) STC - REPLACE DRIVE FOR AIR BLOWER - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-11 |  | 2021-03-12 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2970.26 | 2970.26 | 29.72 | 0 | 0 | 2999.98 | 0 | 0 | 0 | 0 | 2999.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510575 | W-WW-NI-070121- WESTERHILL ROAD WWPS NS628716 - REPLACE SECURITY COVERS (H&S) - 7.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484.11 | 484.11 | 6915.88 | 0 | 0 | 7399.99 | 0 | 0 | 0 | 0 | 7399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512243 | W-WW-NI-070421- MAIDENS WWPS NS215081 - REPLACE SUBMERSIBLE PUMP 1 - 13.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-04-07 |  | 2021-07-07 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13400.03 | 0 | 0 | 13400.03 | 0 | 0 | 0 | 0 | 13400.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510599 | W-WW-NI-080121- NORTHFOOT WWPS 2000 NS942796 - FAST TRACK REPLACEMENT IMPELLER & WEAR RING - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-11 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2946.98 | 2946.98 | 53.02 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511379 | W-WW-NI-080221- KINNEIL KERSE WWTW 2001 NS960811 - REINSTATE WASHWATER SUPPLY TO BELT PRESS BUILDING - 8.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-22 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8024.91 | 8024.91 | 75.09 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 8100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504768 | W-WW-NI-090120- DALRYMPLE WWTW NS353141 - Replace RAS Pump 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -274.64 | 2225.36 | 0 | 0 | 0 | 2225.36 | 0 | 0 | 0 | 0 | 2225.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504757 | W-WW-NI-090120- MACINTYRE COURT WWPS NS353266 - Refurbish Control Panel - 9.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-09-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | -436.85 | 9063.15 | 0 | 0 | 0 | 9063.15 | 0 | 0 | 0 | 0 | 9063.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504665 | W-WW-NI-09012020- WEST KILBRIDE FOUL WWPS NS205464 - REFURBISH FOUL PUMP - URGENT - 17.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-05-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | -605.94 | 16894.06 | 0 | 0 | 0 | 16894.06 | 0 | 0 | 0 | 0 | 16894.06 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507627 | W-WW-NI-090220- GAILES WWPS NS323359 - REPLACE COOLING FANS FOR PUMPS NO2 VSD - 3.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-20 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202.8 | 202.8 | 2897.2 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511685 | W-WW-NI-090321- GIRVAN STC - REPLACE INDUSTRIAL HIGH PRESSURE CLEANER - 2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-11 |  | 2021-06-09 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2245.47 | 2245.47 | 54.53 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506197 | W-WW-NI-090420- BONESS WWTW NT022813- REPLACE SBR 2 DECANT DRIVE - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-10 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1653.91 | 1653.91 | 46.09 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506200 | W-WW-NI-090420- CASTLE LEVAN WWPS - Refurbish Submersible Pump - 10.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-14 |  | 2020-07-28 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10220.33 | 10220.33 | 0 | 0 | 0 | 10220.33 | 0 | 0 | 0 | 0 | 10220.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506196 | W-WW-NI-090420- DALGRAIN WWPS 1976 NS915823 - REFURBISH TRANSFORMER CUBICLE - 4.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-14 |  | 2020-07-20 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12426.27 | 12426.27 | 0 | 0 | 0 | 12426.27 | 0 | 0 | 0 | 0 | 12426.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506194 | W-WW-NI-090420- GIRVAN STC - REPLACE ASC CONTROLLER - 13.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-14 |  | 2020-10-14 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13328.64 | 13328.64 | 0 | 0 | 0 | 13328.64 | 0 | 0 | 0 | 0 | 13328.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506192 | W-WW-NI-090420- GIRVAN WWTW NX190999 - REPLACE BLOWER 1 - 17.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-14 |  | 2020-07-20 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17118.25 | 17118.25 | 0 | 0 | 0 | 17118.25 | 0 | 0 | 0 | 0 | 17118.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506206 | W-WW-NI-090420-LARGS BUCHANAN ST SPS EO PCSO NS198604-REPLACE STORM SCREEN GEARBOX- 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-16 |  | 2020-08-14 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2698.64 | 2698.64 | 0 | 0 | 0 | 2698.64 | 0 | 0 | 0 | 0 | 2698.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507931 | W-WW-NI-090720- ARROCHAR WWPS 2 NN296041 - REPLACE PIPEWORK ON INTERNAL RISING MAIN - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-31 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.36 | 959.36 | 4040.64 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507829 | W-WW-NI-090720- BONNYBRIDGE WWTW NS836811 - Supply and install a remote ACB auto close system for the mains power reset - 2.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-23 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 189.72 | 2710.28 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507800 | W-WW-NI-090720- DALDERSE WWTW 1966 NS903822 - 2 X Critical spare gearboxes and motors - 11.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-22 |  | 2020-09-03 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8277.03 | 8277.03 | 0 | 0 | 0 | 8277.03 | 0 | 0 | 0 | 0 | 8277.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507930 | W-WW-NI-090720- HOLMSBRIDGE WWPS NS362373 - HEALTH & SAFETY: REPLACE ROOF TILES & GUTTERING - 7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-31 |  | 2021-02-10 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6939.54 | 6939.54 | 60.46 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 7000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507929 | W-WW-NI-090720- MAYBOLE WWTW NS310088 - REFURBISH SCREEN REPLACE BASKET - 3.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-29 |  | 2020-08-25 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3311.31 | 3311.31 | 0 | 0 | 0 | 3311.31 | 0 | 0 | 0 | 0 | 3311.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507775 | W-WW-NI-090720- ROTHESAY WWTW 2002 NS100637 - REPLACE RING MAIN PIPEWORK & FLANGES - 3.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-22 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.89 | 215.89 | 5384.11 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 5600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507892 | W-WW-NI-090720-MEADOWHEAD WWTW NS339361- HEALTH & SAFETY: REPLACE GRIT WELL LIGHTING - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-29 |  | 2020-10-02 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1607.21 | 1607.21 | 0 | 0 | 0 | 1607.21 | 0 | 0 | 0 | 0 | 1607.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510225 | W-WW-NI-091220- GAILES WWPS NS323359 - REFURBISH STORM SUMP PUMP 7 - 42.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-10 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780.37 | 2780.37 | 39719.64 | 0 | 0 | 42500.01 | 0 | 0 | 0 | 0 | 42500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510222 | W-WW-NI-091220-GAILES WWPS NS323359 - REPLACE FANS ON VSDs - 5.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-10 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5495.81 | 5495.81 | 4.17 | 0 | 0 | 5499.98 | 0 | 0 | 0 | 0 | 5499.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511155 | W-WW-NI-100221- DALDERSE WWTW 1966 NS903822 - replace aerator gearboxes - 9.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6081.33 | 6081.33 | 3018.67 | 0 | 0 | 9100 | 0 | 0 | 0 | 0 | 9100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511159 | W-WW-NI-100221- DALDERSE WWTW 1966 NS903822 - Replace stub drive shaft - 6.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451.4 | 451.4 | 6448.6 | 0 | 0 | 6900 | 0 | 0 | 0 | 0 | 6900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505628 | W-WW-NI-100320- PRIORITY-DALGRAIN WWPS 1976 NS915823- REFURB 3.3KV STARTER - 15K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-11 |  | 2020-05-27 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 4278.81 | 9232 | 13510.81 | 0 | 0 | 0 | 13510.81 | 0 | 0 | 0 | 0 | 13510.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505621 | W-WW-NI-100320-PRIORITY-DALGRAIN WWPS 1976 NS915823- Replace Motor - 49.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-04-27 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 3244.86 | 41317 | 44561.86 | 0 | 0 | 0 | 44561.86 | 0 | 0 | 0 | 0 | 44561.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508131 | W-WW-NI-100820- BURNBRAE WWPS NS438638 - REINSTATE MAIN POWER CABLE - 12.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-10 |  | 2020-10-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12234.67 | 12234.67 | 0 | 0 | 0 | 12234.67 | 0 | 0 | 0 | 0 | 12234.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508751 | W-WW-NI-100920- COWIE WWTW 1972 NS849899 - H&S - HAND RAILING AROUND SITE - 40.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-22 |  | 2021-02-15 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37682.62 | 37682.62 | 3017.38 | 0 | 0 | 40700 | 0 | 0 | 0 | 0 | 40700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508750 | W-WW-NI-100920- DEANSTON WWTW NN713018 - H&S - COMPLETE HAND-RAILING ON SITE- 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-17 |  | 2020-11-25 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070.68 | 2070.68 | 0 | 0 | 0 | 2070.68 | 0 | 0 | 0 | 0 | 2070.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508748 | W-WW-NI-100920- DUNOON WWTW NS165745 - REPLACE DO PROBES - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-17 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2803.74 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508747 | W-WW-NI-100920- PARTICK WWPS NS565664 - REPLACE DOWN PIPE - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-17 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509709 | W-WW-NI-101120- ERSKINE WWTW NS494691 - POWER SUPPLY AND SLUDGE PIPEWORK - 9.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-11 |  | 2021-02-11 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9799.03 | 9799.03 | 0.98 | 0 | 0 | 9800.01 | 0 | 0 | 0 | 0 | 9800.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510354 | W-WW-NI-101220- AIRTH WWTW NS903881 - REPLACE GEARBOX - 4.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4735.29 | 4735.29 | 64.71 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 4800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510486 | W-WW-NI-101220- ARDROSSAN WWPS 2 NS226419 - REFURBISH STORM PUMP 2 - 15.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-23 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007.48 | 1007.48 | 14392.5 | 0 | 0 | 15399.98 | 0 | 0 | 0 | 0 | 15399.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510497 | W-WW-NI-101220- BONESS WWTW NT022813 - REPLACE PEN-STOCK - 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-23 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235.65 | 1235.65 | 64.35 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510360 | W-WW-NI-101220- DALMARNOCK SLUDGE WWPS 2000 NS610624 - REFURBISH MACERATOR 1 - 4.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-21 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4593.41 | 4593.41 | 6.6 | 0 | 0 | 4600.01 | 0 | 0 | 0 | 0 | 4600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510389 | W-WW-NI-101220- DUNBLANE WWTW NN782006 - REPLACE SCUM PUMP NRV - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-26 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1950.46 | 1950.46 | 49.56 | 0 | 0 | 2000.02 | 0 | 0 | 0 | 0 | 2000.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510372 | W-WW-NI-101220- ERSKINE WWTW NS494691 - REPLACE DO PROBE AERATION LANE 3 - 1.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-18 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113.26 | 1113.26 | 86.73 | 0 | 0 | 1199.99 | 0 | 0 | 0 | 0 | 1199.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510488 | W-WW-NI-101220- GIRVAN STC - REFURBISH CENTRIFUGE 2 DRIVE MOTOR - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-23 |  | 2021-04-02 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2531.6 | 2531.6 | 68.4 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510480 | W-WW-NI-101220- IRVINE SPORTS CLUB SPS 2012 NS314392 - REFURBISH STORM TRANSFER PUMPING B - 9.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-23 |  | 2021-03-26 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9128.05 | 9128.05 | 71.97 | 0 | 0 | 9200.02 | 0 | 0 | 0 | 0 | 9200.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510376 | W-WW-NI-101220- KINNEIL KERSE WWTW 2001 NS960811 - Replace SBR Decanter Arm - 8.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-22 |  | 2021-02-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8490.74 | 8490.74 | 9.24 | 0 | 0 | 8499.98 | 0 | 0 | 0 | 0 | 8499.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510489 | W-WW-NI-101220- NORTH LODGE SPS 2012 NS416364 - REPLACE ROTORK VALVE ACTUATOR - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-23 |  | 2021-03-29 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1473.64 | 1473.64 | 26.37 | 0 | 0 | 1500.01 | 0 | 0 | 0 | 0 | 1500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510374 | W-WW-NI-101220- PARTICK WWPS NS565664 - Replace control interface module and replacement IPD card for MCC - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-04-04 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4337.85 | 4337.85 | 62.16 | 0 | 0 | 4400.01 | 0 | 0 | 0 | 0 | 4400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510401 | W-WW-NI-101220- PORT GLASGOW NO2 CSO (NEWARK STREET) - REPLACE 3X PUMPS PIPES & VALVES - 7.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-12 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7439.83 | 7439.83 | 60.18 | 0 | 0 | 7500.01 | 0 | 0 | 0 | 0 | 7500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510292 | W-WW-NI-101220- SHIELDHALL WWTW NS533659 - REPLACE INLET FINE SCREENS MEGAWASHER 1 - 11.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 758.88 | 758.88 | 10841.13 | 0 | 0 | 11600.01 | 0 | 0 | 0 | 0 | 11600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510293 | W-WW-NI-101220- SHIELDHALL WWTW NS533659 - Replacement screw for compactor for inlet fine screen megawasher No 2 - 11.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-30 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22360.88 | 22360.88 | -10760.88 | 0 | 0 | 11600 | 0 | 0 | 0 | 0 | 11600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510382 | W-WW-NI-101220- STEVENSTON POINT WWTW NS275404 - REFURBISH MCC TRANSFORMER - 10.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693.46 | 693.46 | 9906.54 | 0 | 0 | 10600 | 0 | 0 | 0 | 0 | 10600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510379 | W-WW-NI-101220- STEWARTON WWTW NS408449 - Refurbish inlet and storm screens - 13.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-04-04 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13325.91 | 13325.91 | 74.1 | 0 | 0 | 13400.01 | 0 | 0 | 0 | 0 | 13400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510446 | W-WW-NI-101220- STEWARTON WWTW NS408449 - REPLACE GEARBOX ON PHT - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-26 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1711.91 | 1711.91 | 88.11 | 0 | 0 | 1800.02 | 0 | 0 | 0 | 0 | 1800.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510375 | W-WW-NI-101220- STEWARTON WWTW NS408449 - REPLACE VALVES & PIPES SLUDGE HOLDING TANK 1 - 6.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405.61 | 405.61 | 5794.41 | 0 | 0 | 6200.02 | 0 | 0 | 0 | 0 | 6200.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510388 | W-WW-NI-101220- STIRLING STC - REFURBISH CENTRIFUGE SCROLL - 18K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177.57 | 1177.57 | 16822.44 | 0 | 0 | 18000.01 | 0 | 0 | 0 | 0 | 18000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510478 | W-WW-NI-101220- STIRLING STC - REPLACE RAM ON CENTRIFUGE SLUDGE PRESS FEED PUMP 1 - 6.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-23 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6281.15 | 6281.15 | 18.85 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 6300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510498 | W-WW-NI-101220- STIRLING STC - REPLACE WASTE GAS BURNER PRESSURE SWITCHES & SOLENOID VALVES - 3.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-23 |  | 2021-03-05 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3097.8 | 3097.8 | 2.19 | 0 | 0 | 3099.99 | 0 | 0 | 0 | 0 | 3099.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510495 | W-WW-NI-101220- STIRLING WWTW 1968 NS808935 - REPLACE SPRAY BAR ASSEMBLY ON INLET SCREEN 2 - 3.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-23 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3509.51 | 3509.51 | 90.49 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510359 | W-WW-NI-101220- TYNDRUM WWTW NN330302 - REFURBISH AERATION TANK PIPEWORK - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-02-21 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2067.38 | 2067.38 | 32.64 | 0 | 0 | 2100.02 | 0 | 0 | 0 | 0 | 2100.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510373 | W-WW-NI-101220- TYNDRUM WWTW NN330302 - REPLACE DIFFUSERS - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294.39 | 294.39 | 4205.61 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505697 | W-WW-NI-11032020-FAST TRACK- MEADOWHEAD WWPS NS333356 - REPLACE FOUL PUMP 2 - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-05-14 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 1772.2 | 1903.04 | 0 | 0 | 0 | 1903.04 | 0 | 0 | 0 | 0 | 1903.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505694 | W-WW-NI-110320-FAST TRACK- ARROCHAR WWPS 1 NN294036 - REPLACE FOUL PUMP 1 - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-20 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 287.85 | 4111.48 | 4399.33 | 0 | 0 | 0 | 4399.33 | 0 | 0 | 0 | 0 | 4399.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505670 | W-WW-NI-110320-FAST TRACK- DALDERSE STC- REPLACE FILTRATE PUMP A - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-17 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 0 | 196.26 | 2803.74 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505665 | W-WW-NI-110320-FAST TRACK- ZETLAND PARK WWPS 2000 NS929811 - Refurb Storm Pump No3 - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-05-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 294.39 | 0 | 294.39 | 0 | 0 | 0 | 294.39 | 0 | 0 | 0 | 0 | 294.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508709 | W-WW-NI-110920- FISHERWOOD WWPS NS393815 - FAST TRACK REPLACE FOUL PUMP 1 - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-11 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274.77 | 274.77 | 3925.23 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504406 | W-WW-NI-11219- AUCHANS WWPS NS358349 - Refurb damaged pump - 16.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-07 |  | 2020-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | -15420.56 | 1079.44 | 15420.56 | 0 | 0 | 16500 | 0 | 0 | 0 | 0 | 16500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505805 | W-WW-NI-120320- ARDROSSAN WWPS 1 NS226419 - REPLACE 3X DOORS - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-09-30 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 3515 | 3763.6 | 0 | 0 | 0 | 3763.6 | 0 | 0 | 0 | 0 | 3763.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505807 | W-WW-NI-120320- BALMAHA WWTW NS420907 - H&S - Replace site lighting - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 0 | 170.09 | 2429.91 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505703 | W-WW-NI-120320- CASTLEGREEN WWPS NS408745 - REPLACE DRYWELL PUMP No1 - 17K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-27 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 1112.15 | 15749.92 | 16862.07 | 0 | 0 | 0 | 16862.07 | 0 | 0 | 0 | 0 | 16862.07 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505806 | W-WW-NI-120320- GARTOCHARN WWTW NS425863 - HEALTH & SAFETY- REPLACE LIGHTING - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-19 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 0 | 104.67 | 1495.33 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505795 | W-WW-NI-120320- GIRVAN STC - REPAIR ACCESS ROAD - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-09-29 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 654.21 | 9280 | 9934.21 | 0 | 0 | 0 | 9934.21 | 0 | 0 | 0 | 0 | 9934.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505753 | W-WW-NI-120320- HOPEBANK WWPS NR980700 - Replace Submersible Pump - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-20 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 2264.48 | 2428.03 | 0 | 0 | 0 | 2428.03 | 0 | 0 | 0 | 0 | 2428.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505786 | W-WW-NI-120320- UNDERWOOD (CUMNOCK) STC - REPLACE CONTROL PANEL DOOR - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-07-20 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 1520.94 | 1632.15 | 0 | 0 | 0 | 1632.15 | 0 | 0 | 0 | 0 | 1632.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509926 | W-WW-NI-121120- AIRTH WWTW NS903881 - REFURBISH PST BRIDGES - 8.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-23 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8107.15 | 8107.15 | 392.84 | 0 | 0 | 8499.99 | 0 | 0 | 0 | 0 | 8499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509978 | W-WW-NI-121120- AIRTH WWTW NS903881 - REFURBISH PST TRAILING WHEEL IDLER UNIT - 1.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-25 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1858.34 | 1858.34 | 41.66 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509937 | W-WW-NI-121120- ALLOA WWTW NS887918 - PSTs & STs bridge drive chain refurbishment - 8.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-25 |  | 2021-02-10 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6785.13 | 6785.13 | 2014.88 | 0 | 0 | 8800.01 | 0 | 0 | 0 | 0 | 8800.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509772 | W-WW-NI-121120- ARDROSSAN WWPS 2 NS226419 - REPLACE ELECTRICAL CONNECTIONS - 32.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-16 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24787.08 | 24787.08 | 7912.9 | 0 | 0 | 32699.98 | 0 | 0 | 0 | 0 | 32699.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509790 | W-WW-NI-121120- BALLECHROISK WWPS NN574328 - REPLACE PUMP 1 - 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-16 |  | 2021-02-10 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230.41 | 1230.41 | 69.58 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509861 | W-WW-NI-121120- BONNYBRIDGE WWTW NS836811 - INSTALL SECURITY GATES - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-19 |  | 2021-03-26 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2961.71 | 2961.71 | 38.3 | 0 | 0 | 3000.01 | 0 | 0 | 0 | 0 | 3000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509801 | W-WW-NI-121120- BOURTREEHILL WWPS NS344398 - Refurbish large crack on brick wall - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-16 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274.76 | 274.76 | 1825.24 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509792 | W-WW-NI-121120- BOVIS WWPS NS403414 - REPLACE PUMP - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-16 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2199.48 | 2199.48 | -99.48 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509956 | W-WW-NI-121120- DUNBLANE WWTW NN782006 - REFURBISH INLET SCREEN 2 - 10.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-25 |  | 2021-02-10 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10086.75 | 10086.75 | 13.24 | 0 | 0 | 10099.99 | 0 | 0 | 0 | 0 | 10099.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509808 | W-WW-NI-121120- FAIRLIE WWTW 1998 NS207559 - REPLACE DOOR (H&S) - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-16 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2803.74 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509773 | W-WW-NI-121120- GARTMORE WWTW NS525967 - Refurbish RAS return wheel pump - 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-16 |  | 2020-01-12 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5678.61 | 5678.61 | 0 | 0 | 0 | 5678.61 | 0 | 0 | 0 | 0 | 5678.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509781 | W-WW-NI-121120- GIRVAN WWTW NX190999 - Replace 2 x pump motors - 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-16 |  | 2021-03-28 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6634.72 | 6634.72 | 65.28 | 0 | 0 | 6700 | 0 | 0 | 0 | 0 | 6700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509793 | W-WW-NI-121120- LANGBANK WWPS NS378735 - Replace Foul Pump 1 - 13K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-16 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13815.41 | 13815.41 | -815.41 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 13000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509829 | W-WW-NI-121120- LUSS WWTW NS360927 - REPLACE INLET FLOW METER - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-19 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2803.74 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509821 | W-WW-NI-121120- MAUCHLINE WWTW NS492254 - REPLACE TANK GRATINGS WITH HINGED (H&S) - 6.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-19 |  | 2021-03-06 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6295.15 | 6295.15 | 4.84 | 0 | 0 | 6299.99 | 0 | 0 | 0 | 0 | 6299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509784 | W-WW-NI-121120- NEILSTON KIRKTONFIELD ROAD WWPS NS485573 - REPLACEMENT FOUL TRANSFER PUMP - 5.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-16 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366.36 | 366.36 | 5233.64 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 5600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509849 | W-WW-NI-121120- NORTHFOOT WWPS 2000 NS942796 - REPLACE UPS - 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-19 |  | 2021-02-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235.05 | 1235.05 | 64.94 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509868 | W-WW-NI-121120- PLEAN EAST WWPS NS840865 - REPLACE DISTRIBUTION BOARD - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-19 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2916.18 | 2916.18 | 83.82 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509836 | W-WW-NI-121120- POLMONTHILL WWPS 2000 NS953795 - REPLACE UPS - 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-19 |  | 2021-02-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235.05 | 1235.05 | 64.94 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509791 | W-WW-NI-121120- STEVENSTON POINT WWTW NS275404 - Refurbish Grit Pump No2B - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-16 |  | 2020-02-12 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2865.35 | 2865.35 | 0 | 0 | 0 | 2865.35 | 0 | 0 | 0 | 0 | 2865.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509855 | W-WW-NI-121120- ZETLAND PARK WWPS 2000 NS929811 - REPLACE UPS - 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-19 |  | 2021-02-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235.05 | 1235.05 | 64.94 | 0 | 0 | 1299.99 | 0 | 0 | 0 | 0 | 1299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504476 | W-WW-NI-121219 - DOUNE WWTW NN729008 - Security fence and bio arms - 9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-07 |  | 2020-07-27 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | -271.21 | 8728.79 | 0 | 0 | 0 | 8728.79 | 0 | 0 | 0 | 0 | 8728.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504454 | W-WW-NI-121219- BONESS WWTW NT022813 - Replace Control Probe - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-07 |  | 2020-06-15 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 1954.19 | 0 | 1954.19 | 0 | 0 | 0 | 1954.19 | 0 | 0 | 0 | 0 | 1954.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504555 | W-WW-NI-121219- DALMARNOCK WWTW NS611627 - Replace Aeration Motor - 2.1K - | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-08 |  | 2020-07-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 2207.03 | 0 | 2207.03 | 0 | 0 | 0 | 2207.03 | 0 | 0 | 0 | 0 | 2207.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504559 | W-WW-NI-121219- DALMARNOCK WWTW NS611627 - Replace HMI Screen - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-08 |  | 2020-07-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | -101.66 | 5898.34 | 0 | 0 | 0 | 5898.34 | 0 | 0 | 0 | 0 | 5898.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504417 | W-WW-NI-121219- ERSKINE WWTW NS494691 - replace faulty MLSS Probe - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-07 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -2336.45 | 163.55 | 2336.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504644 | W-WW-NI-121219- FAIRLIE WWTW 1998 NS207559 - Refurbish Pump - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-21 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 10375.97 | 0 | 10375.97 | 0 | 0 | 0 | 10375.97 | 0 | 0 | 0 | 0 | 10375.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504544 | W-WW-NI-121219 -GAILES WWPS NS323359 - REPLACE FOUL SUMP PUMP 3 - URGENT - 81K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-08 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | 4536.4 | 85536.4 | 0 | 0 | 0 | 85536.4 | 0 | 0 | 0 | 0 | 85536.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504598 | W-WW-NI-121219- KINNING PARK WWPS NS55644 - REFURBISH PUMP 3 - 22K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-07-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | -101.76 | 21898.24 | 0 | 0 | 0 | 21898.24 | 0 | 0 | 0 | 0 | 21898.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504596 | W-WW-NI-121219- KINNING PARK WWPS NS575644 - Replacement Soft Start - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | -4672.9 | 327.1 | 4672.9 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504550 | W-WW-NI-121219- PAISLEY LAIGHPARK INLET WWPS NS485655 - REFURBISH GEARBOX INLET PUMP 3 - URGENT - 36K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-08 |  | 2020-11-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 42081.7 | 35729.44 | 77811.14 | 0 | 0 | 0 | 77811.14 | 0 | 0 | 0 | 0 | 77811.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504459 | W-WW-NI-121219- SHIELDHALL WWTW NS533659 - Driveshaft and sprocket assembly - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-07 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 126.26 | 3126.26 | 0 | 0 | 0 | 3126.26 | 0 | 0 | 0 | 0 | 3126.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504577 | W-WW-NI-121219- SNAB LANE WWPS 1985 NS985810 - Replace Guide Poles - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-05-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 4902.29 | 0 | 4902.29 | 0 | 0 | 0 | 4902.29 | 0 | 0 | 0 | 0 | 4902.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504569 | W-WW-NI-121219- STIRLING WWTW 1968 NS808935 - Replacement Actuator - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-08 |  | 2020-05-14 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | -3271.03 | 228.97 | 0 | 0 | 0 | 228.97 | 0 | 0 | 0 | 0 | 228.97 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504592 | W-WW-NI-121219- TILLICOULTRY WWTW NS917965 - Refurbish & Replace Drive Unit critical spare for FSTs - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-10 |  | 2020-05-14 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | -218.34 | 3781.66 | 0 | 0 | 0 | 3781.66 | 0 | 0 | 0 | 0 | 3781.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504564 | W-WW-NI-121219-BRODIE GROVE WWPS NS680649- Replace Guide Rails - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-02-13 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | -175.4 | 4824.6 | 0 | 0 | 0 | 4824.6 | 0 | 0 | 0 | 0 | 4824.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504441 | W-WW-NI-121219-HELENSBURGH WWTW 2001 NS321800 - REPLACE WELL PLATES (H&S) - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-07 |  | 2020-07-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 10521.21 | 0 | 10521.21 | 0 | 0 | 0 | 10521.21 | 0 | 0 | 0 | 0 | 10521.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504619 | W-WW-NI-121219-UNDERCLIFF RD WWPS 1993 NS190698 - Replace dorrs x3 & Self closing gate x1 - H&S - 9.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-04-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | -689.52 | 8810.48 | 0 | 0 | 0 | 8810.48 | 0 | 0 | 0 | 0 | 8810.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504409 | W-WW-NI-12219- DUMBARTON DISTILLERY WWPS NS397751 - Install bauer connection - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-07 |  | 2020-07-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 132.02 | 4632.02 | 0 | 0 | 0 | 4632.02 | 0 | 0 | 0 | 0 | 4632.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505210 | W-WW-NI-130220- AYR SHORE ROAD WWPS NS338232 - Remove overhead gantry - 11K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-17 |  | 2020-07-20 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 10631.12 | 0 | 10631.12 | 0 | 0 | 0 | 10631.12 | 0 | 0 | 0 | 0 | 10631.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505229 | W-WW-NI-130220- DALDERSE STC- 3x Gate Valves for de-watering tree - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-17 |  | 2020-06-09 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | -134.36 | 4965.64 | 0 | 0 | 0 | 4965.64 | 0 | 0 | 0 | 0 | 4965.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505309 | W-WW-NI-130220- ERSKINE WWTW NS494691 - Replace Motor & SCR Board - 20.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-20 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 8377.33 | -7029.67 | 1347.66 | 19252.34 | 0 | 0 | 20600 | 0 | 0 | 0 | 0 | 20600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505253 | W-WW-NI-130220- FAIRLIE WWTW 1998 NS207559 - REPLACE GUIDE RAILS X2 - 4.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-18 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 1992.67 | -1672.11 | 320.56 | 4579.44 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 4900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505227 | W-WW-NI-130220- LAIGHPARK PAISLEY WWTW NS485655 - Repair Access Road - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-17 |  | 2020-05-27 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 1717.76 | 0 | 1717.76 | 0 | 0 | 0 | 1717.76 | 0 | 0 | 0 | 0 | 1717.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505314 | W-WW-NI-130220- MAY STREET WWPS NS205585- Replace MH Covers (H&S) - 1.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-03 |  | 2020-11-11 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 772.67 | 779.63 | 1552.3 | 0 | 0 | 0 | 1552.3 | 0 | 0 | 0 | 0 | 1552.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505268 | W-WW-NI-130220- MEADOWHEAD WWTW NS339361 - Access Platform - H&S - 6.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-24 |  | 2020-08-13 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2602.67 | 3617.67 | 6220.34 | 0 | 0 | 0 | 6220.34 | 0 | 0 | 0 | 0 | 6220.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505311 | W-WW-NI-130220- MEADOWHEAD WWTW NS339361 - New Filter for final effluent washwater - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-20 |  | 2020-05-04 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 1504.67 | 1511.75 | 3016.42 | 0 | 0 | 0 | 3016.42 | 0 | 0 | 0 | 0 | 3016.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505313 | W-WW-NI-130220- MEADOWHEAD WWTW NS339361 - Screen Plates - 3.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-20 |  | 2020-09-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 1382.67 | 1868.92 | 3251.59 | 0 | 0 | 0 | 3251.59 | 0 | 0 | 0 | 0 | 3251.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505242 | W-WW-NI-130220- PAISLEY LAIGHPARK SLDG TFR WWPS NS485655 - refurb sludge pump no.2 - 10.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-17 |  | 2020-07-27 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 10400 | -347.01 | 10052.99 | 0 | 0 | 0 | 10052.99 | 0 | 0 | 0 | 0 | 10052.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505207 | W-WW-NI-130220- TILLICOULTRY WWTW NS917965 - REFURBISH AERATOR - 2.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-14 |  | 2020-06-17 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | -90.82 | 2709.18 | 0 | 0 | 0 | 2709.18 | 0 | 0 | 0 | 0 | 2709.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505312 | W-WW-NI-130220- WEST KILBRIDE FOUL WWPS NS205464 - Foul Pump Refurb - 11.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-20 |  | 2020-05-14 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 4839.33 | 6668 | 11507.33 | 0 | 0 | 0 | 11507.33 | 0 | 0 | 0 | 0 | 11507.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506597 | W-WW-NI-130520-DALDERSE WWTW 1966 NS903822- REPLACE RAS PUMP 6 - 3.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-14 |  | 2020-07-03 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3270.27 | 3270.27 | 0 | 0 | 0 | 3270.27 | 0 | 0 | 0 | 0 | 3270.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508208 | W-WW-NI-130820- BRYCE AVENUE WWPS NS890828 - Refurbish storm pump panels - 4.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-20 |  | 2021-03-06 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4770.34 | 4770.34 | 29.66 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 4800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508212 | W-WW-NI-130820- COWIE WWTW 1972 NS849899 - REPLACE SCREEN WASH WATER PUMP - 3.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-20 |  | 2020-09-30 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3142.35 | 3142.35 | 0 | 0 | 0 | 3142.35 | 0 | 0 | 0 | 0 | 3142.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508272 | W-WW-NI-130820- DALDERSE WWTW 1966 NS903822 - REPLACE SECTIONS OF SLUDGE RISING MAIN - 5.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5514.02 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 5900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508206 | W-WW-NI-130820- GIRVAN STC - REPLACE SLUDGE SCREEN GEARBOX - 2.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-20 |  | 2020-09-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2797.56 | 2797.56 | 0 | 0 | 0 | 2797.56 | 0 | 0 | 0 | 0 | 2797.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508194 | W-WW-NI-130820- IRVINE BEACH PARK WWPS NS312374 - REPLACE 2X FOUL PUMPS - 10.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-20 |  | 2020-10-23 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10295.34 | 10295.34 | 0 | 0 | 0 | 10295.34 | 0 | 0 | 0 | 0 | 10295.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508245 | W-WW-NI-130820- PLEAN WWTW NS841870 - Replace PST wallheads - 9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-20 |  | 2020-10-06 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8975.22 | 8975.22 | 0 | 0 | 0 | 8975.22 | 0 | 0 | 0 | 0 | 8975.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508273 | W-WW-NI-130820- POLMONTHILL WWPS 2000 NS953795 - INSTALL AIR VALVE INTO RISING MAIN - 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263.85 | 1263.85 | 36.15 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508269 | W-WW-NI-130820- STIRLING STC - HEALTH & SAFETY - Replace Handrails & gratings at top of Digester - 9.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-20 |  | 2020-10-27 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9207.41 | 9207.41 | 0 | 0 | 0 | 9207.41 | 0 | 0 | 0 | 0 | 9207.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508227 | W-WW-NI-130820- TYNDRUM WWTW NN330302 - REPLACE ROTORK VALVE ACTUATOR (AERATION TANK 2) - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2376.29 | 2376.29 | 223.71 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508252 | W-WW-NI-130820- ZETLAND PARK WWPS 2000 NS929811 - FAST TRACK- REPLACE FOUL PUMP 3 - 8.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.91 | 529.91 | 7570.09 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 8100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508276 | W-WW-NI-130820-DALGRAIN WWPS 1976 NS915823 - REPLACE INLET SCREEN ACTUATOR - 9.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-20 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634.58 | 634.58 | 9065.42 | 0 | 0 | 9700 | 0 | 0 | 0 | 0 | 9700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503813 | W-WW-NI-131119-Boness WwTW- Replace Service Water Booster Pump 1 - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-07 |  | 2020-09-17 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | -60.53 | 5939.47 | 0 | 0 | 0 | 5939.47 | 0 | 0 | 0 | 0 | 5939.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503821 | W-WW-NI-131119-BRAEHEAD SHOPPING CENTRE WWPS-New Components for electrical & pump install- JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | 209.05 | 4309.05 | 0 | 0 | 0 | 4309.05 | 0 | 0 | 0 | 0 | 4309.05 | 90601.29 | [5 empty] | N | WWNI | 100%
504646 | W-WW-NI-140120-Stevenston Point WWTW-Critical Spares-11.1k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-12 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 11140.71 | 726.17 | 11866.88 | -652.17 | 0 | 0 | 11214.71 | 0 | 0 | 0 | 0 | 11214.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510705 | W-WW-NI-140121- DALRYMPLE WWTW NS353141 - FLOW SURVEY - 6.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6375.86 | 6375.86 | 424.14 | 0 | 0 | 6800 | 0 | 0 | 0 | 0 | 6800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510704 | W-WW-NI-140121- ERSKINE WWTW NS494691 - Turbo Failure machine Inspection - 5.7k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-15 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4811.9 | 4811.9 | 888.08 | 0 | 0 | 5699.98 | 0 | 0 | 0 | 0 | 5699.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506202 | W-WW-NI-140420- FAST TRACK- LEGGATE WWPS NS611131- REPLACE SUBMERSIBLE PUMP - 5.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-16 |  | 2020-07-20 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520.8 | 5520.8 | 0 | 0 | 0 | 5520.8 | 0 | 0 | 0 | 0 | 5520.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506660 | W-WW-NI-140520- AIRTH WWTW NS903881 - REFURB EMS RAM PUMP CHAMBERS - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-04 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586.09 | 2586.09 | 0 | 0 | 0 | 2586.09 | 0 | 0 | 0 | 0 | 2586.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506703 | W-WW-NI-140520- ALLOA WWTW WWPS NS887918 - H&S WORKS - 5.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-09-03 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5237.02 | 5237.02 | 0 | 0 | 0 | 5237.02 | 0 | 0 | 0 | 0 | 5237.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506831 | W-WW-NI-140520- ALLOWAY DUTCH MILL WWPS 2003 NS335178- BUILDING WORKS: RENDER WALL FIX FENCE & GATE - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1962.62 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506653 | W-WW-NI-140520- ALVA WWTW NS874966 - Refurb Aeration Rotor (Aerator 2) - 6.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-18 |  | 2020-06-19 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6159.61 | 6159.61 | 0 | 0 | 0 | 6159.61 | 0 | 0 | 0 | 0 | 6159.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506706 | W-WW-NI-140520- CAMBUSBARRON KERSEBONNY RD NS77924803 - REPLACE ACTUATOR CONTROL PANEL & UPS - 10.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-10-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10309.47 | 10309.47 | 0 | 0 | 0 | 10309.47 | 0 | 0 | 0 | 0 | 10309.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506723 | W-WW-NI-140520- DALDERSE WWTW 1966 NS903822 - INSTALL CRITICAL SPARES X4 - 8.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-07-23 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8473.47 | 8473.47 | 0 | 0 | 0 | 8473.47 | 0 | 0 | 0 | 0 | 8473.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506717 | W-WW-NI-140520- DENNY STW INLET WWPS 1971 NS819829 - REPLACE SPAANS GEARBOX & TOP BEARING - 15.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4745.19 | 4745.19 | 11154.81 | 0 | 0 | 15900 | 0 | 0 | 0 | 0 | 15900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506692 | W-WW-NI-140520- DRONGAN WWTW NS429187 - REPLACE MOTOR & GEARBOX (PST 2 SCRAPER BRIDGE) - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-20 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020.84 | 2020.84 | -20.84 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506629 | W-WW-NI-140520- EASTFIELD GLASGOW WWPS NS610622 - REPLACE GUIDE RAILS (H&S) - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-18 |  | 2020-07-29 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3988.56 | 3988.56 | 0 | 0 | 0 | 3988.56 | 0 | 0 | 0 | 0 | 3988.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506704 | W-WW-NI-140520- FINTRY WWTW NS614873 - REPLACE INLET PUMP 1 - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506782 | W-WW-NI-140520- FINTRY WWTW NS614873- REPLACE TASK LIGHTING: HEALTH & SAFETY - 1.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 78.5 | 1121.5 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506677 | W-WW-NI-140520- KINNEIL KERSE WWTW 2001 NS960811 - REPLACE PUMP ROTOR - 4.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-19 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4082.85 | 4082.85 | 0 | 0 | 0 | 4082.85 | 0 | 0 | 0 | 0 | 4082.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506699 | W-WW-NI-140520- LAIGHPARK PAISLEY WWTW NS485655 - INSTALL CABLE DUCT - 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-20 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242.2 | 1242.2 | 57.8 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506656 | W-WW-NI-140520- NORTH LODGE ROAD WWPS 1 NS504682 - REPLACE 2X VALVE COUPLINGS - 4.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-08 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526.75 | 4526.75 | 0 | 0 | 0 | 4526.75 | 0 | 0 | 0 | 0 | 4526.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506644 | W-WW-NI-140520- SHIELDHALL WWTW NS533659 - DSEAR assessment and training - 13.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-18 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857.01 | 857.01 | 12242.99 | 0 | 0 | 13100 | 0 | 0 | 0 | 0 | 13100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506662 | W-WW-NI-140520- TILLICOULTRY WWTW NS917965 - REFURB INLET SCREEN 1 - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-29 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3469.84 | 3469.84 | 0 | 0 | 0 | 3469.84 | 0 | 0 | 0 | 0 | 3469.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506834 | W-WW-NI-140520-BARRMILL WWTW NS368513- REPLACE pH PROBE - 7.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7668.78 | 7668.78 | -168.78 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506873 | W-WW-NI-140520-BROADWOOD WWPS NS726743- BUILDING WORKS INCL TOILET BASIN & RENDER- 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-06-19 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482.13 | 1482.13 | 0 | 0 | 0 | 1482.13 | 0 | 0 | 0 | 0 | 1482.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506675 | W-WW-NI-140520-CAMBUS MAIN WWPS NS856942- REPLACE NRV ON FOUL PUMP 1 - 3.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-05-20 |  | 2021-02-23 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1841.22 | 1841.22 | 1258.78 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506874 | W-WW-NI-140520-GIRVAN STC- REPLACE EXTRACTION DUCTING (HEALTH & SAFETY) - 39K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-10-13 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40694.4 | 40694.4 | 0 | 0 | 0 | 40694.4 | 0 | 0 | 0 | 0 | 40694.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506738 | W-WW-NI-140520-KINNEIL KERSE WWTW 2001 NS960811- BUILDING ELECTRICAL WORKS - 8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-08-05 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7912.36 | 7912.36 | 0 | 0 | 0 | 7912.36 | 0 | 0 | 0 | 0 | 7912.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506781 | W-WW-NI-140520-KIPPEN WWTW NS653952- REPLACE TASK LIGHTING: HEALTH & SAFETY - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1401.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506792 | W-WW-NI-140520-STEWARTON WWTW NS408449- REPLACE SHOWER AREA (H&S) - 9.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-10-06 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9848.86 | 9848.86 | 0 | 0 | 0 | 9848.86 | 0 | 0 | 0 | 0 | 9848.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509271 | W-WW-NI-141020- TYNDRUM WWTW NN330302 - FAST TRACK - REPLACE PRIMARY SLUDGE TRANSFER PUMP - 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-20 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1233.98 | 1233.98 | 66.02 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509272 | W-WW-NI-141020-STATION AVENUE HOWWOOD SPS - FAST TRACK - REPLACE FOUL PUMP 2 - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-20 |  | 2020-02-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2458.89 | 2458.89 | 0 | 0 | 0 | 2458.89 | 0 | 0 | 0 | 0 | 2458.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503823 | W-WW-NI-141119-Kinning Park WWPS - Refurb & Install of Motor No3 - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | -3831.78 | 268.22 | 3831.78 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503825 | W-WW-NI-141119-Paisley Laighpark SLDG TFR WWPS -Supply & Fit new Ventilation Fan - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-03 |  | 2020-01-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2059.88 | 0 | 2059.88 | 0 | 0 | 0 | 2059.88 | 0 | 0 | 0 | 0 | 2059.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504657 | W-WW-NI-15012020- EASTER DULLATUR WWPS 2008 NS745773 - REPLACE SUBMERSIBLE PUMP - FAST TRACK - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-03-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | -297.55 | 3202.45 | 0 | 0 | 0 | 3202.45 | 0 | 0 | 0 | 0 | 3202.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504669 | W-WW-NI-150120-May Street WwPS-Starter Panel Replacement-2.9k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-09 |  | 2020-05-05 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3803.62 | 3803.62 | 0 | 0 | 0 | 3803.62 | 0 | 0 | 0 | 0 | 3803.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507280 | W-WW-NI-15062020-DUNOON WWTW NS165745- Fast Track: Replace RAS Pump B - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-09-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4354.53 | 4354.53 | 0 | 0 | 0 | 4354.53 | 0 | 0 | 0 | 0 | 4354.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509370 | W-WW-NI-151020- CUMNOCK UNDERWOOD WWTW NS558204 - Replace Hydrovane Compressor - 10.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-26 |  | 2021-02-28 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19140.57 | 19140.57 | 59.43 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 19200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509395 | W-WW-NI-151020- CUMNOCK UNDERWOOD WWTW NS558204 - REPLACE REFRIGERATED SAMPLER UNIT - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-26 |  | 2020-08-12 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1643.61 | 1643.61 | 0 | 0 | 0 | 1643.61 | 0 | 0 | 0 | 0 | 1643.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509342 | W-WW-NI-151020- DALDERSE WWTW 1966 NS903822 - REFURBISH INLET SCREEN 1 - 41.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-26 |  | 2020-11-25 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41199.15 | 41199.15 | 0 | 0 | 0 | 41199.15 | 0 | 0 | 0 | 0 | 41199.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509360 | W-WW-NI-151020- DALDERSE WWTW 1966 NS903822 - REPLACE DRIVE COUPLINGS - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-26 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1962.62 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509356 | W-WW-NI-151020- DALDERSE WWTW 1966 NS903822 - REPLACE MOTORS - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-26 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1711.43 | 1711.43 | 88.57 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509354 | W-WW-NI-151020- DALDERSE WWTW 1966 NS903822 - REPLACE OVER PRESSURE SWITCHES - 10.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-26 |  | 2021-02-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10121.05 | 10121.05 | 78.95 | 0 | 0 | 10200 | 0 | 0 | 0 | 0 | 10200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509353 | W-WW-NI-151020- DALDERSE WWTW 1966 NS903822 - REPLACEMENT MOTOR & VSD DRIVE - 3.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-26 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3095.8 | 3095.8 | 4.2 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509477 | W-WW-NI-151020- DALMARNOCK SLUDGE WWPS 2000 NS610624 - Replace 2x Cylinder RAMs on pumps 2&3 - 11.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-28 |  | 2021-02-25 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11525.88 | 11525.88 | 74.12 | 0 | 0 | 11600 | 0 | 0 | 0 | 0 | 11600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509476 | W-WW-NI-151020- DALMARNOCK SLUDGE WWPS 2000 NS610624 - REPLACE CPU - 2.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-11-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2352.01 | 2352.01 | 0 | 0 | 0 | 2352.01 | 0 | 0 | 0 | 0 | 2352.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509507 | W-WW-NI-151020- DALMARNOCK WWTW NS611627 - ACCESS GATES (H&S) - 15.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15758.58 | 15758.58 | 41.42 | 0 | 0 | 15800 | 0 | 0 | 0 | 0 | 15800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509479 | W-WW-NI-151020- DALMARNOCK WWTW NS611627 - REPLACE CRITICAL SPARE GEARBOX PINIONS - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-28 |  | 2021-03-07 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2007.33 | 2007.33 | 92.67 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509454 | W-WW-NI-151020- DOUNE WWTW NN729008 - REPLACE PORTABLE AREA VELOCITY FLOW METER - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-26 |  | 2020-11-20 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6576.27 | 6576.27 | -576.27 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 6000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509458 | W-WW-NI-151020- ERSKINE WWTW NS494691 - Replace Aeration MLSS Monitor - 1.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-11-23 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075.27 | 1075.27 | 0 | 0 | 0 | 1075.27 | 0 | 0 | 0 | 0 | 1075.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509299 | W-WW-NI-151020- GAILES WWPS NS323359 - REFURBISH STORM PUMP 7 - 15.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-20 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15613.73 | 15613.73 | 86.27 | 0 | 0 | 15700 | 0 | 0 | 0 | 0 | 15700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509397 | W-WW-NI-151020- GIRVAN STC - REPLACE LIGHTING (H&S) - 3.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-26 |  | 2020-11-24 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3073.14 | 3073.14 | 0 | 0 | 0 | 3073.14 | 0 | 0 | 0 | 0 | 3073.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509401 | W-WW-NI-151020- GIRVAN WWTW NX190999 - Replace 2x air inlet control valves - 4.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-26 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4064.22 | 4064.22 | 35.78 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 4100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509474 | W-WW-NI-151020- LARGS BUCHANAN ST WWPS 2009 NS199605 - Refurbish Critical Spare Transfer Pump 1 - 42.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 2800 | 40000 | 0 | 0 | 42800 | 0 | 0 | 0 | 0 | 42800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509475 | W-WW-NI-151020- LARGS BUCHANAN ST WWPS 2009 NS199605 - Refurbish Critical Spare Transfer Pump 2 - 42.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 2800 | 40000 | 0 | 0 | 42800 | 0 | 0 | 0 | 0 | 42800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509412 | W-WW-NI-151020- MAYBOLE WWTW NS310088 - Replace Access Ladder (H&S) - 3.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-26 |  | 2021-03-05 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3363.43 | 3363.43 | 36.57 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509491 | W-WW-NI-151020- NEILSTON WWTW NS479578 - REFURBISH SHOWER AREA - 2.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-28 |  | 2021-02-28 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4450.07 | 4450.07 | 249.93 | 0 | 0 | 4700 | 0 | 0 | 0 | 0 | 4700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509480 | W-WW-NI-151020- NEILSTON WWTW NS479578 - REPLACE DOOR SET (H&S) - 2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-28 |  | 2021-03-01 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2288.19 | 2288.19 | 11.81 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509384 | W-WW-NI-151020- NEW CUMNOCK WWTW NS622140 - REFURBISH MOTOR & GEARBOX UNIT - 8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-26 |  | 2021-02-10 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7910.63 | 7910.63 | 89.37 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509317 | W-WW-NI-151020- PAISLEY LAIGHPARK SLDG TFR WWPS NS485655 - REPLACE ISOLATOR SWITCH (H&S) - 2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-20 |  | 2020-11-14 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2211.86 | 2211.86 | 0 | 0 | 0 | 2211.86 | 0 | 0 | 0 | 0 | 2211.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509468 | W-WW-NI-151020- SCOTT ELLIS WWPS NS437372 - BRICK UP ENTRY TO OLD STORM SCRAPER BUILDING - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1589.67 | 1589.67 | 10.33 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509472 | W-WW-NI-151020- SCOTT ELLIS WWPS NS437372 - REPLACE FENCE - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1414.13 | 1414.13 | 85.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509495 | W-WW-NI-151020- SHIELDHALL WWTW NS533659 - REPAIR SINK HOLE - 6.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-07-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6162.28 | 6162.28 | 0 | 0 | 0 | 6162.28 | 0 | 0 | 0 | 0 | 6162.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509319 | W-WW-NI-151020- SHIELDHALL WWTW NS533659 - REPLACE SCREW FOR MEGAWASHER - 15.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-10-20 |  | 2021-02-20 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15785.64 | 15785.64 | 14.36 | 0 | 0 | 15800 | 0 | 0 | 0 | 0 | 15800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509478 | W-WW-NI-151020- SHIELDHALL WWTW NS533659 - REPLACE SECURITY GATE - 25.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681.31 | 1681.31 | 24018.69 | 0 | 0 | 25700 | 0 | 0 | 0 | 0 | 25700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509463 | W-WW-NI-151020- SHIELDHALL WWTW NS533659 - REPLACE TOUCHSCREEN ON PST 5 BRIDGE - 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-28 |  | 2020-11-13 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5635.4 | 5635.4 | 0 | 0 | 0 | 5635.4 | 0 | 0 | 0 | 0 | 5635.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509364 | W-WW-NI-151020- STIRLING WWTW SPS 2001 NS807935 - REPLACE STORM SCREEN AUGER - 22K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-26 |  | 2021-02-10 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21925.58 | 21925.58 | 74.42 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 22000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509365 | W-WW-NI-151020-BONNYBRIDGE WWTW NS836811- INSTALL SECURITY FENCE - 6.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-26 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6413.23 | 6413.23 | 86.77 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509387 | W-WW-NI-151020-CUMNOCK UNDERWOOD WWTW NS558204 - REFURBISH PERIMETER FENCE - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-26 |  | 2021-02-10 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2622.14 | 2622.14 | 77.86 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509425 | W-WW-NI-151020-DRYMEN WWTW NS474877- REPLACE MANHOLE COVER (H&S) - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-10-26 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1588.79 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509375 | W-WW-NI-151020-MAYBOLE WWTW NS310088- REPLACE SAS PUMP 1- 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-26 |  | 2021-02-10 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5674.4 | 5674.4 | 25.6 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 5700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504799 | W-WW-NI-16012- CAMERON HOUSE (REAR) WWPS NS375830- Replace both internal risers & fit bauer couplings - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-30 |  | 2021-03-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | -311.3 | 3888.7 | 311.3 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504756 | W-WW-NI-16012020- BONNYBRIDGE WWTW NS836811 - Portable Pump - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-05-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -384.49 | 2115.51 | 0 | 0 | 0 | 2115.51 | 0 | 0 | 0 | 0 | 2115.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504707 | W-WW-NI-16012020- BONNYBRIDGE WWTW NS836811 - Replace current feed pump with a Rotary Lobe Feed Pump - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-21 |  | 2020-05-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2080.46 | 7080.46 | 0 | 0 | 0 | 7080.46 | 0 | 0 | 0 | 0 | 7080.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504710 | W-WW-NI-16012020- BONNYBRIDGE WWTW NS836811 - Replace failed Motor Gearbox - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-21 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | -5400.58 | 4599.42 | 5400.58 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504732 | W-WW-NI-16012020- GIRVAN STC - Replace Bi-fold with new Roller door - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-29 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2118.84 | 2118.84 | -118.84 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504790 | W-WW-NI-160120-ABBOTSHAUGH WWPS 1975 NS900815- REPLACE FOUL PUMP - 8.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-05-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8200 | -2806.73 | 5393.27 | 0 | 0 | 0 | 5393.27 | 0 | 0 | 0 | 0 | 5393.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504896 | W-WW-NI-160120-ARDOCH WWTW 2002 NS374758- Gearbox & Wheel Replacement- 6.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-30 |  | 2020-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | -6074.77 | 425.23 | 6074.77 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504794 | W-WW-NI-160120-ARDROSSAN WWPS 2 NS226419- REFURBISH STORM SCREEN - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | -97.56 | 3402.44 | 0 | 0 | 0 | 3402.44 | 0 | 0 | 0 | 0 | 3402.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504795 | W-WW-NI-160120-BUCHANS BRIDGE WWPS NS473062- REPLACE SUBMERSIBLE PUMP - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-30 |  | 2020-03-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1917.58 | 0 | 1917.58 | 0 | 0 | 0 | 1917.58 | 0 | 0 | 0 | 0 | 1917.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504798 | W-WW-NI-160120-DALMELLINGTON WWTW NS476050- Refurbish Inlet Pump - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-30 |  | 2020-04-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -327.99 | 2172.01 | 0 | 0 | 0 | 2172.01 | 0 | 0 | 0 | 0 | 2172.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504793 | W-WW-NI-160120-KIPPEN WWTW NS653952- REPLACE LIQUOR RETURN PUMP - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-23 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | -135.46 | 3864.54 | 135.46 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504792 | W-WW-NI-160120-STIRLING STC- BUILDING ALTERATIONS - 9.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-23 |  | 2020-05-14 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | -634.02 | 8865.98 | 0 | 0 | 0 | 8865.98 | 0 | 0 | 0 | 0 | 8865.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504766 | W-WW-NI-160120-STIRLING WWTW 1968 NS808935- Refurbish Aerator Gearbox - 10.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-05-14 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | -445.89 | 10054.11 | 0 | 0 | 0 | 10054.11 | 0 | 0 | 0 | 0 | 10054.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504796 | W-WW-NI-160120-STIRLING WWTW 1968 NS808935- Replace actuators x2 supply only - 7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-30 |  | 2020-06-15 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | -388.66 | 6611.34 | 0 | 0 | 0 | 6611.34 | 0 | 0 | 0 | 0 | 6611.34 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506260 | W-WW-NI-160420- CAMBUSBARRON KERSEBONNY RD NS77924803 - REFURBISH CSO SCREEN - 9.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-06-03 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9447.41 | 9447.41 | 0 | 0 | 0 | 9447.41 | 0 | 0 | 0 | 0 | 9447.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506254 | W-WW-NI-160420- DALMELLINGTON WWTW NS476050 - REPLACE GEARBOX - 18K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-23 |  | 2020-07-16 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17883.1 | 17883.1 | 0 | 0 | 0 | 17883.1 | 0 | 0 | 0 | 0 | 17883.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506256 | W-WW-NI-160420- KINNING PARK WWPS NS575644 - REFURBISH SEWAGE PUMP - 23.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-06-10 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26671.39 | 26671.39 | 0 | 0 | 0 | 26671.39 | 0 | 0 | 0 | 0 | 26671.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506253 | W-WW-NI-160420- OCHILTREE WWTW NS508215 - REPLACE RAS WHEEL GEARBOX - 3.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-23 |  | 2020-07-16 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093 | 3093 | 0 | 0 | 0 | 3093 | 0 | 0 | 0 | 0 | 3093 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506251 | W-WW-NI-160420- STIRLING WWTW 1968 NS808935- REPLACE SBR 2 DECANT ARM GEARBOX - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-23 |  | 2020-07-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167.85 | 4167.85 | 0 | 0 | 0 | 4167.85 | 0 | 0 | 0 | 0 | 4167.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506249 | W-WW-NI-160420-FAST TRACK- FOUL PUMP 1 - BOURTREEHILL WWPS NS344398- REPLACE FOUL PUMP 1 - 9.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-23 |  | 2020-06-26 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9378 | 9378 | 0 | 0 | 0 | 9378 | 0 | 0 | 0 | 0 | 9378 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505760 | W-WW-NI-170320 - DALDERSE STC - BOILER REPAIR - 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-03-19 |  | 2021-02-25 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 372.9 | 5250 | 5622.9 | 77.1 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 5700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505764 | W-WW-NI-170320- DOLLAR WWTW NS953978 - REPLACE SBR DECANTER ARM - 8.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-19 |  | 2020-04-12 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 536.45 | 7589.7 | 8126.15 | 0 | 0 | 0 | 8126.15 | 0 | 0 | 0 | 0 | 8126.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508887 | W-WW-NI-170920 - CUMNOCK UNDERWOOD WWTW NS558204 - REFURBISH SAND FILTERS - 36K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-28 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35938.09 | 35938.09 | 0 | 0 | 0 | 35938.09 | 0 | 0 | 0 | 0 | 35938.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508929 | W-WW-NI-170920- ARDOCH WWTW 2002 NS374758 - REPLACE GATE ACCESS (DILLICHIP) - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-28 |  | 2020-11-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4457.65 | 4457.65 | 0 | 0 | 0 | 4457.65 | 0 | 0 | 0 | 0 | 4457.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508928 | W-WW-NI-170920- CRAIGENGILLAN WWPS NS475060 - REPLACE TELEMETRY STATION - 1.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-28 |  | 2021-03-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1348.59 | 1348.59 | 0 | 0 | 0 | 1348.59 | 0 | 0 | 0 | 0 | 1348.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508863 | W-WW-NI-170920- GIRVAN WWTW NX190999 - REPLACE ACTUATOR - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-28 |  | 2020-10-27 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2554.09 | 2554.09 | 0 | 0 | 0 | 2554.09 | 0 | 0 | 0 | 0 | 2554.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508833 | W-WW-NI-170920- KINNING PARK WWPS NS575644 - REFURBISH SCREEN - 27.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-22 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27138.83 | 27138.83 | 0 | 0 | 0 | 27138.83 | 0 | 0 | 0 | 0 | 27138.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508867 | W-WW-NI-170920- NEILSTON WWTW NS479578 - HEALTH & SAFETY - SAFETY HANDRAIL AROUND FST DISTRIBUTION CHAMBER - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-28 |  | 2020-11-09 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750.31 | 1750.31 | 0 | 0 | 0 | 1750.31 | 0 | 0 | 0 | 0 | 1750.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508881 | W-WW-NI-170920- ROTHESAY WWTW 2002 NS100637 - REPLACE VJ FLANGE ADAPTERS - 2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-28 |  | 2020-11-09 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2227.15 | 2227.15 | 0 | 0 | 0 | 2227.15 | 0 | 0 | 0 | 0 | 2227.15 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508837 | W-WW-NI-170920- TEMPLETON WWPS NS545224 - REPLACE EJECTOR PUMP - 2.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-22 |  | 2021-02-10 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2815.42 | 2815.42 | 0 | 0 | 0 | 2815.42 | 0 | 0 | 0 | 0 | 2815.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508927 | W-WW-NI-170920- TILLICOULTRY WWTW NS917965 - HEALTH & SAFETY - REPLACE GRATINGS & INSTALL HANDRAILS - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-28 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4361.85 | 4361.85 | 0 | 0 | 0 | 4361.85 | 0 | 0 | 0 | 0 | 4361.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508871 | W-WW-NI-170920- UNDERWOOD (CUMNOCK) STC - REPLACE MEMBRANES - 9.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-28 |  | 2020-01-12 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10046.61 | 10046.61 | 0 | 0 | 0 | 10046.61 | 0 | 0 | 0 | 0 | 10046.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511354 | W-WW-NI-180221 - Lomond Street WWPS NS300821 - OUTSTANDING ROOFING COSTS (REPLACEMENT CODE) - 12K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-19 |  | 2021-04-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11346.04 | 11346.04 | 653.95 | 0 | 0 | 11999.99 | 0 | 0 | 0 | 0 | 11999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511338 | W-WW-NI-180221- ALLOA WWTW NS887918 - REPLACE WASHPACTOR BRUSH - 2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-18 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.47 | 150.47 | 2149.55 | 0 | 0 | 2300.02 | 0 | 0 | 0 | 0 | 2300.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511437 | W-WW-NI-180221- ARDOCH WWTW 2002 NS374758 - REPLACE WASHWATER INLET SCREEN ISOLATION VALVES - 1.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-24 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.61 | 1377.61 | 22.39 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511431 | W-WW-NI-180221- ARDROSSAN WWPS 1 NS226419 - REPLACE STORM SCREEN GEARBOX & DRIVE SHAFT - 7.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484.11 | 484.11 | 6915.9 | 0 | 0 | 7400.01 | 0 | 0 | 0 | 0 | 7400.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511333 | W-WW-NI-180221- BALFRON WWTW NS548883 - REPLACE SUMP PUMP - 1.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-18 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.96 | 71.96 | 1028.05 | 0 | 0 | 1100.01 | 0 | 0 | 0 | 0 | 1100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511397 | W-WW-NI-180221- BEECHCROFT WWPS NS685648 - REPLACE SUBMERSIBLE PUMP 1 - 6.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451.4 | 451.4 | 6448.6 | 0 | 0 | 6900 | 0 | 0 | 0 | 0 | 6900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511446 | W-WW-NI-180221- BISHOPTON WWPS NS444700 - REPLACE DEFECTIVE CABLING - 10.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-05-24 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667.29 | 667.29 | 10200 | 0 | 0 | 10867.29 | 0 | 0 | 0 | 0 | 10867.29 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511341 | W-WW-NI-180221- CALLANDER WWTW NN638072 - REPLACE HUMUS TANK 3 DRIVE WHEEL & BEARINGS - 1.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-18 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1308.4 | 0 | 0 | 1399.99 | 0 | 0 | 0 | 0 | 1399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511340 | W-WW-NI-180221- CALLANDER WWTW NN638072 - REPLACE MOTOR & GEARBOX FOR HUMUS TANK 3 SCRAPER - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-18 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284.05 | 1284.05 | 515.95 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511430 | W-WW-NI-180221- CORNTON ROAD WWPS NS791966 - INVESTIGATE PUMP STARTER ISSUES & REFURB - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228.97 | 228.97 | 3271.05 | 0 | 0 | 3500.02 | 0 | 0 | 0 | 0 | 3500.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511355 | W-WW-NI-180221- DOGS LOAN WWPS NS411743 - REFURBISH ROOF & ROUGHCASTING (H&S) - 15.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-19 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6473.54 | 6473.54 | 9326.46 | 0 | 0 | 15800 | 0 | 0 | 0 | 0 | 15800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511457 | W-WW-NI-180221- FARME CROSS WWPS NS619626 - REPLACE WET WELL COVERS (H&S) - 5.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-05-24 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5900 | 0 | 0 | 6285.98 | 0 | 0 | 0 | 0 | 6285.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511336 | W-WW-NI-180221- GIRVAN STC - REFURBISH CENTRIFUGE 1 - 15.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-18 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040.19 | 1040.19 | 14859.8 | 0 | 0 | 15899.99 | 0 | 0 | 0 | 0 | 15899.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511335 | W-WW-NI-180221- GIRVAN WWTW NX190999 - REPLACE SBR FEED PUMP 1 - 5.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-18 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379.44 | 379.44 | 5420.55 | 0 | 0 | 5799.99 | 0 | 0 | 0 | 0 | 5799.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511329 | W-WW-NI-180221- IRVINE HARBOUR WWPS NS313379 - REFURBISH FOUL PUMP 3 - 18.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-18 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1184.11 | 1184.11 | 16915.9 | 0 | 0 | 18100.01 | 0 | 0 | 0 | 0 | 18100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511433 | W-WW-NI-180221- LOACH AVENUE WWPS NS328384 - REFURBISH PANEL (POWER SUPPLY) - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294.39 | 294.39 | 4205.6 | 0 | 0 | 4499.99 | 0 | 0 | 0 | 0 | 4499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511428 | W-WW-NI-180221- MUIRKIRK WWTW NS677264 - REPLACE PST DESLUDGE PUMP 2 - 3.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.35 | 209.35 | 2990.65 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511429 | W-WW-NI-180221- PIKE ROAD WWPS NS811913 - INVESTIGATE PUMP STARTER ISSUES & REFURB - 2.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 189.72 | 2710.3 | 0 | 0 | 2900.02 | 0 | 0 | 0 | 0 | 2900.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511432 | W-WW-NI-180221- STEVENSTON POINT WWTW NS275404 - REPLACE DOORS (H&S) - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242.06 | 242.06 | 3457.95 | 0 | 0 | 3700.01 | 0 | 0 | 0 | 0 | 3700.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511343 | W-WW-NI-180221- STIRLING WWTW 1968 NS808935 - REPLACE TASK LIGHTING (H&S) - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-18 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1960.73 | 1960.73 | 39.27 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511386 | W-WW-NI-180221- STRATHBLANE WWTW NS547801 - REFURBISH PST1 (OLD) DESLUDGE VALVE - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-22 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242.06 | 242.06 | 3457.95 | 0 | 0 | 3700.01 | 0 | 0 | 0 | 0 | 3700.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511342 | W-WW-NI-180221- TILLICOULTRY WWTW NS917965 - DURBAR PLATING OF FST WALL HEADS - 35.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-18 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2296.26 | 2296.26 | 32803.75 | 0 | 0 | 35100.01 | 0 | 0 | 0 | 0 | 35100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511989 | W-WW-NI-180321- ALLOA WWTW NS887918 - REFURBISH INLET STORM SCREEN - 47.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-23 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3081.31 | 3081.31 | 44018.69 | 0 | 0 | 47100 | 0 | 0 | 0 | 0 | 47100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511980 | W-WW-NI-180321- ALVA WWTW NS874966 - REFURBISH INLET SCREEN - 7.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-23 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471.03 | 471.03 | 6171.42 | 0 | 0 | 6642.45 | 0 | 0 | 0 | 0 | 6642.45 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511936 | W-WW-NI-180321- BANDEATH WWTW NS857914 - INSTALL HANDRAILING AT INLET STORM PLATFORM - 8.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-22 |  | 2021-06-19 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575.7 | 575.7 | 7542.84 | 0 | 0 | 8118.54 | 0 | 0 | 0 | 0 | 8118.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512049 | W-WW-NI-180321- CALLANDER WWTW NN638072 - BUILDING EXTERIOR REFURBISHMENT - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-25 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654.21 | 654.21 | 8571.42 | 0 | 0 | 9225.63 | 0 | 0 | 0 | 0 | 9225.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511988 | W-WW-NI-180321- CALLANDER WWTW NN638072 - REPLACE COWLING & SCRAPER ASSEMBLY (JOURNAL) - 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235.25 | 1235.25 | 64.75 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512028 | W-WW-NI-180321- CARRIDEN WWPS 1985 NT019814 - REPLACE KIOSK ROOF - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-25 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 163.55 | 2142.84 | 0 | 0 | 2306.39 | 0 | 0 | 0 | 0 | 2306.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511937 | W-WW-NI-180321- DALDERSE STC - Install Digester Gas Isolation Valves - 2.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-22 |  | 2021-06-19 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2057.16 | 0 | 0 | 2214.17 | 0 | 0 | 0 | 0 | 2214.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511970 | W-WW-NI-180321- DUNBLANE WWTW NN782006 - REFURBISH STORM SCREENS X 2 - 9.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601.87 | 601.87 | 7885.74 | 0 | 0 | 8487.61 | 0 | 0 | 0 | 0 | 8487.61 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511940 | W-WW-NI-180321- FINTRY WWTW NS614873 - REPLACE HUMUS SLUDGE PUMP - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-22 |  | 2021-06-19 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3257.16 | 0 | 0 | 3505.76 | 0 | 0 | 0 | 0 | 3505.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512048 | W-WW-NI-180321- FINTRY WWTW NS614873 - REPLACE LIFTING EQUIPMENT - 3.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-05 |  | 2021-06-25 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3342.84 | 0 | 0 | 3342.84 | 0 | 0 | 0 | 0 | 3342.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512006 | W-WW-NI-180321- GAILES WWPS NS323359 - REPLACE FILTER CASSETTES X 8 - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-24 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287.85 | 287.85 | 3771.42 | 0 | 0 | 4059.27 | 0 | 0 | 0 | 0 | 4059.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511967 | W-WW-NI-180321- GIRVAN STC - REFURBISH LIME CAKE CONVEYOR - 19.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-23 |  | 2021-06-23 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1282.24 | 1282.24 | 18317.76 | 0 | 0 | 19600 | 0 | 0 | 0 | 0 | 19600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511997 | W-WW-NI-180321- GIRVAN STC - REFURBISH TANKER ACCESS ROAD (H&S) - 5.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-24 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346.73 | 346.73 | 4542.84 | 0 | 0 | 4889.57 | 0 | 0 | 0 | 0 | 4889.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511998 | W-WW-NI-180321- GIRVAN WWTW NX190999 - REPLACE DRAINAGE CHANNEL - 3.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-24 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202.8 | 202.8 | 2657.16 | 0 | 0 | 2859.96 | 0 | 0 | 0 | 0 | 2859.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511941 | W-WW-NI-180321- IRVINE HARBOUR WWPS NS313379 - REFURBISH FOUL PUMP 4 - 7.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-22 |  | 2021-06-19 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510.28 | 510.28 | 6685.74 | 0 | 0 | 7196.02 | 0 | 0 | 0 | 0 | 7196.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511990 | W-WW-NI-180321- KILLIN WWTW 1985 NN575331 - H&S NEEDS - 19K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1242.99 | 1242.99 | 17757.01 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 19000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512047 | W-WW-NI-180321- KIPPEN WWTW NS653952 - REPLACE WINDOWS IN MAIN BUILDING - 1.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-25 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.59 | 91.59 | 1200 | 0 | 0 | 1291.59 | 0 | 0 | 0 | 0 | 1291.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511939 | W-WW-NI-180321- LARBERT CENTRAL BUS PK WWPS NS858840 - REPLACE FOUL TRANSFER PUMP 1 - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-22 |  | 2021-06-19 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 170.09 | 2228.58 | 0 | 0 | 2398.67 | 0 | 0 | 0 | 0 | 2398.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511938 | W-WW-NI-180321- LARBERT CENTRAL BUS PK WWPS NS858840 - REPLACE FOUL TRANSFER PUMP 2 - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-22 |  | 2021-06-19 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 170.09 | 2228.58 | 0 | 0 | 2398.67 | 0 | 0 | 0 | 0 | 2398.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512002 | W-WW-NI-180321- LOMOND STREET WWPS NS300821 - REPLACE NRV - 2.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-24 |  | 2021-06-24 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 189.72 | 2485.74 | 0 | 0 | 2675.46 | 0 | 0 | 0 | 0 | 2675.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511959 | W-WW-NI-180321- MAUCHLINE WWTW NS492254 - REPLACE STORM RETURN PUMPS A&B - 6.7k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-06-22 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5742.84 | 0 | 0 | 5742.84 | 0 | 0 | 0 | 0 | 5742.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512038 | W-WW-NI-180321- MEADOWHEAD WWTW NS339361 - REPLACE LIGHTING IN DITRITOR BUILDING - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-25 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1542.84 | 0 | 0 | 1660.6 | 0 | 0 | 0 | 0 | 1660.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512046 | W-WW-NI-180321- SHEWALTON WWPS NS337372 - UPGRADE DRY WELL LIGHTING (H&S) - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-25 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1371.42 | 0 | 0 | 1476.09 | 0 | 0 | 0 | 0 | 1476.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512042 | W-WW-NI-180321- STEWARTON WWTW NS408449 - REPLACE SCRAPER MECHANISM - 3.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-25 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.35 | 209.35 | 2742.84 | 0 | 0 | 2952.19 | 0 | 0 | 0 | 0 | 2952.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511943 | W-WW-NI-180321- UNDERWOOD (CUMNOCK) STC - REPLACE SUBMERSIBLE MIXER (CDT4) - 8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-22 |  | 2021-06-22 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523.36 | 523.36 | 6857.16 | 0 | 0 | 7380.52 | 0 | 0 | 0 | 0 | 7380.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512045 | W-WW-NI-180321-SHEWALTON WWPS NS337372 - REPLACE EXIT DOORS - 2.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-25 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.01 | 157.01 | 2057.16 | 0 | 0 | 2214.17 | 0 | 0 | 0 | 0 | 2214.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507343 | W-WW-NI-18062020-CORNTON ROAD WWPS NS791966- REPLACE MILLTRONICS LEVEL CONTROLLER - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-25 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.42 | 1959.42 | 40.58 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507321 | W-WW-NI-18062020-PLEAN WWTW NS841870- REPLACE AERATOR GEARBOX - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-25 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3995.63 | 3995.63 | 4.37 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507351 | W-WW-NI-180620-ABBEY ROAD WWPS NS805940- REPLACE FOUL PUMP 1 - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-10-27 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2459.93 | 2459.93 | 0 | 0 | 0 | 2459.93 | 0 | 0 | 0 | 0 | 2459.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507300 | W-WW-NI-180620-ALVA WWTW NS874966- FIT AIR RELEASE KITS TO INLET PUMPS - 3.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-10-29 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3856.47 | 3856.47 | 0 | 0 | 0 | 3856.47 | 0 | 0 | 0 | 0 | 3856.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507324 | W-WW-NI-180620-ALVA WWTW NS874966- FIT TANK CHANNEL BRUSHES (HEALTH & SAFETY)- 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-09-25 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3607.19 | 3607.19 | 0 | 0 | 0 | 3607.19 | 0 | 0 | 0 | 0 | 3607.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507305 | W-WW-NI-180620-ALVA WWTW NS874966- REPLACE CRAIGHORN PUMP 2- 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-16 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1518.03 | 1518.03 | 0 | 0 | 0 | 1518.03 | 0 | 0 | 0 | 0 | 1518.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507335 | W-WW-NI-180620-BATH STREET LARGS WWPS NS201591- CRITICAL SPARE PUMP - 6.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-27 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6333.99 | 6333.99 | 0 | 0 | 0 | 6333.99 | 0 | 0 | 0 | 0 | 6333.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507369 | W-WW-NI-180620-CAMERON HOUSE BOATHOUSE WWPS NS378828- REPLACE RISERS - 7.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-30 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7800 | 0 | 0 | 7800 | 0 | 0 | 0 | 0 | 7800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507350 | W-WW-NI-180620-CASTLEGREEN WWPS NS408745- REFURB DRY WELL PUMP 2 - 10.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-25 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10546.21 | 10546.21 | 53.79 | 0 | 0 | 10600 | 0 | 0 | 0 | 0 | 10600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507332 | W-WW-NI-180620-CROSSHILL WWTW NS322068- Replace SAF Feed Pump 1 - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-08-12 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1444.63 | 1444.63 | 0 | 0 | 0 | 1444.63 | 0 | 0 | 0 | 0 | 1444.63 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507352 | W-WW-NI-180620-DALDERSE STC- CRITICAL SPARE FOR CENTRIFUGE (SLUDGE FEED MACERATOR) - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-07-17 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1531.59 | 1531.59 | 0 | 0 | 0 | 1531.59 | 0 | 0 | 0 | 0 | 1531.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507337 | W-WW-NI-180620-DALRYMPLE WWTW NS353141- REPLACE ROTORK VALVE - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-08-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2964.26 | 2964.26 | 0 | 0 | 0 | 2964.26 | 0 | 0 | 0 | 0 | 2964.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507347 | W-WW-NI-180620-DENNY WWTW NS820830- REPLACE STILLING BOX SUPPORTS - 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-25 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373 | 373 | 5327.1 | 0 | 0 | 5700.1 | 0 | 0 | 0 | 0 | 5700.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507293 | W-WW-NI-180620-DOLLAR WWTW NS953978- Replace SBR Lift/Transfer Pump 1 - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-09-22 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373.56 | 2373.56 | 0 | 0 | 0 | 2373.56 | 0 | 0 | 0 | 0 | 2373.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507362 | W-WW-NI-180620-DUNOON WWTW NS165745- REPLACE FAULTY MLSS MONITOR - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-08-19 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3359.77 | 3359.77 | 0 | 0 | 0 | 3359.77 | 0 | 0 | 0 | 0 | 3359.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507349 | W-WW-NI-180620-HILLFOOT WWPS NS553724- REFURBISH PUMP 1 - 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-08-11 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5695.57 | 5695.57 | 0 | 0 | 0 | 5695.57 | 0 | 0 | 0 | 0 | 5695.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507356 | W-WW-NI-180620-KELLIEBANK WWPS 1967 NS874925- REPLACE FAILED LIGHTING (H&S) - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-07-31 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3607 | 3607 | 0 | 0 | 0 | 3607 | 0 | 0 | 0 | 0 | 3607 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507373 | W-WW-NI-180620-KIRKMICHAEL WWTW NS336086- REPLACE GRATINGS (HEALTH & SAFETY) -7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-26 |  | 2021-03-07 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6994.94 | 6994.94 | 5.06 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 7000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507366 | W-WW-NI-180620-METHLAN PARK WWPS NS390747- REPLACE FAULTY TELEMETRY OUTSTATION - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-25 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 98.13 | 1401.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507328 | W-WW-NI-180620-NEWFORD GROVE CSO 2018 NS576561-REPLACE PUMP & GUIDERAILS - 9.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-25 |  | 2020-10-05 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9336.96 | 9336.96 | 0 | 0 | 0 | 9336.96 | 0 | 0 | 0 | 0 | 9336.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507298 | W-WW-NI-180620-NORTH LODGE ROAD WWPS 1 NS504682- Emergency reinstatement of Pump - 8.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-15 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8083.36 | 8083.36 | 0 | 0 | 0 | 8083.36 | 0 | 0 | 0 | 0 | 8083.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507374 | W-WW-NI-180620-NORTHFOOT WWPS 2000 NS942796- REPLACE VSDs - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-30 |  | 2020-07-13 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1896 | 1896 | 0 | 0 | 0 | 1896 | 0 | 0 | 0 | 0 | 1896 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507334 | W-WW-NI-180620-STEWARTON WWTW NS408449 - Refurbish ADF Pump 1 - 6.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-24 |  | 2020-07-27 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6725.43 | 6725.43 | 0 | 0 | 0 | 6725.43 | 0 | 0 | 0 | 0 | 6725.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510422 | W-WW-NI-181220- BALFRON WWTW NS548883 - REFURBISH INLET SCREEN - 22.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-22 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22534.06 | 22534.06 | 65.94 | 0 | 0 | 22600 | 0 | 0 | 0 | 0 | 22600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510432 | W-WW-NI-181220- BRODIE GROVE WWPS NS680649 - Replace 2x submersible pumps - 10.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-25 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10572.71 | 10572.71 | 27.3 | 0 | 0 | 10600.01 | 0 | 0 | 0 | 0 | 10600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510789 | W-WW-NI-190121 FAST TRACK - BARRHEAD CROSS ARTHURLIE ST 123 APNRV - REPLACE APNRV PUMP - 1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-01-27 |  | 2021-04-02 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985.23 | 985.23 | 14.76 | 0 | 0 | 999.99 | 0 | 0 | 0 | 0 | 999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505283 | W-WW-NI-190220- EAST BAY WWPS NS175767 - fast track - 8.2KReplace Pump - | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-20 |  | 2020-06-24 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 3253.33 | 6190.23 | 9443.56 | 0 | 0 | 0 | 9443.56 | 0 | 0 | 0 | 0 | 9443.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505854 | W-WW-NI-190320- BALFRON WWTW NS548883 - REPLACE DISCHARGE SPIRAL SCREW - 17.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 1144.86 | 0 | 1144.86 | 16355.14 | 0 | 0 | 17500 | 0 | 0 | 0 | 0 | 17500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505863 | W-WW-NI-190320- GIRVAN WWTW NX190999 - Replace Actuator - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 163.55 | 2078 | 2241.55 | 258.45 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505858 | W-WW-NI-19032020- H&S- KELLIEBANK WWPS 1967 NS874925 - RE-ROOF PUMP HOUSE BUILDING - 6.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-07-10 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 405.61 | 5750.8 | 6156.41 | 0 | 0 | 0 | 6156.41 | 0 | 0 | 0 | 0 | 6156.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505856 | W-WW-NI-19032020- STEVENSTON POINT WWTW NS275404 - Replace Bar Screen Ties - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-05-14 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 130.84 | 1857.94 | 1988.78 | 0 | 0 | 0 | 1988.78 | 0 | 0 | 0 | 0 | 1988.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508265 | W-WW-NI-190820- FISHERWOOD WWPS NS393815 - FAST TRACK - Replace Foul Pump 2 - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-20 |  | 2020-10-26 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4361.85 | 4361.85 | 0 | 0 | 0 | 4361.85 | 0 | 0 | 0 | 0 | 4361.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509334 | W-WW-NI-191020- DALDERSE WWTW 1966 NS903822 - URGENT REPLACE SCRAPER BLADES - 4.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-26 |  | 2020-11-25 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4784.16 | 4784.16 | 0 | 0 | 0 | 4784.16 | 0 | 0 | 0 | 0 | 4784.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503865 | W-WW-NI-191119-Kinning Park WWPS- New Hot Wash Power Washer- JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | -4672.9 | 327.1 | 4672.9 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 90601.29 | [5 empty] | N | WWNI | 100%
504667 | W-WW-NI-191219- DOLLAR WWTW NS953978 - Replace Motor & Gearbox Refurbish Jacking Sleeve - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-21 |  | 2020-05-14 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | -314.4 | 5685.6 | 0 | 0 | 0 | 5685.6 | 0 | 0 | 0 | 0 | 5685.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504751 | W-WW-NI-191219- DUMBARTON DISTILLERY WWPS NS397751 - Line Rising Main Pipework - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | -2803.74 | 196.26 | 2803.74 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504690 | W-WW-NI-191219- GIRVAN STC - Replace faulty lighting on SBR gantry walk way - 2k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-03-09 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -433.32 | 1566.68 | 0 | 0 | 0 | 1566.68 | 0 | 0 | 0 | 0 | 1566.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504649 | W-WW-NI-191219- GRANGEBURN ROAD WWPS 1927 NS930821 - Replace Foul Pump - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-05-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | -212.86 | 2787.14 | 0 | 0 | 0 | 2787.14 | 0 | 0 | 0 | 0 | 2787.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504625 | W-WW-NI-191219- HOLMSTON WWPS 2 NS358214 - Replace & Reinstate Duck foot - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-07-16 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 268.98 | 5268.98 | 0 | 0 | 0 | 5268.98 | 0 | 0 | 0 | 0 | 5268.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504616 | W-WW-NI-191219- MACINTYRE COURT WWPS NS353266 - Replace guide rails x4 - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-14 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -1869.16 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504678 | W-WW-NI-191219- PATNA WWTW NS414124 - REPLACE LIFTING GANTRY - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-07-21 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | -618.32 | 3381.68 | 0 | 0 | 0 | 3381.68 | 0 | 0 | 0 | 0 | 3381.68 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504581 | W-WW-NI-191219- POWBURN WWPS NS352266 - Replace Ventilation - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-10 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | -192.98 | 4307.02 | 192.98 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504653 | W-WW-NI-191219- ROTHESAY WWTW 2002 NS100637 - REPLACE 3X KNIFE VALVES & SPINDLES - 8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-22 |  | 2020-03-12 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | -682.42 | 7317.58 | 682.42 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504673 | W-WW-NI-191219- STIRLING WWTW 1968 NS808935 - REPLACE ACTUATOR - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-01-22 |  | 2020-05-14 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | -3738.32 | 261.68 | 3738.32 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504663 | W-WW-NI-191219- STIRLING WWTW 1968 NS808935 - Replace Scum box scrapers winches & hardware - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-05-14 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | -513.76 | 9486.24 | 0 | 0 | 0 | 9486.24 | 0 | 0 | 0 | 0 | 9486.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504677 | W-WW-NI-191219- UNDERWOOD (CUMNOCK) STC - REPLACE SUMP PUMP - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-01-22 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | -1401.87 | 98.13 | 1401.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504438 | W-WW-NI-191219- UNDERWOOD (CUMNOCK) STC -Replace Mobile hoist crane - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-07 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2609.67 | 0 | 2609.67 | 0 | 0 | 0 | 2609.67 | 0 | 0 | 0 | 0 | 2609.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505563 | W-WW-NI-200220- GIRVAN STC- Replace Sludge Mixer Pump - 10.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-06 |  | 2020-07-27 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 673.83 | 9573.21 | 10247.04 | 0 | 0 | 0 | 10247.04 | 0 | 0 | 0 | 0 | 10247.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505402 | W-WW-NI-200220- KINNING PARK WWPS NS575644 -Replace Gas Main Extraction Fan- 3.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-28 |  | 2020-07-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3556.3 | 3556.3 | 0 | 0 | 0 | 3556.3 | 0 | 0 | 0 | 0 | 3556.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505599 | W-WW-NI-200220- LINWOOD WWPS NS447648 - Refurb Pump - 14.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-03-17 |  | 2020-05-14 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 274.77 | 0 | 274.77 | 3925.23 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505535 | W-WW-NI-200220- LOCHWINNOCH WWTW 1971 NS356589 - Replace Ancillary equipment for screen - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-06 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 98.13 | 0 | 98.13 | 1401.87 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505572 | W-WW-NI-200220- NEILSTON WWTW NS479578 - Replace Ancillary Equipment for Screens - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-08-18 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 1605.35 | 1716.56 | 0 | 0 | 0 | 1716.56 | 0 | 0 | 0 | 0 | 1716.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505531 | W-WW-NI-200220- UNDERCLIFF RD WWPS 1993 NS190698 - Replace In-line Pump - 9.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-06 |  | 2020-07-06 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 595.33 | 8473 | 9068.33 | 0 | 0 | 0 | 9068.33 | 0 | 0 | 0 | 0 | 9068.33 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505406 | W-WW-NI-200220-GIRVAN STC- REPLACE DOOR ON HIGH VOLTAGE ROOM (H&S) - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-03 |  | 2020-08-27 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 1708 | 2456.77 | 4164.77 | 0 | 0 | 0 | 4164.77 | 0 | 0 | 0 | 0 | 4164.77 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505419 | W-WW-NI-200220-GIRVAN WWTW NX190999 - Duck Foot Replacement - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-28 |  | 2020-07-27 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010.8 | 2010.8 | 0 | 0 | 0 | 2010.8 | 0 | 0 | 0 | 0 | 2010.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505596 | W-WW-NI-200220-MCCONNELL ROAD WWPS NS349589- Replace Pump- 8.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-07-15 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 536.45 | 7623.44 | 8159.89 | 0 | 0 | 0 | 8159.89 | 0 | 0 | 0 | 0 | 8159.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505581 | W-WW-NI-200220-POLMONTHILL WWPS 2000 NS953795- REFURB FOUL PUMP - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2020-05-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 294.39 | 4122.85 | 4417.24 | 0 | 0 | 0 | 4417.24 | 0 | 0 | 0 | 0 | 4417.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505595 | W-WW-NI-200220-STIRLING STC- Replace digester pressure relief valve - 5.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-17 |  | 2021-02-10 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 4981 | 5334.27 | 65.73 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 5400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505865 | W-WW-NI-20032020- STIRLING STC - REPLACE 2X PUMPS - 9.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 634.58 | 0 | 634.58 | 9065.42 | 0 | 0 | 9700 | 0 | 0 | 0 | 0 | 9700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508381 | W-WW-NI-200820- BALFRON WWTW NS548883 - REPLACE SAMPLE ACCESS POINT GRID - 2.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-28 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.72 | 189.72 | 2710.28 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508335 | W-WW-NI-200820- BONESS WWTW NT022813 - Replace Critical Spare SBR inlet Rotork - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-25 |  | 2020-08-12 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1707.56 | 1707.56 | 0 | 0 | 0 | 1707.56 | 0 | 0 | 0 | 0 | 1707.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508348 | W-WW-NI-200820- CLACKMANNAN MARYS BRIDGE CSO - REPLACE TELEMETRY (RTU) - 5.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5133.4 | 5133.4 | 566.6 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 5700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508368 | W-WW-NI-200820- DALMELLINGTON WWTW NS476050 - REFURBISH INLET SCREEN - 18.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-11-04 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18550.66 | 18550.66 | 0 | 0 | 0 | 18550.66 | 0 | 0 | 0 | 0 | 18550.66 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508378 | W-WW-NI-200820- DALMELLINGTON WWTW NS476050 - Replace Washwater Pump 2 - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-09-15 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517.87 | 1517.87 | 0 | 0 | 0 | 1517.87 | 0 | 0 | 0 | 0 | 1517.87 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508406 | W-WW-NI-200820- DALMELLINGTON WWTW NS476050 - TANKER LOADING ADAPTERS - 2.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-11-20 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2315.71 | 2315.71 | 0 | 0 | 0 | 2315.71 | 0 | 0 | 0 | 0 | 2315.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508405 | W-WW-NI-200820- KINNEIL KERSE WWTW 2001 NS960811 - H&S - REPLACE ODOUR EXTRACTION FAN - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-10-26 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1493.13 | 1493.13 | 0 | 0 | 0 | 1493.13 | 0 | 0 | 0 | 0 | 1493.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508351 | W-WW-NI-200820- MAUCHLINE WWTW NS492254 - REPLACE EQUILIBRIUM FLOAT - 2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-25 |  | 2020-09-19 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209.47 | 2209.47 | 0 | 0 | 0 | 2209.47 | 0 | 0 | 0 | 0 | 2209.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508403 | W-WW-NI-200820- NORTH SHORE RD WWPS NS927826 - GUIDE POLE REPLACEMENT - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-28 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333.64 | 333.64 | 4766.36 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 5100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508382 | W-WW-NI-200820- ROSNEATH SEP NS257778 - ISOLATION PENSTOCKS - 8.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-28 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575.7 | 575.7 | 8224.3 | 0 | 0 | 8800 | 0 | 0 | 0 | 0 | 8800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508307 | W-WW-NI-200820- STEWARTON WWTW NS408449 - HEALTH & SAFETY - REPLACE WELFARE FACILITIES - 7.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-25 |  | 2020-09-22 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7280.43 | 7280.43 | 0 | 0 | 0 | 7280.43 | 0 | 0 | 0 | 0 | 7280.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508404 | W-WW-NI-200820- STIRLING WWTW 1968 NS808935 - ROAD REINSTATEMENT - 9.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-28 |  | 2020-11-02 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9087.81 | 9087.81 | 0 | 0 | 0 | 9087.81 | 0 | 0 | 0 | 0 | 9087.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508320 | W-WW-NI-200820- TYNDRUM WWTW NN330302 - TRANSMITTER & RECEIVER FOR MLSS MONITORS - 5.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3391.94 | 3391.94 | 8.06 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508319 | W-WW-NI-200820-STEVENSTON POINT WWTW NS275404 - STATER SECTION MODIFICATIONS - 5.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-25 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379.44 | 379.44 | 5420.56 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 5800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503896 | W-WW-NI-201119-Dunure WWPS 2 NS256163 - Replace Wet Well Pump No2 - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2461.13 | 0 | 2461.13 | 0 | 0 | 0 | 2461.13 | 0 | 0 | 0 | 0 | 2461.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503893 | W-WW-NI-201119-DUNURE WwPS- Replace Wet Well Pump No1 - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2461.13 | 0 | 2461.13 | 0 | 0 | 0 | 2461.13 | 0 | 0 | 0 | 0 | 2461.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503880 | W-WW-NI-201119-Leggate WwPS - Replace Submersible Pump No1 & Motor - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5037.64 | 0 | 5037.64 | 0 | 0 | 0 | 5037.64 | 0 | 0 | 0 | 0 | 5037.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504763 | W-WW-NI-210120- KILLEARN WWTW 1971 NS517844- Replace RAS Pump 2 - 5K - | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-22 |  | 2020-06-03 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | -354.12 | 4645.88 | 0 | 0 | 0 | 4645.88 | 0 | 0 | 0 | 0 | 4645.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511030 | W-WW-NI-210121- BOWHOUSE WWPS NS934805 - Supply and Install new VSDs onto all foul pumps - 33.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-04 |  | 2021-05-02 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2204.67 | 2204.67 | 31495.35 | 0 | 0 | 33700.02 | 0 | 0 | 0 | 0 | 33700.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511026 | W-WW-NI-210121- CAMBUS MAIN WWPS NS856942 - Free off isolation valves and install NRV - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-02 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1495.35 | 0 | 0 | 1600.02 | 0 | 0 | 0 | 0 | 1600.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511031 | W-WW-NI-210121- CAMERON HOUSE (REAR) WWPS NS375830 - REPLACE STOOLS GUIDE RAILS & VALVES - 10.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-02 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660.75 | 660.75 | 9439.25 | 0 | 0 | 10100 | 0 | 0 | 0 | 0 | 10100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510905 | W-WW-NI-210121- CASTLEGREEN WWPS NS408745 - REPLACE DEFECTIVE LIGHTING (H&S) - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-27 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2803.72 | 0 | 0 | 2999.98 | 0 | 0 | 0 | 0 | 2999.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511028 | W-WW-NI-210121- CASTLEPARK WWPS NS322410 - REFURBISH SUBMERSIBLE PUMP NO1 - 3.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-04 |  | 2021-04-04 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15461.28 | 15461.28 | 38.75 | 0 | 0 | 15500.03 | 0 | 0 | 0 | 0 | 15500.03 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511072 | W-WW-NI-210121- COYLTON WWTW NS401200 - REPLACE ISOLATION & SNIFTER VALVES (H&S) - 10.7k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-05 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511009 | W-WW-NI-210121- DALDERSE STC - Replace digester gas take off hoses - 7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-03 |  | 2021-05-02 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457.94 | 457.94 | 6542.05 | 0 | 0 | 6999.99 | 0 | 0 | 0 | 0 | 6999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511019 | W-WW-NI-210121- DALDERSE WWTW 1966 NS903822 - REPLACE WASHWATER LCP - 21.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-02 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1386.92 | 1386.92 | 19813.1 | 0 | 0 | 21200.02 | 0 | 0 | 0 | 0 | 21200.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510958 | W-WW-NI-210121- DOGS LOAN WWPS NS411743 - Replace submersible pump - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228.97 | 228.97 | 3271.04 | 0 | 0 | 3500.01 | 0 | 0 | 0 | 0 | 3500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511029 | W-WW-NI-210121- DOLLAR WWTW NS953978 - REPLACE VSD FOR BLOWER 1 - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-04 |  | 2021-05-02 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3668.06 | 3668.06 | 31.95 | 0 | 0 | 3700.01 | 0 | 0 | 0 | 0 | 3700.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511075 | W-WW-NI-210121- DRONGAN WWTW NS429187 - REPLACE ISOLATION AND SNIFTER VALVES (H&S) - 10.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-05 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660.75 | 660.75 | 9439.25 | 0 | 0 | 10100 | 0 | 0 | 0 | 0 | 10100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510950 | W-WW-NI-210121- ERSKINE WWTW NS494691 - REPLACE FST BRIDGE DRIVE WHEEL - 2.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.47 | 150.47 | 2149.52 | 0 | 0 | 2299.99 | 0 | 0 | 0 | 0 | 2299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510954 | W-WW-NI-210121- GARNIELAND ERSKINE WWPS NS483699 - Refurbish Foul Pump No3 - 7.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484.11 | 484.11 | 6915.88 | 0 | 0 | 7399.99 | 0 | 0 | 0 | 0 | 7399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510966 | W-WW-NI-210121- GARNIELAND ERSKINE WWPS NS483699 - REPLACE TRANSDUCER UNIT - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.76 | 117.76 | 1682.24 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510942 | W-WW-NI-210121- GIRVAN WWTW NX190999- REPLACE TANKER RECEPTION WELL FLOW RECORDER - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2499.09 | 2499.09 | 100.91 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510927 | W-WW-NI-210121- KILCHATTAN BAY WWPS NS108545 - 4.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.56 | 320.56 | 4579.44 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 4900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511025 | W-WW-NI-210121- POLMONTHILL WWPS 2000 NS953795 - REPLACE FLOW METER - 8.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-05 |  | 2021-05-02 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2594.67 | 2594.67 | 6105.35 | 0 | 0 | 8700.02 | 0 | 0 | 0 | 0 | 8700.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510938 | W-WW-NI-210121-ALLOA WWTW NS887918- Alloa DOA - Kessel PNRV Repair 29 Abercromby Place Tullibody - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3917.46 | 3917.46 | 82.54 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 209381.79 | [5 empty] | N | CM_WWI | 100%
510906 | W-WW-NI-210121-CASTLEGREEN WWPS NS408745- REPLACE PENSTOCK ROTORKS- MAIN INLET SCREEN OUTLET & INLET CHANNEL DIVERTER-24.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-27 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1622.43 | 1622.43 | 23177.56 | 0 | 0 | 24799.99 | 0 | 0 | 0 | 0 | 24799.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510907 | W-WW-NI-210121-CASTLEGREEN WWPS NS408745- REPLACE ROTORKS- INLET SCREW & SCREEN INLET PENSTOCKS- 25K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-27 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635.51 | 1635.51 | 23364.48 | 0 | 0 | 24999.99 | 0 | 0 | 0 | 0 | 24999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510910 | W-WW-NI-210121-DALDERSE STC- REPLACE CRITICAL SPARE MACERATOR - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-01 |  | 2021-03-26 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.17 | 1658.17 | 41.84 | 0 | 0 | 1700.01 | 0 | 0 | 0 | 0 | 1700.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510926 | W-WW-NI-210121-DALDERSE STC-REPLACE GAS COMPRESSOR - 43K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14193.88 | 14193.88 | 28806.12 | 0 | 0 | 43000 | 0 | 0 | 0 | 0 | 43000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510936 | W-WW-NI-210121-KINNEIL KERSE WWTW 2001 NS960811 - Kinneil Kerse DOA - Kessel PNRV Repair 43 Main St Brightons - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-01 |  | 2021-04-02 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2994.52 | 2994.52 | 5.48 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506287 | W-WW-NI-210420- PAN ROCKS WWPS NS322313 - FAST TRACK PUMP REPLACEMENT - REPLACE STORM PUMP 1 - 12.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-22 |  | 2020-08-05 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12670.75 | 12670.75 | 0 | 0 | 0 | 12670.75 | 0 | 0 | 0 | 0 | 12670.75 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506786 | W-WW-NI-210520 - ERSKINE WWTW NS494691 - FAST TRACK: REPLACE SAS PUMP 1 - 3.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-07-21 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3325.91 | 3325.91 | 0 | 0 | 0 | 3325.91 | 0 | 0 | 0 | 0 | 3325.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506852 | W-WW-NI-210520-BATH STREET LARGS WWPS NS201591- REPLACE FOUL PUMP 1- 6.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.23 | 425.23 | 6074.77 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506872 | W-WW-NI-210520-ERSKINE WWTW NS494691- FINE SCREEN CRITICAL SPARES - 4.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-08-07 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4614.39 | 4614.39 | 0 | 0 | 0 | 4614.39 | 0 | 0 | 0 | 0 | 4614.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506871 | W-WW-NI-210520-ROTHESAY WWTW 2002 NS100637- REPLACE OBSOLETE SCADA- 30K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-05 |  | 2020-07-27 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27588.04 | 27588.04 | 0 | 0 | 0 | 27588.04 | 0 | 0 | 0 | 0 | 27588.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510986 | W-WW-NI-211021- LADYSNEUK WWPS NS808952 - REPLACE FOUL PUMP 1 - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-01 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.38 | 137.38 | 1962.6 | 0 | 0 | 2099.98 | 0 | 0 | 0 | 0 | 2099.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504111 | W-WW-NI-211119 - Lomond Street WWPS NS300821 - Roof Work & Fascia Replacement - 10K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-05 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | -9345.79 | 654.21 | 9345.79 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504061 | W-WW-NI-211119- Dalderse WWTW 1966 NS903822 - Replace Failed Lighting (H&S) - 5K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5197.1 | 0 | 5197.1 | 0 | 0 | 0 | 5197.1 | 0 | 0 | 0 | 0 | 5197.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503980 | W-WW-NI-211119- Dalgrain WwPS 1976 NS915823 - Storm Pumps Refurb - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 10566.21 | 0 | 10566.21 | 0 | 0 | 0 | 10566.21 | 0 | 0 | 0 | 0 | 10566.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504052 | W-WW-NI-211119-Ardoch WWTW 2002 NS374758 - Refurb Gearbox - 3.2K 0 JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-11-29 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 3351.89 | 0 | 3351.89 | -151.89 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503911 | W-WW-NI-211119-Dunoon WwTW NS165745 - Replace RAS Pump A - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-05-04 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 149.57 | 2749.57 | 0 | 0 | 0 | 2749.57 | 0 | 0 | 0 | 0 | 2749.57 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503921 | W-WW-NI-211119-Fallin WwTW - H&S Improvements - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-05-04 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 8150.74 | 0 | 8150.74 | 0 | 0 | 0 | 8150.74 | 0 | 0 | 0 | 0 | 8150.74 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509923 | W-WW-NI-21120-STIRLING WWTW 1968 NS808935 - REPLACE LIGHTING IN POLY BUILDING & CAKE BAY (HEALTH & SAFETY) - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-25 |  | 2021-03-08 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4350.34 | 4350.34 | 49.64 | 0 | 0 | 4399.98 | 0 | 0 | 0 | 0 | 4399.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510467 | W-WW-NI-211220- STEWARTON WWTW NS408449 - ROOF REPAIRS (H&S) - 9.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-05 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9386.95 | 9386.95 | 13.05 | 0 | 0 | 9400 | 0 | 0 | 0 | 0 | 9400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505871 | W-WW-NI-22032020- KINNING PARK WWPS NS575644 - INLET BAR SCREEN REPAIR - 25K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-23 |  | 2020-07-20 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 1635.51 | 26761.9 | 28397.41 | 0 | 0 | 0 | 28397.41 | 0 | 0 | 0 | 0 | 28397.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506310 | W-WW-NI-220420- BONESS WWTW NT022813 - REPLACE ACTUATOR DRIVE & SCREWJACK ON SBR2 DECANTER - 14.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-22 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19516.57 | 19516.57 | 16483.43 | 0 | 0 | 36000 | 0 | 0 | 0 | 0 | 36000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506307 | W-WW-NI-220420- COACH CLOSE WWPS NS731777 - REPLACE 2X SUBMERSIBLE PUMPS - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-22 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3407.87 | 3407.87 | 92.13 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503927 | W-WW-NI-221119- GAILES WWPS NS323359 - Replace Circuit Breaker Feeding Transformer - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2019-12-13 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1373.83 | 0 | 1373.83 | 0 | 0 | 0 | 1373.83 | 0 | 0 | 0 | 0 | 1373.83 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503935 | W-WW-NI-221119-Gailes WwPS NS323359 - Replace SCADA HMI - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-05-05 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 4722.62 | -208.31 | 4514.31 | 0 | 0 | 0 | 4514.31 | 0 | 0 | 0 | 0 | 4514.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504943 | W-WW-NI-230120- EASTFIELD GLASGOW WWPS NS610622 - FAST TRACK: NEW PUMP & PANEL UPGRADE - 10k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-03 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 144.53 | 10144.53 | 0 | 0 | 0 | 10144.53 | 0 | 0 | 0 | 0 | 10144.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504884 | W-WW-NI-230120- KILSYTH SOUTH DUMBRECK RD WWPS NS711776 - Replace Submersible Pump- FAST TRACK 2k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-30 |  | 2020-03-13 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -766.35 | 1233.65 | 0 | 0 | 0 | 1233.65 | 0 | 0 | 0 | 0 | 1233.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504904 | W-WW-NI-230120- PAISLEY LAIGHPARK SLDG TFR WWPS NS485655 - Refurbish Sludge Transfer Pump 1 - 29K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-30 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 29000 | -372.14 | 28627.86 | 0 | 0 | 0 | 28627.86 | 0 | 0 | 0 | 0 | 28627.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504900 | W-WW-NI-230120-DALMELLINGTON WWTW NS476050- Supply new motor - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-30 |  | 2020-02-29 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -109.4 | 2390.6 | 0 | 0 | 0 | 2390.6 | 0 | 0 | 0 | 0 | 2390.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504929 | W-WW-NI-230120-PAISLEY LAIGHPARK SLDG TFR WWPS NS485655- Sludge Pump Replacement Survey - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-03 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | -4766.36 | 333.64 | 4766.36 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 5100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511407 | W-WW-NI-230221 - DALDERSE STC - DSEAR Health check Remedials - 250K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511412 | W-WW-NI-230221- GIRVAN STC - DSEAR Health check Remedial - 250K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511419 | W-WW-NI-230221- KINNEIL KERSE STC - DSEAR Health Check Remedial - 250K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511420 | W-WW-NI-230221- STIRLING STC - DSEAR Health Check Remedial - 250K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-24 |  | 2021-05-23 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511421 | W-WW-NI-230221- UNDERWOOD (CUMNOCK) STC - DSEAR Health Check Remedial - 250K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-23 |  | 2021-05-23 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16355.14 | 16355.14 | 233644.85 | 0 | 0 | 249999.99 | 0 | 0 | 0 | 0 | 249999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506359 | W-WW-NI-230420- KINNEIL KERSE WWTW 2001 NS960811 - CRITICAL SPARE STATOR - 6.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-29 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6859.28 | 6859.28 | 40.72 | 0 | 0 | 6900 | 0 | 0 | 0 | 0 | 6900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506356 | W-WW-NI-230420- ROTHESAY WWTW 2002 NS100637 - 2x DO PROBES & MONITORING EQUIPMENT - 8.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-29 |  | 2020-09-17 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8342.64 | 8342.64 | 0 | 0 | 0 | 8342.64 | 0 | 0 | 0 | 0 | 8342.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506355 | W-WW-NI-23042020- ALLOA WWTW NS887918 - REFURB & OVERHAUL KUHN WASHPACTOR - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-29 |  | 2020-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3431.79 | 3431.79 | 0 | 0 | 0 | 3431.79 | 0 | 0 | 0 | 0 | 3431.79 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506401 | W-WW-NI-230420-BONNYBRIDGE WWTW NS836811- REPLACE GEARED MOTOR (STORM SCREEN 1) - 5.2K | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 |  | 2020-05-04 |  | 2021-02-10 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5467.66 | 5467.66 | -267.66 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 5200 | 299983.07 | [5 empty] | N | CM_WWI | 50% | CM_WWNI | 50%
506353 | W-WW-NI-230420-CRAIGENGILLAN WWPS NS475060- REFURB SUBMERSIBLE PUMP 1 - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-29 |  | 2020-05-06 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2609.48 | 2609.48 | 0 | 0 | 0 | 2609.48 | 0 | 0 | 0 | 0 | 2609.48 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506351 | W-WW-NI-230420-POWBURN WWPS NS352266- CRITICAL SPARE FOUL PUMP - 14.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-29 |  | 2020-06-26 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14076.04 | 14076.04 | 0 | 0 | 0 | 14076.04 | 0 | 0 | 0 | 0 | 14076.04 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507957 | W-WW-NI-230720- CARRIDEN WWPS 1985 NT019814 - REFURBISH FOUL PUMP 1 - 2.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-31 |  | 2020-11-12 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2131.72 | 2131.72 | 0 | 0 | 0 | 2131.72 | 0 | 0 | 0 | 0 | 2131.72 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507962 | W-WW-NI-230720- DUNOON WWTW NS165745 - REFURBISH 2 SCREENS AT INLET WORKS - 25K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-31 |  | 2020-08-25 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24398.46 | 24398.46 | 0 | 0 | 0 | 24398.46 | 0 | 0 | 0 | 0 | 24398.46 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508016 | W-WW-NI-230720- OCHILTREE WWTW NS508215 - REPLACE RAS WHEEL GEARBOX & MOTOR - 1.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-10 |  | 2020-08-24 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1160.85 | 1160.85 | 0 | 0 | 0 | 1160.85 | 0 | 0 | 0 | 0 | 1160.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508007 | W-WW-NI-230720- PATNA WWTW NS414124 - REPLACE PRIMARY SLUDGE PUMP - 4.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-10 |  | 2020-10-13 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167.6 | 4167.6 | 0 | 0 | 0 | 4167.6 | 0 | 0 | 0 | 0 | 4167.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507965 | W-WW-NI-230720- PLEAN WWTW NS841870 - RESURFACE ACCESS ROAD - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-31 |  | 2020-08-28 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4806.4 | 4806.4 | 0 | 0 | 0 | 4806.4 | 0 | 0 | 0 | 0 | 4806.4 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507996 | W-WW-NI-230720- ROTHESAY WWTW 2002 NS100637 - REFURBISH FST 2 BRUSH ARM SCUM BUCKET & SCRAPER ARM - .2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-10 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536.45 | 536.45 | 7663.55 | 0 | 0 | 8200 | 0 | 0 | 0 | 0 | 8200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507972 | W-WW-NI-230720- TILLICOULTRY WWTW NS917965 - HEALTH & SAFETY: SUBMERSIBLE PUMP - 9.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-31 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.33 | 595.33 | 8504.67 | 0 | 0 | 9100 | 0 | 0 | 0 | 0 | 9100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507987 | W-WW-NI-230720- TYNDRUM WWTW NN330302 - H&S WORKS - .9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-10 |  | 2020-07-12 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6727.19 | 6727.19 | 0 | 0 | 0 | 6727.19 | 0 | 0 | 0 | 0 | 6727.19 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507888 | W-WW-NI-230720-STEWARTON WWTW NS408449- REPLACE WASHWATER PUMP 1 - 5.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-09-23 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5141.99 | 5141.99 | 0 | 0 | 0 | 5141.99 | 0 | 0 | 0 | 0 | 5141.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504944 | W-WW-NI-240120- MIDDLETON WWPS NS854964- FAST TRACK: PUMP REPLACEMENT - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-03 |  | 2020-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -282.95 | 2217.05 | 0 | 0 | 0 | 2217.05 | 0 | 0 | 0 | 0 | 2217.05 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504496 | W-WW-NI-241219-Bonnybridge WWTW-Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-12 |  | 2021-05-01 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7849.57 | 7849.57 | 92150.43 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504497 | W-WW-NI-241219-Fauldhouse WWTW-Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-12 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7135.9 | 7135.9 | 92864.1 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504494 | W-WW-NI-241219-Stewarton WWTW-Temp Chemical Dosing | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-12 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6709.47 | 6709.47 | 93290.54 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510505 | W-WW-NI-241220- CARRONSIDE WWPS NS892827 - REPLACE SUBMERSIBLE FOUL PUMP 2 - 38K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-23 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2485.98 | 2485.98 | 35514.03 | 0 | 0 | 38000.01 | 0 | 0 | 0 | 0 | 38000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510516 | W-WW-NI-241220- DALDERSE WWTW 1966 NS903822 - REPLACE TRAIN DRIVE - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-30 |  | 2021-02-27 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4124.77 | 4124.77 | 75.24 | 0 | 0 | 4200.01 | 0 | 0 | 0 | 0 | 4200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510517 | W-WW-NI-241220- DENNY STW INLET WWPS 1971 NS819829 - REPLACE SCREW PUMP UPPER BEARING - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-30 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.67 | 104.67 | 1495.32 | 0 | 0 | 1599.99 | 0 | 0 | 0 | 0 | 1599.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510503 | W-WW-NI-241220- GAILES WWPS NS323359 - REFURB STORM SUMP PUMP No6 - 6.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-23 |  | 2021-02-22 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6028.21 | 6028.21 | 71.79 | 0 | 0 | 6100 | 0 | 0 | 0 | 0 | 6100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510515 | W-WW-NI-241220- GIRVAN STC - REPLACE PLC - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-30 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1436.63 | 1436.63 | 63.36 | 0 | 0 | 1499.99 | 0 | 0 | 0 | 0 | 1499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510501 | W-WW-NI-241220- IRVINE HARBOUR WWPS NS313379 - Refurbishment of foul pump 2 - 18.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-23 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18463.79 | 18463.79 | 36.21 | 0 | 0 | 18500 | 0 | 0 | 0 | 0 | 18500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510504 | W-WW-NI-241220- MEADOWHEAD WWTW NS339361 - REINSTATE PENSTOCK AUTOMATION - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-23 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.6 | 248.6 | 3551.4 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510519 | W-WW-NI-241220- STIRLING WWTW 1968 NS808935 - REPLACE CRITICAL SPARE SBR DRIVE - 6.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-30 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412.15 | 412.15 | 5887.86 | 0 | 0 | 6300.01 | 0 | 0 | 0 | 0 | 6300.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510500 | W-WW-NI-241220- TILLICOULTRY WWTW NS917965 - INSTALL DEWATERING SYSTEM - 5.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-23 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5514.03 | 0 | 0 | 5900.01 | 0 | 0 | 0 | 0 | 5900.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510518 | W-WW-NI-241220-CARRONSIDE WWPS NS892827 - REPLACE PULSAR CONTROLLER AT INLET CHAMBER 1 - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-30 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654.21 | 654.21 | 9345.78 | 0 | 0 | 9999.99 | 0 | 0 | 0 | 0 | 9999.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505921 | W-WW-NI-25032020- CHAPEL FIELD WWPS NS835896 - Replace Sump Pump 1 - 2.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-25 |  | 2020-07-20 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 2045.28 | 2189.21 | 0 | 0 | 0 | 2189.21 | 0 | 0 | 0 | 0 | 2189.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507421 | W-WW-NI-250520- DOLLAR WWTW NS953978 - REPLACE MLSS MONITOR ON SBR 1 - 4.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-30 |  | 2020-08-14 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3830.5 | 3830.5 | 0 | 0 | 0 | 3830.5 | 0 | 0 | 0 | 0 | 3830.5 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506817 | W-WW-NI-250520- NORTH LODGE ROAD WWPS 1 NS504682 - REPLACE CONCRETE PLINTHS - 22K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2021-02-10 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21487.76 | 21487.76 | 512.24 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 22000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506818 | W-WW-NI-250520- NORTH LODGE ROAD WWPS 1 NS504682 - REPLACE SUBMERSIBLE PUMP 1 - 32K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-28 |  | 2020-10-07 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31582.65 | 31582.65 | 0 | 0 | 0 | 31582.65 | 0 | 0 | 0 | 0 | 31582.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506825 | W-WW-NI-250520- NORTH LODGE ROAD WWPS 1 NS504682 - SITE SERVICES: PIPEWORK REPLACEMENT - 15.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-28 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15722.06 | 15722.06 | 77.94 | 0 | 0 | 15800 | 0 | 0 | 0 | 0 | 15800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507494 | W-WW-NI-250620- ARDOCH WWTW 2002 NS374758 - REFURB SLUDGE PUMP C - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-15 |  | 2020-08-18 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3954.11 | 3954.11 | 0 | 0 | 0 | 3954.11 | 0 | 0 | 0 | 0 | 3954.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507457 | W-WW-NI-250620- BANKEND WWPS NS562200- HEALTH & SAFETY: REPLACE DAMAGED BRICKWORK & ROOF SECTION - 6.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-01 |  | 2020-10-09 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750.86 | 6750.86 | 0 | 0 | 0 | 6750.86 | 0 | 0 | 0 | 0 | 6750.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507496 | W-WW-NI-250620- DALMARNOCK WWTW NS611627 - REPAIR POTABLE WATER PUMPING STATION - 20.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-15 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1328.04 | 1328.04 | 18971.96 | 0 | 0 | 20300 | 0 | 0 | 0 | 0 | 20300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507461 | W-WW-NI-250620- MAYBOLE WWTW NS310088 - REPLACE DO MONITOR - 1.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-07-01 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810.68 | 1810.68 | 89.32 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507430 | W-WW-NI-250620-ALLOA WWTW NS887918- INSTALL TANKERING CONNECTION - 10.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-01 |  | 2020-10-07 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12753.16 | 12753.16 | 0 | 0 | 0 | 12753.16 | 0 | 0 | 0 | 0 | 12753.16 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507456 | W-WW-NI-250620-TILLICOULTRY WWTW NS917965- REPLACE DO MONITORS - 1.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-01 |  | 2020-10-19 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997.1 | 997.1 | 0 | 0 | 0 | 997.1 | 0 | 0 | 0 | 0 | 997.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503956 | W-WW-NI-251119- Denny WwTW NS820830 - Replacement Washwater Pump - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-05-05 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 1658.27 | 0 | 1658.27 | 0 | 0 | 0 | 1658.27 | 0 | 0 | 0 | 0 | 1658.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503960 | W-WW-NI-251119-Stirling WwTW 1968 NS808935- Washwater Pipework Extension - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-06-15 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 4360.51 | 0 | 4360.51 | 0 | 0 | 0 | 4360.51 | 0 | 0 | 0 | 0 | 4360.51 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505519 | W-WW-NI-260220 - UNDERWOOD (CUMNOCK) STC - Replace Rotor & Stator - 5.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-06 |  | 2020-07-27 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 359.81 | 5055.31 | 5415.12 | 0 | 0 | 0 | 5415.12 | 0 | 0 | 0 | 0 | 5415.12 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505961 | W-WW-NI-26032020 - KINNEIL KERSE WWTW 2001 NS960811 - Replace Liquor Pumps x2 - 6.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-06-05 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12294.53 | 12294.53 | 0 | 0 | 0 | 12294.53 | 0 | 0 | 0 | 0 | 12294.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505996 | W-WW-NI-26032020- BATTERY PARK WWPS NS254779- REPLACE/REFURB CRANE PARTS - 7.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-02 |  | 2020-05-14 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7373.81 | 7373.81 | 0 | 0 | 0 | 7373.81 | 0 | 0 | 0 | 0 | 7373.81 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505982 | W-WW-NI-26032020- BONESS WWTW NT022813 - Replace SBR probe - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-07-20 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943.56 | 1943.56 | 0 | 0 | 0 | 1943.56 | 0 | 0 | 0 | 0 | 1943.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505960 | W-WW-NI-26032020- BRAEHEAD SHOPPING CENT WWPS NS523670 - H&S - REPLACE TECHNO COVERS - 15.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14155 | 14155 | 1045 | 0 | 0 | 15200 | 0 | 0 | 0 | 0 | 15200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505987 | W-WW-NI-26032020- GIRVAN STC - Renew faulty external lighting - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-07-20 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2492.44 | 2492.44 | 0 | 0 | 0 | 2492.44 | 0 | 0 | 0 | 0 | 2492.44 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505962 | W-WW-NI-26032020- KINNEIL KERSE STC - Replacement rotor - 7.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-04-03 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516.82 | 516.82 | 7383.18 | 0 | 0 | 7900 | 0 | 0 | 0 | 0 | 7900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505956 | W-WW-NI-26032020- PARTICK WWPS NS565664 - REPLACE ROTORK - 11.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8754 | 8754 | 2546 | 0 | 0 | 11300 | 0 | 0 | 0 | 0 | 11300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505993 | W-WW-NI-26032020- STIRLING STC - Replace polymer feed pump 1.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-30 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1214 | 1214 | 86 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510324 | W-WW-NI-261120- ALLOA WWTW NS887918 - REFURBISH ROAD SURFACE (H&S) - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-15 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294.39 | 294.39 | 4205.61 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510319 | W-WW-NI-261120- ALLOA WWTW NS887918 - Refurbish Secondary Screw Pump 1 - 18.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-15 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13049.11 | 13049.11 | 5050.89 | 0 | 0 | 18100 | 0 | 0 | 0 | 0 | 18100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510342 | W-WW-NI-261120- ARDGOWAN WWPS 2001 NS202726 - Replace Conductivity system - 7.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-16 |  | 2021-05-01 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2103.96 | 2103.96 | 4996.05 | 0 | 0 | 7100.01 | 0 | 0 | 0 | 0 | 7100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510235 | W-WW-NI-261120- ARDOCH WWTW 2002 NS374758 - REFURBISH FST DRIVE WHEEL - 3.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-14 |  | 2021-02-10 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3858.4 | 3858.4 | 41.58 | 0 | 0 | 3899.98 | 0 | 0 | 0 | 0 | 3899.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510088 | W-WW-NI-261120- ARDROSSAN WWPS 1 NS226419 - REFURBISH STORM PUMP 2 - 7.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-04 |  | 2020-10-12 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7831.14 | 7831.14 | 0 | 0 | 0 | 7831.14 | 0 | 0 | 0 | 0 | 7831.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510116 | W-WW-NI-261120- AUCHINLECK 1 MAIN ST BRIDGEND GARAGE - Dismantle wall repair foundation re-build wall (H&S) - 3.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-04 |  | 2021-04-02 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3815.64 | 3815.64 | 84.36 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510070 | W-WW-NI-261120- AYR SHORE ROAD WWPS NS338232 - STRUCTURAL SURVEY - 1.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-02 |  | 2021-05-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 124.3 | 5075.7 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 5200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510067 | W-WW-NI-261120- CATRINEHOLM WWTW NS522258 - Replace Recirculation drip feed pump - 2.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-02 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2343.22 | 2343.22 | 56.76 | 0 | 0 | 2399.98 | 0 | 0 | 0 | 0 | 2399.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510297 | W-WW-NI-261120- DAILLY WWTW NS265012 - REPLACE SAF BLOWER UNIT - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3652.92 | 3652.92 | 47.08 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 3700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510196 | W-WW-NI-261120- DALDERSE STC - REPLACE SLUDGE PIPEWORK - 10.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000.02 | 0 | 0 | 10700.02 | 0 | 0 | 0 | 0 | 10700.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510137 | W-WW-NI-261120- DALMARNOCK SLUDGE WWPS 2000 NS610624 - REFURBISH SLUDGE TRANSFER PUMPS 1-5 - 4.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-04 |  | 2021-02-10 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4689.48 | 4689.48 | 10.53 | 0 | 0 | 4700.01 | 0 | 0 | 0 | 0 | 4700.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510207 | W-WW-NI-261120- DALMARNOCK WWTW NS611627 - PRESSURE WASHER (H&S) - 5.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-15 |  | 2021-02-13 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5589.36 | 5589.36 | 10.65 | 0 | 0 | 5600.01 | 0 | 0 | 0 | 0 | 5600.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510321 | W-WW-NI-261120- DUNBLANE WWTW NN782006 - REPLACE FAULTY LIGHTING (H&S) - 2.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-15 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 2056.05 | 0 | 0 | 2199.98 | 0 | 0 | 0 | 0 | 2199.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510301 | W-WW-NI-261120- LOCHGOILHEAD WWTW 2004 NN202019 - REFURB BLOWER 1 - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 170.09 | 2429.91 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510094 | W-WW-NI-261120- MAUCHLINE WWTW NS492254 - REPLACE CORRODED HANDRAILS AND KICKPLATES (HEALTH & SAFETY) - 10.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-04 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000.02 | 0 | 0 | 10700.02 | 0 | 0 | 0 | 0 | 10700.02 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510073 | W-WW-NI-261120- MILLPORT SPS NO5 2002 NS160546 - Replace stand by Sewage Pump - 3.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-02 |  | 2021-03-12 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3631.76 | 3631.76 | 68.22 | 0 | 0 | 3699.98 | 0 | 0 | 0 | 0 | 3699.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510051 | W-WW-NI-261120- NORTH SHORE RD WWPS NS927826 - CONTROL PANEL & PUMP REPLACEMENT (H&S) - 21.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 1400 | 20000 | 0 | 0 | 21400 | 0 | 0 | 0 | 0 | 21400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510126 | W-WW-NI-261120- PAISLEY BEN LEDI SPS EO - REPLACE PUMP - 5.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-04 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385.98 | 385.98 | 5514.03 | 0 | 0 | 5900.01 | 0 | 0 | 0 | 0 | 5900.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510230 | W-WW-NI-261120- PLEAN EAST WWPS NS840865 - REPLACE CONTROL PANELS - 15.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1027.1 | 1027.1 | 14672.88 | 0 | 0 | 15699.98 | 0 | 0 | 0 | 0 | 15699.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510237 | W-WW-NI-261120- ROTHESAY WWTW 2002 NS100637 - REPLACE BATTERY BACK UP FOR MCC - 1.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-14 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3 | 124.3 | 1775.7 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510197 | W-WW-NI-261120- SHIELDHALL WWTW NS533659 - REPLACE CABLE & COUPLING PLUG (PST3) - 1.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-14 |  | 2021-03-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1441.26 | 1441.26 | 158.73 | 0 | 0 | 1599.99 | 0 | 0 | 0 | 0 | 1599.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510140 | W-WW-NI-261120- SHIELDHALL WWTW NS533659 - REPLACE CONVEYOR GEARBOX CENTRIFUGE 2 - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-04 |  | 2021-03-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4424.05 | 4424.05 | 75.96 | 0 | 0 | 4500.01 | 0 | 0 | 0 | 0 | 4500.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510201 | W-WW-NI-261120- SHIELDHALL WWTW NS533659 - REPLACE VSD DRIVE WITH KEYPAD - 3.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-15 |  | 2021-02-10 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3258.39 | 3258.39 | 41.61 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 3300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510331 | W-WW-NI-261120- TILLICOULTRY WWTW NS917965 - REFURBISH INLET SCREEN 2 - 10.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-15 |  | 2021-03-05 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8125.84 | 8125.84 | 2074.17 | 0 | 0 | 10200.01 | 0 | 0 | 0 | 0 | 10200.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510059 | W-WW-NI-261120- UNDERWOOD (CUMNOCK) STC - REFURBISH THICKENER FEED PUMPS 1 & 2 - 8.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-02 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8283.55 | 8283.55 | 16.45 | 0 | 0 | 8300 | 0 | 0 | 0 | 0 | 8300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503991 | W-WW-NI-26112019 - Dalgrain WWPS 1976 NS915823 - Replace Roller Door Curtain - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -270.38 | 1729.62 | 0 | 0 | 0 | 1729.62 | 0 | 0 | 0 | 0 | 1729.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510107 | W-WW-NI-261120-KINNEIL KERSE STC- Replacement Cake Pump Rotor - 6.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-04 |  | 2021-02-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6195.26 | 6195.26 | 4.74 | 0 | 0 | 6200 | 0 | 0 | 0 | 0 | 6200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510333 | W-WW-NI-26120- ALLOA WWTW NS887918 - REBUILD SITE TELEMETRY - 6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-15 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6115.12 | 6115.12 | 439.14 | 0 | 0 | 6554.26 | 0 | 0 | 0 | 0 | 6554.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508552 | W-WW-NI-270820- BONNYBRIDGE WWTW NS836811 - REPLACE INTRUDER ALARM - 1.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-10-17 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1367.59 | 1367.59 | 0 | 0 | 0 | 1367.59 | 0 | 0 | 0 | 0 | 1367.59 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508497 | W-WW-NI-270820- CARRONSIDE WWPS NS892827 - REFURBISH WET WELL & PUMPS - 35K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-18 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31078.72 | 31078.72 | 3921.28 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 35000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508500 | W-WW-NI-270820- CARTSIDE ROAD WWPS NS577562 - REPLACE VSDs - 2.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.93 | 143.93 | 2056.07 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508499 | W-WW-NI-270820- COWIE WWTW 1972 NS849899 - REPLACE PST2 SCRAPER BRIDGE SUPPORT LEGS - 10.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 10000 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 10700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508468 | W-WW-NI-270820- COYLTON WWTW NS401200 - REFURBISH RAS PUMP 1 - 2.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-11 |  | 2020-04-12 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2852.86 | 2852.86 | 0 | 0 | 0 | 2852.86 | 0 | 0 | 0 | 0 | 2852.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508518 | W-WW-NI-270820- DALDERSE STC - REPLACE OBSOLETE GAS COMPRESSOR - 41.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-09-07 |  | 2021-02-23 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41375.91 | 41375.91 | 24.09 | 0 | 0 | 41400 | 0 | 0 | 0 | 0 | 41400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508507 | W-WW-NI-270820- DALMARNOCK WWTW NS611627 - REPLACE VSD FANS IN MCC - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-09-19 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1693.71 | 1693.71 | 0 | 0 | 0 | 1693.71 | 0 | 0 | 0 | 0 | 1693.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508533 | W-WW-NI-270820- DALMELLINGTON WWTW NS476050 - REFURB TELEMETRY EQUIPMENT - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-11-20 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5390.14 | 5390.14 | 0 | 0 | 0 | 5390.14 | 0 | 0 | 0 | 0 | 5390.14 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508551 | W-WW-NI-270820- DALMOAK WWPS NS387771 - REPLACE ROTORK ON INLET PENSTOCK - 7.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510.28 | 510.28 | 7289.72 | 0 | 0 | 7800 | 0 | 0 | 0 | 0 | 7800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508484 | W-WW-NI-270820- GARNIELAND ERSKINE WWPS NS483699 - REPLACE TECHNO-COVERS - 7.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-11 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46683.02 | 46683.02 | -38783.02 | 0 | 0 | 7900 | 0 | 0 | 0 | 0 | 7900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508534 | W-WW-NI-270820- GOUROCK CASTLE LEVAN WWPS 1994 NS216766 - REPLAE GATE VALVES & NRV x3 - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-07 |  | 2021-05-01 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333.64 | 333.64 | 4766.36 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 5100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508513 | W-WW-NI-270820- MILLPORT WWTW 2003 NS153540 - REPLACE DRIVE MOTOR ON INLET SCREEN - 4.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-11-03 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4357.85 | 4357.85 | 0 | 0 | 0 | 4357.85 | 0 | 0 | 0 | 0 | 4357.85 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508532 | W-WW-NI-270820- SHIELDHALL WWTW NS533659 - REFURB OF D2 CENTRIFUGE EQUIP - 13.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-09-14 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13110.08 | 13110.08 | 0 | 0 | 0 | 13110.08 | 0 | 0 | 0 | 0 | 13110.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508510 | W-WW-NI-270820- SHIELDHALL WWTW NS533659 - REPLACE DOOR TO E&M WORKSHOP (H&S) - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-10-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1698.35 | 1698.35 | 0 | 0 | 0 | 1698.35 | 0 | 0 | 0 | 0 | 1698.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508455 | W-WW-NI-270820- STIRLING STC - ADJUST SCREW CONVEYOR - 11.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-09-11 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752.34 | 752.34 | 10747.66 | 0 | 0 | 11500 | 0 | 0 | 0 | 0 | 11500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508523 | W-WW-NI-270820- UNDERWOOD (CUMNOCK) STC - REFURBISH BELT THICKENER - 12.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-08-12 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12510.28 | 12510.28 | 0 | 0 | 0 | 12510.28 | 0 | 0 | 0 | 0 | 12510.28 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508549 | W-WW-NI-270820- UNDERWOOD (CUMNOCK) STC - REPLACE DO SENSOR - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-09-23 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2595.09 | 2595.09 | 0 | 0 | 0 | 2595.09 | 0 | 0 | 0 | 0 | 2595.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510052 | W-WW-NI-271120- BURNBRAE WWPS NS438638 - REPLACE SUBMERSIBLE PUMP 1 - 4.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU |  | 2021-05-01 |  | 2021-05-01 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4839.05 | 4839.05 | 60.95 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 4900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510056 | W-WW-NI-271120- NEILSTON KIRKTONFIELD CRES WWPS NS488573 - Replace Foul Transfer Pump 1 - 5.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-01 |  | 2021-05-01 |  | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359.81 | 359.81 | 5140.17 | 0 | 0 | 5499.98 | 0 | 0 | 0 | 0 | 5499.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506943 | W-WW-NI-280520-CAMBUSBARRON KERSEBONNY RD NS77924803- REPLACE OBSOLETE TELEMETRY UNIT - 6.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-10-16 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6372.49 | 6372.49 | 0 | 0 | 0 | 6372.49 | 0 | 0 | 0 | 0 | 6372.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506916 | W-WW-NI-280520-CASTLEPARK WWPS NS322410- REFURB FOUL PUMPS 1&2 - 7.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-03 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7332.57 | 7332.57 | 67.43 | 0 | 0 | 7400 | 0 | 0 | 0 | 0 | 7400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506912 | W-WW-NI-280520-DEAN CRESCENT WWPS NS801943- REPLACE 3X ISOLATION VALVES & 2X NRVs - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-01 |  | 2020-08-13 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3940.1 | 3940.1 | 0 | 0 | 0 | 3940.1 | 0 | 0 | 0 | 0 | 3940.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506908 | W-WW-NI-280520-GREENOCK NO3 CSO (FOX STREET) NS271774- REPLACE MOTOR & GEARBOX FOR LONGWOOD SCREEN - 4.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-01 |  | 2020-08-26 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4868.56 | 4868.56 | 0 | 0 | 0 | 4868.56 | 0 | 0 | 0 | 0 | 4868.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506950 | W-WW-NI-280520-KINNEIL KERSE WWTW 2001 NS960811- RESURFACE ACCESS ROAD - 53.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53450.9 | 53450.9 | 0 | 0 | 0 | 53450.9 | 0 | 0 | 0 | 0 | 53450.9 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506944 | W-WW-NI-280520-KINNING PARK WWPS NS575644- REFURB BOTH INLET PENSTOCKS - 7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-03 |  | 2020-07-15 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6973.42 | 6973.42 | 0 | 0 | 0 | 6973.42 | 0 | 0 | 0 | 0 | 6973.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506941 | W-WW-NI-280520-STIRLING WWTW 1968 NS808935- REPLACE DRIVE MOTOR (FST DRIVE) - 5.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-02 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5571.36 | 5571.36 | 28.64 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 5600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506940 | W-WW-NI-280520-TILLICOULTRY WWTW NS917965- REFURB AERATOR - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-02 |  | 2020-09-25 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2925.01 | 2925.01 | 0 | 0 | 0 | 2925.01 | 0 | 0 | 0 | 0 | 2925.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506942 | W-WW-NI-280520-TILLICOULTRY WWTW NS917965- REPLACE SITE LIGHTING - HEALTH & SAFETY - 4.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-03 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314.02 | 314.02 | 4485.98 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 4800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508501 | W-WW-NI-280820- KIRKHOPE DRIVE TANK SST 2017 NS529704 - FAST TRACK PUMP REFURB - 8.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-02-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8470.78 | 8470.78 | 0 | 0 | 0 | 8470.78 | 0 | 0 | 0 | 0 | 8470.78 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508504 | W-WW-NI-280820-TROON HARBOUR WWPS NS307313- FAST TRACK - REFURBISH FOUL PUMP 1 - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-09-07 |  | 2020-01-12 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2410.47 | 2410.47 | 0 | 0 | 0 | 2410.47 | 0 | 0 | 0 | 0 | 2410.47 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506914 | W-WW-NI-290520-KINNING PARK WWPS NS575644- REPLACE WINDOW & FRAME (H&S) - 4.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-01 |  | 2020-07-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5596.95 | 5596.95 | 0 | 0 | 0 | 5596.95 | 0 | 0 | 0 | 0 | 5596.95 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507415 | W-WW-NI-290620- PAISLEY FERGUSLIE PARK CSO NO1 NS460635 - REFURBISH GEARBOX - 20K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-06-30 |  | 2021-03-27 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18572.03 | 18572.03 | 1427.97 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509587 | W-WW-NI-291020- BUCHLYVIE WWTW 1996 NS574942 - REFURB FST2 SCUM TRAP - 3.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3509.41 | 3509.41 | 90.59 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509679 | W-WW-NI-291020- DALDERSE WWTW 1966 NS903822 - Replace power supply on the RTC ammonia analyser - 3.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-11 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202.8 | 202.8 | 2897.2 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509600 | W-WW-NI-291020- DENNY WWTW NS820830 - REPLACE PST STILLING BOX SUPPORTS - 5.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340 | 340 | 4859.8 | 0 | 0 | 5199.8 | 0 | 0 | 0 | 0 | 5199.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509608 | W-WW-NI-291020- JOHNSTONE WWPS NS437637 - REPLACE DRIVE ON FOUL PUMP 2 - 4.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-04-02 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4667.18 | 4667.18 | 32.82 | 0 | 0 | 4700 | 0 | 0 | 0 | 0 | 4700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509568 | W-WW-NI-291020- KILCHATTAN BAY WWPS NS108545 - Replace duck foot & guide rails at PS - 5.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-02-25 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5138.9 | 5138.9 | 61.1 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 5200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509704 | W-WW-NI-291020- KILLEARN WWTW 1971 NS517844 - REFURBISH WALL REMOUNT FIXING PLATE - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-11 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2803.74 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509684 | W-WW-NI-291020- LINWOOD WWPS NS447648 - Refurbish Penstock in Storm pump well - 4.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-11 |  | 2021-02-12 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.02 | 4799.02 | 0.98 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 4800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509693 | W-WW-NI-291020- MEADOWHEAD WWTW NS339361 - REPLACE GEARBOX DRIVE MOTOR - 7.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-11 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7587.44 | 7587.44 | 12.56 | 0 | 0 | 7600 | 0 | 0 | 0 | 0 | 7600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509613 | W-WW-NI-291020- NEW CUMNOCK WWTW NS622140 - Replace Pump (SLUDGE HOLDING TANK 1 MIXER) - 4.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-05 |  | 2020-11-23 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4685.08 | 4685.08 | 0 | 0 | 0 | 4685.08 | 0 | 0 | 0 | 0 | 4685.08 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509624 | W-WW-NI-291020- POLMONTHILL WWPS 2000 NS953795 - REFURBISH FOUL PUMP 3 - 5.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.27 | 353.27 | 5046.72 | 0 | 0 | 5399.99 | 0 | 0 | 0 | 0 | 5399.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509646 | W-WW-NI-291020- STIRLING WWTW 1968 NS808935 - REFURBISH PST 3 RUNWAYS - 25.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-05 |  | 2021-03-26 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25581.57 | 25581.57 | 18.42 | 0 | 0 | 25599.99 | 0 | 0 | 0 | 0 | 25599.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509617 | W-WW-NI-291020- STIRLING WWTW 1968 NS808935 - REPLACE DRIVE NUTS & BELLOWS ON SBR DRIVE - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-11-05 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4865.49 | 4865.49 | -365.5 | 0 | 0 | 4499.99 | 0 | 0 | 0 | 0 | 4499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509674 | W-WW-NI-291020- THE MANSE WWPS NR803328 - REPLACE SUBMERSIBLE PUMP 2 - 5.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-11 |  | 2021-02-10 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5291.21 | 5291.21 | 8.78 | 0 | 0 | 5299.99 | 0 | 0 | 0 | 0 | 5299.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504193 | W-WW-NI-291119 - Girvan WWTW NX190999 - Refurb Decant Arm - 22K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-08-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 1293.25 | 23293.25 | 0 | 0 | 0 | 23293.25 | 0 | 0 | 0 | 0 | 23293.25 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504118 | W-WW-NI-291119 - North Lodge SPS 2012 NS416364 - Replace VSDs after Fire - 8K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2019-12-05 |  | 2020-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8255.56 | 0 | 8255.56 | 0 | 0 | 0 | 8255.56 | 0 | 0 | 0 | 0 | 8255.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504366 | W-WW-NI-291119 - Paisley LaighparkSLDG TFR WWPS NS485655 - Remove & Investigate Pump No3 complete with NRV - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-17 |  | 2020-07-27 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 10538.9 | 7526.96 | 18065.86 | 0 | 0 | 0 | 18065.86 | 0 | 0 | 0 | 0 | 18065.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504154 | W-WW-NI-291119- Bonnybridge WwTW NS836811 - Refurbish Storm Screens - 9.7K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-06-15 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 10257.58 | 0 | 10257.58 | 0 | 0 | 0 | 10257.58 | 0 | 0 | 0 | 0 | 10257.58 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504196 | W-WW-NI-291119- CUMNOCK UNDERWOOD WWTW - NEW ACTUATOR - 3K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3142.26 | 0 | 3142.26 | 0 | 0 | 0 | 3142.26 | 0 | 0 | 0 | 0 | 3142.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504191 | W-WW-NI-291119- DALDERSE WWTW 1966 NS903822- New PST drive train (Critical Spare) - 6K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-06-15 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 5912.6 | 0 | 5912.6 | 0 | 0 | 0 | 5912.6 | 0 | 0 | 0 | 0 | 5912.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504233 | W-WW-NI-291119- DALMELLINGTON WWTW NS476050 - Replace Pump & Guide Rails - 4K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4009.08 | 0 | 4009.08 | -9.08 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504440 | W-WW-NI-291119- DOLLAR WWTW NS953978 - Replace assist SBR lift & transfer pump - 3k | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-07 |  | 2020-06-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1136.6 | 4136.6 | 0 | 0 | 0 | 4136.6 | 0 | 0 | 0 | 0 | 4136.6 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504230 | W-WW-NI-291119- DUNOON WWTW NS165745 - Replace Sprybar Carousel bearings & proximity switch - 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-05-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -160.44 | 1839.56 | 0 | 0 | 0 | 1839.56 | 0 | 0 | 0 | 0 | 1839.56 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504282 | W-WW-NI-291119- Fintry WWTW NS614873 - Modify Gratings - 7.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-07-27 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 7990.65 | 0 | 7990.65 | 0 | 0 | 0 | 7990.65 | 0 | 0 | 0 | 0 | 7990.65 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504227 | W-WW-NI-291119- GAILES WWPS NS323359 - Urgent Refurb of ABB Drive - 6K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-05-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 8169.1 | 0 | 8169.1 | 0 | 0 | 0 | 8169.1 | 0 | 0 | 0 | 0 | 8169.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504425 | W-WW-NI-291119- KILLEARN WWTW 1971 NS517844 - Replace bauer coupling & pipework | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-07 |  | 2020-07-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -154.46 | 1845.54 | 0 | 0 | 0 | 1845.54 | 0 | 0 | 0 | 0 | 1845.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504269 | W-WW-NI-291119- KINNING PARK WWPS NS575644 - Reinstate Screen 2 - 9K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | -8411.21 | 588.79 | 8411.21 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 9000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504218 | W-WW-NI-291119- LOCHEARNHEAD WWPS NN593238 - Install Safety Cage Around Ladder (Confined Space Entry H&S) - 4K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | -320.32 | 3679.68 | 320.32 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504221 | W-WW-NI-291119- LOMOND IND EST WWPS 1999 NS395808 - Remedial Work to Pump Controls - 10K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-07-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 133.91 | 12133.91 | 0 | 0 | 0 | 12133.91 | 0 | 0 | 0 | 0 | 12133.91 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504091 | W-WW-NI-291119- Pike Rod WWPS NS811913 - Fast track Pump Replacement 4.7K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-05 |  | 2020-06-15 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 4958.18 | 0 | 4958.18 | 0 | 0 | 0 | 4958.18 | 0 | 0 | 0 | 0 | 4958.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504377 | W-WW-NI-291119- Rothesay WWTW 2002 NS100637 - Replace pump and guide rails - 5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-07 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 7.62 | 5007.62 | 0 | 0 | 0 | 5007.62 | 0 | 0 | 0 | 0 | 5007.62 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504161 | W-WW-NI-291119 -Shieldhall WWTW NS533659 - Install Final Effluent Turbidity & PH Instruments - 30K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2019-12-11 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 1539.89 | 31539.89 | -1539.89 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504215 | W-WW-NI-291119- STIRLING WWTW 1968 NS808935 - Install New LED Lights (H&S) - 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-06-15 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -174.16 | 1825.84 | 0 | 0 | 0 | 1825.84 | 0 | 0 | 0 | 0 | 1825.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504234 | W-WW-NI-291119- THE MANSE WWPS NR803328 - Replace Guide rails - 5.5K JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-08-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 2080.21 | 7580.21 | 0 | 0 | 0 | 7580.21 | 0 | 0 | 0 | 0 | 7580.21 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504206 | W-WW-NI-291119-CUMNOCK UNDERWOOD WWTW - 2x Bridge Wheels - 3K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3065.73 | 0 | 3065.73 | 0 | 0 | 0 | 3065.73 | 0 | 0 | 0 | 0 | 3065.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504200 | W-WW-NI-291119-GIRVAN WWTW NX190999 - Replace Washwater Pump - 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2019-12-20 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -270.04 | 1729.96 | 0 | 0 | 0 | 1729.96 | 0 | 0 | 0 | 0 | 1729.96 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510513 | W-WW-NI-291220- STIRLING WWTW 1968 NS808935 - INSTALL HANDRAILS (HEALTH & SAFETY) - 5.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-12-30 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5550.36 | 5550.36 | 49.64 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 5600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504190 | W-WW-NI-2919- North Shore Road WWPS NS927826 - Replacement Pump - 2K - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-12-11 |  | 2020-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1944.72 | 107.65 | 2052.37 | 0 | 0 | 0 | 2052.37 | 0 | 0 | 0 | 0 | 2052.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505025 | W-WW-NI-300120- 8 MILLFIELD DR SST PNRV 2009 NS932786 - REPLACE APNRV - 10.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-06 |  | 2020-05-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 2436.79 | 12936.79 | -1216.8 | 0 | 0 | 11719.99 | 0 | 0 | 0 | 0 | 11719.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504985 | W-WW-NI-300120- ALLOA WWTW NS887918 - Replace Screenings Handling - 8.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-03 |  | 2020-05-25 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 266.27 | 8766.27 | 0 | 0 | 0 | 8766.27 | 0 | 0 | 0 | 0 | 8766.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505017 | W-WW-NI-300120- DALDERSE WWTW 1966 NS903822 - REPLACE LDO SENSOR PROBES X 16 - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-05-05 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | -425.74 | 2574.26 | 0 | 0 | 0 | 2574.26 | 0 | 0 | 0 | 0 | 2574.26 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504960 | W-WW-NI-300120- DALDERSE WWTW 1966 NS903822 - Replacement Autosampler - 7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-03 |  | 2020-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | -58.11 | 6941.89 | 0 | 0 | 0 | 6941.89 | 0 | 0 | 0 | 0 | 6941.89 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505033 | W-WW-NI-300120- LOMOND STREET WWPS NS300821 - REFURBISH ROOF - 11K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | -2197.07 | 8802.93 | 2197.07 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 11000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504964 | W-WW-NI-300120- MUCKHART WWTW NO002003 - REFURBISH INLET SCREEN - 3.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-03 |  | 2020-06-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | -93.83 | 3506.17 | 0 | 0 | 0 | 3506.17 | 0 | 0 | 0 | 0 | 3506.17 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504970 | W-WW-NI-300120- NEW CUMNOCK WWTW NS622140 - Replace Scum Boards & Stilling Baffles - 25K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-03 |  | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | -11974.89 | 13025.11 | 11974.89 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505039 | W-WW-NI-300120- OCHILTREE WWTW NS508215 - Refurb De-watering Float Arm - 7.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-05-05 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | -289.59 | 6910.41 | 0 | 0 | 0 | 6910.41 | 0 | 0 | 0 | 0 | 6910.41 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504953 | W-WW-NI-300120- PARTICK WWPS NS565664 - Refurbish Foul Pump - 17K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-03 |  | 2020-09-04 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | -261.47 | 16738.53 | 0 | 0 | 0 | 16738.53 | 0 | 0 | 0 | 0 | 16738.53 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505026 | W-WW-NI-300120- ROWALLAN WWPS NS440401 - REPLACE FOUL PUMP - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-04-24 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | -156.87 | 1343.13 | 0 | 0 | 0 | 1343.13 | 0 | 0 | 0 | 0 | 1343.13 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505045 | W-WW-NI-300120- STIRLING WWTW 1968 NS808935 - REPLACE RAS PUMP - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-05-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | -348.65 | 3151.35 | 0 | 0 | 0 | 3151.35 | 0 | 0 | 0 | 0 | 3151.35 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505011 | W-WW-NI-300120- STIRLING WWTW 1968 NS808935 - REPLACEMENT SCREEN BRUSH GEARBOX - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-05-05 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 1959.37 | 0 | 1959.37 | 0 | 0 | 0 | 1959.37 | 0 | 0 | 0 | 0 | 1959.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505046 | W-WW-NI-300120- STIRLING WWTW 1968 NS808935 - Telemetry Investigations 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-02-06 |  | 2020-05-14 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -1869.16 | 130.84 | 1869.16 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505042 | W-WW-NI-300120- UNDERWOOD (CUMNOCK) STC - Replace Rotors & Stators for belt thickening feed pumps 1 & 2 - 8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-07-27 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 6420.3 | 0 | 6420.3 | 0 | 0 | 0 | 6420.3 | 0 | 0 | 0 | 0 | 6420.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504992 | W-WW-NI-300120-DALDERSE WWTW 1966 NS903822 - REPLACE FAILED DRIVE GEARBOX & MOTOR - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-03-05 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 1976.37 | 0 | 1976.37 | 0 | 0 | 0 | 1976.37 | 0 | 0 | 0 | 0 | 1976.37 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504938 | W-WW-NI-300120-Stirling WwTW-Replacement Gearbox | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-02-06 |  | 2021-05-01 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | -2149.53 | 150.47 | 2149.53 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506490 | W-WW-NI-300420- KINNEIL KERSE WWTW 2001 NS960811 - Replace Critical Spare Sludge Pump Stator - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-06-18 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.67 | 1969.67 | 0 | 0 | 0 | 1969.67 | 0 | 0 | 0 | 0 | 1969.67 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506443 | W-WW-NI-300420- ARDOCH WWTW 2002 NS374758 - Replace Desludge Pump A - 8.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-05-05 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.91 | 529.91 | 7570.09 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 8100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506470 | W-WW-NI-300420- DAILLY WWTW NS265012 - Replace SAF BLOWER 2 - 3.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-05 |  | 2020-07-16 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3391.39 | 3391.39 | 0 | 0 | 0 | 3391.39 | 0 | 0 | 0 | 0 | 3391.39 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506469 | W-WW-NI-300420- KIRKOSWALD WWPS NS235071 - Replace faulty lighting (H&S) - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-05 |  | 2020-06-01 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2422.49 | 2422.49 | 0 | 0 | 0 | 2422.49 | 0 | 0 | 0 | 0 | 2422.49 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506492 | W-WW-NI-300420-GAILES WWPS NS323359- Refurb Foul Pump 8 - 83K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-08-14 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82105.86 | 82105.86 | 0 | 0 | 0 | 82105.86 | 0 | 0 | 0 | 0 | 82105.86 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506527 | W-WW-NI-300420-MONTEITH GLASGOW WWPS NS583582- REPLACE DE-RAGGER CONTROLLER - 4.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-05-23 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4187.76 | 4187.76 | 0 | 0 | 0 | 4187.76 | 0 | 0 | 0 | 0 | 4187.76 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506529 | W-WW-NI-300420-STIRLING STC- CAKE BAY FABRICATION - 7.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-11 |  | 2020-07-15 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8032.3 | 8032.3 | 0 | 0 | 0 | 8032.3 | 0 | 0 | 0 | 0 | 8032.3 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508079 | W-WW-NI-300720- ALLOA WWTW NS887918 - REFURBISH MAIN SCREEN - 35.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-10 |  | 2020-09-03 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32886.93 | 32886.93 | 0 | 0 | 0 | 32886.93 | 0 | 0 | 0 | 0 | 32886.93 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508091 | W-WW-NI-300720- BONNYBRIDGE WWTW NS83681 - HEALTH & SAFETY: FREE STANDING RUNWAY BEAM WITH ELECTRIC CHAIN HOIST - 13.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-10 |  | 2020-11-11 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13557.01 | 13557.01 | 0 | 0 | 0 | 13557.01 | 0 | 0 | 0 | 0 | 13557.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508090 | W-WW-NI-300720- CATHCART NEW BRIDGE/OLD CASTLE RD E/O - REPLACE STORMFLOW TELEMETRY DEVICE - 5.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-10 |  | 2021-05-01 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333.64 | 333.64 | 4766.36 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 5100 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508068 | W-WW-NI-300720- DALDERSE WWTW 1966 NS903822 - REFURBISH INLET SCREEN - 28K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-10 |  | 2021-02-13 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27991.38 | 27991.38 | 0 | 0 | 0 | 27991.38 | 0 | 0 | 0 | 0 | 27991.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508074 | W-WW-NI-300720- DALDERSE WWTW 1966 NS903822 - REPLACE 2X RAS PUMP DRIVESHAFTS - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-10 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1926.84 | 1926.84 | 0 | 0 | 0 | 1926.84 | 0 | 0 | 0 | 0 | 1926.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508052 | W-WW-NI-300720- DALMARNOCK WWTW NS611627 - REPLACE AERATOR MOTOR - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-10 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2803.74 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508075 | W-WW-NI-300720- KINNING PARK WWPS NS575644 - REFURBISH FOUL PUMP 2 - 27.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-10 |  | 2021-03-25 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27388.84 | 27388.84 | 0 | 0 | 0 | 27388.84 | 0 | 0 | 0 | 0 | 27388.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508064 | W-WW-NI-300720- MAYBOLE WWTW NS310088 - REPLACE COMPACTOR GEARBOX - 10.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-08-10 |  | 2020-11-04 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10433.92 | 10433.92 | 0 | 0 | 0 | 10433.92 | 0 | 0 | 0 | 0 | 10433.92 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508050 | W-WW-NI-300720- STEWARTON WWTW NS408449 - HEALTH & SAFETY: REPLACE EXTERIOR LIGHTING - 10.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-10 |  | 2021-04-04 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12315.98 | 12315.98 | -1915.98 | 0 | 0 | 10400 | 0 | 0 | 0 | 0 | 10400 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508059 | W-WW-NI-300720-DALMARNOCK SLUDGE WWPS 2000 NS610624- REPLACE FAULTY RADAR UNIT - 3.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-08-10 |  | 2021-05-01 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.35 | 209.35 | 2990.65 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509234 | W-WW-NI-300920- DUNOON WWTW NS165745 - REPLACE RAS PUMP A - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-20 |  | 2021-02-10 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3775.28 | 3775.28 | 24.72 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505310 | W-WW-NI-30220- STEVENSTON POINT WWTW NS275404 - Replace Covers (H&S) and road gully - 4.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-03 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 1952 | 3009.28 | 4961.28 | -161.28 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 4800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505003 | W-WW-NI-310120- DALMARNOCK SLUDGE WWPS 2000 NS610624 - REPLACE MACERATORS X2 - 13K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-07-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | -183.89 | 12816.11 | 0 | 0 | 0 | 12816.11 | 0 | 0 | 0 | 0 | 12816.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505005 | W-WW-NI-310120- TILLICOULTRY WWTW NS917965 - REPAIR SCREEN - 10K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-06 |  | 2020-05-05 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 10643.71 | 0 | 10643.71 | 0 | 0 | 0 | 10643.71 | 0 | 0 | 0 | 0 | 10643.71 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512121 | W-WW-NI-310321- MAY STREET WWPS NS205585 - REPLACE FOUL PUMP 1 - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-04-01 |  | 2021-06-30 |  | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542.84 | 0 | 0 | 1542.84 | 0 | 0 | 0 | 0 | 1542.84 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507990 | W-WW-NI-310720- ALVA WWTW NS874966 - HEALTH & SAFETY WORKS - 10.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-10 |  | 2021-03-22 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10548.54 | 10548.54 | 0 | 0 | 0 | 10548.54 | 0 | 0 | 0 | 0 | 10548.54 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509321 | W-WW-NI-511020- DALMARNOCK SLUDGE WWPS 2000 NS610624 - REPLACE MAIN BREAKER (H&S) - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-10-26 |  | 2020-11-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1667.1 | 1667.1 | 0 | 0 | 0 | 1667.1 | 0 | 0 | 0 | 0 | 1667.1 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507288 | W-WW-NI-ARDOCH WWTW 2002 NS374758- FIT ISOLATION VALVES (PST B DESLUDGE VALVES) - 14.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-06-24 |  | 2021-05-01 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14276.11 | 14276.11 | 223.89 | 0 | 0 | 14500 | 0 | 0 | 0 | 0 | 14500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505862 | W-WW-NI-BONESS WWTW NT022813- Replace Obsolete Mounted Lenze Drive - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2020-03-23 |  | 2021-05-01 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 0 | 111.21 | 1588.79 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 1700 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506652 | W-WW-NI-BROADWOOD WWPS NS726743- REFURB SUBMERSIBLE PUMP 1 - 3.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-18 |  | 2020-06-16 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3473.43 | 3473.43 | 0 | 0 | 0 | 3473.43 | 0 | 0 | 0 | 0 | 3473.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503900 | W-WW-NI-FALLIN WwTW 1960 NS835823 - New Handrails H&S - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-05-05 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 3256.8 | 0 | 3256.8 | 0 | 0 | 0 | 3256.8 | 0 | 0 | 0 | 0 | 3256.8 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
503904 | W-WW-NI-Fallin WWTW 1969 NS835923- Walkway Installation (H&S) - JBrodie | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2019-11-29 |  | 2020-05-05 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | -118.48 | 5881.52 | 0 | 0 | 0 | 5881.52 | 0 | 0 | 0 | 0 | 5881.52 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504474 | W-WW-NI-FAST TRACK - KINNEIL KERSE WWTW 2001 NS960811 - Replace Storm Pump - 12K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-07 |  | 2020-05-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 243.43 | 12243.43 | 0 | 0 | 0 | 12243.43 | 0 | 0 | 0 | 0 | 12243.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511093 | W-WW-NI-FAST TRACK 03022021- CORNTON ROAD WWPS NS791966 - REPLACE FOUL PUMPS 1 - 2.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-08 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 2616.8 | 0 | 0 | 2799.98 | 0 | 0 | 0 | 0 | 2799.98 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511590 | W-WW-NI-FAST TRACK 030321- STIRLING WWTW 1968 NS808935 - Replace EMS Pump Push Rod - 1.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-04 |  | 2021-06-03 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1854.3 | 1854.3 | 45.7 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511603 | W-WW-NI-FAST TRACK 040321- CORNTON ROAD WWPS NS791966 - REPLACE FOUL PUMP 2 - 2.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-12 |  | 2021-06-04 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.18 | 183.18 | 2400 | 0 | 0 | 2583.18 | 0 | 0 | 0 | 0 | 2583.18 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509609 | W-WW-NI-FAST TRACK 041120- TARRYHOLME WWPS NS330378 - REPLACE FOUL PUMP 1 - 4.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-05 |  | 2021-02-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4032.39 | 4032.39 | 67.62 | 0 | 0 | 4100.01 | 0 | 0 | 0 | 0 | 4100.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511137 | W-WW-NI-FAST TRACK 090221- TOR-NA-DEE SPS NS168754 - REPLACE FOUL PUMP A - 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-15 |  | 2021-05-09 |  | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1588.8 | 0 | 0 | 1700.01 | 0 | 0 | 0 | 0 | 1700.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
509702 | W-WW-NI-FAST TRACK 091120 - DALDERSE WWTW 1966 NS903822 - Replace RAS return pump - 4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-11-11 |  | 2021-02-10 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3422.06 | 3422.06 | 577.94 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511265 | W-WW-NI-FAST TRACK 100221 - GARTLOCH EAST WWPS NS690674 - REPLACE FOUL PUMPS 1 - 1.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-19 |  | 2021-05-16 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1746.32 | 1746.32 | 53.68 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510427 | W-WW-NI-FAST TRACK 101220- DALMELLINGTON WWTW NS476050 - Replace RAS SAS Pump - 1.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-22 |  | 2021-03-17 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1461.33 | 1461.33 | 38.67 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511256 | W-WW-NI-FAST TRACK 120221- STIRLING STC - REPLACE MIXER PUMP - 3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2021-02-19 |  | 2021-04-04 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.26 | 196.26 | 2803.75 | 0 | 0 | 3000.01 | 0 | 0 | 0 | 0 | 3000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510347 | W-WW-NI-FAST TRACK 151220 - DALDERSE STC - REPLACE DIGESTER 1 SLUDGE CIRCULATION PUMP - 7.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-12-16 |  | 2021-02-25 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7457.91 | 7457.91 | 42.09 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511316 | W-WW-NI-FAST TRACK 170221- ERSKINE WWTW NS494691 - REPLACE BARESHAFT PUMP (FINAL EFFLUENT HIGH PRESSURE PUMP B) - 2.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2856.72 | 2856.72 | 43.28 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 2900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511315 | W-WW-NI-FAST TRACK 170221- ERSKINE WWTW NS494691 - REPLACE DRAIN DOWN PUMP 1 - 2.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-02-18 |  | 2021-05-18 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2099.43 | 2099.43 | 100.57 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 2200 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506301 | W-WW-NI-FAST TRACK 220420 - BALLANTRAE SPS - REPLACE PUMP STATION A - 5.4K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-23 |  | 2020-06-30 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5349.36 | 5349.36 | 0 | 0 | 0 | 5349.36 | 0 | 0 | 0 | 0 | 5349.36 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507837 | W-WW-NI-FAST TRACK 220720 - CASTLEPARK WWPS NS322410 - critical spare pump - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-07-27 |  | 2020-10-05 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3722.88 | 3722.88 | 0 | 0 | 0 | 3722.88 | 0 | 0 | 0 | 0 | 3722.88 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506327 | W-WW-NI-FAST TRACK 230420-CAMBUS MAIN WWPS NS856942- REPLACE FOUL PUMP2 - 16.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-04-23 |  | 2020-08-25 |  | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12640.42 | 12640.42 | 0 | 0 | 0 | 12640.42 | 0 | 0 | 0 | 0 | 12640.42 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
512033 | W-WW-NI-FAST TRACK 240321 - HOWE WWPS NS546219 - REPLACE SUMP PUMP 1 - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-29 |  | 2021-06-25 |  | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294.39 | 294.39 | 3857.16 | 0 | 0 | 4151.55 | 0 | 0 | 0 | 0 | 4151.55 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507398 | W-WW-NI-FAST TRACK 240620- KINGS INCH RD WWPS 2005 NS513678 - REFURB PUMP 1 & REPLACE GUIDERAILS - 6.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-30 |  | 2020-07-27 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6137.43 | 6137.43 | 0 | 0 | 0 | 6137.43 | 0 | 0 | 0 | 0 | 6137.43 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510893 | W-WW-NI-FAST TRACK 250121- IRVINE HARBOUR WWPS NS313379 - REPLACE SUMP PUMP 1 (JOURNAL) 1.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-27 |  | 2021-05-01 |  | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.21 | 111.21 | 1588.8 | 0 | 0 | 1700.01 | 0 | 0 | 0 | 0 | 1700.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511499 | W-WW-NI-FAST TRACK 250221 - STIRLING WWTW 1968 NS808935 - REPLACE SAS PUMP & GUIDE POLES - 4.3K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-05-26 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.31 | 281.31 | 4300 | 0 | 0 | 4581.31 | 0 | 0 | 0 | 0 | 4581.31 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511479 | W-WW-NI-FAST TRACK 250221- HOSPITALITY INN WWPS NS331384 - REFURB FOUL PUMP 1 - 3.8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-05-25 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3710.09 | 3710.09 | 89.91 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505942 | W-WW-NI-FAST TRACK 25032020 - DALMARNOCK WWTW NS611627 - REFURB STORM PUMP - 2.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-07-20 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2475.24 | 2475.24 | 0 | 0 | 0 | 2475.24 | 0 | 0 | 0 | 0 | 2475.24 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
507407 | W-WW-NI-FAST TRACK 250620- GLASGOW GREEN WWPS NS601638- REPLACE FOUL PUMP1 & GUIDE RAILS - 8.7K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-06-30 |  | 2020-08-12 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8069.27 | 8069.27 | 0 | 0 | 0 | 8069.27 | 0 | 0 | 0 | 0 | 8069.27 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
511502 | W-WW-NI-FAST TRACK 260221 - GLENOCHIL WWPS NS874762 - REPLACE FOUL PUMP - 2.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-03-02 |  | 2021-05-26 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.09 | 170.09 | 2600 | 0 | 0 | 2770.09 | 0 | 0 | 0 | 0 | 2770.09 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505948 | W-WW-NI-FAST TRACK 26032020- DALDERSE STC - REPLACE STANDBY SLUDGE PUMP - 10.2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-07-20 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7997.22 | 7997.22 | 0 | 0 | 0 | 7997.22 | 0 | 0 | 0 | 0 | 7997.22 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510036 | W-WW-NI-FAST TRACK 271120 - LEGGATE WWPS NS611131 - REPLACE SUBMERSIBLE PUMP 2 - 5.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-30 |  | 2021-03-21 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5884.32 | 5884.32 | 15.68 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 5900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510040 | W-WW-NI-FAST TRACK 271120- GOOSEHOLM WWPS NS402764 - REPLACE SUBMERSIBLE PUMP 1 & MOTOR - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-11-30 |  | 2021-02-28 |  | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2437.83 | 2437.83 | 62.16 | 0 | 0 | 2499.99 | 0 | 0 | 0 | 0 | 2499.99 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510195 | W-WW-NI-FAST TRACK 301120- KILLEARN DRUMORE RD APNRV 2018 NS519862 - REPLACCE EXISTING APNRV PUMP - 1.9K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-12-14 |  | 2021-02-10 |  | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1893.91 | 1893.91 | 6.09 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504470 | W-WW-NI-FAST TRACK- DALDERSE STC - Supply a critical spare sludge circulation pump - 8K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-21 |  | 2020-07-27 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 7960.64 | 0 | 7960.64 | 0 | 0 | 0 | 7960.64 | 0 | 0 | 0 | 0 | 7960.64 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505544 | W-WW-NI-FAST TRACK- ZETLAND PARK WWPS 2000 NS929811 - Refurb Storm Pump - 4.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-03-06 |  | 2020-05-14 |  | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 294.39 | 3692.82 | 3987.21 | 512.79 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505940 | W-WW-NI-FAST TRACK-25032020- ERSKINE WWTW NS494691- Replace VSD for Launder Pump B - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-03-30 |  | 2020-07-20 |  | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1732.73 | 1732.73 | 0 | 0 | 0 | 1732.73 | 0 | 0 | 0 | 0 | 1732.73 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
508353 | W-WW-NI-GLASGOW GREEN CSO 2012 NS603638 - FAST TRACK REPLACE SCREEN MOTOR - 4.6K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS4 |  | 2020-08-28 |  | 2021-04-03 |  | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4527.67 | 4527.67 | 72.33 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 4600 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
510617 | W-WW-NI-MUIRKIRK WWTW NS677264 - DO OPTIMISATION PROJECT - 14K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 |  | 2021-01-12 |  | 2021-05-01 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 915.89 | 915.89 | 13084.12 | 0 | 0 | 14000.01 | 0 | 0 | 0 | 0 | 14000.01 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
505094 | W-WW-NI-NEWMILNS ROAD WWPS NS502368 - REPLACE 2X FOUL PUMPS - 2.5K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-02-11 |  | 2020-05-20 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | -164.89 | 2335.11 | 0 | 0 | 0 | 2335.11 | 0 | 0 | 0 | 0 | 2335.11 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
504630 | W-WW-NI-STEWARTON WWTW NS408449 - Replacec Isolation valves x2 - 2K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-01-14 |  | 2020-07-08 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -71.68 | 1928.32 | 0 | 0 | 0 | 1928.32 | 0 | 0 | 0 | 0 | 1928.32 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
506696 | W-WW-NI-STEWARTON WWTW NS408449- REFURB PERCOLATING FILTER SLIP RING ASSEMBLY - 2.1K | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 |  | 2020-05-20 |  | 2020-06-10 |  | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2097.38 | 2097.38 | 0 | 0 | 0 | 2097.38 | 0 | 0 | 0 | 0 | 2097.38 | 90601.29 | [5 empty] | N | CM_WWNI | 100%
401441 | Yarrowfeus WSZ Low Pressure Enhancement WSZ001593 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-10-12 | 2011-09-06 | 2012-06-04 | 2013-06-25 | 2013-06-25 | Scottish Borders | 24267 | 0 | -94.24 | 0 | 0 | 0 | 0 | 0 | -94.24 | 0 | 0 | 0 | 24172.76 | 0 | 0 | 0 | 0 | 24172.76 | 0 | [5 empty] | N | CS1 | 100%
403589 | Yarrowford WTW Site - Flood Risk mitigation | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-09-06 | 2014-02-03 | 2014-02-10 | 2014-02-25 | 2014-03-20 | Scottish Borders | 22608 | 0 | -1293.12 | 0 | 0 | 0 | 0 | 0 | -1293.12 | 0 | 0 | 0 | 21314.88 | 0 | 0 | 0 | 0 | 21314.88 | 0 | [5 empty] | N | CS16W | 100%
45042 | Yarrowford WTW Upgrade | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-09-26 | 2012-09-17 | 2013-03-28 | 2013-06-24 | Scottish Borders | 831099.67 | 0 | 106.27 | 0 | 0 | 0 | 0 | 0 | 106.27 | 0 | 0 | 0 | 831205.94 | 0 | 0 | 0 | 0 | 831205.94 | 28761.13 | [5 empty] | N | DW23 | 100%
503595 | Yarrowfues WTW main-out 2019 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water | DWQR | WINF | DWQ Reliability | MS3 | 2013-03-18 | 2020-12-22 | 2021-01-29 | 2022-03-29 | 2022-06-06 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 226106.42 | 1263731.58 | 1489838 | 1533557.98 | 1533557.98 | 2492793.5476 | 3023395.98 | 959235.5676 | 0 | -4.6566e-10 | 959235.5676 | 3982631.5476 | 713665.28 | [5 empty] | Y | DW25P | 100% | [21 empty] | 1 | [45 empty] | 0
505446 | Yell North-a-voe ST - Access Footway | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 |  | 2020-08-28 | 2021-07-14 | 2021-10-20 |  | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11137 | 11137 | 23862.72 | 0 | 0 | 34999.72 | 0 | 0 | 0 | 0 | 34999.72 | 90601.29 | [5 empty] | N | WWNI | 100%
502569 | Yell WTW Growth | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS4 | 2021-01-05 | 2021-01-05 | 2021-01-12 | 2021-01-18 |  | Shetland Islands | 0 | 0 | 0 | 20930.23 | 3854.89 | 73881.46 | 33197.43 | 5118.58 | 136982.59 | 0 | 0 | 0 | 136982.59 | 0 | 0 | 0 | 0 | 136982.59 | 122419.09 | [5 empty] | N | WG1 | 100%
403709 | York Place WWPS Penstock By-Pass | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-10-23 | 2017-03-27 | 2017-03-30 | 2017-11-29 |  | Aberdeen City | 23715 | 0 | 15592 | 28869 | 56379.79 | 0 | 0 | 0 | 100840.79 | 0 | 0 | 0 | 124555.79 | 0 | 0 | 0 | 0 | 124555.79 | 209381.79 | [5 empty] | N | CM_WWI | 100%
503164 | Yr 4 Consultants OMG13 Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-05-29 | 2018-05-29 | 2019-05-07 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 276105.36 | 236306.65 | 132426.02 | 644838.03 | 355161.97 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503163 | Yr 4 MIOS Consultants Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-05-29 | 2018-05-29 | 2018-10-08 | 2021-05-01 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 368127.42 | 527711.99 | 411963.65 | 1307803.06 | -7803.06 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503160 | Yr 4 OMG13 East Area Code Bulk Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-16 | 2018-04-16 | 2018-07-25 | 2021-10-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 196592.41 | 235334.46 | 207340.33 | 639267.2 | 6408.27 | 0 | 0 | 645675.47 | 0 | 0 | 0 | 0 | 645675.47 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503158 | Yr 4 OMG13 North Area Code Bulk Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 | 2021-04-16 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 206975.37 | 280954.38 | 52315.54 | 540245.29 | 0 | 0 | 0 | 540245.29 | 0 | 0 | 0 | 0 | 540245.29 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503159 | Yr 4 OMG13 South Area Code Bulk Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 | 2024-09-19 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 239844.3 | 510671.42 | 72299.28 | 822815 | 6508.04 | 0 | 0 | 829323.04 | 0 | 0 | 0 | 0 | 829323.04 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503155 | Yr 4 SVCD East Area Code Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 | 2021-10-01 |  | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 36313.08 | 126044.06 | 91419.12 | 253776.26 | 46263.51 | 0 | 0 | 300039.77 | 0 | 0 | 0 | 0 | 300039.77 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503153 | Yr 4 SVCD North Area Code Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 | 2021-06-17 |  | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 13554.7 | 1177 | 65988.99 | 80720.68 | 80055.24 | 0 | 0 | 160775.92 | 0 | 0 | 0 | 0 | 160775.92 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503154 | Yr 4 SVCD South Area Code Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-18 | 2018-04-18 | 2018-08-14 | 2022-03-22 |  | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 625680.45 | 816029.89 | -52345.86 | 1389364.48 | 478.23 | 0 | 0 | 1389842.71 | 0 | 0 | 0 | 0 | 1389842.71 | 311236.79 | [5 empty] | N | CM_WSI | 100%
503156 | Yr 4 SVCD West Area Code Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-30 | 2018-04-30 | 2018-06-11 | 2022-04-14 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 700157.39 | 1131636.25 | -87067.4 | 1744726.24 | 1040000.01 | 0 | 0 | 2784726.25 | 0 | 0 | 0 | 0 | 2784726.25 | 311236.79 | [5 empty] | N | CM_WSI | 100%
502335 | Yr 4 to Yr 6 Holding Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2021-02-08 | 2021-02-02 | 2021-02-22 | 2021-02-22 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | N | CM_WSI | 100%
503161 | Yr4-Yr6 OMG13 West Area Code Bulk Line | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-16 | 2018-04-16 | 2018-06-11 | 2022-04-14 |  | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 519500.41 | 726429.04 | 139989.35 | 1385918.8 | 270000.02 | 0 | 0 | 1655918.82 | 0 | 0 | 0 | 0 | 1655918.82 | 311236.79 | [5 empty] | N | CM_WSI | 100%
PH_500112 | Aberlour DOA (DOA000499) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50710 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2019-02-28 | 2019-06-30 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500112 | Aberlour DOA (DOA000499) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Aberlour | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2019-02-28 | 2019-06-30 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500112 | Aberlour DOA (DOA000499) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_003 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2018-12-31 | 2019-01-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500111 | Alloa DOA (DOA000269) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_002 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2017-03-17 | 2017-05-08 | 2018-02-28 | 2018-08-31 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500111 | Alloa DOA (DOA000269) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_008 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2017-03-17 | 2017-05-08 | 2018-05-31 | 2018-08-31 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_503194 | Amlaird RSZ - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508018_01 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-03-31 | 2021-09-13 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_503194 | Amlaird RSZ - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508019_01 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-03-31 | 2021-09-13 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_503194 | Amlaird RSZ - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508020_01 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-04-01 | 2021-09-13 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500114 | Annan DOA (DOA000111) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_013 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-08-11 | 2019-02-28 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500114 | Annan DOA (DOA000111) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50725 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-08-11 | 2019-03-31 | 2019-08-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500113 | Anstruther Billowness DOA (DOA000254) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50837 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-03-21 | 2018-12-31 | 2019-03-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500113 | Anstruther Billowness DOA (DOA000254) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_028 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-03-21 | 2018-09-30 | 2018-11-30 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500121 | Ardoch DOA (DOA000707) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50801 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2016-06-27 | 2016-08-24 | 2020-01-31 | 2020-04-30 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500121 | Ardoch DOA (DOA000707) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_015 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-17 | 2016-06-27 | 2016-08-24 | 2020-01-31 | 2020-01-31 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_502278 | Ayrshire Strategic Resilience- Highlees DSR | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance | TBC_FN_ASR_2 | OMG 07 | Water | DWQR | WINF | Exceptional Capital Maintenance |  | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-31 | 2019-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [26 empty] | 1 | [42 empty] | 0
PH_502278 | Ayrshire Strategic Resilience- Highlees DSR | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance | TBC_FN_ASR_4 | OMG 07 | Water | DWQR | WINF | Exceptional Capital Maintenance |  | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-31 | 2019-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [26 empty] | 1 | [42 empty] | 0
PH_502278 | Ayrshire Strategic Resilience- Highlees DSR | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance | TBC_FN_ASR_3 | OMG 07 | Water | DWQR | WINF | Exceptional Capital Maintenance |  | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-31 | 2019-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [26 empty] | 1 | [42 empty] | 0
PH_500795 | Backies RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50200 | OMG 06 | Water | DWQR | SWD | DWQ Reliability |  | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-09-30 | 2019-02-28 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 97.7 | [43 empty] | 0
PH_500795 | Backies RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53305 | OMG 06 | Water | DWQR | SWD | DWQ Reliability |  | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-09-30 | 2019-02-28 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 9.47 | [43 empty] | 0
PH_500844 | Badentinan RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53206 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-07-27 | 2018-06-28 | 2018-12-04 | 2019-12-31 | 2020-10-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 32.88 | [43 empty] | 0
PH_500844 | Badentinan RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50201 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-07-27 | 2018-06-28 | 2018-12-04 | 2019-12-31 | 2020-10-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 84.97 | [43 empty] | 0
PH_500846 | Balmore A RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53188 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-09-20 | 2017-12-20 | 2017-12-20 | 2019-09-30 | 2020-04-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 6.76 | [43 empty] | 0
PH_500846 | Balmore A RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50248 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-09-20 | 2017-12-20 | 2017-12-20 | 2019-09-30 | 2020-04-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 70.18 | [43 empty] | 0
PH_500227 | Balmore E - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50009_001 | OMG 06 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-04-20 | 2017-02-28 | 2020-03-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 9.6 | [43 empty] | 0
PH_500227 | Balmore E - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50009_002 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-04-20 | 2017-02-28 | 2020-01-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500228 | Balmore F - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50010_001 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2019-03-31 | 2019-03-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500228 | Balmore F - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50010_002 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2018-06-30 | 2019-03-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500228 | Balmore F - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50010_003 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2018-06-30 | 2020-02-29 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500848 | Balmore F RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53190 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-03-31 | 2017-12-19 | 2018-03-20 | 2019-03-31 | 2019-05-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 9.83 | [43 empty] | 0
PH_500848 | Balmore F RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50236 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-03-31 | 2017-12-19 | 2018-03-20 | 2019-03-31 | 2019-05-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 30.32 | [43 empty] | 0
PH_500116 | Bathgate DOA (DOA000537) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_026 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-29 | 2016-09-30 | 2018-09-30 | 2018-11-30 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500116 | Bathgate DOA (DOA000537) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_003 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-29 | 2016-09-30 | 2019-03-31 | 2019-12-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N01 | OMG 21 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [40 empty] | 1 | [28 empty] | 0
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N02 | OMG 21 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [40 empty] | 1 | [28 empty] | 0
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N03 | OMG 21 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [40 empty] | 1 | [28 empty] | 0
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N05 | OMG 21 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [40 empty] | 1 | [28 empty] | 0
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N07 | OMG 21 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [40 empty] | 1 | [28 empty] | 0
PH_500247 | Bathing Water Modelling Updates | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N10 | OMG 21 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [40 empty] | 1 | [28 empty] | 0
PH_500239 | Black Esk - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50013_003 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-03-31 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500239 | Black Esk - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50013_002 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-03-31 | 2019-06-30 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500239 | Black Esk - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50013_001 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-07-31 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500797 | Black Esk RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53202 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2015-09-30 | 2018-06-28 | 2018-09-28 | 2019-11-07 | 2020-12-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 206.56 | [43 empty] | 0
PH_500797 | Black Esk RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50237 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2015-09-30 | 2018-06-28 | 2018-09-28 | 2020-03-31 | 2020-12-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 40.93 | [43 empty] | 0
PH_500800 | Bonnycraig RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53207 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-01-12 | 2017-03-09 | 2017-03-30 | 2019-05-31 | 2019-12-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 16.98 | [43 empty] | 0
PH_500800 | Bonnycraig RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50239 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-01-12 | 2017-03-09 | 2017-03-30 | 2019-05-31 | 2019-12-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 24.15 | [43 empty] | 0
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508048 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-12-13 | 2021-12-13 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508039 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2021-12-13 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508047 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2020-12-31 | 2021-12-13 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508040 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-31 | 2019-10-02 | 2020-12-31 | 2021-12-13 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508046 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2020-12-31 | 2021-12-13 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508045 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2021-12-13 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508044 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2020-12-31 | 2021-11-15 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508042 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-03-31 | 2021-12-13 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_503631 | Bradan WOA- WQ High Priority Customer Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 508041 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2021-12-13 | 2021-12-13 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_502412 | Bradan WTW Water Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50091_TE_500091_02 | OMG 01 | Water | DWQR | NONINF | DWQ Reliability |  | 2015-07-31 | 2017-03-31 | 2017-03-31 | 2018-09-30 | 2019-09-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [20 empty] | 1 | [48 empty] | 0
PH_502412 | Bradan WTW Water Quality | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50749_TE_500749_02 | OMG 01 | Water | DWQR | NONINF | DWQ Reliability |  | 2015-07-31 | 2017-03-31 | 2017-03-31 | 2018-06-30 | 2019-09-30 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [20 empty] | 1 | [48 empty] | 0
PH_500123 | Brechin DOA (DOA000645) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_036 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-11-24 | 2016-11-25 | 2018-09-30 | 2018-11-30 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500123 | Brechin DOA (DOA000645) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Brechin | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-11-24 | 2016-11-25 | 2018-11-30 | 2019-03-31 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_502132 | Burncrooks WTW Quality THM Compliance | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50144 | OMG 01 | Water | SEPA | WINF | DWQ Compliance |  | 2016-03-17 | 2019-03-29 | 2019-03-29 | 2023-01-20 | 2023-04-17 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [20 empty] | 1 | [48 empty] | 0
PH_502132 | Burncrooks WTW Quality THM Compliance | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50144 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2016-03-17 | 2019-03-29 | 2019-03-29 | 2023-01-20 | 2023-04-17 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 5 | [29 empty] | 0
PH_503250 | Carron Valley RSZ Cleaning Flushing | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59069_01_02 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-06-28 | 2019-06-21 | 2019-09-11 | 2021-07-30 | 2022-07-28 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 17.849 | [43 empty] | 0
PH_503250 | Carron Valley RSZ Cleaning Flushing | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59069_01_01 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-06-28 | 2019-06-21 | 2019-09-11 | 2021-03-31 | 2021-09-29 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 326.89 | [43 empty] | 0
PH_502605 | Carron Valley RSZ Cleaning - Mains Conditioning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59067_02 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-06-28 | 2019-06-11 | 2019-08-02 | 2021-09-30 | 2022-04-29 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 143.191 | [43 empty] | 0
PH_502605 | Carron Valley RSZ Cleaning - Mains Conditioning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59067_01 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-06-28 | 2019-06-11 | 2019-08-02 | 2021-03-31 | 2022-04-29 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 32.009 | [43 empty] | 0
PH_500119 | Castle Douglas DOA (DOA000097) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_042 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-01-19 | 2016-03-21 | 2017-07-31 | 2017-08-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500119 | Castle Douglas DOA (DOA000097) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50803 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-01-19 | 2016-03-21 | 2017-07-31 | 2017-08-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500031 | Catchment Assessment Study for Drinking Water Quality Protection | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50186_TE_500186_01_N02 | OMG 47 | Water | DWQR | SWD | DWQ Reliability |  | 2015-02-27 | 2015-07-17 | 2015-07-27 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 14 |  |  | 0
PH_500031 | Catchment Assessment Study for Drinking Water Quality Protection | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50186_TE_500186_01_N01 | OMG 47 | Water | DWQR | SWD | DWQ Reliability |  | 2015-02-27 | 2015-07-17 | 2015-07-27 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 8 |  |  | 0
PH_500062 | Clatto East - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50000_001 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-19 | 2016-05-26 | 2016-05-30 | 2017-09-30 | 2018-12-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500062 | Clatto East - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50000_002 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-19 | 2016-05-26 | 2016-05-30 | 2017-09-30 | 2018-12-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_001 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-09-30 | 2019-07-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_003 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-06-30 | 2019-04-30 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_004 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-03-31 | 2019-07-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_005 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-06-30 | 2019-03-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500006 | Clatto West - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_002 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-12-31 | 2019-07-31 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_045 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_044 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_043 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_042 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_041 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_039 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_046 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_036 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_056 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_034 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_033 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2021-01-31 | 2021-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_038 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_048 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_049 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_050 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_051 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_055 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_057 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_058 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_059 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_060 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_061 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_032 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_005 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_053 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_015 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_001 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_003 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_004 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_054 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_006 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_062 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_008 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_009 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_010 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_011 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-04-02 | 2020-04-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_007 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_014 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_031 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_016 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_017 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_019 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_020 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_022 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_023 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_024 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_026 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_027 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_029 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_030 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-19 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_012 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500190 | Climate Change Model for WRZ | Q&S4 | Climate Change | Climate Change | TE_501313_052 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500098 | Climate Change Risk Assessments | Q&S4 | Climate Change | Climate Change | 51308_TE_501308_001 | OMG 45 | General | SEPA | SWD | Climate Change |  | 2015-03-31 | 2015-09-25 | 2015-09-25 | 2016-06-30 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500098 | Climate Change Risk Assessments | Q&S4 | Climate Change | Climate Change | 51308_TE_501308_002 | OMG 45 | General | SEPA | SWD | Climate Change |  | 2015-03-31 | 2015-09-25 | 2015-09-25 | 2016-06-30 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_025 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_024 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_023 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_022 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_021 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_020 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_019 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_018 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_017 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_015 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_016 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500092 | Climate Change Trends Modelling A Wastewater Catchment | Q&S4 | Climate Change | Climate Change | TE_501311_026 | OMG 45 | Wastewater | SEPA | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500122 | Corpach DOA (DOA000325) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50727 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-09-30 | 2019-12-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500122 | Corpach DOA (DOA000325) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_049 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-08-31 | 2020-01-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500122 | Corpach DOA (DOA000325) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Corpach | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-09-30 | 2019-12-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_004 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_014 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_021 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-08-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_022 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-10-31 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_020 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_019 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-08-31 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_018 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_017 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_016 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2019-07-31 | 2020-02-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_015 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_013 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-08-31 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_012 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_011 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_009 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-08-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_007 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_023 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_005 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_028 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_003 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-02-14 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_002 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_006 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-08-31 | 2018-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_038 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_057 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-31 | 2018-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_055 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-06-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_054 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_052 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-06-30 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_048 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_047 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_046 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_045 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_044 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_042 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_041 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_026 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-10-31 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_039 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_024 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_037 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_036 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_034 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_033 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_032 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_031 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_030 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_029 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_008 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_027 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_001 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-09-30 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_025 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_040 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500843 | Critical Reservoirs 500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_010 | OMG 13 | Water | DWQR | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [32 empty] | 1 | [36 empty] | 0
PH_500124 | Dalscone DOA (DOA000101) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_065 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2018-11-30 | 2019-01-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500124 | Dalscone DOA (DOA000101) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_066 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2018-11-30 | 2019-01-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500124 | Dalscone DOA (DOA000101) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50804 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2019-01-31 | 2019-06-30 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_072 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_071 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_061 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_069 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_067 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_066 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_048 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_065 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_064 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_062 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_059 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_058 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_049 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_073 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_050 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_051 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_052 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-11 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_053 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_054 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_055 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_056 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_063 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_084 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_095 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_094 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_093 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_092 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_091 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_090 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_089 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_088 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_087 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_077 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-06-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_085 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_074 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_083 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_082 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_081 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_080 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_079 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_035 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-11 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_078 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_047 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_076 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_075 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_086 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_010 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_037 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_021 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_020 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_018 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_017 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_016 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_015 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_014 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_013 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_023 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_011 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_024 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_009 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_008 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_007 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_006 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_005 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_004 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_003 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_002 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_001 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_012 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-11 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_034 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_045 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_044 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_043 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_042 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_041 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_040 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_039 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_038 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_096 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_022 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_070 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_046 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_033 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_032 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_031 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_030 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_029 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_028 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_027 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_026 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_025 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_036 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_135 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_124 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_125 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_126 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_127 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_128 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_129 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_130 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_131 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_132 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_123 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_134 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_139 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_136 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_137 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_138 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_140 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_142 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_144 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_145 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-11 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_097 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_068 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-11 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_133 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_103 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_141 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_122 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_100 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_101 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_102 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_099 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_104 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_106 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_107 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_108 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_109 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_110 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_112 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_113 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_114 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-10-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_115 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_117 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_118 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_121 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-08-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_119 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_098 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_120 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500200 | Drought Plans | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_111 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_107 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_097 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_052 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_053 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_114 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_113 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_112 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_111 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_110 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_048 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_108 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_047 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_106 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_105 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_104 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_103 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_101 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_100 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_099 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_109 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_037 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_025 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_026 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_027 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_028 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_030 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_031 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_033 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_034 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_050 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_036 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_096 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_038 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_039 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_040 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_041 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_043 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_044 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_045 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_046 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_035 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_065 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_098 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_072 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_071 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_070 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_069 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_068 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_067 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_024 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_074 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_049 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_075 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_064 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_063 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_062 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_061 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_059 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_058 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2021-02-28 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_054 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_056 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-01-31 | 2020-04-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_066 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_084 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-07-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_095 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_093 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_092 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_091 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_090 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_089 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_088 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_087 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_073 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-01-31 | 2020-04-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_085 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_057 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_083 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_082 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_081 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-01-31 | 2020-04-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_080 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_079 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_078 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_077 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_076 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_086 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 50771_TE_500771_143 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_023 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_051 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_001 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_002 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_003 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_004 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_005 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_006 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_007 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_008 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_009 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_019 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_011 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_012 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_013 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_014 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_015 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_016 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_017 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-03-25 | 2020-04-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_018 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_022 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_010 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_020 | OMG 47 | Water | DWQR | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-08-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_501271 | Dunnswood DOA (DOA000557) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_074 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-31 | 2016-07-29 | 2016-08-18 | 2018-09-30 | 2018-11-30 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501271 | Dunnswood DOA (DOA000557) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_004 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-31 | 2016-07-29 | 2016-08-18 | 2019-03-31 | 2019-12-31 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500128 | Dunoon DOA (DOA002568) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_075 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2015-09-27 | 2015-11-02 | 2017-07-31 | 2017-07-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500128 | Dunoon DOA (DOA002568) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_076 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2015-09-27 | 2015-11-02 | 2017-07-31 | 2017-07-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50175 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50174 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50173 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50172 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50171 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50176 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-04-30 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50169 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-10-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50170 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50167 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-02-28 | 2017-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50166 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50168 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50164 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50162 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50163 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500578 | DW5-13 Trunk Main Systems Mains and Conditioning Designs | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50165 | OMG 47 | Water | DWQR | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-04-30 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_501104 | Edinburgh DAS Aesthetic and Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Edin | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-09-30 | 2017-02-27 | 2017-03-27 | 2018-12-31 | 2019-01-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_501104 | Edinburgh DAS Aesthetic and Catchment Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50829 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-09-30 | 2017-02-27 | 2017-03-27 | 2018-12-31 | 2019-01-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500223 | Eela Water - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50027_002 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-30 | 2020-01-31 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500223 | Eela Water - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50027_001 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-30 | 2018-06-30 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500223 | Eela Water - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50027_003 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-30 | 2018-12-31 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_012 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.0088 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_008 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.046 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_010 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.0039 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_013 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.128 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_015 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.0365 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_004 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.028 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_009 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.15 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_007 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.07 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_005 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.01 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_003 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.07 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_002 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.01 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_001 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.044 | [5 empty] | 0
PH_500483 | Energy Efficiency - Water | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_006 | OMG 44 | Water | SW | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.05 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_010 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.14 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_052 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.011 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_001 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-07-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.046 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_002 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.15 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_003 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.081 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_004 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-12-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.16 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_008 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-07-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.075 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_009 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-11-30 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.475 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_039 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.117 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_012 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.41 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_013 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-11-30 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.052 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_014 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.261 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_015 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-12-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.05 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_016 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 5.921 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_017 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-12-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.54 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_018 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.024 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_019 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-09-30 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.05 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_022 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-10-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.02 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_024 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 1.212 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_034 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-07-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.051 | [5 empty] | 0
PH_500484 | Energy Efficiency Wastewater | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_011 | OMG 44 | Wastewater | SW | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [63 empty] | 0.57 | [5 empty] | 0
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-16 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-12 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-03-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-14 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-11 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-03-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-15 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-10 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500064 | Enhancement of Raw Water PS Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-13 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-20 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-17 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-14 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-13 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-15 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-12 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-16 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-11 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-10 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-19 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-21 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-22 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-23 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-24 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-25 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-26 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-27 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-28 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-5 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-6 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-7 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-8 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-18 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-8 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-7 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-5 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-9 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-9 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502644 | Enhancement of RWP & TWP Security Phase 0 - Year 2 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-6 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-9 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-8 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-7 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-6 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-55 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-54 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-42 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-45 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-35 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-36 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-21 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-37 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-38 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-39 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-4 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-40 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-44 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-43 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-53 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-46 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-47 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-48 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-49 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-5 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-50 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-51 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-52 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-41 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-15 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-23 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-20 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-2 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-19 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-18 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-34 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-16 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-24 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-14 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-13 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-12 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-11 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-10 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-1 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-17 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-27 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-32 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-31 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-30 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-3 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-29 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-22 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-28 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-33 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-26 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-31 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500199 | Enhancement of Treated Water PS - Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-25 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-28 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_24 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_13 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-11-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_14 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-05-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_15 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_16 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-04-30 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_17 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-11-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_18 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-04-30 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_19 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_20 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-11-30 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_11 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-03-31 | 2018-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_21 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-06-30 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_23 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_25 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_26 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-05-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_27 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-06-30 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_30 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-03-31 | 2018-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_29 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-01-31 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_12 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_22 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-05-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502187 | Enhancement of Water Treatment Works Security | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_28 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500126 | Erskine DOA (DOA002466) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_005 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2020-09-30 | 2021-03-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500126 | Erskine DOA (DOA002466) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50721 | OMG 23 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2020-08-31 | 2021-01-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500126 | Erskine DOA (DOA002466) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_083 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2020-09-30 | 2020-10-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500135 | Eyemouth DOA (DOA000070) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_084 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-26 | 2016-06-20 | 2019-02-28 | 2019-03-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500135 | Eyemouth DOA (DOA000070) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Eyemo | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-26 | 2016-06-20 | 2019-09-30 | 2019-09-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500823 | Fairmilehead B RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53192 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2015-10-28 | 2017-12-21 | 2017-12-22 | 2019-03-31 | 2019-07-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 25.51 | [43 empty] | 0
PH_500823 | Fairmilehead B RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50240 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2015-10-28 | 2017-12-21 | 2017-12-22 | 2019-03-31 | 2019-07-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 2.19 | [43 empty] | 0
PH_500241 | Fairmilehead C - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50029_003 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-31 | 2018-09-30 | 2018-09-30 | 2019-02-28 | 2019-09-30 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500241 | Fairmilehead C - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50029_001 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-31 | 2018-09-30 | 2018-09-30 | 2021-03-31 | 2021-06-14 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500824 | Fairmilehead C RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50241 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-08-03 | 2018-03-23 | 2018-06-14 | 2019-03-31 | 2019-08-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 22.58 | [43 empty] | 0
PH_500824 | Fairmilehead C RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53193 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-08-03 | 2018-03-23 | 2018-06-14 | 2019-03-31 | 2019-08-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 16.58 | [43 empty] | 0
PH_500074 | Final Water Sampling Programme Extension | Q&S4 | Climate Change | Climate Change | 51315 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-09 | 2015-06-30 | 2015-06-30 | 2016-03-31 | 2016-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500074 | Final Water Sampling Programme Extension | Q&S4 | Climate Change | Climate Change | 51305 | OMG 45 | Water | SEPA | SWD | Climate Change |  | 2015-03-09 | 2015-06-30 | 2015-06-30 | 2016-03-31 | 2016-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_147 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-07-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_124 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_176 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_159 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_155 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_154 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_153 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_152 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-04-30 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_151 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_148 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_167 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_145 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_144 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_143 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_139 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-09-30 | 2018-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_138 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_137 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_133 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_131 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_130 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_126 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_150 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_191 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_207 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_206 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_205 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_204 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_203 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_202 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_201 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-02-25 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_095 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-12-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_200 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_165 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_194 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_166 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-04-21 | 2020-05-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_187 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-03-19 | 2020-05-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_175 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_174 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_173 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_172 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-03-25 | 2020-05-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_171 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-09-30 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_170 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_169 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_168 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-12-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_196 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-06-30 | 2018-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_022 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_094 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_002 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_001 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_053 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_005 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_009 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_010 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-09 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_011 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-04-30 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_012 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_016 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_017 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-01-31 | 2017-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_018 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-02-28 | 2018-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_090 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-11-30 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_021 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_004 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_023 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_024 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-02-06 | 2020-02-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_025 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-04-30 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_027 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_029 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_031 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_188 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-07-31 | 2020-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_037 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_123 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-08-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_038 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-13 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_039 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-02-28 | 2017-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_043 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_040 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-12-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_019 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-30 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_114 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-11-30 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_045 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_046 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_047 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_085 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_100 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_106 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_054 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-31 | 2018-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_113 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_098 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_115 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_048 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_116 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-04-24 | 2020-05-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_050 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-05-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_117 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_119 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_107 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-30 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_073 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-02-28 | 2018-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_056 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_057 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_060 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_082 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_068 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_070 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-31 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_080 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_078 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_101 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-02-21 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_055 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500215 | Flood Risk Management Act Section 16 Only Studies | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_071 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500127 | Fochabers DOA (DOA000198) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50730 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-03-31 | 2018-03-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500127 | Fochabers DOA (DOA000198) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Fochab | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-03-31 | 2018-03-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500127 | Fochabers DOA (DOA000198) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_087 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-02-28 | 2018-03-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500129 | Forres DOA (DOA000188) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50820 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2019-12-31 | 2019-12-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500129 | Forres DOA (DOA000188) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_006 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2018-02-28 | 2018-06-30 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500129 | Forres DOA (DOA000188) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_089 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2019-09-30 | 2019-12-31 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500141 | Fraserburgh Phingask DOA (DOA000360) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Fraser | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-20 | 2016-03-23 | 2018-03-31 | 2019-02-28 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500141 | Fraserburgh Phingask DOA (DOA000360) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_091 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-20 | 2016-03-23 | 2018-03-31 | 2018-03-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_017 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_005 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_007 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_033 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_009 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-04-30 | 2020-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_010 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-04-30 | 2020-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_012 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_013 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_014 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_015 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_008 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-09-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_049 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_031 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-04-30 | 2020-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_039 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-02-28 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_040 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_041 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_042 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-03-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_043 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-11-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_044 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_045 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_037 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-05-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_048 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-31 | 2018-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_036 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_050 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_051 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-09-30 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_052 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-02-28 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_053 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_055 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-05-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_056 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-07-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_057 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_058 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_047 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-06-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_029 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_019 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-03-31 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_020 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-03-31 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_021 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-05-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_022 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_023 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_024 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_025 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-08-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_026 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_038 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_028 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_018 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_030 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-02-29 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_032 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-11-30 | 2016-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_004 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_003 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_002 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-02-29 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_001 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-07-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_034 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_035 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-09-30 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_500060 | FRMA Improvements | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_027 | OMG 11 | Water | DWQR | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-02-29 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [30 empty] | 1 | [38 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_104 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_177 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-05-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_198 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_062 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_063 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-05-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_064 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-06-30 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_081 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-06-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_088 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_061 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_105 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-04-30 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_120 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_122 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_127 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_141 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_146 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_156 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_157 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_033 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-02-28 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_052 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-10-31 | 2017-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_161 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_035 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-02-28 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_032 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-10-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_051 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501093 | FRMA Section 16 Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_044 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500133 | Galashiels DOA (DOA000032) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_093 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-26 | 2016-12-19 | 2017-01-13 | 2018-06-30 | 2018-08-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500133 | Galashiels DOA (DOA000032) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_007 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-26 | 2016-12-19 | 2017-01-13 | 2018-02-28 | 2018-06-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500245 | Galashiels Manse Street WTW | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 50113 | OMG 20 | Water | SEPA | NONINF | SOSI |  | 2016-12-23 | 2018-09-28 | 2019-03-04 | 2022-08-17 | 2023-01-17 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 3 | [29 empty] | 0
PH_500245 | Galashiels Manse Street WTW | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 50113 | OMG 04 | Water | SEPA | NONINF | SOSI |  | 2016-12-23 | 2018-09-28 | 2019-03-04 | 2022-08-17 | 2023-01-17 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [23 empty] | 1 | [45 empty] | 0
PH_500146 | Girvan DOA (DOA002467) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_097 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-30 | 2016-04-25 | 2018-07-31 | 2018-08-31 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500146 | Girvan DOA (DOA002467) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Girvan | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-30 | 2016-04-25 | 2018-07-31 | 2019-01-31 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500243 | Glendye - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50034_002 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-05-31 | 2020-01-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500243 | Glendye - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50034_003 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-05-31 | 2020-01-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500243 | Glendye - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50034_001 | OMG 06 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-05-31 | 2020-01-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 34.67 | [43 empty] | 0
PH_502606 | Greenock RSZ - DW5 Interventions Phase 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59145_02 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2018-06-28 | 2019-06-12 | 2019-06-17 | 2020-03-23 | 2021-03-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_502606 | Greenock RSZ - DW5 Interventions Phase 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59145_03 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2018-06-28 | 2019-06-12 | 2019-06-17 | 2020-03-23 | 2021-05-10 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_502606 | Greenock RSZ - DW5 Interventions Phase 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59145_04 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2018-06-28 | 2019-06-12 | 2019-06-17 | 2020-03-23 | 2021-05-10 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_501574 | Greenock WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50782 | OMG 04 | Water | DWQR | SWD | DWQ Reliability |  | 2017-03-31 | 2019-06-27 | 2019-06-27 | 2020-11-30 | 2021-04-29 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [23 empty] | 1 | [45 empty] | 0
PH_501574 | Greenock WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50782 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2017-03-31 | 2019-06-27 | 2019-06-27 | 2020-11-30 | 2021-04-29 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_500136 | Gretna DOA (DOA000114) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_208 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-29 | 2016-08-01 | 2018-09-30 | 2019-02-28 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500136 | Gretna DOA (DOA000114) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50807 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-29 | 2016-08-01 | 2018-12-31 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500137 | Halkirk DOA (DOA000726) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_103 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-01-31 | 2019-02-28 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500137 | Halkirk DOA (DOA000726) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50819 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-02-28 | 2019-06-30 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_501233 | Herricks WTW - QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50781 | OMG 05 | Water | DWQR | NONINF | DWQ Reliability |  | 2018-03-22 | 2020-02-28 | 2020-02-28 | 2021-04-30 | 2021-07-23 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501233 | Herricks WTW - QUALITY | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50781 | OMG 04 | Water | DWQR | NONINF | DWQ Reliability |  | 2018-03-22 | 2020-02-28 | 2020-02-28 | 2021-04-30 | 2021-07-23 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [23 empty] | 1 | [45 empty] | 0
PH_500138 | Huntly DOA (DOA000367) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_108 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-02-26 | 2016-04-20 | 2019-02-28 | 2019-03-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500138 | Huntly DOA (DOA000367) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50821 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-02-26 | 2016-04-20 | 2019-03-31 | 2019-06-30 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500032 | Improvement to Supply-Demand Balance - North Hoy WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 53018 | OMG 08 | Water | DWQR | SWMD | SOSI |  | 2017-03-31 | 2017-12-22 | 2018-03-26 | 2018-12-31 | 2019-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [27 empty] | 1 | [41 empty] | 0
PH_500032 | Improvement to Supply-Demand Balance - North Hoy WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 53018 | OMG 04 | Water | DWQR | SWMD | SOSI |  | 2017-03-31 | 2017-12-22 | 2018-03-26 | 2018-12-31 | 2019-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [23 empty] | 1 | [45 empty] | 0
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_005 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2018-12-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_028 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2020-01-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_004 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-06-30 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_003 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-06-30 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_030 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2020-01-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_500475 | Improving Reliability of WQ in Network - Emerging SR risks | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_029 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2020-01-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_012 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_009 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_008 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_007 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_006 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_002 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_013 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_011 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_010 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501039 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 2 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_001 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-31 | 2018-02-02 | 2018-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_023 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2021-05-26 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_024 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-04-30 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_035 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-11-30 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_036 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-08-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_037 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_048 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-01-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_050 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-02-03 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_022 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-08-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_018 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-06-30 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_049 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-09-30 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_019 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2021-07-21 | 2021-10-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_017 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-06-30 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_020 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-06-30 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_021 | OMG 05 | Water | DWQR | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-08-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_014 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_034 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_033 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_032 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_031 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_015 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501145 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 4 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_016 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_046 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-12-31 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_045 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2021-04-30 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_044 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-12-31 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_043 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_042 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-06-30 | 2020-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_038 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2021-02-28 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_041 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-06-30 | 2020-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_047 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_039 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_026 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2021-04-30 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_025 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_027 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2020-12-31 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_040 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-05-23 | 2021-04-30 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power | 50310_003 | OMG 43 | Water | SW | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [62 empty] | 0.053 | [6 empty] | 0
PH_500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power | 50310_001 | OMG 43 | Water | SW | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [62 empty] | 0.04 | [6 empty] | 0
PH_500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power | 50310_006 | OMG 43 | Water | SW | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [62 empty] | 0.2 | [6 empty] | 0
PH_500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power | 50310_004 | OMG 43 | Water | SW | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [62 empty] | 0.05 | [6 empty] | 0
PH_500481 | Installation of Renewable Energy | Q&S4 | Reducing long term cost of service | Renewable power | 50310_005 | OMG 43 | Water | SW | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [62 empty] | 0.08 | [6 empty] | 0
PH_501243 | Invercannie WTW Pre-Treatment CWT and CM | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59000 | OMG 01 | Water | DWQR | NONINF | DWQ Compliance |  | 2019-02-08 | 2020-02-28 | 2020-03-16 | 2023-01-05 | 2024-03-14 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [20 empty] | 1 | [48 empty] | 0
PH_501243 | Invercannie WTW Pre-Treatment CWT and CM | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59002 | OMG 01 | Water | DWQR | NONINF | DWQ Compliance |  | 2019-02-08 | 2020-02-28 | 2020-03-16 | 2023-01-05 | 2024-03-14 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [20 empty] | 1 | [48 empty] | 0
PH_500140 | Inverclyde DOA (DOA000454) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50719 | OMG 23 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2020-03-24 | 2020-04-30 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500140 | Inverclyde DOA (DOA000454) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_008 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2020-06-29 | 2020-07-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500140 | Inverclyde DOA (DOA000454) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_110 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2020-05-11 | 2020-03-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500150 | Inverness DOA (DOA002372) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_006 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-02-28 | 2017-03-21 | 2019-06-30 | 2019-08-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500150 | Inverness DOA (DOA002372) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_001 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-02-28 | 2017-03-21 | 2019-12-31 | 2020-01-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_03 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_18 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-02 | 2021-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_02 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_04 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_05 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_06 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_13 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_17 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_16 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_01 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-03-31 | 2021-06-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_14 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_07 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-06-30 | 2021-09-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_12 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-03-31 | 2021-06-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_11 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-03-31 | 2021-06-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_10 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_09 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-02 | 2021-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_08 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502944 | IR18 CAS Compliance Improvements - Networks East & North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_15 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_19 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_20 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_25 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_35 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_39 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-30 | 2021-10-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_38 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_37 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-30 | 2021-10-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_36 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-09 | 2021-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_29 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-26 | 2021-10-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_34 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-16 | 2021-10-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_22 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_24 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-06-04 | 2021-09-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_26 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-12 | 2021-10-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_33 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_27 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-06-25 | 2021-09-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_32 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_28 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-06-11 | 2021-09-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_21 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-08-12 | 2021-11-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_31 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-01 | 2021-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_23 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502945 | IR18 CAS Compliance Improvements - Networks South & West Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_30 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-08-18 | 2021-11-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_11 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-08-25 | 2021-11-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_12 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-10-22 | 2022-01-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_13 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-09-16 | 2021-12-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_14 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-09-23 | 2021-12-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_07 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_10 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-06-02 | 2021-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_05 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-07-13 | 2021-10-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_06 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_09 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-08-16 | 2021-11-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_08 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2019-12-17 | 2020-03-16 | 2021-06-02 | 2021-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_06 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2020-12-31 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_20 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-01-31 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_07 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-06-18 | 2021-09-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_06 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-07-26 | 2021-10-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_04 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2019-12-18 | 2020-03-16 | 2021-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_03 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2019-12-18 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_02 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2019-12-18 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_01 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2019-12-18 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_38 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_35 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_33 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-05-28 | 2021-08-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_04 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_25 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-01-31 | 2021-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_02 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_19 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_17 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_16 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_15 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-06-30 | 2021-09-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_14 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_13 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_10 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2020-12-31 | 2021-07-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_08 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_05 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2020-12-31 | 2021-05-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502943 | IR18 CAS Compliance Improvements - WWTW Non Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_32 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-05-28 | 2021-08-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_03 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_10 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2019-12-18 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_11 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2019-12-18 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_12 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2019-12-18 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_13 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2019-12-18 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_14 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2019-12-18 | 2020-03-16 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_01 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-03-31 | 2021-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_502947 | IR18 CAS Compliance Improvements - WWTW North Complex | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_02 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  |  |  |  | 2021-01-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_503052 | IR18 Pateshill WTW Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59017a | OMG 47 | Water | DWQR | SWD | DWQ Reliability |  | 2018-02-02 | 2018-06-26 | 2018-08-01 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_503052 | IR18 Pateshill WTW Study | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59129a | OMG 47 | Water | DWQR | SWD | DWQ Reliability |  | 2018-02-02 | 2018-06-26 | 2018-08-01 | 2020-02-27 | 2020-06-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_503195 | IR18 Water Quality Improvement - Camps RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508032_01_01 | OMG 06 | Water | DWQR | WINF | DWQ Compliance |  | 2018-12-20 | 2019-10-31 | 2019-09-30 | 2021-03-31 | 2022-08-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 122.329 | [43 empty] | 0
PH_503195 | IR18 Water Quality Improvement - Camps RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508032_01_02 | OMG 06 | Water | DWQR | WINF | DWQ Compliance |  | 2018-12-20 | 2019-10-01 | 2019-09-30 | 2022-08-30 | 2022-05-17 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 155.777 | [43 empty] | 0
PH_503197 | IR18 Water Quality Improvement - Pateshill RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | TE_508025_01_01 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-12-10 | 2019-12-31 | 2020-01-27 | 2021-03-31 | 2022-09-30 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 22.552 | [43 empty] | 0
PH_503197 | IR18 Water Quality Improvement - Pateshill RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | TE_508025_01_02 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-12-10 | 2019-12-31 | 2020-01-27 | 2021-09-30 | 2022-09-30 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 187.469 | [43 empty] | 0
PH_503198 | IR18 Water Quality Improvement - Rawburn RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | TE_508026_01_01 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-11-30 | 2019-10-01 | 2020-01-31 | 2021-03-31 | 2022-09-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 39.365 | [43 empty] | 0
PH_503198 | IR18 Water Quality Improvement - Rawburn RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | TE_508026_01_02 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-11-30 | 2019-10-01 | 2020-01-24 | 2021-09-30 | 2022-09-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 274.464 | [43 empty] | 0
PH_503199 | IR18 Water Quality Improvement - Roberton RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | TE_508027_01_01 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-10-26 | 2019-12-20 | 2020-02-13 | 2021-03-31 | 2022-09-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 282.885 | [43 empty] | 0
PH_503199 | IR18 Water Quality Improvement - Roberton RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | TE_508027_01_02 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-10-26 | 2019-12-20 | 2020-02-13 | 2021-09-30 | 2022-09-30 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 60.677 | [43 empty] | 0
PH_503200 | IR18 Water Quality Improvement - Spynie RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | TE_508028_01_01 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-12-20 | 2019-09-30 | 2019-09-30 | 2021-03-31 | 2021-09-23 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 75.12 | [43 empty] | 0
PH_503200 | IR18 Water Quality Improvement - Spynie RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | TE_508028_01_02 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-12-20 | 2019-09-30 | 2019-09-30 | 2021-06-17 | 2021-09-23 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 74.458 | [43 empty] | 0
PH_500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50828 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-02-17 | 2020-04-30 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_112 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-03-30 | 2020-05-18 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_009 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-03-31 | 2020-07-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50287 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-02-17 | 2020-02-29 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500142 | Iron Mill Bay DOA & Dunfermline DOA (DOA000206 & DOA000208) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_072 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2020-03-30 | 2020-05-18 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_403975 | Kilmun Hillrig UNS SO - Kilmun Inveroch CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501120_001 | OMG 17 | Wastewater | SEPA | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2018-03-31 | 2018-03-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [36 empty] | 1 | [32 empty] | 0
PH_403975 | Kilmun Hillrig UNS SO - Kilmun Inveroch CSO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501120_003 | OMG 17 | Wastewater | SEPA | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2018-03-31 | 2018-03-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [36 empty] | 1 | [32 empty] | 0
PH_500144 | Kirkwall DOA (DOA000561) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50824 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-02-26 | 2016-04-19 | 2018-12-31 | 2019-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500144 | Kirkwall DOA (DOA000561) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_125 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-02-26 | 2016-04-19 | 2019-01-31 | 2019-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500145 | Langholm DOA (DOA000075) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50808 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-26 | 2016-06-20 | 2018-12-31 | 2019-07-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500145 | Langholm DOA (DOA000075) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_128 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-26 | 2016-06-20 | 2019-01-31 | 2019-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500152 | Largs DOA (DOA002517) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Largs | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-28 | 2018-03-31 | 2018-06-30 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500152 | Largs DOA (DOA002517) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_129 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-28 | 2017-11-30 | 2018-01-31 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500154 | Leven Valley DOA (DOA002460) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50407_Leven | OMG 23 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-12-31 | 2021-01-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500154 | Leven Valley DOA (DOA002460) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_134 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-12-31 | 2021-02-28 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500154 | Leven Valley DOA (DOA002460) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50288 | OMG 23 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-11-30 | 2021-01-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500154 | Leven Valley DOA (DOA002460) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_010 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2021-01-31 | 2021-03-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500156 | Lincluden DOA (DOA000122) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_135 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-22 | 2017-07-31 | 2017-08-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500156 | Lincluden DOA (DOA000122) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50809 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-22 | 2017-11-30 | 2018-03-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500159 | Linlithgow DOA (DOA000533) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50291 | OMG 23 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2019-03-31 | 2019-06-30 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500159 | Linlithgow DOA (DOA000533) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_136 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2018-09-30 | 2018-11-30 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500159 | Linlithgow DOA (DOA000533) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_011 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2019-01-31 | 2019-12-31 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501642 | Loch Eck | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50767 | OMG 05 | Water | DWQR | SWD | DWQ Reliability |  | 2017-03-29 | 2018-12-21 | 2019-08-23 | 2021-03-31 | 2021-06-02 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [24 empty] | 1 | [44 empty] | 0
PH_501642 | Loch Eck | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50767 | OMG 04 | Water | DWQR | SWD | DWQ Reliability |  | 2017-03-29 | 2018-12-21 | 2019-08-23 | 2021-03-31 | 2021-06-02 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [23 empty] | 1 | [45 empty] | 0
PH_500107 | Loch Lomond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50305_TE_500305_020 | OMG 22 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500107 | Loch Lomond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50305_TE_500305_086 | OMG 22 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500107 | Loch Lomond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50305_TE_500305_189 | OMG 22 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-31 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500107 | Loch Lomond Strategic Study | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50489 | OMG 23 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500161 | Lockerbie DOA (DOA000076) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_140 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-30 | 2016-08-05 | 2018-12-31 | 2019-02-28 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500161 | Lockerbie DOA (DOA000076) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50810 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-30 | 2016-08-05 | 2019-06-30 | 2019-07-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500835 | Mannofield West RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53194 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-03-07 | 2018-03-28 | 2018-06-19 | 2020-01-23 | 2020-09-30 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 18.79 | [43 empty] | 0
PH_500835 | Mannofield West RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50195 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-03-07 | 2018-03-28 | 2018-06-19 | 2020-01-23 | 2020-09-30 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 213.76 | [43 empty] | 0
PH_500206 | Marchbank B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_003 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2020-03-01 | 2021-04-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500206 | Marchbank B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_004 | OMG 06 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2020-03-03 | 2021-03-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 22.36 | [43 empty] | 0
PH_500206 | Marchbank B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_001 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2019-06-30 | 2020-02-29 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500206 | Marchbank B - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_002 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2019-02-28 | 2020-02-29 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500165 | Melrose DOA (DOA000072) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50834 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-11-28 | 2017-01-23 | 2018-12-31 | 2019-03-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500165 | Melrose DOA (DOA000072) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_142 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-19 | 2016-11-28 | 2017-01-23 | 2018-09-30 | 2018-10-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500007 | Milngavie C2 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50053_003 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-06-30 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500007 | Milngavie C2 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50053_001 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-06-30 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500007 | Milngavie C2 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50053_002 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-03-31 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500008 | Milngavie C3 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_004 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2018-05-31 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500008 | Milngavie C3 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_003 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2017-12-31 | 2019-02-28 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500008 | Milngavie C3 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_001 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2017-12-31 | 2019-02-28 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500008 | Milngavie C3 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_005 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2017-12-31 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500009 | Milngavie C4 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50055_001 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-23 | 2016-03-30 | 2016-05-02 | 2017-12-31 | 2018-12-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500009 | Milngavie C4 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50055_003 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-23 | 2016-03-30 | 2016-05-02 | 2017-12-31 | 2018-12-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500010 | Milngavie M1 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50056_001 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-06-20 | 2018-08-31 | 2019-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500010 | Milngavie M1 - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50056_002 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-06-20 | 2018-12-31 | 2019-07-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_011 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2021-03-31 | 2022-06-15 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_005 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-30 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_006 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-31 | 2019-03-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_007 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-31 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_004 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-30 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_008 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-31 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_001 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-30 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_010 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-31 | 2020-03-31 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_003 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-30 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_002 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-30 | 2019-02-28 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500207 | Muirdykes- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_009 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2021-03-31 | 2022-03-30 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500162 | Nairn DOA (DOA000470) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_149 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-23 | 2017-11-30 | 2018-01-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500162 | Nairn DOA (DOA000470) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Nairn | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-23 | 2017-12-31 | 2018-03-31 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500867 | North Lochs RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50219 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-09-06 | 2018-09-20 | 2018-11-20 | 2019-09-30 | 2020-07-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 79.99 | [43 empty] | 0
PH_500867 | North Lochs RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53196 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-09-06 | 2018-09-20 | 2018-11-20 | 2019-09-30 | 2020-07-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 18.12 | [43 empty] | 0
PH_500169 | Oban DOA (DOA001020) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_158 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-03-16 | 2016-05-23 | 2017-07-31 | 2017-09-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500169 | Oban DOA (DOA001020) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50814 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-03-16 | 2016-05-23 | 2017-07-31 | 2018-03-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_503630 | OMG06 Shortfall Project | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 58034_02 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2019-09-30 | 2020-03-31 | 2020-03-31 | 2021-09-30 | 2022-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 267.363 | [43 empty] | 0
PH_503630 | OMG06 Shortfall Project | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 58034_01 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2019-09-30 | 2020-03-31 | 2020-03-31 | 2021-03-31 | 2022-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 248.847 | [43 empty] | 0
PH_500171 | Penicuik DOA (DOA000526) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50826 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-30 | 2017-05-31 | 2018-01-31 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500171 | Penicuik DOA (DOA000526) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_160 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-30 | 2017-05-31 | 2017-10-31 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500168 | Perth City DOA (DOA000674) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_162 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-30 | 2016-09-30 | 2019-04-30 | 2019-04-30 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500168 | Perth City DOA (DOA000674) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_012 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-30 | 2016-09-30 | 2019-05-31 | 2019-12-31 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500210 | Perth- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50063_002 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-20 | 2017-09-29 | 2017-09-29 | 2018-12-31 | 2020-03-02 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500210 | Perth- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50063_001 | OMG 02 | Water | DWQR | WINF | DWQ Compliance |  | 2015-03-20 | 2017-09-29 | 2017-09-29 | 2019-03-31 | 2020-05-31 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500170 | Philipshill DOA (DOA000616) & Allers DOA (DOA000617) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_007 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-05-31 | 2019-09-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500170 | Philipshill DOA (DOA000616) & Allers DOA (DOA000617) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_164 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-05-31 | 2019-09-30 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500170 | Philipshill DOA (DOA000616) & Allers DOA (DOA000617) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_013 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-06-30 | 2019-12-31 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500211 | Picketlaw- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50064_001 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-01-31 | 2018-06-30 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500211 | Picketlaw- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50064_002 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-01-31 | 2018-06-30 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500211 | Picketlaw- DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50064_003 | OMG 06 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-06-30 | 2021-06-15 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 6.37 | [43 empty] | 0
PH_403090 | QS3b AR - Kaim WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50148-OMG20 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2013-01-17 | 2016-09-26 | 2016-09-27 | 2021-06-30 | 2021-09-23 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 1 | [29 empty] | 0
PH_403090 | QS3b AR - Kaim WTW | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50148-OMG01 | OMG 01 | Water | SEPA | WINF | DWQ Compliance |  | 2013-01-17 | 2016-09-26 | 2016-09-27 | 2021-06-30 | 2021-09-23 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [20 empty] | 1 | [48 empty] | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_047 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_040 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_027 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_028 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_029 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_030 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_031 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_032 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_033 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_034 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_035 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_026 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_038 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_037 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_041 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_042 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_043 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_044 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_046 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_048 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_049 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_050 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_001 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_045 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_036 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-30 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_013 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_039 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_025 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_004 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_005 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_006 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_007 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_008 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_009 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_010 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_011 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_003 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_018 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_024 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_023 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_022 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_021 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_012 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_019 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_002 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_017 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_016 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_015 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_014 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500095 | Raw Water Resource Trends - Rain Gauges | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_020 | OMG 45 | Water | SEPA | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-30 | 2016-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [64 empty] | 1 |  |  |  |  | 0
PH_500106 | River Carron Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_067 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2018-07-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500106 | River Carron Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50492 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2020-06-18 | 2020-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500106 | River Carron Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_RiCarron | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2019-02-28 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 2 | [26 empty] | 0
PH_500100 | River Don Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_109 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-09-30 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500100 | River Don Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_111 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-12-31 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500100 | River Don Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50408 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2020-04-22 | 2020-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500101 | River Eden Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50490 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2020-02-14 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500101 | River Eden Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_180 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500101 | River Eden Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_059 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2019-07-31 | 2019-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500101 | River Eden Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_190 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2019-06-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-4 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-1 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-2 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-3 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-4 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-56 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-57 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-59 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-8 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-3 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-4 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-5 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-6 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-1 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-7 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-9 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-1 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-2 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-3 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-2 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501640 | Security of RWPs & TWPs Phase 0 - No build | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-58 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-31 | 2016-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-110 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-100 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-10 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-101 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-8 | OMG 10 | Water | DWQR | SWMD | SEMD | [5 empty] | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-102 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-104 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-106 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-107 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-108 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-7 | OMG 10 | Water | DWQR | SWMD | SEMD | [5 empty] | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-11 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-1 | OMG 10 | Water | DWQR | SWMD | SEMD | [5 empty] | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-111 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-112 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-109 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-3 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-105 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-113 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-17 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-18 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-19 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-20 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-31 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-11 | OMG 10 | Water | DWQR | SWMD | SEMD | [5 empty] | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-2 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-3 | OMG 10 | Water | DWQR | SWMD | SEMD | [5 empty] | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-4 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-5 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-10 | OMG 10 | Water | DWQR | SWMD | SEMD | [5 empty] | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-12 | OMG 10 | Water | DWQR | SWMD | SEMD | [5 empty] | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-13 | OMG 10 | Water | DWQR | SWMD | SEMD | [5 empty] | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-14 | OMG 10 | Water | DWQR | SWMD | SEMD | [5 empty] | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-2 | OMG 10 | Water | DWQR | SWMD | SEMD | [5 empty] | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-1 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-62 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-73 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-72 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-71 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-70 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-69 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-68 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-67 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-66 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-65 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-51 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2019-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-63 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-76 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-61 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-60 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-59 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-58 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-57 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-56 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-55 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-54 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-53 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-52 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-64 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-89 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-114 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-103 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-99 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-98 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-97 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-96 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-95 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-94 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-93 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-92 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-74 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-90 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-75 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-88 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-86 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-85 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-84 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-83 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-82 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-80 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-78 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-77 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-79 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-91 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-122 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-24 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-23 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-22 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-21 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-20 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-19 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-18 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-17 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-16 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-25 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-13 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-14 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-121 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-120 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-12 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-119 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-118 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-117 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-50 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-81 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-115 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-116 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-15 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-39 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-48 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-47 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-46 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-49 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-123 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-26 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-45 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-44 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-43 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-42 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-30 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-40 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-28 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-38 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-28 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-29 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2019-09-30 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-41 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-37 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-32 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-30 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-34 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-31 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-35 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-27 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-36 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501244 | Security of RWPS & TWPS Phase 2 - North East - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-33 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-57 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-56 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-59 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-55 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-67 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-61 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-66 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-54 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-43 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-63 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-64 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-65 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-62 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-46 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-39 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-40 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-93 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-68 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-41 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-45 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-44 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-53 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-47 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-48 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-49 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-50 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-51 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-52 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-42 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-95 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-91 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-87 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-88 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-89 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-90 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-85 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-94 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-84 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-96 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-97 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-98 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-99 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-38 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-58 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-92 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-77 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-70 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-71 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-72 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-73 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-74 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-86 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-76 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-69 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-78 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-79 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-80 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-81 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-82 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-83 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-75 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_12 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-114 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-113 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-112 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-111 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-110 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-109 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-108 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-107 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-106 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-105 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-104 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-103 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-102 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-115 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_06 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-37 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-60 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_01 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_02 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_03 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-100 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2017-12-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_05 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_13 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_07 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_08 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_09 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_10 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_11 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-101 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_04 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-36 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-132 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-133 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-134 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-136 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-29 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-131 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-31 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-135 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-116 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_14 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-35 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-32 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-33 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-34 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-30 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-123 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-117 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-118 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-119 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-120 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-121 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-137 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-122 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-124 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-126 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-130 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-127 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-128 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-31 | 2018-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-125 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-30 | 2018-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501245 | Security of RWPS & TWPS Phase 3 - Highlands - Islands | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-129 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-42 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-49 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-41 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-40 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-11 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-96 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-99 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-98 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-97 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-63 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-59 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-53 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-54 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-55 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-56 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-63 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-6 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-58 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-40 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-52 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-62 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-60 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-61 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-57 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-45 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-90 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-64 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-38 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-39 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-4 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-41 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-42 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-44 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-51 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-46 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-47 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-48 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-49 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-5 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-50 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-43 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-37 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-89 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-82 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-83 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-84 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-85 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-86 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-80 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-88 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-8 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-9 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-11 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-91 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-92 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-93 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-94 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-87 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-73 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-66 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-08-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-67 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-68 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-69 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-7 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-70 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-81 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-72 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-65 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-74 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-75 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-76 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-77 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-78 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-79 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-08-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-71 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-8 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-15 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-14 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-12 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-109 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-36 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-107 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-13 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-105 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-104 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-103 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-102 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-101 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-100 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-16 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-2 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-08-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-95 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-1 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-10 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2017-12-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-11 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-12 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-10 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-14 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-02-28 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-1 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-3 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-4 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2020-06-01 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-5 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-6 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-07-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-7 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-108 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-13 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-27 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-35 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-34 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-33 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-32 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-31 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-30 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-3 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-106 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-28 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-17 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-26 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-28 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-25 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-2 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-29 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-19 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-20 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-21 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-22 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-23 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-24 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501246 | Security of RWPS & TWPS Phase 4 - South | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-18 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-32 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-39 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-38 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-37 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-36 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-35 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-34 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-33 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-31 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-30 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-3 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-29 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-4 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-27 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-5 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-26 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-25 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-28 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-52 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-60 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-6 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-59 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-58 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-57 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-56 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-55 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-47 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-53 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-43 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-51 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-50 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-18 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-48 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-24 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-46 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-45 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-44 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-54 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-15 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-2 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-5 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-4 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-3 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-2 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-19 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-18 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-7 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-16 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-8 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-14 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-13 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-12 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-11 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-10 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-1 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-9 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-17 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-10-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-13 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-22 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-21 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-20 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-19 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-64 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-17 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-16 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-6 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-14 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-23 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-12 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-101 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-100 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-10 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-1 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-87 | OMG 10 | Water | DWQR | SWMD | SEMD |  |  |  |  | 2020-12-31 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-9 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-15 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-91 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-83 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-84 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-85 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-86 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-09-30 | 2020-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-87 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-88 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-89 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-82 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-90 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-93 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-92 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-94 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-96 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-97 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-98 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-99 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-62 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-61 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-9 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-7 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-95 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-81 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-65 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-66 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-67 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-68 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-69 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-70 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-71 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-78 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-73 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-74 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-80 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-75 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-8 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-76 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-03-02 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-77 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-72 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_501247 | Security of RWPS & TWPS Phase 5 - West | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-79 | OMG 10 | Water | DWQR | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2019-12-20 | 2020-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_500703 | SEPA Compliance Assessment Scheme - WW Networks | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-4 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_500703 | SEPA Compliance Assessment Scheme - WW Networks | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-3 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_500703 | SEPA Compliance Assessment Scheme - WW Networks | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-2 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_500703 | SEPA Compliance Assessment Scheme - WW Networks | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-1 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501622 | SEPA Compliance Assessment Scheme - WW Networks - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-5 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501622 | SEPA Compliance Assessment Scheme - WW Networks - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-8 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501622 | SEPA Compliance Assessment Scheme - WW Networks - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-7 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501622 | SEPA Compliance Assessment Scheme - WW Networks - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-6 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-10 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-11 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-12 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-2 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_500702 | SEPA Compliance Assessment Scheme - WwTWs | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-1 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-9 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-4 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2018-04-30 | 2018-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-3 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2020-03-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-5 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-6 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-7 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-06-30 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_501621 | SEPA Compliance Assessment Scheme - WwTWs - Phase 2 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-8 | OMG 27 | Wastewater | SEPA | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2020-02-02 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [46 empty] | 1 | [22 empty] | 0
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50150 | OMG 47 | Water | DWQR | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-01-31 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 53307 | OMG 47 | Water | DWQR | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2016-10-31 | 2017-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50750 | OMG 47 | Water | DWQR | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-01-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50102 | OMG 47 | Water | DWQR | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-02-28 | 2017-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50091_TE_500091_01 | OMG 47 | Water | DWQR | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-02-28 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_403762 | Six WTW THM research and investigation | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50751 | OMG 47 | Water | DWQR | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-01-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500178 | Skellyton DOA (DOA002580) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_179 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2015-11-30 | 2016-01-12 | 2018-11-30 | 2019-03-31 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500178 | Skellyton DOA (DOA002580) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Skelly | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2015-11-30 | 2016-01-12 | 2018-10-31 | 2019-03-31 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_503082 | South Uist WTW New Source | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50097 | OMG 01 | Water | DWQR | WINF | DWQ Compliance |  | 2015-11-30 | 2022-12-15 | 2023-01-25 | 2024-07-18 | 2025-09-25 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [20 empty] | 1 | [48 empty] | 0
PH_503082 | South Uist WTW New Source | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 53019 | OMG 08 | Water | DWQR | WINF | DWQ Compliance |  | 2015-11-30 | 2022-12-15 | 2023-01-25 | 2024-07-18 | 2024-10-17 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [27 empty] | 1 | [41 empty] | 0
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_1 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_9 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2018-12-31 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_2 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_3 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_8 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_7 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_10 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-09-30 | 2017-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_4 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_5 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_502422 | SR10 to SR15 transfer sites | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_6 | OMG 10 | Water | DWQR | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [29 empty] | 1 | [39 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50161 | OMG 01 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2018-09-30 | 2018-09-30 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [20 empty] | 1 | [48 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_002 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-12-16 | 2022-12-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 1 | [29 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_001 | OMG 01 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2018-03-31 | 2019-02-28 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [20 empty] | 1 | [48 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50792 | OMG 04 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2018-03-31 | 2018-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [23 empty] | 1 | [45 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_003 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-12-16 | 2022-12-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 1 | [29 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_004 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-12-16 | 2022-12-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 1 | [29 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_005 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-12-16 | 2022-12-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 1 | [29 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_008 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-12-16 | 2022-12-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 1 | [29 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_006 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-12-16 | 2022-12-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 1 | [29 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_007 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-12-16 | 2022-12-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 1 | [29 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_009 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-12-16 | 2022-12-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 1 | [29 empty] | 0
PH_403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_010 | OMG 20 | Water | SEPA | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-12-16 | 2022-12-16 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [39 empty] | 1 | [29 empty] | 0
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_001 | OMG 23 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_007 | OMG 23 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2019-01-31 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_009 | OMG 23 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-31 | 2018-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_010 | OMG 23 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-11-30 | 2018-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_004 | OMG 23 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_003 | OMG 23 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_002 | OMG 23 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2019-02-28 | 2019-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_403671 | SR15 ES - Legacy Sludge Studies | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_006 | OMG 23 | Wastewater | SEPA | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-11-30 | 2019-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_402949 | SR15 ES - LRC3 (Daldowie WWTW to Dalmarnock WWTW FE Transfer and Outfall) Development | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 51163_001 | OMG 17 | Wastewater | SEPA | MPT | UWWTD - Works |  | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2022-08-30 | 2022-11-25 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [36 empty] | 1 | [32 empty] | 0
PH_402949 | SR15 ES - LRC3 (Daldowie WWTW to Dalmarnock WWTW FE Transfer and Outfall) Development | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 51163_001 | OMG 18 | Wastewater | SEPA | MPT | UWWTD - Works |  | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2021-01-31 | 2021-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_402949 | SR15 ES - LRC3 (Daldowie WWTW to Dalmarnock WWTW FE Transfer and Outfall) Development | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 51163_002 | OMG 18 | Wastewater | SEPA | MPT | UWWTD - Works |  | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2021-01-31 | 2021-03-31 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_403983 | SR15 ES - Rhu Torwoodhill Road Uns SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501131_002 | OMG 17 | Wastewater | SEPA | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-05-31 | 2018-11-30 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [36 empty] | 1 | [32 empty] | 0
PH_403983 | SR15 ES - Rhu Torwoodhill Road Uns SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501131_001 | OMG 17 | Wastewater | SEPA | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-11-30 | 2018-11-30 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [36 empty] | 1 | [32 empty] | 0
PH_403983 | SR15 ES - Rhu Torwoodhill Road Uns SO | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501131_003 | OMG 17 | Wastewater | SEPA | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-03-31 | 2018-03-31 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [36 empty] | 1 | [32 empty] | 0
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N05 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-30 | 2020-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 8 |  |  | 0
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N01 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2017-06-30 | 2017-06-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N07 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-30 | 2020-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 9 |  |  | 0
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N02 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-30 | 2020-11-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N03 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2016-07-31 | 2020-08-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 8 |  |  | 0
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N04 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-30 | 2020-02-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 8 |  |  | 0
PH_403817 | SR15 ES - Water resilience studies | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N06 | OMG 47 | Water | DWQR | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-30 | 2020-09-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 8 |  |  | 0
PH_403605 | SR15 ES Clunas WTW and Treatment Trial - Legacy Sludge | Q&S4 | Protecting and enhancing the environment | Sludge | 51145 | OMG 24 | Wastewater | SEPA | SWMD | Sludge |  | 2013-10-31 | 2018-03-20 | 2018-03-26 | 2021-03-31 | 2021-04-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [43 empty] | 1 | [25 empty] | 0
PH_403605 | SR15 ES Clunas WTW and Treatment Trial - Legacy Sludge | Q&S4 | Protecting and enhancing the environment | Sludge | 59080_01 | OMG 24 | Wastewater | SEPA | SWMD | Sludge |  | 2013-10-31 | 2018-03-20 | 2018-03-26 | 2021-03-31 | 2021-04-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [43 empty] | 1 | [25 empty] | 0
PH_500173 | St Andrews DOA (DOA000247) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50290 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-20 | 2019-03-31 | 2019-07-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500173 | St Andrews DOA (DOA000247) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_181 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-20 | 2018-12-31 | 2019-02-28 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500175 | St Monans DOA (DOA000252) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_182 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2015-09-28 | 2015-11-13 | 2017-05-31 | 2017-07-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500175 | St Monans DOA (DOA000252) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50836 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2015-09-28 | 2015-11-13 | 2017-05-31 | 2018-01-31 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500176 | Stevenston DOA (DOA000544) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_014 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2020-02-17 | 2020-04-30 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500176 | Stevenston DOA (DOA000544) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50815 | OMG 23 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2020-02-17 | 2020-02-29 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500176 | Stevenston DOA (DOA000544) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_184 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2020-01-24 | 2020-04-30 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500176 | Stevenston DOA (DOA000544) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50407_Steven | OMG 23 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-12-10 | 2020-04-30 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500179 | Stewarton DOA (DOA000159) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_185 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2019-01-31 | 2019-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500179 | Stewarton DOA (DOA000159) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Stewa | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2019-03-31 | 2019-06-30 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500179 | Stewarton DOA (DOA000159) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50816 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2018-12-31 | 2019-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500180 | Stirling DOA (DOA000281) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_186 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-06-30 | 2019-08-31 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500180 | Stirling DOA (DOA000281) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_015 | OMG 22 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-08-31 | 2020-02-29 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500180 | Stirling DOA (DOA000281) Environmental Study | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50407_Stirl | OMG 23 | Wastewater | SEPA | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-08-31 | 2019-12-31 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_403938 | Stromness UWWTW (Transfer from 400089) | Q&S3B | Completion | Non OMG180 | 403938 | OMG 48 | Wastewater | SEPA | WWINF | Non OMG180 |  | 2009-11-30 | 2015-10-29 | 2015-11-23 | 2018-02-28 | 2018-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [67 empty] | 1 |  | 0
PH_403938 | Stromness UWWTW (Transfer from 400089) | Q&S3B | Completion | Non OMG180 | 403938_works | OMG 48 | Wastewater | SEPA | WWINF | Non OMG180 |  | 2009-11-30 | 2015-10-29 | 2015-11-23 | 2018-02-28 | 2018-03-31 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [67 empty] | 1 |  | 0
PH_500879 | Suainaval Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50226 | OMG 06 | Water | DWQR | SWD | DWQ Reliability |  | 2016-03-31 | 2016-03-31 | 2016-07-18 | 2017-01-31 | 2017-11-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 3.69 | [43 empty] | 0
PH_500879 | Suainaval Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50905 | OMG 06 | Water | DWQR | SWD | DWQ Reliability |  |  |  |  | 2020-09-30 | 2020-09-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 3.7 | [43 empty] | 0
PH_500880 | Tarbert Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50227 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-09-20 | 2018-09-18 | 2018-12-13 | 2019-03-31 | 2019-09-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 31.87 | [43 empty] | 0
PH_500880 | Tarbert Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50905 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-09-20 | 2018-09-18 | 2018-12-13 |  |  | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [69 empty] | 0
PH_500108 | Tay Coastal Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50491 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-12-14 | 2016-12-19 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500108 | Tay Coastal Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_TayCoast | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-12-14 | 2016-12-19 | 2019-06-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_502767 | THM Study 1 - West | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59107a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-07-31 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_502767 | THM Study 1 - West | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59106a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-18 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_502768 | THM Study 2 - North A | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59108a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-25 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_502768 | THM Study 2 - North A | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59122a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-07-31 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_502768 | THM Study 2 - North A | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59104a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  |  |  |  | 2020-08-31 | 2020-06-25 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_502769 | THM Study 3 - South | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59105a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-07-31 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_502769 | THM Study 3 - South | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59112a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-25 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_502769 | THM Study 3 - South | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59111a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-02-26 | 2020-06-25 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_502770 | THM Study 4 - East | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59119a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-06-19 | 2020-07-31 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_502770 | THM Study 4 - East | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59109a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-06-19 | 2020-06-25 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_502770 | THM Study 4 - East | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59003a | OMG 47 | Water | DWQR | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-06-19 | 2020-06-25 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [66 empty] | 1 |  |  | 0
PH_500882 | Tolsta Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50229 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-11-02 | 2018-09-21 | 2018-11-20 | 2019-06-30 | 2020-03-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 51.41 | [43 empty] | 0
PH_500882 | Tolsta Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53198 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-11-02 | 2018-09-21 | 2018-11-20 | 2019-06-30 | 2020-02-29 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 6.04 | [43 empty] | 0
PH_500182 | Troqueer DOA (DOA000121) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50713 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2019-12-05 | 2020-04-30 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500182 | Troqueer DOA (DOA000121) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Troqu | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2019-12-05 | 2020-04-30 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500182 | Troqueer DOA (DOA000121) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_197 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2019-12-31 | 2019-12-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500852 | Tullich RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50231 | OMG 06 | Water | DWQR | SWD | DWQ Reliability |  | 2015-12-10 | 2016-03-30 | 2016-08-08 | 2017-07-31 | 2018-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 14.5 | [43 empty] | 0
PH_500852 | Tullich RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53199 | OMG 06 | Water | DWQR | SWD | DWQ Reliability |  | 2015-12-10 | 2016-03-30 | 2016-08-08 | 2017-07-31 | 2018-03-31 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 4.67 | [43 empty] | 0
PH_500890 | Turriff RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50198 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-10-13 | 2018-09-26 | 2018-11-30 | 2019-06-30 | 2020-01-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 102.66 | [43 empty] | 0
PH_500890 | Turriff RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53200 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-10-13 | 2018-09-26 | 2018-11-30 | 2019-06-30 | 2020-01-31 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 5.6 | [43 empty] | 0
PH_500186 | Underwood Cumnock DOA (DOA000144) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_058 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-29 | 2018-02-28 | 2018-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500186 | Underwood Cumnock DOA (DOA000144) Environmental Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Under | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-29 | 2018-02-28 | 2018-06-30 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500109 | Upper Clyde Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50409 | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-08-31 | 2021-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500109 | Upper Clyde Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_034 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-02-24 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_500109 | Upper Clyde Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_UppClyde | OMG 23 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-03-27 | 2020-06-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 2 | [26 empty] | 0
PH_500109 | Upper Clyde Strategic Study | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_041 | OMG 22 | Wastewater | SEPA | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-04-01 | 2020-05-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [41 empty] | 1 | [27 empty] | 0
PH_502751 | WATER OF LEITH UIDs - BATCH 0 - 2 x STUDY OUTPUTS | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_007 | OMG 18 | Wastewater | SEPA | SWD | UWWTD - UID |  | 2017-05-16 | 2017-07-14 | 2017-07-14 | 2017-05-31 | 2017-10-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_502751 | WATER OF LEITH UIDs - BATCH 0 - 2 x STUDY OUTPUTS | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_003 | OMG 18 | Wastewater | SEPA | SWD | UWWTD - UID |  | 2017-05-16 | 2017-07-14 | 2017-07-14 | 2017-07-31 | 2017-10-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_502749 | WATER OF LEITH UIDs - BATCH 10 - Gyle Public Park No1 and No2 CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_018 | OMG 18 | Wastewater | SEPA | WWINF | UWWTD - UID |  | 2017-10-31 | 2020-03-31 | 2020-03-31 | 2022-03-31 | 2022-07-07 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_502749 | WATER OF LEITH UIDs - BATCH 10 - Gyle Public Park No1 and No2 CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_016 | OMG 18 | Wastewater | SEPA | WWINF | UWWTD - UID |  | 2017-10-31 | 2020-03-31 | 2020-03-31 | 2022-03-31 | 2022-07-07 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_502741 | WATER OF LEITH UIDs - BATCH 2 - Currie Old Mill Off Lanark Road CSO and Juniper Green | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_009 | OMG 18 | Wastewater | SEPA | WWINF | UWWTD - UID |  | 2017-06-01 | 2020-01-29 | 2020-03-23 | 2021-05-28 | 2021-09-02 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_502741 | WATER OF LEITH UIDs - BATCH 2 - Currie Old Mill Off Lanark Road CSO and Juniper Green | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_010 | OMG 18 | Wastewater | SEPA | WWINF | UWWTD - UID |  | 2017-06-01 | 2020-01-29 | 2020-03-23 | 2021-05-28 | 2021-09-02 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_502746 | WATER OF LEITH UIDs - BATCH 7 - Longstone CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_012 | OMG 18 | Wastewater | SEPA | WINF | UWWTD - UID |  | 2017-10-30 | 2021-10-04 | 2022-01-05 | 2022-10-10 | 2023-01-24 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_502746 | WATER OF LEITH UIDs - BATCH 7 - Longstone CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_014 | OMG 18 | Wastewater | SEPA | WINF | UWWTD - UID |  | 2017-10-30 | 2021-10-04 | 2022-01-05 | 2022-10-10 | 2023-01-24 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_502746 | WATER OF LEITH UIDs - BATCH 7 - Longstone CSOs | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_013 | OMG 18 | Wastewater | SEPA | WINF | UWWTD - UID |  | 2017-10-30 | 2021-10-04 | 2022-01-05 | 2022-10-10 | 2023-01-24 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [37 empty] | 1 | [31 empty] | 0
PH_503257 | Water Quality Improvement - Greenock Phase 2 - Flushing | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59123_01_01 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-06-28 | 2019-05-29 | 2019-09-06 | 2021-03-31 | 2021-03-31 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 43.098 | [43 empty] | 0
PH_503257 | Water Quality Improvement - Greenock Phase 2 - Flushing | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59123_01_02 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-06-28 | 2019-05-29 | 2019-09-06 | 2021-07-26 | 2022-07-26 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 69.253 | [43 empty] | 0
PH_503193 | Water Quality Improvement- Amlaird Flushing RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | TE_508022_01_02 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-06-28 | 2018-12-21 | 2019-03-28 | 2021-08-02 | 2021-10-29 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 11.56 | [43 empty] | 0
PH_503193 | Water Quality Improvement- Amlaird Flushing RSZ | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | TE_508022_01_01 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2018-06-28 | 2018-12-21 | 2019-03-31 | 2020-07-31 | 2021-03-31 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 72.592 | [43 empty] | 0
PH_500884 | West Lewis Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50232 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-04-07 | 2018-09-26 | 2018-12-11 | 2019-06-30 | 2020-01-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 48.59 | [43 empty] | 0
PH_500884 | West Lewis Western Isles RSZ Cleaning | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53201 | OMG 06 | Water | DWQR | WINF | DWQ Reliability |  | 2016-04-07 | 2018-09-26 | 2018-12-11 | 2019-06-30 | 2020-01-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [25 empty] | 0.72 | [43 empty] | 0
PH_500216 | West Lewis WI - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50086_002 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-20 | 2016-03-30 | 2016-06-20 | 2017-03-31 | 2018-12-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500216 | West Lewis WI - DW5 Interventions | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50086_001 | OMG 02 | Water | DWQR | SWD | DWQ Compliance |  | 2015-03-20 | 2016-03-30 | 2016-06-20 | 2017-03-31 | 2018-12-31 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [21 empty] | 1 | [47 empty] | 0
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_012 | OMG 23 | Water | SEPA | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2017-12-31 | 2017-12-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_013 | OMG 23 | Water | SEPA | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_014 | OMG 23 | Water | SEPA | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2017-12-31 | 2018-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_015 | OMG 23 | Water | SEPA | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_016 | OMG 23 | Water | SEPA | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
PH_500193 | WFD Fish Pass Studies | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_008 | OMG 23 | Water | SEPA | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-31 | 2018-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | [42 empty] | 1 | [26 empty] | 0
402471 | AIM SR15 Business Plan Preparation | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-12-02 | 2012-10-31 | 2012-10-31 | 2015-01-27 |  | Scottish Water Wide | 4613435.74 | 2306717.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4613435.74 | 0 | 0 | 0 | 0 | 4613435.74 | 0 | [5 empty] | N | CM_M&G | 50% | QS4_SW_E | 50%
402845 | Low Crescent Clydebank | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2012-08-15 | 2014-10-16 | 2014-10-20 | 2014-11-19 | 2014-11-27 | West Dunbartonshire | 90158.85 | 90158.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90158.85 | 0 | 0 | 0 | 0 | 90158.85 | 0 | [5 empty] | N | CM_WWI | 28% | CS11A | 72%
402823 | QS3b AR - Inspection of Reservoirs below 25000m3 capacity | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2012-07-11 | 2013-11-27 | 2013-11-27 | 2013-11-27 | 2013-11-27 | Scottish Water Wide | 184626.24 | 184626.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184626.24 | 0 | 0 | 0 | 0 | 184626.24 | 0 | [5 empty] | N | CS16W | 100%
402044 | QSIV Security Programme Development - Water and Wastewater | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWD | SEMD | MS7 | 2011-03-25 | 2012-06-07 | 2012-06-18 | 2013-04-01 |  | Scottish Water Wide | 99333.99 | 99333.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99333.99 | 0 | 0 | 0 | 0 | 99333.99 | 0 | [5 empty] | N | DW9 | 100%
402840 | SR15 ES - Energy efficiency investment planning | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWMD | Energy efficiency | MS7 | 2012-08-21 | 2012-09-26 | 2012-09-26 | 2013-03-28 |  | Scottish Water Wide | 44283.2 | 44283.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44283.2 | 0 | 0 | 0 | 0 | 44283.2 | 0 | [5 empty] | N | CC2W | 100%
402776 | SR15 ES - Investigation of Phosphorus Impact from WwTW | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2012-08-14 | 2013-04-11 | 2013-04-23 | 2014-02-13 |  | Scottish Water Wide | 180694.06 | 180694.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180694.06 | 0 | 0 | 0 | 0 | 180694.06 | 0 | [5 empty] | N | EC10 | 100%
403553 | SR15 ES - Perth AAD | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2013-09-12 | 2014-09-29 | 2014-10-14 | 2014-10-14 |  | Perth and Kinross | 114036.71 | 114036.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114036.71 | 0 | 0 | 0 | 0 | 114036.71 | 0 | [5 empty] | N | EC06 | 100%
402839 | SR15 ES - Renewable energy investment planning | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2012-08-21 | 2012-09-26 | 2012-09-26 | 2013-03-28 |  | Scottish Water Wide | 95269.16 | 95269.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95269.16 | 0 | 0 | 0 | 0 | 95269.16 | 0 | [5 empty] | N | CC1W | 100%
402735 | SR15 ES - Security of Supply - Bathymetry Surveys | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2012-08-08 | 2012-09-28 | 2012-09-28 | 2012-11-22 |  | Scottish Water Wide | 20076.54 | 20076.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20076.54 | 0 | 0 | 0 | 0 | 20076.54 | 0 | [5 empty] | N | WG4 | 100%
402749 | SR15 ES - Security of Supply - Clatto Lintrathen and Whitehillocks WRZ | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2013-08-26 | 2013-08-20 | 2013-09-02 | 2013-10-07 |  | Scottish Water Wide | 19911.95 | 19911.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19911.95 | 0 | 0 | 0 | 0 | 19911.95 | 0 | [5 empty] | N | WG4 | 100%
402751 | SR15 ES - Security of Supply - Pump Testing | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2012-08-08 | 2013-04-22 | 2013-04-29 | 2013-11-18 |  | Scottish Water Wide | 59124.52 | 59124.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59124.52 | 0 | 0 | 0 | 0 | 59124.52 | 0 | [5 empty] | N | WG4 | 100%
403322 | Craignure WTW Crypto Risk Reduction | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-03-19 | 2013-03-19 | 2013-03-21 | 2013-07-22 |  | Argyll and Bute-North Argyll | 486648.95 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 486648.95 | [5 empty] | 0 |  |  |  |  | 98064 | N | CM_WSNI | 100%
402941 | SVCW Laighpark Office Refurbishment | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-02-06 | 2013-02-06 | 2013-02-07 | 2013-12-23 |  | Renfrewshire | 33930.21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 33930.21 | [5 empty] | 0 |  |  |  |  | 11007 | N | CM_M&G | 100%

## G7 - Asset Maintenance
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2021
SECTION G: INVESTMENT MONITORING
Table G7: Asset maintenance
40
Line Ref | Description | Units | Field Type | Estimated Report Year 2020-21 | CG | Estimated Report Year 2019-20 | CG
1 | Responsive maintenance: water
G7.01 | Inspections and testing | £m | I | 0.092897 | C5 | 0.22276 | C5
G7.02 | Repair | £m | I | 73.891 | C5 | 62.0678 | C5
G7.03 | Refurbishment | £m | I | 32.724 | C5 | 22.4255 | C5
G7.04 | Replacement | £m | I | 35.69 | C5 | 24.9755 | C5
G7.05 | Total responsive maintenance for the water service | £m | C | 142.3978 | C5 | 109.6916 | C5
2 | Responsive maintenance: wastewater
G7.06 | Inspections and testing | £m | I | 0.080495 | C5 | 0 | C5
G7.07 | Repair | £m | I | 39.622 | C5 | 62.3872 | C5
G7.08 | Refurbishment | £m | I | 12.5971 | C5 | 14.409 | C5
G7.09 | Replacement | £m | I | 26.5973 | C5 | 12.708 | C5
G7.10 | Total responsive maintenance for the wastewater service | £m | C | 78.8968 | C5 | 89.5043 | C5
3 | Planned maintenance: water
G7.11 | Inspections and testing | £m | I | 6.0482 | C5 | 1.8797 | C5
G7.12 | Repair | £m | I | 8.3531 | C5 | 25.6803 | C5
G7.13 | Refurbishment | £m | I | 1.2161 | C5 | 4.6748 | C5
G7.14 | Replacement | £m | I | 79.0368 | C5 | 70.9237 | C5
G7.15 | Total planned maintenance for the water service | £m | C | 94.6542 | C5 | 103.1584 | C5
4 | Planned maintenance: wastewater
G7.16 | Inspections and testing | £m | I | 4.2004 | C5 | 2.1519 | C5
G7.17 | Repair | £m | I | 6.361 | C5 | 15.3772 | C5
G7.18 | Refurbishment | £m | I | 0.69683 | C5 | 1.2724 | C5
G7.19 | Replacement | £m | I | 55.1214 | C5 | 99.6752 | C5
G7.20 | Total planned maintenance for the wastewater service | £m | C | 66.3796 | C5 | 118.4766 | C5
5 | Expenditure Totals
G7.21 | Responsive maintenance | £m | C | 221.2947 | C5 | 199.1959 | C5
G7.22 | Planned maintenance | £m | C | 161.0338 | C5 | 221.635 | C5
G7.23 | Total maintenance | £m | C | 382.3285 | C5 | 420.8309 | C5
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by: